## Slide 1: Monitoring & Evaluation and Impact Assessment of Project
By Dharmendra Shakya
M&E Officer
UNDP
18th September 2010
Women Empowerment Centre

## Slide 2: Monitoring
What is monitoring ?
Monitoring is a regular and systematic collection, analysis and dissemination of the progress of the program for the management control and decision-making.
Monitoring is all about what is going on in the project (quantitative monitoring) and why (qualitative monitoring)

## Slide 3
What is monitoring?
Monitoring is a process of regular observation and recording of the activities at all level of management taking place in a project to ensure that input deliveries, work schedule, targeted program and all other activities are proceeding as per the planned document.

## Slide 4
Why monitoring ?
To analyze the current situation and measure progress toward project activities
Identify the problem facing and finding solution
Keep activities on the right direction
Make timely decision for management
Checking the inputs are utilized properly
To make transparency and accountability

## Slide 5
Area of Monitoring
Inputs: Whether the provision of various inputs provision made for programme implementation rationale or not.
  Procurement Plan, FACE/ICE, Consultant
Process: Whether the programme activities are being implemented as per the programme document.
  Training, Validation workshop,
Outputs: Whether the outputs of the programme is coming as indicated in the programme document or not.
  Persons trained, Document produced
Effects & Impact: Basically, assessing effects and impacts are the task of evaluation

## Slide 6: Type of Monitoring
A : Management / Administration |  |  | 
Area | Information to be collected | Source of Information | Use of Information
Staff Personnel | Performance Achievement Expectations | Performance Appraisal Observation Meeting Supervision | Feedback Training and capacity development Improve management
Vehicles | Fuel consumption Mileage Repairs New Parts Performance | Log book Record sheet of R/M Meeting with Drivers Observation | Decisions about replacing old vehicles. Identify problems Checks mechanics performance

## Slide 7: Type of Monitoring
B : Finance |  |  | 
Area | Information to be collected | Source of Information | Use of Information
Project Budget and Expenditure | Budget Vs Expenditure Operation Vs Program Budget Expenditure compared to previous year | Invoice and vouchers. Financial Ledgers Financial reports Expenditure with Budget head | Predict expenditure for budgeting Compare costs of different projects Identify areas of excessive expenditure. Identify any saving.

## Slide 8: Type of Monitoring
C : Program Monitoring |  |  | 
Area | Information to be collected | Source of Information | Use of Information
Results of Activities, Project outputs | What has been done What has not been done What problems have encountered and solved | Regular records of activities Meetings Supervision Reports Observations Survey | Management decision Plan future work Identify problem and solution Review Priorities

## Slide 9: M&E Framework
The Monitoring Framework is a plan which clarify
What is to be monitored ?
What activities needed to monitor ?
Who is responsible
When monitoring activities are planned?
How it is carried out?
What resources are required?
To carry out the monitoring systematically, a clear Monitoring Framework is essential.

## Slide 10: Component of M&E Framework
Narrative Component:
  How the agencies undertake M&E
  Accountabilities assigned to different individuals & agencies
  Existing M&E capacity(Human Resources, Financial Resources)
  Required Resources for implementation (M&E Capacity matrix)

## Slide 11: Components of M&E Framework
2. Result Framework:
  Project Document (Logical Frame)
    Inputs : investment for conducting activities
    Activities : Action, process,
    Outputs : Immediate results of the activities,
    Outcomes : Intermediate results,
    Impact : Long term effect/ change
    Indicators : Measure performance /result
    MoV : Sources that verify the results
    Risks : Risks factors that affect to achieve the results.
  Work Plan : Outputs, Activities, Target, Responsibilities, Time Frame, Budget
  Stakeholders Mapping: List of stakeholders who involve in the project/program and their responsibility.

## Slide 12: Component of Monitoring Framework
3. M&E Matrix/Plan :
It is a frame which includes following components and use for the monitoring activities for the project/program.
Outputs : Outputs that the project Intended to Produce
Indicators : Measuring of Results (Qualitative and Quantitative) from Results Framework
  Baseline : Status of the location, people or target group before starting of the project
  Target : Specific Value (quantity or quality) is expected to reach by a particular date.
Methodology: Data collection method (Survey, a review, meeting )and source of information, Analysis of Information.

## Slide 13: Component of Monitoring Framework
Responsibilities : Who will responsible for organizing the data collection, verifying data quality and source.
Frequency : Periodicity (Daily, Weekly, Monthly, Quarterly, Annual etc)
Mean of Verification : Information or documentations that verify the results/ proof
Recourses required for M&E : amount required to conduct the M&E
Risk factors : The factors that affect the M&E activities.
Rational : This should describe the uses of information and assess of the information.

## Slide 14: Difference between monitoring and evaluation
Subject | Monitoring | Evaluation
Purpose | Know the progress status, correcting problem, | Assess the project result, lesson learned, incorporate to next project
Frequency | Regular | periodic , midterm, after completion of the project
Involvement | Internal project staff | Experts, External Resource Persons
Use | Project and Beneficiaries | Outsiders
Focus Area | Input, Output | Outcome, Effect, Impact
Cost Factor | Less | High
Report | Project Management | Donors,
Answer | What activities were implemented and result achieved | why and how results were achieved

## Slide 15: Process of monitoring (steps)
Understanding of projects goals and objectives
Study /review the main activities which are carried out for getting the goals and objectives
Prepare questionnaires/checklist/Formats
Set qualitative and qualitative indicators for measuring outputs and outcomes.
Specify tools and method for measuring indicators of the project output and outcome

## Slide 16: Process of monitoring (steps)
Who monitors : responsible person to be fixed
Collection of information from field
Analysis and find results
Prepare report of conclusion, recommendation
Dissemination of the information
Decision making

## Slide 17
Monitoring Tools
Routine Reporting / Recording System
Survey
Review meeting
Public audit
Interaction with beneficiaries
Key informant interviews
Regular Staff Meeting
PRA
RRA

## Slide 18: Evaluation
Definition
Evaluation is a process to study what degree of objective has obtained after the completion of the project.
Evaluation is a process of critically assessing whether the immediate objective of the project is being achieved and whether they are contributing to the attainment of the development objective.
Evaluation is a process for determining the relevance, efficiency, effectiveness, impact sustainability of the project activities in the light of the objectives

## Slide 19
  To clarify its objectives and assess their relevance.
  To see how efficient the work in terms of using resources.
  To assess how effective project is and what progress it is making towards achieving its objectives.
  To find out what impact it is making.
Why Evaluation?

## Slide 20
  To look at the long term implications. Is the work sustainable?
  Evaluation is important to identify he constraints or bottlenecks that hinder the project in achieving its objective.
  It is essential for drawing lessons from the project implementation experience and the learning of the lesson is used in the new project.
Why Evaluation?

## Slide 21
a) Ongoing (Mid-Term) Evaluation
Mid-Term evaluation is the analysis, during the implementation phase of an activity, of its determining relevance, efficiency and effectiveness of the present and likely future outputs, effect and impact.
It can assist decision makers by providing information about any needed adjustment of objectives, policies, implementation strategies or other elements of the project as well as providing information for future planning.
Types Evaluation

## Slide 22
Ongoing (Mid-Term) Evaluation
The tasks of Mid-Term evaluation are:
Over all performance of the project during the implementation
To establish whether project objective are being achieved or as likely to be achieved and whether there are unanticipated and unwanted side effect
To assess whether the assumption in the project design are valid.
Types Evaluation

## Slide 23
b) Post (Impact) Evaluation
Post (Impact) evaluation is undertaken at full project document, some years after project completion when full project benefits and impacts are expected to have been relished.
The purpose of terminal and post evaluation in two fold.
To assess the achievement of overall results of the project in terms of efficiency, effectiveness, and impact.
To learn lessons for future planning i.e. design or formulation, appraisal, implementation and monitoring and evaluation of development activities.
Types Evaluation

## Slide 24
b) Post (Impact) Evaluation
The performance i.e. the extent to which it proceeded according to project design and plan.
It is impact in term of the economic, social, and environmental objectives particularly with reference to the target group.
Its institutional development including organizational for project management and delivery of services and institution and procedure established at grass roots level e.g. or beneficiary post, position.
Types Evaluation

## Slide 25: TERM OF REFERENCE FOR EVALUATION
Background and Context
  Description of the intervention (what kind of evaluation)
  Describe about the project
  Geographic context and coverage
  Total budget and donors contribution
  Key partners
Evaluation Purpose
  Mention why the evaluation is being conducted
  Who will use and how they will use?
  Some background and justification for why the evaluation is needed

## Slide 26: TERM OF REFERENCE FOR EVALUATION
Objectives
  Objectives of the evaluation.
4. Evaluation Questions
  What is the checklist / questions for the evaluations
Methodology
  Describe the how the evaluation is carried out.
Evaluation Product
  Inception report
  Draft evaluation report
  Final evaluation report

## Slide 27: TERM OF REFERENCE FOR EVALUATION
Evaluation Team Composition and Required Competencies
  Evaluation skills, competencies and characteristics
  Evaluation Team, roles and responsibilities
Evaluation Ethics
  Evaluation Ethics to be mentioned
Implementation Arrangement
  Line of authorities,
  Lines of and processes for approval and logistical consideration, such as equipment, materials etc.

## Slide 28: TERM OF REFERENCE FOR EVALUATION
10. Time Frame
  Desk review
  Briefings of evaluators
  Finalization of designs
  Field visit / data collection
  Preparing draft report
  Validation
  Finalization
11. Cost
  Mention cost calculation for the evaluation

## Slide 29: TERM OF REFERENCE FOR EVALUATION
12. Annexes
  Result Frame work
  Key stakeholders and partners
  Document to be consulted
  Evaluation Matrix
    Relevant evaluation criteria
    Key questions/sub questions
    Data sources
    Data collection method/tools
    Indicators
    Methods for Data Analysis

## Slide 30: Impact Assessment of the project: how?
  Preparation Phase :
Determine the purpose and users of evaluation result
Determine who needs to be involved in the evaluation process
Define evaluation objectives and questions together with key stakeholders
Draft the Terms of Reference (ToR) for the evaluation; indicate a reasonable time-frame for the evaluation
Identify the need of skills and experiences required in the evaluation team

## Slide 31: Impact Assessment of the project: how?
  Preparation Phase :
Oversee the collection of existing information/data;
Preparation of background document(s) as necessary
Select, recruit and brief the evaluator(s)
Ensure that background documentation/materials compiled are submitted to the evaluator(s)

## Slide 32: Impact Assessment of the project: how?
  Preparation Phase :
Decide whose views should be required (e.g., service providers, service users, etc.)
Ensure the use of a variety of data gathering methods
Propose an evaluation field visit plan
Preparation of Questionnaire/checklists

## Slide 33: Impact Assessment of the project: how?
  Preparation Phase :
Select data collection methodology
Ensure availability of funds to carry out the evaluation
Brief the evaluator(s) on the purpose of the evaluation; use this opportunity to go over documentation and review the evaluation work plan.

## Slide 34: Impact Assessment of the project: how?
  Implementation Phase :
Ensure that the evaluator(s) have full access to files, reports, publications and any other relevant information
Ensure adequate administrative and logistical support during the evaluation
Conduct field work, collection of data and information applying appropriated method.
Data analysis, Preparing report with conclusion, lesson learned and recommendation

## Slide 35
  Implementation Phase :
Follow the progress of the evaluation; provide feedback and guidance to the evaluator(s).
Assess the quality of the evaluation report(s) and discuss strengths and limitations with the evaluator(s) to ensure that the draft report satisfies the ToR, and that evaluation findings are defensible and recommendations are realistic
Arrange for a validation workshop/meeting with the evaluator(s) and key stakeholders to discuss and comment on the draft report
Approve the end product; ensure presentation of evaluation results to stakeholders; include country office programme staff in debriefing to promote information sharing and use of evaluation results.
Impact Assessment of the project: how?

## Slide 36
  Follow-up Phase:
Evaluate the performance of evaluator(s) and place it on record
Disseminate evaluation results to the key stakeholders and other audiences
Promote the implementation of recommendations and use of evaluation results in present and future programming;
Monitor regularly to ensure that recommendations are acted upon.
Impact Assessment of the project: how?

## Slide 37: Evaluation Report Template
Title and opening pages
  Name of the evaluation intervention
  Time frame and date of the report
  Names and organization of the evaluators
  Name of the organization commissioning the evaluation
  Acknowledgements
Table of Contents
List of acronyms and abbreviations

## Slide 38: Evaluation Report Template
3. Executive Summary
  Briefly describe the intervention
  Explains the purpose and objectives of the evaluation
  Describe key aspect of the evaluation approach and methods
  Summarize principle findings, conclusions and recommendations
4. Introduction
  Why the evaluation was conducted
  Explain how the evaluation result could be used.
  Mention the intervention that was evaluated
  How the information contained in the report.

## Slide 39: Evaluation Report Template
Description of the Intervention
  What is being evaluated, who seek to benefit and problem and issue it seeks to address
  Expected results framework, implementation strategies, assumptions
  Significant changes
  Key partners involvements
  Scale of the intervention
  Total resources
  Effects in Social, Political, Economical and Institutional factors
  Design Weaknesses, implementation constrains.

## Slide 40: Evaluation Report Template
Evaluation scope and objectives
  Evaluation scope
  Evaluation Objectives
  Evaluation criteria
  Evaluation Questions

## Slide 41: Evaluation Report Template
Evaluation Methods
  Data sources
  Sample and sampling frame
  Data collection procedures
  Major limitation of the methodology
7. Data Analysis
  Procedure of data analysis
  Accuracy of the data
  Weakness in data analysis and gaps

## Slide 42: Evaluation Report Template
Findings and Conclusions
  Findings
  Conclusions
Recommendations
  Recommendation should be linked to the findings and conclusions.
Lesson Learned

## Slide 43: Evaluation Report Template
Annexes
  TOR
  Methodology (Additional)
  List of individuals or groups interviewed or consulted
  List of supporting document reviewed
  Result framework
  Summary table of findings
  Short biographies of the evaluators and team composition
  Code of conduct signed by evaluators.

## Slide 44: Thank You

## Slide 45
Define terminology
Efficiency: a measure of how economically input is used to produce out puts.
Effectiveness: a measure of the extent to which a programme achieves its results( outcome and objectives)
Relevance: the degree to which the output, outcome and objective of program remain valid
Impact: the change in community from the intervention of the projects.
Output: product that result from the completion of the activities. it assure between input and outcomes.
Outcome: the intended effects, of an intervening of outputs.
Activity: the events carried out for producing output is called activities.