## Slide 1: NAMibia unpaf mtr
Validation Workshop
Nicholas Siwingwa
27th October 2016
UN House, Windhoek

## Slide 2: Presentation outline
Key principles for GRN – UN Partnership
Outline of UNPAF
Assumptions on UNPAF operation
Scope of MTR
Findings
Conclusions
Recommendations

## Slide 3: “Enhanced GRN-UN Partnership through Delivering as One (DaO) in Namibia”
Government ownership and leadership of national development processes
Use of existing government systems
Full alignment of UN country programmes with the NDP 4
Implementation through the UN system, where appropriate, of government-funded sector programmes and projects.
Leveraging the limited available resources
Progressive and sequenced movement towards Delivering as One

## Slide 4: The UNPAF…
Five Year partnership framework between GRN and UN System
Aligned with national development plan – NDP4
Budget of USD 79.5 Million
Institutional Environment
Education & Skills
Health
Poverty Reduction
  Transparency, accountability and effective oversight
  Promoting Human Rights
  Functional M&E and Statistics systems
  Compliance with international treaties
  Four Outcomes
Implementation of policies and programmes to improve learning outcomes
One Outcome
Two Outcomes
Accountable and coordinated multi-sectoral mechanisms to reduce burden of disease
Strengthened health systems
Implementation of poverty reduction and vulnerability strategies and policies
Five Outcomes
Implementation of Gender Action Plan and GBV plans
Strengthened national social protection system
Support to severely poor and vulnerable households
Implementation of environmental and climate change policies

## Slide 5: Assumptions… Coordination
Pillar Coordination Committees
Pillar 1
Pillar 2
Pillar 3
GRN-UN Technical Committee
NPC
RCO
Development Forum
GRN
UN
Other stakeholders
Pillar 4
PS Forum
UN
IPs
*

## Slide 6: Assumptions… Implementation
Joint two year work plans (UN agencies, developed with IPs)
NDP 4 M&E framework for monitoring progress
Mid-term and End-term review

## Slide 7: Assumptions… UN Delivering as One
One Programme Framework
GRN-UN Partnership Agreement Framework
One Budgetary Framework
Budget Plans and Reports
Joint Programmes (HIV/AIDS)
Common Resource Mobilization
One Empowered Leader and One Empowered Team
RC system
UN Country Team
One Office
UN House
Harmonized Business processes
One Voice
Joint advocacy and communication (UNCG)

## Slide 8: Scope of the MTR
Evaluate overall implementation of UNPAF
  Framework management
  Coordination Mechanisms
  Reporting (M&E)
  Capacity
  Sustainability
  Scalability
  Relevance
  UN Delivering as One
Conclusions
Recommendations

## Slide 9: Findings… Framework management
Limited understanding of UNPAF amongst GRN IPs
  Delayed GRN signing of Action Plan and change
  Insufficient use of trouble shooting mechanism when faced with challenges
Insufficient engagement of CSOs and other stakeholders in implementation
Did not delay implementation of the activities!

## Slide 10: Findings… Framework coordination
Coordination is improving… GRN increasingly calling on UN to support: roll out and domestication of SDGs; engagement of UN system in development of NDP 5
However under UNPAF agreed mechanisms:
MTR process
  Little coordination between UN and GRN
GRN-UN Technical Committee
  Met twice in 2015
Pillar Coordination Committee
  Only Education and Skills Pillar meets regularly
Development Forum
  Not met – UN has not presented Annual Report to GRN
PS Forum
  No UN participation

## Slide 11: Findings…
Reporting
GRN M&E framework for NDP4 still being finalised
No UN systematic reporting to GRN
Sustainability
Activities were closely aligned with NDP 4 and sector ministry strategies especially Pillars 3&4 on Education & Skills and Health so scope for sustainability provided GRN capacity is adequately developped.
Pillar 4 on Poverty reduction has a new Ministry, ongoing interaction will determine sustainability
Scalability
Programs are scalable, but need for further capacity development at both the individual and institutional levels

## Slide 12: Findings… emerging development context
“Moving together towards prosperity” NDP 5
“War on Poverty!”
Disaster Risk Management

## Slide 13: Alignment with emerging development context
Emerging issue | UNPAF Alignment | 
Harambee Prosperity Plan | Effective Governance and Social Progression | 
DRM Strategy | Policy and legislative framework for DRM, Monitoring and Reporting on Sendai Framework, Improve education on DRM, Health systems preparedness, Resilience building activities | 
SDGs | No Poverty/ Zero Hunger/ Good Health and Wellbeing/ Quality Education/Gender Equality/Clean Water/Reduced Inequalities/Climate Change/Life on Land/Peace/Justice and Strong Institutions (11 out of 17 SDGs) | 
War on Poverty |  | 
NDP 5 | Social Upliftment, Environmental Sustainability, Good Governance | 

## Slide 14: Findings… UN Delivering as One
Joint Programme on HIV/AIDS – one lead agency, well coordinated, achieving results
Education and Skills Pillar – UN agency coordination, co-ownership of Pillar agenda
Emergency and Humanitarian Focal Point – Coordinated response to Dept. of Disaster Risk Management

## Slide 15: Findings… Where coordination and implementation led to results
Health procurements services
Emergency Response
Support to HIV/AIDS
  UNICEF and WHO supported procurement of vaccines – increased efficiency of government resources - Namibia is now purchasing at 60% below those prices previously agreed in bilateral tenders.
  UN facilitated deployment of experts from Capacity for Disaster Reduction Initiative (CADRI) and the United Nations Disaster Assessment and Coordination System to conduct a capacity assessment - recommendations were adopted at high-level workshop
  The UN JUTA, led by UNAIDS and WHO, the UN has assisted GRN to negotiate an extension of the Global Fund support to December 2017 (from mid-2016 deadline for utilisation), and are now looking to see how it can actually support the absorption of the funds.

## Slide 16: SWOT Analysis on UNPAF delivery…
Strengths
Ongoing implementation of activities
Weaknesses
Coordination and programming capacity of GRN and UN
Challenges
Capacity constraint from IPs and also UN
Opportunities
Sharing or pooling of resources/capacity
Monitoring and Evaluation function
No real information repository
Focus on trying to Deliver as One to gain efficiencies
Strong appreciation from GRN of UN support – partner of choice
Loss of institutional memory

## Slide 17: Conclusions…
Overall MTR found the UNPAF to still be relevant →implementation of the activities is ongoing and progress is being made towards achieving targets.
But to get desired results it must address the following challenges:
Information sharing on the UNPAF
Coordination mechanisms to improve delivery
Reporting
Capacity to coordinate and implement
MTR provides an opportunity to strengthen partnership for effective delivery!

## Slide 18: Recommendations
Theme | Recommendation | Timeframe | Responsible
General | Regular information sharing on UNPAF 2. Wider stakeholder (CSO, DPs, Academia, Private sector) involvement | Short term – immediate Short term - immediate | UN/ NPC UN/NPC
Emerging context | Addendum to show alignment with emerging development context. Reformulate Pillar 1 to include Disaster Risk Management Preparedness Decision on governance related activities | Short term Short term Short term | UN/ NPC UNCT/EHFP/NPC/OPM UN/OPM/NPC
Main recommendation is for the UNPAF to in its current form continue with a few change until 2018….

## Slide 19: Recommendations
Theme | Recommendation | Timeframe | Responsible party
Reporting and M&E | Develop GRN M&E framework Build capacity of UN and GRN on M&E Align UNPAF results matrix to GRN M&E framework | Short term Medium term Short term | NPC UNCT/ M&E Team/ SAU UN
Coordination Mechanism | Reinstate GRN-UN Technical Committee and include IPs Development Forum to be held annually Reinstate Pillar Meetings with GRN counterparts Strengthen coordination capacity | Short term Short term Short term Medium term | NPC/UN (RCO) NPC/RCO NPC/UN/IPs RCO/NPC

## Slide 20
THANK YOU!