EU/UNDP Project on Building Transformative Policy and Financing Frameworks to increase Investment in Biodiversity Management

The Biodiversity Finance Initiative (BIOFIN)

Final Evaluation

February 21, 2017

Stephanie Hodge

International Consultant

November 15 - February 15, 2017

Contents

ABSTRACT	5

Executive Summary	6

1. Introduction	12

1.1. Purpose/scope of the evaluation	12

1.2. Methods/limitations	12

1.3. Structure	14

2. The project and its development context	14

2.1. Project start and its duration	14

2.2. Problem(s) the project seeks to address	14

2.3. Immediate and developmental objectives of the project	14

2.5. Results expected	15

3. Findings and conclusions	16

3.1. Project formulation	16

3.1.1. Conceptualization/strategy/design	16

3.1.2. Global/regional/country ownership/driven-ness	17

3.1.3. Beneficiaries/Stakeholders	17

3.1.4. Replication approach (see results, methods section)	18

3.1.5. Linkages/synergies	18

3.2. Project Implementation	20

3.2.1. Project institutional and management arrangements	20

3.2.2. Implementation approach/adaptive management summarize	22

3.2.3. Monitoring and evaluation	23

3.2.4. Partners participation	25

3.2.5. Finance 	(See All EU Country Delivery / Results Profiles Annex)	26

3.2.6. UNDP role and comparative advantage	29

4. Results	29

4.1. Method	31

Five Principle Steps	31

4.2. Knowledge Management and Global BIOFIN Learning	35

4.3. South-South Cooperation and Learning	36

4.4. Institutional Capacity Strengthening	37

4.5. Policy Level Results	38

5. Sustainability	40

6. Conclusions	41

7. Key Lessons Learned	43

8. Recommendations	44

ANNEX 1: EU/UNDP LOGFRAME EXPECTED RESULTS	48

ANNEX 2 KM and NODES	48

ANNEX 3:  OPTIONS FOR PHASE TWO	49

ANNEX 4: WORKBOOK DESCRIPTION	51

ANNEX 5: LOGFRAME STATUS UPDATE – DECEMBER 2016	52

ANNEX 6: UPDATED PROJECT INFORMATION	61

ANNEX 7: STEERING COMMITTEE MEETINGS SUMMARY	65

ANNEX 8: BIOFIN CHRONOLOGY OF ACTIVITIES	81

ANNEX 9: STATUS OF BIOFIN DELIVERABLES / COUNTRY	91

ANNEX 10: THEORY OF CHANGE 2015	93

ANNEX 11: EXCERPTS FROM THE KEYNOTE SPEECH - BIOFIN CONCEPT - UNDP’S GLOBAL DIRECTOR FOR SUSTAINABLE DEVELOPMENT	94

ANNEX 12: METHODLOGY - PROGRESS REPORTED 2017 FEBRUARY	95

ANNEX 13: KNOWLEDGE MANAGEMENT WORK EXAMPLES OF CASE STUDIES	98

ANNEX 14: CURRENT SENIOR TECHNICAL ADVISOR TABLE	99

ANNEX 15: PHASE TWO - OPTIONS FOR SCALE UP	100

ANNEX 16: EU/UNDP PILOT STATUS REPORTS/FINANCIAL DATA 2017	101

Kazakhstan	101

Malaysia	104

The Philippines	105

Seychelles	108

Uganda	110

Chile	111

Ecuador	114

South Africa	116

# ABSTRACT

BIOFIN was developed in response to the 10th Conference of the Parties (COP-10) of the Convention on Biological Diversity (CBD) which identified the need for better information on current expenditures and financing needs, and a comprehensive methodology to develop resource mobilization strategies. BIOFIN is considered an important support to the ambitious CBD Strategic Plan for Biodiversity 2011-2020. It responds directly to Aichi Target 20 on Resource Mobilization (See Box 2.1), which in turn supports the other 19 Targets, to facilitate the delivery of National Biodiversity Strategies and Action Plans (NBSAP) (See box 2.1). BIOFIN was launched at COP-11 in India in 2012, under an initial grant from the EU, and to date has received additional financial support from Germany, Norway, Switzerland and Flanders.

The goals of BIOFIN include the following:

• Develop and pilot a new approach and methodology to fill the financing gap for biodiversity

• Support CBD parties in reporting on resource mobilization

• Assist countries to better mobilize and align domestic and international finance for biodiversity including implementation of NBSAPs and to achieve sustainable development goals.

Figure 1 MAP OF BIOFIN countries, 2016

| 30 core countries of implementation | Eurasia-Pacific: Bhutan, Fiji, Georgia, India, Kazakhstan, Kyrgyzstan, Indonesia, Malaysia, Mongolia, Philippines, Sri Lanka, Thailand, Vietnam. Africa: Botswana, Mozambique, Rwanda, Seychelles, South-Africa, Uganda and Zambia. Latin America/The Caribbean: Belize, Brazil, Chile, Colombia, Costa Rica, Cuba, Ecuador, Guatemala, Mexico and Peru. |
| --- | --- |

# Executive Summary

Background

The Biodiversity Finance Initiative, BIOFIN, is jointly supported by the European Union (EU) and the governments of Germany, Switzerland, Norway and Flanders. As a multi-donor initiative, BIOFIN holds US$ 29 million, with an initial contribution of Euro 4 million from the European Union (EU). The EU contribution from October 2012 to December 2016 included specific support to eight countries: Chile, Ecuador, Kazakhstan, Malaysia, Philippines, Seychelles, South Africa and Uganda. In accordance with UNDP and EU M&E policies and procedures, all UNDP-supported projects are required to undergo a terminal evaluation upon completion of implementation.

BIOFIN is a global partnership addressing the biodiversity finance challenge in a comprehensive manner, and aims to provide an innovative methodology, enabling countries to measure their current biodiversity expenditures, assess their financial needs in the medium term and identify the most suitable finance solutions to bridge their national biodiversity finance gaps.

BIOFIN now involves thirty pilot countries, coordinated by a global UNDP-managed team supporting the new methodology development. The global team works closely with inter-disciplinary national teams including UNDP and key local counterparts who are customizing the methodology to the national contexts. At the national level, BIOFIN teams generally work with Ministries of Finance (treasury), Economy, Planning and or Environment/Natural Resources Management bringing together a core group of national key stakeholders, including NGOs and the Private sector. The private sector has emerged as a major target for policy change, engagement in finance solutions with governments and for capacity building.

In this light, UNDP-GEF, as part of its agreement with EU, is evaluating the project for results. Although this is a terminal evaluation for the agreement, it is progress towards expected outcomes: 1. Program learning support global and national M/E System is in place or not, 2. Transformation of the biodiversity financing landscape, 3. Methodology Development on Biodiversity Finance, 4. Leveraging Resources for Biodiversity Finance.

………………………………………………………………………………….

RELEVANCE: Rating:  Relevant (R)

The project was part of a multi-donor partnership: UNDP, Germany, Flanders, Norway and Switzerland. The high demand, scalability and ownership of governments are clear indicators of high relevance. Also, during the Regional workshop in Antigua, January 2017, the relevance was clearly expressed by all presenting key stake holders including high level official from country delegations (MOE, MOF, UNDP, PS, and MOP) The 2017 global BIOFIN progress report shows also the data from its survey on BIOFIN Relevance being affirmative of the same. The project concept is perceived by stakeholders to be highly relevant because its unique focus on Efficiency, Production, Markets, and Budgeting in line with national development plans. This has been confirmed in discussion with Ministries of Finance and Planning in all eight BIOFIN pilot countries, Seychelles, the Philippines, Seychelles, South Africa, Uganda, Kazakhstan, Malaysia and Chile, during the evaluation. It opened a global window of opportunity on biodiversity financing for development, responding to the need for efficiency, effectiveness and better decision-making, planning and budgeting processes for sustainable development gains (linked to SDGs).

The year 2015 was a turning point in the global debate on sustainable development finance, witnessing several major milestones. In July, the third global conference on financing for development in Addis Abba set out a new agenda to move from billions to trillions, in order to meet the needs of this new universal goal. In September, the formal adoption of the Sustainable Development Goals provided the world with concrete targets to achieve sustainable development. In December 2015, the signing of the Paris Climate Change Agreement delivered governments a mandate to phase out growth policies that ignore environmental impacts.

BIOFIN is very relevant in its support to the environment and international commitments. The project is aligned with the conducive global policy environment cantered on the financing of development goals. Under the CBD framework, BIOFIN is directly contributing to Aichi targets 17 and 20. BIOFIN’s contributions to countries were mentioned by 22 parties during the CBD COP 13 plenary in Mexico 2016.

The concept and its objectives proved to be appropriate and are very appreciated by UNDP, countries and donors interviewed at the National level. For instance, BIOFIN had excellent uptake in the Philippines and Kazakhstan and interest to co-finance -for finance solutions in the Philippines and Chile.

The project is responding to a global demand for new skills and demonstration of concepts. It is fully aligned with the countries’ EU and UNDP objectives. When the evaluator asked why this had not been done before, a simple concept that makes so much sense, the reply was “The obscure takes time to be noticed, the obvious takes even more.” (Director of Biodiversity for Business Philippines)

EFFECTIVENESS: Ratings: Highly Satisfactory (HS)

A central question framing the evaluation was “how well does the BIOFIN project and the tested methodology help countries put in place policies, knowledge, values and skills that provide institutional and market incentives to encourage a shift in production patterns to reduce adverse impacts on biodiversity.” The following questions framed the BIOFIN results, indicating how well BIOFIN has done for: 1. contributing to the transformation of the global Biodiversity Financing Landscape. 2. Developing a scalable methodology and 3. Leverage Resources for Biodiversity Finance.

That said, this project and its implementation approach exceeded its expectations to deliver.

For PP1: number of participating CBD parties that integrate considerations on biological diversity and its associated ecosystem services into development plans, strategies and budgets (target: eight pilot-countries- Fully Met Expectations). For PP2: number of participating countries that have identified and reported funding needs, gaps and priorities (target: eight pilot-countries Fully Met Expectations). For PP3: number of participating countries that have developed national financing plans for biodiversity (target: eight pilot-countries Fully Met Expectations). Baseline: No frameworks exist. Target groups: Ministry of Finance and Ministry of Environment of eight pilot-countries: Chile, Ecuador, Kazakhstan, Malaysia, Philippines, Seychelles, South Africa and Uganda.

The project was implemented through pilots in 30 countries (8 EU financially supported) to complete BIOFIN Workbooks (first and second drafts) including three assessments (Policy Institutional Review PIR, Biodiversity Expenditure Review BER, Financial Needs Assessment FNA and Financial Planning FP) and finally - Finance Solutions FS (added last) to complete a transformative process.

Since countries began implementing the BIOFIN methodology, a wealth of new practices and finance solutions emerged. For instance, the first two steps PIR, BER, in workbook are now separated. Implemented through UNDPs global DIM modality, a very rich body of global experiences transpired through global and regional workshops, webinars, country calls and technical missions, knowledge and experience sharing events to inform, capture and distil an essential update and upgrade of the first BIOFIN Workbook (originally drafted in 2014 and in its revised version launched at the CBD COP in 2016). The EU ROM evaluation (2015), was noted as instrumental for the guidance it had provided to pilots and for updating the workbook to help solidify the results.

The methodology (BIOFIN Workbook) was updated and reviewed by peers. It is now a model programme ready for translation to a global learning module and further rollout. BIOFIN contains stepwise guidance on engaging with the policy and budgetary processes and has a strong focus on a transformative inter-governmental and private public change process, much more than just the delivery of a technical BIOFIN finance guidebook.

The BIOFIN approach (2016 BIOFIN Workbook, December 2016) has received positive feedback from all pilot countries visited and interviewed. The country respondents (testified the BIOFIN process has enabled a generation of solid figures (backed by evidence and methodology) to be presented to their key policy-makers, including a first generation of multi-year expenditure reviews and detailed calculations of future needs in financing biodiversity. Partners and external experts shared the view that BIOFIN was a technical set of assessments and skills, and has “been a venue for discussing the barriers and broader policy and financial reforms.” This includes the need to identifying finance solutions for expanding the reach of biodiversity finance to sustainable development planning.

The BIOFIN implementation approach involved a decentralized and flexible roadmap, in response to its different contents and changing environments (currently more structured for capacity strengthening and institutionalization), and has delivered a peer reviewed methodology applicable for the different content.

Respondents from pilots say the valued added of BIOFIN’s approach are it’s cross sectoral and transformative focus, based on a solid policy analysis, identifying the change agents for Biodiversity finance, while also targeting private public partnerships for the financing solutions. The final important step is resource mobilization through Finance Solutions (Workbook Chapter 7) which completes the cycle of change. The scope of the analysis and planning is broad, focusing on all types of solutions, national & international, public & private, traditional & innovative, short & long term.

Factors for BIOFIN success included mobilizing resources for work on implementation, including financial planning and solutions. The early input of additional capital by partners to BIOFIN was an excellent global financing result. Notably it was also recorded a challenge for the management team responsible for roadmap design in the eight countries. The rapid growth questioned the early project setup (geographical expansion and expansion in terms of content). Consequently, the new resources from global partners were successfully employed to countries to help undertake additional work on financing solutions in EU countries which will help to demonstrate the cycle of change.

Principle learning from the early implementation included a refocus of the target beneficiary from Ministries of Environment to that of the Ministries of Finance and Planning. Though delivering (and developing together) the BIOFIN workbooks, critical revision to enable the political dimension around the softer aspects of relationships and engagement. This involved identifying key agents of change for work on the harder skills of data collection and processing and imparting the language of the production and business was critical for success. It was also important to identify champions for the messages. In Philippines for example, a local governor was the BIOFIN National champion. Champions are being identified as instrumental for leveraging policy dimensions and financing for longer term work and subnational BIOFIN implementation.

While pilot countries reported in depth on how BIOFIN is actively influencing policy changes in their quarterly reports and in consults: Chile, the Philippines, Kazakhstan, Seychelles, Uganda, Ecuador, South Africa and Malaysia, the institutionalization process needs to be accompanied by more strategic communication.

With further refinements consolidation and packaging of the case studies, BIOFIN is readied to be scaled as a global learning agenda targeting decision makers all over the world. UNDP and the EU are uniquely positioned to continue to support this agenda.

EFFICIENCY: Rating: Highly Satisfactory (HS)

The intervention has thus been highly cost effective. As a small investment, BIOFIN was implemented in countries with relatively modest financing, outsourcing TAs and a small team in Istanbul. Project costs are justified -many early results recorded including significant policy changes and financial system infrastructure improvements. National level implementation has been through teams. Technical workshops and regional workshops were recorded as cost effective, pilot country teams supported the methodology development and engaged in learning by doing through South-South and triangular cooperation.

Although there was significant delay in the start of implementation, the upfront time and investment spent in developing the draft Workbook to start piloting was time well spent. It was consequential to have helped with management decisions to set up the best possible team of global experts* (with unique skill sets) to inform the principle methodological approach, a process of active learning with countries and distilling lessons and refinements from all 30 countries. This is a good choice. Countries reported that they are now advancing rapidly through the workbooks. All pilot countries will have completed the four steps, and some will have begun implementing financing solutions by December 2016.

With support of an emerging Technical Committee, a peer-review system, feedback came through implementation at country level which was collected through the regional workshops. The governance at global level was adequate (GST includes the UNDP and donors, meets at least twice per year and provides adequate guidance to the overall project). At country level, National Steering Committees (NSC) were established, sometimes within the NBSAP Steering Committees, with participation of relevant institutions (MoE, MoF) and in some cases the private sector (the Philippines, Seychelles). Except in a few cases, the NSCs focused on the delivery of the outputs but had improved toward more specific outcomes and objective-based monitoring (post ROM) with strategic guidance by NSCs towards achieving these objectives. The performance monitoring and ME system has been improved with the recent engagement of an ME expert in the Global Team and recruitment of a complete team of STAs to follow-up implementation at country level. The original two STAs recruited in 2014 could not adequately cover all the countries, and two more were recruited in 2015. Five STAs were on board by early 2016. The follow-up system can be improved. In general, the EU delegations have been contacted, but few have attended project activities. Only the EU delegation in Uganda was reportedly involved in the project.

The fifth and last step of the BIOFIN process, Implementing Finance Solutions/Resource mobilization is a critical step to catalyse the policy shifts and incentivize private sector engagement and finances to help fill the funding gap.

BIOFIN is positioned to help broker new financing and development relationships, including around the SDGs. Three countries integrated PIR financial reviews with climate change and poverty: Bhutan, Indonesia and Kyrgyzstan. Rwanda and Mozambique are deploying a similar approach. Bhutan supported the full integration with UN PEI, a joint institutional and policy analysis. Moving to integrated PER approaches to support SDG planning is an important next step and has value added, leading to more sustainable financing solutions. Countries can learn from BIOFIN’s transformative approach to finance infrastructural improvements.

Direct implementation approach (DIM) has enabled South-South and cross-country learning with decentralized monitoring and implementation support working globally directly with Minister of Finance, Ministry of Environment and key partners through steering and technical committees.

It was effective to have established partnerships and synergies with related initiatives at the global and national level. More can now be done to support a phase two and broker partnerships for a package of services for greater momentum, i.e. private sector, TEEB and WAVES, and build complementary for a full package offer of finance solutions. The work with the private sector is very interesting with great potential for high global impact. A close partnership can be forged with UNDP regional work on the private sector.

SUSTAINABILITY: [Rating: Likely (L):]

Although the Workbook is peer reviewed and ready for scale-up/rollout, before the project can be a demonstrated transformation, the completed final step to develop a financing plan and solutions should be implemented. The project can only then be said to be consolidated and packaged by December 2018 to show the complete approach to transformative change. It will be thus a good idea to implement and document in leading BIOFIN mega-diverse countries with financing and TA for the demonstration of finance solutions to show the private sector, public and the government the full benefit and stimulate the market interest in driving biodiversity finance solutions.

Demonstration of Private Sector Drivers of Biodiversity Business Solutions

As the Executive Director of NGO business for Environment in the Philippines stated, “If there’s a hundred things to do, pushing for a business-friendly policy for offsets is the one that will really matter.” This key project focus on working with the private sector was reiterated by the Kazakhstan BIOFIN pilot team who noted the work on a policy for biodiversity business and startups is key to stimulate the changes necessary for transformative change.

Showcase Regional BIOFIN work - Exit strategy

Latin America is ready to work regionally on biodiversity offsets. It would be good if UNDP can support one regional scale initiative as a pilot, i.e. Latin America.

IMPACT: Global and national level impacts Rating: Significant (S)

The BIOFIN methodology is helping pilot countries through a transformative change process, policies, skills and market incentives to encourage a shift in production patterns to reduce adverse impacts on biodiversity. “The way to protect biodiversity is through a business model,” according to the Philippines BIOFIN team 2017.

This project-tested methodology for biodiversity financing in a step-by-step approach has proven to being promoting a new global discourse on biodiversity financing. The approach is empowering participant countries at COPs. A major political result is that the global discourse on Biodiversity finance has shifted. BIOFIN promoted a new global discourse on biodiversity financing for developing and developed country partners. It exceeded expectations by designing a new methodology informed by practice in eight pilot countries.

The BIOFIN approach identifies the key interlocker for change by bridging work of important ministries and putting the ministry of finance at the centre, while empowering Ministries of Environment with important figures. The countries have been enabled to map out the expenditures and costs and to build a strong case for a financing plan that is focused on rescheduling and mobilizing resources. BIOFIN is all-encompassing, superseding other expenditure review methods as a transformative approach that includes the political and resource dimensions. As a partnership, financing has already increased momentum. The local level work is also already beginning to tap resources.

# 1. Introduction

# 1.1. Purpose/scope of the evaluation

In line with the original EU/UNDP agreement signed on October 25, 2012, this is the final evaluation of the agreement which was originally planned to end in July 2015. An extension was granted for 14 months. The terminal evaluation covers the period 2012–2016 and all BIOFIN countries funded by the EU. It has addressed the results of BIOFIN implementation. The central research question of the evaluation is: To what extent did BIOFIN achieve the expected results?

# 1.2. Methods/limitations

The BIOFIN Terminal Evaluation (TE) set out to vet, qualify and quantify the original EU/UNDP Partnership agreement including four expected outcomes, 18 activities and 4 composed indicators (each consisting of several sub-indicators). The evaluator set out to document the story of BIOFIN, its evolution, implementation and results, capturing key lessons learned and key recommendations. The purpose (as per the TOR attached) was a terminal evaluation of the EU/UNDP partnership agreement as per expected results and timeline. As per the evaluation goal (also see TOR), the evaluator considered the goals and activities - global, regional (TAs) and country level inputs against the broader UNDP/EU sustainable development goals for improved global biodiversity management. The project was an integral part of a broader UNDP-GEF Biodiversity, Ecosystems and Sustainable Development change agenda focused on instilling new methods, standards, mainstreaming environmental goals into national accounting systems and developing tools for financing sustainability.

The evaluative work was forward looking, participatory and inclusive of the entire global EU/UNDP team, Steering Committee members, eight country teams and external stakeholders and experts (See complete list of stakeholders interviewed and observed in Annex). Standard criteria of relevance, effectiveness, efficiency, sustainability and impact[i] were employed, as defined and explained in the EC evaluation standards and the UNDP Guidance for Conducting Evaluations of UNDP-supported programs and projects. As UNDP-GEF NBSAPs featured as country based co-financing, the GEF guidelines for evaluations were adhered to as well.

The evaluation scope included global, regional and country level assessment: design, strategies, theory of change (developed in 2015), implementation, results, lesson learned and sustainability based on a predetermined set of indicators (see results framework in EC-UNDP agreement and Annex). The report outline was agreed in an inception report, through which the evaluator confirmed understanding of the TOR. Evaluating BIOFIN included scrutiny of the original partnership agreement, including the Log Frame Results and Resources framework (Status of planned outputs and activities reported by management - Annex 2). The evaluator questioned if it was used as a monitoring tool. The evaluator reviewed the risk log and tested the assumptions.

The evaluation data was collected from primary and secondary sources and observation. Data was collected through desk studies (DS), Skype, focus groups and face-to-face interviews. Government counterparts and UNDP focal points were interviewed through Skype calls, survey questions (questions attached in annex) and face-to-face case field visits. The evaluator was provided with the ROM 2015 data, a comprehensive monitoring mission report on BIOFIN’s progress in the eight pilot countries. In addition, she was provided with full access to project reporting, including annual and quarterly reports and annual progress reports. These reports were scrutinized and compared, and insights compiled. The evaluator also conducted Skype calls to BIOFIN country and regional focal points and counterparts to fill in gaps in data and/or poor quality responses.

Headquarters, Field and Case Visits

An initial data gathering mission was undertaken to project implementation unit Istanbul November 31–December 3, 2016. The evaluator visited BIOFIN pilots on three continents (Asia, Europe, and Latin America) and held field level consultations with seven of eight BIOFIN EU national pilot teams. During this period, the evaluator visited UNDP offices: headquarters (Istanbul, New York), four regions and two countries, including the Philippines Jan–Feb 5, 2017, and Guatemala Jan 22–Jan 27, 2017 (during a regional workshop featuring 10 LAC countries). The regional visits and country work provided in-depth insight into the contribution of EU/UNDP support and a vetting of national level results. The evaluator participated at the Regional and Global Team meetings in Guatemala on Jan 26, 2017 and provided preliminary analysis and garnered feedback.

focus areas

The evaluation was forward oriented. The analysis delved into the question of sustainability of results: program performance, methodology, transformation of the entire biodiversity financing landscape and finance mobilization. It considered closely the objective of mainstreaming and reviewing the enabling legal and policy environment for biodiversity finance. It set out to document the strategic partnerships (whether BIOFIN was facilitating bridges between groups, people or sectors) and lessons learned (positive and negative).

Focus issues included the following:

BIOFIN Toolkit Methodology/Technical Analysis: As an innovative technical project, the evaluation study included rigorous focus on the methods as a framework for biodiversity finance for results. To test the rigor, i.e. methods for assessing and mainstreaming biodiversity financing needs and gaps for planning, a review of the 2016 BIOFIN Workbook was undertaken. The BIOFIN methodology included a review of the following BIOFIN methodology main steps:

- Policy and Institutional Review (Original)

- Biodiversity Expenditure Review (Original)

- Financial Needs Assessment (Original)

- Biodiversity Finance Plan (Original)

- Implementing Financing Solutions. (Added)

Addition scrutiny included these activities:

- BIOFIN Monitoring

- Strategies for Institutional Capacity Building and Sustainability

- Alignment with national priorities

- Partnerships/networking

- Cost effectiveness (not an econometrical study but an analysis of the resources available vs outputs/outcomes) and UNDP/EU role in cost effectiveness.

- Contribution to policy results.

Evaluation limitations

The original EU/UNDP documentation specified the implementation and testing of the methodology would only be extended to up to 13 countries subject to committed co-funding by other donors. This was not adhered to as the BIOFIN project grew from piloting in eight countries to thirty in the first two years. The resources for biodiversity finance (as a pilot) tripled and thus exceeded all resource mobilisation expectations. With that rapid growth, the original project concept deemed a redesign, but its absence led to complexity from a management and M&E perspective. To deal with the limitation, the evaluator focused the review on the expected output areas (2016 Workbook Five Steps - PIR, BER, FNA, FP and FS), progress towards their institutionalization and the overall transformation of the global financing for biodiversity landscape. During the Guatemala evaluation workshop, full-scale BIOFIN process indicators were being drafted by the global team to evaluate the national level expected results. These were vetted as the basis for monitoring results of implementation phase beyond the workbook development (outputs) towards outcome level changes (improvements in the Finance architecture of the countries).

# 1.3. Structure

This report is structured by seven chapters.

# 2. The project and its development context

# 2.1. Project start and its duration

The UNDP/EU support is to eight BIOFIN countries through its DCI-ENV financing instrument. The signed UNDP/EU agreement was for an initial 36 months, signed on Oct 25, 2012, with a contribution of 4 million Euro and co-sharing by UNDP/GEF US$ 2,418,317. On July 15, 2015, the project was granted a no cost extension until December 2016. Originally seven out of the ten countries would be funded: Ecuador, Kazakhstan, Malaysia, Mexico, the Philippines, Seychelles, South Africa, Thailand, Uganda and the Congo basin. This later changed as Mexico, Thailand and Congo were replaced with Argentina, then replaced by Chile in 2013.

# 2.2. Problem(s) the project seeks to address

The project goal (project documentation) is to address the global biodiversity financing gap, an issue recognized by the Conference of Parties on Biodiversity (EU/UNDP ProDoc, Annex 19) in 2010. This work has two main challenges. Firstly, a comprehensive assessment of the funding baseline was not carried out in countries. Secondly, credible, hard data on the amount of funding needed to address biodiversity loss, taking cost-effectiveness into account is not available. The lack of such information hinders countries’ biodiversity proponents from making a sound business case for expenditure on biodiversity conservation and its management. In order to meet the new targets set by the Convention on Biological Diversity (CBD) for 2011–2020, efforts to address the underlying challenges will need to be drastically scaled up. This means, inter alia, that a significant increase in finance will be essential. See Annex UNDP, Nik Sekhran’s introduction to the global BIOFIN concept.

# 2.3. Immediate and developmental objectives of the project

The project will contribute to reducing the global financing gap for the conservation and sustainable use of biological diversity by assisting developing countries in identifying, accessing, combining and sequencing sources of biodiversity funding to meet their specific needs. The specific objectives were to develop, test (in pilot countries) and disseminate: a). a framework for mainstreaming biodiversity into national and development and sectoral planning; b). a methodology for assessing a country’s biodiversity financing needs, a framework for national level biodiversity financing.

2.4. Stakeholders and implementing partners

The project concept had built on the needs expressed by countries through the Convention on Biological Diversity during 2010 to support the identification of funding requirements, gaps and priorities and the development of national financial plans (project agreement documents). All parties of the CBD are stakeholders in BIOFIN reports. In terms of implementation, an indicative list of countries proposed for participation in piloting the methodologies developed was proposed and seven partner countries were selected. The final list (mention in 2.1 above) was confirmed through a dialogue between the relevant Commission services and the UNDP’s Biodiversity Global Programme, based on a criterion.

The expectations for the country piloting, in addition to indigenous people and local communities, were to engage other key stakeholders, and target groups are technical staff and policy-makers in national ministries and subnational authorities responsible for (1) national development planning, sectoral planning and related budget allocations, and (2) the planning and implementation of biodiversity management measures. National CBD focal points, together with colleagues involved in the development of NBSAPs and the relevant focal points responsible for the formulation of Poverty Reduction Strategy Papers are also key stakeholders.

Representatives from globally and regionally relevant academic centres and think-tanks (e.g. in environmental economics) were involved in the formulation and testing of methodologies. Through implementation, the project has also engaged key intergovernmental and nongovernmental organizations, the private sector and representatives from international and regional organizations representing indigenous peoples’ rights, in both the formulation and implementation phases, to secure their input and their endorsement of the project’s objectives and outputs.

# 2.5. Results expected

The BIOFIN Project Framework, based on the UNDP/EU documentation, has four complementary expected outcome areas, 27 indicative activities: These are outlined in the partnership agreement LogFrame Annex. The LogFrame expected outputs and activities are listed below.

Component 0: Project Management and lead technical expertise in place and operational, and all project objectives and results disseminated and welcomed.

Component 1: Integrate biodiversity and ecosystem services in sectoral and development policy, planning and budgeting.

Component 2: Assess the financing and governance needs for the management and conservation of biodiversity and ecosystem services.

Component 3: Identify, combine and sequence different sources of funds to meet biodiversity-financing needs.

………………………………………………….

# 3. Findings and conclusions

# 3.1. Project formulation

# 3.1.1. Conceptualization/strategy/design

The project was formulated based on global policy developments in environmental economics (see implementation section) and discussions by partners at COP 10. The European Commission (EC) and UNDP (Principal Technical Advisor for Biodiversity, with support from Regional Practice Leaders and Technical Advisors) aimed to complete the proposal formulation phase during the (Northern) Summer of 2011, and for UNDP and project stakeholders (including the CBD Secretariat, UNEP, PEI, TEEB, the World Bank, GEF, OECD, IUCN, relevant national and regional UNDP offices and others) to conduct internal preparations and methodological discussions in parallel. The target date for signature of the project contract was December 2011. It was signed a year later. The early design discussions focused, according to respondents, on actions to help countries develop the methodologies for assessing the biodiversity finance gap and to pragmatically identify finance solutions. Particularly, the national teams assisted by the global team would implement a methodology consisting of three assessment workbooks, PIR/BER, FNA and FP, cantered around four key finance expected results to generate revenues, deliver better, realign expenditures and avoid future expenditures. The concept emphasizes greater efficiency utilizing existing resources and therefore less focus on outside assistance.

The project was launched to a receptive global environment. The financing for BIOFIN rapidly expanded, in fact tripled, during its first two years of implementation. The additional resources, initially funds from Germany, were then followed by resources from Switzerland, Norway and Flanders. The additional resources helped to expand pilot implementation to 30 countries. Although there was no redesign plan, UNDP dealt with the challenge by resorting to hiring further technical support to cover countries. Its quick actions in this regard were commendable (see implementation section).

According to the feedback, there was enormous global policy pressure to advance the project goals. The evaluator learned momentum was growing on biodiversity finance based on the Stern report 2006 (annex). BIOFIN’s value added was foreseen as a dedicated focus on financing, country level operationalization of concepts, working with Ministries of Finance on biodiversity budgeting and expenditures and the exploration of what this means for policy development and private sector management.

According to the project manager, “it was clear that more donors would support more countries.” The project team had been very successful, through CBD meetings and Steering Committee meetings, to bridge the demand from further countries to support BIOFIN. The implementation did not actually begin in first eight pilot countries until 2014 (interview with Steering Committee and project manager). The Steering Committee members jointly determined (see BIOFIN implementation chronology and synopsis of SCM minutes decisions) that a draft methodology to pilot/provide guidance for the countries first note of Mr. Nik Sekhran, BIOFIN basic concept).

The first version of the methodology (first draft BIOFIN Workbook launched in early 2014) was developed by the UNDP senior expert advisor and the BIOFIN project manager based in Bratislava with other global BIOFIN team members. The first draft workbook was viewed as robust enough to start. The project proceeded with piloting the methodology.

The design spoke directly to global demand mounting in the convention on biodiversity circles. Language of efficiency and language of the market were the main foci. UNDP Senior management reported it as a strategic activity as it connected with donors, based on country demands and linkages on biodiversity actions with NBSAPs and other related GEF, GCF and AF projects. The operationalization of BIOFIN thus started with four areas of focus - 1. Policy and Institutional Review, PIR 2. Biodiversity Expenditure Review BER; 3. Financial Needs Assessment FNA; 4. Finance Plan, FP. It was later extended based on learning to a fifth step, Finance Solutions/Resource Mobilization. “It is very relevant in CBD countries...” “…very logical, simple concept, never done and or scaled to this extent and very powerful.”

LogFrame/Strategies

The project suggested four expected results (see results in LogFrame Annex) including: 0: outcome, the project monitoring system and set up. The original concept of the methodology was expanded to include work on financing solutions. A design assumption was that the global and country strategies and results roadmap would be fleshed out by the project team in close consultations with the Steering Committee (interview with the first project manager).

The original LogFrame was global and broad, without specific targets or indicators for country level results. The LogFrame was used as a management tool for the global senior managers but indicators for national level results were found to be weakly presented. Respondents stated that the concept was a good visualizing point of the BIOFIN idea, but it had no operational backbone. Many respondents suggested that the project design thinking came very late after the signing of agreements and BIOFIN EU/UNDP project documents lacked vision in term of the project framework from evolution start to finish. It was also found, however, that implementation strategies were experimental and necessarily adapted to each country’s context. The EU led an eight-country ROM monitoring mission in 2015. This evaluative activity was regarded highly by all EU countries’ teams as it was reported to have provided important evidence for future country roadmaps (Chile, the Philippines, and South Africa). Chile reported the ROM report supported their future focused on the subnational and institutional aspects of their roadmap. They also became to see they needed more public and political level communications and subnational planning work.

# 3.1.2. Global/regional/country ownership/driven-ness

BIOFIN is driven by all its partners at global and national level (see statement above). Everybody interviewed felt attached to the new, exciting concept and the emerging results. Quantifying the values and financial needs for biodiversity is very timely. The year 2015 was a turning point in the global debate on environment and development of finance-enabling environment globally. In July, the third global conference on financing for development set a new agenda to move from “billions to trillions” in order to meet the needs of this new universal goal. In September, the formal adoption of the Sustainable Development Goals provided financing targets to achieve sustainable development. In December 2015, the signing of the Paris Climate Change Agreement delivered to governments a mandate to phase out growth policies that ignore environmental impacts. Biodiversity is an outlier, and knowledge of how to measure biodiversity expenditures was unknown. This project is operationalizing this work.

# 3.1.3. Beneficiaries/Stakeholders

Global Stakeholders

The global partners are member of the Global Steering Committee. These include UNDP, EU, Norway, Flanders, Germany and Switzerland. (Also see synergies and partnerships sections below.) Globally, BIOFIN supports the stakeholders and parties to the CBD processes.

National Stakeholders

BIOFIN beneficiaries and stakeholder at the country level (eight pilots) include a core group of national stakeholders from the UNDP, ministries of finance (treasury), economy, planning and environment, the private sector, civil society and donors.

# 3.1.4. Replication approach (see results, methods section)

Many lessons for BIOFIN countries fed into the development of a rigorous method. The BIOFIN Workbook has been peer reviewed internally and externally. The workbook was finally launched at the COP 13. December 2016. The final includes three basic assessments and a planning and solutions stage (most important according to participants). The concept is ready to be consolidated and packaged for scale-up/rollout. Scaling BIOFIN uniquely means guiding the learning to all other countries.

# 3.1.5. Linkages/synergies

A number of current initiatives are complementary to the EC-UNDP project, based on the EU UNDP agreement:

The World Bank’s Global Partnership for Wealth Accounting and the Valuation of Ecosystem Services (WAVES) aims to work with Ministries of Finance and economic planning agencies to measure and value ecosystem services and integrate these values into national accounting. In the medium and long term, tracking stocks and flows of environmental assets can contribute to the documentation of impacts from investments in biodiversity. BIOFIN has its own niche regarding both. WAVES is a complementary and supportive concept focused on strengthening national accounting systems for biodiversity and other natural resources. The BIOFIN idea, in contrast, works through the budget, not national systems of accounting. WAVES goes beyond and covers other sectors. For instance in the Philippines, WAVES is under the foreign assisted and special projects Services (FASPS), a staff bureau under the DENR. Biodiversity Management develops policy notes using the project results particularly on the WAVES’ mangrove, mineral and biodiversity accounts. However, the WAVES biodiversity account needs to be further developed. BIOFIN can explore these partnerships further for phase two.

The United Nations System of Environmental Economic Accounting (SEEA) is an international standard for including environmental elements in national statistical reports and especially in national accounts. The key area of work outside EU expected results is more concentration on UN standards for environmental economic accounts, now aligned with statistical accounts (UN statistical division). Discussions have been held with the UN Statistics Division (UNSD), which oversees SEEA to support the alignment of the BIOFIN approach with that of the international standards. A series of dialogues has taken place with UNSD to develop synergies. The new BIOFIN classification is fully compatible with SEEA categories. Eurostat is also active in the development ecosystem accounting. The global standard development process is something that is not a responsibility; BIOFIN feeds into it. It is an international process around the statistic commission and its workbook led that work.

The Economics of Ecosystems and Biodiversity (TEEB) initiative has worked to draw attention to the global economic benefits of biodiversity, to highlight the growing costs of biodiversity loss and ecosystem degradation and to draw together expertise from the fields of science, economics and policy to enable practical actions moving forward. TEEB works in many countries assessing, summarizing and deepening the understanding of how economic valuation studies can provide insight and guidance on biodiversity policy and planning. A link with TEEB is being made through several steps in the BIOFIN Methodology Process. From the beginning teams were given guidance to liaise with related initiatives, in particular TEEB. As TEEB does not usually have a project team in place, the coordination was often limited to when TEEB missions where undertaken. Under the 2016 version of the BIOFIN Workbook, there is a more explicit linkage with TEEB/Economic valuation studies in general. Under the Policy and Institutional Review, country teams are to review which economic valuation data are already available and document their findings. Then when formulating the finance plans, they use this data to help them write up the business case for biodiversity. The challenge that projects focusing on economic valuation studies have faced was that the economic data alone don’t bring change; they need to be part of a broader process. In this way BIOFIN aims to bring the economic valuation data into the ongoing policy dialogue. In summary, in the countries starting early, there was not much data on TEEB work on the analysis. For countries working on their PIR and Finance Plans, this linkage and orientation can also mutually benefit common outcome goals.

The CBD Secretariat’s work to promote the revision of National Biodiversity Strategy and Action Plans (NBSAPs) and to implement the Programme of Work on Protected Areas (PoWPA) is a critical complementary action to the EC-UNDP project. The intent was for the BIOFIN team to help countries with NBSAP country level implementation work. In addition, the project was designed to support CBD parties to implement their targets for resource mobilization after starting implementation, as this was a finance project and the linkage to the NBSAPs was limited and needed exploration. Several countries reported that identifying straightforward synergies was not so easy. The action plans were often standalone processes, not sufficiently embedded into existing planning and budgeting processes. In addition, recurring costs and activities, such as managing the protected area system, were often not considered, making it challenging to use the NBSAP as the basis of defining (biodiversity) finance needs. Many countries implemented NBSAP activities and stated that the link was critical. In countries like Chile, and to a degree in the Philippines, where an NBSAP was not in existence, it was an opportunity to develop the NBSAP as results-based. Respondents say BIOFIN is a great input for the next round of NBSAPs inclusion of a financing piece. Countries like Chile going through process, reported that BIOFIN methodology is of instrumental value linked to the CUD reporting and action plan. When the public expenditure is considered and budgets are allocated to policies, the NBSAP is a legal recognition with no budget. When results are determined and numbers are provided, a BIOFIN perspective for policy is possible. NBSAP usually has a costed action plan and NBSAP captures all of it. BIOFIN is making a business case into biodiversity conservation. It then asks what the focus of the gap is. The resources available and closing gaps make up the final piece of the puzzle.

The Green Climate Fund (GCF) is a new opportunity for work on biodiversity financing in countries. Most countries interviewed are designing for the GCF. In EU countries surveyed, this opportunity was not yet fully expanded upon by the teams. During the Regional workshop in Guatemala, the team received a presentation on how to access the GCF for Biodiversity financing. The lessons are leading towards programmes like GCF readiness for design and also forest conservation as a finance solution.

GIZ’s ValuES provide guidance and training on methods related to environmental economic analysis, combining country-level technical capacity development activities with a central knowledge management platform. It provides support particularly on the value of ecosystem services. BIOFIN does not allow time or resources to generate such analysis.

Programming on conservation finance by a large number of organizations, including UNDP-GEF, WWF, CI, WCS, TNC, often includes work on protected area finance and innovative finance solutions and is confirmed by participating countries to be closely consulted when developing the finance plan. CBD is active in global workshops and technical workshops, which were also represented by Bes-Net, NBSAP Forum, Equator Initiative and the Green Commodity Programme. UN PEI: BIOFIN drew strongly on PEI learning for the BIOFIN Workbook and work on three joint-programmes to link with Climate Policy and Expenditure Reviews (CPEIR).

# 3.2. Project Implementation

# 3.2.1. Project institutional and management arrangements

According to project documentation, BIOFIN would be implemented through the joint management and multi-donor modality whereby the European Union’s contribution was entrusted to UNDP through a Standard Contribution Agreement which established the overall frame of the Financial and Administrative Framework Agreement (FAFA). Originally, the project’s implementation was to be managed by UNDP’s Biodiversity and Ecosystems Programme, with its regional centres in Pretoria, Bratislava, Panama and Bangkok and its country offices in the eight pilot countries (ProDoc 2010, also see list of original countries above). The EC’s network of offices and delegations would provide additional support as appropriate.

A Global Steering Committee (GSC) was established as the oversight mechanism. The GSC committee includes representatives of the EC, UNDP’s Biodiversity and Ecosystems Programme, and Norway, Switzerland, Flanders and Germany. The team was expected to meet face-to-face at least twice a year in order to evaluate progress, exchange information and provide guidance and orientation on the overall priorities and management of the action. The SC actually meets (either in person or on Skype) on a needs basis and exceeded the requirement. The GSC has been an important venue for BIOFIN resources mobilization efforts (see financing section). Soon after implementation began, Germany, Switzerland, Norway and Flanders donated. In the absence of the additional financing, the enhanced expectation for the implementation phase finance solutions would not have been tapped. The European Commission actively supported BIOFIN through the Steering Committee meetings. The EU gained acceptance for and commissioned a mid-term evaluation entitled ROM mission in 2015, which was reported by countries as instrumental to support national strategies and provided good guidance to the global programme on course of action. Although the EU played a good oversight role in global BIOFIN, EU country teams might have been more engaged in supporting national implementation.

Global Project Team (CIU) The Global Team was finally established late 2013. The early staffing breakdown included: 1 senior, 1 project manager, one assistant—the original staff as projected in the project grant. This setup was modified during implementation. As no suitable candidate for a P-5 Global Team Leader could be identified, the functions were carried out by an existing UNDP P-4 and a Senior Technical Advisor (STA) who supported the development of the methodology; the Team Leader position was to be tendered again in late 2015/early 2016. The Senior Technical Adviser was supported by a Global Project Officer (GPO) hired in 2013. The job evolved to include substantial research duties, as well as duties related to organizing meetings and learning workshops, hiring consultants, coordinating country-level activities, producing reports and liaising within UNDP administrative, financial and monitoring and evaluation systems. The GPO and STA were supported by a full-time administrator based at UNDP New York. This administration role became instrumental to BIOFIN’s results as the person was very experienced and able to take on additional work as the programme grew. This position was augmented with a second project associate based with the team in Istanbul from July 2016. This is working out very well.

A Global Methodology Team (GMT) this evolved based on the implementation needs with a much stronger Steering Committee guiding and five expert TAs. The TAs and how they supported the programme were recognized as instrumental for the implementation approach and for the development of a global methodology that required a unique skill set. The decision was to hire the best TAs possible to support the countries and be part of the Global Core Team. The set of five TAs was eventually recruited (see chronology). TAs played a substantive role in improving the methodology, networking on the results and improving countries’ implementation based on the workbooks as they evolved.

National Steering Committees (NSCs) were established in each of the eight countries and were a requirement of the functioning. This core team was then engaged in a dynamic learning by doing process that gained important political capital/capacity and attention locally as it oversaw piloting and institutionalization of the methodologies. It was composed of UNDP and a focal point in the Ministry of Finance or Economy and or Environment/NR. NSCs were expected to be established and convened by the Project Coordinator in each country of the UNDP-managed “National Biodiversity Planning to Support the Implementation of the CBD 2011–2020 Strategic Plan” Project. [ii][1] This actually varied from country to country.

Each country team appointed a government counterpart to provide a stable contact point in the relevant national institution, mostly in the finance or development/planning ministry. It was confirmed that the focal points have been involved in the project through the NSC to ensure links with all relevant national policy processes.

Technical Assistance

In the original documentation, technical assistance to countries was planned, as an important vehicle for the methodology development and for generating lessons and to strengthen capacity. The global technical experts were to support country implementation, “smart strategy to support methodology and guide countries.” However, that said, with the implementation approaches learning by doing and decentralized country based strategies, there was no national monitoring for results system at onset to support countries with implementing the workbooks. During review TAs reported having a rudimentary terms of reference focused on helping them distil lesson learned and good practices. TAs reported that they could have done better with a clearer managerial role for results of their countries. A recommendation for phase two is to include strong ME in the function for the TAs linked to a global ME system for results.

The national ME work included a clearer focus post ROM mission. Countries reported the ROM recommendations helped them with recommendation that informed the national level theories of change. This process was supported by the global ME officer. The programme had become the basis for a clear ME framework for scale-up plans.

Global Team suggested that the BIOFIN approach can be improved with TA on applying Gender Mainstreaming in different contexts (e.g., policy review, research, gender budgeting, mainstreaming: gender in the project cycle management, etc.). A great example is included through case studies with useful examples from other countries. The 2016 BIOFIN Workbook for the first time includes a section on gender.

# 3.2.2. Implementation approach/adaptive management summarize

While aligning its approach to the broader global developments, BIOFIN continued growing in outreach and progressed on many levels. Since the first eight countries began to implement the BIOFIN methodology, Workbooks 1 and 2, a wealth of new practices and solutions have emerged and continue to emerge. The project was implemented through a dynamic learning and testing approach and a series of national, regional and global learning and technical workshops for implementation and encouraging engagement that had set a good precedent. The project rolled out in a varied, staggered manner. It had already scaled to over 22 countries, proving there was demand uptake.

The first global BIOFIN workshop was in February 2014 in Bratislava. The implementation actively began with the distribution of funds and technical support to the Philippines, Ecuador and, to a lesser extent, in Chile and Malaysia. Full implementation in the rest of the countries took off in 2015. The most delayed was South Africa, where the team needed to be recruited (this is working well now). In Malaysia activities were initiated by staff of the UNDP Country Office and the focal point, but their team was late in being recruited (as government initially intended to take up the entire work with existing resources).

The global project manager engaged new financing partners who wanted to invest and grow scale quickly; however, growth occurred even before the global team had a robust design for piloting. Early growth led to renewed expectations for the global results, and in the absence of a redesign, posed operational and monitoring issues. The project management’s engagement of a global technical team to work with pilots was commendable.

Global Implementation Approach

Implemented through DIM modality. The global team began project implementation in December 2012 (verified with the global PM). The implementation was initially led by a two-man team: one project coordinator and one biodiversity expert. It grew to a full team. The project and institutional arrangement grew as functions of the expected results and content strategy were embedded in its core work, the development and rollout of the BIOFIN methodology.

During implementation, management had to contend with geographical and content expansion. The concept attracted a lot of attention at the COPs 10, 11 and 12 in the first years. Two months after its conceptual launch, UNDP requested EU funds to start. The EU was active on the Steering Committee and requested monitoring support for national implementation. The startup had been a challenge for managing donor expectations as the BIOFIN team needed to be in place, and work on a draft methodology advanced. This was the priority. The pilot was thus developed and rolled out.

The UNDP procurement system was slow for on boarding new recruitments quickly. Other factors interrupted the process, including the UNDP management decision to move the Regional Centre (where the main BIOFIN team is based) from Bratislava to Istanbul. Recruitment was put on hold due to a 2013 UNDP global restructuring to a new strategic operational plan. Istanbul was challenging because applicants were reported as not wanting to live there. There was very little expertise available globally and nothing in the line of biodiversity finance. Rather than constrain it into positions, the management decision was to build the entire team on technical advisory jobs. The IC system has worked out well.

Countries started pilot implementation in a staggered way. Newer countries move more quickly (clearer with more defined methods - to be expected). Fastest countries now conclude the entire process this year, while some of the slower countries will take until December 2018. Respondents agreed that for the new phase, BIOFIN will be evolving to the real meat of the project, the “financing solutions,” and resource mobilization strategies are needed. The implementation scale-up phase to other countries will require a stable, dedicated, structured team and an including a strong ME plan nationally and globally. It will require take investment in new design and period to make phase two - fit for its new purpose, achieving financing solution wins, scaling up and deepening and- to deepen the learning to all CBD countries. This redesign-exit strategy work is reported happening and several options are tabled (see option for phase two annex). A much broader and ambitious learning agenda is being considered.

The management team is currently reviewing support needed for resource mobilization, including the political skills. They are currently planning a second BIOFIN committee in 2017, which is a technical committee for global oversight involving GEF, WCS, UNSD, Eurostat, WWF and the planning institute in India. EU TC provides a good link to UNDP programmes. This is endorsed by the evaluator. The programme manager was doing monitoring at the beginning and managing a remote highly technical senior team. Team skills were all senior level. Regarding growth, it is proportional to administration. Logistics indicates that if the program grows, BIOFIN will also need to grow exponentially.

# 3.2.3. Monitoring and evaluation

ME was scrutinized for its adherence against the original LogFrame matrix as a management tool, the work plan and the monitoring progress reports. The following other documents were shared and reviewed: a new project ME framework document with roles, procedures, indicators, the ME reporting template and the ME PowerPoint presentation for the Webinar series. Key indicators for performance and measuring progress were initially described in original ProDoc LogFrame. It has an action plan for implementation also provided in Section 6 of the original project agreement. The global Steering Committee was the main mechanism for overseeing performance level results. In 2015, the project hired an ME specialist to support teams. The EC representation has led ROM mid-term evaluation missions in 2015, a key intervention for roadmap corrections in many countries.

History of BIOFIN M&E

As an innovation pilot, BIOFIN was intended as a national and international learning process. BIOFIN was originally conceived a methodology, a product or deliverable to be considered by different   originally (pre ROM mission), reported primarily on activity implementation but successfully evolved into a complete process mirroring short, medium and longer term expected results (witnessed and reported by global and national project pilot delegations), including awareness raising, government ownership, policy making and financial solutions to biodiversity loss worldwide. The project team is supporting its move from reporting on activities to more on process of change and results-based reporting.

The project, therefore, did not have a strong TOC at onset. Developing programme-level ME frameworks for biodiversity finance programmes was a new practice area with limited global experience to draw on. It was perceived as an exciting opportunity to contribute to building the evidence and knowledge base and important financial baselines for biodiversity monitoring and measurement for the global community.

Finally, with its full team complement on board and work ongoing in all pilots by 2015, including five country roving TAs and a global M&E advisor, the global team began developing a theory of change TOC more systematically. Monitoring strategies at country level were intentionally stakeholder-led. The BIOFIN roadmap has to be carved out in every country. This is one of the lessons learned and a redeeming feature of the work.  As detailed above, it was an innovative pilot with a new practice area, Biodiversity Finance. The project monitoring was operating on a floating target for results (confirmed by respondents in the global team). However, as the team began to fine-tune the methods and undertake more systematic work on country level result in 2015, revelation of BIOFIN ME framework as a learning step for BIOFIN to improve its ME practice and systematic evidence generation from within the pilots (now 30). The team addressed the following M&E challenges, moving from concepts to a new BIOFIN M&E global practice in 2016:

- moved from activity-based to results-based reporting,

- rolled out a global-level ME framework across 30 countries,

- tested/implemented quantitative/qualitative reporting approaches at global and national levels,

- aggregated and synthesized highly contextually specific data,

- Captured knowledge through case studies.

These experiences have generated new insights into monitoring and results-based reporting for BIOFIN. In 2016, BIOFIN teams embraced the monitoring and reporting of changes occurring within the pilots. There were many key lessons emerging from BIOFIN’s experience that supported the translation of the original concept into practice. As a variety of interdisciplinary teams implemented BIOFIN in 30 countries with different entry points, reporting tools and tutorials needed to be standard and user-friendly. The strategy was originally centred on hard indicators around cost and expenditures, but the process of change began to highlight the need for new measurement indicators relating to BIOFIN progress, qualitative indicators contextualizing the changes related to results and enabling the results around the wider contextual and political realities that the national teams operated within. There was a risk of losing and obscuring critical learning about BIOFIN implementation if the success was measured using just metrics. Understanding the determinants of BIOFIN’s success could not be restricted to simple “yes” or “no” answers. A theory of change was thus timely developed in 2015 to support the translation of the BIOFIN M&E process from inputs to measurements for results. A theory of change is now available that helps countries monitor their inputs to turn them into outcomes. Teams are reporting this has been a significant exercise and the Philippines has even developed its own indicators and TOC.

BIOFIN Theory of Change

Finally, to support the M&E, during 2016 BIOFIN conducted two M&E webinars with 40 participants. Different regional calls included training materials on ME and one-on-one sessions and tutorials. The global and regional workshops covered M&E topics and had specific events, i.e. Technical workshop in Bogota (November) and the technical workshop in Sri Lanka (December). Each country counts with its detailed work plan and qualitative and quantitative indicators relating specifically to progress and results, which can be tracked by an internal monitoring system that focuses on results. With these actions BIOFIN global team have demonstrated a greater ME capacity by elaborating an ME framework with specific ME tools, roles and procedures; a new template for national level reporting and for global level reporting; a new annual work plan template with SMART indicators; and a ME dashboard that also served as management tool to visualize early warnings and progress. The impetus for the tool is to track BIOFIN’s progress and results to demonstrate change. The tool is interactive, allowing the user to aggregate or disaggregate data as needed.

# 3.2.4. Partners participation

Global Partners

The global BIOFIN partners are actively involved in implementation including those through the Steering Committee, including the EU, Norway, UNDP, German, Flanders and Switzerland. Resource mobilization activities are centred at the COP.

Private Sector

BIOFIN has two (2) tracks for its finance solutions: 1) national level; 2) private sector; a key aspect of the methodology was the need to engage and create enabling environment for private sector finance solutions. Philippines for example for example moved forward to create a market place and even developed criteria for evaluating marketplace proposals. BIOFIN is espousing a paradigm shift among proponents to create inclusive business models (see Philippines -Criteria for evaluating the marketplace proposals-Annex). Drivers for biodiversity business and finance solutions are beginning to emerge from the private sector. The Evaluator met with proponents for BIOFIN biodiversity finance solutions proponents in Guatemala and in Philippines. BIOFIN business proposals should be driven by the private sector. All countries expressed more work is needed around large financing solutions and enabling environment for private sector. I.e. Biodiversity Offsets.

NGOs and Communities

NGO participation was limited but beginning to be more prominent during the implementation of financing solutions phase. NGOs have been a source of information and involved in workshops at national and international level.

# 3.2.5. Finance 	(See All EU Country Delivery / Results Profiles Annex)

The status of project funding: total 29 Million. Originally in Dec 2012: 8.3 M, in 2013: 15.1 in 2014: 28.3 M in 2015: and final tally at 28.9 M. This is an incredible result -Actual finance mobilized for biodiversity finance globally. These figures the show project has delivered over and above.  For a small strategic project facilitated excellent work for mobilization resources and on co-financing. Many of the pilots were also co-financed with German funding. The national funding was reported as catalytic and enabling for results i.e., funding for EU pilots was augmented from a number of donors; see financing profiles in Annex.

Three levels of the BIOFIN budget include: 530,000, 750,000 and 1,000,000.

Rate of Delivery

The project has delivered at 99% and the EU country pilots delivered at 99%

The finance considerations include the cost effectiveness, rate of delivery, resource mobilization and financial prudence.

Cost effectiveness: Value for Money /cost effective ness of BIOFIN is high: this small project has achieving a lot in terms of its approach and cross-country learning.

Learning KM approach.  DIM modality was reported enabling for transaction cost to results ratio- to be low.  The outsourcing of TA was an effective and good business model for UNDP. The teams were provided with a generous amount of TA support compared to similar global projects.

Co-Financing: The evaluator learned that no actual co-financing was required to receive a BIOFIN grant.

The idea was to make synergies with GEF, and in some cases this is happening. UNDP project officers were to leverage financing for BIOFIN. This includes making GEF project and also other strategic project linkages. This is occurring also at the sub-national level downstream GEF projects. Several countries reported concrete linkages to other GEF projects for undertaking or leveraging co-financing, e.g. Malaysia, Chile, and Ecuador.

Resource mobilization for implementing financing solutions

Resource mobilization was not nurtured in design and resource mobilization targets were centred on global partners; however, the project is showing good results working with other project and with the private sector in several countries.  For GEF/GCF financing, UNDP project officers are linking work at the national and subnational level. Several counties are making linkages on other GEF/GCF projects for undertaking or leveraging co-financing for subnational work, e.g. Malaysia.   Interesting work with the private sector is however beginning to emerge. The lesson, however for BIOFIN policy, is how the government approaches and provide incentives for private sector engagement in biodiversity business. The tendering of innovative solutions and ideas to engage the PS is beginning for example - through the chamber of commerce was an important learning noted by Guatemala and other BIOFIN countries approaching this problem.

EU contribution and Co-Financing funds as agreed with the donor.

| Summary | Euro |
| --- | --- |
| Total EU | € 4,000,000.00 |
| Total Co-Fin | € 2,418,317.00 |
| Total Action | € 6,418,317.00 |

Summary Financial Information

| Donor | Total Funds in USD | Contract Signature Year |
| --- | --- | --- |
| European Union | $ 4,968,147 * | 2012 |
| Government of Switzerland | $ 318,135 | 2012 |
| Government of Germany | $ 22,172,065 | 2012, 2013, 2014 |
| Government of Norway | $ 701,899 | 2014 |
| Government of Flanders | $ 129,068 | 2014 |
| Government of Switzerland | $ 605,449 | 2015 |
| Total | $ 28,894,763 |  |

Geographical coverage (all donors):

Table for the EU expenses and budget plan/expected expenditures until the end of Dec. 2016

| Budget Category | Total Action Revised Budget/Addendum no.1 (Euro) | Total Action Expenses as of 31 December 2015 (Euro) | Planned 2016 |  |
| --- | --- | --- | --- | --- |
| Central Technical Unit (including evaluation) | € 1,210,342.00 | € 749,602.67 | € 460,739.33 |  |
| Travel | € 416,306.50 | € 136,136.83 | € 280,169.67 |  |
| Equipment and supplies | € 20,072.00 | € 3,951.39 | € 16,120.61 |  |
| Office expenses | € 30,108.00 | € 11,308.46 | € 18,799.54 |  |
| Global Workshop and seminars | € 301,929.00 | € 210,937.60 | € 90,991.40 |  |
| Publications, Lessons learnt (including visibility) | € 135,727.00 | € 40,308.41 | € 95,418.59 |  |
| International Consultants (Including Audit) | € 27,097.00 | € - | € 27,097.00 |  |
| National level activities* | € 3,996,735.50 | € 3,123,096.20 | € 873,639.30 |  |
| Total direct costs of the Action | € 6,138,317.00 | € 4,275,341.56 | € 1,862,975.44 |  |
| Indirect costs (4.562% of the direct costs) | € 280,000.00 | € 194,912.05 | € 85,087.96 |  |
| Total project eligible costs | € 6,418,317.00 | € 4,470,253.61 | € 1,948,063.39 |  |

# 3.2.6. UNDP role and comparative advantage

UNDP is appropriately placed to collaborate first most because of its competencies and its large biodiversity programme, with over 400 global biodiversity initiatives working on aspects of biodiversity finance (such as Protected Area financing through its work programme on Environment and Energy). UNDP provides the institutional breadth and depth to work on methodology development and testing at both the multi-regional/global level and the national level. Modality is good for expanding UNDP business model/technical support. Cost recovery mechanism or growth comes with donor confidence through expanding donors in the BIOFIN pool in key areas of its/UNDP’s core technical competence.

Operational

UNDP is uniquely positioned in country as a key implementing agency to support governments with for decisions made under the CBD and other biodiversity-related MEAs. UNDP enjoys a close trusted relationship with a range of government departments in developing countries and a fundamental role in supporting national planning processes. UNDP is operational, and involved in the revision of NBSAPs through providing access to GEF country funding for biodiversity enabling activities. World Bank and UNEP would have the capacity but do not the national officer network that UNDP has. WAVES could have integrated the whole of BIOFIN but is not working on biodiversity. Why doesn’t UNDP work together with these agencies? WB/UNDP could raise financing together and improve on the biodiversity specific national accounting domain. UNDP has a regional advantage: the network helps get access to technical support and platforms for South-South cooperation. UNDP can mobilize momentum with biodiversity national accounting standards and economic with UN statistics.

Resource mobilization

UNDP engaged with all pilot countries and global partners by raising financing for BIOFIN. BIOFIN through work on financing solutions and implementation can concentrate efforts to position for more resources for BIOFIN at all levels - country, regional and global level. UNDP is positioned to foster resources. Alignment to SDGs and sub-national work are key areas to promote for resource mobilization...

Synergies and alignments

BIOFIN goals are complicated with the vertical funding implementation that it is siloed. A strategic advantage is that the BIOFIN process is outcome oriented with key stakeholders for change. Three countries have reported on fully integrated PIR financial reviews: Bhutan, Indonesia and Kyrgyzstan. A Bhutan pilot supported the full integration of PER approaches with CPEIR, a joint institutional and policy analysis.  Integrated planning and support with alignment especially around SDG planning is a key BIOFIN support asset. South Africa recorded this linkage as did 6 other EU/UNDP pilot countries interviewed. UNDP’s comparative ability to design/operationalize/ approach/monitor the link between BIOFIN upstream and downstream -  policy and programming systems of the government, of its ability to link the short-term to the long-term and the national to the subnational and community. BIOFIN is doing this in Philippines and Chile through sub- national BIOFIN implementation - see country results profiles Annex.    UNDP supports government with SDGs and national development plans. BIOFIN work supports an important linkage to localizing SDGs. BIOFIN’s comprehensive finance and planning approach is well suited the UNDP’s broader work on SDGs planning. There are clear synergies for BIOFIN finance oriented support work on the biodiversity SDGs targets and for improvements in SDG implementation and planning work.

# 4. Results

Regarding BIOFINs contribution to overall attainment of outcomes/objectives, this project has excelled in delivering its objectives and stated results. The BIOFIN methodology is ready to be scaled to other countries. The new BIOFIN workbook highlights a transformative process, including a focus on policy, learning processes and engagement with the Private Sector (See Status of implementation of workbooks in all EU counties in Annexes). The Official launch of the 2016 BIOFIN Workbook and the Regional Nodes at the COP 13 in Mexico during the Global BIOFIN team side events on 5th of December. BIOFIN was mentioned by CBD parties 22 times in CBD 2016 plenary signifying the general interest and excitement around the approach. (Annex).

Conceptual Development and Approach

BIOFIN functions by bringing together a core group of national stakeholders from the Ministries of Finance (treasury), Economy, Planning and Environment, NGOs and the private sector, civil society and donors. This is an important outcome in itself, as coordination mechanisms for this level of engagement are not always functional or present in many countries. Such mechanisms are also the subject of institutionalization and of further enabling activities, i.e. policy incentives and enabling environment for public private sector engagement (also discussed in results section on capacity development and in the sustainability section). Stress is really needed on the enabling environment for the private sector. This group is essential to engage closely on biodiversity financing issues and is needed to initiate the most effective finance solutions for biodiversity.

In the short term, the expected outcomes of the BIOFIN process and methodology at the national level include the following:

- Create an effective dialogue among multiple ministries and actors in the biodiversity finance space that improves communication and efficiency in budget planning, resource mobilization and biodiversity management;

- Improve understanding of the current situation in the country with regard to economic and financial drivers of biodiversity loss, enabling targeted policy recommendations and the identification of entry points for mainstreaming biodiversity into national development plans and budgets and private sector engagement;

- Determine a baseline level of biodiversity expenditures for the country as a whole, thus enabling both future projections and ultimately tracking biodiversity in budgets;

- Identify specific financial needs for successful implementation of national biodiversity strategies and plans and assess financing gaps;

- Develop, pilot and implement a suite of finance solutions.

# 4.1. Method

# Five Principle Steps

To assess the transformation effect of BIOFIN on the global and national biodiversity financing policy and mainstreaming landscape, the evaluator considered the BIOFIN Workbook’s status and influence on national level changes.

Step 1 - Biodiversity Finance Policy and Institutional Review (PIR).

The first stage of the BIOFIN process is embodied by its Workbook 1, “Biodiversity Finance Policy and Institutional Review” (PIR). This step is built around an analysis of major national biodiversity goals and trends, including TEEB and WAVES data (where available), builds on the NBSAPs’ actions plans, undertakes a detailed assessment of sectoral impacts, dependencies, risks and opportunities regarding biodiversity, a comprehensive stakeholder analysis, a rapid assessment of major governmental subsidies that could impact biodiversity (not included in Workbook 1), a legal and regulatory analysis of the main issues identified and the development of a series of recommendations to reduce the barriers to successful biodiversity finance and management in the country. The importance of pilot results, ownership and drivers of change (Ministry of Finance, Planning and Environment/Natural Resource Management and engagement of the private sector) was found to be a key aspect of the project learning. This point was reiterated over and over by pilot countries’ respondents (The Philippines, Chile, Uganda, Seychelles, South Africa and Kazakhstan).

The policy review process guides countries towards an in-depth analysis into the barriers and bottlenecks in the institutional framework for finance solutions, the national budgeting process and biodiversity-relevant subsidies. Based on this step, a clearer framework for stakeholder analysis and who to engage with was presented for implementation. This first step was central to the expected results and project sustainability. This step is emphasized as a critical first step to achieve the transformative change. Its value added is that it enables the project teams to identify leadership for capacity building and policy agenda challenges with clear focus on imparting new finance method and skills for biodiversity expenditure review.

Step 2 - Biodiversity Expenditure Review (BER)

In general, not a lot was known about how much money was being spent on biodiversity actions. Countries assumed very low current biodiversity expenditures. The Biodiversity Expenditure Review BER, is the second workbook assessment process that analyses past biodiversity expenditures dating back to 2006, where possible, to better understand absolute and relative biodiversity allocations and spending based on projects and organizations, sources of revenues and biodiversity harmful subsidies. Expenditure reviews provide insight into how policy priorities were or were not reflected in actual expenditures and opportunities for improved allocation. In this workbook, a comparison among organizations and sectors is complemented with an analysis of the financing levels relative to each sector’s contribution to GDP, jobs and other sustainable development goals. Future expenditures are predicted under different scenarios to establish the “business as usual” financing case that will be measured against the financial needs assessment to determine financing gaps for each biodiversity (NBSAP) strategy, organization and CBD targets.

Improved guidance in version two of the BER includes the following:

- Definition of “biodiversity expenditure” to increase among country comparisons and consistency over time and guidance on boundaries,

- Detailed guidance and examples of how to attribute expenditures to biodiversity for “indirect” expenditures, including sector by sector guidance,

- Tagging systems for a range of analyses,

- Guidance on engaging with the private sector,

- Approaches to avoid double counting, among others.

BIOFIN Data and Monitoring Tool

This project is responding to a rise in demand for data, globally and nationally, in order to make good decisions and planning. Countries interviewed reported that they did not have good, solid data as existing local biodiversity finance data is limited. This is the essence of the BIOFIN Workbook assessment work. Data is sensitive, however, and the project had negotiated a data sovereignty rule to assure countries of their ownership of their data being extrapolated. Country-level quality data for monitoring global targets is only shared when the data is validated by the pilot countries. Countries advise on what they agree to share. The BIOFIN bottom-up data is a clear value added. In this sense, the project has improved the quality of reporting to the global resource mobilization targets of the CBD (better quality data for reporting) already - an indirect result. As for good practices, Peru and Mexico are using GIS data to precisely calculate biomass, determining how to calculate financial needs of a country.

BIOFIN data collection was a meticulous process involving the weighting of attribution per programme. From beginning before data collection, clear parameters needed to be set, using standard definitions, precise language and biodiversity expenditures available. Although BIOFIN methodology uses the objective and targets of the CBD, countries are currently free to prioritize their own data collection/presentation objectives. Countries reported needing detailed guidance to apply definitions. For project-level results, methodology development, work on a global data collection and the reporting tool are reported to be ongoing (interviews and observation of data tools with global team members). However, achieving quality data for a BIOFIN global data set will take time because countries are at different levels in their finance and planning frameworks and capacities, i.e. abilities, knowledge and skills on how to calculate cost and expenditures and report nationally and internationally. Countries interviewed expressed they are at different stages with programme-based budgeting (Chile will not allow tagging, while Philippines is very advanced this way), also a key feature for work around setting national standards and generating local indicators for data collection. Eventually, there will be more cross-country data analysis. Countries expressed a need for global support for national monitoring and data collection systems. There is enormous potential to support countries with standard reporting support to the CBD financing targets. The entire exercise helps countries to get good data to report.

According to the country based respondents (See Annex, Project reports), having global indicators for data collection will be good. Uganda, Philippines, Kazakhstan and Chile reported a need for more support with a well-formatted data management system (data gathering/collection, storage and retrieval). A challenge reported by pilots is that governments are reluctant to formally publish reports. The BIOFIN team is currently negotiating for at least the biodiversity finance plan to be published. It encompasses key data from the assessments. Work on the data tool is a major area of work for BIOFIN for global results. It will require a special focus and resources to take it forward.

Excel-based Data Tool

An Excel-based data entry tool was prepared to facilitate data entry and analysis. It is still in its design stage (interview with global team). The global team reportedly rolled out a technical PPT to support countries. It was a first go at the substantive data work. BIOFIN has engaged an Excel specialist to develop a series of data tools to facilitate data entry and analysis for the data-heavy parts of the BIOFIN methodology (noted above). The draft version of the FNA tool is being tested in South Africa and Mexico. It has been delivered in the Philippines and Kazakhstan (See full implementation status in Annex). Once initial tests are completed, the tool is to be distributed. An additional Word/Excel document with a series of suggested tables that complement the revised workbook is available and will later be integrated with the Excel tools to form an Excel toolkit that complements the written workbook. For budget spending graphs, not only biodiversity expenditure figures, but also information on the current allocation of financial resources to show where and how much is spent already are currently available. This is a “deliver better” lesson. An innovation in the BIOFIN tool design was the better detection of the biodiversity asset double counting issue. Inflated figures are not helpful for end results. It was necessary to go deeper. The built-in system provides a methodology lesson, but the tool must be used from the very beginning.

It is expected that the teams will eventually automate PIR and BER information linked to a global set of standards. Every country has different standards. With incompatible data, it is necessary to fix attribution as double counting occurs.

Step 3 - Financial Needs Assessment (FNA) This step is the actual detailed bottom-up costing of the NBSAP and other key biodiversity strategies. The assessment is built on the NBSAP, and where the NBSAP is not comprehensive or inclusive of issues around sustainable use, such as sustainable fisheries, forestry and agriculture, it includes those strategic plans as well. A key step in the BIOFIN methodology is refining the NBSAP activities so that they provide enough detail and quantitative results-based indicators to be easily budgeted. Then an activity or results-based budgeting process is launched with significant consultation with experts and stakeholders. BIOFIN encourages countries to identify specific results that they seek to achieve with the Financial Needs Assessment as this provides the indicators that Ministries of Finance often seek to assist them in allocating resources. Once the details are established through government standard budgeting and, where needed, with detailed financial models, the results are summarized by goal, by strategies and by organization. A financial gap or surplus is determined through comparison with the future expenditure scenarios calculated in the Biodiversity Expenditure Review. The actual data collected and analysed is, in general, is showing results that countries are reporting efficiencies and gains through their newfound understanding of the current flow of resources to the sector (The Philippines, Chile, South Africa, Seychelles, Uganda and Kazakhstan).

Step 4 - Biodiversity Finance Plan (BFP). The final assessment (three) embodied by the workbook process is the Biodiversity Finance Plan (BFP), which provides a strategic and practical plan for transforming the way biodiversity is financed. The plan summarizes the previous BIOFIN assessments, highlighting increased and more effective use of finance and economic tools in biodiversity management. The approach includes combining 2015 (see BIOFIN Progress Report 9) a review of all currently used biodiversity finance solutions and potential solutions. These are also elaborated by the evolving Biodiversity Finance Solutions Catalogue (see below) to give advice on the best options for potential solutions. This list is then subjected to two screening tools to prioritize the solutions to arrive at a list of 5–15 solutions, the subject of detailed feasibility analyses to determine how they can be initiated, scaled or improved. The plan will cover some of the most important solutions, such as increasing the level and visibility of biodiversity financing in the national budget and reforming harmful subsidies. The BFP contains a completed action plan for implementing a range of solutions and initial guidance on others that would require significant funding for the design stage. The technical PPT for the Finance Plan is prepared, reviewed and updated. The 2nd Regional Workshop for the African countries (October) had dedicated sessions on subsidies and revenues, which have become more central elements of the BIOFIN methodology.

Step 5 - Biodiversity Finance Solutions (BFS) - Resource Mobilization Strategies

During implementation, the fourth step of the BIOFIN workbook process, implementing finance solutions became a very important part of the process of change so as to the reap benefits of the BIOFIN assessments and planning processes. It is the final step after all three above assessments. It is the step that enables the public to reap the fruits—the results—in closing the financial gap. During implementation, it became clear that countries wanted to go further and develop a financing plan and complement by a resources mobilization strategy. The team responded with support and development of a global catalogue. Global team also supported 10 countries in their identification of financing solutions and towards their implementation. In the Philippines, for example, ten solutions were short-listed, with four determined as relevant to the Philippines context. These four will be supported for implementation. This final stage is now instrumental to results, a showcase for the important private public work and incentivizing the business demand for biodiversity startups. Demand for biodiversity finance solutions is to be supported by a global collection of vetted good practices (UNDP).

Going full circle is about the change in mindset. For instance, work with the private sector is important to incentive them as the new drivers for biodiversity solutions and startups. It is very important to invest in the demonstration of public and private sector partnerships of the finance solutions, an integral part of the methodology, before this project can be proven fully effective. The Philippines is leading on this work and can be a global model but needs support. In addition, as a mega-diverse country, the Philippines is a natural leader also on the issue of financing from royalties from access to benefit sharing. That country is ready to be supported as a global leader on the legalities of ABS as a global BIOFIN demonstration.

Countries reported the importance of having BIOFIN champions and making deep relationships, which are key to help with political capital, to scale up the learning and to pilot BIOFIN at sub-national level. A few good examples of this include the BIOFIN counterpart in Romania when BIOFIN was developed (EU), who is now head of the CBD secretariat. In the Philippines, the local governor is a BIOFIN champion and pushing for financing of a subnational pilot.

BIOFIN Data Tool

A great deal of time, effort and money has been put into spreadsheet support for the BIOFIN workbook in both its 2014 and 2016 versions.  To date this is reported as not yet yielding positive results, potentially for a variety of reasons including the uniqueness of country accounting systems and the lack of BIOFIN’s ability to clearly articulate why a country would want to go to the effort of completing (enter inputs to) the sheets (the outputs and outcomes) and that the tool is not completed, nor is the guidance, nor is it integrated into the workbook such that people can follow the workbook and spreadsheets simultaneously.  The Evaluator perceives this work as central to the globally expected support outcome and for monitoring global biodiversity finance baselines as per CBD goals.  Much more work can be advanced to support countries with data and information management. This important work need to be further defined during 2017 -18 and well considered in the exit strategy for phase two of this project.

Aggregating and synthesizing data while retaining context specificity requires time, resources and thorough synthesis methodologies.  Countries reported that the data indicator and collection is the basic work - how to collect and analyse and apply the results for decision making.  The ME national work needs to be clear on what indicators and systems exist to support this work.

For ME to be useful, meaningful and burden-free, it must present a future global standard and long term data collection and reporting goals. The ME system and dashboard are in place, and the team is developing an exit strategy including with a ME plan for phase two work: scale-up and deepening results in pilot countries. The global framework and standard for ME will ultimately affect the comparability of data sets arising from countries.

A smart monitoring framework for BIOFIN is needed at two levels- global and national, the technical advisors’ work was not to monitor or oversee the countries’ work but to support shape contextual roadmaps. The M&E system is in place and TAs had requested more accountability for monitoring to oversee the country-level results which, in hindsight, this might have been strengthened in the past year with an accountability for results framework. Consensus of all respondents is the project TAs needed clearer performance targets linked to country-level institutional development /policy change expected results.

As a global partnership, the EU country and regional network for disseminating advance on the BIOFIN could have been tapped more extensively for national level monitoring for results.  A suggestion for future is a joint ME programme level monitoring system for steering committee members to play more explicit role in country level results oversight.

# 4.2. Knowledge Management and Global BIOFIN Learning

A major principle was that the BIOFIN learning and approach would be eventually accessible to all CBD countries. The assumption underscoring BIOFIN was to test methodology that would eventually inform a practice on biodiversity finance and that the project learning would be scaled to other countries. The aim was to implement this through a global learning approach. In this regard, the evaluator finds many floating parts of a global KM and learning strategy that still need to be consolidated and systematic.

The M&E officer is currently responsible for KM. Among the advisors’ delegated tasks was developing case studies and overseeing development of a webinar series (see Annex). Knowledge management, however, is the basis of building a strong community practice. It is a factor of the broader learning and scaling impact and sustainability, and it is vital to have explicit and tacit BIOFIN knowledge for sharing innovations and learning from best practices. "Institutional memory" is also important to create synergies among current and future country teams and shorten the learning curve, and in general to develop a global community of practice. The team has begun to design a BIOFIN global KM platform, which will share BIOFIN case studies, guidelines, publications, info graphs, videos and more. For example, in 2016 BIOFIN produced a series of KM tools to identify and transfer lessons learned from the experience (Annex). A series of country case studies is now available for other counties to learn from.

Aspects of the global BIOFIN Knowledge Sharing and Learning Network

Global BIOFIN Community of Practice

Observations, based on respondents’ views, underscore the importance of a BIOFIN KM Learning strategy: Significant global capacity development is needed to achieve the outcome level, mind-set change about biodiversity as a productive asset and to advocate the change needed in the policy environment for this shift. The BIOFIN learning module is connected to the broader UNDP’s sustainable finance development platform. That project is compiling a catalogue of finance solutions. The Biodiversity finance theme has been added to BES-Net. The Global Biodiversity Solutions section and a webinar series (three on biodiversity finance solutions, four on the methodology) exists and has been disseminated. A huge resource database is also available for sharing publications, and the team is creating a library of financing solutions. Learning and sharing of good practices was perceived by all countries interviewed as an important aspect of BIOFIN sustainability.

Catalogue of Financing Solutions

An important development was responding to the need to identify financing solutions. Currently, the global team is providing a comprehensive list of finance solutions. The catalogue contains the solution name, the main expected results of the solution implementation, a brief description and list of different sectors for which the solution may be relevant. The development of the catalogue is associated with a larger UNDP program on Financing Solutions for Sustainable Development that is described on the website: http://www.undp.org/content/sdfinance/en/home.html. This area of work is significant as a global service and needs to be developed and further vetted. The evaluator recognizes this collection as a flagship knowledge service for the growing BIOFIN community of practice.

Regional Nodes

The strategy (see Annex 2) has begun to engaging a concept of scale-up learning to more countries through the knowledge nodes (funded by Flanders). More nodes are expected to be financed before end of year. Three CBD-BIOFIN Regional Nodes advisors are being hired. The idea is to enable all CBD parties to gain access to support to understand and apply the BIOFIN methodology. The first one, Regional Node for African and Central Asia countries is on board.

A coherent KM strategy that brings all this above together would bring all the above together. This area of work is the basis for scale-up and could benefit from external KM expertise input as part of the exit strategy. The learning plan for countries will also need to be flushed out more coherently for a phase two ME strategy.

# 4.3. South-South Cooperation and Learning

At the regional and global level, the BIOFIN community is enabling the participating countries to exchange experiences through South-South cooperation mechanisms: regional and global workshops, the BIOFIN website and dedicated webinars. BIOFIN collates learning materials on its website, www.biodiversityfinance.net, which is constantly updated and expanded with new knowledge management materials and BIOFIN Workbook updates, presentation materials, new stories, case studies and data management tools. BIOFIN participates actively in other web platforms, including the NBSAP forum (www.nbsapforum.net) and BES-Net, http://besnet.world/biodiversity-finance, which has co-developed a resource library on biodiversity finance with BIOFIN.

# 4.4. Institutional Capacity Strengthening

Although Institutional Capacity Strengthening was not written about explicitly in the original project agreement and documents, it is an inherent aspect of the EU/UNDP pilot approach that a pilot would also involve activities and an approach that would impart some level of capacity. As part of the pilot, the team was also working on an ME framework that includes capacity development indicators at the global level and the national level. The evaluator reviewed the proposed ME framework and an explicit BIOFIN capacity development framework put forward at the Global team meeting in Guatemala, January 26, 2017. Institutionalization is thus perceived to have three parts: 1. Normative includes polices supporting (new laws, public budget, improving aid effectiveness). It also covers institutional change and improved policy implementation. 2. Organizational framework deals with hiring. Hiring or re-engineering of personnel, developing new TORs or functions to finances. It is a constituent of BIOFIN’s steering committee and creates units and departments. 3. Dynamics/effectiveness is the culture (politics, personality and values). This is used for capacity values. Capacity building, ME and replication and organization of the BIOFIN method at the subnational sectoral level helps by improving the financial architecture of a country. There is gender inclusion in BIOFIN literacy.

Implementation Approach

The national BIOFIN implementation approach varied based on each unique context. In general, the approach has been learning by doing.

The process was thus: the global technical team visited countries to discuss and design a country level action plan that was signed and agreed upon by global level before it was accepted. The country would then do a yearly action plan and file quarterly monitoring reports. These monitoring report text was designed by an ME officer in 2015 and updated with outcome and output level indicators (see ME section).

The work was generally conducted through a local project board or steering committee and a permanent technical team. A member of the Ministry of Finance and Ministries of Environment and/or Planning were normally a core part of the national team’s mechanisms, including steering committee and technical working groups. The permanent secretary (or equivalent) of Environment and the Finance Minister chaired the board/steering committees became the drivers of BIOFIN processes. How the local teams engaged these important stakeholders around the learning by doing process was reported as a central to the results- see description of the methods below. Teams were engaged in global technical and learning workshops - consistently reported to have successfully included delegations including from finance, planning and environment who engaged in the developing BIOFIN process. Development of national-level capacity building strategies quantitative and strategic work with MOF and/or MOE or their subnational governments. These committees were important for gaining national ownership. Project boards were normally an evolution of NBSAP planners. BIOFIN utilized existing NBSAP boards and enhanced membership, including planning and finance ministers. The program strategy was reported as BIOFIN as a good conduit between ministers of finance and environmental work.

Inter-ministerial national delegations inclusion in the global and regional learning events was reported as critical to BIOFIN results. For example, pilot countries reported participating in two global, three South-South technical and three regional workshops since inception. All country teams, including delegations from local UNDP, MOE and MOF, reported full engagement in the global and regional meetings. The technical meetings were appreciated and found to be very useful for their interpretation of the methodologies in consultation with other BIOFIN countries. In terms of unique implementation approaches, some countries preferred structure i.e. full-scale project document while others preferred much lighter processes with a simple, more flexible but effective monitoring framework and a learning by doing approach. The outcome was a richer workbook filled with learning and more comprehensive guide.

Respondent countries stated that BIOFIN is a strategic upstream project. Its focus on policy change and budgeting (power) processes was central, however, the local UNDP office sometimes put administrative restrictions on use of petty cash, which was needed to facilitate of the day to day meetings. This was a policy and finance influencing project with mostly meetings, and so petty cash was important for teams to access. Otherwise they would need to put cash up front themselves.

To support future institutionalization, interviewees present a consensus that the project must consolidate and deepen the results on financing solutions in a few countries to demonstrate success full cycle. To enable planners to scale up and engage fully on BIOFIN, the need is to continue to implement the financing solutions.

In addition, before scaling up globally, countries agree more analysis on the current project results is needed to study the trends for example to help maximize South-South cooperation approach how countries might be better grouped for learning together, i.e. islands, middle income, etc.

# 4.5. Policy Level Results

Many countries have recorded significant advances and some roadmap strategies related to policy impacts and changes. These include the following: movement towards institutionalization of BIOFIN. The methodology is to be replicated or used in combination with other methods, e.g. CPEIR, SDGs. Implementation of the financing solutions is a main target for all countries.

National Level

In 2015, 11 additional countries signed up for BIOFIN; Belize, Bhutan, Brazil, Cuba, Georgia, Kyrgyzstan, Mongolia, Mozambique, Sri Lanka, Vietnam and Rwanda. 19 countries joining earlier are at an advanced level with their Public Institutional Review (PIR) and Biodiversity Expenditure review (PER) (Annex), and have advanced through the Finance Needs Assessments and Biodiversity Finance Plans. The following results and analysis of progress reported by TAs was vetted in conversations of countries focal and government counterparts with the evaluator. TAs reported during Global Workshop 2017 and vetted evaluation missions. Also see EU country status reports in Annex.

Kazakhstan is a lead country for BIOFIN and has reported to be through with workbooks and working on four finance solutions. The country has evolved policies into laws and engaged in many successful capacity building workshops. It has recorded strong collaboration with BIOFIN on other projects. Capacity building is reported a still being needed. Payment for Ecosystem Services PES is related to its component four, -which is also looking at subsidies and taxes. The target is the legal BIOFIN framework. Kazakhstan has record being very vocal in international negotiation and using him data and experience from BIOFIN to strengthen their arguments for global finance and support.

.

Uganda’s government is leading the BIOFIN process. The work has generally focused on outputs including finance plan and expenditure review for long-term sustainability. Uganda reported to need more work on cross sectoral integration with other ministries as a NEMA based project. The country expressed need to do more cross-sectoral work and to implement financing solutions. It is also recording a need for more support on development of a BIOFIN data management system. Uganda has an expanding population, water shortages, it is a LDC, and these are all entry points for BIOFIN work. The capacity and opportunities for BIOFIN success is there.

South Africa has strong buy-in, and BIOFIN is being implemented as cross-sectoral work. There is a good opportunity for expansion. The country had advanced on the finance solutions and private sector engagement and has the opportunity to link with SDGs and poverty reduction. A lot of complementary solutions were identified. Capacity is strong. South Africa has a model of a finance plan. The country can strengthen it by applying for a new grant. There is an opportunity in South Africa to work with curricula and universities and public sector training. There is a strong capacity for supporting finance national solutions for biodiversity unit using economic valuation. Normative work is needed going forward. The treasury and others do one-on-one engagement and one-on-one relationships and undertake trainings in the department. BER is an important piece of work.

Seychelles is currently focusing on its exit strategy. It has made links to sustainable development planning and finance and instituting a BIOFIN approach and work with the biodiversity programme coordination unit. They hope to integrate with NBSAP anchored in the MOE. The work can be linked to the green climate funding planning which is reported as becoming more and more complex to engage with - UNDP can help in this regard- integrated design thinking. A complete SD support architecture that combines finance loans and grants is needed. The country should justify the project proposal. This will help GCF design thinking all these funds. The creation of the BIOFIN unit was suggested by the NBSAP implementation unit, as an SD resource mobilization unit for biodiversity. As per its work on finance solutions, Seychelles work on biosecurity is based with the private sector. The need for fisheries management is a good potential for linking BIOFIN finance solutions work i.e. there is not enough revenue from fishing. The country can mobilize resources by asking the government in a personal proposal to support with co-financing and capacity development. Seychelles held a workshop on sustainable tourism in May 2016. The Ministry of Finance made it clear to all concerned that they could use up to half of the Corporate Social Responsibility (CSR) Tax to fund their biodiversity programmes by using an NGO to execute.

Malaysia reported included elements of PES and green bonds in their national development plan. They have linked BIOFIN work to their protected areas and interest in having an environmental fund. The UNDP office has recruited its team. Its strategy is to builds on what exists. The work is showing signs of traction.

Chile is doing subnational work and work on BIOFIN strategic communications for policy. The draft expenditure review indicates the proportion of biodiversity expenditures as a share of total government expenditures grew from 0.11 to 0.16% between 2010 and 2014, indicating an upward trend.

Ecuador has changed governments. BIOFIN is positioning the project into one unit, the ministry of water, the vehicle reported to keep it sustainable. The country has reported a need for an internal regulatory framework to apply to the target. Now they are connected to a regional strategy for sustainable water targets. BIOFIN can continue to help develop the target and give support. A second target to set up is an economic valuation unit, connecting it to a new environmental fund. The MOE is not the best group to target the position.

The BIOFIN studies in the Philippines revealed a significant finance gap. The country has yet to fully fund its NBSAP. Private public partnerships PPPs and biodiversity finance education and public awareness is planned for scale up. Sub-national level BIOFIN implementation and demonstration is ongoing with a local governor champion. The team is working on accessing earmarked funds and has recently hired a local legal consultant to look at policy instruments. The team is also working on matching livelihoods to market livelihoods. Departments are funding a cascading activity. The BIOFIN team is working on a variety of finance solutions, including a national fund from oil and gas revenues, local government funding and a marketplace to match biodiversity investors with projects, in order to help fill the gap. Policy papers on biodiversity tagging and, public-private partnerships have been developed. Research on PPP modalities was conducted. A policy paper on the use of the Malampaya Fund for biodiversity conservation was developed and BIOFIN is working with a congress member who formally submitted a draft bill for the new legislation.

# 5. Sustainability

Political

BIOFIN learning is at a crossroads. More analysis on the results arising from the countries is needed. In addition, Countries report (Chile, Philippines, Seychelles, South Africa) that communications and advocacy are instrumental for results. The project is lacking a good global communication specialist. Reports are they leave because the project headquarters is in Istanbul. Respondents suggest undertaking trend analysis on countries of similar levels of development. Countries’ support is necessary for financing solutions. More support is needed on the analytics, and financing solution.

Institutional

Although BIOFIN was not designed specifically for this, biodiversity finance core content, financing solutions is a critical area for capacity building support of BIOFIN institutional sustainability work.  Secondly, is the need to scale BIOFIN approach linked to NBSAPs as to propagate a results-based approach for the NBSAP action plan?

Resources/Finance Solutions

The work on biodiversity finance methodology focused on the policy landscape, expenditure and costing review, financing planning and now is implementing financing solutions. Helping countries with their financing plans and implementing finance solutions has proven a critical step for demonstrating the utility of the action. Mobilizing resources for gap requires going one further step and helping demonstrate innovative Financing solutions. In this regard, the project’s natural evolution is also its most important risk. Now BIOFIN need resource to scale and deepen. The work that must be done to complete the cycle of change to show complete BIOFIN transformation success.

BIOFIN Project Scale-up

EU provided a very catalytic, strategic grant and a highly visible investment. BIOFIN’s cost effectiveness is high: the relative small projects are achieving with a unique approach to finance and to cross-sector BIOFIN learning. It has been successful to attach financing in phase one. More partners can now support scale-up. In the short run, the project team is in the process of designing phase two exit strategy, to focus on deepening the learning in original countries and scaling to other countries. UNDP is willing to absorb more funding.

Environmental

If there is no sustainable biodiversity management ultimately, goals for sustainable development will fail.

# 6. Conclusions

In conclusion, the EU investment in the Biodiversity Finance Initiative – BIOFIN – can be seen as very successful at achieving its stated objectives. BIOFIN has grown from its initial goal of developing and piloting an innovative methodology for biodiversity finance in 8 countries to a global program with an expanded reach – 30 countries – a detailed methodology, and a focus on significantly improving how biodiversity is managed through financial and economic solutions.

Specifically, the following points have been supported by this evaluation.

Relevance

The high demand, scalability and ownership of governments are clear indicators of high relevance of BIOFIN.  The project concept is perceived by stakeholders to be highly relevant because its focus on efficiency, effectiveness, economic drivers, and budgeting in line with national development plans. This has been confirmed in discussion with Ministries of Finance and Planning in all eight BIOFIN pilot countries, Seychelles, the Philippines, Seychelles, South Africa, Uganda, Kazakhstan, Malaysia and Chile, during the evaluation.  Part of the BIOFIN process involves the alignment of the biodiversity agenda (often through the NBSAP) with national strategic development priorities. The effective alignment of these biodiversity issues with the national development agenda allows more effective financing of biodiversity and a more efficient national planning and budgeting process. At the global level, BIOFIN is very relevant in its support to the environment and international commitments.  Under the CBD framework, BIOFIN is directly contributing to Aichi targets 17 and 20. As proof, BIOFIN’s contributions to countries were mentioned by 22 parties during the CBD COP 13 plenary in Mexico 2016.

Effectiveness

The overall programme cost effectiveness and straightforward implementing modality (direct implementation) has been a determining factor in BIOFIN’s early results. In addition, the shift of the discourse and language of BIOFIN methods to that of finance, policy and business is found to have been instrumental (noted by government respondents in 75 percent of the country interviewed).  A very rich body of global experiences transpired through global and regional workshops, webinars, country calls and technical missions, knowledge and experience sharing events to inform, capture and distil a growing body of evidence and methodology on biodiversity finance.  This information has been captured in an essential update and upgrade of the first BIOFIN Workbook – initially prepared in 2012, updated in 2014 and revised version launched at the CBD COP in 2016. The EU ROM evaluation (2015) showed significant results and was useful guidance for programme refinement.

Evidence of BIOFIN’s effectiveness includes (i) its contribution towards the transformation of the global biodiversity financing landscape; (ii) development of a scalable methodology and; (iii) leveraging resources for biodiversity finance. The transformation of global biodiversity finance is evidenced by the number of participating CBD parties that integrate considerations on biological diversity and its associated ecosystem services into development plans, strategies and budgets; number of participating countries that have identified and reported funding needs, gaps and priorities; and those that have developed national financing plans. From the original target of 8 countries initially financed by the EU, these numbers are expected to increase to include all 30 countries of BIOFIN and further to include those who have benefitted from the regional nodes.

Factors for BIOFIN success included mobilizing resources for work on implementation, including financial planning and solutions. The early input of additional capital by partners to BIOFIN was an excellent global financing result. Notably it was also recorded a challenge for the management team responsible for roadmap design in the eight countries. The rapid growth questioned the early project setup (geographical expansion and expansion in terms of content). Consequently, the new resources from global partners were successfully employed to countries to help undertake additional work on financing solutions in EU countries which will help to demonstrate the cycle of change.

Efficiency

BIOFIN has been assessed as highly cost effective. With its focus on finance, most actions result in improved efficiency, effectiveness, and support additional resource mobilization.  As a small initial investment, BIOFIN was implemented with relatively modest financing in countries, outsourcing TAs and maintaining a very small team in Istanbul and New York. From its initial investment of $ 4,968,147 from the EU to work in 8 countries, the project now has a global budget of 29 million and is working in 30 countries. Early results in countries include significant policy changes and changes to budgeting and financial systems. National level implementation has been almost entirely through national teams with support from the global BIOFIN TA team. Technical workshops and regional workshops were recorded as cost effective, pilot country teams supported the methodology development and engaged in South-South learning and triangular cooperation.  The lessons learned through the BIOFIN process has been integrated into the 2016 BIOFIN Workbook and the BIOFIN Data Tool which can capture a wide range of data from countries and facilitate the data collection and analysis process. Another area where impact was evident is the way BIOFIN has improved the NBSAP planning process (e.g. Kazakhstan, Philippines, Seychelles) based on cost effectiveness and prioritization. In some cases, the same team was responsible for the NBSAP and BIOFIN implementation. Revised NBSAPs in many countries included additional data on taxes, subsidies and finance solutions, while better articulating the specific targets they aim to achieve.

It was effective to have established partnerships and synergies with related initiatives at the global and national level. More can now be done to support a phase two and broker partnerships for a package of services for greater momentum, i.e. private sector, TEEB, WAVES, and SEEA and build complementation for a full package offer of finance solutions. The work with the private sector is very interesting with great potential for high global impact.

Sustainability

Project sustainability is supported by the design and implementation of BIOFIN both on the national level and at the global level. On the national level, there are three areas that promote the long-term impact of BIOFIN efforts.  First, capacity is built in country by using national consultants provided with significant international technical support and south-south learning.  This includes areas such as expenditure reviews, biodiversity financing solutions, national and subnational budgeting processes, economic instruments, and more.  Secondly, many countries are exploring or developing budget tracking to follow spending patterns for biodiversity and improve spending outcomes.  This is especially the case where progress has been made on results based budgeting. Thirdly, several countries are exploring opportunities to institutionalize the BIOFIN process through establishment of a post or unit that continues the efforts of BIOFIN to identify and implement finance solutions in the country.  The finance solutions themselves are also designed to be sustainable finance mechanisms in most cases and have built in sustainability principles.  On the global level the refinement and expansion of the methodology allows for the BIOFIN learnings to be continued within target countries and expanded to other countries through the regional nodes and through increased knowledge and communication around the full range of biodiversity finance solutions.

Impact

The impact the BIOFIN project can be seen at the national level and at the global level.  At the national level, changes in key relationships have occurred providing an elevation to sustainable biodiversity management issues such as NBSAP implementation in the eyes of key decision makers – especially ministries of finance and planning. Even certain private sector actors and associations (e.g. CR banking association), are deepening their engagement in biodiversity issue.  In several cases, biodiversity finance solutions identified and promoted by BIOFIN have started to produce increased financing or improved management effectiveness.  As noted above, capacity is being built in all BIOFIN countries that will have lasting impact on biodiversity finance and management.  At the global level, BIOFIN is changing the dialogue around biodiversity finance through providing a detailed and effective approach to identify financing needs and expenditures – supporting the CBD process – both financial reporting framework and NBSAP development and implementation.  In the resource mobilization aspects of the CBD process, BIOFIN became one of the most visible initiatives, resulting in a formal and universally supported recommendation to continue and scale. p the initiative (see figure 1). negotiations, leading to a more harmonious discussion between developing and developed countries. As well, through the efforts of BIOFIN and partners, knowledge about and awareness of biodiversity finance solutions, tools and mechanisms is expanding through methodology documentation, case studies, global and regional workshops, and other communications. The critical role of the EU financing for the development and piloting the BIOFIN methodology in the 8 initial countries cannot be underestimated.

# 7. Key Lessons Learned

This section on key lessons learned contains insights derived from this evaluation and are presented here to inform the EU and UNDP on national implementation practices, design and methodology development and application, and management oversight. Immediate application of these key lessons would benefit the prospective BIOFIN Phase 2 and inform both UNDP and the EU on specific best practices in terms of piloting a new methodology at the global level.

National implementation

- Embedding BIOFIN in ministries of finance and planning, has been a key to success. In most of BIOFIN countries the initiative is hosted by the Ministry of Finance while the remaining countries are hosted either by the Ministry of Environment / Agriculture or the Planning Agency. The improved integration of finance and economics thinking into the biodiversity management process is a vital development and effective communication approach in all BIOFIN countries. Often enormous improvements in communication among the ministries of environment and finance occurs from simple collaboration around the BIOFIN process – this impact is difficult to measure but appears to have strong benefits in most BIOFIN countries. Thus, even for those countries whose host is the environment or agriculture department, the benefits of improved understanding of finance contribute to sustainability of BIOFIN and its transformative impact. The technical capacity being built among national partners appears to increase the likelihood of successful biodiversity financing. At the national level, this interaction is evident in the membership of the Project Steering Committees while BIOFIN regional and global processes influence country representation.

- To ensure relevance and country ownership of the process, a key lesson learned is investing sufficient time and resources during the scoping phase. The 2016 BIOFIN workbook has devoted an entire section towards this phase where UNDP presents the BIOFIN process, identifies opportunities for transforming the biodiversity finance framework, and ascertains political commitment and capacities for implementation.

- While BIOFIN is a standard methodology, its evolution varied according to each country’s context. Countries appreciated the flexibility in the national processes for creating a country-based road map and focusing on mainstreaming and local demand standards for data collection and rigor. The country focus of BIOFIN and the use of the methodology to improve biodiversity financing at the country level is a key success factor.

Design and methodology development

- One of the main design issues was the timeframe towards completing the workbooks. Some flexibility should have been afforded countries and the global team considering that this is a pilot project and that some lag time between application and incorporation of learning from the method is expected.

- At time of writing, a theory of change (TOC) is being completed by the global team although some countries have decided to formulate their own. While it would have structured the M&E framework, there was no serious drawback from not having a TOC at the start of the project. Some countries that required a PRODOC utilized materials provided by BIOFIN with little difficulty. Owing to the “pilot” nature of the project, the flexibility allowed by the donors contributed to the robust methodology development that would have otherwise been constrained by an early subscription to the rigidities of a TOC and M and E framework.

- Methodology development has benefitted greatly from UNDP parallel programs including climate, health, and governance. Likewise, the methodology has been quick to adapt to new frameworks such as the SDGs. Subsequent versions of the methodology provide a direct link to SDGs such as through tagging.

Management and oversight

- Global management structure of having pooled funds, one steering committee and one donor report greatly reduced transaction costs for the Project Team, which was able to focus more on implementation.

- Global DIM was recognized as superior for simpler implementation, cross-country and promotion of South-South learning. Learning, including on the administration for DIM support results, starts with basic formats and evolves. DIM helps UNDP project teams to leverage co-financing in human resources. In some countries project assistance was needed. Most are part time and they cost share with the country offices.

# 8. Recommendations

This terminal evaluation makes a number of recommendations that could be addressed immediately by the global team, the EU and UNDP senior management, in conjunction with global and national stakeholders and other development partners and which if implemented are expected to enhance the scale up and impact potential of BIOFIN.

EU (and other BIOFIN Donors)

- Recommendation Priority 1. Implement Biodiversity Finance Plans. BIOFIN should deepen its support for Biodiversity Finance Plan implementation in select core countries through the direct financing mechanism (DIM) and by encouraging countries to seek additional funding for their BFPs.

  - Focus on fine tuning the BIOFIN global efforts and strengthening and consolidating the work in the current countries. EU/UNDP should spend time to pursue the uptake of finance solutions and the sustainability of the BIOFIN process in the current countries.

  - Host a donor round table in 2017 to resource BIOFIN phase two. To procure further investment, it is recommended that the EU/UNDP scale-up their successful initial intervention in the 8 initial pilots, expand support for the implementation of the biodiversity finance plan and prioritized finance solutions.

- Recommendation Priority 2.  Scale BIOFIN Globally. BIOFIN should expand its reach to additional countries with additional financing for new core countries and by providing light support through the concept of “regional nodes”.

UNDP

Recommendation Priority 3. A new LogFrame (outcome, outputs and indicators) needs to be validated and vetted for Phase 2 to be reviewed by UNDP management for two levels of results: global and national level institutionalization, capacity strengthening and sustainability.

Additional Recommendation. Integrate BIOFIN lessons into future NBSAPs.  Advocacy for further links of BIOFIN methods to next generations of NBSAPs is needed. The BIOFIN methodology can improve future NBSAP’s cost-effectiveness as demonstrated in Chile and Philippines. A firm recommendation can now be made for the CBD to consider BIOFIN lessons into NBSAP guidance.

BIOFIN Global

- Recommendation Priority 4. BIOFIN Resource Mobilization for Phase Two.  In 2017, BIOFIN global team should prepare and secure funding for a full second phase of BIOFIN activities focusing on deepening BIOFIN’s impacts in core countries and sharing lessons learned more broadly.  This phase 2 programme can include:

  - Further integration and coordination across projects including WAVES/SEEA, SDF, various climate initiatives, TEEB and others to further support long-term outcomes

  - Clarification of a comprehensive exit strategy for phase two, including growth scenarios and positioning, and designed exit strategies for the 19 most advanced countries.

  - An evidence-based, fleshed-out design concept for scale-up.

  - Further define future global support work including with private sector finance engagement, data and practice standards, and BIOFIN capacity building support. This will be enhanced by a cross-country meta-analysis of 30 countries for comparison and trend analysis.

- Recommendation Priority 5. Deepen ongoing support for Biodiversity Finance Plan development and implementation.  In the near term (by the end of 2017), the global team can deepen the preliminary results (in a subset of countries) to create more advanced “pilot” countries who are creating and implementing powerful BFPs to serve as examples for other countries.  This will demonstrate both the value of the BFP itself and demonstrate specific finance solutions including engagement with the private sector for example.

- Additional Recommendation. In the final year of implementation (2018), a global BIOFIN communications effort can showcase the BIOFIN approach. This communication effort should highlight BIOFIN success in relation to its utility for supporting SDG planning, integration with climate and Sustainable Development Finance work.

- Additional Recommendation. Enhance Private Sector Engagement globally and nationally. Develop an improved engagement strategy for work (demonstration, education, partnerships) with the private sector. Review private sector engagement in key countries for improved advocacy and national resource mobilization. Undertake a series of webinars on private sector engagement. Share UNDP due diligence processes and rules on the private sector with BIOFIN national teams.

- Recommendation Priority 6. BIOFIN Data Tool Enhancement.  Long term global results are partially dependent on improving standards for biodiversity finance data collection. The Alpha version of the BIOFIN Data Tool should be improved and further integrated into the BIOFIN national process. A global subset of data and baseline on biodiversity finance linked to biodiversity expenditures and finance needs, finance solutions etc. is essential for the CBD, donors, and countries. Clarification on expenditure attribution (especially for indirect expenditures) will enhance usefulness of country and global analysis.  Ongoing work with UNSD, Eurostat and OECD, should continue and national efforts to integrate UN SEEA frameworks with the BIOFIN process should be supported.

- The speed of resources growth - geographical and expansion in content was a challenge. Growth of management team in retrospect need be proportional, including support staff.  Phase II can be designed as a larger programme from the onset, while growing proportionally in an incremental matter, based on the availability of funds.

BIOFIN National Programs

Recommendation Priority 7.  Exit strategies and institutionalization at the national level should be further developed and implemented. This may include institutionalization of the biodiversity tagging process, adaption of the BIOFIN method with policy support, replication of the method in other sectors or at sub national level, and hiring / re-engineering of some staff positions towards biodiversity finance.

Recommendation Priority 8. Enhanced South-South learning.  The expansion and increased systematization of South-South learning among all BIOFIN core countries can be broadened and include countries engaged in the regional nodes.

Additional Recommendation. Communication and Advocacy.  The BIOFIN global team should develop improved “strategic BIOFIN communication guidance”.  This guidance will aid with the support of national communication efforts to assure greater impact of BIOFIN efforts with key decision makers as well as build enhanced capacity at the national level.

Additional Recommendation. Education, Knowledge Management and Communication Strategies. BIOFIN can explore the potential for increased higher level education products to enhance national capacity for understanding and implementing biodiversity finance solutions. A BIOFIN learning and knowledge sharing plan can be developed targeted to public sector employees (finance, planning, and other sectors), key civil society actors (NGOs, CBOs), and key implementation partners (private sector) building on good examples of work.

Additional recommendation. The BIOFIN process can become more focused towards building longer-term national capacity which might include the integrating the BIOFIN methodology into national higher-level education curricula (i.e. Masters level).

# ANNEX 1: EU/UNDP LOGFRAME EXPECTED RESULTS

# See annex 5

# ANNEX 2 CBD-BIOFIN REGIONAL NODES – OFFICIAL NOTICE

Official Communication of the CBD-UNDP Regional Nodes

Launching of CBD-UNDP Regional Technical Support Nodes on Financial Planning and Reporting

Dear Madam/Sir,

We are pleased to inform you that the Secretariat of the Convention on Biological Diversity (CBD), in close collaboration with the Biodiversity Finance Initiative of the United Nations Development Programme (UNDP-BIOFIN), is launching the CBD-BIOFIN Regional Nodes, with a view to provide technical support for financial planning and reporting to non-BIOFIN pilot countries. This launching event will take place during the thirteenth meeting of the Conference of the Parties to the CBD in Cancun, Mexico.

To this effect, a dedicated resource person will be available in each region to provide such technical support, based on the various approaches and tools assembled in the BIOFIN methodology. Support can be made available to all developing countries and countries with economies in transition that are not among the 30 core participating countries of BIOFIN.

The type of support that can be provided consists of bilateral webinars, general webinars, specific knowledge management products, and limited in-country missions by the resource persons. The regional node resource persons are scheduled to start their duties in November 2016. Please refer to the rollout schedule in annex for details.

Countries are encouraged to submit their informal expressions of interest for support at their earliest convenience to BIOFIN@undp.org with a copy to secretariat@cbd.int.

Please accept, Madam/Sir, the assurances of our highest consideration.

Braulio Ferreira de Souza Dias, Magdy Martínez-Solimán

Executive Secretary Director, Bureau for Policy and Programme Support

Secretariat of the Convention on Biological Diversity United Nations Development Programme

# ANNEX 3:  OPTIONS FOR PHASE TWO

PHASE TWO OPTIONS

Position

Option 1: implement the Finance Plan developed under Phase 1; this will need a greater budget per country than under Phase 1, in my eyes anything between $2-20m per country; UNDP / BIOFIN could support this alone without any content partner; I estimate that we would only be able to support a max of 10 countries to this height i.e. total of $20-100m; that means that these efforts will need to be supported by OTHER agencies with budgets such as WB, GIZ, ADB, WWF CI, etc. in other countries

Option 2: expand BIOFIN conceptually into (sector specific) economic valuation of BD and natural capital accounting, to offer a more complete package; for this BIOFIN will need content partners egg WB/WAVES, or UNSD/SEEA; budgets per country will be even higher, yet new leverage would be possible for fundraising and also national impact. NCA / EV would bring the political/economic case while BIOFIN brings more some data on finance without giving a good rationale able to convince govt to invest more in BD; here link to SDGS is also important be SEEA will likely become the main SDG indicator framework i.e. there are links to MAPS, etc.

Evaluator recommend to keep and work on both options and see what is possible, to have discussions with partners and donors on their interest

Also the BIOFIN approach could be applied to many sectors also beyond envy. If UNDP could agree to apply the BIOFIN concept to all the SDGs across silos this could be powerful for UNDP. Implement this not via UNDP Country offices be capacity is too low. But through Regional Hubs: and not as BIOFIN alone, or CC/BD alone, but for SDG sectors more widely; this could deserve dedicated staffing at Rehabs

Risk

·         BIOFIN is a globally unique initiative highly positioned and visible – it hence carries also a high risk for UNDP. Donors had for a long time pointed out to the need to sort out the BIOFIN Management situation and were disappointed to see the lack of appropriate response from UNDP in terms of HR and Programme Support.

·         Visibility implies a high risk in terms of donor and community reputation if UNDP doesn’t address the capacity gap in the team, even if that may not be acknowledged as a problem anymore

·         Lost opportunity if BIOFIN 1) doesn’t deliver the national outputs to an acceptable degree; 2) doesn’t grow within itself into Phase 2; and 3) doesn’t expand to become more useful to UNDP and Environment and SDGS more widely;

# ANNEX 4: WORKBOOK DESCRIPTION

# ANNEX 5: LOGFRAME STATUS UPDATE – DECEMBER 2016

This LogFrame captures the duration of the original EU-UNDP project including the no-cost Extension (October 2012-December 2016, in light green) in addition to the added duration facilitated through the contributions by the Governments of Switzerland, Norway, Flanders and Germany (the latter of which concludes in December 2018, in dark green).

| Outcomes Baselines, Indicators Sources of Verification, Targets | Results Activities |
| --- | --- |
| Outcome 0: Project management and lead technical expertise in place and operational, and project objectives and results disseminated and welcomed. Baseline: CTA-BD is appointed from within UNDP. Neither other staff nor national project units selected. Awareness about project exists amongst key global experts but no results available/ disseminated. Indicators: 0.1 Technical and administrative staff recruited and teams completed and operational. By the end of 2016, the global team had reached 12 persons complemented by short term experts and national teams jointly totalled over 75. The team has 2 internship assignments going on throughout the year. 0.2 CBD side-events and other meeting presentations/ participations. 2014: COP 12 Side event with partners In 2015 BIOFIN was represented at various CBD regional workshops, OECD meetings on finance flows and a DIE meeting on biodiversity finance impacts. In 2016, side events were organised at the CBD SBI, the World Conservation Congress and COP 13. 0.3 Project products (primers) received by parties and used/ recognised in CBD negotiations and decisions. COP-12 decision on Resource Mobilisation calls for the application and upscaling of BIOFIN, similar references are made in various other COP documents and country statements for COP 13. 0.4 Evaluation meeting held. 2015: Regular progress evaluation takes place through Steering Committee Meetings. An evaluation meeting specifically for the EU agreement is planned for October 2016. 0.5 Follow up project(s) aimed at a wider roll-out of the methodologies and tools. 2012: Contributions from Germany and Switzerland added 2013: One additional contribution. From Germany 2014: Three additional contributions received from Germany, Norway and Flanders 2015: One additional contribution received from Switzerland, to add one more country to the programme, brought the total number to 30 and the budget at 29 Million US$. SOV: Signed staff contracts. Project inception report. Side events on CBD website. Meeting agendas and summaries. CBD reports, recommendations or decisions. Feedback from parties and relevant institutions. | Result 0.1 Global central technical unit and national project units set up and operational throughout the project Activities: Recruitment of project staff and establishment of Central Technical Unit and national units, procurement of national consultants, establishing systems and coordination mechanisms, procuring equipment. Oversight, management and technical leadership throughout the project, to include travel, procurement, coordination, administration, monitoring and reporting. 2012-13: Management and technical work by existing UNDP-GEF team 2013: Project Management Specialist and Programme Management Associate hired 2014: Two senior advisors and communications expert hired, start of internship programme. 2015: The global team added a KM M&E Expert and 3 more senior advisors. A new Programme Associate and junior consultant were on board early 2016. The number of national BIOFIN team members has exceeded 75, set to reach over 100 in 2016. |
|  | Result 0.2 Project objectives and outline, interim results/products and final results/products disseminated. Activities: Develop dissemination plan for methodology frameworks and tools and for the results of in-country assessments. Prepare preliminary but substantial reports for CBD WGRI-5 and COP-12. Organise side-events at CBD COP-11, WGRI-5, COP-12 and participate/ present in other strategic events. Complete final publications for WGRI-6 and COP-13. Post relevant project reports on EC, UNDP, project and other relevant websites, and widely circulate. Final evaluation meeting with stakeholders to discuss uptake and explore future/ complementary actions. 2015: Outline for new workbook version developed, regular web articles published, and 12 case studies to be published in 2016. Major publication of next workbook version at COP 13. A new platform is developed on biodiversity finance resources on BES-NET with support from BIOFIN, also launched at the COP. |
| Component 1. Analyse the integration of biodiversity and ecosystem services in sectoral and development policy, planning and budgeting Outcome 1: A framework for mainstreaming biodiversity into national development and sectoral planning is developed, tested, refined and disseminated Baseline: No consistent, effective and widely accepted framework exists Outcome indicators: Completion of methodology framework, tools and primer. Number of participating CBD Parties that integrate considerations on biological diversity and its associated ecosystem services in development plans, strategies and budgets (cf. CBD resource mobilization indicator #10) Activity indicators: Draft and final framework, tools and primer. Number of national workshops held. Thematic workshop held. Number of sets of national biodiversity targets and mainstreaming strategies developed. 2015: 3 major regional workshops used to distil country learning, combined with observations from regional calls and in-country missions, analysed in a technical meeting in July 2015 to produce a new outline by the end of 2015. Published version printed and launched at COP 13 in December 2016. SOV: Project/ workshop reports and publications. EC, UNDP and project websites. National documentation of biodiversity targets and mainstreaming strategies: NBSAPs, CBD 5th NR, national development plans and budgets, poverty reduction strategy papers, national adaptation programmes of action, sectoral plans. Targets: Final mainstreaming methodology framework, tools and primer. 8 pilot-country mainstreaming reports. | Result 1.1 Analysis of mainstreaming opportunities in development and sectoral planning at country level Activities: Analyses of opportunities for mainstreaming biodiversity into development and sectoral planning in pilot countries, through desk-top survey and consultation workshop. Production of reports by country-level contractors. 2016: Policy and Institutional Reviews is ongoing in 28 countries and in the final stages in 18 countries. The Expenditure Review is at an advanced stage in 15 countries. |
|  | Result 1.2 Development of generic mainstreaming framework including tools Activities: Side-event at COP-11. Review related past and current initiatives and their usefulness. Development of draft generic mainstreaming framework including tools, including on the costs of inaction/BAU; the costs, opportunity costs and benefits of various development scenarios and trade-offs; a process to develop sector-specific work plans which integrate biodiversity priorities into their processes, policies and budget allocations; and estimates of reductions in biodiversity management cost under different mainstreaming scenarios. Global thematic workshop to present and refine draft mainstreaming framework and tools. 2014: 2014 Workbook developed. 2016: Two mainstreaming tools developed: (1) Biodiversity Finance Policy and Institutional Review and (2) Biodiversity Expenditure Review, refined based on implementation lessons, published in December 2016. |
|  | Result 1.3 Piloting of draft framework at country level Activities: Prepare background information for and hold national workshop to present and test mainstreaming framework and tools, and to brainstorm sector-specific work-plans. Produce workshop report and costed sector-specific work-plans. National teams backed by NSC pilot draft mainstreaming framework working closely with government and in line with NBSAP processes. 2016: Piloting taken off in 30 countries. |
|  | Result 1.4 Lessons from piloting incorporated into final methodology. Activities: Country teams and contractors provide feedback to CTU & GMT. CTU and GMT incorporate feedback from piloting into finalised methodology framework and tools. Production of primer publication on framework for mainstreaming biodiversity into national development and sectoral planning. 2013: Peer review process of first BIOFIN Workbook 2014: Further review during 1st Global Workshop – 100 persons = Launch of 2014 BIOFIN Workbook in December 2015: Consultation 3 regional workshops 150 persons 2016: Final internal and external peer review process Launch of 2016 BIOFIN Workbook |
|  | Result 1.5 Development of national biodiversity targets and mainstreaming strategies through NBSAP revision processes Activities: Taking stock of biodiversity status and policies and CBD implementation progress and of barriers to implementation. National consultations and workshops. Developing national biodiversity targets and integrating mainstreaming aspects into NBSAP documents and processes, and developing costed action plans for sectoral implementation. Preparing 5th CBD National Reports. 2016: Most NBSAPs are at advanced stage, 17 countries formally submitted to CBD, while all 30 countries submitted the 5th national report (by January 2016). |
| Component 2 Assess future financing flows, needs and gaps for managing and conserving biodiversity and ecosystem services Outcome 2: A methodology for assessing a country’s biodiversity financing needs is developed, tested, refined and disseminated Baseline: No consistent, effective and widely accepted framework exists Outcome indicators: Completion of methodology framework, tools and primer. Number of participating countries that have identified and reported funding needs, gaps and priorities (cf. CBD resource mobilization indicator #5). 2015: 3 major regional workshops used to distil country learning, combined with observations from regional calls and in-country missions, analysed in a technical meeting in July 2015 to produce a new outline by the end of 2015. 2016 Workbook published in Decmember2016. Activity indicators: Draft and final methodology, tools and primer. Thematic workshop held. Number of national workshops held. SOV: Project/ workshop reports and publications. EC, UNDP and project websites. NBSAP. CBD 5th NR. National reports on biodiversity funding flows, effectiveness, needs and gaps. Targets: Final financing needs and gaps methodology framework, tools and primer. 8 pilot-country preliminary data reports. | Result 2.1 Preliminary data collection and analysis, integration with NBSAP and national biodiversity target setting processes. Activities: Preliminary data gathering and compilation pilot countries on current financing of biodiversity management, additional needs and barriers. National and global analysis of the data. Integration with NBSAP and national target processes. 2012-3-scoping of related methodologies and relevant country data. 2013-4: Initial scoping in first 12 countries 2014-5 Scoping in further 7 countries 2015-6 Scoping in 11 more countries |
|  | Result 2.2 Draft methodology and tools for assessing a country’s biodiversity financing needs and gaps are developed Activities: Side-event at COP-11. Review related past and current initiatives and their usefulness. Draft methodology and tools produced for assessments of: finance flows and spending: finance needs and gaps; biodiversity management cost and cost-effectiveness; current and future opportunities and barriers to implementation and meeting the costs and achieving cost-effectiveness; and the costs of removing barriers. Global thematic workshop to present and refine draft methodology framework and tools. GMT consolidates draft methodology and tools for pilot phase. 2014: Launch of the 2014 BIOFIN Workbook and related tools 2016 Launch of the 2016 BIOFIN Workbook and related tools |
|  | Result 2.3 Draft methodology is tested through country piloting Activities: Together with NSC and government, apply the draft methodology and tools and prepare comprehensive national assessments as outlined above, resulting in national reports on biodiversity funding flows, effectiveness, needs and gaps. 2015: The Finance Needs Assessment is at an advanced stage in 16 countries. |
|  | Result 2.4 Lessons from piloting incorporated into final methodology Activities: Country teams and contractors provide feedback from piloting process to CTU & GMT. CTU and GMT incorporate feedback from piloting and finalise methodology and tools. Production of primer publication on assessing national biodiversity financing needs and gaps. 2013: Peer review process of first BIOFIN Workbook 2014: Further review during 1st Global Workshop – 100 persons = Launch of 2014 BIOFIN Workbook in December 2015: Consultation 3 regional workshops 150 persons 2016: Final internal and external peer review process Launch of 2016 BIOFIN Workbook |
|  | Result 2.5 Biodiversity finance needs and gap assessments under the national NBSAP processes are conducted with input from the project and in turn contribute data to the project Activities: National consultations and workshops. Development of biodiversity finance assessments in line with relevant guidance from the CBD and the Strategy for Resource Mobilisation. 2015: The Finance Needs Assessment is at an advanced stage in 16 countries. |
| Component 3: Develop comprehensive national Resource Mobilisation Strategies to meet the biodiversity finance gap Outcome 3: A framework for national-level biodiversity financing is developed, tested, refined and disseminated Baseline: No consistent, effective and widely accepted framework exists Outcome indicators: Completion of methodology framework, tools and primer. Number of participating countries that have developed national financing plans for biodiversity (cf. CBD resource mobilization indicator #5) 2015: 3 major regional workshops used to distil country learning, combined with observations from regional calls and in-country missions, analysed in a technical meeting in July 2015 to produce a new outline by the end of 2015. Fully published version launched December 2016. Activity indicators: Draft and final methodology, tools and primer. Thematic workshop held. Number of national workshops held. Number of national PA financing and PES frameworks. SOV: Project/ workshop reports and publications. EC, UNDP and project websites. NBSAP. CBD 5th NR. National frameworks for biodiversity financing. National PA financing and PES frameworks. Targets: Final financing options methodology framework, tools and primer. 8 pilot-country national financing frameworks. | Result 3.1 Draft methodology framework and tools on options for national-level biodiversity financing Activities: Side-event at COP-11. Review related past and current initiatives and their usefulness. Assess the current state of global biodiversity markets and innovative funding and policy instruments. Develop draft methodology framework and tools to assess different biodiversity financing options, including innovative sources of funding, current and potential policy instruments, including economic instruments. Global thematic workshop to present and refine draft methodology framework and tools. Consolidate for pilot phase. 2015: The 2014 Workbook is in use in countries, as the team captures all relevant lessons learnt to be included in the 2016 version. |
|  | Result 3.2 Country piloting of draft methodology framework and tools to produce framework for biodiversity financing Activities: National workshops, to build capacity on the use of the methodology framework and tools and the development of national frameworks for biodiversity financing, and initiate the piloting of the methodology framework and tools. Assess national financing options - analysis of potential for traditional and innovative sources and instruments, including an outline of the country's fiscal and budgeting system. Produce and distribute national frameworks for biodiversity financing aimed at identifying, accessing, combining and sequencing multiple sources of funding. 2016: The Biodiversity Finance plan is drafted based on a highly consultative trajectory. In 15 countries. |
|  | Result 3.3 Lessons from piloting incorporated into final framework for national-level biodiversity financing Activities: Country teams and contractors provide feedback from piloting process to CTU & GMT. CTU and GMT incorporate feedback from piloting and finalise methodology and tools. Production of primer publication on frameworks for national-level biodiversity financing. 2013: Peer review process of first BIOFIN Workbook 2014: Further review during 1st Global Workshop – 100 persons = Launch of 2014 BIOFIN Workbook in December 2015: Consultation 3 regional workshops 150 persons 2016: Final internal and external peer review process - Launch of 2016 BIOFIN Workbook |
|  | Result 3.4 National biodiversity financing strategies prepared and used under the national NBSAP processes, and they are conducted with input from the project and in turn contribute data to the project Activities: National consultations and workshops. Development of biodiversity financings strategies in line with relevant guidance from the CBD and the Strategy for Resource Mobilisation. 2016: The Biodiversity Finance plan is under development in 15 countries |
|  | Result 3.5 Development of national PA financing and PES frameworks, including relevant policy and institutional support Activities: Developing legal, policy and institutional frameworks to enable sustainable financing of national parks agencies. Capacity strengthening for environmental ministries and partners in financial planning and cost-effective management of PAs and PA system. Developing ICT-based ecosystem service valuation tools and government capacity to use them in trade-offs with different land-use options. Developing the enabling policy/legal environment for PES mechanisms; design, negotiation and formalization; national system for monitoring, reporting and verification of services, and payment distribution mechanisms. In Malaysia, a strategy paper for the establishment and operationalization of the Malaysian Conservation Trust Fund (MCTF) was developed. In Ecuador, a gap analysis was completed for the protected area legislation and regulations developed and adopted for the national cooperation of private reserves. |
| Component 4 Initiate implementation of the Resource Mobilisation Strategy at national level 2016: Outcome and Indicators, Baseline, Targets and SOV to be developed at national level in each country. | 2016: Implementation ongoing in 12 countries. |

# ANNEX 6: UPDATED PROJECT INFORMATION REPORT TO IKI

# International Climate Initiative (IKI)

# Current Project Information

| Project number |  |
| --- | --- |
| Project title | The Biodiversity Finance Initiative - BIOFIN |
| Country/countries of implementation | 30 core countries: - Eurasia-Pacific: Bhutan, Fiji, Georgia, India, Kazakhstan, Kyrgyzstan, Indonesia, Malaysia, Mongolia, Philippines, Sri Lanka, Thailand, Vietnam. - Africa: Botswana, Mozambique, Rwanda, Seychelles, South-Africa, Uganda and Zambia. - Latin America/The Caribbean: Belize, Brazil, Chile, Colombia, Costa Rica, Cuba, Ecuador, Guatemala, Mexico and Peru. |
| Implementing organisation | United Nations Development Programme - UNDP |
| Project duration | 11/12/2012 - 31/12/2018 |
| Date of report | 10/10/2016 |

- Please note the length requirements for the two headings a) and b) -

| A) Political relevance of the project | Global - At the global level, interaction with the CBD process is of critical importance. BIOFIN has organised activities jointly with the CBD Secretariat, including regional workshops (2013 and 2014) and a global experts workshop in May 2015 (Mexico). Through the COP-12 decision on Resource Mobilisation (UNEP/CBD/COP/DEC/XII/3), CBD parties formally endorsed the BIOFIN methodology, recommending countries to apply its tools and calling for BIOFIN to further upscale. At SBI (May), several governments positively mentioned their involvement in BIOFIN during plenary discussions. BIOFIN is working with the CBD to provide inputs into the COP agenda and draft texts related to BIOFIN, while 2 COP 13 side events are planned. - A series of dialogues has taken place with UNSD to develop synergies. The new BIOFIN classification is fully compatible with SEEA categories. BIOFIN presented at several sessions during the IUCN World Conservation Congress and helped develop a module on biodiversity finance for the BES-Net http://besnet.world/biodiversity-finance - In 2016, the 2nd BIOFIN Global workshop was held in Mexico (12-14 April), with over 25 high-level participants (e.g. the Ministers of Environment from Mexico and Guatemala). Highlights included discussions about how to guide countries to ensure finance solutions such as green bonds, impact investment and climate finance have an actual impact on biodiversity. One of the strongest comments from the meeting was the need to expand the focus on the private sector. - The 2016 BIOFIN workbook is nearly completed, and is based on the lessons learnt in countries. It is based on four main finance results: generate revenues, deliver better, realign expenditures, and avoid future expenditures. This emphasises the need to look at opportunities beyond resource mobilisation alone. - The CBD-BIOFIN Regional Nodes are being launched, enabling all CBD parties to gain access to some level of support to understand and apply the BIOFIN methodology. National Level In 2015, 11 additional countries signed up for BIOFIN; Belize, Bhutan, Brazil, Cuba, Georgia, Kyrgyzstan, Mongolia, Mozambique, Sri Lanka and Vietnam and Rwanda. Most of the 19 countries joining earlier are at an advanced level with their Public Institutional Review (PIR) and Biodiversity Expenditure review (PER), and have started their Finance Needs Assessments and Biodiversity Finance Plans. - Peru: In June 2016, the Ministry of Economy and Finance officially approved a new version of the General Guidelines for Public Investment Projects (supported by BIOFIN), including criteria for biodiversity and ecosystems that need to be considered. - BIOFIN studies in Philippines, suggest a significant finance gap, remains for the country to be able to fully fund its NBSAP. The team is now working on a variety of finance solutions, including a national fund from oil and gas revenues, local government funding and a marketplace to match biodiversity investors with projects, in order to help filling this gap. - The national BIOFIN Team in Costa Rica, led by former Minister of Finance Mr Guillermo Zuñiga, is closely engaged with a variety of stakeholders, in particular with the private sector. BIOFIN is now working on a range of finance solutions, including how to allocate revenue from green bonds to biodiversity. - BIOFIN in India is largely driven by government, working primarily through two technical agencies, The Wildlife Institute of India and the National Institute of Public Finance and Policy. Some of the emerging opportunities include the ‘greening’ of India’s large government schemes and building a better framework to direct CSR payments to biodiversity objectives. - In Guatemala, the national team completed the PIR, BER, FNA and BFP and is now working on the implementation of different finance solutions such as the creation of a tax on port activities, permits of fishing to protect sailfish activities and allocating land fee revenues to the protected are system. - In Chile, the draft expenditure review indicates the proportion of biodiversity expenditures as a share of total government expenditures grew from 0.11 to 0.16% between 2010 and 2014, indicating an upward trend. - Seychelles held a workshop on sustainable tourism in May 2016. The Ministry of Finance made it clear to all concerned that they could use up to half of the Corporate Social Responsibility (CSR) Tax to fund their biodiversity programmes by using an NGO to execute such programme. - The 2nd Regional Workshop for the African countries (October) had dedicated sessions on subsidies and revenues, which have become more central elements of the BIOFIN methodology. |
| --- | --- |
| B) Information of public interest | 2016 - The 2nd BIOFIN Global workshop, (Mexico, 12-14 April) highlighted the need to further explore biodiversity finance within a broader range of finance solutions, such as green bonds, impact investment and climate finance, producing some initial mapping of possibilities. Around 25 high level participants attended, including the Mexican Minister of Environment and the Vice Minister of Finance of the Philippines. - Regional Workshops took place in Chile (26-28 January), Indonesia (2-4 March) and Zambia (5-7 October) - BIOFIN organised a side event during CBD’s SBI (May) and presented at the IUCN World Conservation Congress in Hawaii (September) - A new version of the BIOFIN workbook 2016 is nearly completed, to be launched at COP 13. The new methodology include all the lessons learnt in the different core countries of BIOFIN and new features that will be implemented to address the four main finance results of BIOFIN: generate revenues, deliver better, realign expenditures, and avoid expenditures. The methodology is enriched at all levels, providing more specific guidance on how to set up BIOFIN as a policy process, integrating the economic values of ecosystems into the policy analysis and how to prioritise potential biodiversity finance solutions. - In Peru in June 2016 the Ministry of Economy and Finance officially approved a new version of the General Guidelines for Public Investment Projects, incorporating a focus on sustainability and highlighting the importance of investing in ecosystem services. BIOFIN supported the dialogue between the Ministry of Economy and the Ministry of Environment, and provided technical assistance. (link) - In Guatemala, the national team completed the PIR, BER, FNA and BFP and is now working on the implementation of different finance solutions such as the creation of a tax on port activities, permits of fishing to protect sailfish activities and the implementation of laws allowing to earmark a certain percentage of taxes to the institution in charge of the protected areas the CONAP. - The national BIOFIN Team in Costa Rica, led by former Minister of Finance Mr Guillermo Zuñiga, engaged with a variety of stakeholders, collaborating with the Chamber of Banks and Financial Institutions, the Chamber of Industries and the Costa Rican Union of Chambers of Private Enterprise to collect private sector biodiversity expenditure data. BIOFIN is now requested to support the development of a range of finance solutions. - South Africa completed their policy analysis and assessed expenditures in private protected areas, using links between SDGs to mainstream biodiversity with the different stakeholders. - BIOFIN in Bhutan is integrated into a broader initiative to develop finance solutions for three SDGs, related to poverty, climate change and biodiversity. Dasho lam Dorji, former secretary of Finance, is now the national BIOFIN team leader (link). - BIOFIN in India is largely driven by government, working primarily through two technical agencies, The Wildlife Institute of India and the National Institute of Public Finance and Policy. Activities are also undertaken at the state level. They are working on an improved framework for allocating Corporate Social Responsibility (CSR) payments to biodiversity objectives. 2015 - Eleven new countries joined BIOFIN; Belize, Bhutan, Brazil, Cuba, Georgia, Kyrgyzstan, Mongolia, Mozambique, Rwanda, Sri Lanka and Vietnam. - Three regional workshops (around 150 participants) were organised in Kuala Lumpur (Malaysia), Quito (Ecuador) and Gaborone (Botswana). Through these workshops, representatives from Ministries of Finance and Environment, National BIOFIN teams and UNDP offices, learned about the BIOFIN methodology and shared feedback of their learning. 2014 - Colombia, Fiji, Guatemala, India, Mexico, Thailand and Zambia joined. - The 1st Global BIOFIN workshop brought together over 100 participants from BIOFIN countries, donors and related initiatives to discuss the draft BIOFIN methodology. - The BIOFIN Website was created: www.biodiversityfinance.net. - BIOFIN Twitter and YouTube were launched. - The user-friendly BIOFIN workbook 2014 was released in November at the CBD COP 12 in Korea, including a set of datasheets. 2013 - BIOFIN activities started in 12 countries; Botswana, Chile, Costa Rica, Ecuador, Indonesia, Kazakhstan, Malaysia, Peru, Philippines, Seychelles, South Africa and Uganda. - The first draft of the BIOFIN workbook was developed. It consisted of 3 steps, a policy and expenditure analysis, costing of national finance needs for biodiversity and developing a resource mobilisation plan. |

# ANNEX 7: STEERING COMMITTEE MEETINGS SUMMARY

| DATES | ACTIVITIES AND EVENTS |
| --- | --- |
| 07 March 2013, 11:00-16:00 UNDP Representation Office in Brussels 14 Rue Montoyer - 1000 Brussels | 1st Steering Committee Meeting. Participants: o EC/LL – EC Laure Ledoux, European Commission, DG ENV o EC/JP – Jerome Petit, European Commission, DG DEVCO o DE – Axel Bennemann, Federal Ministry for the Environment, Nature Conservation and Nuclear Safety, Germany o CH – Nathalie Rizzotti, Federal Office for the Environment, Switzerland o UNDP/AH – Anna Hysbergue, UNDP Brussels o UNDP/IG – Irene Garcia, UNDP Brussels o UNDP/YdS – Yves de Soye, UNDP-GEF & BIOFIN CTA. BIOFIN & NBSAP Forum - Basic funding for the NBSAP Forum is secured for the first year, it is starting to become operational, and the website is about to be developed; decisions about other funding proposals remain pending; - DE: don’t make it like the POWPA platform, not v useful if only online platform - hands-on tech support needed. Emphasises again that the remit of the shared staff should not comprise wider support to the core of the NBSAP Forum, but remain focused on the Biodiversity Finance aspects. Broad consensus on this. Methodology Toolkit & Work Plan - Some areas are (too) complex and detailed. Filling in the toolkit will be very difficult. - Make it less academic, more praxis oriented, focus on the critical information/aspects - what do we need to achieve the project outcomes/objectives - The aim is review and generate recommendations report at end, based on the completed Toolkit - So far the Methodology / Guidance focuses on how to collect the data; but is misses guidance and explanations on the data generated can be processed. - What we need is a costing of the NBSAP - paying attention to the policies that govts are willing to in to leverage change. Should not look at ideal world but at actual realistic targets. The key is that it is useful for countries, for which less detail is needed. - three levels of ambition: - Step 1: “ideal biodiversity conservation world” = 100% of costs/needs to achieve each of the Aichi Targets (in each country) - Step 2: national targets as defined by NBSAP = already reduced level given that some countries will not deliver on all Aichi Targets – because they may not want to (i.e. they do not consider it important or economically/politically feasible), or cannot (for lack of capacity or resources) - Step 3: further reduced level = what of the NBSAP latter can be funded after prioritisation exercise under Resource Mobilisation section - The main focus of BIOFIN costing should be on Steps 2 and 3 – but it would make limited sense to not have some idea of the costs/needs under Step 1. - for Res Mob - need to identify what financing mechanisms are feasible in reality (considering policy envt, capacity, etc.); i.e. not a full wish list catalogue. - UNDP to clarify the difference between Tiers 1-3, and what additional resources will be used for and how this influences the Toolkit and country selection; different scenarios needed for different budget levels; - Do not want BIOFIN and MAG (Methodology Advisory Group) to be connected institutionally to the HLP - Pilot countries will be fully involved and consulted during the development of the methodology. Workplan - Review scope of methodology (sector, ecosystems, opportunity costs, etc.) - Do Not expect that all is ready by COP. The quality of the outcome should not be compromised – the most important is to develop and implement useful strategies and processes for countries – the proposed in-country processes focused on the CBD timelines look very compressed - it will not be possible to establish a transformational process/output in only one year and it will be also hard to achieve the necessary retro-feed from countries on national feasibility (costs/needs & target definition & resource mobilisation). However, the methodology and its implementation in some pilot countries should be presented. The consolidation - The project should 1. provide more national engagement opportunity and time incl. through workshops, committees, etc. 2. ensure national ownership (i.e. should not be perceived as an external intervention) 3. leave an enhanced capacity legacy. - Broad consensus that objective is not to have all the national assessments fully completed/finalised by the COP; preliminary results is good enough – but need to define scenarios of what is the minimum to be achieved by CBD WGRI and COP in 2014. Staffing - DE confirms agreement that DE funded staff can be shared between BIOFIN and NBSAP Forum BD Finance - Should we share staffing costs for CTU to avoid reporting/contractual conflicts, especially w/ EC? - EC/JP: not an issue that EC-funded global posts (CTU) work on issues and countries not directly covered by the EC-UNDP contract; but he will need to check with colleagues. Communication: - Broad agreement (incl. CH, DE and EC/JP) that all donors/partners can communicate about BIOFIN as a whole, i.e. results and countries are shared by all, there is no ownership by specific donors of specific countries/results. Further fundraising / Donor roundtable Conclusion that : o Try non-EU donors next such as China, Brazil, India, Canada, etc o If successful can return to considering a EU donor meeting such as next to a WPIEI - otherwise too Europe-biased |
| 10 July 2013, 11:00-14:00 By video conference | 2nd Steering Committee Meeting. Participants: - At DG DEVCO (European Commission): - Thierry Dudermel, DG DEVCO, European Commission [TD] - Jerome Petit, DG DEVCO, European Commission [JP] - Laure Ledoux, DG ENV, European Commission [LL] - Irene Garcia, UNDP Brussels [IG] - Yves de Soye, UNDP Bratislava [YdS] - At BMU Bonn (Germany): Axel Benemann [AB] - At FOEN (Switzerland): Nathalie Rizzotti [NR] - At UNDP Pretoria (South Africa): Nik Sekhran [NS] - At UNDP Kampala (Uganda): Jamison Ervin [JE], Susanne Olbrisch [SO] Update on global NBSAP work / NSBAP Forum [NS, JE] - Fundamental funding for the NBSAP Forum ($1.8 million) has now been secured. It will remain separate from BIOFIN but there are important connection points on biodiversity finance. BIOFIN global team recruitment: - Recruitments for full time staff positions are far advanced and highly qualified staff pre-selected as per a demanding competitive process. - Financed by EC: - P5 Project Manager and Technical Advisor for Environmental Finance and P3 Project Specialist. Duty station for these will be Istanbul given that the Bratislava Centre will move there in 2014. Interim arrangements involve work from home or other UNDP offices. - G7 Project Management Associate, to be recruited into UNDP NYC HQ given the financial management support there. - Financed by BMU: Jamison Ervin will be under contract throughout the project, currently funded by UNDP and moving to BMU funding later; she will assume the hybrid BIOFIN-NBSAP Forum role. Following a query from AB, assurance was given that there is no risk of double accounting. - Susanne Olbrisch onboard as technical and administrative support consultant until end 2013. - Emphasis on the fact that UNDP is covering the project start-up period and delivering the methodology with its own internal staff from different offices distributed globally. - Must align with High Level Panel to not produce inconsistent approaches. - HLP hoped that BIOFIN would contribute country data, but we must be very cautious and cannot give out data that countries may consider confidential; JE is invited by CBD to discuss alignment of BIOFIN methodology with HLP and Resource Mobilisation Framework Methodology Development, National/Regional Outreach and Planning - The current version of the emerging methodology toolkit (workbook) was presented. - General agreement that this version is greatly improved compared to the one presented at the 1st Steering Committee, less detailed and more policy focused. - In 8 countries receiving EC and CH/FOEN funding, BIOFIN Components 1-3 will be implemented, which will ultimately lead to the development of a (nationally-adapted) resource mobilisation strategy (based on policy and institutional and expenditure reviews, costing of financing needs/gaps and an assessment of financing mechanisms). - In 4 countries receiving DE/BMU funding, a 4th component will be added to Initiate implementation of the resource mobilisation strategy at national level. Workshops: - JE provided summaries of the regional workshops for LAC (Bogota), Africa (Kampala) and Asia (Bangkok). The best was the dedicated BIOFIN workshop in Bangkok for Asia. Secured good ownership by Ministries of Finance, and received good feedback on BIOFIN methodology. Countries even expressed interest in expanding this with more/national resources. - Countries expressed willingness to present outcomes at WGRI/SBSTTA - Plan for a suitable event at COP-12 in 2014 with country presentations - The Regional Workshops will now be followed by Regional Webinars to further advance in-country ownership, and already a 2nd LAC workshop is planned in Panama in October. Peer review of BIOFIN Workbook, Planned for August. Data: - General agreement/awareness that there are sensitive issues that must be observed/respected (national data ownership/sovereignty, also in context of CBD negotiations) - Detailed (and nationally disclosed) data will be available for the BIOFIN partners (UNDP, EC, DE, CH) but only aggregated data should be circulated further (e.g. to HL-Panel) Work Plan and Budget [YdS] - Targeted timelines haven’t changed since 1st Steering Committee, plans remain ambitious but UNDP is delivering with its own team. Expect results on Policy and Institutional and Expenditure Reviews by WGRI, results on biodiversity finance needs/gaps (costing) by WGRI or COP12, but most of the Resource Mobilisation Strategy and Synthesis Recommendations will only be developed (and implemented) after COP12. Fact Sheet: YdS committed to deliver a final version soon after the Steering Committee meeting. Concerning the Global and Regional workshops: - UNDP will discuss internally and with countries, and make a proposal integrated into the overall meetings plan BMU / GIZ and Namibia. AB reported that BMU will likely finance a bilateral project in Namibia through GIZ that has aims very similar to BIOFIN. It will develop a resource mobilisation strategy, integrate TEEB and WAVES, and have a strong target on mainstreaming; it will have more resources and time than BIOFIN. Agreement that this was a welcome synergy opportunity in a priority country, and that Namibia should be invited / involved whenever possible but as a separate and self-funded initiative. Annex 1 (in the main document): BIOFIN Global Summary Budget: |
| 18 December 2013, 11:00 - 14:00 By video conference | 3rd Steering Committee Meeting Nodes and participants: • EC (Belgium): Thierry Dudermel (TD), Arnold Jacques de Dixmude (AJD), Augustin Malou (AM), Laure Ledoux (LL), Strahil Christov (SC) • BMU (Germany): Rudolf Specht (RS) • BMU (India): Axel Benemann – partial (AB) • FOEN (Switzerland): Nathalie Rizzotti (NR) • UNDP: Yves de Soye (YdS), Jamison Ervin (JE), Onno van den Heuvel (OH), Susanne Olbrisch (SO) - Additional funding from German government (up to end of 2016) - CBD Coordination: need to keep overview of related BIOFIN and CBD activities and need for transparent reporting. It should be clear how the BIOFIN involvement is additional, avoid duplication - Increased budgets for 8 original countries – Additional funding of c. US$ 180,000 is added to implement component 4 in the 8 original countries. This restores equity amongst all pilot countries because in all the full scope of 4 components will be implemented. BIOFIN is often new/uncharted territory so it is normal that there is evolution along the way. - BIOFIN will be expanded by 6-7 countries. The final decision on countries to be included is yet to be made. BIOFIN has criteria and can share and involve the whole SC - Exchanges and discussions in 2013 with Canada and Australia were not successful. Also South Korea was not interested in financing BIOFIN. In general further resource mobilisation is not a priority at the moment considering the significant amount of available funds and focus on delivery. Recruitment: - Completion of recruitments for P3 Project Specialist and G7 Project Management Associate by September 2013. As the P5 Senior Advisor/Project Manager was not filled, YdS takes up the role of Project Manager (working on part-time basis); 2 senior environmental finance experts will be recruited as consultants to provide oversight and support to in-country implementation. Another senior consultant will be hired focusing on costing, while the Senior Advisor (Jamie E) will continue to lead the methodological work. - Agreement was reached to await the outcome of the ongoing recruitment process to discuss the staffing situation again in January. Methodology: - The peer review report is completed. The updated methodology will be completed by the first week of January and the quick guide by mid-January - Launch of NBSAP Forum and use for BIOFIN: The platform http://www.nbsapforum.net/ is live now and contains a lot of useful materials. - Regional and global NBSAP workshops with BIOFIN input: Series of 4 regional workshops planned: 10-14 February Uganda for Africa, 24-28 March Malaysia for Asia, 13-19 April in Brazil for LAC, and possibly a 4th workshop for Eastern Europe, with dates and location to be determined upon discussion with CBD on 19 Dec. Also a set of sub-regional webinars in different languages are envisaged. - Website & online platform: www.biodiversityfinance.net should be main web address and www.biodiversityfinance.org the one from where one is redirected to .net. Web developer hired to set up with general site and design (first phase); second phase: online tool to be up for the end of February; third phase: gradually expand the site. Plan to link to NBSAP Forum section on learning. - Brochure/factsheet: Being updated based on the new incoming funds. Summary of preliminary expenditures in US$ by November 2013 (excluding commitments) EC; Germany; Switzerland; Total. Staff: 128,820.44; Costa Rica: 9,928.48. Travel: 27,819.29; Travel: 3,321.17. Supplies: 87.95. Office: 1,870.75. Workshops: 33,533.24. 192,131.67; 13,249.65; 0; 205,381.32. - The reason for the limited expenses and lack of expenditures are that much of the activities have been done with current internal staff already, particularly on the methodology development. For example the Senior Advisor (Jamie E) who led the methodology was financed from other sources in 2013. Some expenses are yet to be recorded and will show under 2013 once the accounts are closed. - Financial report prepared and under clearance to be formally submitted by early January. Global BIOFIN Workshop planed on 25-27 February 2014, Bratislava |
| 10 January 2014 14:00 – 17:00 | 3rd Steering Committee Meeting n°2 Nodes and Participants: EC (Brussels/BE): Thierry Dudermel, Arnold Jacques de Dixmude, Augustin Malou, Laure Ledoux BMU (Bonn/DE): Axel Benemann FOEN (Bern/CH): Nathalie Rizzotti UNDP (SK & USA): Yves de Soye, Jamison Ervin, Onno van den Heuvel, Susanne Olbrisch, Blerina Gjeka BIOFIN Global Team: The application deadline has passed for 2 consultancy contracts (senior advisors environmental finance) including one Spanish speaker for Latin American countries. Several highly qualified candidates have applied. Agreement to wait until late January to see the final outcomes of recruitments and then revisit the need for a P5 position. BIOFIN Methodology Development and Linkage with global NBSAP work Several dozen global experts contributed to the peer review process, which generally showed a lot of consensus. A 7-page summary report is available with all feedback received. It is a learning process and the workbook will continue to evolve Global BIOFIN Workshop, 25-27 February 2014, Bratislava BIOFIN team should propose a discussion paper on the link between BIOFIN and CBD negotiations to be used and discussed at the workshop. In-Country Progress - YdS: explained Argentina’s departure from the project. The Chilean government then showed interest and sent an endorsement letter. - Most countries have completed their work plans and are recruiting their national teams. Some countries started the data collection for the workbooks. Boost missions are planned to countries experiencing bottlenecks. Inception workshop in Kazakhstan is planned for January. - UNDP and BMU screened/discussed 60 potential countries including those on original list, to select the 6-7 new countries under the 2nd BMU contribution. BMU and UNDP will re-discuss and provide more final list next week. Finance: The expenditures had increased from 192,000 US$ to over 311,000, which included activities throughout the year that were booked recently, not only activities in December 2013. WAVES/TEEB representatives will be invited to join the global BIOFIN workshop, maybe also the Costa Rica national WAVES coordinator CBD High Level Panel on Resource Mobilisation II - India Meeting • JE: participated in meeting by conference call and gave an update on BIOFIN and workbook. Key findings: 1. Importance of political will and key barriers. 2. Need to prioritize. 3. High-level report has thinking on cost-benefit analysis. 4. Shifting costs and sources of revenue, and setting good incentives. 5. Clear linkages between Aichi Targets and national/sustainable development. |
| 20 May 2014, 15:00 – 17:00 By video conference | 4th Steering Committee Meeting Nodes and participants: EC: Arnold Jacques de Dixmude (AD), Strahil Christov (SC), Susanna Von Sydow (SS) BMU (Germany): Axel Benemann (AB) FOEN (Switzerland): Gabriela Blatter (GB) UNDP Jamison Ervin (JE), Onno van den Heuvel (OH), Blerina Gjeka (BG), Marlon Flores (MF) BIOFIN Global team - The team was recently strengthened with the 2 senior advisors environmental finance, while the recruitment of the costing expert is near completion. Two interns now work with the BIOFIN team to develop a resources database. A communications expert is being recruited to support the global and national teams with all aspects of visibility and communication, including support for key events like the COP. Resource mobilisation • Seeking additional financial contributions to BIOFIN is not a priority at the moment. The main priority now is to get good results on the ground in the countries. • BIOFIN team needs to conceptualise possible ways for expansion, in time for post-WGRI/COP 12 discussions. The BIOFIN Global workshop 25-27 February 2014 The draft report was shared with the members. Five main points: (1) General acceptance and endorsement of the approach (2) Request for further support with the costing methodology. (3) Discussions on how to define boundaries of the Expenditure Review (4) Clarified the issue of data sovereignty (5) Have clearer ideas on how countries plan to position BIOFIN recommendations, which will be supported under component 4. Following these discussions it was decided to expand the scope of component 4 beyond support for specific finance mechanisms, to allow activities such as advocacy or support the development of a clear business case for biodiversity. Participation of key ministries like finance and planning which are related to process of resource allocation, need to be taking a key role in BIOFIN . Fundamental challenge is to have NBSAP financed. A sectoral approach is needed; the Resource Mobilisation Strategy needs to have sector specific activities. Some small modification to the Workbook. Other global and regional meetings Quito dialogue seminar. BIOFIN was presented quite prominently. Much discussion and quite some positive signals. Big interest of countries and negotiators help shift to more holistic approach of finance, away from north-south process. High expectation for BIOFIN to present more concrete results at WGRI and COP. Connection with WAVES on environmental accounting and BIOFIN expenditure review, where WAVES can provide important baseline data. BIOFIN and WAVES overlap in few countries. WAVES has more focus on incorporating things into accounting standards Plans for WGRI/COP 12 BIOFIN will organise a side event for both meetings. For WGRI 5 an information note on BIOFIN will be prepared in advance, to be published on the CBD website. Caroline will be on a panel on Resource Mobilisation and Yves will lead the BIOFIN side event. Country updates - The 7 new countries are progressing well and endorsement letters were received from several governments, some are already developing the workplan (Colombia) and recruiting staff. In India a biodiversity expenditure review has been carried out rather than actual expenditures) and government requested to review what would be the added value of the BIOFIN process. The team reviewed the work already done which is documented in the 5th national report, and found BIOFIN activities complementary to the existing work, which did not cover expenditures per se but rather budgets, and did not include private sector expenditures. In Mexico first meetings with government organisations were organised. - The 12 original countries are at varied stages of progress, with interesting activities emerging in many countries. In Peru the BIOFIN team was requested by the government to help develop a guideline for programming biodiversity related activities at the local level. Inception workshops took place in Philippines, Kazakhstan and Seychelles recently. In the Philippines a review was carried out with stakeholders which finance mechanisms need further support, with a lot of interest for improving implementation/enforcement of existing mechanisms. In Malaysia inputs are given into the national development plan. - Each country needs to define linkages with the NBSAP process Many NBSAPs are at a very advanced stage. Only for Colombia it was submitted to the CBD and others, for example the Seychelles, Philippines and Ecuador have almost finalized it. Several countries, such as the Seychelles, are reviewing whether they should update their NBSAP or not based on the BIOFIN inputs. Several countries have completed their 5th national biodiversity reports. This includes India, Uganda, South Africa, Cost Rica, Ecuador, Malaysia and Colombia, and here a lot of the baseline information for the BIOFIN work is already available - Recent mission to Ecuador, had many discussions with government organisations, including the Ministry of Finance, the National Secretariat for Planning and Development and the Environment Ministry. The team is reviewing which sectors they should focus on during the BIOFIN work in order to show concrete results. The website is now online, The Workbook will also be available online |
| 28 August 2014, 15:00 – 17:00 By video conference | 5th Steering Committee Meeting Nodes with tentative participants (TBC): EC: Arnold Jacques de Dixmude, Strahil Christov BMU (Germany): Axel Benemann FOEN (Switzerland): Gabriela Blatter UNDP Caroline Petersen, Yves de Soye, Jamison Ervin, Onno van den Heuvel, Blerina Gjeka Global Team - The team has grown further in recent months. The costing expert and communication experts are on board with good track records. An intern starts next week. BIOFIN Costa Rica Lead Expert Guillermo Zuniga expands his role with additional global tasks, providing technical and political support. Currently discussing further staffing evolution linked to the budget revision process. BIOFIN Methodology - A new Excel workbook spreadsheet for data entry was developed to accompany the workbook. A common taxonomy was adopted for different sections In-country progress snapshot - Now see even more clearly than before different levels of progress amongst BIOFIN countries. There are different types of institutional/capacity/personal barriers that have caused delays in a group of countries, most notably South Africa, Uganda and India. For some, problems are related to the inception period when different expectations may have been created of working mainly through ministries of environment. Out of the remaining countries that joined BIOFIN this year, Colombia and Guatemala are the most advanced and already recruiting national team members. Thailand and Mexico are also moving on, despite some delays in Thailand due to the political situation. Teams are at least partly in place and assessments started in Botswana and Chile. Kazakhstan, Seychelles, Indonesia, Malaysia, Ecuador and Peru are at an advanced stage with workbook 1 and the overall process. Costa Rica and the Philippines have made the most visible progress. Interesting examples include the Philippines, the first country to have a draft costing work, Cost Rica where the institutional and policy review is known to be very thorough and breaking new. Global and Regional events - WGRI 5 – BIOFIN was well positioned within the main discourse and recommendations, which suggested BIOFIN should be scaled up further. - HLP – The latest HLP report has partly moved away from the earlier use of more rudimentary calculations to arrive at the finance gap. - CBD Biodiversity Finance Workshop Ittingen - BIOFIN most visible of all initiatives. Positive about BIOFIN presence. There was no participant who did not know what BIOFIN was. Impact on negotiations is high. Resource Mobilisation Workshops with CBD - BIOFIN was primary content of the workshops with over 100 participants from 4 regions. Objective was mainly to familiarise countries with BIOFIN thinking. Pleased to see how well workshops were received. Appreciated BIOFIN countries lead and explain approach. COP 12 Planning/side event BIOFIN future developments - Budget revision: Budget revision is ongoing. Staffing will be expanded in line with available finances. - Geographical Expansion: New strategy is to aim for an expansion enabling up to 40 countries in total. For the moment keep consolidating results and prepare to mobilise further resources after the COP. Some interest was expressed by countries including the Belgium Government who solicited a proposal for US$ 40,000. Others also expressed tentative interest. - Upcoming activities: Second global BIOFIN workshop late 2015? Planning Regional Workshops, 3 per year in each region costing around US$ 30,000 each. |
| 29 January 2015, 15:00 – 17:00 (CET) By video conference | 6th Steering Committee Meeting Nodes with participants: EC: Arnold Jacques de Dixmude, Strahil Christov Germany (BMU): Axel Benemann Switzerland (FOEN): Gabriela Blatter Norway (MFA): Inger Holten Flanders (LNE): Els van de Velde UNDP: Yves de Soye, Jamison Ervin, Onno van den Heuvel - Status of the BIOFIN Team - New status of the core team. The project is led by BIOFIN Manager and Regional Technical Advisor Yves de Soye. The management team further consists of Project Specialist Onno van den Heuvel (programme management) and Project Management Associate Blerina Gjeka (finance/administration). Jamison Ervin is the lead senior advisor on the development of the methodology, with 2 senior advisors, Marlon Flores and David Meyers, guiding national implementation. Communications Expert Matthew Taylor came on board in August and led the media impact campaign around COP 12, including of UNDP Administrator Helen Clark speaking on BIOFIN as a key UNDP flagship initiative (with references to donors) during the HL Segment opening and a subsequent press event. As he was offered a position at the UNDP HQ a new communications advisor is being recruited, shared with the NBSAP Forum. The Costing Expert was hired in August 2014 but did not produce the agreed deliverables and has left. The replacement will be integrated as a 3rd Senior Advisor, providing in-country support and global expertise. 5 such Advisors are planned in order to cover the now 29 countries in the portfolio. As part of UNDP’s global re-organisation an environment finance team was set up under the new sustainable development cluster, led by Nik Sekhran, in the Bureau for Programming and Policy Support, including an environmental finance expert and an environmental economist who are tasked with contributing to the work of BIOFIN, thus enriching the team further. Two new interns are expected to start in March/April. New members will be brought on board in the coming months as a result of the recent additional funding. The team is set to expand further should additional funds be added. - Quick reflections on CBD COP 12 - COP resolutions related to BIOFIN - Side-Event on Transformative Initiatives - The COP 12 gave BIOFIN very good visibility in several ways: 1) In the discussion on resource mobilisation, with recognition by many parties, and references to BIOFIN in the COP decision on Resource Mobilisation (UNEP/CBD/COP/12/L.32), most importantly a call for further upscaling and naming BIOFIN as a provider of leading methodological guidance on resource mobilisation 2) At the side event on transformative initiatives organised with World Bank, UNEP, OECD and others – leading the various initiatives to conclude they should work together more closely. 3) At a number of high-profile events at which UNDP Administrator Helen Clark spoke, highlighting the central importance BIOFIN - including a Special Side Event on Biodiversity and the Sustainable Development Goals, the Official Opening of the High Level Segment of the COP, and a press conference, on which the team has developed videos for the BIOFIN channel on YouTube. - The timing coinciding with the high level segment and related negotiations caused many to miss out. This is an important lesson for future events, where BIOFIN could look into different timings for side events. - Update on new funding and activities - New donors and income and key objectives - New core country candidates - New timelines - CBD/BIOFIN collaboration - Three new funding contributions were received in December 2014, bringing the total funding volume for BIOFIN to over 28 Million US$, adding new activities and expanding the overall timeline into 2018: - The German Ministry of Environment, Nature Conservation, Building and Nuclear Safety (10 Million EUR/12.5 Million US$) Activities: A further 9 countries will be included and discussions on the proposed countries are now ongoing. Existing countries will receive additional funds for component 4 (tentative $80,000). It will allow more solid investment into regional nodes; regional workshops and a global workshop in 2018 will be added. Work on knowledge management and M&E will be intensified, by adding an expert to the team, with a primary focus on developing high-quality KM products and monitoring impact. More senior advisors (to reach a total of 5) are to be hired to accommodate the growth and prepare for any further expansion. Together with the CBD one global workshop on PER and costing methodologies in April and regional workshops later in the year are to be organised in 2015 (CBD-funded). For the regional nodes the new plan is to work through regional/national organisations as implementing partners, in order to increase sustainability and accountability of the process and build their capacity. - The Norwegian Ministry of Foreign Affairs (5.1 Million NKR/701,889 US$) Activities: One additional country will be added (to be decided) to implement the full range of activities, with a proportionate contribution to the global team and activities. - The Government of Flanders (115,00 EUR/135,294 US$) Activities: Focusing on regional nodes supporting countries in Southern Africa, with the exact scope to be identified (discussions are ongoing). - Need to review the rationale for national budget levels. It is not clear why larger countries such as Mexico and South-Africa have the same budget as for example the Seychelles. The BIOFIN team will look at the national budget levels for the new countries and consider introducing a more flexible new formula, such as having 3 or more levels. - There was also good visibility for BIOFIN at the Climate Change COP in Peru, where BIOFIN was mentioned. - On the proposed no-cost extension: all deliverables of the relevant countries financed by the Commission must be fully completed within the new timelines under the Commission contract. Country Implementation - Overall there is good progress and some interesting approaches and results are emerging. There are now distinct levels of progress between countries that have completed their first deliverables and a few countries that had a very long inception phase, in particular South-Africa and Uganda, even though national teams are now emerging there and the SA lead expert has been hired. Most of the original 12 countries have by now produced their first technical materials, under review by national experts/governments. The first institutional and policy reviews have been very thorough (e.g. Philippines and Costa Rica), mapping the links to biodiversity of a wide range of policies, laws and institutes. In some countries very interesting specific approaches are developed, an example being Ecuador where the private sector expenditure review is done for 4 selected economic sectors. From the 7 countries starting in 2014, Guatemala has progressed the most, with the first assessment already being drafted. All 19 countries are now fully on board with governments having formally endorsed their participation. A more extended implementation package is being developed for countries joining newly, based on lessons learned of the past 2 years. - Some of the main challenges encountered include capacity challenges with many countries not having been able to hire all team members. The global team is working with these countries to find solutions by adjusting the team profiles. In some countries the NBSAP process is delayed, although this also provides an opportunity for more interaction with the process. Countries have increasingly started to use the peer review system of the NBSAP forum, helping them to strengthen their NBSAP (e.g. Seychelles, Kazakhstan). In some countries the NBSAPs have shown to have a limited scope and may not be a suitable framework for calculating the national finance gap. - BIOFIN retreat and next developments for BIOFIN - The retreat took place in January 2015 with the dual purpose to review challenges of in-country implementation and planning for 2015 and beyond. For the new countries we will undertake inception missions to start interacting directly from the start with national counterparts and support them with an updated and expanded inception package. More Senior Advisors supporting national implementation will be hired to strengthen support and accommodate growth to 29 core countries (one is already selected and due to start soon, and another two are planned). For the methodological framework additional guiding materials will be developed to further outline specific steps in the implementation of studies and strategies to be carried out under the workbook. - Discussions were held at the retreat on the future direction of BIOFIN, concluding we will aim to support a maximum of 60 core countries by 2020. It was also proposed that in parallel to the existing stream of work built around the BIOFIN workbook, a second workstream will be developed on resource mobilisation to implement the action points of developed resource mobilisation strategies, expanding the current work done under component 4. - The idea for 3-5 regional nodes/non-core countries is to establish a support programme taking off with an online training programme and by working with existing organisations rather than individuals. Non-core countries can then evolve to either: graduate into a BIOFIN core country (for example with UNDP-BIOFIN donor resources); implement BIOFIN with domestic resources; or implement BIOFIN with other partners/donors such as GIZ, CI, TNC. - The CBD/BIOFIN global workshop on methodologies will probably be held in April in Istanbul or Mexico. The Mexico CBD COP-13 organising team approached the BIOFIN team to meet Lichtinger and discuss the role of BIOFIN at the COP. The global team will undertake a mission to Mexico soon. - Several rounds of discussions with UNSD showed their work on SEEA-EEA / NCA is more complementary to BIOFIN with limited points for actual integration of programmes. |

# ANNEX 8: BIOFIN CHRONOLOGY OF ACTIVITIES

HISTORICAL CHRONOLOGY OF THE INITIATIVE ACTIVITIES

| DATES | ACTIVITIES AND EVENTS |
| --- | --- |

| The project “The Biodiversity Finance Initiative - BIOFIN” (2013-2016) |  |
| --- | --- |
| 2010 – Idea |  |
| October | CBD COP 10 in Japan - European Commission DGENV proposes project opportunity to UNDP for 1 m EUR |
| 2011 – Proposal preparation and submission |  |
|  | Proposal prepared and submitted (Nik S, Yves dS and Alice Ruhweza), adjusted to 4m EUR / 8 countries under DEVCO |
| 2012 |  |
| Jan-Oct | Final negotiations on UNDP-EC contract, contract signature in October. |
| Feb | BIOFIN introduced at 1st Quito Seminar on Resource Mobilisation |
| Oct | Project launch at a CBD COP11 side event in India in October. |
| Nov | 1st internal methodology workshop in Nov 2012. |
| Dec | Germany joins as 2nd partner/donor w 2.3m EUR + 4 new countries and additional funding for original 8 |
| Dec | CH joins as 3rd partner/donor w 300K CHF, taking over most funding for Kazakhstan |
| 2013 |  |
|  | 2nd internal methodology workshop in Feb 2013. |
| 07 March | 1st Steering Committee Meeting with EC, Germany, Switzerland, UNDP Brussels and Yves de Soye. The meeting helped to clear the linkages between the NBSAP Forum and BIOFIN. The SC meeting also allowed to review the scope of the initiative and the methodology. The review of the methodology concluded that the methodology was too complicated/academic and should be simplified to be more realistic and applicable. For example, Res Mob - need to identify what financing mechanisms are feasible in reality (considering policy envt, capacity, etc.); i.e. not a full wish list catalogue. Pilot countries will be fully involved and consulted during the development of the methodology. It was agreed that BIOFIN should have some result focusing on the CBD deadline and COP 2014 however, without rushing the project because BIOFIN needs to prioritize quality. The project should 1. provide more national engagement opportunity and time incl. through workshops, committees, etc. 2. ensure national ownership (i.e. should not be perceived as an external intervention) 3. leave an enhanced capacity legacy. BIOFIN should also look at other non EU donors. |
|  | The first draft of the BIOFIN workbook was developed and peer reviewed. It consisted of 3 steps, a policy and expenditure analysis, costing of national finance needs for biodiversity and developing a resource mobilisation plan. |
|  | Outreach to 12 selected BIOFIN countries. EC: Argentina, Ecuador, Kazakhstan, Malaysia, Philippines, Seychelles, South Africa and Uganda; GER: Botswana, Costa Rica, , Indonesia, Peru,. |
| April | Presentation to EU Expert Group on BD and Development |
| 10th July | 2nd Steering Committee Meeting with EC, BMUB, FOEN, UNDP Brussel, Nik Sekhran, Jamison Ervin, Susanne Olbrisch. The NBSAP forum is separated from BIOFIN but there will be important synergies. Recruitments of the Global BIOFIN team advanced (P5,P3,G7 + Yves de Soye) and Jamison Ervin will be under contract throughout the project, and will assume the hybrid BIOFIN-NBSAP Forum role. Susanne Olbrisch onboard as technical and administrative support consultant until end 2013. HLP hoped that BIOFIN would contribute country data, but we must be very cautious and cannot give out data that countries may consider confidential. The current version of the emerging methodology toolkit (workbook) was presented. General agreement that this version is greatly improved compared to the one presented at the 1st Steering Committee, less detailed and more policy focused. In 8 countries receiving EC and CH/FOEN funding, BIOFIN Components 1-3 will be implemented. In 4 countries receiving DE/BMU funding, a 4th component will be added to Initiate implementation of the resource mobilisation strategy at national level. Summaries of the regional workshops for LAC (Bogota), Africa (Kampala) and Asia (Bangkok). Secured good ownership by Ministries of Finance, and received good feedback on BIOFIN methodology. Countries even expressed interest in expanding this with more/national resources. Plan for a suitable event at COP-12 in 2014 with country presentations. Detailed data will be available for the BIOFIN partners (UNDP, EC, DE, CH) but only aggregated data should be circulated further. Work Plan and Budget Targeted timelines haven’t changed since 1st Steering Committee, plans remain ambitious but UNDP is delivering with its own team. Expect results on Policy and Institutional and Expenditure Reviews by WGRI, results on biodiversity finance needs/gaps (costing) by WGRI or COP12, but most of the Resource Mobilisation Strategy and Synthesis Recommendations will only be developed (and implemented) after COP12. Concerning the schedule for Global and Regional workshop a plan will be made by UNDP. Namibia begins a similar project through GIZ with more resources and time, communication between the country are welcome. (Annex 1 BIOFIN Global Summary Budget) |
| September 2013 | Recruitment of the BIOFIN global core team: P3 Project Officer (OvdH) and G7 Project Management Associate (BG); P5 Project Manager - recruitment not followed through due to UNDP realignment exercise, YdS assumes role on part time basis. |
| Dec | Germany adds a further 5m EUR + 7 new countries to join in 2014 (Colombia, Fiji, Guatemala, India, Mexico, Thailand and Zambia). |
| 18 December | 3rd Steering Committee Meeting with EC, BMU, FOEN, Yves de Soye, Jamison Ervin, Onno van den Heuvel, Susanne Olbrisch. Additional funds from German Governement, 7 new countries to join in 2014. Increased budget for 8 original countries to implement component 4. Completion of recruitments for P3 Project Specialist (Onno van den Heuvel) and G7 Project Management Associate (Blerina Gjeka). As the P5 Senior Advisor/Project Manager was not filled, YdS takes up the role of Project Manager (working on part-time basis); 2 senior environmental finance experts will be recruited as consultants to provide oversight and support to in-country implementation. Another senior consultant will be hired focusing on costing, while the Senior Advisor (Jamie E) will continue to lead the methodological work. The peer review report for the Workbook is completed. The updated methodology will be completed by the first week of January. The platform http://www.nbsapforum.net/ is live. Regional and global NBSAP workshops with BIOFIN input: Series of 4 regional workshops planned: 10-14 February Uganda for Africa, 24-28 March Malaysia for Asia, 13-19 April in Brazil for LAC, and possibly a 4th workshop for Eastern Europe, with dates and location to be determined upon discussion with CBD on 19 Dec. Web developer hired to set up with general site and design www.biodiversityfinance.net. Global BIOFIN Workshop planed on 25-27 February 2014, Bratislava. |
| 2014 |  |
| 10th January | 3rd Steering Committee Meeting n°2 with EC, BMU, FOEN, Yves de Soye, Jamison Ervin, Onno van den Heuvel, Susanne Olbrisch, Blerina Gjeka. The hiring process is going on and the application deadline has passed for 2 consultancy contracts (senior advisors environmental finance) including one Spanish speaker for Latin American countries. Several highly qualified candidates have applied. Agreement to wait until late January to see the final outcomes of recruitments and then revisit the need for a P5 position. Several dozen global experts contributed to the peer review process for the Workbook, which generally showed a lot of consensus. It is a learning process and the workbook will continue to evolve. Global BIOFIN Workshop planned for 25-27 February 2014, Bratislava. Explanation of Argentina’s departure from the project. The Chilean government then showed interest and sent an endorsement letter. Most countries have completed their work plans and are recruiting their national teams. Some countries started the data collection for the workbooks. Boost missions are planned to countries experiencing bottlenecks. Inception workshop in Kazakhstan is planned for January. UNDP and BMU screened/discussed 60 potential countries including those on original list, to select the 6-7 new countries under the 2nd BMU contribution. |
| Feb | The 1st Global BIOFIN workshop brought together over 100 participants from BIOFIN countries, donors and related initiatives to learn about and discuss the draft BIOFIN approach and draft methodology. |
| Feb | BIOFIN very prominent at 2nd Quito Seminar on Resource Mobilisation |
| Feb | BIOFIN prominently mentioned in the report of CBD High Level Panel on Res Mobilisation for the CBD Strategic Plan |
| 20th May | 4th Steering Committee Meeting with EC, BMU, FOEN, Jamison Ervin, Onno van den Heuvel, Blerina Gjeka, Marlon Flores. The team was recently strengthened with the 2 senior advisors environmental finance, while the recruitment of the costing expert is near completion. Two interns now work with the BIOFIN team to develop a resources database. A communications expert is being recruited to support the global and national teams with all aspects of visibility and communication, including support for key events like the COP. Seeking additional financial contributions to BIOFIN is not a priority at the moment. The main priority now is to get good results on the ground in the countries. The draft report was shared with the members on the BIOFIN Global workshop 25-27 February 2014. Five main points: (1) General acceptance and endorsement of the approach (2) Request for further support with the costing methodology. (3) Discussions on how to define boundaries of the Expenditure Review (4) Clarified the issue of data sovereignty (5) Have clearer ideas on how countries plan to position BIOFIN recommendations, which will be supported under component 4. Following these discussions it was decided to expand the scope of component 4 beyond support for specific finance mechanisms, to allow activities such as advocacy or support the development of a clear business case for biodiversity. BIOFIN was presented quite prominently at Quito dialogue seminar. Big interest of countries and negotiators help shift to more holistic approach of finance, away from north-south process. High expectation for BIOFIN to present more concrete results at WGRI and COP. Connection with WAVES on environmental accounting and BIOFIN expenditure review. BIOFIN will organise a side event for both meetings WGRI and COP 12. Country updates: The 7 new countries are progressing well and endorsement letters were received from several governments, some are already developing the workplan (Colombia) and recruiting staff. The 12 original countries are at varied stages of progress, with interesting activities emerging in many countries. The website is now online, the Workbook will also be available online |
| June | BIOFIN prominent at CBD WGRI 5 in Montreal |
| July | BIOFIN prominent at CBD COP Prep Workshop in Switzerland |
|  | The BIOFIN Website was created: www.biodiversityfinance.net. |
|  | BIOFIN Twitter, Facebook and Youtube were launched. |
|  | Global team adds 2 STAs to provide implementation support to 19 countries |
|  | The first national BIOFIN teams established and national activities are started |
|  | BIOFIN methodology/workbook is further consolidated into a user-friendly October 2014 version |
|  | At CBD COP 12 the new Workbook version is released, and a major day-long side event on Transformative Initiatives is led by UNDP. COP decisions in South Korea make reference to the value of BIOFIN and request upscaling |
| 28th August | 5th Steering Committee Meeting with EC, BMU, FOEN, Caroline Petersen, Yves de Soye, Jamison Ervin, Onno van den Heuvel, Blerina Gjeka. The team has grown further in recent months. The costing expert and communication experts are on board with good track records. An intern starts next week. BIOFIN Costa Rica Lead Expert Guillermo Zuniga expands his role with additional global tasks, providing technical and political support. Discussing further staffing evolution linked to the budget revision process. A new Excel workbook spreadsheet for data entry was developed to accompany the workbook. A common taxonomy was adopted for different sections. • Now see even more clearly than before different levels of progress amongst BIOFIN countries. There are different types of institutional/capacity/personal barriers that have caused delays in a group of countries, most notably South Africa, Uganda and India. Out of the remaining countries that joined BIOFIN this year, Colombia and Guatemala are the most advanced and already recruiting national team members. Thailand and Mexico are also moving on. Teams are at least partly in place and assessments started in Botswana and Chile. Kazakhstan, Seychelles, Indonesia, Malaysia, Ecuador and Peru are at an advanced stage with workbook 1 and the overall process. Costa Rica and the Philippines have made the most visible progress. BIOFIN well represented at WRGI 5, HLP, CBD Biodiversity Finance Workshop Ittingen, Resource Mobilisation Workshops with CBD. Planning COP12 side event. Budget revision ongoing and staffing will expand in function of available Finance. Proposition from Belgium of US$ 40 000. There will be 3 regional workshops per year. |
| Dec | Germany adds a further 10m EUR + 10 new countries to join in 2015 (Rwanda, Mozambique, Mongolia, Vietnam, Georgia, Bhutan, Sri Lanka, Belize, Brazil, Cuba). |
| Dec | Flanders joins as 4th partner/donor w 115K EUR for global work |
| 2015 |  |
| Jan | OvdH promoted to Deputy Manager |
| 29th January | 6th Steering Committee Meeting with EC, BMU, FOEN, MFA, LNE, Yves de Soye, Jamison Ervin, Onno van den Heuvel. New status of the core team. The project is led by BIOFIN Manager and Regional Technical Advisor Yves de Soye. The management team further consists of Project Specialist Onno van den Heuvel (programme management) and Project Management Associate Blerina Gjeka (finance/administration). Jamison Ervin is the lead senior advisor on the development of the methodology, with 2 senior advisors, Marlon Flores and David Meyers, guiding national implementation. Communications Expert Matthew Taylor came on board. The replacement of the costing expert will be integrated as a 3rd Senior Advisor, providing in-country support and global expertise. 5 such Advisors are planned in order to cover the now 29 countries in the portfolio. As part of UNDP’s global re-organisation an environment finance team was set up under the new sustainable development cluster, led by Nik Sekhran, in the Bureau for Programming and Policy Support, including an environmental finance expert and an environmental economist who are tasked with contributing to the work of BIOFIN, thus enriching the team further. Two new interns are expected to start in March/April. New members will be brought on board in the coming months as a result of the recent additional funding. The team is set to expand further should additional funds be added. The COP 12 gave BIOFIN very good visibility. There was also good visibility for BIOFIN at the Climate Change COP. Three new funding contributions were received in December 2014, bringing the total funding volume for BIOFIN to over 28 Million US$, adding new activities and expanding the overall timeline into 2018: - The German Ministry of Environment, Nature Conservation, Building and Nuclear Safety (10 Million EUR/12.5 Million US$) - The Norwegian Ministry of Foreign Affairs (5.1 Million NKR/701,889 US$) - The Government of Flanders (115,00 EUR/135,294 US$) The BIOFIN team will look at the national budget levels for the new countries and consider introducing a more flexible new formula, such as having 3 or more levels of budget. Most of the original 12 countries have by now produced their first technical materials, under review by national experts/governments. From the 7 countries starting in 2014, Guatemala has progressed the most, with the first assessment already being drafted. All 19 countries are now fully on board with governments having formally endorsed their participation. A more extended implementation package is being developed for countries joining newly, based on lessons learned of the past 2 years. A BIOFIN global team retreat took place in January 2015 with the dual purpose to review challenges of in-country implementation and planning for 2015 and beyond. The idea for 3-5 regional nodes/non-core countries is to establish a support programme taking off with an online training programme and by working with existing organisations rather than individuals. Several rounds of discussions with UNSD showed their work on SEEA-EEA / NCA is more complementary to BIOFIN with limited points for actual integration of programmes. |
| 3 - 5 March | Regional BIOFIN Workshop, Kuala Lumpur, Malaysia. Representatives from Ministries of Finance and Environment, National BIOFIN teams and UNDP offices, learned about the BIOFIN methodology and shared feedback of their learning. |
| 24 - 26 March | Regional BIOFIN Workshop, Quito, Ecuador. Representatives from Ministries of Finance and Environment, National BIOFIN teams and UNDP offices, learned about the BIOFIN methodology and shared feedback of their learning. |
| May 2015 | The BIOFIN-supported international Convention on Biological Diversity –CBDtechnical expert workshop reviewed approaches used globally to track and measure biodiversity expenditures. |
| 3 - 5 June | Regional BIOFIN Workshop, Gaborone, Botswana. Representatives from Ministries of Finance and Environment, National BIOFIN teams and UNDP offices, learned about the BIOFIN methodology and shared feedback of their learning. |
| 7 October | 7th Steering Committee Meeting with EC, BMU, FOEN, MFA, LNE, Yves de Soye, Jamison Ervin, Onno van den Heuvel, Diego Ochoa, Blerina Gjeka. Looking back at the 6th meeting, Onno van den Heuvel, BIOFIN Deputy Manager, responded to the recommendation to develop more than 2 budget levels for countries, depending on their size and national needs. From January 2016 a new Project Associate (PA) based in Istanbul will be added. Due to the increased number of countries and apparent national capacity constraints, three additional Senior Advisors were hired in the last months: Andrew Seidl (USA, offering a wide experience as economics advisor for IUCN, UNEP-TEEB, WWF Australia etc);. Annabelle Trinidad (Philippines, former BIOFIN Lead in Philippines); and Ms. Fabiana Issler (Brazil, Denmark; currently a Regional Technical Advisor with UNDP-GEF in Africa, starting January 2016). The Communications Specialist Mr. Diego Ochoa was hired. The process of procuring the support of an M&E and KM expert is now complete. Three Regional workshops were organized between March and June 2015. The objectives were to introduce BIOFIN to new countries; experience sharing; documenting best practices and lessons learned; discuss progress in implementation, provide technical guidance, etc. The workshops generated a lot of feedback on the methodology CBD-BIOFIN Global Experts workshop in Mexico City, 5-7 May 2015, at the request of the CBD Secretariat, BIOFIN supported with preparatory work and active participation by global and national BIOFIN teams. On June 2015 UNSD SEEA workshop and the Global BIOFIN Team meeting to work on next Workbook. 10 More countries are added to the BIOFIN family; Belize, Bhutan, Brazil, Cuba, Georgia, Mongolia, Mozambique, Rwanda, Sri Lanka and Vietnam. Discussion on the Regional Nodes and the final decision is to hire individual contractors/national in Istanbul, Bangkok and Panama. The EU contribution has been extended (at no additional costs) until the end of 2016. There will be three missions by Deutsche Welle to three BIOFIN countries: Seychelles, Philippines and Costa Rica. The BIOFIN Global workshop will be held in Mexico, from 12-14 April 2016 |
| Dec | CH adds a further 600K CHF + 1 new country to join in 2016 (Kyrgyzstan). |
|  | 2 new STAS join the team, KM/M&E and Comms expert |
| 2016 |  |
| Jan | 1 new STA joins the team for 6 months, and a 2nd Management Associate |
| Jan | YdS resigns from BIOFIN |
| Jan | New BIOFIN Manager recruitment launched, fails in mid-2016, after which Onno becomes the new Manager |
| 26-28 January | 2nd Regional BIOFIN Workshop for Latin-America and the Caribbean in Chile |
| Early 2016 | Two more regional BIOFIN workshops were used to further discuss the emerging new version of the methodology, while enabling countries in-depth sharing of lessons learnt. |
| 2-4 March | 2nd Regional BIOFIN Workshop for Asia-Pacific, Indonesia |
| 12-14 April | The 2nd BIOFIN Global workshop in Mexico is the largest event organised by BIOFIN to date with over 175 participants from 30 BIOFIN countries, partner organisations and UNDP teams around the and with over 25 high-level participants (eg the Ministers of Environment from Mexico and Guatemala). Highlights included discussions about how to guide countries to ensure finance solutions such as green bonds, impact investment and climate finance have an actual impact on biodiversity. One of the strongest comments from the meeting was the need to expand the focus on the private sector. |
| April 2016 | BIOFIN finds a new partner with the UNDP BESnet platform and helped develop a module on biodiversity finance. The BESnet platform is implemented through partnerships with the Norwegian Environment Agency, SwedBio at the Stockholm Resilience Centre, and Germany's Federal Ministry for the Environment, Nature Conservation, Building and Nuclear Safety (BMUB). In addition, through BES-Net, UNDP contributes to the capacity building work of the Intergovernmental Platform for Biodiversity and Ecosystem Services (IPBES). |
| May 2016 | BIOFIN organised a side event during CBD’s SBI. BIOFIN was well represented and praised during the meeting. |
| May 2016 | BIOFIN began a series of webinar on biodiversity finance solutions after the important demand during the 2nd Global Workshop. As of today 7 webinars in total have been done including Green bonds, protected area budgeting and biodiversity offsets. Others on reforming subsidies, philanthropy, payment for ecosystem services will soon follow. |
| May 2016 – September 2016 | BIOFIN made a series of webinars on the new methodology development in order to receive national team’s comments and write the 2016 BIOFIN Workbook. |
| May 2016 | Seychelles held a workshop on sustainable tourism. The Ministry of Finance explained that private sector could use up to half of the Corporate Social Responsibility (CSR) Tax to fund their biodiversity programmes by using an NGO to execute such programme. |
| 20th June | 8th Steering Committee Meeting with EC, BMU, FOEN, MFA, Onno van den Heuvel, Jamison Ervin, Blerina Gjeka, Marco Arlaud, Oscar Huertas, David Meyers, Massimiliano Riva. New members for EC and BMU. The team now includes a full set of (5) Senior Technical Advisors and a second Project Management Associate based in Istanbul. The hiring process for the BIOFIN Manager is still ongoing and Onno van den Heuvel has fulfilled this role since February. Experts on communications and K&M/M&E are on board as well. A Junior international consultant in Environmental Finance have been hired to help the project management and the technical team. The resource person for the regional node supporting Africa and Central Asia were also hired. The global BIOFIN Workshop held in Los Cabos, Mexico (12 - 14 April 2016) was the largest event organized by BIOFIN to date (over 175 participants). The workshop included over 25 high level participants (including the Minister of Environment of Mexico, the UNDP Global Director for Sustainable Development, the Vice Minister of Finance from the Philippines, etc.). The donors congratulated the team for the good work on this workshop. 2016 regional workshops took place in Chile and Indonesia while the Africa Regional Workshop is postponed to October 2016 upon request of the countries. BIOFIN engages with the CBD in various ways. One important link is between the CBD financial reporting and data produced from BIOFIN assessments. The first SBI meeting of the CBD (May 2016) included participation from the BIOFIN Manager and BIOFIN Mexico, Seychelles and Indonesia. During the plenary sessions, many governments expressed their appreciation for the BOIFN process. One or more side events are planned for the COP 13 in Mexico in December 2016. In the coming months the, BIOFIN team will start developing the concept note for BIOFIN phase 2 and increase the attention for resource mobilization. The importance of a follow up phase is high, in particular considering the strong momentum present at both the global level and in countries, where the BIOFIN process has seen promising first results. Both expanding and deepening could make sense by paying due attention to building national capacity. The positive momentum at the global level was demonstrated by the high level attention for BIOFIN in many recent meetings, including the GEF Council, SBI, the ASEAN biodiversity meeting and others. BIOFIN received many formal and informal requests from countries to join the initiative (Zimbabwe, South Soudan, Myanmar, etc.). The current support to the non-core BIOFIN countries is part of the Terms of Reference of the Regional Nodes. Concerning the new possible funds for BIOFIN, Canada is a country to approach, as they expressed strong interest in in BOFIN during the SBI. Methodology: BIOFIN tested the methodology and improved it based on the lesson learnt. The global BIOFIN team is now producing technical PowerPoints going into details of the methodology and those can be easily modified in function of the feedback from the countries. The global team plans to finalise the full workbook by the next COP in December. BIOFIN discussed with UNCEEA to see the compatibility with the BERs. Work has started in the majority of the new 11 countries which joined BIOFIN last year. The current 19 counties which joined earlier are producing interesting and real results and countries which were behind earlier are now progressing quickly, such as South Africa and Uganda. |
| June 2016 | In Peru the Ministry of Economy and Finance officially approved a new version of the General Guidelines for Public Investment Projects, incorporating a focus on sustainability and highlighting the importance of investing in ecosystem services. BIOFIN supported the dialogue between the Ministry of Economy and the Ministry of Environment, and provided technical assistance. (link) |
|  | In Guatemala, the national team completed the PIR, BER, FNA and BFP and is now working on the implementation of different finance solutions such as the creation of a tax on port activities, permits of fishing to protect sailfish activities and the implementation of laws allowing to earmark a certain percentage of taxes to the institution in charge of the protected areas the CONAP. |
| August 2016 | In Guatemala, a Workshop was organised to present the results from the BIOFIN initiative. A high level panel including the Vice Minister of Finance, the Secretary to Plan, the Minister of Environment and the UNDP Resident Representative participated to the event. The Vice Minister of Finance of Guatemala during an interview made by BIOFIN highlighted his support and the importance of BIOFIN in the country. |
|  | The national BIOFIN Team in Costa Rica, led by former Minister of Finance Mr Guillermo Zuñiga, engaged with a variety of stakeholders, collaborating with the Chamber of Banks and Financial Institutions, the Chamber of Industries and the Costa Rican Union of Chambers of Private Enterprise to collect private sector biodiversity expenditure data. BIOFIN is now requested to support the development of a range of finance solutions. |
|  | South Africa completed their policy analysis and assessed expenditures in private protected areas, using links between SDGs to mainstream biodiversity with the different stakeholders. |
|  | BIOFIN in Bhutan is integrated into a broader initiative to develop finance solutions for three SDGs, related to poverty, climate change and biodiversity. Dasho lam dorji, former secretary of Finance, is now the national BIOFIN team leader (link). |
|  | BIOFIN in India is largely driven by government, working primarily through two technical agencies, The Wildlife Institute of India and the National Institute of Public Finance and Policy. Activities are also undertaken at the state level. They are working on an improved framework for allocating Corporate Social Responsibility (CSR) payments to biodiversity objectives. |
|  | BIOFIN studies in Philippines, suggest a significant finance gap, remains for the country to be able to fully fund its NBSAP. The team is now working on a variety of finance solutions, including a national fund from oil and gas revenues, local government funding and a marketplace to match biodiversity investors with projects, in order to help filling this gap. |
|  | In Chile, the draft expenditure review indicates the proportion of biodiversity expenditures as a share of total government expenditures grew from 0.11 to 0.16% between 2010 and 2014, indicating an upward trend. |
| September 2016 | BIOFIN presented at several sessions during the IUCN World Conservation Congress |
| October 2016 | The 2nd Regional Workshop for the African countries in Zambia had dedicated sessions on subsidies and revenues, which have become more central elements of the BIOFIN methodology. |
| November 2016 | The 3 CBD-BIOFIN Regional Nodes advisors are being hired, enabling all CBD parties to gain access to some level of support to understand and apply the BIOFIN methodology. The first one, Hervé Barois, Regional Node for African and Central Asia countries is on board. |
| October-November 2016 | Internal and External peer review of the 2016 BIOFIN Workbook |
|  | A series of dialogues has taken place with UNSD to develop synergies. The new BIOFIN classification is fully compatible with SEEA categories. |
| December 2016 | Official launch of the 2016 BIOFIN Workbook and the Regional Nodes at the COP 13 in Mexico during the Global BIOFIN team side events on 5th of December. Other BIOFIN side events will follow, with Mexico on 7th and Belize on 9th. BIOFIN will also be mentioned in other country side event such as Cuba and Costa Rica. |
| 2017 |  |
| January 2017 | 3rd Regional BIOFIN Workshop for LAC countries in Guatemala |
| January 2017 | Beginning of public Webinar series on the new methodology based on the 2016 BIOFIN Workbook and another series on finance solutions. |
| January 2017 | New version of the BIOFIN website |
| April 2017 | 3rd Regional BIOFIN Workshop for Asian countries in Kazakhstan |
|  | 3rd Regional BIOFIN Workshop for African countries |
| 2018 |  |
| 2018 | 3rd Global BIOFIN Workshop in India |

| BIOFIN team evolution |  |
| --- | --- |
| 2012 | Nik Sekhran come up with the idea of BIOFIN and select Yves de Soye as Manager (from 2012 to January 2016), Jamieson Ervin write the 2014 BIOFIN Workbook |
| 2013 -2014 | -Onno van de Heuvel hired as Deputy Manager -Blerina Gjeka as Programme Assistant. -David Meyer and Marlon Flores hired as Senior Technical Advisors -Matthew Taylor as communication specialist (resigned after COP) |
| 2015 | -Andrew Seidl and Annabelle Trinidad hired as Senior Technical Advisors -Diego Ochoa as new Communication Specialist -Oscar Huertas as M&E and KM specialist -Massimiliano Riva from UNDP New York give 25% of his time to support BIOFIN |
| 2016 | -January 2016 Onno van den Heuvel becomes Manager and Yves de Soye leaves BIOFIN -June 2016: Marco Arlaud hired as Environmental Finance Expert -July 2016: Semiray Emeksiz hired as Programme assistant - August 2016 Communications Expert Diego Ochoa phases out - November2016: Hervé Barois as Regional Node for African countries |
| 2017 | -January 2016: Communication specialist James Maiden and Regional Node for LAC Simone Bauch join |

# ANNEX 9: STATUS OF BIOFIN DELIVERABLES / COUNTRY

More on the section “National Progress” P14 of the donor report.

https://www.dropbox.com/s/2qowwdxrc7rd5ww/EU_report_2016_logframe_edits2.pdf?dl=0

# ANNEX 10: THEORY OF CHANGE 2016

BIOFIN ME dashboard

# ANNEX 11: EXCERPTS FROM THE KEYNOTE SPEECH - BIOFIN CONCEPT - UNDP’S GLOBAL DIRECTOR FOR SUSTAINABLE DEVELOPMENT

The CBD estimated the necessary funds to achieve the Aichi biodiversity targets to be between USD 110 billion and USD 440 billion per year. However, these numbers come from a top down calculation and today, we need a more precise analysis coming from a bottom-up approach, since ignorance is not bliss for this issue but ignorance leads to catastrophe. This is why BIOFIN was created, to work with Ministries of Finance and start to track the biodiversity expenditures into different sectors. Mr. Sekhran further explained that BIOFIN evolved and identified four critical types of finance results:

(1) Avoid future expenditures where possible, which means spend money now to avoid future costs. A good example to illustrate this issue, would be the control of invasive alien species. In the future, avoiding cost will be the key challenge. For example, we can forecast the cost of removing plastic from oceans will be tremendously high.

(2) Realign expenditures, or using existing funds, that are not spent well or have biodiversity adverse impact, in a more effective and sustainable way. For example, global subsidies for fisheries represent USD 45 billion a year and leads to overexploitation of the marine ecosystems. There is a clear case to reorient such expenditures.

(3) Delivering Better. Ministries of Environment usually suffer from poor delivery rates. We need to deliver better and show the resources spent have results and are used efficiently. A lot of countries are facing an economic crisis and it became necessary to do more with less. Therefore, we need to track expenditures and link them to policies, effectiveness and increase the capacity to deliver.

(4) Resource Mobilisation. We also need to generate new revenue streams and new sources of funds; mobilise domestic, international, private and public resources. BIOFIN gives a bottom-up analysis to see what the solutions might be at the country level, looking for win-win solutions that also impact other SDGs positively.

Watch the video: https://www.youtube.com/watch?v=7xsW2Pdyg1o https://www.youtube.com/watch?v=7xsW2Pdyg1o

# ANNEX 12: METHODLOGY - PROGRESS REPORTED 2017 FEBRUARY

The actual methodology has been under revision over the course of the last few years as the national teams and the Global BIOFIN Team have learnt from a combination of hands on experience and outreach to key partners and other initiatives. The methodology revision began with the development of technical PowerPoint presentations, shared with countries for feedback through regional workshops and online webinars. Secondly, the feedback was brought together in a writing / editing session at UNDP HQ in New York in August where main elements of the methodology were revised and chapter drafts were prepared. The full drafting of the Workbook was supported by a technical writer. Technical workshops were held in Bangkok and in Colombia to provide additional BIOFIN core country feedback on the drafts. Finally, an updated draft was circulated internally at UNDP and among national BIOFIN teams and a revised draft was circulated among a range of global colleagues from various organisations for comments and suggestions.  The final draft was then prepared and presented at the COP in electronic form and can be downloaded from the BIOFIN website.  Translations are underway for a French, Spanish, and Russian version.

Additional methodology work was conducted to finalize and share the BIOFIN Data Tool – a series of Excel-based datasheets that can be used to facilitate, standardize, and ultimately consolidate data from BIOFIN countries. Final adjustments are currently being worked on and a full public website release is expected in February.

Figure 2: The main theoretical framework for BIOFIN

The new Workbook now provides much additional guidance on how to establish an effective national BIOFIN Process. The main focus is to strengthen partnerships with Ministries of Finance and the private sector, and the workbook provides several useful entry points to engage with the private sector, such as working with chambers of commerce, Corporate Social Responsibility and partnering with foundations. New guidance is provided on integrating gender considerations throughout the BIOFIN process, in particular when designing finance solutions.

The revised Biodiversity Finance Policy and Institutional Review (PIR) chapter guides countries towards a more in-depth analysis into the institutional framework for specific finance solutions, the national budgeting process and biodiversity-relevant subsidies. The PIR also includes a clearer framework for stakeholder analysis and engagement. One more additional feature is to compile a broader package of economic and economic valuation data, to be used as input when formulating the business case for the finance plan and individual finance solutions.

The Biodiversity Expenditure Review allows countries to analyse past biodiversity expenditures and understand absolute and relative biodiversity allocations and spending. Expenditure reviews provide insight into how policy priorities were or were not reflected in actual expenditures as well as opportunities for improved allocation. The BER predicts future expenditures under different scenarios to establish the “business as usual” financing case that will be measured against the financial needs assessment to determine financing gaps for each biodiversity (NBSAP) strategy, organization, and CBD targets.

The new BER version includes enhancements such as: (i) clarifying the definition of “biodiversity expenditure”, (ii) detailed guidance and examples of how to attribute expenditures to biodiversity for “indirect” expenditures including sector by sector guidance, (iii) tagging systems for a range of analyses, (iv) guidance on engaging with the private sector, and (v) approaches to avoid double counting, among others.

The guidance is complemented by a new classification system of biodiversity activities that can be used to systematically sort and analyse biodiversity expenditure data, including suggested ranges for coefficients. This classification system is evolving in close dialogue with the United Nations Statistics Division, which could eventually lead to the adaptation of the categorisation as a subset of formal UN data standards.

The Financial Needs Assessment (FNA) has evolved substantially and covers a detailed costing of the NBSAP and other key biodiversity strategies or strategies and programmes around sustainable use such as sustainable fisheries, forestry and agriculture. The BIOFIN methodology can help refine the NBSAP activities so they provide adequate detail and quantitative results-based indicators to be easily budgeted. Then a results-based budgeting process is conducted in a participative manner with experts and stakeholders. Once the details are established through government standard budgeting and where needed, detailed financial models, the results are summarized by goal, strategies, and by organization. The result of the analysis is a financial gap, determined through comparison with the future expenditure scenarios calculated in the Biodiversity Expenditure Review.

The Biodiversity Finance Plan provides a strategic and operational plan for transforming the way biodiversity is financed in each country. The plan summarizes the main results from the previous BIOFIN assessments, highlighting the main opportunities for increased and more effective use of finance and economic tools in biodiversity management. The approach includes combining a review of all currently used biodiversity finance solutions with a list of potential solutions that are described in an evolving Biodiversity Finance Solutions Catalogue to build a list of potential solutions. This list is then subjected to two screening tools to prioritize the solutions that will be the subject of detailed feasibility analyses and technical design.

The plan contains a completed action plan for implementing a range of solutions and initial guidance on others that would require significant funding for a comprehensive design stage. The Biodiversity Finance Solution Catalogue is an excel-based tool that provides a comprehensive list of finance solutions that are relevant for biodiversity (but can also contribute to sustainable development in general).

# ANNEX 13: KNOWLEDGE MANAGEMENT WORK EXAMPLES OF CASE STUDIES

# ANNEX 14: CURRENT SENIOR TECHNICAL ADVISOR TABLE

| Name: | Countries |
| --- | --- |
| Onno van den Heuvel | 2: Mongolia, Mozambique |
| David Meyers | 8: Rwanda, Uganda, Kazakhstan, Georgia, India, Kyrgyzstan, Botswana, Seychelles |
| Marlon Flores | 8: Cuba, Ecuador, Colombia, Peru, Chile, Guatemala, Costa Rica, Mexico |
| Andrew Seidl | 5: Fiji, Indonesia, Malaysia, Brazil, Belize |
| Annabelle Trinidad | 7: Thailand, Vietnam, The Philippines, South Africa, Sri Lanka, Zambia, Bhutan |

The 8 European Commission Countries in bold

# ANNEX 15: PHASE TWO - OPTIONS FOR SCALE UP

There is enormous demand from governments to make BIOFIN fully accessible to all countries. One way to do this is through facilitated virtual learning, with occasional in-person workshops and limited South-South exchanges. Delivery of BIOFIN approach to a target audience of 100 countries (assuming a modest expansion of 15 countries to the existing core set of 30 countries) would entail:

- Direct relationships with the governments involved in the development and implementation of NBSAPs;

- An e-learning self-paced tutorial in 5 languages that makes the content of the BIOFIN Workbook widely accessible;

- A facilitated on-line course, led by BIOFIN mentors and champions, with weekly webinars, and interactivity, in English, French, Spanish and Russian;

- A team that can handle the logistics of weekly learning, webinars, network building and communications, and review of assignments, among other responsibilities inherent in developing a capacity-building program;

- Partnerships in place for hosting and executing the e-learning platform and support required.

The Global Biodiversity Programme is well placed to provide support and leadership in the delivery of capacity building on resource mobilization. Through its work on GEF and NBSAPs, it is directly supporting 45 countries in the development of their NBSAPs, and with UN Environment is supporting 135 countries, through its direct support and through partnership with the NBSAP Forum Global Support Project and its partners, SCBD and UN Environment. On e-learning, the UNDP Global Biodiversity Programme is already leading on capacity-related work, it has developed over 20 e-learning modules, with a learning base of more than 10,000, in five languages. Building off of the successful protected area course, which reached an audience of >1,500 learners during an 8-week course, it is currently planning a resource mobilization course, using the BIOFIN Workbook, for early 2017. The Global Biodiversity Programme has a team in place that is familiar with running virtual courses, and we have a full-time e-learning specialist under contract, as well as e-learning consultants and an agreement with The Nature Conservancy to host the course.

Learning products pursuant to capacity building

Support (or lead, if that is the most appropriate role to assume) development of a learning products library from the workbook and existing BIOFIN materials. In the nearest term (Q1 2017), that might include:

- A Power Point suitable for presentation for each chapter of the workbook. It should be ‘the mother of all’ power point versions for each chapter, such that users will first cut to customize, not find gaps, then add locally relevant points and examples. The current Power Points have useful information, but definitely should not be presented (even though they have been on a number of occasions).

- 1-2 page fact sheets on each chapter.

In the near term (Q2-3 2017), this might include:

- Initiate a work group or discussion forum on the development of university and agency appropriate courses and training modules on the BIOFIN methodology. We want to be ahead of this game and provide leadership due to branding, quality control, potential for resource mobilization, potential for different delivery modes, reduction of redundant effort, etc.

- Learning products emanating from the completed data tool will need to initiate from David and/or Csoban. Once that is completed, integrating guidance from the workbook to the data tool and back and communicating this to the country teams will probably need to be a team effort.

- Development and integration of video clips of specific cases or examples or concepts into our materials above. Imagine this would be led by Oscar and is not my area of expertise, but I do use them in my university classes with frequency (e.g., from TEEB).

In the longer term (Q4 2017 and into 2018):

- BIOFIN could estimate bottom-up, data driven, costing/investment coefficients for the top 25 biodiversity outcomes identified in the NBSAPs (could also look at the other tags, particularly SDGs and SEEA) and get it into early preparation documents for CoP 14 and published in Nature or similar.

- From that we should estimate the global biodiversity finance gap based upon our data and get it published in Nature.

- (Virtually?) Convene a group of interested applied academics to work with this data set and generate interesting results around biodiversity finance the results of which could be published in a special issue of Ecological Economics and/or Ecosystem Services and be used by all BIOFIN countries, nodes, CBD, etc.

# ANNEX 16: EU/UNDP PILOT STATUS REPORTS/FINANCIAL DATA 2017

## Kazakhstan

Progress on development of BIOFIN reports and recommendations

Overall progress: The Kazakhstan BIOFIN programme has completed most of the three BIOFIN assessments and is currently in the process of detailed feasibility studies for the Biodiversity Finance Plan and piloting implementation of finance solutions. The BIOFIN working group includes representatives of subdivisions of the Ministry of Agriculture, Ministry of Finance, Ministry of National Economy, Central Asia Regional Environmental Centre. The major representative of the private sector which collaborates with the BIOFIN project is National Chamber of Entrepreneurs “Atameken”. The private sector is involved mainly through participation in project workshops. A workshop was recently held on putting forest certification and biodiversity offsets into practice by the example of the pilot project “Kansu” with the support of Atameken during the reporting period. As part of implementation of biodiversity offsets the key private sector project partner is LLP “KMG-Kansu-Operating”.

Policy and Institutional Review: The PIR identified 7 main sectors as having the strongest links with biodiversity: 1. Forestry, forest and non-wood resources, 2. Fishery and fish resources, 3. Agriculture, agrobiodiversity and adaptation to climate change in agriculture 4. Hunting management and wildlife management, 5. Water management and water resources, 6. Tourism and PAs, 7. Industrial development. Some of the conclusions of the PIR were that there was inadequate definition of ecosystem services in Kazakhstan’s existing legislation for some advanced finance solutions to be implemented (PES, offsets, etc.) and the BIOFIN team has subsequently submitted text for revised legislation to better define ecosystem services.

Biodiversity Expenditure Review: The BER needs minor editorial adjustments and all three will be published in the 1st quarter of 2017. The main conclusions are that the bulk of biodiversity financing is coming from the state budget although some corporations are providing some direct and indirect funding.  Overall, the amount of money going towards biodiversity is a small fraction of the current government budget – less than 0.1%.

Financial Needs Assessment: The Financial Needs Assessment (FNA) was able to provide detailed cost expectations for the national biodiversity concept and action plan (NBSAP) and has concluded that there is a significant financial gap. To implement the National Biodiversity Concept and achieve the biodiversity management goals will cost 57 187 688 thousand KZT (170 201 451 USD) per year from 2016 through 2020. However, since the NBSAP is largely a project based action plan and the BER covered a wider range of expenditures, the “finance gap” is largely underestimated.

Biodiversity Finance Plan: The development of the Biodiversity Finance Plan is currently in progress; a workshop was held with stakeholders, government and private sector in November 2016. The work on screening of financial solutions was conducted during the workshop, resulting in the selection of the 11 most relevant solutions. To complete the Finance Plan and implement pilot finance solutions, national experts in the field of tax policy, subsidies and gas industry were hired in 2016. The 10 key ecosystem services of the Ile-Balkhash pilot area were identified, as a first step towards setting up a full PES-scheme. Preliminary calculations were prepared for the economic valuation of ecosystem services together with the the first analytical report (with the GEF/UNDP CB2 project).

Finance Solutions: Negotiations were held with the leaders of LLP “KMG-Kansu Operating” company and the Department of Nature Resources Management of Mangystau region to discuss opportunities for the development of an offset mechanism at Kansu site near Ustyurt Reserve.

Main areas were defined to mobilize investments for the conservation of forest and grassland ecosystems of Kazakhstan as part of the work on assessment of the potential of forests and pastures of Kazakhstan to absorb CO2. Recommendations were developed to mobilize resources for sustainable management of forest and grassland ecosystems of Kazakhstan through various sources of climate funding.

Based on an in-depth analysis of the effectiveness of existing taxes, payments and fees in Kazakhstan and their impact on biodiversity and ecosystems, new types of tax regulations were developed for Kazakhstan – taxes for using pesticides, taxes for acquisition of shotguns, taxes for using accelerated depreciation rates for equipment with eco-friendly characteristics, granting “tax holidays”, etc.

Based on the analysis of the current practice of subsidies for forestry, fishery and agriculture, new types of subsidies were developed such as subsidies for procurement of domestic fodder, subsidies for procurement of fish fry and intensification technologies for the recirculation system of water supply, subsidies for providing consulting services, subsidies for forest management certification, etc. that will allow the mobilization of resources for biodiversity conservation and sustainable management of ecosystems.

Biodiversity offsets and payments for ecosystem services that are new in the context of Kazakhstan and suggested amendments were included in draft Law of Kazakhstan “On making amendments and supplements to the legislation in the field of flora and fauna of the Republic of Kazakhstan”. The amendments will become a basis for resource mobilization to conserve biodiversity through the investments of the private sector. The BIOFIN project manager and the expert on financial tools were both included in the list of the working group members that would review the amendments to the environmental legislation.

## Malaysia

Progress on development of BIOFIN reports and recommendations

Overall process: In Malaysia, BIOFIN has followed a programme rather than a project approach. From the onset, BIOFIN was directly providing inputs into policy discussions, while government indicated it would not be necessary to assemble a national team. This view changed throughout 2016, as the need for a team to support government became more evident.

BIOFIN Malaysia works closely with 4 active projects on biodiversity financing outcomes, supported by UNDP with GEF grant financing by advocating the application of BIOFIN methodology in the development and implementation of biodiversity finance solutions at the national and sub-national level. The 4 projects are: (i) Biodiversity Conservation in the Multiple Use Forest Landscape in Sabah, (ii) Enhancing Effectiveness and Financial Sustainability of Protected Areas in Malaysia, (iii) Developing and Implementing a National Access and Benefit-Sharing Framework in Malaysia and (iv) Improving Connectivity in the Central Forest Landscape in Malaysia.

Outputs: The PIR report is at the Desk Study phase. The first draft PIR is to be completed in April 2017. The BER report is under Data collection, and the first draft is to be complete in July 2017. The Finance Need Assessment is also in Desk Study. Biodiversity finance solutions such as Payment for Environmental Services, REDD+, fiscal transfer have been determined in the 11th Malaysia Plan and the National Policy on Biological Diversity 2016 – 2025 Goal 5 Target 17.

UNDP has successfully advocated the application of BIOFIN workbook to develop the business case and financial needs assessment for the State of Sabah’s Conservation Finance Strategy and PES scheme through its membership in the Interim Committee for Conservation Finance Strategy in Sabah and participation as keynote speaker and facilitator in the Heart of Borneo Conference in November 2016

UNDP Malaysia through BIOFIN and other UNDP supported projects with biodiversity financing components provided inputs to the formulation of 11th Malaysia Plan 2016 – 2020 and the National Policy on Biological Diversity 2016 – 2025. Both policies provisioned for sustainable financing for biodiversity through indicative financing solutions such as PES, REDD+, fiscal transfer, green bond

The Economic Planning Unit at the Prime Minister’s Department – National BIOFIN Focal Point is committed to undertake the BIOFIN process to achieve the development targets set forth in the 11th Malaysia Plan and to support the implementation of National Policy on Biological Diversity 2016 – 2025

## The Philippines

Progress on development of BIOFIN reports and recommendations

Overall process: Work in the Philippines is at an advanced stage, as most outputs under the first components were already finalised. The process is led by the Department of Environment and Natural Resources, but implementation is characterized by intelligent stakeholder engagement for each sub-activity. The BIOFIN Philippines team previously completed their PIR and FNA and focused in 2016 on completing the BER, developing the Finance Plan and working with government on a variety of finance solutions.

Finance Plan and Finance Solutions: Regarding the Financial Plan implementation, the Philippines is currently implementing and testing the following finance solutions:

- Budget realignment (biodiversity expenditure tagging);

- Mainstreaming (integrating NBSAP targets into the new Philippine Development Plan);

- Improved access to earmarked funds (providing technical assistance to local government units to access the Peoples Survival Fund and the ER 1-94 trust funds, House Bill 4604 to authorize the use of the Malampaya Fund for biodiversity conservation aside from energy development);

- Localization of the NBSAP (implementation of the BIOFIN methodology at the local government unit level and cascading of the NBSAP to the Department of Environment and Natural Resources (DENR) field offices); and

- Private sector engagement (marketplace, corporate social responsibility and research into public-private partnerships for biodiversity conservation).

A pre-feasibility assessment of other finance mechanisms through a key informant survey was conducted and the top 10 responses were: official development assistance; earmarked funds related to environment/climate change; debt-for-nature swaps; enterprise challenge funds; user fees; ecological fiscal transfers; environmental trust funds; green bonds; crowd funding; and corporate social responsibility/philanthropy.

BIOFIN has achieved important results regarding public policy; the election of the new Philippine President in May 2016 ushered the commencement of the national planning process and the National Economic and Development Authority (NEDA) started national and regional consultations to ensure that issues and concerns are considered in the strategies, policies, and programs of the PDP 2017-2022.  The Project team has been closely attending all consultations particularly on the chapter on Ecological Integrity where the NBSAP thematic areas and a number of national targets have been included.

Presidential Decree (PD) No. 910, as amended, created a Special Fund from government shares representing royalties, rentals, production share on service contracts and similar payments on the exploration, development and exploitation of energy resources. It is more popularly known through one of its components, the “Malampaya fund,” which consists of the government share from the Malampaya Deepwater Gas-to-Power Project. According to Department of Budget and Management (DBM) Secretary Benjamin Diokno, the 2016 figure for Malampaya Fund is about PhP183 billion, and it is still increasing. The Malampaya Fund is a potential finance source for biodiversity conservation. The BIOFIN team is working with a parliament member to formally submit legislation that would divert some of its funds towards biodiversity objectives.

In addition, BIOFIN has drafted a policy paper on public-private partnership in protected areas and legal memoranda on green bonds and biodiversity offsets.

## Seychelles

Overall process: BIOFIN in the Seychelles has been integrated into a range of initiatives as the country is small and has a well-focused biodiversity community.  Seychelles completed the PIR in 2015, and the BER draft report has been submitted, and is currently incorporating peer review suggestions and comments from the Global BIOFIN team (to be submitted in January 2017).

The BIOFIN process has from the outset strived to emphasise the need to mainstream BD conservation and its financing into the national planning and budgetary process. Seychelles BIOFIN has ever since its launch in 2014, stressed the need to have greater coordination and harmonization among the different local initiatives and plans viz. NBSAP; Seychelles Sustainable Development Strategy (SDDS); Blue Economy Initiative; National Development Strategy (NDS) and the Budgetary Planning Process. The SSDS Steering Committee (which had remained mostly dormant since the SSDS was approved in 2013) met with the Blue Economy Steering Committee in 2016 in order to avoid duplication of purpose and harmonise their roles moving forward. Similarly, Seychelles BIOFIN welcomed the implementation of the Programme Performance - Based Budgeting process first at pilot level in 2015 and now set to be extended to all Government ministries and departments in 2017. Seychelles BIOFIN team however believe that much work remains to be done by way of integrating BD conservation and financing in a more holistic way into the overall planning processes.

Seychelles BIOFIN has determined that there is a need to review and strengthen the overall legal framework for BD conservation, notwithstanding recent progress made by way of the revised Environment Protection Act (2016) and the Biosecurity Act (2015). Equally importantly, there is need to develop greater capacity in order to ensure that all legislation is duly enforced. For example, the BioSecurity Act has been in place for almost two years, but resources are insufficient to implement it at border level in order to stave off the increase in invasive alien species. There is now expectation that the recently set up BioSecurity Agency may provide not only the structure and leadership but especially the required resources using innovative funding mechanisms recommended by Seychelles BIOFIN Team.

Since the start of Seychelles BIOFIN, there has been no effort spared in engaging Government and its relevant agencies in the BIOFIN Process. The fact that Steering Committee is co-chaired at senior level by the ministries responsible for finance and environment typifies such engagement. Furthermore, both the national and Global BIOFIN have kept relevant Ministers apprised of BIOFIN. It should be noted that since the launch of BIOFIN in Seychelles, there has been three successive Ministers of finance and two Ministers of environment. Besides the Steering Committee Meetings, Government has been actively involved in all BIOFIN meetings and Workshops, whether locally or abroad. In particular, Government was represented at senior level at the Global BIOFIN Workshop in Los Cabos, Mexico in April 2016 during which Seychelles Principal Secretary for Environment made a presentation on Seychelles BIOFIN Journey while the Director of Public Debt Management made a presentation on the Seychelles Blue Bonds Initiative.

The strongest strategic alliance of Seychelles BIOFIN must have been with the NBSAP process followed by that with the PA Finance Project and currently the PA Financial Plan. In the absence of support from Seychelles BIOFIN, it is not obvious that Seychelles’ second NBSAP would have been finalized and approved in 2015. It was upon the request of Seychelles BIOFIN Team that GEF / UNDP funded the local consultant to have the NBSAP costed and realigned with Aichi Targets. BIOFIN then organized the Validation Workshop for the revised NBSAP in November 2016.

Seychelles BIOFIN in 2016 funded the Assignment to Assess Tourism Development in Protected Areas. There are undeniable synergies between the PA Financial Plan and the BIOFIN Finance Plan. Furthermore, the respective teams ensured that notwithstanding tight timelines, the key Workshops for these respective Plans were held on successive days on 30th November and 1st December 2016.

BIOFIN has also forged strong links with Seychelles’ Blue Economy Initiative as well as with Seychelles’ Debt for Climate Change Adaptation Swap which was signed alongside COP21 in Paris in December 2015. The Debt for Climate Change Adaptation Swap comprises of the Marine Spatial Planning (MPS) Project under the aegis of the recently set up Seychelles Climate Change Adaptation Trust (SEYCCAT). BIOFIN fully supports the proposal for 30% of Seychelles Exclusive Economic Zone to be Protected Areas and that half of such PAs be “No Take Zones”. However, mindful of the resistance of EU fishing vessels to such proposals, BIOFIN has recommended that a cost benefit study be first carried out. There has also been strong links between BIOFIN and GEF funded projects as highlighted above by the GEF funding of the consultancy to cost and realign Seychelles second NBSAP.

BIOFIN has engaged private sector especially from the tourism and fisheries sectors, initially by way of the BIOFIN Tourism Sustainable Workshop held in May 2016, and subsequently during the BIOFIN Finance Plan Workshop held in December 2016. (Please see above Sections under Meetings and Workshops). Attached are list of participants from both Workshops. During the Sustainable Tourism Workshop, the fact that BIOFIN engaged selected hotel resorts to present and showcase their respective BD programme to peers from the sector, was enough evidence of engagement of such operators. Both Workshops in 2016 received coverage by the local media including local TV. Seychelles BIOFIN also got coverage from Deutsche TV as one of three BIOFIN countries selected to receive such coverage.  Seychelles BIOFIN has its own website which it updates regularly; it has also produced a BIOFIN Brochure and Posters which were used in Global BIOFIN Workshops.

## Uganda

Overall process: The National Environment Management Authority (NEMA) closely cooperating with other stakeholders such as the Ministry of Finance is leading BIOFIN in Uganda. The project has greatly benefitted from the strong capacity of NEMA who has been leading the NBSAP process including an initial costing exercise and a guide to resource mobilization.

The steering committee is composed of the Ministry of Water and Environment, the Ministry of Energy and Mineral Development, the Ministry of Local Government, the National Planning Authority, the Uganda Wildlife Authority, the Ministry of Finance, Planning and Economic Development, the Ministry of Agriculture, Animal Industry and Fisheries, the National Forestry Authority, and the Uganda Bureau of Statistics. The national BIOFIN team has initiated meetings with Ministry of Finance, Planning and Economic Development as a strategy to engage the Ministry during the budgetary process.

Policy and Institutional Review: The Uganda PIR report was one of the first BIOFIN PIRs to include a full listing of existing finance solutions currently being implemented in the country. The list produced was quite comprehensive and included taxes and subsidies as well as more traditional solutions such as fees and fines.

The team selected five key sectors based on their priority in the NBSAP and for biodiversity finance. These sectors are: Water and Environment; Agriculture; Tourism, Trade and Industry; Energy and Mineral Development; and Works and Transport. The team also highlights the different challenges existing for the protected areas (PAs) in Uganda. BIOFIN also identified some inefficient and harmful finance mechanisms.

Other outputs: The BER report focused almost entirely on public sector and was very inclusive about what was considered biodiversity expenditures. The BIOFIN team is currently working on the Financial Needs Assessment and will begin the Biodiversity Finance Plan in the upcoming quarter.

## Chile

Overall process: Chile has completed the main deliverables. Draft reports have been revised and final documents are to be published in early 2017. The BIOFIN team analysed budget expenses, programs, plans and projects related to biodiversity for the 2010-2014 period. The analysis covered the central and sectorial levels including five ministries (Agriculture, Economy, Energy, Environment and Mining) and the Regional Development Agency (SUBDERE). Chile has achieved strong political support from key institutions such as the Ministry of Treasury, The Council for Clean Development, The Ministry of Environment, CONAF and other key sectorial institutions.

Like Costa Rica, Chile has a strong Steering Committee and has established a technical committee to support the formulation of their resources mobilization strategy (Financial Plan) for 2016- 2030.

The Treasury played an important role in enabling the flow of financial information from sectorial agencies for the BIOFIN analyses. BIOFIN is supporting the strengthening of institutional capacities in planning, interagency collaboration and methodology standardization; and contributing to the development of environmental statistics and indicators related to biodiversity. Besides, initial BIOFIN data is being used to report to the Convention on Biological Diversity.

Chile was the host for the 2016 LAC regional workshop in Santiago. The BIOFIN team has conducted trainings in planning and results-based budgeting for the Ministry of Environment, Ministry of Economy, Ministry of Agriculture, Regional Governments, Ministry of Energy, and NGOs.

BIOFIN information has been used for the OECD and CDB national reports; this was done for the Environmental Performance Review of Chile made by the OECD 2016.

1. Policy and Institutional Review: The PIR in Chile provided evidence that the major drivers of biodiversity loss are the results of the limited government role in environmental management, particularly in terms of effective regulation, enforcement and funding. There have been however important positive actions, for instance, in 2010, the reforms package to the General Environmental Law included the creation of the Ministry of Environment, The Sustainable Development council, and the Secretariat for Environmental Monitoring and Evaluation. However, the establishment of the National Service for Biodiversity and Protected Areas is still uncertain.

The PIR mapped the key policies, sectors and institutional capacities linked to biodiversity loss and gain. The report noted that the development sectors that cause most of the biodiversity loss include: forestry, agriculture and husbandry, fisheries, mining and a wide variety of unsustainable strategies used in the manufacturing sector. The report also highlights the allocation of financial resources for those government agencies that have environmental responsibilities such as biodiversity and ecosystems protection, restoration, management and sustainable use is highly inadequate.

2. Biodiversity Expenditure Review: The team is advancing with the BER as initial estimates indicate during the 2010-2014 period Government spent approximately 2,180,561,164 Chilean Pesos (USD 3.2 million) on biodiversity related activities. The analysis shows biodiversity expenses have a minor impact in the National Budget, i.e., 0,13% in 2014. Nevertheless, there has been a 68% increase from $32.115.969 (Chilean pesos) in 2010 to $53.950.133 (Chilean pesos) in 2014; an average growth of 13,85%.  This rate is higher than the overall growth of public expenditure, estimated at 5,08%. The team is now revising data and preparing the final BER Report

3. Finance Needs Assessment: The FNA estimated the cost of the six strategic plans of the NBSAP. Out of the six, the National Action Plan for the Conservation of Marine Biodiversity and Oceanic Islands concentrates 60.14% of the resource requirements, followed by the Biodiversity Climate Change action plans with the 13, 72%, Invasive Exotic Species 11,73%, while Native Species (EN), Protected Areas (AP) and Wetlands only account for 5.68%, 4.81% and 3.65%, respectively. This high incidence is explained by the low attention that has had in the past the management and protection by the Chilean State of marine biodiversity as well as by its extension.

The FNA indicates that there is a low requirement for resources, giving a total of $ 79,654,588,811 (values in pesos to 2015) for the period 2015-2030, whose equivalence in dollars corresponds to US $ 121,782,972.

Biodiversity Finance Plan: BIOFIN has supported the NBSAP planning process promoting a results-based approach and training institutions to implement it. In addition, there is an ongoing synergy with the Climate Change Adaptation Plan.

The following financial instruments are being considered: 1. Biodiversity related action that will be supported by the Green Climate Fund, 2. Mainstreaming biodiversity costs in Regional Government budgets, 3. A mechanism linked to artisanal fisheries, 4. A mechanism linked to the “Urban Decontamination Plans”, 5. A mechanism linked to the “Decontamination Plan of Lago Villarrica”. A strong collaboration with the Council for Clean Development is expected to support the Financial Plan and improve private sector investment in biodiversity conservation.

In addition, the results of the GEF Sustainable Finance Project for the National System of Protected Areas (NSPA) and other related projects will be considered to support the Finance Plan; i.e., introducing results-based budgeting and other cost-effectiveness measures in CONAF (National Forestry Commission) that operates the NSPA.

A private sector pilot was implemented with the Council for Clean Production: the results will be expressed in quality labels or certifications, achieving two relevant objectives in the promotion of environmental public policies, the protection of biodiversity and the commercial valuation of goods and services offered by the private sector. Offsets pilot: the generation of a new market requires to work on a design of an institutional platform to operationalize and include public regulations, particularly those regarding coordination (and intermediation) levels and the required information for its functioning. The BIOFIN Chile proposal adjusts to agreements reached by main actors (public and private) with respect to the urgency of moving towards its design and implementation, which will provide clear rules for the private sector and investment projects, as well as, the availability of an instrument validated by society, which will establish the terms of exchange and equivalences in a transparent and environmental manner.

## Ecuador

Overall process:  Ecuador has completed the PIR, BER and FNA and is now drafting the BFP. Financing for the environment and biodiversity sectors and many other sectors has been averse in the last years and potentially may get worse. The economy has been impacted by several factors and in addition, on May 2017 there will be new elections in the country. Therefore, the team will try to begin the implementation of certain finance solutions before the election.

Policy and Institutional Review: The key sectors that are the most prominent drivers of biodiversity loss include agriculture and husbandry, mining and oil, and energy. The mainstreaming of biodiversity policy in these sectors is lagging behind and institutional capacity and coordination is limited.

The PIR notes government is pushing for significant environmental improvements by shifting to a more sustainable national productive strategy. However, progress has been slow. Some recent positive moves include the introduction of tax exemptions for the renewable energy sector, the expansion of public investment in PAs, support for national programmes for the conservation and use of natural heritage and a large reforestation programme (known as Socio-Bosque). Further, the government is also supporting research and development through the new national Institute for Biodiversity and the new Universidad Regional Amazónica "Ikiam"

However, key sectors such as oil and mining are not yet incorporating improved production practices and the National Hydropower Development Plan is also considered a threat to ecosystems services. At local government level, biodiversity and ecosystems management is not yet mainstreamed and institutional capacity is limited. The PIR assessed the Ecuadorian Decentralized System of Environmental Management to assess strengths and weakness and has pointed out recommendations for its improvement, mainly to address the lack of coordination with key sectors that drive biodiversity loss.

Biodiversity Expenditure Review: The findings of the BER indicate that the environment sector’s budget during the period 2008-2011 was approximately USD 928.03 million. However, this sector only spent, on average, 82.6% (USD 559.30 million) per year. For the same period, expenditures on biodiversity conservation, at central government level, were estimated at USD 325.48 million with an average execution of 90.67%. This represents a spending of USD 1.21 per person in 2008 and USD 3.03 per capita in 2014. As for other key sectors that impact biodiversity (i.e., energy and agriculture) expenditures were estimated at USD 233.82 million with an execution of 78.45 %.

The Ministry of Environment and underlying agencies are the major actors in terms of biodiversity spending, with an estimate of USD 459.76 million during the same period with an average of 77.59% execution. The baseline for the 2014 spending on biodiversity was established at USD 114.372.268 million.

Finance Needs Assessment: The report shows the estimated total cost of implementing the selected set of 8 priority results and measures of the NBSAP is USD 267.3 million annually; out of this, USD 33.3 million correspond to recurrent costs and USD 234 million to investment costs. Thus, when compared to the 2014 spending base line the current spending barely covers 43% of the annual financial needs. Financial gaps were estimated at US$ 95 million and USD 153 million for the basic and optimal level respectively.

Biodiversity Finance Plan: The team in Ecuador is currently discussing with the government for several potential financial mechanisms to be included in the Financial Plan. For instance: a) a new mechanism to increase funding to pay for forest conservation through the Socio-Bosque Program with support of the Hydropower Sector, b) the consolidation of several environmental funds including the National Environmental Fund (FAN) into a larger Environmental Fund, c) a green certification called “Green Point” (in collaboration with the National System of PAs) to promote private contributions for conservation. In addition, the Ecuador team is closely collaborating with the Vice Minister of Water to implement tariffs for biodiversity conservation and restoration of watersheds in the country.

The consolidation of the Financial Strategy and the design of the two prioritized financial mechanisms (water tariffs and national environmental fund) are progressing as planned and are expected to be completed by May 2017.

The team also developed partnerships with projects such as TEEB with a formal agreement to use the two economic valuation studies done in the Ecuador for the definition of the water rate. But also with the UNDP environment and energy program, coordination lines and collaboration have been established with several projects. For example, with the Financial Sustainability of the National System of Protected Areas Project. With the CPEIR Project and the different synergies of methodology. The team is also developing financial mechanism with Targeted Support REED Project. Other partnerships exist with Senagua for the implementation of one financial mechanism and with ESPOL (Polytechnic School) for the promotion of Bio-industry.

The Ecuador team approached the National Financial Corporation (public banking) and the Association of Private Banks of Ecuador, with the purpose of presenting the results achieved by BIOFIN and proposing financial products that could interest the productive sector (energy efficiency and development of bio-industry).

## South Africa

Progress on development of BIOFIN reports and recommendations

Overall process: BIOFIN South Africa has made strong progress this year, in order to catch up for the delays in earlier years.  Members of National Government and provincial conservation authorities are members of the BIOFIN Steering Committee and BIOFIN Technical Reference Group. In addition, BIOFIN is a standing agenda item at Working Group 1. Working Group 1 meets four times a year, and has representation from all national and provincial government entities in the environmental sector addressing biodiversity management and conservation. Lastly, consultants have engaged with several representatives from provincial and national government entities to inform the various reports with the South Africa’s BIOFIN Programme.

Communications on the importance of biodiversity in achieving the SDGs have been developed in the form of 11 videos. While these do not explicitly mention BIOFIN, they form part of BIOFIN implementation. Some of these videos were showcased at the CBD COP in Dec. The full launch of the products, both within SA and internationally, will take place in early 2017, following the development of a launch strategy in January 2017.

Policy and Institutional Review: The PIR final report was submitted on the March 2016. The study identified 10 negative and 5 positive trends and drivers of change in biodiversity. A broad range of finance actors were identified through the PIR. A prioritisation process based on the institution’s ability to influence- and likely interest in biodiversity matters subsequently identified key finance actors to inform the biodiversity expenditure review and resource mobilisation plan. These include the national Department of Environmental Affairs, National Treasury, donor agencies, provincial environmental authorities, the national departments responsible for agriculture, forestry and fisheries; and water and sanitation, Catchment Management Agencies and the National Disaster Management Centre. The PIR also made recommendations to major challenges in the biodiversity sector related to funding.

Biodiversity Expenditure Review: The BER has been completed and submitted to the government for final approval.

Biodiversity Finance Plan: The first draft of the BFP was provided to Project Leader and Project Coordinator on the 6th December 2016. Comments have been received from the BIOFIN Global Team and the BFP Consultant will now revise the final draft. This is expected to be completed by the end of February 2017.

Finance Solutions: As per the Finance Plan implementation, the team is 1) Developing a national policy for biodiversity stewardship. 2) Contributed to the development of a national policy for biodiversity offsets (currently out for public comment). 3) Drafting a ToR for an economic case for protected areas.  4) Provided content and technical leadership for the development of 11 videos communicating the importance of biodiversity in supporting the national development agenda and achieving the SDGs.  To be officially launched in 2017. 5) Contributing to changes in the income tax legislation and the Biodiversity Act.

South Africa’s BIOFIN Project Leader, is part of the steering committee for the Department of Environmental Affairs (DEA’s) policy development on biodiversity stewardship. BIOFIN continues to collaborate on drafting a national policy on biodiversity stewardship, as well as a national implementation guideline. This work is likely to be partly funded by the GEF, in order to bring in NGO expertise. BIOFIN is also supporting GEF funded work on improving tax incentives for protected areas. BIOFIN is represented on the Steering Committee of the GEF6 Protected Areas project, run by SANParks (although, to date, have not been able to attend any of the meetings due to clashes in diary).

BIOFIN also contributed to the development of the national biodiversity offsets policy, which is currently out for public comment as well as potential changes to the income tax legislation and the Biodiversity Act.  Submission of a resolution on privately protected areas (through the Department of Environmental Affairs) on private protected areas at the IUCN WCC in 2016, which was accepted by Parties. This will result in, among other things, the development of global guidelines for privately protected areas during 2017 and 2018, which the BIOFIN Project Leader is expected to be an author of.

Proposed Program

Monitoring Mission

January 30 – February 3, 2017

| Date | Activity | Venue | Remarks/Persons in Attendance |
| --- | --- | --- | --- |
| January 30, 2017 (Monday) |  |  |  |
|  | Arrival in Manila |  |  |
| January 31, 2017 (Tuesday) |  |  |  |
| 9:00 AM – 12:00 nn | Meeting with Project Team | Conference Room, Biodiversity Management Bureau (BMB), Ninoy Aquino Parks & Wildlife Nature Center, North Avenue, Quezon City | - Ms. Stephanie Hodge - Ms. Floradema Eleazar, Team Leader, Inclusive and Sustainable Development (ISD) Unit, UNDP Country Office - Grace Tena, Programme Associate, UNDP Country Office - Biodiversity Management Bureau (BMB) Officials - Dr. Theresa Mundita Lim, Director - Ms. Armida Andres, Division Chief, Biodiversity Policy and Knowledge Management (BMB-BPKMD) - Ms. Nancy Corpuz, Biodiversity Policy and Knowledge Management (BMB-BPKMD) - Ms. Angelita Meniado, Coordinator, Foreign-Assisted Projects (BMB) - BIOFIN Philippines Team - Ms. Anabelle Plantilla, Project Coordinator - Ms. Annabelle Trinidad, Senior Technical Advisor, BIOFIN Global Team - Mr. Lorenzo Cordova, Environmental Finance Expert - Ms. Miraflor Sanchez, Local Government Specialist - Atty. Alton Durban, Policy Specialist - Ms. Angelique Ogena, Information & Communications Assistant - Ms. Kamille Rosales, Programme Assistant |
| 12:00 – 1:00 PM | Lunch |  |  |
| 2:00 – 3:30 PM | Meeting with Atty. Jonas Leones, Undersecretary for International Environmental Affairs, Department of Environment & Natural Resources (DENR) | DENR | - Foreign-Assisted and Special Projects Service (FASPS) Officials - Director Edwin Domingo - Ms. Madel Villalon - Ms. Stephanie Hodge - Ms. Floradema Eleazar, ISD Team Leader, UNDP Country Office - Grace Tena, UNDP Country Office - BMB Officials - BIOFIN Philippines Team |
| February 1, 2017 (Wednesday) |  |  |  |
| 9:00 – 10:00 AM | Meeting with the Philippine Business for the Environment (PBE) | PBE Office, 604 Tycoon Centre, Pearl Dr, Pasig, 1601 Metro Manila | - PBE Officials - Mr. Bonar Laureto, Executive Director - Ms. Katherine Odullo - Ms. Stephanie Hodge - BIOFIN Philippines Team |
| 11:00 – 12:00 NN | Meeting with National Economic and Development Authority (NEDA) | NEDA Building, Jose Escriva Drive, Pasig City | - NEDA Officials - Assistant Secretary Mercedita Sombilla - Ms. Diane Llanto, OIC - Assistant Director, Agriculture, Natural Resources and Environment Staff (ANRES) - Ms. Jane Magturo, ANRES - Ms. Stephanie Hodge - BIOFIN Philippines Team |
| Lunch | 12:00 – 1:00 pm |  |  |
| 2:00 – 3:00 pm | Courtesy call to UNDP Country Office | 30/F Yuchengco Tower, RCBC Plaza, 6819 Ayala Ave. cor. Sen. Gil Puyat Ave., Makati City | - Mr. Titon Mitra, Country Director, UNDP - Ms. Stephanie Hodge - Ms. Floradema Eleazar, ISD Team Leader - Ms. Grace Tena, Programme Associate - BIOFIN Philippines Team |
| 4:00 – 5:00 PM | Meeting with Mr. John Narag, Department of Finance | Department of Finance | - Ms. Stephanie Hodge - BIOFIN Philippines Team |
| February 2, 2017 (Thursday) |  |  |  |
| February 3, 2017 (Friday) |  |  |  |
|  | Leave Manila |  |  |

References made to the BIOFIN good work by CBD parties in plenary 22 times.  Also see reference to this in  annex.

Towards the end of 2015, monitoring missions conducted by the European Commission, covering eight countries, indicated BIOFIN is a highly relevant initiative, on track to refine its methodology and country outputs to achieve transformative results. It highlighted the need to better specify national level outcome targets and further align country work with the latest version of the BIOFIN methodology, something which the global BIOFIN team had already started to address.

i] The evaluation followed the UNDP and EU evaluation criteria:

Relevance: Relevance looked at the relationship between the needs and problems identified and the objectives of the intervention. The extent to which the objectives of a development intervention are consistent with beneficiaries’ requirements, country needs, global priorities and partners’ and donors’ policies.

Effectiveness: The extent to which the development intervention’s objectives were achieved. The evaluation formed an opinion on the progress made to date and the role of BIOFIN in delivering the observed changes. If the objectives have not been achieved, an assessment should be made of the extent to which progress has fallen short of the target and what factors have influenced why something hasn't been successful or why it has not yet been achieved.

Efficiency: A measure of how economically resources/inputs (funds, expertise, time, etc.) are converted to results.

Sustainability: The continuation of benefits from BIOFIN after the project ends. The probability of continued long-term benefits.

Impact: Positive and negative, primary and secondary long-term effects produced by BIOFIN, directly or indirectly, intended or unintended (in this case early effects and foreseen mid-term or long-term changes).

An evaluation inception report was delivered on December 19, 2017. This document detailed the methods and clarified to both client and evaluator the understanding of the work. It included developing a detailed evaluation matrix with questions and interview protocols. [iii] (See focus areas below).

[ii] The following questions and ratings were addressed.

Relevance: [Rating: 2. Relevant (R), 1. Not-relevant (NR)]

·       To what extent is BIOFIN still relevant?

·       To what extent have the (original) objectives proven to have been appropriate for the focused countries?

·       How flexible has BIOFIN been in response to changing environments?

·       How aligned is BIOFIN with the countries’ needs, as well as EU and UNDP objectives?

·       Are there lessons learned which would improve the work of BIOFIN on gender mainstreaming in the future?

·       Are there lessons which would improve the BIOFIN ME work in the future?

Effectiveness: [Ratings: 6: Highly Satisfactory (HS): no shortcomings; 5: Satisfactory (S): minor shortcomings; 4: Moderately Satisfactory (MS); 3. Moderately Unsatisfactory (MU): significant shortcomings; 2. Unsatisfactory (U): major problems; 1. Highly Unsatisfactory (HU): severe problems]

·       To what extent have the objectives been achieved?

·       What are the expected and non-expected results observed by the evaluation?

·       What have been the quantitative and qualitative effects of the intervention? (tangible and intangible)

·       To what extent can these changes/effects be credited to BIOFIN?

·       What factors influenced the achievements observed?

Efficiency: [Ratings: 6: Highly Satisfactory (HS): no shortcomings; 5: Satisfactory (S): minor shortcomings; 4: Moderately Satisfactory (MS); 3. Moderately Unsatisfactory (MU): significant shortcomings; 2. Unsatisfactory (U): major problems; 1. Highly Unsatisfactory (HU): severe problems]

·       How has BIOFIN established synergies with related initiative at the global and national level and what have been its results?

·       To what extent are the costs involved justified, given the changes/effects which have been achieved?

·       To what extent are the costs proportionate to the benefits achieved? What factors are influencing any particular challenges?

·       What factors influenced the efficiency with which the achievements observed were attained?

·       To what extent has the intervention been cost effective?

Sustainability: [Ratings: 4. Likely (L): negligible risks to sustainability; 3. Moderately Likely (ML): moderate risks; 2. Moderately Unlikely (MU): significant risks; 1. Unlikely (U): severe risks

·       Capacity building

·       Will BIOFIN benefits continue in time once the EU project is over?

·       Are there any policy frameworks/policy results to sustain BIOFIN initiative in time?

·       What are the main alliances/partnerships from BIOFIN?

·       Is there any potential for replicability processes?

·       What evidence can be observed toward a shift in thinking about the benefits of the application of the BIOFIN methodology and the relevance of adopting additional finance solutions?

Impact

·       Global and national level impacts [Ratings: 3. Significant (S), 2. Minimal (M), 1. Negligible (N)]

[iii] The evaluation will follow the UNDP and EU evaluation criteria:

Relevance: Relevance looks at the relationship between the needs and problems identified and the objectives of the intervention. The extent to which the objectives of a development intervention are consistent with beneficiaries’ requirements, country needs, global priorities and partners’ and donors’ policies.

Sustainability: The continuation of benefits from BIOFIN after the project ends. The probability of continued long-term benefits.

Impact: Positive and negative, primary and secondary long-term effects produced by BIOFIN, directly or indirectly, intended or unintended (in this case early effects and foreseen mid-term or long-term changes).

Evaluation questions:

Relevance: [Rating: 2. Relevant (R), 1. Not-relevant (NR)]

to what extent is BIOFIN still relevant?

to what extent have the (original) objectives proven to have been appropriate for the focused countries?

how flexible has BIOFIN been in response to changing environments?

How aligned is BIOFIN with the countries’ needs, as well as EU and UNDP objectives?

Are there lessons learned which would improve the work of BIOFIN on gender mainstreaming in the future?

Are there lessons which would improve the BIOFIN ME work in the future? Effectiveness: [Ratings: 6: Highly Satisfactory (HS): no shortcomings; 5: Satisfactory (S): minor shortcomings; 4: Moderately Satisfactory (MS); 3. Moderately Unsatisfactory (MU): significant shortcomings; 2. Unsatisfactory (U): major problems; 1. Highly Unsatisfactory (HU): severe problems]

To what extent have the objectives been achieved?

What are the expected and non-expected results observed by the evaluation?

Efficiency: [Ratings: 6: Highly Satisfactory (HS): no shortcomings; 5: Satisfactory (S): minor shortcomings; 4: Moderately Satisfactory (MS); 3. Moderately Unsatisfactory (MU): significant shortcomings; 2. Unsatisfactory (U): major problems; 1. Highly Unsatisfactory (HU): severe problems]

How has BIOFIN established synergies with related initiative at the global and national level and what have been its results?

To what extent are the costs involved justified, given the changes/effects which have been achieved?

To what extent are the costs proportionate to the benefits achieved? What factors are influencing any particular challenges?

What factors influenced the efficiency with which the achievements observed were attained?

To what extent has the intervention been cost effective?

Sustainability [Ratings: 4. Likely (L): negligible risks to sustainability; 3. Moderately Likely (ML): moderate risks; 2. Moderately Unlikely (MU): significant risks; 1. Unlikely (U): severe risks

Capacity building

Will BIOFIN benefits continue in time once the EU project is over?

Are there any policy frameworks/policy results to sustain BIOFIN initiative in time?

What are the main alliances/partnerships from BIOFIN?

Is there any potential for replicability processes?

What evidence can be observed toward a shift in thinking about the benefits of the application of the BIOFIN methodology and the relevance of adopting additional finance solutions?

Impact

Global and national level impacts [Ratings: 3. Significant (S), 2. Minimal

National Institutional Change The sustainability of the EU GEF/UNDP capacity development actions takes incentives and time to strengthen, especially for impacts on the national systems development and to institute local level planning mechanisms and capacities that bring forth sustainable change for actual biodiversity (Impacts on Biodiversity) specific impacts/results as per the Theory of Change TOC. Testimonials will be support and collected from stakeholders, including government level staff working at the institutional level concerning institutional and their own individual change, i.e. impacts. These will be included in the final report as an annex.

Knowledge Management, Learning and South-South Cooperation At the global and regional levels, the evaluation will consider the learning aspects of BIOFIN, including the monitoring, knowledge sharing (global, regional and national) and technical cooperation and the promotion of South-South cooperation through a global UNDP program approach. At the national level the evaluation considers the impact on institutions through instilling a new mainstreaming approach and developing cap cities for mainstreaming and working across sectors.

Alignment / Integration - There are a plethora of finance tools including PER, BPER, CPER, for different thematic areas. Evaluator will consider how these support the outcomes beyond outputs.

The final list will be confirmed through a dialogue between the relevant Commission services and the UNDP’s Biodiversity Global Programme, based on the following criteria:

- The final selection of countries has to be geographically balanced and representative of all types of developing countries (including megadiverse countries, Small Island Developing States (SIDS), Least Developed Countries (LDCs) and emerging and transition economies).

- The government of the country has shown commitment to mainstreaming biodiversity concerns into national development planning, to quantifying the biodiversity management financing gap and to finding innovative ways to finance biodiversity management in the medium to long term, through a combination of state, private sector and ODA resources.

- The country has a plan in place to update its National Biodiversity Strategy and Action Plan, in many cases receiving assistance through UNDP’s Biodiversity Global Programme to ensure that the new NBSAP includes financial needs assessments, addresses the CBD Strategic Plan for 2011-2020, and becomes a more relevant policy instrument through its integration into development plans, development finance and strategies aimed at managing climate risk.

- The country has a current or recently completed project funded by the Global Environment Facility or other sources through UNDP dealing with financing of Protected Areas, economic valuation of biodiversity and ecosystem services, or capturing values through Payments for Ecosystem Services – generating valuable new knowledge and data, and building the capacity of a range of national and sub-national stakeholders to take this work further.

The Tenth Meeting of the Conference of the Parties to the CBD (CBD COP 10) agreed to the headline target “take effective and urgent action to halt the loss of biodiversity […] by 2020 […] thereby […] contributing to human well-being, and poverty eradication”. Parties also agreed to by 2020 integrate biodiversity values into national and local development and poverty reduction strategies and to increase substantially the mobilization of financial resources for implementing the Convention.

Current Official Development Assistance (ODA) from donor countries cannot alone bridge the financing gap, and further development and adoption of innovative financing mechanisms will be essential. Developing countries will need to be assisted to identify, access, combine and sequence multiple sources of environmental and development finance, as well as channelling their own resources, in order to meet their biodiversity management needs. Countries will need to adapt and strengthen their governance and policy frameworks in order to catalyse and adequately manage the expected increase of financial resources. The project will support work pilot countries whose governments are supportive of this approach, laying the groundwork for a major focus of discussion on biodiversity finance at the CBD COP-11 in 2012.

Critically, also, the project will build on the process currently being overseen by the Secretariat of the Convention on Biological Diversity (SCBD) through which countries are revising their National Biodiversity Strategy and Action Plans (NBSAPs) to tie in with the CBD’s Strategic Plan 2011-2020, providing policy-makers with a new vehicle and opportunity for promoting enhanced mainstreaming of biodiversity considerations in development planning (see Section 2.3).

Thee final selection of countries has to be geographically balanced and representative of all types of developing countries (including megadiverse countries, Small Island Developing States (SIDS), Least Developed Countries (LDCs) and emerging and transition economies).

The government of the country has shown commitment to mainstreaming biodiversity concerns into national development planning, to quantifying the biodiversity management financing gap and to finding innovative ways to finance biodiversity management in the medium to long term, through a combination of state, private sector and ODA resources.

The country has a plan in place to update its National Biodiversity Strategy and Action Plan, in many cases receiving assistance through UNDP’s Biodiversity Global Programme to ensure that the new NBSAP includes financial needs assessments, addresses the CBD Strategic Plan for 2011-2020, and becomes a more relevant policy instrument through its integration into development plans, development finance and strategies aimed at managing climate risk.

The country has a current or recently completed project funded by the Global Environment Facility or other sources through UNDP dealing with financing of Protected Areas, economic valuation of biodiversity and ecosystem services, or capturing values through Payments for Ecosystem Services – generating valuable new knowledge and data, and building the capacity of a range of national and sub-national stakeholders to take this work further.

The key project components as  stated in the original agreement was to use the three complementary -also key project components - approaches below to help developing countries increase the importance attributed to biodiversity and in consequence bridge the financing gap.

Component 1: Integrate biodiversity and ecosystem services in sectoral and development policy, planning and budgeting

Decades of development experience have taught us that it is important to mainstream biodiversity into national development plans, as well as into the policy, planning and financing frameworks of other key sectors (including National Adaptation Programs of Action and Nationally Appropriate Mitigation Actions), making best use of available mutual benefits. Even though many countries have mainstreamed wider environmental concerns into national development and poverty reduction strategies (National Development Plans/Poverty Reduction Strategy Papers), the linkages to biodiversity and ecosystem services often remain poorly articulated. To address this shortcoming, it is imperative that new analyses, tools and operational approaches are developed for determining and quantifying the benefit ecosystems provide to other sectors; the threats posed by sectors to biodiversity and policy measures to reduce these threats (which will have a bearing on the costs of addressing biodiversity loss).

Component 2: Assess the financing and governance needs for the management and conservation of biodiversity and ecosystem services

Too often the debate on financing has focused on revenue generation only, without an assessment of the actual investment needs. Any strategy aimed at deepening environmental finance at the country level will need to start with an evaluation of the true costs of management and its cost-effectiveness, as well as of the barriers to successful implementation. Several fundamental questions need to be answered in this regard, including: (a) what are the cost coefficients for the delivery of basic biodiversity management functions against which cost-effectiveness can be assessed? What opportunities and barriers exist to improved cost-effectiveness? (b) How much would it cost to remove the above barriers? What other options are available? What are the costs of inaction? (c) What financing is hence required at a national level to meet national targets set in terms of the global biodiversity targets adopted under the new CBD Strategic Plan for the period 2011-2020?

To address these questions in a comprehensive and rigorous manner, new methodologies and analytical tools will be required, including the development of costed action plans for addressing the gaps and barriers. The resulting analyses will also contribute valuable elements to the CBD’s Resource Mobilization Strategy, and to the formulation of the next generation of NBSAPs which will require an assessment of financial needs.

Component 3: Identify, combine and sequence different sources of funds to meet biodiversity-financing needs

Once the costs of biodiversity management have been projected, the revenue side of the funding equation will need to be addressed. Countries will need to identify, combine and sequence different sources of funds, to meet their biodiversity financing needs. A large number of potential financing instruments exist, including innovative financing and market mechanisms, such as carbon markets, biodiversity offsets and payments for ecosystem services, including sharing of benefits arising from the utilization of genetic resources. However, there is no one-size-fits-all strategy for environmental finance. The strategies that need to be employed to tap into each of these funding sources will vary considerably. An assessment of the suitability of different funding options needs to be undertaken, with full consideration of country-specific circumstances, in order to determine how financing can be configured to meet the previously defined financial needs. Particular attention will be paid to the potential risks and barriers related to the implementation of innovative financing instruments, given country-specific circumstances, ways and means to overcome these barriers when possible, and the potential need for environmental and social safeguards.

Baseline CTA-BD is appointed from within the UNDP: neither other staff nor national projects units selected. Awareness about the project exists among key global experts, but no results available or disseminated.

Indicators: Technical and administrative staff recruited and teams completed and operational. CBD side events and other meeting presentation/participations organized. Evaluation meeting held. Follow-up project aimed at wider rollout of the method and tools.

Decades of development experience have taught that it is important to mainstream biodiversity into national development plans, as well as into the policy, planning and financing frameworks of other key sectors (including National Adaptation Programs of Action and Nationally Appropriate Mitigation Actions), making best use of available mutual benefits. Even though many countries have mainstreamed wider environmental concerns into national development and poverty reduction strategies (National Development Plans/Poverty Reduction Strategy Papers), the linkages to biodiversity and ecosystem services often remain poorly articulated. To address this, it is imperative that new analyses, tools and operational approaches are developed for determining and quantifying the benefit ecosystems provide to other sectors; the threats posed by sectors to biodiversity and policy measures to reduce these threats (which will have a bearing on the costs of addressing biodiversity loss).

The debate on financing has often focused on revenue generation only, without an assessment of actual investment needs. Any strategy aimed at deepening environmental finance at the country level needs to start with an evaluation of the true costs of management and its cost-effectiveness, as well as of the barriers to successful implementation. Several fundamental questions need to be answered in this regard, including: (a) What are the cost coefficients for the delivery of basic biodiversity management functions against which cost-effectiveness can be assessed? What opportunities and barriers exist to improved cost-effectiveness? (b) How much would it cost to remove the above barriers? What other options are available? What are the costs of inaction? (c) What financing is hence required at a national level to meet national targets set in terms of the global biodiversity targets adopted under the new CBD Strategic Plan for the period 2011-2020. To address these questions in a comprehensive and rigorous manner, new methodologies and analytical tools will be required, including the development of cost action plans for addressing gaps and barriers. The resulting analyses will also contribute valuable elements to the CBD’s Resource Mobilization Strategy, and to the formulation of the next generation of NBSAPs, which will require an assessment of financial needs.

Once the costs of biodiversity management have been projected, the revenue side of the funding equation will need to be addressed. Countries will need to identify, combine and sequence different sources of funds, to meet their biodiversity financing needs. A large number of potential financing instruments exist, including innovative financing and market mechanisms, such as carbon markets, biodiversity offsets and payments for ecosystem services, including sharing of benefits arising from the utilization of genetic resources. However, there is no one-size-fits-all strategy for environmental finance. An assessment of the suitability of different funding options needs to be undertaken, with full consideration of country-specific circumstances, in order to determine how financing can be configured to meet the previously defined financial needs. Particular attention will be paid to the potential risks and barriers related to the implementation of innovative financing instruments, given country-specific circumstances, ways and means to overcome these barriers when possible, and the potential need for environmental and social safeguards.

Through the COP-12 decision on Resource Mobilisation (UNEP/CBD/COP/DEC/XII/3), CBD parties formally endorsed the BIOFIN methodology, recommending countries to apply its tools and calling for BIOFIN to further upscale. German IKI report.

All three project are confirmed to be complementary to their collective contribution to the improvements in the nation’s financial architecture for sustainable development. Here, the evolution and history of BIOFIN is important. The Stern report published in 2007 brought the evidence and knowledge about ecosystem services and valuation to a new level. Global champions, including Tony Blair, took it forward and made it an important economic and development issue with its conceptual leap between development, biodiversity and nature. WAVES was launched building on this work on national accounts at COP 2010. TEEB had also been successfully raising the awareness of the value of ecosystem services and linkages to other economic sectors. BIOFIN was to address the need for biodiversity financing and answer the question of how to fund the strategic plans. A working group was preparing a manual on financing the strategic biodiversity plan and assessment of funding streams and gaps. The bigger picture was that this work was part of a dialogue around the inadequacies of ODA development and a need to leverage private sector funding for development. Biodiversity offset is a case in point. The financing solutions were not as obvious as the areas for climate change financing, such as energy and investments infrastructures and less carbon-intensive pathways.

followed by the G-8 countries recommendation for a global study - TEEB project that had successfully began to advance awareness of biodiversity values in the market. WAVES was launched in 2010 to work on natural capital accounts (interview with WAVES Project director World Bank).By greening national income accounts, the project aims to enable policy makers to take the economic value of biodiversity and ecosystem services into account when making policy decisions. The EC-UNDP project will build on the tools to be developed through Waves, assisting countries to develop financing plans and identify funding options for the conservation of biodiversity and the maintenance of ecosystem services.

The TEEB has completed its set of reports for national, international, regional and local policy-makers and the business sector, as well as its final synthesis report. It continues to undertake follow-up initiatives, particularly through UNEP-supported valuation work in countries.

The TEEB has completed its set of reports for national, international, regional and local policy-makers and the business sector, as well as its final synthesis report and continues to undertake follow-up initiatives, particularly through UNEP-supported valuation work in countries.

FASPS first coordinated with us regarding WAVES, it was not clear how biodiversity will be incorporated in the mangroves component for DRR. When you say mangrove, they are looking at single species of mangrove only for DRR. Diversifying mangrove species gives higher value to the mangrove formation for DRR. The diversity of mangrove species is critical. BIOFIN can do work on assisting BMB in terms of developing further the biodiversity account for WAVES in terms of educating and raising awareness on the importance of biodiversity in the context of WAVES.

The overall goal of the project is to better integrate ecosystem assessment and economic valuation of ecosystem services into sustainable national development planning. The five pilot countries are different from those involved in the EC-UNDP project, and ProEcoServ does not have a financial focus, but there will be significant areas where learning can be shared between the two projects.

Long-term engagement on a countries finance plan is progressive with several stages, and this work also provides lessons for future NBSAP action planning (to involve finance assessments along the way and resource mobilization tactics). The technical need for biodiversity finance needed assessments. Step 4 of the financing plan requires intense engagement with the private sector. There have to be platforms and central frameworks already in place to work with. NBSAP process has not targeted the policy incentive or education needed to spur private sector engagement.

According to members interviewed, the steering committee met every three months until the  project team was on boarded  and then , less and less. In total, there were 9 steering committee meetings (Summarized and Reviewed in Annex). Review of the minutes and decision show the extent to which the original partners were involved in guiding project implementation in the early stages. This group was instrumental guiding the implementation approach and also development of the methodology and in the early days to a limited extent[i]. The first draft methodology workbook was reported by project management to have been entirely developed by the project team (first project manager).

2013

- BIOFIN activities started in 12 countries; Botswana, Chile, Costa Rica, Ecuador, Indonesia, Kazakhstan, Malaysia, Peru, Philippines, Seychelles, South Africa and Uganda.

- The first draft of the BIOFIN workbook was developed. It consisted of 3 steps, a policy and expenditure analysis, costing of national finance needs for biodiversity and developing a resource mobilisation plan.

2014

- Colombia, Fiji, Guatemala, India, Mexico, Thailand and Zambia joined.

- The 1st Global BIOFIN workshop brought together over 100 participants from BIOFIN countries, donors and related initiatives to discuss the draft BIOFIN methodology.

- The BIOFIN Website was created: www.biodiversityfinance.net.

- BIOFIN Twitter and YouTube were launched.

- The user-friendly BIOFIN workbook 2014 was released in November at the CBD COP 12 in Korea, including a set of datasheets

2015

- Eleven new countries joined BIOFIN; Belize, Bhutan, Brazil, Cuba, Georgia, Kyrgyzstan, Mongolia, Mozambique, Rwanda, Sri Lanka and Vietnam.

- Three regional workshops (around 150 participants) were organised in Kuala Lumpur (Malaysia), Quito (Ecuador) and Gaborone (Botswana). Through these workshops, representatives from Ministries of Finance and Environment, National BIOFIN teams and UNDP offices, learned about the BIOFIN methodology and shared feedback of their learning.

The project had been operating with a floating target for result (see monitoring), with good and bad aspects. This dichotomy was compounded by the sudden influx of donor funding.

Reporting on BIOFIN. Qualitative and explanatory frameworks offer an opportunity to complement quantitative indicators. BIOFIN processes involve tangible (measurable) and intangible processes in terms of policy making and government awareness. Therefore, the ME template includes both quantitative and qualitative fields to report on. BIOFIN wants to shift from accountability to learning-oriented ME. Having the complete picture is expected to reduce the learning curve for core and non-core countries. Timely and accurate monitoring will support strategic decision-making, improve overall data quality, and maximize the expected results. The new reporting template (Annex) thus focuses on progress as stated in BIOFIN reports and recommendations, BIOFIN process (institutional and political change and action, results i.e. policies), BIOFIN results and BIOFIN Indicators (quantitative).

The original GEF co-financing projects flagged included.

- Ecuador: National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in Ecuador (PIMS 4828, Atlas Project Id: 00082536); [GMS: 10% - GEF]

- Ecuador: Financial Sustainability for the National System of Protected Areas (SNAP) (PIMS 4142, Atlas Project Id: 00073902). [GMS: 10% - GEF]

- Kazakhstan: National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in Kazakhstan” (PIMS no: 4877, Project Id: 00081748). [GMS: 10% - GEF]

- Malaysia: National Biodiversity Planning to Support the Implementation of the CBD 2011 – 2020 Strategic Plan in Malaysia (PIMS: 4803; Project number: 00082290) [GMS: 10% - GEF and 6% for 11888 fund]

- Malaysia: Enhancing Effectiveness and Financial Sustainability of Protected Areas in Malaysia (PIMS no: 3967; Project number: 00082355). [GMS: 10% - GEF]

- Philippines: “National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in the Republic of the Philippines” (PIMS: 4809, Project id: 00082869). [GMS: 10% - GEF]

- Seychelles: “National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in Seychelles (Project Atlas no: 00080329; PIMS no: 4862)”. [GMS: 10% - GEF]

- South Africa: “National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in South Africa (PIMS no. 4894, Atlas ID: 00083783). [GMS: 10% - GEF]

The annual progress report includes the narrative part for all donors and countries, the financial report is provided to each donor separately. This is the list of co-financing projects.

List of Co-financing Projects:

- Ecuador: National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in Ecuador (PIMS 4828, Atlas Project Id: 00082536); [GMS: 10% - GEF]

- Ecuador: Financial Sustainability for the National System of Protected Areas (SNAP) (PIMS 4142, Atlas Project Id: 00073902). [GMS: 10% - GEF]

- Kazakhstan: National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in Kazakhstan” (PIMS no: 4877, Project Id: 00081748). [GMS: 10% - GEF]

- Malaysia: National Biodiversity Planning to Support the Implementation of the CBD 2011 – 2020 Strategic Plan in Malaysia (PIMS: 4803; Project number: 00082290) [GMS: 10% - GEF and 6% for 11888 fund]

- Malaysia: Enhancing Effectiveness and Financial Sustainability of Protected Areas in Malaysia (PIMS no: 3967; Project number: 00082355). [GMS: 10% - GEF]

- Philippines: “National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in the Republic of the Philippines” (PIMS: 4809, Project id: 00082869). [GMS: 10% - GEF]

- Seychelles: “National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in Seychelles (Project Atlas no: 00080329; PIMS no: 4862)”. [GMS: 10% - GEF]

- South Africa: “National Biodiversity Planning to Support the implementation of the CBD 2011-2020 Strategic Plan in South Africa (PIMS no. 4894, Atlas ID: 00083783). [GMS: 10% - GEF]

*) The total amount of funds could have small changes due to the exchange rate of incoming funding transfers.

**) The total expenditures/delivery rate does not include commitments. 2016 expenditure figures are preliminary pending UNDP’s closure of accounts. Unspent funds from the EU contribution will be deducted from the final tranche of the agreement. This unspent balance includes funds planned for audit costs which have been paid by UNDP along with some remaining country funds which have been covered by the UNDP Country Office (less than 1% of the contribution)

***) A co-financing contribution of USD 3.2 million has been ensured from 2012-2015 as parallel contribution to the project through GEF projects in Ecuador, Kazakhstan, Malaysia, Philippines, Seychelles, South Africa. In 2016, a total amount of USD 188,500 was planned as BIOFIN co-financing in Bhutan and Kyrgyzstan through the contribution of UNDP RR’s Funds, PEI, INDC, GNHC-CIF. The 2017 Annual Work Plans include further co-financing from UNDP Zambia (USD 300,000), PEI & NCSA III Kyrgyzstan (USD 107,000) while other contributions are under discussion (e.g., Government of Chile).

The challenge was to get the data on a programme level because taking the programme from the Ministry of Finance (3–4%) or governmental organizations and agencies was difficult. The programme needed to go into specific projects in deep detail. Coefficients were essential to the programme so that much goes into biodiversity. The programme approach for biodiversity attributes can be used for good data. Some countries don’t have an attributions rate, but to have a firm understanding of this very difficult project, it is advisable to have different people on the team. (India has already done this in budget review—a good step forward).

Biodiversity and Ecosystem Services Network (Bes-Net)

BIOFIN has worked with Bes-Net on a second major platform for knowledge sharing, designing a dedicated resource module on biodiversity finance to be launched soon. (See www.besnet.world for the platform with the existing four modules.) The new module will harbor prioritized publications collected by the BIOFIN team. Closely aligned with IPBES areas of work and capacity building needs, the Biodiversity and Ecosystem Services Network (Bes-Net) is a capacity sharing network of networks that promotes dialogue between science, policy and practice for more effective management of biodiversity and ecosystems, contributing to long-term human well-being and sustainable development.

Chile reported on the process as follows. It began with a mission by technical assistants to design country-level action plans, including a scoping mission, undertake bilateral discussion and work planning. Local teams then set up a series of the implementation approaches to work through the national steering committee and or technical committees at both national and subnational level. Capacity was reported to be stretched for expenditure analysis, including across the related disciplines, i.e. climate, DRR.

UNDP has 2 main implementation modalities, the other being NIM – National Implementation Modality – working through formal government accounts and contracts, while DIM is lead by government but administered through UNDP offices.

A separate meeting with the global team the 2 days after the regional workshop in Antigua, Guatemala

The need for more accurate assessment of biodiversity finance flows was one of the reasons why BIOFIN was developed. (Page 29) Mobilizing Resources for Biodiversity and Economic Development (December 2016).

The new communications Specialist is on board since February 2017