## Slide 1: Socio-economic development of communities around radioactive sites in Kyrgyzstan funded by the Government of Russian Federation
Alisher Nazirov
May 2017
Final Evaluation
Preliminary Findings and Recommendations

## Slide 2: Purpose of Final Evaluation
Assess the overall project progress, relevance, efficiency and effectiveness;
Assess the progress in achieving expected outputs as well as realized intended and unintended results and effects of the project;
Collect quantitative and qualitative data, including a defensible choice of indicators, which leads to credibility of findings;
Highlight key /major results, gaps, lessons learned, methodologies and good practices;
Identify concrete options and objectives for further support in this area, including scalability and replication of the project interventions.

## Slide 3: Project Components
Socio-economic development of communities around radioactive sites in Kyrgyzstan
Increasing local population awareness and creating a system for regular environmental monitoring
Rehabilitating social and economic infrastructure and developing income-generating activities
Supporting local initiatives with funding to be provided by the small grant fund
Capacity building of local authorities and communities

## Slide 4: Evaluation Areas of Focus
Relevance - the extent to which the objectives of the project are consistent with the needs of intended beneficiaries, UNDP and the Kyrgyz Republic overarching strategies and policies.
Effectiveness - the extent to which the project achieves its objectives and outputs.
Efficiency - a measure of how resources/inputs (funds, expertise, time, etc.) are converted into outputs.
Sustainability - measuring whether the benefits of a project are likely to continue after its completion.

## Slide 5: Evaluation Areas of Focus
Human Rights and Gender - which groups benefit and which groups contribute to the intervention under review;
Partnerships and cooperation - the level and quality of coordination and collaboration arrangements that have been made with partners and stakeholders;
Lessons learnt - best practices and innovative ideas and approaches in management and implementation of activities.
Recommendations on how the project can most effectively continue to support appropriate central authorities, local communities and civil society in a long-term perspective.

## Slide 6: Methodology
Desk review of relevant documents;
Consultations with UNDP management and staff;
Semi-structured interviews with pre-determined sets of questions for project staff, stakeholders and beneficiaries;
Site visits (35);
Focus groups;
Summary table of the four project components;
Surveys (18);
A presentation to UNDP CO to validate preliminary findings and recommendations.

## Slide 7: Methodological Challenges
The project activities are still underway, which hinders to finalize the overall achievement of the project – the data to be provided in the report might be incomplete;
Lack of logical framework within the project document to compare final results with the baseline or target indicators;
The three outputs provided in the project annual workplans for 2015 and 2016 do not seem to represent all four components of the project.

## Slide 8: Relevance – NSDS 2013-2017
Chapter 4 - Resolving social issues and challenges;
Chapter 5 - Environmental protection to ensure sustainable development;
Chapter 6 - Economy as principal driver of sovereignty and national security;
Chapter 8 - Improving business environment and investment climate;
Chapter 10 - Development of strategic industries of the economy;
Chapter 11- Economic development of the regions.

## Slide 9: Relevance – UNDAF 2012-2016
Pillar C: Inclusive and Sustainable Job-Rich Growth for Poverty Reduction
Outcome 1 (or 5 in CPAP) - By the end of 2016, population, especially vulnerable groups, benefit from inclusive growth leading to decent and productive employment and improved access to productive natural resources, markets, services and food security; Indicators 4-4
Outcome 2 (6) – By the end of 2016 sustainable management of energy, environment and natural resources practices operationalized; Indicators 2-5
Outcome 3 (7) – By 2016, DRM framework in compliance with international standards, especially the Hyogo Framework of Action; Indicators 2-3

## Slide 10: Relevance – CPAP 2012-2016
Output 4.2 - Local authorities are able to expand opportunities for income generation and employment among vulnerable groups with the focus on environmental security and gender equality;
Output 6.2 - Disaster risk assessment and monitoring system established for effective socio-economic development programming;
Output 6.3 - Local level DRM actors engaged in comprehensive regional development, integrating DRR approach into sectoral policies and practices. Best DRR practices institutionalized for sustainable community development.

## Slide 11: Efficiency
Efficiency captures the extent to which UNDP is producing its planned outputs in relation to expenditure of resources.
Management arrangements for the implementation of UNDP activities have been uniformly praised by partners and recipients of assistance for their efficiency and responsiveness;
Project implementation under Naryn ABD for cost-efficiency;
Procurement Assistant based in Bishkek as most activities are carried out at the CO level;
Tendering process by local municipalities;
Co-funding ratio of total 67 projects only made up 24.6%.

## Slide 12: Effectiveness
20 events in total (5 in each site) conducted to increase local population awareness on DRR attended by 387 people (including 220 female) and basis created for a regular environmental monitoring system;
13 projects are implemented for developing income-generating activities (48 jobs created, including 30 female); 19 training events arranged attended by 67 persons (26 female);
42 local initiatives are supported through small grant funds to rehabilitate social and economic infrastructure (16 jobs created, including 11 female);
15 capacity building events conducted in total, attended by 43 people (19 female) national/local authorities and communities.

## Slide 13: Effectiveness ctd.
64 (64) poor households have increased income for livelihood improvement – vs 350 targeted (18%);
13 (13) SMEs created including ones on processing of agricultural products and rendering service – vs 35 targeted (37%);
10,000 (15,000) people (at least 40% are women) received access to rural infrastructure vs 15,000 targeted (67%);
43 (85) local government officials developed their skills on: social project development and procurement management; delivering public services; maintaining social infrastructure; developing tourism vs 80 targeted (56%);
52 (67) projects are operating on a sustainable basis vs 50 targeted;
19 (19) national and local authorities have strengthened capacity in integrated DRR;
Delays caused mainly by weather and public procurement processes did not affect the quality of projects. Other effects.

## Slide 14: Sustainability
Sustainability is about being strategic and looking to the future.
54 projects out of total 67 are social infrastructures, which is under the respective Ayil Okmotu;
Equipment and tools provided in 13 IG belong to the respective municipality for 2-3 years depending on the cost based on agreements;
Model provision on Single Windows developed; Draft Governmental Decree “Provision on a comprehensive monitoring and prognosis of emergencies in Kyrgyz Republic”; Changes and amendments to the Law on Civil Protection (will be adopted by the end of the year); Strategy on the Comprehensive Protection of Population in Emergencies till 2030 with action plans for every 5 years;
Capacity building and further support is needed to qualify for public tender (bakery/greenhouse-kindergarten);
Juice production workshop in Kadzhi Sai works only in Aug-Sep;

## Slide 15: Partnership
Close collaboration with donor agency, satisfied with all programmes;
Collaboration with district and municipality was effective: Total: $1,133,950; UNDP $854,802; co-funding $279,148 (24.6%);
Project signboards have been across all sites with information on UNDP and counterpart contribution;
Partnership with other local/international agencies: GIZ, Destination Karakol, Respective villages Keneshes, Village Advisory Services, the two research institutions of the RF, Scientific and Technical Council of the MCHS, National Red Crescent Society, Association of Beekeepers, Fish Farmers Association.

## Slide 16: Human Rights and Gender
Almost half of 15,000 beneficiaries are female;
Reports reflect on gender disaggregation;
Annual Gender Mainstreaming Plans are developed by Naryn ABD with budget specified and reported at the end of the year;
AWPs (Gender Specific activities and indicators) and ProDoc (Gender Marker) are cleared also by Country Gender Coordinator and the ProDoc also screened on Gender, Human Rights and Environment;
Most activities involved social infrastructure, which ensure access to local population without any exception.

## Slide 17: What do the UNDP partners say
We learned a lot through trainings and awareness raising campaigns;
UNDP is performing well (donor) and authorities;
We are grateful to UNDP for its responsiveness (beneficiaries);
Approach is different from those agencies, which support was limited to certain activities. It is comprehensive, participatory and inclusive;
Requested to continue the project.

## Slide 18: Lessons Learnt
Radiation measurement before the project and its results has enabled local communities to change their perspectives and hope for a better future;
Municipalities taking care of tendering process along with ensuring efficiency and transparency, also contributed to ownership;
SGP has proved to be a proper mechanism as better ideas are submitted and supported;
Lack of RRF and pre-defined end-project targets, although provided certain flexibility in planning, overall caused ambiguity in assessing results expected/formulated at the project design phase;
Flexibility at the project levels have been critically important: hiring small grants consultant, training of municipalities on online public procurement, conducting monitoring while traveling for other purposes, election processes considered, etc.
Results are more tangible when the approach is comprehensive.

## Slide 19: Opportunities in Moving Forward
Willingness of local authorities to co-fund and support similar initiatives;
Potential for development is available (for instance, tourism in Kadzhi Sai and Ak Tyuz, etc.);
Municipalities gained experience of working with international organizations, capacitated on tendering process;
Population have skills on project design, implementation and reporting.

## Slide 20: Recommendations
Project logic (theory of change) should be clear from the project document, monitoring indicators should be realistic and appropriate and logically linked to CPAP and ideally UNDAF (in line with Rec 3 of the ADR);
Streamline cooperation and information sharing with the project stakeholders, especially donor and the national partner, through Project Steering Committee Meetings;
Involve the national partner in joint monitoring visits as well;
Deepen horizontal collaboration with other UNDP projects (for example, AFT);
Notes: (in Naryn the meeting was combined with the Comprehensive Development Programme (donor, UNDP, local authorities, Governor of Naryn Region, without IssykKul and Chui) in 2015; In Feb 2016 the donor and national partner were in the grant committee meeting

## Slide 21: Recommendations
In case decision on Phase II is made, it is advisable to start in parallel with the recultivation activities (people’s positive views would facilitate recultivation activities);
Radiation measurement to be conducted before, during and after project completion in every site;
In designing water supply projects support also to be envisaged on improving the existing management model;
Under similar circumstances and volume, a grant specialist to be hired;
Experience sharing /site visits among participating communities.

## Slide 22
Thank you very much
If you have any suggestions and comments, please send them to
alisher.mn@gmail.com