Terms of Reference (ToR)

Individual consultant for project final evaluation of “Management and Disposal of PCBs in Rwanda”

| # Application Type: | # External Vacancy |
| --- | --- |
| # Job Title: | # Open to International and national consultant |
| # Category: | # Final evaluation |
| # Duty Station: | # Kigali, Rwanda |
| # Application Deadline: | # 25th October 2017 |
| # Type of contract: | # Individual contract (national or international) |
| # Expected starting date: | # Immediately |
| # Expected completion date: | # 20th December 2017 |
| # Duration of assignment: | # 30 working days (over a period of 7 weeks) |
| # Language required | # English |

- BACKGROUND AND CONTEXT

Exposure to Polychlorinated Biphenyl’s (PCBs) has been demonstrated to cause environmental and health effects including cancer, as well as a variety of other adverse effects on the immune, reproductive, nervous, and endocrine systems. Due to PCBs' environmental toxicity and negative effects on human health, PCBs production was banned by the United States Congress in 1979 and by the Stockholm Convention on Persistent Organic Pollutants (POPs) which was adopted in 2001 and entered into force in 2004. The convention requires its parties to take measures to eliminate or reduce the release of POPs into the environment.

In its efforts to manage POPs including PCBs, Rwanda ratified the Stockholm Convention in July 2002. The country also deposited a National Implementation Plan (NIP) with the Stockholm Convention in 2007 that outlined the National Action Plan for the management of POPs in the country.

In order to support the implementation NIP, the Global Environment Facility (GEF) and United Nations Development Programme (UNDP) provided funds with co-financing from Energy, Water and Sanitation Authority (currently Rwanda Energy Group Limited) and Rwanda Environment Management Authority (REMA) to support the Management and Disposal of PCBs project in Rwanda. This project is implemented by REMA in collaboration with relevant government institutions. The project fits within the country’s evolving priorities associated with sound management of chemicals and environmental management initiatives. The project is consistent with the following UNDAP (2013 -2018) outcome: Rwanda has an in place improved systems for: sustainable management of the environment, natural resources and renewable energy resources, energy access and security, for environmental and climate change resilience, in line with Rio+20 recommendations for sustainable development.

The project has an overall objective of providing Rwanda with the tools to achieve effective compliance with respect to its convention obligations and to substantively minimize the environmental and health risks of PCBs, both locally and globally. The project has the following components:

- Complete PCB inventory through enhanced cooperation with the Government bodies and equipment holders and selection of options for PCB disposal;

- Legislative support to aid the operation of PCB management system;

- Stakeholders and public sensitized, PCB equipment holders handle equipment in well informed and responsible manner;

- Safe disposal of PCB equipment, oils and waste material.

Implementation of this project has a major global environmental benefit in the mitigation or elimination of risks associated with the release of PCBs into the environment and their subsequent global distribution with resultant ecological and human health impacts from the exposure to this chemical. In Rwanda, the project will greatly improve the management and disposal of PCBs stockpiles and waste while at the same time strengthening technical, regulatory and institutional capacity to handle PCBs.

- EVALUATION PURPOSE

The final evaluation of the project will be conducted according to the guidance, rules and procedures established by UNDP and GEF as reflected in the UNDP Evaluation Guidance for GEF Financed Projects.

The evaluation report produced is aimed at critically assessing the stages of the project through participatory approaches, measuring to what extent the objective/outputs/activities have been achieved against the results and resources framework, and identifying factors that have hindered or facilitated the success of the project. The lessons learned section is aimed at capturing key lessons to assess the success of the project based on several criteria, so that the legacies of the project will be replicated and sustained beyond the project lifetime. Furthermore, the final evaluation is intended to identify weaknesses and strengths of the project design and implementation, and to come up with recommendations for any necessary changes in the overall design and orientation of similar projects  as well as assessing the achievements the project outputs and outcomes. The results and recommendations of the evaluation would therefore help UNDP and implementing partners to document lessons learnt and best practices and prepare for the next project cycle.

- EVALUATION SCOPE AND OBJECTIVES

Objectives

The objectives of the evaluation are to assess the achievement of project results, and to draw lessons that can both improve the sustainability of benefits from this project, and aid in the overall enhancement of UNDP programming.

The final evaluation main objectives are the following:

- Assess the Project’s implementation strategy.

- Assess the relevance, efficiency, effectiveness, sustainability, and impact of the interventions.

- Assess the mainstreaming of UNDP programming principles (gender, human rights, RBM, environment, capacity building)

- Assess the Project’s processes, including budgetary efficiency

- Assess the extent to which planned activities and outputs have been achieved.

- Identify the main achievements and impacts of the project’s activities

- Identify the underlying causes and issues of non-achievement of some targets

- Assess the project exit strategy

- Document lessons learnt

- Formulate key recommendations for the way forward for the programme

Scope

The evaluation covers the implementation period of the project, from January 2012 up to December 2017. The geographic coverage of the evaluation is the whole country (Rwanda). The scope of the final evaluation covers all activities undertaken in the framework of the project. This refers to:

- Planned outputs of the project compared to actual outputs and the actual results as a contribution to attaining the project objectives.

- Problems and necessary corrections and adjustments to document lessons learnt.

- Efficiency of project management, including the delivery of outputs and activities in terms of quality, quantity, timeliness and cost efficiency.

- Likely outcomes and impact of the project in relation to the specified goals and objectives of the project.

The evaluation comprises the following elements related to project design and implementation:

- Assess whether the project design was clear, logical and commensurate with the time and resources available;

- An evaluation of the project’s delivery of achievement of its overall objectives;

- An evaluation of project performance in relation to the indicators, assumptions and risks specified in the logical framework matrix and the Project Document; An assessment of the scope, quality and significance of the project outputs produced to date in relation to expected results; Identification of any programmatic and financial variance and/or adjustments made during the duration of the project and an assessment of their conformity with decisions of the PSC and their appropriateness in terms of the overall objectives of the project;

- An evaluation of the project’s contribution to the achievements of UNDAP’s outcome and outputs as well as the project’s contribution to national government strategies such as the EDPRS II and Vision 2020;

- Identification and, to the extent possible, quantification of any additional outputs and outcomes beyond those specified in the Project Document;

- An evaluation of project coordination, management and administration. This includes specific reference to:

  - Organizational/institutional arrangements for collaboration among the different stakeholders involved in project arrangements and execution;

  - The effectiveness of the monitoring and evaluation framework/mechanisms used by REMA in monitoring on a day to day basis, progress in project implementation;

  - Administrative, operational and/or technical challenges and constraints that influenced the effective implementation of the project;

  - An assessment of the functionality of the institutional structure established and the role of the Project Steering Committee (PSC);

  - Financial management of the project, including the balance between expenditures on administrative and overhead charges in relation to those on the achievement of substantive outputs.

- A prognosis of the degree to which the overall objectives and expected outcomes of the project were met;

- Progress towards sustainability and replication of project activities;

- Assess the extent to which the design, implementation and results of the project have incorporated a gender equality perspective and human rights-based approach

- Assess of the extent to which the design, implementation and results of the project have incorporated the environmental sustainability concerns and make recommendations accordingly

- Lessons learned during project implementation;

- Evaluate the project’s exit strategy in terms of quality and clarity

- EVALUATION

Evaluation criteria & ratings

The project will be evaluated on the basis of the DAC evaluation criteria:

- Relevance: measures whether the project addresses an important development goal and whether its objectives are still valid.

- Effectiveness: measures whether the project activities achieve their goals.

- Efficiency:  measures the cost effectiveness, i.e. the economic use of resources to achieve desired results.

- Sustainability: measures whether the benefits of the project are likely to continue after donor funding has been withdrawn. The project needs to be environmentally as well as financially sustainable.

- Impacts of intervention:  measure the positive and negative changes produced by the project, directly or indirectly, intended or unintended.

An assessment of project performance will be carried out, based against expectations set out in the Project Logical Framework/Results Framework (see Annex 1), which provides performance and impact indicators for project implementation along with their corresponding means of verification. The evaluation will at a minimum cover the criteria of: relevance, effectiveness, efficiency, sustainability and impact. Ratings must be provided on the following performance criteria. The completed table must be included in the evaluation executive summary.   The obligatory rating scales are included in Annex 4.

| Evaluation Ratings: |  |  |  |
| --- | --- | --- | --- |
| 1. Monitoring and Evaluation | rating | 2. IA& EA Execution | rating |
| M&E design at entry |  | Quality of UNDP Implementation |  |
| M&E Plan Implementation |  | Quality of Execution - Executing Agency |  |
| Overall quality of M&E |  | Overall quality of Implementation / Execution |  |
| 3. Assessment of Outcomes | rating | 4. Sustainability | rating |
| Relevance |  | Financial resources: |  |
| Effectiveness |  | Socio-political: |  |
| Efficiency |  | Institutional framework and governance: |  |
| Overall Project Outcome Rating |  | Environmental : |  |
|  |  | Overall likelihood of sustainability: |  |

Evaluation questions

More specifically, the final evaluation aims at addressing the following questions for each evaluation criteria:

Relevance

- Where is this Project being implemented? How was the Project site selected? What has been the main focus of the project implementation so far? Who are the main beneficiaries? How were they selected? How was the project aligned to the national development strategy (EDPRS 2, Vision 2020)?

- The extent to which the project activities are suited to the priorities and policies of the target group, recipient and donor.

- To what extent are the objectives of the project still valid?

- Are the activities and outputs of the project consistent with the overall goal and the attainment of its objectives?

- Are the activities and outputs of the project consistent with the intended impacts and effects?

Effectiveness

- To what extent were the objectives achieved?

- What were the major factors influencing the achievement or non-achievement of the objectives?

- Did the activities contribute to the achievement of the planned outputs?

- Have the different outputs been achieved?

- What progress toward the outcomes has been made?

- To what extent the design, implementation and results of the project have incorporated a gender equality perspective and human rights based approach? What should be done to improve gender and human rights mainstreaming?

- What has been the result of the capacity building/trainings interventions? Were qualified trainers available to conduct training?

- How did UNDP support the achievement of project outcome and outputs?

- How was the partnership strategy conducted by UNDP? Has UNDP partnership strategy been appropriate and effective? What factors contributed to effectiveness or ineffectiveness? What were the synergies with other projects?

Efficiency

- Were activities cost-efficient?

- Were objectives achieved on time?

- Was the project implemented in the most efficient way compared to alternatives?

- What was the original budget for the Project? How have the Project funds been spent? Were the funds spent as originally budgeted?

- Are there any management challenges, which affected efficient implementation of the Project? What are they and how were they addressed?

Sustainability

- To what extent the design, implementation and results of the project have incorporated environment sustainability? What should be done to improve environmental sustainability mainstreaming?

- To what extent will the benefits of the programme or project continue after donor funding stops?

- What were the major factors that influenced the achievement or non-achievement of sustainability of the programme or project?

- Does the project have a clear exit strategy?

Impact of interventions

- What are the stated goals of the Project? To what extent are these goals shared by stakeholders? What are the primary activities of the programme and expected outputs? To what extent have the activities progressed? How did the project contribute to the achievement of UNDAP and EDPRS II outcomes and outputs?

- What has happened as a result of the project?

- How many people have been affected?

- Has the project contributed or is likely to contribute to long-term social, economic, technical, environmental changes for individuals, communities, and institutions related to the project?

- What difference has the project made to beneficiaries?

- How did the role of UNDP in the project contribute to the UNDAP and EDPRS II outcomes and outputs?

- METHODOLOGY

General guidance on evaluation methodology can be found in the UNDP Handbook on Monitoring and Evaluating for Development Results, the UNDP Guidelines for Outcome Evaluators, and UNDP Outcome-Level Evaluation: A Companion Guide to the Handbook on Monitoring and Evaluating for Development Results). UNDP’s Evaluation Policy provides information about the role and use of evaluation within the M&E architecture of the organization.

An overall approach and method for conducting project terminal evaluations of UNDP supported GEF financed projects has developed over time. The evaluator is expected to frame the evaluation effort using the criteria of relevance, effectiveness, efficiency, sustainability, and impact, as defined and explained in the UNDP Guidance for Conducting Terminal Evaluations of UNDP-supported, GEF-financed Projects. A set of questions covering each of these criteria have been drafted and are included with this TOR, under the section “Evaluation questions”. The evaluator is expected to amend, complete and submit this matrix (see Annex 5) as part of an evaluation inception report, and shall include it as an annex to the final report.

The evaluation must provide evidence‐based information that is credible, reliable and useful. The evaluator is expected to follow a participatory and consultative approach ensuring close engagement with government counterparts, in particular the GEF operational focal point, UNDP Country Office, project team, UNDP GEF Technical Adviser based in the region and key stakeholders. Interviews will be held with the following organizations and individuals at a minimum.

- DELIVERABLES (EVALUATION PRODUCTS)

This section presents the key evaluation products the evaluation team will be accountable for producing. The deliverables are the following:

| Deliverable | Content | Timing | Responsibilities |
| --- | --- | --- | --- |
| Inception Report | Evaluator provides clarifications on timing and method | 1 week after mission start | Evaluator submits to UNDP CO |
| Draft Final Report | Full report, (per annexed template) with annexes | Within 3 weeks of submitting inception report | Sent to CO, reviewed by RTA, PCU, GEF OFPs |
| Final Report* and policy brief | Revised report and a policy brief | Within 1 week of receiving UNDP comments on draft | Sent to CO for uploading to UNDP ERC. |
| Presentation of final report | Presentation (Power Point) of findings of report and policy brief | Within 1 week after final report | Evaluator makes a presentation |

*When submitting the final evaluation report, the evaluator is required also to provide an 'audit trail', detailing how all received comments have (and have not) been addressed in the final evaluation report.

- EVALUATION TEAM COMPOSITION AND REQUIRED COMPETENCIES

The evaluation team will be completed by 1 international or national evaluator. The consultant shall have prior experience in evaluating similar projects.  Experience with GEF financed projects is an advantage. The evaluator selected should not have participated in the project preparation and/or implementation and should not have conflict of interest with project related activities.

Evaluation methods and selection criteria

The offer will be evaluated by using the best value for money approach. Technical proposal will be evaluated on 70% whereas the financial proposal will be evaluated on 30%. Below is the breakdown for the technical proposal on which will be brought to 70%.

| Criteria | Weight | Max. Point |
| --- | --- | --- |
| Technical |  |  |
| At least master’s degree in Public Policy and Management, Public Administration, Development studies, International Development, Environmental Sciences (preferred degree in scientific field related to chemicals and waste management) | 10% | 10 |
| Minimum 10 years of relevant professional experience | 20% | 20 |
| Proven expertise, knowledge and experience in the field of environmental management (in particular waste management and chemicals) as well as knowledge of UNDP and GEF and a good understanding of gender equality, human-rights based approach and environmental sustainability concepts; | 15% | 15 |
| Overall Methodology (clear demonstration of evaluation methodology and understanding of the ToR); | 30% | 30 |
| At least 10 years’ experience in programme management support including formulation, monitoring and evaluation and RBM implementation | 15% | 15 |
| Fluent in English (written and verbal skills) and basic knowledge of French would be a value adding | 10% | 10 |

- HOW TO APPLY

Qualified and interested candidates are hereby requested to apply. The application should contain the following:

• Personal CV or P11, indicating education background/professional qualifications, all past experiences, as well as the contact details (email and telephone number) of the candidate and at least three (3) professional references;

• Brief description of why the individual considers him/herself as the most suitable for the assignment, and a methodology, on how they will approach and complete the assignment;

• Financial Proposal that indicates the all-inclusive fixed total contract price, supported by a breakdown of costs of the assignment (including daily fee, per diem and travel costs).

UNDP applies a fair and transparent selection process that will take into account the competencies/skills of the applicants as well as their financial proposals. Qualified women and members of social minorities are encouraged to apply.

Submissions are to be made by email to: offers.rw@undp.org by no later than 12h00 on 25th October, 2017. Note that no hard copy submissions will be accepted unless deemed necessary by Agency.

- EVALUATION ETHICS

The evaluation will be undertaken in-line with the following principles:

- Independence

- Impartiality

- Transparency

- Disclosure

- Ethical

- Partnership

- Competencies and Capacities

- Credibility

- Utility

Evaluation consultants will be held to the highest ethical standards and are required to sign a Code of Conduct (Annex) upon acceptance of the assignment. UNDP evaluations are conducted in accordance with the principles outlined in the UNEG 'Ethical Guidelines for Evaluations'

- IMPLEMENTATION ARRANGEMENTS

The evaluation will be conducted for a period of 30 working days of which the consultant will conduct the detailed final evaluation with methodology which will be agreed, as part of the contract finalisation process.

The consultant will start the evaluation process with an inception meeting with relevant the UNDP representative(s) and REMA’s Project Focal Point. The consultant should submit an inception plan based on the meeting within the issuance of contract. S/he will then undertake the review of documentation (home-based), interviews with key stakeholders/field visits (mission), preparation of an evaluation report and lessons learned documents (home-based). S/he will submit the draft products to UNDP CO for comments and finalise the products after receiving the feedback.

Every deliverable will be assessed by a technical team made up by representatives from REMA (Project Focal Point), the UNDP Project Manager and a Technical Advisor from GEF.

The consultant will report directly to DG of REMA, and the UNDP Country Director.

- TIME FRAME FOR THE EVALUATION PROCESS

The suggested timeline/tasks are as follows:

| Activity | Time proposed for each deliverable |
| --- | --- |
| Preparation and submission of inception report | 5 working days |
| Draft Evaluation Report | 15 working days |
| Review of Draft by stakeholders (no action required from consultant) | 5 working days* |
| Final Report and policy brief | 5 working days |
| Presentation (Power Point) | 5 working days |

*The duration of assignment will be 30 working days for the consultant over a period of 7 weeks. A review of the draft will be undertaken for 1 week, during which no action is required from the consultant.

- PRICE PROPOSAL AND SCHEDULE OF PAYMENTS

The consultancy fee will be paid as a lump sum (inclusive of all expenses related to the consultancy), and will be fixed regardless of changes in the cost components of the consultancy. The consultancy fee will be paid upon completion of the following milestones:

| % | Milestone |
| --- | --- |
| 20% | Submission and approval of inception report |
| 40% | Following submission and approval of the 1st draft terminal evaluation report |
| 40% | Following submission and approval (UNDP-CO and UNDP RTA) of the final terminal evaluation report, policy brief, presentation of the final report and management response |

UNDP is committed to achieving workforce diversity in terms of gender, nationality and culture. Individuals from minority groups, indigenous groups and person with disabilities are equality encouraged to apply. All applicants will be treated with the strictest confidence.

- ANNEXES

ANNEX 1: RESULTS AND RESOURCES FRAMEWORK

ANNEX 2: KEY STAKEHOLDERS

| No | Name and Postname | Institution | Phone/e-mail |
| --- | --- | --- | --- |
| 1 | NDIZEYE R. Eliezer | REMA | 0788683561, rusakanael@yahoo.fr |
| 2 | Dr. KAMATARI Aloys | INATEK | 0788427780, aloys.kamatari@gmail.com |
| 3. | NSENGIYUMVA Jacques | REMA | Jnsengiyumva@rema.gov.rw |
| 4 | KAKA Benon | MINIRENA | bkaka@minirena.gov.rw |
| 5 | Frank RUTEHENDA | MINECOFIN | Frank.rutehenda@minecofin.gov.rw |
| 6 | RUTIKANGA Adrien | UR/College of Science and Technology | 0788461872, rutikad@gmai.com |
| 7 | TUSHABE Rachel | REMA | 0788408339; rtushabe@gmail |
| 8 | CIZA Philbert | MINISANTE | cizaphilbert@gmail.com, 0788891626 |
| 10 | KAGISHA Wiclef | RBS | Kagisha@yahoo.fr |
| 11 | MUKAKALISA Francoise | REG ltd | 0788650818, mukafranco@yahoo.fr; fmukakalisa@ewsa.rw |
| 12 | MULINDANKAKA Evalde | MINICOM |  |
| 13 | NDIBWAMI Clement | NIRDA | 0788586044, cndibwami@gmail.com |
| 14 | GASANA SEKA | UR/College of Medicine and Health Sciences | 0788750853; gasana1@yahoo.fr |
| 15 | KABALISA Appollon | AGROTECH | a.kabalisa@kiphagro.com |
| 16 | HAKIZAMUNGU Leon | RAB | 0788686690, lhakizamungufr@yahoo.fr |
| 17 | GATERA Raymond | Rwanda Law Reform Commission | 0788424348, Gateragray@yahoo.fr |
| 18 | MUGABO John | Kigali City | 0788716358, mugjohn@yahoo.fr |
| 20 | HAREREIMANA Donath | REG ltd | 0788567420, dharerimana@ewsa.rw; |
| 22 | NIYONZIMA Steven | Cleaner Production Centre | niyosteve@gmail.com; 0788306742 |
| 23 | Prof. KALISA Daniel | UR/College of Science and Technology-Huye campus | 0788502502, daniel.kalisa@gmail.com |
| 24. | MUKAKAMARI Dancilla | ARECO | Arecorwa@yahoo.fr |
| 25. | Dr. MUKASA Joseph | ISUKU | 0788772288 |
| 26. | Bernardin UZAYISABA | UNDP | Tel: 0788873471 bernardin.uzayisaba@undp.org |

ANNEX 3: DOCUMENTS TO BE CONSULTED

- Project document

- Project annual works plan and reports

- The Montreal Protocol on Substances that Deplete the Ozone Layer

- Government of Rwanda, 2006. National Implementation Plan of the Stockholm Convention on POPs in Rwanda: 2007-2025, Government printer, Kigali.

- MINITERE, 2005. Inventaire national initial des polychlorobipheniles et des equipment les contenant au Rwanda, réalisée par Musonera Gaspard.

- REMA, 2013. PCB Inventory update in Rwanda, preliminary report developed by Richard Ngendahayo. Rwanda, Kigali;

- Ministry of Infrastructures, Republic of Rwanda, 2011. National action plan for eradication of asbestos from buildings in Rwanda;

- Stockholm Convention on Persistent Organic Pollutants; available at: www.pops.int.;

- Rotterdam convention on the Prior Informed Consent Procedure for Certain Hazardous Chemicals and Pesticides in International Trade, 2005. Geneva, Switzerland;

- GEF, 2008. Persistent organic pollutants (POPs) an awareness module for national coordinators and steering committees. New York, USA;

- Government of Rwanda, 2005. Organic Law Determining the Modalities of Protection, Conservation and Promotion of Environment in Rwanda, Government printer, Kigali;

- Swedish Chemicals Agency, March 2010. Capacity Building for Sound Management of Chemicals Organisation, responsibilities and tasks of governmental institutions and enterprises. Sundbyberg;

- Basel convention, 2005. Technical Guidelines for the Environmentally Sound Management of Wastes Consisting of, Containing or Contaminated with Polychlorinated Biphenyls (PCBs), Polychlorinated Terphenyls (PCT s) or Polybrominated Biphenyls (PBBs). Basel convention series. SBC Nr. 2005/2.

ANNEX 4: RATING SCALES

| Ratings for Outcomes, Effectiveness, Efficiency, M&E, I&E Execution | Sustainability ratings: | Relevance ratings |
| --- | --- | --- |
| 6: Highly Satisfactory (HS): no shortcomings 5: Satisfactory (S): minor shortcomings 4: Moderately Satisfactory (MS) 3. Moderately Unsatisfactory (MU): significant shortcomings 2. Unsatisfactory (U): major problems 1. Highly Unsatisfactory (HU): severe problems | 4. Likely (L): negligible risks to sustainability | 2. Relevant (R) |
|  | 3. Moderately Likely (ML): moderate risks | 1.. Not relevant (NR) |
|  | 2. Moderately Unlikely (MU): significant risks 1. Unlikely (U): severe risks | Impact Ratings: 3. Significant (S) 2. Minimal (M) 1. Negligible (N) |
| Additional ratings where relevant: Not Applicable (N/A) Unable to Assess (U/A |  |  |

ANNEX 5: EVALUATION REPORT OUTLINE

| i. | Opening page: - Title of UNDP supported GEF financed project - UNDP and GEF project ID#s. - Evaluation time frame and date of evaluation report - Region and countries included in the project - GEF Operational Program/Strategic Program - Implementing Partner and other project partners - Evaluation team members - Acknowledgements |
| --- | --- |
| ii. | Executive Summary - Project Summary Table - Project Description (brief) - Evaluation Rating Table - Summary of conclusions, recommendations and lessons |
| iii. | Acronyms and Abbreviations (See: UNDP Editorial Manual) |
| 1. | Introduction - Purpose of the evaluation - Scope & Methodology - Structure of the evaluation report |
| 2. | Project description and development context - Project start and duration - Problems that the project sought to address - Immediate and development objectives of the project - Baseline Indicators established - Main stakeholders - Expected Results |
| 3. | Findings (In addition to a descriptive assessment, all criteria marked with (*) must be rated) |
| 3.1 | Project Design / Formulation - Analysis of LFA/Results Framework (Project logic /strategy; Indicators) - Assumptions and Risks - Lessons from other relevant projects (e.g., same focal area) incorporated into project design - Planned stakeholder participation - Replication approach - UNDP comparative advantage - Linkages between project and other interventions within the sector - Management arrangements |
| 3.2 | Project Implementation - Adaptive management (changes to the project design and project outputs during implementation) - Partnership arrangements (with relevant stakeholders involved in the country/region) - Feedback from M&E activities used for adaptive management - Project Finance: - Monitoring and evaluation: design at entry and implementation (*) - UNDP and Implementing Partner implementation / execution (*) coordination, and operational issues |
| 3.3 | Project Results - Overall results (attainment of objectives) (*) - Relevance (*) - Effectiveness & Efficiency (*) - Country ownership - Mainstreaming - Sustainability (*) - Impact |
| 4. | Conclusions, Recommendations & Lessons - Corrective actions for the design, implementation, monitoring and evaluation of the project - Actions to follow up or reinforce initial benefits from the project - Proposals for future directions underlining main objectives - Best and worst practices in addressing issues relating to relevance, performance and success |
| 5. | Annexes - ToR - Itinerary - List of persons interviewed - Summary of field visits - List of documents reviewed - Evaluation Question Matrix - Questionnaire used and summary of results - Evaluation Consultant Agreement Form |

This TOR is approved by : [indicate name of Approving Manager]

Signature

Name and Designation

Date of Signing

For more guidance on this, the consultants will be requested to use UNEG’s Guidance in Integrating Human Rights and Gender Equality in Evaluation” http://uneval.org/document/detail/1616

For additional information on methods, see the Handbook on Planning, Monitoring and Evaluating for Development Results, Chapter 7, pg. 163

UNDP Style Manual, Office of Communications, Partnerships Bureau, updated November 2008

Using a six-point rating scale: 6: Highly Satisfactory, 5: Satisfactory, 4: Marginally Satisfactory, 3: Marginally Unsatisfactory, 2: Unsatisfactory and 1: Highly Unsatisfactory, see section 3.5, page 37 for ratings explanations.