UNITED NATIONS DEVELOPMENT PROGRAMME

AZERBAIJAN

OUTCOME EVALUATION ON

REHABILITATION OF BLOOD TRANSFUSION SERVICES IN AZERBAIJAN

00034950

An Outcome Evaluation Report

| Prepared by Casper Jersild | December 2006 |
| --- | --- |

Table of Contents

Executive Summary	4

1	Introduction	6

1.1	Purpose of Evaluation	7

1.2	Key issues addressed by the Evaluation	8

1.3	Description of Evaluation Methodology	8

2	National Context	9

2.1	The HIV/AIDS Epidemic in Azerbaijan and Blood Transfusion	9

2.2	Development impacts	10

2.3	The National Response to HIV/AIDS in Azerbaijan	10

Government response.	10

3	UNDP Response to HIV/AIDS	11

3.1	Resources for HIV/AIDS Response and Safe Blood Supply in Azerbaijan	11

4	Findings related to outcome, outputs and UNDP contributions	13

4.1	Status of the Outcome	13

4.1.1	Strengthened policies, institutional capacity, and awareness regarding HIV/AIDS and STI prevention	13

4.1.2	Number of blood units collected.	13

4.1.3	Un-paid voluntary blood donors.	13

4.2	Relevance of Outcome	14

4.3	Factors Affecting the Outcome	14

4.4	UNDP Contributions to the outcome through outputs	14

4.4.1	Output: Blood Bank related product and service are further developed and/or improved.	14

4.4.2	Output: Framework for blood donor recruitment developed.	16

4.4.3	Output: Institutional, policy and legal frameworks related to blood transfusion are revised and improved.	17

4.5	UNDP Partnership Strategy	18

5	Recommendations	19

5.1	Implementation of the new Law on Blood Transfusion	19

5.2	Financing the NBTS	19

5.3	Recruitment of blood donors	20

5.4	Appoint support staff for IT system	20

5.5	Continued support for extended project.	20

6	Lessons Learned	20

7	Annexes	23

7.1	Persons met	23

7.2	Documents reviewed	24

List of Abbreviations

| BB | Blood Bank |
| --- | --- |
| BTS | Blood Transfusion Service |
| CCM | Country Coordination Mechanism |
| cGMP | current Good Manufacturing Practice |
| CP | Country Programme |
| HIV/AIDS | Human Immunodeficiency Virus/Acquired Immunodeficiency Syndrome |
| IDU | Injecting Drug Users |
| IFIs | International Financial Institutions |
| IFRC | International Federation of Red Cross and Red Crescent Societies |
| IT | Information Technology |
| MoH | Ministry of Health |
| MYFF | Multi Year Funding Framework |
| NBTS | National Blood Transfusion Services |
| NGO | Non-Governmental Organization |
| NSP | National Strategic Plan |
| PLHIV | People living with HIV/AIDS |
| RCS | Red Crescent Society |
| SOPs | Standard Operating Procedures |
| SPPRED | State Programme for Poverty Reduction and Economic Development |
| STI | Sexually Transmitted Infection |
| TTI | Transfusion Transmitted Infections |
| UNDAF | United Nations Development Assistance Framework |
| UNDP | United Nation Development Program |
| UNOPS | United Nations Office for Project Services |
| WHO | World Health Organization |

Executive Summary

Monitoring of the HIV/AIDS epidemic in Azerbaijan was initiated in 1987, and only few cases were recorded until 1998. A sharp rise in number of registered cases has been observed from 1998 till present and the epidemic are presently described as concentrated and of low prevalence. Route of transmission can be ruled out in 75% to 87% of the newly diagnosed cases, and it appears that almost 70% of cases have been infected through injecting drug use. Surveys among Injecting Drug Users indicate that 13% (Baku) - 20% (Lenkoran) are HIV positive and that Hepatitis C infection in present in more than 50%. Risk for a further spread of HIV/AIDS in the population is high.

UNDP’s response to the HIV/AIDS epidemic in Azerbaijan goes back to 1997 and in 1999 a Resource Centre on HIV/AIDS for NGO’s was created in order to facilitate information, education and counselling on HIV/AIDS prevention issues at the community level.

In October 2002 UNDP launched this project, which addresses the urgent need for safe blood for the health care system in Azerbaijan. It focused its activities at the Blood Banks in Baku and Ganja, and one of the primary objectives of this project was to recruit non-paid voluntary blood donors with low risk for transfusion transmitted infections, i.e. HIV and Hepatitis type B and C.

This outcome evaluation considers how UNDP has contributed to strengthening the national institutional response against the epidemic throughout the project period 2002 – 2006. The evaluation concludes that, both through project interventions and “soft assistance” such as policy dialogue, advocacy, and coordination, UNDP has made significant contribution to improve capacity to respond to the challenges of HIV/AIDS in Azerbaijan. The UNDP’s approach was appropriate to the Azerbaijan context, including the low priority given to the HIV/AIDS by the Government of Azerbaijan at the beginning of the project period evaluated, the weakness of coordination and strategic planning, and the need to develop civil society.

The evaluation concludes with the following specific recommendations:

1. Implementation of the new Law on Blood Transfusion: It is important to implement the new law on the National Blood Transfusion Service in Azerbaijan, and that this will cover the whole country. It is also recommended that a more formal management structure is implemented and that this include a Board of Directors, a Financial Director, and Quality Managers. It is also recommended that an Advisory Group be established and that this represents user’s of blood and blood bank services.

Of equal importance is the establishment of regular current Good Manufacturing Practice (cGMP) inspections of all blood producing entities by a National Inspectorate, which will have the power to licence the individual departments based upon compliance with cGMP regulations.

2. Financing the NBTS: It is recommended that the MOH provide the necessary funds for running costs of the blood banks, i.e. blood bags, test kits and other consumables, as well as upgrading of essential equipment. Also, that the funds from the MOH include the necessary support for salaries to staff.

3. Recruitment of blood donors: Recruitment and retention of non-paid, voluntary blood donors is of major importance for increasing safety of blood supply. The experiences of the project indicate that it is entirely possible to recruit non-paid blood donors, however the recruitment efforts should be increased not only in Baku and Ganja, but should cover the whole country. In order to accomplish this task, there is an urgent need to employ additional staff at each blood bank, and to train this staff in donor recruitment techniques and methods. This should involve a more scientific approach, which draw on the available statistical information and past experience. It is important that there is an increased involvement of the NBTS in this area and that NBTS assist the Red Crescent Society in its efforts.

4. Appoint support staff for IT system: The project has provided IT support staff for the Baku Blood Bank during and after the implementation of the IT System. This support is no longer available, but there is a continued need for support related to (1) occasional help with problems encountered in daily routines, (2) running of maintenance and implementation of programme upgrades, and (3) validation of the system in use. It is thus important that the NBTS identify and recruit the necessary IT staff, and that the MOH provide the necessary funds for salaries for such staff.

5. Continued support for extended project: The present project focused on only two of the five regional blood banks in Azerbaijan, Baku and Ganja. For the project to be successful it is important to extend the project to cover the remaining three or four regional blood banks in Quba, Sheky, Nakhcivan and Lenkoran. This will require the full participation of the Government and the MOH in budgetary support for staff salaries, consumables such as blood bags and test kits, refurbishment of premises, and procurement of necessary modern equipment.

It is recommended that the UNDP in Azerbaijan will continue its role as project coordinator and administrator of funds, and assist in formulating project proposals and applications for necessary funding. Project funds should be devoted entirely towards technical support, training and education as well as research.

It is also advised that planning of an extended project will involve the already established network of stakeholders, and that the WHO should contribute in a more visible way with expert advice and provide guidance on training of staff.

# Introduction

At the end of 1990s the United Nations conducted situation assessment to identify the major driving forces of HIV spread in Azerbaijan. One of the findings of the assessment was that though HIV-prevalence rates are not well established some data indicated that a sharp rise in occurrence of HIV infection should be expected if drastic measures are not taken. There was a reported case of HIV transmission through blood transfusion. To prevent further dissemination of HIV through blood transfusion, the assessment report recommended strengthening of the national blood transfusion and blood bank services.

During the ‘Soviet period’ the total number of blood donations per year in Azerbaijan was substantially higher than today. In 1986 Azerbaijan had a total of 173,000 blood donations. This is the highest number of donations per year in Azerbaijan ever. The number of donations has decreased every year until 2001 when the total number was 13,000. The number of blood donations per 1000 inhabitants decreased from about 25 in 1986 to 2 in 2001. Blood donors were mainly family/replacement or paid donors, which are known to carry a high risk for Transfusion Transmitted Infections (TTI). Such a low number of blood donations are not even sufficient to cover basic needs for transfusions in the population of Azerbaijan.

The reasons for the decline in number of donations seem complex. Governmental funding of the blood banks in Azerbaijan has decreased since the peak in 1986 (leading to lack of consumables and modern equipment), the number of blood donor campaigns has decreased, and there has been a continuing “brain drain” from the blood banks in the country. During the ‘Soviet period’ donors had other incentives for giving blood than today, e.g. paid leave from work.  At the same time the social development changed as the country became less tied to the USSR, and finally became independent in 1991. Despite the low number of donations, there still exist more than 70 establishments for blood donations in Azerbaijan.

The need for rehabilitation of the blood bank and transfusion services in Azerbaijan was based on a few important facts:

- The HIV/AIDS-epidemic is a serious threat to public health and welfare. This and other diseases can be transmitted by transfusion of blood or blood products. At present the prevalence of blood related infectious diseases in the donor population in Azerbaijan is too high.

- An adequate blood transfusion service is a cornerstone in the development of professional health services in areas like surgery, obstetrics and hematology. In Azerbaijan there is a wide gap between blood supply and need.

- Blood transfusion services are expensive. These services in Azerbaijan have not been adequately funded.

- Red blood cells and platelets are living cells with limited storage properties. Competent handling and adequate cooling are needed through the whole chain of actions from collection of donated blood, processing, storage, transportation and transfusion to the recipient. At present there is a mismatch between the geographical distribution of patients and of transfusion services.

UNDP launched a project aimed to build capacity of the blood transfusion system to prevent transmission of HIV/STIs through blood transfusion and reverse the decline of blood donations. The project is directly executed by UNDP. The key project beneficiaries during the evaluation period are: Institute of Hematology and Transfusiology, Blood Bank in Baku and Ganja, Ministry of Health, Parliament, patients in need of blood transfusion.

The project contributes to the achievement of the UNDP Country Programme (CP) Outcome:

Strengthened policies, institutional capacity, and awareness regarding HIV/AIDS and STI prevention.

A detailed results framework for the CP Outcome is summarized below:

MYFF Goal 5:	Responding to HIV/AIDS

Service Line 5.3:	HIV/AIDS, Human Rights and Gender

CP Outcome:	Strengthened policies, institutional capacity, and awareness regarding HIV/AIDS and STI prevention

The main outputs of the project expected to have contributed to the Outcome are:

- Blood-bank related product and service are further developed and/or improved;

- Framework for blood donor recruitment developed;

- Institutional, policy and legal frameworks related to blood transfusion are revised and improved.

## Purpose of Evaluation

The outcome evaluation assess the progress of the UNDP’s project interventions towards achievements of the Country Programme Outcome – Strengthened policies, institutional capacity, and awareness regarding HIV/AIDS and STI prevention, including contributing factors and constraints.

The evaluation should also generate lessons and experiences that could provide inputs or feed into the review of the current Country Programme and/or design and implementation of the next Country Programme.

Evaluation is undertaken almost a year after the completion of the active phase of the project. This timing was decided to enable the evaluator to not only assess the performance of the project itself but to assess sustainability of the project’s results upon its completion and provide recommendations to the Blood Banks and the Institute and the Ministry of Health, key project beneficiaries, on further actions to sustain and expand the results achieved, and to UNDP on additional strategies/interventions to fully achieve the CP outcome.

It should be noted however that the above mentioned CP Outcome has been formulated and included only in the latest Country Programme of 2005 - 2009, and thus after the initiation in 2002 of the project being evaluated.

## Key issues addressed by the Evaluation

The outcome evaluation will be looking at the relevance and contribution of UNDP project activities with regard to the outcome and evaluate the efficacy of strategies employed in contributing to the achievement of outputs. The scope of evaluation is expected to include lessons learnt, findings and recommendations in the following areas:

- Assess adequacy of the project design for the achievement of outcome and outputs;

- Assess what and how much progress has been made towards achievement of the outcome, in part or full, the reasons for any shortfall in its achievement and whether any unexpected effects have occurred;

- Assess relevance and effectiveness of the applied strategies to the achievement of the outcome;

- Analyse the underlying factors beyond UNDP’s control that influence the outcome (including the opportunities and threats affecting the achievement of the outcome);

- Assess whether UNDP’s outputs and other interventions (soft assistance) can be credibly linked to the achievement of the outcome;

- Assess whether UNDP’s partnership strategy has been appropriate and effective, including the range and quality of partnerships and whether this has contributed to the achievement of the outcome.

## Description of Evaluation Methodology

Time period covered.

The time period covered by this assessment is the entire project period from October 2002 to the end of 2006. This evaluation covers the first two years of the Country Programme implementation and thus is defined as an early/mid-term evaluation in the Country Programme.

Approach.

The evaluation was carried out by one international consultant, medical doctor with in-depth experience in blood transfusion services, assisted when needed by a local interpreter. The international consultant was briefed by UNDP upon arrival in Baku. The basic approach employed was examination of project documents, reports (documents reviewed are listed in the Annex) as well as interview with key stakeholders (list of stakeholders met is attached as Annex), and visits to the Institute of Hematology and Transfusiology in Baku and the Blood Bank section of the institute. Participatory techniques - interactive evaluation workshop with Blood Bank personnel, UNDP, project contractor and other project stakeholders – were also applied. At the completion of the mission in Baku the consultant prepared a presentation for a debriefing session.

Constraints.

The evaluation mission was scheduled with short notice, and due to time constrains of the mission it was not possible to encompass a visit to the Blood Bank in Ganja. An interview with the Medical Director of the Ganja Blood Bank was however possible in Baku during this mission.

# National Context

## The HIV/AIDS Epidemic in Azerbaijan and Blood Transfusion

HIV-prevalence rates are not well established, but some data indicate a sharp rise in occurrence of HIV infection in Azerbaijan from the late 1990’ies, the risk groups being Injecting Drug Users (IDUs) and sex workers. In order to prevent further dissemination of these infections through blood transfusion, it is important to establish a National Blood Transfusion Service based on non-paid, voluntary blood donors, and to ensure that regional hospitals are equally provided with safe blood.

A more recent update on the statistics of HIV/AIDS for Azerbaijan dated 1 December 2006 shows that the total number of people living with HIV/AIDS 
(PLHIV) is 842, and that a total of 111 people have died from AIDS. Among all registered cases 805 (or 84%) are men, and 148 (or 16%) are women. The way of transmission has been listed in the statistics as follows:

Intravenous drug users		56,7%

Sexual contact (hetero, homo)	21,3%

Mother-to-child transmission		0,8%

Unknown				21,2%

Only one case of transfusion transmitted HIV infection has been recorded since the start of the HIV/AIDS epidemic. This represents certainly an underestimate especially since reporting of adverse effects of blood transfusion is not in place.

The Blood Transfusion Service of Azerbaijan was created by the former Soviet Union and consisted of a central institute for blood transfusion in Baku and four regional blood transfusion stations located in Sheki, Gandja, Kuba, and Nakhichevan. Following the collapse of the Soviet system and the associated economic crisis in Azerbaijan, the number of collected blood units has shown a dramatic decrease, from a total of 130,000 in 1986 to approx. 16,000 in 2000. This extremely low number of blood units made available to the health care system does far from meet the basic needs of the country, and furthermore the majority of units has been released without proper testing for transfusion transmitted infections (TTI) and is thus unsafe.

In 2000 there was no provision of adequate amounts of safe blood to the health care system in Azerbaijan. Not only had the number of donations reached an extremely low level (16,000 units in 2000), but donors were also family/replacement or paid donors, which are known to carry a high risk for Transfusion Transmitted Infections, notably Hepatitis type B and type C as well as HIV.

Women in labour constitute a major group of patients, which require blood transfusions, as will patients with Thallasemia, glucose-6-phosphate deficiency, and hemophiliacs.

## Development impacts

The overall development objective of this project is to increase the health of the population of Azerbaijan through the provision of a sufficient number of safe blood units, which can be made available to those patients in need. If the project is successful there will be no patients dying due to lack of blood transfusions and also, there would be no patients who will contract TTI due to transfusion with infected blood units.

At project start the number of donations in Azerbaijan blood banks totalled 1,8 donations/1000 inhabitants per year, which is very far below average for EU countries (43 Donation/1000 inhabitants/year). It has been suggested that the goal for blood collections by year 2007 should average 10 donations/1000 inhabitants/year.

## The National Response to HIV/AIDS in Azerbaijan

## Government response.

Overall national framework for HIV/AIDS response is embodied in two documents: the Law of the Republic of Azerbaijan on the Prevention of Spread of HIV/AIDS (1996) and National Strategic Plan on Prevention on HIV/AIDS covering 2002-2006.

The National Strategic Plan (NSP) on prevention of HIV/AIDS in Azerbaijan was approved on September 25, 2002 by the Cabinet of Ministers decree no 205s. NSP includes nine key strategies with a total budget of $31 million. Its goal is to decrease the transmission of HIV-infection by an urgent and adequate response, through a multisectoral, complex and modern approach. It supported to increase a multisectoral (multidisciplinary) approach and cooperation between various ministries, state departments, NGOs, and international organizations as partners in the implementation of related actions.

The strategies of the NSP are:

•	Formulating a national policy in the field of HIV/AIDS prevention,

•	Providing for safe blood transfusions and medical intervention,

•	Preventing the spread of HIV transmission among youth, from mother-to-child, among IDUs and their sexual partners, and among migrants and refugees,

•	Preventing heterosexual transmission of HIV/AIDS,

•	Providing medical and social support to PLWHA and their families, and

•	Strengthening the epidemiological surveillance and monitoring of HIV/AIDS.

HIV/AIDS response is part of the mandate of several medical services within the Ministry of Health, including the Republican AIDS Centre, Republican Narcological Dispensary, the Republican Dermato-Venerological Dispensary (STI clinics), the Blood Transfusion Service, and the Republican Reproductive Health Service.

While HIV/AIDS has been acknowledged as a social and economic problem as well as a medical issue, a multi-sectoral response has been elusive.  Internal government coordination and participation by civil society institutions has been lacking.  The establishment of a Country Coordination Mechanism (CCM) offers an avenue for improvement.  This body, chaired by Ministry of Health and composed of government ministries, NGOs and international agencies, is charged with overseeing the use of Global Fund resources.  In a best-case scenario, the CCM will contribute to a more effective response to the epidemic by enabling all stakeholders to participate in the national response to HIV/AIDS.

# UNDP Response to HIV/AIDS

The UNDP Country Programme 2005-2009 for the Republic of Azerbaijan emerged from two national consultation processes: preparation and adoption of the State Programme for Poverty Reduction and Economic Development (SPPRED) which includes achievement of Millennium Development Goals (MDGs) and preparation of the United Nations Development Assistance Framework (UNDAF). Both were participatory processes engaging the Government, Parliament, UN agencies, IFIs, bilateral donors, NGOs and businesses. During the First Joint Strategy Meeting of Azerbaijan’s in March 2004, the Government reviewed and validated the UNDP Country Programme and its linkage to the UNDAF. UNDP being the first organization which initiated activity for the government support on HIV-related area in Azerbaijan in 1997, has made a great input to building national capacity and realization of national response to HIV-infection. HIV-related issues have been included into SPPRED as well as in UNDAF.

UNDP’s strategic orientation in response to HIV/AIDS reflected in the Country Programme is aligned with key objectives of the National Strategic Plan on HIV/AIDS, namely providing for safe blood transfusion and medical interventions, and promoting multi-sectoral approaches to HIV response.

There are two key directions of UNDP HIV interventions: civil society mobilization and capacity development for HIV prevention activities and support a National Strategy on Blood Safety, including rehabilitation of the blood transfusion system & access of the population to safe blood.

## Resources for HIV/AIDS Response and Safe Blood Supply in Azerbaijan

HIV/AIDS is just one among many competing priorities on the national agenda. The allocation of domestic resources to implement the National Strategic Plan combat the threat of HIV/AIDS is unable to meet the growing need. Additionally, the insufficient resources spent on HIV are often poorly targeted. Until now, domestic spending on HIV has been limited to paying salaries for HIV-related medical staff as well as maintaining an archaic, Soviet-created health infrastructure.  This outdated, hospital-based system is expensive, oversized, and crumbling, often unable to meet the demands created by this relatively new epidemic. Few resources remain for prevention activities. The benefit of investing in preventive care and knowledge dissemination – techniques that may help curtail the epidemic as well as ease higher costs in the future – has not been realized.

From 2005, financial resources devoted to combating HIV/AIDS have increased; to a large extend due to the approval of a 2004 proposal by Azerbaijan to the Global Fund on HIV/AIDS, Tuberculosis and Malaria (GFTAM), in which $6.5 million in aid over a two year period was requested. In addition, in the coming years, projected increases in tax revenue due to international oil sales are slated to be appropriated for social programs, perhaps easing or eliminating the existing shortfall in financial resources.

The National Strategic Plan envisions allocation of USD 6,241,000 over the period of 2002- 2006 to ensure safety of blood transfusions and its components. In absence of the adequate financial reporting mechanisms it is hard to extract data on actual financial spending to improve blood transfusion services.  The MOH has underestimated the regular allocated budgets for the blood transfusion service for several years, and it has still not reached sufficient financial support during 2006. From several sources it has been expressed however, that from 2007 the budget allocation to blood transfusion service will increase dramatically.

Considering the cost of providing safe blood transfusion nationwide, and the time it takes to educate, train and implement major changes in the existing blood banks, it must be concluded that the funding of this limited project has been insufficient in both time and financial support. The external funding has been as follows: The UNOPS have through its Nordic Fund been able to initiate this project, which was funded for a 1 year period with 500,000 US$. Additional funding was applied for through the Norwegian Embassy to the Ministry of Foreign Affairs, who allocated additional funds of 580,000 US$. Finally the Statoil Fund provided supplementary funding at the end of the extended project with a total of 25,000 US$, and UNDP Azerbaijan has provided supplementary fund of 193,755 US$.

The Red Crescent Society of Azerbaijan was unable to provide any assistance before 2004 due to heavy involvement of the RC in refuge camps within the country. During 2004 a letter of understanding between the MOH, the National Blood Transfusion Service and Red Crescent was signed, which provided Red Crescent with the task to recruit blood donors. 3 persons are working in the health department, which are doing this job. For the period 2007 – 2010 an annual budget of 20.000 US$ are allocated to donor recruitment by the Red Crescent.

It is interesting to note that the WHO country program for 2006 – 7 was revised in September 2005, and the Safe Blood component of the AIDS program was deleted/ removed. This is an extraordinary situation since the WHO does have the technical capacity to provide high quality support to these project activities in Azerbaijan. It should however also be noted that the director of the WHO Office resigned beginning 2006 and no replacement has been identified yet.

A Safe Blood Component is part of the strategy for the Global Fund against HIV, TB and Malaria. For the Azerbaijan Global Fund programme, the 1st phase did not have any Safe Blood component, but the 2nd Phase, which will begin by June 2007 will have a smaller component devoted to safe blood activities. The 2007 budget will be approved in April 2007 and allocated to actual project by June – July 2007. The proposed activities for Safe Blood will include procurement of a PCR equipment for diagnostic purpose of HIV and Hepatitis C and B. In addition it proposed to procure a Flowcytometer also for diagnostic purposes. In addition training of 50 MD’s has been planned; the specific outline of the training programme is still to be discussed.

# Findings related to outcome, outputs and UNDP contributions

## Status of the Outcome

### Strengthened policies, institutional capacity, and awareness regarding HIV/AIDS and STI prevention

The UNDP-Azerbaijan Country Programme 2005 – 2009 have listed as National Priority No. 2: “Basic needs for health, education, and social protection are met for all people”, and the corresponding UNDAF Outcome 3: that “The level of health and nutrition improves, particularly among women, children, and vulnerable groups.”

The MYFF Goal 1.7 addresses the above mentioned CP outcome, however it is stated that there at present are no credible indicators for the HIV/AIDS epidemic available in Azerbaijan. The specific indicators selected for the output “Blood transfusion system rehabilitated and related policy framework revised” have been: (1) Number of blood units collected (baseline: 2001: 16,000 collections), and (2) Percentage of donors, who are voluntary and non-remunerated (baseline: not available).

### Number of blood units collected.

Information on number of blood units collected were one of the parameters included in a uniform data collection sheet, which was developed by the project and used by the blood banks. The collected data shows that number of donations rose from 14.057 in 2002 to 22.862 in 2005 or almost 65%. At the time of evaluation data for fiscal year 2006 were not yet available. It was however made clear by the project management that the increase during 2006 in number of units collected were less than projected, and that this was due to limited resources at the Red Crescent Society of Azerbaijan.

It should be noted that the increase in total number of donations for the whole country is due mainly to the increased activity in Baku and Ganja Blood Banks, which were part of the project. It is also evident, that the provision of safe blood for the health care system of the country is still far from sufficient. However, the steps taken to improve the supply of safe blood were the right ones, only should the activities be increased further, or said in another way, staff allocated to blood donor recruitment at the Red Crescent Society of Azerbaijan should be increased, but also the Blood Banks should provide more staff, which should focus on this work.

In order to reach an improved level of health, particularly among women, children and vulnerable groups of the society (UNDAF outcome 3), and especially to provide this improvement for the whole country, it is estimated that 10 – 15 donations per 1.000 inhabitants per year should be reached. This would require a total of 84,000 – 126,000 blood units to be collected annually.

### Un-paid voluntary blood donors.

Provision of safe blood requires that blood donors are un-paid and voluntary. Unfortunately there are no firm baseline figures available, but data collected annually by the project for the whole country for 2003 to 2005 indicate, that in 2003 (July – December only) 58% of donations were from un-paid donors whereas in 2005 this figure rose to 72%. In conclusion, the selected indicator shows a tendency to increase. It should be noted that a change away from a paid blood donor system towards an un-paid system is complicated and require several years of intensive work involving education and recruitment among the low risk part of the population.

## Relevance of Outcome

Blood supply for the health care system in Azerbaijan is far from sufficient, and fatalities due to lack of blood are observed regularly. In order to adjust this situation, which will affect the overall health situation of the country, it is necessary to (1) increase number of blood donations, and (2) recruit safe blood donors, which are un-paid and voluntary.

The selected outcome is therefore highly relevant considering the present situation of the health care system.

## Factors Affecting the Outcome

It has been noted on several occasions that the financial support to the National Blood Transfusion Service provided through the MOH is far from sufficient. The decline in production of blood units is primarily a result of the insufficient budget allocations for blood bank activities. Despite the very good achievements of this project, which over the project period has provided a total of 1,298,755US$, the MOH continues to underestimate the financial support needed for an up-to-date blood bank function. The project budget has primarily been spend on essential equipment upgrade for two blood banks, implementation of training and study tours, and in special conditions for consumables such as test kits (initial project period) and blood bags (in urgent situation). It was assumed, that the MOH would cover the running cost of the blood banks, however this has not been the case. This situation put the whole project in danger of not being able to meet the intended objective, and there is an urgent need for renegotiating the budgets for the National Blood Transfusion Service. Expansion of the successful results in Baku and Ganja to the other regional Blood Banks should be initiated within the coming year, and a budget for this new development has to come from the MOH.

## UNDP Contributions to the outcome through outputs

With reference to the Project Results and Resource Framework the following outputs can be evaluated:

### Output: Blood Bank related product and service are further developed and/or improved.

Indicative activities 1.1.1 to 1.1.4 have all more or less been carried out and are summarised below.

#### Sustainability analysis for Blood Transfusion Services.

A comprehensive Sustainability Analysis was delivered by the Consultants in November 2003. It discusses in great detail the following issues: (1) The present transfusion service in Azerbaijan, (2) Quality issues related to blood and blood components, (3) An estimate of future need for blood in Azerbaijan and its clinical use, (4) Analysis of costs connected to production of blood, (5) Models for cost recovery and financing of the national blood transfusion service, (6) A Future structure and organisation of the national blood bank and transfusion service, and (7) A detailed discussion and recommendations.

The Sustainability analysis does provide a balanced and useful discussion of the many and various aspects of a blood transfusion service which needs to be taken into consideration by the Government if the further development shall be successful.

#### Safe Blood (Test Line, Product Line, Quality Systems, IT).

Appropriate testing of all collected blood was ensured by provision of test kits (initially procured by the project) and new ELISA equipment delivered during April 2003. The staffs were very knowledgeable and performed these tests well. Test routines were changed by the consultants in order to assure a smoother and more reliable testing process than what had existed before.

Product lines have been improved using the procured IT equipment, which secure correct reporting of test results for TTI markers and blood grouping. The result of this is relatively safer blood.

The project delivered more than expected in this activity.

Establishment of a second product line using modern blood component technology in separating whole blood into red cell in additive solution, plasma and buffy coat for possible platelet production has not yet been fully implemented due to lack of procurement of appropriate blood bags due to insufficient funding from the MOH.

Development of a quality management system has been initiated through lectures given, development of a standardised frame for Standard Operation Procedures, and creation of a supporting project group to assist Blood Banks in Baku and Ganja. Visit to the Baku Blood Bank with interview with its director did not bring any evidence that a more comprehensive quality management system was in place. There were no organogram of the institute, job descriptions or records of training of staff. Also from visit to the different laboratories, there were no recording of maintenance of equipment. Production of SOP’s were initiated, and in use.

#### Research and Education.

Training and education has been an integral part of all visits of consultants to Azerbaijan. In addition a total of 16 people from Azerbaijan with relation to the project have been visiting Norway in smaller groups and on several occasions during the project. The aims of educational activities are well documented however there is no evaluation of training outcome documented. From interviewing some of the participating staff members it is clear, that the overall objectives of this activity were reached. In addition these visits contributed to motivate staff and give them an in depth understanding of modern blood banking in Europe.

Input from WHO Euro in training sessions on Clinical use of Blood is seen as a result of the collaborative efforts of the Project Coordination Group.

The project has thus performed well according to planned project activities.

#### Blood Bank and Project Management.

Consultants have met on several occasions with senior blood bank staff in both Baku and Ganja providing guide on Quality Management requirements. Discussions and meeting on work flow in the blood banks, organisation of regular training activities for staff members, and computerisation of the blood bank in Baku has been the main activities.

Measurable indicators for these activities are lacking, but verification of outcome for the Baku blood bank has been done through visit and interview with various staff members.

In conclusion there are no firm indicators attached to these activities, but it is obvious that the workflow in the blood bank has been revised and allows a smoother workflow. Also the handlings of blood donors seems now to be more in line with the new requirements, and are user friendly to the donors.

### Output: Framework for blood donor recruitment developed.

Indicative activities 1.2.1 ‘Develop programme for and implement education activities for blood donors’ and 1.2.2 ‘Develop the donors recruitment plan’ have been carried out.

The most important activity of this project was to increase the number of non-paid, voluntary blood donors and to create a panel of repeat donors with low risk for TTI’s. In order to monitor this activity the project developed a comprehensive data collection sheet to cover the main blood bank activities. This ensured a uniform reporting of data related to blood donation and their use and this also ensured a reliable set of detailed data for evaluation of progress. The data sheets were developed by the consultants in close collaboration with senior blood bank staff.

Recruitment of blood donors was carried out by the Red Crescent Society of Azerbaijan, based on a memorandum of understanding between the Institute and the RCS. Reporting of the RCS activities is not detailed as to number of recruitment sessions held and outcome in terms of persons willing to become a blood donor. In the future however, they will report outcome of activities, which may facilitate a more focused approach to upcoming recruitment efforts.

As a result of the project, a close collaboration between the RCS of Azerbaijan, IFRC in Azerbaijan, the Norwegian RC and the Institute has been created and will contribute to the sustainability of this activity.

In terms of actual blood donations the collected data shows that donations rose from 14.057 (2002) to 22.862 (2005). Data for 2006 are not yet available. During the same period the percentage of unpaid voluntary donors rose from 48% (2003) to 76% (2005) for the Baku Blood Bank, and a similar increase was recorded for the Ganja Blood Bank.

The project has thus performed well according to projected activity. But it has not been possible to verify if mechanisms for a national blood donor campaign have been established (project activity 1.2.3), and how effective it is. It should though be mentioned that the international Blood Donors Day has been celebrated all over the country and reported in national TV news channels.

### Output: Institutional, policy and legal frameworks related to blood transfusion are revised and improved.

Most of the planned activities which support this output have been performed: 1.3.1, 1.3.2, 1.3.4, 1.3.5, 1.3.7, 1.3.9 and are summarised below:

#### Legal framework.

A Draft Law regulating the Blood Transfusion Service in Azerbaijan was developed and presented to the Parliament, who held several hearings on this topic. In addition a visit to Norway for some members of Parliament to meet with counterparts in Norway was arranged. Following initial hearings, the draft law passed the third and final hearing on 3rd May 2005.

National Strategy on Blood Safety and Donations regulating the Blood Transfusion Service in Azerbaijan was developed by the MOH and the Blood Banks as an implementing mechanism for the Law, without support of the project.

#### Clinical use of Blood.

Printing of guidelines for clinicians on clinical use of blood was one of the main activities. The Council of Europe “Guide on the preparation, use and quality assurance of blood components” 10th Edition was translated into Azeri language by the project. In addition WHO Azerbaijan arranged for the translation of its handbook: “Clinical use of Blood”. And finally, a major conference for approx. 250 clinicians was held in Baku 27 October 2005. The project thus delivered in full the planned activity.

An action plan for implementation of activities proposed in the sustainability report has not been made available (1.3.3). An information system recording all blood transfusion events and possible adverse reaction has not yet been implemented. The IT system installed in Baku is able to handle such information but is presently not yet in use (1.3.6). The kind of support for initiation of a national society for blood bank related issues (Society for Transfusion Medicine) has not been described in the reports and has not been established yet (1.3.8).

In summary, the vast majority and the most important outputs of this project have thus been accomplished.

All outputs are directed towards the main outcome of the Country Programme, that is to Strengthen policies, institutional capacity, and awareness regarding HIV/AIDS and STI prevention.

In a broader view of the outcome, it should be noted that access to safe blood will reduce excess mortality of poor and marginalized populations. It will also reduce the risk of blood-transmissible and transfusion-related diseases. This project also contributes to development of a sustainable health system by building a sustainable management capacity in the technology involved in blood and blood products. And finally, by developing global norms and standards and support national policies for blood products, it promotes and enables an institutional environment, which will promote an effective health dimension in the development policies.

In evaluating these outputs, it is not possible to access the impact of the project on transfusion transmitted infections and notably HIV/AIDS. The background figure for Transfusion Transmitted HIV is simply too low and no cases have been registered during the project period.

It should also be noted that the project have created a close collaboration between the AIDS Centre and the Blood Banks with regard to post donation counselling of HIV positive blood donors. This collaboration is important since VTC by the AIDS Centre or its affiliates is of major importance in avoiding the Blood Banks to become free of charge testing laboratories for those in need of an HIV test.

Finally, during the process of recruiting blood donors, the initial steps include sensitization and education, which involve specific information to the general population on risk factor and risk behaviour for HIV/AIDS. Through such activity this programme reaches a broad section of the population, providing increased knowledge on HIV/AIDS. In these efforts the Red Crescent Society of Azerbaijan will be able to profit from the UNDP HIV/AIDS programme for training of its voluntary staff with regard to pre-donation counselling as well as formulation of its printed materials for donor education and recruitment.

In conclusion it is evident that the project outputs have been achieved. Lack of specific indicators for HIV/AIDS transmission through blood transfusion should be noted.

## UNDP Partnership Strategy

Partnership Strategy comprised Ministry of Health, Institute of Haematology and Transfusiology, WHO, IFRC, National Red Crescent Society, Parliament, Embassy of Norway and Statoil.

A Coordination Committee was established to address the increasing need to coordinate the activities in the area of blood safety with the stakeholders such as by bringing various organizations together for dialogue and practical collaboration.

Members of the Coordination Committee were representatives from the Ministry of Health, The National Blood Transfusion Service and the Institute of Haematology and Transfusiology, UNDP, WHO Azerbaijan Office, International Federation of Red Cross and Red Crescent Societies, and Red Crescent Society of Azerbaijan.

The UNDP strategy and management of this project has to a great extent contributed to the achievement of the Country Programme outcome.

The project’s implementation strategy was based on the following approach:

- Focus on extensive participation of local personnel to ensure knowledge transfer and ownership to the project

- Encourage development of long term relations between involved parties both within Azerbaijan and with Norwegian “sister-organisations”

- Continuous adjustment of project tasks in dialogue with project stakeholders

- Continuous sensitization and partnership building with potential stakeholders

The evaluation has provided strong evidence that the planned strategy has been followed and been successful. Through interview of stakeholders it was evident, that local personnel have been deeply involved, for example during the process of refurbishment of the Blood Bank in Baku by the MOH. At the same time planning for computer workstation and workflow in the blood bank was revised, based on intensive discussions with the staff and management of the blood bank. All staff expressed a positive attitude towards these changes and was highly motivated during the implementation of the computer system.

The visits by selected staff members of Baku and Ganja Blood Banks to Norway, personal relations between blood bank staff in Norway and Azerbaijan were established.

Adjustments of project tasks have mainly been obtained through the meetings of the Coordination Committee, which had members of all operational stakeholders.

It has been possible to exploit synergies between this project and other HIV/AIDS programme activities within the UNDP Office in Azerbaijan, specifically mobilization of and capacity development for the civil society, as outlined above. The project and its Resource Centre have been of significant importance for the Azerbaijan Red Crescent Society in their efforts to undertake donor recruitment efforts under the present project, Rehabilitation of the Blood Bank and Transfusion Service in Azerbaijan. It is thus evident that the two present projects of UNDP in Azerbaijan do act in synergy towards the common goal as outlined in the Country Programme: Strengthened policies, institutional capacity, and awareness regarding HIV/AIDS and STI prevention.

The individual outputs have been effective in contributing to the overall outcome of the Country Programme. UNDP has played a major role in establishing a network between the International Consultants and key persons within the MOH and Blood Transfusion Service in formulating the Legal Frame for the blood transfusion service and getting it finally approved in Parliament hearings.

In a similar way, setting the scene for blood donor recruitment by the Red Crescent Society of Azerbaijan, UNDP were instrumental in assisting in formulating a Memorandum of Understanding between RCS, MOH and the NBTS on donor recruitment to be carried out by RCS.

# Recommendations and Conclusions

## Implementation of the new Law on Blood Transfusion

It is important to implement the new law on the National Blood Transfusion Service in Azerbaijan, and that this will cover the whole country. It is also recommended that a more formal management structure is implemented and that this include a Board of Directors, a Financial Director, and Quality Managers. It is also recommended that an Advisory Group be established and that this represents clinical user’s of blood and blood bank services.

Of equal importance is the establishment of regular current Good Manufacturing Practice (cGMP) inspections of all blood producing entities by a National Inspectorate, which will have the power to licence the individual departments based upon compliance with cGMP regulations.

## Financing the NBTS

It is recommended that the MOH provide the necessary funds for running costs of the blood banks, i.e. blood bags, test kits and other consumables, as well as upgrading of essential equipment. Also, that the funds from the MOH include the necessary support for salaries to staff.

## Recruitment of blood donors

Recruitment and retention of non-paid, voluntary blood donors is of major importance for increasing safety of blood supply. The experiences of the project indicate that it is entirely possible to recruit non-paid blood donors, however the recruitment efforts should be increased not only in Baku and Ganja, but should cover the whole country. In order to accomplish this task, there is an urgent need to employ additional staff at each blood bank, and to train this staff in donor recruitment techniques and methods. This should involve a more scientific approach, which draw on the available statistical information and past experience. It is important that there is an increased involvement of the NBTS in this area and that NBTS assist the Red Crescent Society in its efforts.

## Appoint support staff for IT system

The project has provided IT support staff for the Baku Blood Bank during and after the implementation of the IT System. This support is no longer available, but there is a continued need for support related to (1) occasional help with problems encountered in daily routines, (2) running of maintenance and implementation of programme upgrades, and (3) validation of the system in use. It is thus important that the NBTS identify and recruit the necessary IT staff, and that the MOH provide the necessary funds for salaries for such staff.

## Continued support for extended project.

The present project focused on only two of the five regional blood banks in Azerbaijan, Baku and Ganja. For the project to be successful it is important to extend the project to cover the remaining three or four regional blood banks in Quba, Sheky, Nakhchivan and Lenkoran. This will require the full participation of the Government and the MOH in budgetary support for staff salaries, consumables such as blood bags and test kits, refurbishment of premises, and procurement of necessary modern equipment.

It is recommended that the UNDP in Azerbaijan will continue its role as project coordinator and administrator of funds, and assist in formulating project proposals and applications for necessary funding. Project funds should be devoted entirely towards technical support, training and education as well as research.

It is also advised that planning of an extended project will involve the already established network of stakeholders, and that the WHO should contribute in a more visible way with expert advice and provide guidance on training of staff.

# Lessons Learned

The CP Outcome formulate that “Strengthened policies, institutional capacity, and awareness regarding HIV/AIDS and STI prevention” should be supported by the specific output: 3.3.2 civil society develops/implements HIV preventions activities and 3.3.3 blood transfusion system rehabilitated and related policy framework revised. Although specific targets are to be determined, a baseline for number of collected blood units in 2001 (16,000) has been listed.

Since the project focused on two blood banks only, Baku and Ganja, it is obvious that the overall effect of the project on the country-wide supply of blood would be less spectacular. It is therefore of importance to focus on the CP Outcome, where this project was able to provide national support such as (1) HIV prevention activities due to safe blood and (2) revision of policy framework (for blood banks), which assist in shifting the blood supply from paid to safe blood donors (un-paid and voluntary).

It is extremely difficult to assess the outcome of safe blood intervention in preventing the spread of HIV/AIDS through blood transfusion. There is no doubt that the effect does occur, and that past experience in some African countries indicate that this seems to contribute to approx. a 10% reduction in HIV/AIDS incidence. It has not been possible to quantify the effect in the present outcome evaluation also because the registration of side effects (Haemovigillance) in patients treated with blood transfusion is not in place. Only one case of transfusion transmitted HIV infection has in the past been observed prior to the initiation of this project. It is obvious that the health care system in Azerbaijan will be very negatively judged by the population if such cases are more frequent, and this may very well explain the difficulties encountered in getting the true figures.

The policy to shift from paid donors to non-paid donors is formally supported by the new policy and law. It is a major enterprise to implement these changes, and it seems that these activities are not sufficiently funded. One important aspect of this change, which relates directly to the CP outputs of developing and implementing HIV prevention activities are the broad approach to the younger population groups with education and training in HIV/AIDS and how to stay healthy. This aspect is not in focus in the present project, and there are no indicators set to quantify this activity, such as number of people sensitised and trained as potential blood donors.

# Annexes

## Persons met

- Harald Noddeland, MD, Medical Director, Project Consultant, PWC, Norway

- Bjarte Solheim, MD, Blood Transfusion Specialist, Consultant Oslo, Norway

- Elkhan Rahimov, Executive Secretary, Azerbaijan Red Crescent Society

- Dilbar Iskandarova, Deputy Executive Secretary, Azerbaijan Red Crescent Society

- Mustafayeva Aynur, Health Assistant, Azerbaijan Red Crescent Society

- Elkan Gasimov, MD, Liason Officer, WHO Office, Azerbaijan

- Gøril Johansen, First Secretary, Royal Norwegian Embassy, Baku

- Gajiev Azad, MD, PhD, Director, Scientific Research Institute of Haematology and Transfusiology, Baku

- Asadov Chinqiz, MD, Head Haematologist, Scientific Research Institute of Haematology and Transfusiology, Baku

- Tahire Mammedova, MD, Chief Doctor, Regional Blood Transfusion Service, Ganja

- M. Fatih Yegul, Director, International Center, Qafqaz University

- Adila Z. Abasova, Professor, Dr., Chief, Social Legislation Department of the National Assembly of the Azerbaijan Republic

- Jamila Ibrahimova, Senior Programme Adviser, UNDP Azerbaijan

- Ashraf Kuliyev, Project Manager, UNDP Azerbaijan

- David Eizenberg, Deputy Resident Representative, UNDP Azerbaijan

## Documents reviewed

- “Rehabilitation of the Blood Bank and Transfusion Services in Azerbaijan”. Sustainability Analysis, Novermber 2003. Pricewaterhouse Coopers.

- “Rehabilitation of the Blood Bank and Transfusion Services in Azerbaijan”. Final Report, 15.03.2006. Pricewaterhouse Coopers.

- “Rehabilitation of the Blood Bank and Transfusion Services in Azerbaijan”. Bi-annual Project Report No. 1, January – June 2003, 30.06.2003. Pricewaterhouse Coopers.

- “Rehabilitation of the Blood Bank and Transfusion Services in Azerbaijan”. Bi-annual Project Report No. 2, July – December 2003, 20.02.2003. Pricewaterhouse Coopers.

- “Rehabilitation of the Blood Bank and Transfusion Services in Azerbaijan”. Bi-annual Project Report No. 3, January – June 2004, 09.07.2004. Pricewaterhouse Coopers

- “Rehabilitation of the Blood Bank and Transfusion Services in Azerbaijan”. Bi-annual Project Report No. 4, July – December 2004. 22.02.2005 Pricewaterhouse Coopers.

- “Rehabilitation of the Blood Bank and Transfusion Services in Azerbaijan”. Final Report, 15.03.2006. Pricewaterhouse Coopers.

- “Rehabilitation of the Blood Bank and Transfusion Services in Azerbaijan”. Annex 2: Budget for Purchase Order with Pricewaterhouse Coopers, Oslo.04.07 and 25.09.2002.

- “Rehabilitation of the Blood Bank and Transfusion Services in Azerbaijan”. Annex 2: Budget for Purchase Order with Pricewaterhouse Coopers, Oslo.09.03.2004.

- “Rehabilitation of the Blood Bank and Transfusion Services in Azerbaijan”. Technical Component of Proposal for Consultancy Services for UNDP/UNOPS. Project Plan 2003 – 2004 (Report from Inception Mission. Pricewaterhouse Coopers, Oslo.25.11.2002.

- UNOPS: INT/97/R12 Fund for Norwegian Consultancy Services and Programme Activities 00 AZE 2130 – Rehabilitation of Blood Transfusion System, 27.12.2002.

- Project Document: Government of the Republic of Azerbaijan, UNDP, Ministry of Health, WHO, and IFRC: Rehabilitation of the Blood Transfusion Services in Azerbaijan. Project period 2004 - 2005.

- UNDP Project Fact Sheets (from web-site)

- Statistics on AIDS in Azerbaijan (updated). Press release of the National Center on Struggle with AIDS, 1.12.2006.

- Ibrahimova, J. & Mamedova, L.: HIV/AIDS in Azerbaijan. In press.

- UNDP Country Programme 2005 – 2009.

- UNDP Annual Report, Health section. 2002.

For UNDP, soft assistance activities include advocacy, policy advice/dialogue, and facilitation/brokerage of information and partnerships.