Strengthening Capacity of Civil Society in

Response to HIV/AIDS (2002-2006)

Project ID: 00011278

The Outcome Evaluation

Prepared by:

Dr. Larisa Bashmakova, PhD

Baku, 2006

Table of contents

Abbreviations	3

Executive Summary	5

Introduction	8

Objectives of the Evaluation	8

Scope of the Evaluation	8

Methodology	9

Limitations	10

1. Background	11

1.1. The general information about the country	11

1.2. Economy	11

1.3. Spread of HIV	11

1.4. Driving Factors	12

1.5. Gender	12

1.6. State Policy on HIV prevention	13

1.7. UNDP Response	14

2. Key Findings	16

2.1. Achievement of the Outcome	18

2.2. Achievement of the Outputs	19

2.2.1. Capacity Building of the Civil Society	19

2.2.2. Information Support to National Stakeholders	20

2.2.3. Awareness Raising, Advocacy and Policy Dialogue on Strategic Approach to HIV Response	20

3. Outcome Evaluation	22

Conclusions	26

Positive Lessons Learnt:	27

Weaknesses and Constraints in Achieving the Outcome:	27

Recommendations on Future UNDP Response to HIV	27

# Abbreviations

| AIDS | - Acquired Immune Deficiency Syndrome |
| --- | --- |
| AZ | - Azerbaijan (Republic of Azerbaijan) |
| AzeriCASO | - Azerbaijan’s Council of AIDS Service Organizations |
| BP | - British Petroleum Oil Company |
| BTC | - Baku-Tbilisi-Ceyhan oil pipeline |
| CBOs | - Community Based Organizations |
| CSOs | - Civil Society Organizations |
| CCM | - Country Coordination Mechanism |
| CD | - Compact Disk |
| CEDAW | - UN Convention on Elimination of All Forms of Discrimination against Women |
| CIS | - Commonwealth of Independent States |
| CO | - Country office |
| DDRP | - Drug Demand Reduction Program |
| GDP | - Gross Domestic Product |
| GFATM/GF | - Global Fund to Fight AIDS, TB and Malaria/Global Fund |
| GO | - Governmental Organization |
| HDR | - Human Development Report |
| HIV | - Human Immunodeficiency Virus |
| HQ | - Headquarters |
| IDP | - Internally Displaced Person |
| ILO | - International Labor Organization |
| IDUs | - Injecting Drug Users |
| KAPB | - Knowledge, Attitude, Practice and Belief |
| M&E | - Monitoring and Evaluation |
| MDG | - Millennium Development Goals |
| MoH | - Ministry of Health |
| MoIA | - Ministry of Internal Affairs |
| MoJ | - Ministry of Justice |
| MSM | - Men who have Sex with Men |
| NGO | - Non Governmental Organization |
| NICTS | - National Information and Communication Technologies Strategy |
| NSP | - National Strategic Plan |
| OSI | - Open Society Institute |
| PAF/UNAIDS | - UNAIDS Programme Acceleration Funds |
| PIU | - Programme Implementation Unit |
| PLHIV (PLWHA) | - People Living with HIV |
| RBEC (UNDP) | - Regional Bureau for European Countries (UNDP) |
| SCWRA | - State Committee for Work with Religious Associations |
| SOFAR | - State Oil Fund |
| SPPRED | - State Programme for Poverty Reduction and Economic Development |
| SRF | - Strategic Results Framework |
| STI | - Sexually Transmitted Infections |
| SW | - Sex workers |
| TB | - Tuberculoses |
| UN | - United Nations |
| TORs | - Terms of Reference |
| UNADS | - Joint United Nation Programme on HIV/AIDS |
| UNDAF | - United Nations Development Assistance Framework |
| UNDP | - United Nations Development Programme |
| UNESCO | - United Nations Education, Science and Culture Organization |
| UNGASS | - United Nations General Assembly Special Session |
| UNFPA | - United Nations Population Fund |
| UNICEF | - United Nations Children Fund |
| USAID | - United States Agency for International Development |
| USD | - United States Dollar |
| VCT | - Voluntary Counselling and Testing |
| VG | - Vulnerable groups |
| WHO | - World Health Organization |

# Executive Summary

Like in other countries of Central and Eastern Europe, the primary mode of HIV transmission in the Republic of Azerbaijan is the injecting drug use. According to the sentinel surveillance data, Azerbaijan is at the second - concentrated - stage of the epidemic and HIV is primarily being spread among the injecting drug users and sex workers.

Difficulties of transition period resulted in high levels of poverty. Social hardship, unemployment, migration, socio-economic vulnerability, in particular of women, human trafficking, gender inequity are the major driving factors of the HIV epidemic.

The National Policy on HIV embedded in the National Strategic Plan on HIV Prevention was designed on the basis multisectoral approach. The HIV-related issues have also been mainstreamed into the State Programme for Poverty Reduction and Economic Development, 2003-2005.

The country is actively supported with financial and technical assistance by international donors, of which one is UNDP. HIV-infection is considered as one of the six UNDP priorities. Since 1998 the HIV related aspects have been incorporated into the UNDP programme in the Republic of Azerbaijan. Though the project represents a modest spending of UNDP resources in the country, it targets a strategic player in the HIV response – civil society. It is commonly recognized that resources available in the non-governmental sector are better positioned to respond to the community needs in prevention and NGOs are more motivated and able to work with vulnerable and marginalized groups. Prior to the project little attention has been paid to engagement of various civil society groups and their capacity has not been utilized.

The report analyses contribution of the UNDP Project Strengthening Capacity of Civil Society in Response to HIV/AIDS (2002-2006) towards achievement of the Country Programme Outcome “Strengthened policies, institutional capacities, and awareness raising regarding HIV/AIDS and STI prevention“. The Project covers three areas: 1) capacity building for non-governmental organizations; 2) capacity building for religious organizations, and 3) capacity building for community of people living with HIV (PLHIV). The findings of the evaluation allow concluding that progress towards the achievement of the anticipated outcome has been made. Positive developments in areas targeted by the project interventions are attributed to project implementation.

Achievement of the outcome. UNDP was the first organization which initiated promotion of the multi-sectoral approach and involvement of the civil society in response to HIV. This made a significant contribution to the developing national response on HIV-infection in general and incorporation of HIV-infection problem into the key country development concept - State Programme for Poverty Reduction and Economic Development. With approval of UNDP Country Programme outcome of Strengthened policies, institutional capacity and awareness regarding HIV/AIDS and STI prevention, it is logical to expect that UNDP focuses its efforts on multi-sectoral impact and support to the Three Ones principles. Yet, poor national coordination that does not ensure a truly multi-sectoral approach and broad involvement of civil society, is considered to be the limiting factor to more efficient use of NGOs capacities in the national response to HIV.

Achievement of the outputs.  Key outputs were achieved too.

1) Building capacities of the civil society:

Representatives of NGOs, religious communities and PLHIV were trained using peer education approaches and provided with resource materials (two training modules and five information toolkits). Capacities of the civil society organizations to design and implement HIV-related interventions increased; new stakeholders from religious communities and PLHIV were mobilized; regional coverage with HIV activities was extended;

2) Information support to national stakeholders:

A specialized library was  set up in the UNDP Resource Center on HIV/AIDS; a specialized web-site in the Azerbaijani language was created and remains the only on-line HIV resources in the country; 14 information materials of different types with total circulation of above  50 thousand copies were developed.

3) Advocacy and policy dialogue for strategic planning and awareness:

Multi-sectoral approach to HIV response was promoted through round tables and local events in support of the World AIDS Campaigns, hereby increasing interest and involvement of civil society; policy dialogue on various issues (e.g. human rights) was strengthened; understanding and tolerance of religious leaders towards HIV related issues improved.

At the time of evaluation the legal support component, namely establishment of Alliance (Council) for monitoring of violation PLH human rights and training for lawyers on legal support to PLHIV was to be re-scheduled for 1st Quarter 2007.

Though establishment of Azerbaijan’s Council of AIDS Service Organizations (AzeriCASO) envisaged in the project document was supported by all project partners, applications from potential members were collected and two meetings were held for the elaboration of its Charter, it was not established as planned. AzeriCASO  is still very much needed and plan to establish it in the future should not be abandoned.

By achieving the above outputs, the UNDP ensured progress towards achievement of the outcome through capacity-building and technical support to civil society organizations to enable them work on their own.

Partnership. Various forms of partnerships with international, governmental, non-governmental and community-based organizations were built by the project. The project mobilized financial resources from UN Agencies (UNFPA, UNAIDS) and other international organizations (OSI-SOROS). It has also made available knowledge and skills of its personnel to a number of international organizations and companies, e.g. ILO, World Bank, BP, IRD, IFRC. The project team developed partnership with the NGOs, religious leaders, communities and people living with HIV. The major highlight of the project was the religious communities succeeding in realizing various HIV/AIDS activities through the Forum for Religious Organizations initiated by religious leaders and uniting all confessions registered in Azerbaijan. Undoubtedly, this inter-confessional amalgamation has been one of the critical external factors that contributed to the achievement of the project outputs. The persisting poor understanding by the governmental organizations of importance of the civil society in implementing the national response to HIV particularly among the vulnerable groups of the population, constrains involvement of civil society into decision-making and their impact on planning and implementation of the national response.

Sustainability. Mobilization, commitment raising and capacity-building in NGOs, religious leaders and communities of PLHIV are the key factors that ensure sustainability of the project outputs.  However, to fully achieve the UNDAF/CP outcome, there is a pressing need to continue  providing UNDP support to the organizations involved in the project as well as to expand the present programmatic scope to strengthen multi-sectoral approach and promote the Three Ones principles. Mainstreaming HIV activities into other areas of the UNDP Country Programme will ensure broader involvement of decision-makers and the population that provide continuity and sustainability of the initiated HIV-related programmes.

# Introduction

HIV prevention is one of the five thematic Practice Areas of UNDP. UNDP in Azerbaijan has been active in this area since 1998 with the aim to support multi-sectoral approach to the national planning and policy-making in response to HIV. In 2002, building on its experience UNDP initiated the project Strengthening Capacities of Civil Society in Response to HIV/AIDS which focused on participation and capacity development of NGOs, religious leaders and PLHIV community. The intended outcome as stated in the SRF was Increased participation of NGOs/CSOs and youth movement through involvement of planning/management of development activities backed up by strengthening of their capacity. A new UNDP Country Programme for 2005-2009 retained this area as a priority.  However, to meet the current requirements and to reflect the joint contribution of the four UN Agencies – UNDP, UNICEF, UNFPA and WHO - in responding to the HIV the intended outcome has been adjusted to: Strengthened policies, institutional capacity and awareness regarding HIV/AIDS and STI prevention (2005-2009).

The UNDP intervention was made in the three main directions:

- Capacity building of the civil society;

- Information support to the national stakeholders;

- Awareness raising, advocacy and policy dialogue on approaches to HIV response

Following the completion of the successive stages of the UNDP project and according to the UNDP rules and procedures, an external evaluation was made to review the implementation of relevant outcome of the Country Programme. This report evaluates degree of achievement of the Country Programme outcome.

# Objectives of the Evaluation

According to the Terms of Reference (Attachment 1), the evaluation at the outcome level is to assess progress of UNDP’s project interventions towards achievement of the Country Programme Outcome - Strengthened policies, institutional capacity, and awareness regarding HIV/AIDS and STI prevention, including contributing factors and constraints. The evaluation should also generate lessons and experiences that could provide inputs or feed into the review of the current Country Programme and/or design and implementation of the next Country Programme.

The evaluator enables making an assessment of the performance of the project and sustainability of the project’s results upon its completion, as well as providing recommendations to UNDP and key project beneficiaries on further actions to sustain and expand the results achieved and additional strategies/interventions to fully achieve the CP outcome.

# Scope of the Evaluation

According to the Terms of Reference (Attachment 1), the outcome evaluation will be looking at the relevance and contribution of UNDP project activities with regard to the CP Outcome and evaluate the efficacy of strategies employed in contributing to the achievement of outputs. The scope of evaluation is expected to include lessons learnt, findings and recommendations in the following areas:

- Assess adequacy of the project design for the achievement of the CP outcome and project outputs;

- Assess what and how much progress has been made towards achievement of the  outcome, in part or full, the reasons for any shortfall in its achievement and whether any unexpected effects have occurred;

- Assess relevance and effectiveness of the applied strategies to the achievement of the outcome;

- Analyse the underlying factors beyond UNDP’s control that influence the outcome (including the opportunities and threats affecting the achievement of the outcome);

- Assess whether UNDP’s outputs and other interventions (soft assistance) can be credibly linked to the achievement of the outcome;

- Assess whether UNDP’s partnership strategy has been appropriate and effective, including the range and quality of partnerships and whether this has contributed to the achievement of the outcome.

# Methodology

The evaluation visit to Baku, Azerbaijan lasted for ten days (December 4-14, 2006). The evaluator got familiarized and followed the UNDP Guidelines: Guidelines for Outcome Evaluators: Monitoring and Evaluation Companion Series, #1; Handbook on Monitoring and Evaluating for Results.

The evaluator had the opportunity to meet the UNDP Project staff. Information was collected from about 44 people (18 meetings) from governmental, non-governmental, international organizations and beneficiaries (see list of the meetings – attachment 2). The meetings were arranged with UNDP staff for briefing at the start of the mission, advice and debriefing at the end of the mission with presentation of preliminary results.

The Outcome Evaluation was implemented using following methodology:

- Key informant interviews: Two project staff (Attachment 2) were interviewed about their experiences with the project and with UNDP, the constraints on implementation and how they had overcome them, their recommendations for improvements, the most significant change caused by the implementation of the project, their vision and plans for the project development in the future.

- Interviews with concerned individuals: The evaluator had open and frank discussions about the UNDP project, the local context and opportunities for improvements with 22 persons (Attachment 2) amongst whom were former and present governmental officials, representatives of international organizations and NGOs, and members of the target groups (PLHIV).

- Review of official records and key documents (Attachment 3): Ms. Jamila Ibrahimova, UNDP AZ Senior Programme Adviser, and Dr Ludmila Mamedova, UNDP Project Coordinator, provided the evaluator with all relevant documents such as the project documents, the Annual & Quarterly project reports, IEC materials produced under the project; reports on MDGs, HDR, UNESCO research. The evaluator also used the references from the Law of Azerbaijan on Prevention of Spread of HIV, National Strategic Plan on HIV/AIDS and UNDAF. The evaluator has used the UNDP (AZ, RBEC, HQ), and UNDP Project Resource Centre web sites.

- Site visits: The evaluator visited the UNDP Project’s Resource Centre for civil society, National AIDS Centre, the GFATM PIU, 3 NGOs, PLHIV community, 3 international organizations (UNDP, UNICEF, UNFPA).

- Focus group discussions with beneficiaries: were held with 8 members of the PLHIV in the office of their NGO.

- Direct observations: The evaluator participated at the Jazz concert organized by PLHIV community on the occasion of the World AIDS Day and a meeting under the  Ombudsman’s auspices to discuss human rights in the context of HIV.

- Geographically the evaluation cover Baku only but THE evaluator had an opportunity to meet representatives from youth regional NGOs from Ganja targeted by the project. Mr. Rovshan Muradov, The Voice of the Future” NGO, and Mr. Anar Guseinov, “The Bridge to the Future” NGO visited Baku specifically to meet the evaluator.

# Limitations

The evaluator visited Baku only and met representatives from one of the targeted region (Ganja). While this was a time-saving arrangement, it limited possibility to meet other people and obtain first-hand information on situation at the local level. The evaluator did not have a chance to meet Regional UNAIDS Advisor Ms. Renate Ehmer as she postponed her visit to Baku planned for other purposes. It was not possible to arrange the meeting with Soros Foundation Azerbaijan, one of the partners of the UNDP Project.

Establishment of Alliance (Council) for monitoring of violation PLHIV human rights and lawyers training on legal support to this community have been rescheduled for 2007 and have not been covered by the evaluation

# 1. Background

# 1.1. The general information about the country

Azerbaijan is the largest out of the three South Caucasian countries with a total land area of 86,600 sq. km. It has border with the Russian Federation (specifically Dagestan) to the north, Georgia to the north-west, Armenia to the west and Iran to the south. The country consists of 65 rayons (regions), and the Autonomous Republic of Nakhchivan. The largest city in Azerbaijan is Baku, the capital, with a  population of  1,725,900  (estimated as of 1 January 1998). Other large towns in the republic include Ganja, Sumgayit, Mingacevir and Nakhchivan. According to the State Statistics Committee, the country has a population of 8 265,7 thousand people at the beginning of 2004, 50.9% out of them are women and 51.5% live in urban area. About 10% of the country’s population are  refugees (311 000) и internally displaced persons (577 906), which had to change their place of residence as a result of the conflict in and around Nagorno Karabakh, or have moved from other places (Afghanistan, Russia, Iraq, Iran, Palestine). These groups are poor and the most vulnerable to HIV infection.

# 1.2. Economy

For the third year in a row, increased hydrocarbon production is forecast to give Azerbaijan the fastest growing economy in the world in 2007. GDP is $8.5 bln. ($1041 GDP per capita). The poverty has been decreasing every year, but still remain on a high level. 40.2% people were under absolute poverty line in 2004 ($36.4), while about 10% of population (9.6%) lived in extreme poverty ($25.26 a month). The unemployment rate was 1.43% of the labor force or 54365 persons, who were registered at the state employment offices. According to the independent assessment the real data can be higher (up to10.7%) and the majority of unemployed are people of the 15-34 age group.

# 1.3. Spread of HIV

HIV-infection is a problem of growing concern in Azerbaijan. The first case of HIV-infection among the citizens of the country was registered in 1992. In 1998 the number of reported PLHIV increased two fold and over the past 10 years, it has increased by 33.6 times, with an annual growth rate from  27% to 70%. Such a high rate of infection growth is characteristic for all CIS countries and considered by experts of WHO/UNAIDS the highest in the world.  The total number of HIV cases as on the 1st December 2006 was 1007 people, but most of them (84.5%) were registered during last six years. According to sentinel surveillance, HIV prevalence among IDUs was 16% (average Baku and Lankaran) and among sex workers – 8.5%. It means that HIV is concentrated among vulnerable population and the country is in the second – concentrated - stage of the epidemic. Thus, despite the present relatively low HIV incidence rate in Azerbaijan, a serious epidemiological situation is emerging in the country. HIV incidence is on the increase, in particular in Baku and Lankaran. More drug use and HIV cases, primarily among injecting drug users (IDUs), implies that new cases of infection may be snowballing. Indeed, such a scenario may already be underway based on the sentinel epidemiological surveillance data.

# 1.4. Driving Factors

Poverty and socio-economic vulnerability draws more and more people towards lifestyles and practices that place people at a high risk of HIV infection. High level of poverty follows limited access to school education. About 13% children aged 5-14 are working in order to supplement the family budged.

Poverty and unemployment stimulate migration, both internal and external. Meanwhile, people in search of better economic opportunities migrate from countries with low HIV-infection prevalence to those with more advanced epidemics (like Russia and Ukraine) and later return back hence facilitating the spread of infection.  Thus, according to data at November 1, 2004, 299 people (44.3% of total newly detected PLHIV) were infected outside the country. Unfortunately, it was not possible to find the assessment data on number of labor migrants.  Regional UNESCO survey estimates that 500 000 labor migrants have been moving to Russia and Ukraine since 1991. When interviewed, respondents estimated that over one million of Azerbaijani citizens work in other countries, predominantly in Russia and Ukraine.

Drug use has increased 10-fold in the last fifteen years and drug use prevalence is 135.1 per 100 000 of the population. Out of 17 000 officially registered drug users 84% were injecting drug users. Taking into consideration the closedeness of this group, it is thought that the real number of drug users is much higher than the official reports state, though assessment of the real size of this group has not been made. More than half of IDUs share syringes and needless. Use of condoms is reported in 13% and 20% of IDUs and SWs correspondingly in Baku and 1.7% and 4% IDUs with irregular and commercial sex partners in Lankaran. Sexual exploitation of women and human trafficking are increasing too.

# 1.5. Gender

The country ratified CEDAW in year 1995. The governmental gender policy is implemented under the coordination of the State Committee for Family, Women and Children Affairs. In 2000 the State Programme on Women’s Issues was adopted by Presidential Decree.

Gender based violence, mainly domestic violence and human trafficking, constitutes a particular public problem. According to the USAID Azerbaijan Assessment (2001) up to 30% of women have suffered from various abuses (verbal, physical, sexual). The same assessment found out “that concept of domestic violence was not well understood or widely discussed, but commonly accepted as a traditional norm within the general population”.

# 1.6. State Policy on HIV prevention

The Government of Azerbaijan has recognized HIV-related problems and initiated measures to intensify the responses to HIV epidemic. Having subscribed to a number of important, strategic international documents including the Millennium Development Goals (2000); the Declaration of Commitment on HIV/AIDS "Global Crisis — Global Action" adopted in the special session of the General Assembly of the United Nations in 2001 and the "Programme for Urgent Measures of CIS member-states for Control of HIV/AIDS epidemic" in 2002, Azerbaijan has taken the commitment to implement a complex of measures aimed at halting the HIV epidemic and alleviating its social and economic impact. Millennium Development Goals (MDG) laid foundation for the State Programme on Poverty Reduction and Economic Development (SPPRED) for 2003-2005. Hence, measures to combat HIV reflected in one of the eight MDGs, was incorporated into the key country development strategy.

Development of the Government policy in the area of HIV/AIDS started with the adoption of the Law "On preventing the Spread of AIDS caused by HIV". A strong base of HIV-related legislation is now in place that guarantees rights and service provision tor PLHIV and establishes institutional mechanisms for the prevention and treatment of HIV and AIDS. However,  legislative barriers and law-enforcement practices limiting access of vulnerable groups to prevention programmes are reported alongside with high stigmatization and discrimination of people living with HIV. Such situation calls for a deep analysis of the existing legislation and development of legislation improvement strategy as well as development of measures for reduction of social ostracism of PLHIV.

The first National Programme on prevention of HIV/AIDS spread on the territory of Azerbaijan (1997-2002) ,was developed with a view to implement the Law. The Programme facilitated development of complex prevention initiatives based on multi-sectoral approach and attraction of international technical and financial support.

The second National Strategic Plan (NSP) on prevention of HIV/AIDS in Azerbaijan was approved on September 25, 2002 by the Cabinet of Ministers decree no 205s. NSP includes nine key strategies with a total budget of $31 million. Its goal is to decrease the transmission of HIV-infection by an urgent and adequate response, through comprehensive and modern approach. It supported promotion of the multi-sectoral (multidisciplinary) approach and cooperation between various ministries, state departments, NGOs, and international organizations as partners in the implementation of the NSP’s actions . Managerial and coordinating role belongs to the National Committee to Fight and Prevent AIDS (NICCHIV/AIDS) established by the Decree N 164 of the Cabinet of Ministers on August 16, 2002.

From the programmatic perspective, the national response to HIV epidemic in Azerbaijan has not been adequate, to a large extent due to socioeconomic turmoil, deteriorating health care system and the collapse of the social safety nets that accompanied the shift to a market-driven economy. In the country much has been done under the framework of the first and the second national programmes, however, there is still a need to improve the interventions among vulnerable populations (IDUs, CWs, MSM), youth and PLHIV.

The multi-sectoral response to HIV-infection has been developing slowly. The country needs establishment of effective and efficient coordination mechanism enabling all stakeholders to participate in the national response.  Public health system continues to have centralized responsibility and coordination of HIV-related programmes. The Ministry of Health acts as lead executing agency of the Strategic Programme; as a key recipient of the GFATM grant and chairs  the Country Coordination Mechanism (CCM). At the same time representatives of main sub-recipients of GFATM (UNICEF and OSI Azerbaijan) are the members of the CCM. This contradicts the policy of the Global Fund and creates a conflict of interests. Civil society groups have not been adequately involved in the national response. For example, Azerbaijan is the only country that did not involve NGOs in the sentinel surveillance among high risk behaviour groups in three countries (2003-2004).

The Strategic Programme remained largely unfunded and domestic spending on HIV has been limited to paying salaries for HIV-related medical staff and maintenance of health infrastructure. In year 2005 Azerbaijan received GFTATM grant in the amount $ USD 10.3 million, including USD 6.5 million for the first two years (2005-2007). The country is a beneficiary of international technical assistance and financial support from the UN agencies, OSI and other financial institutions. Yet, with state budget allocations and GFATM resources, available funding for  the Strategic Programme was just 25% of the total requirement. This resulted in low coverage of vulnerable groups of the population, low efficiency and consequently in persisting threat of rapid escalation of HIV, which is now observed in other CIS countries.

Draft of a new National Programme on prevention and control of HIV and STI for 2007-2011 in the Republic of Azerbaijan was developed (but not yet approved) in the country.  However, prior situation and response analyses have not been made, nor wide discussion with partners from various government structures and other sectors were arranged. This reveals the problem with the governance of the response and the existing niche for possible involvement of UNDP and UNAIDS in the area of improvement of national policy and attraction of international technical assistance from the UN with a view to strengthen the national response. Adequate national policy and increase of the state financing are of crucial importance for attainment of the sixth Millennium Development Goal in Azerbaijan: «Have halted by 2015 and began to reverse the spread of HIV/AIDS”.

# 1.7. UNDP Response

During the last several years, UNDP’s contribution to the global effort to reverse the HIV spread has greatly intensified, focusing on the governance challenge of planning and implementing a truly multi-sectoral and society-wide response to the epidemic. In Europe and the CIS, where the number of people living with HIV has increased nine-fold in the past decade and continues to rise, UNDP promotes placing HIV problem at the centre of national development dialogue and budget decisions; helps build national capacity to manage and implement strategies that engage people and institutions not usually involved with public health; promotes decentralized and gender-sensitive responses that support community-level action; and mobilizes domestic and international resources for programmes. UNDP programming supports a coordinated UN response to HIV epidemic within the UNAIDS Division of Labour.

UNDP was the first international organization in Azerbaijan which provided support to the government in HIV-related area back in 1997, and for past 10 years has made a great contribution into promoting the concept of multi-sectoral response and building national capacities to fight HIV. The central role in operationalizing UNDP response belongs to the Resource Centre on HIV/AIDS for civil society organizations established by UNDP in 1999.

The UNDP Country Programme 2005-2009 for the Republic of Azerbaijan emerged from two national consultation processes: preparation and adoption of the State Programme for Poverty Reduction and Economic Development (SPPRED) which includes achievement of Millennium Development Goals (MDGs) and preparation of the United Nations Development Assistance Framework (UNDAF). Both were participatory processes engaging the Government, Parliament, UN agencies, IFIs, bilateral donors, NGOs and businesses. During the First Joint Strategy Meeting of Azerbaijan’s in March 2004, the Government reviewed and validated the UNDP Country Programme and its linkage to the UNDAF.

The Country Programme identifies two key directions for UNDP interventions in HIV:

1) Civil society develops/implements HIV prevention activities, and

2) Rehabilitation of the blood transfusion system and revision of related policy framework.

In addition to two dedicated interventions aimed at preventing HIV, UNDP has indirectly addressed driving factors of the epidemic such lack of access to information, unemployment, human rights violations, through projects supporting development of national ICT strategy, employment strategy, and establishment and support to the Ombudsman institution,

# 2. Key Findings

UNDP project Strengthening Capacity of Civil Society in Response to HIV/AIDS (2002-2006) has been implemented with co-funding from UNFPA and OSI-SOROS in the first years of implementation. Its success allowed attracting additional resources from UNAIDS for expansion of its scope both in terms geographic coverage and target groups within the civil society such as like religious leaders and PLHIV.  Total budget of the project at the time of evaluation was $285 985 of which $152 100 was contributed by UNDP.

In the outcome evaluation the project is considered as an integrated whole regardless of timing and sources of financing.  Evaluation of the CP outcome & project outputs was at the heart of the evaluating process. As a result, it revealed that progress towards the CP outcome was achieved. The project activities resulted in positive developments in all areas targeted by the project interventions.

The UNDP contribution was assessed in three key areas (relevant to key project outputs):

- Capacity building of the civil society;

- Information support to the national stakeholders;

- Awareness raising, advocacy and policy dialogue on strategic approach to HIV response.

The evaluation includes evaluation of each area against the following parameters:

  - achievement of the outputs;

  - achievement of the outcome;

  - partnership;

  - sustainability.

The table below summarizes intended outputs and actual achievements of the project and their contribution to the achievement of the CP Outcome. Tabulated presentation allows to reflect specific project activities of the project and demonstrate their linkages with and contribution to the outcome.

Table 1

Achievements of the UNDP Project Strengthening Capacity of Civil Society in Response to HIV/AIDS

| Intended outcome (UNDAF) Strengthened policies, institutional capacity and awareness regarding HIV/AIDS and STI prevention (2005-2006) |  |  |  |  |
| --- | --- | --- | --- | --- |
| ## | Intended outputs | Outputs target | Progress towards achievement of the project outputs | Progress towards achievement of the CP Outcome |
| 1 | 1.1.NGOs are trained to design and implement HIV/AIDS prevention programmes and impetus is given to initiation of HIV prevention activities in the regions of the country 1.2.Peer education approaches are introduced | NGOs are able to identify the environmental and organizational factors, that influence successful design and delivery of HIV/AIDS intervention | NGOs in the regions were trained on topic of the project design, funding and implementation. Training materials and 5 information toolkits were designed and distributed. The project staff provided consultancy to NGOs in Baku and selected region on project design, implementation and resource mobilization. | NGOs and community of PLHIV have developed their capacity to design projects and manage HIV/AIDS interventions among their target groups |
|  |  | At least three regions of AZ are covered with training activities | Five regions has been covered with training activities (including training activities for religious leaders) | NGOs and CBOs of five regions of AZ are involved into the national response to HIV epidemic |
|  |  | At least 20 NGOs will become familiarized with approaches to peer education and hard-to reach groups in a resource scarce environment | 57 NGOs, 80 religious communities and PLHIV community were educated on peer approaches and involved into national response to HIV epidemic | NGOs and CBOs have obtained knowledge and skills on peer education and work with hard-to reach groups: as MSM, SW, IDU, PLHIV in a resource scarce environment. The number of civil society organizations has increased and their role in National response received acknowledgement. For the first time in Azerbaijan religious community and people living with HIV were involved into HIV prevention programmes All this has further promoted application of the concept of the multisectoral approach in national response planning and implementation . |
| 2 | 2.1.Information sources on HIV/AIDS and related topics are easily accessible at HIV/AIDS Recourse Center’s library and the website | The library of the NGO RC monthly accommodated 20 visitors | The Resource Center’s library has more than thousand national and international sources of information on Azeri, English and Russian. 14 information materials, including 2 СDs with total circulation of 50 450 copies were issued; 6 issues of quarterly AIDS INFO Newsletters were published. 13 visitors attended the library of the NGO RC monthly. | The country received a solid information base which can support the national response to HIV epidemic. Resource Center became a facility providing easy access to information, education, counseling for NGOs, GOs, mass media and religious organizations. National capacity to develop information materials was built. The first and the only HIV/AIDS dedicated website in AZ was created, became relevant and used |
|  |  | Website is operational and user friendly | Above 32 thousand people have already visited this site |  |
| 3 | 3.1.Strategic planning approach is promoted through stakeholders discussion 3.2. Awareness of socio-economic impact of HIV/AIDS across various sector of the society increased | Policy dialogue with a view to build consensus around priorities and policies among key stakeholders scaled up | Three round table discussions were conducted on “Human Rights and AIDS”, “Religion and AIDS”, “Role of NGOs in Multisectoral Response” topics Two national conferences were held with participation of 110 people | Dialogue between civil society and governmental organizations has been established. Religious leaders have increased their awareness on HIV problematics,, developed commitment to make their contribution to the national response and reached consensus on key directions of their activities in response to HIV. |
|  |  | Professionals of various background including decision makers have broader understanding of the HIV problems | Special trainings for NGOs members, teachers, heads of district branches of the government (Baku), religious leaders etc. were held in Baku and 4 regions of the country |  |

# 2.1. Achievement of the Outcome

The purpose of the Project Strengthening Capacity of Civil Society in Response to HIV/AIDS (2002-2006) fits into the  Country Programme Outcome 3.3 «Strengthened policies, institutional capacity, and awareness regarding HIV/AIDS and STI prevention». The Project contributes to  the achievement of the CP Outcome in three ways:

- Strengthening of HIV-related policy in the country;

- Development of civil society institutions;

- Awareness raising on HIV-related issues.

Strengthening of HIV-related policy

The Project supported promotion of the concept the multi-sectoral approach by advocating for CSOs involvement in the HIV–relates programmes and their capacity building. It has raised awareness of the NGOs, governmental organizations, mass media on the multi-faceted nature of the epidemic and its driving factors and facilitated initiation of the inter-sectoral dialogue.  In the public events, Resource Centre website and printed materials UNDP put a strong emphasis on socio-economic impact of HIV thus contributing to an important shift in the policy from medicalized to broader developmental approach. Furthermore, it has also acted as a strong advocate of the International Guiding Principles on human rights in the context of HIV/AIDS by, inter alia, organizing a high-profile public event to launch the principles in Azerbaijan. Inclusion of HIV-related issues into the State Programme for Poverty Reduction and Economic Development (SPPRED) can be attributed to the significant advocacy efforts of the UNDP Project. .

Development of civil society institutions

This is a major and direct result of the Project. The project represents the first comprehensive and consistent attempt to build capacities of the civil society to participate in the HIV response which at that time exclusively relied on the top-bottom system and was unlikely to effectively reach the community level. NGOs at the national and regional level benefited from highly professional trainings, easily accessible information materials and consultancy support available from the Resource Centre upon demand. NGOs at the national and regional level were educated, built their capacity and have been participated in national response to HIV epidemic. It is noteworthy that the project worked with a large variety of civil society organizations such as NGOs working with women, youth, MSM, sex workers, IDUs, refugees/IDPs, human rights associations, religious organizations and PLHIV community, For example, the project facilitated establishment of the first support groups for PLHIV.

The project has immensely contributed to the change of relations between the Government and NGOs contributing to trust building and partnership. NGOs and PLHIV community are members of the Country Coordination Committee and benefited from the small grants programme financed by the Global Fund...

Awareness raising on HIV-related issues

UNDP project effectively raised awareness of all key players on a wide range of HIV-related issues such as driving factors of the epidemic, socio-economic impact of HIV epidemic; role of the CSOs in the national response, stigma and discrimination against PLHIV and other marginalized groups. The project created the largest multi-lingual information resource on HIV/AIDS in Azerbaijan which played a crucial role in increasing HIV awareness.. The first and the only national website and library specialized in HIV contain diverse information materials that to the best international sources information such as UNAIDS, WHO, CDC and other reputable organizations. The project has also collaborated with mass media that further contributed to the awareness raising.

# 2.2. Achievement of the Outputs

The project has planned to achieve 5 outputs (see table above) which can be clustered in three areas conventionally names as:

- Capacity building of the civil society;

- Information support to the national stakeholders;

- Awareness raising, advocacy and policy dialogue on strategic approach to HIV response

The biggest progress was achieved in the first and second intervention areas.

Following the meetings with the project implementation team, project partners and beneficiaries and based on the analysis of the available documents, one can conclude that undoubted success was reached in these intervention areas. Analysis of progress towards intended project outputs is presented in the table above with some comments and analytical remarks thereto.

### 2.2.1. Capacity Building of the Civil Society

The project has reached out to 137 civil society organizations which benefited from various capacity building opportunities such as trainings, round tables, meetings and consultancy support. These were reported to have been conducted in a friendly atmosphere. The organizations were helped to acquire skills and knowledge in project design and formulation, partnership building and resource mobilization. During the mission the evaluator had 8 meetings with CSOs, stakeholders from governmental and international organizations who provided positive feedback that is regarded as a proof of successful work.

A special mention goes to the wide scope of the project activities, both in terms of geography – five regions of the country, and target groups.  The project beneficiaries are NGOs with various missions among which are those working with vulnerable groups such as women, youth, high risk behaviour groups, PLHIV communities and 80 religious communities representing different confessions. Sustainability of the process has been ensured not just by transfer of skills, knowledge and access to technical and information support, but by building commitment to the fight against HIV. It is particularly noteworthy that some project beneficiaries succeeded in receiving grants support from GFATM, OSI-AZ and have had a chance to apply their skills in practice.

The project created conditions for the establishment of Council of AIDS Services Organizations (AzeriCASO) as a body for coordination of activities among NGOs/CSOs, exchange of experience and information, and networking. In this respect, one should note certain challenges faced here. In particular, these challenges refer to under-developed leadership skills of NGOs that still rely on international support and facilitation in promoting HIV prevention programmes, participation in the Country Coordinating Mechanism, resource mobilization and network building. Considering the remaining points of disagreement between the civil society institutions and weakness of the national coordination tools there is a pressing need in further unifying civil society institutions and partnership promotion.

### 2.2.2. Information Support to National Stakeholders

The biggest achievement was the national capacity building in developing the informational materials adapted to the local mentality and cultural traditions. The UNDP Resource Center has set standard for production of an information material on HIV that is written in a simple non-discriminatory language, is ethical and esthetical, based on reliable international resource and tailor-made to local context.

The website of the Resource Centre presents HIV/AIDS related information in a user-friendly manner. It remains the only source of online information on HIV in the Azerbaijani language and it is undoubtedly a very popular and actively visited site. Availability of the Resource Center, its website and the library allow interested parties have an easy access to information on practically all HIV related issues. Great deal of work has been accomplished for the collection, systematization and cataloguing of information materials and development of the information provision system, when provision of information is supplemented by advice and consultancy of a professional of the Resource Centre.  This unique system needs further support from the UNDP and other donors to make it widely accessible.

Joint financing would allow increasing the circulation of informational materials, which currently remains insufficient and would promote partnership and coordination. Besides, it would provide the Resource Center with additional information on activities of other  stakeholders, thereby increasing value and visibility of the Resource Center.

### 2.2.3. Awareness Raising, Advocacy and Policy Dialogue on Strategic Approach to HIV Response

This area of intervention includes two outputs:

3.1. Strategic planning approach is promoted through stakeholders’ discussion;

3.2. Awareness of socio-economic impact of HIV/AIDS across various sectors of the society increased.

Advocacy and awareness activities reached out to diverse audiences. A series of round tables organized on various topics highly pertinent to the socio-economic aspects of the epidemic provided forum for discussions between the governmental and non-governmental stakeholders. The project created opportunities for almost all line ministries and interested NGOs to exchange opinions and make progress towards consensus building on key priorities for response in Azerbaijan.

A major breakthrough is mobilization of religious leaders by building their motivation and commitment and inter-confessional partnership. Here one should emphasize importance of cooperation reached between the governmental body - the State Committee for the work with Religious Associations - and religious communities from various confessions. Sustainability of this area of intervention is beyond question.  Moreover, such unification of religious leaders from various confessions is testimony to high level of tolerance and can serve as a good practice example for partnership development.  This experience needs to be widely promoted in and outside the country, especially in multi-ethnic countries of Eastern Europe and Central Asia.

Unfortunately, immature state of democracy impedes implementation of a truly multisectoral approach to strategic planning, in particularly in terms of utilization of civil society potential which in turn is an obstacle to the fully-fledged implementation of the national response to HIV in the Republic of Azerbaijan. Therefore, still much has to be done in this area.

It should be noted that predominant focus on civil society capacities building limited the project’s impact. It is the author’s opinion that better results can be achieved by working in parallel at the senior official level. While recognizing important role of the civil society, the decision on the national policy are taken by the governmental structures.  Without their good will, acknowledgement and respect of civil society one can hardly expect any serious breakthrough in involvement of the civil society and elaboration and implementation of the national policy.

As far as the strategic planning – in compliance with the Three Ones principles – is concerned,  one national  policy, one coordination mechanism and one M&E system still remain to be developed. Emphasis should be made on full involvement of civil society in the implementation of the Three Ones that is not yet genuinely applied in practice. Country cannot have a separate policy for civil society – it should be an integral part of the national policy on HIV..

# 3. Outcome Evaluation

This chapter includes information on the relevance and contribution of UNDP project activities to the CP Outcome and evaluation of the efficacy of strategies employed in contributing to the achievement of outputs. The scope of evaluation includes lessons learnt, findings and recommendations in the following areas:

Assess adequacy of the project design for the achievement of the CP outcome and project outputs

The UNDP Country Programme for the Republic of Azerbaijan covers 2005-2009 and the outcomes encompass five UNDP corporate practice areas and mainstream cross-cutting issues such as human rights and gender. It was approved in 2004, i.e. the third year of the project’s implementation. The CP adopted UNDAF outcome on HIV/AIDS shared by four UN Agencies (UNDP, UNICEF, UNFPA and WHO). Correspondingly, the CP Outcome «Strengthened policies, institutional capacity, and awareness regarding HIV/AIDS and STI prevention» is focused on attainment of the results that are broader than the scope defined in the design of this project.

Project activities are adequately formulated to achieve the intended project outputs and fully aligned with the overall goal of the project to strengthen civil society development for the implementation of HIV prevention activities.

While the project design is adequate to achieving the progress towards the CP outcome it is not sufficient to fully achieve it. It is therefore recommended that in 2007-2009 UNDP re-orients its contribution towards supporting the development of the country policy in general and strengthening coordination system based on the Three One’s principles. Such change is attributable to needs of the mandate, policy and practice of UNDP and is a roadmap to attaining the goals embedded in the UN General Assembly Special Sessions on AIDS in 2001 and 2006 and the Millennium Development Goals.

Design of future UNDP programmes should consider closer integration of HIV and gender programmes. Such integrated approach will demonstrate the strong linkages and inter-action between the two problems as well as will demonstrate cumulative economic, demographic and social impact arising from juxtaposition of these problems. On the one hand, integrated approach to designing interventions can further strengthen multi-sectoral approach, bring prevention programmes closer to mobile and rural populations, and increase political commitment. On the other hand, it would enable to mobilize and efficiently utilize additional resources including those from the state budget and oil business. Furthermore, integration would add on sustainability and strengthen collaboration between international organizations and funds working  in HIV-related areas.

Assess what and how much progress has been made towards achievement of the  outcome, in part or full, the reasons for any shortfall in its achievement and whether any unexpected effects have occurred

This project is the first intervention that gave impetus to the development of partnership between the governmental institutions and civil society. Still the unwarrantable competition and distrust between these sectors continue to exist. Detailed assessment of progress towards the achievement of the outcome was described on pages 16-17 under ‘Key findings” Section. Based on the findings one can state that the CP outcome has been partially achieved.

As stated above due to some disaccord in timing between the development of the project in 2002_ and formulation of the new UNDP Country Programme of 2005-2009 the project’s scope does not fully address the multiple challenges of improving policies, strengthening institutions and raising awareness. It is not attributable to the project shortcoming per se; rather it results from the UNDP programme formulation process. It should also be noted that this is a mid-term outcome evaluation of UNDP contribution only and full achievement of the outcome is realistic to expect towards the end of the Country Programme and with joint participation of the four participating UN Agencies.

Assess relevance and effectiveness of the applied strategies to the achievement of the outcome

The key strategies applied in the project are:

-	maintenance of a specialised HIV/AIDS Resource Centre for CSOs;

- education;

- information support;

- provision of consultancy services;

- facilitation of multi-sectoral dialogue.

Resource Centre serves as a technical facility managed by professional, well educated, creative and committed project staff providing different types of capacity development tools (trainings, information support, consultancy services) to CSOs working in the area of HIV/AIDS. Interactive and peer-to-peer methodology applied during trainings was found efficient for strengthening capacities of CSOs.

It is noteworthy that the strategies were not only aimed at developing in-house capacity of the CSOs but also facilitated building relations and trust between various groups of CSOs (NGOs, religious communities, PLHIV) and with stakeholders from other sectors (government, international organizations) thus paving the avenue towards a multi-sectoral response.

This combination of the capacity development strategies was found relevant, effective and comprehensive in supporting progress towards the achievement of the Outcome.

Analyse the underlying factors beyond UNDP’s control that influence the outcome (including the opportunities and threats affecting the achievement of the outcome)

Civil society participation in the national policy development and other important processes remains tokenistic.  A good example is the WHO-supported sentinel surveillance among hard-to-reach groups in three countries of the CIS (Azerbaijan, Moldova, Russian Federation). Only in Azerbaijan NGOs working with these groups were not involved in the study. .

Another factor affecting achievement of the outcome is lack of assessment and evaluation culture in developing national programmes. Formulation of a new Strategic Plan on HIV was not based on assessment of the situation and evaluation of the response strategies employed in the previous Strategic Plan and thus maybe misleading in terms of the set priorities to which UNDP is to align its support.

Insufficient attention is accorded to the needs of vulnerable groups. This has strikingly shown at the meeting in the Ombudsman office devoted to human rights of PLHIV in which none of the representatives from the vulnerable groups participated.

There is a persisting conflict of interests in the implementation of the GFATM grant, with the Ministry of Health performing the execution function as Principal Recipient and the supervisory function as chair of the CCM while the other two sub-recipients – UNICEF and OSI AZ – are the members of the CCM.

Some legislative acts, law-enforcement practices and negative discriminatory attitudes make it difficult to reach out to the vulnerable groups of the population (like sex workers and drug users), thereby impeding prevention programmes among these groups.

The Government is not yet ready for targeted investing into the epidemic response while donors’ resources are inadequate to prevent further spread of HIV-infection in the country. All this is the evidence of urgency of increased UNDP contribution in terms of capacity building and technical assistance to the Government of Azerbaijan for the development and implementation of national policies and response.

Assess whether UNDP’s partnership strategy has been appropriate and effective, including the range and quality of partnerships and whether this has contributed to the achievement of the outcome.

The project developed partnerships with the following range of partners:

Civil society organizations (non-governmental organizations, religious communities, PLHIV):

Considering the strategic role of the CSOs in the HIV response, this is the most critical type of partner for the success of the project and the progress towards the outcome. Relations between UNDP and the CSOs were first established as those of service provider – beneficiary later evolving into that of allies in advocacy for policy changes and promoting UN principles, initiatives and approaches.

UN Agencies (UNFPA, UNAIDS):

This relations can be characterized as those of co-funders of various project components in compliance with their mandates, priorities and criteria while pursuing common goal of preventing spread of HIV in the country;

Other international organizations (IRD, IFRC, IMC, World Vision, ISAR, World Bank):

Though service provision to international NGOs was initially out of the scope of the project, the need in UNDP knowledge, experience and resources was in high demand by international organizations. The project trained peer leaders from refugee community for IRD; provided information support to IMC for the HIV components of BTC community investment programme; assisted IFRC in designing programme for youth; organized HIV in workplace sessions for the staff of the World Bank and BP etc.  The partnership created enabling conditions for multiplication of good practices developed by the UNDP Resource Centre critical for spillover effect.

Government:

UNDP built commendable partnership with the SCWRA in the course of implementing the component on religious communities. Both parties showed high level of commitment and fully delivered on their responsibilities which were clearly defined and based on their mandates. This partnership resulted in what can be described as ‘best practice’ in HIV-work with religious organizations, at the same time provided a model of relations between civil society and government. Other line ministries were provided with information support and engaged in the dialogue through round table discussions.

In general, the partnership strategy has been appropriate and effective and has clearly contributed to the progress towards the outcome.

However, UNDP’s partnership strategy around achievement of the outcome will benefit from further expansion. On the one hand, UNDP, being the technical assistance agency, needs additional financial resources to sustain and expand its interventions. On the other hand, the newly launched projects, like the GFATM grant project, need the technical expertise that the UNDP is capable to provide in areas of its comparative advantages as defined in the Global Division of Labour building on its 10- year experience in fighting HIV in the country and its coordinating role for the UN System. UNDP is undoubtedly capable to help strengthen coordination between the UN HIV Theme Group and the Country Coordination Mechanism and build the Government capacities for coordination of HIV-related programmes in compliance with the Three Ones’ principles and, multi-sectotal approach.

# Conclusions

Azerbaijan had political will to develop national strategy on HIV-infection prevention and accumulated experience from its implementation thus improving its capacity to counteract the epidemic.  The major indicator to this is the incorporation of HIV-infection issues into the State Programme for Poverty Reduction and Economic Development. Meanwhile, high poverty level, consequences of the conflict, abundant refugees and internally displaced populations continue to be a factor of potential instability in the society and absorb huge amounts of resources which could have otherwise been spent on social projects. With its sizeable oil stocks, Azerbaijan is perceived by the international community as a rich country. This, in turn, results in rather small allocations of external aid to the country; and creates dissatisfaction with limited capacities among the population. Yet, the country faces serious challenges such as unbalanced growth, slow pace of reforms, deterioration in health and education standards, escalating rate of HIV.

Analysis of the HIV response shows that until now the civil society capacities have not been fully employed, CSOs have not been treated as legitimate partners and fully-fledged participants of the national response on the part of the government. This is largely due to inadequate understanding of the role of the CSOs and lack of partnership building skills.

Strengthening capacities in response to HIV is one of the areas of support identified in the UNDP Country Programme. .UNDP contribution in 2002-2006 was of paramount importance for for national capacity-building for multi-sectoral approach and overall implementation of the national response, especially at the community level through CSOs.  Indirectly it has also contributed to the recognition of the needs of vulnerable groups.

Some of UNDP deliverables can be described as the best practices. This applies to the concept of the Resource Centre on HIV/AIDS and component on the religious communities. As a result of the project the first cohort of NGOs working in Baku and four regions of the country to overcome spread of HIV-infection was established, foundation for the involvement of the civil society in the national response was laid down. The project set a model of interrelation between vulnerable groups and people forming public opinions which can be replicated in other geographic areas and with other partners.

This experience may be useful to other countries with similar political pattern and epidemic stage. Soft types of assistance such as initiation and facilitation of round tables and informal discussion with a wide range of stakeholders from the government, non-governmental and international organizations provided forum, virtually inexistent prior to the project, for debates on priorities and approaches to HIV prevention programmes, the first step towards consensus reaching. Institutionalization through the establishment of the Resource Center and forum of religious organizations secured sustainability of the initiated interventions.

All project outputs have been fulfilled and progress toward the outcome was achieved. The outcome can only be fully achieved if the interventions have longer term perspective and HIV is mainstreamed into other sectors of the programme. As its next step UNDP should think through its future support along the lines of the UN global initiatives such as Three Ones and the country’s commitments, first of all, in the framework of the UNGASS Declaration. UNDP should continue to advocate and promote interests and involvement of civil society in decision-making and strategy formulation processes, strengthening capacities for strategic planning and coordination at the national level, as well as among the UN Agencies. The mandate, experience and capacity accumulated since 1998 position UNDP to be the lead organization in pursuing these challenging tasks.

# Positive Lessons Learnt:

- Knowledge, skills and commitment of the project staff were instrumental for the delivery of all planned activities;

- Long-term presence and good reputation of the UNDP project in the country generated respect and confidence in its activities;

- Advocacy, effective communication and partnership building approaches allowed to build the commitment of the stakeholders;

- Development of user-friendly learning and information materials support replication and sustainability;

- Intervention among PLHIV  helped the community to get self-organized and initiate their involvement into decision making through CCM membership;

- Strengthening organizational capacities of CSOs in project management, fundraising, partnership building were important for long-term sustainability of civil society organizations;

- Engagement of the religions leaders further contributed to the attitudes of tolerance and non-discrimination among the general population;

- Information materials tailor-made to the national mentality increased their understanding and value to the target groups;

- Comprehensive approach to information sharing including distribution of printed materials, DVDs, training kits, online resources and mass media participations makes the information accessible to different groups of the population.

# Weaknesses and Constraints in Achieving the Outcome:

- Impact of the capacity building efforts can be multiplied if all national partners in the response are reached, i.e. Government, NGOs, international organizations;

- Change of the partner in the key Government position (e.g. Chair of the State Committee for Work with Religious Associations) may jeopardize long-term success and thus require continued attention and support from UNDP and other donors;

- Partnerships building should be a long-terms process building on consultation and consensus with all stakeholders from governmental institutions, civil society, international organizations;

- Lack of national coordination constrains the process of national policy development and implementation.

# Recommendations on Future UNDP Response to HIV

Outcome: Strengthened policies, institutional capacity and awareness regarding HIV/AIDS and STI prevention (UNDAF 2005-2009)

Support to Three Ones initiative:

- Strengthening  of the Country Coordination Mechanism;

- Review and improvement of national legislation;

- Support of the national strategic and sectoral plans development (for line ministries and  state committees);

- Scaling up technical and informational support to the civil society organizations;

- Design and implementation of partnerships in response to HIV;

- Advocacy and leadership development for increased commitment;

- Expansion of  the information support .

Support within the UN System:

- Strengthening  the coordination of the UN Agencies through the UN Theme Group on HIV/AIDS or through the UN Resident Coordinator system;

- Annual review of  progress towards  the HIV-related outcome of UNDAF;

- Mainstreaming of HIV  into various sectors covered by UNDAF  and the Country Programme;

- Longer-term (5 years) planning and resource-mobilization for HIV projects .

Strengthening Capacity of Civil Society in Response to HIV/AIDS, the project document. Baku, 2001.

For UNDP, soft assistance activities include advocacy, policy advice/dialogue, and facilitation/brokerage of information and partnerships.

State Programme on Poverty Reduction & Economic Development. Progress Report 2003/2004. Baku, 2005, p. 23.

ibidem, p. 50.

ibidem, p. 26-27; 32-33.

ibidem, p. 36-37.

AIDS Epidemic Update: December 2003; 2004; 2005; 2006. UNAIDS/WHO, Geneva, Switzerland, 2003; 2004; 2005; 2006.

Smolskaya T. HIV sentinel surveillance in high-risk groups in Azerbaijan, the Republic of Moldova and the Russian Federation. EURO WHO, 2004.

Smolskaya T. HIV sentinel surveillance in high-risk groups in Azerbaijan, the Republic of Moldova and the Russian Federation. EURO WHO, 2004, p. 42.

HIV/AIDS Regional Report: HIV/AIDS in Eastern Europe and the Commonwealth of Independent - Reversing the Epidemic / Facts and Policy options. UNDP, Bratislava, 2004, p. 48.

State Programme on Poverty Reduction & Economic Development. Progress Report 2003/2004. Baku, 2005,p.47.

HIV and AIDS in the Caucasus Region: A Socio-Cultural Approach. UNESCO, 2005, p. 22.

HIV and AIDS in the Caucasus Region: A Socio-Cultural Approach. UNESCO, 2005, p. 54, 21.

ibidem, p. 59.

Ibidem, p. 67.

HIV and AIDS in the Caucasus Region: A Socio-Cultural Approach. UNESCO, 2005, p. 62

National Programme on prevention of HIV/AIDS spread on territory of Azerbaijan Republic, was approved by the Decree of the Cabinet of Ministers of  Azerbaijan Republic number 210s on October 20, 1997.

National Strategic Plan (NSP) on prevention of HIV/AIDS in Azerbaijan was approved on September, 25 2002 by the Cabinet of Ministers decree no 205s. P. 4.

The proposal of the Republic of Azerbaijan to the GFATM. 2004, p. 20

HIV and AIDS in the Caucasus Region: A Socio-Cultural Approach. UNESCO, 2005, p.62.

Smolskaya T. HIV sentinel surveillance in high-risk groups in Azerbaijan, the Republic of Moldova and the Russian Federation. EURO WHO, 2004.

www.undp.org.

UNDP Country Programme for the Republic of Azerbaijan (2005-2009). Baku, 2004, p. 2, 6.

During the elaboration of a new  National Programme on prevention and control of HIV and STI for 2007-2011 in the Republic of Azerbaijan civil society institutions participated neither in development nor in discussion of the document in 2006.

Smolskaya T. HIV sentinel surveillance in high-risk groups in Azerbaijan, the Republic of Moldova and the Russian Federation. EURO WHO, 2004.