Republic of Senegal

One people-One Goal-One faith

Mid-term Evaluation of the PRGTE

(From 24 November to 20 December 2018)

Project ID: 00094237

PIMS: 4964

Final Report

(03 April 2019)

Authors:

Pierre Kamtchouing M.S. (International Consultant);

Nathalie Manga Badji (National Consultant).

NNNNN

This report was commissioned by UNDP’s Country Office in Senegal. Comments in this report are solely the opinions of the evaluators

Summary/Table of contents

List of acronyms	3

1. EXECUTIVE SUMMARY	4

1.1. Table of information relatiing to the project	4

Tableau 1 : Project information	4

1.2. Project Description	5

1.3.Summary of the progress of the project	5

1.4. Mid-term Evaluation and Performance Summary Table	6

1.5. Conclusions	6

1.6. Recommendations	8

2. INTRODUCTION	9

2.1. Purpose and objectives of the mid-term review	9

2.2.Scope of the mid-term evaluation	9

2.3. Methodology	10

2.4. Structure of the mid-term review report	12

3. Project Description and Context	13

3.1. Context	13

3.2. Problems that the project seeks to solve	14

3.3. Project Description and Strategy	15

3.4 Agreements relating to the implementation of the Project	16

3.5 Project chedule and milestones	16

3.6. Main Stakeholders	16

4. RESULTS	17

4.1. Project Strategy	17

4.2. Progress towards results achievement	23

4.3. Project Implementation and reactive management	33

4.4.  Sustainanbility	38

5.	CONCLUSIONS AND RECOMMENDATIONS	41

5.1. Conclusions	42

5.2. Recommendations	46

6. ANNEXES	50

Annex 6.1 : Terms of Reference for the mid-term review	50

Annex 6.2 : Evaluation matrix for the mid-term review	59

Annex 6.3 : Sample interview questionnaire or guide for data collection	69

Annex 6.4 : Mission Itinerairy for the mid-term review	75

Annex 6.5 : List of interviewees	77

Annex 6.6 : List of Documents Reviewed	82

Annex 6.7 : Mid-term results of the project	84

Annex 6.8 : Signed GENU Code of conduct Form	86

Annex 6.9 : Signed Mid-term Final Report Approval Form	91

* The photos on the cover of this report refer to the subsequent activities conducted during the data collection mission in the communes of Léona, Mboro, and Niamone (November 28 to December 04, 2018).

List of acronyms

| ACC | Adaptation to climate change |
| --- | --- |
| ACMAD | African Center for Meteorological Applications for Development |
| AGR | Income generating activities |
| AGRHYMET | Regional Center of agro-hydro-meteorology |
| AMAT | Monitoring and evaluation tool for adaptive capacity |
| ANA | National Aquaculture Agency |
| ANACIM | National Civil Aviation and Meteorology Agency |
| ANCAR | National Agricultural and Rural Advice Agency |
| ANSD | National Statistics and Demography Agency |
| CADL | Local Development Support Centers |
| UNFCCC | United Nations Framework Convention on Climate Change |
| CILSS | Interstate Standing Committee for Drought Control in the Sahel |
| UNCCD | United Nations Convention to Combat Desertification |
| COMNACC | National Committee on Climate Change |
| COMRECC | Regional Committee on Climate Change |
| CRS | Regional Monitoring Committee |
| CSE | Ecological Monitoring Center |
| DAMCP | Directorate of community-managed marine protected areas |
| DEFCCS | Directorate of Waters, Forests, Hunting and Soil Conservation |
| DGPRE | Directorate of Water Resources Management and Planning |
| DP | Directorate of Planning |
| DRDR | Regional Directorate for Rural Development |
| GEF | Global Environment Facility |
| FLDC | Fund for Least Developed Countries |
| GPF | Women's advancement groups |
| GTP | Multidisciplinary working group |
| HACT | Harmonized Approach to Cash Transfer/Approche Harmonisée sur les Transferts de Fonds |
| IREF | Water and Forestry Regional Inspectorate |
| MEDD | Ministry of the Environment and Sustainable Development |
| MEFP | Ministry of Economy, Finance and Planning |
| NEX (NIM) | "National Execution" Modality |
| NGO | Non-governmental organization |
| PADEC | Support Program to Casamance Economic Development |
| PADEN | Program for the management and Economic Development of the Niayes area |
| NAPA | National Action Plan for Adaptation |
| PERACOD | Program for the promotion of renewable energies, rural electrification and sustainable supply in domestic fuels |
| UNDP | United Nations Development Program |
| PRGTE | Strengthening the management of the lands and ecosystems of the Niayes and Casamance in a context of climate change |
| PTA | Annual Action Plan |
| URAC | Union of Associative and Community Radios |
| CDH | Horticulture Development Center |

1. EXECUTIVE SUMMARY

1.1. Table of information relating to the project

Table 1: Project Information

| Project Title | Strengthening the Management of the Niayes and Casamance Lands and Ecosystems in a Context of Climate Change - Republic of Senegal (PRGTE) |
| --- | --- |
| GEF project Number | 5566 |
| UNDP GEF PIMS | 4964 |
| Country | Senegal |
| Region | Africa |
| Focus Area | Climate Change Adaptation |
| Investment fund | PMA |
| Strategic objective of GEF focus area | - CCA-1 Objective: reduce vulnerability to adverse effects of climate change, including variability, at local, national, regional and global levels - CCA-2 Objective - Strengthening Adaptation Capacity to cope with climate change impacts, including variability, at local, national, regional and global levels |
| FIP approval date | 2014 |
| Date of approval of the Chief Executive Officer | February 2015 |
| Date of PRODOC signature | October 26, 2015 |
| Launch workshop | November 28, 2016 |
| Expected closure date | November 2020 |
| Government Coordinating Agency | Ministry of Economy, Finance and Planning |
| Government Cooperation Agency | Ministry of Environment and Sustainable Development |
| Executing Agency | UNDP |
| Implementing partner | DEFCCS |
| Project budget : |  |
| GEF Grant | 4 100 000 USD |
| UNDP Senegal | 500 000 USD |
| Government | 800 000 USD |
| Government (in kind) | 200 000 USD |
| Co-financing |  |
| ANACIM | 3 500 000 USD |
| UNDP Senegal | 2 000 000 USD |
| Government | 7 000 000 USD |
| Total | 18 100 000 USD |

1.2. Project Description

- The PRGTE, which is among the priorities of the NAPA of the Republic of Senegal, was designed to create the necessary conditions for the implementation of adaptive measures to cope with climate change, articulated around the management of ecosystems in the Niayes and Casamance through three effects: (i) implementation of information management systems to identify and monitor the effects of climate change on ecosystems for effective forecasting, readiness and decision-making ;

- Reducing climate change risks by adopting ecosystem management-based adaptation options in the two targeted areas (the Niayes and Casamance), including the adoption of resilient land and ecosystem management practices in a context of climate change and

- Building individual, family, and community capacity to better spread awareness of climate change responses and provide strong support for adaptation efforts.

Through these adaptive measures, this project would enable beneficiary local communities to adopt practices and systems that can help them cope with climate change and variability.

1.3. Summary of the progress of the project

Status of the project’s progress by activity component for the various components of the PRGTE

- Component 1   : 77.7% of activities planned in the project document (7 out of 9 planned activities, of which 3 are performed at 100% or more).

- Component 2   : 100% of activities planned in the project document (10 out of 10 planned activities, of which 5 are performed at 100% or more).

- Component 3   : 100.0% of activities planned in the project document (7 out of 7 planned activities, of which 1 is performed at more than 100%).

Status of the project’s progress in relation to the consumption of the budget by component

Overall, the progress of budget consumption by the PRGTE is 66.1% compared to the mid-term budget estimates and 40.2% compared to the overall budget estimates of the project. That is:

- Component 1   : 33.6% compared to the mid-term budget estimates and 21.1% of the overall project budget estimates for this component.

- Component 2   : 91.6% compared to the mid-term budget estimates and 54.5% of the overall project budget estimates for this component.

- Component 3   68.1% compared to the mid-term budget estimates and 40.2% of the overall project budget estimates for this component.

Status of the project’s progress in relation to the achievement of targets

The rate of achievement of the project’s various targets is shown in the table below:

Table 2. Project target achievement rate

| Target1: At least 3,500 people in the regions of Dakar, Louga, Thiès, Ziguinchor, Sedhiou and Kolda (including 50% women) covered by risk management measures such as resilient land and ecosystem management practices. | Target 2 : At least 3,000 people (including 50% women) will have access to appropriate climate information through the sharing platform set up to ensure continuous monitoring of the weather / climate, hydrological and agricultural situation for the purpose to alert communities in time. |  | Target 3 : 100 ha of mangrove restored to reduce storm impacts and coastal erosion, 110 ha of hedges planted in Niayes vegetable gardens to protect the production from wind erosion and prevent the encroachment of sand dunes on arable land, 100 ha of reforestation in Soukou Valley to protect the watershed from erosion | Target 4 : At least 30 community groups (about 1,500 people, including 80% women) in Casamance undertake agro-forestry and agro-pastoral activities, as well as sustainable water management practices in rice paddies | Target 5 : At least 200 local technical staff, 1,000 people from community-based organizations (CBOs) of which 50% are women, and 100 teachers were provided relevant climate risk knowledge to better respond to climate change and provide effective support for adaptation efforts. |
| --- | --- | --- | --- | --- | --- |
| 106.1% including 28% women. |  | 156, 3% including 42% women. | 133% for the restoration of the mangrove, 203.3% for the reforestation of hedgerows and 253% for the reforestation of Soukou valley. | 17% | 70% for staff awareness and 8% for members of community-based organizations. |

1.4. Mid-term Evaluation and Performance Summary Table

The table below shows the performance of the project   :

Table 3: Summary of the project’s performance

| Assessment of progress towards the achievement of results |  |  |
| --- | --- | --- |
| Objective 1 | Satisfactory enough | Out of 9 activities planned, 3 were carried out at 100%, 3 at 50%, 1 at 75% and 2 were not carried out. Significant deficiencies to be corrected with respect to : - dissemination of weather information in rural areas ; - identifying adaptation options for local communities and ecosystem resilience ; - creating a network between the sharing system mentioned in the above project activity and other information systems on food security and the environment, etc. |
| Objective 2 | Satisfactory | Out of 10 activities planned, 6 were carried out at 100% or more, 1 at 75% and 3 at less than 50%, Minor deficiencies to be corrected with respect to: - support for the establishment of a micro-irrigation system ; - support for the conduct of IGAs. |
| Objective 3 | Satisfactory enough | Out of 5 planned activities, 1 was carried out at 100% or more, 2 at more than 60% and 3 at less than 3%. Significant deficiencies to be corrected with respect to : - training communities in the use of climate information and the use of technologies ; - training on climate risk management and the use of the results of risk and vulnerability assessments ; - producing textbooks on climate risk management and providing training for teachers and other school staff |
| Evaluation of the project’s implementation and adaptive management |  |  |
|  | Satisfactory | For a mid-term review, the implementation of most of the three components has enabled the effective and efficient implementation of the PRGTE and adaptive management, with the exception of few component 1 and 2 activities that are being remediated. |
| Evaluation of sustainability |  |  |
|  | Fairly likely | Moderate risks; The achievements should be maintained, given the progress towards the results of the achievements observed during the mid-term review. |

1.5. Conclusions

Project Strategy

Apart from water management, the Project fully addressed most of the issues related to strengthening the management of the Niayes and Casamance lands and ecosystems in a context of climate change, as identified in the NAPA and other situational analyzes. In addition, the project’s objectives have been adapted as much as possible to the national needs and priorities expressed by the Senegalese government in this regard. The people involved in the decision-making process were taken into consideration in the design of the project at several levels. It is also the same for gender with the principles of inclusiveness and the participation of women and youth, who have come up against the weight of custom and customs during implementation. However, if the project targets were achievable, attainable and defined over time, this was not the case with specificity and measurability that were often difficult to pin down. In addition, with 106.1% of target 1 achieved, 188.3% of target 2 achieved and 200.46% of target 5 achieved in November 2018, the size of some targets seems to have been underestimated.

Progress towards achieving results

The collaboration of the project with various actors contributed to implementing a response adapted to the context and the theme dealt with, but this effort was hampered by difficulties related to coordination and monitoring. Overall, implementation rates for the mid-term activities were above 100% for all the project components. Despite that, several positive effects have been noted during the implementation of the PRGTE, the most important of which are the strong mobilization, participation and involvement of communities in the project activities, as well as synergistic actions with FAO within the framework of the project "High End Climate Impact and eXtreme" which has enabled the empowerment of 37 community radio agents of the URAC network.

Project implementation and adaptive management

Overall, the funds were adequate at mid-term to meet the implementation needs of components 1 and 3. However, the funds were not released according to the timeline with respect to the majority of the implementing partners, which delayed the implementation of field activities, resulting in the demobilization and demotivation of the staff concerned.

Human resources management has been fairly efficient in terms of minimized management costs thanks to the strong involvement of the staff of the public service structures. This has not been the case for communication actions, which have been marked by several shortcomings, both in terms of the pedagogical approach used in training and the near absence of appropriate awareness and training tools. The same is true of the project's website, which has no information on the knowledge generated by the project as part of its implementation.

Sustainability

Overall, the risks identified in the Project Document, the Annual Project Review/PIR, and the ATLAS Risk Management Module, including organizational or strategic, have proven to be the most important and the most appropriate assessment of these risks. On the other hand, political will and gender-related social conflicts, were expressed only very weakly during the implementation of the first phase of the project. In addition, implementing partners and beneficiary communities are already integrating the PRGTE’s equipment, tools and other achievements into their production system, which reduces the risk of lack of funding after the end of the project. However, given their limited financial capacity, communities may not be able to ensure the sustainability of this equipment after the project ends. Conflicts between farmers and pastoralists, the return of pests in restored forests and the high mobility of the staff of the Directorate of Water, Forests, Hunting and Soil Conservation (DEFCCS) are the most likely external risks that have been identified during the implementation of the PRGTE and out of the control of this project.

1.6. Recommendations

Project strategy

Recommendation 1   : Ensure the implementation of the recommendations of baseline studies at the request of local authorities for water management so that the needs of beneficiaries in all the areas where the project is implemented (Niayes and Casamance) be taken account for the provision of small irrigation technologies.

Addressees of the recommendation: PRGTE, DEFCCS, DRDR, UNDP.

Recommendation #2 : Strengthen the adaptation of the PRGTE to the cultural, economic and environmental context of beneficiaries at the local level, in order to encourage the involvement and participation of everyone, including men, women and the youth people in the various activities of this project,

Addressees of the recommendation: PCU, UNDP and DEFCCS

Recommendation # 3   : Review the specificity and measurability of the project various targets so that they are fully SMART and define additional means for coordination and monitoring, so that the Project Coordination Unit (PCU) can carry out a monitor closely the  implementation of the project in the field.

Addressees of the recommendation: UNDP, DEFCCS and other partners

Progress towards achieving results

Recommendation # 4: Ensure that the capacities of ANACIM staff in the various implementation regions, as well as those of all implementing partners, are strengthened in the production and dissemination of meteorological information.

Addressees of the recommendation   : PCU, UNDP, DEFCCS.

Project implementation and adaptive management

Recommendation # 6: Ensure the implementation of a cash management forecasting system in the in the rest of the project and ensure that consistency is established between the project's financing needs, the schedule of the project activities and the deadlines for the release of funds.

Addressees of the recommendation: PRGTE, UNDP.

Recommendation # 7: Strengthen the project coordination and monitoring by recruiting two additional national UNV to cover the regions of Louga and Thiès.

Addressees of the recommendation: PRGTE, UNDP.

Recommendation # 8: Operationalize the project's communication strategy by adopting an approach that includes both institutional visibility and development (behavior change) objectives and that communication for development promotes participation and social and political change.

Addressees of the recommendation: PRGTE, UNDP.

Sustainability

Recommendation # 09: Next, explore and take advantage of opportunities for individual members of beneficiary communities to contribute to funding the PRGTE activities through a co-funding process.

Addressees of the recommendation: PRGTE, UNDP.

Recommendation # 10: Increase the search for partnerships with microfinance stakeholders to support the IGAs set up as part of the project activities to ensure their profitability.

Recipients of the recommendation: PRGTE, UNDP.

2. INTRODUCTION

A team of evaluators was recruited in November 2018 to conduct the mid-term evaluation of the project "Strengthening Land and Ecosystem Management in the Niayes and Casamance in a context of climate change (PRGTE)". This 5-year project (2016-2021), which began implementation in February 2016, is funded by the GEF/LDCF, UNDP and the Government of Senegal for USD18,000,000 (USD 5,600,000 grant and USD 12,500,000 co-financing), and has three components, including:

- Implementation of information management systems to identify and monitor the effects of climate change on ecosystems for effective forecasting, preparation and decision-making ;

- Reducing climate change risks by adopting ecosystem management-based adaptation options in the two targeted areas (Niayes and Casamance), including adoption of resilient land and ecosystem management practices in a context of  climate change;

- Individual, family and community capacity-building to make the responses to climate change better known and provide a significant support for adaptation efforts.

2.1. Purpose and objectives of the mid-term review

The mid-term review of the PRGTE will identify and measure the first signs of success or failure. The recommendations that will be made at the end of this mid-term evaluation should first be used as a basis for defining the changes that need to be made to put the project back on track to achieving the expected results. This mid-term evaluation also aims at questioning the project strategy and risks regarding its sustainability, in order to consider the appropriate mitigation elements.

2.2. Scope of the mid-term evaluation

In line with the learning and accountability objectives of the evaluation, data collection and analysis focused on the program’s three areas of intervention, particularly: 1) implementation of information management systems to identify and monitor the effects of climate change on ecosystems, for effective forecasting, preparation and decision-making;  2) reducing climate change risks by adopting ecosystem management adaptation options in both target areas (Niayes and Casamance), including the adoption of resilient land and ecosystem management practices in a context of climate change; 3) individual, family and community capacity-building to make the responses to climate change better known and provide a significant support for adaptation efforts.

More specifically, while the document review of the evaluation made it possible to estimate the state of implementation in all the sites of the project, the field data collection work was conducted in four main regions (Louga, Thiès, Ziguinchor and Kolda). In the selection of the sites, the evaluation team with the support of the project coordination unit, ensured that the perspectives of all the target groups of the project in different contexts are adequately taken into account.

2.3. Methodology

Following a participatory and consultative approach ensuring close collaboration between all actors involved, this mid-term review has been conducted through a dual approach. On the one hand, it focused on obtaining the necessary information, provided by the different actors involved in the management of the PRGTE at different level. In particular the PRGTE coordination unit, government actors, UNDP Country Office, UNDP-GEF Regional Technical Advisors, and other stakeholders.

On the other hand, this evaluation, conducted according to the UNDP evaluation standards, facilitated the participation of a sample of project beneficiaries (local authorities, farmers ‘organizations, women's organizations, other communities involved in reforestation and bushfire fighting activities, etc.). This approach known as "management-oriented evaluation approach", was based on an analysis of the following 4 factors: Context, Inputs, Products and Processes.

Based on an adapted version of the bottlenecks analysis approach, this evaluation attempted to take stock of the progress made and analyze the results achieved by the PRGTE on the basis of indicators initially defined. It highlighted the strengths and weaknesses of the corresponding interventions, the constraints encountered during the implementation, as well as the challenges and opportunities that will have to be taken into account in order to sustain the project results or define new directions for further implementation; while using existing mechanisms. For this purpose, this mid-term evaluation was based on the sharing of experiences of actors in the field (government staff, local authorities, farmers' organizations, women's organizations, etc.) who are supposed to benefit from the project. The implementation of this evaluative study was based on the use of a combination of quantitative and qualitative methods whose specificities were taken into account throughout the process, from the development of the conceptual framework to data collection and analysis, as well as the dissemination of results, and gender considerations that were incorporated into the research and analysis of each component of the study. The evaluation team therefore conducted a document review conducted during the first phase of this mandate and guided by the guidelines of the two approaches to this evaluation. This review contributed to the identification of issues that have helped to better address the concerns raised by the sponsor. To respond in a credible and rigorous manner to each of the evaluation questions (see Evaluation Matrix, Annex 6.2), and in the interest of triangulation, several methods were used in the collection of data, including:

- individual interviews with all actors involved in the implementation of the project: beneficiaries (administration, local authorities, community organizations, Women’s Advancement Groups (GPF), etc.), technical and financial partners (UNDP, GEF/LDC, DEFCCS, ANACIM, ANA, DRDR, ACAR, etc.), project staff and other partners;

- focus groups with the beneficiaries ;

- direct observations (structured) regarding physical media for the services performed.

. The evaluation team also conducted a qualitative data analysis in a second step, using the qualitative data analysis software (MAXQDA) while quantitative data (especially quantitative data sources) was done with SPSS and/or Excel software.

Sampling strategy

The sampling strategy consisted in identifying a four-step sample:

First Step: After using the list of all the localities where the Project activities are implemented, the evaluators grouped them into two clusters. In this particular case, each of the two clusters had to correspond to an area of implementation: the eco-geographical area of Niayes for the first cluster and that of Casamance for the second cluster.

Second step: Under the guidance of the coordination unit of the PRGTE (UCP), the localities selected in the first cluster correspond to the regions of Louga and Thiès, whereas, those selected in the second cluster, correspond to the regions of Ziguinchor and Kolda. In each region selected, sub-clusters corresponding to the communes of implementation characterized by a high concentration of activities related to several project components and which have not been monitored or evaluated in the fairly recent past have been selected. In particular, the communes of Léona and Kab Gaye (Louga), Mboro (Thiès), Nianone and Coubalan (Ziguinchor) and finally Saré Bidji and Dioulacolon (Saré Oumar).

Such a "clustering" process ensured a certain geographical proximity between the sites included in the sample and, consequently, reduced the costs as well as the time of transport between the intervention sites in question.

Third step: In each sub-cluster selected and under the guidance of the evaluation steering committee (and depending on the areas of activity target by the project), the mid-term evaluation team of the PRGTE selected a number of communities in which the evaluation field phase took place.

Fourth stage: In each of the communities identified in the third phase, the evaluation team selected a purposive sampling of those who participated in the focus groups. Following the same logic, the evaluators identified a certain number of achievements of the project which were either very efficient or very inefficient (“A case sampling") with the UCP, as well as on the basis of the document review, which have been specifically observed.

Limits

Data collection was limited by a number of factors that the evaluator attempted to address as much as possible during the mission (Table 4).

Table 4: Reactivity of the mission to the challenges encountered

| CHALLENGES | STRATEGIES OF MITIGATION |
| --- | --- |
| - limited accessibility to some regions targeted by the project (mainly due to distance or the time it takes to get there) | The evaluation team conducted, on the one hand, face-to-face interviews with service providers (consultants or UNVs having worked) in these regions. On the other hand, telephone interviews with mayors of communes, circles of these regions. At the same time, the evaluation team made an effort to identify and make use as much as possible of secondary data regarding activities in the regions in question. |
| - Lack of availability of key informants in the regions of implementation. | The evaluation team engaged in follow-up work by phone and Skype with project partners who could not be reached at the time of the field mission. |

Ethical considerations

This evaluation, which was not approved by an ethics committee due to the low level of risk estimated for the subjects interviewed, was guided by the greatest compliance with ethical principles and standards in the evaluation. All the subjects who participated in this evaluation were invited to give their verbal consent before taking part in the individual interviews as well as the focus groups in the communes, which were held ​​preferably in local languages. In addition, the evaluation team explained to all participants the reason of the evaluation and how its results would be used before starting each data collection activity. Next, interviewees’ confidentiality was also ensured at all time and all communications via e-mail and telephone, as well as all interview texts, images and videos have not been accessible to third parties. Finally, the evaluator has followed the recently revised evaluation standards of the United Nations Evaluation Group (UNEG), as well as the ethical standards currently used by UNDP, International Development Evaluation Association (IDEAS), American Evaluation Association  (AEA), AfrEA ( African Evaluation Association) with use of some of AGDEN’s methodology (Network of African Gender and Development Evaluators ).

2.4. Structure of the mid-term review report

To help better understand this mid-term evaluation work, we have structured this contribution in three parts.

The first part, which focuses on the description of the project, presents its context, then the problems that the project seeks to address, the description of its strategy, the agreements related to its implementation, timetable and milestones, and finally the key stakeholders involved in its implementation.

The second part presents the results of the evaluation based on the analysis of the following four criteria: the relevance of the strategy adopted by the project, effectiveness with which the mid-term results were achieved, efficiency, sustainability, particularly the establishment of tools and mechanisms that can ensure the sustainability of interventions.

Finally, the report suggests recommendations that implementing partners could adopt in further implementation of this project and for its full success.

| Association of forestry with agriculture in the context of reforestation: Egg planting in the region of Thiès (November 30, 2018) | Block dyke of stone in the region of Kolda (04 December 2018) |
| --- | --- |

3. Project description and context

Figure 1. Areas targeted by the Project

3.1. Context

Land degradation is both the cause and the consequence of climate change. These two phenomena interact because intensification of production increases emissions while land and ecosystem degradation through vegetation significantly reduces carbon sequestration (carbon sinks). Today, it is established that the increase in carbon content in the atmosphere is fueling a vicious circle in which land degradation leads to biodiversity loss and hence climate change. However, it is possible to turn this destructive spiral into a virtuous circle by reinforcing the positive elements of this interaction through emission management measures, on the one hand and climate change adaptation initiatives, on the other hand. The adoption and dissemination of sustainable land and ecosystem management practices would have significant positive impacts in terms of climate stability as well as for farmers, consumers and the environment.

This observation has been made by the international community which, through the United Nations, has set itself the goal under the Sustainable Development Goals (SDGs), in particular SDG 15, of preserving and restoring terrestrial ecosystems, by ensuring their sustainable use, sustainably managing forests, combating desertification, halting and reversing land degradation and stopping biodiversity loss by 2030.

In response to this concern, the Global Environment Facility (GEF), whose vision is to be a champion of the global environment, by supporting transformational changes and having a large-scale impact, has decided to collaborate with Member States to promote and fulfill this ambition. This is how the GEF supports projects for environmental protection in member countries and particularly those eligible for the “Least Developed Countries (LDCs)” initiative through the Least Developed Countries Fund.

As a Least Developed Country (LDCs), Senegal has therefore been eligible for the Least Developed Countries fund (LDCs) managed by the GEF. In fact, according to the National Action Plan for Adaptation (NAPA) of Senegal, the country has experienced recurrent droughts that have ended up causing a significant alteration of the hydrological regime and plant cover. Moreover, there are also periodic floods. Particularly in the Niayes and Casamance areas, these changes are marked by climate variability which can be summarized as follows: decrease in rainfall (200-400 mm from north to south); high inter annual and intra-seasonal rainfall variability; increase in average breaks of 3 months; and a rise in temperatures.

The combination of the effects of climate change and human activities in the project areas, as in the rest of the country, is leading to significant degradation of ecosystems, which remain the only means of livelihood for poor people living in rural and urban areas and who represent the majority of the population. Serious threats due to the effects of climate change  weigh on production from the eco-geographical areas in  the Niayes and Casamance, including water shortage, land degradation, salinization, siltation of valleys linked to soil erosion in mountainous regions, and degradation of the most productive and sensitive habitats such as mangroves and coastal areas. In conclusion, it should be noted that almost all social, economic and environmental aspects in the two areas targeted by the project are already deeply affected by the visible negative impacts of climate change. It also clearly appears that these impacts will worsen in the short term.

To help the Republic of Senegal in this perspective, the Global Environment Facility (GEF) and the United Nations Development Program (UNDP) assisted the Government in formulating the project "Strengthening Land and Water Management ecosystems in the Niayes and Casamance in a context of climate change (PRGTE)" which is part of the National Action Plan for Adaptation (NAPA) of Senegal.

With an initial duration of five years (June 2015-June 2020), this project aims to develop an enabling environment for adaptation measures based on ecosystem management in the eco-geographical areas of the Niayes and Casamance. It is formulated on the basis of three components and three effects that focus on the establishment of alternative solutions that would promote the adoption by local communities of practices and systems that can help them cope with climate change and variability. In fact, the combination of climate change effects and human activities in the project areas, and in the rest of the country, is leading to significant degradation of ecosystems, which remain the only livelihood of poor people living in rural areas, and who represent the majority of the population. Serious threats to production that are already visible in the eco-geographical areas of the Niayes and Casamance weigh on the populations of these regions. These are already affected by the visible negative impacts of climate change.

As the project arrived at mid-term and in accordance with the project document, this evaluation has been initiated to ponder over the performance, methods and dynamics of this initiative in order to deliver evidence relevant for the achievement of the objectives assigned to the project at this stage of its implementation and the capitalization of achievements as a result of the implementation.

3.2. Problems that the project seeks to resolve

In its social, economic and environmental dimensions in the two areas of implementation, the PRGTE actions aim to address adaptation to the impacts of climate change that are visible in those localities, and whose populations are already experiencing the consequences on a daily basis. In fact, the degradation of vegetation strips annihilates its protective functions (sand dune fixation, protection of vegetable farms, houses, etc.) and production (firewood, lumber, seeds, etc.). On another side, rainfall decrease and temperature increase, on the one hand, lead to groundwater salinization and degradation, more particularly in the areas covered by sand dunes, thus generating a lowering of ground water, and the other hand, lead to the early depletion of surface water caused by strong evaporation. The same goes for mangrove destruction of which leads to the disappearance of the buffer area between the Atlantic Ocean and the interior of the Casamance River, thus causing an acceleration of coastal erosion, the rise of saline water towards the mainland and the decline in protection against the effects of wind, waves and currents. This increasing salinization has consequences for both fauna and flora. For example, the increasing salinization of rice fields has forced many women to abandon their fields. One of the major consequences of rice paddies becoming unproductive due to excessive salinity is the withdrawal of the populations to the plateau whose massive deforestation exposes the land to uncontrolled logging and bush fires. This deforestation in turn leads to soil and water erosion which causes the silting up of rice paddies, thus causing reduction of rice-cropping surfaces. Due to greater erosion in the areas of implementation and low yields of rain-fed crops, the economic sectors most sensitive and most affected by climate change and therefore requiring adaptation measures are rice growing, mangrove forest, and the high plateaux.

3.3. Project description and strategy

The PRGTE is part of the National Strategy for Economic and Social Development (SNDES) (2013-2017) established for Senegal, “Senegal Emergent Plan” (PSE) which is anchored in the vision of an emerging Senegal by 2035, No 2 General Objective of the Environmental and Natural Resources Sector Policy Letter (LPSERN), the Multi-annual Expense Programme Document (DPPD) (2013-2015) of the Ministry of Environment and Sustainable Development (MEDD), as well as the implementation of the Agro-Sylvo–Pastoral Law (LOASP). It is in line with the National Adaptation Program of Senegal (NAPA), including its four priorities i.e. coastal protection, agroforestry and water resources, awareness and education, and is working in the Niayes and Casamance regions to protect the dunes, mangrove restoration and water management (component 2). In addition, the project provides relevant climate information to help technical services and communities better plan and manage climate risks (component 1). As well as individual, family and community empowerment to raise awareness of climate change responses and provide strong support for adaptation efforts.

This project complies with the criteria of the LDC Fund, including:

- aligning behind the participatory approach initiated by a country (this project has developed through a participatory process involving key stakeholders and direct beneficiaries.);

- supporting the practice-based approach (this project provides local communities with the opportunity to develop agro-forestry-pastoral practices and systems that are integrated and resilient to climate change and variability, that will improve horticulture and rice production, strengthen the protection and production function of the casuarinas band and ensure sound management of water resources, forests and mangroves, to the benefit of  local communities);

- promoting gender equality (during the project development phase, efforts were made to involve women's groups and youth in the focus groups, as well as civil society and institutional leaders) ;

- implementing a complementary approach (this completed project complements other programs and projects that are implemented in the intervention area with different priorities and objectives).

This project was designed according to the GEF's general requirements for development and operationalization, including:

- promoting the sustainability (the project was designed to have a sustainable impact at both community and national levels) ;

- implementing monitoring and evaluation (the project implementation strategy included a monitoring and evaluation plan) ;

- promoting reproducibility (the project is demonstrative, since it focuses on implementation of integrated interventions tailored to selected councils) ;

- involving stakeholders (the project facilitates coordination and participation of the different stakeholders, including those involved in environmental management and development planning).

Finally, this project supports national development goals and plans to achieve the Millennium Development Goals (MDGs) 1, 3 and 7 including, eradicating extreme poverty and hunger, promoting gender equality and women’s empowerment, and ensuring sustainable environment, with management arrangement based on NEX procedures.

3.4 Agreements related to the implementation of the project

As a member of the Least Developed Countries (LDCs), Senegal is eligible for the Least Developed Countries Fund (LDCF), which is managed by the GEF. Senegal joined the UNFCCC after ratifying the Convention in December 1994. The country has also been a signatory to the Kyoto Protocol since 2001. In accordance with the requirements of the United Nations Framework Convention on Climate Change, Senegal designed its first national communication in 1997 and finalized its National Adaptation Action Plan (NAPA) in December 2006. These reports are prepared with the support of the National Committee on Climate Change (COMNACC) through a participatory approach involving a wide range of national stakeholders from all levels. The country also acts as interim Secretariat of the Environment Component of NEPAD.

3.5 Schedule and major stages of the project

The main stages of this project include the following:

- Starting date: June 2015 ;

- Effective start of activities: February 2016 ;

- Completion date: June 2020 ;

- CLEP meeting date: August 10, 2015

3.6. Main stakeholders

Several stakeholders contributed to the implementation of the PRGTE. The main ones are as follows:

- 14 national institutions involved in environmental monitoring and producing information on the climate participate in the implementation of the PRGTE as implementing partners. These include the five Inspections of Waters and Forests (IREF) of Louga, Thiès, Ziguinchor, Kolda and Sedhiou, two Regional Directorates for Rural Development (DRDR) of Ziguinchor and Sédhiou, National Civil Aviation and Meteorology Agency (ANACIM),  Ecological Monitoring Center (CSE), National Aquaculture Agency (ANA), National Forestry Research Center (CNRF/ISRA), Horticultural Development Center ( HRC/ISRA), Directorate of Water Resources Management and Planning (DGPRE) and the Childhood and Peace NGO. The same goes for the Directorate of community-managed marine protected areas (DAMCP), and the Union of Associative and Community Radios (URAC)

- Regional and local authorities, technical teams of Louga, Thiès, Ziguinchor, Kolda, Sedhiou and chiefs of the targeted villages ;

- Community-based organizations (women's and youth associations) living in the targeted rural areas, including the participation of potentially vulnerable groups such as women.

| Rice produced by women from a GPF in Kolda (04 December 2018). | Small agricultural equipment made available to Dioufana Seed Producers, Dioulacolon Commune (04 December 2018) |
| --- | --- |
| Rice thresher made available to a GPF from Kolda region (04 December 2018) | Automatic weather station in Thiès (01 December 2018) |

4. RESULTS

4.1. Project Strategy

Question 1: To what extent do the project activities as designed, allow to address issues related to land and ecosystem management in Senegal in a context of climate change and as identified in the country’s development strategies?

- The analysis of the content of the project documents "Strengthening the management of the lands and ecosystems of the Niayes and Casamance in a context of climate change", as well as direct field observations and interviews with the PRGTE’s staff and implementing partners indicate that the project document fully addresses issues of strengthening the management of Niayes and Casamance lands and ecosystems in a context of climate change identified in the NAPA (2006), situational analyzes, and research and consultation on the subject in five specific domains: dune fixation, reforestation, mangrove restoration, adapted varieties and awareness/information. In addition, the project addresses less effectively the issues of promoting water conservation techniques and weakly those of construction of protection works for vulnerable sites and watershed management, and has not address the issues of groundwater recharge and wastewater reclamation at all (Table 5).

Table 5: Links between the NAPA and the PRGTE

| Issues of land restoration and ecosystem management in a climate change context identified in the NAPA | Extent to which the Project addresses the issue |
| --- | --- |
| - Dunes fixation. | Fully |
| - Reforestation. | Fully |
| - Protection works for vulnerable sites. | Weakly |
| - Promotion of water saving techniques (drip, etc.). | Partially |
| - Awareness/information. | Fully |
| - Groundwater recharge by impluviums. | Not addressed at all |
| - Valorization of wastewater . | Not addressed at all |
| - Restoration of the mangrove. | Fully |
| - Adapted varieties. | Fully |
| - Watershed management. | Weakly |

Question 2: To what extent did the objectives of the project address the national needs and priorities expressed by the Senegalese government in its design?

- Before answering this question, it should be recalled that the PRGTE is one of the priorities of the Republic of Senegal's NAPA with the aim of strengthening the environment conducive to implementing appropriate adaptation measures revolving around the management of ecosystems in the Niayes and Casamance. To do this, the PRGTE acts on 3 relevant levers: information systems, adaptation alternatives and capacity building

- Moreover, it is implemented in the eco-geographical areas of the Niayes and Casamance. It covers five (05)  of the 14 Senegalese administrative regions and in two (02) of the six (06) Senegalese eco-geographical areas that are among the areas most affected by climate variability (such as the region of Thiès). It is therefore an essential component of land and ecosystem management in the context of climate change in these 2 eco-geographical areas. This being said, in general, the project objectives have been adapted as much as possible to the national needs and priorities expressed by the Senegalese government, as identified by the exploitation of the PRGTE documents, as well as the situational analyzes carried out during the project design, from its conception to the strategic level. In addition to the NAPA, which is the main benchmark for climate change, there are also the following documents:

- Senegal Emergent Plan (PSE) the public programming reference document for 2035, particularly in its strategic focus 2: Human Capital, Social Protection and Sustainable Development.

- Sector Policy Letters (Environment and Natural Resources) ; Agriculture, Fisheries and the Operational Plan for the Development of Aquaculture; hydraulic, among others).

- The PRGTE is also consistent with UNDP and GEF’s strategic architecture including a contribution to 2012-2018 UNDAF (Outcome 7) and forthcoming 2019 - 2023 UNDAF (Outcome 3), the Outputs 1 and 2 of the Country Program Action Plan (CPAP), as well as GEF’s Objectives 1 and 2.

- At the level of the institutions promoting climate change adaptation and mitigation, the PRGTE, anchored in the DEFCCS of the MEDD, is in partnership with the civil society and some technical structures, the most important of which include:

- The Ministry of Agriculture and Rural Equipment through its Regional Directorates of Rural Development (DRDR)   ;

- The national institutions involved in monitoring the environment and producing climate information (e.g. ANACIM, CSE, DEEC, DGPRE ANA, DEFCCS, DEEC   ? DAMCP etc.);

- Regional and local authorities, technical teams of Louga, Thiès, Ziguinchor, Kolda, Sedhiou and the chiefs of the targeted villages;

- Community-based organizations (women's and youth associations) living in the targeted rural areas, including the participation of potentially vulnerable groups such as women;

- The Senegalese Agricultural Research Institute through ISRA/CNRF and ISRA/CDH.

- The Civil society and NGOs supporting communities in their activities (e.g. Enfance et Paix of Sedhiou and SSOS environment of Kolda) ;

- And the Community Radio Union for mass communication and spots.

- These key partners of the PRGTE benefit at the regional level from the relevant operational dismemberments that have been able to carry out operational implementation in line with the NEX modality. With implementation at the operational level of regions, led by a PRGTE Monitoring Committee under the steering of the Regional Governor. However during the project implementation, several partners who had been selected in the project document and whose expertise was proven necessary for its implementation were not involved (example: AGRHYMET , ACMAD, etc.).

Question 3: To what extent has the theory of change and the approach used to implement the project been adapted to the local context?

- First, for the theory of change as well as the approach used to implement the project, document review, individual interviews and focus groups confirmed that for PRGTE it is focused on impact, that is, beneficiaries desired change for adopting adaptive measures to address climate change, through land restoration and ecosystem management through more sustainable exploitation and equitable management and distribution of all natural resources.

- That said, to have an impact on the generation of economic, social and environmental benefits, the PRGTE must make a difference by creating a favorable environment for the implementation of adaptation measures in the Niayes and Casamance areas. Pre-conditions to this environment were anticipated through the implementation of agro-hydraulic information management systems, demonstration in selected sites and communities and strengthening capacity for multiple stakeholders and levels. To do this, the project through its activities and processes had to materialize a package of products and services). As this change in the environment and CCA practices was to take place in a given context, it was important for the Project to monitor a certain number of risks that could make certain results possible by ensuring that assumptions (Cooperation and complementarity, GAR, etc.) necessary for the achievement of the results were made effective.

Question 4: To what extent have the views of those affected by the project decisions, those who could influence the results, and those who could contribute to the information or other resources for the process, have been considered during the project design?

- Document review, interviews with the project staff as well as implementing partners and beneficiaries showed that the people concerned by the decision making were taken into consideration during the project design and this at several levels. First, a multidisciplinary team consisting of a meteorologist, a forestry expert, and a socio-economist was recruited to design the PRGTE. Secondly, almost all public service structures involved in the project implementation as implementing partners were consulted during the design phase. Finally, a situational survey was conducted among beneficiaries in the five implementation regions. Thus, more than 5 meetings were held with beneficiaries, regional technical services and other key partners working in the target areas of the project.

Question 5: What steps have been taken in the design to ensure that the resources prove less costly compared to existing alternatives?

- One of the steps taken during the project design to ensure the efficiency of the activities financed by the project was that be followed the establishment of standardized procedures based on the financial procedures governing the national implementation measures (MNE) to reduce supplier costs.

Question 6:  To what extent the project targets at mid-term are "SMART" (specific, measurable, achievable, relevant and time-bound)?

- Before answering this question, it is necessary to recall that the PRGTE, whose implementation has a duration of 5 years (March 2016-March 2021), is involved in 3 major areas (dune protection, mangrove restoration and water management) and covers the agro-ecological areas of Niayes and Casamance.

- That being said, to ensure proper legibility of the PRGTE in terms of its objectives, to have a view of ​​its development, to become aware of its feasibility and finally to invest just the time and resources required, the design of this project has 4 targets to be reached at the end of its implementation.

- The analysis of the document content of the PRGTE    project   and direct field observations and interviews with the PCU staff and implementing partners indicate that   SMART criteria (specific, measurable, achievable, realistic and temporal) were taken into account in defining the targets with variable impact (Table 6). However :

- Target 1 is partially measurable as it does not allow a balanced distribution of beneficiaries across the implementation regions, leaving a blur in the concentration of project resources to achieve this result.

- Targets 2 and 5 do not specify the regions where these results will be achieved and also remain unclear on the distribution of beneficiaries in the various regions of implementation.

- Targets 3 and 4 do not specify the regions in which the achievements will be restored or the 30 community groups will be recruited, as well as the distribution of these results by region. Moreover, for target 4, it is difficult to measure in hectares the area of ​​hedges planted because this operation which concerns fences is generally done in lengthwise.

- Overall, the literature search showed that targets 1, 2 and 5 are easily attainable and achievable. Indeed, at project mid-term in November 2018, 106.1% of the target 1 including 28% of women and 99.3% of target 2 including 27.7% of women were reached, while Target 5 has been reached at 95% for staff awareness and 23.9% for community-based organizations. On the other hand, target 3 has been reached at 133% for the restoration of the mangrove, 203.3% for hedgerows reforestation and 253% for the reforestation of the Soukou valley. For Target 4, if 5 out of 30 targeted community groups (17%) were reached, it is difficult to say how many people were reached.

Table 6: Level of Assessment of SMART Criteria of the PRGTE’s targets

| Target for the end of the project | Criteria |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | S | M | A | R | T |
| - At least 3,500 people in Dakar, Louga, Thiès, Ziguinchor, Sédhiou and Kolda regions (including 50% of women) covered by risk management measures such as resilient land and ecosystem management practices (for example, mangrove restoration/reforestation, resilient agro-pastoral and agro-forestry activities and sustainable water management). |  |  |  |  |  |
| - At least 3,000 people (including 50% of women) will have access to appropriate climate information through the sharing platform established to ensure a continuous monitoring of the weather/climate and the hydrological and agricultural situation in order to alert communities in time. |  |  |  |  |  |
| 3. - 100 ha of mangrove restored to reduce the impacts of storms and coastal erosion; - 110 ha of hedges planted in the Niayes vegetable gardens to protect the production from wind erosion and prevent the encroachment of sand dunes on arable surfaces; - 100 ha of reforestation in the Soukou Valley to protect the watershed from erosion. |  |  |  |  |  |
| 4. At least 30 community groups (approximately 1,500, including 80% of women) in Casamance undertake agro-forestry and agro-pastoral activities, as well as sustainable water management practices in rice paddies. |  |  |  |  |  |
| 5. At least 200 local technical staff, 1,000 community-based organizations (CBOs) of which 50% are women, and 100 teachers have been provided relevant climate risk knowledge to better respond to climate change and provide effective support for adaptation efforts. |  |  |  |  |  |

Totally                                           Partially                                                                Weakly

Question 7: To what extent have relevant gender issues been raised during project design?

- At the planning stage, gender (including the principles of inclusion, participation and equity, especially for the most vulnerable and marginalized groups in the sites targeted by the project) have been taken into account as evidenced by the concern identified in the project document to retain gender-based indicators for measuring the various targets, including in Component 3, with more strategic economic empowerment measures for women (specifically in Component 2). The same is true for UNDP/GEF and implementing partners to promote respect for fundamental human rights of women and to reduce inequalities between women and men in the areas of implementation of the PRGTE.

- As far as community participation is concerned, the project has from its design clarified the localities covered by the project. Within these communes, a base of criteria around the provision by the participating communities, producers of the basic means of production necessary for the good conduct of activities (secured land, wells (for agriculture) human resources and commitment, etc.) was defined with a particular and measurable focus on  Women’s Advancement Groupings (GPF) participation.

- That being said, during the implementation, certain identifying conditions regarding beneficiaries (example: owning the plot of land to be exploited, owning a well, etc.) excluded women from certain activities of the project (example: peanut seed production in the region of Louga), this has in itself reduced the participation of women in the project’s activities.

Testimony of Fatou Diaw, President of the Federation of GPF NDJALEN, MAKA, YEGOUN BOYO. Not long ago, the fields were buried by sand and there was no water, people were leaving the area because they could not work because of silting but since the project has become operational, there is a clear improvement and this migration is greatly reduced. Young people also sometimes got up at night to draw water from the wells but with the advent of solar kits and drip technology, the situation has greatly changed, the youth are now going to draw water around 8 am. Villages need the project’s help to fight against silting and drip technology has shown that despite the difficult conditions, we can also do agriculture. Women came from kilometers to take part in the focus groups because they have expectations. Indeed, the project has helped clear a house in the village of NDJALEN, which was totally buried by dunes (sand). In addition, all the plants produced by the group were distributed, i.e. 6000 plants for each GPF. 4 producers benefited from a 16 panels solar kit in the village NDJALEN, which allowed to triple the arable land and consequently to increase production. Overall, there are 64 solar panels in the villages; yields are increasing because dunes are somewhat fixed, and the producers' income is increased, which reduces the need for funding. The project allowed the groups to get credit through a memorandum of understanding with the CAURI Microfinance Institution. However, women's hope must not be destroyed, so discrimination should be prevented.

4.2. Progress towards the achievement of results

Question 1: To what extent did the objectives set to the project allowed achieving results at mid-term within the deadlines set?

- In order to answer this first question, it should be recalled that the project aims to achieve key results (Table 7) around which activities have been planned and performed. In general at mid-term, the results of the second and third components were easier to pin down by the service implementing partners, the other consultants or the technical experts engaged in the implementation of the PRGTE project, as well as by the beneficiaries.

Table 7. The three intervention components of the project

| OBJECTIVES |  | DESCRIPTION |
| --- | --- | --- |
| OBJECTIVE 1 | An information platform on climate change and socio-environmental aspects to identify climate change-induced vulnerabilities and propose effective adaptation options in the Niayes and Casamance regions. |  |
| OBJECTIVE 2 | Reduce the risks of climate change in target lands and ecosystems with adaptive restoration measures. |  |
| OBJECTIVE 3 | Support mechanisms for acquiring knowledge and information. |  |

- As confirmed by the analysis of the implementation rate of all the project activities grouped by intervention component (establishment of an information platform on climate change and effective adaptation options, reducing the risks related to climate change in the target lands and ecosystems with adaptive restoration measures, and finally supporting for knowledge and information acquisition mechanisms) (Annexes 6.7 and 6.8), the targets set have been fully achieved at:

- 155.5% as compared with the mid-term forecasts for activities related to setting up a climate change information platform and effective adaptation options (3 out of 9 activities performed at 100%) and 77.7% against all activities to be implemented for this component (7 out of 9 planned activities) ;

- 179.3% as compared with the mid-term forecast for climate change risk reduction activities in the target lands and ecosystems with adaptive restoration measures (5 out of 10 were performed  at 100% or more)  and 100% against all the activities to be implemented for this component (10 out of 10 planned activities) ;

- 105.4% as compared with the mid-term forecast for activities to support knowledge and information acquisition mechanisms (1 out of 7 activities was performed at more than 100%) and 100.0% against all the activities to be implemented for this component (7 out of 7 planned activities).

- The good performance of the project was also confirmed by the triangulation of these achievement rates with :

- The results of the analysis of the financial reports produced by the PGRTE, which shows the results of the Project compared to the various financial envelopes released;

- The estimates of the performance level by the members of the PRGTE’s staff in Dakar and;

- The results presented in the monthly, quarterly and final reports of the different implementing agencies.

- However, it should be noted that one of the factors that prevented the implementation of activities in the field was the lack of specific deliverables for some activities, which made their verification by the team more complicated than expected (e.g. for activity 2.12.1, specification sheets were met only for market gardening routes and seeds multiplication, which has not been the case for agroforestry, reforestation, dune fixation, etc.).

Component 1: Setting up a of climate change information platform and effective adaptation options

- Among the most important contributions of the PRGTE in this area, direct field observations and individual interviews with the staff of this project in Dakar, as well as with implementing partners in the field, made it possible to achieve  among others the following results (Table 8):

- Acquisition and installation of hydrometeorological equipment (01 automatic static level recorder and physicochemical parameters, 03 hydrometric stations, automatic water level recorder and physicochemical parameters, differential GPS, etc.;

- The establishment of eight (8) multidisciplinary working groups (Thiès, Louga, Tivaouane, Kébémer, Bignona, Ziguinchor, Sédhiou, Kolda), as well as their running through GTP meetings and the production of agri-climate newsletters ;

- The establishment of innovation platforms in the regions of Louga and Thiès   ;

- Identification and awareness of inter-village committees and characterization of all the partners involved in the operation and management of basins

- Collection and dissemination of climate information to agricultural producers.

- Participatory evaluation of the impact of the sensitivity and exposure of the Niayes area to climate change and its impact.

| Dune fixation in the region of Thiès (30 November 2018). | Oyster farming supported by the project in the region of Ziguinchor (03 December). |
| --- | --- |

Table 8.  Achievement Rate for Component 1

| Activities | Achievement rate Nov. 2018 |
| --- | --- |
| Activity 1.1.1: Participatory identification of the needs of the potential users in terms of climate information and diagnosis of the climate network, meteorology, hydrology and hydrodynamic observations. | 75% |
| Activity 1.1.2: Acquisition and installation of hydro meteorological instruments | 100% |
| Activity 1.1.3: Training of technical staff (meteorological, hydrological, agricultural, etc.) and producers on data collection, processing and analysis. | 50% |
| Activity 1. 2. 1: Create a climate database (correlated with socio-economic and environmental data) and vulnerability assessment tools for climate change. | 50% |
| Activity 1.2.2: Analyze in a participatory way the sensitivity and exposure of the targeted ecosystems (Niayes, mangroves, Kalounayes forest, etc.) and the past and future livelihoods (in 2030, 2050 or 2100), then assess their impacts in a context of climate change. | 50% |
| Activity 1.2.3: Identify adaptation options for local communities and ecosystem resilience and analyze the costs and benefits of the various options. | 0% |
| Activity 1.3.1: Identify the sharing platforms that exist (e.g. GTP, Info Clim, Siena, etc.), and evaluate their effectiveness and sustainability and study models of collaboration. | 100% |
| Activity 1.3.2: Establish an operational and sustainable system for sharing information and assessments regarding vulnerability to climate change for the benefit of local actors (local authorities, technical services, producers and households). | 100% |
| Activity 1.3.3: Create a network between the sharing system mentioned in the above project activity and other well established food security and environmental information systems. | 0% |

Component 2: Reducing Risks related to Climate Change in Target Lands and Ecosystems with Adaptive Recovery Measures

- Among the most important contributions of the PRGTE in this area, direct observations in the field and individual interviews with the staff of this project in Dakar, as well as with implementing partners in the field, made it possible to achieve among others the following results (Table 9):

- The restoration of 142.7 ha of mangrove in the regions of Ziguinchor and Sédhiou, against 100 ha planned at mid-term ;

- The planting of 122.2 ha of windbreaks around individual market gardens to protect them from silting against 110 ha planned at mid-term ;

- The adoption of resilient agricultural technology solutions through the provision of drought-resistant varieties and adaptive agroforestry practices to producers.

Table 9. Achievement rate for Component 2

| Activity | Achievement rate Nov. 2018 |
| --- | --- |
| Activity 2.1.1: Regeneration/restoration of 100 ha of mangroves in Tobor (Ziguinchor) and Diendé (Sedhiou). | 142.7% |
| Activity 2.1.2: Developing and applying sustainable mangrove farming techniques in Ziguinchor and Sédhiou forest reserves to prevent their cutting and degradation. | 100% |
| Activity 2.2.1: Identify best adapted forest species and appropriate technologies for better protection of vegetable basins against silting as well as vegetable garden packages adapted to the biophysical context | 100% |
| Activity 2.2.2: Planting of 110 ha of windbreaks around individual vegetable garden basins to protect them from silting and the establishment of close protection of crop plots against the harmful effects of winds (the harmattan and the trade wind). | 122.2% |
| Activity 2.2.3: Establish 60 ha of micro-irrigation systems to save water in pilot vegetable gardens. | 33.3% |
| Activity 2.3.1: Reforest and apply natural regeneration techniques over 100 ha of the palm grove with adapted varieties, in order to strengthen natural stands, given the high erosion of these plant genetic resources caused by climate change and human pressure. | 90.1 % |
| Activity 2.3.2: Support at least 10 women's groupings in the conduct of income-generating activities (market gardening, poultry farming, small livestock farming, marketing of forest products, salt production, etc.). | 45% |
| Activity 2.3.3: Adoption of resilient agricultural technology solutions (drought-resistant varieties, agroforestry practices, etc.). | 130% |
| Activity 2.3.4. Restoration of 100 ha of community forests in the watersheds of the Soukou Valley (Rural Community of Saré Bidji in Kolda) to protect the banks of the watercourse against land erosion. | 75% |
| Activity 2.3.5: Combat bush fires in the forest of Kalounayes to support the effort of regenerating valuable forest species adapted to the biophysical context. | 166% compared to the areas covered |

Component 3: Support for knowledge and information acquisition mechanisms

- Among the most important contributions of the PRGTE in this area, direct observations in the field and individual interviews with the staff of this project in Dakar, as well as with implementing partners in the field, made it possible to achieve among others the following results (Table 10):

- Training of community advisers (60 members) from eight municipalities on the integration of risks and opportunities related to climate and adaptation options;

- Capitalization of the project’s achievements and experiences, as well as the design of relevant strategies and means of communication adapted to local communities.

Table 10. Achievement rate for Component 3

| Activity | Achievement rate Nov. 2018 |
| --- | --- |
| Activity 3.1.1: Train community advisers (60 members) from eight municipalities on the integration of the risks and opportunities related to climate change and on adaptation options. | 126.6% |
| Activity 3.1.2: Train 200 extension staff from ministries (responsible for water resources, agriculture, environment, livestock, etc.) on climate risk management and utilization the results of risk and vulnerability assessments, in order to make adjustments to policies and plans that govern land and ecosystem management. | 91% |
| Activity 3.1.3: Train members of 100 community organizations, including 50 women's organizations, in the use of climate information and technology adoption. | 03% |
| Activity 3.2.1: Capitalize on the project’s achievements and experiences and design relevant strategies and means of communication adapted to local communities. | 70% |
| Activity 3.2.2: Share the project’s experiences with communities through the organization of exchange visits or intra- or inter-community forums; information is broadcast on radio and television at the local, regional and national levels; and also through awareness and information sessions. | 60% |
| Activity 3.2.3 : which consisted in producing three textbooks to be multiplied by 1000 on climate risk management and providing training for teachers and other school staff to support the integration of CC into school curricula in order to promote a culture of resilience to climate change. | 25% |
| Activity 3.2.4: Make the project’s results measurable at regional and international meetings, but also through written reports and technical and scientific publications. | 50% |

Question 2: For the expected mid-term results, what are the factors within and outside the control of the MEDD and DEFCCS that contributed to their achievement?

- Through document review and individual interviews with the staff of the PRGTE and the implementing partners, and focus groups with the project’s beneficiaries, a number of factors internal (Table 10A) and external (Table 10 B) to the DEFCCS that contributed to the successful completion of the project was identified.

Table 11 A. List of Factors internal to the MEDD and DEFCCS that contributed to achieving the Project’s expected results at mid-term

Internal Factors to the MEDD and DEFCCS

- The presence of a steering committee made up of members with transversal expertise to assess the activities relevance and coherence, to review and approve technical and financial reports, annual action plans and beneficiary eligibility criteria

- The project problematic is part of the DEFCCS portfolio of sovereign activities

- Despite the delays observed during the project’s implementation, sometimes due to the late release of funds, the staff of the IREFs made a great effort to reach as many targets as possible from the beginning until the mid-term. Also the DEFCCS is contributing in kind to the financing of this project.

- The use of an implementation contract signed directly with the IREFs directly at the regional level has contributed to strengthening the ownership of the project by these public institutions.

- Technical support provided to IREFs in the field by UNVs in the regions of Ziguinchor and Kolda.

- The experience gained by the IREFs when implementing other projects in the same regions.

- The presence of a sustained collaboration between IREFs and DRDRs at the regional level

- Communications made by the IREFs to increase the visibility of the project, through the production of videos broadcast in the national media.

Table 11 B. List of Factors external to the MEDD and DEFCCS that contributed to achieving the Project’s expected results at mid-term

External factors to MEDD and DEFCCS

- Strengthening the political will of the Senegalese government.

- The existence of UNDP NEX procedures that have been adapted to the management of the project.

- The actual presence of partners in the field and the level of their experience already gained in most of the sites targeted by the project.

- Collaboration established by implementing partners with traditional leaders and local authorities in the sites targeted by the project.

- The participation of the MEDD which has the normative tools that will facilitate the sustainability of the activities (example: the multi-year expenditure planning document (DPPD) (2013-2015).

- Collaboration established by the project with the administrative and local authorities in the target regions.

- The presence within the project of the financial management tool (TOMPRO) which makes it possible to generate the expenditure made for the various periods.

Question 3: what are the factors within and outside the control of MEDD and DEFCCS that have prevented achieving the expected results at mid-term?

- Through document review and individual interviews with the staff of the PRGTE and the implementing partners, and focus groups with the project’s expected beneficiaries, a number of internal (Table 10A) and external (Table 10 B) factors to the DEFCCS that prevented the successful completion of the project was identified

Table 12 A. List of MEDD and DEFCCS internal factors that prevented achieving of the expected results

Internal Factors to the MEDD and DEFCCS

- The lack of a continuous sharing of information concerning field activities between the various implementing partners, despite the holding of the few annual meetings organized by regional monitoring committees.

- The low degree to which the other implementing partners were taken into consideration in making operational decisions, under the pretext that the PRGTE is first and foremost a DEFCCS’s project, and therefore operational decisions are left to IREFs.

- The lack of obligation for the project implementation partners to produce a capitalization report or a global analysis report of interventions carried out in the field did not allow a participatory diagnosis of the project implementation at mid-term by all implementing partners to identify the strengths and weaknesses. This has prevented the effective capitalization of the project's impacts and, consequently, a collective reflection on what worked well and what worked not too well in the first phase of project’s implementation.

- The lack of a capacity building strategy for the IREFs’ staff on the project’s participatory monitoring in the field, in relation to the impacts on beneficiaries socio-economic activities.

- The cumbersomeness of market procedures and the slowness observed in the processing of project’s files at the level of the MEDD Contracts Committee.

Tableau 12 B. List of MEDD and DEFCCS External Factors that prevented achieving results mid-term expected

External Factors to the MEDD and DEFCCS

- The distance between the project’s implementation areas and the Ministries and other implementing partners from where the majority of the technical and steering committee members come from.

- The difficult access to certain partners targeted by the project for the development of a sustainable collaboration in the technical and financial fields.

- The bungling concerning the role of implementing partner between the DEFCCS and UNDP that has not always arranged things.

- The presence of three financial control positions for the project in particular at the level of the PCU, the MEFP and UNDP, which has increased the procedures for releasing funds for the implementing partners.

- The late release of funds for the implementation of the project

Question 4: To what extent has the Project Coordination Unit (PCU) contributed to its mid-term success?

- Through document review and individual interviews with the staff of the PRGTE and  implementing partners, and focus groups with beneficiaries, a number of factors attributable to the Project Coordination Unit (Table 13 A)and which contributed to its mid-term success was identified.

Table 13 A. List of Factors attributable to the Coordinating Unit that contributed to achieving mid-term expected results

Factors attributable to managers

- The strong capacity and commitment of the group of managers to manage the project

- The experience and professionalism of the team leader of UNDP’s environment unit to provide technical support to the PCU.

- The experience and dynamism of the project coordinator, as well as his perfect knowledge of the actors involved, made it possible to obtain good results in the field.

- The closeness of the project’s coordinator and the expert in monitoring and evaluation with the IREFs in the various regions because of the spirit of solidarity.

- The designation of a PRGTE focal point in each public structure involved in the project implementation

- The existence of an administrative and financial procedures manual for the project that has been developed, validated and shared with all the partners of the project.

- External audits carried out by several independent firms for monitoring and ad hoc auditing of the project accounts

- Use of AMAT tool for adaptive capacities monitoring and evaluation

- Through the same process, the evaluation team has also identified a number of factors that have hindered the success of the project and can be attributed to managers (Table 13B).

Table 13 B. List of factors attributable to the management team that prevented achieving the expected results

Factors attributable to managers

- The project’s coordination entity in Dakar did not enough perceive as a priority the need to get closer to the implementing partners so that together they could find solutions to the problems arising out of the partnership.

- Project management fairly centralized at PCU level in Dakar and lack of systematic sharing of all project documents (including memoranda of understanding with implementing partners). Which could have allowed them to know the role of everybody in the implementation of the PRGTE and to consider opportunities for synergistic collaboration.

- Activity planning did not seem too realistic as it does not seem to have taken into account implementation during the first three months of the project. In the context of a new project, this is sometimes premature if not impossible, unless pre-financing mechanisms are available and agreements with implementing partners are already in place and duly signed before the first day of the project.

- The monitoring and evaluation of the project did not sufficiently carry out studies and activities for monitoring the impact of activities which should make it possible to consider corrective actions. Example1: the monitoring and evaluation of the project did not assess, after the training and accompaniment, what beneficiaries (especially the GPF) have retained from activities and how they use the skills acquired in their work. Example 2: monitoring and evaluation has not sufficiently explored partnership activities to identify new avenues for development.

- Although a monitoring and evaluation plan was drawn up by the head of monitoring and evaluation and even shared with the implementation actors in the field, its implementation did not have the support of all the stakeholders and the lack of resources has also been a limitation. The lack of implementation of this monitoring and evaluation plan did not help the situation.

- The release of funds intended for the implementation of the activities carried out by implementing partners not always in agreement with the agricultural calendar.

- The lack of equipment has prevented the Ziguinchor-based UNV from carrying out his monitoring and coordination activities easily in the communes of his area of ​​responsibility.

Question 5: To what extent has the project developed synergies with other stakeholders in the areas targeted by the Project to avoid duplication of effort?

- The use of the document review, individual interviews with the PRGTE’s staff, and implementing and steering partners, as well as reports of group discussions with beneficiaries showed that the PRGTE has established protocols with some ten implementing partners, including public service structures. However, despite the interest in the fact that the activities implemented are part of their traditional mission, and that such an initiative allows them to value this expertise, the partners to these protocols have caused many delays in the implementation of the projects’ activities. This was detrimental to the project effectiveness as for some partners the activities assigned by the project did not seem to be a priority in their agenda.

- In most cases the content of the protocols identifying the part to be contributed by each partner has been respected. However, the coordination of the PRGTE did not sufficiently bring together the different implementing partners around a synergy highlighting the complementarity of the contribution of each other in achieving the project objectives. For example, outside the CRSs and GTPs, the PRGTE could have organized several joint working sessions among the implementing partners to develop synergistic strategies. However, according to the information obtained during the interviews, these meetings were seldom held.

- Document review exploitation, individual interviews carried out with the PRGTE’s staff and implementing and steering partners, as well as reports of the group discussions with beneficiaries also showed that despite the multiplicity of projects involved on the same focus area than the PRGTE and in the same areas of implementation (PADEC, PADEN, PRECODE, FAO, etc.), the project has established a synergy with FAO as part of the project "High-End climate Impact and eXtreme", which allowed for the empowerment of 37 community radio agents from the URAC network in the interpretation and dissemination of weather and climate forecasting tools. The project worked also in close cooperation with the NGO “Enfance et Paix” for the restoration of the Mangrove and the NGO SOS Environment for awareness raising against bush fires and the establishment of firebreaks. Although the search for partnership was not defined as an activity during the project design, it was nevertheless selected as the driving force of the PRGTE's sustainability strategy.

- The PRGTE has also established partnership with CAURIE MF Microfinance for the implementation of this project activity and the provision of financial products at preferential interest rates (6 to 8%). However, as we found during the individual interviews and the focus groups, this activity is still in the starting stage with an amount of FCFA 75,000,000 granted as a loan within the partner groupings. However, it should be noted that the financial needs of beneficiaries to boost their IGA are a source of concern.

- However, the PRGTE has encountered several challenges in the search of partnerships. In addition to the distance between Dakar and the areas of implementation, the absence of UNVs in the regions of Louga and Thiès, the search for partnership is impeded by the reluctance of partners (especially projects) who have not always understood the relevance of such an action.

Question 6: To what extent has the participation of other stakeholders in the areas targeted by the project helped to advance the achievement of the project's mid-term objectives?

- Before answering this question, it should be noted that the PRGTE selected the “To Do” approach as an implementation strategy; it has mobilized more than a dozen actors for the implementation of its activities. Thus, three (03) formal frameworks including the Regional Monitoring Committees (CRS), the Steering Committee (COPIL) and the Technical Committee (TC) were to roll out the planned activities.

- However, the follow-up committees held during the first phase of project implementation were mixed. Outside the Ziguinchor region, where regional monitoring committee meetings are held on a quarterly basis, in the other regions the meeting was held annually, thereby diluting the possibilities for exchange and complementarity of actions between the different implementing partners. Apart from IREF and DRDR, which works in synergy and complementarity in the field, the evaluation team found that each implementing partner operates in a vacuum, with no real interest in sharing with others.

- In addition, although several GTPs (the role of the GTPs is well played, a 10-day information-sharing meeting) have been set up by the project, they are lagging to play their role because of the virtual absence of meetings and the lack of effective coordination of efforts in this regard in different regions.

Question 7: What are the unexpected effects (positive and negative) of the project's interventions at the social, economic and environmental levels, among the technical and financial partners, the target groups or other local authorities?

Unexpected Positive effects

- Most of the positive unexpected effects were observed at the level of beneficiaries :

- The beneficiaries of the micro-irrigation solar kits share more and more the water obtained with the other neighboring farms, generally of small surface area (less than 01 hectare)   ;

- There was a pooling of forces between IREF services, GPFs and young people for the restoration of the mangrove swamp in Diende;

- There was also a pooling of the sensitized community members' strengths on the effects in climate change, for the construction of grass bunds with vetiver or stone blocks in the Soukou valley in Sare Bidji commune ;

- The beneficiaries of Kolda and Sedhiou have shown the need to obtain small irrigation kits for the development of market gardening   ;

- The villages that had not been targeted by the project were strongly interested in participating in the activities of the beneficiary communes and at the same time expressed the wish that activities be organized at the level of the communes and the chief towns of the regions for a participation of all;

- The availability of improved seeds adapted to the agro-ecology conditions of the production areas allowed men to take an interest in rice farming, which was an activity exclusively carried out by women in the Kolda region. [7] .

- GPFs are involved in the production of seedlings for their own use.

- The Sare Samba Diaba GPF is ready to make a substantial financial contribution as a supplement to the credit needed by the CAURIE MF MFI to acquire a tractor that will allow each member to boost their rice production.

- Beneficiary populations have begun to understand that water and forest agents can also be agents of development compared to the image of law enforcement officer against poaching and illegal logging.   ;

- In the dunes, a farmer has agreed to co-finance 1.5 million for the fixation of the rural habitat   ;

- Having noted that irrigation kits are structuring investments to boost production, small producers in the Niayes area are ready to make a 25% financial contribution to facilitate the purchase of this equipment under the PRGTE program.

- Through a consensus of the villagers of the locality of Soukou have accepted a local convention for the development of the Soukou valley

Unexpected Negative effects

- Most of the unexpected negative effects concern the beneficiaries. These effects include, among others:

- Solar kits for micro-irrigation by drip technology could not be deployed in municipalities in the Thiès region because of the ferrous nature of the soil. In fact, the water in this region contains ferrous ions which clog the drainage holes of the water, making at the same time the inoperative drains;

- The lack of a communication strategy which has often led to misunderstandings about the type of product offered by the project and the eligibility criteria [8] ;

- Dissemination of false information about the project's support, which often creates misunderstandings among the members of the beneficiary communities.

- The virtual unavailability of producers during the winter season, which paralyzes the activities of the project to be implemented.

- The enrichment of mangrove forests restored to fish triggers conflicts between the riparian villages for access to this new fishing area (example: the villages bordering the town of Coubalan).

Testimonies of Seydou Balde and Moussa Mballo spokespersons of the DIOUFANA / DIOULACOUN communities The DIOUFANA/DIOULACOUN community benefited from two flagship activities of the PRGTE, including the provision of climate-adapted seeds and agricultural equipment. With regard to seeds, the support of the PRGTE which benefited 30 producers covered 2 speculations namely maize (area planted with 4 hectares) and rice (area planted with 6 hectares). The support of the PRGTE also allowed the beneficiaries to obtain 7 kits of agricultural equipment consisting of coupled plows, seed drills, etc., as well as training in land legislation. The project touched on one of our main concerns, which is the availability of adapted seeds, since we started with the sowing. It is difficult to produce seeds but if the production is well conducted, its use leads to an increase in yields of 30%. To ensure the quality of the seeds produced, we want to obtain supports, including threshing machines and fences to cope with the stray animals. Aissatou Mballo, a member of the community I thank Mrs. Diatta (VNU) for her assistance. Before the intervention of the PRGTE, we did all our field work with rudimentary agricultural equipment (hoe, daba, etc.) now, with the equipment we received from the project, the tasks are automated and simpler. Seed multiplication is different from food production: to be an approved seed multiplier, we have been trained. But, what remains is the production of seed, that is to say of small area planted of which one cannot consume the product, whereas the process of production is very constraining: the choice of plots, sowing techniques, isolation, etc. Before rice production was an all-women activity. But now with BIRICA, men are more and more involved in rain-fed rice production. Testimonials Mamadou Balde a member of the community It is primarily the quality of the seed which is at the origin of the increase of the production, the equipment comes in second position. We have heard that the fund is available at CAURIE-Microfinance and with well-negotiated terms (rate of 7 to 8%). However, CNCA charges 5% for the campaign credit, however for seed production, it is not necessarily that we will have funding there. No fears for reimbursement we used to have in traditional microfinance. If people do not repay, there will be no development. There is a strong demand for seed production and the provision of small equipment is a motivating factor

4.3. Project implementation and adaptive management

Introduction

- The total project budget ($ 18.1 million) comes from GEF/LDCF grants ($ 4.1 million, or 22.7%), UNDP ($ 500,000, or 8.9%), Government of Senegal ($ 1 million, of which   200,000 in kind, or 17.8%) and ANACIM ($ 3.5 million, co-financed). The amount of the budget actually allocated to the project is $ 5.6 million and comes from GEF/LDCF (73.2%), UNDP (8.9%) and the Government of Senegal (17.8%).

Financial resources Management

Question 1: To what extent were funds earmarked for the implementation of the mid-term project sufficient to meet the needs of the target groups?

- The distribution of the budget (Table 14) between the different headings reveals that, in general, 95% of the financial resources were devoted to the implementation of the activities in the field whereas only 5% of these resources were dedicated to the operation of the project.

Table 14. Breakdown of project budget by activities

| Budget Type of activity | Allocated Budget Indicated in the Project Document ($) | % |
| --- | --- | --- |
| Activities of Component 1 : Setting up a climate change information platform and effective adaptation options | 1 400 000 | 34% |
| Activities of Component 2: Reducing Risks of Climate Change in Target Lands and Ecosystems with Adaptive Recovery Measures | 1 828 000 | 45% |
| Activities of Component 3: Support for knowledge and information acquisition mechanisms | 6 75 000 | 16% |
| Activities contributing to the management of the project | 197 000 | 5% |
| Total | 4 100 000 | 100% |

- The exploitation of the document review (project accounting document, HACT audit report of the 2016 PRGTE, etc.), interviews with the project staff showed that while the mid-term budget was sufficient for the activities in strands 1 and 3, this was not the case for Part 2 (Table 15). In fact, unlike the budget forecasts, the achievements are as follows:

- Activities of Component 1 received 33.6% of the planned mid-term budget for this component, compared with a 155.5% achievement rate for the mid-term forecast (3 out of 6 activities were implemented 100%) and 66.6% compared to all the activities to be implemented for this component (6 out of 9 planned activities)   ;

- Activities of Component 2 received 91.6% of the mid-term budget for this component, compared to a 200% performance rate compared to the mid-term forecast (5 out of 10 were executed at 100% or even more) and 100% compared to all the activities to be implemented for this component (10 out of 10 planned activities)   ;

- Activities of Component 3 received 68.1% of the planned mid-term budget for this component, compared to an activity completion rate of 142.9% compared to the mid-term forecast (1 out of 7 activity was completed at more than 100%) and 71.4% compared to all the activities to be implemented for this component (5 out of 7 planned activities).

Table 15: Difference between the planned mid-term budget and the actual budget received (15/11/2018) by activity component

|  | Budget indicated in the Project Document ($) | Mid-term budget indicated in the Project Document ($) | Budget actually received ($) | (%) Budget actually received / Mid-term budget indicated in the Project Document | (%) Budget actually received / Budget indicated in the Project Document |
| --- | --- | --- | --- | --- | --- |
| Component 1 | 1,400,000 | 878,400 | 295,427.94 | 1,400,000 | 878,400 |
| Component 2 | 1,828,000 | 1 088 700 | 996,707.19 | 1,828,000 | 1 088 700 |
| Component 3 | 675,000 | 404,400 | 275,416.43 | 675,000 | 404,400 |
| Total | 3,903,000 | 2,371,500 | 1,567,551.56 | 3,903,000 | 2,371,500 |

Question 2: To what extent have the funds for the implementation of the mid-term project been released on time?

- Budget General Observations (Table 16) show that at mid-term, 47.3% of the budget foreseen in the project document was actually granted. That being said, the GEF/LDCF is the financial partner that has made the most significant contribution to the project with 49.8% of funding provided compared to what was planned, while UNDP is the financial partner that contributed less (29.7%) in project funding planned.

Table 16: Funds released by financial partners (15/11/2018)

|  | Allocated Budget Indicated in the Project Document ($) | Budget actually allocated at 30/04/2018 ($) | % of the Actual Budget allocated on the 30/04/2018 ($) | Difference between the planned budget and the actual budget allocated ($) at 30/04/2018 | Difference between planned budget and actual budget (%) |
| --- | --- | --- | --- | --- | --- |
| GEF/LDCF | 4 100,000 | 2,042,610.24 | 49.8% | -2,057,389.76 | -50.2% |
| UNDP | 500,000 | 148,591.50 | 29.7% | -351 408.50 | -70.3% |
| Government | 800 000 | 354,082.25 | 44.3% | -445,917.75 | -55.7% |
| Total | 5,400,000 | 2,545,283.98 | 47.1% | -2,854,716.02 | -52.9% |

- Almost all of the different implementing partners interviewed during the evaluation mission both in Dakar and in the implementation regions admitted that, despite the effort made by the coordination in Dakar, the funds have not been released on time. Indeed, two reasons could explain this situation:

- Firstly, the delay in the release of funds by the financial partners to the benefit of the project account (example : the first payment of the financial partners for the benefit of the project was made only on April 24, 2016, just over 02 months after the start of the project) ;

- Secondly, for the implementing partners, the weakness in the application of NEX procedures and the heavy bureaucracy at institutional level, as well as the difficulty for some partners to incur certain expenses already transferred into their accounts. Indeed, the NEX procedure requires conformity of the supporting documents both in substance and in form, a demand that implementing partners could not always comply with and the biggest delay factor in the execution of semi-annual funding requests made by PTAs. Indeed, the multiplicity of monitoring and control posts (PCU, UNDP, Directorate of Cooperation and External Financing (DCFE) of the Ministry of Economy and Finance and Planning and UNDP) with the rejection of the file at one level being the source of the delay.

- This late release of funds for implementing partners explains the delay in implementing some activities in the field. Moreover, the delay in the release of the funds has a negative impact on the implementation of agricultural activities which depend on the necessity to respect the agricultural calendar and reforestation (for example: the funds can be available only when the sowing period has long passed, making it even pointless).

- However, as a mitigation measure, the PCU has drawn the attention of its partners about these delays, as well as the need to anticipate activities and procedures in order to acquire equipment and services and to avoid demobilization. To this end, the monitoring and evaluation team in relation with the Coordinator, sent several correspondences to clarify certain situations in the execution of the expenses and their justifications and therefore improve and build the capacities of the agents.

- Another initiative taken by the PCU was to transfer a correspondence from the Minister of the Environment to his colleague in charge of agriculture, who is responsible for supervising the DRDRs, in order for them to implement the activities of the PRGTE, entrusted to its decentralized services. The Director of Water and Forests also acted in the same manner towards his Regional Inspectors of Water and Forests.

- It is also important to note that the implementation deadline was not respected in some cases because several activities planned by the project required the mobilization and training of targets, which were affected by the unavailability of funds in a timely manner. In general terms, as soon as funds were available, implementing partners reworked a plan that was followed by the book.

Question 3: What steps have been taken in the project implementation to ensure that resources prove less costly compared to existing alternatives?

- During implementation, the use of the procurement code, competitive bidding procedures and the use of quality bidding documents allowed the project to buy at lower cost with a better quality.

Human Resource Management

Question 4: To what extent has mid-term human resource management been the least costly compared to existing alternatives?

- First, in its implementation strategy, the project design focused on the "Do-it-yourself" approach that enabled the use of the human resources of the public services for the implementation of project activities. This has limited operating costs including staff salaries to 5% of the budget allocated compared to the 30% often required in projects implemented by various UN agencies.

- Human resources management has been fairly cost-effective thanks to the strong involvement of public service staff. Despite the extent of the areas of implementation and the 26 activities to be carried out, the PMU of the PRGTE has 10 agents including 5 strategic agents (Coordinator, Expert in Monitoring Evaluation, Administrative and Financial Assistant, Evaluation Monitoring Assistant and Accounting Assistant) all located in Dakar, 5 operational including 02 in Dakar (Executive Assistant and Driver) and 03 (01 Driver and 02 VNU) in the Casamance area. The presence of UNVs among the project staff helped to reduce the payroll.

- Compared to the budget of the project released mid-term, the salaries of the project staff represented 17.2%, which corresponds to 137% compared to the 5% of the overall budget that had been planned for operation, which shows that the project's operating costs were underestimated when it was designed.

Question 5. To what extent have the number and capacity of staff initially available for project management and implementation (since October 2015) been sufficient to meet the needs of beneficiaries at mid-term?

- The use of the document review, individual interviews with PRGTE staff, implementation and steering partners, as well as reports of group discussions with beneficiaries also showed that although coordination in the Casamance area, which has 02 UNVs coordinating and monitoring project activities in the region, has improved significantly. On the other hand, the Niayes area seems to be left to itself. Indeed, the absence of agents capable of ensuring monitoring and coordination in the regions of Thiès and Louga, precludes smooth of exchanges between the implementing partners on the one hand and coordination in Dakar on the other hand, which greatly hinders the implementation of project activities in this region.

- However, among the implementing partners, there is some instability of the technical staff in charge of supervising the population on the ground because of redeployment which has often undermined some efforts to mobilize and energize the actors to boost the implementation of the project activities (For instance: the Colonel in charge of Kolda IREF has been in office since 2 October 2018 only (02 months)).

- The evaluation team raised the weakness of skills and technologies  at the level of ANACIM and other implementing partners to transform the weather data produced at the stations into information easily understandable and usable by the producers, as well as the identification of the appropriate channels for this information to be able to reach them.

Management of goods and equipment

Question 6: To what extent has the management of project assets / equipment been the least costly compared to existing alternatives?

- To minimize equipment acquisition costs, the project relied on NEX procedures. In any case, purchases were made locally in accordance with the country's procurement procedures, which favors competitive bidding and makes it possible to buy at lower price with better quality.

- However, the slowness of the NEX procedure has resulted in delays in the availability of equipment, which has had an impact on the activities in question while hindering complementary activities (For instance: the Thiès station was installed in October whereas it was planned in the 2016 PTA).

Communication Management

Question 7: How effective was the internal communication of the mid-term project?

- Document review, interviews with the project’s staff and the implementing partners, as well as the direct field observations made by the evaluation team revealed the beginning of the implementation of the project up to the end of the project. At the mid-term, the project did not use any media communication tools as part of its internal communication. What they used include meetings, mail, email and phone. However, the use of these tools has not been integrated into an internal communication strategy that would have brought project coordination closer to the other actors involved in its implementation. However the most used channels including the telephone and internet being the lowest on the market has allowed the internal communication to be less expensive.

- The literature research, the interviews with the project staff, as well as the direct observations made by the evaluation team also revealed that the PRGTE has set up a website. However, this website only provides basic information about the project and had not been updated for over than 2 years. In addition, this website does not include any publication of knowledge generated as part of the implementation of the project.

Question 8: To what extent have the appropriate means of communication been put in place or are being put in place to inform the public of progress made in the project and its expected impact?

- The desk research, the interviews with the project staff and the implementing partners, as well as the direct field observations made by the evaluation team revealed that several communication tools have been put in place by the PRGTE to communicate to the public the progress made in the project and its impact.

- These include a dozen documentary films about the project's achievements, and some radio advertisements for possible dissemination in the local media. These tools remain very insufficient with regard to demand. Indeed the evaluation team noted a virtual absence of visibility tools such as leaflets, signs, posters for awareness, data sheets, etc. (For instance: during the whole mission, the evaluators found 02 informative signs showing the achievements of the project in a single plantation of Kolda).

Question 9: To what extent have the appropriate means of communication been put in place to facilitate the ownership and implementation of the knowledge needed to strengthen land and ecosystem management in a climate change context?

- To inform the partners and the public about the project's achievements, increase the project's impact on the beneficiaries and enable them to adopt adaptive behaviors in the face of climate change, the PRGTE set up a communication plan whose deployment was meant to allow to correct the shortcomings noted in this area. However, due to the weakness of communication for the visibility of PRGTE's flagship activities at the level of television, community radio and other media, the communication focused on the non-media means with awareness meetings, training sessions etc. This revealed a mixed result, which questions the efficiency of the communication of the project.

- However, during the capacity building sessions in the implementation sites, the trainers did not discriminate against the target (literate and illiterate individuals). A single pedagogical approach not based on andragogy and intended for literate adults was used for the entire target group (literate and illiterate) with unsuitable support material (notebook and mimeograph). Such an approach has only been used by literate participants, which at the same time caused information asymmetry for illiterate learners.

- That being said, the evaluation team also noted during the evaluation, a virtual absence of communication tools that could help the sustainability of the project including, posters, awareness pictures, data sheets that can be interpreted by the greatest number. The same is true of other communication tools for development, such as skits and plays, in local or non-local languages, attended by the public or broadcast in community radios, awareness posters, etc...).

4.4. Sustainability

Question 1: To what extent are the risks identified in the Project Document, the Annual Project/PIR Review and the ATLAS Risk Management Module the most significant, and the evaluations of these risks the most appropriate?

- Before answering this question, it is important to remember that the most significant risks that have been identified in the project document, the annual review of  PIR/ATLAS project are organizational or strategic, and mainly concern the current weak institutional and individual capacity of public service structures in terms of adaptation, financial capacity of beneficiaries, lack of adequate human resources, political will, social conflicts related to gender and the intensity of climate change impact.

- With regard to organizational risks, literature search, interviews with the project staff, as well as implementation partners, organizational risk was one of the main challenges throughout the implementation of the project, in particular with the difficulty of putting the different public service structures having different but complementary missions together, and use this complementarity in the implementation project activities. This difficulty was illustrated in terms of availability, mobilization, commitment, sometimes lack of appropriate human resources, etc.

- The literature search, interviews with project staff, partners and beneficiaries also allowed to highlight the importance of the intensity of climate change for the implementation and success of the project activities (example : the inaccuracy of the information made available to farmers by ANACIM on the likelihood late rains in the region of Thiès (Thialé) during the last crop year, led farmers to take ineffective adaptive measures, which resulted in the lack of agricultural production and especially groundnut seeds for the upcoming crop year. Example 2: the increasingly long dry season in the Kolda region has seriously compromised reforestation activities through the establishment of oil palm plantations, as the planted plants that are not watered have been under water stress. Example 3: the increasingly long dry season increases the risk of bush fires caused, or spontaneous).

- As for the political will and social conflicts related to gender, these two risks were expressed only very slightly during the implementation of the first phase of the project. First, during this implementation phase, the political situation in the Republic of Senegal remained stable and the strategic option was maintained, which may not be the case for the next phase. Then, the endogenous measures were taken by the communities to minimize the risk of gender-related conflict (example1: in Casamance, men have also begun producing rice but in the plateaux, leaving flooded rice paddies traditionally exploited by women. Example 2: in the Thiès and Kolda regions, women's lack of access to property has been resolved by family arrangements allowing them to exploit an area even if they are not the owners of it).

Testimony of Mamodou Mba, spokesman of the bushfire fighting committee in the village of SARE BILALI. The project has trained members of the Bushfire Fighting Committee of the Village in bushfire techniques. We have learned that there are active and passive techniques, one doesn’t tackle bushfire in frontal position, but on the sides. The project has also enabled the members of the Bushfire Fighting Committee to obtain a small equipment (machetes, rakes, etc.) but there are still pumps allowing to extinguish major bushfires to put in place. As for bushfire fighting itself, since our training and equipment, we have noticed that there are fewer and fewer damages from bushfire in our village and its surroundings. We are in December, this is presently the period in question. At the end of this month, the straw will dry and the brushfires will restart. The priority of the community at this time is to put in place firewalls to preserve forest resources. But for this purpose, we need adapted equipment.

Question 2: What is the likelihood of the lack of financial and economic resources after the end of the GEF support?

- To answer to this question, it is necessary to remember that the project has so far made it possible to put in place a set of equipment, infrastructures and tools that have all been transferred either to public service structures (4 weather stations, 3 hydro stations and 5 GPS), or communities that are beneficiaries of the project (17 bunds in frame, 01 bund grassed with vetiver, 01 stone barrier, 01 water storage project (45 m x 90 cm), 10 fish ponds, 20 floating cages and an oyster disgorging center in Ziguinchor (under way) or community members (03 solar pumps 48 panels, 10 solar pumps, 160 panels, 13 solar pumps, 208 panels of small agricultural equipment, etc. ). As well as other achievements (forest of restored mangrove, village palm grove, etc.)

- All such equipment, tools and achievements have been transferred by the PRGTE to these different actors who are already incorporating them into their production system, which in itself greatly reduces the lack of resources likelihood after the end of the project for the public service structures. Indeed, interviews with the project staff and especially the different implementing partners showed that the activities for which they are responsible will continue to be financed by their budget, some of which already have dedicated budget lines, if not part of their state activities they can easily create.

- In addition, beneficiary communities in the Niayes and Casamance areas have agreed to make a financial contribution for strengthening land and ecosystem management. In fact :

- In the context of dune fixation in the Niayes area, a farmer agreed to co-finance up to 1,5 million FCFA for fixing the rural habitat; On another side, since irrigation kits are structuring investments, small farmers in need agree to contribute 25% of acquisition equipment cost.

- In the Casamance region, the populations are strongly involved in the implementation of mangrove management plans, particularly in the village of Soukou in the Kolda region. Most of villagers have accepted a local convention for the development of the valley of Soukou.

- However, these interviews have also shown that, given the low financial capacity of the communities of their members, it will be difficult for them to keep these equipment in working order or to make them work after the end of the project, if the IGAs they practice are unsustainable or lack adequate financial support.

Question 3: Are there any social, political, institutional or environmental risks that could threaten the sustainability of the project's achievements?

- The literature search, the interviews with the project staff, the implementing partners enabled us to highlight the external risks identified during the implementation of the PRGTE and which are not under the control of this project ( Table 17), the most likely of which are: conflicts between farmers and pastoralists, the return of pests to restored forests, the great mobility of DEFCCS staff due to placement, and the likely eviction of small agricultural producers who benefit from the PRGTE and who settled in the private property of the concessionaires in the Niayes areas and who may be evicted at any moment.

Table 17: Risks identified during the project mid-term implementation

| Type of risk | Risk presentation | Likelihood of achievement |
| --- | --- | --- |
| Financial | Community IGAs do not generate sufficient financial resources to maintain the infrastructure and equipment available to them. | Moderately likely |
| Social | The reluctance of producers to appropriate new adaptive capacities to the detriment of age-old practice. | Moderately likely |
|  | Conflicts between farmers and pastoralists: producers in the different production areas are confronted with the ravages made by the cattle herd that destroys agricultural crops. | Likely |
|  | Eviction of small agricultural producers who benefit from the PRGTE and who occupy the private domain of concessionaires in the Niayes Areas . | Likely |
| Environmental | The restocking of restored mangroves and reforested forests by previously undesirable species (granivorous birds, and other carnivorous animals (crocodiles)). | Likely |
|  | Increased soil salinity as a result of seawater rising towards the river or its infiltration into the soil. | Moderately likely |
|  | The reduction of water at groundwater level. | Moderately likely |
| Institutional | Provision of bad base seed to seed multipliers. | Moderately likely |
|  | Non-certification of seeds produced under the PRGTE activities. | Likely |
|  | The high mobility of DEFCCS staff due to placement. | Likely |

|  | Wind break in the Louga region (28 November 2018) |
| --- | --- |

- CONCLUSIONS AND RECOMMENDATIONS

5.1. Conclusions

Project Strategy

- The activities of the project fully addressed most of the issues related to strengthening the management of lands and ecosystems in the Niayes and Casamance in a context of climate change, which had been identified in the NAPA and situational analyses as well as any other research and consultation meeting on the subject. This was not the case for the need to promote water saving techniques and the construction of small water retention infrastructures (Finding 1, footnotes 1 and 2).

- In general, the objectives of the project have been adapted as much as possible to the national needs and priorities expressed by the Senegalese government, as identified by the exploitation of the PRGTE documents, the situational analyses carried out during its conception at the strategic level. However during the implementation of the project, several partners who had been selected in the project document and whose expertise was proven for the implementation were not involved (example: AGRHYMET, AGRHYMET, ACMAD, etc.) (Findings 2 to 5).

- With regard to theory of change as well as project implementation approach, the document review, individual interviews and focus groups confirmed that for the PRGTE, it is focused on impact, i.e. the desired change of beneficiaries for adopting adaptive measures to address climate change, through land restoration and ecosystem management thanks to a more sustainable exploitation, management and equitable distribution of all natural resources (Findings 6 and 7).

- The people involved in the decision-making were taken into account during the project design at several levels, including the multidisciplinary team (meteorologist, forestry expert and socio-economist) that was selected for the design of almost all public service structures involved in project implementation and the situational survey of beneficiaries in the five implementation regions (Finding 8).

- In planning, gender (in particular the principles of inclusion, participation and equity especially for the most vulnerable and marginalized groups in the sites targeted by the project) including gender-specific indicators for measuring targets of the project, as well as specific activities for women in components 2 and 3. However, during the implementation of the project, the conditions for selecting beneficiaries did not sufficiently take into account the weight of habits and customs which is a factor limiting the participation of women (Findings 9, 10 and 11).

- In general terms, the project targets have been fully attainable, achievable and defined over time, which was not the case of the specificity, only the target 1 totally was, the targets 3 and 4 partially, and the targets 2 and 5 weakly. The same goes for the measurability in which all the targets were partially measured. However, the size of some targets seems to have been underestimated (Finding 13).

- Overall, the literature search showed that targets 1, 2 and 5 were easily attainable and achievable. In fact, at the arrival of the mid-term project in November 2018, 106.1% of target 1 and 188.3% of target 2 were achieved, while for target 5, 200.46%  was achieved (Finding 14).

Progress towards the achievement of results

- The component contributing to achieving the objective 2 of the project is the one with the highest achievement rate (200% of the expected results at mid-term and 100% compared to the overall activities of this component). Then, the component contributing to the achievement of the result 3 (which reached 142.9% of the expected results at mid-term and 71.4% compared to the overall activities of this component). Finally, the component contributing to the achievement of the objective 1 with an achievement rate of 133.3% compared to the expected results at mid-term and 66.6% compared to the overall activities of this component. However, due to the lack of visible achievements on the ground, the result of some of the activities implemented by ANACIM and often carried out from Dakar has been very difficult to verify (finding 19, footnote 10).

- The collaboration of the project with a diverse typology of actors (government, public service structures, local authorities, civil society and other agencies of the United Nations) contributed to the implementation of a contextualized response to the strengthening of land and ecosystem management in a context of climate change. That being said, shortcomings in coordination and monitoring and evaluation have limited the effectiveness of the project (Findings: Tables 11A, 11B, 12A, 12B, 13A and 13B).

- The PRGTE has established protocols with about 10 implementing partners, including public service structures. However, despite the interest in the fact that the activities implemented are part of their traditional mission, and that such an initiative allows them to value this expertise, the partners involved in these protocols have caused a great deal of slowness in the implementation of activities. Nevertheless, the PRGTE has established a synergy with the FAO under the "High End Climate Impact and eXtreme" project, which has allowed the ability of 37 community radio agents of the URAC network to interpret and disseminate weather and climate forecasting tools (findings 30 to 33).

- Several positive effects were noted during the implementation of the PRGTE, one of the most important of which is the strong mobilization, participation and involvement of communities in the restoration of the mangrove, reforestation and the construction of bunds (note 37).

Project implementation and adaptive management

- Overall, the funds have been sufficient at mid-term to meet Components 1 and 3 implementation needs, which was not the case for Component 2 activities where funds were found to be insufficient. In addition, only 5% of these resources were devoted to the operation of the project (Findings 39, 40 and 41).

- In general terms, the release of funds did not take place according to the deadline for most of implementing partners, despite the efforts made by the coordination to facilitate them to appropriate the NEX procedures, despite the fact that this delay is also due to the disbursement by the project's main donors of funds that are not always in time. However, the latter have not sufficiently capitalized on this opportunity to avoid cash-flow tensions, often leading to a shutdown during the implementation (Findings 42 and 43).

- In addition, the coordination of the project appealed by correspondence to the authority of the Minister of the Environment, his colleague in charge of agriculture ensuring the supervision of the DRDR, for a good handling of the activities of the PRGTE, entrusted to its decentralized services (observations 45 and 46).

- Human resources management have proven to be fairly cost-effective thanks to the strong involvement of public service structures staff. For all the large areas of implementation and the 26 activities to be carried out, the PCU of the PRGTE has 10 agents. However, this in itself reduced the adaptive effectiveness of project coordination in the field, this prompted management to recruit 02 national UNVs to cover Casamance. This is still insufficient, given the coordination difficulties encountered in the Niayes area. However, it is a contextual adaptation measure set forth in the project document (finding 50).

- given the great inadequacy of the budget for  activities 1 and 3, this in itself resulted in a relatively low mid-term budget consumption rate (27.1%) for an activity achievement rate of 133.3% compared to the expected result and above the average (68.1%) for an activity achievement rate of 142.9% for component 3. However, the salaries of the project staff were accounted for only 17.2% of the total funds released at mid-term, i.e. 137% of the project overall operating budget, which shows that operating costs were underestimated when designing the project (finding 51).

- However, although the PRGTE has a website, this platform, which has not been updated for more than 2 years, has only basic information about the project and is characterized by a complete lack of publications on knowledge generated in the context of the implementation of the project (finding 58).

- To inform the partners and the public about the achievements of the project, increase the effects of the project to the beneficiaries, the communication of the project focused on the non-media with awareness during meetings, training sessions, etc. However, these communication actions were marked by several deficiencies, both in terms of pedagogical approach used and virtual absence of appropriate awareness and training tools, which raises questions about the efficiency of the project communication ( findings 62, 63 et 64).

Sustainability

- Overall, the risks identified in the Project Document, the Annual Project Review/PIR, and the ATLAS Risk Management Module, particularly organizational or strategic, have proven to be the most important and the most appropriate assessment of these risks. The organizational risk (in the availability, mobilization, commitment and sometimes capacity) of partner staff selected for the implementation was one of the main challenges to be met throughout the implementation of the first phase of the project. The same is true of the importance of the intensity of climate change, which has also been expressed as a challenge during the implementation of project activities. However, regarding political will and gender-related social conflicts, these two risks were expressed only very weakly during the implementation of the project’s first phase (findings 64 to 67).

- All the equipment, tools and achievements put in place by the PRGTE have been transferred to the implementing partners, the beneficiary communities and its members. These different actors are already incorporating them into their production system, which in itself greatly reduces the likelihood of a lack of financial resources for the public service structures after the end of the project. This will not always be the case for the community and its members, who, given the weakness of their financial capacity, may not be able to maintain and operate these equipment after the end of the project, if the IGAs they practice are not sustainable or do not receive adequate financial support. However, some members of the beneficiary communities in the Niayes are ready to co-finance certain activities of the project (findings 69 and 70).

- Conflicts between farmers and breeders, pests returning to restored forests, and high mobility of DEFCCS staff due to placement are the most likely external risks that were identified during the implementation of the PRGTE and are not under the control of this project (finding 66).

- The small agricultural producers benefiting from the PRGTE and who have settled in the private property of the concessionaires in the Niayes Area are at risk of being evicted at any time (finding 72).

| Drip technology in a vegetable garden in Louga (28 November 2018) | Sand dune fixation in the region of Thiès (29 November 2018) |
| --- | --- |

  - . Recommendations

Project Strategy

| Finding 1, footnotes 1 and 2) |  |
| --- | --- |
| Recommendation 01: The implementation of basic studies recommendations on the demand of producers in the Niayes and Casamance areas for water saving and small infrastructure techniques should be carried out within a maximum of 3 months, which take into account not only hydro-soil conditions, but also climatic conditions. | Recipient of the recommendation - PRGTE - DEFCCS - DRDR - PNUD |
| Strategic option : - Use the studies carried out as part of the design and implementation of the project, as well as monitoring and evaluation reports to better identify the needs of beneficiaries in terms of water management. Ensure that the needs of beneficiaries in all project implementation areas are taken into account in the provision of small-scale irrigation technologies |  |
| Findings 9, 10 and 11 |  |
| Recommendation 02: In order to allow the involvement and participation of all, including men, women and youth in its various activities, the PRGTE adaptation to beneficiaries’ cultural, economic and environmental context at the local level must be enhanced. | Recipient of the recommendation • PRGTE • UNDP • DEFCCS • Other partners |
| Strategic option : Include in the choice of beneficiaries criteria related to habits and customs practiced in the context of land ownership (example: beneficiary who exploits a family property, etc.). |  |
| Finding 14 |  |
| Recommendation 03: The criteria of specificity and measurability of the different project targets must be reviewed so that they can be totally SMART. | Recipient of the recommendation - PCU - UNDP - DEFCCS |

Progress towards achievement of results

| Findings 19, footnote 10 |  |
| --- | --- |
| Recommendation 04: ANACIM staff capacity in producing and disseminating meteorological information for development in the different regions of implementation, including those of all implementing partners, should be strengthened. | Recipient of the recommendation - PCU - UNDP - DEFCCS - Other partners |
| Strategic option: Organize capacity building sessions for ANACIM staff and other partners involved in the implementation of the project in the regions. To this end, ACMAD's expertise could help. |  |
| Findings: Tables 11A, 11B, 12A, 12B, 13A and 13B |  |
| Recommendation 05: The additional means of coordination and monitoring should be defined so that the PCU can carry out local monitoring as part of the implementation of project activities in the field. | Recipient of the recommendation - PCU - UNDP - DEFCCS |
| Strategic option: Set up a monthly and budgeted schedule of field visits for the project staff and define the necessary means for this company. |  |

Project implementation and adaptive management

| Findings: 42 and 43 |  |
| --- | --- |
| Recommendation 06: A cash-management forecast system should be put in place as a result of project implementation and ensure that there is consistency between the project's funding requirements, the project activity schedule, and deadlines for the release of funds. | Recipient of the recommendation - PRGTE - DEFCCS - DRDR - UNDP |
| Strategic option: - Train the financial service staff and implementing partners’ accountant in NEX procedures as well as the presentation of supporting documents within one month. |  |
| Findings: 45, 46 and 53 |  |
| Recommendation 07 : - Coordination and monitoring of the project in the regions of implementation need to be strengthened through the recruitment of additional 02 national UNVs to cover the regions of Louga and Thiès ; - And ensure that all UNVs of the project have the necessary means to carry out the operational work of coordination and follow-up in the field. | Recipient of the recommendation - PRGTE - UNDP |
| Strategic option: - Set a deadline of 02 months for this recruitment and ensure that all project national UNVs have the operational means to effectively monitor the coordination activities in the field. For this purpose, additional funds could be sought at UNDP or another partner. |  |
| Findings 61 |  |
| Recommendation 08: Operationalizing the project's communication strategy by adopting an approach that includes both institutional visibility and development (behavior change) objectives and that participation and social and political change should be promoted by the communication for development. | Recipient of the recommendation - PRGTE - UNDP |
| Strategic option: Update and enrich the PRGTE website by putting online the various studies produced as part of the project, as well as other awareness-raising projects |  |

Sustainability

| Finding 69 |  |  |
| --- | --- | --- |
| Recommendation 09: We need to explore and take advantage of the potential contribution of beneficiary communities’ individual members to the funding of PRGTE activities through a co-funding process. | Recipient of the recommendation - PRGTE - UNDP |  |
| Strategic option: Set a deadline of 02 months for this recruitment and ensure that all the project national UNVs have the operational means to effectively monitor the coordination activities in the field. For this purpose, additional funds could be sought at UNDP or another partner. |  |  |
| Finding 70 |  |  |
| Recommendation 10: We need to increase the search for partnerships with microfinance actors to support the IGAs set up as part of the project activities to ensure their profitability. | Recipient of the recommendation - PRGTE - UNDP |  |
| Strategic option: - Focus on financial products that combine credit with training. - Strengthen the beneficiaries' capacities in micro-enterprise management, particularly in the management of fish farms, oyster farming, farming, etc. Strengthen the capacity of IGA beneficiaries in Marketing and Financial Management. |  |  |
| Finding 72 |  |  |
| Recommendation 11: Among the selection criteria for choosing the PRGTE beneficiaries in the Niayes area, it is necessary to consider that their farms are not included in the private domain of concessions. | Recipient of the recommendation - PRGTE - UNDP |  |

6. Annexes

Annex 6.1: Terms of reference for the mid-term review

BACKGROUND:

## The Global Environment Facility (GEF) and the United Nations Development Program (UNDP) assisted the Government of Senegal in formulating a project for Strengthening the Management of Lands and Ecosystems in the Niayes and Casamance in a Context of Climate Change (PRGTE) (PIMS No. 4964), implemented by the Ministry of Environment and Sustainable Development (MEDD), through the Directorate of Waters, Forests Hunting and Soil Conservation (DEFCCS), which is to be completed in 2018. The project was launched on October 26, 2015 and is in its third year of implementation. In accordance with the UNDP-GEF Mid-Term Review Guidelines, the mid-term review process was initiated prior to the submission of the Second Project Implementation Report (PIR). This mandate sets out the elements to be taken into account in the mid-term review. The review process should follow the guidelines in the document Guidelines for Conducting Mid-Term Review of UNDP-Supported Projects Funded by GEF (UNDP PPOP):http://www.undp.org/content/undp/en/home/accountability/policies-and-procedures.html).

The project was designed to develop an enabling environment for ecosystem management-based adaptation measures in the eco-geographical areas in the Niayes and Casamance. It is formulated on the basis of three components and three outcomes.

Component 1: An information platform on climate change and socio-environmental aspects to identify climate change-induced vulnerabilities and suggest effective adaptation options in the Niayes and Casamance regions.

Outcome 1: Information management systems to identify and monitor the effects of climate change on ecosystems are implemented for forecasting and monitoring.

Component 2: Reduction of climate change risks in target lands and ecosystems with adaptive restoration measures.

Outcome 2: Adaptation options focused on ecosystem management in the two target areas (Niayes and Casamance), including the adoption of resilient land and ecosystem management practices in a context of climate change, reduce the risks of climate change in such areas.

Component 3: Support mechanisms for acquiring knowledge and information.

Outcome 3: Individual, family and community capacities will be strengthened to increase awareness of climate change responses and provide strong support for adaptation efforts.

The project is executed according to the NEX modality.

3.  OBJECTIVES OF THE MID-TERM REVIEW

The mid-term review will evaluate progress towards the achievement of the project objectives and results, as set out in the Project Document, and measure the project first signs of success or failure, in order to define the changes needed to get the project back on track to achieving the expected results. The mid-term review will also examine the project's strategy and the risks related to its sustainability.

The mid-term review should provide information based on factual, credible, reliable and useful evidence. The review team will review all relevant sources of information, including documents developed during the project preparation phase (e.g., Project Identification Form (PIF), UNDP Project Initiation plan, UNDP Environmental and Social Safeguards Policy, Project Document, Project Reports including the Annual Project Review/PIR, revision of project budgets, lessons learned reports, national strategic and legal documents and any other material that the team considers useful to support the review). The mid-term review team will review the GEF focal area reference tracking tool presented to the GEF with the approval of the manager, as well as the mid-term monitoring tool of the GEF focal area which should  be completed before the field mission begins, conducted for the mid-term review.

The mid-term review team should follow a collaborative and participatory approach to ensure active participation of the project team, government counterparts (the GEF operational focal point), country UNDP, UNDP-GEF regional technical advisors, and other key stakeholders.

Stakeholder participation is fundamental for conducting successfully the mid-term review. This participation should consist of interviews with stakeholders with project responsibilities, including (ANACIM, ANCAR, ANA, DGPRE, CDH, CRPF, local communities): implementing agencies, senior officials and work/activity team leaders, key experts and consultants in project’s related areas, Project Steering Committee, project stakeholders, academia, local governments and CSOs, etc. In addition, the mid-term review team should conduct field missions in (Thiès, Louga, Ziguinchor and Kolda), particularly at the project sites.

The final mid-term review report should detail the approach used for the review, explicitly indicating the reasons for the approach, the initial assumptions, the challenges, the strengths and weaknesses of the methods and the approach applied for the examination.

UNDP is recruiting a team leader International Consultant, to lead the evaluation mission of this project.

DUTIES AND RESPONSIBILITIES:

The mid-term review team will evaluate the evolution of the project in the four categories mentioned below. Please refer to the document Guidelines for Conducting the Mid-Term Review of UNDP-Supported Projects Funded by the GEF for a detailed description of these categories.

i.    Project Strategy

Project Design:

- Analyze the problem the project is addressing and the basic assumptions. Review the consequences of any wrong assumptions or any contextual changes to the achievement of project results as set out in the Project Document.

- Examine the relevance of the project strategy and determine whether it is the most effective way to achieve the expected results. Have the lessons learned from other relevant projects been properly taken into account in the design of the project?

- Explore how the project meets the country's priorities. Take stock of national ownership. Is the project concept in line with the country's national sector development priorities and plans (or participating countries for multi-country projects)?

- Review decision-making processes: have the views of those who will be involved in the project decisions, those who may influence the results, and those who may contribute to provide information or additional resources for the process been taken into account during project design?

- Examine the extent to which relevant gender issues have been raised during the project design. See Annex 9 of the Guidelines for conducting the mid-term review of UNDP-supported projects funded by the GEF for further guidance.

- Identify whether there are areas of major concern that require improvement.

Results Framework/Logical framework:

- Critically analyze the indicators and targets of the project logical framework, evaluating the extent to which the mid-term targets are "SMART" (specific, measurable, achievable, relevant and time-bound), and suggest modifications/specific revisions to targets and indicators when necessary.

- Are objectives, results or elements of the project clear, applicable in practice and achievable on time?

- Determine whether the progress made to date has produced, or could in the future produce development benefits (e.g. income generation, gender equality and women's empowerment, better governance, etc...) that should be included in the project results framework and annually monitored.

- Ensure that the general aspects of project development and gender are effectively followed. Develop and recommend "SMART" development indicators, particularly gender-disaggregated indicators and indicators of development benefits.

ii.    Progress towards achievement of results

Analysis of progress towards achievements:

- Review the logical framework indicators in the light of progress towards the achievement of end-of-project targets, using the Matrix of Progress towards Achievement of Results and Guidelines for Conducting the mid-term review of UNDP-supported Projects funded by the GEF; progress is indicated by color according to the principle of "traffic light" depending on the level of progress made for each achievement; make recommendations for sectors falling under the category "are not in progress" (in red).

After analyzing the progress towards obtaining the achievements:

- Compare and analyze the GEF departure tracking tool with the one completed just before the mid-term review.

- Identify obstacles that still hinder the achievement of the project objectives for the remaining project period.

- By reviewing the beneficial effects of the project to date, identify ways in which these effects could be increased.

iii.   Project implementation and adaptive management

Management Mechanisms:

- Assess the overall effectiveness of project management as outlined in the Project Document. Have changes been made and are they effective? Are the responsibilities and hierarchical structure clear? Is the decision-making process transparent and initiated in a timely manner? Recommend improvements to be made.

- Review the quality of implementation of the implementing agency/implementing partners and recommend improvements to be made.

- Assess the quality of support provided by the GEF partner organization (UNDP) and recommend improvements to be made.

Activity planning:

- Review any delays in starting and implementing the project, identify what caused the delays, and ensure that the causes have been eliminated.

- Are the business planning processes results-oriented? If not, suggest ways to reorient business planning so that it is results-oriented.

- Review the implementation of the results framework/logical framework of the project as a management tool and review any changes that have been made since the beginning of the project.

Financing and co-financing:

- Examine the financial management of the project, paying particular attention to the cost-effectiveness of interventions.

- Review any changes in funding allocations resulting from budget revisions, and evaluate the adequacy and appropriateness of these revisions.

- Is the project accompanied by appropriate financial controls, in particular data reporting and planning that allow management to make informed budget decisions and disburse funds in a timely manner?

- On the basis of the co-financing follow-up table to be completed, comment on co-financing: is co-financing strategically applied to contribute to the achievement of the project objectives? Does the project team regularly hold meetings with co-financing partners to align funding priorities and annual work plans?

Monitoring and evaluation systems at the project level:

- Review the monitoring tools currently in use: do they provide the necessary information? Do they involve the participation of the main partners? Are they aligned with or incorporated into national systems? Do they use available information? Are they efficient? Are they cost-effective? Are other tools needed? How could they be more participatory and inclusive?

- Examine the financial management of the project monitoring and evaluation budget. Are the resources allocated sufficient for monitoring and evaluation? Are these resources effectively allocated?

Participation of stakeholders:

- Project management: Have the necessary and appropriate partnerships been put in place and strengthened with direct and indirect stakeholders?

- Participation and country-led processes: Do government stakeholders at local and national levels support the project objectives? Do they still play an active role in the project decision-making that support the efficiency and effectiveness of the project implementation?

- Participation and public awareness: To what extent does the participation of stakeholders and public awareness contribute to progress in the achievement of the project objectives?

Data communication:

- Evaluate how the project management has reported changes resulting from reactive management and notified them to the Project Steering Committee.

- Evaluate whether the project team and partners adequately comply with the GEF data reporting requirements (i.e., actions taken to address a poor evaluation in the PIR, where appropriate)?

- Evaluate how lessons learned from the reactive management process have been documented, communicated to key partners and incorporated by them.

Communication:

- Review internal communication with stakeholders regarding the project: Is communication regular and effective? Are some key stakeholders excluded from the communication? Do feedback mechanisms exist in the context of communication? Does communication with stakeholders contribute to raise awareness about the project achievements and activities, and investments for the sustainability of project results?

- Examine the external communication regarding the project: are appropriate means of communication in place or in the process of being put in place to inform the public about the progress made in the project and its expected impact (is there a website , for example?, or has the project implemented appropriate public awareness campaigns?)

- For reporting purposes, write a half-page paragraph summarizing the progress towards the project results achievement in terms of contribution to the beneficial effects for sustainable development and global environment.

iv.   Sustainability

- Check whether the risks identified in the Project Document, the Annual Project Review/PIR    and the ATLAS risk management module are the most important and whether the risk assessments are appropriate and up-to-date. If not, explain why.

- In addition, assess the risks for sustainability in the following categories:

Financial risks for sustainability:

- What is the likelihood of lack of financial and economic resources available after the end of GEF assistance (consider that possible resources may come from different sources, such as public and private sectors, income-generating activities and other funding that can be financial resources adapted to the sustainability of the project's achievements)?

Socio-economic risks for sustainability:

- Are there social or political risks that can threaten the sustainability of the achievements of the project? What is the risk that stakeholder ownership level (including governments and other key stakeholders) is not sufficient to sustain project achievements/benefits? Are the different main stakeholders aware that it is in their interest to maintain the benefits of the project? Is public/stakeholder awareness sufficient to support the long-term objectives of the project? Does the project team document the lessons learned on an ongoing basis, and are these documents shared with stakeholders who could learn from the project and potentially replicate and/or replicate it on a larger scale in the future?

Risks related to the institutional framework and governance for sustainability:

- Do the legal frameworks, policies, governance structures and processes present risks that could threaten the sustainability of the project benefits? When assessing this parameter, also ensure that systems/mechanisms required for accountability, transparency and transfer of technical knowledge are in place.

Environmental risks for sustainability:

- Are there environmental risks that could threaten the sustainability of the achievements of the project?

Conclusions and recommendations

A paragraph setting out the evidence-based conclusions of the mid-term review will be included in the report by the mid-term review team, in the light of the results.

Recommendations will be formulated as succinct proposals for basic interventions which will be specific, measurable, achievable and appropriate. A table of recommendations should be attached to the summary of the report. Please refer to the Guidelines for conducting the mid-term review of UNDP-supported projects funded by GEF for guidance on the table of recommendations.

The mid-term review team will have to make up to 15 recommendations.

Evaluation

The mid-term review team will communicate the evaluations made of the project results and provide a brief description of the associated achievements in the Summary Table of Evaluations and Achievements in the mid-term review report summary.  Refer to annex E for the evaluation matrix. Evaluations of the project strategy and the project as a whole are not required.

## EXPECTED RESULTS OF THE MISSION (DELIVERABLES)

The evaluation team is expected to:

- comply with the ToRs and the terms of the provision agreement binding it to the Sponsor;

- produce a methodological guidance note;

- produce a draft report at the end of the third week :

  - drawing specific conclusions regarding the progress of the project;

  - making detailed and targeted recommendations for better a implementation of project activities not only for the remaining duration of this phase but also that can provide guidance for a possible Phase 2 project or for a new project ;

- produce a final report by the end of the fourth week , taking into account the observations of the steering committee and the project coordination unit;

- complete the UNDP project evaluation forms (Project Evaluation Summaries).

Note:

The Head of Mission international consultant is responsible for writing the report. It will be written in French and submitted to UNDP in electronic format. Five (05) printed copies in “hard copy” will also be sent to UNDP at the end of the mission.

Detailed rules for the implementation

The mission work will be supervised by a joint UNDP/Government committee called Steering Committee responsible for monitoring and validating the evaluation results. It will organize at least two meetings between the committee and the mission:

- a briefing meeting at the start of the mission;

- a debriefing meeting to review the findings and recommendations of the draft report.

The project team will liaise with the team of evaluators to conduct stakeholder interviews and field visits, as well as coordination with the government, etc.

The documentation necessary for the proper conduct of the evaluation will be made available to the mission (electronic version, documents in "hard copies".) It should be noted that before the beginning of the work, the members of the mission will have basic documents (project description, quarterly and annual reports, technical documents…).

TIMING FOR THE EVALUATION

- The mission will last in total  four calendar weeks, i.e. 20 working days from the signature of the contract and according to the following plan:

- Preparation of the mission and briefing meeting: 3 days after the signing of the contract;

- Assessment mission (collection, processing and analysis of data): 10 days;

- Draft evaluation report: 5 days after the evaluation mission

- Final evaluation report incorporating the comments of the evaluation committee: 2 days after receipt of the committee's comments.

REQUIRED SKILLS:

The final evaluation mission will be composed of an international team leader consultant and a national consultant. The consultants may not have participated in the preparation, formulation, and/or implementation of the project (including the drafting of the Project Document) and should not have any conflict of interest in relation to the activities related to the project.

The international head of the mission consultant should have the following profile:

Education:

He/she will also have a post-graduate degree (PHD) or equivalent in the environmental sector, or Engineering Social Sciences or other closely related sectors.

Experience:

- be an expert in sustainable development strategy;

- Solid experience in Natural Resource Management and Integrated Ecosystem Management;

- Have strong experiences in nature-based and value chain-based trade mechanisms and in the synergistic implementation of environmental conventions dealing at the same time with climate change, land degradation and conservation of the environment biodiversity, essential object of the project ;

- proven skills in analysis;

- Have at least 10 years of relevant professional experience and at least 5 years of recent international experience in results-based management evaluations ;

- Experience in working with GEF or GEF project and program evaluations

- At least 10 years of professional experience in the environmental sector; experience of Senegal will be an asset;

- Demonstrated understanding of gender issues; experience in gender-sensitive assessment and analysis ;

• Experience in project Assessment/review in the United Nations system will be an asset

Language:

Fully fluent in French and English

COMPETENCIES

- Technical skills :

- Competence in socio-economic and environmental data  collecting process, processing and analysis;

- Competence in contextual development analysis;

- Good command of GEF-UNDP projects evaluation method;

- Understanding of gender mainstreaming in socio-economic and environmental analyzes

Functional skills:

- Excellent analysis skills;

- Ability to work in a complex environment, with multiple actors and demonstrating sensitivity and diplomacy;

- Rigor in the work, flexibility and proactive;

- Great oral and written communication skills in French;

- Be a team player.

APPLICATION PROCESS

UNDP has a fair and transparent selection process that takes into account the skills and competences of applicants and their financial proposals. Applications from qualified women and members of social minorities are strongly desired.

The selection of consultants will be based on a file including both a technical and a financial offer.

The technical proposal must include:

a)    Letter confirming the expression of interest and availability using the template   provided by UNDP;

b)    CV and Personal History Profile (P11 Form);

c)     Brief description of the method of work/technical proposal indicating the reasons for which the applicant believes he/she is the right person for the assigned mission, and proposed methodology indicating how he/she will address it and carry it out; (2 pages maximum);

d)   Financial proposal indicating the total amount all-inclusive of the contract and any other expense related to trip (plane ticket, daily allowances, etc.), which will be detailed in accordance with the template attached to the Letter of Expressions of Interest. For cases where an applicant works for an organization/firm/institution and provides for the invoicing by his/her employer of the management fees regarding the procedure for making it available to UNDP under a repayable loan agreement (RLA), he shall report it here and ensure that all associated fees are included in the financial proposal submitted to UNDP.

Incomplete applications will not be considered.

Criteria for the technical evaluation are as follows:

- At least 5 years of recent experience at the international level in results-based management evaluation methodologies (20 points);

- Experience in working with GEF or GEF project and program evaluations (10 points) ;

- Brief description of the method of work/technical proposal indicating the reasons for which the applicant considers he/she is the right person for the assigned mission, and proposed methodology indicating how he/she will address it and carry it out; (2 pages maximum) (20 points);

- At least 10 years of professional experience in the environmental sector; experience of Senegal will be an asset (10 points);

- Known understanding of gender issues; experience in gender-sensitive assessment and analysis (10 points).

- Proven skills in analysis (10 points);

- Experience in project assessment/review in the United Nations system (10 points) ;

- Have a postgraduate degree (Ph.D.) in the environment sector, or Engineering Social Sciences or other closely related sectors (10 points) ;

Only applications with a technical score of at least 70 points out of 100 will be selected for financial analysis. Tenders will be assessed using a methodology that combines several assessments - training and experience in similar functions will account for 70 percent and the proposed tariff will account for 30 percent of the total evaluation. The applicant who will obtain the best assessment and who will accept the terms and conditions of the UNDP, will be awarded the contract.

UNDP has a fair and transparent selection process that takes into account the skills and competences of applicants and their financial proposals. Qualified women and members of social minorities are invited to apply.

11. CODE OF ETHICS OF THE EVALUATOR

Evaluation consultants are required to adhere to the highest ethical standards and must sign a code of conduct (see Annex E) for acceptance of the assignment. UNDP evaluations are conducted in accordance with the principles set out in the "UNEG Ethical Guidelines for Evaluations.

Annex 6.2: Evaluation Matrix for the mid-term review

| Project Strategy: To what extent is the project strategy tailored to country priorities, national ownership and the best way of achieving the expected results? |  |  |  |
| --- | --- | --- | --- |
| 1. Questions | Indicators | Sources | Methodology |
| - To what extent have the project activities, as designed, addressed issues related to land and ecosystem management in Senegal in the context of climate change and as identified in country development strategies? | % of issues related to land and ecosystem management identified in Senegal by studies prior to the launch of the project are: -Mentioned in the project document; and -Specifically addressed by one or more project activities | Document Review | - Project document - Researches and analyses on land and ecosystem management carried out by the Government of Senegal (Senegal’s PANA, 2013-2017 SNDES, PSE 2014, (DPPD) (2013-2015 of the MEDD, LOASP, etc.), the UN Agencies (2012-2016 UNDAF, UNDP 2014-2017 Strategic, UNDP environmental and social safeguard policy, Strategic framework for climate change adaptation , etc.) and other development partners. |
|  |  | Direct Observation | - Implementing Agency: Directorate of Water, Forests, Hunting and Soil Conservation (DEFCCS). - Other implementing partners ( ANACIM, DGPRE, CSE, ANA, ANCAR, CDL, ISRA, ANRSA, etc.). |
|  |  | Interviews | - Implementing Agency (Directorate of Waters, Forests, Hunting and Soil conservation (DEFCCS) ; - Other implementing partners (ANACIM, DGPRE, CSE, ANA, ANCAR, CDL, ISRA, ANRSA, etc.); - Steering committee; - Expected beneficiaries (staff of local authorities and associations of farmers, organizations of producers involved in the various value chains, community organizations, communities involved reforestation activities and the fight against bush fires, small-scale agricultural producers, etc.) |
| - To what extent have the objectives of the project addressed the national needs and priorities expressed by the Senegalese government in its elaboration? | % Percentage of needs identified by needs assessments before project start and which are : - Mentioned in the project document ; and -Specifically addressed by one or many activities of the project | Document Review | - Project document - Researches and analyses on the management of lands and ecosystems carried out by the Government of Senegal (Senegal’s PANA, 2013-2017 SNDES, 2014 PSE, (DPPD) (2013-2015 of the MEDD, LOASP, etc.), the UN Agencies(2012-2016 UNDAF, UNDP 2014-2017 Strategic, UNDP environmental and social safeguard policy, Strategic framework for climate change adaptation , etc.) and the other development partners. |
|  |  | Direct Observation | - Implementing agency: Directorate of Water, Forests, Hunting and Soil Conservation (DEFCCS). |
|  |  | Interviews | - Service providers (consultancy/board and supervision) - Expected beneficiaries (local collectivities administrative staff and associations of producers, organizations of producers involved in the various value chains, community organizations communities involved reforestation activities and the fight against bush fires, small-scale agricultural producers, etc.). |
| - To what extent has the theory of change and the approach used to implement the project been adapted to the context? | Number and Type of - questions on the mapping of causes; - questions on the assumptions which underlie the causal chain from the means to the results; - questions on the mixity of the methods used; - questions on the social, cultural, economic and environmental contexts; Impacting the link and management of the lands, the ecosystems and climate changes in the target areas identified by the studies before the launch of the project and which are mentioned in the project document; and percentage of the said questions; As well as the gaps noted between what needed to be done and what was actually done. Number of mitigation strategies of the said questions: social, cultural, security and economic. | Document Review | - Project document - Researches and analyses of the consequences of the poor management of lands and ecosystems on the climate changes conducted by the UN agencies (UNDP Country Programme), the Senegalese government or any other development partner in the Sahel region in general and Senegal in particular |
|  |  | Direct Observation | - Type of behaviors as well as the language level and quality of de communication from the service providers towards the project beneficiaries. |
|  |  | Interviews | - UNDP and Global Environment Fund Technical Advisor - National Steering Committee Experts - Project regional committees’ experts (CR): |
|  |  | Focus groups | - Project Management Unit Experts |
| 1.4. To what extent have the views of those affected by the project decisions, those who could influence the outcome, and those who could contribute to the information or other resources for the process, have been taken into consideration during project elaboration? | Percentage of those affected by the project who have consulted during the elaboration of the project. | Document Review | - Comparison between the project documents and UNDP document on the theory of change (Guidance Note) Paper link: https://undg.org/wp-content/uploads/2017/06/UNDG-UNDAF-Companion-Pieces-7-Theorie - Comparison between the project documents and the Guidance Document for the Integration of the Links between Poverty and Environment in UNDP-UNEP Development Planning Paper link https://www.unpei.org/sites/default/files/publications/primer-FRENCH.pdf - Comparison between the project documents and the UNDP guidance for capacity building Paper link: www.undp.org/.../Capacity_Development_A_UNDP_Primer_Frenc.h. |
|  | % of projects that include the UNDP revised instructions for the integration and the participation | Interviews | - UNDP Technical Advisor - Members pf the project management unit |
|  |  | Document Review | Comparison between the strategies of various projects and the UNDP revised with regard to capacities building, inclusive growth and gender mainstreaming Paper link www.undp.org/content/.../GenderEqualityStrategy2014-17_FR.pdf. |
|  |  | Interviews | Members of the DEFSCC management teams |
| 1.5. To what extent have relevant gender issues been raised during project elaboration? | Percentage of the relevant issues taken into consideration during the elaboration phase of the project: | Document Review | Comparison between the project documents at Annex 9 See Annex 9 of the Instructions of the conduct of the mid-term review of the UNDP-backed projects which are financed by the GEF. |
|  |  | Interviews | Members of the project management unit |

| Progress towards results: To what extent have the project's achievements and expected objectives been achieved so far? |  |  |  |
| --- | --- | --- | --- |
| 2. Questions | Indicators | Sources | Methodology |
| 2.1. To what extent the project objectives set during its elaboration have been clear, practically applicable to help achieve mid-term results in a timely manner? | Number and Percentage of the results that have been achieved at mid-term and according to the time frame for each of the 3 components | Document review | - Follow-up report (monthly, quarterly and annual) from the staff of the implementing agency and (DEFCCS), communication material on the results achieved by the project, Report of the monthly missions, joint mission reports, etc. - Matrix of progress towards the achievement of the results and the Instructions for the conduct of the mid-term review of the UNDP-backed projects and which are financed by the GEF - Launch follow-up tool of GEF |
|  |  | Interviews | Beneficiaries of services (in each target area) |
|  |  |  | - UNDP and GEF Technical Advisor - Members of the team of the project management unit - Service providers |
|  |  | Direct Observations | - Observations of the contractors at work - Observation of tangible achievements on the ground |
| 2.2. With regard to the expected mid-term results what are the factors within and outside the DEFCCS that have contributed to their achievement? | Type and number of positive factors (by component) | Document Review | - Monthly mission’s reports, joint mission report, follow-up report of the UNDP and GEF Technical Advisor, of MEDD and DEFCCS, communication outlet on the results achieved by the Project - Matrix of progress toward the achievement of the results and the Instructions for the conduct of the mid-term review of the UNDP-backed projects and which are financed by GEF - Launch follow-up tool of GEF |
|  |  | Interviews | - Members of the management team of the implementing agency (DEFCCS) - Service providers - Other partners (UN agencies, stakeholders involved in the implementation) |
|  |  | Online questionnaire | - GTS members |
| 2.3 With regard to the unexpected results at mid-term, what are the factors within and beyond the control of the MEDD and the DEFCCS that hindered their achievement? | Type and number of negative factors (by component) | Document review | Monthly reports of missions, joint mission report, follow-up report of the UNDP and GEF Technical Advisor, of MEDD, of the DEFCCS, communication outlet on the results achieved by the Project |
|  |  | Interviews | - CP and MEDD Experts - Project management unit - Service providers - Other partners (UN agencies, stakeholders involved in the implementation) |
| 2.4 To what the extent the mid-term targets of the project are « SMART » (specific, measurable, achievable, Relevant and Time-bound)? | % of targets with « SMART » indicators | Document Review | - Log Framework - Results follow-up forms - Follow-up Evaluation Control Mechanism (DISEC) - Follow-up report (quarterly and annual) - Annual work plan, etc. - The Matrix of progress towards the achievement of results and the Instructions of the conduct of mid-term review of the UNDP-backed projects which are financed by the GEF |
|  |  | Interviews | - Members of the project steering committee - Project manager - Evaluation and Monitoring Expert |
| 2.5. To what extent the implementing agency (DEFCCS) of the project has contributed to its success? | Technical capacity index of DEFCCS in each of the following areas: - Governance/Leadership - Management of organization - Human Resources Management - Financial Management - Project Management - External Relations | Interviews | -Project Partners - Stakeholders involved in the implementations |
|  |  | Survey | The survey questions will be based on adapted version of the tool published on ALNAP website “organization capacity assessment tool (OCAT) “. Link of the paper: http://www.alnap.org/resource/21687 |
|  | Level of competence of the contractors based on the opinions of the: -project managers, and - expected beneficiaries of the project | Interviews | - Project management unit - Project regional committees (CR) - Stakeholders involved in the implementation - Expected beneficiaries |
|  |  | Document Review | Monthly reports of missions, joint missions report, follow-up report of UNDP and GEF Technical Advisor, CP and CRs experts, communication outlet on the results achieved by the Project |
|  |  | Observations | Verification of the correlation between -the adopted practices for the strengthening of the management of lands and ecosystems in the context of climate change and Standard Operational Procedures. |
| 2.6. To what extent has/have the PRGTE manager/s contributed to the project’s mid-term success? | Strengths and weaknesses of the project’s managers who worked in the project since its launch | Interviews | - Project management unit - CR |
|  |  | Focus groups | - Stakeholders involved in the implementation - Service providers |
| 2.7. To what extent the project has developed synergies with other actors in the target areas of the Project in a bid to avoid duplication efforts? - To what extent the participation of other actors in the project target areas has contributed to sustain the progress toward the achievement of mid-term objectives? | Type of strengths and weaknesses of each of the partners | Survey | - Representatives of other UN Agencies in the project implementation - Partner programmes (PADEC, PADEN, PERACOD, etc.) |
|  |  | Interviews | - Implementing Agency (DEFCCS) - PMU - Partner programmes (PADEC, PADEN, PERACOD, etc.) |
| 2.8. What are the unexpected effects (positive and negative) of the interventions of the project at the social, economic and environmental level or among the target groups? | % of the unexpected effects (positive and negative) of the project’s interventions at the social, economic and environmental level among the target groups | Survey | - Representatives of other UN Agencies involved in the project implementation areas - Partner programmes (PADEC, PADEN, PERACOD, etc.) - Service providers |
|  |  | Interviews | - Implementing Agency (AEDD) (including the State authorities) - Partner programmes (PADEC, PADEN, PERACOD, etc.) - Service providers - Project beneficiaries |

| Project Implementation and Adaptive Management: Has the project been implemented efficiently and cost-effectively? Has the project been able to adapt to new circumstances, if any? To what extent have the project's monitoring and evaluation systems, data reporting and project-related communication supported the implementation of the project? |  |  |  |
| --- | --- | --- | --- |
| 3. Questions | Indicators | Sources | Methodology |
| Financial resources management 3. 1 To what extent the funds meant for the implementation of the project at mid-term have been sufficient so as to meet the needs of the target groups? | Number and type of activities whose expected results have been achieved without any budgetary adjustment since the launch of the project | Document Review | Financial reports of the MEDD, of DEFCCS, Missions’ reports, follow-up reports |
|  |  | Interviews | - CP and MEDD Experts - DEFCCS Experts’ committee - Project management unit |
|  |  | Interviews or Focus Group | Expected beneficiaries of the project: Administration, community-based organizations, farmers, etc. |
| 3.2 To what extent the funds meant for the mid-term implementation of the project have been released according to the deadline | Number of quarters during which the resources (for each of the objectives) have been released according to the deadline | Document Review | Financial reports) and those of the project management unit, DEFCCS, Missions report, follow-up report |
|  |  | Interviews | - CP and MEDD experts - PMU’s Experts |
|  |  | Meetings or Focus Group | Beneficiaries of the project: Administration, community-based organizations, farmers, etc. |
| 3.3. What steps have been taken during project elaboration and implementation to ensure that resources are less costly compared to existing alternatives? | Strategies put in place when elaborating and implementing projects to keep costs of activities fairly competitive | Meetings | UGP, experts du CP et du MEDD |
|  |  | Document Review | - Financial Reports of Technical Experts (CET) and of the project management unit - Financial reports available to other agencies /partners |
| Human resources management 3.4. To what extent has mid-term human resources management been the less expensive compared to existing alternatives? | Proportion between the Project’s staff unit costs and the consultants And the Unit costs of the staff working in similar projects in the same areas | Document Review | - Financial reports of Technical Experts (CET) of the project management unit - Financial reports available to other agencies/partners |
|  |  | Interviews | - Project management unit Experts |
| - To what extent the number and the skills of the staff initially available for the management and implementation of the project (since October 2015) have been sufficient to meet the needs of the beneficiaries at the mid-term? | Percentage of the tasks related to the project included in the ToRs of the staff of the Experts of the project management unit, the CP experts (MEDD, UNDP, GEF etc.) that have been reached during the implementation of the project. | Document Review | ToRs of the staff of Technical Experts (CET) of the project management unit and of CP experts (MEDD, UNDP and GEF) |
|  |  | Interviews | - Technical Experts (CET) of the project management unit - Experts of CNP, MEDD, and UNDP and UN Environment through IPE-Africa |
|  | Percentage of the project managers, Technical Experts (GEF) and the AEDD management unit, CNP, MEDD, UNDP and UN Environment through IPE-Africa who acknowledge a limit in the number and the skills available to the management and implementation of the project. Type of limits in terms of identified skills | Interviews | - CNP and MEDD Experts - Technical Experts Committee (CET) of the AEDD - AEDD management unit - Contractors/ service providers (consultants and others) |
| - To which extent have the skills of the contractors/service providers been supported and developed by the project at mid-term? | Changes at the level of the technical skills in taking into consideration the poverty environment nexus in the policies, the budget and programmes following the trainings offered within the project | Document Review | Assessment of the training offered to the beneficiaries |
|  |  | Interviews | - Beneficiaries (administration, etc.) - CNP and MEDD Experts - Technical Experts Committees (CET) of the AEDD - AEDD management unit - Service providers |
|  |  | Direct observation | Contractors at work |
| Management of properties and equipment 3.8. To what the extent has the management of the equipment of the project proved less costly compared to the existing alternatives? | Ration between the unit costs of the Project activities And the Unit costs of the similar activities conducted within other projects in the same target areas | Document Review | - Financial reports of the project management unit and the DEFCCS - Financial reports available to other agencies/partners |
| Communication management 3.9. To what extent has the mid-term communication of the project been efficient? 3.10. To what extent have adequate communication means been put in place or were being put in place to inform the public about the progress made within the project and its expected impact? 3.11. To what extent have the adequate means of communication been put in place to facilitate ownership and the implementation of the knowledge required for the strengthening of the management of lands and ecosystems in the context of climate change. | - % of internal communication measures used within the implementation of the project with less cost - % of communication tools that have been used for the awareness as part of the implementation of the project - % of development communication tools used in the framework of the transfer of knowledge necessary enable smooth skill acquisition of the beneficiaries concerning the strengthening of the management of lands and ecosystems in the context of climate change | Document Review | - Follow-up reports (monthly, quarterly and annual) of the staff of the implementing agency and (DEFCCS), communication outlet on the results achieved by the Project , Monthly missions report, joint mission reports, etc. |
|  |  | Interviews | - CP - PMU - Beneficiaries (administrations and territorial collectivities, beneficiary community organizations, association of small-scale producers involved in the various existing value chains etc.) |
|  |  | Direct observations | - Available communication tools |

| Evaluation criteria 5 : SUSTAINABILITY Sustainability: to what extent does financial, institutional, socio-economic and/or environmental risk exist for the long-term sustainability of the results of the project |  |  |  |
| --- | --- | --- | --- |
| 5. Questions | Indicators | Sources | Methodology |
| 5.1. To what extent the risks defined in the Project Document, the Annual Project Review/PIR and the ATLAS module risk management are the most important and the risk evaluations more appropriate? | % of risks defined in the project document, the annual project review/PIR and risk management module that are more important and most appropriate | Document Review | - Project document - Atlas Module Risk Management - Report of the project final review |
|  |  | Interviews | - CP - PMU - DEFCCS Expert |
| 5.2. How likely is the absence of financial and economic resources at the end of the support from GEF? | % of possible sources of resources that could be available at the end of the support from GEF | Document Review | - Project document - Atlas module risks management - Monitoring and Evaluation tool for adaptation (AMAT) of the Funds for the LDCs - Follow-up method of the climate impact of investments (MRV) applied to agricultural and forestry projects of the National Development Banks. http://www.fao.org/fileadmin/templates/ex_act/doc/M%C3%A9thode_de_suivi_de_l_impac |
|  |  | Interviews | - CP - PMU - DEFCCS expert |
| 5.3 Do social, political, institutional or environmental risks exist and which are likely to threaten the sustainability of the achievements of the project? | - of social, political, institutional or environmental risks likely to threaten to sustainability of the achievements of the project -% of mitigation measures available to reduce the effects of those probable risks | Document Review | - Reports of other climate change related projects active in the target areas of the project - Integration of environment and climate change for poverty reduction and sustainable development - Handbook for the strengthening of the planning and budgeting process https://www.unpei.org/sites/default/files/publications/UNDP_UNEP_%20PEI_Handbook_French_pdf.low%20resolution.%20pdf.pdf - Adapt agriculture to climate change http://www.fao.org/fileadmin/templates/tci/pdf/backgroundnotes/Webposting_FR.pdf - Taking into consideration climate change adaptation in the development cooperation (Orientation Document) http://www.oecd.org/fr/environnement/cc/42551810.pdf |
|  |  | Interviews or Focus Group | - Beneficiaries (administration and territorial collectivities, community organizations, associations of farmers, etc.) |
|  |  | Direct observations | - Beneficiaries (administration and territorial collectivities, community organizations, association of farmers, etc.) |

Annex 6.3: Sample of questionnaire or guidance concerning data collection interviews

Annex 6.3.1: Interview guide for PRGTE partners

Introduction

Name and Given name:

Name and area of the service:

Function:

Phone number and e-mail address:

Focus area:

Establishment of an effective climate change information platform and adaptation options

Reduction of the risks of climate change in target lands and ecosystems with adaptive restoration measures

Support for knowledge and information acquisition mechanisms

Context

Q 1.1. How long have you collaborated with PRGTE?

Q 1.2. What kind of partnership have you had with PRGTE?

Q.1.3. What was the level of involvement of each partner in the relation?

Progress achieved towards the achievement of results

Coordination

Q2.1.1 How good was the coordination within the partnership?

Q2.1.2 How good was the communication within partnership?

Q2.1.3 How good were the management and the facilitation?

Q2.1.4 How good was the quality of the relations between the partners?

Q2.1.5 How good were the Monitoring and Evaluation?

Administrative organization

Q2.2.1 Do you know the administrative structure of the project?

Q2.2.2 Were the schedules of the meetings established by mutual agreement?

Q2.2.3 Was the schedule of the meeting published in advance for all stakeholders?

Q2.2.4 Were the meetings, announced earlier, held according to the schedule established by agreement?

Q2.2.5 Were minutes of the meetings written and disseminated rapidly?

Q2.2.6 Do partners contribute to the interim reports and to the final report?

Project implementation and responsive management

Q.3.1 Were the time and resources of each partner mobilized in conformity with the working plan established by mutual agreement?

Q3.2 As a partner of the project was you informed about the budget?

Q3.3 What were the financial implications of that partner and to what extent the effects were positive/negative for mid-term achievements of the project results?

Q3.3 How has PRGTE built the capacities of the implementing partners in the strengthening of the management of the lands and ecosystems?

Gender and DHS mainstreaming

Q5.1. What strategies have been developed by PRGTE project in the framework of the partnership with the view to mainstream gender and DHS in the project?

Q5.2. What issues related to Women and youth empowerment have been raised during the elaboration, planning and monitoring and evaluation phases of PRGTE?

Q5.3. How has the PRGTE helped Women become change agents?

Project sustainability

Q6.1- To what extent are the risks defined in the Project Document, the project annual review/PIR and the Atlas module on risk management more important and the assessment of those risks more appropriate?

Q6.2- How likely is the probably of lack of available financial resources at the end of the support of GEF?

Q6.3- Are there any social, political, institutional or environmental risks likely to threaten the sustainability of the project?

Annex 6.3.2 Questionnaire for the interviews with the beneficiaries of PRGTE

Name and Given name:

Name and area of the service:

Function:

Phone number and e-mail address:

Focus area:

Context

Q. 1. How have you been aware of the PRGTE?

Q 2. What kind of service have you received from the project?

Training

IGA

Material support/seed and equipment

Q3. If you have been trained

Q3.1 Towards which area of service provision was the training geared?

Q 3.1. How have you been selected to be a beneficiary of that project’s service?

Q3.2. Which factors have influenced the condition and quality of the service offered?

Q.3.3. What do you think about the following aspects of the training?

The objectives of the training were clear and well-defined for all the learners

1. Do not agree at all              2. Do not agree                3. Agree               4. Do agree

Why?

The audience has been clearly identified

1. Do not agree at all              2. Do not agree                3. Agree               4. Do agree

Why?

The work plan has been developed by mutual agreement between the trainer and trainees

1. Do not agree at all              2. Do not agree                3. Agree               4. Do agree

Why?

The work plan has been respected

1. Do not agree at all              2. Do not agree                3. Agree               4. Do agree

Why?

The communication was clear (were the explanations of the trainer easy to understand?

1. Do not agree at all              2. Do not agree                3. Agree               4. Do agree

Why?

Were the modules understandable?

1. Do not agree at all              2. Do not agree                3. Agree               4. Do agree

Why?

The module was innovative in its content.

1. Do not agree at all              2. Do not agree                3. Agree               4. Do agree

Why?

The module was innovative in its form.

Why?

The module’s summary (virtual valley) was articulated in a logical and well-structured manner

1. Do not agree at all              2. Do not agree                3. Agree               4. Do agree

Why?

Was the duration of the training sufficient?

1. Do not agree at all              2. Do not agree                3. Agree               4. Do agree

Why?

Was the facilitator competent?

1. Do not agree at all              2. Do not agree                3. Agree               4. Do agree

Q3.4 Have you been given technical sheets during the training? If so what can tell about those documents?

The document was reader friendly

1. Do not agree at all              2. Do not agree                3. Agree               4. Do agree

Why?

The content of the document was clear and concise

1. Do not agree at all              2. Do not agree                3. Agree               4. Do agree

Why?

It is easy to understand

1. Do not agree at all              2. Do not agree                3. Agree               4. Do agree

Why?

The local language version is available

1. Do not agree at all              2. Do not agree                3. Agree               4. Do agree

Why?

Q3.5 Have your skills in the area of the link poverty-environment improved thanks to this training?

Q3.6 Have you put into practice the knowledge acquired during the training?

Q3.7 Do you use these knowledge in your work?

Q3.8 Have you watched documentary films broadcast by PRGTE?

Q.3.8.1 If yes

Q.3.8.2 Through which media?

Radio?                                          Television?                     Print media?       Was the film shown to us?

Q.3.8.3 If so which film documentary was it?

Q.3.8.4 Can you say a few words about the content of the film? What was its main topic?

Q.3.7.5 What have you learnt about the management of the lands and climate change in that film?

Q.3.7.6 Have the information you’ve retained, influenced the way you appreciate and put into practice the nexus between poverty and environment?

If yes how?

Q4.  Have you received an IGA?

Q 4.1. What was that IGA about?

Q 4.2. How have you been selected to be a beneficiary of that support of the project?

Q4.3. What are the reasons that motivated your choice about this IGA?

Q.4.5. Do you have the required skills for the management of the IGA?

Otherwise how has PRGTE help you acquire the necessary skills for the management of the PRGTE?

Q.4.6. Have the incomes generated by IGAs help you improve the economic situation and that of your household? If yes how?

Q6. In case you’ve received equipment

Q 6.1. What was this equipment or material/seeds meant for?

Q 6.2. How have you been selected to be a beneficiary of this project?

Q6.3. What are the factors which influenced the nature and quality of PRGTE?

Q.6.4 How has the use of the material/seeds or equipment influenced the management of the lands and ecosystems?

Q.6.5. What is the impact of the use of such material/seeds or equipment on your production?

Q.6.6 Has it helped you improve your economic situation and that of your household? If yes, how?

Q7- Gender mainstreaming and the inclusion of DHS in the activities of the project IPE-Mali

Q7.1. How has PRGTE helped ensure gender equality between men and women and the promotion of human rights? (Women empowerment and the promotion of the enforcement of their rights?

Q7.2. Has the empowerment of youth and women been taken into consideration in the elaboration, planning and monitoring and evaluation of PRGTE?

Q7.3. How has PRGTE helped Women become agents of change?

Q7.4. How has PRGTE enabled women manage the development process key to their existence?

Q7.5. How has PRGTE help men and boys take part in the defense of gender equality and the adoption of measures to that end?

Q7.7. Has PRGTE benefited men and women in an equal manner?

Why?

Q7.8. During which stage of the PRGTE were the women involved in the decision-making process?

Annex 6.3.3: Questionnaire for the interviews with the service providers/contractors

Name and Given Name:

Name and area of the service:

Function: Consultant

Phone number and e-mail address:

Focus area:

Establishment of an information platform on climate change and effective adaptation options

Climate change reduction risks in the target lands and ecosystems with restoration measures for adaptation

Support for the knowledge and information acquisition mechanisms

Context

Q. 1a. To what extent have you known PRGTE?

Q 1.b. For how long have you worked in PRGTE?

Q 1.c. What type of service have you provided to the project?

Q 1.e. Who were the beneficiaries?

Q 1.f. How have you identified the beneficiaries?

Q 1.e. What was the quality of the beneficiaries? their backgrounds?

Men:

Women:

Q2. What the external/internal factors specific to this center which influenced the nature and quality of the services?

Q.3. With regard to your first day of work within the project, have important changes occurred with the management or functioning during the time that followed?

Q4 a. Have you undergone a training financed by the PRGTE for capacity building?

Q4 b. If yes, describe the training? -Positive aspects: -Negative aspects:

Q4 .c With regard to the training you underwent, would you please answer the following questions: What the duration of the training long enough? Were the modules understandable? Was the facilitator competent?

Q4. d To what extent have your skills improved thanks to the training?

Q5. Efficacy

Within the framework of your services in the project

Q.5 a How was the work organized?

Within the framework of capacity building

•	Were the objectives of the module clear and well-defined for all the partners?

•	Did the module respond to a need for the learners?

•	Was the working plan respected?

•	Were the modules innovative in terms of content?

•	Were the modules innovative in terms of form?

•	Was the summary of the modules displayed in a logical and well-structured manner?

•	Was the activity sheet a good guidance for the elaboration of pedagogical scenarios?

Q.6 b how did the project ensure the follow-up?

Q.6 c how did you assess the results of your work?

Q. 6d.  what were the strengths of that organization?

Q. 6e. what were the weaknesses of that organization?

Q7. Capacity

To what extent the project had the capacity to meet adequately the needs of the beneficiaries?

Q. 8 a. According to you, what are the needs in your focus area which have been covered?

Q. 8 b.  What are the needs in your focus area which have not been covered?

Q.9, To what extent have you used the benchmark standards to ensure the quality of your services is gender-sensitive?

Q.10. What were the services which your clients/beneficiaries seemed to appreciate the most?

Q.11. To what extent have your services been integrated with other services/projects? Which ones?

Efficiency

Q. 12. (….) To what extent the funds meant for the implementation of the activities were used efficiently?

Q. 13. To what extent the funds meant for the implementation of your activities were unleashed according to the set schedule?

Q. 14 What are the challenges you met in the past but which you and your colleagues managed to overcome? Please give more details

Q.15. What are the challenges you and your colleagues are facing until now? Please give more details

Q. 16 What unintended consequences (real surprises), POSITIVE and/or NEGATIVE have you noticed with regard to the services offered to the beneficiaries?

Q.17. To what extent have innovate and/or alternative execution strategies been explored and used?

Annex 6.3.4 Interview guide for the Focus groups

Q.1 Could you tell me a few words about yourself?

Q.2 a. I was told that there had been a few activities of PRGTE within the commune and which concerned the strengthening of the management of lands and climate change. Have you heard about it?

Q. 2b. What was it about?

In case there isn’t any answer, ask participants who had never heard about it to talk about:

- The restoration of the mangrove, reforestation, dunes’ fixation, micro irrigation by solar kit, production of improved seeds, dissemination weather information, construction of levees, etc.

- Training for climate changes adaptation, IGAs management, etc.

-Other:

Q. 2c. Have you benefited from the support (equipment, material/seeds) of the project?

Q.2.d. If you have benefited from the project, what type of support was it (equipment, material/seeds)?

Q2.c how have you been selected to be a beneficiary of this service of the project?

Q. 3. Do you remember how the offer was made by the project? How was it organized?

Q.4. How has that support (equipment, material/seeds) helped improve your economic situation and that of your household?

Q.5. In case you have undergone trainings

- where did it take place?

- what was the content of the trainings/restitutions?

- have you been given course materials?

- what were those course materials made up of?

- how long has the training/restitution lasted?

- were the explanations of the trainer translated in local language?

Q.6 Is there anything that you have particularly liked about this service?

Q. 7. What do you think about the following aspects of the trainings/restitutions?

•	Availability (was the trainer always present?)

•	Accessibility of training website (the access was it complicated or expensive?)

•	Adaptability (did the trainer speak your language?)

•	Confidentiality (did you trust the trainer?)

•	Clarity of communication (was the trainer easy to understand?)

Were the course materials easily accessible (was it easy to understand?)

Q.8    Have you or your community put into practice the courses?

How?

Q.9     How has the training received impacted the way you appreciate the management of lands, ecosystems and climate change?

Q.10 How do you think the services of the project can be improved?

Q.11 What are the other services in the area of the management of lands and ecosystems that you would like to be provided with?

Q.11 Do you have anything else to say about this project delivery?

Annex 6.4: Mission itinerary for the mid-term review

| Dates | Activities | Target Actors |
| --- | --- | --- |
| Wednesday 28th/11/ 2018 | Dakar-Louga Trip | Head of mission |
|  | Meeting with IREFDRDR Staff Louga | Cdt BADJI and BAMPOKY |
|  | Meeting with Authority Louga | Governor/IREF/DRDR |
|  | Visit Thiès weather station | Weather service |
| Thursday 29th/11/2018 | Visit site 1 DRDR Multiplication of seeds, CAURIE Agency MF of Louga Visit of IREF’s site 2 Visit of the hedgerows, windbreak and drip irrigation Visit of IREF’s site 3 Visit of hedgerows, windbreak and drip irrigation Interviews with farmers (discussion with the maire and all the farmers) | DRDR Louga, IREF Louga, CAURIE MF Agency Louga |
| Friday 30th/11/2018 | Louga-Thiès Trip |  |
|  | Meetings with IREF DRDR TH | IREF, DRDR, Governor House |
|  | Meeting with authority Thiès : governor of Thiès |  |
|  | Visit site 1 SMA Thiès military barrack Visit CAURIE MFe MF meeting with Director of partnerships Visit site 2 DRDR, Thiès Visit site 3 IREF Meeting with farmers | DRDR, IREF |
| Saturday 01st/12/ 2018 | Visit site 1 Meeting with GPF de Mboro | Responsible persons and Chairperson of GPF Mboro |
|  | Meeting with GPF Mboro | CAURIE MFe Micro Finance/GPF |
|  | Thiès Dakar Trip |  |
| Sunday 2nd/12/2018 | Dakar Ziguinchor Trip |  |
|  | Synthesis work with the consultants |  |
| Monday 3rd/12/ 2018 | Visit Authority ZG | Governor/IREF/DRDR |
|  | Visit of DRDR’s site 1 Visit ANCAR/BMC’s site 2 Visit of IREF’s site 3 (mangrove,) Visit of ANA’s site 4 | DRDR ANCAR/BMC IREF ANA |
|  | Overnight stay in Ziguinchor |  |
| Tuesday 4th/12/2018 | Ziguinchor Kolda Trip |  |
|  | Visit to ZG’s Governor | Governor ZG |
|  | Visit of DRDR’s site 1 Visit of IREF’s site 1 Soukou and committees committed to the fight against bush fires Visit of 3 IREF’s Palmeraie | DRDR IREF |
|  | Overnight stay in Kolda |  |
| Wednesday 05th /12/2018 | Kolda Ziguinchor Trip Plane trip back to Dakar |  |
| Thursday 06/12/2018 | Restitution at UNDP |  |

Annex 6.5: List of the persons interviewed

|  | Given name and Name | Function | Email | Date | Place |
| --- | --- | --- | --- | --- | --- |
| UNDP/GEF | Henry Rene DIOUF | UNDP-GEF Regional Technical Advisor | henry.rene.diouf@undp.org | 26&27 Nov.18 | Dakar |
| UNDP/GEF | Clotilde GOEMAN | UNDP-GEF Regional Technical Advisor | clotilde.goeman@undp.org | 26&27 Nov.18 | Dakar |
| UNDP | Ndeye Fatou Diaw GUENE | Climate Change Specialist and Team Leader of Environment Unit | ndeye.fatou.diaw.guene@undp.org | 26&27 Nov.18. 6 Dec. &18 | Dakar |
| PRGTE | Colonel Oumar DIAW | Coordinator PRGTE |  | 26&27 Nov.18 6 Dec. &18 | Dakar |
| PRGTE | Colonel Cheikh NDIAYE | Monitoring-Evaluation Expert |  | 26&27 Nov.18 6 Dec. &18 | Dakar |
| PRGTE | Papa Matar NDIAYE | Administrative and Financial Assistant |  | 28 Nov. 6 Dec. &18 | Dakar |
| PRGTE/VNU | Mamadou Lamine COLY | VNU-Ziguinchor | erfdlorg@live.fr | Monday 3 Dec. | Ziguinchor |
| PRGTE/VNU | Mrs. Salimata DIATTA | VNU-Kolda | salyarendor@gmail.com | Tuesday 4 Dec. | Kolda |
| Validation Methodological note | - Mamadou N’GOM - Adama DIOP - Mamadou DIAWARA - Souleymane DIOP - Ousseynou NDIAYE - Baba BA - Dr. Ma Anta MBOW - Staff PRGTE et UNDP-GEF | ANA DGPPE/MEFP DCFA/DGB/MEFP CSE | mamadoungom599@gmail.com adama_diop64@yahoo.fr diawaramd@hotmail.com sdiop@cse.sn ousseynou.ndiaye.@mha.gouv .sn babasba64@gmail.com maanta1810@gmail.com | 27 Nov.18 | Dakar |
| Governance | Alioune Badara MBENGUE, | Governor of the region of LOUGA | golflouga@yahoo.fr | 28 Nov. | Joli tableau |
|  | Cyprien BALLO | Deputy Governor of Kolda, responsible of administrative affairs |  | 4 Dec. |  |
|  | Guedj DIOUF | Governor of the region of Ziguinchor | mbamboulane1@yahoo.fr | Wed. 5 Dec. 18 |  |
| IREF-Louga | Commander Badji | Inspector | abeune69@yahoo.fr | 28 Nov. |  |
| IREF-Louga | Major Aboulouye BODIAN | Head of Brigade | bodianabdoulaye9@gmail.com | 28 Nov. |  |
| IREF-Louga | Sergeant Ndiack DIOP | Marshalling yard of Sague/Leona |  | 28 Nov. |  |
| IREF-Thies | Lt Colonel Birame DIENG | Inspector IREF |  | Friday 30 Nov. | Thies |
| IREF-Thies | Commander Ndeury DIAW | Deputy inspector and focal point of PRGTE, since March 2018 | ndeury@hotmail.com | 30 Nov. | Thiès |
| IREF-Thiès | Sergeant Nfaly DJIBA Lieutenant Amy DIAGNE Lieutenant Awa FALL Captain Youssoupha SAGNA | Head of Brigade of Meouane Sub-Sector Pambal-Meouane Deputy Head of Sector Tivaouane Head of Forestry sector Tivaouane |  | 30 Nov. | Thiès- Tivaouane |
| SDDR Thiès | Cheikh Tidiane BA | Person in charge |  | 30 Nov. | Thiès |
| DRDR | Jean Paul BAMPOKY And his staff Mouhamadou M. MBAYE Madoune DIAGNE, DIAGNE Salla and Abdourahmane TAMB, and Focal Point PRGTE | Director | drdrlouga@yahoo.fr |  |  |
| CAURIE MFe MF | Daouda DIA | Chief of Agency | daouda.dia@CAURIE MFe-mf.info |  | 29 Nov. |
| Farmer/ Region of Louga | Serigne CHEIKH |  |  |  | 29 Nov. |
| Farmer/ Region of Louga | Seydou DIOP& Sadibou DIOP | Living fence /break wind Council | Sague Sagnioro /Leona |  | Comments on wells |
| Farmer/ Region of Louga | Sadibou & Abdoulaye KA | Living fence /break wind Council |  |  | Fulani Village opposite OCEAN |
| Farmer/ Region of Louga | Around DIA / Fatou SOW farm | Living fence /break wind and dunes fixation Council |  | 29 Nov. |  |
| City Hall of Potou | Mamadou BA | Mayor |  | 29 Nov. |  |
| Female Farmers / Ndialegne village in the Region of Louga | # Coumbel SOW and her association involving over 30 persons (Women, men and youths in a similar proportion | Living fence /break wind and solar kit Council And expecting micro-financing for the Women | Ndialegne village | 29 Nov. |  |
| ANACIM | Diabel NDIAYE | Agro-weather engineer: | diabel.ndiaye@anacim.sn | 26 Nov. |  |
| ANACIM Louga | Fadel NGOM | Person in charge |  | 29 Nov. |  |
| PasaLouMaKaf - Louga | Malick GNINGUE |  |  | 28 Nov. |  |
| ANCAR | Khaly SYLLA | Water and Forestry engineer, Head of the M&E division (retired) | khalysylla@yahoo.fr | 26 Nov. |  |
| ANA | Mamadou NGOM: | focal point ANA, Head of training and dissemination division | mamadoungom599@gmail.com | 26 Nov. |  |
| Female Producer /Eggplant farm | Mariama et Oumar SOW | Living fence /break wind Solar panel applicant |  | 30 Nov. |  |
| Farmer | Saliou LO | Living fence /break wind / Citrus |  | 30 Nov. |  |
| Farmer ; Taiba NDIAYE/Darou Khoudoss | Ngagne GUEYE Chief of village | Break wind fence/ |  | 30 Nov. |  |
| Seed producers of the Village of Thiale | Demba Fall NDIAYE and 5 other seed producers | Peanut and pea seed producers |  | 30 Nov. |  |
| DRDR Thiès | Mamadou GUEYE | Director | Phone interview | 1st Dec. |  |
| IREF Ziguinchor | Captain Mamadou GOUDIABY |  | mamadougoudiaby@yahoo.fr | Monday 03rd Dec. |  |
| DRDR | Casimir SAMBOU | DRDR | casimiradrien@yahoo.fr | Monday 3rd Dec. |  |
| DRDR | Boubacar BADJI | DRDR PF PRGTE | B_badji@yahoo.fr | 3rd Dec.18 |  |
| IREF | Modou Fall DIALLO | IREF PF PRGTE | modfall85@gmail.com | 3rd Dec.18 |  |
| IREF/Bignona | Moussa DIEME | IREF/B | diememoussa@yahoo.fr | 3rd Dec.18 |  |
| National Aquaculture Agence (ANA | Moussa DIEDHIOU | Person in charge | Diedhiou367@gmail.com | 3rd Dec.18 |  |
| ANA | Yoro MANGA | LEADER ANA ZG |  | 3rd Dec.18 |  |
| ANCAR | Ibrahima BADIANE | BMC Director | ancarbmc@gmail.com | 3rd Dec.18 |  |
| ANCAR | Mbar SECK | Focal Point PRGTE | Mbseck77@gmail.com | 3rd Dec.18 |  |
| IA | Mamadou GOUDIABY | IA | mgoudja@gmail.com | 5th Dec.18 |  |
| IA PF PRGTE | Samba SARR | IA PF PRGTE | Bathieis2@gmail.com |  |  |
| Aquaculture/ Tobor | Youlayi Association /Chairperson Mrs. MANGA, Mariama DIEDHIOU | Aquaculture /Oyster farming | Some 25 Women present | 3th Dec.18 |  |
| Djilacoune | Karembenor association, Fanta Goudiaby | Aquaculture /Oyster farming | Some 15 Women present | 3th Dec.18 |  |
| Coubalan /Moussa Sane | Moussa Sane Aliou Sane | Peanut seeds producers |  | 3rd Dec.18 |  |
| Tao /Nouha SANE | Nouha SANE | Rice seed producers |  | 3rd Dec.18 |  |
| Coubalan /Site Mangrove reforestation | Coubalan /Site Mangrove reforestation | Observation |  | 3rd Dec.18 |  |
| Soukou /Commune Sare Bidji / Department of Kolda | Abdoulaye CISSE: facilitator/ SoS Environnement Mamadou BA (Sare Bilali) Aissata Mballo Ibrahima Diao | Restoration of Soukou forest (Reforestation, protection against bush fires, dykes and levees.) | Some thirty participants including a dozen from Women | Tuesday 4 Dec. |  |
| Dioufana/ Dioulacolon | Translation support : Seydou BALDE: 77 5957392 Moussa MBALLO 77 1985994 Aissatou Mballo / Mamadou BALDE | Seed Production: 2 flagship activities (seed and equipment), 2 speculations (4ha maize and 6a rice) with 30 beneficiary producers. | Some thirty participants including a dozen from Women | Tuesday 4 Dec. |  |

Annex 6.6: List of documents consulted

- Ababacar BOYE and Baba SENE (2017).  “Communication plan: draft report” PRGTE.

- IREF KOLDA and PRGTE “2018 Temporary final report of activities (protocol IREF KOLDA /PRGTE”.

- IREF ZIGUINCHOR and PRGTE (2018) “Temporary final report of activities of the project for strengthening of the management of lands and ecosystems of the Niayes and Casamance (PRGTE)”.

- PRGTE (2016). “Annual activity report”.

- PRGTE (2017). “Annual activity report”.

- PRGTE (2015). “PRGTE Project Document”.

- UNDP (2009) “Instructions to conduct final evaluation of the projects of GEF and which are supported by UNDP “.

- UNDP (2009). “Guide for planning, monitoring and evaluation based on the results of development”.

- Burundian Association for the protection of Birds and Birdlife international (2012).  “Analysis of the link between biodiversity conservation and climate change adaptation”

- FAO SENEGAL (2013). “FAO response programme against the food crisis and nutritional crisis 2013”

- GIZ (2015) “Monitor and evaluate high-level adaptation to climate change: comparative analysis of ten systems”.

- UNDP (2011) “United Nations Development Assistance Framework Plan (UNDAF) Senegal 2012-2016”.

- UNDP (2011). “United Nations Development Assistance Framework Plan (UNDAF) Senegal 2012-2016 “.

- UNDP (2012). “Integrating climate change into national development and country programming processes of the United Nations”.

- Directorate General of Niger Rural Management (2015) “Small Irrigation Strategy in Niger (SPIN)”.

- UNDP (2012). « Guide of operating procedures».

- DRDR of Kolda (2018) “Report of mission for the selection of producers of seed multipliers adapted to the conditions of the environment and restitution (rice and maize) under the DRDR (Kolda) -PRGTE protocol”.

- IREF Thiès (2018). “First semester report 2018”.

- IREF of Kolda (2018). “First semester report 2018”.

- IREF of Sedhiou (2018). “First semester report 2018”.

- IREF of Ziguinchor (2018). “First semester report 2018”.

- IREF of Louga (2018). “First semester report 2018”.

- DRDR of Ziguinchor (2018). “Report of mission on the training of seed producers (rice and peanut) under the PRGTE/DRDR protocol”.

- PRGTE-IREF of Ziguinchor (2016). “Protocol of agreement between PRGTE and IREF of Ziguinchor”.

- PRGTE-IREF of Kolda (2016). “Protocol of agreement between PRGTE and IREF of Kolda“.

- PRGTE-IREF of Sedhiou (2016). “Protocol of agreement between PRGTE and IREF of Sedhiou”.

- PRGTE-IREF of Thiès (2016). “Protocol of agreement between and IREF of Sedhiou”.

- PRGTE-IREF of Louga (2016).  “Protocol of agreement between PRGTE and IREF of Louga”.

- PRGTE-IREF de Louga (2016). “Protocol of agreement between PRGTE and IREF of Louga”.

- PRGTE-IREF of Louga (2016). “Protocol of agreement between le PRGTE and IREF of Louga”.

- PRGTE-IREF of Louga (2016). “Protocol of agreement between PRGTE and IREF of Louga”.

- PRGTE-IREF of Louga (2016). “Protocol of agreement between PRGTE and IREF of Louga”.

- PRGTE-IREF of Louga (2016). “Protocol of agreement between PRGTE and IREF of Louga”.

- PRGTE-ANCAR (2017). “Protocol of agreement between PRGTE and ANCAR”

- PRGTE-ANA (2016). “Protocol of agreement between PRGTE and ANA”.

- PRGTE-ANACIM (2016). “Protocol of agreement between PRGTE and ANCIM”.

- PRGTE-DGPRE-DEFCCS (2016). “Protocol of agreement between PRGTE, DGPRE and DEFFCS”.

- PRGTE and ISRA/CNRF (2016). “Protocol of agreement between PRGTE and ISRA/CNRF”.

- IREF of Ziguinchor (2016). “PRGTE-IREF report of activities”

- PRGTE (2016). “Annual work plan (PTA)”.

- PRGTE (2017). “Annual work plan (PTA)”.

- PRGTE (2017). “Annual work plan (PTA)”.

- DRDR-SDH and PRGTE (2016). “Summary report of the follow-up of lands dedicated to rice seed production”.

- PRGTE and DRDR Sedhiou (2016). “Terms of Reference of the workshop on good agricultural techniques”.

- Aminata Diallo BA (2016). “Final report of the study on the participatory identification of the needs of users of information on the climate of the Niayes and Casamance ecosystems (2017). “Participatory diagnosis and vulnerability analysis in the Niayes area: identification of adapted / resilient forest species and appropriate agroforestry technologies for better protection of market garden basins”.

- PRGTE (2017). “HACT Audit report”.

- Grant Thornton (2018). “Regular monitoring report”

Other documents

Orders

- Order establishing, organizing and defining the operating a regional monitoring committee for the Project to Strengthen the Management of the Lands and Ecosystems of Niayes and Casamance in the context of climate change in the region of Sedhiou

- Order establishing, organizing and defining the operating a regional monitoring committee for the Project to Strengthen the Management of the Lands and Ecosystems of Niayes and Casamance in the context of climate change in the region of Thiès

- Order establishing, organizing and defining the operating a regional monitoring committee for the Project to Strengthen the Management of the Lands and Ecosystems of Niayes and Casamance in the context of climate change in the region of Louga

- Order establishing, organizing and defining the operating a regional monitoring committee for the Project to Strengthen the Management of the Lands and Ecosystems of Niayes and Casamance in the context of climate change in the region of Ziguinchor

- Order establishing, organizing and defining the operating a regional monitoring committee for the Project to Strengthen the Management of the Lands and Ecosystems of Niayes and Casamance in the context of climate change in the region of Kolda

Financial documents

- 2016, 2017 and 2018 THIRD PARTIES BALANCE SHEET

- 2016, 2017 and 2018 DISBURSEMENT

- PRGTE STAFF REMUNERATION 2016, 2017 et 2018

Annex 6.7: Mid-term results with respect to the targets to be reached by the project

| Component 1. Establishment of a climate change information platform and effective adaptation options |  |
| --- | --- |
| Activities | Achievement rate Nov. 2018 |
| Activity 1.1.1: which consisted of participatory identification of the needs of potential users of climate information and diagnosis of the climate network, meteorology, hydrology and hydrodynamic observations led to 2 studies of the identification of the needs of users with 01 report available while the second study is underway. | 75% |
| Activity 1.1.2: which consisted of the acquisition and installation of hydro-meteorological instruments allowed the installation of three automatic hydrometric stations which were installed or rehabilitated in Medina Oumar (Kolda), Sedhiou and Ziguinchor. Implementation of 5 differential GPS and accessories, as well as the acquisition of 4 weather stations and 3 hydro stations | 100% |
| Activity 1.1.3: which consisted of the training of the technical staff (meteorological, hydrological, agricultural, etc.) and the producers on the collection, the processing and the analysis of the data made it possible to train 18 agents of the DGPRE and the PRGTE on the assembly / disassembly and on the operating of the differential GPS | 50% |
| Activity 1. 2. 1: which consisted of creating a climate database (correlated with socio-economic and environmental data) and tools to assess vulnerability to climate change is underway. | 50% |
| Activity 1.2.2: which consisted in analyzing in a participatory way the sensitivity, the exposure of the target ecosystems (the Niayes, the mangrove, the Kalounayes forest, etc.) and the past and future livelihoods (in 2030, 2050 or 2100), then assess their impacts in a context of climate change enabled the completion of the first study in 2017, the second being underway. | 50% |
| Activity 1.3.1: which consisted in identifying the existing sharing platforms (e.g. GTP, Info Clim, Siena, etc.), and assessing their effectiveness and sustainability, and studying collaborative models was carried out in 2016. | 100% |
| Activity 1.3.2: which consisted of setting up an operational and sustainable system for sharing information and assessing the vulnerability to climate change for the benefit of local actors (local authorities, technical services, producers and households) was carried out in 2017. | 100% |

| Component 2 : Reducing the risks of climate change in target lands and ecosystems with adaptive restoration measures |  |
| --- | --- |
| Activities | Achievement rates Nov. 2018 |
| Activity 2.1.1: consisted of the regeneration / restoration of 100 ha of mangroves in Tobor (Ziguinchor) and Diendé (Sedhiou). There was awareness and information of the population, local elected officials and partners on the approach; stakeholder training; the involvement of the population in the planning of activities; research of propagules by the populations for the rhizophora species; the management of populations in the reforestation 142.7 ha of mangroves in Kalounayes | 142.7% |
| Activity 2.1.2: which consisted in developing and applying sustainable mangrove harvesting techniques in Ziguinchor and Sedhiou forest reserves to prevent their cutting and decay, has led to the installation of 06 oyster blocks in the Ziguinchor region, as well as the establishment of a fish farm of 3 ponds in Tobor and 10 floating cages Djilacoune. | 100% |
| Activity 2.2.1: which consisted in identifying better adapted forest species and appropriate technologies for better protection of vegetable basins against silting, as well as market gardening packages adapted to the biophysical context, allowed for the distribution of certified cabbage and carrot seeds as well as small agricultural equipment which were distributed to the selected producers. | 100% |
| Activity 2.2.2: which consisted in planting 110 ha of windbreaks around individual market gardens to protect them from silting and the establishment of close protection of crop plots against the harmful effects of the winds (the harmattan and the trade wind) enabled 122.2 ha of windbreaks to be built around the individual market basins to protect them against silting in the Niayes area. | 122.2% |
| Activity 2.2.3: which consisted in the establishment of 60 ha of water-saving micro-irrigation systems in pilot vegetable gardens resulted in the establishment of 20 ha (19 ha of drip and 1 ha of micro irrigation. | 33.3% |
| Activity 2.3.1: which consisted in reforesting and applying natural regeneration techniques of 100 ha palm grove with adapted varieties, allowed to plant 90.1 ha of palm groves. | 90.1% |
| Activity 2.3.2 : which consisted of supporting at least 10 groupings of women in the conduct of income-generating activities (market gardening, poultry farming, small livestock farming, marketing of forest products, salt production, etc.) involved supporting 6 flagship activities, namely: restoration of palm groves, support to 10 GPF to carry out income-generating activities, resilient seed production, system of rice intensification (SRI), the restoration of watersheds and the fight against bush fires. | 45% |
| Activity 2.3.3: which consisted in adopting resilient agricultural technological solutions (drought-resistant varieties, agroforestry practices, etc.) | 130% |
| Activity 2.3.4. which consisted in the restoration of 100 ha of community forests in the watersheds of the Soukou Valley (Sare Bidji CR in Kolda) to protect the banks of the watercourse against land erosion resulted in following results: the forests of Kourouch, Kalounayes, Caparan and Digoune were enriched by 50.5 ha. In Niamone and Dioubour the plantings in 2016 replenished an area of 0.45 ha. In Sedhiou, the forest of Diende has been enriched over an area of 50 ha. In Kolda, the Mahon-Bakor classified forest and the Dioulacolon community forest have been enriched over an area of 50 ha. In addition, IREF Kolda has produced 5 anti-erosion small dykes in Sare Oumar. | 75% |
| Activity 2.3.5: which consisted in fighting bushfires in the Kalounayes forest to support the regeneration effort of valuable forest species adapted to the biophysical context has allowed the revitalization of 10 control committees in the communes of Coubalan, Niamone and Ouonck | 166% with respect to the covered areas |

| Component 2: Support for knowledge and information acquisition mechanisms |  |
| --- | --- |
| Activities | Achievement rate Nov. 2018 |
| Activity 3.1.1: which consisted in training community counselors (60 members) from eight municipalities on integrating risks and opportunities related to climate change and on adaptation options resulted in the training of 76 local elected officials from eight municipalities. | 126.6% |
| Activity 3.1.2: which consisted in training of 200 staff of the extension services of ministries (responsible for water resources, agriculture, environment, livestock, etc.) on climate risk management and utilization of results of Risk and Vulnerability Assessments, in order to make adjustments to the policies and plans that govern land and ecosystem management, led to the organization of a training workshop for Ziguinchor, Kolda and Sedhiou technicians on integration of risks and opportunities related to climate change Between 2016 and 2018, 182 staff of the extension services of ministries (responsible for water resources, agriculture, environment, livestock, etc.) were effectively trained. | 91% |
| 3.2.1: which consisted in capitalizing the project’s achievements and experiences and crafting relevant strategies and means of communication adapted to the local communities made it possible to produce and broadcast some 60 programs, and 600 advertisements in the network of the URAC (community radios network) | 70% |
| Activity 3.2.2: which consisted in sharing the project's experiences with communities by organizing exchange visits or intra- or inter-community fora; with the information being broadcast on radio and television at the local, regional and national levels; and through awareness and information sessions, has allowed to conceive a dozen documentary films on the activities of the PRGTE which are available for widespread distribution. | 60% |
| Activity 3.2.3: which consisted in issuing three textbooks to be multiplied by 1000 on climate risk management and providing training for teachers and other school staff led to the production of 03 draft textbooks, as well as the training of 45 teachers | 25% |
| Activity 3.2.4: which consisted in making the results of the project measurable during the regional and international meetings but also through written reports and technical and scientific publications allowed for the creation of a website to share the publications and written reports of the project | 50% |

Annex 6.8: The results with respect to the mid-term targets to reach

| Component 1. Establishment of a climate change information platform and effective adaptation options |  |  |
| --- | --- | --- |
| Activities | Mid-term targets | Achievement rates Nov. 2018 |
| Activity 1.1.1: which consisted of participatory identification of the needs of potential users in terms of climate information and diagnosis of the climate network, meteorology, hydrology and hydrodynamic observations led to 2 studies of the identification of the users’ needs with 01 report available while the second is underway | 1 report | 200% |
| Activity 1.1.2: which consisted in acquiring and installing hydro meteorological instruments allowed for the installation or rehabilitation of three automatic hydrometric stations in Medina Oumar (Kolda), Sedhiou and Ziguinchor and the implementation of 5 differential GPS and accessories, as well as the acquisition of 4 weather stations and 3 hydro stations | 4 weather stations 3 hydro stations 5 GPS 10 automatic rain gauges 01 ecolog | 250% |
| Activity 1.1.3: which consisted of the training of the technical staff (meteorological, hydrological, agricultural, etc.) and the producers on the collection, the processing and the analysis of the data made it possible to train 18 agents of the DGPRE and the PRGTE on the assembly / disassembly and on the operating of the differential GPS |  | 125% |
| Activity 1.2.1: which consisted in creating a climate database (correlated with socio-economic and environmental data) and tools to assess vulnerability to climate change is underway. | 0 1 study | 50% |
| Activity 1.2.2: which consisted in analyzing in a participatory way the fragility, the exposure of the targeted ecosystems (the Niayes, the mangrove, the Kalounayes forest, etc.) and the past and future livelihoods (in 2030, 2050 or 2100), then assessing their impacts in a context of climate change led to the completion of the first study in 2017, while the second study is underway. | 01 study | 200% |
| Activity 1.3.1: which consisted in identifying existing sharing platforms (e.g. GTP, Info Clim, Siena, etc.) and assessing their effectiveness and sustainability, and studying collaborative models was carried out in 2016. | Workshop with GTP members | 150% |
| Activity 1.3.2 : which consisted of setting up an operational and sustainable system for sharing information and assessing vulnerability to climate change for the benefit of local actors (local collectivities, technical services, producers and households) was carried out in 2017. | Regional platforms for sharing climate information in the form of GTP (Thiès, Tivaouane, Kébémer, Louga, Bignona, Ziguinchor, Sedhiou, Kolda etc.) | 112% |

| Component 2 : Reduction of the climate change risks in the target lands and ecosystems with adaptation restoration measures |  |  |
| --- | --- | --- |
| Activities | Mid-term targets | Mid-term achievement rates |
| Activity 2.1.1: consisted of the regeneration / restoration of 100 ha of mangroves in Tobor (Ziguinchor) and Diende (Sedhiou). There was also awareness and information activities for the population, local elected officials and partners on the approach; stakeholder training; the involvement of the population in the planning of activities; search of propagules by the populations for the rhizophora species; the management of populations in the reforestation of 142.7 ha of mangrove in Kalounayes, compared to the 70 hectares planned for the mid-term. | 70 ha | 202.8% |
| Activity 2.1.2 : which consisted in developing and applying sustainable mangrove harvesting techniques in the Ziguinchor and Sedhiou forest reserves to prevent their cutting and degradation have allowed for the installation of 06 oyster blocks in the Ziguinchor region, as well as the establishment of a fish farm with 3 ponds in Tobor and 10 floating cages Djilacoune | 3 oyster farming blocks And 2 ponds | 225% |
| Activity 2.2.1: which consisted in identifying the best adapted forest species and appropriate technologies for better protection of vegetable basins against silting, as well as market gardening packages adapted to the biophysical context, made it possible to distribute cabbage and carrot certified seeds as well as small-scale agricultural equipment to the various selected producers. A study was also carried out | 1 study | 275% |
| Activity 2.2.2 : which consisted in planting 110 ha of windbreaks around individual market gardens to protect them from silting and the establishment of close protection of crop plots against the harmful effects of the winds (the harmattan and the trade wind) enabled the completion of 69.1 km of windbreak for a mid-term objective of 60 km | 60 km of windbreak | 115.16% |
| Activity 2.2.3 : which consisted in the establishment of 60ha systems of micro-irrigation to save water in the pilot market gardens has allowed for the establishment of 60ha (19 ha of drip technology and 1 ha of spray irrigation) | 10 ha | 200% |
| Activity 2.3.1: which consisted in reforesting and applying the natural regeneration techniques of 100 ha palm groves (including 35 ha at mid-term) with adapted varieties has allowed for the planting of 90.1 ha of palm groves. | 35 ha | 257.455% |
| Activity 2.3.2: which consisted in supporting at least 10 groupings of women in the conduct of income-generating activities (market gardening, poultry farming, small livestock farming, marketing of forest products, salt production, etc.) led to the implementation of 6 flagship activities including: restoration of palm groves, support to 10 GPF to carry out income-generating activities, resilient seed production, system of rice intensification (SRI), watershed restoration and the fight against bushfires. The 10 GPFs received partial support. | 10 GPF | 100% |
| Activity 2.3.3: which consisted of the adoption of resilient agricultural technological solutions (drought-resistant varieties, agroforestry practices, etc.) made it possible to produce at mid-term: 6.24 ha of drought-resistant seeds, 15 ha plantation and/or regeneration of palm stands and 14 ha of Community Forest Restoration in the Soukou and Dioulacolon Valleys, | 42 ha | 83.9% |
| Activity 2.3.4. which consisted in restoring of 100 ha of community forests in the watersheds of the Soukou Valley (Sare Bidji CR in Kolda) to protect the banks of the watercourse against land erosion resulted in following: the forests of Kourouch, Kalounayes, Caparan and Digoune were enriched over 50.5 ha. In Niamone and Dioubour the 2016 plantings were replenished on a surface of 0.45 ha. In Sedhiou, the forest of Diende has been enriched on an area of 50 ha. In Kolda the Mahon-Bakor classified forest and the Dioulacolon community forest have been enriched over an area of 50 ha. In addition, IREF Kolda has produced 5 anti-erosion small dykes in Sare Oumar. | 50 ha | 184% |
| Activity 2.3.5 : which consisted in fighting bushfires in the Kalounayes forest to support the regeneration effort of valuable forest species adapted to the biophysical context has allowed for the revitalization of 10 control committees in the communes of Coubalan, Niamone and Ouonck compared to 4 communes planned for the mid-term. | 02communes | 150% compared to the covered areas. |

| Component 3: Support of the knowledge and information acquisition mechanisms |  |  |
| --- | --- | --- |
| Activities | Mid-term targets | Mid-term Achievement rates |
| Activity 3.1.1: which consisted in training 80 community councilors from eight municipalities on integrating climate change risks and opportunities and adaptation options resulted in the training of 76 local elected representatives from eight municipalities | - Training of 70 agents of the technical staff - Training of 80 local elected officials - Training of 20 producers | 106.6% |
| Activity 3.1.2: which consisted in training of 200 extension staff from ministries (responsible for water resources, agriculture, environment, livestock, etc.) on climate risk management and the utilization of results of the risk and vulnerability assessments, in order to make adjustments to the policies and plans that govern land and ecosystem management, led to a training workshop for Ziguinchor, Kolda and Sedhiou technicians on integrating of risks and opportunities related to climate change Between 2016 and 2018, 182 extension staff from ministries (responsible for water resources, agriculture, environment, livestock, etc.) were in fact trained. | Training of 200 extension staff from ministries (responsible for water resources, agriculture, environment, livestock, etc.) | 91% |
| 3.2.1: which consisted in capitalizing the achievements and experiences of the project and designing relevant strategies and means of communication adapted to the local communities allow to achieve and diffuse either 60 programs produced and diffused, and 600 spots in the URAC network . | 60 programs et 600 advertisements produced 50 advertisement signs and billboards of PRGTE 01 communication plan | 100% |
| Activity 3.2.2: which consisted in sharing the project's experiences with the communities by organizing exchange visits or intra- or inter-community fora; with information being broadcast on radio and television at the local, regional and national levels; and through awareness and information sessions has allowed to develop a dozen documentary films on the activities of the PRGTE which are available for a wide distribution. |  | 60% |
| Activity 3.2.3: which consisted in preparing three school textbooks to be multiplied by 1000 on climate risk management and providing training for teachers and other school staff has in fact enabled the production of 03 drafts school textbook, as well as the training of 45 teachers. | 2 training sessions for the inspectors | 125% |
| Activity 3.2.4: which consisted in making visible the results of the project during the regional and international meetings but also through written reports and technical and scientific publications allowed for the establishment of a communication plan, a website to share written project publications and reports, signpost for project visibility; etc.. | 50 advertisement signs and billboards of PRGTE 01 communication plan | 150% |

Annex 6.9: Code of conduct form of GENU signed

The evaluators /Consultants : 1. Must display complete and fair information in their assessment of strengths and weaknesses so that decisions or actions taken are well grounded. 2. Must disclose all evaluation findings, as well as information on their limitations and make them available to all those involved in the evaluation and who are legally entitled to access the results. 3. Must protect the anonymity and confidentiality to which the persons providing the information to them are entitled. Evaluators must ensure that time is sufficient, minimize wasted time, and respect the individual's right to privacy. Evaluators must respect the right of individuals to provide information confidentially and ensure that the so-called sensitive information cannot be trace back to their source. Evaluators do not evaluate individuals and must maintain a balance between the assessment of management functions and this general principle. 4. May sometimes find evidence of wrongdoing while conducting assessments. Such cases must be reported confidentially to the relevant authorities responsible for investigating the matter. They should consult with other competent oversight entities when there is any doubt as to whether to report issues, and how it must be properly done. 5. Must be mindful of beliefs, habits and customs, and demonstrate integrity and honesty in their interactions with all stakeholders. In accordance with the Universal Declaration of Human Rights, evaluators must pay attention to and address issues of discrimination and gender disparity. Evaluators must avoid anything that might offend the dignity or self-respect of those with whom they come into contact during an assessment. Recognizing that an assessment may negatively impact the interests of some stakeholders, evaluators must conduct the evaluation and communicate its purpose and results in a way that is respectful of the dignity and sense of respect of the stakeholders. 6. Are responsible for their performance and what it entails. Evaluators must be able to present in writing, orally, in a clear, accurate and honest manner, the evaluation, its limitations, findings and recommendations. 7. Must respect the recognized accounting procedures and use caution in the use of evaluation resources. Agreement form with the Consultant responsible for the mid-term review Code of Conduct Accord of the United Nations system in terms of evaluation: Consultant’s name : Kamtchouing Noubissi Pierre Name of the Counseling Organization (if applicable): __________________________________________ I confirm having received and understood the Code of Conduct Accord of the United Nations system in terms of evaluation and I am committed to complying with it. Signed in ___Douala - Cameroon (Place) on _____03/02/2019 (Date) Signature: ________________________________

Annex 6.9: Approval form of final report of the mid-term review signed

Mid-term review report reviewed and approved by:

Ordering unit

Name: _____________________________________________

Signature: __________________________________________     Date: _______________________________

UNDP -GEF Regional Technical Advisor

Name: _____________________________________________

Signature : __________________________________________     Date : _______________________________

In the area of Kolda where the project has built some bunds made of stone block and vetiver, this water retention strategy has not been sufficiently explored during situational surveys carried out with beneficiaries. Indeed, the evaluators noted very actual needs in terms of water retention both in the whole of the Niayes area and in the region of Sedhiou.

The same observation was also made on the promotion of water saving techniques on which the project confined itself to offer beneficiaries the drop technology not adapted to the region of Thiès because of the nature of the soils rich in iron, while this issue has not been addressed in the area of Casamance.

This question was not provided by PRODOC, let alone by the Steering Committee (CP).

The same goes for wastewater reclamation.

These are Dakar, Thiès and Louga for the Niayes Area and Ziguinchor, Sedhiou and Kolda for Casamance.

As an example, the objective of the Environmental Policy and Natural Resources Sector Letter (LPSERN) is to improve the knowledge base of the environment and natural resources (i), the reversal of the current trend of degradation (ii), concerted management (iii), etc. These instruments include the different codes (forestry, environment, hunting and wildlife protection, ...) different strategies and plans: (i) the Strategy and the National Action Plan for the Conservation of the Biodiversity (CBD), (ii) the National Action Plan to Combat Desertification (PAN / LCD), (iii) the National Wetland Management Policy (PNZH), (iv) the Implementation Strategy of the United Nations Framework Convention on Climate Change (UNFCCC), (v) the National Adaptation Action Plan (NAPA), among others.

AGRHYMET centers could do much to assist in building GTP capacity. The example of Kaffrine where this partner has been involved since 2011 in the dissemination of hydrometeorological information to farmers is a success, thanks to the use of community radios and SMS.

For definition of targets, see Table 2.

The mid-term achievement rates correspond to the average achievement rates of the component’s various activities compared to the targets. For more details on the activities completion rates at mid-term, see Annex 6.8.

It is necessary to mention that the market gardening itineraries disseminated by the PRGTE were designed by the PADEN. This dissemination was made with the PADEN’s prior authorization, who kindly allowed the PRGTE to include in the documents the words "multiplied and distributed by the PRGTE".

Of the two studies planned for this activity, only that on the Niayes area is available.

Due to the lack of measurable achievements with respect to beneficiaries, the results of this activity were very difficult to verify. Indeed, ANACIM's actions are often carried out from Dakar, without a real involvement of regional directorates, who often do not have the necessary skills to take action in this context, which is the source of coordination failures between Dakar and the implementation areas.

Although document review mentions that this activity has started and that 03 textbook drafts have been produced and 45 teachers trained.

This situation often held back the DEFCCS selected as the main implementing partner when designing the project.

At least 02 external audits commissioned by UNDP and the PRGTE were conducted in 2017 and 2018 by independent firms to establish the accuracy of the project’s accounting and financial information.

The interviews with the various implementing partners enabled the evaluation team to note that their grievances, which could help to relieve bottlenecks (lack of clarity in the management of supporting documents, for example) are not enough taken into account by the PCU.

It should also be noted that no budget for monitoring the impacts of activities has been included in any PTAB. However, such studies require the support of forest consultants, socio-economists etc.

Some stakeholders did not always produce their activity reports despite multiple reminders from the monitoring team (e.g. ANACIM, whose activities, yet complementary, were not always in line with those of the other implementing partners).

In order to establish the truthfulness of the 2016 accounts and to question the management procedures of the project, a financial audit HACT was commissioned by the Coordination Unit of PRGTE in 2017.

1 $ USD = 550 FCFA

It is important to note that ANACIM is testing the sending of weather information by SMS. But this only concerns a small number of producers, especially those who took part in training.

The ANACIM service had foreseen a possible delay of the rains in the agricultural calendar during the year 2018. However the arrival and the availability of the rains were more irregular than expected because it only rained on June 27 and August 23 i.e. 01 month apart.

Many of the producers are on concessionaire operating plans (l Chemical Industries of Senegal, etc.). We should not finance in these areas heavy, because these equipment are supposed to be evicted.

For ideas on innovative and participatory strategies and techniques for monitoring and evaluation, please refer to the document UNDP Discussion Paper: Innovations in Monitoring & Evaluating Results, 5 Nov 2013.

To more actively engage stakeholders in the monitoring and evaluation process, see UNDP's Guide to Planning, Monitoring and Evaluating for Development Results, Chapter 3, and page 93.

The conclusions of the mid-term review can also be incorporated into the body of the report.

https://intranet.undp.org/unit/bom/pso/Support%20documents%20on%20IC%20Guidelines/Template%20for%20Confirmation%20of%20Interest%20and%20Submission%20of%20Financial%20Proposal.docx

http://www.undp.org/content/dam/undp/library/corporate/Careers/P11_Personal_history_form.doc