****

**United Nations Country Team**

**New Sustainable Development Cooperation Framework (SDCF) Roadmap** (18 Dec.)

|  |  |  |  |
| --- | --- | --- | --- |
| **Milestones/key actions** | **Responsible** | **Deadline** | **Status / Comments** |
| Set up **Youth Advisory Board** (YAB) to consult in the course of the CCA and SDCF formulation | Youth TF (UNICEF and UNFPA) | 28 Jan. 2020 | UNFPA has prepared draft TOR  Approve in next UNCT 28 Jan. |
| **UNDAF Evaluation** |  |  |  |
| Consolidate UNCT comments | RCO (MU) | 24 December |  |
| Prepare the **UNCT Management Response** and consult with the Regional UNSDG | UNCT with RCO support (MU) | 15 Jan. 2020 |  |
| Translation of UNDAF Evaluation report | RCO | 15 Feb. 2020 |  |
| Share the Evaluation Report with the UNDAF Steering Committee (national partners) | RCO (MU/LK) | 28 Feb. 2020 |  |
| **Common Country Analysis (CCA)** |  |  |  |
| **CCA:** Share draft CCA report with UNCT for feedback and subsequently with DCO for quality review, and share with CCA Team for incorporation | RCO | 18 December | PENDING  Share with DCO (Jorg). 23 Dec. |
| **CCA:** Finalize CCA Report NARRATIVE based on comments from UNCT / DCO and validation workshop (internal version) | CCA Consultants | 25 December |  |
| **CCA:** Finalize CCA Report NARRATIVE and share with PSG | RCO (ZJ) | 15 Jan. 2020 |  |
| **CCA:** Prepare a public version of the report for sharing with externals (layout, infographics, etc.) + translation EN>RU | RCO (ZJ) | 30 Jan. 2020 |  |
| **Cooperation Framework** |  |  |  |
| **UNSDCF narrative part** - Drafting | RCO  (CL MU, AS) | 03 Jan. 2020 | With inputs from UNCT and CCA team |
| **UNSDCF narrative part** - Consolidation | RCO (AS) | 03-06 Jan. 2020 | Send to HF for verification by 06 Jan. |
| **UNSDCF narrative part** – Draft Sent to DCO, UNCT and CCA for review | RCO (HF) | 09 Jan. 2020 | Consultation with DCO, UNCT and CCA for review |
| **UNSDCF narrative part** – Draft Sent for translation | RCO (MU) |
| **UNSDCF narrative part** – Review by DCO, UNCT, and CCA Team on draft | DCO, UNCT and CCA | 15 Jan. 2020 |
| **UNSDCF narrative part** – Review and finalize draft | RCO  (CL MU, ZJ, AS) | 19 Jan. 2020 |  |
| **UNSDCF narrative part** – Submission to PSG | RCO (HF) | 1. 20 Jan. 2020 |  |
| Refine and share the draft SDCF with Government and national stakeholders including YAB to validate | UNCT |  |
| **Multi-stakeholder consultations**   * Round table with IFIs | RCO (Helena and Christian) | 21 Jan. 2020 | Moderator:   * Helena Fraser, UNRC * UNCT member (TBC) |
| **Multi-stakeholder consultations**   * Round table with development partners (and EU) | RCO (Helena and Christian) | 23 Jan. 2020 | Moderator:   * Helena Fraser, UNRC * UNCT member (TBC) |
| **UNCT** – 1. Update on UNSDCF, 2. discussion on UNCT configuration, 3. Approve Youth Advisory Board TOR | UNCT | 28 Jan. 2020 |  |
| Conduct a **final round of consultation (workshop/Multi-stakeholder Forum) with Government** to validate the outcomes and Results Matrix | RCO (All) | 30 Jan. 2020 | **With UNCT participation** |
| Finalize the **UNSDCF monitoring framework** and evaluation plan | RCO (MU) / M&EDG | 15 Feb. 2020 | Members of M&EDG |
| Refine and finalize the SDCF document based on the Government’s and other stakeholders’ comments | RCO, CCAT | 21 Feb. 2020 |  |
| **UNCT to approve Final UNSDCF** (with consolidated Government, stakeholders and PSG comments) | UNCT | 28 Feb. 2020 |  |
| Conduct consultations with resident and non-resident UN agencies and regional UN entities on reviewing the UNCT’s assets and configuration in support of the UN SDCF | UNCT with support of RCO | March 2020 |  |
| Conduct SDCF Steering Committee meeting to validate and approve the SDCF for signing | UNCT, RCO | April 2020 |  |
| Conduct launch event with engagement of national and international partners | UNCT, RCO | November 2020 |  |
| **Financing for SDGs** |  |  |  |
| Conduct the Financial Landscape analysis | UNDP, with RCO support | October 2019 – February 2020 | DCO and PSG to comment |
| Conduct consultations with all participating UN entities as well as IFIs on a Funding Framework and SDG Financing Strategy | RCO | By end of February 2020 | DCO and PSG to comment |
| Finalize the Funding Framework | UNCT, RCO | By end of March 2020 |  |
| Conduct consultations with Government and donor community on SDG Financing Strategy | UNCT, RCO, UNDP | TBC April 2020 | External consultant would be required |
| Secure UNCT agreement on Revised RG approach, TOR, chairing arrangements.  Establish the Results Groups | UNCT | By 1 August |  |
| Organize consultations on the Joint Workplans with UN agencies and Government | Chairs of Results Groups | Quarter 3 2020 |  |
| Finalize the Joint Workplans in UN INFO and approve by the Steering Committee | UNCT | Quarter 4 |  |
| **Completed Tasks** |  |  |  |
| **UNDAF Evaluation** share draft with UNCT for comments/feedback and DCO for quality review | Consultants, RCO (MU/LK) | By 11 October 2019 | UNCT to comment by COB 25 October |
| **Common Country Analysis:**  Data collection, synthesis and analysis with engagement of CCA facilitators:   * Consultations within the UNDAF Results Groups, key national counterparts under the UNDAF and SDG implementation processes, IFIs, donors and development partners * Consultation workshop with the UNDAF Results Group to cross-check and cross-reference findings and conclusions | CCA Team, consultants, UNDAF RGs Secretariats, RCO (Zarif Jumaev) | 9 – 17 October  18 October |  |
| **UNCT Strategic Planning Retreat**  Validate CCA and UNDAF Evaluation conclusions, agree comparative advantages, discuss the UN Vision & emerging strategic priorities for 2021-2025 | RCO | 21-22 October | Facilitators: DCO ECA and UNSDG PSG  Guests: CCA facilitators |
| UNCT retreat outcomes including draft UN Vision 2030 and emerging strategic priorities  Draft UN Vision 2030 and share with UNCT | RCO (Christian) | 23- 31 October |  |
| **Youth poll** on SDGs through U-Report platform | n/a | 22 October |  |
| **Strategic prioritization consultations preparation**  Set up a group of facilitators from UN agencies and prepare a guidance note/methodology for multi-stakeholder consultations | RCO  (MU) | Before 28 October for regional consultations  Before 7 November for national consultations | External consultant for developing methodology & agenda  UNCT is requested to confirm UN staff to volunteer facilitation as suggested below |
| Consultants to finalize the Evaluation Report | Consultants | By 1st November |  |
| **Strategic prioritization regional consultations**  Multi-stakeholder consultations (youth and NGOs, private sector, local governments and communities) on strategic priorities at field level in 5 regions  Facilitated by Yuksalish, DPOs, and RCO  N.B. Nukus consultations already held. | RCO  (MU and AM) | 28 October – 23 November | External consultant required for methodology/guidance note for facilitators  Yuksalish Team and DPOs  Surkhandarya: 28-30 Oct  Kashkadarya: 30-31 Oct  Namangan region: 4-6 Nov  Andijan region: 6-7 Nov  Syrdarya region: 21-23 Nov |
| **Multi-stakeholder consultations**   * Workshop with government counterparts with attendance of the YAB | RCO  (All) | 12 November |  |
| **Multi-stakeholder consultations**   * Round table with the Senate and the Legislative Chamber * with attendance of the YAB | RCO (Matluba and Anvar) | 14 November |  |
| **Multi-stakeholder consultations**   * Workshop with civil society, including youth NEET/vulnerable groups, NGOs and HR activists   with attendance of the YAB | RCO (Matluba and Anvar) | 19 November |  |
| **Multi-stakeholder consultations**   * Expert discussion with academia and think-tanks | RCO (Zarif) | 22 November |  |
| Based on and throughout multi-stakeholder consultations, work out and **draft the Theory of Change**, draft strategic priorities, outcomes, outcome-level TOCs and Results Framework (outcomes and outputs) | RCO (Christian) | 2 – 6 December | With inputs from UNCT and CCA team |
| **Hold in-house UN workshop** to discuss and agree on the TOCs and Results Matrix (outcomes and outputs) | RCO (Christian) | 10 December | With participation of the UNCT and Programme staff of UN agencies (members of UNDAF RGs and M&EDG) |
| **Meeting of the UN M&E and Data group** to discuss the UNSDCF Monitoring framework | RCO (Matluba)/M&EDG | 12 December | Members of M&EDG |