## UNDP-GEF Midterm Review Terms of Reference

**Standard Template 1: Formatted for attachment to** [**UNDP Procurement Website**](http://procurement-notices.undp.org/)

1. **INTRODUCTION**

This is the Terms of Reference (ToR) for the UNDP-GEF Midterm Review (MTR) of the *full* -sized project titled *Comprehensive Environmentally Sound Management of PCBs in Montenegro* (PIMS 5562) implemented through the *UNDP Montenegro*, which is to be undertaken in *2019*. The project started on the *16th January 2017* and is in its *third* year of implementation. In line with the UNDP-GEF Guidance on MTRs, this MTR process was initiated before the submission of the second Project Implementation Report (PIR). This ToR sets out the expectations for this MTR. The MTR process must follow the guidance outlined in the document [*Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects*](http://web.undp.org/evaluation/documents/guidance/GEF/mid-term/Guidance_Midterm%20Review%20_EN_2014.pdf).

**2. PROJECT BACKGROUND INFORMATION**

 The project Comprehensive Environmentally Sound Management of PCBs in Montenegro intends to support the country with the necessary technical and financial assistance to ensure that all the remaining PCBs in the country (estimated in not less than 900 t of PCB contaminated equipment, waste and soil) are identified and disposed of. The project will be implemented side by side with the relevant institutional and industrial stakeholders, i.e. the Ministry for Sustainable Development and Tourism, private and state owned companies, holders of PCB containing equipment. Although the project expects to solve all remaining PCBs issues in the country, it will also ensure that enough capacity for the sound management of PCBs would have been built for the management of any further such hazardous waste identified in time after project’s closure.

The disposal or decontamination of PCBs in Montenegro presents a number of issues and risks. First of all, the reliability of initial PCB inventory is very low and mostly limited to phased out equipment that needs to be disposed of. In Montenegro where most of information on PCBs from NIP inventory comes from disconnected equipment. This is due to the fact that electrical equipment (transformers, capacitors) when in good operating condition are usually not inspected for PCB content. The reasons are that:

• the cost of replacing transformer and capacitor is capital intense (very high), and

• the sampling and analysis of in-use equipment is a complex task requiring a significant coordination effort (for instance, coordination with maintenance schedule of electric equipment).

A second feature is that, being not immediately perceived as a hazard by the common public, the issue of PCBs is very often given a low priority from the authorities. Therefore, the existing legislation on PCB is not effectively enforced. As explained in the chapter above, although the Montenegrin legislation is well advanced and generally compliant with the Stockholm convention and the EU directive on PCBs management, and the government updated the inventory of PCB waste, the requirements related to the PCB management plans, and PCB “logbooks” are almost completely disregarded. In the absence of a sound level of enforcement of current legislation, even the industry’s commitment to address the issue of PCBs – given the high costs related to the decontamination or disposal (with subsequent replacement) of contaminated equipment – is low. For this reason, the national PCB management situation can be effectively addressed only if the government’s commitment and capacity are high.

A third feature is the lacking of PCB treatment technologies at local level. This is a common feature in many countries supported by UN/GEF projects in PCBs management. This usually results in industries undertaking substantial investment for shipping PCB contaminated equipment for abroad, typically EU, for disposal. In the case of Montenegro, there are no technologies for treatment of low PCB-contaminated equipment or disposal facilities available for high PCB contaminated equipment or waste, therefore until now only the highly PCB contaminated equipment has been to date treated by shipping and disposal abroad.

The project strategy is therefore designed to address simultaneously all these important aspects as outlined below.

1) Increasing national PCB management capacities and the enforcement of the legislation. This will require working side by side with the control authorities (mainly the Ministry for Sustainable Development and Tourism) and the key stakeholders (the electric power industry and other potential owners of PCB containing equipment) to:

• develop and implement a practical guidance on PCB environmentally sound management (ESM);

• provide assistance in fulfillment of legal obligations towards recording and reporting PCB related information;

• conduct inspections at sites where electrical equipment (transformers, capacitors) operates,

• train operators and officers on both sides – the governmental authorities and PCB equipment/waste owners.

2) Increasing the industry and general awareness. PCBs are very often a not very well known environmental issue. Except for extremely high pollution levels, resulting in acute and immediate health impacts, the toxic effect of PCBs (increase of cancer probability) is delayed in time and not associated to any “visible” pollution like black smoke from open burning or factories’ stacks or turbidity in water. Therefore, the PCB hazard is usually not perceived as an immediate threat by many. However, an unsafe disposal of PCBs results in the contamination of food chain and other environmental media (like, for instance, sediments and soil) which may last for years. PCBs have been recently (March 2013) re-assessed by the IARC and are now classified as “known human carcinogens (class 1)” compared to the previous “probable human carcinogens (class 2)” category. There is therefore the need to inform the main stakeholders and the public at large on the benefit brought by the project so that the government and the industry are encouraged in undertaking necessary actions.

3) Engagement of stakeholders. As in other environmental programmes, only in case of key stakeholder’s buy-in, the project’s goals can be satisfactorily achieved. No major change in current practices can be achieved if there is little or no awareness of the risks posed by PCBs, and if stakeholders do not feel the need to address the PCB management issue once and for all. As previously described in more detail, the project had identified at PIF stage a number of important stakeholders which will be involved in all project activities during its implementation. Besides MoSDT, which will be the national implementing institution, key PCB holders, like EPCG (both for electricity generation and distribution) and KAP were informed on the project’s related benefits and on the expected and required level of commitment towards it. As a result, they participated proactively in all the project development activities, including providing lists of their power equipment and facilitating oil sampling and analysis for PCB content. More stakeholder engagement, by involving other line Ministries, academic institutions and NGO sector is planned during the project implementation which will too include civil society associations, trade unions, and other beneficiaries.

4) Strengthening the reliability of information through updating of the PCB inventory. At PIF stage, the only available information was related to the list of phased-out PCB equipment and waste, a few pure PCB transformers, online or stored at KAP, oil tanks and contaminated material (sawdust, soil, waste) potentially contaminated by PCBs. Due to the low enforcement of the legislation, there was very little information available on the concentration of PCB online equipment. The information concerning the number, age and level of contamination of PCB equipment is indeed essential for both management purposes and identification of the proper treatment / disposal technologies. This situation was already evident at the PIF formulation stage, and therefore the main focus in the preliminary inventory carried out during preparation of the FSP project document concerned existing offline and online equipment at EPCG company. At same time, only limited PCB content in transformers stored or online at KAP was re-confirmed, including that data on PCB contaminated soil. The project will continue consolidating the PCB inventory by undertaking dielectric oil sampling and analytical determination of PCBs in 3,000 pieces of equipment during the first two years of its implementation.

5) Provide know-how and financial support on the technologies for the disposal of PCB equipment. Clearly, one of the central issues on the side of PCB ESM concerns the availability of technical and financial resources for PCB disposal. In the absence of a sound know-how related to disposal operations of PCB contaminated equipment, the cost / benefit ratio is always very high, for the following reasons:

• the options allowing the chemical destruction of the PCBs in the dielectric oil without destroying the oil itself are usually not considered, so that the dielectric oil, which is usually a very expensive asset, is lost;

• the planning of PCB equipment phasing out is not aligned with their residual value, so that very often a strategy aimed at minimizing the cost of disposal of PCB contaminated equipment is not pursued; and

• the legal aspects related to the storage of PCB containing equipment under maintenance versus PCB phased out equipment (to be considered waste) are usually neglected, exposing therefore owners of PCB equipment to a severe liability risk.

The project budget from the GEF Trust Fund is 3,5 mil USD, UNDP TRAC resources are 50,000 USD and total co-financing is 19,803,691 USD.

**3. OBJECTIVES OF THE MTR**

The MTR will assess progress towards the achievement of the project objectives and outcomes as specified in the Project Document, and assess early signs of project success or failure with the goal of identifying the necessary changes to be made in order to set the project on-track to achieve its intended results. The MTR will also review the project’s strategy, its risks to sustainability.

**4. MTR APPROACH & METHODOLOGY**

The MTR must provide evidence based information that is credible, reliable and useful. The MTR team will review all relevant sources of information including documents prepared during the preparation phase (i.e. PIF, UNDP Initiation Plan, UNDP Environmental & Social Safeguard Policy, the Project Document, project reports including Annual Project Review/PIRs, project budget revisions, lesson learned reports, national strategic and legal documents, and any other materials that the team considers useful for this evidence-based review). The MTR team will review the baseline GEF focal area Tracking Tool submitted to the GEF at CEO endorsement, and the midterm GEF focal area Tracking Tool that must be completed before the MTR field mission begins.

The MTR team is expected to follow a collaborative and participatory approach[[1]](#footnote-1) ensuring close engagement with the Project Team, government counterparts (the GEF Operational Focal Point), the UNDP Country Office(s), UNDP-GEF Regional Technical Advisers, and other key stakeholders.

Engagement of stakeholders is vital to a successful MTR.[[2]](#footnote-2) Stakeholder involvement should include interviews with stakeholders who have project responsibilities, including but not limited to *Ministry of Sustainable Development and Tourism, Environmental Protection Agency, The Administration for Inspection Affairs, Companies that have PCB contaminated equipment, Center for Eco-toxicological Research,* executing agencies, senior officials and task team/ component leaders, key experts and consultants in the subject area, Project Board, project stakeholders, academia, local government and CSOs, etc. Additionally, the MTR team is expected to conduct field mission to Podgorica and Bar*,* including the following project sites UNIPROM KAP and CEDIS in Podgorica, and Hemosan in Bar.

The final MTR report should describe the full MTR approach taken and the rationale for the approach making explicit the underlying assumptions, challenges, strengths and weaknesses about the methods and approach of the review.

**5. DETAILED SCOPE OF THE MTR**

The MTR team will assess the following four categories of project progress. See the *Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects* for extended descriptions.

**i. Project Strategy**

Project design:

* Review the problem addressed by the project and the underlying assumptions. Review the effect of any incorrect assumptions or changes to the context to achieving the project results as outlined in the Project Document.
* Review the relevance of the project strategy and assess whether it provides the most effective route towards expected/intended results. Were lessons from other relevant projects properly incorporated into the project design?
* Review how the project addresses country priorities. Review country ownership. Was the project concept in line with the national sector development priorities and plans of the country (or of participating countries in the case of multi-country projects)?
* Review decision-making processes: were perspectives of those who would be affected by project decisions, those who could affect the outcomes, and those who could contribute information or other resources to the process, taken into account during project design processes?
* Review the extent to which relevant gender issues were raised in the project design. See Annex 9 of *Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects* for further guidelines.
* If there are major areas of concern, recommend areas for improvement.

Results Framework/Logframe:

* Undertake a critical analysis of the project’s logframe indicators and targets, assess how “SMART” the midterm and end-of-project targets are (Specific, Measurable, Attainable, Relevant, Time-bound), and suggest specific amendments/revisions to the targets and indicators as necessary.
* Are the project’s objectives and outcomes or components clear, practical, and feasible within its time frame?
* Examine if progress so far has led to, or could in the future catalyse beneficial development effects (i.e. income generation, gender equality and women’s empowerment, improved governance etc...) that should be included in the project results framework and monitored on an annual basis.
* Ensure broader development and gender aspects of the project are being monitored effectively. Develop and recommend SMART ‘development’ indicators, including sex-disaggregated indicators and indicators that capture development benefits.

**ii. Progress Towards Results**

Progress Towards Outcomes Analysis:

* Review the logframe indicators against progress made towards the end-of-project targets using the Progress Towards Results Matrix and following the *Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects*; colour code progress in a “traffic light system” based on the level of progress achieved; assign a rating on progress for each outcome; make recommendations from the areas marked as “Not on target to be achieved” (red).

Table. Progress Towards Results Matrix (Achievement of outcomes against End-of-project Targets)

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Project Strategy** | **Indicator[[3]](#footnote-3)** | **Baseline Level[[4]](#footnote-4)** | **Level in 1st PIR (self- reported)** | **Midterm Target[[5]](#footnote-5)** | **End-of-project Target** | **Midterm Level & Assessment[[6]](#footnote-6)** | **Achievement Rating[[7]](#footnote-7)** | **Justification for Rating**  |
| **Objective:**  | Indicator (if applicable): |  |  |  |  |  |  |  |
| **Outcome 1:** | Indicator 1: |  |  |  |  |  |  |  |
| Indicator 2: |  |  |  |  |  |
| **Outcome 2:** | Indicator 3: |  |  |  |  |  |  |  |
| Indicator 4: |  |  |  |  |  |
| Etc. |  |  |  |  |  |
| **Etc.** |  |  |  |  |  |  |  |  |

**Indicator Assessment Key**

|  |  |  |
| --- | --- | --- |
| Green= Achieved | Yellow= On target to be achieved | Red= Not on target to be achieved |

In addition to the progress towards outcomes analysis:

* Compare and analyse the GEF Tracking Tool at the Baseline with the one completed right before the Midterm Review.
* Identify remaining barriers to achieving the project objective in the remainder of the project.
* By reviewing the aspects of the project that have already been successful, identify ways in which the project can further expand these benefits.

**iii. Project Implementation and Adaptive Management**

Management Arrangements:

* Review overall effectiveness of project management as outlined in the Project Document. Have changes been made and are they effective? Are responsibilities and reporting lines clear? Is decision-making transparent and undertaken in a timely manner? Recommend areas for improvement.
* Review the quality of execution of the Executing Agency/Implementing Partner(s) and recommend areas for improvement.
* Review the quality of support provided by the GEF Partner Agency (UNDP) and recommend areas for improvement.

Work Planning:

* Review any delays in project start-up and implementation, identify the causes and examine if they have been resolved.
* Are work-planning processes results-based? If not, suggest ways to re-orientate work planning to focus on results?
* Examine the use of the project’s results framework/ logframe as a management tool and review any changes made to it since project start.

Finance and co-finance:

* Consider the financial management of the project, with specific reference to the cost-effectiveness of interventions.
* Review the changes to fund allocations as a result of budget revisions and assess the appropriateness and relevance of such revisions.
* Does the project have the appropriate financial controls, including reporting and planning, that allow management to make informed decisions regarding the budget and allow for timely flow of funds?
* Informed by the co-financing monitoring table to be filled out, provide commentary on co-financing: is co-financing being used strategically to help the objectives of the project? Is the Project Team meeting with all co-financing partners regularly in order to align financing priorities and annual work plans?

Project-level Monitoring and Evaluation Systems:

* Review the monitoring tools currently being used: Do they provide the necessary information? Do they involve key partners? Are they aligned or mainstreamed with national systems? Do they use existing information? Are they efficient? Are they cost-effective? Are additional tools required? How could they be made more participatory and inclusive?
* Examine the financial management of the project monitoring and evaluation budget. Are sufficient resources being allocated to monitoring and evaluation? Are these resources being allocated effectively?

Stakeholder Engagement:

* Project management: Has the project developed and leveraged the necessary and appropriate partnerships with direct and tangential stakeholders?
* Participation and country-driven processes: Do local and national government stakeholders support the objectives of the project? Do they continue to have an active role in project decision-making that supports efficient and effective project implementation?
* Participation and public awareness: To what extent has stakeholder involvement and public awareness contributed to the progress towards achievement of project objectives?

Reporting:

* Assess how adaptive management changes have been reported by the project management and shared with the Project Board.
* Assess how well the Project Team and partners undertake and fulfil GEF reporting requirements (i.e. how have they addressed poorly-rated PIRs, if applicable?)
* Assess how lessons derived from the adaptive management process have been documented, shared with key partners and internalized by partners.

Communications:

* Review internal project communication with stakeholders: Is communication regular and effective? Are there key stakeholders left out of communication? Are there feedback mechanisms when communication is received? Does this communication with stakeholders contribute to their awareness of project outcomes and activities and investment in the sustainability of project results?
* Review external project communication: Are proper means of communication established or being established to express the project progress and intended impact to the public (is there a web presence, for example? Or did the project implement appropriate outreach and public awareness campaigns?)
* For reporting purposes, write one half-page paragraph that summarizes the project’s progress towards results in terms of contribution to sustainable development benefits, as well as global environmental benefits.

**iv. Sustainability**

* Validate whether the risks identified in the Project Document, Annual Project Review/PIRs and the ATLAS Risk Management Module are the most important and whether the risk ratings applied are appropriate and up to date. If not, explain why.
* In addition, assess the following risks to sustainability:

Financial risks to sustainability:

* What is the likelihood of financial and economic resources not being available once the GEF assistance ends (consider potential resources can be from multiple sources, such as the public and private sectors, income generating activities, and other funding that will be adequate financial resources for sustaining project’s outcomes)?

Socio-economic risks to sustainability:

* Are there any social or political risks that may jeopardize sustainability of project outcomes? What is the risk that the level of stakeholder ownership (including ownership by governments and other key stakeholders) will be insufficient to allow for the project outcomes/benefits to be sustained? Do the various key stakeholders see that it is in their interest that the project benefits continue to flow? Is there sufficient public / stakeholder awareness in support of the long term objectives of the project? Are lessons learned being documented by the Project Team on a continual basis and shared/ transferred to appropriate parties who could learn from the project and potentially replicate and/or scale it in the future?

Institutional Framework and Governance risks to sustainability:

* Do the legal frameworks, policies, governance structures and processes pose risks that may jeopardize sustenance of project benefits? While assessing this parameter, also consider if the required systems/ mechanisms for accountability, transparency, and technical knowledge transfer are in place.

Environmental risks to sustainability:

* Are there any environmental risks that may jeopardize sustenance of project outcomes?

**Conclusions & Recommendations**

The MTR team will include a section of the report setting out the MTR’s evidence-based conclusions, in light of the findings.[[8]](#footnote-8)

Recommendations should be succinct suggestions for critical intervention that are specific, measurable, achievable, and relevant. A recommendation table should be put in the report’s executive summary. See the *Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects* for guidance on a recommendation table.

The MTR team should make no more than 15 recommendations total.

**Ratings**

The MTR team will include its ratings of the project’s results and brief descriptions of the associated achievements in a *MTR Ratings & Achievement Summary Table* in the Executive Summary of the MTR report. See Annex E for ratings scales. No rating on Project Strategy and no overall project rating is required.

Table. MTR Ratings & Achievement Summary Table for (*Project Title*)

|  |  |  |
| --- | --- | --- |
| **Measure** | **MTR Rating** | **Achievement Description** |
| **Project Strategy** | N/A |  |
| **Progress Towards Results** | Objective Achievement Rating: (rate 6 pt. scale) |  |
| Outcome 1 Achievement Rating: (rate 6 pt. scale) |  |
| Outcome 2 Achievement Rating: (rate 6 pt. scale) |  |
| Outcome 3 Achievement Rating: (rate 6 pt. scale) |  |
| Etc.  |  |
| **Project Implementation & Adaptive Management** | (rate 6 pt. scale) |  |
| **Sustainability** | (rate 4 pt. scale) |  |

1. **TIMEFRAME**

The total duration of the MTR will be approximately *(25 working days)* over a time period of *18 weeks* starting *16 May 2019* and shall not exceed five months from when the consultant(s) are hired. The tentative MTR timeframe is as follows:

|  |  |
| --- | --- |
| **TIMEFRAME** | **ACTIVITY** |
| *(20 April 2019)* | Application closes |
| *(15 May 2019)* | Select MTR Team |
| *(16 May 2019)*  | Prep the MTR Team (handover of Project Documents) |
| *(16 May -28 May 2019) 4 days*  | Document review and preparing MTR Inception Report |
| *(3 June – 10 June 2019) 2days*  | Finalization andValidation of MTR Inception Report- latest start of MTR mission |
| *(24 June -28 June 2019) 6 days*  | MTR mission: stakeholder meetings, interviews, field visits |
| *(28 June 2019)*  | Mission wrap-up meeting & presentation of initial findings- earliest end of MTR mission |
| *(29 June – 19 July 2019) 10 days*  | Preparing draft report |
| *(16 September – 20 September 2019) 2 days*  | Incorporating audit trail from feedback on draft report/Finalization of MTR report (note: accommodate time delay in dates for circulation and review of the draft report) |
| *(16 September 2019)*  | Preparation & Issue of Management Response |
| *(n/a)*  | (optional)Concluding Stakeholder Workshop (not mandatory for MTR team) |
| *(20 September 2019)* | Expected date of full MTR completion |

Options for site visits should be provided in the Inception Report.

1. **MIDTERM REVIEW DELIVERABLES**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **#** | **Deliverable** | **Description** | **Timing** | **Responsibilities** |
| **1** | **MTR Inception Report** | MTR team clarifies objectives and methods of Midterm Review | No later than 2 weeks before the MTR mission: (10 June 2019) | MTR team submits to the Commissioning Unit and project management |
| **2** | **Presentation** | Initial Findings | End of MTR mission: (28 June 2019) | MTR Team presents to project management and the Commissioning Unit |
| **3** | **Draft Final Report** | Full report (using guidelines on content outlined in Annex B) with annexes | Within 3 weeks of the MTR mission: (19 July 2019) | Sent to the Commissioning Unit, reviewed by RTA, Project Coordinating Unit, GEF OFP |
| **4** | **Final Report\*** | Revised report with audit trail detailing how all received comments have (and have not) been addressed in the final MTR report | Within 1 week of receiving UNDP comments on draft: (20 September 2019) | Sent to the Commissioning Unit |

\*The final MTR report must be in English. If applicable, the Commissioning Unit may choose to arrange for a translation of the report into a language more widely shared by national stakeholders.

1. **MTR ARRANGEMENTS**

The principal responsibility for managing this MTR resides with the Commissioning Unit. The Commissioning Unit for this project’s MTR is *UNDP Montenegro.*

The commissioning unit will contract the consultants and ensure the timely provision of per diems and travel arrangements within the country for the MTR team. The Project Team will be responsible for liaising with the MTR team to provide all relevant documents, set up stakeholder interviews, and arrange field visits.

1. **TEAM COMPOSITION**

A team of two independent consultants will conduct the MTR - one team leader / international expert (with experience and exposure to projects and evaluations in other regions globally) and one local expert. The consultants cannot have participated in the project preparation, formulation, and/or implementation (including the writing of the Project Document) and should not have a conflict of interest with project’s related activities.

Local expert will be engaged to support Mid Term Evaluation by preparing necessary inputs for the Team Leader to conduct the evaluation and prepare respective reports. Local Expert will review all relevant sources of information, such as the project document, project progress reports – including Inception Report, Annual APR/PIR,  documents produced in the scope of the project etc, GEF focal area tracking tools, project files, national strategic and legal documents, and any other materials that the team leader considers useful for this evidence-based assessment.

Local Expert will have the task to conduct most interviews with selected stakeholders outside Podgorica in the inception phase, based on the selection done jointly with the Team Leader and Project Team, and to accompany the team leader in interviews scheduled during his/her field mission.

The selection criteria for the Local Expert are the following:

* University degree in natural or social sciences, Master’s degree would be considered as an asset – 15%
* Minimum 5 years of working experience in the fields relevant to this ToR – environment, chemicals, waste management; - 20%
* Experience in project evaluation / experience with results‐based monitoring and evaluation methodologies – 20%
* Excellent social, facilitation and communication skills; - 10%
* Working experience with UN organizations and donors (GEF) is considered to be an asset; - 15%
* Demonstrated understanding of issues related to gender mainstreaming in issues related to environment portfolio; - 10%
* Fluency in English and Montenegrin both written and spoken. – 10%
1. **PAYMENT MODALITIES AND SPECIFICATIONS**

10% of payment upon approval of the final MTR Inception Report

40% upon submission of the draft MTR report

50% upon finalization of the MTR report

1. **APPLICATION PROCESS[[9]](#footnote-9)**

**Recommended Presentation of Proposal:**

1. **Letter of Confirmation of Interest and Availability** using the [template](https://intranet.undp.org/unit/bom/pso/Support%20documents%20on%20IC%20Guidelines/Template%20for%20Confirmation%20of%20Interest%20and%20Submission%20of%20Financial%20Proposal.docx)[[10]](#footnote-10) provided by UNDP;
2. **CV** and a **Personal History Form** ([P11 form](http://www.undp.org/content/dam/undp/library/corporate/Careers/P11_Personal_history_form.doc)[[11]](#footnote-11));
3. **Brief description of approach to work/technical proposal** of why the individual considers him/herself as the most suitable for the assignment, and a proposed methodology on how they will approach and complete the assignment; (max 1 page)
4. **Financial Proposal** that indicates the all-inclusive fixed total contract price and all other travel related costs (such as flight ticket, per diem, etc), supported by a breakdown of costs, as per template attached to the Letter of Confirmation of Interest template. If an applicant is employed by an organization/company/institution, and he/she expects his/her employer to charge a management fee in the process of releasing him/her to UNDP under Reimbursable Loan Agreement (RLA), the applicant must indicate at this point, and ensure that all such costs are duly incorporated in the financial proposal submitted to UNDP.

All application materials should be submitted to the address (fill address) in a sealed envelope indicating the following reference “Consultant for (*project title*) Midterm Review” or by email at the following address ONLY: (fill email) This email address is being protected from spam bots, you need Javascript enabled to view it by ***(time and date).*** Incomplete applications will be excluded from further consideration.

**Criteria for Evaluation of Proposal:** Only those applications which are responsive and compliant will be evaluated. Offers will be evaluated according to the Combined Scoring method – where the educational background and experience on similar assignments will be weighted at 70%and the price proposal will weigh as 30% of the total scoring. The applicant receiving the Highest Combined Score that has also accepted UNDP’s General Terms and Conditions will be awarded the contract.

**ToR ANNEX A: List of Documents to be reviewed by the MTR Team**

1. PIF
2. UNDP Initiation Plan
3. UNDP Project Document
4. UNDP Environmental and Social Screening results
5. Project Inception Report
6. All Project Implementation Reports (PIR’s)
7. Quarterly progress reports and work plans of the various implementation task teams
8. Audit reports
9. Finalized GEF focal area Tracking Tools at CEO endorsement and midterm - *POPs Tracking Tool*
10. Oversight mission reports
11. All monitoring reports prepared by the project
12. Financial and Administration guidelines used by Project Team

The following documents will also be available:

1. Project operational guidelines, manuals and systems
2. UNDP country/countries programme document(s)
3. Minutes of the Comprehensive Environmentally Sound Management of PCBs in Montenegro Board Meetings and other meetings (i.e. Project Appraisal Committee meetings)
4. Project site location maps

**ToR ANNEX B: Guidelines on Contents for the Midterm Review Report**[[12]](#footnote-12)

|  |  |
| --- | --- |
| **i.** | Basic Report Information *(for opening page or title page)** Title of UNDP supported GEF financed project
* UNDP PIMS# and GEF project ID#
* MTR time frame and date of MTR report
* Region and countries included in the project
* GEF Operational Focal Area/Strategic Program
* Executing Agency/Implementing Partner and other project partners
* MTR team members
* Acknowledgements
 |
| **ii.**  | Table of Contents |
| **iii.** | Acronyms and Abbreviations |
| **1.** | Executive Summary *(3-5 pages)* * Project Information Table
* Project Description (brief)
* Project Progress Summary (between 200-500 words)
* MTR Ratings & Achievement Summary Table
* Concise summary of conclusions
* Recommendation Summary Table
 |
| **2.** | Introduction *(2-3 pages)** Purpose of the MTR and objectives
* Scope & Methodology: principles of design and execution of the MTR, MTR approach and data collection methods, limitations to the MTR
* Structure of the MTR report
 |
| **3.** | Project Description and Background Context *(3-5 pages)** Development context: environmental, socio-economic, institutional, and policy factors relevant to the project objective and scope
* Problems that the project sought to address: threats and barriers targeted
* Project Description and Strategy: objective, outcomes and expected results, description of field sites (if any)
* Project Implementation Arrangements: short description of the Project Board, key implementing partner arrangements, etc.
* Project timing and milestones
* Main stakeholders: summary list
 |
| **4.** | Findings *(12-14 pages)* |
| **4.1** | Project Strategy* Project Design
* Results Framework/Logframe
 |
| **4.2** | Progress Towards Results * Progress towards outcomes analysis
* Remaining barriers to achieving the project objective
 |
| **4.3** | Project Implementation and Adaptive Management* Management Arrangements
* Work planning
* Finance and co-finance
* Project-level monitoring and evaluation systems
* Stakeholder engagement
* Reporting
* Communications
 |
| **4.4** | Sustainability* Financial risks to sustainability
* Socio-economic to sustainability
* Institutional framework and governance risks to sustainability
* Environmental risks to sustainability
 |
| **5.** | Conclusions and Recommendations *(4-6 pages)* |
|  |  **5.1**   | Conclusions * Comprehensive and balanced statements (that are evidence-based and connected to the MTR’s findings) which highlight the strengths, weaknesses and results of the project
 |
|  **5.2** | Recommendations * Corrective actions for the design, implementation, monitoring and evaluation of the project
* Actions to follow up or reinforce initial benefits from the project
* Proposals for future directions underlining main objectives
 |
| **6.**  | Annexes* MTR ToR (excluding ToR annexes)
* MTR evaluative matrix (evaluation criteria with key questions, indicators, sources of data, and methodology)
* Example Questionnaire or Interview Guide used for data collection
* Ratings Scales
* MTR mission itinerary
* List of persons interviewed
* List of documents reviewed
* Co-financing table (if not previously included in the body of the report)
* Signed UNEG Code of Conduct form
* Signed MTR final report clearance form
* *Annexed in a separate file:* Audit trail from received comments on draft MTR report
* *Annexed in a separate file:* Relevant midterm tracking tools (*METT, FSC, Capacity scorecard, etc.)*
 |

**ToR ANNEX C: Midterm Review Evaluative Matrix Template**

|  |  |  |  |
| --- | --- | --- | --- |
| **Evaluative Questions** | **Indicators** | **Sources** | **Methodology** |
| **Project Strategy: To what extent is the project strategy relevant to country priorities, country ownership, and the best route towards expected results?**  |
| (include evaluative question(s)) | (i.e. relationships established, level of coherence between project design and implementation approach, specific activities conducted, quality of risk mitigation strategies, etc.) | (i.e. project documents, national policies or strategies, websites, project staff, project partners, data collected throughout the MTR mission, etc.) | (i.e. document analysis, data analysis, interviews with project staff, interviews with stakeholders, etc.) |
|  |  |  |  |
|  |  |  |  |
| **Progress Towards Results: To what extent have the expected outcomes and objectives of the project been achieved thus far?** |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
| **Project Implementation and Adaptive Management: Has the project been implemented efficiently, cost-effectively, and been able to adapt to any changing conditions thus far? To what extent are project-level monitoring and evaluation systems, reporting, and project communications supporting the project’s implementation?** |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
| **Sustainability: To what extent are there financial, institutional, socio-economic, and/or environmental risks to sustaining long-term project results?** |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |

**ToR ANNEX D: UNEG Code of Conduct for Evaluators/Midterm Review Consultants[[13]](#footnote-13)**

**Evaluators/Consultants:**

1. Must present information that is complete and fair in its assessment of strengths and weaknesses so that decisions or actions taken are well founded.
2. Must disclose the full set of evaluation findings along with information on their limitations and have this accessible to all affected by the evaluation with expressed legal rights to receive results.
3. Should protect the anonymity and confidentiality of individual informants. They should provide maximum notice, minimize demands on time, and respect people’s right not to engage. Evaluators must respect people’s right to provide information in confidence, and must ensure that sensitive information cannot be traced to its source. Evaluators are not expected to evaluate individuals, and must balance an evaluation of management functions with this general principle.
4. Sometimes uncover evidence of wrongdoing while conducting evaluations. Such cases must be reported discreetly to the appropriate investigative body. Evaluators should consult with other relevant oversight entities when there is any doubt about if and how issues should be reported.
5. Should be sensitive to beliefs, manners and customs and act with integrity and honesty in their relations with all stakeholders. In line with the UN Universal Declaration of Human Rights, evaluators must be sensitive to and address issues of discrimination and gender equality. They should avoid offending the dignity and self-respect of those persons with whom they come in contact in the course of the evaluation. Knowing that evaluation might negatively affect the interests of some stakeholders, evaluators should conduct the evaluation and communicate its purpose and results in a way that clearly respects the stakeholders’ dignity and self-worth.
6. Are responsible for their performance and their product(s). They are responsible for the clear, accurate and fair written and/or oral presentation of study limitations, findings and recommendations.
7. Should reflect sound accounting procedures and be prudent in using the resources of the evaluation.

**MTR Consultant Agreement Form**

Agreement to abide by the Code of Conduct for Evaluation in the UN System:

Name of Consultant: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Name of Consultancy Organization (where relevant): \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**I confirm that I have received and understood and will abide by the United Nations Code of Conduct for Evaluation.**

Signed at *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (Place)* on *\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (Date)*

Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**ToR ANNEX E: MTR Ratings**

|  |
| --- |
| **Ratings for Progress Towards Results:** (one rating for each outcome and for the objective) |
| 6 | Highly Satisfactory (HS) | The objective/outcome is expected to achieve or exceed all its end-of-project targets, without major shortcomings. The progress towards the objective/outcome can be presented as “good practice”. |
| 5 | Satisfactory (S) | The objective/outcome is expected to achieve most of its end-of-project targets, with only minor shortcomings. |
| 4 | Moderately Satisfactory (MS) | The objective/outcome is expected to achieve most of its end-of-project targets but with significant shortcomings. |
| 3 | Moderately Unsatisfactory (HU) | The objective/outcome is expected to achieve its end-of-project targets with major shortcomings. |
| 2 | Unsatisfactory (U) | The objective/outcome is expected not to achieve most of its end-of-project targets. |
| 1 | Highly Unsatisfactory (HU) | The objective/outcome has failed to achieve its midterm targets, and is not expected to achieve any of its end-of-project targets. |

|  |
| --- |
| **Ratings for Project Implementation & Adaptive Management:** (one overall rating) |
| 6 | Highly Satisfactory (HS) | Implementation of all seven components – management arrangements, work planning, finance and co-finance, project-level monitoring and evaluation systems, stakeholder engagement, reporting, and communications – is leading to efficient and effective project implementation and adaptive management. The project can be presented as “good practice”. |
| 5 | Satisfactory (S) | Implementation of most of the seven components is leading to efficient and effective project implementation and adaptive management except for only few that are subject to remedial action. |
| 4 | Moderately Satisfactory (MS) | Implementation of some of the seven components is leading to efficient and effective project implementation and adaptive management, with some components requiring remedial action. |
| 3 | Moderately Unsatisfactory (MU) | Implementation of some of the seven components is not leading to efficient and effective project implementation and adaptive, with most components requiring remedial action. |
| 2 | Unsatisfactory (U) | Implementation of most of the seven components is not leading to efficient and effective project implementation and adaptive management. |
| 1 | Highly Unsatisfactory (HU) | Implementation of none of the seven components is leading to efficient and effective project implementation and adaptive management. |

|  |
| --- |
| **Ratings for Sustainability:** (one overall rating) |
| 4 | Likely (L) | Negligible risks to sustainability, with key outcomes on track to be achieved by the project’s closure and expected to continue into the foreseeable future |
| 3 | Moderately Likely (ML) | Moderate risks, but expectations that at least some outcomes will be sustained due to the progress towards results on outcomes at the Midterm Review |
| 2 | Moderately Unlikely (MU) | Significant risk that key outcomes will not carry on after project closure, although some outputs and activities should carry on |
| 1 | Unlikely (U) | Severe risks that project outcomes as well as key outputs will not be sustained |

**ToR ANNEX F: MTR Report Clearance Form**

*(to be completed by the Commissioning Unit and UNDP-GEF RTA and included in the final document)*

**Midterm Review Report Reviewed and Cleared By:**

**Commissioning Unit**

Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**UNDP-GEF Regional Technical Advisor**

Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

## UNDP-GEF Midterm Review

## Terms of Reference

**Standard Template 2: Formatted information to be entered in** [**UNDP Jobs website**[[14]](#footnote-14)](https://jobs.undp.org/)

**BASIC CONTRACT INFORMATION**

**Location: Podgorica, Montenegro**

**Application Deadline:**

**Category:** Energy and Environment

**Type of Contract:** Individual Contract

**Assignment Type:** Local Consultant

**Languages Required: Montenegrin and English**

**Starting Date:** (16 May 2019)

**Duration of Initial Contract:**

**Expected Duration of Assignment: 25 working days over the period of 18 weeks**

**BACKGROUND**

**A. Project Title**

Comprehensive Environmentally Sound Management of PCBs in Montenegro

##### **B. Project Description**

This is the Terms of Reference for the UNDP-GEF Midterm Review (MTR) of the full -sized project titled *Comprehensive Environmentally Sound Management of PCBs in Montenegro* (PIMS 5562) implemented through the UNDP Montenegro, which is to be undertaken in 2019. The project started on the 16th January 2017 and is in its third year of implementation. In line with the UNDP-GEF Guidance on MTRs, this MTR process was initiated before the submission of the second Project Implementation Report (PIR). The MTR process must follow the guidance outlined in the document *Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects* (see Annex).

The project Comprehensive Environmentally Sound Management of PCBs in Montenegro intends to support the country with the necessary technical and financial assistance to ensure that all the remaining PCBs in the country (estimated in not less than 900 t of PCB contaminated equipment, waste and soil) are identified and disposed of. The project will be implemented side by side with the relevant institutional and industrial stakeholders, i.e. the Ministry for Sustainable Development and Tourism, private and state owned companies, holders of PCB containing equipment. Although the project expects to solve all remaining PCBs issues in the country, it will also ensure that enough capacity for the sound management of PCBs would have been built for the management of any further such hazardous waste identified in time after project’s closure.

The disposal or decontamination of PCBs in Montenegro presents a number of issues and risks. First of all, the reliability of initial PCB inventory is very low and mostly limited to phased out equipment that needs to be disposed of. In Montenegro where most of information on PCBs from NIP inventory comes from disconnected equipment. This is due to the fact that electrical equipment (transformers, capacitors) when in good operating condition are usually not inspected for PCB content. The reasons are that:

• the cost of replacing transformer and capacitor is capital intense (very high), and

• the sampling and analysis of in-use equipment is a complex task requiring a significant coordination effort (for instance, coordination with maintenance schedule of electric equipment).

A second feature is that, being not immediately perceived as a hazard by the common public, the issue of PCBs is very often given a low priority from the authorities. Therefore, the existing legislation on PCB is not effectively enforced. As explained in the chapter above, although the Montenegrin legislation is well advanced and generally compliant with the Stockholm convention and the EU directive on PCBs management, and the government updated the inventory of PCB waste, the requirements related to the PCB management plans, and PCB “logbooks” are almost completely disregarded. In the absence of a sound level of enforcement of current legislation, even the industry’s commitment to address the issue of PCBs – given the high costs related to the decontamination or disposal (with subsequent replacement) of contaminated equipment – is low. For this reason, the national PCB management situation can be effectively addressed only if the government’s commitment and capacity are high.

A third feature is the lacking of PCB treatment technologies at local level. This is a common feature in many countries supported by UN/GEF projects in PCBs management. This usually results in industries undertaking substantial investment for shipping PCB contaminated equipment for abroad, typically EU, for disposal. In the case of Montenegro, there are no technologies for treatment of low PCB-contaminated equipment or disposal facilities available for high PCB contaminated equipment or waste, therefore until now only the highly PCB contaminated equipment has been to date treated by shipping and disposal abroad.

The project strategy is therefore designed to address simultaneously all these important aspects as outlined below.

1) Increasing national PCB management capacities and the enforcement of the legislation. This will require working side by side with the control authorities (mainly the Ministry for Sustainable Development and Tourism) and the key stakeholders (the electric power industry and other potential owners of PCB containing equipment) to:

• develop and implement a practical guidance on PCB environmentally sound management (ESM);

• provide assistance in fulfillment of legal obligations towards recording and reporting PCB related information;

• conduct inspections at sites where electrical equipment (transformers, capacitors) operates,

• train operators and officers on both sides – the governmental authorities and PCB equipment/waste owners.

2) Increasing the industry and general awareness. PCBs are very often a not very well known environmental issue. Except for extremely high pollution levels, resulting in acute and immediate health impacts, the toxic effect of PCBs (increase of cancer probability) is delayed in time and not associated to any “visible” pollution like black smoke from open burning or factories’ stacks or turbidity in water. Therefore, the PCB hazard is usually not perceived as an immediate threat by many. However, an unsafe disposal of PCBs results in the contamination of food chain and other environmental media (like, for instance, sediments and soil) which may last for years. PCBs have been recently (March 2013) re-assessed by the IARC and are now classified as “known human carcinogens (class 1)” compared to the previous “probable human carcinogens (class 2)” category. There is therefore the need to inform the main stakeholders and the public at large on the benefit brought by the project so that the government and the industry are encouraged in undertaking necessary actions.

3) Engagement of stakeholders. As in other environmental programmes, only in case of key stakeholder’s buy-in, the project’s goals can be satisfactorily achieved. No major change in current practices can be achieved if there is little or no awareness of the risks posed by PCBs, and if stakeholders do not feel the need to address the PCB management issue once and for all. As previously described in more detail, the project had identified at PIF stage a number of important stakeholders which will be involved in all project activities during its implementation. Besides MoSDT, which will be the national implementing institution, key PCB holders, like EPCG (both for electricity generation and distribution) and KAP were informed on the project’s related benefits and on the expected and required level of commitment towards it. As a result, they participated proactively in all the project development activities, including providing lists of their power equipment and facilitating oil sampling and analysis for PCB content. More stakeholder engagement, by involving other line Ministries, academic institutions and NGO sector is planned during the project implementation which will too include civil society associations, trade unions, and other beneficiaries.

4) Strengthening the reliability of information through updating of the PCB inventory. At PIF stage, the only available information was related to the list of phased-out PCB equipment and waste, a few pure PCB transformers, online or stored at KAP, oil tanks and contaminated material (sawdust, soil, waste) potentially contaminated by PCBs. Due to the low enforcement of the legislation, there was very little information available on the concentration of PCB online equipment. The information concerning the number, age and level of contamination of PCB equipment is indeed essential for both management purposes and identification of the proper treatment / disposal technologies. This situation was already evident at the PIF formulation stage, and therefore the main focus in the preliminary inventory carried out during preparation of the FSP project document concerned existing offline and online equipment at EPCG company. At same time, only limited PCB content in transformers stored or online at KAP was re-confirmed, including that data on PCB contaminated soil. The project will continue consolidating the PCB inventory by undertaking dielectric oil sampling and analytical determination of PCBs in 3,000 pieces of equipment during the first two years of its implementation.

5) Provide know-how and financial support on the technologies for the disposal of PCB equipment. Clearly, one of the central issues on the side of PCB ESM concerns the availability of technical and financial resources for PCB disposal. In the absence of a sound know-how related to disposal operations of PCB contaminated equipment, the cost / benefit ratio is always very high, for the following reasons:

• the options allowing the chemical destruction of the PCBs in the dielectric oil without destroying the oil itself are usually not considered, so that the dielectric oil, which is usually a very expensive asset, is lost;

• the planning of PCB equipment phasing out is not aligned with their residual value, so that very often a strategy aimed at minimizing the cost of disposal of PCB contaminated equipment is not pursued; and

• the legal aspects related to the storage of PCB containing equipment under maintenance versus PCB phased out equipment (to be considered waste) are usually neglected, exposing therefore owners of PCB equipment to a severe liability risk.

The project budget from the GEF Trust Fund is 3,5 mil USD, UNDP TRAC resources are 50,000 USD and total co-financing is 19,803,691 USD.

**DUTIES AND RESPONSIBILITIES**

##### **C. Scope of Work and Key Tasks**

The MTR team will consist of two independent consultants that will conduct the MTR - one team leader (with experience and exposure to projects and evaluations in other regions globally) and one local expert.

The MTR team will first conduct a document review of project documents (i.e. PIF, UNDP Initiation Plan, Project Document, ESSP, Project Inception Report, PIRs, Finalized GEF focal area Tracking Tools, Project Appraisal Committee meeting minutes, Financial and Administration guidelines used by Project Team, project operational guidelines, manuals and systems, etc.) provided by the Project Team and Commissioning Unit. Then they will participate in a MTR inception workshop to clarify their understanding of the objectives and methods of the MTR, producing the MTR inception report thereafter. The MTR mission will then consist of interviews and site visits to UNIPROM KAP, CEDIS, HEMOSAN in Bar.

The MTR team will assess the following four categories of project progress and produce a draft and final MTR report. See the [*Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects*](http://web.undp.org/evaluation/documents/guidance/GEF/mid-term/Guidance_Midterm%20Review%20_EN_2014.pdf). No overall rating is required.

1. **Project Strategy**

*Project Design:*

* Review the problem addressed by the project and the underlying assumptions. Review the effect of any incorrect assumptions or changes to the context to achieving the project results as outlined in the Project Document.
* Review the relevanced of the project strategy and assess whether it provides the most effective route towards expected/intended results.
* Review how the project addresses country priorities
* Review decision-making processes

*Results Framework/Logframe:*

* Undertake a critical analysis of the project’s logframe indicators and targets, assess how “SMART” the midterm and end-of-project targets are (Specific, Measurable, Attainable, Relevant, Time-bound), and suggest specific amendments/revisions to the targets and indicators as necessary.
* Examine if progress so far has led to, or could in the future catalyse beneficial development effects (i.e. income generation, gender equality and women’s empowerment, improved governance etc...) that should be included in the project results framework and monitored on an annual basis.
1. **Progress Towards Results**
* Review the logframe indicators against progress made towards the end-of-project targets; populate the Progress Towards Results Matrix, as described in the *Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects*; colour code progress in a “traffic light system” based on the level of progress achieved; assign a rating on progress for the project objective and each outcome; make recommendations from the areas marked as “not on target to be achieved” (red).
* Compare and analyse the GEF Tracking Tool at the Baseline with the one completed right before the Midterm Review.
* Identify remaining barriers to achieving the project objective.
* By reviewing the aspects of the project that have already been successful, identify ways in which the project can further expand these benefits.
1. **Project Implementation and Adaptive Management**

Using the *Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects*; assess the following categories of project progress:

* Management Arrangements
* Work Planning
* Finance and co-finance
* Project-level monitoring and evaluation systems
* Stakeholder Engagement
* Reporting
* Communications
1. **Sustainability**

Assess overall risks to sustainability factors of the project in terms of the following four categories:

* Financial risks to sustainability
* Socio-economic risks to sustainability
* Institutional framework and governance risks to sustainability
* Environmental risks to sustainability

The MTR consultant/team will include a section in the MTR report setting out the MTR’s evidence-based **conclusions**, in light of the findings.

Additionally, the MTR consultant/team is expected to make **recommendations** to the Project Team. Recommendations should be succinct suggestions for critical intervention that are specific, measurable, achievable, and relevant. A recommendation table should be put in the report’s executive summary. The MTR consultant/team should make no more than 15 recommendations total.

##### **D. Expected Outputs and Deliverables**

The MTR consultant/team shall prepare and submit:

* MTR Inception Report: MTR team clarifies objectives and methods of the Midterm Review no later than 2 weeks before the MTR mission. To be sent to the Commissioning Unit and project management. Approximate due date: (10 June 2019)
* Presentation: Initial Findings presented to project management and the Commissioning Unit at the end of the MTR mission. Approximate due date: (28 June 2019)
* Draft Final Report: Full report with annexes within 3 weeks of the MTR mission. Approximate due date: (19 July 2019)
* Final Report\*: Revised report with annexed audit trail detailing how all received comments have (and have not) been addressed in the final MTR report. To be sent to the Commissioning Unit within 1 week of receiving UNDP comments on draft. Approximate due date: (20 September 2019)

\*The final MTR report must be in English. If applicable, the Commissioning Unit may choose to arrange for a translation of the report into a language more widely shared by national stakeholders.

**E. Institutional Arrangement**

The principal responsibility for managing this MTR resides with the Commissioning Unit. The Commissioning Unit for this project’s MTR is *UNDP Montenegro.*

The Commissioning Unit will contract the consultants and ensure the timely provision of per diems and travel arrangements within the country for the MTR team. The Project Team will be responsible for liaising with the MTR team to provide all relevant documents, set up stakeholder interviews, and arrange field visits.

**F. Duration of the Work**

The total duration of the MTR will be approximately *25 days* over a period of 18 w*eeks* starting 16 May 2019*,* and shall not exceed five months from when the consultant(s) are hired. The tentative MTR timeframe is as follows:

* *20 April 2019:* Application closes
* *15 May 2019:* Selection of MTR Team
* *16 May 2019:* Prep the MTR Team (handover of project documents)
* *16 May - 28 May 2019, 4 days:* Document review and preparing MTR Inception Report
* *3 June – 10 June 2019, 2 days:* Finalization andValidation of MTR Inception Report- latest start of MTR mission
* *24 June – 28 June 2019, 6 days:* MTR mission: stakeholder meetings, interviews, field visits
* *28 June 2019:* Mission wrap-up meeting & presentation of initial findings- earliest end of MTR mission
* *29 June – 19 July 2019, 10 days:* Preparing draft report
* *16 September – 20 September 2019, 2 days:* Incorporating audit trail on draft report/Finalization of MTR report (note: accommodate time delay in dates for circulation and review of the draft report)
* *16 September 2019:* Preparation & Issue of Management Response
* *n/a:* (optional)Concluding Stakeholder Workshop (not mandatory for MTR team)
* *20 September 2019:* Expected date of full MTR completion

The date start of contract is 16 May 2019.

**G. Duty Station**

Duty station for this assignment would be Podgorica, Montenegro with travel to Bar.

**Travel:**

* International travel will be required to Montenegro during the MTR mission;
* The Basic Security in the Field II and Advanced Security in the Field courses must be successfully completed prior to commencement of travel;
* Individual Consultants are responsible for ensuring they have vaccinations/inoculations when travelling to certain countries, as designated by the UN Medical Director.
* Consultants are required to comply with the UN security directives set forth under <https://dss.un.org/dssweb/>
* All related travel expenses will be covered and will be reimbursed as per UNDP rules and regulations upon submission of an F-10 claim form and supporting documents.

**REQUIRED SKILLS AND EXPERIENCE**

**H. Qualifications of the Successful Applicants**

Local expert will be engaged to support Mid Term Evaluation by preparing necessary inputs for the Team Leader to conduct the evaluation and prepare respective reports. Local Expert will review all relevant sources of information, such as the project document, project progress reports – including Inception Report, Annual APR/PIR,  documents produced in the scope of the project etc, GEF focal area tracking tools, project files, national strategic and legal documents, and any other materials that the team leader considers useful for this evidence-based assessment.

Local Expert will have the task to conduct most interviews with selected stakeholders outside Podgorica in the inception phase, based on the selection done jointly with the Team Leader and Project Team, and to accompany the team leader in interviews scheduled during his/her field mission.

The selection criteria for the Local Expert are the following:

* University degree in natural or social sciences, Master’s degree would be considered as an asset – 15%
* Minimum 5 years of working experience in the fields relevant to this ToR – environment, chemicals, waste management; - 20%
* Experience in project evaluation / experience with results‐based monitoring and evaluation methodologies – 20%
* Excellent social, facilitation and communication skills; - 10%
* Working experience with UN organizations and donors (GEF) is considered to be an asset; - 15%
* Demonstrated understanding of issues related to gender mainstreaming in issues related to environment portfolio; - 10%
* Fluency in English and Montenegrin both written and spoken. – 10%

***Consultant Independence:***

The consultants cannot have participated in the project preparation, formulation, and/or implementation (including the writing of the Project Document) and should not have a conflict of interest with project’s related activities.

**APPLICATION PROCESS**

**I. Scope of Price Proposal and Schedule of Payments**

***Financial Proposal:***

* Financial proposals must be “all inclusive” and expressed in a lump-sum for the total duration of the contract. The term “all inclusive” implies all cost (professional fees, travel costs, living allowances etc.);
* For duty travels, the UN’s Daily Subsistence Allowance (DSA) rate is 110€ for Podgorica, which should provide indication of the cost of living in a duty station/destination *(Note: Individuals on this contract are not UN staff and are therefore not entitled to DSAs. All living allowances required to perform the demands of the ToR must be incorporated in the financial proposal, whether the fees are expressed as daily fees or lump sum amount.)*
* The lump sum is fixed regardless of changes in the cost components.

***Schedule of Payments:***

10% of payment upon approval of the MTR Inception Report

40% upon submission of the draft MTR Report

50% upon finalization of the MTR Report

**J. Recommended Presentation of Offer**

1. Completed **Letter of Confirmation of Interest and Availability** using the [template](https://intranet.undp.org/unit/bom/pso/Support%20documents%20on%20IC%20Guidelines/Template%20for%20Confirmation%20of%20Interest%20and%20Submission%20of%20Financial%20Proposal.docx) provided by UNDP;
2. **Personal CV or a** [**P11 Personal History form**](http://www.undp.org/content/dam/undp/library/corporate/Careers/P11_Personal_history_form.doc), indicating all past experience from similar projects, as well as the contact details (email and telephone number) of the Candidate and at least three (3) professional references;
3. **Brief description of approach to work/technical proposal** of why the individual considers him/herself as the most suitable for the assignment, and a proposed methodology on how they will approach and complete the assignment; (max 1 page)
4. **Financial Proposal** that indicates the all-inclusive fixed total contract price, supported by a breakdown of costs, as per template provided. If an applicant is employed by an organization/company/institution, and he/she expects his/her employer to charge a management fee in the process of releasing him/her to UNDP under Reimbursable Loan Agreement (RLA), the applicant must indicate at this point, and ensure that all such costs are duly incorporated in the financial proposal submitted to UNDP. See Letter of Confirmation of Interest template for financial proposal template.

Incomplete applications will be excluded from further consideration.

**K. Criteria for Selection of the Best Offer**

The award of the contract will be made to the Individual Consultant who has obtained the highest Combined Score and has accepted UNDP’s General Terms and Conditions. Only those applications which are responsive and compliant will be evaluated. The offers will be evaluated using the “Combined Scoring method” where:

1. The educational background and experience on similar assignments will be weighted a max. of 70%;
2. The price proposal will weigh as 30% of the total scoring.

**L. Annexes to the MTR ToR**

* Guidance for Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects
* UNDP-GEF MTR Report Audit Trail Template
1. For ideas on innovative and participatory Monitoring and Evaluation strategies and techniques, see [UNDP Discussion Paper: Innovations in Monitoring & Evaluating Results](http://www.undp.org/content/undp/en/home/librarypage/capacity-building/discussion-paper--innovations-in-monitoring---evaluating-results/), 05 Nov 2013. [↑](#footnote-ref-1)
2. For more stakeholder engagement in the M&E process, see the [UNDP Handbook on Planning, Monitoring and Evaluating for Development Results](http://www.undg.org/docs/11653/UNDP-PME-Handbook-%282009%29.pdf), Chapter 3, pg. 93. [↑](#footnote-ref-2)
3. Populate with data from the Logframe and scorecards [↑](#footnote-ref-3)
4. Populate with data from the Project Document [↑](#footnote-ref-4)
5. If available [↑](#footnote-ref-5)
6. Colour code this column only [↑](#footnote-ref-6)
7. Use the 6 point Progress Towards Results Rating Scale: HS, S, MS, MU, U, HU [↑](#footnote-ref-7)
8. Alternatively, MTR conclusions may be integrated into the body of the report. [↑](#footnote-ref-8)
9. Engagement of the consultants should be done in line with guidelines for hiring consultants in the POPP: <https://info.undp.org/global/popp/Pages/default.aspx> [↑](#footnote-ref-9)
10. <https://intranet.undp.org/unit/bom/pso/Support%20documents%20on%20IC%20Guidelines/Template%20for%20Confirmation%20of%20Interest%20and%20Submission%20of%20Financial%20Proposal.docx> [↑](#footnote-ref-10)
11. <http://www.undp.org/content/dam/undp/library/corporate/Careers/P11_Personal_history_form.doc> [↑](#footnote-ref-11)
12. The Report length should not exceed *40* pages in total (not including annexes). [↑](#footnote-ref-12)
13. [www.undp.org/unegcodeofconduct](http://www.undp.org/unegcodeofconduct) [↑](#footnote-ref-13)
14. https://jobs.undp.org/ [↑](#footnote-ref-14)