## Sheet1
conclusions | recommendations | learned lessons
The project was designed to advance, in parallel, on three highly challenging fronts: i) modify the serious trends and patterns of ecosystem degradation observed in Chile's Mediterranean Ecoregion; ii) strengthen organized communities so they can act in concert to identify and implement appropriate technical innovations to generate environmental and global benefits; and iii) develop a new model of sustainable rural development based on coordinated institutional action. It is clear that addressing the three fronts aforementioned meant developing a complex project, with several assumptions, ambitious proposals for mechanisms and very demanding goals that were not fulfilled. All these design factors are very relevant to the weak results achieved. | Projects should avoid facing several challenges and complex problems simultaneously, especially when some of them combine several levels of work that require very different capacities and partnerships. | In complex projects, which work at different levels and thematic dimensions, the requirements of active and strongly articulated presence between the implementing agency, the agency responsible for the execution and the execution team, are critical to maximize the possibilities of progress towards results and must therefore consider the necessary human and material resources in the design of the project.
conclusions | recommendations | learned lessons
The greatest achievement of the project was the strengthening and empowerment of the participating community organizations. The execution of this component presented great successes and quite a lot of continuity throughout the project's development. This situation has resulted in a very significant advance in the development of methodologies for strengthening and empowering the rural population in the management of self-managed development projects, which will undoubtedly be very useful for other projects and for national initiatives in support of the rural population | Rapid progress must be made in systematizing and disseminating the methodologies used to develop component 4, and, if possible, holding workshops that allow for the transfer of such methodologies and lessons learned to other public services. | Project design problems can have a severe impact on certain outcomes without having the same impact on others. This must be considered in order to maximize the use of the experience, both successful and negative
Progress in biodiversity conservation, carbon sequestration and ecosystem services is very limited. The activities developed by the project are mainly agricultural, therefore, not relevant, nor projected for the conservation of the various species and habitats of the Mediterranean Ecoregion. On the other hand, the types of land and type of property in which such activities were developed do not correspond with the types of land and type of property predominant in the 352 thousand ha covered by the IET. | Great care must be taken to define indicators in the project design so that they are compliant and measurable. One way to minimize this problem is by consulting extensively with institutions that are experts in the issues identified during project development.
The design of the project explains an important part of the limitations in the progress towards its results. Generally, the project's focus on small farmers who have land that, in the case of the vast majority, is devoid of ecosystem assets and habitats in the ecoregion, which generated difficulties when designing activities relevant to the project's objective and, therefore, the project was unable to develop experiences that could be scaled up to the ecoregion. Basically, there were very ambitious indicators and goals that are impossible to achieve. |  | It is extremely important to create appropriate indicators for the desired results of any project, since very ambitious goals can lead to serious delays in project implementation, such as having to request authorization from the GEF to change poorly conceived indicators.
| The design of projects must pay strong attention to the extent to which the territorial assets of the central subjects, with whom we work with, are relevant and sufficient so that the interventions can generate a staggered aggregation of benefits to support progress towards the objective and the achievement of global environmental benefits. | At the time of their implementation, projects must be carefully analyzed, paying particular attention to determining the mechanisms that lead to the generation of the benefits that they propose, so as to generate a relevant strategy for this purpose and the appropriate M&E mechanisms
conclusions | recommendations | learned lessons
The project did not develop actions to project the criteria established for the identification of IET, for the identification of conservation assets at the level of locality and property. This weakness meant that the actions developed did not pay attention to such assets and therefore did not generate, by aggregation, benefits for the conservation of the macro-region's biodiversity, and therefore did not generate global benefits either. | Projects working at various spatial levels must develop criteria and methodologies that allow them to identify conservation objectives at different scales, so that they can be identified and incorporated into interventions. This allows for the generation of global benefits in a staggered manner, from the most local territorial levels to the most aggregated levels. | Conservation assets are not distributed homogeneously in the matrix, which leads to the need to develop methodologies relevant to each type of asset and each scale
The shortcomings observed in the progress of results 1, 2 and 3 limit the possibility that the methodologies developed in result 4 incorporate relevant criteria for biodiversity conservation, or carbon capture/emission avoided.
The processes of rural-urban migration (and also of return to the rural community) showed positive examples of leadership, openness and renewal of practices among local communities. This gave a broader view of the social and environmental phenomena affecting communities. | Reverse migration processes (city - countryside) should be seriously considered in the design of projects aimed at rural and farming areas, in order to incorporate new visions and types of roles among local beneficiaries. | Reverse migration leaderships can bring greater understanding and initial openness to projects that seek to introduce change and complex issues among rural communities.
There is a large participation of women in organizations at the rural level, who show high levels of participation and assume leadership roles with high frequency. | The new projects should include, from their design, the realization of studies that make a comparison between the initial and final situation, but also provide an understanding of both the causes of the initial situation, as well as the changes introduced and the keys that give rise to such changes. | The rigorous documentation of background information and the development of gender strategies from the beginning of the projects, will allow the developed initiatives to better reflect the vision and needs of women, their visions and interests and allows future projects to use this experience from their design.
The design of the CMS contemplated a very small and centralized professional team in Santiago, with no counterpart in the regions where the project was executed, causing a great expense in travel and little operation in the field, which meant great problems of execution during the first phase of the project. | Projects that have a strong operational character and broad areas of intervention, must have sufficient technical teams deployed in the field from the beginning of the project and with the necessary implementation capabilities and achieve the replicability and scalability of the intervention models developed. | Underestimating the number and type of professional support a project needs can have a negative impact on the installation stage of the project and produce inefficiencies that will impact the approach and results of the projects.
conclusions | recommendations | learned lessons
M&E System
Project design issues should be addressed early in project implementation, either during the kick-off workshop or by establishing a thorough project review with key partners, while considering a planning and M&E system that allows for timely and documented adaptive management. Unfortunately, the first implementation team began to implement activities without adequate planning or justification, which eventually impacted the entire project execution cycle. | It is recommended that project teams, along with their key partners, conduct a thorough review of the project document, its strategy, and its indicators and assumptions - including the possibility of inviting the person who wrote the project to participate in this process - before beginning to implement actions. | Project implementation should begin with a thorough understanding of the project's strengths and weaknesses, as well as making the necessary adjustments early on. This will result in effective execution that is more in line with project objectives, while at the same time improving efficiency in the management of resources.
The project's M&E system was partially complete, being adequate to verify progress in the implementation of project activities and products, but was insufficient to monitor and verify the desired changes in the different environmental and socioeconomic dimensions, at the local and territorial level | For complex projects such as the CMS, it is recommended that an M&E person be available to design a system that not only defines procedures for monitoring outputs and activities, but also develops an M&E plan that defines a set of indicators and results that are specific to each level of the project and directly related to the various overall project results. | The establishment of a good M&E system will allow projects to measure not only their performance, but also to have certainty regarding the contribution of the various outputs and partial results to the overall expected results of the projects.
Achievement of Results
The CMS managed to reintroduce the concept of community work among local organizations, demonstrating that significant improvements can be achieved for the collective. It also strengthened local organizations and advisory bodies in technical and managerial aspects, as well as improving the self-esteem of their members, demonstrating that they can plan and manage their community projects. | The design of GEF projects should always include a community organization development component, so that they contribute to strengthening these organizations in their technical and management capacities. | Trained and empowered communities can greatly increase the effectiveness and sustainability of the projects in which they participate,
Inter-agency coordination and the adoption of new approaches to the APF were limited in scope, and this coordination was subordinated to the interest of the official involved. With respect to the FPA, the approach remains the same as before the project, with modest progress being made by launching special competitions. | The MMA should promote an articulation with the Ministries, services and municipalities involved in the different IET to establish mechanisms that respond to the interest of different communities, to continue advancing, and to support them in a process that leads to the "graduation" of these, to continue their route in a more autonomous way. | The goals and assumptions of modifying laws and reorganizing areas of the State located in other ministries require a political effort that far exceeds the capabilities of the teams in charge of implementing the projects.
Coordination of public actors requires a coordinating agent who is at least in a high and central position in the government structure.
conclusions | recommendations | learned lessons
Differences and Similarities between CMS, FPA and PPS-Chile
The FPA and the PPS-Chile have similarities in that both require beneficiaries to compete for funding and both have very local impacts. However, the FPA functions as a fund that defines the environmental issues to be addressed in each competition, where public officials select the projects that are ultimately awarded. On the other hand, PPS-Chile has made for a more participatory organization made up of a board of directors that includes public services and OSC. | The differential and aggregate impact on the issues of self-esteem, community work and organizational development, which generate the longest duration of the projects; the higher financial amounts, the participation of users in the definition of the issues to be addressed in the projects; and the sustained and close technical support throughout the development of the project should be studied. | The local governance model implemented in the PPS-Chile and strengthened in the CMS, means great advances in organizational development, empowerment and development of innovations relevant to the local reality.
Gender and indigenous peoples
The project was concerned with generating a study on the situation of indigenous and peasant women of different ages in the intervened territories during 2016. However, this valuable information was not translated into a strategy to address the issue, nor into concrete plans and activities. Instead, the gender issue was relegated to the number of women participating in the CMS. | It is suggested that any studies conducted be quickly transformed into concrete actions that address the needs of these groups. | An early analysis of the conditions of women and other marginalized groups will enhance the inclusive approach that UNDP has been promoting.
Although there was no formal strategy, in the indigenous issue perhaps the approach was more culturally relevant. The CMS successfully provided cultural translators and strengthened small indigenous consulting companies that transferred knowledge to community organizations in very successful projects, as for example in the case of Pedregoso, where the actions seems to have a good chance for sustainability. | Early studies on the needs and potential of these groups are suggested to develop a strategy to effectively incorporate them into project activities.
Sustainability
The sustainability of the results achieved to date have little likelihood of continuity, due to the lack of an exit strategy for the project, as well as the lack of systematization of the experience and lessons learned. | It is suggested to install an agreed upon agenda with the partners, based on the project's exit strategy, so that the issue remains installed in the institutions, even if they do not have priority in the short term. | The exit strategy of any project, as well as the systematization of its experience and lessons learned, must be carried out within a prudent timeframe that allows the executing team to implement the first steps of this strategy and to disseminate the experience among the key actors.
Citizens' expectations of the October 2020 plebiscite and the upcoming municipal, presidential and gubernatorial elections in 2021 could change the level of priorities for CMS-related programs and activities in the short and medium term.