## impact-results
Table 7. Project Theory of Change Analysis
Causal Pathways | Objective and results | [6 empty] | Impacts
| Objective: To develop, demonstrate and integrate the achievement of important environmental benefits by community organizations in the management of seriously threatened territories in the Chilean Mediterranean Ecoregion. | [6 empty] | Biodiversity of global importance preserved thanks to : i) reduced rate of loss of forest ecosystems in the Chilean Mediterranean ecoregion; ii) restored and enabled forest ecosystems in the Chilean Mediterranean ecoregion; iii) improved and protected agro-ecosystem environmental services
| Results |  | Logical | Assumptions | Media chain towards results | Impact Drives | Intermediate results
Conservation, restoration and improvement strategy | 1. Sustainable management of landscapes for biodiversity conservation | 1.1. Conservation of Mediterranean forest territories through community actions, with a minimum of 700,000 ha of certified and sustainably managed Mediterranean forest. | Results and products do not have definition problems | Wrong assumptions make it very unlikely that the sub-result will be achieved. | The assumptions underlying sub-result 1.1 make it very unlikely that this sub-result, result 1 and impacts (i) and (ii) will be achieved, and the impact will be seriously affected | 1. Sectoral Ministry coordinates the institutional action of sustainable rural development taking the experience of the project and with the support of the MMA; 2. To have both technical and financial support mechanisms to support and replicate existing experiences; 2. There is joint governance between the communities, large and medium owners, and the relevant government agencies in the development of the territory; and 3. Communities gain the skills and knowledge to make decisions, manage, monitor carbon stocks and maintain environmental services in their territories | A land management system for production landscapes that conserve biodiversity agreed, coordinated and implemented by local communities, large and medium-sized landowners and relevant government agencies.
|  | 1.2. The long-term sustainability of territorial management in the Mediterranean Ecoregion is improved and strengthened at the institutional and financial level. | There is a very ambiguous wording of the sub-result | The fragile assumptions regarding the existence of a territorial management system in the EM and institutional and financial management mechanisms can be traced back, but the assumption that the MMA has the institutional and role capacities and conditions to improve the EM' territorial management is unsustainable. | i) The assumption regarding the capacities and role of the MMA seriously threatens the possibility of achieving the sub-result, but does not prevent, although it seriously affects, the possibilities of achieving the result and achieving the impacts i) and ii) affecting also iii); and ii) although PRODOC establishes coordination and articulation actions at various points, it is clear, from the point of view of the media chain towards results, that the project should have generated a formal and stable mechanism, independent of the existence of the project, for the coordination of public agencies in charge of rural development and their resources to advance towards the sustainability of the EM. This system is placed on intermediate results, but seems to be more of a weakness of the chain established by PRODOC.
| 2. Demonstration and promotion of conservation and enhancement of carbon stocks through land use, land use change and forestry, and local carbon monitoring systems |  | The statement of this result, is more like a product than a result. | Wrong assumptions make it unlikely to achieve what the product-result is looking for. | In this case, the chain from means to results is discontinued due to the weaknesses in the construction of the result. This fact is also expressed in the fact that the issue of capturing/avoiding CO2 emissions has a low presence in PRODOC, which does not allow it to be openly placed in the impacts, where it appears implicitly in the services of the agro-ecosystems. |  | Carbon stocks maintained and enhanced by communities and other relevant stakeholders, through the implementation of a payment system for carbon credits
| 3. Maintaining and improving the flow of forest and agro-ecosystem services to sustain the livelihoods of local communities |  | Results and products do not have definition problems. | Erroneous assumptions make it very unlikely that the result will be achieved in terms of maintaining and improving the flow of forest services; similarly, there may be a reduced scope for agro-ecosystem services. | The assumptions on which this result is based lead to the consideration that the result with respect to forest services is very unlikely to be achieved; similarly, progress towards agro-ecosystem flows is likely to be more limited than assumed. Based on the above, progress towards impact (iii) is significantly limited. |  | The EM has an improvement in the flow of agro-ecosystem services that are adopted by the owners and relevant actors of the territory.
Strategy of strengthening | 4. Community capacity building and knowledge management |  | Results and products do not have definition problems. | No wrong assumptions are appreciated. | Conditioned to the impact of what happens with the other results, it is considered that the chain of means to results is well constructed in this case and therefore this result generates a good support in the chain of means to results, to advance towards the impacts. |  | Communities apply sustainable forestry and agro-ecological production techniques to safeguard biodiversity, carbon stocks and critical environmental services.

## result 1
Result 1
Impact | Result |  | Comments/Assumptions | Products | Analysis
Biodiversity of global importance preserved thanks to : i) reduced rate of loss of forest ecosystems in the Chilean Mediterranean ecoregion; ii) restored and enabled forest ecosystems in the Chilean Mediterranean ecoregion; iii) improved and protected agro-ecosystem environmental services | SUSTAINABLE MANAGEMENT OF LANDSCAPES FOR BIODIVERSITY CONSERVATION | 1.1 Conservation of Mediterranean forest areas through Community actions, with a minimum of 700,000 ha of certified and managed Mediterranean forest sustainable. | Assumptions: 1. the small landowners (PP), central users of the project have Mediterranean forest (BM) in medium or good state of conservation; 2. the area of BM in the hands of PP, is significant; 3. the BM of the PP are adjacent to BM in the hands of other PP; 4. the products that the PP extract from the BM have consolidated and formal markets that value and use certification mechanisms | 1. Eighteen community-led integrated management plans for key Mediterranean landscapes. | The relationship between means and results is solid in this result, within the framework of what was also proposed in result 4. However, the basic assumptions seem not to be fulfilled according to the following figures and data: i) agriculture occupies 70-75% of the surface of the Mediterranean ecoregion (EM) the figure (provided by PRODOC) seems wrong, for the whole EM. However, it is plausible in the area that the project planned to intervene; ii) The original remaining vegetation (ecosystems of the MA) reaches only 15% of what it was (again the data seems erroneous, but plausible for the area to be intervened); iii) PP have 18% of the area of the EM (another data from PRODOC indicates 25%); iv) the EM is highly fragmented; and v) the participants have an average area of six to seven hectares, with most having only one hectare or less. The above data show that the surface of EM in the hands of the PP is only 2.7%, which makes it illusory to think that the project can achieve progress towards the impacts (i) and (ii), a situation that is aggravated by the fragmentation of the EM, which together with the small surface area of the PP (6-7 ha at most) makes the efforts to achieve such impacts unfeasible, beyond the period we are considering. It should also be remembered that, in general, biodiversity conservation requires, as PRODOC proposes, management at the landscape level, in which the combination of actions on connected lands is essential to achieve results. Such a situation, both because of the size of the PP property, the discontinuity of its ownership and the deterioration of the few mini-fragments of BM that the PP may have, is of very low probability that it is among these stakeholders.
2. Twenty or more community forest management associations formed
3. Veinte o más planes de gestión forestal comunitaria para optimizar la conservación de la biodiversidad, los servicios del ecosistema y los valores productivos a lo largo del territorio
4. Twenty or more community forest management plans implemented
5. Community-adapted forest monitoring techniques and guidelines developed and disseminated
6. Certified production of timber and other forest products on at least 700,000 ha of land (>20 projects)
7. Microfinance mechanisms in place to increase market access by producer
|  | 1.2. The long-term sustainability of territorial management in the Mediterranean Eco-region is improved and strengthened at the institutional and financial level. | 1. Although it is not entirely clear, the statement is based on the assumption that there is territorial management in the Mediterranean Ecoregion; 2. subsidiarily, there is an assumption that there are n institutional and financial mechanisms for the management of the EM; and 3. the MMA has the capacity and institutional and role conditions to improve the EM's territorial management in financial and institutional terms | 8. A formal Partners Committee of institutional stakeholders with clear accountability and governance mechanisms | The relationship of means to results is weak, firstly, because the result is ambiguous. However, the most relevant fact is that the products do not lead to territorial management in the Mediterranean Ecoregion being improved and strengthened at the institutional and financial level in the short or medium term, given that with the exception of product 9 (1.2.2 in PRODOC), the rest of the products are located and impact exclusively during the development of the project, as they are project management instruments. Among the assumptions, it should be noted that the MMA does not have the institutional and role capacities and conditions to improve the EM's territorial management in the financial and institutional areas. The MMA is not in a position to coordinate and articulate changes in the management modality and methodologies used to support the PP sector.
9.Modified instruments of the Ministry of the Environment to support the strategic objectives of global environmental protection and local sustainable development in the Mediterranean Ecoregion
10. At least three institutional instruments of non-MMA participating members of the Committee - financial, programmatic, and regulatory - reviewed to support the strategic objectives of environmental protection and sustainable local development in the Mediterranean Ecoregion.
11. A high-level Advisory Council (CATEM) to provide technical and strategic advice to the Committee.

## result 2
Result 2
Impact | Result | Comments/Assumptions | Products | Analysis
Biodiversity of global importance preserved thanks to : i) reduced rate of loss of forest ecosystems in the Chilean Mediterranean ecoregion; ii) restored and enabled forest ecosystems in the Chilean Mediterranean ecoregion; iii) improved and protected agro-ecosystem environmental services | 2. Demonstration and promotion of conservation and enhancement of carbon stocks through land use, land use change and forestry, and local carbon monitoring systems | Comment: The statement of this result, is more similar to a product than a result. Assumptions: see assumptions 1, 2 and 3 of sub-result 1.1 | 12. Five pilot demonstrations of best practices, 200 ha each, for reducing carbon stock emissions or sequestering carbon such as forest fire suppression or prevention, reforestation, restoration, and improved land use planning and management. | As already indicated, this result, as it has weaknesses in being an actual result, constitutes a chain of means to results that is discontinuous. On the other hand, assumptions 1, 2 and 3 attempt to undermine the achievement of what is sought at this point (see analysis of sub-result 1.1)

## result 3
Result 3
Impact | Result | Comments/Assumptions | Products | Analysis
Biodiversity of global importance preserved thanks to : i) reduced rate of loss of forest ecosystems in the Chilean Mediterranean ecoregion; ii) restored and enabled forest ecosystems in the Chilean Mediterranean ecoregion; iii) improved and protected agro-ecosystem environmental services | 3. Maintaining and improving the flow of forest and agro-ecosystem services to sustain the livelihoods of local communities. | Assumptions: The assumptions, regarding forest services, are the same as already indicated in sub-result 1.1 (assumptions 1,2 and 3). On the other hand, the average size of the PP plots, generates doubts about the possible levels of scaling in terms of maintaining and improving the flow of agro-ecosystem services. | 13. Sustainable Land Management practices are applied to at least 140.000 ha of productive landscape | The relationship between means to results is solid in this result, within the framework of what has been proposed, as well as in result 4. However, it shows weaknesses in terms of improving the flow of forest services (see Comments/Assumptions and analysis of sub-result 1.1.), as well as probable limitations in terms of agro-ecosystem services.
14. 10.000 ha of degraded agricultural lands are rehabilitated
15. Micro-finance mechanisms in place to support transition from degraded lands to sustainable management

## result 4
Result 4
Impact | Result | Comments/Assumptions | Products | Analysis
Biodiversity of global importance preserved thanks to : i) reduced rate of loss of forest ecosystems in the Chilean Mediterranean ecoregion; ii) restored and enabled forest ecosystems in the Chilean Mediterranean ecoregion; iii) improved and protected agro-ecosystem environmental services. | Result 4. Community capacity development and knowledge management |  | 16. No less than ten cross-cutting territorial Communities of Practice established | The average ratio to results looks solid in this result
17. Ten ecoregion-wide training workshops on project development and management, the function of landscape management in achieving GEB, and the role of local communities
18. Knowledge management products from results and lessons learnt disseminated to CBOs, CSOs and others
19. Training programme on identification and tracking of indicators, and project participatory monitoring