**TERMS OF REFERENCE**

**HIRING OF INDIVIDUAL CONSULTANT FOR TERM EVALUATION OF PROJECT**

|  |  |
| --- | --- |
| **Project Title** | **Sustainable Forest Management (SFM) to secure multiple benefits in Pakistan's high conservation value forests** |
| **Post Title**  | **National Consultant to support Team Leader** |
| **Duty Station** | **Home based** |
| **Duration**  | **35 working days spread across 04 months**  |
| **Contract** | **Individual Consultancy Contract – Short Term** |

1. **INTRODUCTION**

In accordance with UNDP and GEF M&E policies and procedures, all full- and medium-sized UNDP-supported GEF-financed projects are required to undergo a Terminal Evaluation (TE) at the end of the project. This Terms of Reference (ToR) sets out the expectations for the TE of the full-sized project titled *“Sustainable Forest Management (PIMS# 4674)”* implemented through *Ministry of Climate Change*. The project started on January 2016and is in its *sixth* year of implementation. The TE process must follow the guidance outlined in the document ‘Guidance for Conducting Terminal Evaluations of UNDP-Supported, GEF-Financed Projects’ ([Guidance for Terminal Evaluations of UNDP-supported GEF-financed Projects](https://eur03.safelinks.protection.outlook.com/?url=http%3A%2F%2Fweb.undp.org%2Fevaluation%2Fguideline%2Fdocuments%2FGEF%2FTE_GuidanceforUNDP-supportedGEF-financedProjects.pdf&data=02%7C01%7Cmohammad.saleem%40undp.org%7C45f089e7684e40370ec608d82e1203a5%7Cb3e5db5e2944483799f57488ace54319%7C0%7C0%7C637310002190012148&sdata=OSKOAKnEhnP95Ieo6tqz74PnpEkcoFk79ad13OgWKOE%3D&reserved=0)).

1. **PROJECT BACKGROUND AND CONTEXT**

Programme Period: 70 months ( Inclusive of 10 months extension)

Total resources required: USD 8,338,000

Total allocated resources:

* **GEF USD 8,338,000**
* **Co-financing USD**
	+ Government USD 47,770,000
	+ UNDP USD 1,000,000
	+ CBOs USD 650,000

Sustainable Forests Management is a five years project funded by GEF and supported by UNDP. Ministry of Climate Change (MoCC) is the executing agency/Implementing Partner for this project. The Project Management Unit (PMU) is established in Islamabad which serves as the secretariat for IP. Provincial Forest Departments are the co-implementing partners in KPK, Punjab and Sindh. Similarly, Provincial Management Implementation Units (PMIUs) are established for implementing the planned activities in the respective landscapes.

There are six landscapes selected for executing the project interventions. Project forest landscapes have been selected based on their global and national significance for biodiversity conservation and climate mitigation, operational feasibility, local security, governance, and well-defined land tenure. The target areas include state-owned forests as well as communal and private forests.

Objective of the SFM project is to promote sustainable forest management in Pakistan's Western Himalayan Temperate Coniferous, Sub-tropical broadleaved evergreen thorn (Scrub) and Riverine forests for biodiversity conservation, mitigation of climate change and securing of forest ecosystem services. In particular, it aims at implementation of three inter-related and mutually complementary components that are focused at addressing the barriers of inadequate planning, regulatory and institutional frameworks to integrated forest resource management, and enhancing the limited experience among key government and civil society stakeholders in developing and implementing SFM practices on the ground.

Location of the landscapes in Punjab as per project document were fixed as scrub forest in Chakwal and Riverine forest in South Punjab. When the project started its activities’ implementation on the ground, it was found not feasible due to numerous reasons to pursue implementation of the SFM activities regarding restoration of riverine forest in South Punjab. The issue was discussed in Project Board Meeting and the Boards Members suggested to visit and make a feasibility report for selection of an alternative site. UNDP and SFM management jointly visited the sites and selected pine forest in Rawalpindi North (Kahuta and Kalar Syedan) and an addition of Samarkand in the Scrub landscape at Chakwal. Deciding restoration and reforestation targets for the sites in Punjab are under consideration and shortly be finalized to be used in evaluation missions of the project to judge the progress made during course of the project.

7,436 hectares will have to be reforested and 13,128 hectares will be used for conservation of biodiversity in Sukkur and Kot Dingano Lakhat riverine forest in Benazir Abad. Interventions in Kaghan and Siren landscapes at KPK for SFM cover approximately 28,005 ha of state and community forests, of which approximately 18,000 ha are of high conservation value, 7,848 ha require forest restoration and 2,157 ha require reforestation. There are three major outcomes the project is pursuing its attainment towards the institutionalization of SFM in the country.

**Outcome 1:** will support the incorporation of sustainable forest management objectives and safeguards in forest management planning, forestland allocation and compliance of monitoring systems at the local level.

**Outcome 2:** will identify, demarcate and implement on-the-ground approaches to improving management of high conservation value forests within six landscapes covering an area of 58,545 ha with the aim of meeting life requisites of the target species, and habitats such as breeding areas, feeding areas, water sources, dispersal and connectivity corridors, etc. It will be achieved through the following four objectives:

**Outcome 3:** will develop practical approaches to enhancing carbon sequestration through restoring degraded and former forested areas (LULUCF activities) by a combination of restoration and reforestation of 10,005 ha of degraded conifer forests; ,400 ha of degraded scrub forests, and reforestation of 7,436 ha of Riverine forests with native species.

1. **TE PURPOSE**

The TE will assess the achievement of project results against what was expected to be achieved and draw lessons that can both improve the sustainability of benefits from this project, and aid in the overall enhancement of UNDP programming. The TE report promotes accountability and transparency, and assesses the extent of project accomplishments.

1. **TE APPROACH & METHODOLOGY**

The TE report must provide evidence-based information that is credible, reliable and useful.

The TE team will review all relevant sources of information including documents prepared during the preparation phase (i.e. PIF, UNDP Initiation Plan, UNDP Social and Environmental Screening Procedure/SESP) the Project Document, project reports including annual PIRs, project budget revisions, lesson learned reports, national strategic and legal documents, and any other materials that the team considers useful for this evidence-based evaluation. The TE team will review the baseline and GEF focal area /Tracking Tools submitted to the GEF at the CEO endorsement and midterm stages and the terminal /Tracking Tools that must be completed before the TE field mission begins.

The TE team is expected to follow a participatory and consultative approach ensuring close engagement with the Project Team, government counterparts (the GEF Operational Focal Point), Implementing Partners, the UNDP Country Office(s), the Regional Technical Advisor, direct beneficiaries and other stakeholders.

Engagement of stakeholders is vital to a successful TE. Stakeholder involvement should include interviews with stakeholders who have project responsibilities, including but not limited to Ministry of Climate Change, Economic Affairs Division (EAD) , Pakistan Forest Institute, Planning Commission of Pakistan, , Provincial Forest Departments of Punjab, Sindh and KP, , Executing Agencies, Senior Officials and task team/ component leaders, key experts and consultants in the subject area, Project Board, project stakeholders, academia, local government and CSOs, etc. Additionally, the **National Consultant** is expected to conduct field missions to KPK, Sindh, Punjab and meet with the local communities if permitted by UNDP as per the SOPs under COVID-19 pandemic.

The specific design and methodology for the TE should emerge from consultations between the TE team and the above-mentioned parties regarding what is appropriate and feasible for meeting the TE purpose and objectives and answering the evaluation questions, given limitations of budget, time and data. The final approach and methodology must be documented in the inception report and agreed upon by both the parties. The TE team must use gender-responsive methodologies and tools and ensure that gender equality and women’s empowerment, as well as other cross-cutting issues and SDGs are incorporated into the TE report.

Engagement of stakeholders is vital to a successful Final Evaluation. Stakeholder involvement should include (where possible, given the COVID situation) surveys/questionnaires, focus groups, interviews with stakeholders who have project responsibilities, including but not limited to executing agencies, senior officials and task team/component leaders, key experts and consultants in the subject area, Project Steering Committee, project stakeholders, local government, CSOs, project beneficiaries, etc. If not all stakeholders are available to engage virtually, this must be documented in the Evaluation report.

Data collection will be used to validate evidence of results and assessments (including but not limited to assessment of Theory of Change, activities delivered, and results/changes occurred).

The final Evaluation report should describe the full evaluation approach taken and the rationale for the approach making explicit the underlying assumptions, challenges, strengths and weaknesses about the methods and approach of the review. The final report must also describe any limitations encountered by the Evaluation team during the evaluation process, including limitations of the methodology, data collection methods, and any potential influence of limitation on how findings may be interpreted, and conclusions drawn. Limitations include, among others: language barriers, inaccessible project sites (due to travel restrictions because of COVID), issues with access to data or verification of data sources, issues with availability of interviewees, methodological limitations to collecting more extensive or more representative qualitative or quantitative evaluation data, deviations from planned data collection and analysis set out in the ToR and Inception Report, etc. Efforts made to mitigate the limitations should also be included in the Interim Evaluation report.

The final methodological approach including interview schedule, field visits and data to be used in the evaluation must be clearly outlined in the TE Inception Report and be fully discussed and agreed between UNDP, stakeholders and the TE team.

As of 11 March 2020, the World Health Organization (WHO) declared COVID-19 a global pandemic as the new coronavirus rapidly spread to all regions of the world. Travel to the country although not restricted and travel in the country is well but to follow UNDSS SOPs for domestic travels which may not permit UNDP contract holder to travel. If it is not possible to travel within the country for the TE mission then the TE team should develop a methodology that takes this into account the conduct of the TE virtually and remotely, including the use of remote interview methods and extended desk reviews, data analysis, surveys, and evaluation questionnaires. This should be detailed in the TE Inception Report and agreed with the Commissioning Unit.

If all or part of the TE is to be carried out virtually then consideration should be taken for stakeholder availability, ability or willingness to be interviewed remotely. In addition, their accessibility to the internet/computer may be an issue as many government and national counterparts may be working from home. These limitations must be reflected in the final TE report.

The National Consultant is expected to start the field mission in case that the international consultant cannot travel to Islamabad, he/she will work remotely from his/her home country with supports from National evaluator.

If a data collection/field mission is not possible then remote interviews may be undertaken through telephone or online (skype, zoom etc.). International consultants can work remotely with national evaluator support in the field if it is safe for them to operate and travel. No stakeholders, consultants or UNDP staff should be put in harm’s way and safety is the key priority.

The final report must describe the full TE approach taken and the rationale for the approach making explicit the underlying assumptions, challenges, strengths and weaknesses about the methods and approach of the evaluation.

1. **DETAILED SCOPE OF THE TE**

The TE will assess project performance against expectations set out in the project’s Logical Framework/Results Framework (see ToR Annex A). The TE will assess results according to the criteria outlined in the Guidance for TEs of UNDP-supported GEF-financed Projects ([Guidance for Terminal Evaluations of UNDP-supported GEF-financed Projects](https://eur03.safelinks.protection.outlook.com/?url=http%3A%2F%2Fweb.undp.org%2Fevaluation%2Fguideline%2Fdocuments%2FGEF%2FTE_GuidanceforUNDP-supportedGEF-financedProjects.pdf&data=02%7C01%7Cmohammad.saleem%40undp.org%7C45f089e7684e40370ec608d82e1203a5%7Cb3e5db5e2944483799f57488ace54319%7C0%7C0%7C637310002190012148&sdata=OSKOAKnEhnP95Ieo6tqz74PnpEkcoFk79ad13OgWKOE%3D&reserved=0))

The Findings section of the TE report will cover the topics listed below.

A full outline of the TE report’s content is provided in ToR Annex C.

The asterisk “(\*)” indicates criteria for which a rating is required.

Findings

1. Project Design/Formulation
* National priorities and country driven-ness
* Theory of Change
* Gender equality and women’s empowerment
* Social and Environmental Safeguards
* Analysis of Results Framework: project logic and strategy, indicators
* Assumptions and Risks
* Lessons from other relevant projects (e.g. same focal area) incorporated into project design
* Planned stakeholder participation
* Linkages between project and other interventions within the sector
* Management arrangements
1. Project Implementation
* Adaptive management (changes to the project design and project outputs during implementation)
* Actual stakeholder participation and partnership arrangements
* Project Finance and Co-finance
* Monitoring & Evaluation: design at entry (\*), implementation (\*), and overall assessment of M&E (\*)
* Implementing Agency (UNDP) (\*) and Executing Agency (\*), overall project oversight/implementation and execution (\*)
* Risk Management, including Social and Environmental Standards
1. Project Results
* Assess the achievement of outcomes against indicators by reporting on the level of progress for each objective and outcome indicator at the time of the TE and noting final achievements
* Relevance (\*), Effectiveness (\*), Efficiency (\*) and overall project outcome (\*)
* Sustainability: financial (\*) , socio-political (\*), institutional framework and governance (\*), environmental (\*), overall likelihood of sustainability (\*)
* Country ownership
* Gender equality and women’s empowerment
* Cross-cutting issues (poverty alleviation, improved governance, climate change mitigation and adaptation, disaster prevention and recovery, human rights, capacity development, South-South cooperation, knowledge management, volunteerism, etc., as relevant)
* GEF Additionality
* Catalytic Role / Replication Effect
* Progress to impact

Main Findings, Conclusions, Recommendations and Lessons Learned

* The TE team will include a summary of the main findings of the TE report. Findings should be presented as statements of fact that are based on analysis of the data.
* The section on conclusions will be written in light of the findings. Conclusions should be comprehensive and balanced statements that are well substantiated by evidence and logically connected to the TE findings. They should highlight the strengths, weaknesses and results of the project, respond to key evaluation questions and provide insights into the identification of and/or solutions to important problems or issues pertinent to project beneficiaries, UNDP and the GEF, including issues in relation to gender equality and women’s empowerment.
* Recommendations should provide concrete, practical, feasible and targeted recommendations directed to the intended users of the evaluation about what actions to take and decisions to make. The recommendations should be specifically supported by the evidence and linked to the findings and conclusions around key questions addressed by the evaluation.
* The TE report should also include lessons that can be taken from the evaluation, including best and worst practices in addressing issues relating to relevance, performance and success that can provide knowledge gained from the particular circumstance (programmatic and evaluation methods used, partnerships, financial leveraging, etc.) that are applicable to other GEF and UNDP interventions. When possible, the TE team should include examples of good practices in project design and implementation.
* It is important for the conclusions, recommendations and lessons learned of the TE report to include results related to gender equality and empowerment of women.

The TE report will include an Evaluation Ratings Table, as shown below:

**ToR Table 2: Evaluation Ratings Table for *(project title)***

|  |  |
| --- | --- |
| Monitoring & Evaluation (M&E) | Rating[[1]](#footnote-1) |
| M&E design at entry |  |
| M&E Plan Implementation |  |
| Overall Quality of M&E |  |
| Implementation & Execution | Rating |
| Quality of UNDP Implementation/Oversight  |  |
| Quality of Implementing Partner Execution |  |
| Overall quality of Implementation/Execution |  |
| Assessment of Outcomes | Rating |
| Relevance |  |
| Effectiveness |  |
| Efficiency |  |
| Overall Project Outcome Rating |  |
| Sustainability | Rating |
| Financial resources |  |
| Socio-political/economic |  |
| Institutional framework and governance |  |
| Environmental |  |
| Overall Likelihood of Sustainability |  |

1. **TIMEFRAME**

The total duration of the TE will be approximately *(35 working days)* over a time period of June – September 2021). The tentative TE timeframe is as follows:

|  |  |
| --- | --- |
| **TIMEFRAME** | **ACTIVITY** |
| 07-06-2021 - 20-06-2021 (14 days) | Application closes |
| 21-06-2021 – 02-07-2021( 10 days) | Selection of TE Team |
| 05-07-2021 – 06-07-2021( 02 days) | Prep the TE Team (handover of Project Documents) |
| 07-07-2021 – 14-07-2021( 06 days) | Document review and preparing TE Inception Report |
| 15-07-2021 – 21-07-2021( 05 days) | Finalization andValidation of TE Inception Report- latest start of TE mission |
| 22-07-2021 – 11-08-2021( 15 days) | TE mission: stakeholder meetings, interviews, field visits (if not possible virtual meetings will be conducted) |
| 12-08-2021 – 13-08-2021(02 days)  | Mission wrap-up meeting & presentation of initial findings- earliest end of TE mission |
| 16-08-2021 – 27-08-2021( 10 days) | Preparing draft final report and sharing with UNDP for review |
| 30-08-2021 – 02-09-2021(04 days) | Incorporating audit trail from feedback on draft report/Finalization of TE report  |
| 03-09-2021 – 09-09-2021(05 days) | Preparation & Issue of Management Response |
| 10-09-2021 – 21-09-2021(08 days) | Expected date of full TE completion |

1. **TE DELIVERABLES**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **#** | **Deliverable** | **Description** | **Timing / no of days** | **Responsibilities** |
| **1** | **TE Inception Report** | TE team clarifies objectives and methods of Terminal Review | No later than 2 weeks before the TE mission: **21 July 2021** | TE team submits to the Commissioning Unit and project management |
| **2** | **Presentation** | Initial Findings | End of TE mission:**13 August 2021** | TE Team presents to project management and the Commissioning Unit |
| **3** | **Draft Final Report** | Full report (using guidelines on content outlined in Annex B) with annexes | Within 3 weeks of the TE mission:**27 August 2021** | Sent to the Commissioning Unit, reviewed by RTA, Project Coordinating Unit, GEF OFP |
| **4** | **Final Report\*** | Revised report with audit trail detailing how all received comments have (and have not) been addressed in the final TE report | Within 1 week of receiving UNDP comments on draft: **21 September 2021** | Sent to the Commissioning Unit |

\*All final TE reports will be quality assessed by the UNDP Independent Evaluation Office (IEO). Details of the IEO’s quality assessment of decentralized evaluations can be found in Section 6 of the UNDP Evaluation Guidelines.[[2]](#footnote-2)

1. **TE IMPLEMENTATION ARRANGEMENTS**

The principal responsibility for managing the TE resides with the Commissioning Unit. The Commissioning Unit for this project’s TE is UNDP Pakistan Country Office*.*

The Commissioning Unit will contract the evaluators and ensure the timely provision of per diems and travel arrangements to Pakistan and within the country for the TE team, if the travel is permitted. The Project Team will be responsible for liaising with the TE team to provide all relevant documents, set up stakeholder interviews, and arrange field visits.

The national evaluator is require to meet with all the key stakeholders within Islamabad. For any visits outside Islamabad, the UNDP CO will arrange travel and bear the cost as per UNDP rules and policies. If the travel to project sites is restricted, the logistic support in the implementation of remote/virtual meetings shall be carried out by the project team in coordination with the UNDP CO.

Following to be noted for travel:

* International travel may or may not be required to Pakistan during the TE mission in view of COVID-19 situation in the country
* The BSAFE course must be successfully completed prior to commencement of travel, if required;
* Individual Consultants are responsible for ensuring they have vaccinations/inoculations when travelling to certain countries, as designated by the UN Medical Director.
* Consultants are required to comply with the UN security directives set forth under: <https://dss.un.org/dssweb/>
* All related travel expenses will be covered and will be reimbursed as per UNDP rules and regulations upon submission of an F-10 claim form and supporting documents, as and if required.
1. **TE TEAM COMPOSITION**

A team of two independent evaluators will conduct the TE- One international team leader (with experience and exposure to projects and evaluations in other regions globally) and one National expert from the country of the project. The team leader will be responsible for the overall design and writing of the TE report. The team expert will assess emerging trends with respect to regulatory frameworks, budget allocations, capacity building, work with the Project Team in developing the TE itinerary, etc.)

The National Evaluator will work closely with the International Evaluator in supporting any work that needs to be undertaken as laid out in this ToR, and other tasks, as required. The National Evaluator will also act as a focal point for coordinating and working with relevant stakeholders in Pakistan. In the case of international travel restriction and the mission is not possible, the ME team will use alternative means of interviewing stakeholders and data collection (i.e. Skype interview, mobile questionnaires, etc.) including the field visit by the National Evaluator under the International Evaluator’s guidance.

The evaluator(s) cannot have participated in the project preparation, formulation and/or implementation (including the writing of the project document) and should not have a conflict of interest with the project’s related activities.

The selection of National Evaluators will be aimed at maximizing the overall “team” qualities in the following areas:

Education

* Master’s degree in Forestry, Natural Resources, or other closely related field

Experience

* Experience in relevant technical areas of (Sustainable Forest Management, BD/ Ecosystems; Conservation) for at least 10 years;
* Experience in evaluating GEF, UNDP or UN agencies funded projects;
* Relevant experience with results-based management evaluation methodologies;
* Experience applying SMART indicators and reconstructing or validating baseline scenarios;
* Experience working in Asia Pacific preferable in South Asia;
* Demonstrated understanding of issues related to gender and Sustainable Forest Management and Biodiversity and experience in gender responsive evaluation and analysis;
* Excellent communication skills;
* Demonstrable analytical skills;
* Project evaluation/review experience within United Nations (other than UNDP) system will be considered an asset.
* *Experience with implementing evaluations remotely will be considered an asset.*

Language

* Fluency in written and spoken English.
* Demonstrable analytical skills.
1. **SELECTION CRITERIA FOR EVALUATIOR**

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Individual consultants will be evaluated based on the Cumulative analysis. The award of the contract should be made to the individual consultant whose offer has been evaluated and determined as:1. Responsive/compliant/acceptable, and
2. Having received the highest score out of a pre-determined set of weighted technical and financial criteria specific to the solicitation.
	1. Technical Criteria weight: 70%
	2. Financial Criteria weight: 30%

Only candidates obtaining a minimum of 49 out of 70 points will be considered for the FinancialEvaluation

|  |  |  |
| --- | --- | --- |
| **Criteria** | **Weight** | **Max. Point** |
| ***Technical Competencies*** | **70** |  |
| * A Master’s degree in Forestry, Natural Resources Management or other closely related field.
 | 10 |  |
| * Experience in relevant technical areas of (Sustainable Forest Management, BD/ Ecosystems; Conservation) for at least 10 years;
* Experience in evaluating GEF, UNDP or UN agencies funded projects;
* Relevant experience with results-based management evaluation methodologies;
* Experience applying SMART indicators and reconstructing or validating baseline scenarios;
* Experience working in Asia Pacific preferable in South Asia;
* Demonstrated understanding of issues related to gender and Sustainable Forest Management and Biodiversity and experience in gender responsive evaluation and analysis;
* Demonstrable analytical skills;
* Project evaluation/review experience within United Nations (other than UNDP) system will be considered an asset.
* *Experience with implementing evaluations remotely will be considered an asset*
 | 100505050505050505 |  |
| * Excellent communication skills;
* Demonstrable analytical skills;
 | 10 |  |
| Financial proposal  | **30** |  |
| **Total Score** | **Technical score 70+30 Financial** |

|  |
| --- |
| **Weight per Technical Competence** |
| Weak: Below 70% | The individual consultant/contractor has demonstrated a **WEAK** capacity for the analyzed competence  |
| Satisfactory : 70-75% | The individual consultant/contractor has demonstrated a **SATISFACTORY** capacity for the analyzed competence |
| Good: 76-85% | The individual consultant/contractor has demonstrated a **GOOD** capacity for the analyzed competence |
| Very Good: 86-95% | The individual consultant/contractor has demonstrated a **VERY GOOD** capacity for the analyzed competence |
| Outstanding: 96-100% | The individual consultant/contractor has demonstrated a **OUTSATNDING** capacity for the analyzed competence |

 |

1. **EVALUATOR ETHICS**

The TE team will be held to the highest ethical standards and is required to sign a code of conduct upon acceptance of the assignment. This evaluation will be conducted in accordance with the principles outlined in the UNEG ‘Ethical Guidelines for Evaluation (Annex’ E). The evaluator must safeguard the rights and confidentiality of information providers, interviewees and stakeholders through measures to ensure compliance with legal and other relevant codes governing collection of data and reporting on data. The evaluator must also ensure security of collected information before and after the evaluation and protocols to ensure anonymity and confidentiality of sources of information where that is expected. The information knowledge and data gathered in the evaluation process must also be solely used for the evaluation and not for other uses without the express authorization of UNDP and partners.

1. **PAYMENT SCHEDULE**
* 20% payment upon satisfactory delivery of the final TE Inception Report and approval by the Commissioning Unit
* 40% payment upon satisfactory delivery of the draft TE report to the Commissioning Unit
* 40% payment upon satisfactory delivery of the final TE report and approval by the Commissioning Unit and RTA (via signatures on the TE Report Clearance Form) and delivery of completed TE Audit Trail

Criteria for issuing the final payment of 40%[[3]](#footnote-3):

* The final TE report includes all requirements outlined in the TE TOR and is in accordance with the TE guidance.
* The final TE report is clearly written, logically organized, and is specific for this project (i.e. text has not been cut & pasted from other TE reports).
* The Audit Trail includes responses to and justification for each comment listed.

1. **APPLICATION PROCESS[[4]](#footnote-4)**

*(Adjust this section if a vetted roster will be used)*

Recommended Presentation of Proposal:

1. **Letter of Confirmation of Interest and Availability** using the [template](https://intranet.undp.org/unit/bom/pso/Support%20documents%20on%20IC%20Guidelines/Template%20for%20Confirmation%20of%20Interest%20and%20Submission%20of%20Financial%20Proposal.docx)[[5]](#footnote-5) provided by UNDP;
2. **CV** and a **Personal History Form** ([P11 form](http://www.undp.org/content/dam/undp/library/corporate/Careers/P11_Personal_history_form.doc)[[6]](#footnote-6));
3. Brief description **of approach to work/technical proposal** of why the individual considers him/herself as the most suitable for the assignment, and a proposed methodology on how they will approach and complete the assignment; (max 1 page)
4. **Financial Proposal** that indicates the all-inclusive fixed total contract price and all other travel related costs (such as flight ticket, per diem, etc), supported by a breakdown of costs, as per template attached to the [Letter of Confirmation of Interest template](https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/PSU_%20Individual%20Contract_Offerors%20Letter%20to%20UNDP%20Confirming%20Interest%20and%20Availability.docx&action=default). If an applicant is employed by an organization/company/institution, and he/she expects his/her employer to charge a management fee in the process of releasing him/her to UNDP under Reimbursable Loan Agreement (RLA), the applicant must indicate at this point, and ensure that all such costs are duly incorporated in the financial proposal submitted to UNDP.

All application materials should be submitted to the address (insert mailing address) in a sealed envelope indicating the following reference “Consultant for Terminal Evaluation of *(project title)*” or by email at the following address ONLY: *(insert email address)* by *(time and date)*. Incomplete applications will be excluded from further consideration.

**Criteria for Evaluation of Proposal:** Only those applications which are responsive and compliant will be evaluated. Offers will be evaluated according to the Combined Scoring method – where the educational background and experience on similar assignments will be weighted at 70% and the price proposal will weigh as 30% of the total scoring. The applicant receiving the Highest Combined Score that has also accepted UNDP’s General Terms and Conditions will be awarded the contract.

1. **TOR ANNEXES**

*(Add the following annexes to the final ToR)*

* ToR Annex A: Project Logical/Results Framework
* ToR Annex B: Project Information Package to be reviewed by TE team
* ToR Annex C: Content of the TE report
* ToR Annex D: Evaluation Criteria Matrix template
* ToR Annex E: UNEG Code of Conduct for Evaluators
* ToR Annex F: TE Rating Scales
* ToR Annex G: TE Report Clearance Form
* ToR Annex H: TE Audit Trail

**ToR Annex A: Project Logical/Results Framework**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **Indicator** | **Baseline** | **Targets** **End of Project** | **Source of verification** | **Risks and Assumptions** |
| **Project Objective[[7]](#footnote-7)**Promotion of Sustainable Forest Management in Pakistan’s Western Himalayan Coniferous, Sub-tropical broadleaved evergreen thorn and Riverine forest (scrub forests) for biodiversity conservation, mitigation of climate change and securing forest ecosystem services | Number of forest landscape management plans integrating considerations of biodiversity, ecosystem services, climate mitigation and community resource use (integrating sustainable forest management principles) | 0 | 7 | * Landscape management plans
* - Project work plan. Progress and monitoring reports
 | * Assumptions:
* -The GoP and Provincial Governments actively promoting and supporting sustainable forest management principles, planning and practices
* The GoP and Provincial Governments maintains suitable policies and legal frameworks to ensure land use changes do not undermine forest conservation

Risks: * Failure to generate adequate revenues from SFM might change government priorities
* Failure to effectively engage local stakeholders (herders, land owners, forest dependents and other stakeholders leads to conflict
 |
| Total avoided and/or sequestrated carbon benefits over thirty-year period due to improved sustainable management of forests. | N/A | 9,908,090 tCO2.eq | Updates on forest cover, carbon monitoring reports  | **Assumptions:**- The GOP and Provincial Governments remain committed to sustainable management of forests and land, as well as set-aside of areas conservation.- Federal and Provincial institutions develop capacity and skills for monitoring and assessing C benefits- The affects of climate change on forests is unlikely to be significant to undermine forest rehabilitation**Risks:**-Reduced revenues from reduced timber exploitation and meeting demands of communities for timber and fuelwood might shift government priorities away from sustainable use and conservation. |
| Extent in hectares of forest area managed for multiple sustainable forest management and ecosystem benefits  | 0 | 67,861 ha | Quarterly and Annual project progress reports, forest monitoring reports and independent evaluation reports | * Assumption:
* -The Federal and provincial Governments are committed to management of the forest for multiple benefits and not just timber production
* Risks:
* Management of forests for multiple benefits might impinge on user rights and misunderstandings that needs to be managed
 |
| **Outcome 1[[8]](#footnote-8)**Embedding SFM into landscape-scale spatial planning | Number of forest management plan protocols/guidelines for mainstreaming ecosystem, climate risk mitigation and biodiversity considerations into forest management in Pakistan  | 0 | One set of SFM guidelines (for the three forest types included in the project) approved by Ministry of Climate Change and adopted by the provinces, by the fourth year of the project | * forest management guidelines/protocols
 | **Assumptions:**-Federal and Provincial Governments commitment to sustainable forest management and shift from wood production to ecosystem benefits and biodiversity conservation**Risks:**Inability to assess economic benefits of ecosystem services and derive direct measurable benefits to local economy may result in reluctance to move away from forestry related economic activities |
| Number of forest landscapes completed forest inventory and maps in support of sustainable forest management  | 0 | 7 | * Forest inventory and GIS maps
 | **Assumptions:**-Provincial governments and Forest communities and private forest owners remain committed to integrated forest planning and management-Provincial forest entities other implementing entities have adequate staffing, capacity and counterpart funding for forest inventory and mapping **Risks:**Rapid turnover of staff can undermine capacity improvements for inventory and mapping skills |
| Number of provincial/district level forest entities effectively applying consideration of the needs for biodiversity, climate mitigation, forest ecosystem services and community sustainable use |  0  | 3 | Sustainable Forest management plans | **Assumptions:**-Provincial and District governments and Private Forest Owners and forest communities remain committed to integrated forest planning and management-Provincial and district forest agencies and other implementing entities have adequate staffing, capacity and counterpart funding for forest management-Stakeholders are willing to participate in conservation and protection-Incentives are adequate and targeted to correct recipients, and benefits are equitable and fair**Risks:**Longer gestation period to see visible benefits may hamper efforts at selling SFM principles to policy makers |
| Number of forest monitoring protocols to assess effectiveness of adoption for SFM in forestlands | 0 (Existing practice, monitoring protocols used for recording forest violations and fires, not for consideration of ecosystem values and functions) | 3 sets of monitoring protocols, one for each of the 3 forest types of pilots, approved by the Ministry of climate change and adopted by the provincial respective Forest Departments | Forest management plan monitoring reports  | **Assumptions:**-Monitoring protocols would be easy to measure, be low cost and do not need highly developed skills.-Implementing entities have established monitoring system and capacity to monitor threats and impacts of conservation actions |
| Number of provincial and district staff trained in the use of ecosystem based planning tools | 0 | 30 | Training records and training evaluation reports | **Assumptions:**-Staff are provided adequate incentives for training and capacity development for SFM-Training designed for practical and on-the-job application**Risks:**-staff turnover may constraint improvement in capacity development and retention |
| Number of forest community members and private forest owners undergone technical and skills training and development in sustainable forest management | 0 | At least 200 (of which at least 10% are women) | Training records and training evaluation reports | **Assumptions:**-Forest dependent stakeholders willingness to engage in management of forest resources-Provincial and district forest staff committed to community forest management and resource use-Training design simple and easy to apply in the field**Risks:**- Failure of Provincial and district forest staff to effectively engage local stakeholders in forest management decision-making |
| Number of Baseline assessment report on current unsustainable and sustainable resource use practices, state and/or condition of resources and baseline of key indicator species | 0 | At least seven baseline assessment reports completed, one for each forest landscape | * -Baseline assessment reports, progress reports and self monitoring report
 | **Assumption:**Capacity and skills for development of such technical reports are available in the country  |
| Number of forest resource use conflicts effective resolved | 0 | At least 50% of identified and documented conflicts effectively resolved | * -List of identified and documented conflicts with necessary details
* - Case studies of resolved conflicts

-Progress reports | * Assumption:
* Political will, and negotiation and mediation skills as well as processes will be used to resolve the conflicts
* Risk
* Lack of political will, objectivity and weak governance may impede success in certain types of conflicts e.g retrieval of encroached forest lands and of non compliant agro-forestry leased lands
 |
| Number of comprehensive recommendations for scaling-up and replication of sustainable forest management approaches emanating from the project sites | 0 | One set each of best practices, successful models and composite recommendations developed by the project implementing provincial governments in consultation with the Ministry of Climate Change, adopted, publicized and supported in the country as part of future regular or development programs and shared widely through case studies etc. | Project progress reports, Mid Term Review report and end line evaluation report | * Assumptions:
* -Federal and provincial agencies willing and committed to sustainable forest management
* Risk:

-GoP and provincial governments would be less conducive to make changes from existing narrowly focused forest production priorities |
| **Outcome 2** Biodiversity conservation strengthened in and around High Conservation Value Forests | Hectares of high biodiversity conservation value forests identified, designated and effectively managed for biodiversity and climate mitigation | 0 | At least 18,000 ha of Western Himalayan Conifer forests, 4,459 ha of sub-tropical evergreen thorny forests and 18,898 ha of riverine forests | * Landscape management plans;
* Forest working plans include SFM prescriptions
 | * Assumptions:
* -Provincial governments willingness to provide staff and resource mobilization for meeting biodiversity conservation outcomes in areas already assigned for this purpose
* - Additional areas set-aside for conservation are based on clearly defined criteria for biodiversity conservation

**Risk**: -Government priorities may change from forest protection to industrial use.  |
| -Population trends of key indicator species of *Ovis vignei punjabensis, Axis porcinus, Pucrasia macrolop, Platanista gangetica minor* stable or increasing | Riverine forests[[9]](#footnote-9):*Axis porcinus 345**Plantanista gangetice minor –1,650*Scrub forests:*Ovis vignei punjabensis – 200**Gazella gazella - 25*Conifer forests[[10]](#footnote-10):*Lophorus lophorus impejanus – 375**Semnopithecus entellus – 150* | * Population of indicator species stable or increase over baseline values[[11]](#footnote-11)
 | Annual Forest surveys and inventory at defined number of sites in each forest landscapes | * Assumptions:

-Adequate resources and training provided to staff and researchers to conduct inventory and monitoring |
| Emissions of metric tCO2 avoided from conservation set-asides over a 30-year period | **0** | 4,759,145 tCo2 eq. | * Forest (biomass) carbon inventory/baseline (emission data) and deforestation rate (activity data)
 | * Assumptions:
* -Provincial governments willingness to set-aside areas for conservation from current production
* -Provincial government commitment and resources available for carbon monitoring
* Risks:

-Lack of capacity and skills for C assessments |
| Extent of forest ecosystem covered under a model for Community Managed Conservation in High Value Coniferous Forests with high potential for replication established in  | 0 | At least 8,000 ha | -Community surveys and records of forest improvement and increased incomes and production of NTFP-Self monitoring and independent evaluation~~s~~* Independent evaluations
 | **Assumption:** * -Local community members and private forest owners are willing and cooperate in implementation of SFM practices

**Risks:**-Level on incentives generated through SFM practice might be insufficient to ensure adequate commitment to SFM-Climate change impacts may increase to the extent that even if the project implements activities to improve pasture lands may not be enough to make a difference  |
| Percentage of households reporting increased incomes in Community managed conservation areas from forest and non-forest resources  | Baseline incomes would be assessed once forest inventory and mapping completed and locations for community forest use identified | 20%, of which at least 30% of beneficiaries are women | Social surveys and reports at village level | **Risks:**-Engaging local stakeholders more robustly contains some risk in Pakistan, where centralized approaches are still the norm. -Elite capture at local level would prevent marginalized groups and forest dependents from generating benefits of project |
| Number of forest dependent community members and private forest owners trained in technical and community organizational skills for conservation-based sustainable resource use. | **0** | At Least 100, of which at least 10% would be women  | -Training modules-Socio-economic and social organizational activities’ reports-Progress reports-Monitoring reports | **Assumption:*** All stakeholders will participate in the trainings which will not only enhance their capacities but would also positively change their mindset

**Risk:**Owners and big right holders may not agree to joint trainings with the members of the community organizations for maintaining the status quo |
| Number of provincial forest staff trained in use of tools and techniques for improved protected area management and species conservation | **0** | 60 forest and 30 wildlife staff of different levels trained in forest biodiversity conservation in two weeks to three months training courses  | - Training modules- Training activities reports-Progress reports-Monitoring reports | **Assumption:*** The staff at different levels and the provincial government including forest departments and wildlife departments will be interested in such training courses and allow the trainee staff to attend these.
* There is capacity in the country to conduct such courses effectively

**Risks*** Middle level and senior staff may shy to attend the formal training courses
* The trainee staff may not be released for attending the courses for attending to short term priorities

The risks (if any) would be avoided by motivating and providing incentives to the trainees and joint planning of these courses with the senior government staff |
| **Outcome 3** Enhanced carbon sequestration in and around HCVF in target forested landscapes | Number of hectares of Sub-tropical broadleaved evergreen thorny forests and Western Himalayan Temperate Coniferous forests rehabilitated | 0 | 3,400 ha of Sub-tropical broadleaved evergreen thorny forests and 10,005 ha of Western Himalayan Temperate Coniferous forests | Provincial forest department and community records of forest activities | **Assumptions**: * Areas selected for natural regeneration are based on potential for assisted natural regeneration, reforestation, rehabilitation, conservation including availability of seeding stocks, land suitability water availability and other biotic, edaphic and socio-economic factors

**Risks:**-Climate change impacts may increase to the extent that even if the project implements activities to improve condition in forest lands it may not be enough to make a difference |
| Number of hectares of riverine forest reforested with native species | **0** | 13,099 ha  | Provincial forest department records of reforestration activities; department and community records of forest activities and project self-monitoring reports | **Assumptions:** Areas selected have potential for assisted natural regeneration, are regularly flooded by the mighty River Indus, and fulfil other conditions including availability of seed stocks, receptive land and other biotic and edaphic factors are conducive |
|  | Metric tons of CO2 eq sequestrated through regeneration and reforestation over 30-year period | **0** | 5,148,943 metric tons CO2 eq  | * Forest (biomass) carbon inventory/baseline (emission data) and deforestation rate (activity data)
 | * Assumption:
* -Criteria for selection of degraded lands assisted natural regeneration has adequate soil and biological conditions conducive for forest regeneration and reforestation

**Risks:**-Lack of capacity and skills for assessments of carbon |
|  | Number of best practice notes documenting forest restoration and reforestation and SFM | **0** | At least 5 best practice notes document and disseminated  | * Best practice notes,

Number of dissemination events undertaken | **Assumption**: * -The Project management, in particular its self monitoring system will be able to identify, document and disseminate the best practices

-Mid Term Review and Terminal Evaluation of the project will also contribute to identifying the best practices |
|  | Number of Carbon stock assessments and coefficients for key forest types in Pakistan developed and monitored | **0** | One set of baseline assessment completed and monitoring | * Forest (biomass) carbon inventory/baseline (emission data) and deforestation rate (activity data)
 | **Assumptions:*** -Federal and provincial government commitment to carbon inventory and monitoring and available financing and staffing
* -national methodology for measuring carbon stocks and fluxes developed under UN-REDD+ readiness program

**Risks**:* Lack of capacity and skills for assessments
* Delay in developing national methodological framework for carbon stock monitoring
 |

**ToR Annex B: Project Information Package to be reviewed by TE team**

|  |  |
| --- | --- |
| # | Item (electronic versions preferred if available) |
| 1 | Project Identification Form (PIF) |
| 2 | UNDP Initiation Plan |
| 3 | Final UNDP-GEF Project Document with all annexes |
| 4 | CEO Endorsement Request |
| 5 | UNDP Social and Environmental Screening Procedure (SESP) and associated management plans (if any) |
| 6 | Inception Workshop Report |
| 7 | Mid-Term Review report and management response to TE recommendations |
| 8 | All Project Implementation Reports (PIRs) |
| 9 | Progress reports (quarterly, semi-annual or annual, with associated workplans and financial reports) |
| 10 | Oversight mission reports |
| 11 | Minutes of Project Board Meetings and of other meetings (i.e. Project Appraisal Committee meetings) |
| 12 | GEF Tracking Tools (from CEO Endorsement, midterm and terminal stages) |
| 13 | GEF/LDCF/SCCF Core Indicators (from PIF, CEO Endorsement, midterm and terminal stages); for GEF-6 and GEF-7 projects only |
| 14 | Financial data, including actual expenditures by project outcome, including management costs, and including documentation of any significant budget revisions |
| 15 | Co-financing data with expected and actual contributions broken down by type of co-financing, source, and whether the contribution is considered as investment mobilized or recurring expenditures |
| 16 | Audit reports |
| 17 | Electronic copies of project outputs (booklets, manuals, technical reports, articles, etc.) |
| 18 | Sample of project communications materials |
| 19 | Summary list of formal meetings, workshops, etc. held, with date, location, topic, and number of participants |
| 20 | Any relevant socio-economic monitoring data, such as average incomes / employment levels of stakeholders in the target area, change in revenue related to project activities |
| 21 | List of contracts and procurement items over ~US$5,000 (i.e. organizations or companies contracted for project outputs, etc., except in cases of confidential information) |
| 22 | List of related projects/initiatives contributing to project objectives approved/started after GEF project approval (i.e. any leveraged or “catalytic” results) |
| 23 | Data on relevant project website activity – e.g. number of unique visitors per month, number of page views, etc. over relevant time period, if available |
| 24 | UNDP Country Programme Document (CPD) |
| 25 | List/map of project sites, highlighting suggested visits |
| 26 | List and contact details for project staff, key project stakeholders, including Project Board members, RTA, Project Team members, and other partners to be consulted |
| 27 | Project deliverables that provide documentary evidence of achievement towards project outcomes |
|  | *Additional documents, as required* |

**ToR Annex C: Content of the TE report**

1. Title page
* Title of UNDP-supported GEF-financed project
* UNDP PIMS ID and GEF ID
* TE timeframe and date of final TE report
* Region and countries included in the project
* GEF Focal Area/Strategic Program
* Executing Agency, Implementing partner and other project partners
* TE Team members
1. Acknowledgements
2. Table of Contents
3. Acronyms and Abbreviations
4. Executive Summary (3-4 pages)
* Project Information Table
* Project Description (brief)
* Evaluation Ratings Table
* Concise summary of findings, conclusions and lessons learned
* Recommendations summary table
1. Introduction (2-3 pages)
* Purpose and objective of the TE
* Scope
* Methodology
* Data Collection & Analysis
* Ethics
* Limitations to the evaluation
* Structure of the TE report
1. Project Description (3-5 pages)
* Project start and duration, including milestones
* Development context: environmental, socio-economic, institutional, and policy factors relevant to the project objective and scope
* Problems that the project sought to address, threats and barriers targeted
* Immediate and development objectives of the project
* Expected results
* Main stakeholders: summary list
* Theory of Change
1. Findings

(in addition to a descriptive assessment, all criteria marked with (\*) must be given a rating[[12]](#footnote-12))

4.1 Project Design/Formulation

* Analysis of Results Framework: project logic and strategy, indicators
* Assumptions and Risks
* Lessons from other relevant projects (e.g. same focal area) incorporated into project design
* Planned stakeholder participation
* Linkages between project and other interventions within the sector
	1. Project Implementation
* Adaptive management (changes to the project design and project outputs during implementation)
* Actual stakeholder participation and partnership arrangements
* Project Finance and Co-finance
* Monitoring & Evaluation: design at entry (\*), implementation (\*), and overall assessment of M&E (\*)
* UNDP implementation/oversight (\*) and Implementing Partner execution (\*), overall project implementation/execution (\*), coordination, and operational issues
	1. Project Results
* Progress towards objective and expected outcomes (\*)
* Relevance (\*)
* Effectiveness (\*)
* Efficiency (\*)
* Overall Outcome (\*)
* Country ownership
* Gender
* Other Cross-cutting Issues
* Social and Environmental Standards
* Sustainability: financial (\*), socio-economic (\*), institutional framework and governance (\*), environmental (\*), and overall likelihood (\*)
* Country Ownership
* Gender equality and women’s empowerment
* Cross-cutting Issues
* GEF Additionality
* Catalytic Role / Replication Effect
* Progress to Impact
1. Main Findings, Conclusions, Recommendations & Lessons
* Main Findings
* Conclusions
* Recommendations
* Lessons Learned
1. Annexes
* TE ToR (excluding ToR annexes)
* TE Mission itinerary, including summary of field visits
* List of persons interviewed
* List of documents reviewed
* Evaluation Question Matrix (evaluation criteria with key questions, indicators, sources of data, and methodology)
* Questionnaire used and summary of results
* Co-financing tables (if not include in body of report)
* TE Rating scales
* Signed Evaluation Consultant Agreement form
* Signed UNEG Code of Conduct form
* Signed TE Report Clearance form
* *Annexed in a separate file*: TE Audit Trail
* *Annexed in a separate file:* relevant terminal GEF/LDCF/SCCF Core Indicators or Tracking Tools (METT, FSC, Capacity scorecard, etc), as applicable
* *Annexed in a separate file: GEF Co-financing template (categorizing co-financing amounts by source as ‘investment mobilized’ or ‘recurrent expenditure’)*

**ToR Annex D: Evaluation Criteria Matrix template**

|  |  |  |  |
| --- | --- | --- | --- |
| **Evaluative Criteria Questions** | **Indicators** | **Sources** | **Methodology** |
| Relevance: How does the project relate to the main objectives of the GEF Focal area, and to the environment and development priorities a the local, regional and national level? |
| *(include evaluative questions)* | *(i.e. relationships established, level of coherence between project design and implementation approach, specific activities conducted, quality of risk mitigation strategies, etc.)* | *(i.e. project documentation, national policies or strategies, websites, project staff, project partners, data collected throughout the TE mission, etc.)* | *(i.e. document analysis, data analysis, interviews with project staff, interviews with stakeholders, etc.)* |
|  |  |  |  |
| Effectiveness: To what extent have the expected outcomes and objectives of the project been achieved? |
|  |  |  |  |
| Efficiency: Was the project implemented efficiently, in line with international and national norms and standards? |
|  |  |  |  |
|  |  |  |  |
| Sustainability: To what extent are there financial, institutional, socio-political, and/or environmental risks to sustaining long-term project results? |
|  |  |  |  |
|  |  |  |  |
| Gender equality and women’s empowerment: How did the project contribute to gender equality and women’s empowerment?  |
|  |  |  |  |
|  |  |  |  |
| Impact: Are there indications that the project has contributed to, or enabled progress toward reduced environmental stress and/or improved ecological status? |
|  |  |  |  |
| *(Expand the table to include questions for all criteria being assessed: Monitoring & Evaluation, UNDP oversight/implementation, Implementing Partner Execution, cross-cutting issues, etc.)* |

**ToR Annex E: UNEG Code of Conduct for Evaluators**

Independence entails the ability to evaluate without undue influence or pressure by any party (including the hiring unit) and providing evaluators with free access to information on the evaluation subject. Independence provides legitimacy to and ensures an objective perspective on evaluations. An independent evaluation reduces the potential for conflicts of interest which might arise with self-reported ratings by those involved in the management of the project being evaluated. Independence is one of ten general principles for evaluations (together with internationally agreed principles, goals and targets: utility, credibility, impartiality, ethics, transparency, human rights and gender equality, national evaluation capacities, and professionalism).

**Evaluators/Consultants:**

1. Must present information that is complete and fair in its assessment of strengths and weaknesses so that decisions or actions taken are well founded.
2. Must disclose the full set of evaluation findings along with information on their limitations and have this accessible to all affected by the evaluation with expressed legal rights to receive results.
3. Should protect the anonymity and confidentiality of individual informants. They should provide maximum notice, minimize demands on time, and respect people’s right not to engage. Evaluators must respect people’s right to provide information in confidence, and must ensure that sensitive information cannot be traced to its source. Evaluators are not expected to evaluate individuals, and must balance an evaluation of management functions with this general principle.
4. Sometimes uncover evidence of wrongdoing while conducting evaluations. Such cases must be reported discreetly to the appropriate investigative body. Evaluators should consult with other relevant oversight entities when there is any doubt about if and how issues should be reported.
5. Should be sensitive to beliefs, manners and customs and act with integrity and honesty in their relations with all stakeholders. In line with the UN Universal Declaration of Human Rights, evaluators must be sensitive to and address issues of discrimination and gender equality. They should avoid offending the dignity and self-respect of those persons with whom they come in contact in the course of the evaluation. Knowing that evaluation might negatively affect the interests of some stakeholders, evaluators should conduct the evaluation and communicate its purpose and results in a way that clearly respects the stakeholders’ dignity and self-worth.
6. Are responsible for their performance and their product(s). They are responsible for the clear, accurate and fair written and/or oral presentation of study imitations, findings and recommendations.
7. Should reflect sound accounting procedures and be prudent in using the resources of the evaluation.
8. Must ensure that independence of judgement is maintained, and that evaluation findings and recommendations are independently presented.
9. Must confirm that they have not been involved in designing, executing or advising on the project being evaluated and did not carry out the project’s Mid-Term Review.

**Evaluation Consultant Agreement Form**

Agreement to abide by the Code of Conduct for Evaluation in the UN System:

Name of Evaluator: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Name of Consultancy Organization (where relevant): \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

I confirm that I have received and understood and will abide by the United Nations Code of Conduct for Evaluation.

Signed at \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (Place) on \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (Date)

Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**ToR Annex F: TE Rating Scales**

|  |  |
| --- | --- |
| Ratings for Outcomes, Effectiveness, Efficiency, M&E, Implementation/Oversight, Execution, Relevance | Sustainability ratings:  |
| 6 = Highly Satisfactory (HS): exceeds expectations and/or no shortcomings 5 = Satisfactory (S): meets expectations and/or no or minor shortcomings4 = Moderately Satisfactory (MS): more or less meets expectations and/or some shortcomings3 = Moderately Unsatisfactory (MU): somewhat below expectations and/or significant shortcomings2 = Unsatisfactory (U): substantially below expectations and/or major shortcomings1 = Highly Unsatisfactory (HU): severe shortcomingsUnable to Assess (U/A): available information does not allow an assessment | 4 = Likely (L): negligible risks to sustainability3 = Moderately Likely (ML): moderate risks to sustainability2 = Moderately Unlikely (MU): significant risks to sustainability1 = Unlikely (U): severe risks to sustainabilityUnable to Assess (U/A): Unable to assess the expected incidence and magnitude of risks to sustainability |

|  |
| --- |
| **Evaluation Ratings Table** |
| Monitoring & Evaluation (M&E) | Rating[[13]](#footnote-13) |
| M&E design at entry |  |
| M&E Plan Implementation |  |
| Overall Quality of M&E |  |
| Implementation & Execution | Rating |
| Quality of UNDP Implementation/Oversight  |  |
| Quality of Implementing Partner Execution |  |
| Overall quality of Implementation/Execution |  |
| Assessment of Outcomes | Rating |
| Relevance |  |
| Effectiveness |  |
| Efficiency |  |
| Overall Project Outcome Rating |  |
| Sustainability | Rating |
| Financial resources |  |
| Socio-political/economic |  |
| Institutional framework and governance |  |
| Environmental |  |
| Overall Likelihood of Sustainability |  |

**ToR Annex G: TE Report Clearance Form**

|  |
| --- |
| **Terminal Evaluation Report for** *(Project Title & UNDP PIMS ID*) **Reviewed and Cleared By:****Commissioning Unit (M&E Focal Point)**Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**Regional Technical Advisor (Nature, Climate and Energy)**Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |

**ToR Annex H: TE Audit Trail**

*The following is a template for the TE Team to show how the received comments on the draft TE report have (or have not) been incorporated into the final TE report. This Audit Trail should be listed as an annex in the final TE report but not attached to the report file.*

**To the comments received on** *(date)* **from the Terminal Evaluation of** *(project name) (UNDP Project PIMS #)*

The following comments were provided to the draft TE report; they are referenced by institution/organization (do not include the commentator’s name) and track change comment number (“#” column):

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Institution/****Organization** | **#** | **Para No./ comment location**  | **Comment/Feedback on the draft TE report** | **TE team****response and actions taken** |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

1. Outcomes, Effectiveness, Efficiency, M&E, I&E Execution, Relevance are rated on a 6-point rating scale: 6 = Highly Satisfactory (HS), 5 = Satisfactory (S), 4 = Moderately Satisfactory (MS), 3 = Moderately Unsatisfactory (MU), 2 = Unsatisfactory (U), 1 = Highly Unsatisfactory (HU). Sustainability is rated on a 4-point scale: 4 = Likely (L), 3 = Moderately Likely (ML), 2 = Moderately Unlikely (MU), 1 = Unlikely (U) [↑](#footnote-ref-1)
2. Access at: <http://web.undp.org/evaluation/guideline/section-6.shtml> [↑](#footnote-ref-2)
3. The Commissioning Unit is obligated to issue payments to the TE team as soon as the terms under the ToR are fulfilled. If there is an ongoing discussion regarding the quality and completeness of the final deliverables that cannot be resolved between the Commissioning Unit and the TE team, the Regional M&E Advisor and Vertical Fund Directorate will be consulted. If needed, the Commissioning Unit’s senior management, Procurement Services Unit and Legal Support Office will be notified as well so that a decision can be made about whether or not to withhold payment of any amounts that may be due to the evaluator(s), suspend or terminate the contract and/or remove the individual contractor from any applicable rosters. See the UNDP Individual Contract Policy for further details:

<https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/PSU_Individual%20Contract_Individual%20Contract%20Policy.docx&action=default> [↑](#footnote-ref-3)
4. Engagement of evaluators should be done in line with guidelines for hiring consultants in the POPP <https://popp.undp.org/SitePages/POPPRoot.aspx> [↑](#footnote-ref-4)
5. <https://intranet.undp.org/unit/bom/pso/Support%20documents%20on%20IC%20Guidelines/Template%20for%20Confirmation%20of%20Interest%20and%20Submission%20of%20Financial%20Proposal.docx> [↑](#footnote-ref-5)
6. <http://www.undp.org/content/dam/undp/library/corporate/Careers/P11_Personal_history_form.doc> [↑](#footnote-ref-6)
7. *Objective (Atlas output) monitored quarterly ERBM and annually in APR/PIR* [↑](#footnote-ref-7)
8. All outcomes monitored annually in the APR/PIR. It is highly recommended not to have more than 4 outcomes. [↑](#footnote-ref-8)
9. Numbers are estimates for the four riverine landscapes as follows: *Plantanista gangetice minor (*Sukkur-1,100, Southern Punjab and Taunsa-500, Dhingano Lakhat-50) and *Axis porcinus ((*Sukkur-150, Southern Punjab-100, Taunsa-70 and Dhingano Lakhat-25) [↑](#footnote-ref-9)
10. Numbers are estimates for the two temperate conifer sites as follows: *Lophophorus impeyanus* (Kaghan-250, Siran-125); *Semnopithecus entellus (*Kaghan-150) [↑](#footnote-ref-10)
11. Pre-project baseline numbers will be validated and adjusted during Year 1 of the project [↑](#footnote-ref-11)
12. See ToR Annex F for rating scales. [↑](#footnote-ref-12)
13. Outcomes, Effectiveness, Efficiency, M&E, I&E Execution, Relevance are rated on a 6-point rating scale: 6 = Highly Satisfactory (HS), 5 = Satisfactory (S), 4 = Moderately Satisfactory (MS), 3 = Moderately Unsatisfactory (MU), 2 = Unsatisfactory (U), 1 = Highly Unsatisfactory (HU). Sustainability is rated on a 4-point scale: 4 = Likely (L), 3 = Moderately Likely (ML), 2 = Moderately Unlikely (MU), 1 = Unlikely (U) [↑](#footnote-ref-13)