## Preparatory
| lead | supervised | status | July |  |  |  | August |  |  |  | September |  |  |  | October | November |  |  |  | December |  |  |  | January |  |  |  | Febuary |  |  |  | March
|  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Phase 1: Preparation
Development of the CF evaluation roadmap | UNCT | RCO | ongoing
Clearance of the roadmap | UNCT | RCO
Nomination of the Evaluation Manager (EM) | UNCT | RC
Constitution of the Evaluation Steering Committee (ESC) | EM | RC/UNCT
Development of TOR for CF evaluation
Review and clearance of ToR by ESC, PCG
Quality assurance of ToR by regional bodies (UN evaluation network; Regional Office-DCO) for review and clearance
Quality assurance and approval of ToR by DCO-HQ
Extraction of ToR for Request for Proposal (RFP) for the recruitment of international evaluator
Extraction of ToR for RFP for recruitment of national consultant
Publication of RFPs for International consultant & National Consultant and distribution to identified evaluators
Consultants’ recruitment process | EM | RC/UNCT | bar: November 1 to November 2
Review panel constituted | bar: November 3
Assessment of CVs report submitted to RCO | bar: November 3
Assessment report submitted to DCO-HQ with CVs of proposed consultants for pre-qualification | EM/RCO | UNCT | bar: November 4
Pre-qualification of DCO-HQ | bar: December 1
Contracting of Evaluation Team: | bar: December 3
Onboarding of evaluation team | bar: December 4
[1] recommended that the UN agency holding the position of chair of the M&E group, or the chair of the PMT or any other agency with a substantive M&E officer
[2] a technical subset of the joint national and UN steering committee
[3] See CF Evaluation Templates-Tools
[4] Adhere to procurement requirements

## Complete Roadmap
| lead | supervised | status | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  | Month 8
|  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Phase 1: Preparation
Development of the CF evaluation roadmap | UNCT | RCO
Clearance of the roadmap | UNCT | RCO
Nomination of the Evaluation Manager (EM) | UNCT | RC
Constitution of the Evaluation Steering Committee (ESC) | EM | RC/UNCT
Development of TOR for CF evaluation[3]
Review and clearance of ToR by ESC, PMT
Quality assurance of ToR by regional bodies (UN evaluation network; RO-DCO) for review and clearance
Quality assurance and approval of ToR by DCO-HQ
Draft TOR is translated (if necessary)
Extraction of ToR for RFP for the recruitment of international evaluator
Extraction of ToR for RFP for recruitment of national consultant
Publication of RFPs for IC & NCs[4] and distribution to identified evaluators
Consultants’ recruitment process | EM | RC/UNCT
Review panel constituted
Assessment of CVs report submitted to RCO
Assessment report submitted to DCO-HQ with CVs of proposed consultants for pre-qualification | EM/RCO | UNCT
Pre-qualification of DCO-HQ
Contracting of Evaluation Team:
Onboarding of evaluation team
Phase 2: Design phase
Compilation of documents for desk review | bar: July 2 to August 4
IC’s arrival in the country | bar: September 1
Initial desk review by evaluation team (ET) | bar: September 2 to September 3
Development of inception report | bar: September 3
Updating the operational workplan with details on field phase | ET | EM | bar: September 3 to September 4
Submission of draft inception report | ET | EM | bar: September 3 to September 4
Quality assurance and clearance of IR by UNCT | EM | RCO | bar: October 1
Review and finalization of the IR | IC | EM | bar: October 1
Quality assurance and clearance of IR by DCO-HQ | RB[5] | DCO-HQ | bar: October 2
Phase 3: Field phase
Secondary desk review | ET | IC | bar: October 3 to November 1
Data collection | bar: October 3 to November 1
Phase 4: Analysis, reporting and management response phase
Data mining, validation and analysis | ET | EM | bar: November 2 to November 3
Preliminary findings presented to RCO/UNCT and comments | IC | EM | bar: November 2 to November 3
Preliminary findings presented to ESC | bar: November 3
Submission of first draft of the report | ET | IC
Quality assurance on the draft report (UNCT/ESC/RCO) | EM | RCO
Submission of final draft report | ET | IC
Evaluation quality assessment on the report by regional bodies | EM | DCO-HQ
Approval of final report | EM | RCO
UNCT
Stakeholders workshop for presentation of findings
Management response development | EM | RCO
UNCT
Submission of management response to PPB-HQ (Inter agency programming section)
Phase 5: Dissemination of the report
DCO internal dissemination
Report distributed to in-country stakeholders
Uploading of final evaluation report with MR on DCO Evaluation Database by PPB
*
[1] recommended that the UN agency holding the position of chair of the M&E group, or the chair of the PMT or any other agency with a substantive M&E officer
[2] a technical subset of the joint national and UN steering committee
[3] See CF Evaluation Templates-Tools
[4] Adhere to procurement requirements
[5] Regional evaluation bodies/consultants