**The UNDP Response to the Recommendations of the Jatropha Project: Final Evaluation Report**

**Management Response to the Recommendations**

| Recommendations (addressed to UNDP) | **\*Administration Response** |
| --- | --- |
| Proposed response (per relevance, timeliness, and feasibility) | Key Actions (that implement the recommendation) | Timeframe for action implementation | **Responsible Unit**  |
| 1/ Hold at least one self-evaluation workshop with representatives of beneficiaries, the implementation team and partner institutions in each region of intervention, with recommendations for the finalisation/consolidation of project achievements | Possible: Workshop is potentially relevant but there is no current budget provision. | This workshop could be merged with the national assessment workshop. Failing that, it could be organized by the Ministry of Energy, via the DGER. | Early May 2020, COVID-19 permitting. | E&E; DGER |
| 2/ Organise a national review workshop with implementation partners, in addition to other stakeholders identified as relevant at the time of project formulation | Relevant: Review workshop is planned and budget allocation guaranteed. | Workshop to be organised following the reception and validation of the Jatropha Project: Final Evaluation Report | End May 2020, COVID-19 permitting | PCU, with the support of the UNDP E&E unit |
| 3/ Formalise service agreements and partnership agreements with strategic partners (INERA, IRSAT, ABNORM, SP CNDD) to serve as a relay for the continuation and sustainability of the project's achievements | Relevant: Formalisation to be explored with the DGER, considering partners’ interests in the sustainability of the project's achievements. | The strategic partners to be invited to the review workshop where the end-of-project documents (final evaluation - closing report etc.) will be shared. | May 2020, COVID-19 permitting | E&E; DGER |
| 4/ Collect the lessons learned and good practices established by the project and disseminate in the form of articles, posters, news briefs, summary notes etc. to actors and stakeholders involved in the Jatropha Curcas  | Relevant: A ‘Lessons Learned’ report is planned with PCU and DGER but no current budget provision for dissemination | Suggest dissemination activities are led by the Ministry for Energy via the DGER | November 2019 | E&E is undertaking the monitoring |

PCU: Projet Coordination Unit

E&E: UNDP Energy and Environment Unit, Burkina Faso

DGER: Directorate-General for Renewable Energy, Burkina Faso Ministry for Energy