## Slide 1: Policy Support Programme Evaluation
Key Findings

## Slide 2: Evaluation Scope
Analysis of Project achievements - both expected and unexpected results
Evaluation criteria: Relevance, coherence, effectiveness, efficiency, impact, and sustainability, as well as Leaving No One Behind.
Limited to activities and interventions funded by PSP
Limited to impact in terms of policy actions (not impact on the ultimate beneficiaries of the policies)
Project Period 2013 – 2020

## Slide 3
Inception: Clarity on TORs, scope, finalization of methodology, report outline
Data: 1) Secondary data analysis (Project reports, online information); 2) Primary data / feedback from Key Informant Interview, Focus Group Discussion
Analysis - Largely qualitative through: (1) Triangulation (primary and secondary information); (2) Quotes / citations from KIIs; (3) Performance rating by KIIs
Presentation: Standard UNDP evaluation report template
Limitations: Qualitative analysis, online interviews, impact in the form of policy actions and not at the beneficiary level
Evaluation Process and Methodology

## Slide 4
 | Stakeholders | Project Focus Area
1 | UNDP / Project Staff | Project design, implementation, oversight Inter-unit collaboration
2 | Planning Ministry | Evidence based policy analysis, Data analysis and statistical indices (MPI) COVID-19 Socioeconomic Impact Assessment
3 | Metropolitan Corporation Islamabad, Private sector partners | Urban platform
4 | Pakistan Bureau of Statistics (data) | Data analysis and statistical indices (MPI)
6 | Policy Research Institutes and Academia | Evidence based policy analysis Dissemination: Policy dialogues and conferences
8 | UN Agencies | Inter-agency collaboration
Sampling Frame (KIIs)

## Slide 5
Findings

## Slide 6
Highly relevant to Pakistan’s MIC context, UNDP SP, UN SDF and CPD 2018-22
Key enablers: (1) Focus on inclusion and innovation; (2) Unique products - MPI, NHDR on Youth and Inequality; (3) Sustained policy advocacy through DAP; (4) Flexibility and promoting innovation (urban platform, water recycling)
Areas for improvement: (1) Project design – theory of change, stakeholder consultations, results framework including linking to right outcomes and outputs; (2) Greater focus on sustainable production and consumption; (3) Leave No One Behind, with focus on key issues facing vulnerable populations
Relevance

## Slide 7
Both Internal and external coherence satisfactory
Key enablers for internal coherence: (1) Unique project interventions; (2) DAP Advisory Council with all ARRs represented (3) DAP and MPI informing programmatic interventions
Key enablers for external coherence: (1) Joint research work and policy dialogues with civil society and academia; (2) NHDR Advisory Board – RCO, UNICEF; (3) MOU / Cost Sharing with UNICEF
Areas for improvement: (1) Internal coherence through joint research beyond DAP, project concepts / ideations; (2) External coherence through partnerships with private sector
Coherence

## Slide 8
87% achievement against output targets. Output 1 progress higher than other two outputs. Overall positive effective in influencing public policy.
Key enablers: (1) Output 1: DAP and NHDRs; (2) Output 2: DPU to support other program units, project developments (reform and innovation, SDGs project, Balochistan SDG Acceleration); (3) Output 3: Urban platform, water recycling, Randomized Control Trial, matching platform with Bangkok Office
Areas for improvement: (1) Going beyond, DPU for cross-unit support, should emphasis on joint assessment and ideas generation; (2) Follow up to urban platform and water recycling; (3) Project design issues: output targets articulation (separate for research on innovation and prototypes); (4) Private sector partnership; (5) specific interventions for ‘Leave No One Behind’.
Effectiveness

## Slide 9
Highly efficient cost wise, efficient time wise.
Key enablers: (1) Project organogram: National professionals, DPU core staff embedded for advice, management and oversight; (2) Partnerships with diverse stakeholders; (3) Use of DPU internal capacities; (4) Less reliance on outside consultants by strengthening institutions; (5) Continuous learning – e.g., reduction in NHDR cost
Areas for improvement: (1) Clear / numeric annual targets; (2) Substantial annual reports; (3) Treatment and updating assumptions and risks
Efficiency

## Slide 10
Effects on public policy (in terms of policy actions) and UNDP programming is satisfactory. Effects on policy actions for vulnerable populations need further improvement.
Key enablers: (1) Institutionalization of MPI; (2) NHDR on Youth informing Kamyab Jawan Programme; (3) MPI informing 12th 5 Year Plan, poverty targeting (Ehsaas); (4) MPI informing UNDP project’s design; (5) PSP providing launching pad for National SDGs project
Areas for improvement: (1) Going beyond composite indices (HDI, MPI, GII) to focus on specific impact areas for vulnerable population; (2) Engagement with local / city governments; (3) Follow ups to urban platform and water recycling
Impact

## Slide 11
Sustaining project impact is more likely compared to financial sustainability.
Key enablers: (1) MPI already institutionalized and sustained; (2) NHDR on Youth - 3Es informed Kamyab Jawan Programme; (3) Low-cost project, easy to sustain through UNDP and outside resources; (4) DAP, MPI informing UNDP projects
Areas for improvement: (1) More focus on government capacity development; (2) sub-national engagement.
Sustainability

## Slide 12
Project design: Stakeholders’ engagement, Theory of Change, Results Framework should be strengthened
Link the project to the right UN SDF outcome and CPD outputs
Sub-national partnerships for sub-national policy instruments
Leave No One Behind: Specific areas, specific interventions focusing on specific marginalized groups (besides comprehensive / composite indices)
Project documentation: Lessons, experiences, reporting
Political engagement: Build on NHDR’s Advisory Councils’ format
Broaden UN agencies’ participation
More focus on sustainability issues (consumption and production)
Financing for development: private sector financing, bonds etc
Recommendations

## Slide 13
UNDP core team’s lead on policy support is more impactful.
Project focus on specific project issues, rather than spreading too thin, generates impact.
UNDP direct implementation modality suits policy work on sensitive issues
UNDP leading NHDR preparation, as a UNDP product, is the better option
Political engagement is key to policy actions (example: NHDRs)
Lessons

## Slide 14
Note: Both the arithmetic means and median is around 4. This is based on 19 responses.
KIIs Respondents Performance Rating
Evaluation Criteria | Rating | Description and Evidence
Relevance | 4 | The project focus on inclusive growth and human development is highly relevant to the national context. Policy instruments HDI, MPIs, DAP, and research studies have been very relevant in advocating for policy actions related to inclusive development.
Coherence | 3 | Internal coherence through unique project activities and products and platforms (DAP Advisory Board) for cross unit collaboration. Partnerships with diverse stakeholders including civil society, government, UN agencies and academic for external coherence.
Effectiveness | 4 | Achievement of more than 87% progress against targets. The production of flagship policy products including NHDRs, MPI and their contributions to the public policy actions. Water recycling prototype, a low-cost indigenous technology with huge potential for improving water conservation in urban settings.
Efficiency | 4 | Low budget, high impact project. Efficient project organogram and management arrangements. Efficient use of internal UNDP capacities. Timely completion of all major project interventions. Efficient project implementation and partnership arrangements.
Impact | 4 | Effects on public policy including the institutionalization of MPI as official poverty measure and the 3 Es of NHDR in government national youth programme (Kamyab Jawan). Effects on UNDP programming in terms of using PSP as platform for designing “reform and innovation” and “National SDG” projects. DAP informing project on SDG Acceleration in Balochistan.
Sustainability | 3 | Sustainability of policy impact in terms of institutionalization of MPI and key recommendations of NHDR on Youth. Financial sustainability in terms of low cost and high impact activities which could be easily funded from UNDP internal resources and donors’ contributions (there is already evidence of donors’ financing)
Leave no one behind | 2.5 | MPIs and HDIs for poverty targeting. Special sections of DAP for gathering women and youth inputs. No standalone focused work.
Overall | 4 | Highly Satisfactory
Rating scale: 1 (poor), 2 (average), 3 (satisfactory), 4 (highly satisfactory), 5 (excellent)