**Terminal Evaluation Terms of Reference (ToR) for**

**The Strengthening National Protected Areas Systems (SNPAS) in Eswatini (PIMS #4932) -** *formatted for the* [UNDP Jobs website](https://jobs.undp.org/cj_view_jobs.cfm)

**BASIC CONTRACT INFORMATION**

**Location: Home based**

**Application Deadline: 30 June**

**Type of Contract: Individual contract**

**Assignment Type: IPSA**

**Languages Required: English**

**Starting Date: 20 July 2021**

**Duration of Initial Contract: 20 days**

**Expected Duration of Assignment: 8 weeks**

**BACKGROUND**

##### **Introduction**

In accordance with UNDP and GEF M&E policies and procedures, all full- and medium-sized UNDP-supported GEF-financed projects are required to undergo a Terminal Evaluation (TE) at the end of the project. This Terms of Reference (ToR) sets out the expectations for the TE of the full-size project titled Project Title: The Strengthening National Protected Areas Systems (SNPAS) in Eswatini (PIMS #4932) implemented through the Eswatini National Trust Commission/Ministry of Tourism and Environmental Affairs. The project started on the 03 October 2014 (final signature date) and is in its *7th* year of implementation. The TE process must follow the guidance outlined in the document ‘Guidance for Conducting Terminal Evaluations of UNDP-Supported, GEF-Financed Projects’ (<http://web.undp.org/evaluation/guideline/documents/GEF/TE_GuidanceforUNDP-supportedGEF-financedProjects.pdf>).

1. **PROJECT BACKGROUND AND CONTEXT**

The Strengthening National Protected Areas Systems (SNPAS) in Eswatini is funded by Global Environment Facility (GEF), supported by the United Nations Development Programme (UNDP) and implemented by the Eswatini National Trust Commission (ENTC) in collaboration with the Eswatini Tourism Authority and Local Governments (Tinkhundlas). Eswatini’s formal Protected Areas (PAs) baseline covered approximately 3.9% of the country’s total land area. These areas are relatively rich in biodiversity with their share of endemism as represented in various ecosystems. Furthermore, the country has set targets for the conservation of its ecosystems and species in line with the National Development Strategy (Vision 2022) and other international targets such as the Aichi Targets under the auspices of the Convention on Biological Diversity. While some of the critical ecosystems and species are found in existing PAs, some are found in areas prone to unstainable utilization and overexploitation of resources, thereby threatening livelihoods and impeding sustainable development.

The SNPAS project’s goal was to strengthen the management effectiveness of the PA system of Eswatini to ensure a viable set of representative samples of the country’s full range of natural ecosystems are conserved, through a network of PAs. The project objective is to effectively expand, manage and develop Swaziland’s protected area network in order to adequately protect the biodiversity and landscapes of the country. This involved devising a system of integrating land and natural resource management that transforms the current PA patchwork into a protected areas network, while creating incentives for all Swazis (land management agencies, conservancies, private landowners and tourism operators) to work together toward conservation and sustainable economic development. In order to achieve the project goal and objective , the project’s interventions have been organised in three components:

**Component 1:** Knowledge based platform operationalised at the National and regional level to address current and emerging threats to PAs and biodiversity conservation.

**Component 2:** Landscape approach operationalised and leads to expansion of PA network.

**Component 3:** Strengthening PA functioning through improved Conservation management and Operational support for existing and new PAs, including both formal and informal PAs.

The project was designed to contribute to objective 8 of the Eswatini National Development Strategy 2022: to ensure environmental sustainability and strategic area 3.7 on environmental management; and outcome 3 of UNDAF/CPD 2011-2015 on National institutions have the capacity and providing guidance on the ulitilisation of natural resources in a sustainable and equitable manner. Implementation of the project has spanned three UNDAF/CPD frameworks including UNDAF/CPD 2016-2020 and 2021-2025. The project started on the 03rd October 2014 and is in its 7th year of implementation. Financing for the project included: US$ 5,500,000 GEF grant and co-financing of US$ 23,600,000. Implementation followed UNDP policies and procedures for Nationally Executed projects with Country Office support. Although it was designed for a six year implementation period, following the mid-term review recommendations and COVID19 pandemic the project was extended for an additional 12 months.

Like many countries, Eswatini has been affected and impacted by the COVID19 pandemic. The country has registered 823 cases with 676 death as at 17th June 2021[[1]](#footnote-1). A total of 35227 have been vaccinated since the programme was rolled out at the end of March 2021. Following the registration of positive COVID-19 cases in the country, the Government, on 17 March 2020, declared the COVID-19 pandemic a National Emergency. It further activated a comprehensive programme for managing initial and cascading impacts, which were induced by the strain on the health care capacity as well as the enforcement of core measures as means to mitigate the spread of the virus. Measures undertaken included cross border and air travel bans and limitations, suspension of public gatherings, closure of offices and businesses except for emergency services to minimise the spread of the virus. As a result of these measures, a number of project activities were disrupted, delayed and suspended due to COVID restrictions.

COVID-19 Pandemic delayed implementation of all activities that required international travel, community engagements and delayed deliveries of equipment’s and civil works materials due to restrictions in travels and closure of many none essential service providers. The ban of international travel delayed service delivery on other effective conservation measures (OECM) activities and site evaluations to expand protected area networks (ultimate objective) disbursement of catalytic funding for communities Furthermore, supply chain for some civil works such as cement and steel materials imported from South Africa took longer than planned thus delaying completion of deliverables.

In accordance with UNDP and GEF M&E policies and procedures, all full- and medium-sized UNDP-supported GEF-financed projects are required to undergo a Terminal Evaluation (TE) at the end of the project. This Terms of Reference (ToR) sets out the expectations for the TE of the full-sized project titled Strengthening National Protected Areas Systems (SNPAS) in Eswatini (PIMS 4932) implemented through the ENTC.

1. **TE PURPOSE**

The TE report will assess the achievement of project results against what was expected to be achieved, and draw lessons that can both improve the sustainability of benefits from this project, and aid in the overall enhancement of UNDP programming. The TE report promotes accountability and transparency, and assesses the extent of project accomplishments.

The objective of the TE is to assess project performance against expectations set out in the project’s Logical Framework/Results Framework. The TE will assess results according to the criteria outlined in the Guidance for TEs of UNDP-supported GEF-financed Projects.

**DUTIES AND RESPONSIBILITIES**

##### **TE Approach & Methodology**

The TE report must provide evidence-based information that is credible, reliable and useful. The TE team will review all relevant sources of information including documents prepared during the preparation phase (i.e. PIF, UNDP Initiation Plan, UNDP Social and Environmental Screening Procedure/SESP) the Project Document, project reports including annual PIRs, project budget revisions, lesson learned reports, national strategic and legal documents, and any other materials that the team considers useful for this evidence-based evaluation. The TE team will review the baseline and midterm GEF focal area Core Indicators/Tracking Tools submitted to the GEF at the CEO endorsement and midterm stages and the terminal Core Indicators/Tracking Tools that must be completed before the TE field mission begins.

The TE team is expected to follow a participatory and consultative approach ensuring close engagement with the Project Team, government counterparts (the GEF Operational Focal Point), Implementing Partners, the UNDP Country Office(s), the Regional Technical Advisor, direct beneficiaries and other stakeholders.

Engagement of stakeholders is vital to a successful TE. Stakeholder involvement should include interviews with stakeholders who have project responsibilities, including but not limited to *(Eswatini National Trust Commission; Eswatini Tourism Authority, Tikhundulas in the Ngwempsis, Maloloja and Lubombo Landscapes, Ministry of Tourism and Environmental Affairs)*; executing agencies, senior officials and task team/component leaders, key experts and consultants in the subject area, Project Board, project steering committee, project beneficiaries, academia, local government and CSOs, etc. Additionally, the TE team is expected to conduct field missions to *(Ngwempisi, Maloloja and Lubombo landscapes/clusters and interact with project stakeholders and beneficiaries)*, including the following project sites *(Mlawula Wildlife Reserve, Shewula community Camp, of Lubombo Landscape; Maloloja Wildlife Reserve, Mlwane, Mantenga Nature Reserve)*.

In line with COVID19 standard operating procedures to minimise spread of the virus, protect consultants, communities and partners, the TE team will use extended desk reviews, secondary data, and virtual interviews. The consultants may also use spatial technologies to assess status of investments undertaken by the project.

The specific design and methodology for the TE should emerge from consultations between the TE team and the above-mentioned parties regarding what is appropriate and feasible for meeting the TE purpose and objectives and answering the evaluation questions, given limitations of budget, time and data. The TE team must use gender-responsive methodologies and tools and ensure that gender equality and women’s empowerment, as well as other cross-cutting issues and SDGs are incorporated into the TE report. The final methodological approach including interview schedule, field visits and data to be used in the evaluation must be clearly outlined in the TE Inception Report and be fully discussed and agreed between UNDP, stakeholders and the TE team.

The final report must describe the full TE approach taken and the rationale for the approach making explicit the underlying assumptions, challenges, strengths and weaknesses about the methods and approach of the evaluation.

As of 11 March 2020, the World Health Organization (WHO) declared COVID-19 a global pandemic as the new coronavirus rapidly spread to all regions of the world. Travel to the country has been restricted since 17March 2020 and travel in the country is also restricted.

If it is not possible to travel to or within the country for the TE mission then the TE team should develop a methodology that takes this into account the conduct of the TE virtually and remotely, including the use of remote interview methods and extended desk reviews, data analysis, surveys and evaluation questionnaires. This should be detailed in the TE Inception Report and agreed with the Commissioning Unit.

If all or part of the TE is to be carried out virtually then consideration should be taken for stakeholder availability, ability or willingness to be interviewed remotely. In addition, their accessibility to the internet/computer may be an issue as many government and national counterparts may be working from home. These limitations must be reflected in the final TE report.

If a data collection/field mission is not possible then remote interviews may be undertaken through telephone or online (skype, zoom etc.). International consultants will work remotely with national evaluator support in the field if it is safe for them to operate and travel. No stakeholders, consultants or UNDP staff should be put in harm’s way and safety is the key priority.

A short validation mission may be considered if it is confirmed to be safe for staff, consultants, stakeholders and if such a mission is possible within the TE schedule. Equally, qualified and independent national consultants will be hired to undertake the TE and interviews in country as long as it is safe to do so.

1. **Detailed Scope of the TE**

The TE will assess project performance against expectations set out in the project’s Logical Framework/Results Framework (see ToR Annex A). The TE will assess results according to the criteria outlined in the Guidance for TEs of UNDP-supported GEF-financed Projects *(*[*http://web.undp.org/evaluation/guideline/documents/GEF/TE\_GuidanceforUNDP-supportedGEF-financedProjects.pdf*](http://web.undp.org/evaluation/guideline/documents/GEF/TE_GuidanceforUNDP-supportedGEF-financedProjects.pdf).

The TE consultants will review all relevant sources of information including documents prepared during the preparation phase (i.e. PIF, UNDP Initiation Plan, UNDP Social and Environmental Screening Procedure/SESP) the Project Document, project reports including annual PIRs, project budget revisions, lesson learned reports, national strategic and legal documents, and any other materials that the team considers useful for this evidence-based evaluation. The TE team will review the baseline and midterm GEF focal area Core Indicators/Tracking Tools submitted to the GEF at the CEO endorsement and midterm stages and the terminal Core Indicators/Tracking Tools that must be completed before the TE field mission begins. The TE consultants are expected to follow a participatory and consultative approach ensuring close engagement with the Project Team, government counterparts (the GEF Operational Focal Point), Implementing Partners, the UNDP Country Office(s), the Regional Technical Advisor, direct beneficiaries and other stakeholders.

The Findings section of the TE report will cover the topics listed below. A full outline of the TE report’s content is provided in ToR Annex C.

The asterisk “(\*)” indicates criteria for which a rating is required.

Findings

1. Project Design/Formulation
* National priorities and country driven-ness
* Theory of Change
* Gender equality and women’s empowerment
* Social and Environmental Safeguards
* Analysis of Results Framework: project logic and strategy, indicators
* Assumptions and Risks
* Lessons from other relevant projects (e.g. same focal area) incorporated into project design
* Planned stakeholder participation
* Linkages between project and other interventions within the sector
* Management arrangements
1. Project Implementation
* Adaptive management (changes to the project design and project outputs during implementation)
* Actual stakeholder participation and partnership arrangements
* Project Finance and Co-finance
* Monitoring & Evaluation: design at entry (\*), implementation (\*), and overall assessment of M&E (\*)
* Implementing Agency (UNDP) (\*) and Executing Agency (\*), overall project oversight/implementation and execution (\*)
* Risk Management, including Social and Environmental Standards
1. Project Results
* Assess the achievement of outcomes against indicators by reporting on the level of progress for each objective and outcome indicator at the time of the TE and noting final achievements
* Relevance (\*), Effectiveness (\*), Efficiency (\*) and overall project outcome (\*)
* Sustainability: financial (\*) , socio-political (\*), institutional framework and governance (\*), environmental (\*), overall likelihood of sustainability (\*)
* Country ownership
* Gender equality and women’s empowerment
* Cross-cutting issues (poverty alleviation, improved governance, climate change mitigation and adaptation, disaster prevention and recovery, human rights, capacity development, South-South cooperation, knowledge management, volunteerism, etc., as relevant)
* GEF Additionality
* Catalytic Role / Replication Effect
* Progress to impact
1. Main Findings, Conclusions, Recommendations and Lessons Learned
* The TE team will include a summary of the main findings of the TE report. Findings should be presented as statements of fact that are based on analysis of the data.
* The section on conclusions will be written in light of the findings. Conclusions should be comprehensive and balanced statements that are well substantiated by evidence and logically connected to the TE findings. They should highlight the strengths, weaknesses and results of the project, respond to key evaluation questions and provide insights into the identification of and/or solutions to important problems or issues pertinent to project beneficiaries, UNDP and the GEF, including issues in relation to gender equality and women’s empowerment.
* Recommendations should provide concrete, practical, feasible and targeted recommendations directed to the intended users of the evaluation about what actions to take and decisions to make. The recommendations should be specifically supported by the evidence and linked to the findings and conclusions around key questions addressed by the evaluation.
* The TE report should also include lessons that can be taken from the evaluation, including best practices in addressing issues relating to relevance, performance and success that can provide knowledge gained from the particular circumstance (programmatic and evaluation methods used, partnerships, financial leveraging, etc.) that are applicable to other GEF and UNDP interventions. When possible, the TE team should include examples of good practices in project design and implementation.
* It is important for the conclusions, recommendations and lessons learned of the TE report to include results related to gender equality and empowerment of women.

The TE report will include an Evaluation Ratings Table, as shown in the ToR Annex.

1. **Expected Outputs and Deliverables**

The TE *consultant/team* shall prepare and submit:

* TE Inception Report: TE team clarifies objectives and methods of the TE no later than *2 weeks* before the TE mission. TE team submits the Inception Report to the Commissioning Unit and project management. Approximate due date: *(05 August)*
* Presentation: TE team presents initial findings to project management and the Commissioning Unit at the end of the TE mission. Approximate due date: *(20 August)*
* Draft TE Report: TE team submits full draft report with annexes *within 3 weeks* of the end of the TE mission. Approximate due date: *(31 August)*
* Final TE Report\* and Audit Trail: TE team submits revised report, with Audit Trail detailing how all received comments have (and have not) been addressed in the final TE report, to the Commissioning Unit *within 1 week* of receiving UNDP comments on draft. Approximate due date: *(10 September)*

\*The final TE report must be in English. If applicable, the Commissioning Unit may choose to arrange for a translation of the report into a language more widely shared by national stakeholders.

All final TE reports will be quality assessed by the UNDP Independent Evaluation Office (IEO). Details of the IEO’s quality assessment of decentralized evaluations can be found in Section 6 of the UNDP Evaluation Guidelines.[[2]](#footnote-2)

1. **TE Arrangements**

The principal responsibility for managing the TE resides with the Commissioning Unit. The Commissioning Unit for this project’s TE is UNDP Eswatini Country Office.

The UNDP Country Office will i) contract the evaluators ii) ensure timely provision of per diems and travel arrangements within the country for the TE team; iii) procure venue and provide zoom/team platforms for virtual stakeholder consultations (inception and validation workshops). The Project Team will be responsible for liaising with the TE team to provide all relevant documents, set up stakeholder interviews, and arrange field visits where possible.

1. **Duration of the Work**

The total duration of the TE will be approximately *30 working days* over a time period of *8 weeks* starting *20 July* and shall not exceed five months from when the TE team is hired. The tentative TE timeframe is as follows:

1. *30 June:* Application closes
2. *15 July:* Selection of TE Team
3. *20 July:* Prep the TE team (handover of project documents)
4. *02 August: 05* days (recommended 2-4): Document review and preparing TE Inception Report
5. *09 August: 02* days: Finalization and Validation of TE Inception Report- latest start of TE mission
6. *10 August: 15* days: TE mission: stakeholder meetings, interviews, field visits
7. *20 August:* Mission wrap-up meeting & presentation of initial findings- earliest end of TE mission
8. *30 August: 08* days: Preparation of draft TE report
9. *31 August:* Circulation of draft TE report for comments
10. *10 September: 02* days (r: 1-2): Incorporation of comments on draft TE report into Audit Trail & finalization of TE report
11. *15 September:* Preparation & Issue of Management Response
12. *30 September:* Expected date of full TE completion

The expected date start date of contract is *30 September.*

1. **Duty Station**

*This is a home based assignment with one mission to Eswatini and project sites.*

**Travel:**

* International travel to Eswatini will be optional considering COVID19 pandemic situationduring the TE mission;
* The BSAFE course must be successfully completed prior to commencement of travel;
* Individual Consultants are responsible for ensuring they have vaccinations/inoculations when travelling to certain countries, as designated by the UN Medical Director.
* Consultants are required to comply with the UN security directives set forth under: <https://dss.un.org/dssweb/>
* All related travel expenses will be covered and will be reimbursed as per UNDP rules and regulations upon submission of an F-10 claim form and supporting documents.

**REQUIRED SKILLS AND EXPERIENCE**

1. **TE Team Composition and Required Qualifications**

A team of two independent evaluators will conduct the TE – one team leader (with experience and exposure to projects and evaluations in other regions) and one national expert. The team leader will be responsible for the overall design and writing of the TE report, etc.) The national expert will report to the team leader. S/he will assess emerging trends with respect to regulatory frameworks, budget allocations for co-financing, capacity building, work with the Project Team in developing the TE itinerary and lead stakeholder consultations and field visits and contribute to preparation of required reports.

The evaluator (s) cannot have participated in the project preparation, formulation and/or implementation (including the writing of the project document), must not have conducted this project’s Mid-Term Review and should not have a conflict of interest with the project’s related activities.

The selection of evaluators will be aimed at maximizing the overall “team” qualities as outlined below:

**Team Leader (International)**

Required Qualifications and expertise

* Master’s degree in in Sustainable development, Environmental Science, Natural Resources Management, Monitoring and Evaluation or other closely related field;

Experience

* Relevant experience with results-based management evaluation methodologies;
* Experience applying SMART indicators and reconstructing or validating baseline scenarios;
* Competence in adaptive management, as applied to *biodiversity conservation Focal Area;*
* Experience in evaluating projects;
* Experience working in *the SADC region;*
* Experience in relevant technical areas for at least *10 years;*
* Demonstrated understanding of issues related to gender and *biodiversity conservation* experience in gender responsive evaluation and analysis;
* Excellent communication skills;
* Demonstrable analytical skills;
* Project evaluation/review experience within United Nations system will be considered an asset.
* *Experience with implementing evaluations remotely will be considered an asset.*

Competencies

* Experience in leading multi-disciplinary, multi-national teams to deliver quality products in high stress, short deadline situations.
* Excellent Analytical Skills;
* Positive, constructive attitude towards work;
* Ability to act professionally and flexibly to engage with government officials, donor representatives, and local communities.

Language

* Fluency in written and spoken English.
1. **Evaluator Ethics**

The TE team will be held to the highest ethical standards and is required to sign a code of conduct upon acceptance of the assignment. This evaluation will be conducted in accordance with the principles outlined in the UNEG ‘Ethical Guidelines for Evaluation’. The evaluator must safeguard the rights and confidentiality of information providers, interviewees and stakeholders through measures to ensure compliance with legal and other relevant codes governing collection of data and reporting on data. The evaluator must also ensure security of collected information before and after the evaluation and protocols to ensure anonymity and confidentiality of sources of information where that is expected. The information knowledge and data gathered in the evaluation process must also be solely used for the evaluation and not for other uses without the express authorization of UNDP and partners.

1. **Payment Schedule**
* 20% payment upon satisfactory delivery of the final TE Inception Report and approval by the Commissioning Unit
* 40% payment upon satisfactory delivery of the draft TE report to the Commissioning Unit
* 40% payment upon satisfactory delivery of the final TE report and approval by the Commissioning Unit and RTA (via signatures on the TE Report Clearance Form) and delivery of completed TE Audit Trail

Criteria for issuing the final payment of 40%

* The final TE report includes all requirements outlined in the TE TOR and is in accordance with the TE guidance.
* The final TE report is clearly written, logically organized, and is specific for this project (i.e. text has not been cut & pasted from other MTR reports).
* The Audit Trail includes responses to and justification for each comment listed.

**APPLICATION PROCESS**

*(Adjust this section if a vetted roster will be used)-RTA to advise*

1. **Scope of Price Proposal and Schedule of Payments**

**Financial Proposal:**

* Financial proposals must be “all inclusive” and expressed in a lump-sum for the total duration of the contract. The term “all inclusive” implies all cost (professional fees, travel costs, living allowances etc.);
* For duty travels, the UN’s Daily Subsistence Allowance (DSA) rates are (fill for all travel destinations), which should provide indication of the cost of living in a duty station/destination *(Note: Individuals on this contract are not UN staff and are therefore not entitled to DSAs. All living allowances required to perform the demands of the ToR must be incorporated in the financial proposal, whether the fees are expressed as daily fees or lump sum amount.)*
* The lump sum is fixed regardless of changes in the cost components.
1. **Recommended Presentation of Proposal**
2. **Letter of Confirmation of Interest and Availability** using the [template](https://intranet.undp.org/unit/bom/pso/Support%20documents%20on%20IC%20Guidelines/Template%20for%20Confirmation%20of%20Interest%20and%20Submission%20of%20Financial%20Proposal.docx) provided by UNDP;
3. **CV** and a **Personal History Form** ([P11 form](http://www.undp.org/content/dam/undp/library/corporate/Careers/P11_Personal_history_form.doc));
4. **Brief description of approach to work/technical proposal** of why the individual considers him/herself as the most suitable for the assignment, and a proposed methodology on how they will approach and complete the assignment; (max 1 page)
5. **Financial Proposal** that indicates the all-inclusive fixed total contract price and all other travel related costs (such as flight ticket, per diem, etc.), supported by a breakdown of costs, as per template attached to the [Letter of Confirmation of Interest template](https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/PSU_%20Individual%20Contract_Offerors%20Letter%20to%20UNDP%20Confirming%20Interest%20and%20Availability.docx&action=default). If an applicant is employed by an organization/company/institution, and he/she expects his/her employer to charge a management fee in the process of releasing him/her to UNDP under Reimbursable Loan Agreement (RLA), the applicant must indicate at this point, and ensure that all such costs are duly incorporated in the financial proposal submitted to UNDP.

All application materials should be submitted to the address (insert mailing address) in a sealed envelope indicating the following reference “Consultant for Terminal Evaluation of ***Strengthening National Protected Areas Systems (SNPAS) in Eswatini Project***” or by email at the following address ONLY: bidsubmission.sz@undp.org by *(time and date)*. Incomplete applications will be excluded from further consideration.

1. **Criteria for Selection of the Best Offer**

Only those applications which are responsive and compliant will be evaluated. Offers will be evaluated according to the Combined Scoring method – where the educational background and experience on similar assignments will be weighted at 70% and the price proposal will weigh as 30% of the total scoring. The applicant receiving the Highest Combined Score that has also accepted UNDP’s General Terms and Conditions will be awarded the contract.

1. **Annexes to the TE ToR**

*Suggested ToR annexes include:*

* ToR Annex A: Project Logical/Results Framework
* ToR Annex B: Project Information Package to be reviewed by TE team
* ToR Annex C: Content of the TE report
* ToR Annex D: Evaluation Criteria Matrix template
* ToR Annex E: UNEG Code of Conduct for Evaluators
* ToR Annex F: TE Rating Scales and TE Ratings Table
* ToR Annex G: TE Report Clearance Form
* ToR Annex H: TE Audit Trail template

**Annexes to Terminal Evaluation Terms of Reference**

*[Share ToR Annexes directly with short-listed applicants. Include link to ‘Guidance for Conducting Terminal Evaluations of UNDP-Supported GEF-Financed Projects’ and other existing literature or documents that will help candidates gain a better understanding of the project situation and the work required.*

* **ToR Annex A: Project Logical/Results Framework**
* **ToR Annex B: Project Information Package to be reviewed by TE team**
* **ToR Annex C: Content of the TE report**
* **ToR Annex D: Evaluation Criteria Matrix template**
* **ToR Annex E: UNEG Code of Conduct for Evaluators**
* **ToR Annex F: TE Rating Scales and TE Ratings Table**
* **ToR Annex G: TE Report Clearance Form**
* **ToR Annex H: TE Audit Trail template**

**ToR Annex A: Project Logical/Results Framework**

*(Insert the project’s results framework)*

**ToR Annex B: Project Information Package to be reviewed by TE team**

|  |  |
| --- | --- |
| # | Item (electronic versions preferred if available) |
| 1 | Project Identification Form (PIF) |
| 2 | UNDP Initiation Plan |
| 3 | Final UNDP-GEF Project Document with all annexes |
| 4 | CEO Endorsement Request |
| 5 | UNDP Social and Environmental Screening Procedure (SESP) and associated management plans (if any) |
| 6 | Inception Workshop Report |
| 7 | Mid-Term Review report and management response to MTR recommendations |
| 8 | All Project Implementation Reports (PIRs) |
| 9 | Progress reports (quarterly, semi-annual or annual, with associated workplans and financial reports) |
| 10 | Oversight mission reports |
| 11 | Minutes of Project Board Meetings and of other meetings (i.e. Project Appraisal Committee meetings) |
| 12 | GEF Tracking Tools (from CEO Endorsement, midterm and terminal stages) |
| 13 | GEF/LDCF/SCCF Core Indicators (from PIF, CEO Endorsement, midterm and terminal stages); for GEF-6 and GEF-7 projects only |
| 14 | Financial data, including actual expenditures by project outcome, including management costs, and including documentation of any significant budget revisions |
| 15 | Co-financing data with expected and actual contributions broken down by type of co-financing, source, and whether the contribution is considered as investment mobilized or recurring expenditures |
| 16 | Audit reports |
| 17 | Electronic copies of project outputs (booklets, manuals, technical reports, articles, etc.) |
| 18 | Sample of project communications materials |
| 19 | Summary list of formal meetings, workshops, etc. held, with date, location, topic, and number of participants |
| 20 | Any relevant socio-economic monitoring data, such as average incomes / employment levels of stakeholders in the target area, change in revenue related to project activities |
| 21 | List of contracts and procurement items over ~US$5,000 (i.e. organizations or companies contracted for project outputs, etc., except in cases of confidential information) |
| 22 | List of related projects/initiatives contributing to project objectives approved/started after GEF project approval (i.e. any leveraged or “catalytic” results) |
| 23 | Data on relevant project website activity – e.g. number of unique visitors per month, number of page views, etc. over relevant time period, if available |
| 24 | UNDP Country Programme Document (CPD) |
| 25 | List/map of project sites, highlighting suggested visits |
| 26 | List and contact details for project staff, key project stakeholders, including Project Board members, RTA, Project Team members, and other partners to be consulted |
| 27 | Project deliverables that provide documentary evidence of achievement towards project outcomes |
|  | *Add documents, as required* |

**ToR Annex C: Content of the TE report**

1. Title page
* Tile of UNDP-supported GEF-financed project
* UNDP PIMS ID and GEF ID
* TE timeframe and date of final TE report
* Region and countries included in the project
* GEF Focal Area/Strategic Program
* Executing Agency, Implementing partner and other project partners
* TE Team members
1. Acknowledgements
2. Table of Contents
3. Acronyms and Abbreviations
4. Executive Summary (3-4 pages)
* Project Information Table
* Project Description (brief)
* Evaluation Ratings Table
* Concise summary of findings, conclusions and lessons learned
* Recommendations summary table
1. Introduction (2-3 pages)
* Purpose and objective of the TE
* Scope
* Methodology
* Data Collection & Analysis
* Ethics
* Limitations to the evaluation
* Structure of the TE report
1. Project Description (3-5 pages)
* Project start and duration, including milestones
* Development context: environmental, socio-economic, institutional, and policy factors relevant to the project objective and scope
* Problems that the project sought to address: threats and barriers targeted
* Immediate and development objectives of the project
* Expected results
* Main stakeholders: summary list
* Theory of Change
1. Findings

(in addition to a descriptive assessment, all criteria marked with (\*) must be given a rating[[3]](#footnote-3))

4.1 Project Design/Formulation

* Analysis of Results Framework: project logic and strategy, indicators
* Assumptions and Risks
* Lessons from other relevant projects (e.g. same focal area) incorporated into project design
* Planned stakeholder participation
* Linkages between project and other interventions within the sector
	1. Project Implementation
* Adaptive management (changes to the project design and project outputs during implementation)
* Actual stakeholder participation and partnership arrangements
* Project Finance and Co-finance
* Monitoring & Evaluation: design at entry (\*), implementation (\*), and overall assessment of M&E (\*)
* UNDP implementation/oversight (\*) and Implementing Partner execution (\*), overall project implementation/execution (\*), coordination, and operational issues
* Risk Management incl. Social and Environmental Standards (Safeguards)
	1. Project Results
* Progress towards objective and expected outcomes (\*)
* Relevance (\*)
* Effectiveness (\*)
* Efficiency (\*)
* Overall Outcome (\*)
* Country ownership
* Gender
* Other Cross-cutting Issues
* Sustainability: financial (\*), socio-economic (\*), institutional framework and governance (\*), environmental (\*), and overall likelihood (\*)
* Country Ownership
* Gender equality and women’s empowerment
* Cross-cutting Issues
* GEF Additionality
* Catalytic Role / Replication Effect
* Progress to Impact
1. Main Findings, Conclusions, Recommendations & Lessons
* Main Findings
* Conclusions
* Recommendations
* Lessons Learned
1. Annexes
* TE ToR (excluding ToR annexes)
* TE Mission itinerary
* List of persons interviewed
* List of documents reviewed
* Summary of field visits
* Evaluation Question Matrix (evaluation criteria with key questions, indicators, sources of data, and methodology)
* Questionnaire used and summary of results
* Co-financing tables (if not include in body of report)
* TE Rating scales
* Signed Evaluation Consultant Agreement form
* Signed UNEG Code of Conduct form
* Signed TE Report Clearance form
* *Annexed in a separate file*: TE Audit Trail
* *Annexed in a separate file:* relevant terminal GEF/LDCF/SCCF Core Indicators or Tracking Tools, as applicable

**ToR Annex D: Evaluation Criteria Matrix template**

|  |  |  |  |
| --- | --- | --- | --- |
| **Evaluative Criteria Questions** | **Indicators** | **Sources** | **Methodology** |
| Relevance: How does the project relate to the main objectives of the GEF Focal area, and to the environment and development priorities a the local, regional and national level? |
| *(include evaluative questions)* | *(i.e. relationships established, level of coherence between project design and implementation approach, specific activities conducted, quality of risk mitigation strategies, etc.)* | *(i.e. project documentation, national policies or strategies, websites, project staff, project partners, data collected throughout the TE mission, etc.)* | *(i.e. document analysis, data analysis, interviews with project staff, interviews with stakeholders, etc.)* |
|  |  |  |  |
|  |  |  |  |
| Effectiveness: To what extent have the expected outcomes and objectives of the project been achieved? |
|  |  |  |  |
|  |  |  |  |
| Efficiency: Was the project implemented efficiently, in line with international and national norms and standards? |
|  |  |  |  |
|  |  |  |  |
| Sustainability: To what extent are there financial, institutional, socio-political, and/or environmental risks to sustaining long-term project results? |
|  |  |  |  |
|  |  |  |  |
| Gender equality and women’s empowerment: How did the project contribute to gender equality and women’s empowerment?  |
|  |  |  |  |
|  |  |  |  |
| Impact: Are there indications that the project has contributed to, or enabled progress toward reduced environmental stress and/or improved ecological status? |
|  |  |  |  |
| *(Expand the table to include questions for all criteria being assessed: Monitoring & Evaluation, UNDP oversight/implementation, Implementing Partner Execution, cross-cutting issues, etc.)* |

**ToR Annex E: UNEG Code of Conduct for Evaluators**

Independence entails the ability to evaluate without undue influence or pressure by any party (including the hiring unit) and providing evaluators with free access to information on the evaluation subject. Independence provides legitimacy to and ensures an objective perspective on evaluations. An independent evaluation reduces the potential for conflicts of interest which might arise with self-reported ratings by those involved in the management of the project being evaluated. Independence is one of ten general principles for evaluations (together with internationally agreed principles, goals and targets: utility, credibility, impartiality, ethics, transparency, human rights and gender equality, national evaluation capacities, and professionalism).

**Evaluators/Consultants:**

1. Must present information that is complete and fair in its assessment of strengths and weaknesses so that decisions or actions taken are well founded.
2. Must disclose the full set of evaluation findings along with information on their limitations and have this accessible to all affected by the evaluation with expressed legal rights to receive results.
3. Should protect the anonymity and confidentiality of individual informants. They should provide maximum notice, minimize demands on time, and respect people’s right not to engage. Evaluators must respect people’s right to provide information in confidence, and must ensure that sensitive information cannot be traced to its source. Evaluators are not expected to evaluate individuals, and must balance an evaluation of management functions with this general principle.
4. Sometimes uncover evidence of wrongdoing while conducting evaluations. Such cases must be reported discreetly to the appropriate investigative body. Evaluators should consult with other relevant oversight entities when there is any doubt about if and how issues should be reported.
5. Should be sensitive to beliefs, manners and customs and act with integrity and honesty in their relations with all stakeholders. In line with the UN Universal Declaration of Human Rights, evaluators must be sensitive to and address issues of discrimination and gender equality. They should avoid offending the dignity and self-respect of those persons with whom they come in contact in the course of the evaluation. Knowing that evaluation might negatively affect the interests of some stakeholders, evaluators should conduct the evaluation and communicate its purpose and results in a way that clearly respects the stakeholders’ dignity and self-worth.
6. Are responsible for their performance and their product(s). They are responsible for the clear, accurate and fair written and/or oral presentation of study imitations, findings and recommendations.
7. Should reflect sound accounting procedures and be prudent in using the resources of the evaluation.
8. Must ensure that independence of judgement is maintained, and that evaluation findings and recommendations are independently presented.
9. Must confirm that they have not been involved in designing, executing or advising on the project being evaluated and did not carry out the project’s Mid-Term Review.

**Evaluation Consultant Agreement Form**

Agreement to abide by the Code of Conduct for Evaluation in the UN System:

Name of Evaluator: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

Name of Consultancy Organization (where relevant): \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

I confirm that I have received and understood and will abide by the United Nations Code of Conduct for Evaluation.

Signed at \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (Place) on \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ (Date)

Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_

**ToR Annex F: TE Rating Scales & Evaluation Ratings Table**

|  |
| --- |
| **TE Rating Scales** |
| Ratings for Outcomes, Effectiveness, Efficiency, M&E, Implementation/Oversight, Execution, Relevance | Sustainability ratings:  |
| 6 = Highly Satisfactory (HS): exceeds expectations and/or no shortcomings 5 = Satisfactory (S): meets expectations and/or no or minor shortcomings4 = Moderately Satisfactory (MS): more or less meets expectations and/or some shortcomings3 = Moderately Unsatisfactory (MU): somewhat below expectations and/or significant shortcomings2 = Unsatisfactory (U): substantially below expectations and/or major shortcomings1 = Highly Unsatisfactory (HU): severe shortcomingsUnable to Assess (U/A): available information does not allow an assessment | 4 = Likely (L): negligible risks to sustainability3 = Moderately Likely (ML): moderate risks to sustainability2 = Moderately Unlikely (MU): significant risks to sustainability1 = Unlikely (U): severe risks to sustainabilityUnable to Assess (U/A): Unable to assess the expected incidence and magnitude of risks to sustainability |

|  |
| --- |
| **Evaluation Ratings Table** |
| Monitoring & Evaluation (M&E) | Rating[[4]](#footnote-4) |
| M&E design at entry |  |
| M&E Plan Implementation |  |
| Overall Quality of M&E |  |
| Implementation & Execution | Rating |
| Quality of UNDP Implementation/Oversight  |  |
| Quality of Implementing Partner Execution |  |
| Overall quality of Implementation/Execution |  |
| Assessment of Outcomes | Rating |
| Relevance |  |
| Effectiveness |  |
| Efficiency |  |
| Overall Project Outcome Rating |  |
| Sustainability | Rating |
| Financial resources |  |
| Socio-political/economic |  |
| Institutional framework and governance |  |
| Environmental |  |
| Overall Likelihood of Sustainability |  |

**ToR Annex G: TE Report Clearance Form**

|  |
| --- |
| **Terminal Evaluation Report for** *(Project Title & UNDP PIMS ID*) **Reviewed and Cleared By:****Commissioning Unit (M&E Focal Point)**Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**Regional Technical Advisor (Nature, Climate and Energy)**Name: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_Signature: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ Date: \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ |

**ToR Annex H: TE Audit Trail**

*The following is a template for the TE Team to show how the received comments on the draft TE report have (or have not) been incorporated into the final TE report. This Audit Trail should be listed as an annex in the final TE report but not attached to the report file.*

**To the comments received on** *(date)* **from the Terminal Evaluation of** *(project name) (UNDP Project PIMS #)*

The following comments were provided to the draft TE report; they are referenced by institution/organization (do not include the commentator’s name) and track change comment number (“#” column):

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Institution/****Organization** | **#** | **Para No./ comment location**  | **Comment/Feedback on the draft TE report** | **TE team****response and actions taken** |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

1. Eswatini Ministry of Health, Daily information update [↑](#footnote-ref-1)
2. Access at: <http://web.undp.org/evaluation/guideline/section-6.shtml> [↑](#footnote-ref-2)
3. See ToR Annex F for rating scales. [↑](#footnote-ref-3)
4. Outcomes, Effectiveness, Efficiency, M&E, I&E Execution, Relevance are rated on a 6-point rating scale: 6 = Highly Satisfactory (HS), 5 = Satisfactory (S), 4 = Moderately Satisfactory (MS), 3 = Moderately Unsatisfactory (MU), 2 = Unsatisfactory (U), 1 = Highly Unsatisfactory (HU). Sustainability is rated on a 4-point scale: 4 = Likely (L), 3 = Moderately Likely (ML), 2 = Moderately Unlikely (MU), 1 = Unlikely (U) [↑](#footnote-ref-4)