Evaluation Mission for Outcome 3 of the UNDP Strategic Results Framework:

“The involvement of authorities and communities, rural and urban, in the planning and management of development”

Outcome Evaluation applied to Decentralization

Final Report

(11/03/2003)

Evaluation Team:

| Christian BONIFAS | Economics Consultant, Head of Mission |
| --- | --- |
| Maro DIABATE | Decentralization Consultant |
| Brahima FONTE | Decentralization Consultant |
| Gilbert OLOKO | Monitoring and Evaluation Consultant |

| # Contents |  |  |
| --- | --- | --- |
|  | # Preface | # ii |
|  | # INTRODUCTION | # 1 |
| # I. | # CONTEXT | # 3 |
| # 1. | # The national context and its development (1998-2002) | # 3 |
| # 2. | # Specific intervention context of UNDP-Mali | # 6 |
| # II. | # DEVELOPMENTS OBSERVED (OUTCOME STATUS) | # 8 |
| # 1. | # Measuring outcome | # 8 |
| # 2. | # Progress towards Outcome | # 10 |
| # III. | # FACTORS INFLUENCING COMMUNITY AND LOCAL COLLECTIVE INVOLVEMENT | # 13 |
| # 1. | # Factors linked to the institutional framework | # 13 |
| # 2. | # Factors linked to the legal and regulatory framework regulating local governance | # 16 |
| # 3. | # Factors linked to human capacity of local actors | # 18 |
| # 4. | # Factors linked to the planning and budgeting process | # 21 |
| # 5. | # Factors linked to the mobilization of resources for regional development | # 23 |
| # 6. | # Factors linked to the process of regional management and other parameters | # 28 |
| # IV. | # UNDP CONTRIBUTION TO OUTCOME | # 30 |
| # 1. | # UNDP strategy and projects linked to Outcome 3 | # 30 |
| # 2. | # Scope of geographic intervention, financing and products | # 36 |
| # 3. | # Support for institutions and to the decentralization policy framework | # 39 |
| # 4. | # Capacity-building assistance to local actors | # 41 |
| # 5. | # Support for the planning and budgeting process | # 43 |
| # 6. | # Support for the local management of development | # 45 |
| # 7. | # Support for resource mobilization for local development | # 46 |
| # V. | # UNDP PartnerSHIP Strategy | # 48 |
| # 1. | # Key partners in achieving Outcome 3 | # 48 |
| # 2. | # Partnerships implemented by UNDP on Outcome 3/ SRF | # 49 |
| # 3. | # Relevance and Effectiveness of Established Partnerships | # 52 |
| # VI. | # CONCLUSIONS | # 53 |
| # 1. | # Changes implemented and current decentralization challenges | # 53 |
| # 2. | # UNDP Contribution | # 55 |
| # VII. | # Recommendations | # 59 |
| # 1. | # Recommendations to decentralization actors and partners | # 59 |
| # 2. | # Recommendations to UNDP | # 61 |
| # ANNEXES (separate document) |  |  |
| # 1. | # Terms of reference of the evaluation mission |  |
| # 2 | # Methodology proposed by the mission |  |
| # 3. | # Acknowledgements and Bibliography |  |
| # 4. | # Analysis of the contributions of projects linked to Outcome 3 |  |
| # 5. | # Evaluation of Outcome 3 and current information systems |  |
| # 6. | # Synthesis on development partner strategies and programmes in regard to decentralization |  |
| # 7. | # Supplementary data - intervention framework and decentralization policy results |  |

## PREFACE

This report stems from one of the first Outcome Evaluations introduced by UNDP.  The assessment centers on Outcome 3 as referred to in the UNDP Strategic Results Framework (“The involvement of authorities and communities, rural and urban, in development planning and management”).   The evaluation mission focused its analysis on the development of outcome observed in the framework of the decentralization process, using the programming cycle that has just ended (1998-2002) as a reference period. The mission had three main concerns: (i) assessing the importance of changes observed on this front, (ii) demonstrating the principal factors influencing the results of the process, (iii) evaluating the specific contribution of UNDP as well as the quality of its intervention strategy, including partnership initiatives.

Progress

Solid progress was made during this period, with the beginning of the implementation phase of decentralization in 1999/2000.  The process now seems irreversible. Having greatly contributed to the very establishment of communal areas, the local communities appointed councillors for 682 new rural communes.  Commune councils, as well as cercle councils and regional assemblies have been set up and are rapidly getting down to the elaboration of development plans.  More than 700 Social and Economic Development Plans (PDESC, Plans de Développement Économique et Social) have been prepared in this way, covering 94% of communes and cercles and, by and large complying with the participatory approach advocated by law.  Repeated consultation carried out in this framework, in addition to presentation of the problems and principle concerns of each of the localities, has helped to establish the beginnings of regional/territorial identity in most of the communities.  Furthermore, councillors have begun to address the administrative demands of their collectives.

The accelerated pace recorded largely results from the effort made to initiate the new communes.  With sustained support from development partners (in the region of CFAF40 billion, solely in terms of the initial FICT/ANICT contribution), a national assistance mechanism, both technical (network of Communal Council Centres) and financial (National Agency for the Investment of Territorial Collectives), has been in operation since 2000.

The national technical assistance mechanism has, in a relevant way, been able to capitalize on existing projects/operators in the various regions and propose a unifying framework based on a minimum of joint intervention principles.  With 460 training sessions to its credit, the CCC network has provided considerable support for the preparation of the plans (approximately ¾ of plans) and budgets, while providing some working knowledge to the commune councils on other priority thematic areas (commune administration, revenue mobilization, civil status registry,..)

Moreover, some 1,500 project briefs have already been developed with the support of the CCC.  Nearly a thousand have been disseminated to the ANICT, thus initiating the establishment of investments decided on by the local collectives themselves; these investments are financed by a sustainable national mechanism in which collectives are broadly represented.  Out of CFAF30 billion, the first 3-yearly ANICT funds, half has thus already been allocated to these projects.  New partners are joining the initial donors (European Union, France, UNDP/UNCDF, Government of Mali), which demonstrates increasing donor support of the national mechanism and presents the prospect of additional drawing rights for the collectives.

Strengthening of the Mali Municipality Association (l’Association des Municipalités du Mali, AMM) since 2000 has afforded commune councillors an active team at the national level to safeguard their interests.  The recent appointment of the High Council of Collectives has complemented the institutional framework planned by the Constitution.

#### Limitations

Local collectives have clearly not all had the same aptitude in embarking on decentralization for varying reasons such as:  level of training, dynamism, proaction of community leaders, collective traditions, existence or absence of projects in the area, social cohesion within new communes.

Several limitations have been observed firstly at the organizational level: human and financial capacity of territorial collectives which is still very limited; limited cooperation between territorial collectives and the deconcentrated administrative structures of sector-based policy, weakened consultation and policy advice frameworks at the regional and national level; and a coordination mechanism between the government and development partners which has been shelved.  Moreover, the “steering centre” for decentralization policy  (DNCT, Direction Nationale des Collectivités Territoriales / Department of National Territorial Collectives) has not been strengthened as expected.

Though coherent and relevant overall, the legal and regulatory decentralization framework is still suffering from a major weakness, concerning the very foundation of decentralization, the efficient transfer of competencies, resources and property.  It has taken 3 years to produce the first decrees that detail competencies to transfer in 3 priority sectors (June 2002).  It would seem that, in addition to clear resistance from certain actors, the long 2000-2002 electoral period, and a certain dulling of political will on the part of some, explains this slow pace to some extent.  Other inadequacies have emerged, notably in relation to intercommunality and the working conditions of commune personnel.

Development of collectives’ plans has largely been a success but significant weaknesses nevertheless remain to be corrected: the frequent non-consideration of the issue of financing and the consequent lack of realism of programmes; a view of development which often amounts to project investment; limited integration of women’s concerns and women-specific projects; arbitration procedures that are not always participatory once plans are approved; and finally, lack of coordination between commune planning and other levels of planning.

Capacity development, which is primarily targeted at elected councillors has, on account of their limited representation in commune councils, benefited women little; although certain programmes have sought to correct this point by specific training targeted at women and at other community leaders, to enable them to act as a vital counterweight to good local governance.  Deconcentrated technical services have equally been under-integrated.  Moreover, the issue of the technical assistance mechanism’s sustainability remains intact.

Finally, in regard to collectives’ financing, certain aspects of the financial assistance mechanism should be amended, principally those concerning criteria for allocating drawing rights and the size/uniformity of the collectives’ own contribution.  Moreover, the sectoral programmes - with the slowness typical of payment - continue to manage the resources earmarked for local investment financing, which, will henceforth develop from communes’ prerogatives.  The regressive tendency of fiscal revenue is indeed a considerable problem.

Reporting these limitations in no way mars the excellence of the results obtained but it highlights the need to correct imperfections observed at the level of tools and practices used, as one goes along, in order to improve their effectiveness and evolve towards more durable support systems for territorial collectives and communities.

### UNDP Contribution

UNDP’s contribution to the decentralization process has, on the whole, been positive, especially when specific constraints that have heavily impeded the last programming cycle are taken into account: severe decrease in resources, organizational reform and the “reprofiling” of the country office.

Though up to 1999/2000 UNDP played a driving role in decentralization policy, the organization has lost this preferential position in ‘soft’ assistance to government although important support needs persist. Today, the organization is almost unrepresented at the level of decentralization steering.   As for its upstream assistance in decentralization planning and land-use planning, which is chiefly delivered through developing Test-Outlines for the Planning and Development of Cercles (Schémas-test d’Aménagement et de Développement de Cercles, SADC) and through deliberation on the coherence of the various planning levels, they have not to date led to specific reform measures.

Generally, ‘regionalized’ projects have become more visible, more mobilizing - especially in terms of partnerships -, more effective in terms of their results and their role in development, and have a tangible impact on local collective and community involvement.  The UNDP-UNCDF teaming has played a vital role in running the first ‘implementation’ actions of Decentralization for these principal intervention zones which comprise all of the cercles of the of Mopti region and 3 cercles of the Tombouctou region.  In these regions, as with ACODEP in Kangaba, it has served to power the technical assistance mechanism (Communal Council Centres).  Overall, these projects have affected a considerable number of communes (more than 200).

The input of these projects has particularly been significant in social mobilization around villages/factions - commune relations (particularly the PARCT), assistance in the preparation of development plans and commune budgets, training of councillors, organization of and support for local field staff and mobilization of fiscal resources.  Various training material and methodological guides have been developed.  PACRT, which was involved before ANICT was established, has implemented finance mechanisms relevant to ‘profit-sharing’, linking allocations to communes to criterias of good governance, which include local revenue collection.  It has equally implemented an active communication strategy, an essential counterpart to training actions targeted to Decentralization “actors”. The establishment of commune self-evaluation, the PACRM training strategy, even development of anti-poverty action plans (plans d’action de lutte contre la pauvreté) undertaken by the ACODEP project are experiences that will need to be disseminated.  Indeed, efforts have been made with developing collaboration at the intervention zone level in mind, (other projects, NGOs, trainers, certain deconcentrated services), even if they do not develop into true partnerships.

The major limitations on the intervention of UNDP regard the strategic positioning of the Programme in relation to the Decentralization thematic and the pronounced gap, in this regard, between starting intentions and the actions effectively implemented.  The inadequacy of “soft” assistance, as much at the level of national steering of Decentralization as at the level of regional coordination, prevents UNDP from being active and visible on that which conforms to its mandate and represents one of its “comparative advantages”.

Other inadequacies are observed: absence of an overall strategy which is expressed by some dispersal of actions; almost non-existent synergies between projects; weak application of the capitalization processes anticipated at the start of the cycle; limited understanding of the gender perspective in projects linked to decentralization; and the continuing limited performance of the monitoring and evaluation system.

### Recommendations

The general recommendations of the mission, which are developed in the report centre on:

- Developing a medium-/long- term strategy for Decentralization policy;

- Taking priority actions to guarantee accelerated competency transfer;

- Refining and harmonising planning tools;

- Consolidating the technical assistance mechanism and promoting sustainable and autonomous solutions to respond to the assistance requirements of territorial collectives;

- Improving mobilization of financial resources and optimising their use;

- Developing consultation and monitoring-evaluation mechanisms.

In regard to UNDP, recommendations stem from 4 priorities:

- Repositioning UNDP on upstream “soft” assistance;

- Concentrating upstream and downstream activities on a limited number of thematic areas;

- Reducing the scope of geographic intervention for UNDP projects and, over time, financial input to these projects;

- Developing an exchange and monitoring-evaluation mechanism linking the UNDP country office, UNDP project field staff and beneficiaries in order to facilitate mutual capitalization of inputs.

The main line of recommendation regards adaptation of the 2003-2007 programming framework, taking into account the “coups partis” (projects in progress) and the following actions:

- Repositioning “soft” assistance to the government by implementing a new 5-year assistance programme;

- Reconciling the aims and inputs of projects built on the UNDP/UNCDF partnership (Tombouctou and Mopti);

- Rebuilding the logical planning framework of the UNV/PARCAD Programme;

- Repositioning the actions of the ACODEP project on Outcome 3 (short-term) and preparing a disengagement strategy for its intervention zones (medium-term);

- Focusing PRECAGED on support in the implementation of the CSLP (Cadre Stratégique de Lutte Contre La Pauvreté / Strategic Framework for Poverty Reduction) and Millennium Development Goals monitoring.

The second line of recommendation regards improvement of strategic management connected to Outcome 3, with:

- Development of monitoring and evaluation and reporting tools;

- Implementation of an SNU platform in order to capitalize on the findings of projects in the framework of achieving Outcome 3;

- Adoption of a range of measures to enable UNDP to better communicate on findings.

INTRODUCTION

Outcome Evaluation

“Outcome Evaluation” is a new evaluation method advocated by UNDP and is presently in its test phase.  Four countries (Mali, Macedonia, Cuba, and Pakistan) have consequently been short-listed to carry out the test evaluation; the aim was to refine the methodology before globalising its application.  Implementation of outcome evaluation is incorporated in the UNDP reform framework, which undertakes to promote results-based management (RBM).  This particularly necessitates the adjustment of tools and procedures for planning and management of monitoring and evaluation activities.

Outcome evaluation can mainly be distinguished from traditional evaluations (of programmes or projects) in the following ways:

- Focus on outcome – discernible changes in development conditions that UNDP intervention aims to prioritize1 - rather than on inputs and outputs.

- Evaluations are not limited to a particular project; they are aimed at apprehending the overall contribution of UNDP integrating all of the assistance brought to bear, contribution of the various projects linked to outcome, activities of field offices, activities undertaken at other levels (regional office and headquarters).

- UNDP contribution is assessed in terms of all of the contributions in relevant to achieving outcome – which leads to a detailed understanding of the action of other partners in the evaluation – and particular emphasis is put on the partnerships implemented.

Strategic Results Framework and choice of Outcome 3 of the SRF

This evaluation refers to the most recently concluded programming cycle (Country Programme 1998- 2002).  It is based on the logical planning framework introduced during the programme: the Strategic Results Framework (SRF).  This is made up of 5 goals: Governance, Poverty, Environment, Gender, and Support to the UN system.  Within the Governance goal, UNDP intervention targets 4 outcomes one of which is Outcome 3, the subject of the present evaluation and set out as follows: “local authorities and rural and urban communities are involved in the planning and management of development actions, including provision of public services.”  The decentralization process clearly represents the vital “carrier” of the outcome in question.

New UNDP procedures anticipate that each country office will implement the evaluation after specifying its priorities in this area (evaluation plan).  Although the present evaluation is not yet part of a formalised evaluation plan, the choice of proposed outcome is justified in several rights:

- Decentralization has held strategic importance in government policy since 1991.  This importance has just been re-emphasized in the Anti-Poverty Strategic Framework and in the Head of State’s address to the Prime Minister (22 October 2002).

- Decentralization represents a major challenge in terms of national development.  It, in effect, offers significant potential as much in terms of strengthening democracy (local governance) as in economic growth as in economic growth and anti-poverty measures (dynamics of local development and of improvement of community service provision).  The government and the key development partners have greatly invested in decentralization and local governance over 10 years.  The current period, which is marked by the advent of a new government after the 2002 elections, is a suitable time to make an inventory and reposition public intervention and development programmes within a new point of view.  This all the more so as the first lessons of the implementation phase of decentralization, which began in 1999-2000, can already be drawn on.

This evaluation finds there to be supporting evidence, specifically from the UNDP perspective:

- Governance has been specified as one of the main areas of UNDP intervention for the new programming cycle (2003-2007).  UNDP intends to considerably extend its decentralization assistance in this regard.  By an approach that is both global (overall assessment of the decentralization process) and targeted (assessment of UNDP own findings and potential intervention “gaps” for the future), the evaluation mission can help in clarifying the choices of the UNDP-Mali office in this area.

- The 1998-2002 Country Programme, which has just ended, includes no less than 5 projects which directly intervene in the area of decentralization and whose run will only end in 2004-2005.  It would seem useful to assess overall added value at this juncture and to propose suitable adjustment at the onset of a new programming cycle.

#### Evaluation Aims and Methodology

According to the terms of reference (annex 1), the evaluation should appraise: (i) degree of progress towards the achievement of Outcome; (ii) factors which impact on the achievement of Outcome; (iii) the strategic nature and relevance of outcome for UNDP; (iv) credibility of UNDP outputs (projects and other interventions) in regard to the desired outcome and their logical coherence; (v) sustainability of the outcome; (vi) relevance of established partnerships  (standard, nature, form and scope); and (viii) comparative advantages of UNDP, strengths and weaknesses and role of UNDP in the given area.

The detailed methodology proposed by the mission (annexe 2) has used the principle of adaptability required for outcome evaluation to good advantage.  In accordance with the Government and the UNDP country office, the mission has therefore chosen to focus the exercise on the decentralization process: outcome is apprehended by means of elected councillors’ involvement - community representatives - in development management.  Moreover, it has deliberately emphasized measurement and analysis of developments (steps 1 and 2 of the evaluation) at the national level.

Content of the Report

The mission’s report is comprised of a principal report which successively presents: (I) context, (II) developments noted (outcome status), (III) factors affecting outcome, (IV) UNDP contribution to outcome, (V) partnership strategies implemented, (VI) conclusions, (VII) recommendations.  The report is finished off by a file of annexes which expand on various points:  achievements of the national assistance mechanism for collectives, analysis of the inputs of UNDP projects linked to Outcome 3; analysis of M&E systems and indicators; synthesis of strategies and development partner programmes in terms of decentralization.

Due to a concern for readability, this report does not elaborate on methodological issues.  A specific comment on conclusions to draw from this first outcome evaluation has been drafted by the mission.

A provisional report (dated 29/01/03) has been circulated to all institutions encountered during the mission. It has served as a basis in the running of the restitution workshop held on 05/02/03, and attended by some 60 participants.

- CONTEXT

  - The National context and its development (1998-2002)

  - Social and Economic Parameters

Mali is among the poorest nations in the world.  The country’s economy is organized around a production structure that has developed little; remaining dominated by primary and tertiary sectors (40% and 42% respectively of GDP).  The economy is weakened by its dependence vis-à-vis climatic hazards and three principal external influences (market price of cotton, fluctuations in external aid, sub-regional situation).  Nearly four fifths (4/5) of the population still resides in a rural area.  The economy’s competitiveness is hindered by the low level of qualifications of the working population, the landlocked position of the country, the poor quality of road infrastructure and the high cost of production factors (such as energy, telecommunications, …).

From the start of the Country Programme, Mali has been registering the benefits of economic recovery initiated in the post-devaluation period with somewhat sustained growth (in the 1994-2000 period, average annual increase in GDP has been 4.8% in real terms and average growth in GDP 2.6% per head), even if certain indicators, such as deceleration in private investment, are already cause for concern.  Development recorded in 2001/2002 once again demonstrates the vulnerable nature of the economy with a deceleration in economic activity primarily linked to the fall in cotton production.  The Ivorian crisis has presented another adverse factor, the effects of which are felt at various levels  (trade, import prices, social demand, security).

Nearly two out of three people are affected by poverty, with an even higher percentage in rural areas.  Among the social indicators, it is fitting to underscore those major constraints for a full involvement of local communities in development management:

- Illiteracy: only 29% of adults were literate in 1998 (12% of women), the gross school enrolment ratio was less than 70% in 1999-2000 (46% for girls);

- A considerable number of Malians have limited access to various basic services and live in conditions of extreme poverty: half of the population (49% in 1999 do not have access to safe drinking water; nine out of ten households do not have an adequate sanitation system at their disposal, a fair number of core health centres (CSCOM) are not functional, principally as a result of staffing problems

- The more disadvantageous situation of women: though they often play a more dominant role in economic activities in rural communities, women are penalized at various levels: access to learning, access to capital, access to positions of responsibility et participation in decision-making

  - Political and Institutional Parameters

On the political front, since the beginning of the 90s Mali has experienced profound changes, primarily communicated by (i) establishment and progressive consolidation of institutions and democratic practices; (ii) the burgeoning non-governmental organizations (1650 NGOs identified at year-end 2002), evidence of a very dynamic civil society, with a pronounced presence in rural areas.

These very favourable contextual ingredients are, at the point of the commencement of 1998-2002 UNDP Country Programme, reinforced by other elements more closely linked to the decentralization process:

- After several previous failures to implement regional and local participatory mechanisms by authorities 2, perspectives have radically shifted following the National Conference of July-August 1991 and the incorporation of the principle of open management of territorial collectives in the Constitution of 12 January 1992.  Since this time, sustained political will has not ceased to support the decentralization process in its aforementioned preparation phase.  This will has, since 1993, been conveyed through the Decentralization Mission, which was at that time the MDRI3 (Mission de La Décentralisation et des Réformes Institutionelles / Mission For Decentralization And Institutional Reform), which had minor mission management power, and recognized dynamism and skills, and which benefited from strong institutional positioning at 1997-1998 (through its attachment to the State).

- At the onset of the Programme, the decentralization framework was largely defined by a collection of legislative and regulatory texts adopted during the 1993-1997 period.  These primarily concern the Code of Collectives, the division of communes, the status of officers, commune taxation and the transfer of competencies.

- From 1995 onwards the preparation phase has equally been marked by the implementation of a training strategy, in part targeted to management decision-makers and officers of decentralized services, with the aim of preparing the officers for expected change.  At the same time, an extensive information and communication campaign was brought about, mainly by drawing on the Study and Mobilization Groups (Groupes d’études et de mobilization) at the regional (GREM) and local (GLEM) level.

- Territorial reorganization resulting in the creation of 684 new rural communes has been pursued in a very participatory manner, and was based on several inter-village consultations carried out over the entire area (1995-1996).

- Partners were widely called up to support the government in this preparation phase, even if certain fund donors seemed sceptical in relation to the choices made and distanced themselves from a decentralization programme which would not, in their opinion, sufficiently concentrate on the private sector and civil society.

The start of the UNDP Country Programme will precede the introduction of new communes and the launch of the implementation phase of decentralization policy by barely a year. Over the course of the 1998-2002 period, the political and institutional context will in fact experience two important developments:

- Firstly, the commencement of the implementation phase of decentralization will slightly precede the start of the electoral period, which begins in the first months of the year 2000 (voter registration) and will only end in the second quarter of 2002.  This prolonged focus on the elections will clearly contribute to impeding the current dynamic by pushing decentralization. – as with other reforms elsewhere -  into the background of concerns of the various political leaders.  It will in the same way further a certain “wait and see” attitude on the part of fund donors.

- Secondly, the institutional framework for steering decentralization will alter: the MDRI is going to disappear and a Ministry of Territorial Administration and Local Collectives (Ministère de l’Administration Territoriale et des Collectivités Locales, MATCL) will be created to oversee the effective implementation of decentralization.  In the event of a lack of improvement of means of the new structures, and if there is less sensitive political engagement, this change of steering will equally impact on the rhythm of reform.

This period will also mark a change in terms of public policy with:

- Adoption of the Prospective Study - Mali 2025 (L’Étude Prospective Mali 2025) which delineates a common outlook on the long-term development of the country;

- Adoption and commencement of medium-term programmes in several key sectors4;

- Development and approval of the Strategic Framework for Poverty Reduction (CSLP) in May 2002 that will serve as the central frame of reference for overall national development policy and the assistance programmes of the key development partners.

1.3 Key Partners for Outcome 3

Since the departure of the MDRI, the Ministry of Territorial Administration and Local Collectives (MATCL) has become the key institution in the implementation of the decentralization process.  The Ministry for the Economy and Finance is also largely involved: in developing nomenclatures for commune budgets, and in monitoring and development of the local resource mobilization (Local Finance Committee / Comité des Finances Locales).  Other major partners – the majority of whom will only emerge during the period under review - are:

- The High Council of Collectives (Haut Conseil des Collectivités, HCC), appointed in 2002;

- Authorities elected to different decentralization levels (Regions, District of Bamako, Cercles, Communes), established in 2000;

- State representatives at the different levels (Hauts Commissaires of the Regions, Préfets and Sous-préfets) as well as the deconcentrated services of ministerial departments, to whom the task of “soft” assistance and supervision for the collectives will revert from now on;

- The National Investment Agency For Territorial Collectivities (l’Agence Nationale d’Investissement des Collectivités Terrritoriales, ANICT)

- The Mali Municipality Association (l’Association de Municipalités de Mali) and the Association for Cercles and Regions (l’Association des Collectivités Territoriales);

- Development partners, many of whom support the decentralization process;

- The various actors of civil society, in particular associations established with a view to managing core public services (APE, ASACO,….)

Local communities are the ultimate beneficiaries of intervention undertaken within the framework of Outcome 3, through various channels: strengthening of the democratic structure/system/framework, greater participation by local communities in the decision-making and management process, better ensuing understanding of their interests and aspirations, improved quality of and access to core services, increased opportunity for local economic development and the establishment of interdependent systems.

  - Specific Intervention Context of UNDP-Mali

2.1 Prior UNDP Experience

UNDP has lent its support to the decentralization process, practically from its commencement in 1993. Its assistance has particularly materialised through the Capacity- Building Project For The Promotion of Decentralized Development Management (le project de Renforcement des capacités pour la promotion d’une gestion décentralisée du Développement) (MLI/94/003).  Granted a budget nearing US$3 million, this plan has allowed many thematic studies to be put into practice, has supported establishment and operation of the GLEM/GREM (Groupes d’études et de mobilization / Study and Mobilization Groups), contributed to the capacity-building of local actors and taken part in the establishment of dialoguing structures at the regional level.  The project has, equally, supported the establishment of the “panel”, which integrates government and development partners, in order to track the progress of decentralization programmes.  It has finally prepared the Draft Outline for Planning and Development (ESAT, l’Esquisse de Schéma d’Aménagement et de Developpement,) and the AP-SRAD (Preliminary Draft of Regional Outlines for Planning and Development / les Avant Projets de Schémas Régionaux d’Aménagement et de Développement) for Mali’s eight regions and Bamako district.  This operation has played an important role in furthering a very close collaboration between UNDP and the government, particularly the MDRI, UNDP even intervened in financing the Head of Mission.

Similarly, UNDP has sought to develop decentralization support practices within various projects/programmes, notably the Support Project for the Promotion of Women (Projet d’Appui à la Promotion des Femmes), the Support Project for Good Governance, Conflict Prevention and the Promotion of Peace (Projet d’Appui à la Bonne Gouvernance, à la Prévention des Conflits et à la Culture de Paix), as well as three operations which directly preceded three of the five projects this evaluation is concerned with: Phase I of the ACODEP project (1993-1997), The Project for Village Land Management (le projet de Gestion des terroirs villageois) in Seno Gondo and the Sourou valley (Mopti Region) and the Project For Hydro-Agricultural Planning (le projet d’Aménagements hydro-agricoles) in the Tombouctou and Gao regions.

2.2. The Country Cooperation Framework 1998-2002 and developments arising during this cycle

Following the five-year programming cycle (5th Country Programme 1992-1997) launched after the National Conference, the Country Cooperation Framework (CCF) for the 1998-2002 period was established following a participatory process that was conveyed by many wide-ranging dialogues.  The Programme is based on two priority main lines: (i) Poverty Reduction, and (ii) Good Governance.  Decentralization represents, next to political and economic governance, one of the 3 measures of the second main line.

Since development of the CCF preceded the implementation of the Strategic Results Framework by 3 years, it is no surprise to note differences in the organization of projects according to the two programming approaches.  CCF organization thus does not facilitate an straightforward understanding of actions likely to contribute to achievement of Outcome 3: projects including direct support to decentralization (such as ACODEP) are, for example classed under the Poverty Reduction goal, and not under Governance.  The same observation goes for the division of responsibility within the UNDP office:  held up by the initial structure of the cooperation programme (CCF), the country offices’ organization will have some difficulty in applying all its interventions that are linked to decentralization and local governance in a global and coherent manner.

The UNDP-Mali country office anticipated UNDP strategy reform by, from 1997 onwards, emphasizing coordination between (i) upstream - improvement of policies (development of strategies and action plans, intersectoral coordination mechanisms, mobilization and administration of resources, capacity-building at national and local levels, advocacy, and awareness-raising campaigns), and (ii) downstream – short-term validation of these policies by actions to improve living conditions at the local level, those of vulnerable communities, in particular.

During the evaluation period in question, three major developments altered the general programming framework:

- Firstly, a severe reduction in resources was registered at the end of the 90s, which often lead to programme/project removal, and a change in financial commitments as targeted objectives of the programmes. This stricture will significantly penalize some anticipated assistance in the area of decentralization.

- Within the framework of the UNDP reform, the organization’s mandate has been redefined, halting new courses of action (thematic priorities, nature of support, modes of cooperation with governments and development partners, etc).

- Finally, reform has been complemented by a major revision of all programming methods and instruments, monitoring and evaluation as much at the global programming level (SRF, ROAR,..) as at programme/project level (new project information document format incorporating the logical planning framework, reporting, etc).

These developments, which have resulted in subsequent modifications of the framework that must serve as reference for the evaluation, evidently make analysis difficult.  None of the baseline references are suitable here: the initial frameworks are obsolete as much from the perspective of planned resources as from that of its references to UNDP strategic mandates; as to the new frameworks, they appear to be recreations, which are certainly more in line with requirements – strategies, logical planning frameworks, etc – of the headquarters, but are too recent and often unstable (cf. project indicator frameworks or the SRF for example).

The Strategic Results Framework (SRF), introduced in 2001, has reorganized the Cooperation Framework around the five goals specified in the following boxed text.  Revision of the SRF in 2002 resulted in a decrease in the number of targeted outcomes, from eleven to eight.

| ### Box 2: Strategic Results Framework (SRF) and targeted outcomes |  |  |
| --- | --- | --- |
| The Strategic Results Framework is structured around five practices (goals): (i) Governance, (ii) Poverty, (iii) Environment, (iv) Gender, and (v) Support/ UN System. Outcome 3 arises from the first area. In its Strategic Results Framework (SRF), UNDP-Mali settled on 11 outcomes or medium-term strategic results for the 2002-2003 period. |  |  |
|  | Governance |  |
| 1. | Increased use in developing and implementing policies by SHD concept decision-makers |  |
| 2. | Enhanced capacity of Parliament in carrying out its legislative and supervisory functions |  |
| 3. | Involvement of local authorities and rural and urban communities in development planning and management, including the provision of public services |  |
| 4. | Effective take-over by government of mobilization and management of flows of external assistance |  |
|  | Poverty |  |
| 5. | Reduction of fiscal poverty and human poverty presented as a major element of macro-economic policy |  |
| 6. | Improved access of the poor to financial resources. |  |
| 7. | Revision of the national education policy framework in order to achieve universal access to basic services Environment |  |
| 8. | Enhanced capacity of national/sectoral authorities in planning and implementing integrated approaches in the field of environmental management and energy development |  |
| 9. | Improved regional capacity in coordinating and standardizing national policies and programmes around shared natural resource management and sustainable energy development |  |
|  | Gender |  |
| 10. | Enhanced decision-making based on gender evaluations and integration of gender perspective in statistics and databases Support to the UN System |  |
| 11. | Effective use of UNDAF to facilitate national response to overall development goals |  |

- DEVELOPMENTS OBSERVED (OUTCOME STATUS)

The first stage of outcome evaluation entails measuring, in a synthetic manner, change observed in terms of the implication of local and community authorities in development planning and management.  The current information system, presents great limitations as much at UNDP level as at government level. (see annex 5). Consequently discussion here will be limited to the review of certain key indicators of change, before tackling the specific analysis of changes and their determinants (Chapter III) then UNDP’s own contribution to outcome (Chapter IV).

1. Measuring Outcome

  - Problems connected to defining Outcome

In its current form, outcome is very general and can lend itself to several interpretations according to the meaning ascribed to the terms “involvement”, “local authorities”, “development management”, and “public services”.  If one defines outcome very loosely, measurement of change concerning Outcome 3 can encompass practically all development actions and the policies/programmes that they support.

Moreover, the outcome concerned refers to changes that can be observed in the medium/long term.  The period selected in the terms of reference (1998-2002) can thus seem unsuited to a thorough understanding of outcome.  The mission has agreed to some flexibility in this regard, generally reframing analysis of progress and particularly its determinants, on a larger plane, often using the year 1993 (commencement of the design phase of the decentralization policy) as a benchmark.

  - Problems connected to results measurement

First of all, the Strategic Results Framework, which in principal should provide an important starting point for assessment of results achievement, can only with difficulty fulfil this mission in its current form:

- Precise indicators which enable characterisation of the starting situation (baseline) are generally not used

- The norms which, in the SRF, define the expected situation over various years (targets for 2001, 2002,…) were defined while the Programme was being implemented, and were adjusted on several occasions, while understanding of the concepts and information was being improved. On the other hand, the indicators selected during the monitoring of Outcome 3 do not enable assessment of all of the dimensions of outcome.

- Indicators set out in the SRF do not have national reference status. They only concern UNDP and so do not, in their current state, lend themselves to a progress measurement of services as a whole.5

Secondly, the UNDP’s new internal information system can be considered to still be in its installation phase.  If the implementation of logical planning frameworks and the consecutive adaptation of the reporting system enable improved monitoring of project results in regard to different outcomes, important progress is still required to bring about consolidated and coherent information on the UNDP intervention results both within and outside the bounds of programmes.

Other constraints are noticeable on a more global level:

- The CSLP (Cadre Stratégique de Lutte Contre La Pauvreté/ Strategic Framework for Poverty Reduction), which was validated less than a year ago, is too recent to be used as a baseline in defining medium-term targets.  The current grid of M&E and CSLP indicators is also only of limited use since it doesn’t offer any specific indicator for governance and decentralization.

- Despite recent efforts, the national information system still remains insufficient as a means of apprehending performance (process indicators) and impact (results indicators) obtained in terms of decentralization in any precise way, and more generally as regards “quality” of involvement of communities/local collectives in development.  The establishment of OISE (DNCT/CCN/CCC) data and the consolidation of the monitoring system offers certain prospects in the near future, from this perspective. However, an important task remains to be carried out in order to create an integrated information system that operates on baseline cases and precise targets and facilitates the production of comprehensive profiles on elements as essential as resources received and/or administered by local collectives.

  - Mission approach

Measurement of outcome can be tackled according to several possible logics of “outcome deconstruction” in relation to: (i) type of actor (grassroots communities, different levels of collective), (iii) the sector concerned (education, health, facilities management,… ), and (iv) potential for participation (workability of structures  involving communities and local authorities, resources in play, quality of participation, effect of participation on public choices.

The mission proposes to assess outcome:

- By structuring the results obtained around the following nomenclature:

  - Institutional and legal framework for local governance

  - Human capacity of local actors;

  - Planning and budgeting process;

  - Local management of development;

  - Resource mobilization for local development.

- By offering a global approach to outcome measurement and analysis: here outcome is considered from the “national” perspective, and not in relation to the limited prism of the UNDP Strategic Results Framework.  Specifically, UNDP intervention is deliberately only taken into account in the third stage of Outcome Evaluation.

The magnitude of the field of investigation has made a balanced treatment of the actors (local collectives, community organizations, State services, private-sector service providers) concerned difficult, just as it would be over-ambitious to want to cover all the areas of local Governance, particularly its sectoral dimensions.  The mission has concentrated on communes – particularly those that are rural – as a new and essential actor in local governance by concerning itself with the participatory processes that have characterised the creation of new territorial collectives.  In this sense “involvement of local communities” is filtered through:

- Direct (local management) or indirect (management at the level of cercles/regions, and at the national level, via its representatives) involvement of its elected representatives (communes) in development planning and management;

- Involvement of local communities and civil society organizations in the processes which have been implemented since 2000 as part of decentralization policy, that is, primarily elaboration of development plans and establishment of the first communal investments;

- Involvement “potential” created by “external rules” (legal and regulatory framework), organizations and capacity-building actions.

- Progress towards outcome

Table 1, below, presents the most typical results for the period under review

# Table 1: Progress Towards Outcome

Legal and institutional framework for local governance

- Establishment of all elected bodies of territorial collectives made provision for by law - Policy Advice and consultation structures set up - High Council of Collectives established, from April 2002 - Restructuring of the Mali Municipality Association in 2000 and Association for Cercles and Regions established at year-end 2002 - Institutional technical assistance mechanism for local collectives set up (2000) - National Agency for the Investment of Territorial Collectives appointed (2000) - Participatory mechanism proposed for development and implementation of the CSLP (2001/2002)

Human Capacities of local actors

- Assistance plans for communes developed and implemented by the Communal Council Centre (CCC) network - More than 458 training programmes carried out in aid of new territorial collectives by the CCN/CCC - Numerous training programmes (difficult to quantify) carried out within the framework of programmes (sectoral and non-sectoral) to the benefit of various actors of local governance

###### Planning and Budgeting Process

- More than 700 3-year development plans developed at the commune, cercle and regional level - Anti-Poverty Action Plans developed in certain communes - Outlines for Planning and Development tested out in one cercle of each of the regions - Participatory process implemented for development of the principal sectoral programmes: PRODESS/PDDS (health), PRODEC (education), PNAE (environment), updating of SDDR (rural development) - Regional consultations on the CSLP

###### Process of local development management

- General competencies (civil status, budgeting, …) taken over by the new territorial collectives - Regulatory bases defined in order to organize involvement of the collectives in management of the 3 priority areas of education, health, and hydro-power (implementation decrees for competency transfer, 2002) - Project management capacities of territorial collectives implemented within the framework of implementation of first-stage FICT projects - Role of grassroots community organizations (village associations, women’s organizations, producer groups) consolidated within the framework of sectoral programmes or governance/civil society support programmes

###### Resource mobilization for local development

- Endowment for the Operation of Collectives (Dotation de Fonctionnement des Collectivités) established (1999) - ANICT financing resources in use (14.6 billion outstanding for projects already submitted) - Mobilization of the contribution of local communities to the new investments of collectives according to the selected norm of 20% (ANICT projects) - Involvement of territorial collectives by means of the local tax system (including the TDRL) - Upgrading of the participatory mechanisms for local communities in financing core services, particularly within the framework of APE (education), ASACO (health) and water management committees (hydro-power)

Certain indicators mentioned here deserve deeper consideration, in as much as training of local actors is concerned, for example, or even diverse mechanisms for local communities involvement (planning, management, financing) that were put in place in the various areas of activity.  The table is, however, sufficient to accurately show developments registered over the course of the period being examined (1998-2002) in terms of the involvement of local communities and local collectives in development planning and management.

In view of the time period and its development condition, Mali has performed impressively:

- All the elected bodies for decentralized collectives (703 Commune Councils, 49 Cercle Councils and 9 Regional Assemblies) were set up and are currently operational.  Considering the powers granted to the collectives, particularly the communes, and the provisions of the Code of Collectives, which governs the various decision-making processes, this opens up great prospects for addressing local affairs by local communities and their elected councillors.

- The institutional framework has been improved at the level of representative structures of territorial collectives in other respects.  To begin with, by the establishment of the High Council for Collectives.  Restructuring of the Mali Municipality Association (AMM, l’Association des Municipalités de Mali) and the establishment of the Association for Cercles and Regions (l’Association des Cercles and Régions) will strengthen the capacity now given to the collectives to voice their views on national development issues and public policy.

- Such involvement of territorial collectives in the public administration mechanism is also expressed by the establishment of several policy advice and consultation structures: Local Advisory Committees (Comités Locaux d’Orientation), Regional Advisory Comittees (Comités Régionaux d’Orientation), a National Advisory Committee (Comité National d’Orientation), and a Decentralization “panel”.

- Finally, the two national assistance mechanisms – technical and financial assistance – which were set up in 2000, were at the centre of this first step in the “implementation phase” of decentralization. The standing accorded to collectives in ANICT (National Agency for the Investment of Territorial Collectives / l’Agence Nationale d’Investissement des Collectivités Territoriales) management6, demonstrates that they are not simply considered here to be beneficiaries of an assistance mechanism, but rather to be co-managers who are entirely separate from local development financing.

- Three-year development plans (Social and Economic Development Plans / Plans de Développement Économique et Social, PDESC) were elaborated by almost all the collectives (94% of communes and cercles).  Their preparation has enabled elected councillors, local communities and other local actors to reflect on the local development priorities, to rank them in order of importance, and to use them to agree a plan of action in order to respond to the priority needs of the local communities.  Recourse to inter-village dialogue with the goal of establishing arbitration has contributed to establishing a sense of community identity

- Through their adoption, these plans were put into practice in 2001/2002, this gave rise to the new investment plans, now administered at the level of collectives. At year-end 2002, 1,430 project briefs were already developed with the assistance of the Communal Council Centres (Centres de Conseils Communaux) network, nearly a thousand of these were sent to the National Agency for the Investment of Territorial Collectives (ANICT)

- Access to specific resources (Endowment for the Operation of Collectives/ Dotation de Fonctionnement des Collectivités and particularly the ANICT-administered National Investment Fund for Territorial Collectives/ Fonds d’Investissement des Collectivités Territoriales, established in 2000) is, for the collectives, a vital tool to consolidate their involvement in development management.  The first 3-year financial resource (2001-2003) available to the ANICT, is in the region of CFAF3 billion, about half of which is already allocated to projects submitted by the collectives.  Outside the national financial assistance mechanism, considerable external financing (international cooperative institutions, NGOs, and decentralized cooperation) has assisted local collectives and grassroots communities.   Another considerable factor in development involvement is the broadening of the principle of community/local collective involvement in investment financing as well as in core public services financing.

- Involvement of community leaders (heads of villages, district and factions), and local communities in local decision-making can draw on the specific conditions of the Code of Territorial Collectives, which are, in the main, applied.

- Adoption of the first implementation decrees relating to competency transfers in 3 priority sectors (education, health, hydro-power) is an important step in actual implementation of missions passed on to territorial collectives.

- Considerable effort has been engaged around local actor capacity-building during the period concerned (development of plans, budgets of collectives, project management), with a particular emphasis on the necessary mastery of new tools and procedures of decentralized management.  For the national technical assistance mechanism (CCC network) alone, 458 training programmes, which were essentially carried out in 2001-2002, were identified.  The presence of decentralized assistance structures makes it easier to identify training needs and build capacity for local response.

Generally, the rhythm of change since the beginning of the decentralization effort seems remarkable, and the decentralization process embarked upon seems irreversible.

However, it should be noted that, if a significant dynamic exists at the level of the technical and financial assistance mechanism to territorial collectives (CCC and ANICT network, other critical areas of reform – especially consolidating competency and resource transfers to new collectives – are not moving ahead at the same pace.  Their implementation seems to throw up the dual – inevitable - problems of inadequate resources and resistance to reform, particularly from certain local State representatives and ministerial departments, who are not ready to give up a portion of their allocations.  The degree of political commitment by authorities in favour of reform in the last years of the period under review should thus be questioned.  Opinions differ slightly on this point.

These limitations, which should clearly be imparted alongside consideration of how new the process is, are developed in the following chapter.  Among other viewpoints on  “Outcome 3”, they are expressed by:

- A not yet effective transfer of the majority of specific competencies passed on to local collectives;

- Limited availability of resources for the realisation of priority investments for projects under the control of local collectives;

- Capacities which are limited and differ greatly within elected councils;

- Insufficient grasp of the respective roles of local communities, territorial collectives and the State, which is expressed by the continuation of a certain “wait and see” attitude in regard to external aid (by the State and/or donors) to the detriment of strategy and practices which put the mobilization and solidarity of local communities first;

- Very limited involvement of women in the various local decision-making and consultation authorities, which contrasts with their effective participation in economic activity.

- FACTORS INFLUENCING COMMUNITY AND LOCAL COLLECTIVE INVOLVEMENT

The second step of the Outcome Evaluation consists of identifying and analyzing factors which, in a positive or negative way, contributed to the changes observed.  It will here be limited to significant factors, by identifying to what degree each of them are carriers of opportunity and/or constraints.  Because of a concern for brevity, details relating to the legal framework of decentralization and to the technical and financial assistance mechanisms for territorial collectives, have been consigned to the annex.

  - Factors linked to the institutional framework

  - Strengths

The existence of a coherent and relevant institutional framework is a vital feature in implementing decentralization and promoting local collectives involvement in public governance.  In the space of 4 years, the entire mechanism has become operational.

- Following free and transparent commune elections, all the elected bodies of decentralized collectives were set up: Commune Councils for 703 communes, Cercle Councils (49 cercles) and Regional Assemblies (8 regions and Bamako district). At each of these levels, State representatives (supervisory authority/ tutelle) chiefly provide a “soft” assistance and support mission to the collectives: Haut Commissaires (regions), Preféts (cercles) and Sous-Preféts (communes).

- Implementation of the High Council of Collectives (HCC, Haut Conseil des Collectivités) has been a recent finishing touch the institutional fabric (implementation decree of January 2002 and appointment in April 2002 by the President of the Republic).  Composed of 75 national councillors elected by indirect suffrage from the council members from communes, cercles of the regions, Bamako district and Malians Abroad (les Maliens de l’Exterieur), the HCC advises on all aspects of decentralization policy, local as well as regional.  It can also, of its own volition, (self-seisin) analyse and make proposals to government on any issue relating to the environment and the quality of life of its citizens, obligating the government to translate this into a draft bill submitted to the National Assembly.  Finally, the government must seek the view of the High Council on any action relating to the condition of territorial collectives within the framework of decentralization.  The HCC held its first session in December 2002.  An action plan was developed on the basis of the strategic planning workshop, which took place in January 2003 with the support of Swiss cooperation.

- The Decentralization and Institutional Reform Mission played the leading role in steering decentralization policy until the end of the “preparation phase” (1993-1999).  Since February 2000, implementation of decentralization falls to the Ministry for Territorial Administration and Local Collectives (MATCL, Ministère de l’Administration Territoriale et des Collectivités Locales).  Within this ministry, the National Department for Territorial Collectives (DNCT) took over from the MDRI (Mission de La Décentralisation et des Réformes Institutionelles / Mission For Decentralization And Institutional Reform), inheriting some of its prerogatives and its team.

- Since 2000, the government has had a specific mechanism in place to assist the new territorial collectives (National Assistance Programme for Territorial Collectives / Programme National d’Appui aux Collectivités Territoriales) which is made up of 2 sections:

The first section concerns the technical assistance mechanism, which, in essence, was provisionally implemented for the 2001/2003 period.  It is steered by the National Coordination Unit (Cellule de Coordination Nationale, CCN), attached to the DNCT (Direction Nationale des Collectivités Territoriales/Department of National Territorial Collectives) and based on a network of Communal Council Centres (CCC), by way of 1 centre per cercle, with the exception of the Kidal region, which has only one CCC available.  The CCC have a mission of “soft” assistance to the communes, and a mission of liaison in the elaboration of commune development plans, budgetary plans, etc. Currently they are all operational.  Branches (responsible for monitoring and evaluation) are being set up in the 8 regions of the country.

The second section - the financial assistance mechanism – is based on the National Agency for the Investment of Territorial Collectives (ANICT), established in 2000 with the statute of 7/07/00 and the decree of 10/08/00.  The agency has a dual objective: first of all, provision of a long-lasting response  (from which the sustainable nature of the proposed structure arises) to the financial support needs of territorial collectives; then, to carry out an equitable redistribution of resources between these two (identical criteria for all).

- The Mali Municipality Association (AMM) was restructured in 2000.  It brings together all the commune council members and today actively intervenes in defending the interests of communes, and leading debate on decentralization.  It has a publication (Voice of the Communes” / La Voix des communes) and organizes a yearly Journée Nationale des Communes (National Commune Day)7.   Moreover, an Association for Cercles and Regions (Association des Cercles et Régions) has just been inaugurated and has signed a collaboration protocol with AMM.  The goal is construction of a federative system of associations to represent the various category of council member.

- One must emphasize that important resources were mobilized to strengthen the process of the various institutions coming in operation.

- Territorial collectives have benefited from a great deal of technical assistance financed by the key development partners8, a growing part of which was channelled through the national technical assistance mechanism (CCC network).  Inputs of equipment and operating methods have also been granted within the framework of projects.  Finally, from 2002, they began to benefit from their drawing rights from the ANICT, all of these having already been used up by many of them.

- Outside of its contribution (10% of initial funds) to initial ANICT financing, the State has made an effort to respond to the most pressing needs of State representatives in the regions, cercles and communes.

- The MATL receives permanent technical assistance (Cabinet, DNCT, CCN), as does the ANICT.

- The AMM chiefly receives assistance from USAID and German cooperation.

- Although a very recent creation, the HCC has already received limited financial assistance from Swiss and German cooperation.

  - Weaknesses

This institutional framework still presents some weaknesses, which is hardly surprising considering the infancy of these institutions, in conjunction with the chronic inadequacy - in quantity and in quality – of human resources, which continues to confront every one of the public structures.

- Territorial collectives firstly still have very limited human and financial resources, which need to be improved in the long-term.  With no thorough appraisal of this area9, huge needs still persist, despite effort engaged, particularly within the framework of the CCC mechanism and the various projects supported by international aid.  Moreover, current conditions governing the personnel of the collectives (status, frequent delays in salary payments, relations with mayors) represent another handicap.

- One of the great weaknesses of the current mechanism is the absence of simultaneous and clearly articulated reform action between the territorial collectives and the ministerial departments.  The deconcentrated services, themselves under-equipped (concentration of qualified personnel in the regional capitals and particularly in Bamako), are not in a position to carry out their technical mission of policy advice, monitoring and monitoring.  Thus the tax collectors of the Treasury can only with difficulty play the role that they should in terms of budgetary and financial advice to the collectives.  Similarly, the Regional Departments of Planning and Statistics (Directions Régionales de la Planification et de la Statistique, DRPS) do not have an active role in the decentralization process.  The large number of communes requiring training certainly does not facilitate things.

Representatives of the supervisory authority (tutelle) at the regional and local level also exhibit a certain resistance in regard to the new institutional framework that grew out of decentralization.  Though the bills have made provision for State-Collective collaboration (for example, the Préfet is President of the Local Policy Advice Committee) it should be noted that, in practice, such collaboration is very limited.

At the level of major technical departments, various management and policy advice structures linked to sectoral programmes have been established with the aim, in principal, of complementing decentralization, be it at the central level (Decentralization unit at the PRODEC level, for instance), or the regional and local level.  Besides problems tied to non-agreement between the sectoral intervention zones (for example the health district for the health sector) and the territories of the collectives, these bodies only engage in limited collaboration with the new territorial collectives.  Their structure expresses a view of decentralization that remains very static, and which seems to confuse itself with deconcentration.  As for the missions devolved to these sectoral bodies, they are often at odds with the decentralization bills, as with the various sectoral procedures such as those relating to the award of public contracts.

- The institutional steering framework for decentralization throws up weaknesses that in part explain the slow-down in reform implementation registered since 2000, at least in terms of the “transfer of competencies” measure.

Firstly, the shift from steering by mission administration attached at the highest decision-making level (Presidency of the Republic), to steering by a ministerial department, has played an important role.  In principal, this change is justified and even represents a forward move.  In reality, the reform has been “diluted” among other dossiers - notably that of the elections organization – and the National Department for Territorial Collectives (Direction Nationale des Collectivités Territoriales, DNCT) has had trouble carrying out its brief of designing and steering decentralization policy at a time when decentralization entered its “implementation” phase and when it was imperative to demonstrate DNCT authority in regard to other ministries.  The inadequacy of DNCT resources has not been rectified10 and the department does not always have sustainable regional-level structures to disseminate its policy advice, monitoring and “soft” assistance missions (the CCC, which to a degree carry out this role at cercle-level, are mainly provisional, and are intended to disappear at the end of 2003.

Thus, a clarification of responsibilities and improved collaboration is needed between: the MATCL (Ministère de l’Administration Territoriale et des Collectivités Locales / Ministry for Territorial Administration and Local Collectives), the alternate Ministry responsible for State Reform (and the Commission for Institutional Development / Commissariat au Développement Institutionnel, which itself will be attached from now on), the Civil Service Ministry, and the Governance Unit of the President’s office.

- Another weakness regards the capacity of national institutions to coordinate the various programmes and to carry out regular consultation with partners.  Certainly the two assistance mechanisms (CCN/CCC and ANICT) represent a powerful means of aligning the partners on goals, modes of assistance and common procedures.  As with operational coordination, exchange of information remains inadequate.

Thus it is with difficulty that the MATCL provides monitoring for programmes and projects that directly support decentralization.  For projects over which it has supervisory authority (more than twenty), monitoring is carried out in a fragmented way (projects are distributed between the seven advisors of the Minister’s office).

Similarly, the “Decentralization panel”  (quarterly consultation meeting with development partners) became virtually dormant for 3 years, that is, as of the disappearance of the MDRI.   From this point of view the panel’s re-launch meeting, which was organized in December 2002 and was on competency transfer, is an encouraging sign.

  - Factors linked to the legal and regulatory framework regulating local governance

2.1 Strengths

The legal and regulatory decentralization framework, which has been developed since 1993, confirms the principles affirmed by the Constitution of the 3rd Republic.  Many texts have been produced (cf. annex 7), foremost of which is the Code of Collectives (Code des Collectivités), published in 1995, modified in 1998, and currently under revision11.

This framework, which is largely clear and coherent, presents important strengths from the perspective of local governance:

- It affirms the principal of open management of decentralized territorial collectives by elected councils – by direct (communes) or indirect (cercles, regions and District), universal suffrage – and grants important competencies to the 3 levels of collective, enabling them to play an essential role in development planning and management.

- The commune (formed from urban districts or villages and/or rural factions) is given precedence, it is the level of collective that is closest to local communities and the only level where a collective is elected by direct universal suffrage.

- The Code of Collectives also emphasizes the participation of grassroots communities.  Thus, obligations of the Commune Council include (i) gathering advice from villages/factions/districts (v/f/d) on any deliberation relating to specified areas (introduction of shared equipment, for example), (ii) publicising all the progress reports on sessions (by billposting or v/f/d assemblies), (iii) consulting v/f/d advisors on development programmes, (iv) linking v/f/d leaders with the elaboration and implementation of development actions, and (v) Ensuring that consultations and public debate precede the budget vote.

- By the establishment of the High Council of Collectives (January 2002), it enables local collective representation at the highest level.

  - Weaknesses

- Though the legal framework may be a good foundation for decentralization, decentralization implementation comes up against a major obstacle: that of the implementation of the transfer of competencies, resources and property of the State to territorial collectives.  Seven years after the ballot on decentralization law and three years after having starting the work relating to the competency transfer, a comprehensive framework which would enable overall definition of the competencies and resources transferred, the conditions of these transfers or even the new collaborations which should be established between the collectives and State services, is still not available.  This situation is explained by, among other factors, the significance of the previously-presented resistance.

Certainly, progress has been made.  Following the establishment of governing bodies for the collectives in 1999, a first wave of automatic competency transfer took place, without any particular problems, by means of transfer of power between State representatives and elected councillors at all levels: budgets and accounts, financial resources made provision for by statute no. 00-44 of 7 July 2000 (which determines the financial resources of the communes, cercles and regions) civil status registry, census, health and sanitation, administrative policing, archives and documentation.

In order to clarify the provisions of the Code of Territorial Collectives – which demarcates the competencies of the collectives in very broad terms – several steps were monitored.  After identifying competencies transferable to the communes for 10 ministries, a national workshop was organized to define the workable methods of competency transfer (June 2000) and a work group has been created around the DNCT (National Department for Territorial Collectives /Direction Nationale des Collectivités Territoriales).  But it was only in June 2002 that three decrees12 were finally published, identifying the particulars of competencies transferred in the three priority sectors of education, health, and rural and urban hydro-power.  An action-taking schedule for the implementation of decrees was defined immediately after this by the DNCT but to date has not been applied.

Transfer poses no significant problem for hydro-power, as water management has already been the object of measures in this regard, and management committees which were set up are operating rather well (the problem from this point on being the sustainability of potable water supply systems).  It is not so for the two other sectors where implementing transfer comes up against multiple difficulties: technical difficulties in estimating the numbers and resources appropriate to different tasks which are the objects of transfer; difficulties then in proposing a detailed tasking order for the phased implementation of transfer; resistance exhibited by some of the managers of the ministries concerned; and the need to revise or repeal various sectoral texts which have become inconsistent with the spirit and the letter of decentralization policy.

Outside of the three sectors mentioned, transfer of competencies and resources is as yet unclarified for the other spheres of public-sector action, particularly the environment. Similarly, the delicate issue of the devolution of State property to territorial collectives should be legislated on.  In their present form, all the bills in force translate into an overlapping of mandates, even at commune council level.

- Beside the issue of transfer, the judicial framework remains incomplete in regard to three important points: intercommunality, the territorial civil service and regulation relating to the intervention of NGOs and decentralized cooperative actions.

Lack of a legal framework for management of intercommunal affairs is contrary to the implementation of various development actions. Intercommunality would enable a response to be brought to the problem of local investment financing (for example, water conveyance) at relatively high levels and the problem of the financial non-viability of certain communes.

As to regulation relating to the status of agents working with the territorial collectives, it represents a strong constraint.  Thus, strengthening community services not only comes up against a quantitative shortage of qualified personnel (nurses, midwives, teachers, etc) but also the fact that new personnel recruited by the collectives do not have desirable working conditions or guaranteed employment.  Considerable demobilization among the young managers employed to support the communes can also be noted, which can be explained by their conditions of work and frequent delays in salary payments.

- Finally, the framework for territorial division continues to be a delicate issue. Thus more than 200 ‘dispute’ dossiers pending at the level of MATCL (Ministère de L’Administration Territoriale et des Collectivités Locales / Ministry for Territorial Administration and Local Collectives) are documented. These situations, observed by the mission (Kangaba cercle), are hindering the communes’ initiative, and directly impacting on the degree of adherence to communal decisions particularly, as well as on mobilization of fiscal revenue.

  - Factors linked to the human capacity of local actors

The establishment of decentralization institutions has brought about an urgent and large-scale need in a context marked by high illiteracy and a very low level of training of local actors.  The percentage of illiterate local councillors is thus estimated to be at around 80%13.

It is not possible to assess the capacity of all the local actors, their needs, the responses brought to bear (diverse as these responses are), as well as the channels across which capacity-building is carried out. This report will confine itself to presenting the most meaningful elements available by means of the monitoring carried out by the technical assistance mechanism to collectives. It should be noted that the CCC intervene on demand and do not have the monopoly on technical assistance to the collectives. A substantial portion of training intended for local councillors, for example, escapes the monitoring system of the CCN (this is the case for, among others, many training programmes financed within the framework of the USAID Governance programme).

3.1 Strengths

- Since the establishment of the CCN team (April 2001), the strength of the mechanism has been demonstrated in at least three fundamental areas:

- It began to deliver a response to the considerable assistance needs of collectives and has had an indisputable effect as much on the quantity of initiatives implemented by the collectives (PDESC, training sessions,..) as on the quality of outputs (the vast majority of commune development plans now meet minimum standards of quality).

- It has been called upon as a national frame of reference for organizing support to the communes, harmonizing interventions which were to this point run to the advantage of the programmes of fund donors everywhere.

- It has mobilized considerable financing from these fund donors (CFAF6.5 billion with fifteen or so partners).

Today, all the Communal Council Centres anticipated are operational (46 teams covering the 49 cercles of Mali) and are lead by 27 field staff (projects, research units, NGOs) working either together or individually within the framework of contracts signed with the CCN.  Nine out of ten CCC already have a year of practice14.  The CCC (Communal Council Centres / Centres de Conseil Communaux) carry out differing assistance missions: technical supervision, organization of training programmes, assistance in setting up projects, liaison between fund donors and collectives, introducing collectives to service providers, etc.

All the policy advice instruments at cercle level (Comités Locaux d’Orientation / Local Advisory Committees), regional level (CRO) and national level (CNO) have also been installed.  From the CCC membership rate, which has reached 72% (percentage of communes to have signed an agreement with the CCC of their cercle and effectively paid the annual subscription, fixed at CFAF50,000) it appears that collectives have largely subscribed to the mechanism.

- In terms of capacity-building of territorial collectives and service providers, the following results were entered:

- 458 training sessions – representing some 167,000 people/day – have been supplied to the communes in priority target areas, owing to the assistance of the CCC: development of the PDESC (Plans de Développement Économique et Social / Social and Economic Development Plans), preparation of commune budgets, award of public contracts and project management.  New training sessions, based on the demands of the collectives, have developed to spread the effect of the initial modules.

- Most communes (88%) drew on CCC assistance in elaborating their 2002 budgets (which have in all cases incorporated the right to draw on the ANICT, input of the commune in mobilizing these rights, and the possible external financing linked to these).

- The CCC has enabled a dual, quantitative and qualitative, improvement of the communes’ PDESC.  Development plans have similarly been elaborated at the level of all cercles and regions (adoption of these plans being a preliminary condition for access to ANICT drawing rights).

- Support delivered for project management has enabled more than 1,400 project briefs to be handled, 991 of these have in fact been submitted for ANICT financing.

- Other activities have been run, this time in order to strengthen the capacities of the CCC itself:  training sessions for CCC operators (to upgrade skills in management and communal administration), dissemination of tools and management materials (guide to planning and programming of local development, manual of collective-related procedures  for public contracts amounting to less than CFAF10 million, training guides for commune officers and training of councillors,…), allocation by documentary credit, etc.

The 2001 “Journées Nationales” equally enabled experience-sharing between the CCC that were already operational, and resulted in production of manuals on priority thematic areas: local development planning, project management for territorial collectives, mobilization of commune resources, elaboration of assistance plans, and communication.

An inventory of service providers  - grouped according to area of expertise – has been generated at the level of each Cercle, and a database (OPAC - Opérateurs d’Appui aux Collectivités Territoriales / Support Operators for Territorial Collectives) has been set up. The OPAC database is regularly updated and accessible for all the CCC.  Training actions by trainers have begun to be organized to progressively develop the capacity of these operators to support the territorial collectives.

3.2 Weaknesses

- Certain weaknesses first of all concern the assistance mechanism itself:

  - Problems have firstly been encountered in providing financing for certain CCC (Mopti, Tombouctou), and in guaranteeing resources for the initial 3-year period anticipated for the mechanism.

  - Policy advice instruments do not have the requisite resources available and are rarely functional at regional level (CRO).  As for the National Advisory Council (CNO, Conseil National d’Orientation), meetings are not being run.

  - The technical steering team (CCN, National Coordination Unit /Cellule de Coordination Nationale) is restricted in terms of its mission, the number of CCC and the expanse of territory.  Some CCC have thus not yet been the focus of a monitoring mission by the Unit.  Its support capacities are, however, being strengthened by means of technical assistance to the CCN (from SNV and AFD), and the phased establishment of region level monitors, which is already effective in four regions and being carried out in two other regions.

  - At the local level, CCC capacities are equally limited and clearly are rather variable from cercle to cercle.  The question arises both in quantitative terms (the current CCC staffing levels do not facilitate close monitoring of the all the communes falling within their intervention zones), and qualitative terms (current profiles often continue to be inadequate for effective provision of a “soft” assistance mission that is devolved from the structure).

  - The monitoring and evaluation system is being instituted slowly, and dissemination of information still presents inadequacies (the increase of CCC information to the CCN).  A considerable lack of information exchange is observable; this leads to limited capitalization on experience particular to each CCC, and is also conveyed by the replication of activities (unnecessary preparation of training materials for example).

  - State technical services remain under-involved in the mechanism.  This goes back to the previously presented problem of the need for a real deconcentration dynamic at the level of the key sectors; it seems to have come to a standstill over priority support needs for local collectives.

The issue of the mechanism’s sustainability also remains intact.  The principle of dismantlement of the CCN/CCC mechanism at the end of a 3-year period hardly seems realistic as it seems difficult to envisage the possibility of self-financing the mechanism with local resources in the near future.  As this has been accomplished at the financial assistance mechanism level, a mechanism should be recommended that “secures” and globalises (from the project planning framework) financing of technical assistance, which will still remain necessary for many years, whether it be a question of training, support for feasibility studies, or even assistance to project quality control.

- As regards capacity-building more specifically, the major problem here is delivering a targeted response to a training demand that is difficult to satisfy.  It should be noted that:

- A considerable effort is still needed to bring the collection of elected councillors up to standard.  For example, training carried out at commune-level has particularly benefited the mayor, his deputies, the Secretary-General and officials. Whilst the other members of the commune council have not benefited or very benefited little from the training.  It can similarly be noted that technical assistance has been somewhat limited in terms of the Cercle Councils and the Regional Assemblies.

- Training actions come up against several constraints on the objectives linked to the public target: procurement capacities of the majority which are limited overall, diversity of levels of training, geographic dispersal, etc.

- Certain training programmes have had a particularly limited impact, due to a need for manuals in local languages and specific training materials for the illiterate.  Even when translated, training materials are often under-used.  Audio-visual resources and particularly community radio seem to be the best vehicle for information/training for a significant number of actors.

- Owing to insufficient coordination of training actions (a lack of comprehensive training programmes put together from unified modules), some resource wastage has been noted.  With better preparation/coordination, more and better training could have been carried out with the same means.  The proliferation of training materials, besides representing a waste of resources, has also created some confusion at councillor-level, despite the efforts of the DNCT around production of reference manuals for priority themes (local development planning, project management for collectives, commune resource mobilization, elaboration of assistance plans and communication between councillors and local communities).

- Operators agree on the need to now shift to more structured training action (training policy), which is diversified (modules tailored to the different target-group categories) and which gives more weight to supporting measures (training-action).

  - Factors linked to the planning and budgeting process

Elaboration of development and budget plans has been one of the first tasks of the DNCT (National Department for Territorial Collectives / Direction Nationale des Collectivités Territoriales) in terms of technical assistance to new territorial collectives.  It has similarly been the chief opportunity, since the beginning of decentralization implementation, to test the level and quality of community involvement, elected councillors, and other local actors.  The prospect of mobilizing resources from the ANICT has clearly encouraged mobilization of actors around the planning process.

4.1 Strengths

Today, almost all the territorial collectives have a 3-year development plan (PDESC, Plan de Développement Économique et Social / Social and Economic Development Plan). At year-end 2002, 703 PDESC encompassing 94% of the collectives (communes and cercles) affected by the technical assistance mechanism were thus monitored.  Of this total, more than three-quarters (541 plans) were developed with the assistance of the CCC.  Their implementation, in tandem with their adoption, began with development of the first project briefs principally tailored to the ANICT.

The commune development plans have, in the main, complied with the government-promoted participatory approach, guidelines for which are incorporated in the statute.  Different categories of local actor have thus participated in the various steps of the process, pursuing varied approaches.  Information campaigns and multiple training sessions have ensured the large-scale involvement of local communities and minimum mastery of the process.  Organization of grass-roots consultation (at village-level and district-level), and involvement of community leaders in the arbitration preceding the validation of plans by the communes, has contributed to developing information exchange on local problems and deliberation on priorities – at the level of village/district/faction then at commune-level.

It is, however, difficult to assess the quality of all of the documents since there are more than 700 programming documents that do not appear to have been subjected to comprehensive evaluation.  As to the quality of community involvement, it has depended on several parameters: methods used, management capacity of the process, level of training of principal actors, previous incidence of projects, social cohesion within villages, districts or factions and cohesion between the various v/d/f which make up a given commune.

4.2 Weaknesses

The chief limitations evidenced through field visits and examination of several PDESC concern the content of the plans, arbitration mechanisms and coordination between the PDESC and the other available planning tools.

- Realism of programmes:  PDC (Plans de Développement Communaux / Commune Development Plans) are often alike in including investment lists whose completion over three years is completely unrealistic15.  This situation firstly falsifies the preliminary local planning base with capital budgeting that is unrelated to mobilizable resources.  It can also give rise to frustrations among the communities who have little chance of seeing the promised developments being carried out over the three coming years.

- Limited view of local development problems:  The PDC, often developed around use of ANICT drawing rights, are polarised on the same investments.  They thus put little emphasis on other key measures of what should be their “local action plan”: mobilization of fiscal revenue; management of the system of community services levies; measures to be taken to ensure the upkeep of infrastructure and community facilities, recruiting the necessary Teaching and Health personnel, better organization of local production operations, consideration of the poorest commune categories, resolution of conflict between livestock-rearers and farmers, etc.

- Prioritization of investment and arbitration: Plans are often developed without investment prioritization from the grass-roots level, that is, that of local communities.  In these conditions, arbitration is then more complicated, longer and more tension-/frustration- generating.  It is also observed that in spite of measures taken to assure significant participation by grass-roots communities (villages and districts), commune development plans tend to promote projects localised in the principal town of a commune or in neighbouring villages.  Some experiences (for example, that of PACR-T, which limited the number of investments presented per village before organizing inter-communal days) should from this point of view be turned to advantage.  It is important to emphasize that the priorities of women frequently seem to have been mostly ignored in the PDESCs (restriction to a few revenue-generating projects, which are also not always eligible for ANICT financing).

- Choice of positive investments at the time of plan implementation and implementation monitoring: Once the plan is adopted, it is observed that no specific procedure exists for choosing individual investments to carry out from an over-ambitious list of priority projects.  True arbitration thus takes place after the participatory process is conducted, due to not having integrated the variable of mobilizable resource potential into the process.  As to community consultation and information mechanisms, at this point they are limited, indeed non-existent16. The development plan thus partly bypasses one of its essential interests: strict and consensual investment prioritization.

- Coordination between communal planning and other planning levels: This problem of integrating the various planning levels has been presented since the 1977 reform, which led to the creation of regional and local grass-roots authorities for planning. No specific mechanism still holds together the planning and arbitration respectively realised at the commune, cercle, region and central levels.  The present Public Investment Programme manual is limited to “national” (PI-Etat) and “regional” (PI-Région) programming. PDESC for communes, cercles and regions have not been the subject of an iterative consultation procedure between the various levels of collective.  Similarly, there is no systematic coherence between the PDESC for collectives and the sectoral plans (for example, the Health and Social Development Plans for Cercles / Plans de Développement Sanitaire et Social des Cercles prepared within the framework of PRODESS, The Health and Social Development Programme /Programme de Développement Sanitaire Et Social).  It is observed that the content of plans at the intermediary levels of regions and cercles often accords with activities scheduled by the various fund donors.

- Involvement of deconcentrated services: The Regional Departments of Planning and Statistics, as with the other deconcentrated services, have been technically under-involved in the PDESC preparation process, even though technical services were generally integrated in the final step of plan development.

  - Factors linked to resource mobilization for local development

Local collective financing is currently based around three key sources.  External aid heavily dominates and is chiefly delivered by means of projects financed by bilateral and multilateral donors.  Assistance from the Budget is delivered through the Endowment for the Operation of Collectives (Dotation de fonctionnement de collectivités), its contribution to FICT/ANICT and the consideration to the PIP (Programme d’Investissement Public / Public Investment Programme) on projects intended to support collectives.  Finally, the actual revenues of collectives (taxes and local dues, levies on service provision,..), only play a very limited role.

5.1 Strengths

- Local development financing is important particularly because of the favourable image Mali enjoys, this being linked to the quality of its democratic institutions and to the dynamism of its civil society.  This positive image encourages development partners to deliver substantial assistance, by means of project aid or budgetary aid.  Within the framework of the HIPC initiative, debt alleviation aid could total some US$870 million, of which US$220 million has already been granted; a very limited portion of this has been used to support decentralization.

In terms of budgetary aid, partners will henceforth emphasize the consolidation of budgetary mechanisms with a view to ensuring accountability of funds, the aim being generally to enlarge the portion of allocations with most immediate effect on the local communities.  This shift represents a positive development for the local communities.  As to project aid, annex 6 indicates a significant volume of assistance that does not pass through the ANICT.

The importance of the part played by resource transfer by Malians living abroad should also be emphasized.  Such transfers have been estimated to total 80 billion in the Kayes region, the chief emigration zone.  They are in part assigned to satisfying the basic needs of communities of origin and represent a means for unlocking the local financing constraint in many communes.

- In more specific regard to the national financial assistance mechanism to territorial collectives (ANICT), several valuable specificities are observed:

- At “demand” level: Financial assistance only occurs on the specific initiative of the collective.  It does take into account demand stemming from communes (and is thus distinguished from assistance funds supporting operator groups or user communities.  It only finances investment expenses – an illustrative list counterbalanced by a downside list  - answering to certain conditions (preliminary endorsement of PDC,…)

- At “offer” level:  Unlike a direct subsidy system, territorial collectives benefit from a drawing right to use over a 3-year period, calculated according to 3 criteria (population, geographical location, present level of equipment) and within the framework of regional budgets constraints determined by the Executive Board of the agency.  A supplementary drawing right (with an upper limit of 50% of the initial drawing right) is accorded to collectives that have discharged all of their initial drawing right before the end of the 3-year scheme.

- At investment choice level: The briefs are, in effect, prepared and dealt with at regional level, as are arbitrations (financing decisions) which are carried out under the aegis of the Regional Advisory Council (Conseil Régional d’Orientation).

The mechanism is new but commencement of operations demonstrates obvious benefits:

- ANICT benefits from considerable support (CFAF30 billion) for initial funds (2001-2003) from 3 partners (CFAF19 billion from the European Union, CFAF32.5 billion from the French Development Agency and CFAF3.5 billion from UNDP/UNCDF) and from the Government (CFAF3 billion). Since then, new fund donors (Switzerland, KFW/Germany, ADB) have become involved in supporting the agency.  It is a sign of partners’ increasing confidence in the mechanism but also an encouraging indicator for the process of harmonizing assistance procedures for fund donors, an essential ANICT challenge.  A significant portion of development partners now agree on the need to channel financial assistance to local collectives through the FICT, which moreover does not hinder continuance of technical assistance within the framework of project aid.

- The ANICT presents high payment rates with not relation to the particularly weak levels - around 15% - registered at the level of sectoral education and health programmes (PRODEC and PRODESS).  The mechanism seems to benefit from effective intervention of Treasury departments (the delay between ANICT payment and fund mobilization by the mayors is generally less than 1 week), demonstrating the success of the principle of a common fund, argued for by the system’s designers.  ANICT-financed investment projects already totalled CFAF14.6 billion at mid-December 2002, which represents a remarkable performance over hardly 14 months of payment activity.

- Commitments in terms of contributions from local collectives (3% of TDRL - ‘’regional and local development tax” - revenues for financing the mechanism and 20% from participation in the implementation of investment projects) are, in the main, fulfilled.

- The handling of briefs evidences the relative technical quality of investment proposals, as the rejection rate for briefs requiring additional information has not exceeded 5%.

- Procedures seem to have been mastered by collectives and financial monitoring of resource use seems to satisfy partners who have the option of, if they wish, targeting their financial assistance (specific sector and/or zone).

- The ANICT draws on ensuing human resources (headquarters and regional outposts) and benefits from permanent technical assistance (European Union).

5.2 Weaknesses

ANICT Mechanism

The ANICT has scheduled an evaluation of its mechanism during the 1st half-year of 2003.  The mission has noted the following problems:

- The principal problem, raised by the “clients” of the mechanism concern the local contribution of 20% to investment financing.  Firstly, this rate is felt to be a significant constraint for local communities.  Then, uniformity of rate is questionable on two accounts since, real investments and social investments on the one hand, and both rich and poor communes on the other hand, are treated in the same way.  Furthermore, it can be observed that the input required from collectives continues to vary for the same investment according to the mechanism used: many partners – including UNDP/UNCDF or UNFPA – stipulate a less substantial input from the communes (at the level of 10% of the cost of the investment).

- Criteria for drawing rights allocation are improvable.  Use of capacity criteria for local resource mobilization is desirable; which brings us back, as per sound financial logic, to the proposal that rights are allocated according to savings capacity.  Its application is, however, not so easy, considering the degree of reliability of objective verification sources (use of receipt lists for measuring the effective level of local tax recovery).  These criteria do not otherwise consider the relative poverty of local communities/zones covered (save the public equipment allocation) but it is true that, even there, the problem of limited statistical data is come up against.  In fact, refinement of allocation criteria, which are the product of consensus, remains dependent on improvement of the statistical information system.

- Non-eligibility of certain investments (case of irrigated areas) represents a handicap for certain regions in terms of food security.

- Problems in the field are noted according to the quality of certain projects, evidencing the necessity of clarifying and systemising project monitoring missions.

- A significant information effort remains necessary in order to guarantee generalised awareness of ANICT as much as of other mobilizable resources (sectoral programmes, Microproject Programmes, specific funds of missions, etc) and their procedures.

- A number of the development partners encountered are awaiting clarification on ANICT operating methods, particularly on the efficiency and quality of work carried out at the regional agency level or even of the monitoring and evaluation system which must be in a position to accurately inform on the specific use of resources, performance of activities in progress and the impact of investments.

- The availability of funds from donors to the ANICT remains to be improved (delays observed being generally connected to the procedures of these partners).

- The validation system of investment proposals must be consolidated17.

- Finally, that a TDRL (‘’regional and local development tax”) payment of 3% to ANICT is an arrangement that has finally been adopted in practice but which is not incorporated in law, should be noted.

Resource Planning

- Financial visibility for communal planning.  The communes do not possess the financial elements necessary to develop real multiyear programming for PDC development.  They can prioritize actions but do not have access to information on the various potential resources (for example on anticipated supplementary drawing rights for the mobilization of new external financing inputs).

- Harmonization of fund donor approaches: The very existence of a national investment fund gathering the inputs of various fund donors – whether allocated or not – is in itself an important step forward.  The increase of financing entrusted to ANICT confirms this positive development. However, some partners continue to be hesitant in regard to this new national system of local collective financing.

General Domestic Resource Mobilization

- The economic context and the degree of poverty is a significantly slows down the decentralization process.  With a GDP/per capita of less than US$300 and weak economic growth, the country continues to face immense difficulties in financing its development.  At the local level, precise data on fiscal poverty is not at present available.  The composite indicator used for the CSLP (Cadre Stratégique de Lutte Contre la Pauvreté / Strategic Framework for Poverty Reduction) however attests to the dominant nature of poverty even if it may have lessened in the last few years from 71.6% in 1996 to 69.0% in 1998 and 64.2% in 1999.  The incidence of poverty is certainly higher in rural areas (71%) - that is, in the establishment zones of new communes - than in urban areas (31%).

- Commitment of the State in the financial assistance mechanism to collectives (3 billion to ANICT) must be made relative since it only represents 10% of mobilized financing and is partially made up of resources previously registered in the Endowment for the Operation of Collectives (Dotation de fonctionnement de collectivités). As to the State allocation to the territorial collectives, it remains almost unchanged since 1999 (outside of levies carried out to finance the ANICT).  The increase in the allocation that took place in 2002 remains limited  (+3.7%) and only concerns the Region level (Regional Assemblies) and the Cercle level (Cercle Councils).  Financing of collectives thus essentially remains dependent on external aid.

Specific Local Resource Mobilization

- The resources of territorial collectives have been specified by law but, these resources are not available in view of the delay in transfer of competencies and resources that has been identified.

- A significant section of the community does not pay taxes. This “fiscal incivism” also affects many more urban communities than rural communities, though they are poorer overall.  In this area decentralization has had contrasting results. If in some cases (PACR-T zone for example), commune assistance is conveyed by an increase in fiscal revenue – or at least of rates of collection –, it seems that generally the reverse18 phenomenon has been observed.  At least three factors have come into play here.  Firstly, specific resources of territorial collectives (contract rights, haulage depots, royalties from occupancy of public places or land) “return” with difficulty due to lack of means and competencies. Then, the fact that the communes and no longer the State is responsible for revenue-collection has, it seems, very much reduced the coercive factor on taxpayers.  Finally, pressure on agricultural revenues (unfavourable climatic conditions) for three years makes recovery more favourable.

- Knowledge of actual possibilities for resource ‘harnessing’ by means of taxation and levies linked to provision of local public services remains very limited. Similarly, rare are the collectives to have deeply deliberated on a local strategy for resource mobilization which would be likely to improve the tax base, the volume of emissions and the rate of collection.

- In order to maintain the centralisation and transparency of accounts, a framework has been proposed leading to an at least annual verification of accounts by the supervisory body. In spite of inspection missions that have been carried out (integrating the MATCL (Ministère de L’Administration Territoriale et des Collectivités Locales / Ministry for Territorial Administration and Local Collectives), the Ministry of Finance, Côntrole d’Etat and the Accountancy Division of the Supreme Court), verification of communes’ financial statements is difficult.  Moreover, a procedure for information centralisation does not exist.  This would, for example, enable understanding of comparative performance in terms of emissions and collection, and thus impact evaluation for the various assistance projects for communes from this point of view.

  - Factors linked to the process of local development management and other parameters

Factors linked to participatory management of local development actions

Considering the mission approach, which is fixed on the decentralization process, analysis of involvement in actual management of local development actions has not been developed.  This can be explained on several grounds: new local governance has only beginning; management activities implemented within the framework of new collectives are only starting; finally, competency transfer, which is the basis of local collective participation in development management, is not always efficient.

As regards local collectives, they have taken over responsibility for their general competencies since 2000 (civil status registry, budget,…), and benefit from the assistance already presented.  On the other hand, their involvement in the management of facilities and public services remains very limited, due to the inefficient transfer of competencies and necessary resources and where it exists, management is carried out in conditions which are often testing (see for example, the management of teaching personnel from the new communes).  However, the recent decrees and the works in progress offer the hope that the participatory framework for the collectives in the management of the education, health, and hydro-power sectors will be quickly completed.  It should be noted that the older (urban) communes, with the assistance of several projects including the Urban Development Programme, already have significant experience.

Since the PDESC (Plans de Développement Économique et Social / Social and Economic Development Plans) are now practically all finalised, assistance delivered by the CCC should concentrate on project management capacity-building for the territorial collectives.  The training programmes already completed and support delivered in preparing and implementing the first FICT-financed projects have already led to mobilizing collectives on these works.

During the period, involvement of local communities in the development of certain public services has been improved within the framework of sectoral policies, by means of assistance delivered to various grass-roots community organizations (village associations, women’s groups, producer groups).  Communities also play a significant part in priority sectors through water management committees, ASACO, (management of CSCOM, Community Health Centres) and the APE (school management).  Thus, the ASACO (Associations de Santé Communautaire / Community Health Associations) recruit health representatives, run the pharmaceutical storage site, and fix the tariffs on services.  It will be noted that the financial contribution required from local communities, particularly for involvement in civil engineering work for constructing the CSCOM, has been progressively reduced (from 50% to 20% then to 10%).  Management of community health services continues to face problems in financial and, particularly, human resourcing, which is why of a total of 1044 health sites, barely half (559) are functional.

Factors linked to the system of representation

The system of democratic representation has several strengths: free and transparent elections, presence of elected councillors over the whole system (communes, cercles, regions, HCC), several information and advocacy campaigns for decentralization undertaken by the MDRI (Mission de la Décentralisation et des Réformes Institutionelles / Mission for Decentralization and Institutional Reform), and a participatory process administered as part of communal planning.

Councillors are, of course, legitimate but their capacity to represent the interests of local communities is limited by several factors.  Firstly, involvement in local elections is not very high (around 33%).  This figure, which markedly exceeds the rate recorded for legislative elections (25% in the 2nd round), should, however, be made relative; it can be accounted for by (among other factors) an illiteracy rate which is still significant, the system of automatic registration on electoral registers, and the quality of the upkeep of these registers (multiple registration). In some regions (North of Mali), rates are 60% -70%.

Considerable efforts must still be made to create a true culture of local democracy.  The conduct of councillors and functioning of the commune councils do not always promote real exchange with local communities.  Thus local communities perceive mayors and municipal councillors as public servants and not as elected representatives who have informational responsibilities and who are obliged to achieve results.  It has been observed that, in various localities, once the local elections were over local communities continued to remain estranged from the process of public decision-making, and that a good number of councillors do not seek to establish a regular link with the administration.  Councillors’ access to certain benefits can also be misinterpreted, facilitating an upsurge of fiscal incivism.

A survey commissioned by UNDP and carried out in January 2003 presents revealing indications of this perspective.  Whilst 90% of those polled consider holding regular elections to be essential and 80% have confidence in the democracy of their country, 48% declare themselves under-satisfied or unsatisfied with the role of the commune council in representing local communities.  73% of them also feel that they cannot influence commune council policy-making.

Factors linked to women’s participation

The limited participation of women in local governance represents one of the major weaknesses of the process underway:

- Statistics do not enable assessment of women’s right to be included in electoral lists, or their participation rate in elections, particularly commune elections.  On the other hand, the very low representation of women within local collectives is demonstrated: women represent 13.4% and 15.7% respectively of the total councillors for urban and rural communes, and only 5 female mayors of a total of 704 (0.7%) 19are recorded. This situation is all the more prejudicial as women play a very active role in grass-roots initiatives, particularly in rural areas, whether for revenue-generating activities or activities of a social nature.

- Illiteracy, the burden of familial responsibility and under-information represent obstacles to women’s involvement and participation in the decentralization process.  Certain socio-cultural forces also contribute to limiting their actual participation in general debate.

- The limited place accorded to women in the management of activities linked to decentralization is also explained by the limited consideration of the gender perspective by institutional actors.  Training programmes, which are often targeted to councillors and State representatives, only very marginally concern women. Some partners, particularly USAID, have had a more positive impact in this regard by starting from targeting which is more oriented to civil society.  The financing mechanism does not promote consideration of women’s needs, which are sometimes distorted through all-purpose projects (market gardening, etc).

- UNDP CONTRIBUTION TO OUTCOME

As with the national level, UNDP inputs will be assessed by restricting the scope of the evaluation to projects and activities directly linked to the implementation of decentralization policy.

Even working within the bounds of a circumscribed scope of analysis, evaluation of UNDP’s input is made difficult by the fact that references to outcome in UNDP intervention and the logical planning frameworks that are used to assess developments and inputs, have been progressively introduced during the 1998-2002 period.  Thus, (i) no baseline case to draw against exists – particularly in terms of indicators – to assess the progress and contribution of UNDP intervention in terms of outcome; (ii) project strategy in relation to Strategic Results Framework outcomes has not been developed; (iii) a single project can refer to several outcomes; (iv) the results structure has been changed several times.

First of all, initial UNDP strategy, such as it arises from the Cooperation Framework and its realisation by means of the development and implementation of five projects, which have been attached to Outcome 3, will be retraced. The scope of geographic intervention, financing mobilized and the quantifiable outputs of UNDP assistance will then be identified.

Finally, assessment will be made of UNDP’s contribution roughly following the previously proposed interpretation for “deconstruction” of outcome.  The following will thus be dealt with:

- Support for institutions and the decentralization policy framework;

- Capacity-building assistance to local actors;

- Support for the planning and budgeting process

- Support for the local development management process;

- Support for resource mobilization for local development.

  - UNDP strategy and projects linked to Outcome 3

  - UNDP strategy and implementation constraints

Owing to the factors that were previously presented, UNDP has not at the outset been able to develop a strategy relative to Outcome 3.  Starting with the Cooperation Framework and information gathered, the approach favoured by the country office at the start of the Programme and which led to development of the five projects studied can be demonstrated.

This approach is based on the following key strategic options:

- Promoting local governance by implementing, via field projects, UNCDF intervention methods which were previously developed elsewhere and that are specifically based on capacity-building for communes and grass-roots communities, the establishment of local development funds and a local resource mobilization strategy;

- Coupling anti-poverty actions and decentralization assistance actions;

- Develop coordination between upstream and downstream interventions, entailing advising government on decentralization policy by drawing on capitalized field experience in the various areas concerned (planning, resource mobilization, implementation of anti-poverty actions,…);

- Support strategic steering and aid coordination in the area of governance, with preparation of a donor Round Table on decentralization in mind.

This strategy accorded with government shifts and could benefit from:

- Very close collaboration between the UNDP country office and the Decentralization Mission;

- Meaningful UNDP positioning on the anti-poverty strategy, via the DHD (Sustainable Human Development And Poverty Reduction) Observatory created in 1997 and the accompanying measure of SNLP (National Strategy for the Fight Against Poverty) development;

- Lessons learned from projects of the previous cycle implemented in the area of assistance to local and anti-poverty initiatives.

- A solid partnership between UNDP and UNCDF.

These initial guidelines will come up against a series of constraints over the course of their implementation, which will combine to limit the coherence and impact of UNDP intervention the area of decentralization:

- Firstly national constraints, with the removal of the main UNDP intermediary, the MDRI, and a certain estrangement of the MATCL (Ministère de L’Administration Territoriale et des Collectivités Locales / Ministry for Territorial Administration and Local Collectives) on strategic issues;

- Constraints linked to UNDP as an organization, with the severe reduction of resources (30% drop of CIP, falling from US$60.4 million to US$42.5 million) and subsequent application of new guidelines regarding repositioning the strategies of the country office, changes to the majority of reference tools (adoption of the RBM system) and particularly “reprofiling”:

- Constraints specific to UNDP-Mali, including difficulty in maintaining synergy between projects linked to decentralization and good flow of information between stakeholders.

  - Project strategies linked to Outcome 3

Five projects from the 1998-2002 Country Programme are directly linked to Outcome 3.  Implemented within the framework agreement signed between April 1999 and June 2001, they are of varying duration, from 3 to 5 years.  In principal, all the projects will therefore be running in 2003 and at least three of them will be running in 2004 (PARCAD which must be concluded soon is in fact relayed by the UNV Decentralization Assistance Programme).

Table 2:  Database on the key projects linked to Outcome 3 :

(Data – preliminary budgets)(US$)

ProjectsAgreemt.DurationMgmtNatio. org.Coop. org.Total cost UNDP (a)Govern.Others (b)PRECAGED01/04/994 yrSG/MEFUNOPS3,118,5303,118,530CFAF30 M-PACR-T01/04/995 yrMEPI (c)UNOPS8,018,500631,500137,0007,250,000PARCAD28/08/003 yrNEXMATCLDAES704,250704,25072,250-PACR-M24/07/005 yrMATCL- 12,100,5721,200,000 2,400,0008,500,572ACODEP08/06/013 yrDNAMR/MDR- 3,457,050800,000380,0002,277,050Total27,398,902

(a) For PACR-M, only US$500,000 out of US$1,200,000 is guaranteed on signing the Prodoc (2000-2002 contribution), the remainder of the funds remaining to be confirmed in 2002 according to the general resourcing situation.

(b) “Other” contributions are:

for PACR-T : UNCDF (US$6,123,000), WFP (US$715,000) and local communities (US$412,000).

for ACODEP : European Union (US$111,666 ) and other partners (US$2,165,384 ; seeking financing )

for PACR-M : UNCDF (US$6,000,572) and  Communes/Mopti region (US$2,500,000).

These projects arise from three different departments: the Ministry for Territorial Administration and Local Collectives, for PARCAD, PACR-M and PACR-T; the Ministry of the Economy and Finance (MEF), for PRECAGED; and the Ministry of Rural Development and Environment, for the ACODEP project.

Their implementation, which is generally completed in accordance with national implementing methods, is supported in three cases by a cooperating organization (DAES for PARCAD, UNOPS for PRECAGED and PACR-T).

These projects can be classed according to several criteria:

- Two “regionalized” projects (PACR-T and PACR-M) each targeted to a specific region (the Tombouctou and Mopti regions respectively), all the outputs of which can be reattached to Outcome 3;

- A regionalized project (ACODEP), with broader geographic targeting (the three regions of Kayes, Koulikoro and Sikasso), only a section of whose outputs are directly linked to Outcome 3;

- A project (PARCAD) which is also geographically targeted (Tombouctou and Mopti regions), and all the outputs of which are linked to Outcome 3, but to which in some cases national scales are applied;

- A project of national scope (PRECAGED) which, however, includes activities in certain specific zones (Commune IV/ Bamako, 8 test-cercles in 8 regions, 2 test-communes in 8 cercles) and linked to Outcome 3 by certain components.

This preliminary programming framework which, for some, reflects the diversity of positive approaches would have benefited from simplification, especially in regard to resources mobilized and the difficulty that there often is in establishing sustained collaboration between different project units. This relative complexity is confirmed by a brief review of priorities and the intervention methods of these projects.  Only the objectives/outputs linked to Outcome 3 have been studied within the framework of projects competing for several outcomes (ACODEP, PRECAGED).  Table 1 summarises the grid of results for the 5 projects.

PRECAGED

The National Capacity-Building Programme for Strategic Development Management (PRECAGED, Programme de renforcement des capacités nationales pour une gestion stratégique du développement) is based on 3 main lines of intervention: (i) Strategic management; (ii) Decentralization planning and land-use planning; and (iii) Training.

The project information document indicates excellent preparation and a globally coherent approach.  Programme interventions follow a long line of assistance projects centred on the functions of planning and management of the economy; the programme’s adaptation to the new decentralization climate was conveyed during the Segou National Seminar on planning renewal (1997).  By devoting a specific section of the project to decentralized planning and land-use planning, the programme acts in response to the dual necessity of (i) integrating the public policy of the new local collectives in a more global strategic framework of national spatial development, and (ii) developing upstream deliberation on the decentralized planning tools and their coordination with planning tools/central programming, particularly the CSLP(Cadre Stratégique de Lutte Contre la Pauvreté / Strategic Framework for Poverty Reduction)  and the sectoral programming frameworks (PRODESS, PRODEC,…).

Although it may not be specifically linked to decentralization, the PRECAGED training section also presents a benefit for Outcome 3.  Development of a national training plan can in effect meet the considerable training need at different levels (regions, cercles, communes).  Such a plan can equally promote joint training programmes relating to representatives of deconcentrated services and territorial collectives, and serve as an additional tool for an overall public administration deconcentration programme.

In terms of Outcome 3, the main flaw of the strategy is inherent in the decentralized planning method’s having anticipated the development of various planning outputs – development plans or outlines for planning and development – without proposing the means for monitoring their use and without identifying the synergies with the other UNDP interventions, in terms of decentralization planning (or at least with the PACRT whose document was prepared at the same time).

Table 3: Projected Results for projects linked to Outcome 3*

| Projects | Results | Intervention Zones |
| --- | --- | --- |
| PRECAGED | - Establishment of planning structures adapted to decentralization policy in the regions, cercles and test-communes. | - National scale - “Regionalized” actions: Commune IV/Bamako, - 8 test-cercles, 5 communes per test-cercle. |
|  | - Finalisation and approval of regional planning documents and Land-Use Planning documents. |  |
|  | - Elaboration of outlines for planning and development at cercle level and test- commune level. |  |
|  | - Development and implementation of tools of consistency between the different levels of planning. |  |
|  | - Replication and dissemination of cartographical planning tools at commune level. |  |
|  | - Development of a realistic training plan following a process of beneficiary consultation and dialogue with development partners. |  |
|  | - Beneficiaries of the training plan are trained. |  |
| PARCAD | - Decentralization actors in the communes, cercles and the Mopti and Tombouctou regions are updated on, and trained for, their role, their rights, and duties in the education, health and natural resource management sectors. | - Mopti region - Tombouctou region |
| ACODEP | - Development and implementation of anti-poverty action plans in 131 communes. | - Koulikoro region, targeting the Kangaba et Dioila cercles - Kayes region, targeting the Kita cercle - Sikasso region, targeting the Bougouni cercle |
|  | - Development of local planning and management capacity in 246 communes. |  |
| PACR-M | - Introduction and implementation of transparent and participatory mechanisms of local development planning and programming. | - Mopti region (107 rural and urban communes, excluding the former urban communes of Mopti) |
|  | - Access of communes and all cercles to financial resources, internal and external, and the appropriate administration of these resources. |  |
|  | - Local capacity in terms of implementation of monitoring & evaluation development actions is reinforced. |  |
|  | - Sustainable initiatives to promote usage/management systems for renewable natural resources, planned in a participatory manner at the level of territorial collectives, and administered by the village communities. |  |
| PACR-T | - Establishment of a decentralized consultation, planning, participatory programming and financing strategy. | - Tombouctou region, targeting 3 cercles, Tombouctou, Diré and Gourma-Rharous (27 communes) |
|  | - Local capacity strengthened in terms of undertaking development initiatives. |  |
|  | - Improvement of access conditions of local communities to infrastructure and social and economic services. |  |
|  | - Implementation of a communication and information system. |  |

* Only outputs linked to Outcome 3

PACR-T

The Assistance Project to the Rural Commune of Tombouctou (PACR-T, Programme de renforcement des capacités nationales pour une gestion stratégique du développement) has been established in an area in which UNDP and the UNCDF have intervened since the 80s.  It, in fact, meant regaining a commitment whose implementation had been made difficult in the 90s by conflicts in North Mali.  This project aims at improving the living conditions of rural communities of the area, via (i) development of a decentralized strategy (dialogue, planning, participatory programming, resource mobilization), (ii) building local capacities of development planning and management, and (iii) improvement, by a local public investment policy, of community access to services and social and economic infrastructure.

The project area, which would initially cover the 5 rural communes of Tombouctou, has been extended to include the two other cercles of the Mopti region benefiting from assistance within the framework of the Assistance Project for Local Development (PADL, Projet d’Appui au Développement Local), jointly financed by the French Development Agency (AFD) and the Rhône-Alpes Regional Council (Conseil Régional de Rhône-Alpes). It is a region which is poorly integrated into the national economy and whose considerable poverty has been exacerbated by passing ecological crises (the bad droughts of 1973, 1984, 1997-1998), economic and political crises (the1990-95 rebellion).

Project strategy can be summarized as follows:

- Action targeted to promoting local governance and resource mobilization for local investment;

- Group of beneficiaries extended to include almost all the local actors: local administrative authorities and deconcentrated services, councillors and commune personnel, councillors of Cercle Councils, rural communities, livestock-rearer groups, NGOs and other local service providers;

- The project is based on a participatory approach which aims to involve and give a sense of responsibility for local resource management actions to rural communities; pastoral and agricultural intensification actions and diversification of remunerative activities;

- The project undertakes to promote partnership between technical deconcentrated services of the State, NGOs and grassroots communities for planning and execution of actions;

- Finally, the project incorporates a communication and information section which aims on one hand, to improve analysis of results obtained and consequently improve the effectiveness of actions and, on the other, to capitalize on lessons learned and circulate the “best practices” examined as part of the project.

Drawing on financing of some US$8 million, this project presents a structured strategy, which is inspired by the approach developed by UNCDF, allying governance and economic and social development goals at local level.  The project, which was established during local elections, has enabled support for communes of intervention zones as soon as they are set up. The PACR-T was able to afterwards develop, adapting to the change of context.  Planning procedures and financing systems have firstly been reviewed in order to position the commune at the centre of the mechanism, while continuing to accord specific attention to community participatory mechanisms.  PACR-T modes of intervention have then been revised in order that they are integrated in new national mechanisms created for technical (DNCT/CCN/CCC) and financial (ANICT) assistance to local collectives.

PACR-M

The Assistance Project to the Rural Communes of Mopti (PACR-M, Projet d’Appui aux Communes Rurales de Mopti) is bears a strong resemblance to the PACR-T. Thus, references to promoting practices of good local governance, involvement of all the actors (particularly village communities) in commune affairs, the application of the principle of subsidiarity and even to the increased mobilization of local resources as an indicator of Commune effectiveness are to be found.

Having been developed later, it has been able to give greater emphasis to issues of of elected councillor and local governance capacity-building, and to be better accord with mechanisms responsible for implementing decentralization.  The project is differentiated from the previous project by:

- Greater financial capacity: PACR-M, which currently has a budget of US$12.6 million, is by far the most significant of the five operations under review in terms of resources;

- Sizeable commitment of the Malian government (US$2.4 million) and communes of the Mopti area (US$2.5 million);

- Comprehensive coverage of the intervention area (107 communes covered);

- Entering the new national assistance mechanism for collectives: UNCDF will thus be one of the first external assistance donors at ANICT level.

PARCAD and the UNV Programme

The Capacity-building Assistance Project (PARCAD, Projet d’Appui au Renforcement des Capacités) aims, by means of training activities, to build the capacities of decentralization actors (elected councillors, civil society representatives and deconcentrated government) in regions, cercles and communes.

Strategy is built around triple targeting: in terms of outputs (training-centred activities), sectors (training thematics targeted to three sectors: education, health, and natural resource management) and intervention zoning (two areas of Tombouctou and Mopti).  In addition to training actions, the project has a measure dedicated to enhancing mobilization and coordination around the decentralization process (Round Table monitoring, etc), to communication strategy and to the strengthening of MATCL (Ministry for Territorial Administration and Local Collectives / Ministère de L’Administration Territoriale et des Collectivités Locales) capacities specifically.

If the intervention priorities are justified, the response given by the project information document is not always comprehensible.  The initial logical planning framework presents inadequacies, and its priority concept – building the capacities of decentralization actors by, under MATCL supervision, establishing sectoral training modules – can seem inappropriate, especially in a zone limited to two areas, as much in terms of the limitations it puts on training interventions as in the choice of institutional arrangements.  Moreover, synergies with the two PACR-T and PACR-M programmes - which account for the choice of the PARCAD intervention zone – are not clarified.

Mobilization of financing for a UNV decentralization assistance programme has been an opportunity to institute project revision.  In fact, handicapped by an insufficiently appropriate strategy, a situation of uncertainty over the development of the project as well the need for a coordinator, PARCAD continued its activity until the end of 2002 at a rather slow pace and with limited results.

The UNV Programme information document - preparation of which commenced at the beginning of 2001 - was only signed in August 2002, and the programme only effectively started in January 2003 with an anticipated duration of 30 months.  This programme has again taken over responsibility for a portion of the inputs of personnel from PARCAD, which must shortly be concluded.  However, the UNV programme information document should be closely examined again.  The paper is, in effect, outdated in a number of regards (context, stage of the decentralization process, activities in progress at PACR-T and PACR-M level,…).  Moreover, the programme only amounts to human resources availability (20 volunteers) with no real strategy.  Alternating between assistance to national structures and assistance to UNDP projects, the UNV Programme could well, if it were applied in its present form, lead to a proliferation of areas of responsibility, which would not be very favourable for the overall effectiveness and adequate visibility of UNDP intervention.

ACODEP Project

The ACODEP project is in fact the second phase of a project implemented by the Ministry of Rural Development during the 1993-1997 period, based on the principles of integrated rural development, and a participatory approach.  The new phase more or less maintains the same objectives: building management and planning capacities of decentralized collectives and civil society organizations; socio-economic integration of poor and marginalized strata (by professional training for rural youth and access to credit for women); institutional strengthening of partners in the field (NGOs and rural partners).

The second phase is represented by three vital distinctions.  Firstly, the project takes the new communal order into account by supporting the training of elected councillors (mayors, adjuncts, municipal councillors).  Then, it proposes to improve grassroots planning with development of new plans (village development plans now titled anti-poverty actions plans).  Finally, the project continues to intervene in the three intervention regions of the first phase (Kayes, Koulikoro and Sikasso) but from this point undertakes to reach all of the 246 rural and urban communes of these areas (and 3,848 villages) and no longer the 131 communes and 345 villages of the first phase.

In relation to the new UNDP programming framework, the ACODEP project, which only effectively started in April 2001, presents the disadvantage of being linked to several outcomes.  Only the first two sections are to be linked to Outcome 3 (and considered in the evaluation.  These are (i) assistance to 131 communes in the development and implementation of anti-poverty action plans, and (ii) building management and planning capacities in 246 communes.

For the two sections that concern us, the project presents the following characteristics:

- It clearly links the strengthening of decentralized collectives’ management and planning capacities with poverty reduction.   However worthwhile the principle may be, in practice it is expressed by assistance to elaboration of commune development plans (PDESC, Plans de Développement Économique et Social / Social and Economic Development Plans) as per the conventional approach.  Anti-poverty action plans do not have “status” and their elaboration only began in 2002, closely following adoption of the PDESC.  Clear though it may be that practising commune planning must not be confined to simply cataloguing public amenities’ projects and should take other local anti-poverty dimensions into account, it also seems important to avoid increasing processes, and reproducing at local level the saturation that has been noted at the level of State central services in the past.

- The project is distinguished from other “regionalized” projects by its institutional anchoring (Ministry of Rural Development).

- The project does not intervene in financial assistance to communes.

- At its initiation, the project presented a considerable financing need that was not covered (US$2.2 million out of an overall budget of US$3.5 million).  This financing need has only partly been covered (by recourse to HIPC funds).  Considering available resources and the presence of other operators in the three intervention areas, the project is in fact targeted to a limited number of cercles.

2. Scope of geographic intervention, financing and outputs

2.1 Scope of Geographic intervention

The five projects linked to Outcome 3 cover a considerable number of areas of the country – in very distinct ways – including Bamako district.

The Mopti region is certainly the most “invested in”.  In effect PACR-M covers all the territorial collectives of the region (107 rural communes and the Mopti cercle) with the exception of the former urban commune of Mopti.  PARCAD also began by intervening in the region (training programmes at Mopti and Djenné).  Finally, PRECAGED prepared an

Outline for the Planning and Development of Cercles (Schéma d’Aménagement et de Développement de Cercles, SADC) -  (Koro cercle) and is now elaborating a planning and development outline for the two test-communes.

In the Tombouctou region, UNDP also has a “central project” (PACR-T), which is, however, targeted to three cercles – Tombouctou (5 RC), Diré (13 RC) and Gourma-Rharous (9 RC) – a total of some 27 rural communes.  Here PARCAD and PRECAGED have intervened in the same manner as in the Mopti region: region-level training actions and development of a SADC for the Tombouctou cercle.

For the Koulikoro region, ACODEP project interventions target the cercles of Kangaba (9 RC) and Dioïla (23 RC).  However, the project has selected a commune from another cercle (Kita) to test out its proposed new programming tool (anti-poverty action plan, Séféto-West commune).  PRECAGED decided upon a fourth cercle (Nara) for SADC preparation.

In the Kayes region, ACODEP in theory targets all the communes.  In fact, the Kita cercle (33 communes) is more specifically targeted.  PRECAGED assistance (SADC preparation) centred on the Kayes cercle.

In the Sikasso region, the ACODEP project intervenes at the level of the Bougoni cercle alone (26 communes) and PRECAGED in that of Niono (SADC).

Other regions have only been the target of activities, via pilot-operations implemented by PRECAGED. These are one hand the Outline for the Planning and Development of the two cercles of Ansongo (Gao area) and Kidal, and on the other hand elaboration of the 3-year Development Plan and the annual action plan of Commune IV in Bamako district.

Undoubtedly the scope of ACODEP activity specifically linked to Outcome 3 and which is UNDP-financed has been limited.  That PRECAGED-supported activities are of a specific nature (pilot-operations) should also be considered.  Be that as it may, the geographic scope of these five projects can seem too dispersed when UNDP resources and the priority from now given to upstream actions are considered.  It is observable that synergy has not been sought.

If PRECAGED and PARCAD interventions are excluded, the three regionalized projects are noted to cover 265 communes, 38% of all collectives.

2.2 Mobilized financing

Taking into account the entirety of financing, the five projects that the evaluation concerns represent US$27.4 million (excluding the UNV programme).  The UNDP-specific contribution is limited to a quarter of this sum (US$6.5 million, including US$700,000 financing that remains to be mobilized to promote PACR-M for the next programme). The UNCDF contribution is in excess of US$12 million.

In view of the last CCN (Cellule de Coordination Nationale / National Coordination Unit) assessment (January 2003), UNCDF/UNDP with a total of CFAF652 million represent 10% of total DNCT/CCN resources available for financing the technical assistance mechanism for territorial collectives.

  - Outputs

The chief outputs of UNDP assistance linked to Outcome 3 can be summarised as follows:

Table 4: “Consolidated” main outputs for the 5 projects linked to Outcome 3

| Area | Output | Project Covered |
| --- | --- | --- |
| Structures and tools of decentralized planning | - 8 outlines for the planning and development of cercles (1 cercle/region) - Commune development plan in an urban commune (Commune IV/ Bamako District) - Methodological guides for the elaboration of the SAD (outlines for the planning and development) of Cercles and for elaboration of the SAD (outlines for the planning and development) of communes - A methodological lessons paper on the experience of planning in Commune IV - Analysis of the coherence of the various planning levels - Analysis of the restructuring of planning and development management services | PRECAGED |
|  | - 444 Grassroots Planning Committees (Comités de Planification à la Base, CPB), 27 Communal Development Commissions (CCD, Commissions Communales de Développement) and 3 functional Inter-Communal Commissions (CIC, Commissions Inter Communales) - Three programming tools (Financing Code, planning, self-evaluation) implemented - 27 PDESC (Plans de Développement Économique et Social / Social And Economic Development Plans) validated and implemented | PACR-T |
|  | - 105 PDESC validated and implemented for the communes (out of 107 rural communes of the Mopti area) 26 of which with the direct assistance of the project - 8 cercle PDESC 1 region PDESC validated - 74 commune budgets approved by the supervisory authority within the statutory time period | PACR-M |
|  | - 42 commune development plans elaborated - 32 anti-poverty action plans being redeveloped | ACODEP |
| Methodological Tools and Training Media | - 12 training modules developed in annual planning, management of natural resources, archiving and drafting, local taxation | PACR-T |
|  | - Development of 8 manuals or guides for territorial collectives regarding (i) commune development planning, (ii) communal administration, (iii) development of commune budgets, (iv) planning development of cercles/regions, (v) commune project management, (vi) criminal investigation services within the commune, (vii) administrative policing within the commune, (viii) civil status registry (in development), (ix) local resource mobilization strategy (under construction). | PACR-M |
|  | - A methodological guide for development of the cercle SAD (outlines for the planning and development). - A methodological guide for development of the commune SAD - A methodological lessons paper on the planning experience in Commune IV - A study of the coherence of the various planning levels | PRECAGED |
| Information and Training of local actors | - 1141 people trained in techniques of decentralization and communal administration, budget development and implementation, award of public contracts, civil status registry - commune councils trained in annual planning (10) self-evaluation (24) - 30 Secretaries-General trained in archiving and administrative drafting - 267 elected councillors and commune officers trained in ANICT financial procedures - 404 elected councillors and commune agents trained in the manual of commune management procedures - 4,461 community members (via the CPB - Comités de Planification à la Base/Grassroots Planning Committees) and 1,202 women trained in decentralization - communication activities for citizens | PACR-T |
|  | - production of some 160 radio and television broadcasts (preparation of the PDESC, information on the national assistance mechanism for collectives,…) - communication strategy paper - 64 members of CCC and service providers trained in project management - 564 people trained in budget development and implementation - 239 people trained in civil status registry and administrative drafting - 241 people trained in personnel management - 64 women commune councillors and managers of associations or groups trained on the electoral process - 1075 village leaders (including 45 women) trained in planning tools - Training of officers (109 officers: commune personnel, collectors/tax collectors and representatives of the supervisory authority | PACR-M |
|  | - 1,438 elected councillors trained: development of the PDC, project management, local governance - commune resource mobilization and public service provision modules - competency transfer workshop - elected councillors and managers of 9 communes (Kangaba cercle) trained in project management for implementing ANICT-financed projects - 38 SLACAER and NGO representatives trained in commune assistance and development of anti-poverty action plans - 24 Communal Council Centre officers and partners trained. | ACODEP |
| Mobilization of financial resources for investment | - Manuals: payment procedures, FICOM (Intercommunal funds) - Grants to local collectives (61% of total paid out) - 262 socio-economic infrastructures/facilities completed - Recovery of taxes and dues improved (average rate of 65%) - Study of local taxation | PACR-T |
|  | - 149 projects approved by the ANICT Regional Committee (CFAF1.7 million) | PACR-M |
|  | - Resource mobilization study and forum (communes/Kangaba cercle) | ACODEP |
| Local Management of Natural Resources | - Intercommunality Study based on natural resource management | PACR-T |
|  | - Communal consultations on the environment and management of pastoral resources - Regional forum on communal and intercommunal management of natural resources | PACR-M |

In terms of efficiency (inputs →outputs), UNDP assistance via the five projects studied has had satisfactory results overall.  Efficiency is clearly somewhat variable according to projects.  The PACRT and PACRM projects demonstrate elevated performances from this point of view and it is observable that for 2002 the targets by outputs are practically all achieved, indeed exceeded.  On the other hand, results are less distinct for the ACODEP project: some slowness is observed in the realisation of outputs although the project has a strong team.  The PARCAD team demonstrates weaker results.  As to PRECAGED, performance has been judged satisfactory by the mid-term evaluation mission.  The current mission is however more cautious in terms of the relevance of some outputs and their impact (cf. below).

In terms of effectiveness (outputs → outcomes), the observations are similar at the level of the respective performance of projects.  The overall effectiveness of UNDP interventions – which is the true scope of outcome evaluation analysis – is analysed below by more or less re-employing the structure previously proposed to analyse outcome development and outcome factors at national level.

3. Support for institutions and the Decentralization policy framework

Strengths

- In the early stages of the period, UNDP has operated according to its experience of assistance delivered within the framework of the Capacity-building Project for the Promotion of Decentralized Development Management.  The findings of this project, which came to an end at the beginning of the cycle, convey the crux of UNDP-delivered upstream assistance during the period under study.

- At the beginning of the cycle, UNDP and UNCDF collaborated closely with the MDRI (Mission de la Décentralisation et des Réformes Institutionelles / Mission for Decentralization and Institutional Reform), the architect of decentralization policy.  UNDP even intervened in financing the Head Officer of the Mission of Decentralization. UNDP and UNCDF helped, by means of their expertise and the dissemination of their experiences of earlier projects in deliberation on technical and financial assistance mechanisms that today form the bases of the national assistance programme for territorial collectives.  Continuing exchanges, realised for preparation of PACR-Tombouctou have enhanced this input in terms of substance.  It seems that close relations, which are as individual as they are institutional, which have existed and continue to exist between UNDP (country office and project teams) and the national decentralization steering structures (MDRI then MATCL) have had a considerable affect.

- This upstream assistance is initially conveyed by development of papers for a decentralization Round Table, PARCAD having, among others, been initially designed to carry out decentralization monitoring and extend government “soft” assistance.

- Completion of the of the Department of National Territorial Collectives’ audit (July 2002), on the basis of UNDP/UNCDF/SNV collaboration, constitutes the only meaningful assistance action to Decentralization steering institutions.  This study can now represent the entry point for UNDP repositioning in regard to its upstream assistance mission.

Weaknesses

- UNDP’s “driving role” in defining the tools of decentralization implementation, as mentioned by several speakers, is not - as with the country office’s specific assistance in terms of strategic advice on decentralization and local development (“soft” action) issues - easy to assess, particularly for previous years.  The facts reveal that other partners have committed themselves and have played a central role in this area, including at the level of conception of mechanisms and tools of technical assistance to the degree that UNDP does not have – or no longer has – specific positioning and cannot claim a position of preferential advisor in terms of decentralization policy.

- In fact UNDP investment in terms of “soft” assistance to various central structures intervening in decentralization steering has remained very limited although significant needs continue to persist without being covered, particularly at DNCT level.  This point was also highlighted by the mid-term evaluation of the 1998-2002 Programme which concluded that that the chief weakness of the programme was its lack of ambition in the area of decentralization:  “Having played a key role over several years within the MDRI, UNDP made a U-turn, moving towards downstream activities.”  Today, other partners are positioned on upstream assistance:  the European Union (assistance to two financial and technical assistance mechanisms, and advice particularly in setting up the monitoring-evaluation system at ANICT-level), The Netherlands (assistance to the CCN, training policy, implementation of competency transfer), France (assistance to the technical support mechanism and deliberation on deconcentration and decentralization coordination), Germany (particularly on training policy).  In this panorama of “soft” assistance, UNDP’s role is limited.

- In the area of aid coordination, no tangible result has been achieved.  The Round Table of partners on decentralization has not been held and mechanisms established to ensure regular dialogue between Government and development partners on decentralization policy (panel), which were formerly supported by UNDP, have been shelved since 2000. It is difficult to assess whether a more vigorous advocacy action for the UNDP Country Office would have led the government to be more vigilant in regard to aid coordination mechanisms and the need to enshrine the action of the two technical and financial assistance mechanisms in a medium-term/long-term strategic framework.

- Finally, it should be noted that decentralization policy must from now on be carried out in close partnership with collectives’ representative institutions, to which UNDP has not delivered any assistance, either to AMM (l’Association des Municipalités du Mali / Mali Municipality Association) or HCC (Haut Conseil des Collectivités/ High Council of Collectives) (which, admittedly, is a recent creation).

4. Capacity-Building Assistance to local actors

Strengths

- Training is an element common to the five projects.  PACRT, PACRM, and the ACODEP project have wished to build the capacities of local actors by proposing training likely to ensure satisfactory preparation of commune development plans and command of responsibilities essential to getting the communes underway.  PARCAD recently began training programmes on its sectoral modules.  PRECAGED, which does not have authority to directly assist elected councillors’ training, has proposed a training plan for development planning and management structures and has carried out dissemination of proposed methodologies for the outlines for the planning and development of cercles and communes.

- Table 4 attests to the sustained level of actions implemented for the training of decentralization actors, even if it is not easy to present an exact consolidated totalling up of training programmes20. PACRT has also trained more than 1,800 people (principally elected councillors and commune representatives), approximately 4,500 community members, excluding training encompassing all members of commune councils or training programmes targeted to women.  More recently, PACRM has the training of 2,300 people, including nearly 1,100 village leaders, to its credit. The ACODEP project has, for its part, trained more than 1,400 elected councillors, excluding training on project management for effecting ANICT- financed projects and training carried out within the framework of Anti-Poverty Action Plan establishment.

- Training has covered all the priority thematics.  The modules delivered, some of which intersect, relate to commune planning (PACRT, ACODEP); budget development and implementation (PACRT, PACRM); award of public contracts (PACRT, PACRM); project management (PACRT, PACRM, ACODEP); civil status registry, archiving and administrative drafting (PACRT, PACRM); ANICT financial procedures (PACRT), commune management procedures (PACRT); and personnel management (PACRM).

Differences between projects are observed, which are linked, among other things, to the commencement period and to specific objectives sought.  Thus the training spectrum seems somewhat narrow for ACODEP (planning and project management).  As to PACRT, which has supported the communes of its intervention zone since their establishment, it has developed and delivered no less than 12 training modules. The more recently established PACRM has targeted its capacity-building action to themes more in keeping with the operational responsibilities of collectives (collection of fiscal revenue, personnel management, administrative policing and criminal investigation services).

- Other useful initiatives, likely to contribute to capacity-building of local actors and which it would be desirable to capitalize on have been put into action:

- Formation of a pool of local trainers and determination of a “mandatory minimum” for commune capacity-building (PACRM);

- Training and putting in practise in 2002 of a self-evaluation of commune councils (PACRT; all targeted communes);

- Constitution of a yearly data bank (idem);

- Implementation of a communication strategy centred on community radio and enabling development of information on local populations on decentralization (PACRT);

- Organization of exchange fora on mobilization of commune resources and the organization (ACODEP)

- Organization of a competency transfer workshop (ACODEP);

PACRM also, understandably, emphasizes shifting to a new stage of commune training, based on supported assistance. It must thus test this blueprint in 2003 at the level of civil status registry organization for a limited number of communes, as circulation of best practices to other communes operates on the basis of intercommunal exchange.

- Even though a weighting scheme, which also varies from project to project has been introduced, projects strive to cover all the decentralization actors.  If the chief target has been elected councillors and commune officers, various sessions have been open to technical services officers, presidents of other collectives (cercle councils and regional assemblies), officials, tax collectors, sous-préfets, CCC advisors and even to local service providers.

Within the framework of grassroots planning (CPB: Comités de Planification à la Base/ Grassroots Planning Committees), PACRT has supported training of community leaders (more than 4,300) and leaders of women’s associations (nearly 800) in a meaningful way.

- Although impact evaluation of all these training programmes is not easy, the programmes have played an essential role in the quality of the participatory process for development of commune plans (PDESC, Plans de Développement Économique et Social / Social and Economic Development Plans) and in mastering initial commune management responsibilities. This feeling is substantiated by the findings of the achievement evaluation survey carried out by PACRT21, by the capacity of communes – without external assistance – to suitably work out their budget and administrative accounts or even by the progress noted in respect of procedures of public contracts awarding.

Weaknesses

- These training programmes have certainly contributed to outcome in respect of intervention communes giving to new elected councillors the minimal know-how necessary for a true “involvement” in local governance.  This contribution, on the other hand, is more limited in respect of communities, with the exception of the PACRT zone.  Simultaneous capacity-building of elected councillors and civil society organizations is dependent on establishment of good local governance.  At the same time as optimal use of community radio, projects must be able to develop activities and encourage production/transmission of audio-visual media.  It is noted that, as per projects financed by other partners, not many actions were run for other collectives.

- In part from the fact of targeting elected councillor training (very low representation by women), women have been insufficiently taken into account.  Assistance to leaders of women’s organizations can particularly contribute to improved articulation of their demands and promote further incorporation of their concerns in development action plans.

- Training has not given rise to a common strategy for the various UNDP projects and information exchange on the lessons learned and training outcomes (as with all the rest also) have been limited between projects.  Training materials have been developed in a separate way and have often not been exchanged or then have been after a long interval.  The same observation, presented on the national front, of duplication of outputs and under-capitalization, is found at the level of UNDP project teams.

- Thematics of sectoral management have hardly been addressed because of the very reduced pace of activities experienced by PARCAD (the first training programmes carried out by this project have, to the contrary, shown the importance of training local actors on these thematics).

- The training plan (2001-2003) developed by PRECAGED (training plan for planning and management structures within the administration and in decentralized collectives has not been able to serve as a unifying framework. The implementation of this plan, which was introduced in May 2001, came up against a lack of resource mobilization for its financing.

5. Support for the planning and budgeting process

Strengths

UNDP has delivered a meaningful contribution to the development and implementation of tools and mechanisms of decentralized and participatory planning.  This input is important in both quantitative (number of Social and Economic Development Plans developed) and qualitative (participatory approach and introduction of new ideas) terms.

- UNDP has firstly supported upstream deliberation on reform of the planning system and coherence of the various tools.  Considering the proliferation of commune, cercle and region plans, and given the lack of a framework to enable coordination of decentralized and sectoral planning processes, UNDP has supported the government by financing a study on the coherence of the various planning levels (PRECAGED, February 2002).  UNDP has also sought to proffer its support to decentralized planning with a view to overall reform of the planning system.  It is thus that, still within the framework of PRECAGED, it has produced an appraisal of the human resources of development planning and management structures (October 2000) and published a study on restructuring of the development planning and management system, which was validated in May 2002.

- All the projects, apart from PARCAD, proposed methodological manuals and documents on preparation of commune plans and budgets.  Methodological guides have also been produced for the development of outlines for the planning and development of cercles and communes (PRECAGED) or even for development of Anti-Poverty Action Plans (PALCP).

- Generally, all the PDESC (Plans de Développement Économique et Social / Social and Economic Development Plans) developed within the framework of UNDP (and UNCDF) assistance are based on participatory processes.

From this point of view, tools proposed by PACR-T are certainly the most useful.  Owing to the CPB (Comités de Planification à la Base/Grassroots Planning Committees) they firstly enabled considerable participation by village communities: the project thus succeeded in involving more than 50,000 people (more than 20% of the population of the 27 communes) in the preparation of plans.  By virtue of their composition, these CPB have enlarged the traditional village councils, by integrating other groups (women, youth), and today continue to play a role in consultation between communes and villages/ factions.  CPB members also regularly participate in commune council sessions.  Other consultation mechanisms have been created such as the CCD (Commission Communale de Développement/ Communal Development Commission) or the CIC (Commission Inter Communale/ Intercommunal Commission).  This CPB presence as well as the principle of building communal planning on “primary level” (community) planning is very positive from the point of view of local governance.  It has also helped the arbitration process, (for it is based on a preliminary list of priority investments limited to five projects per village).

As to the ACODEP project, it has sought to better integrate the anti-poverty problematic into the work of local planning by proposing to develop anti-poverty action plans.

Weaknesses

- Upstream efforts around reform of the planning system have not to date given rise to policies.  Study on the coherence of planning levels has at present only been examined by a group that has been limited to managerial staff of a few local services (DNCT, MAT, DNP).  As to planning reform, it is a pity that the work, which is part of a functional analysis, should give rise to proposals reduced to a simple “structure/mission” matrix without developing the key elements, that is job sharing and information exchange around each function.

- As regards methodological tools, UNDP resource wastage, as previously presented, produced by running similar projects on identical subjects, will be raised.

- Implementation of the SADC poses a range of problems.  The land-use planning level is questionable for various reasons.  It would have been preferable to favour the region level rather than that of the cercle.  Firstly, because of specific prerogatives granted to the regions in terms of economic and land-use development.  Then, when availability of information, which is very low at cercle-level, is considered. Finally, for reasons of cost since nearly fifty collectives should be covered.  It is also observable that the cercles have been almost systematically selected from outside of the intervention zones of UNDP “regionalized” projects, thus impeding any possible synergy between SADC preparation and development of the PDESC. The SADC thus do not seem to have been very mobilizing tools, for their operational importance has not been clearly shown.  No financial partnership has been able to take shape in this area either.

- The contribution of the ACODEP projects to local planning has to date been limited due to  (i) delays identified in project commencement then in the implementation of activities linked to planning, (ii) difficulties encountered in the realisation of anticipated supplementary financing.  The mission also deliberated on the validity of introducing a new planning tool at commune level.  The anti-poverty action plans are not part of the decentralized planning reference tools of the DNCT/CCN and their status is unclear.  It would be better to concentrate energies on the implementation of that which exists (the PDESC) rather than to introduce a new planning tool at commune level.  This does not, as part of PDESC revision, prevent improvement of their content (strategic “vision” and consideration of the problems of commune poverty resolution of which is not solely limited to the realisation of investments).  Moreover, it seems that local communities do not always understand the aim of a new planning process although commune plans have only just been finalised.   Restoration of the 99 PALCP (Plans d’Action de Lutte Contre la Pauvreté / Anti-Poverty Action Plans) that are in development should in the short-term give more precise information on this assessment and on the added value of these plans.

- Generally, UNDP projects have not been able to avoid some of the stumbling blocks already mentioned in the preceding chapter:

- Insufficient consideration of women’s priorities22;

- Cost of the participatory process: numerous meetings and advocacy missions in villages are high-cost and local resources are inadequate to support these activities.  The issue of sustainability thus remains intact;

- Understanding of the planning procedure: this remains weak at the village leader level;

- Content of programmes: managers obstinately persist in proposing microprojects outside of the financial scope of the communes.

  - Support for the local management of development

    - On account of the very recent nature of new communes’ establishment, projects have specifically concentrated their support on the planning process and availability of core knowledge for the day to day administration of communes (understanding of administrative procedures, accounts, etc..).

    - In terms of day to day management, improvements are particularly visible at the levels of PACRM and, particularly, PACRT projects: understanding of budget preparation, regular convening of commune council sessions, practice as regards statutory provisions, particularly in council session advertising and publication of records of proceedings.

    - PACRT has the completion of more than 260 infrastructures and socio-economic facilities for the use of the communities of the 27 intervention communes to its credit.  If implementation exceeds expectation important problems are thrown up:

- Conditions for sustainable participatory monitoring of development plan implementation have not yet been created;

- Feasibility studies have often been of inadequate quality and conditions of their cost-effectiveness have not been sufficiently examined and discussed;

- Project management assistance, by means of the CCC, still represents an area where capacities are very weak.  Moreover, auditing and monitoring functions are not always dissociated.  Finally, in the case of the Tombouctou region, interventions come up against a dual problem of the quantity of and expertise of local enterprises (PACR-T is thus obliged to train assistants in project management for preparation of tender appeal papers and work monitoring).

    - As to management of capital stock and activities arising from the sectoral prerogatives of the communes, the mission has not been aware of specific assistance of UNDP projects in this area.  It is clear than the present context (lack of concretisation of transfer of competencies and resources) makes initiative-taking difficult.  However, it would be worthwhile to develop consultation between in-the-field actors on these issues and to explore models of contracting on some test-communes.

    - Finally, the two PACRT and PACRM projects have sought to promote sustainable systems of natural resource utilisation/management involving communities as much as local collectives.  Results in this area are mitigated:

- The number of natural resource management projects allowed for in the approved PDESC (Social and Economic Development Plans is low (PACRM’s estimation for the Mopti region is less than 7% of financing).

- FICOM (PACRT) has not been established, due to texts regulating intercommunality not having been passed.

- PACRM has, however, supported implementation of commune councils on the environment and the management of pastoral resources, in all the sous-prefectures of the Mopti region.  These have led to the convening of a regional forum on pastoral resources (more than 300 participants) and the development of an action plan.

  - Support for resource mobilization for local development

Strengths

- The two projects which have made provision for inputs of capital for local collectives in their budget (PACRT, PACRM) contribute to financing the investments of new communes in a non-negligible way.  Thus for the PACR-M, investment funds allocated to FICT/ANICT total US$4.6 million (UNCDF budget), to which resources mobilized for FAGEL should be added (Luxembourg financing of US$500,000).  For its first disbursement exercise, more than 150 projects are observed to have been approved by the ANICT regional committee for a sum of CFAF1.7 billion, and almost all the communes have mobilized their contribution of the requisite 20%.

PACR-T, which to date has been using its own mechanisms, has financed investments of some CFAF1.5 billion.  It has already paid out more than 60% of the resources allocated to investment although it is only halfway through its run.

- By choosing to entrust all resources for financing local investments to the ANICT, PACR-M has contributed to creating a positive public image for this agency.  The fact that the PACR-T is at the moment at standstill due to this very mechanism will further enhance the effect.

- In accordance with other projects, training actions, management of budgeting responsibilities and an, in the main, satisfactory collaboration between the communes and the deconcentrated services of the Treasury have been able to have a positive impact on fiscal revenue.  Within the framework of PACRT, observed improvement in the rate of income tax and local taxes collection is linked to conditions of access to funds, which link resources granted to specific performance criteria (including a fiscal revenue collection rate which must be higher than 50%).

- The three PACRT, PACRM and ACODEP projects seek to afford higher priority to local revenue consolidation.  A PACRT study on the tax system has thus been carried out in 2002.  The ACODEP project has financed both a study on resource mobilization and the organization of a resource mobilization forum (in the nine communes of the Kangaba cercle).

Weaknesses

Delays in the availability UNCDF resources have been observed.

Information gathered by the mission in the PACRM and ACODEP intervention zones conversely indicate the negative growth of collection rates.  In this regard, it would be worthwhile to observe the development of the situation in the three cercles covered by the PACRT from its subscription to the ANICT mechanism, which, at present doesn’t make provision for links between collectives’ drawing rights and their fiscal revenue.  This development should equally have consequences for local communities’ contributions to investment financing (fixed ratio of 20% for the ANICT, variable ratio and generally in the region of 10% for the preliminary PACRT mechanism).

Effort employed around the issue of resource mobilization is also not included in thorough inter-project exchange discussions, likely to lead to a cooperative intervention strategy.

In a fair number of intervention communes, problems of “fiscal incivism” persist, and indeed are exacerbated by the behaviour of certain commune councillors, turning their post to their own advantage for personal gain and thus discouraging fiscal efforts.  Other difficulties are observed, owing to communes’ lack of information on allocation of revenue from certain locally-collected taxes (trading dues, for example) and to non-payout of the portion owing to communes.  However, these problems are not specific to UNDP projects.

Apart from PACR-M at local level (cf. below), UNDP has not had a meaningful impact in terms of overall mobilization of external aid and development of financial partnerships.

- UNDP PARTNERSHIP STRATEGY

This fourth and final “category of analysis” of the Outcome Evaluation aims to evaluate how partnerships are designed, built and implemented.  It leads to deliberation on the conditions under which UNDP works with other actors, particularly those most concerned by outcome.

  - Key partners in achieving Outcome 3

  - National Partners

The key national partners have already been presented.  These are principally MATCL (Ministry for Territorial Administration and Local Collectives), MEF, the main technical departments concerned by competency transfer, and of course, the territorial collectives themselves and their institutional representatives (HCC) or associates (AMM, ACCM).  Numerous national NGOs should be included, some of which have developed considerable know-how in terms of participatory approaches and local development assistance.

  - Development Partners

Decentralization is a very mobilizing theme and most partners support the development of more participatory development management. This assistance is carried out either via specific decentralization assistance projects, or within sectoral or multi-sectoral projects that draw on local collectives and/or village communities in order to achieve some of their objectives.  There are some 30 projects relating to decentralization and more than 10 development partners who deliver their direct support to decentralization policy.  This proliferation of actors does not, of course, facilitate coordination of inputs and the monitoring of activities and outcomes.

For technical assistance to collectives, six multilateral (European Union and UNCDF) and bilateral (France, Netherlands, Switzerland, Germany) partners as well as two NGOs (NEF and World Vision are directly involved in financing the national mechanism (CCC network) with a budget in excess of CFAF6 billion over three years.  Besides the project units themselves, about twelve NGOs are registered in the mechanism as chief CCC project operators or associates.  In financial terms, the largest contributors are the European Union as well as French (AFD, and SCAC), German, Dutch and Swiss bilateral cooperation.  Besides UNDP and UNCDF, other partners are USAID, Canadian and Belgian cooperation, UNICEF, the WFP, etc.  NGOs play an important role here, be it through direct assistance, or be it within the framework of projects financed by the partners cited.  A solid partnership for financial assistance for collectives is being established around the ANICT.  Several partners thus already make their financial assistance to territorial collectives – or a portion of this assistance – go through the agency: European Union, UNCDF, France (AFD), ADB, Germany (KfW) and Switzerland.

Other fund donors also contribute to achievement of Outcome 3 of the SRF in a meaningful way, but their assistance is carried out in accordance with methods on the fringe of the national assistance mechanism for territorial collectives.  This is, for example, the case for the World Bank PAIB (Grassroots Initiatives To Fight Hunger and Poverty) and PDUD (Urban Development And Decentralization) projects and the USAID Governance Programme.

This assistance to development partners (detailed in annex 7) poses three main problems in the area of Decentralization:

- Coherence of approaches.  Partners intervene in accordance with various approaches and tools, and do not necessarily take account of policy advice and frameworks of action defined by the Malian Government.  In some cases, a single partner may develop distinct modes of intervention according to projects/programmes.  This, for example, is the case, for the World Bank with the PDUD projects (local collectives-centred approach). The PAIB (approach centred on direct financing of the microprojects of specific operators: producer groups, NGOs, etc) and assistance brought to bear within the framework of PRODESS and PRODEC (vertical /sectoral approach at standstill due to implementation mechanisms in conflict with the new outline of responsibilities defined by decentralization regulations).  Similarly, the European Union supports local initiatives administered by communes (via ANICT), while directly financing village initiatives – without bypassing these very communes – as part of the Microproject Programme.

- Resource allocation criteria.  Development partners tend to define their interventions according to a system of territorial partition, as this is observed in various APD beneficiary countries, which has a potential dual adverse outcome.  Firstly, this situation does not promote programme coordination or the uniformity of strategies and tools used.  Then, it proscribes a reasoning system of controlled distribution of financial flows between the various regions, cercles and communes.  One of the ANICT objectives is integration of the two logics of targeted aid (donors) and equitable allocation of resources to local collectives.

- Assistance to sectoral programmes.  The establishment of sectoral programmes in several sectors (education, health, transport, justice…) for use as frameworks for harmonizing development partners’ interventions, in various ways represents significant progress in external aid coordination.  These programmes unfortunately tend to strengthen the position of managers who display clear resistance towards competency transfers from technical ministries to territorial collectives.  Moreover, they display very low delivery figures, on account of ponderous procedures and mechanisms for contracts awarding, fund mobilization and project management which are still very centralised.  Finally, their implementation is based on institutional arrangements that are inconsistent with the regulatory provisions for decentralization.

  - Partnerships implemented by UNDP on Outcome 3/SRF

During the 1998-2002 period, the UNDP-Mali country office developed partnership in a meaningful way.  This is particularly expressed by the reconciliation of databases and programming tools with the other United Nations agencies (CCA, UNDAF) and by financial partnerships with certain bilateral donors (Norway for governance, Japan for tourism). In terms of Outcome 3, since the beginning of the 1998-2002 cycle, UNDP has emphasized in its project documents the need to propose active partnership strategies for these projects and to maintain close synergies between projects.  Some financial partnerships also implicitly represented a condition for the implementation of all activities scheduled (case of the ACODEP project).

2.1 Partnerships with national institutions

The first and key UNDP national partners have been the institutions providing project supervision and/or directly supported within the framework of their activities.  In relation to the three ministerial departments concerned (Ministry of Rural Development for ACODEP; Ministry of Planning for PRECAGED and, initially, PACR-T; and the MATCL for PACR-M and PARCAD).  It is observable that:

- The partnership with the MDR (Ministère du développement rural / Ministry of Rural Development) is very under-active, so loose does the relationship between this department and ACODEP seem.

- The Ministry of Planning and PRECAGED have implemented more active cooperation.  Most of the activities closely relate to the responsibilities devolved to this department.  Problems arise from the fact that certain prerogatives of the Department of National Planning have been transferred or are exercised in a shared (indeed competitive) way by other structures: CSLP (Cadre Stratégique de Lutte Contre la Pauvreté / Strategic Framework for Poverty Reduction) Unit for development and implementation of anti-poverty strategy, the Land-use Planning Mission for policy of the same name, DNCT for certain sections of decentralized planning.  Finally, it is observed that collaboration between the Directions Régionales du Plan et de la Statistique (DRPS / Regional Departments of Planning and Statistics) and the two PACR-T and PACR-M projects remains limited23.

- MATCL will from now on provide national supervision for three projects: PACR-T, PACR-M and PARCAD. Inasmuch as this ministry does not have divisions, it is difficult to base sustained technical cooperation with projects in progress within the country on it.

The most meaningful partnership – though it is not UNDP-specific – is that which links three of these projects with the national technical assistance mechanism for territorial collectives.  It is expressed by a true contractual engagement for a period and by clearly-defined objectives (CCC statement of work).  Thus, PACR-T intervenes in the Tombouctou region, as a Communal Council Centre in the two cercles of Diré and Tombouctou  (agreement signed in November 2000 for a duration of 3 years).  PACR-M, however, intervenes in the Mopti region as a CCC for the Ténenkou and Youwarou cercles. Finally, the ACODEP project is partner to the mechanism in the region of Koulikoro, in the capacity of CCC for the Kangaba cercle (agreement signed in April 2001 for a duration of 3 years).

Besides contracting relating to the two cercles of Ténenkou and Youwarou, PACR-M, which intervenes over all of the Mopti region, has concluded its draft financing agreements with almost all of the CCC operators, excluding the Koro CCC (which is run by World Vision and a portion of whose financing comes from the European Union):  NEF (in Douentza and Mopti), World Vision (in Koro), AFVP (in Bandiagara and Djenné), Care (in Bankass).  PACR-M is, it seems, also recognized as a true technical partner as much by the Haut Commissariat, as by the local collectives encountered.

Two recent initiatives attest to UNDP and UNCDF willingness to strengthen their relationship with the DNCT.  It first concerns the study-analysis jointly produced with the SNV, then the input delivered to establishing the network of regional monitoring managers (agreement signed in September 2002 between DNCT and PACRM for the establishment of a monitoring manager in the Mopti area).

The other projects do not seem to go as far.  The partnership presented in the consultations in fact corresponds more to more or less selective cooperation, achieved as part of subcontracting contracts.  Thus PARCAD has worked with the CCN in the replication of training materials and with DENAPLA in the production of audio-cassettes for the illiterate beneficiaries of the training programmes.  ACODEP has sought to conserve the same service providers (CEPROCIDE, AM CDR / Kita and ECOFOR / Bamako) throughout the process of anti-poverty action plan development.  PRECAGED has worked with the national NGO, Mali 2001, in decentralized planning.  The anticipated partnership with MAT (which joined the project steering committee) has not, since the inception of the mission, given rise to any definite action apart from convening of a workshop (2000) and the exchange of documents.  Connections are, however, being formed in order to examine assistance that could be delivered around implementing the recent Land-Use Planning policy paper.

2.2 Partnerships with external organizations

Financial Partnerships

The two PACR-M and PACR-T projects are based on financial and technical partnership between UNDP and UNCDF.  They benefit from joint financing by two bilateral donors (Belgium for the PACR-T by means of the Belgium Survival Fund; Luxembourg for PACR-T by means of FAGEL) totalling US$3.7 million and the assistance of the WFP (PACR-T).  A significant national contribution is also delivered, particularly at the level of PACR-M, which receives an input of US$2.4 million from the government (the grant to FICT and other contributions representing 19% of the total project cost) and US$2.5 million for communes of the Mopti region (20% of the cost).  The local contribution to PACRT, which was designed and established before the introduction of ANICT, is very much based on the input of grassroots communities to investment financing.  For these two operations, the contribution of UNDP only represents 9.5% (PACR-M) and 7.9% (PACR-T) respectively of the total cost.

ACODEP has benefited from an input (US$116,000) from the European Union though it has not on the other hand succeeded in mobilizing the external financing required for ring-fencing financing (financing gap of US$2.2 million representing 64% of the total cost…), despite approaches applied, particularly towards USAID and Belgium.  HIPC resources have covered a portion of this gap24.

Technical Partnerships

The DNCT audit involved UNCDF, SNV and PDM-Cotonou.  No follow-up to this collaboration has at present been made.

Despite contacts made, PRECAGED has not succeeded in mobilizing new partners to support the development of outlines for the planning and development of cercles and communes.  On the other hand, the project has set up two joint actions with the GTZ, firstly as part of its assistance for the preparation of the Commune IV development plan and its capitalization, then as part of organizing and financing the validation workshop relating to the study on restructuring the development planning and management system.

  - Inter-project Partnerships

These partnerships are very under-developed.  It has already been emphasized that the various UNDP projects working on decentralization do not maintain any organized cooperation.  Even information exchange and the dissemination of their respective outputs is very limited.  This impedes mutual enrichment (experience capitalization) and is also expressed by some resource wastage (methodological production tools, training materials,..).  Establishment of a decentralization work group within the country office is a relevant initiative, so long as this group functions as a network, integrating the project teams as well as other partners (MATCL management, other projects,…).  In this case is should be attached to the group that has already been set up, by a European Union initiative.

  - Relevance and Effectiveness of Established Partnerships

Effectiveness of the partnership strategy varies widely from project to project, indeed from section to section.  Various factors intervene here: technical quality of the media on which one undertakes to build the partnership, network of relationships, individual conviction capacities, specific interest in the partnership sphere of partners contacted, etc.

For UNDP the partnership has both become a new way of working and an imperative means of guaranteeing the effectiveness of its actions (critical financial mass) and their legibility.  The five projects linked to Outcome 3 have displayed a certain ambition in this area but outcomes are mitigated overall:

- Beyond the UNDP/UNCDF alliance, several financial partnerships have been implemented.  These are particularly on account of PACR-M, which benefits from even more significant capital resources than the other projects and pronounced positioning in the technical assistance mechanism for collectives (subscribing to the ANICT mechanism from its inception, full coverage of rural communes of the area).  The results of other projects in this area limited (partnership with the GTZ and the SNV).

- The search for additional financing from other partners has not had concrete results (ACODEP, section 2/PRECAGED).  According to consultation with partners, it seems that, for at least some of them, (i) outputs proposed for financing (for example the outline for the planning of cercles) are not prioritized, (ii) the partners, who are excluded from the outset until the creation of output are not inclined to see their role limited to simply that of financing.

- The most meaningful technical partnership has been accomplished within the framework of the technical assistance mechanism for territorial collectives.  In the field, UNDP shares its place with others.  Upstream, the organization is under-represented.  No partnership has been established although there are significant opportunities around designing new tools for decentralization policy: strategic planning, training policy, organization of competency transfer, local strategies of resource mobilization, sustainability of the technical assistance mechanism, consultation and experience capitalization mechanisms.

- Partnership-building is adversely affected by an inadequate communication strategy.  Consultation with partners demonstrates that UNDP projects linked to Outcome 3 are poorly understood (approaches, activities, outcomes and teams).  UNDP is also not solely at issue.  A general compartmentalization of the activities of the various partners is observed, linked both to the need for a national and regional exchange framework (particularly at the technical level) and to the donors’ own ideas, particularly concerned as they are with their own strategy and the achievement of – physical as well as financial – fixed objectives for their operations.

- The synergies reported between the various UNDP projects (Outcome 3) were not realised.  With the exception of PACR-T and PACR-M, which are run by the same UNDP-UNCDF tandem and based on close intervention strategies, projects function independent of one another and at present no mechanism enables redress of the situation.

- CONCLUSIONS

  - Changes implemented and current decentralization challenges

Progress

Decentralization work only really began in 1993 and implementation itself was only begun four years ago.  The progress made from the point of view of the outcome analyzed is remarkable.

These advances are firstly realised by means of the establishment of a new institutional framework and the phased introduction of new rules of governance enacted by decentralization laws.  Thus, all the regulatory structures have been put in place and are now operational:  the three levels of territorial collective, the High Council of Collectives, the two mechanisms (CCN/CCC network and ANICT) which are respectively responsible for technical and financial assistance for territorial collectives, with their various territorial intermediaries.  Local communities have been very deeply involved in the establishment of collectives, firstly in the very creation of new communes, then by means of local elections, which have led to some 10,000 elected councillors being introduced.  Local communities and new elected councillors thus taken over a process that is now judged to be irreversible.

Secondly, the Malian government, with the assistance of development partners, has designed and succeeded in quickly implementing a complete and relevant framework for assistance to local collectives. This accompanied a decentralized planning process over the whole area, which has resulted in production of more than 700 plans developed by the different levels of territorial collective.  Over and above this quantitative result, this process has been a first opportunity – and has been successful overall – for local communities’ involvement in communal choices.  The development plans (PDESC, Plans de Développement Économique et Social / Social and Economic Development Plans) have, in large part, been elaborated around local development priorities on the basis of broad consultation between the new elected councillors and the various communities.  Preparation and arbitration procedures have often complied with legal guidelines as regards participatory approach.  At the same time, other collectives (Cercle Councils and Regional Assemblies) were equipped with their development plans.

Many training programmes and inputs contributed by the CCC have also enabled elected councillors to tackle their preliminary responsibilities with a minimal understanding (budgeting, civil status registry, preparation and submission of the first projects to FICT,…)  There again, criteria laid down as regards  publicizing meetings (particularly), and the disclosure of policy decisions have, in the main, been complied with.  The realisation of information campaigns and specific training actions for civil society organizations has facilitated the creation of conditions favourable to good local governance.

Similarly, establishment of the ANICT marks a turning point.  First of all, because it sanctions the principle of a sustainable mechanism, based on specific budgetary allocation, for the investment of collectives; collectives are broadly represented within the mechanism.  Then, because a growing number of partners subscribe to the mechanism, which allows a more unified and equitable resource flow management, to benefit the various regions and localities to be planned for.

Limitations

The chief limitation of the process that was implemented is the slowness with which competency, resource and goods transfers operate.  From the point of view of the outcome aim of the evaluation, this issue is clearly crucial since it is by effective implementation of these transfers that the collectives will see their involvement in local management develop.  It has taken three years to produce the decrees that enable identification of competencies transferred in the three priority sectors of health, education and hydro-power.  Even for these sectors, the essential still remains to be done, that is, to specify how these transfers will operate in real terms, on what timetable, with what resources and according to what mode of cooperation between local collectives and the State services?

Thus, the government seems to be more fixed on setting up the various mechanisms requisite for ensuring the start-up of collectives, than to resolving the issues concerning the very essence of reform.  Several possible explanations have been put forward in this report:  inadequate political will in the face of the considerable resistance to decentralization that was observed; effects of the long electoral period which has broadly engaged consciousness and mobilized the Ministry for Territorial Administration and Local Collectives (Ministère de L’Administration Territoriale et des Collectivités Locales, MATCL) in particular; the need for a true national strategy of decentralization and deconcentration to serve as a framework for action by setting out a clearly-demarcated outlook in terms of priorities, steps, development, and cooperation between actors (State, territorial collectives and communities) at the level of each of the sectors; the clear lack of human resources and means, particularly at DNCT level, to take over the considerable number of actions to implement; change of decentralization policy steering.

There are other weak points concerning the assistance mechanisms, tools or approaches employed.  This is, moreover, normal at the present stage.  Among these additional limitations are:

- Development plan limitations: the report has identified flaws that are observed as much in terms of the content of plans as in the efficiency of involvement in a certain number of cases, or even in adoption of plans by all the elected councillors;

- Mitigated findings obtained in the area of local resource mobilization and the battle against fiscal “incivism”;

- Low involvement of deconcentrated technical services in the start-up of local collectives and the need for prospects for making the technical assistance mechanism sustainable;

- Inadequate involvement of women in the process and limited consideration of their needs in development plans; this is partly explained by their low representation in commune councils though also by limited integration of the gender perspective in the design and implementation of assistance; on this front, considerable differences between projects and donors are noted;

- Relative dispersal of training programmes and a certain degree of resource wastage linked to the surplus production of training materials; capacity-building needs of collectives are still vast, considering the dual perspective of re-election of elected councils (2004 local elections) and phased competency transfer to the collectives;

- Weak consultation and coordination mechanisms, which are observed at different levels.  This is firstly observed between MATCL and other government structures (State Reform, Civil Service, Land-Use Planning, Governance) working on “mainstreaming” reforms as well.  This weakness then exists between MATCL and the main sectoral departments although dialogue is here a matter of priority in deciding upon on phased methods of competency and resource transfer.  A lack of consultation between government and partners since the shelving of the decentralization “panel” has also been noted here.  Finally, in the field, cooperation between elected councillors and deconcentrated services is most often virtually non-existent;

- In a general way, the weak coordination of conceptual and operational activities linked to poverty reduction strategy (CSLP) with those activities run as part of the decentralization framework, considering the non-operation of the CNO (Conseil National d’Orientation / National Advisory Council)

Challenges

The first challenge concerns the need to prepare for the possibilities of disenchantment and movement away from a reform that may not, in the end, have met expectations.  The government must demonstrate its commitment to making decentralization policy part of a new phase.   This commitment should firstly be conveyed by taking steps to solidify effective – but phased - transfer of competencies and resources to communes, by drawing on a system of contracting.  Other priorities of this new chapter are: enhancement of development plans, sustainability of the technical assistance mechanism for collectives, and improvement of local revenues.

Moreover, at the level of the new local collectives, repeating outlines of poor governance as created by the State for a long time, should be avoided. In this regard, it is crucial to build more effective and transparent audit mechanisms for collectives.

More fundamentally, the link between decentralization and anti-poverty measures should be reinforced as much at the level of programming  (PDESC) as at the level of action (community–local collectives–NGO/association collaboration).  Impact emerges from outcome: the success of the reform must be visible in the impact that these various structures/tools will have on poverty reduction, improvement of the quality of public service provision and living conditions generally, and finally, on  the establishment of local dynamics of economic growth.  Decentralization has not yet reached this stage.

  - UNDP Contribution

General contribution to achievement of outcome

Within the Strategic Results Framework, outcome is supposed to be achieved by means of achievement of three outputs which regard elaboration of commune development plans or anti-poverty plans respectively, training of elected councillors and supervisory authority/civil society administrative officers as well as the establishment of participatory mechanisms at the expense of anti-poverty activities.

UNDP may clearly not achieve outcome but only contribute to it, as with the government, other external partners, civil society organizations and society generally.

When confined to the three outputs proposed by the SRF, it can be concluded that UNDP has fulfilled its commitments or is in the process of doing so (Anti-Poverty action plans).  Quantitative goals (targets) have most often been satisfied, indeed exceeded in the case of the PACR-M, particularly as regards training and availability of resources for financing local collectives’ investments. Although limited in financial terms, the contribution of the organization, delivered within the framework of decentralization, has been positive (if confined solely to UNDP inputs), especially when the considerable constraints that have weighed on the last programming cycle are taken into account (30% decrease in resources, organizational reform, change of management procedures, audit and “reprofiling” of the country office).

To provide a better appreciation of UNDP’s contribution this time on a qualitative front, another interpretation has been suggested.

Contribution via assistance delivered to institutions and to the Decentralization policy framework

Though UNDP was still able to play a significant part in defining Decentralization policy at the beginning of the programming cycle, it has not capitalized on the benefits of the preceding cycle. It has lost this preferential position in “soft” assistance to government, although important needs persist and the organization has clearly called for the upstream repositioning of its country offices.

UNDP has certainly lacked “proaction” in this regard but has also been hindered by major external constraints (especially resource cutbacks) and a certain loss of drive observed at governmental level, which has coincided with the disappearance of the MDRI (Mission de la Décentralisation et des Réformes Institutionelles / Mission for Decentralization and Institutional Reform).  UNDP has resumed “soft” assistance to the MATCL (Ministère de l’Administration Territoriale et des Collectivités Locales / Ministry for Territorial Administration and Local Collectives) by financing the DNCT (Direction Nationale des Collectivités Territoriales / Department of National Territorial Collectives) audit but for the moment has not capitalized on this operation.

Curiously, UNDP assistance has bypassed local collectives’ institutions, just as it has not taken advantage of these field projects to sustain regional coordination mechanisms.  However, the projects of other donors have been tested out in this area with little success.

Contribution via human capacity-building assistance to local actors

In the three intervention zones of the PACR-T, PACR-M and ACODEP projects, UNDP delivered meaningful support to the training of local actors, especially elected councillors. This support covered all the priority thematics and largely contributed to the quality of the process of commune planning, and has enabled commune councils to acquire an overall understanding of their most typical tasks.  Promising initiatives have been integrated in the development of standard modules such as the introduction of commune council self-evaluation, the establishment of pools of local trainers and the introduction of a new step built on commune supported assistance and progressive input in issues of sectoral management.

Aside from PACRT, the input to community leader training is rather limited, although it should operate in a synchronous way in order to ensure good local governance; evidently, it is difficult to train everybody, however.  The solution lies in building partnerships with other programmes that are specifically committed to strengthening the capacities of civil society.  This is also vital if improved integration of women is desired, as they are, for the most part, under-represented by the projects examined.

Contribution via assistance to the planning and budgeting process

UNDP has played a meaningful part in the commune planning process as much in terms of the number of plans supported as in methodology.  The participatory approach method has been complied with, and the exercises run have, in the main, facilitated the involvement of the two categories of actors presented in Outcome 3, that is, collectives as communities.

Besides limited consideration of women’s specific needs in the proposed plans, plan preparation has not been able to circumvent certain shortcomings (limited awareness of the resource perspective in plan development, a lack of realism in programming, the tendency to reduce commune planning solely to investment, etc).  In this regard, carrying out an assessment of anti-poverty action plan development in a few months time will be useful.

In terms of the arbitration issue, PACR-T has proposed an original and very positive approach for optimising the involvement of grassroots communities in the choice of commune development priorities.  At the level of local collective involvement, the fact that assistance has particularly been focused on the communes should be noted.

Contribution via assistance to the process of local management of development

Considering the current phase of decentralization, UNDP has particularly contributed to the process of local planning.  Its input to the development of community-based management was particularly focused on raising elected councillors’ levels of awareness – the municipal executive principally – in order that the commune councils be in a position to take over the day-to-day administrative functions of the communes (budgeting, accounting, various administrative procedures).

By ensuring compliance with guidelines in terms of the transparency of decisions, the projects have created the preliminary conditions for the progressive involvement of local communities, in the knowledge that building true local democracy will take a long time and require the lifting of structural constraints (fiscal poverty, literacy and rise in the general teaching standard, improved integration of women in political organizations, etc).

For the zone covered by the PACR-T, early availability of resources to finance priority investments has facilitated the implementation of a considerable amount of infrastructure and socio-economic systems for community use.  However, despite assistance delivered to new elected councillors in the area of project management, essential weaknesses (which concern almost all the new communes) persist.  Thus, the technical assistance mechanism should be strengthened, in order to deliver specialized assistance and in order to locate sustainable mechanisms to guarantee good project management by collectives.  The existence of clear methods for engaging the efficient transfer of competencies and resources is also dependent on continued support for communal management under the right conditions.

Contribution via assistance to resource mobilization

Besides the input in capital – which does not come from UNDP – that has been implemented at the level of the two PACR-T/PACR-M projects, and the good performance in terms of payment that has been observed, the impact of PACR-T intervention on fiscal revenue mobilization, and thus on local communities’ involvement in financing commune activities, must be emphasized.  Criteria introduced by the project, for resources access and for ascertaining the level of funding to be allocated to communes, are valuable, and have demonstrated their effectiveness; and this all the more so if one considers the context and degree of development of the Tombouctou region.  By choosing to entrust all the resources for local investment financing to ANICT, PACR-M, along with others, contributed to creating a positive public image for the agency.  The fact that PACR-T is currently at standstill over this same mechanism will have the same effect.

In the short term, subscription to the ANICT mechanism requires abandoning some of the criteria that have constituted one of the PACR-T successes.  It will be necessary to closely monitor the impact that this will have on resource mobilization.  Moreover, “fiscal incivism” is a structural issue, which in the long term, can only be addressed by changing attitudes and, particularly, by poverty reduction.  Effort committed to build resource mobilization strategies must be intensified and must principally be carried out on the basis of close collaboration between the various UNDP projects intervening within the country.  These strategies must lay emphasis on information and dialogue.

Vehicles of UNDP assistance

It has been difficult to assess the contribution of UNDP country office “soft” activities, however it seems clear that, during the cycle, these activities have only played a small part compared to the projects that continue to be essential vehicles of UNDP assistance.

Generally, the “regionalized” projects are run in a very professional way and appear more mobilizing, particularly for partnership-building.  They are also better understood.  Their impact on the involvement of local collectives and communities is direct and tangible.  This will particularly concern projects built around the UNCDF-FENU tandem, which in several regards represent successes as much at the level of quality of their outputs as at the level of their impact in terms of the social dynamic and Governance.  This is due to the quality of teams, the coherence of UNCDF-developed strategies, as well as the impact of actions proposed in this framework, which is easy to measure.  The performance of other operations is more moderate.

The ACODEP project’s less significant input can firstly be explained on financial grounds:  it has been adversely affected by the non-mobilization of expected external financing and cannot rely on investment funds.  Moreover, its strategy does not today seem an optimum one, for it combines very dissimilar activities: local governance support; development of local planning tools specific to poverty reduction; operational activities for rural youth training, and assistance to women’s savings and credit groups.

As regards PRECAGED, useful methodological challenges are raised.  However, it should be borne in mind that use of a specific project to test out various methodological tools from the “centre” is not a credible approach, especially if not locally replaced by field projects that can then provide the monitoring of the tools established. This observation particularly concerns the SADC (Outlines for the Planning and Development of Cercles), an output whose relevance is also not apparent to the mission. It is also regrettable that the output which possibly represents the most expected added value in the present context – the establishment of an outline of coherence between the various planning levels - should still not have produced results in terms of operational decisions, and that only one collaboration with “field projects” was set up.

PARCAD represents a separate case considering the diverse transformations that it has undergone.  Its integration into the new UNVP programme is a good thing so long as the UNVP intervention framework is itself reviewed.

Regarding performance of UNDP assistance, some general limitations will be emphasized:

- Lack of an overall strategy enabling rationalization of assistance proposed within the framework of the five projects examined;

- A certain discrepancy between starting intentions and actions effectively implemented which ends in somewhat inadequate results for upstream assistance (“soft” assistance);

- Continuance of a relative geographic scattering of actions, which can be challenged from the viewpoint of available resources as well as a redefined mandate for UNDP;

- The need for synergies between projects which, although they may be working on identical thematics or similar thematics do not keep up regular cooperation;

- Limited implementation by the UNDP country office of monitoring for these various projects (information distribution, information exchange between the country office and the projects,…);

- The low visibility of UNDP actions - although undeniable successes are observed - which does not promote realisation of technical and financial partnerships that have by and large been under-developed.

- RECOMMENDATIONS

  - Recommendations to Decentralization actors and partners

Develop a medium-/long- term strategy for Decentralization policy

Development of such a strategy is a response to the need to include reform activities in a comprehensive as well as medium/long term framework that may serve as a benchmark for all the actors.  Such a strategy must identify objectives and various road maps in order to achieve them, must prioritize actions and define the respective responsibilities of territorial collectives and the State in their implementation.

Its development must facilitate joint assessment of present fiindings and must enable the issues presented below to be put in perspective, particularly: competency transfer and local management of public facilities, sustainability of technical assistance for collectives, consolidation of financial assistance and local resource mobilization, relaunch of information and awareness campaigns, or even the harmonization of planning tools with the CSLP (Cadre Stratégique de Lutte Contre la Pauvreté / Strategic Framework for Poverty Reduction).

This strategy could be prepared in 2003 by an interministerial team (MATCL, Finance, Planning, State Reform, Civil Service, and the main technical departments) with the participation of collectives’ organizations.  Thematic work groups, supported by a ‘light’ technical assistance team (expert teams on site and short-term consultants) could be formed with a view to preparing a policy-making workshop.  The key development partners would be mobilized to deliver a financial (consultation) and technical (group established on the initiative of the European Union) input.

Take priority measures to guarantee acceleration of competency transfer

The government must now affirm its political engagement by means of the following measures:

- A relaunch of ministries on the proposed schedule and detailed and realistic action plans for competency and resources transfer that are up and running, beginning with implementation of the three acts adopted in June 2002, and in accordance with the legislative principle of progressiveness;

- Examination of the various plans for texts or communications that are pending (revision of the Code of Collectives, intercommunality, status of territorial collective personnel, resolution of conflicts linked to territorial division,..);

- Proposal of additional measures aiming to guarantee working conditions and adequate remuneration for the officers of collectives, commune Secretary-Generals and officials, in particular;

- Proposal of a preliminary package of restructuring measures for State representatives, in the principal areas, in order to provide improved support to deconcentrated State services and in anticipation of a more comprehensive deconcentration reform action for sectoral departments;

- Establishment of an interministerial structure around the Prime Minister, integrating HCC (Haut Conseil des Collectivités/ High Council of Collectives) and AMM (l’Association des Municipalités du Mali / Mali Municipality Association) representatives in order to steer deliberation and ensure efficient monitoring of policy responses within the framework of competency transfer;

Refine and harmonize planning tools

Proposals for planning system reform and developments in progress must from now on be capitalized upon: programme approach at the sector level, establishment of the PDESC (Plans de Développement Économique et Social / Social and Economic Development Plans) of collectives, reform of the cooperation systems of development partners (suspension of the project approach in favour of budgetary aid).  Such adaptation of the planning system could be carried out according to the following steps:

- Proposal and establishment of a participatory monitoring mechanism to implement the plans of collectives, by drawing on - for the State - the DRPS (Regional Departments of Planning and Statistics) and CCC monitoring managers recruited at region-level, and, for collectives, drawing on the regional AMM branches;

- Adoption of an integrated planning framework enabling identification of status and rules governing consistency of global (DRPS), sectoral (sectoral programmes), and regional/local (PDESC for regions, cercles and communes) programmes;

- Completion of a study on the regionalization of the CSLP (Cadre Stratégique de Lutte Contre la Pauvreté / Strategic Framework For Poverty Reduction);

- Continuance of deliberation with a view to implementing Land-Use policy;

- Evaluation of the impact of investments realised within the framework of PDESC adopted in 2001/2002;

- Revision of the tools and methodology of PDESC preparation and, once local elections have been carried out, development of 2nd generation development plans in accordance with the following principles: (i) improved understanding of the financing problematic, (ii) development of the region level for local development planning, (iii) local plans (for cercles/communes) which are not limited to public investment alone and which demonstrate priority actions for improving effectiveness of community public services and those services targeted to poverty reduction.

Consolidate the technical assistance mechanism and promote sustainable and autonomous solutions in order to meet the assistance needs of territorial collectives

In the short term, measures first of all concern strengthening CCN and CCC capacities by increasing CCN manning levels, continuing to train CCC officers, improving the CCN-CCC information cycle and improving capitalization on local practices by developing inter-CCC exchanges.

A strategy and action plans for the training of decentralization actors equally remain to be proposed.  Priorities are:

- Reducing the resource wastage that has been observed (proliferation of superfluous tools/materials, the need for coordination between the actions financed by various projects, etc) resulting in the harmonization of procedures manuals and training materials;

- Development of new modules as part of specific training plans at the level of each cercle and integrating elected councillors, commune/cercle officers, representatives of deconcentrated services and operating service providers of services for the collectives;

- Setting up a pre-implementation approval system for training programmes and service-provider quality control by the DNCT;

- Consolidation of local service provider networks;

- Unification and improved use of training impact evaluation systems;

- Development of thematics linked to the delivery of core public services;

Finally, deliberation on the proposal of a sustainable mechanism of assistance for collectives is necessary, as part of overall decentralization strategy development, considering the vast need that remains to be met, the prospect of the imminent arrival of new elected councillors and the transitory nature of the current CCC mechanism.  The aim is to evolve towards a less project-dependent mechanism based, as per the ANICT model, on budgetary financing, supporting significant deconcentrated technical services involvement, and built around contractual formulas.

Enhance financial resource mobilization for collectives and optimise exploitation

A resource mobilization strategy is to be built around the following elements:

- Improvement of the decentralized planning process (consideration of financing issues during plan preparation and not afterwards);

- Adjustment of the resource allocation mechanisms of large sectoral programmes (PRODESS, PRODEC,…) in view of the prerogatives of collectives;

- Revision of criteria of financial resource allocation to collectives (use of contingency systems, eligible projects, improved awareness of vulnerable groups including women) and standardization of contribution rates (ANICT, other funds/projects);

- Proposal of more efficient mechanisms of recovery, and enhancement of information and awareness actions for local communities and elected councillors on the issue;

- Development of intercommunality to build the critical mass of internal resources and rationalize financing requests;

- Creation of an information system enabling centralisation of local taxation data and regular evaluation of the performance and impact of local collection systems (taxation, levies from public services).

Develop consultative and monitoring-evaluation mechanisms

Recommendations relate to the following:

- Establishment of regular liaison between government and development partners (revival of the panel);

- Improvement, within MATCL, of the internal monitoring system for projects under administrative supervision;

- Delineation of a precise statement of work for coordinating development actions at the region level (Haut Commissaire);

- Implementation of the CCC/DNCT information system (OISE database) and establishment, by stages, of consolidated management charts on the project indicators and the two assistance mechanisms;

- Creation of working areas/mechanism for information exchange and capitalization on local governance experience, at the regional and national level.

  - Recommendations to UNDP

In regard to context, the country’s needs and results already obtained, inserting Outcome 3 (“involvement of communities and local authorities in development planning and management”) into the Strategic Results Framework 2003-2007 is wholly justified.  The challenge for UNDP is a three-pronged one.

Conformity with its mandate of repositioning “soft” assistance upstream is the first thing.  In order to be effective, it should (i) concentrate on a limited number of thematics, (ii) enter into substantive partnership with the main donors who today support the mechanisms of technical and financial assistance, particularly the European Union, (iii) ensure that this “soft” assistance is centred on the proposal of solutions effectively contributing to outcome, that is, improving the participatory mechanisms of collectives and communities.  In this sense, standard institutional assistance actions or targeted appraisals that are not directly linked to this problematic should be avoided.

The second challenge is connected with the development of assistance delivered in field. UNDP should firstly propose substantive solutions to the often-mentioned synergy between upstream and downstream projects, where a certain commonality of action themes between field projects in progress and the new “soft” assistance activities to be implemented occurs.  It also requires a framework of common collaboration and a network working method between the various project units, the UNDP country office and other selected resources.

The third challenge regards reduction of the geographic scope of intervention for UNDP projects as well as the preparation and implementation of consecutive disengagement strategies.  UNDP must closely consult with UNCDF to ascertain a medium term agenda, and begin with the PACR-T, conclusion of which is expected approximately two years from now.

In terms of operation and management of the country office, recommendations are part of the following policy framework:

- Amendment of the programming framework

  - Repositioning government ‘soft’ assistance by the establishment of a new five-year assistance programme

  - Revision of objectives and inputs of projects based on the UNDP/UNCDF partnership (Tombouctou and Mopti)

  - Rebuilding the logical planning framework of the UNV/PARCAD Programme

  - Refocusing the actions of the ACODEP project on Outcome 3 (short-term) and preparation of a disengagement strategy for its intervention zones (medium-term)

  - Focusing PRECAGED on assistance in CSLP (Strategic Framework for Poverty Reduction) implementation and on Millennium Development Goals monitoring.

- Enhancement of strategic management linked to Outcome 3

  - Developing monitoring and evaluation and reporting tools

  - Establishment of an SNU platform for capitalization on project findings within the framework of achieving of Outcome 3

  - Improving communication on outcomes

Repositioning government “soft” assistance by establishment of a new assistance programme

Considering the ‘coup partis’ that projects in progress represent, development of a new assistance programme to serve as a ‘vehicle’ in repositioning UNDP intervention upstream is recommended.  Tied to the duration of the SRF and linked to Outcome 3 in a one-to-one way, this programme would be implemented over a five-year period, including preparatory assistance to implement from 2003 onwards.

The preparatory phase will promote intensified deliberation on UNDP intervention gaps with the government (particularly MATCL and DNCT Offices), the HCC, the AMM, as well as the principal development partners supporting the assistance mechanisms for collectives (European Union, France, Germany, the Netherlands, Switzerland).  It would also give rise to consultation at regional level with the Hauts Commissaires of the current intervention zones and Presidents of Regional Assemblies.   This period will enable UNDP to build technical exchange with the various partners, while facilitating the execution of intervention strategy at country office level.

The suggested approach should (i) draw lessons from past experience (incomplete National Programme and non-convened Round Table), (ii) be practical and targeted (thematics), (iii) be negotiated with partners already providing MATCL with institutional assistance and take account of the ‘lead’ position that the European Union maintains in the sector, (iv) demonstrate the central responsibility of the State in steering reform while making itself available to institutions or organizations representing the collectives.

The programme could centre on the following focal points:

- Strategic planning of reform;

- Institutional support for MATCL (Office and DNCT) and, should the occasion arise, for an inter-ministerial structure responsible for coordinating actions linked to decentralization and deconcentration;

- Consolidation of communal planning tools;

- Regional assistance strategy.

The first focal point refers to decentralization strategy development, presented above.

Institutional assistance would essentially be demonstrated by:

- Assistance in reorganizing the DNCT (implementation of audit recommendations completed in 2002);

- Possible assistance in the implementation of an inter-ministerial structure for decentralization coordination;

- Management training actions (improvement of selected technical themes, information and exchange on experience garnered in other countries, workshops promoting concept-sharing and tool-sharing between MATCL and the various sectoral departments);

- Selective studies carried out on priority themes of decentralization policy relating to Outcome 3.

Of the themes likely to be covered by UNDP assistance, could be selected:

- Appraisal of the methods of possible contracting between territorial collectives, deconcentrated services and other operators (private sector, NGO, community organizations);

- Development of the monitoring and evaluation of local collectives’ resources;

- Improvement and harmonization of criteria for access to resources;

- Training strategy (emphasis on preparing actions for future elected councillors of 2004 as well as on harmonization of materials used since 2000);

- Improved integration of women in processes linked to decentralization.

As regards enhancement of communal planning tools, actions could relate to:

- Proposal of a participatory monitoring system for communal development;

- Continuance of deliberation on the consistency of planning tools in order to bring about an integrated planning framework;

- Impact evaluation of investment realised as part of the PDESC;

- Adaptation of preparatory tools and methodologies for the PDESC with a view to developing 2nd generation plans (see above).

The fourth focal point – Regional assistance strategy – would aim to emphasise this currently neglected level although it has lead to a strategic role in planning and coordination of development actions.  It would comprise two sections:  (i) assistance in defining coordination mechanisms and procedures, (ii) assistance in developing regional anti-poverty plans to regionalize the CSLP by capitalizing on experience acquired elsewhere.

UNDP should be conscientious in targeting national partnerships in order to avoid a disadvantageous dispersal of assistance between all the stakeholders.

Repositioning actions relating to projects in progress

Proposed repositioning takes four principles into account:

- Additional reduction in the scope of geographic intervention involving partial future disengagement of certain zones;

- Repositioning of projects on a single outcome of the Strategic Results Framework;

- Thematic concentration of field activities;

- Development of inter-project synergies.

Projects built on the basis of the UNDP/UNCDF partnership (PACR-Tombouctou and PACR-Mopti) should not, considering the observations of the various evaluations, give rise to appreciable modifications.  Besides establishment of systematic information-sharing between the two project teams within the framework of the network to be built (cf. below), it is suggested that emphasis be placed upon:

- Improvement of the planning perspective by use of, among others, a tool of standardized participatory appraisal and taking into consideration all the actors including the sectoral departments; this tool would benefit from PACR-T experience but also from other experiences and would be in a position to correct problems presented above about the first PDESC;

- Delving into issues linked to fiscal incivism, upscaling strategies for fiscal revenue mobilization;

- Conduct of specific actions enabling increased involvement of women in commune activity;

- Systemization of the self-evaluation practice – which was introduced by the PACR-T – in all the communes supported by UNDP;

- Development of contracting between collectives, deconcentrated services and management community structures (ASACO, Association de Santé Communautaire / Community Health Association,…) for the management of core services; and organization of a quality control mechanism for these services integrating the various commune, cercle and region levels;

- Enhancement of communication activities (optimal use of community radio) and use of the NICT by proposing to test out the “cybercommune”concept whose importance was demonstrated in Mauritania for example;

- Assistance to efficient implementation of policy advice and consultation frameworks, particularly to the CRO (Comités Régionaux d’Orientation / Regional Advisory Committees).

The UNV Programme must be entirely re-evaluated before an effective shift into the operational phase.  The intervention-planning framework should first be redeveloped and a real action strategy, taking into account changes that have occurred since initial development, should be proposed.  This exercise must be carried out in close collaboration with the principal national partners (MATCL Office, DNCT, ANICT, representatives of the State and territorial collectives of the Tombouctou and Mopti regions,…), the PACRT, PACRM, and ACODEP projects as well as UNDP Programme Management.

The Programme should, at the end of this exercise, establish partnership agreements that enable optimised use of inputs of available voluntary expertise.  A degree of flexibility in allocations should, however, be facilitated in order to safeguard the possibility of using some volunteers in the Five-Year Programme framework presented above.  Such volunteers could play a significant role in the coordination of upstream and downstream activities.

The ACODEP Project should be continued to its conclusion by repositioning its action within the framework of a technical partnership with other projects of its intervention zone.  Experience from anti-poverty action plans should be evaluated beforehand.  The first option would entail falling into line on the themes specified in regard to PACRT/PACRM, and integrating into the exchange platform proposed (cf. below).  The second option would be to facilitate regional anchorage by developing collaboration with the SNV (and if need be the GTZ) within the Koulikoro region.  This would mean prioritizing both project management capacity-building actions and actions to strengthen operational collaboration between the collectives and the State services in the various cercles, with the aid of the CCC.  It is also recommended that a short-term disengagement strategy for activities not directly linked to Outcome 3 should be proposed for this project in the short term.

Finally, PRECAGED should, apart from finalising activities undertaken with regard to the coherence of the various planning levels, concentrate on activities linked to CSLP implementation, particularly the monitoring & evaluation of poverty and Millenium Development Goals monitoring.

Strengthening actions for strategic management linked to Outcome 3

The first section concerns development of monitoring & evaluation and reporting tools (see specific annex paper).

The second section focuses on capitalization on results.  Establishment of an SNU “platform” for capitalization on experience within the framework of achieving Outcome 3, is proposed.  This platform could be set up by stages starting with the UNDP-Mali country office – Projects – SURF (Sub-Regional Resource Facility) alliance then integrating other participants (2-3 country offices of the sub-region, operators of other agencies of United Nations system.

The platform would aim at establishing an inter-project technical partnership and, thus, at supporting monitoring and capitalization on results.  It would take on the functions of (i) collection and dissemination of information, (ii) management of thematic deliberations linked to decentralization-related SNU project actions, (iii) organizing exchange with project teams and beneficiaries (field visits), as well as, (iv) quality control and development of appraisal reports produced within the framework of each of the projects.

The mission equally recommends stronger relations between the Programme Management, the Governance Unit and the project teams.  Thus (i) establishment of an annual Assessment and Capitalization themed meeting between all the participants linked to Outcome 3 (in preparation for an assessment workshop proposed below), and (ii) organization of quarterly meetings between the Programme Management, the Programme Analysts, and Project Coordination, are suggested.

The third section is closely linked to the preceding one and aims at improving communication of the UNDP-Mali Country office on activities and results linked to Outcome 3.

Effort already led to enhance communication on UNDP programmes and activities and to make its interventions more visible should be continued.  Activities relating to Outcome 3 could here be the subject of (pilot) activities centred on:

- Establishment and management of mailing lists, in collaboration with projects and the Decentralization platform, to enable notification of data updates and new information resources);

- Upgrading the website with all core information for projects (review of current project profile along with regular updates or links to project sites);

- Improving rapid access to complete project data (programming, physical monitoring and financial tracking, documentary inventory of projects, download of project documents, activity reports, case studies);

- Implementation of annual assessment workshops.

1Outcome is defined as the intermediary result between output and the impact.  The results chain is thus: Inputs (experts, equipment, financial resources…)  Outputs (studies completed, people trained,…)  Outcome (revenue built up, employment created,…)  Impact (improved living conditions, increased involvement of local communities,…)

2 The most significant attempt concerns the 1977 reform, conveyed by the establishment of regional, and local development committees who would integrate decentralized services and local communities.

3 The Decentralization Mission, appointed in 1993, had its scope of activities extended to include institutional reform in 1997, at which time it was renamed the Mission for Decentralization and Institutional Reform (Mission de la Décentralisation et des Réformes Institutionelles, MDRI).

4 These are (i) the Health and Social Development Programme /Programme de Développement Sanitaire et Social (PRODESS 1998-2002), the first five-year segment of the Ten-Year Health and Social Development Plan / Plan Décennal de Développement Sanitaire et Social  (PDDS 1997-2007), (ii) the Ten-Year Education Development Programme / Programme Décennal de Développement de l’Education (PRODEC 2000-2010), (iii) National Environmental Action Programme / Programme National d’Action Environnemental (PNAE 1997-2007), (iv) Judicial Development Programme / Programme de Développement de la Justice (PRODEJ 2000-2010), and the (v) Master Plan for the Rural Development Sector /Schéma Directeur du secteur de Développement Rural (SDDR, updated in 2001)

5  For the SRF, achievement of Outcome 3 is reliant on 3 outputs: (i) elaboration of development plans and anti-poverty action plans; (ii) consecutive mobilization of communities within the framework of the preparation of the first commune development plans); (iii) the establishment of participatory mechanisms at the expense of Anti-Poverty activities.

6 Of the 12 members of the Agency’s Executive Board, 7 are representatives of territorial collectives

7 The last Journée was staged in December 2002, presided over by the Head of State.

8 See annex 7 for detailed information on the assistance delivered by the key development partners.

9 During the 1st half-year, 2003, the DNCT has expected to complete missions throughout all the regions in order to evaluate the current capacities of the communes, with the prospect of elaborating a training strategy.

10 Whilst provision was made for progressive growth in staff size, the number of posts allocated has not changed since 2000, and currently surveys record 27 agents for 42 posts budgeted for.  Outside of this under-staffing, the DNCT suffers from a shortage of specialised profiles (80% of civil administrators).

11 Amendment of the Code was sidelined in 2001/2002 for various reasons (electoral context, complexity, local risks linked to issues of division).  The dossier is still at the level of Secretary General of Government.

12 Decrees no. 2-213, 2-214 and 2-215/P-RM of 4 June 2002

13 Source: Prodoc ACODEP, 2001

14 Figures taken from the CCN assessment at 31/12/02 (provisional report)

15 By way of illustration, the Sangha commune, which was visited by the mission, has a development plan comprising of 25 specific objectives, about 50 priority activities which are not sufficiently clear, and which portrays a financing need of CFAF600 million, unrelated to resource mobilization capacities (initial drawing rights, which are granted by ANICT to the commune over 3 years, total CFAF46.7 million, less than 8% of the cost of the 3-year plan).

16 For example, according to the data of the Bandiagara CCC, 16 out of the 17 commune projects submitted for FICT financing to date, concern the construction of town halls…

17 In the field, the mission has observed some cases of investment briefs which despite being ineligible for ANICT financing have passed the approval stages at CLO level and the regional ANICT branch level

18 For 2000, the rate of collection of the TDRL was around 66%.  More recent data is not available  (use of commune management accounts for the 2001 financial year has not yet begun).  In the communes visited, a very significant drop in revenues from local taxation between 2000 and 2002 was generally observed.

19 There are only 13 women in the National Assembly of a total of 147 representatives (less than 9%).

20 This would require a nomenclature and a common accounting method for all projects (accounting by trainees/themes, trainees/category, trainees/sex, people /day).

21 cf. Project Self-Evaluation Report, 2002

22 For communes assisted by the PACRT, it has thus been observed that despite a significant female presence (33%) in the general assemblies for project ideas identification, projects related to women included in the PDESC represent less than 5% of scheduled investments.

23 PACR-T has initially been implemented under Ministry of Planning supervision.  Its institutional anchorage has changed in the process, MATCL providing supervision at national level whilst the Regional Planning and Statistics Department  (DRPS – Direction Régionale du Plan et de la Statistique) of Tombouctou has remained the governmental frame of reference at regional level (the regional steering committee is chaired by the Haut Commissaire).  As to PACR-M, it should be noted that the Project Coordination Unit (Cellule de Coordination de Projet), which should be reattached to the DRPS has, in practice, moved its anchoring to the Haut Commissariat level, which responds better to a regionalized shift of the project.

24 CFAF240 million for 2001 and CFAF432 million for 2002.