Mid-Term Evaluation of Capacity Building Programme for the Government of Ethiopia to comply with Paris Agreement and its Transparency requirements

United Nations Development Programme, Ethiopia

FINAL REPORT

August, 2023

Abhijit Bhattacharjee

Acknowledgement

The Review Consultant is grateful to a number of people who participated in the mid-term review of the Capacity Building Initiative for Transparency (CBIT) project, managed by the UNDP country office in Ethiopia. Special thanks are due to Getnet Abate, CBIT Project Manager, for providing overall support to the review process. He went out of his way to arrange meetings and interviews, besides providing relevant data and documents during the entire review process.

I thank officials of the Environmental Protection Authority of the Federal Government of Ethiopia and several their Ministries who gave their valuable time for interviews and participated in this MTR.

My deepest gratitude to all.

Abhijit Bhattacharjee

31 March 2023

| Summary Table |  |
| --- | --- |
| Agency Name | United Nations Development Programme (UNDP), Ethiopia |
| Partners | Environmental Protection Authority, Ministry of Planning and Development, Government of Ethiopia |
| Location | Ethiopia |
| Project budget | US$ 1,358,000 |
| Project Start Date | 01 November 2019 (Inception: October 2020) |
| Project End Date | August 31, 2023 |
| Donor | Global Environment Facility (GEF), UNDP and Government Ethiopia |
| Evaluation Commissioner | UNDP Ethiopia |
| Evaluation Manager | Berhanu Alemu – M&E Specialist |
| Evaluation Type | Country level project evaluation |
| Evaluation Dates | January- August 2023 |

Disclaimer: The views expressed in this report are those of the authors and may not necessarily represent the views of UNDP or its partner agencies in Ethiopia.

# Abbreviations

CBIT		Capacity Building Initiative for Transparency

CO		Country Office

ENDC		Ethiopia Nationally Determined Contribution

EPA		Environmental Protection Authority

ETB		Ethiopian Birr (US$1=ETB54, as on 13 February, 2023)

EU		European Union

FAO		Food and Agriculture Organisation

FGD		Focus Group Discussion

GEF		Global Environment Facility

GHG		Greenhouse Gas

GoE		Government of Ethiopia

ICAT		Initiative on Climate Action and Transparency

IPCC		Intergovernmental Panel on Climate Change

IPPU		Industrial Processes and Product Use

JC		Judgment Criteria

KII		Key Informant Interview

MoA		Ministry of Agriculture

MoF		Ministry of Finance

MoI		Ministry of Industry

MoPD		Ministry of Planning and Development

MoT		Ministry of Transport

MoWE		Ministry of Water and Energy

MRV		Measurement, Reporting and Verification

MTR		Midterm Review

NAP		National Adaptation Plan

NDC 		Nationally Determined Contribution

PMU		Project Management Unit

POPP		Programme and Operations Policies and Procedures

Prodoc		Project Document

REDD		Reducing Emission due to Deforestation and Forest Degradation

RQ		Review Question

RTA		Regional Technical Adviser

SDG		Sustainable Development Goal

SRPC		Green Sector Reform Project Contract

TASCA		Tracking and Strengthening Climate Action

TACCC		Transparency Completeness Consistency Comparability Accuracy

TOC		Theory of Change

ToR		Terms of Reference

UNDP		United Nations Development Programme

UNFCCC	United National Framework Convention on Climate Change

Table of content

Executive Summary	x

1.	INTRODUCTION, SCOPE AND METHODOLOGY OF THE EVALUATION	1

1.1	Introduction	1

1.2	Purpose, scope and objectives of the MTR	1

1.3 	The MTR criteria, cross-cutting issues and questions	2

1.4 	Review approach and methodology	3

1.4.1 Key stakeholders…………………………………………………………………………………………………..……..................3

1.4.2 Organisation of the evaluation and declaration of conflict of interes…………………………………………..4

1.4.3 MTR approach and data collection methods………………………………………………………………………………..4

1.5 	Data protection protocol and evaluation ethics	5

1.6 	Quality assurance	5

1.7	Limitations	6

2. 	PROJECT DESCRIPTION AND BACKGROUND CONTEXT 	7

2.1	Project context	7

2.2 	The problems addressed by the project	7

2.3 	Key partners	9

2.4	Project implementation arrangements, management and finance	9

2.5 	Project timing and milestones	10

3. 	FINDINGS OF THE REVIEW	13

3.1	Project strategy	13

3.1.1 National priorities and development needs………………………………………………………………………………..13

3.1.2 Project design…………………………………………………………………………………………………… ……………………….14

3.1.3 Results framework………………………………………………………………………………………………………………………16

3.1.4 Gender sensitivity……………………………………………………………………………………………………………………….19

3.2	Progress towards results……………………………………………………………………………………………………….19

3.2.1 Institutional capacity for transparency………………………………………………………………………………………..19

3.2.2 GHG inventory and functional database system………………………………………………………………………….20

3.2.3 Strengthened technical capacity…………………………………………………………………………………………………23

3.2.4 Overall summary of progress and results……………………………………………………………………………………24

3.2.5 Factors affecting results – partnership and synergy…………………………………………………… ……………..31

3.3	Project implementation and adaptive management……………………………………………………………31

3.3.1 Management arrangements……………………………………………………………………………………………..31

3.3.2 Project monitoring and evaluation…………………………………………………………………………………..33

3.3.3 Adaptive management…………………………………………………………………………………………………….33

3.3.4 Communication and dissemination………………………………………………………………………………….34

3.4	Sustainability	34

4. 	CONCLUSIONS, LESSONS AND RECOMMENDATIONS	36

ANNEXES	38

Annex 1: CONSULTANT TERMS OF REFERENCE GENERAL INFORMATION	38

Annex 2: CBIT MTR Evaluation  Matrix	56

Annex 3 – List of key documents consulted	60

Annex 4: List of Key Informant Interviews	62

Annex 5: MTR Consultant Itinerary	63

Annex 6 – Interview Guide	64

Annex 7 - Rating scale used	68

Annex 8: Co-financing Table for UNDP Supported GEF Finnanced Projects	69

Annex 9: UNEG Code of Conduct for Evaluators/Midterm Review Consultants……………………………………70

Annex 10: MTR Report Clearance Form	71

Annex 11: Details of Training provided	72

TABLES AND FIGURES

Table 1: Financing plan - CBIT project…………………………………………………………………………………………..10

Table 2: CBIT project expenditure 2020-2022………………….……………………………………………………………12

Table 3: CBIT project objective and indicators………………………………………………………………………………17

Table 4: Overall results achieved against the results framework…………………………………………………...26

Table 5: Annual Workplan budget and Actual expenditure (US$)…………………………………………………33

Figure 1: Schematic diagram showing organisation of GHG data collection and flow………………….10

# Executive Summary

# Project Information Table

| Project Title | Capacity-building programme to comply with the Paris Agreement and implement its transparency requirements at the national level |  |  |
| --- | --- | --- | --- |
| UNDP Project ID (PIMS #): | 6208 | PIF Approval Date: | 29 August 2019 |
| GEF Project ID (PMIS #): | 9967 | CEO Endorsement Date: | 1 November 2019 |
| Country(ies): | Ethiopia | ProDoc Signature Date: | 2 December 2019 |
| Region: | Africa | Date project manager hired: | 22 July 2020 |
| Focal Area: | Climate change adaptation | Inception Workshop date: | 27 October 2020 |
| GEF Focal Area Strategic Objective: |  | Midterm Review Date: | March 31, 2023 |
| Trust Fund: |  | Planned closing date: | 5 August 2023 |
| Executing Agency/ Implementing Partner | Ministry of Environment, Forest Commission for Climate Change |  |  |
| Other execution partners: |  |  |  |
| Project Financing | at CEO endorsement (US$) | at Midterm Review (US$) |  |
| [1] GEF financing: | 1,166,000 | 830,192 |  |
| [2] UNDP contribution: | 50,000 | 38,000 |  |
| [3] Government: | 142,000 | 103,000 |  |
| [4] Other partners: | 0 | 0 |  |
| [5] Total co-financing [2 + 3+ 4]: | 192,000 | 141,000 |  |
| PROJECT TOTAL COSTS [1 + 5] | 1,358,000 | 971,192 |  |

# Introduction and project description

The United Nations Development Programme (UNDP) in Ethiopia commissioned a mid-term review (MTR) of the project ‘Capacity-building programme to comply with the Paris Agreement and implement its transparency requirements at the national level’ (PIMS# 6208), implemented through the Environmental Protection Authority (EPA) of Government of Ethiopia (GoE). Funded by Global Environment Facility (GEF) grant, with co-financing from the GoE and UNDP, the project aims to develop GoE’s capacity for scientifically monitoring, measuring and reporting on the greenhouse gas (GHG) emissions and withdrawals. The United Nations Framework Convention for Climate Change (UNFCCC) of which Ethiopia is a signatory requires countries to adhere to the principle of measurement, reporting and verification (MRV) in the context of enhancing action at the national level to mitigate climate change.

The Paris Agreement calls for Transparency in reporting for the GHG emissions to track both the emissions and the efforts given to the developing countries. Whilst the country is committed to global efforts of reducing GHG emissions through its Climate Resilient Green Economy, the country lacked proper technical and institutional capacity to adhere to the Paris Agreement Frameworks. The project sought to close the existing technical and institutional capacity challenges by enhancing institutional and technical capacity related to climate transparency in Ethiopia. This was to be achieved by strengthening institutional and technical capacity for transparency through training and development of guidelines. The project started in December 2019 and is due to end at the end of September 2023. Out of a total budget of US$ 1.35 million (including co-financing), an amount of US$ 971,000 has been utilised by the end of December 2022. The project focused on two outcomes, namely: (a) institutional capacity development, and (b) technical capacity development tools, training and assistance.

# The MTR purpose, scope and criteria

- The purpose of the MTR was to assess the overall performance of the project on the basis of impartial and independent evidence to assist UNDP and implementing partner (EPA) to identify the results achieved, the key gaps and challenges. The MTR assesses early signs of project success or failure and identifies necessary corrective actions to achieve the project’s intended objectives. The MTR covers all activities planned and/or implemented during the period 2020-2022 and focuses particularly on: (a) project strategy, (b) progress towards results, (c) project implementation and adaptive management, and (d) sustainability issues. The geographical scope covers the entire country, both at the national and sub-national levels. During the inception phase, review questions based on the four criteria were agreed with UNDP. The primary audience of the MTR are the UNDP Ethiopia country office (CO), UNDP Africa Bureau, Government stakeholders at national and sub-national levels and GEF.

# Review approach and method

A stakeholder analysis during the inception stage showed that the primary stakeholders were UNDP CO, EPA which is the implementing agency, and the Project Steering Committee which is responsible for approval of project plans and revisions, and ensuring oversight of project implementation. The MTR was commissioned and managed by the UNDP country office. An external independent consultant was contracted to conduct the MTR.

The MTR used mixed methods combining key informant interviews (KII) and desk review of key documents so as to enable the review consultant to triangulate information and perspectives from multiple sources through both quantitative and qualitative data. The documents review included the baseline GEF focal area Tracking Tool (TT) submitted to the GEF at CEO endorsement and the midterm GEF focal area Tracking Tool. The key informants were selected based on a stakeholder analysis and an informed judgement of their involvement and familiarity with the project, directly or indirectly. Content analysis was performed on both the primary and secondary data following an essentially interpretative approach, classifying findings in view of providing concrete suggestions and recommendations. In line with UNDP-GEF evaluation guidelines, the MTR has provided ratings for: (a) results achieved, (b) implementation and adaptive management, and (c) sustainability on a 6-point scale for the first two and a 4-point scale for sustainability.

# Main findings of the MTR

## Project progress summary

At the start of the project (baseline), the EPA did not have a well-established GHG inventory and database and information system which met the UNFCCC requirement. Capacity was also lacking for the generation, archiving, analysis and sharing of quality GHG emission information and data for the formulation of BURs and NCs. The MTR findings show that good progress has been, or is being, made on all of these, though some of these will require more efforts in the remaining period of the project to achieve satisfactory results at the terminal evaluation. A GHG inventory database system has been developed and is in the process of being operationalised following a trial phase. Specialised technical training on IPCC 2006 software has been provided to nearly 600 climate change experts at the federal and regional/zonal/woreda levels. A guideline document to help different sectors prepare detailed MRV framework and implementation plan has been developed and disseminated, with some ministries already beginning to develop their respective plans. The project has been putting in place a credible QA/QC system to validate all GHG data for MRV purposes; significant progress in this regard has been made particularly in the forest sector, while work is in progress in other sectors.

## Project strategy and design

The project was designed to address the challenges Ethiopia faced in meeting its Nationally Determined Contribution (NDC) obligation and reporting to the UNFCCC, and was in line with UNDP’s country programme outcome 3 which relates to Ethiopia becoming resilient to environmental risks and adapting to climate change. The project design was based on an analysis of critical capacity weaknesses in relation to the country’s ability to measure, track and communicate its carbon emission/sink and plan its mitigation and adaptation strategies effectively as per the UNFCCC requirement. The project’s theory of change (TOC) is validated by the results in that continuous engagement and training provided is enabling key ministries in the government to implement various activities in relation to the MRV system. While the project undertakes regular consultation with key stakeholders, and a number of stakeholders were consulted during the design process, certain critical engagement with a few ongoing or emerging initiatives were missed; these could have further enriched the project’s scope and focus.

## Progress towards results - Rating: ‘Satisfactory’ on four outputs and ‘Mostly Satisfactory’ on four outputs

### Institutional capacity for transparency

The project’s steering committee involving all key ministries works at technical level to coordinate the project’s activities across the ministries. An inter-ministerial CRGE body chaired by the Minister for Planning and Development which already exists may be the best forum to take forward the MRV issues at ministerial level in future, instead of aiming to set up another permanent inter-ministerial body which was envisaged in the Project document.

### GHG inventory and functional database system

A GHG inventory database system has been developed in partnership with a European Union (EU) project and is in the process of being operationalised following a trial phase. Once completed, the database will be formally handed over to the EPA for which ICT and MRV Directorate staff have been trained at the federal level through the CBIT project. Several sectors have made progress in establishing baseline inventories, while in a few sectors this is still work-in-progress. Among various sectors/ministries, the forest and waste sub-sectors were seen to have a better system and capacity in managing the GHG inventory within their remits as well as the data management system. The consolidated data on emissions reported by EPA sometimes lacks consistency over the years.

- Strengthened technical capacity

The most significant achievement on technical capacity has been the specialised training provided to nearly 600 climate change experts. The in-depth nature of technical training on the IPCC 2006 software provided is considered by stakeholders as the most important contribution of this project as the training covered federal staff, as well as experts in the regions, zones and woredas. A guideline document to help different sectors prepare detailed MRV framework and implementation plan has been developed and disseminated, with some ministries already beginning to develop their respective plans. The development of guidelines for budgeting and monitoring of expenditure linked to GHG emissions/withdrawals is now beginning to happen. The project has been putting in place a credible Quality Assurance/Control (QA/QC) system to validate all GHG data for MRV purposes; significant progress in this regard has been made particularly in the forest sector, while in other sectors work is in progress.

## Project implementation and adaptive management - Rating: Satisfactory

The project has taken into account a number of changes and new needs in the course of project implementation; the management arrangements have been efficient. The Covid-19 pandemic delayed start of the project, but thereafter the project managed to speed up implementation. The first was in defining its role in relation to a European Union (EU) project as potential overlaps between the two projects came to notice at the inception phase of the CBIT. Overall, the project has been cost-effective, considering the unique role it is playing in taking the MRV system to the level of woredas, zones and regions on the one hand, and enabling an integrated system at the federal level, on the other. There is a robust financial management system in place and by the end of December 2022, the project had utilised nearly 72 per cent of its original budget, meaning that it still has about 28 per cent of funds to be utilised in the remaining period.

## Sustainability - Rating: Likely

With strong ownership demonstrated by the government, the project outcomes are likely to be financially sustainable in medium to long term. The project plays a catalytic role in the country’s effort to establish a credible and verifiable MRV system. In this regard, the entire administrative and management apparatus is owned and already supported by the government from its own resources. Policies, legal and regulatory frameworks underpinning this project are all conducive to sustaining the benefits even after the project ends.

# MTR Ratings & Achievement Summary Table

(Yellow highlighted indicates the output is on track to achieve results by the end of the project; Green highlighted indicates that results have already been achieved; and Red highlighted indicates that the output is not on target to achieve intended results).

| Measure | MTR rating | Achievement |
| --- | --- | --- |
| Project strategy | NA | The project was designed to meet a critical gap in Ethiopia’s ability to deliver on its NDC commitments in a credible and transparent way, and ensured that there was a whole-of-government approach in addressing the capacity gap. |
| Progress towards results | Objective: To enhance institutional and technical capacity related to climate transparency in Ethiopia. Mostly Satisfactory | Good progress made in terms of enabling EPA to provide leadership on MRV and providing training and guidance to various ministries. |
| Outcomes | Outcome 1: Strengthened institutional capacity for transparency-related activities Satisfactory | 8 line ministries are fully conversant with their roles and tasks on MRV, and other ministries are beginning to work on it. A steering committee has been functioning well, though with a more limited remit than what a ministerial group could have provided leadership on. The GHG inventory database has been developed and is on trial now. |
|  | Outcome 2: Strengthened technical capacity for transparency-related activities, including tracking of progress towards attaining ENDC Satisfactory | Model guideline to track and report on NDC implementation developed and disseminated; some ministries have begun to adapt this model to their sector-specific guidelines while others lag behind. Significant progress made on training of GoE staff on IPC guidelines, exceeding the target, and quality assurance mechanisms are now being put in place, with support from national Universities. |
| Project implementat-ion and adaptive management | Satisfactory | The project is implemented under the national implementation modality, with close working relationship established between UNDP and the Environmental Protection Authority which is the implementing partner, enabling good two-way communication and smooth operational decision-making. The project’s annual planning, budgeting and financial controls follow standard UNDP procedures, with annual audit of accounts undertaken each year. The finance officer of the project works closely with UNDP’s finance department and ensures compliance with required procedures, and risks are well-manged. The Annual Plans show realistic budget allocations and adjustments made during the year, with small acceptable variations between the planned budget and actual expenditure. |
| Sustainability | Likely | The project outcomes are likely to be sustainable, given the strong ownership, financial commitment and regulatory environment set up by the government. |

# Overall conclusion

Ethiopia has set before itself a challenging goal of building a climate resilient net-zero emission economy by 2030, for which it has promulgated a slew of policy measures and regulatory frameworks. However, the country was hamstrung in developing national plans and strategies in accordance with its climate resilience strategy by lack of reliable GHG data. The CBIT project is addressing this gap which should enable the country to deliver on its NDC commitments in a credible and transparent way. The project has galvanised strong partnership with key institutions and achieved significant results, though some of the results were affected by reorganisation within various ministries of the government that weakened the manpower capacity dedicated to MRV and climate change related issues. The project facilitated technical inter-sectoral coordination through a steering committee set up with officials from key ministries. Moving forward, there is scope to leverage an already-existing inter-ministerial forum involving EPA on CRGE to provide leadership across the government to strengthen the MRV regime.

The project is rated ‘mostly satisfactory to satisfactory’ for the results achieved and are likely to be achieved by the end of the project. The project management is also rated satisfactory. Given the strong ownership and commitment of the government, the project’s outcomes are likely to be sustained. The project could be more proactive in disseminating and sharing learning with regions within the country as well as in tapping into lessons emerging in other countries within the East Africa region.

# Lesson

Two crucial decisions UNDP took at the inception contributed to the project’s ability to deliver on most of its intended results: (a) the decision to co-locate the project management unit within the EPA; and (b) a small national staff team managing the project. These gave the project good access to EPA stakeholders and other ministries which helped in smooth communication flow and building good working relationships.

# Recommendations

All recommendations are addressed to the project management unit and UNDP.

|  | Recommendations |
| --- | --- |
| R1 | Working with the EU and EPA, UNDP needs to engage at senior level with all key ministries to advocate for the need to invest adequate level of human resources in the MRV system within each ministry, and ensure inter-ministerial leadership to promote and strengthen the MRV regime through the existing inter-ministerial forum chaired by the Minister for Planning and Development. |
| R2 | Support EPA to develop and deliver regular training and refresher courses, including sector-specific training, related to MRV system. Apart from class-room teaching, this should also include greater structured sharing of experiences among regions and with other countries in East Africa region. |
| R3 | Working together with the EU project on MRV, assist EPA in developing capacity for cross-checking for consistency in all data in its reports. |
| R4 | In the remaining duration of the project, the QA/QC system should be embedded fully in the key categories sector identified by the EPA at woreda, zonal, regional and federal levels, and in other sectors ensure that the federal level consolidated data have gone through QA/QC. |
| R5 | Develop appropriate platforms/mechanisms for sharing of lessons and challenges with regions within the country and with other countries in the East Africa region. |

# INTRODUCTION, SCOPE AND METHODOLOGY OF THE EVALUATION

# Introduction

- The United Nations Development Programme (UNDP) in Ethiopia has been supporting the Federal Government of Ethiopia (GoE) in developing capacity for scientifically monitoring, measuring and reporting on the greenhouse gas (GHG) emissions and withdrawals in line with international standards developed by the Intergovernmental Panel on Climate Change (IPCC). The United Nations Framework Convention for Climate Change (UNFCCC) of which Ethiopia is a signatory requires countries to adhere to the principle of measurement, reporting and verification (MRV) in the context of enhancing action at the national level to mitigate climate change. The initiative ‘Capacity-building programme to comply with the Paris Agreement and implement its transparency requirements at the national level’ (PIMS# 6208), is implemented through the Environmental Protection Authority (EPA) of GoE. Funded by a Global Environment Facility (GEF) grant, with co-financing from the GoE and UNDP, the project requires a mid-term review (MTR) which was commissioned by UNDP Ethiopia. The evaluation was undertaken by one international consultant during January-March 2023, and this report brings together the findings, conclusions and recommendations from the various processes and methods followed in the evaluation.

# Purpose, scope and objectives of the MTR

- As described in the terms of reference (ToR, Annex 1), the purpose of the MTR was to assess the overall performance of the project in relation to the outcomes and draw lessons and recommendations for future programming by providing impartial and independent evidence to assist UNDP and implementing partner (EPA) to identify the results achieved, the key gaps and challenges. The MTR has a particular focus on assessing early signs of project success or failure and identifying necessary corrective actions that will enable the project to achieve its intended objectives as specified in the project document (ProDoc). The MTR covers all activities planned and/or implemented during the period 2020-2022 through the project and focuses particularly on: (a) project strategy, (b) progress towards results, (c) project implementation and adaptive management, and (d) sustainability issues. The geographical scope covers the entire country, both at the national and sub-national levels.

- The project focused on two outcomes, namely: (a) institutional capacity development, and (b) technical capacity development tools, training and assistance. The specific outcomes and outputs intended by the project are presented in the Box below (Box 1).

Box 1: Outcomes and outputs of CBIT project

Outcome 1.1: Strengthened institutional capacity for transparency-related activities

Output 1.1.1: An established inter-ministerial body to provide oversight to the implementation of National Determined Contributions (NDC);

Output 1.1.2: Clearly defined roles and tasks of stakeholders for the implementation of the transparent requirement for the MRV;

Output 1.1.3: National system for GHG emissions inventory and functional GHG database and information system established.

Outcome 2.1: Strengthened technical capacity for transparency-related activities, including tracking of progress towards attaining NDC

Output 2.1.1: Guidelines on the formulation of the GHG emission mitigation policy measure;

Output 2.1.2: Methods to quantify and integrate support needs into the public budget and report on effective utilisation of the support received;

Output 2.1.3: Experts in key sectoral ministries regional states and city administration fully conversant on the transparency framework;

Output 2.1.4: Data collection widened and improved to sustain the use of 2006 IPCC guidelines;

Output 2.1.5: Training on the use of 2006 IPCC guidelines at relevant ministries and university carried out;

Output 2.1.6: National universities engaged to support the competent authority in establishing QA/QC procedure and uncertainty analysis of the GHG inventory.

- The primary audience of the MTR are the UNDP Ethiopia country office, UNDP Africa Bureau, Government stakeholders at national and sub-national levels and GEF.

# 1.3 The MTR criteria, cross-cutting issues and questions

- The MTR covered the following areas of focus based on the Guidance for Conducting Midterm Reviews of UNDP-Supported GEF-Financed Projects - project strategy, progress towards results, project implementation and adaptive management, and sustainability. During the inception phase, the reviewer undertook a rapid evaluability of the review questions (RQ) outlined in the ToR and further refined the RQs and developed an evaluative matrix which is presented in Annex 2. The matrix presents a mapping the RQs and corresponding judgment criteria (JC), as well as indicative methods and sources of data that will enable the reviewer to address the RQs systematically. The JCs are based on various commitments made in the project document results framework, as well as an understanding of the context in the country. A full list of RQs the review covered is presented in Box 2 below.

Box 2: MTR criteria and questions

Project strategy

1. To what extent the project addressed priority needs of the country, and were the focus of the project in line with the national sector development priorities and plans of the country?

2. Was the project design coherent in the country context and were the assumptions made in the design stage valid during the course of implementation? If not, were adjustments made based on evidence and lessons?

3. Were perspectives of those affected by the project, those who could affect the outcomes, and those who could contribute information or other expertise to the process, taken into account during the project design process?

4. Was the project’s results framework coherent in clearly stating in realistic terms the anticipated outcomes and outputs, and did the corresponding indicators/targets render themselves to be monitored and measured adequately during the course of implementation?

5. To what extent was the project design and its implementation process based on a gender-sensitive approach that proactively worked to promote gender equality?

Progress towards results

6. By reviewing the programme results and resources framework, is the CBIT programme on track to achieve intended results at the outcome and output levels? How does the progress so far compare against end-of-project targets envisaged in the results matrix and GEF tracking tool baseline?

7. What are the factors (positive and negative) that contributed to the success or shortcomings in implementation of the project? What lessons can be drawn from the experience so far?

8. Were there significant changes in the social, economic and environmental context in the country and how did these affect the achievement of project results?

9. How well did the project collaborate with other similar ongoing initiatives in the country to ensure effectiveness of interventions and greater impact? To what extent has the project been effective in building synergies and leveraging other programmes and stakeholders in the country?

Project implementation and adaptive management

10. Were the project management structure, system and their functioning sufficiently streamlined with clear lines of responsibility and roles to enable efficient planning and execution of projects activities?

11. Is the project being managed in a cost-effective and cost-efficient manner with good financial control and management of funds? Is co-financing being used strategically to help the objectives of the project?

12. Is the monitoring system generating relevant data in a timely manner that enables good project management and reporting?

13. Has the project developed and leveraged necessary and appropriate partnerships with direct and tangential stakeholders? Do national and subnational government stakeholders support the objectives of the project and continue to have an active role in project decision-making that supports efficient and effective project implementation?

14. Were adaptive management changes and lessons reported by the project management and shared with the Project Board, and to what extent these lessons were disseminated for wider learning?

15. Are there adequate communication established with stakeholders/ partners to enhance their awareness of project progress and challenges, and is there a system to disseminate the project progress and intended impact to the public or government?

Sustainability

16. What is the likelihood of financial and economic resources being available once the GEF assistance ends that will be adequate for sustaining the project outcomes?

17. Are there any social or political risks that may jeopardise sustainability of project outcomes? What is the risk that the level of stakeholder ownership (including ownership by governments and other key stakeholders) will be insufficient to allow for the project outcomes/benefits to be sustained?

18. To what extent are policy and regulatory frameworks in place that will support the continuation of benefits? Do the legal frameworks, policies, governance structures and processes pose risks that may jeopardise sustenance of project benefits?

19. Are there any environmental risks that may jeopardise sustenance of project outcomes?

(Source: Inception Report Final, CBIT Evaluation 2023)

# 1.4 Review approach and methodology

## 1.4.1 Key stakeholders

- A stakeholder analysis was undertaken during the inception stage which showed that the primary stakeholders were UNDP CO, EPA which is the implementing agency, and the Project Steering Committee which is responsible for approval of project plans and revisions, and ensuring oversight of project implementation. Additional stakeholders for this project are the line ministries and the public institutions mainly the Ministry of Finance, Ministry of Health, Ministry of Agriculture (MoA), Ministry of Water and Energy (MoWE), Ministry of Transport (MoT), Ministry of Industry (MoI), Ministry of Urban Development and Infrastructure, Ministry of Mines and Petroleum, Space Science and Geospatial Institute, National regional states and a number of National Universities.

## Organisation of the evaluation and declaration of conflict of interest, if any

- The MTR was commissioned and managed by the UNDP country office, with day-to-day oversight and support provided by the CBIT Project Management Unit (PMU). An external independent consultant was contracted to conduct the MTR; the consultant had never been involved in either design or implementation of the project or any other programme of UNDP Ethiopia.

## MTR approach and data collection methods

- The evaluation used mixed methods combining key informant interviews (KII) and desk review of key documents so as to enable the review consultant to triangulate information and perspectives from multiple sources through both quantitative and qualitative data. The documents review included the baseline GEF focal area Tracking Tool (TT) submitted to the GEF at CEO endorsement and the midterm GEF focal area Tracking Tool. The key informants were selected based on a stakeholder analysis and an informed judgement of their involvement and familiarity with the project directly or indirectly. The consultant reviewed all documents related to the project which include project documents, project implementation reports, relevant policy documents and various assessment reports. A full list of all documents consulted is annexed as Annex 3. Throughout the evaluation, data collected from both KIIs and documents were recorded systematically for evidence assessment based on the judgment criteria against each RQ defined in the evaluative matrix. The reviewer interviewed a total of 18 key informants (4 from UNDP/PMU and 14 from the GoE and Universities); most of the interviews were undertaken in face-to-face meetings in Addis Ababa between February 7-14, except three interviews which were completed online. A full list of key informants is annexed as Annex 4. The itinerary of the review consultant is attached as Annex 5 and the interview guide used for key informant interviews during data collection is attached as Annex 6.

- Content analysis was performed on both the primary and secondary data following an essentially interpretative approach, classifying findings in view of providing concrete suggestions and recommendations. Documents, consultation/interview notes and qualitative data from all sources were analysed to identify common trends as well as diverging patterns for each of the RQs. The extent to which gender equality dimensions are integrated in the project design and implementation was also analysed.

- As required for midterm review of GEF-financed Projects, on completion of data analysis and findings, the MTR has provided ratings for: (a) results achieved, (b) implementation and adaptive management, and (c) sustainability on a 6-point scale for the first two and a 4-point scale for sustainability. The rating scale used is attached as Annex 7.

- Triangulation: Rigorous data triangulation was done mainly through comparing information gathered from multiple sources. Where discrepancies occurred that could not be reconciled, the reviewer was careful in using such data for drawing findings or conclusions. The MTR utilised three types of triangulations to highlight any inconsistencies between different data sources. These are:

- Methods triangulation - both qualitative (KII) and quantitative data was used to elucidate complementary aspects of the same subject;

- Data source triangulation – involving examining the consistency of different data sources (UNDP internal and external key informants) within the same methods;

- Theory triangulation - which involves using multiple theories to interpret and examine the data obtained (process tracing).

- All data from the desk review and individual interview notes was systematically assessed for their convergence or otherwise to examine their: (i) representativeness – do the data/information represent the whole or a sizeable picture? (ii) relevance – to the questions in the evaluation matrix; and (iii) attributability – if the data convey a ‘state’, is it attributable to the intervention/cause being described? The outliers were not rejected outright and, where relevant, additional data was gathered for validation. Validated data from available independent evaluation reports, where available, which have gone through quality assurance checks was weighted higher than self-reported progress reports.

# 1.5 Data protection protocol and evaluation ethics

- Protecting personal data is essential in any evaluation so as to respect dignity and ensure security of all stakeholders involved. Any personal data collected was minimal and is anonymised in the report. For all key informants, although their names and title (function/role in an organisation) were collected by the reviewer for analysis of any trend with regard to information/data collected, information and data provided by them has been presented in a manner that these cannot be traced back to an individual interviewee, unless authorised otherwise by the latter in writing.

- The reviewer followed the United Nations Evaluation Group (UNEG) ethical guidelines throughout the evaluation process. The main ethical issues involve considerations of confidentiality, data protection, protecting vulnerable respondents, and ensuring that the review process avoided causing any harm. In specific terms, the reviewer adhered to the following ethical principles in collecting data:

- Principle 1: independence and impartiality of the reviewer – the consultant’s engagement with UNDP staff and other stakeholders was underpinned by the principle of impartiality and independence of reviewer;

- Principle 2: Avoiding harm – the reviewer ensured that the basic human rights of individuals and groups with whom he interacted, as well as their health and safety (risks related to Covid-19, for example) were protected during the evaluation process;

- Principle 3: Voluntary participation - participation in research and evaluation should be voluntary and free from external pressure; all participants have a right to withdraw from research/ evaluation and withdraw any data concerning them at any point without fear of penalty;

- Principle 4: Informed consent – the reviewer pre-informed participants about how information and data obtained was to be used, processed, shared, disposed of, prior to obtaining their consent to participate in the review process; stakeholders were informed of the purpose of data collection and were offered the opportunity to withdraw from the process at any time;

- Principle 5: Ensuring confidentiality – the reviewer ensured that people were able to provide information in confidence, and that information cannot be traced to its source, if the latter is an individual; no audio or video recording were used during interviews and discussions.

# 1.6 Quality assurance

- Broadly, the following criteria were used to ensure quality of the review to ensure that:

- robust findings that can be clearly linked to various evidence gathered through the quality-assurance process adopted;

- clear links between MTR findings, conclusions and recommendations on the specific questions outlined in the ToR (and as expanded/amended in the inception report);

- adherence to UNDP-GEF evaluation guidelines  and UNEG evaluation standards;

- successful execution of the foregoing activities in an independent manner so as to ensure credibility of the report’s findings and recommendations, and be respectful of the stakeholders involved in the process; and

- the final document submitted to UNDP was proofread, edited and produced according to UNDP style guide for evaluation reports.

# Limitations

- The number of key informants actually interviewed was less than half of what was initially proposed in the inception report. It turned out that in several instances, one individual key informant held the focal point responsibility for a number of areas which the inception report had envisaged as separate key informants. Additionally, interviews could not be arranged with as many regions as was envisaged, or some of the stakeholders had moved on and the new incumbent was not fully on board regarding the CBIT project. Despite this, the reviewer thinks that the data obtained from the interviews conducted and the documents reviewed provide substantial basis for this MTR.

# 2. PROJECT DESCRIPTION AND BACKGROUND CONTEXT

# Project context

- The project document (Prodoc) provides an overview of the country context and the main challenges the country faces in dealing with climate change. The Government of Ethiopia (GoE) is a party to the United National Framework Convention on Climate Change (UNFCCC) and is required to report all its greenhouse gas (GHG) emissions and reduction efforts periodically as per the Paris Agreement. Ethiopia’s total national emissions in 1994 were 108,333 Gg of CO2e which increased to 368,835 Gg of CO2e in 2018, an increase of around 240%. A significant portion of Ethiopia's overall GHG emissions come from the agriculture, forests and other land use (AFOLU) sector activities - CO2e emissions in this sector in 2018 was 334,579.8 Gg (over 90% of total emissions). Within the AFOLU sector, the majority of the overall emission came from the livestock subsector (44%) with enteric fermentation methane (CH4) followed by the land use and forestry (30%). Ethiopia’s livestock population is the largest in Africa, with 60 million cattle, 31.3 million sheep, 32.7 million goats, 1.4 million camels and 56.9 million poultry. On the removal side, the AFOLU sector is crucial, as it removed 108,422 Gg of CO2e in 2018, with net GHG emissions attributable to this sector at 226,157 Gg of CO2e. Interventions on the land subsector by the government such as afforestation, reforestation, and forest restoration have contributed to the removal of GHG. Next to the AFOLU sector, the energy sector accounted for about 7% of the total emissions. The burning of liquid and solid fuel takes up the largest share of energy sector’s GHG emissions, followed by the CO2 emission from the transport sector (48% of the total CO2 emission in the energy sector).

- Other sectors (namely waste, IPPU, construction) contributed nearly 3% of total CO2 emissions in 2018. There is a growing rate of waste generation, especially in the urban areas due to population increase, urbanisation and industrial development, and thus an increase in GHG emissions from the waste sector. From 1994 to 2018 the GHG emission from waste generated (in cities) nearly trebled increasing from 1565.59 Gg CO2-eq in 1994 to 4656.82 Gg CO2-eq in 2018. Total aggregate emissions for the industrial processes and product use (IPPU) sector ranged between 200.102 Gg CO2-eq and 3747.846 Gg CO2-eq during the period 1994 to 2018 - the cement industry is responsible for 97% of the aggregated emissions followed by lime production (3%).

- The mitigation options identified in the AFOLU sector are divided into three categories; livestock, land/forestry and agricultural crops sub-sectors. The primary IPPU sector mitigation options focus on emissions from cement production. Waste sector mitigation options Include: implementing integrated solid waste management programme (source reduction, reuse/recycling, composting, and waste to energy programme), promote sanitary landfill, improve faecal sludge management system, implement integrated wastewater treatment systems, enhance sewer line connection, and promote zero liquid discharge.

# 2.2 The problem addressed by the project

- The Paris Agreement calls for transparency in reporting of the GHG emissions and removals using internationally agreed Measurement, Reporting and Verification (MRV) system which provide internationally agreed methodologies intended for use by countries to estimate greenhouse gas inventories to report to the UNFCCC. Following the Paris Agreement, the MRV system requirements have increased dramatically and the Ethiopian Government is in need of a much more robust and extensive MRV system. The existing MRV framework encompasses submitting national communications every four years and biennial update reports (BURs) every two years. Whilst the country is committed to global efforts towards reducing GHG emissions through its Climate Resilient Green Economy (CRGE) strategy adopted in 2011, the country lacks proper technical and institutional capacity to adhere to the Paris Agreement Frameworks. This challenge hobbles the country in accessing benefits from the financial and technological flows which have been identified as critical to the attainment of the country’s ambitious target of reducing GHGs while striving towards attaining a middle-income country status by 2025. This project seeks to enhance the institutional and technical capacity related to climate transparency in Ethiopia in line with the updated MRV system following the Paris Agreement.

- Despite all the commitment and policy thrust on a green economy, there are major obstacles in Ethiopia accessing international climate funds, especially for the mitigation pillar in its CRGE strategy, low institutional and technical capacity being the key factors. Each ministry hosts a CRGE unit linked to the CRGE Facilities at the Ministry of Finance and the Environmental Protection Authority which is the nodal agency for coordination of climate change initiatives under the aegis of the Ministry of Planning and Development (MoPD). The EPA is primarily mandated to lead the coordination of MRV implementation at national level, while line ministries’ CRGE units are responsible for MRV related actions within their sectoral remit. This means that all CRGE implementing line ministries are meant to have a standing institutional arrangement that can easily facilitate data collection, report preparation and monitoring. These units are responsible for mainstreaming of environmental objectives, providing training on climate and environment issues and aiming to ensure coherence between sectoral policy decisions and the environmental legal framework. Different ministries accord the units varying degrees of priority and resources, and as a consequence, their performance vary. Frequent restructuring and staff turnover in the government has meant that progress has been uneven in different ministries.

- The Assessment of Ethiopia institutional capacity and key MRV needs for ENDC detailed some major weaknesses in the country’s readiness to comply with the Paris Agreement and implement its transparency framework. Major barriers identified in the project document included lack of technical skills within the respective line ministries and key sectors to undertake comprehensive and robust GHG emission inventory in accordance with the MRV framework. Moreover, the available data often was not adequate for inter-sectorial climate change-related policy planning. This key barrier has been reported to be endemic throughout the key sectors. Consequently, this constrained the GoE in monitoring and reporting their GHG emission in a coherent manner. Critically, there was also lack of proper planning for GHG emissions as a result of lack of technical skills. Furthermore, due to absence of an inter-institutional system for data homogenisation, monitoring, reporting and existing data sharing system was fragmented and inconsistent.

# 2.3 Key partners

- Over the years, the GoE has strived to achieve the UNFCCC obligation of reporting its climate change efforts. This has been achieved through institutional reforms such as the establishment of the Environment, Forest Commission for Climate Change (EFCCC) which subsequently became the Environmental Protection Authority (EPA) in 2022. At the time of the project conceptualisation, the Ministry of Environment and Forests had the primary mandate to coordinate all technical requirement related to the Paris Agreement. Subsequently, this became the EFCCC within the Ministry of Agriculture, and in the past one year it metamorphosed into the EPA under the MoPD. The country has produced the first, second and third national communications and the Ethiopia Nationally Determined Contributions (ENDC). Importantly, the country has also developed a low emission pathway to implement the ENDC through the CRGE. Every sector is required to prepare and implement a sector strategy to address effects of climate change by identifying and implementing appropriate mitigation and adaptation measures. Moreover, the country has developed the Ten-Year National Development Plan, Nationally Determined Contributions (NDCs), and the Long-Term Low Emission Development Strategy (LT-LEDs).

- The CBIT project’s main implementing partner is the MRV Directorate in EPA. Ethiopia’s GHG MRV Directorate was established in June 2016 as the national coordinator for the GHG Inventory development process and it provides necessary administrative and logistical support to ensure an efficient and sustainable GHG Inventory Management System and National Communication processes. EPA prepared comprehensive Memorandum of Understanding (MOU) with seven (7) line Ministries and two Agencies to collect the activity data and compilation of the inventory report. Based on this, line Ministries send data (with gaps) to the Central Statistical Agency (CSA) and forwards these to the EPA which compiles the data according to the IPCC 2006 Guidelines and calculates emission using the 2006 IPCC software. The MRV Directorate is responsible for initiating and coordinating the processes of data collection, developing a national schedule of activities, and communicates with line ministries during the activity data collection and compilation.

# Project implementation arrangements, management and finance

- The CBIT project is implemented at federal level and with CRGE implementing sector offices. A steering committee comprising CRGE members from all participating line ministries provides oversight and strategic guidance to the project implementation. The members of the Steering committee include, besides the participating ministries, Deputy Director of the EPA, a representative from the European Union (EU-project on MRV capacity building) and UNDP Climate Change Programme Officer. A small project management unit (PMU) comprising a Project Manager (PM) and a Finance Officer co-located in the MRV Directorate undertake the day-to-day implementation of the project in close collaboration with the latter. The following diagram (Figure 1) represents the data collection and flow process – the central thrust of the project - that was put in place.

Figure 1: Schematic diagram showing organisation of GHG data collection and flow

# 2.5 Project timing and milestones

- The project started on 2 Dec 2019 (ProDoc signature date). However, due to delays related to Covid-19 pandemic restrictions, the project management unit was set-up in August 2020 and the inception workshop took place on 27 Oct 2020. The intended project outcomes and outputs are presented in Box 1 (section 1.3. The financing plan for the project over the four years of its duration included a GEF Trust financing to the tune of US$ 1,166,000, and co-financing of US$ 192,000 from the GoE and UNDP sources (Table 1 below)

Table 1: Financing plan and project milestones - CBIT project

| GEF Trust Fund | US$ 1,166,000 |  |
| --- | --- | --- |
| Cash co-financing to be administered by UNDP | US$ 50,000 |  |
| - Total Budget administered by UNDP | US$ 1,216,000 |  |
| Parallel co-financing (all other co-financing that is not cash co-financing administered by UNDP) |  |  |
| Government | US$ 142,000 |  |
| - Total co-financing | US$ 142,000 |  |
| - Grand-Total Project Financing (1) + (2) | US$ 1,358,000 |  |
| Milestone |  | Date |
| PIF Approval Date |  | 29 August 2019 |
| CEO Endorsement Date |  | 1 November 2019 |
| Project Document Signature Date (project start date) |  | 2 December 2019 |
| Project Inception Workshop |  | 27 October 2020 |
| Date of the Mid-term Review |  | 31 March 2023 |
| Expected Date of Terminal Evaluation |  | Within 6 months of closure of project |
| Planned Closing Date |  | 5 August 2023 |

- The actual expenditure as at the end of 2022 is presented in the Table 2 below. As can be seen, out of a total budget of US$ 1.35 million (including co-financing), an amount of US$ 971,000 has been spent by the end of December 2022, leaving approximately US$ 404,000 (28 per cent of the total budget) to be utilised by the end of the project (September 2023).

Table 2: CBIT project expenditure 2020-2022 (Birr)

# 3. FINDINGS OF THE REVIEW

# Project strategy

3.1.1 National priorities and development needs

Key finding:

1. The project was designed to meet a critical gap in Ethiopia’s ability to deliver on its NDC commitments in a credible and transparent way, and ensured that there was a whole-of-government approach in addressing the capacity gap.

- Ethiopia has set before itself the goal of achieving middle-income country status by 2025. It strives to attain this through its national development plan which emphasises continued reduction in GHG emission through CRGE strategy discussed in section 2.1. The CRGE strategy is supplemented by a number of sectoral climate resilience strategies developed for the agriculture and forestry sectors, water and energy sectors, transport sector, urban as well as health sectors. Additionally the country developed a comprehensive National Adaptation Plan (NAP) which builds on ongoing efforts to address climate change in the country’s development policy framework, including the CRGE strategy and the second Growth and Transformation Plan (GTP II), as well as the sectoral climate resilience strategies and regional and municipal adaptation plans. Its goal is to reduce vulnerability to the impacts of climate change by building adaptive capacity and resilience. The NAP aims to strengthen holistic integration of climate change adaptation in Ethiopia’s long-term development pathway. All of these are part of Ethiopia’s commitment to the UNFCCC and in line with the Paris Agreement to strive to follow a low-emission development strategy.

- Ethiopia has been investing significantly in dealing with climate change and reducing the country’s already-low carbon footprint while seeking to grow its economy. The GoE ratified the UNFCCC in 1994, the Kyoto Protocol in 2005, the Doha Amendment to the Kyoto Protocol in 2015 and the Paris Agreement in 2017. It has also prepared and implemented a number of strategic measures and various projects aimed at building a climate resilient net-zero emitting economy by 2030 with a net reduction of 250 Mt CO2e envisaged between 2010 and 2030 compared to a business-as-usual (BAU) scenario. These include: the Climate CRGE, NAP 2020, the Sectoral Reduction Mechanism, Ethiopia’s Nationally Determined Contributions (E-NDC, 2015 & 2021) and sectoral, regional and city administrations’ adaptation plans and various projects to contain the adverse impacts of climate change. The CRGE strategy has identified the following priority sectors as instrumental in reaching middle-income status by 2025, namely agriculture, forestry, power, industry, transportation, and buildings. The CRGE strategy has focused on the climate change mitigation aspects and did not specifically address climate change adaptation. The gap was recognised and rectified through the development of sectoral climate resilience strategies for the agriculture and forestry sectors, water and energy sectors, the transport sector, urban as well as health sectors.

- The project was designed to address the challenges Ethiopia faced in meeting its ENDC obligation and reporting to the UNFCCC, and this was in line with UNDP’s country programme outcome 3 which relates to Ethiopia becoming resilient to environmental risks and adapting to climate change. The project’s central aim is to enable the country measure, track and communicate its carbon emission/sink and plan its mitigation and adaptation strategies effectively. Lack of reliable GHG data acted as an impediment in developing national plans and strategies in accordance with the CRGE strategy. The project has a limited focus on institutional and technical capacity for putting in place a robust MRV system as there already were multiple other initiatives on green growth and low emission interventions in key high-emission sectors namely agriculture, forests, energy and transport, waste management, and infrastructure. As a party to UNFCCC, GoE is required to report all its GHG emissions and reduction efforts by submission of its National Determined Contributions (ENDC) every five years. However, despite the huge progress made in meeting the UNFCCC obligations as a non-annex country, GoE had significant challenges, gaps and barriers to fully comply with the Paris Agreement in reporting its GHG emission as per the MRV frameworks. These barriers, namely lack of technical skills within line ministries and key sectors to undertake comprehensive and robust GHG emission inventory have been acknowledged and reported in the second national communication, the ENDC and the CRGE strategic report. This project rightly aimed to help GoE develop capacity to monitor, generate and report its GHG emissions from various sectors in a robust manner that complies with the IPCC 2006 guidelines for transparency, quality and consistency of data. As the scope of the project spanned across all sectors, the project emphasised both the inter-ministerial as well as the vertical nature of engagement of key stakeholders to ensure a whole-of-government approach to GHG monitoring as required within the UNFCCC framework.

## 3.1.2 Project design

Key findings:

2. The project’s theory of change and its assumptions have been validated by the results; continuous engagement and training provided is enabling key ministries in the government to meet the UNFCCC requirement in relation to the MRV system.

3. While the project undertakes regular consultation with key stakeholders, and a number of stakeholders were consulted during the design process, certain critical engagement with a few ongoing or emerging initiatives were missed; these could have further enriched the project’s scope and focus.

- The project design was underpinned by an analysis of the capacity weaknesses in relation to UNFCCC requirement. The analysis showed that the government did not have a well-established i) GHG inventory system, ii) GHG database and information system, iii) quality control (QC) and quality assurance (QA) system, iv) guidance document for determining sector specific national emission factors, base-year emissions, the most likely emission scenario and estimating GHG emission effects ex-post. All of these are UNFCCC requirement, and financial assistance through UNFCCC and instruments related to the Paris Agreement are conditional upon a country demonstrating transparency and conformity to quality standards in its GHG reporting, monitoring and planning of development interventions. The production of National Communication and biennial updated reports (BUR) required to be submitted to the UNFCCC also demand these capacities to be put in place. The project design rightly targeted the EFCCC (now EPA) as the nodal agency to spearhead the development and promotion of MRV capacity across key ministries and institutions in the country. The project therefore aimed at establishment and operationalisation of a national system for GHG emission inventory, and a functional GHG database and information system.

- The project’s theory of change (TOC) was straight-forward in that (a) an inter-ministerial mechanism would bring about a whole-of government participation in developing a robust MRV system, and (b) training and guidelines in key sectors on technical aspects of the IPCC 2006 software and subsequent amendments will bring about the necessary capacity needed across the government to deliver on UNFCCC-compliant GHG measurement and reporting system. The underlying assumption was one of relative stability in the government structure. Specific assumptions behind the TOC were: (a) the current personnel within the key line ministries were trainable and could easily assimilate the concepts and procedures relating to GHG emission inventories and MRV transparency frameworks; (b) structures exist within the relevant line ministries to deal with transparency requirements; and (c) the proposed guidelines that will be developed by the project will be used by relevant stakeholders to continuously train and familiarise themselves with the procedures and concepts of GHG emission inventories. By and large, these have been upheld, despite some changes in structures and frequent changes in personnel within different ministries which affected the project. Key informant interviews with six ministries indicated that many of the staff who were trained moved into other roles where their new skills and knowledge were not being utilised. The CRGE Assessment report notes that in five of the seven key ministries, the number of experts working on climate change has drastically reduced following a government restructuring in 2022. One Ministry (Mines) has reduced its number of experts from 14 to 1, and abolished the Environment Directorate it earlier had. Another Ministry (Transport and logistics) also did away with its climate change unit which is now merged with the Strategic Affairs Executive office. The Ministry of Agriculture similarly underwent change from being a climate change directorate in 2018-2019 to being a climate change team under the Strategic Affairs Executive Chief in 2021; now there is reconsideration going on regarding upgrading climate change team back to the Directorate level. The staff strength has drastically declined from 20 to only six experts during a restructuring in the summer of 2022. Similar reductions in staff strength were reported in all the ministries interviewed during the MTR.

- Overall, the TOC seems to hold, in that continuous engagement and training provided is enabling key ministries in the government to implement various activities in relation to the MRV system, challenges notwithstanding.  The governance structure envisaged for the project has enabled creating an ecosystem and a platform for coordinating the activities involving data collection and reporting on the GHG emission as per IPCC guidelines, and produce updated NDC reports, National Communications and biennial Update report requirements. The Federal Republic of Ethiopia comprises 11 autonomous regional states and two chartered city administrations. The regional states have the power to issue policies and regulations, and regional bureaus and agencies, zonal departments, and woreda offices are responsible for implementing policies. The project design envisaged working through the MRV Directorate as the national coordinator for the GHG Inventory development process and provide the necessary administrative and logistical support to ensure an efficient and sustainable GHG Inventory Management System and National Communication processes. The MRV Directorate signed Memorandum of Understanding (MOUs) with seven (7) key Ministries/institutions including the CSA to ensure data collection and data flow from the regions to the MRV Directorate using tools that complied with the Transparency Completeness Consistency Comparability Accuracy (TACCC) criteria of the IPCC guidelines.

- While the project undertakes regular consultation with key stakeholders, and a number of stakeholders were consulted during the design process, certain critical engagement with a few ongoing or emerging initiatives were missed; these could have further enriched the project’s scope and focus. The project emerged through a process of consultation with the MRV Directorate and the latter was involved in commenting on the proposal which was developed by a consultant hired by UNDP. It is understood from interviews and documents that several other ministries or institutions were also consulted in designing the project. Around the time the CBIT project was developed, the European Union had launched a similar project (Green Sector Reform Project) for capacity building on MRV focusing on generating and collating GHG data based on IPCC 2006 guidelines. The project aims at improving Ethiopia's GHG MRV actions and coordination through capacity building and improved data information flows. Interviews suggest there was no consultation with the EU during the initial stages, though subsequently as the implementation of both projects began, the projects have been working closely together, often coordinating and complementing each other. Additionally, the Food and Agriculture Organisation (FAO) of the UN has been also working in Ethiopia through its global CBIT-AFOLU project which has similar objectives with regard to strengthening the transparency and integrity of GHG data in the Agriculture, Forest and other Land Use (AFOLU) sector. FAO is also the technical lead on providing support to the GoE on the National REDD+ strategy which aims to deliver large part of the emission reduction and carbon removal targets of the CRGE strategy in the forestry sector, working with the World Bank. As AFOLU sector accounts for the largest emission/ withdrawals, greater direct interaction between these projects from early stages could have helped build synergy.

## 3.1.3 Results framework

Key finding:

4. The results framework is coherent and the output indicators for the two outcomes are clear enough and easy to track progress on, though at the level of objective of the project, the indicators defined in the logframe do not add much value to the results framework.

- The results framework outlined the objective of the project which was broken down into two outcomes, with each outcome having corresponding indicators and their targets. The logframe conflates outputs and indicators and there is no separate statement of outputs. Despite these weaknesses, one could say that the other indicators work well and are straight-forward as these capture the various outputs intended by the project. However, the two indicators at objective level (IRRF) add very little value to the results framework. The first indicator (Table 3 below) cannot be attributed to this project as this refers to overall efforts in the country on sustainable management of natural resources, which is beyond the scope of this project. This indicator does not capture the expected result of the project – ‘solutions’ can be scaled up even without enhancing institutional capacity for climate transparency. The second mandatory indicator repeats one of the indicators (indicator 8) of outcome 2 and thus adds little value at objectives level.

Table 3: CBIT project objective and indicators

|  | Objective and Outcome Indicators (no more than a total of 15 -16 indicators) | Baseline | Mid-term Target | End of Project Target | Comments on the outputs/indicators/target |
| --- | --- | --- | --- | --- | --- |
| Project Objective: To enhance institutional and technical capacity related to climate transparency in Ethiopia | Mandatory Indicator 1: IRRF1.4.1- Solutions scaled up for sustainable management of natural resources, including sustainable commodities and green and inclusive value changes. | 2 | N/A | 4 | The IRRF indicator cannot be attributed to this project as this refers to overall efforts in the country on sustainable management of natural resources, which is beyond the scope of this project. Hence the target is not relevant. |
|  | Mandatory Indicator 2: Number of personnel/ experts (including Women) from all 11 stakeholder institutions involved in transparency-related initiatives will be engaged in the project activities. | 0 | N/A | 180 | This indicator is redundant and could be deleted as it is covered by indicator 8 under outcome 2. |
| Component 1- Institutional capacity development Outcome 1- Strengthened institutional capacity for transparency-related activities | Indicator 3: Presence of a well-functioning permanent inter-ministerial body/ organisation inclusive of all line ministries | 0 | N/A | 1 | Clear statement of output and target indicators, as well as reasonably SMART, though the definition of a “well-functioning“ body remains unclear - the project needs to clarify if its intent is to create a new body or strengthen the existing inter-ministerial forum to provide leadership on MRV-related issues. |
|  | Indicator 4: Number of line ministries are fully conversant with the roles and tasks in implementing the MRV | 0 | N/A | 11 | Clear statement of output and target indicators, as well as SMART, though the target of bringing 11 Ministries/entities to be “fully conversant” is over-ambitious. This could be revised to 7 which include: MoA, MoWE, MoUI, MoT, EPA, MoF and MoI. |
|  | Indicator 5: A functional national GHG inventory database established | 0 | N/A | 1 | Clear statement of output and target indicators, as well as SMART. Realistic target. |
| Component 2: Technical capacity development tools, training and assistance Outcome 2 - Strengthened technical capacity for transparency-related activities, including tracking of progress towards attaining ENDC | Indicator 6: An existence of 1 set of guidelines document detailing processes and steps applied in the framework of the domestic MRV system to track and report on NDC implementation measures | 0 | N/A | 1 set of Completed guideline | Clear statement of output and target indicators, as well as SMART. Realistic target. |
|  | Indicator 7: Number of guidelines detailing processes and steps for integrating supports needs into budgets | 0 | N/A | 1 set of Completed guidelines | Clear statement of output and target indicators, as well as SMART. Realistic target. |
|  | Indicator 8: Number of skills/trained staff on 2006 IPCC guidelines, GHG Inventory and MRV | 0 | N/A | 180 | Clear statement of output and target indicators, as well as SMART. Target has been achieved nearly three times over. One cannot say that the target was too low to start with. What now needs attention is to confirm that those trained have opportunities for further/ refreshers training for embedding their learning in practice. |
|  | Indicator 9: number of national universities engaged to support the component Authority in establishing QA/QC procedures and uncertainty | 0 | N/A | 3 | Clear statement of output and target indicators, as well as SMART. |

## 3.1.4 Gender sensitivity

Key finding:

5. The project outcome does not directly or indirectly relate to addressing wider gender issues in the country except in ensuring gender equality among participants in the project which remains constrained by the skewed imbalance in workforce composition – a factor beyond the project’s control.

- The project outcome does not directly or indirectly relate to addressing wider gender issues in the country except in ensuring gender equality among participants in the project. The project document refers to a gender assessment within line ministries earmarked for institutional and technical capacity development which revealed significant gender imbalance within the work forces. Though the project has emphasised gender equality in all its interactions with stakeholders, the evidence in PIRs and from KIIs show that there has not been any substantive change in this regard as the line ministries are conspicuously skewed and dominated by the male counterparts. Data on training participants show only a small number of women from the federal government being trained, while more women from the regions make up bulk of the 138 women participants in trainings as of September 2022. Interviews suggest that as it was more competitive in Addis Ababa than in the regions, relatively a smaller number of women get recruited into positions in the capital that play a key role in climate change and MRV systems. The upshot of this has been that despite conscious efforts by the project and key stakeholders, only 24 per cent of the 581 participant experts in the use of 2006 IPCC guidelines were women. According to one key informant, the gender indicators in the results framework of the project were unrealistic as there is a dearth of women technical experts across the government departments. This is reflected in the composition of the steering committee as well – only two of the ten members are women. However, the reviewer sees very little scope and opportunity for the project to integrate broader issues of gender equality into the project which has a limited aim of building institutional and technical capacity for embedding the MRV system in tracking Ethiopia’s GHG emission/withdrawals.

# Progress towards results

Rating: S on four outputs and MS on four outputs

## 3.2.1 Institutional capacity for transparency

Key findings:

6. A permanent inter-ministerial body to provide high level leadership on MRV has not been realised; presently, the project has a steering committee which works at technical level to coordinate the project’s activities across different ministries.

7. There is scope to leverage an already-existing inter-ministerial forum involving EPA on CRGE to provide leadership across the government to strengthen the MRV regime.

- The permanent inter-ministerial body for high-level leadership and planning support which was envisaged in the Prodoc has not materialised. Eight (8) line ministries are now conversant with the roles and tasks in implementing the MRV. With the current configuration of the EPA headed by a Director General, as opposed to previous structure (as Ministry of environment and forest) which accorded it a full ministerial status, the EPA finds its political space to operate at inter-ministerial level constrained. At the ministerial level, there is an annual forum of ministers convened by the Minister for Planning and Development, with the involvement of EPA, where issues related to the CRGE covering mitigation, adaptation and MRV are discussed, but it does not provide the opportunity for in-depth discussions on challenges. The EPA has set up a working group with Directors from several relevant line ministries and Departments to function as a MRV working group in the AFOLU sector. This initiative was supported through the EU project. Key informant interviews indicated that while this group works well at technical level, it does limit the extent it can influence practices related to MRV in different Ministries involved in the AFOLU sector. The steering committee faces similar challenges. For example, the Ministry of Urban Development and Infrastructure has three departments, each headed by a director, following a restructuring in early 2022. While the waste sector and urban greening departments are fully engaged on the MRV mechanism and systematic data collection using the IPCC tools, interviews showed that it has been difficult to get buy-in from the urban infrastructure department which controls the largest share of funds and is responsible for roads, bridges and public buildings. Advocacy at the level of minister becomes challenging in the current structure. In the Ministry of Mines and Petroleum, the climate change unit stands disbanded since the summer of 2022, with no staff dedicated to MRV.

- Key informant interviews indicated that because all ministries are used to working vertically, it may not be easy to get much traction to the idea of a separate permanent inter-ministerial body, in addition to the one already existing (headed by the Minister for Planning & Development). As the existing inter-ministerial forum has a CRGE remit, it may be best to explore through advocacy by EPA, UNDP and the EU how this body can be strengthened and facilitated to address the challenges facing MRV system-wide. This will enable the top-level leadership in ministries to appreciate the critical importance of the roles and responsibilities of staff involved in MRV and transparency requirements, and develop subsidiary instruments that enable mandatory data development and archiving, research on emissions, operations of the GHG national system and database, reporting and verification required under the Paris Agreement. Operating jointly with the technical level steering committee which now exists, this should provide the right level of leadership to ensure that the country has a credible MRV and quality control system for sharing information and data across institutions.

## GHG inventory and functional database system

Key findings:

8. A GHG inventory database system has been developed in partnership with the EU project and is in the process of being operationalised following a trial phase. Several sectors have made progress in establishing baseline inventories, while in a few sectors this is still work-in-progress.

9. The consolidated data on emissions in various official reports sometimes lack consistency over the years, reflecting a need for further strengthening of quality assurance of data, particularly at baseline.

- A GHG inventory database system has been developed in partnership with the EU project and is in the process of being operationalised. The EPA has undertaken key category analysis of all emissions and identified four key sectors as the largest contributors to GHG emission – AFOLU, IPPU, waste and energy (including transport) sectors. Within these sectors, the country has further drilled down to identify the sub-sectors which account for the bulk of emissions/sinks. The primary IPPU sector mitigation options focus on emissions from cement production. The mitigation options identified in the AFOLU sector are divided into three sub-categories; livestock, land/forestry and agricultural crops sub-sectors. Waste sector mitigation options Include: implementing integrated solid waste management (source reduction, reuse/recycling, composting, and waste to energy programme), promote sanitary landfill, improve faecal sludge management system, implement integrated wastewater treatment systems, enhance sewer line connection, and promote zero liquid discharge. In the energy sector, biofuel and light rail transit were identified as key to mitigation efforts. The database builds on data provided by regions to the respective ministries who then forward the data to MRV Directorate for consolidation. UNFCCC’s Tier 1 methods were used to estimate emissions for the energy, IPPU and waste, whereas Tier 2 methods were used for livestock and forest sector GHG emission calculations. During the trial phase when 2 years’ GHG data from various sectors was uploaded, it showed a number of technical glitches which are now been rectified. Once completed, the database will be formally handed over to the EPA for which ICT and MRV Directorate staff have been trained at the federal level through the CBIT project. In the initial phase, the database will be held and managed at the federal level. Once up and running, all relevant stakeholders at the federal level will be able to access the system virtually in order to check, review and improve data, as well as revise calculations used for the elaboration of the inventory, thus creating an additional layer of quality assurance. The project is working to operationalise a user-friendly integrated web-based and GIS-embedded communication and feedback system for managing all NDC information and data collected from the energy, IPPU, AFOLU, waste and transport sector activities in a transparent manner. The operationalisation of the database and information system will allow the EPA to further engage stakeholders in the MRV process thus strengthening Ethiopia’s capacities to fulfil its enhanced transparency framework. This will be facilitated through the provision of technical support on the collection of activity data, calculation of GHG emissions, assessment of uncertainties and implementation of QA/QC procedures so as to make certain the accuracy, completeness, consistency, transparency and reliability of an inventory and documentation of the inventory process.

- Among various sectors/ministries, the forest and waste sub-sectors were seen to have a better system and capacity in managing the GHG inventory within their remits as well as the data management system. The progress in the forests sub-sector owes much to the support received from FAO and other organisations over the years, starting with the REDD+ programme (Reducing Emissions from Deforestation and forest Degradation) over a decade ago, according to key informants. However, though part of the same ministry, the agriculture and livestock sub-sectors had not made much progress on MRV system until the commencement of the EU project, and subsequently the CBIT project, which are focusing on these critical areas. The waste and urban greeting sectors in the Ministry of Urban Development and Infrastructure have demonstrated good capacity to generate good quality data on emissions/sinks, backed by a written quality control plan. These sub-sectors have developed good institutional arrangement from the federal to the regional, zonal and woreda levels for data flow, allowing for quality control oversight with the help of external (Universities, consultants) experts. Other ministries are yet to start putting in place a quality assurance plan, according to a study undertaken in 2022. This study also found that the Ministry of Industry was struggling with its data management and documentation system for GHG inventory, with no clear delineation of roles and responsibilities. One reason for this is that the Ministry works mostly with the private sector which is not always ready to share data. The Ministry of Mines & Petroleum also lag behind in setting up a MRV system as part of its CRGE strategy linking the federal and regional data points; lack of engagement of top leadership in the process is cited to be one of the factors contributing to slow progress. The Ministry of Transport & Logistics also suffers from weak engagement of senior leadership on MRV system and has three in the CRGE team.

- The consolidated data on emissions reported by EPA sometimes lacks consistency over the years. As per the TACCC principles of the 2006 IPP guidelines, data consistency is ensured when inventory estimates for different years for different gases are made in such a way that differences in the results between years and source categories reflect real differences in emissions. Further, it prescribes that, as far as practicable and appropriate, the same data are reported under different international reporting obligations. The latest (first) BUR report estimates total (net) emissions to be in the range of 236,636 Gg CO2e in 2018 to 249,459.49 Gg CO2e in 2020, with the AFOLU sector accounting for 80 percent of total net emissions in 2020, followed by the energy sector (15 per cent) and the IPPU and waste sector accounting for 3 per cent and 2 per cent respectively. However, in an assessment report dated September 2022, the EPA reported that agriculture sector contributed about 76 per cent, followed by the energy sector (22 per cent) and 2 per cent emission from Industrial Process and Product Use (IPPU) of the total national emission. This gets more confusing when compared against data presented in the third national communication which shows that gross/net emission from the AFOLU sector stood at 90 per cent in 2018 and energy sector emission was 7 per cent during the same year. If the data presented in the TNC were correct, this would imply a doubling of emission (15 per cent in 2020, BUR) in the energy sector between 2018 and 2020, with nearly 10 per cent (80 per cent in 2020, BUR) corresponding decline in the AFOLU sector. None of the reports explain this discrepancy. According to one expert interviewed during the evaluation, some of the key emission data used in the country are historical and originate in the CRGE document in 2011 and these have never been validated; the fact is “baseline data does not exist in several sectors and these are now gradually being established.”

## Strengthened technical capacity

Key findings:

10. The most significant achievement on technical capacity has been the specialised training provided to nearly 600 climate change experts. The in-depth nature of technical training on the IPCC 2006 software provided at the federal and regional/zonal/woreda levels is considered by stakeholders as key to Ethiopia’s MRV system.

11. A guideline document to help different sectors prepare detailed MRV framework and implementation plan has been developed and disseminated, with some ministries already beginning to develop their respective plans. The development of guidelines for budgeting and monitoring of expenditure linked to GHG emissions/withdrawals is now beginning to happen.

12. The project has been putting in place a credible QA/QC system to validate all GHG data for MRV purposes; significant progress in this regard has been made particularly in the forest sector, while work is in progress in other sectors.

- The project helped develop guidelines for assessment of mitigation policy measures in the waste sector which outlined detailed process and methodology for putting in place a MRV system. The aim was to identify the impacts of GHG mitigation policy measures on waste management (landfill management), light rail transit and the use of biofuel, and develop guideline on the formulation of mitigation policy measures assessment, which will provide a guidance and skill development road-map for experts in different sectors. This was disseminated to all relevant ministries in 2021 as a model to be used for development of their own respective guidelines for assessing mitigation plans and GHG measurement and reporting, linking data from woreda level through to the zones and regional to the federal. A few ministries have been working on it, though a number of others (Ministries of Transport, Water & energy, Urban Development & infrastructure) are yet to start work on this.

- Progress on development of guidelines for quantifying funds received and spent on climate change related actions to the country’s NDC commitment has been slow. This involves quantifying the GHG effect of each activity proposed in different plans and ensuring that budgets and expenditures are reported accordingly. The project intended to develop capacity on quantification of the expenses needed for the attainment of the NDC goals and for the evaluation of the effectiveness of expenditures on climate change mitigation and adaptation actions. The CBIT project’s engagement with the MoF has so far been limited to exploring how to go about developing such a guideline and the parameters to be included in the exercise. The first BUR report shows that the MoF is already producing data on funds received and spent on various mitigation and adaptation actions; however, the gap remains in various ministries, regions and zones translating the GHG goals into financial terms for budgeting and reporting on expenditure on NDC related actions.

- The training provided through the project has two distinctive elements: (i) in-depth nature of technical training on the IPCC 2006 software, and (ii) training provided in the regions. The project has provided training to 581 (135 women) participants from the federal and regional governments so far on the 2006 IPCC software and transparency framework. The participants came from all the regions except Tigray. KIIs indicated that while all participants found the training handy in using the software, several ministries expressed the need for training more staff and providing retraining/refreshers’ training for those who have had one round of training. To extend the training to zones and woredas, scaling up of training will be needed and number of trainers will need to increase substantially. In one of the regions where over 100 people from all the woredas were trained in the IPCC 2006 software, the region is facing difficulty in using the software due to its complicated nature which can be mastered only through repeated exposure to training and support. In this regard, the need for ongoing support was emphasised in all interviews. The EPA staff in the regions provide training on various aspects of pollution, environmental impact assessment, etc., and training on IPCC is provided through the CBIT project. Some of the ministries had staff trained earlier on MRV through the EU project; however, the CBIT training was more intensive on the 2006 software while the EU training covered wider issues on MRV. The forest department, for example, which has been one of the first to developing GHG measurement systems through its REDD+ project some 10+ years ago with assistance from FAO HQ had 30 of their staff at sub-national level trained through the CBIT which allowed them to have trainers who could undertake training in the regions. KIIs confirmed that there was no duplication between the EU and CBIT training. The need for more such training courses from time to time was expressed in several interviews which also highlighted the importance of need-based training tailored to each sector and dedicated support for each line ministry on MRV.

- The CBIT project developed a general, sector-specific, and cross-cutting Quality Assurance (QA) and Quality Control (QC) guideline, and is engaging with three universities to support regions and various ministries in the QA process. The project developed a generic outline of QA/QC plan for AFOLOU, IPPU, Waste and transport sectors which relevant ministries are meant to elaborate and develop into action plans. The sector coordinators were charged with ensuring that adequate QA/QC procedures were performed for the inventory, its supporting documents, calculation spreadsheets and usage of the IPCC GHG inventory software. Addis Ababa University and Wondogenet College of Forestry are engaged to support the Federal and Regional Environmental Protection Authority in the development of a national greenhouse gas inventory, accounting and reporting (GHG) mechanism. Wondogenet College of Forestry also provided AFOLU training for Sidama Region Environmental Protection Authority and Addis Ababa University assisted in developing Third National Communication of Ethiopia. Discussions started in the last quarter of 2022 with Haramaya University to explore their engagement in QA/QC and providing advisory support to CRG sector for the Ministry of Agriculture on livestock and crops production. Moreover, all regional departments have a mandate to check the quality assurance/quality control (QA/QC) in their respective organisations starting from the grassroot level data collection to the line ministries. QA/QC implementation needs a very good institutional arrangement from federal to the Woreda level that makes the data flow easier, but currently there is no institutional arrangement for QA/QC in place that links the processes at federal level with the regions and the regions with the zones and zones with Woredas. The roles and responsibility of data collector, data encoder, data compiler, and that of the data coordinator is not clearly indicated at the national level for each line ministry. One can say that this is work-in-progress; at least the principles and methods are laid down and clear to the Universities involved as well as EPA and some of the line ministries.

## Overall summary of progress and results

- In line with the UNDP country programme outcome 3 - Ethiopia becoming resilient to environmental risks and adapting to climate change - the project is enabling the country to develop a system to measure, track and communicate its carbon emission/sink and plan its mitigation and adaptation strategies. At the start of the project (baseline), the EPA did not have a well-established GHG inventory and database and information system which met the UNFCCC requirement. Capacity was also lacking for the generation, archiving, analysis and sharing of quality GHG emission information and data for the formulation of BURs and NCs. As the above discussion shows, good progress has been, or is being, made on all of these, though some of these will require more efforts in the remaining period of the project to achieve satisfactory results at the terminal evaluation. The overall progress in terms of results achieved based on data from various PIRs and this MTR is summarised in the Table 4 below. The different shades of colour in the achievement rating column denote the following:

Yellow: On target to be achieved

Green: Achieved

Red: Not on target to be achieved

Table 4: Overall results achieved against the results framework

| Project Strategy | Indicator | Baseline Level | Level in 3rd PIR (self- reported) | Midterm Target | End-of- project Target | Midterm Level & Assessment | Achievement Rating | Justification for Rating |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: To enhance institutional and technical capacity related to climate transparency in Ethiopia | Indicator (if available) Mandatory Indicator 1: IRRF1.4.1- Solutions scaled up for sustainable management of natural resources, including sustainable commodities and green and inclusive value changes | 2 | 4 | NA | 4 | Good progress made in terms of enabling EPA to provide leadership on MRV and providing training and guidance to various ministries. The indicator however is stated in a way that’s beyond the scope of the project which is simply to strengthen capacity for GHG measurement and reporting, rather than scaling up for: (i) the government’s afforestation programme; (ii) building renewable power generation capacity; (iii) solar irrigation and improved livestock practices; and (iv) use of appropriate advanced technologies in industry, transport, and buildings | MS | 1. In forestry and agriculture sectors, while progress has been made on MRV, the project could have better complemented FAO’s ongoing efforts from the beginning. 2. The indicator could be revised to align it with the objective. 3. Progress on MRV systems in the energy sector and industry, transport has been less than satisfactory. |
|  | Mandatory Indicator 2: Number of personnel/experts (including Women) from all 11 stakeholder institutions involved in transparency-related initiatives will be engaged in the project activities | 0 | 581 (443 M & 138F) Experts trained | NA | 180 |  | NA | See Indicator 8 |
| Outcome 1: Strengthened institutional capacity for transparency-related activities | Indicator 3: Presence of a well-functioning permanent inter-ministerial body/ organisation inclusive of all line ministries. | 0 | Steering committee established | NA | 1 | Although no ministerial level group has been formed due to changes within the government, a steering committee with technical staff from various ministries has been formed. | S | The steering committee has been functioning well, though with a more limited remit than what a ministerial group could have provided leadership on. |
|  | Indicator 4: Number of line ministries are fully conversant with the roles and tasks in implementing the MRV | 0 | 8 | NA | 11 | Satisfactory progress in four key sectors, but not all ministries have put in place adequate structures and mechanisms that can support MRV across all sectors within their remit. As discussed above, Ministry of Transport & Logistics, Urban Dev. & Infrastructure, Mines and Petroleum, have some way to go before they demonstrate a minimum capacity for credible MRV. | S | The project will need to intensify advocacy and engagement with the ministries lagging behind to maintain a ‘S’ rating at the end of the project. |
|  | Indicator 5: A functional national GHG inventory database established | 0 | In process | NA | 1 | A GHG inventory and database has been developed which is now in trial phase and is likely to be completed in the next 2-3 months. | MS | Since the trial is not yet completed, difficult for the MTR to speculate how users receive this and when it will be rolled out. Since only another 6 months remain of the project, one hopes this leaves enough time for rolling out and providing training to users. If it does, the rating will become an “S” at project end. |
| Outcome 2: Strengthened technical capacity for transparency-related activities, including tracking of progress towards attaining ENDC | Indicator 6: Existence of 1 set of guidelines document detailing processes and steps applied in the framework of the domestic MRV system to track and report on NDC implementation measures | 0 | In process | NA | 1 completed guideline | Model guideline developed and disseminated; some ministries have begun to adapt this model to their sector-specific guidelines while others lag behind. | S | This is rated ‘S’; however, effort needs to be put into it in the coming months to ensure socialisation at woreda, zones, regional and national levels. |
|  | Indicator 7: Number of guidelines detailing processes and steps for integrating supports needs into budgets | 0 | In process | NA | 1 completed guideline | Discussions with MoF began and progress made on integrating GHG goals into financial terms for estimating the needs and financial gap in Ethiopia meeting its NDC commitments, and monitoring expenditure against NDC. | MS | Discussion with Ministry of Finance on a guideline detailing processes and steps for integrating GHG goals in budgeting and monitoring is taking place. |
|  | Indicator 8: Number of skills/trained staff on 2006 IPCC guidelines, GHG Inventory and MRV | 0 | 581 trained | NA | 180 | This component of the project made substantial progress and is valued by all stakeholders, particularly those in the regions who otherwise were little exposed to the tools. | S | A ’HS’ rating is not provided as the training currently provided is a good starter, there is need for customised training in different sectors. |
|  | Indicator 9: number of national universities engaged to support the component Authority in establishing QA/QC procedures and uncertainty | 0 | 3 Universities – Adama Science & Technology (waster, energy & transport), and Wondogenet College of Forestry, and Harmaya (crop & livestock) engaged to support the EPA in development of a national GHG inventories | NA | 3 | Engagement with Universitates on QA/QC ongoing. Generic QA/QC plans for 4 key sectors outlined, but institutional linkages between woredas, zones, regions and federal data hubs and QA/QC at each stage remains unclear. | MS | The incipient QA/QC systems will require further work and systematization in the remaining period of the project to achieve ‘S’ rating at the end of the project. |

## Factors affecting results – partnership and synergy

Key findings:

13. The strong partnership with EPA and the EU project on MRV have been critical for the project’s results.

14. Internal organisational issues within the government affected some of the project results which continuing advocacy by UNDP at senior levels may help move things forward.

- Though project implementation was delayed, good partnership with the EPA and EU project have contributed to achieving positive results in several key areas. The project implementation effectively started in October 2020 after nearly a year’s delay following the formal project approval by GEF, due to the COVID-19 pandemic and delays in putting the project team together. As the project concept was new and involved a number technical issues, it was a challenge to get a dialogue going with various stakeholders at the federal and state levels to get their full involvement. Another compounding factor has been a number organisational changes within the government which continues to negatively affect grounding of MRV and transparency systems within several ministries. Despite this, good progress has been made on a number of areas namely: (a) setting up a functioning steering committee, (b) GHG database system which is in the final stages of completion, and (c) training on IPCC 2006 software. Although the MRV initiative of the EU-funded project and the CBIT project overlap to an extent, good cooperation and coordination between the project staff helped avoid any duplication and ensure complementarity. The EU projects target four outcomes, all of which complement what CBIT aims to achieve: (i) AFOLU sector emission; (ii) improvement in the cement sector inventory (almost 97 per cent of GHG in IPPU sector are attributed to cement production and use); (iii) coordination and database management for a national MRV system; and (iv) public financial management to strengthen Ethiopia’s NDC regime.

- Internal organisational issues within the government affected some of the project results; sustained advocacy at senior levels might have helped move things forward. The project has built good working relationship with the CRGE units, where these exist, in line ministries. The steering committee of 10 members drawn from key ministries (and UNDP) helps facilitate this engagement. The EU project works on developing national MRV data systems for the AFOLU sector and has a technical working committee specifically for the sector. The work done through this project is then fed back into the steering committee discussions to take stock of national level MRV. At the national level, there is a CRGE forum which allows for participation of NGOs/CSOs, besides government and UN agencies. The CRGE forum is convened by the Minister for Planning and Development. The project has been unable to engage in high-level advocacy on organisational issues that affected some of the ministries’ engagement on MRV system development within their relevant sectors due to restructuring of the EPA.

# Project implementation and adaptive management

Rating: S

## 3.3.1 Management arrangements

Key findings:

15. Overall, the project has been cost-effective, considering the unique role it is playing in taking the MRV system to the level of woredas, zones and regions on the one hand, and enabling an integrated system at the federal level, on the other.

- The Steering Committee comprising 10 members (section 2.4) functions as the governing body for the project and meets annually, besides informal meetings conducted by the Project Manager (PM) with individual participating ministries every quarter or as and when required. So far, the steering committee has met three times, of which one meeting (2020) was conducted online. A close working relationship has been forged between the MRV Directorate and the PM, enabling good two-way information flow and smooth operational decision-making. In terms of timeliness of delivery of actions, as discussed earlier, the project had a late start by nearly a year from the date of signing of the contract. It is only after August 2020 when the PM was recruited, activities began. The project is implemented under the CO support to NIM modality where UNDP provides support services to the national implementing partner, the EPA. UNDP’s support services include: identification and recruitment of programme or project personnel, procurement of goods and services, financial management, etc. The project management structure is lean, with two full-time dedicated staff – PM and finance officer. The project, located in the MRV Directorate of the EPA, receives additional support from the latter in various matters namely, transport and communication, occasional administrative assistance, etc. The PM has regular meetings with the MRV Directorate and UNDP where any administrative or programmatic issues that arise during implementation are resolved. The Implementing Partner is responsible for:

- Approving and signing the multiyear workplan

- Approving and signing the combined delivery report at the end of the year, and

- Signing the financial report or the funding authorisation and certificate of expenditures.

- The project’s annual planning, budgeting and financial controls appear to follow standard UNDP procedures, with annual audit of accounts undertaken each year. The project undergoes annual auditing by the GoE as per its procedure, and in 2021 an independent audit was also conducted. The independent audit found the financial records and internal control systems satisfactory and in compliance with UNDP Programme and Operations Policies and Procedures (POPP). UNDP advances funds to the project (EPA) every quarter which the latter accounts for in its quarterly report and requests subsequent instalment. The finance officer of the project works closely with EPA’s finance department and ensures compliance with required procedures. The Annual Plans show realistic budget allocations and adjustments being made during the year, with small acceptable variations between the planned budget and actual expenditure, except for the year 2020 when the implementation was affected by COVID-19 and late start of the project. The following Table (Table 5) shows the actual expenses against workplans. The figures for UNDP and the GoE relate to the respective co-financing contributions – UNDP in cash, and the GoE in-kind, as discussed in section 2.2.

Table 5: Annual Workplan budget and Actual expenditure (US$)

| Year | AWP budget | Actual expenditure | Variance (per cent) |
| --- | --- | --- | --- |
| 2020: Cash | 273,930 (UNDP: 13,000) 42,000 | 230,000 42,000 | -16.03 |
| In-kind (GoE) |  |  | 0 |
| 2021: Cash | 280,000 (UNDP: 12,000) 31,000 | 273,038 31,000 | -2.5 |
| In-kind (GoE) |  |  | 0 |
| 2022: Cash | 344,845 (UNDP: 13,000) 30,000 | 364,632 30,000 | +1.9 |
| In-kind (GoE) |  |  | 0 |

- Overall, the project has been cost-effective, considering the unique role it is playing in taking the MRV system to the level of woredas, zones and regions on the one hand, and enabling an integrated system at the federal level with data from all sectors, on the other. The project is managed by national staff which helps keep the costs low. The co-financing by the Government (US$142,000), mainly through in-kind support by way of office space, transport, communications, day-to-day administrative assistance also help keep costs low. The UNDP component of co-finance (US$50,000) is in cash and goes towards salary of the Finance Officer and other minor administrative expenses. The project’s close working relationship with the EPA enabled good access to a number of line ministries which, together with the strategic guidance from steering committee, generated good participation and buy-in from a number of key ministries for the MRV initiative. In this regard, the project can be said to be cost-efficient – a US$1.35 million project being able to bring several key ministries together to engage in a relatively new initiative. Cost-effectiveness is about the project’s outcomes in relation to its costs: how well the cost of assistance stacked up against what was achieved. This is a broader question and the outcome depends not just on good project management on the ground, but on the initial choice of programme approach, design and set up, discussed in section 3.2. An example of the project’s unique value comes from the support on the AFOLU sector: FAO’s global CBIT project has been supporting Ethiopia develop its MRV system for forests for several years, with most of the work being done by international staff/consultants visiting the country for short periods of time, thus with little opportunity for local capacity development and knowledge transfer. The CBIT project enables EPA to work with forest officials at local level to ensure that they have access to necessary training. Likewise, as mentioned earlier, the project’s support on training and technical capacity at regional/woreda levels on agriculture and livestock sector complements the work supported by the EU project.

## Project monitoring and evaluation

- The project monitoring is done through periodic meetings between UNDP, project management and EPA, and through discussions with steering committee members either informally or through formal steering committee meetings which take place once a year. A number of ad hoc meetings of some of the steering committee members takes place in between, either online or in person, and through emails. However, since the restructuring in 2022 in all ministries, as a number of key officials have changed, setting up periodic meetings has not always been feasible. Besides this, regular discussions with MRV Directorate enables the PMU to deal with any relevant issue. There are no specific monitoring tools used as such, and the regular meetings and quarterly progress reports from the implementing partner suffice for the project management and UNDP to track progress and challenges where they arise. The annual PIRs offer an opportunity to take a comprehensive stock on all outputs and these provide good account of progress made and challenges faced in implementation.

## Adaptive management

- The project has taken into account a number of changes and new needs in the course of project implementation. The Covid-19 pandemic delayed start of the project, but thereafter the project managed to speed up implementation. The first was in defining its role in relation to the EU project as potential overlaps between the two projects came to notice at the inception phase of the CBIT. Through mutual discussions, it was agreed that the two projects would work closely and complement each other. The EU project concentrated, for example, on the development of GHG central database, with CBIT taking on the lead in socialising it among various ministries and training of ICT staff of EPA. Likewise, while the EU project focused on developing the GIS/web-based data system, the CBIT project undertakes training of relevant stakeholders in woreda, zones and regions in use of the database. During the course of preparation of Ethiopia’s updated NDC for submission to the UNFCCC (2021), as it was realised that the EPA will need help in its preparation, the CBIT project was able to provide support. Similar support was provided in the preparation of third national communication and the recent BUR (2022).

- The UNDP CO maintains a risk register which is updated and tracked every three months for any development that may impede project implementation. At present there are no social or political risks to the project or its outcomes. Even if the government or its policies change, it is highly unlikely to take a complete U-turn and abandon its CRGE strategy and NDC, at least in foreseeable future. The project will not lead to any displacement or forced relocation, nor is the project dealing with sensitive social or cultural issues that could result in community backlash. As stated in the Prodoc, there is no perceived environmental risk to the project. On the contrary, the project will have indirect environmental benefits through enabling the government to move towards green economy. The benefits will be through reduced deforestation, increased afforestation, reduced GHG emissions, improved ecosystem services and waste management.

## Communication and dissemination

- The project is not required to have a direct interface and communication with public, and all direct communication by the project is with the EPA and other ministries as well as the steering committee. The project shares a narrative report with financial statement every quarter with the EPA (Director of Climate Change, Director General’s Office and Resource Mobilisation Directorate), and makes an oral presentation bi-annually to all the participating ministries, EPA and the regional representatives (from EPA). Regular communication through emails and meetings take place with partner-ministries who are well informed about the project, and communication with the EPA is continuous as the project is housed within the EPA. The steering committee is another forum through which information is shared among various ministries. General communication on the project’s progress is also disseminated through the EPA website. Key informant interviews with government counterparts indicated that while communication from the project has been good, there is need for more sharing between regions and with other countries in the East Africa region.

# Sustainability

Rating: L

Key finding:

16. The project outcomes are likely to be highly sustainable, given the strong ownership and regulatory environment set up by the government.

- With strong ownership demonstrated by the government, the project outcomes are likely to be institutionally and financially sustainable in medium to long term. The project plays a catalytic role in the country’s effort to establish a credible and verifiable MRV system. In this regard, the entire administrative and management apparatus is owned and already supported by the government from its own resources. Once the protocols for data collection, collation and analysis, including their QA/QC, are developed, the EPA and line ministries will be in a position to continue the work, with need for occasional training and refresher courses in order to further embed the capacity. The EPA has now adequate technical capacity to carry forward the work of MRV and with support of independent research and academic institutions on QA/QC, it is very likely that GHG measurement and monitoring sytem will continue to become stronger as all stakeholders see the importance of this project in enabling them to track GHG emissions and report on these in a transparent way. The GoE has over the years demonstrated its commitment to addressing climate change and GHG emissions issues, as seen in various policy documents and reports to UNFCCC, besides the significant investment made by it is ensuring delivery capacity at staff and administrative levels in all the relevant ministries and regions.

- Policies, legal and regulatory frameworks underpinning this project are all conducive to sustaining the benefits even after the project ends. There are agreements in place between the EPA and line ministries for continuing to prioritise the MRV activities. However, mitigation actions require funds, and like most developing countries, Ethiopia will be looking to the international climate financing instruments to supplement national resources. If the international scenario and financing environment altered radically for the worse, this is bound to have an effect on countries like Ethiopia, going forward. Some of these factors may warrant Ethiopia reviewing its CRGE strategy or put in on hold. At present, there is strong political will and commitment to moving the country towards a green economy and this augurs well for the project’s sustainability. The project’s strong link to the country’s CRGE which outlines the country’s ambitious plan of being a middle income country by 2025 enhances the chances for sustainability of the project outcomes. Apart from these, environmental or socio-economic factors have no bearing on sustainability of the outcomes of this project as the project’s aim is limited to developing capacity for MRV; however, the project outcomes may have indirect effect on how environmental or socio-economic services are delivered by various institutions of the government. The project has no direct interface with the public as this is not relevant, and at present there are no social and political risks to sustainability of the project’s outcomes.

- The project undertakes periodic review with participaition of stakeholders through the steering committee and informal discussions as discussed in sections 2.4 and 3.3.4. Lessons and challenges are documented in the PIRs. As discussed previously, the project could strengthen its stakeholder ownership through greater sharing of experiences and lessons within different regions of the country as well as with other countries in the East Africa region.

# 4. CONCLUSIONS, LESSONS AND RECOMMENDATIONS

# Overall conclusion

- Ethiopia has set before itself a challenging goal of building a climate resilient net-zero emission economy by 2030, for which it has promulgated a slew of policy measures and regulatory frameworks. However, the country was hamstrung in developing national plans and strategies in accordance with its climate resilience strategy by lack of reliable GHG data. The CBIT project is addressing this gap which should enable the country to deliver on its NDC commitments in a credible and transparent way. While not perfect, the project’s result framework has laid a good basis for the project delivery.

- The project has galvanised strong partnership with key institutions who have a critical role in Ethiopia’s MRV system. The project has achieved significant results, though some of the results were affected by reorganisation within various ministries of the government that weakened the manpower capacity dedicated to MRV and climate change related issues. The project facilitated technical inter-sectoral coordination through a steering committee set up with officials from key ministries, though the initial idea of a permanent inter-ministerial forum of ministers who could provide a collective leadership on MRV did not materialise. Moving forward, there is scope to leverage an already-existing inter-ministerial forum involving EPA on CRGE to provide leadership across the government to strengthen the MRV regime.

## Conclusions on results, adaptive management and sustainability

- The project is rated ‘mostly satisfactory to satisfactory’ for the results achieved which are likely to be sustained. One of the key achievements on technical capacity has been the specialised training provided to 600 climate change experts at the federal and regional/zonal/woreda levels on MRV system. Frequent changes in staff within the government would require periodic training, retraining and development of a cadre of trainers in the coming years. Baseline inventories have also been established in several sectors, and a national GHG inventory database system has been developed and is in the process of being operationalised following a trial phase. A quality assurance/control system as required for UNFCCC reporting is in the process of development and should be fully in place by the time the project ends. At the moment, the consolidated data on emissions in various official reports sometimes lack consistency over the years, and will require strengthening. Production of guidelines for sector-specific MRV framework and mitigation plans and linking budgeting and financing to GHG data has seen mixed progress. The project management is rated satisfactory. As the project started a year late due to factors beyond its control, it has effectively had about two and a half years of implementation so far. With nearly 28 per cent of funds remaining unutilised as of 31 December 2022, it is likely that the project will be able to complete all ongoing and pending activities by the end of the project in August 2023. Given the strong ownership and commitment of the government, besides the capacity of the EPA, the project’s outcomes are likely to be sustained. The project could be more proactive in disseminating and sharing learning with regions within the country as well as in tapping into lessons emerging in other countries within the East Africa region.

# Lesson

- Two crucial decisions UNDP took at the inception contributed to the project’s ability to deliver on most of its intended results: (a) the decision to co-locate the project management unit within the EPA; and (b) a small national staff team managing the project. These gave the project good access to EPA stakeholders and other ministries which helped in smooth communication flow and building good working relationships. This was especially important for this project, given the exclusive thrust on capacity building. For a project with a small budget, this approach also enabled linking with the regions and zones.

# Recommendations

R1:	Working with the EU and EPA, UNDP needs to engage at senior level with all key ministries to advocate for the need to invest adequate level of human resources in the MRV system within each ministry, and ensure inter-ministerial leadership to promote and strengthen the MRV regime through the existing inter-ministerial forum chaired by the Minister for Planning and Development.

R2:	Support EPA to develop and deliver regular training and refresher courses, including sector-specific training, related to MRV system. Apart from class-room teaching, this should also include greater structured sharing of experiences among regions and with other countries in East Africa region.

R3:	Working together with the EU project on MRV, assist EPA in developing capacity for cross-checking for consistency in all data in its reports.

R4:	In the remaining duration of the project, the QA/QC system should be embedded fully in the key categories sector identified by the EPA at woreda, zonal, regional and federal levels, and in other sectors ensure that the federal level consolidated data have gone through QA/QC.

R5:	Develop appropriate platforms/mechanisms for sharing of lessons and challenges with regions within the country and with other countries in the East Africa region.

# ANNEXES

# Annex 1: CONSULTANT TERMS OF REFERENCE GENERAL INFORMATION

INDIVIDUAL CONTRACT (IC)

PROPOSAL SUBMISSION FORM

Advertisement for Recruitment of International Individual consultant for a Consultancy service to undertake Project Midterm Review (MTR)

Procurement Notice Ref. No.:

Published (Posted on): 2022

Submission Deadline: October 28, 2022@ 10:30 AM (UTC+03:00) Addis Ababa/Nairobi Time Zone

United Nations Development Program (UNDP)

Addis Ababa, Ethiopia

Services/Work Description: To undertake Project Mid Term Review (MTR)

Project/Program Title: Capacity-building program to comply with the Paris Agreement and implement its transparency requirements at the national level

## Location: Addis Ababa, Ethiopia with travel to the selected Regions as deemed necessary

Type of Contract: Individual Contract

Post Level: International Consultant to undertake Project’s Midterm Review (MTR)

## Languages Required: English

Starting Date: (Immediately after the signing of the Contract)

Consultant Level: Level (C)

Expected Duration of Assignment: 45 days (October 31/2022 –December 9/2022)

BACKGROUND

# 1. INTRODUCTION

This is the Terms of Reference (ToR) for the UNDP-GEF Midterm Review (MTR) of the medium-sized project titled Capacity-building program to comply with the Paris Agreement and implement its transparency requirements at the national level (PIMS# 6208) implemented through the Federal Environmental Protection Authority. The project started on the 1 July 2020 and is in its Third year of implementation. In line with the UNDP-GEF Guidance on MTRs, this MTR process was initiated before the submission of the second Project Implementation Report (PIR). The MTR is delayed because of the new government restructure of the Environment Forest and Climate Change Commission (EFCCC) in to Environmental Protection Authority (EPA) it takes a long process and still EPA is under restructuring. This ToR sets out the expectations for this MTR.  The MTR process must follow the guidance outlined in the document Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects.

# 2.  PROJECT BACKGROUND INFORMATION

The project Goal is "By 2020 key Government institutions at federal and regional levels, including cities, are able better to plan, implement and monitor priority climate Change mitigation and adaptation actions and sustainable resource management.”

The project was designed to: The Government of Ethiopia (GoE) is a party to UNFCCC and is required to report all its GHG emissions and reduction efforts periodically as per the Paris Agreement and requirement. Incidentally, the Paris Agreement calls for Transparency in reporting for the GHG emissions to track both the emissions and the efforts given to the developing countries. Whilst the country is committed to global efforts of reducing GHG emissions through its Climate Resilient Green Economy, the country lacks the proper technical and institutional capacity to adhere to the Paris Agreement Frameworks. This challenge will inhibit the country to benefits from the financial and technological flows which have been identified as critical to the attainment of the country’s ambitious target of middle income by 2025. Capacity Building program to comply with the Paris Agreement and implement its transparency requirement at the national level project seeks to close the existing technical and institutional capacity challenges by enhancing institutional and technical capacity related to climate transparency in Ethiopia. This will be achieved by strengthening institutional and technical capacity for transparency through training and development of guideline.

The project’s key strategic areas in jettisoning the country’s challenges of measuring and reporting GHG emissions in accordance with the Paris Agreement will be based on two (2) components being;

- Institutional capacity development and,

- Technical capacity development tools, training and assistance

## Outcome 1.1: Strengthened institutional capacity for transparency-related activities

The work will culminate in the following project outputs:

- An established inter-ministerial body to provide oversight to the implementation of National Determined Contributions (NDC);

- Enhanced capacity of the stakeholders by lobby and advocating for clearly defined roles and tasks in climate change work sphere; and

- The establishment and operationalization of a national GHG emission inventory system.

## Outcome 2.1: Strengthened technical capacity for transparency-related activities, including tracking of progress towards attaining NDC

The work will culminate in the following project outputs:

- Developed guidelines for GHG emission mitigation policy measures;

- Guidelines for mainstreaming mitigation projects cost into public budgets and reporting processes;

- Development of training material on Paris Agreements and transparency;

- Trained manpower of IPCC 2006 guidelines; and

- Development of the Quality Assurance and Quality Control (QA/QC) guidelines.

Currently the project has established a well-functioning inter-ministerial body which provide oversight the implementation of the Climate Resilient Green Economy ( CRGE) and National Determined Contribution (NDC): The Directorate enhanced the capacity of the stakeholders through training and awareness creation which is basically build up the capacity of stakeholders (Regional, Zonal and Woreda level experts) on transparent GHGs emission inventory approaches, and guidelines that used for successful Measuring Reporting and Verifying  (MRV) and on mechanisms or approaches to mainstream CRGE into development plans and effectively implement both climate adaptation and mitigation actions at the grass root level.

The GHG database and information system facilitates the storage of key documentation and data, data sources, methods, assumptions used. The operationalization of a functional GHG database and information system will then allow the EPA to further engage stakeholders in the MRV process thus strengthening Ethiopia’s capacities to fulfil its enhanced transparency framework. . Currently the project developed a general, sector-specific, and cross-cutting Quality Assurance (QA) and Quality Control (QC) plan. The objective of the plan is to improve emission estimate by reducing the uncertainty of national GHG inventory reports. The plan will provide as a roadmap for the national Universities to implement a quality assurance, quality control (QA/QC) and verification procedures which is an important part of the development of a national greenhouse gas inventories, accounting and reporting on Green House Gas (GHG) mitigation actions. As part of a recommendation on project implementation reports (PIR) the project need to go through to a midterm evaluation (MTR) in order to identify challenges and outline corrective actions to ensure that a project is on track to achieve maximum results by its completion. The primary output/deliverable of this MTR process is the MTR report that will allow the project management unit to implement adaptive management actions if need it.

# 3.  MTR PURPOSE

The MTR will assess progress towards the achievement of the project objectives and outcomes as specified in the Project Document, and assess early signs of project success or failure with the goal of identifying the necessary changes to be made in order to set the project on-track to achieve its intended results. The MTR will also review the project’s strategy, its risks to sustainability.

MTR are very instrumental to assess the project progress so far and check whether the project is on Track or need adjustments. This exercise result is very instrumental for the donor, UNDP, Project Management Unit and implementing partner (Environmental Protection Authority). Moreover, the timing of the MTR review fits with UNDP Ethiopia Country office evaluation time table. Accordingly, the office will benefit from its result to assess its quality assurance responsibility.

# 4. MTR APPROACH & METHODOLOGY

The MTR must provide evidence based information that is credible, reliable and useful. The MTR team will review all relevant sources of information including documents prepared during the preparation phase (i.e. PIF, UNDP Initiation Plan, UNDP Environmental & Social Safeguard Policy, the Project Document, project reports including Annual Project Review/PIRs, project budget revisions, lesson learned reports, national strategic and legal documents, and any other materials that the team considers useful for this evidence-based review). The MTR team will review the baseline GEF focal area Tracking Tool submitted to the GEF at CEO endorsement, and the midterm GEF focal area Tracking Tool that must be completed before the MTR field mission begins.

The MTR consultant is expected to follow a collaborative and participatory approach ensuring close engagement with the Project Team, government counterparts (the GEF Operational Focal Point), the UNDP Country Office(s), UNDP-GEF Regional Technical Advisers, and other key stakeholders.

Engagement of stakeholders is vital to a successful MTR. Stakeholder involvement should include interviews with stakeholders who have project responsibilities, including but not limited to (Ministry of Agriculture (MOA), Ministry of Water and Energy (MOWE), Ministry of Industry (MOI), Ministry of Trade (MOT), Ministry of Mines (MOM),Ministry of Urban and infrastructure Development (MOUI, ); executing agencies, senior officials and task team/ component leaders, key experts and consultants in the subject area, Project Board, project stakeholders, academia, local government and CSOs, etc. Additionally, the MTR team is expected to conduct Federal level (Addis Ababa), Federal EPA.

The final MTR report should describe the full MTR approach taken and the rationale for the approach making explicit the underlying assumptions, challenges, strengths and weaknesses about the methods and approach of the review.

In general, the approach and methodology will be

- Conduct desk review

- Collect primary data using appropriate tools in line with evaluation questions and log frame indicators

- Key informant interview (KII) with program stakeholders and Focus Group Discussion (FGD) with communities

- Office visits to the implementation institutions

The final MTR report should describe the full MTR approach taken and the rationale for the approach making explicit the underlying assumptions, challenges, strengths and weaknesses about the methods and approach of the review.

# 5.  DETAILED SCOPE OF THE MTR

The MTR consultant will assess the following four categories of project progress. See the Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects for extended descriptions.

## i.    Project Strategy

Project design:

- Review the problem addressed by the project and the underlying assumptions.  Review the effect of any incorrect assumptions or changes to the context to achieving the project results as outlined in the Project Document.

- Review the relevance of the project strategy and assess whether it provides the most effective route towards expected/intended results. Were lessons from other relevant projects properly incorporated into the project design?

- Review how the project addresses country priorities. Review country ownership. Was the project concept in line with the national sector development priorities and plans of the country (or of participating countries in the case of multi-country projects)?

- Review decision-making processes: were perspectives of those who would be affected by project decisions, those who could affect the outcomes, and those who could contribute information or other resources to the process, taken into account during project design processes?

- Review the extent to which relevant gender issues were raised in the project design. See Annex 9 of Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects for further guidelines.

- If there are major areas of concern, recommend areas for improvement.

Results Framework/Log frame:

- Undertake a critical analysis of the project’s indicators and targets, assess how “SMART” the midterm and end-of-project targets are (Specific, Measurable, Attainable, Relevant, Time-bound), and suggest specific amendments/revisions to the targets and indicators as necessary.

- Are the project’s objectives and outcomes or components clear, practical, and feasible within its time frame?

- Examine if progress so far has led to, or could in the future catalyse beneficial development effects (i.e.

income generation, gender equality and women’s empowerment, improved governance etc...) that should be included in the project results framework and monitored on an annual basis.

- Ensure broader development and gender aspects of the project are being monitored effectively.  Develop and recommend SMART ‘development’ indicators, including sex-disaggregated indicators and indicators that capture development benefits.

## ii. Progress Towards Results

Progress Towards Outcomes Analysis:

Review the indicators against progress made towards the end-of-project targets using the Progress Towards Results Matrix and following the Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects; colour code progress in a “traffic light system” based on the level of progress achieved; assign a rating on progress for each outcome; make recommendations from the areas marked as “Not on target to be achieved” (red).

The MTR report should describe the objective of the project, the expected results and the development context. Much of this information is available from the Project Identification Form (PIF), and the Project Document.

This section should include:

- Development Context: how the project objectives align with the executing agency/implementing partners’ strategies and priorities and UNDP programming priorities

- Problems that the project sought to address: threats and barriers targeted

- The project description and strategy: objective, outcomes, and expected results,

- Project implementation arrangements: short descriptions of management arrangements, Project Team and/or management unit, Project Board, implementing partner arrangements, etc.

- Significant socio-economic and environmental changes since the beginning of project implementation and any other major external contributing factors

- Key partners and stakeholders involved in project implementation.

## Table. Progress towards Results Matrix (Achievement of outcomes against End-of-project Targets)

| Project Strategy | Indicator | Baselin e Level | Level in 1st PIR (self- reported) | Midter m Target | End- ofproject Target | Midterm Level & Assessmen t | Achieveme nt Rating | Justificati on for Rating |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: | Indicator (if applicable): |  |  |  |  |  |  |  |
| Outcome 1: | Indicator 1: |  |  |  |  |  |  |  |
|  | Indicator 2: |  |  |  |  |  |  |  |
| Outcome 2: | Indicator 3: |  |  |  |  |  |  |  |
|  | Indicator 4: |  |  |  |  |  |  |  |
|  | Etc. |  |  |  |  |  |  |  |
| Etc. |  |  |  |  |  |  |  |  |

## Indicator Assessment Key

| Green= Achieved | Yellow= On target to be achieved | Red= Not on target to be achieved |
| --- | --- | --- |

In addition to the progress towards outcomes analysis:

- Compare and analyse the GEF Tracking Tool at the Baseline with the one completed right before the Midterm Review.

- Identify remaining barriers to achieving the project objective in the remainder of the project.

- By reviewing the aspects of the project that have already been successful, identify ways in which the project can further expand these benefits.

### iii.   Project Implementation and Adaptive Management

Management Arrangements:

- Review overall effectiveness of project management as outlined in the Project Document.  Have changes been made and are they effective?  Are responsibilities and reporting lines clear?  Is decision-making transparent and undertaken in a timely manner?  Recommend areas for improvement.

- Review the quality of execution of the Executing Agency/Implementing Partner(s) and recommend areas for improvement.

- Review the quality of support provided by the GEF Partner Agency (UNDP) and recommend areas for improvement.

Work Planning:

- Review any delays in project start-up and implementation, identify the causes and examine if they have been resolved.

- Are work-planning processes results-based?  If not, suggest ways to re-orientate work planning to focus on results?

- Examine the use of the project’s results framework/ logframe as a management tool and review any changes made to it since project start.

Finance and co-finance:

- Consider the financial management of the project, with specific reference to the cost-effectiveness of interventions.

- Review the changes to fund allocations as a result of budget revisions and assess the appropriateness and relevance of such revisions.

- Does the project have the appropriate financial controls, including reporting and planning, that allow management to make informed decisions regarding the budget and allow for timely flow of funds?

- Informed by the co-financing monitoring table to be filled out, provide commentary on co-financing: is co-financing being used strategically to help the objectives of the project? Is the Project Team meeting with all co-financing partners regularly in order to align financing priorities and annual work plans?

| Sources of Cofinancing | Name of Cofinancer | Type of Cofinancing | Co-financing amount confirmed at CEO Endorsement (US$) | Actual Amount Contributed at stage of Midterm Review (US$) | Actual % of Expected Amount |
| --- | --- | --- | --- | --- | --- |
| Government |  |  |  |  |  |
|  |  | TOTAL |  |  |  |

Project-level Monitoring and Evaluation Systems:

- Review the monitoring tools currently being used:  Do they provide the necessary information? Do they involve key partners? Are they aligned or mainstreamed with national systems?  Do they use existing information? Are they efficient? Are they cost-effective? Are additional tools required? How could they be made more participatory and inclusive?

- Examine the financial management of the project monitoring and evaluation budget.  Are sufficient resources being allocated to monitoring and evaluation? Are these resources being allocated effectively?

Stakeholder Engagement:

- Project management: Has the project developed and leveraged the necessary and appropriate partnerships with direct and tangential stakeholders?

- Participation and country-driven processes: Do local and national government stakeholders support the objectives of the project?  Do they continue to have an active role in project decision-making that supports efficient and effective project implementation?

- Participation and public awareness: To what extent has stakeholder involvement and public awareness contributed to the progress towards achievement of project objectives?

Reporting:

- Assess how adaptive management changes have been reported by the project management and shared with the Project Board.

- Assess how well the Project Team and partners undertake and fulfil GEF reporting requirements (i.e. how have they addressed poorly-rated PIRs, if applicable?)

- Assess how lessons derived from the adaptive management process have been documented, shared with key partners and internalized by partners.

Communications:

- Review internal project communication with stakeholders: Is communication regular and effective? Are there key stakeholders left out of communication? Are there feedback mechanisms when communication is received? Does this communication with stakeholders contribute to their awareness of project outcomes and activities and investment in the sustainability of project results?

- Review external project communication: Are proper means of communication established or being established to express the project progress and intended impact to the public (is there a web presence, for example? Or did the project implement appropriate outreach and public awareness campaigns?)

- For reporting purposes, write one half-page paragraph that summarizes the project’s progress towards results in terms of contribution to sustainable development benefits, as well as global environmental benefits.

### iv.   Sustainability

- Validate whether the risks identified in the Project Document, Annual Project Review/PIRs and the ATLAS Risk Management Module are the most important and whether the risk ratings applied are appropriate and up to date. If not, explain why.

- In addition, assess the following risks to sustainability:

Financial risks to sustainability:

- What is the likelihood of financial and economic resources not being available once the GEF assistance ends (consider potential resources can be from multiple sources, such as the public and private sectors, income generating activities, and other funding that will be adequate financial resources for sustaining project’s outcomes)?

Socio-economic risks to sustainability:

- Are there any social or political risks that may jeopardize sustainability of project outcomes? What is the risk that the level of stakeholder ownership (including ownership by governments and other key stakeholders) will be insufficient to allow for the project outcomes/benefits to be sustained? Do the various key stakeholders see that it is in their interest that the project benefits continue to flow? Is there sufficient public / stakeholder awareness in support of the long term objectives of the project? Are lessons learned being documented by the Project Team on a continual basis and shared/ transferred to appropriate parties who could learn from the project and potentially replicate and/or scale it in the future?

Institutional Framework and Governance risks to sustainability:

- Do the legal frameworks, policies, governance structures and processes pose risks that may jeopardize sustenance of project benefits? While assessing this parameter, also consider if the required systems/ mechanisms for accountability, transparency, and technical knowledge transfer are in place.

Environmental risks to sustainability:

- Are there any environmental risks that may jeopardize sustenance of project outcomes?

### Conclusions & Recommendations

The MTR team will include a section of the report setting out the MTR’s evidence-based conclusions, in light of the findings.

Recommendations should be succinct suggestions for critical intervention that are specific, measurable, achievable, and relevant. A recommendation table should be put in the report’s executive summary. See the Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects for guidance on a recommendation table.

The MTR team should make no more than 15 recommendations total.

### Ratings

The MTR team will include its ratings of the project’s results and brief descriptions of the associated achievements in a MTR Ratings & Achievement Summary Table in the Executive Summary of the MTR report. See Annex E for ratings scales. No rating on Project Strategy and no overall project rating is required.

### Table. MTR Ratings & Achievement Summary Table for (Capacity-building program to comply with the Paris Agreement and implement its transparency requirements at the national level)

| Measure | MTR Rating | Achievement Description |
| --- | --- | --- |
| Project Strategy | N/A |  |
| Progress Towards Results | Objective Achievement Rating: (rate 6 pt. scale) |  |
|  | Outcome 1 Achievement |  |
|  | Rating: (rate 6 pt. scale) |  |
|  | Outcome 2 Achievement Rating: (rate 6 pt. scale) |  |
| Project Implementation & Adaptive Management | (rate 6 pt. scale) |  |
| Sustainability | (rate 4 pt. scale) |  |

# 6. TIMEFRAME

The total duration of the MTR will be approximately (45 days) over a time period of (4 of weeks) (October 31/2022 –December 9/2022) starting (after agreement), and shall not exceed five months from when the consultant(s) are hired. The tentative MTR timeframe is as follows:

| ACTIVITY | NUMBER OF WORKING DAYS | COMPLETION DATE (45 days) (October 31/2022 –December 9/2022) |
| --- | --- | --- |

Document review and preparing MTR Inception Report 	5 days) 	4

(MTR Inception Report due no later than 2 weeks before

the MTR mission)

MTR mission: stakeholder meetings, interviews, office 	10 days 	10

visits

Preparation and Presentation of initial findings- last day of 	1 day 	1

the MTR mission

Preparing draft report (due within 3 weeks of the MTR 	10 days 	10

mission)

Finalization of MTR report/ Incorporating audit trail from 	5days 	5

feedback on draft report (due within 1 week of receiving

UNDP comments on the draft) (note: accommodate time delay

in dates for circulation and review of the draft report)

Options for site visits should be provided in the Inception Report.

# 7. MIDTERM REVIEW DELIVERABLES

| # | Deliverable | Description | Timing (October 31/2022 – December 9/2022) | Responsibilities |
| --- | --- | --- | --- | --- |
| 1 | MTR Inception Report | MTR team clarifies objectives and methods of Midterm Review | In four days of contract signature Nov 14/2022 | MTR consultant submits to the Commissioning Unit and project management |
| 2 | Presentation | Initial Findings | End of MTR mission: Nov 18/2022 | MTR consultant presents to project management and the Commissioning Unit |
| 3 | Draft Final Report | Full report (using guidelines on content outlined in Annex B) with annexes | Within 3 weeks of the MTR mission: Dec 2/2022 | Sent to the Commissioning Unit, reviewed by RTA, Project Coordinating Unit, GEF OFP |
| 4 | Final Report* | Revised report with audit trail detailing how all received comments have (and have not) been addressed in the final MTR report | Within 5 days of receiving UNDP comments on draft: Dec 9/2022 | Sent to the Commissioning Unit |

*The final MTR report must be in English. If applicable, the Commissioning Unit may choose to arrange for a translation of the report into a language more widely shared by national stakeholders.

# 8. MTR ARRANGEMENTS

The principal responsibility for managing this MTR resides with the Commissioning Unit. The Commissioning Unit for this project’s MTR is UNDP/EPA.

The Project Team will be responsible for liaising with the MTR team to provide all relevant documents, set up stakeholder interviews, and arrange field visits.

# 9.  TEAM COMPOSITION

One independent international consultant will conduct the MTR - (with experience and exposure to projects and evaluations in other regions globally). The consultant cannot have participated in the project preparation, formulation, and/or implementation (including the writing of the Project Document) and should not have a conflict of interest with project’s related activities.

The selection of consultant will be qualities in the following areas: 70%

- 10 years of recent experience with result-based management evaluation methodologies; Experience applying SMART indicators and reconstructing or validating baseline scenarios; 15%

- Competence in adaptive management, as applied to Climate Change focal area; Work experience in relevant technical areas for at least 10 years; 20%

- Experience working with the GEF or GEF-evaluations; and Experience working in (Eastern African region of project); 15%

- 4 years of experience of issues related to gender and (Improving women's participation and decisionmaking power; experience in gender sensitive evaluation and analysis). Demonstrable analytical skills; Project evaluation/review experiences within United Nations system will be considered an asset; 15%

- A Master’s degree in Climate change, sustainable development, Environmental Science/Environmental Studies) or other closely related field. 5%

# 10. ETHICS

The MTR team will be held to the highest ethical standards and is required to sign a code of conduct upon acceptance of the assignment. This MTR will be conducted in accordance with the principles outlined in the UNEG ‘Ethical Guidelines for Evaluation’. The MTR team must safeguard the rights and confidentiality of information providers, interviewees and stakeholders through measures to ensure compliance with legal and other relevant codes governing collection of data and reporting on data. The MTR team must also ensure security of collected information before and after the MTR and protocols to ensure anonymity and confidentiality of sources of information where that is expected. The information, knowledge and data gathered in the MTR process must also be solely used for the MTR and not for other uses without the express authorization of UNDP and partners.

# 11. PAYMENT SCHEDULE

- 20% payment upon satisfactory delivery of the final MTR Inception Report and approval by the Commissioning Unit

- 30% payment upon satisfactory delivery of the draft MTR report to the Commissioning Unit

- 50% payment upon satisfactory delivery of the final MTR report and approval by the Commissioning Unit and RTA (via signatures on the TE Report Clearance Form) and delivery of completed TE Audit Trail

Criteria for issuing the final payment of 40%:

- The final MTR report includes all requirements outlined in the MTR TOR and is in accordance with the MTR guidance.

- The final MTR report is clearly written, logically organized, and is specific for this project (i.e. text has not been cut & pasted from other MTR reports).

- The Audit Trail includes responses to and justification for each comment listed.

# 12. APPLICATION PROCESS

| Criteria |  | Weight | Max. Point |
| --- | --- | --- | --- |
| Technical Competence (based on CV, Proposal and interview (if required) |  | 70% | 100 |
| Criteria a. Educational relevance: close fit to post |  |  | 10 |
| Criteria b. Understanding the scope of work and organization of the proposal |  |  | 50 |
| Criteria c. Experience of similar assignment |  |  | 30 |
| Criteria d. Previous work experience in Africa/ Ethiopia |  |  | 10 |
| Financial (Lower Offer/Offer*100) 30% 30 |  | 30% | 30 |
| Total Score | Technical Score * 70% + Financial Score * 30% |  |  |

Recommended Presentation of Proposal:

## a) Letter of Confirmation of Interest and Availability using the template11 provided by UNDP; b) CV and a Personal History Form (P11 form12);

- Brief description of approach to work/technical proposal of why the individual considers him/herself as the most suitable for the assignment, and a proposed methodology on how they will approach and complete the assignment; (max 1 page)

- Financial Proposal that indicates the all-inclusive fixed total contract price and all other travel related costs (such as flight ticket, per diem, etc), supported by a breakdown of costs, as per template attached to the Letter of Confirmation of Interest template.  If an applicant is employed by an organization/company/institution, and he/she expects his/her employer to charge a management fee in the process of releasing him/her to UNDP under Reimbursable Loan Agreement (RLA), the applicant must indicate at this point, and ensure that all such costs are duly incorporated in the financial proposal submitted to UNDP.

All application materials should be submitted to the address (procurement.et@undp.org) in a sealed envelope indicating the following reference “Consultant for (Capacity-building program to comply with the Paris Agreement and implement its transparency requirements at the national level) Midterm Review” or by email at the following address ONLY: (procurement.et@undp.org) by (tentative date October 28,2022@ 10:30 AM in the morning) Time Zone: (UTC+03:00) Addis Ababa/Nairobi. Incomplete applications will be excluded from further consideration.

Criteria for Evaluation of Proposal:  Only those applications which are responsive and compliant will be evaluated.  Offers will be evaluated according to the Combined Scoring method – where the educational background and experience on similar assignments will be weighted at 70% and the price proposal will weigh as 30% of the total scoring.  The applicant receiving the Highest Combined Score that has also accepted UNDP’s General Terms and Conditions will be awarded the contract.

## ToR ANNEX A: List of Documents to be reviewed by the MTR Team

- PIF

- UNDP Initiation Plan

- UNDP Project Document

- UNDP Social and Environmental Screening Procedure (SESP)

- Project Inception Report

- All Project Implementation Reports (PIR’s)

- Quarterly progress reports and work plans of the various implementation task teams

- Audit report

- Finalized GEF focal area Tracking Tools/Core Indicators at CEO endorsement and midterm (Climate change focal area/ ensure transparency framework.

- Oversight mission reports

- All monitoring reports prepared by the project

- Financial and Administration guidelines used by Project Team

The following documents will also be available:

- Project operational guidelines, manuals and systems

14. UNDP country/countries programme document(s)

### 15. Minutes of the (Capacity-building program to comply with the Paris Agreement and implement its transparency requirements at the national level) Board Meetings and other meetings (i.e. Project Appraisal Committee meetings)

- Project site location maps

- Any additional documents, as relevant.

## ToR ANNEX B: Guidelines on Contents for the Midterm Review Report

i. 	Basic Report Information (for opening page or title page)

- Title of  UNDP supported GEF financed project

- UNDP PIMS# and GEF project ID#

- MTR time frame and date of MTR report

- Region and countries included in the project

- GEF Operational Focal Area/Strategic Program

- Executing Agency/Implementing Partner and other project partners

- MTR team members

- Acknowledgements ii.  	Table of Contents iii. 	Acronyms and Abbreviations 1. 		Executive Summary (3-5 pages)

- Project Information Table

- Project Description (brief)

- Project Progress Summary (between 200-500 words)

- MTR Ratings & Achievement Summary Table

- Concise summary of conclusions

- Recommendation Summary Table

- Introduction (2-3 pages)

    - Purpose of the MTR and objectives

    - Scope & Methodology: principles of design and execution of the MTR, MTR approach and data collection methods, limitations to the MTR

    - Structure of the MTR report

- Project Description and Background Context (3-5 pages)

    - Development context: environmental, socio-economic, institutional, and policy factors relevant to the project objective and scope

    - Problems that the project sought to address: threats and barriers targeted

    - Project Description and Strategy: objective, outcomes and expected results, description of field

sites (if any)

    - Project Implementation Arrangements: short description of the Project Board, key implementing partner arrangements, etc.

    - Project timing and milestones

    - Main stakeholders: summary list

- Findings (12-14 pages)

  - Project Strategy

      - Project Design

      - Results Framework/Logframe

  - Progress Towards Results

      - Progress towards outcomes analysis

      - Remaining barriers to achieving the project objective

  - Project Implementation and Adaptive Management

      - Management Arrangements

      - Work planning

      - Finance and co-finance

      - Project-level monitoring and evaluation systems

      - Stakeholder engagement

      - Social and Environmental Standards (Safeguards)

      - Reporting

      - Communications & Knowledge Management

  - Sustainability

      - Financial risks to sustainability

      - Socio-economic to sustainability

      - Institutional framework and governance risks to sustainability

      - Environmental risks to sustainability

- Conclusions and Recommendations (4-6 pages)

  - Conclusions

 	Comprehensive and balanced statements (that are evidence-based and connected to the

MTR’s findings) which highlight the strengths, weaknesses and results of the project

  - Recommendations

      - Corrective actions for the design, implementation, monitoring and evaluation of the project

      - Actions to follow up or reinforce initial benefits from the project

      - Proposals for future directions underlining main objectives

- Annexes

    - MTR ToR (excluding ToR annexes)

    - MTR evaluative matrix (evaluation criteria with key questions, indicators, sources of data, and methodology)

    - Example Questionnaire or Interview Guide used for data collection

    - Ratings Scales

    - MTR mission itinerary

    - List of persons interviewed

    - List of documents reviewed

    - Co-financing table (if not previously included in the body of the report)

    - Signed UNEG Code of Conduct form

    - Signed MTR final report clearance form

    - Annexed in a separate file: Audit trail from received comments on draft MTR report

    - Annexed in a separate file: Relevant midterm tracking tools (METT, FSC, Capacity scorecard, etc.) or Core Indicators

    - Annexed in a separate file: GEF Co-financing template (categorizing co-financing amounts by source as ‘investment mobilized’ or ‘recurrent expenditure’)

## ToR ANNEX D: UNEG Code of Conduct for Evaluators/Midterm Review Consultants

Evaluators/Consultants:

- Must present information that is complete and fair in its assessment of strengths and weaknesses so that decisions or actions taken are well founded.

- Must disclose the full set of evaluation findings along with information on their limitations and have this accessible to all affected by the evaluation with expressed legal rights to receive results.

- Should protect the anonymity and confidentiality of individual informants. They should provide maximum notice, minimize demands on time, and respect people’s right not to engage. Evaluators must respect people’s right to provide information in confidence, and must ensure that sensitive information cannot be traced to its source. Evaluators are not expected to evaluate individuals, and must balance an evaluation of management functions with this general principle.

- Sometimes uncover evidence of wrongdoing while conducting evaluations. Such cases must be reported discreetly to the appropriate investigative body. Evaluators should consult with other relevant oversight entities when there is any doubt about if and how issues should be reported.

- Should be sensitive to beliefs, manners and customs and act with integrity and honesty in their relations with all stakeholders. In line with the UN Universal Declaration of Human Rights, evaluators must be sensitive to and address issues of discrimination and gender equality. They should avoid offending the dignity and self-respect of those persons with whom they come in contact in the course of the evaluation. Knowing that evaluation might negatively affect the interests of some stakeholders, evaluators should conduct the evaluation and communicate its purpose and results in a way that clearly respects the stakeholders’ dignity and self-worth.

- Are responsible for their performance and their product(s). They are responsible for the clear, accurate and fair written and/or oral presentation of study limitations, findings and recommendations.

- Should reflect sound accounting procedures and be prudent in using the resources of the evaluation.

- Must ensure that independence of judgement is maintained and that evaluation findings and recommendations are independently presented.

- Must confirm that they have not been involved in designing, executing or advising on the project being evaluated.

MTR Consultant Agreement Form

Agreement to abide by the Code of Conduct for Evaluation in the UN System:

Name of Consultant: Abhijit Bhattacharjee___________________________________________________________________

Name of Consultancy Organization (where relevant): __________________________________________

I confirm that I have received and understood and will abide by the United Nations Code of Conduct for Evaluation.

Signed at _____________________________________  (Place)     on ______20.12.2022______________________    (Date)

Signature: ___________________________________

# Annex 2: CBIT MTR Evaluation  Matrix

| Project Strategy: To what extent is the project strategy and design relevant to country priorities, country ownership, and the provide best route towards expected results? |  |  |  |
| --- | --- | --- | --- |
| Evaluative questions (EQ) | Indicators/Judgment criteria | Data sources | Method of data collection and analysis |
| 1. To what extent the project addressed priority needs of the country, and were the focus of the project in line with the national sector development priorities and plans of the country? | The project continues to address key MRV needs for ENDC as identified in the Assessment of Ethiopia Institutional Capacity; the project continues to focus on strengthening inter-institutional system for oversight, standardization and sharing of GHG emission and mitigation data. | Ethiopia RCGE strategy; ENDC; 1st and 2nd National Communication (NC); Ten Year Perspective Development Plan; Home Grown Economic Reform Programme; Inter-ministerial oversight body; Project Board | Desk review and KII; Qualitative analysis |
| 2. Was the project design coherent in the country context and were the assumptions made in the design stage valid during the course of implementation? If not, were adjustments made based on evidence and lessons? | The project design and assumptions underpinning the change pathway for the two outcomes remained valid during implementation, or were adjusted for any changes in the context. | ToC, Prodoc and Results framework, PMU, EPA, other complementary projects (TASCA, ICAT, SRPC), World Bank, UNEP, FAO | Desk review and KII; Meta analysis of qualitative data |
| 3. Were perspectives of those who would be affected by the project, those who could affect the outcomes, and those who could contribute information or other expertise to the process, taken into account during the project design process? | Evidence of consultation with line Ministries, EPA (former EFCCC), and complementary ongoing projects during project design and inception phase. | PMU, EPA, other complementary projects (TASCA, ICAT, SRPC), MoA, MoWIE, MoI, MOT, Ministry of Urban Development and Construction, MoF. | KII. Qualitative analysis of interview data |
| 4. Was the project’s results framework coherent in clearly stating in realistic terms the anticipated outcomes and outputs, and did the corresponding indicators/targets render themselves to be monitored and measured adequately during the course of implementation? | The results chain and targets in the results framework were SMART and evidence shows that these were used for regular monitoring and annual reporting through PIRs. | PIRs for 2021 and 2022, Monitoring reports; EPA, PMU, Steering Committee | Desk review and KII; Content analysis of qualitative data |
| 5. To what extent was the project design and its implementation process based on a gender-sensitive approach that proactively worked to promote gender equality? | The Prodoc clearly identifies gender issues and corresponding strategies to address gender equality, and subsequent implementation shows that the project has actively pursued these. | Prodoc, PIRs for 2021 and 2022; EPA, PMU | Desk review and KII; Content analysis of qualitative data |
| Progress towards results: To what extent have the expected outcomes and objectives of the project been achieved thus far? |  |  |  |
| 6. By reviewing the programme results and resources framework, is the CBIT programme on track to achieve intended results at the outcome and output levels? How does the progress so far compare against end-of-project targets envisaged in the results matrix and GEF tracking tool baseline? | Analysis of Key outputs and indicators as per Box 1 and changes resulting from these clearly establish CBIT’s distinctive contribution; comparison of baseline and mid-term tracking tools show progress towards the intended endline as per the results matrix. | Prodoc, PIRs for 2021 and 2022, Mid-term tracking tools matrix; EPA, PMU, MoA, MoWIE, MoI, MOT, Ministry of Urban Development and Construction, MoF, Ministry of Mines, Space Science and Geospatial Institute | Desk review, KII. Contribution analysis through mixed-method data; Process tracing; TT compilation and rating using GEF rating scale |
| 7. What are the factors (positive and negative) that contributed to the success or shortcomings in implementation of the project? What lessons can be drawn from the experience so far? | Analysis of Key outputs ad indicators as per Box 1 and changes resulting from these clearly establish CBTI’s distinctive contribution | Same as those for EQ6 | Desk review, KII. Contribution analysis and process tracing |
| 8. Were there significant changes in the social, economic and environmental context in the country and how did these affect the achievement of project results? | Linked to JC for EQ7 | Same as those for EQ6 | Desk review, KII. Contribution analysis and process tracing |
| 9. How well did the project collaborate with other similar ongoing initiatives in the country to ensure effectiveness of interventions and greater impact? To what extent has the project been effective in building synergies and leveraging other programmes and stakeholders in the country? | The project has created synergies working closely with TASCA, ICAT, SRPC and other similar initiatives in the country, with clear delineation of its role vis-à-vis others to ensure a multiplier effect of all initiatives together. | EPA, TASCA, ICAT, SRPC, EU, Italian Cooperation, World Resources Institute, World Bank, UNEP, FAO | KII. Qualitative analysis of interview data |
| Project implementation and adaptive management: To what extent the project management and leadership aspects enabled smooth planning, execution, efficient financing and funds management, monitoring, reporting and communications, and engagement with stakeholders? |  |  |  |
| 10. Were the project management structure, system and their functioning sufficiently streamlined with clear lines of responsibility and roles to enable efficient planning and execution of projects activities? | The Project Board has established clear lines of accountability and reporting, managed on a day-to-day basis by the PMU; UNDP as GEF partner agency providing effective and timely support in implementation of the project | EPA, PMU, UNDP, MoA, MoWIE, MoI, MOT, Ministry of Urban Development and Construction, MoF, Ministry of Mines, Space Science and Geospatial Institute; Annual Workplans and project implementation schedule. | KII & desk review; Qualitative analysis of interview data |
| 11. Is the project being managed in a cost-effective and cost-efficient manner with good financial control and management of funds? Is co-financing being used strategically to help the objectives of the project? | Project management demonstrates Cost efficiency, Quality, Timeliness (CQT) factors being taken into consideration throughout the implementation cycle; co-financing by UNDP and GoE used strategically. | EPA, PMU, UNDP Finance, RTA | KII; Co-financing Table compilation |
| 12. Is the monitoring system generating relevant data in a timely manner that enables good project management and reporting? | Monitoring data generates gender-disaggregated data and output and outcome-oriented data for progress reports, and evidence of good project reporting for GEF. | Monitoring reports, PIRs; EPA, PMU, RTA | Qualitative assessment |
| 13. Has the project developed and leveraged necessary and appropriate partnerships with direct and tangential stakeholders? Do national and subnational government stakeholders support the objectives of the project and continue to have an active role in project decision-making that supports efficient and effective project implementation? | Linked to JC for EQ9; All stakeholders (EPA, PMU, MoA, MoWIE, MoI, MOT, Ministry of Urban Development and Construction, MoF, Ministry of Mines, Space Science and Geospatial Institute) actively involved in project decision-making and implementation. | Prodoc, PIRs for 2021 and 2022; EPA, PMU, RTA, MoA, MoWIE, MoI, MOT, Ministry of Urban Development and Construction, MoF, Ministry of Mines, Space Science and Geospatial Institute. EPA, TASCA, ICAT, SRPC, EU, Italian Cooperation, World Resources Institute, World Bank, UNEP, FAO | KII; Qualitative assessment |
| 14. Were adaptive management changes and lessons reported by the project management and shared with the Project Board, and to what extent these lessons were disseminated for wider learning? | Monitoring data being used in adaptive management of the project and reported to Project Board, and lessons are systematically documented and shared. | EPA, PMU, RTA, MoA, MoWIE, MoI, MOT, Ministry of Urban Development and Construction, MoF, Ministry of Mines, Space Science and Geospatial Institute. | KII; Qualitative assessment |
| 15. Are there adequate communication established with stakeholders/ partners to enhance their awareness of project progress and challenges, and is there a system to disseminate the project progress and intended impact to the public or government? | Effective communication established with partners; relevant lessons from the project are used for advocacy and communication with GoE and regional governments. | Policy/advocacy papers; EPA, PMU, RTA, MoA, MoWIE, MoI, MOT, Ministry of Urban Development and Construction, MoF, Ministry of Mines, Space Science and Geospatial Institute. | KII & desk review; Qualitative analysis of interview data |
| SUSTAINABILITY: The extent to which the net benefits of the project continue, or are likely to continue beyond the life of the project. |  |  |  |
| 16. What is the likelihood of financial and economic resources being available once the GEF assistance ends that will be adequate for sustaining the project outcomes? | Budgetary support for continuation of MRV related activities are available within the EPA; Lessons learned are shared/ transferred to appropriate agencies who could learn from the project and potentially replicate and/or scale up in the future. | EPA, PMU, MOF | KII; Risk register review; Qualitative analysis of interview data |
| 17. Are there any social or political risks that may jeopardize sustainability of project outcomes? What is the risk that the level of stakeholder ownership (including ownership by governments and other key stakeholders) will be insufficient to allow for the project outcomes/benefits to be sustained? | Strong ownership of the project by the GoE; Risks were clearly identified in the Prodoc and are being monitored regularly to reduce likelihood of these affecting the project’s sustainability. | EPA, PMU | KII; Validation of the risk matrices in the Prodoc and PIRs |
| 18. To what extent are policy and regulatory frameworks in place that will support the continuation of benefits? Do the legal frameworks, policies, governance structures and processes pose risks that may jeopardize sustenance of project benefits? | Policies, regulatory frameworks and government structure has been stable, and measures are in place for the project benefits to sustain should any change in structure and processes take place. | EPA, PMU, MOF | KII; Validation of the risk matrices in the Prodoc and PIRs |
| 19. Are there any environmental risks that may jeopardize sustenance of project outcomes? | Risk register updated regularly for any environmental concerns, if any, that may affect the project. | EPA, PMU | Desk review, KII. Content analysis |

# Annex 3 – List of key documents consulted

UNDP Ethiopia CBIT MTR, March 2023

List of Key Documents

Basal Consulting. Report on Situational Assessment of Greenhouse Gas (GHG) Mitigation Policy for Waste Management, Light Transit and Biofuel, Environmental Protection Agency, December 2021.

Basal Consulting, Development of Quality Control (QC) and Quality Assurance (QA) Plan for Green House Gas Inventory, June 2022

Environment, Forest and Climate Change Commission, UNDP & GEF. Report of the Inception Workshop for the Project "Capacity Building Initiative for Transparency (CBIT)", Oct 27, 2020

Environmental Protection Authority, CBIT – Steering Committee Meeting minutes, 25 January 2022

Environmental Protection Authority, CBIT – First Steering Committee Meeting minutes, 22 October 2020

Environmental Protection Authority, General Greenhouse Gas (GHG) Mitigation Policy Assessment Guideline, June 2022

Ethiopia Environmental Protection Authority, UNDP/GEF. UNDP Ethiopia Annual Report 2020-2021 intervention highlight templates

Ethiopian Environmental Protection Authority, Ethiopia’s GHG Emission and Mitigation (2020 & 2021) – Implementation Assessment Report, September 2022

Federal Republic of Ethiopia, Ethiopia’s Climate Resilient Green Economy National Adaptation Plan, May 2019

Federal Government Ethiopia, Updated Nationally Determined Contribution, July 2021

Federal Republic of Ethiopia, Environmental Protection Authority, Ethiopia’s First Biennial Update Report (FBUR) Under the United Nations Framework Convention on Climate Change (UNFCCC) (Final Report), February, 2023

Federal Republic of Ethiopia, Environmental Protection Authority, Ethiopia’s GHG Emission and Mitigation (2020 &2021) – Implementation Assessment Report, September 2022

Federal Republic of Ethiopia, UNDP/GEF, Project Implementation Report (PIR) 2022 – CBIT Ethiopia

Federal Democratic Republic of Ethiopia, Environmental Protection Authority. Ethiopia’s Third National Communication to the United Nations Framework Convention on Climate Change (UNFCCC), 2018

GEF-6 PROJECT IDENTIFICATION FORM (PIF), TYPE OF TRUST FUND: Capacity Building Initiative for Transparency, Capacity-building program to comply with the Paris Agreement and implement its transparency requirements at the national level, Ethiopia (GEF ID 9967), 2018.

GEF-6 REQUEST FOR PROJECT ENDORSEMENT/APPROVAL - Capacity-building program to comply with the Paris Agreement and implement its transparency requirements at the national level (CBIT)

UN Evaluation Group, UNEG Ethical Guidelines for Evaluation, 2020

UNDP-GEF, Guidance for Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects, 2014

UNDP, Project document: Capacity-building program to comply with the Paris Agreement and implement its transparency requirements at the national level, 2019

UNDP, Capacity-Building Program to Comply with the Paris Agreement and Implement its Transparency Requirements at the National Level, Project Report for Year 2020/2021

UNDP/Federal Government of Ethiopia, Financing Strategy for Updated Ethiopia’s Nationally Determined Contribution & its Implementation Plan, October 2021

UNDP/GEF, Project Implementation Report (PIR) 2021 – CBIT Ethiopia

UNDP/GEF, Project Implementation Report (PIR) 2022 – CBIT Ethiopia

UNEG, Norms and Standards for Evaluation in the UN System, 2016

UNFCC, 2006 IPCC Guidelines for National Greenhouse Gas Inventories and its subsequent amendment (2019).

UNFCC, Handbook on Measurement, Reporting and Verification for developing country Parties, 2014

# ANNEX 4: List of Key Informant Interviews

UNDP Ethiopia CBIT MTR, March 2023

List of Key Informant Interviews

Name				Organization				Title/Role

1, Yizengoul Yitayih		Ministry of Transport & Logistics, GoE	Climate Change Senior Expert

2. Dr. Yosef Melka.                   Environmental Protection Authority	National Focal Point for CC 									Budget Support (EU Project)

3. Brahanau Alamu.                  UNDP, Ethiopia				M&E Specialist

4. Getnet Demissie.                  UNDP, Ethiopia				M&E Officer

5. Dr. Tessama Toru	Haramaya University			Assistant Professor, Environmental 								Sciences

6. Esmael Mohammed	Ministry of industry			Team Leader, Climate Change

7. Heiru Sebrala Ahmed           Ethiopia Forestry Development		Director, Forest Resources Assessment								& Monitoring Directorate

8. Gatechew Shiferaw              Ministry of Urban and Infrastructure	Environment Protection Infrastructure 								Engineer

9. Benti Firdissa.                        GHG Emissions Verification Directorate	Director

10. Getnet Abate                       UNDP-EPA project			Project Manager, CBIT

11. Altaye Yebo Gilo.                 Sidama Regional EPA			Environment Officer

12. Toleso Benbi.                       Ministry of Agriculture		 	Sr. Environment & Climate Change Expert

13. Tagay Hamza                        Ministry of Water & Energy		Sr. Expert & MRV Focal Person

14. Fisseha Alemoyehu             UNDP-EPA project			Finance Officer, CBIT

15. Wubua Mekonnen              UNDP, Ethiopia				Team Leader, Climate Change & 									Environment

16. Henock Atnafe                     Ministry of Mines			Public Health Specialist

17. Ms. Fentu Kifle                       Addis Ababa City Administration	Team Leader, /climate Change 									Mainstreaming

18. Misganaw Eyassu                Ministry of Finance, GoE			Programme Coordinator, CRGE Unit

# Annex 5: MTR Consultant Itinerary

| Date | Activity |
| --- | --- |
| 05 Feb | Travel London-Addis Ababa |
| 06 Feb | Arrival Addis Ab; Meetig with CBIT |
| 07 Feb | Meetings with Min. of Transport and Focal point for EU project; meeting with CBIT |
| 08 Feb | Meetings with Min. of Industry, UNDP, Haramay University, Forestry Department |
| 09 Feb | Meetings with Min. of Urban and Infrastructure Development, MVA Directorate |
| 10 Feb | Meetings with Sidama Regional State (online); meetings with CBIT |
| 13 Feb | Meetings with Min. of Agriculture, Min. of Water and Energy; CBIT Project Manager |
| 14 Feb | Meetings with CBIT ad warp up |
| 15 Feb | Travel Addis Ab-London |

# Annex 6 – Interview Guide

A. UNDP staff (including PMU)

(Interviewer: at the start, provide brief introduction about the aim of the evaluation, evaluation protocol and ethics, how data will be used, outline confidentiality protocol, obtain permission to take notes, agree time needed for the interview – about 50-60 minutes – with some individuals, the evaluator may need to negotiate more than one session; introducing each other).

Before each interview, the interviewer to select maximum of 8-10 priority questions for each individual interviewee, depending on an understanding of the latter’s role and functional expertise. Questions may be amended/adapted/ supplemented as the interviews progress to allow for deeper probing.

Inter-ministerial

- How established/functional is the inter-ministerial mechanism for oversight on a whole-of-government approach to GHG emission/mitigation monitoring and data system? What specifically has been the role of CBIT in this regard?

- Is there now a coordinated approach to data sharing by various ministries, particularly in the waste, AFOLU, energy and IPPU sectors? Does the mechanism for collating and sharing these data function effectively as per 2006 IPCC guidelines?

Project design and ToC

- What was the causal pathway envisaged in the project design and what were the rationale for selecting this pathway? What were the key drivers envisaged for the change to happen?

- Were alternative pathways explored?

- What were the assumptions made, and have these been found to be valid? Was any change in the overall design necessitated in the course of implementation?

Consultation

- Who were involved in design of the project? Were relevant line ministries and other complementary project holders consulted to determine where CBIT created the most value?

- If no evidence of such consultations is recorded/recalled, what is the general consultation practice within UNDP when new projects are formulated? Who’s involved, who participates, who is consulted?

Results framework

- Do you find the outputs and targets as stated in the results framework adequate for monitoring and reporting on the project? Any area of the results framework that is problematic/inadequate? If so, why?

Gender

- The PIRs show that the project has struggled to bring into its fold good participation of women – what was the reason? Could more have been done by those implementing the project to enhance gender-parity?

Results

- Were there significant changes in the social, economic and environmental context in the country and how did these affect the achievement of project results?

- Go through each of the outputs (as below) and explore: (a) what specific interventions made through CBIT, (b) to what result, and (c) what evidence exists to show that this was mainly due to CBIT contribution?

Outcome 1.1: Strengthened institutional capacity for transparency-related activities

Output 1.1.1: An established inter-ministerial body to provide oversight to the implementation;

Output 1.1.2: Clearly defined roles and tasks of stakeholders for the implementation of MRV;

Output 1.1.3: System for GHG emissions inventory and functional GHG database system established.

Outcome 2.1: Strengthened technical capacity for transparency-related activities, including tracking of progress towards attaining NDC

Output 2.1.1: Guidelines on the formulation of the GHG emission mitigation policy measure

Output 2.1.2: Methods to quantify and integrate support needs into the public budget and report on effective utilization of the support received;

Output 2.1.3: Experts in key sectoral ministries regional states and city administration fully conversant on the transparency framework;

Output 2.1.4: Data collection widened and improved to sustain the use of 2006 IPCC guidelines

Output 2.1.5: Training on the use of 2006 IPCC guidelines at relevant ministries and university carried out

Output 2.1.6: National universities engaged to support in establishing QA/QC procedure and uncertainty analysis of the GHG inventory.

- What interactions did the project have with TASCA, ICAT, SRPC, World Bank, UNEP, etc? What is distinctive about CBIT’s contribution? Is there is any overlap, and if so, are there measures to ensure that they complement and reinforce each other?

Roles & responsibilities

- Are the roles and responsibilities including accountability clearly defined for various entities (Project Board, PMU, IP and line ministries) in implementation of the project?

- What support is provided by UNDP to IP, and are these adequate, timely and useful? Any area where UNDP could do better?

Efficiency

- Are the project activities implemented in a timely manner and are the choices of interventions optimal in cost terms, or were there other options?

- How was the co-financing made available by UNP and GoE utilized? Was this the most effective way to utilize co-financing?

M&E

- What specific mechanisms exist to monitor the project? What is the quality of data produced during regular monitoring? Do you find this adequate for reporting on outputs and outcome?

- Are monitoring data used in adaptive management of the project? If so, how?

- Is there a practice of analysing and documenting lessons emerging from the project?

Communication & advocacy

- What mechanisms exist for effective communication with partners? Are there advocacy actions taken by the project to engage the GoE and regional governments? If so, how?

Sustainability

- Does the government now provide regular budget support to EPA and other Ministries for systematic MRV activities? How adequate is this support for EPA’s ability to ensure transparency and quality in the GHG inventory data?

- Does the CBIT project have an engagement with other agencies/projects who could take over the activities of the project once it comes to an end? Are there measures in place to ensure that the project benefits sustain in the coming years?

Risk register

- Is the risk register maintained up-to-date and monitored regularly? What are the current risks that the project may not achieve all/some of its intended outputs at the end of the project? What actions being taken to rectify these?

B. EPA/MRV Directorate

(Interviewer: at the start, provide brief introduction about the aim of the evaluation, evaluation protocol and ethics, how data will be used, outline confidentiality protocol, obtain permission to take notes, agree time needed for the interview – about 50-60 minutes – with some individuals, the evaluator may need to negotiate more than one session; introducing each other).

Before each interview, the interviewer to select maximum of 8-10 priority questions for each individual interviewee, depending on an understanding of the latter’s role and functional expertise. Questions may be amended/adapted/ supplemented as the interviews progress to allow for deeper probing.

- How established/functional is the inter-ministerial mechanism for oversight on a whole-of-government approach to GHG emission/mitigation monitoring and data system? What specifically has been the role of CBIT in this regard?

- Is there now a coordinated approach to data sharing by various ministries, particularly in the waste, AFOLU, energy and IPPU sectors? Does the mechanism for collating and sharing these data function effectively as per 2006 IPCC guidelines?

- Was your department involved in design of the project? Were relevant line ministries and other complementary project holders consulted to determine where CBIT created the most value?

- Do you find the outputs and targets as stated in the results framework adequate for monitoring and reporting on the project? Any area of the results framework that is problematic/inadequate? If so, why?

- The PIRs show that the project has struggled to bring into its fold good participation of women – what was the reason? Could more have been done by those implementing the project to enhance gender-parity?

- Were there significant changes in the social, economic and environmental context in the country and how did these affect the achievement of project results?

- Go through each of the outputs (as below) and explore: (a) what specific interventions made through CBIT, (b) to what result, and (c) what evidence exists to show that this was mainly due to CBIT contribution?

Outcome 1.1: Strengthened institutional capacity for transparency-related activities

Output 1.1.1: An established inter-ministerial body to provide oversight to the implementation;

Output 1.1.2: Clearly defined roles and tasks of stakeholders for the implementation of MRV;

Output 1.1.3: System for GHG emissions inventory and functional GHG database system established.

Outcome 2.1: Strengthened technical capacity for transparency-related activities, including tracking of progress towards attaining NDC

Output 2.1.1: Guidelines on the formulation of the GHG emission mitigation policy measure

Output 2.1.2: Methods to quantify and integrate support needs into the public budget and report on effective utilization of the support received;

Output 2.1.3: Experts in key sectoral ministries regional states and city administration fully conversant on the transparency framework;

Output 2.1.4: Data collection widened and improved to sustain the use of 2006 IPCC guidelines

Output 2.1.5: Training on the use of 2006 IPCC guidelines at relevant ministries and university carried out

Output 2.1.6: National universities engaged to support in establishing QA/QC procedure and uncertainty analysis of the GHG inventory.

- What interactions did the project have with TASCA, ICAT, SRPC, World Bank, UNEP, etc? What is distinctive about CBIT’s contribution? Is there is any overlap, and if so, are there measures to ensure that they complement and reinforce each other?

- Are the roles and responsibilities including accountability clearly defined for various entities (Project Board, PMU, IP and line ministries) in implementation of the project?

- What support is provided by UNDP to IP, and are these adequate, timely and useful? Any area where UNDP could do better?

- Are the project activities implemented in a timely manner and are the choices of interventions optimal in cost terms, or were there other options?

- How was the co-financing made available by UNP and GoE utilized? Was this the most effective way to utilize co-financing?

- What specific mechanisms exist to monitor the project? What is the quality of data produced during regular monitoring? Do you find this adequate for reporting on outputs and outcome?

- Is there a practice of analysing and documenting lessons emerging from the project?

- Does the government now provide regular budget support to EPA and other Ministries for systematic MRV activities? How adequate is this support for EPA’s ability to ensure transparency and quality in the GHG inventory data?

- Does the CBIT project have an engagement with other agencies/projects who could take over the activities of the project once it comes to an end? Are there measures in place to ensure that the project benefits sustain in the coming years?

C. Other stakeholders

Using the above list of questions, specific questions will be tailored to each entity based on an understanding of the nature of engagement of the stakeholder.

# Annex 7 - Rating scale used

| MTR Ratings for Progress Towards Results: (one rating for each outcome and for the objective) |  |  |
| --- | --- | --- |
| 6 | Highly Satisfactory (HS) | The objective/outcome is expected to achieve or exceed all its end-of-project targets, without major shortcomings. The progress towards the objective/outcome can be presented as “good practice”. |
| 5 | Satisfactory (S) | The objective/outcome is expected to achieve most of its end-of-project targets, with only minor shortcomings. |
| 4 | Moderately Satisfactory (MS) | The objective/outcome is expected to achieve most of its end-of-project targets but with significant shortcomings. |
| 3 | Moderately Unsatisfactory (HU) | The objective/outcome is expected to achieve its end-of-project targets with major shortcomings. |
| 2 | Unsatisfactory (U) | The objective/outcome is expected not to achieve most of its end-of-project targets. |
| 1 | Highly Unsatisfactory (HU) | The objective/outcome has failed to achieve its midterm targets, and is not expected to achieve any of its end-of-project targets. |
| Ratings for Project Implementation & Adaptive Management: (one overall rating) |  |  |
| 6 | Highly Satisfactory (HS) | Implementation of all seven components – management arrangements, work planning, finance and co-finance, project-level monitoring and evaluation systems, stakeholder engagement, reporting, and communications – is leading to efficient and effective project implementation and adaptive management. The project can be presented as “good practice”. |
| 5 | Satisfactory (S) | Implementation of most of the seven components is leading to efficient and effective project implementation and adaptive management except for only few that are subject to remedial action. |
| 4 | Moderately Satisfactory (MS) | Implementation of some of the seven components is leading to efficient and effective project implementation and adaptive management, with some components requiring remedial action. |
| 3 | Moderately Unsatisfactory (MU) | Implementation of some of the seven components is not leading to efficient and effective project implementation and adaptive, with most components requiring remedial action. |
| 2 | Unsatisfactory (U) | Implementation of most of the seven components is not leading to efficient and effective project implementation and adaptive management. |
| 1 | Highly Unsatisfactory (HU) | Implementation of none of the seven components is leading to efficient and effective project implementation and adaptive management. |
| Ratings for Sustainability: (one overall rating) |  |  |
| 4 | Likely (L) | Negligible risks to sustainability, with key outcomes on track to be achieved by the project’s closure and expected to continue into the foreseeable future |
| 3 | Moderately Likely (ML) | Moderate risks, but expectations that at least some outcomes will be sustained due to the progress towards results on outcomes at the Midterm Review |
| 2 | Moderately Unlikely (MU) | Significant risk that key outcomes will not carry on after project closure, although some outputs and activities should carry on |
| 1 | Unlikely (U) | Severe risks that project outcomes as well as key outputs will not be sustained |

# Annex 8: Co-financing Table for UNDP Supported GEF Finnanced Projects

| Source of co-financing | Type of cofinancing | Name of cofinancer | Amount confirmed at CEO endorsement ($) | Actual amount contributed at the time of MTR ($) | Actual % of expected amount |
| --- | --- | --- | --- | --- | --- |
| UNDP | Cash | Mr. Turhan Saleh UNDP Ethiopia Country Office | 50,000 | 38,000 | 76 |
| Government of Ethiopia | In-kind | Getahun Garedw (PhD)- EPA | 142,000 | 103,000 | 73 |
| Total |  |  | 192,000 | 141,000 | 73 |

## Annex 9: UNEG Code of Conduct for Evaluators/Midterm Review Consultants

Evaluators/Consultants:

- Must present information that is complete and fair in its assessment of strengths and weaknesses so that decisions or actions taken are well founded.

- Must disclose the full set of evaluation findings along with information on their limitations and have this accessible to all affected by the evaluation with expressed legal rights to receive results.

- Should protect the anonymity and confidentiality of individual informants. They should provide maximum notice, minimize demands on time, and respect people’s right not to engage. Evaluators must respect people’s right to provide information in confidence, and must ensure that sensitive information cannot be traced to its source. Evaluators are not expected to evaluate individuals, and must balance an evaluation of management functions with this general principle.

- Sometimes uncover evidence of wrongdoing while conducting evaluations. Such cases must be reported discreetly to the appropriate investigative body. Evaluators should consult with other relevant oversight entities when there is any doubt about if and how issues should be reported.

- Should be sensitive to beliefs, manners and customs and act with integrity and honesty in their relations with all stakeholders. In line with the UN Universal Declaration of Human Rights, evaluators must be sensitive to and address issues of discrimination and gender equality. They should avoid offending the dignity and self-respect of those persons with whom they come in contact in the course of the evaluation. Knowing that evaluation might negatively affect the interests of some stakeholders, evaluators should conduct the evaluation and communicate its purpose and results in a way that clearly respects the stakeholders’ dignity and self-worth.

- Are responsible for their performance and their product(s). They are responsible for the clear, accurate and fair written and/or oral presentation of study limitations, findings and recommendations.

- Should reflect sound accounting procedures and be prudent in using the resources of the evaluation.

Consultant Agreement Form

Agreement to abide by the Code of Conduct for Evaluation in the UN System:

Name of Consultant: Abhijit Bhattacharjee_ __________________________________________________________________

Name of Consultancy Organization (where relevant): __________________________________________

I confirm that I have received and understood and will abide by the United Nations Code of Conduct for Evaluation.

Signed at _____________________________________  (Place)     on ______20.12.2022______________________    (Date)

Signature: ___________________________________

# Annex 10: MTR Report Clearance Form

Midterm Review Report Reviewed and Cleared By:

Commissioning Unit

Name:

Signature:                                                                                    Date: _                       _______________________

UNDP-GEF Regional Technical Advisor

Name:

Signature:______________________________________________

# Annex 11: Details of Training provided

UNDP-GEF, 2014, Guidance for Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects

The 6-point rating for Progress Towards Results and implementation & adaptive management is: HS – highly satisfactory; S – satisfactory; MS – mostly satisfactory; MU – mostly unsatisfactory; U – unsatisfactory; HU – high unsatisfactory.

The 4-point rating scale for sustainability is: L – likely; ML – moderately likely; MU – moderately unlikely; U – unlikely.

For details, see summary Table at the end of the executive summary for rating of results as per GEF MTR rating scale.

Henceforth ‘the evaluation’ and ‘the review’ have been used in this document to mean ‘the mid-term review’.

The 6-point rating for Progress Towards Results and implementation & adaptive management is: HS – highly satisfactory; S – satisfactory; MS – mostly satisfactory; MU – mostly unsatisfactory; U – unsatisfactory; HU – high unsatisfactory.

The 4-point rating scale for sustainability is: L – likely; ML – moderately likely; MU – moderately unlikely; U – unlikely.

UN Evaluation Group, 2020, UNEG Ethical Guidelines for Evaluation

UNDP-GEF, 2014, Guidance for Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects

UNEG, 2016, Norms and Standards for Evaluation in the UN System

The Federal Democratic Republic of Ethiopia, Environmental Protection Authority. Ethiopia’s Third National Communication to the United Nations Framework Convention on Climate Change (UNFCCC), 2018

The Federal Democratic Republic of Ethiopia, Environmental Protection Authority. Ethiopia’s Third National Communication to the United Nations Framework Convention on Climate Change (UNFCCC), 2018

2006 IPCC Guidelines for National Greenhouse Gas Inventories and its subsequent amendment (2019).

UNFCCC, Handbook on Measurement, Reporting and Verification for developing country Parties, 2014

UNDP, 2019, Project document: Capacity-building program to comply with the Paris Agreement and implement its transparency requirements at the national level

Basal Consulting, Development of Quality Control (QC) and Quality Assurance (QA) Plan for Green House Gas Inventory, June 2022

UNDP, 2019, Project document: Capacity-building program to comply with the Paris Agreement and implement its transparency requirements at the national level

Initially it was a Ministry (Ministry of Environment, Forest and Climate Change), then it became Commission.

Ethiopian Environmental Protection Authority, Ethiopia’s GHG Emission and Mitigation (2020 & 2021) – Implementation Assessment Report, September 2022

MOA, MOT, MOWE, MOT, Ministry of Urban Infrastructure, Ministry of Mines, Ministry of Finance, Ministry of Industry

UNDP/GEF, Project Implementation Report (PIR) 2021 – CBIT Ethiopia

For details, refer to Table 5.

The Federal Democratic Republic of Ethiopia, Environmental Protection Authority. Ethiopia’s Third National Communication to the United Nations Framework Convention on Climate Change (UNFCCC), 2018

The Federal Democratic Republic of Ethiopia, Ethiopia’s Climate Resilient Green Economy National Adaptation Plan, May 2019

The net emission during 2010 was estimated at 150 Mt CO2e

GEF-6 PROJECT IDENTIFICATION FORM (PIF): Capacity Building Initiative for Transparency, Capacity-building program to comply with the Paris Agreement and implement its transparency requirements at the national level, Ethiopia (GEF ID 9967), 2018.

The Federal Democratic Republic of Ethiopia, Environmental Protection Authority. Ethiopia’s Third National Communication to the United Nations Framework Convention on Climate Change (UNFCCC), 2018

Currently the GoE is submitting the Third National Communication and the Biennial Update Report (BUR) as well.

Federal Republic of Ethiopia, Environmental Protection Authority, Ethiopia’s GHG Emission and Mitigation (2020 &2021) – Implementation Assessment Report, September 2022

Ministries of Agriculture, Urban and Infrastructure, Water and energy, Industry, and Mines.

The National Communication and BURs need to be submitted to the UNFCCC in four-year and two-year cycle respectively.

Federal Republic of Ethiopia, Environmental Protection Authority, Ethiopia’s First Biennial Update Report (FBUR) Under the United Nations Framework Convention on Climate Change (UNFCCC) (Final Report), February, 2023

Baseline, mid-term and end of project target levels must be expressed in the same neutral unit of analysis as the corresponding indicator. Baseline is the current/original status or condition and need to be quantified. The baseline must be established before the project document is submitted to the GEF for final approval. The baseline values will be used to measure the success of the project through implementation monitoring and evaluation.

Target is the change in the baseline value that will be achieved by the mid-term review and then again by the terminal evaluation.

Federal Republic of Ethiopia, Ethiopian Environmental Protection Authority, Ethiopia’s GHG Emission and Mitigation (2020 & 2021) – Implementation Assessment Report, September 2022

EPA as key stakeholder; Ministry of Agriculture & Forests, Ministry of Water, Irrigation and Energy; Ministry of Urban Development and Infrastructure; Ministry of Transport; Ministry of Mines and Petroleum; Ministry of Trade & Industry; and Ministry of Health.

Federal Republic of Ethiopia, UNDP/GEF, Project Implementation Report (PIR) 2022 – CBIT Ethiopia

Ministry of Urban and infrastructure; Forest Department, Agriculture & Land Use

A tier represents a level of methodological complexity. Tier 1 is the basic method, Tier 2 intermediate and Tier 3 the most demanding in terms of complexity and data requirements. Tier 1 are simple methods with default values; Tier 2 is similar but with country specific emission factors and more granular data on each sub-category/sub-sector (for example, emission/sink estimation in AFOLU sector will require a detailed analysis of national data on animal population, livestock species (the number of animals produced annually), fertilizer application, area of crop cultivation and crop production, area deforested/afforested/reforested and type of forest etc.

Federal Republic of Ethiopia, Environmental Protection Authority, Ethiopia’s First Biennial Update Report (FBUR) Under the United Nations Framework Convention on Climate Change (UNFCCC) (Final Report), February, 2023

Federal Republic of Ethiopia, Ethiopian Environmental Protection Authority, Ethiopia’s GHG Emission and Mitigation (2020 & 2021) – Implementation Assessment Report, September 2022

Basal Consulting, Development of Quality Control (QC) and Quality Assurance (QA) Plan for Green House Gas Inventory, June 2022

Basal Consulting, Development of Quality Control (QC) and Quality Assurance (QA) Plan for Green House Gas Inventory, June 2022

Basal Consulting, ibid

Federal Republic of Ethiopia, Environmental Protection Authority, Ethiopia’s First Biennial Update Report (FBUR) Under the United Nations Framework Convention on Climate Change (UNFCCC) (Final Report), February, 2023

Ethiopian Environmental Protection Authority, Ethiopia’s GHG Emission and Mitigation (2020 & 2021) – Implementation Assessment Report, September 2022

For details of training conducted and timeline for the same, please see Annex 11

Federal Republic of Ethiopia, Environmental Protection Authority, Ethiopia’s First Biennial Update Report (FBUR) Under the United Nations Framework Convention on Climate Change (UNFCCC) (Final Report), February, 2023

Basal Consulting, Development of Quality Control (QC) and Quality Assurance (QA) Plan for Green House Gas Inventory, June 2022

Populate with data from the Logframe and scorecards

Populate with data from the Project Document

If available

Colour code this column only

Use the 6-point Progress Towards Results Rating Scale: HS, S, MS, MU, U, HU

EFCCC and key stakeholder; Ministry of Agriculture, Ministry of water, Irrigation and Energy; Ministry of Urban Development and Construction; Ministry of Transport; Ministry of Mines and Petroleum, Ministry of Trade & Industry and Ministry of Health

Abraham Berhanu Admasu, Audited Financial Statements, UNDP Assisted Project, Capacity Building CBIT Ethiopia, 31 December 2021

https://www.epa.gov.et

For ideas on innovative and participatory Monitoring and Evaluation strategies and techniques, see UNDP Discussion Paper: Innovations in Monitoring & Evaluating Results, 05 Nov 2013.

For more stakeholder engagement in the M&E process, see the UNDP Handbook on Planning, Monitoring and Evaluating for Development Results, Chapter 3, pg. 93.

Populate with data from the Logframe and scorecards

Populate with data from the Project Document

If available

Colour code this column only

Use the 6 point Progress Towards Results Rating Scale: HS, S, MS, MU, U, HU

Alternatively, MTR conclusions may be integrated into the body of the report.

The Commissioning Unit is obligated to issue payments to the MTR team as soon as the terms under the ToR are fulfilled.  If there is an ongoing discussion regarding the quality and completeness of the final deliverables that cannot be resolved between the Commissioning Unit and the MTR team, the Regional M&E Advisor and Vertical Fund Directorate will be consulted.  If needed, the Commissioning Unit’s senior management, Procurement Services Unit and Legal Support Office will be notified as well so that a decision can be made about whether or not to withhold payment of any amounts that may be due to the evaluator(s), suspend or terminate the contract and/or remove the individual contractor from any applicable rosters. See the UNDP Individual Contract Policy for further details:

https://popp.undp.org/_layouts/15/WopiFrame.aspx?sourcedoc=/UNDP_POPP_DOCUMENT_LIBRARY/Public/PSU_Individ ual%20Contract_Individual%20Contract%20Policy.docx&action=default

Engagement of the consultants should be done in line with guidelines for hiring consultants in the POPP:

https://popp.undp.org/SitePages/POPPRoot.aspx

The Report length should not exceed 40 pages in total (not including annexes).

http://www.unevaluation.org/document/detail/100

Efficiency is about how well inputs are converted into outputs; cost-efficiency relates to choice of interventions that optimize delivery. Cost-Effectiveness is about the project’s outcomes in relation to its costs: how well the cost of assistance stacked up against what was achieved. This is a broader question, as the outcome will depend not just on good project management on the ground, but on the initial choice of programme approach, design and set up.

http://www.unevaluation.org/document/detail/100