FINAL REPORT

MID TERM REVIEW (MTR) OF THE PROJECT:

“A Ridge to Reef Approach for the Integrated Management of Marine, Coastal and Terrestrial Ecosystems in the Seychelles” (PIMS 5502)

Date: 13 October 2022

Prepared by :

Jan Rijpma, International Consultant

Basic Report Information

| UNDP Project ID (PIMS #): 5502 |  | PIF Approval Date: 30th November 2017 |  |
| --- | --- | --- | --- |
| GEF Project ID (PMIS #): 9431 |  | CEO Endorsement Date: 4th October 2019 |  |
| ATLAS Business Unit, Award # Proj. ID: 00116471 |  | Project Document (ProDoc) Signature Date (date project began): 9th January 2020 |  |
| Country(ies): Seychelles |  | Date project manager hired: Part time January 2020, Full time July 2020 |  |
| Region: Indian Ocean, Africa |  | Inception Workshop date: 28th February 2020 |  |
| Focal Area: Multi-focal area |  | Midterm Review completion date: 14th October 2022 |  |
| GEF Focal Area Strategic Objective: BD 1, Programme 2; BD 3, Programme 6; LD 2, Programme 3 |  | Planned planed closing date: Jan 9, 2025 |  |
| Trust Fund [indicate GEF TF, LDCF, SCCF, NPIF]: GEF TRUST FUND |  | If revised, proposed op. closing date: January 2026 |  |
| Executing Agency/ Implementing Partner: Ministry of Agriculture, Climate Change and Environment (MACCE) |  |  |  |
| Other execution partners: Terrestrial Restoration Action Society of Seychelles, Marine Conservation Society Seychelles, Seychelles Parks and Gardens Authority, Blue Economy Research Institute/ University of Seychelles, Department of Agriculture |  |  |  |
| Project Financing | at CEO endorsement (US$) |  | at Midterm Review (US$) |
| [1] GEF financing: | 3,898,914 |  | 3,898,914 |
| [2] UNDP contribution: | 2,893,000 |  | 2,893,000 |
| [3] Government: | 3,836,714 |  | 3,836,714 |
| [4] Other partners: | 20,475,232 |  | 20,475,232 |
| [5] Total co-financing [2 + 3+ 4]: | 27,204,946 |  | 27,279,946 |
| PROJECT TOTAL COSTS [1 + 5] | 31,178,860 |  | 31,178,860 |

The Mid-Term Review (MTR) of the project: “A Ridge to Reef Approach for the Integrated Management of Marine, Coastal and Terrestrial Ecosystems in the Seychelles” was undertaken by Jan Rijpma, International Consultant, from 17 August to 14 October 2022.

The Consultant / Reviewer would like to thank the Ridge to Reef project team: Joanna Prosper, Evelyn Drawec, Didier Dogley and Emma Valentin, for their support, insights and time. The organization and logistics of interviews and visits was spotless, despite some on-going challenges (COVID, new office, scheduling meetings with some decision-makers, etc.). The reviewer also wants to thank UNDP for the support, time and vision, especially Preethi Sushil Nair, Oksana Vovk and Penny Stock. And of course all other stakeholders for their time, insights and open and frank discussions, as well as their continued commitment to the project.

I wish you and all Seychellois all the best in these challenging times.

Mersi Bokou!

TABLE OF CONTENTS

ACRONYMS	3

EXECUTIVE SUMMARY	4

1.	INTRODUCTION	8

2.	PROJECT DESCRIPTION	9

3.	FINDINGS	11

3.1.	Project Strategy	11

3.2.	Progress Towards Results	12

3.3.	Project Implementation and Adaptive Management	21

3.4.	Sustainability	27

4.	CONCLUSIONS	32

5.	RECOMMENDATIONS	33

ANNEXES	36

Annex I: Mid Term Review Terms of Reference	36

Annex II: Evaluative Matrix	44

Annex III: Ratings Scales	47

Annex IV: List of documents reviewed	48

Annex V: Interview Schedule	49

Annex VI: Progress Towards Outcomes	52

Annex VII:  Risk Log	66

Annex VIII: Detailed Co-financing commitments	86

Annex IX: Signed UNEG Code of Conduct form	87

Annex X: Audit Trail for comments received	88

Annex XI: Signed MTR final report clearance form	91

# ACRONYMS

AF		Adaptation Fund

BERI		Blue Economy Research Institute (UNISEY)

CEPS		Citizens Engagement Platform, Seychelles

COVID 19	Coronavirus Disease of 2019

CSR		Corporate Social Responsibility

DA		District Administrator

EbA		Ecosystem based Adaptation

FA 		Farmers Association

FAO		Food and Agriculture Organization (of the UN)

GEF		Global Environment Facility

KBA		Key Biodiversity Area

MACCE 		Ministry of Agriculture, Climate Change and Environment (from 2020)

MCSS		Marine Conservation Society of Seychelles

MEECC		Ministry of Environment, Energy and Climate Change (until 2020)

METT 		Management Effectiveness Tracking Tool (UNDP-GEF)

MLGCA		Ministry of Local Government and Community Affairs

MLH 		Ministry of Lands and Housing

MT 		Mid Term (Target)

MTR		Mid Term Review

NGO		Non Governmental Organization

PDCS		Programme Development and Coordination Section

PCU		Programme Coordination Unit

PIMS 		Project Information Management System (UNDP)

PSC		Project Steering Committee

PIR 		Project Implementation Report (UNDP-GEF)

RBM		Results Based Management

R2R		Ridge to Reef (Project)

RP		Responsible Partner (R2R Project)

SEYCATT 	Seychelles Conservation and Climate Adaptation Trust

SGP		Small Grants Programme (UNDP – GEF)

SIAH		Seychelles Institute for Agriculture and Horticulture

SLM 		Sustainable Land Management

SFM		Sustainable Forest Management

SNPA		Seychelles National Parks Authority

SOP		Standard Operating Procedure

SPGA		Seychelles Parks and Garden Authority

TRASS		terrestrial Restoration Action Society Seychelles

UNDP		United Nations Development Programme

UNISEY		University of Seychelles

# EXECUTIVE SUMMARY

This is the Mid Term Review (MTR) of the GEF funded, full-sized and multi-focal project “A Ridge to Reef Approach for the Integrated Management of Marine, Coastal and Terrestrial Ecosystems in the Seychelles”, or “Seychelles R2R Project” for short. The MTR was carried out from mid August to mid October 2022 by an International Consultant, with an in-country mission from 31/08 to 20/09/2022.

The objective of the project is: “To manage and conserve the flow of marine, coastal and terrestrial ecosystem services in targeted islands of the Seychelles for multiple benefits through the Ridge-to-Reef approach”. This is to be addressed through the following Outcomes:

- Expansion of marine and terrestrial protected areas of the Seychelles’ Inner Islands;

- Strengthened management of upland KBAs and adjacent areas to enhance the flow of ecosystem services through the R2R approach;

- Promoting the ‘Ridge to Reef’ (R2R) approach through knowledge management, ecosystem health monitoring and inter-sectoral coordination

- Knowledge Management, M&E and Gender Mainstreaming

The project is implemented by the Ministry of Agriculture Climate Change and Environment (MACCE), through the Project Team (Project Manager, 2 part-time Technical Advisers for Agriculture and Forestry / Ecosystems, respectively and new part-time “Media, Community Gender and Youth” and “Communication” officers) based at the Programme Coordination Unit (PCU, now revamped as the Programme Development and Coordination Section (PDCS) of MACCE). Specific activities are implemented in selected Protected Areas, Key Biodiversity Areas (KBAs) and Watersheds, where conservation and sustainable management activities are implemented through designated “Responsible Partners”, either Government agencies, NGOs, University of Seychelles (UNISEY), Farmers Associations or Watershed Committees.

The R2R concept was found to be very relevant to the Seychelles by all stakeholders. The project was also found to be well designed and its content is well elaborated, with however some sections  less well developed (e.g. agriculture). The Results Framework was well detailed and fit for purpose. Some of the discussed and agreed changes to the Indicators at Inception have not been recorded by PIMS and still appear in UNDP reporting templates, which should be changed. The project end date January 2026should also be correctly recorded in PIMS:.

The progress towards results is varied.

The Indicators and targets for the Project Objective are  progressing “Moderately Satisfactory” to “Satisfactory”, with some of the new policies and Bills / Laws in place, others still being worked on and not yet validated / assented, and some of the regulations needing more work. The “Capacity of national partners implementing integrated Ridge to Reef approaches” has improved significantly as measured by the UNDP score card and is well on its way to reach the end of project target.

Outcome 1 has progressed “satisfactory” with all its new to be designated areas (KBAs and SPAs) delineated and nomination files presented. A concern remains with the survival rate and sustainability of some of the rehabilitated areas in mangroves and coastal forests, and this should be monitored going forward.

Outcome 2 is progressing “moderately satisfactory”, with 3 functioning watershed committees in place and rehabilitation works on-going and having reached its mid-term targets, though these areas should also be monitored. The agroforestry work hasn’t reached its target (by far) and it is recommended to shift from Anse Royale (one of the 2 intended sites) to another watershed. The CO2 mitigation targets have not been reached, even after recalculation.

Outcome 3 is progressing “moderately unsatisfactory” to “moderately satisfactory”, with work on the online platform only just starting and policy recommendations from the gap analysis not yet worked on. Efforts for these should be stepped up. The ecosystem monitoring has started and is progressing “moderately satisfactory”. The mid-term target for numbers of officials sensitized has been reached.

Outcome 4 is progressing “Moderately Satisfactory” to “Satisfactory” with the mid-term targets for number of policies / programmes supporting R2R approaches and % of women among project participants reached. But the Number of direct project beneficiaries has not reached the Mid-term target though is progressing well with many activities and trainings currently on-going and picking up after COVID restrictions have been lifted.

Overall progress towards results is “moderately satisfactory”, with some areas doing well and others in need to accelerate. This is a laudable achievement considering the challenges faced in its 1st 2 years with COVID-19 restrictions, destruction of the office and numerous changes in government and administration.

The project is well managed, monitored and reported upon, despite the early challenges. The overarching PCU where the project is housed transitioned into PDCS with the new Chief Programme Coordinator (CPC) already in place, and new officers being recruited and SOPs being finalized. This should help in support and oversight for the Project, although there are some concerns what following government procedures may mean for project operations, e.g. procurement. UNDP is “stepping back” some of its monitoring functions and will concentrate on quality assurance and cash advances, following the “full NIM” approach.

Project activities are well planned, but implementation varies with the different RPs. The project team has a remarkable focus on indicators and targets. However, some of the RP activities have been taken over by the project because of slow delivery due to capacity constraints. This can mean that some partners could display less “ownership” of these activities, with possible consequences for sustainability. Financial disbursement and delivery is still slow, mainly caused by the slow start with the COVID-19 pandemic and its restrictions, as well as some of the RPs that are not delivering on time and have difficulties in reporting. Co-financing lags also behind the stated commitments, mainly because of financial constraints due to the effects of COVID-19; the project however managed to ensure new co-financing from some new partners. Stakeholder engagement of the project is good, although communication and awareness efforts can be stepped up. Overall the project implementation is “Satisfactory”.

Sustainability of the project is questionable at this point, also taking into consideration previous experiences of similar projects. The financial, institutional, socio-economic and environmental risks will need to be foreseen and managed through an elaborate exit strategy, that should contain clear commitments, responsibilities, actions and monitoring & reporting mechanisms. Socio-economic and environmentally related risks may also have consequences for project sustainability. The sustainability of the project is therefore considered moderately unlikely, that can be mitigated through the elaboration of a comprehensive and actionable exit strategy.

The overall rating of the project is Moderately Satisfactory. By following the recommendations of this MTR, most of the project end targets can be achieved, though the sustainability of the project needs extra and timely attention (through an elaborate exit strategy).

See further the summary of achievements, ratings  and recommendations below:

| Measure | MTR Rating | Achievement Description |
| --- | --- | --- |
| Project Strategy | N/A | Relevant concept and well elaborated Project Document and Design, though with few weaknesses |
| Progress Towards Results | Objective Achievement Rating: 4-5 (MS - S) | Some of the new policies and Bills / Laws in place, others not yet validated / assented and needing more work. The Capacity scores have reached their targets. |
|  | Outcome 1 Achievement Rating: 5 (S) | New Key Biodiversity Areas and Seasonal Protected Areas delineated and nomination files presented. Mangroves and coastal forests rehabilitated as per target, but the survival rate should be monitored in future. |
|  | Outcome 2 Achievement Rating: 4 (MS) | Three functioning watershed committees are in place and rehabilitation works reached its targets. The agroforestry work is off target, and it is recommended to shift from Anse Royale to another watershed. The CO2 mitigation targets have not been reached. |
|  | Outcome 3 Achievement Rating: 3-4 (MU - MS) | Some of the activities just started (online platform and ecosystem monitoring). Policy recommendations from the gap analysis have not yet been worked on. Efforts on these activities should be stepped up. The mid-term target for numbers of officials sensitized has been reached. |
|  | Outcome 4 Achievement Rating: 4-5 (MS – S) | Mid-term targets for number of policies / programmes supporting R2R approaches and % of women among project participants have been reached. Number of direct project beneficiaries has not reached the mid-term target though is picking up fast after COVID restrictions have been lifted. |
| Project Implementation & Adaptive Management | Rating: 5 (S) | The project is well planned, managed, monitored and reported upon. Financial delivery and disbursement is slow because of early challenges (mainly COVID-19 restrictions) and also because of varying project implementation through Responsible Parties. |
| Sustainability | Rating: 2 (MU) | There are considerable financial, institutional, socio-economic and environmental risks for the project’s sustainability that will need to be foreseen and managed. Work on an elaborate and early exit strategy, that should contain clear commitments, responsibilities, actions and monitoring & reporting mechanisms is recommended. |

| Rec. | Recommendation (summarized) | Entity Responsible |
| --- | --- | --- |
| A | Project Strategy |  |
| A.1 | To correct in PIMS, before the next PIR (2023): - Project end date; - Changes in indicators and targets that were discussed and agreed at Inception; - Change total committed co-financing from USD27,204,946 to USD27,279,946 as recorded and detailed at CEO endorsement. | UNDP |
| A.2 | No request for “project extension” at this early point in the project but continue to monitor the project progress and re-discuss this possible extension request after submission of the PIR in 2024 with all pertinent stakeholders and PSC. | Project Team, UNDP, PSC, MACCE |
| A.3 | Record changes in the Results Framework at MTR, before next PIR (2023): - Indicator 6: End target of “No. of KBAs with required technical documents and draft legal documents for gazetting presented to the Government”, to be adjusted from 6 to 5, as 2 of the envisaged KBAs have now been merged, with the same coverage (2,235 ha). - Indicator 10: Change in location for agroforestry sites from “Anse Royale Watershed” to “Caiman Watershed” and/or any suitable Watershed on Praslin (to be identified). - Indicator 11: Adjust targets from 18,273 tCO2eq to 7,070 tCO2eq at mid-term and from 43,853 tCO2eq to 16,134tCO2eq at end target (recalculated by an international expert). | Project Team, UNDP |
| B | Project Objective |  |
| B.1 | Monitor and push for the finalization, approval and assenting / promulgation of the targeted laws + designation of KBAs, as well as the capacity for its monitoring and enforcement, by Project end. | Project Team, MACCE |
| C | Outcome 1: Expansion of marine and terrestrial protected areas of the Seychelles’ Inner Islands |  |
| C.1 | Monitor periodically the survival rate and final area of “rehabilitated areas”, e.g. before each PIR through “evidence based reports”. | RPs, Project Team |
| C.2 | Identify new sites for rehabilitation, before the 2023 Workplan. These should preferably be sites in the Districts and watersheds where the project is already operating and where the R2R links can be established and shown. | Project Team, MACCE |
| D | Outcome 2: Strengthened management of upland KBAs and adjacent areas to enhance the flow of ecosystem services through the R2R approach |  |
| D.1 | Shift activities under Indicator 7 away from Grand Police to the Caiman watershed, because of continuing uncertainty about claims of land ownership and possible tourism development in Grand Police, and include this in the 2023 Workplan. Continue the activities on SPAs in Grand Police, and monitor developments with the possibility to restart watershed management activities if feasible and when time allows, e.g. until end 2024. | Project Team, Caiman, Watershed Committee, MACCE |
| D.2 | Shift agroforestry activities from Anse Royale to other areas where agroforestry is possible and farmers are interested, e.g. Baie Lazare, Caiman watershed, Praslin. Identify and plan these activities in time to include in the 2023 Workplan. | Project, Agriculture Department |
| E | Outcome 3: Promoting the ‘Ridge to Reef’ (R2R) approach through knowledge management, ecosystem health monitoring and inter-sectoral coordination |  |
| E.1 | Support the policy revisions as recommended in the policy gap analysis report, especially on agriculture, i.e. developing a possible new “Agriculture Lands Protection Act” and “Agricultural Policy”, so that relevant R2R approaches are integrated. | Project, Agriculture Department |
| F | Outcome 4: Knowledge Management, M&E and Gender Mainstreaming |  |
| F.1 | Pursue the focus on achieving gender parity and to include more youth in project activities by developing a “Gender and Youth Strategy and Action Plan” for the project by end 2022 | Project |
| F.2 | Include all DAs in relevant R2R awareness and training programmes, with continuation of specific trainings for those DAs directly involved in the project. | Project, RPs, DAs. MLGCA |
| G | Project Implementation & Adaptive Management |  |
| G.1 | Find and implement a solution to the delayed financial and activity reporting of some RPs, that endanger and delay the timely disbursement of advances to the project. | Project, PDCS, UNDP |
| G.2 | Continue discussions with and renew attempts to implement activities in close collaboration with the intended partners, even if this could potentially temporarily delay the timely achievement of targets, with possible capacity assessments for new partners or partners that have undergone significant transitions in order to counter possible implementation delays. | Project, RPs |
| G.3 | In order to mitigate the slow financial disbursement and delivery, put in place a Delivery Action Plan by the end of 2022, in time for the 2023 Workplan. | Project, PDCS, UNDP, RPs |
| G.4 | Develop an updated and more targeted communication action plan to increase the awareness and disseminate the results and successes of the project. | Project, PDCS |
| H | Sustainability |  |
| H.1 | Develop a project Exit Strategy including responsibilities, commitments, actions, financial and monitoring mechanisms of the main stakeholders. | Project, PDCS, MACCE, UNDP |

# INTRODUCTION

This is the Mid Term Review (MTR) of the GEF funded, full-sized and multi-focal project “A Ridge to Reef Approach for the Integrated Management of Marine, Coastal and Terrestrial Ecosystems in the Seychelles”, or “Seychelles R2R Project” for short. The project is implemented through the Ministry of Agriculture, Climate Change and Environment (MACCE, formerly Ministry of Environment, Energy and Climate Change - MEECC) in the Seychelles with a total budget of USD31,178,860, including GEF funding of USD 3,898,914 and co-financing of USD27,204,946  according to the signed project document. The document was signed in January 2020 with an end date of December 2025, and is in its 3rd year of implementation. Shortly after the start of the project the first cases of COVID19 pandemic affected Seychelles and disrupted activities in 2020 and 2021 due to stringent public health measures.

An International Consultant, Jan Rijpma, was recruited by the UNDP Mauritius / Seychelles Office on 12/08/2022 to conduct this MTR. The consultant was overseen and supervised by UNDP office in Seychelles in close cooperation with the UNDP Mauritius Office and the UNDP Regional Technical Advisor. According to the TORs for this assignment, the deliverables of the assignment are: an MTR Inception Report, Presentation of initial findings (Mission Debrief), Draft Final Report and Final Report. This document presents the Draft MTR Report for this assignment. The “Guidance for Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects” mentions that: “The MTR inception report should outline the MTR team’s understanding of the project being assessed and the methodology(ies) the team will use to ensure the data collected is credible, reliable and useful”. See further the TORs in ANNEX I.

The objective of the MTR is to identify potential project design problems, to assess progress towards the achievement of the project objectives and outcomes, and assess early signs of project success or failure with the goal of identifying the necessary changes to be made in order to set the project on-track to achieve its intended results. The MTR reviews the project's strategy, its risks to sustainability, the effectiveness, efficiency and timeliness of project implementation, highlights issues requiring decisions and actions, and presents initial lessons learned about project design, implementation and management. Findings of this review will be incorporated as recommendations for enhanced implementation during the remainder of the project’s term.

The MTR  provides evidence-based information that is credible, reliable and useful. The MTR follows a collaborative and participatory approach ensuring close engagement with the project team, government counterparts, project consultants, the UNDP Country Office, UNDP-GEF Regional Technical Adviser and project implementers, key beneficiaries and other stakeholders.

The MTR consultant has reviewed all relevant sources of information in detail, including documents prepared during the preparation phase, e.g. PIF, Project Document, Project Inception Report, Environmental & Social Safeguard Policy (SESP), Project Progress Reports, Project Implementation Reviews (PIRs), Project Workplans, Mission and Back To Office Reports, Workshop Reports, technical and final reports, Communication products, Project Steering Committee Minutes, Consultant Reports, Back To Office Reports, Workshop Reports, Project Financial Statements, Project Tracking Tools,  lessons learned reports, national strategic, policy briefs and legal documents, and any other materials considered useful for this evidence-based review, see also ANNEX III.

Most key stakeholders were interviewed to supplement the written documentation and provide an opportunity for project management team, project beneficiaries and other key project stakeholders to present their views directly to the MTR consultant, see Annex IV for the list of stakeholders interviewed. The interviews followed a set, though flexible semi-structured questionnaire format, based on the Evaluative Framework, see ANNEX II. Pertinent issues, comments and qualifications from the interviews were be compared and triangulated with reports, reviews and desk review analysis. Pertinent field project sites were also visited, i.e. Baie Lazare, Val d’Endor, Anse Royale, Mont Plaisir, Grand Police, Port Launay on Mahe and Pointe Chevalier, Pasquiere, Baie St. Anne and Curieuse on Praslin.

The MTR was scheduled for mid August – mid October 2022, with a mission to Seychelles from 30/08 – 20/09/2022, that took place during the still ongoing COVID-19 pandemic. All restrictions on COVID-19 in Seychelles were lifted as of July 15th 2022, but there were still some active cases in Seychelles (COVID update Report of 16/08/2022). The consultant followed the guidance for undertaking evaluations during COVID from the UNDP Independent Evaluation Office that mentions that “care should be taken to not place any consultant or stakeholders (national or international) in harm’s way and evaluation methodologies proposed should limit the exposure of stakeholders to the pandemic”.  Safety protocols based on venues were followed, with wearing of masks and sanitization recommended while conducting meetings. During the mission some Project Team members that were in close contact with the consultant tested positive, and therefore during the week of 12 – 16 September all meetings, including a project team working session and mission de-brief, were conducted virtually.

The report below gives an outline of the project, the purpose, objective, scope, approach and limitations of the MTR, and its findings, recommendations and conclusions, including the various Annexes. This draft is submitted to the UNDP Country Office and the Project, and will be presented to all relevant stakeholders and commented upon. The report will be finalized by taking into account the received and pertinent comments.

# PROJECT DESCRIPTION

The strategy of the project is to undertake a comprehensive Ridge to Reef (R2R) approach that addresses the ‘whole island’ priorities of improved management and conservation of upland forest and agricultural ecosystems as well as coastal and marine ecosystems in the Seychelles to produce global benefits in terms of conservation of globally significant biodiversity and the effective management of large marine ecosystems (including coastal and near-shore marine ecosystems), and to arrest and reverse ecosystem degradation.

The project is designed to:

i) reduce threats to globally significant biodiversity by strengthening the country’s system of marine protected areas and reducing negative land-based impacts on those ecosystems, as well as strengthening the management of forested Key Biodiversity Areas (KBAs) and their surroundings;

ii) reverse land degradation in areas outside of formally protected areas and in productive land through the promotion of Sustainable Land Management (SLM) and Sustainable Forest Management (SFM) practices and agroforestry, leading to the restoration and sustainable flows of forest ecosystem services with positive impacts to communities as well as to adjacent coastal and marine ecosystems; and

iii) strengthen capacity and partnerships to promote integrated ecosystem management based on the R2R approach.

By addressing a range of terrestrial threats to the marine environment, including flows of pollutants, nutrients and sediment, disrupted hydrological services, degradation of critical habitat, etc. that have significant negative impacts on important coastal/marine ecosystems including wetlands, mangroves, seagrass beds and coral reefs, the project will simultaneously improve the management of the terrestrial landscape, improve the effectiveness of integrated coastal management practices, and secure the integrity of existing and new marine protected areas in the Seychelles.  At the policy and strategic level, the project will unite the three most important spatial and resource planning processes in the country, namely the Marine Spatial Plan (for the seascape), the Seychelles Strategic Plan (for the landscape), and national and district level Land Use Plans. The project will build on these baseline activities by providing strategic incremental funding to implement priority actions in each of the plans.

The stated objective in the project document is: “To manage and conserve the flow of marine, coastal and terrestrial ecosystem services in targeted islands of the Seychelles for multiple benefits through the Ridge-to-Reef approach”.

This is to be addressed through the following Outcomes:

- Expansion of marine and terrestrial protected areas of the Seychelles’ Inner Islands;

- Strengthened management of upland KBAs and adjacent areas to enhance the flow of ecosystem services through the R2R approach;

- Promoting the ‘Ridge to Reef’ (R2R) approach through knowledge management, ecosystem health monitoring and inter-sectoral coordination

- Knowledge Management, M&E and Gender Mainstreaming

The project is implemented by the Ministry of Agriculture Climate Change and Environment (MACCE), through the Project Team (Project Manager, 2 part-time Technical Advisers for Agriculture and Forestry / Ecosystems, respectively and new part-time “Media, Community Gender and Youth Officer” and “Communication Officer”) based at and with accounting and administrative support from the Programme Coordination Unit (PCU), now revamped as the Programme Development and Coordination Section (PDCS) of MACCE. Specific activities are implemented in selected Protected Areas, Key Biodiversity Areas (KBAs) and Watersheds, that are connected and where conservation and sustainable management activities are implemented through designated “Responsible Partners”, either Government agencies, NGOs, University of Seychelles (UNISEY), Farmers Associations or Watershed Committees.

# FINDINGS

## Project Strategy

The project strategy and design were considered appropriate for Seychelles. Especially the “Ridge to Reef” concept, even when not specifically defined in the project proposal, was understood and considered to be “very appropriate”, “most suitable”, “excellent” and “just what is needed” for Seychelles (though one stakeholder added: “but difficult to do with only USD3million”).

The Project Document is considered to be well written, comprehensive, with good descriptions of barriers and challenges, and a lot of technical detail that was relevant to national priorities. Though most also considered it “too ambitious in scope”. For instance  the proposed revisions to 7 Acts that was considered to be “heavy”. Another stakeholder mentioned that it looked if “everything was piled up”. Some parts of the project document were also found to be less well elaborated, especially the agriculture section, that also included some activities and proposed implementing parties that were questioned. Some of the implementation modalities were also questioned, e.g. the “Low Value Grants”. It was also commented by a project implementer that there are “few activities that really feed the R2R connection”. And budgets for various activities were considered “too small”. A critical element  considered a “good practice” of the project was the close link to and in effect the follow up and upscaling of the activities of the earlier UNDP-AF EbA project, e.g. the continuation and further linking of the Watershed Committees with different activities.

One element of confusion is the discrepancy between different documents in the project end date. The reviewer has seen several project end dates, but the correct one is what appears in the project document and is “December 2025”, or rather January 2026, considering that the project was signed on 9 January 2020 and in all documents this is supposed to be a “72 months project”. This was incorrectly recorded in the UNDP Project Information Management System (PIMS), where January 2025 is stipulated as end date and this now emanates automatically in different documents, including the yearly Project Implementation Report (PIR). This also had as a consequence that the MTR was scheduled to be in July 2022. This was delayed until August – October 2022, but which is still before the mid term date. This was not found to be a problem by the reviewer and stakeholders; in fact this was found to be beneficial so that the project could possibly be redirected if necessary at an early date. In any case the project end date should be corrected in PIMS going forward.

The project tentatively predicts the impact of Covid-19 has delayed project implementation for at least 6-8 months. The destruction of the earlier project office (which caught fire in October 2021, further disrupting work flows with requiring to work from home for nearly 4 months) and changes in the Government administration due to elections in 2020 also caused delays. There have been therefore discussions about a potential “no cost extension” beyond the foreseen end date of the project. Given the now confirmed official end date of the project (January 2026 instead of January 2025) and the fact that this MTR is taking place before mid-term (after some 32 months in a 72 months project), the reviewer finds it premature to request a “no cost extension” at this time. Also, as UNDP pointed out, an extension never comes at “no cost”; even if there is still a project budget there are always extra cost for administration, time and other costs, notably for UNDP and Government, but also for other partners. The reviewer recognizes the challenges and delays caused by COVID-19, project housing and administration changes, as also noticeable in the project expenditure (see below). But the reviewer also notes that the project has picked up pace and is making good progress after the main COVID-19 restrictions have been lifted (early – mid 2022) and with a full and dedicated team in place, including new media, community, gender & youth and communication officers, and a new established office. Also the PDCS is now being mounted and coming on steam, which should further assist the project implementation. Therefore the reviewer recommends not to officially request for a project extension at this early point in the project, also because the GEF seems reticent to allow this (despite some COVID-19 related extensions in existing other projects) and the fact that new and unforeseen challenges may occur in the future project lifetime. The reviewer nevertheless recommends to continue to monitor the project progress and re-discuss this possible extension request in the future, e.g. in 2023 or 2024 (preferably), after the PIRs have been submitted and a clear and evidence based picture may have newly emerged. This should then be comprehensively and openly discussed in a full stakeholder environment, e.g.. a full day workshop / conference, with the main project proponents and stakeholders present, including the NPD, Ministry officials, PDCS, RPs, UNDP (plus the RTA), beneficiaries and others. A potential extension could then be sanctioned by the Project Steering Committee (PSC) and officially submitted through Government and UNDP.

The Results framework was considered to be fit for purpose. Some indicators and targets were adjusted during Inception, that was held shortly after the signing of the project and that was well organized and attended, with the experienced project manager already in place, which is considered “Good Practice”. These changes have however not been recorded in the official UNDP PIMS, which means that the original indicators, baselines and targets still feature in the PIRs and other documents emanating from the PIMS. This means that every time this needs to be amended and justified in each PIR and other reports, which is found tedious and unnecessary, and may confuse readers and overseers of the project. It is recommended to also change this in the PIMS.

## Progress Towards Results

Below is a Summary Table following the MTR template for “Progress towards outcomes”. See Annex VI for full table. The table below uses the following Assessments and Ratings:

| Indicator Assessment Key Green= Achieved | Yellow= On target to be achieved | Red= Not on target to be achieved |
| --- | --- | --- |

| Highly Satisfactory (HS) | The objective/outcome is expected to achieve or exceed all its end-of-project targets, without major shortcomings. The progress towards the objective/outcome can be presented as “good practice”. |
| --- | --- |
| Satisfactory (S) | The objective/outcome is expected to achieve most of its end-of-project targets, with only minor shortcomings. |
| Moderately Satisfactory (MS) | The objective/outcome is expected to achieve most of its end-of-project targets but with significant shortcomings. |
| Moderately Unsatisfactory (MU) | The objective/outcome is expected to achieve its end-of-project targets with major shortcomings. |
| Unsatisfactory (U) | The objective/outcome is expected not to achieve most of its end-of-project targets. |
| Highly Unsatisfactory (HU) | The objective/outcome has failed to achieve its midterm targets, and is not expected to achieve any of its end-of-project targets. |

Changes to original indicators and targets at Inception are recorded below in Red font, and proposed changes at this MTR in red font and yellow highlight.

| Project Strategy | Indicator | Baseline Level | Mid-term Target | End-of- project Target | MT Level & Assessment | Rating | Justification for Rating |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: To manage and conserve the flow of marine, coastal and terrestrial ecosystem services in targeted islands of the Seychelles for multiple benefits through the Ridge-to-Reef approach | - Gender-responsive legal and regulatory frameworks, policies and institutions strengthened and solutions developed and submitted to address conservation, sustainable use and equitable benefit sharing of natural resources, in line with international conventions and national legislation | a) National Forestry Policy: being revised | - a) Revised and discussed with stakeholders in partnership with FAO Project | - a) Submitted to Govt. for approval in partnership with FAO Project |  | MS – S | 63% of the mid-term target has been achieved. Consultancy for 1.b. 1 Forest Mngt Bill signed. Status water regulations to check. |
|  |  | b) 1. Breadfruit and Other Trees Act (out of date), b) 2. the Lighting of Fires Act, b 3. the State Lands and Rivers Act (1903): Out of Date | - b) Updated and discussed with stakeholders | - b) Submitted to Govt. for approval |  |  |  |
|  |  | c) Regulatory amendments under new Water Act to better conserve watersheds and wetland ecosystem services: None | - c) Drafted and discussed with stakeholders | c) Submitted to Govt. for approval |  |  |  |
|  |  | d) Water Quality and Effluent Standards and Codes of Practice: Outdated | - d) Drafted and discussed with stakeholders | - d) Submitted to Govt. for approval |  |  |  |
|  |  | e) Policies and/or regulations regarding compensation of landowners whose land uses are affected by PA designations: None |  |  |  |  |  |
|  |  | f) Review and amend the Acquisition of land in Public Interest Act to include biodiversity value and criteria | f) drafted and discussed with stakeholders | f) Drafts sent to MEECC and Planning |  |  |  |
|  |  | g) Regulations for new Nature Reserve and Conservancy Bill | g) Draft (under the GOS-GEF-UNDP Outer - Islands Project) | - g) Drafts sent to MEECC and Planning |  |  |  |
|  | - Capacity of national partners implementing integrated Ridge to Reef approaches, as measured by total scores on the UNDP Capacity Scorecard | 71% (32/45) | - 76% (34/45) | - 82% (37/45) |  |  | The mid-term target has been 100 % (35/45) achieved |
| Outcome 1: Strengthened management of upland KBAs and adjacent areas to enhance the flow of ecosystem services through the R2R approach | - 5 new Turtle Temporal Protected Areas (TPAs) encompassing 40 ha is strengthened formally established and supported by regulations to conserve biodiversity and maintain ecosystem goods and services (GEF Core Indicator - Marine protected areas newly created) | 0 | 5 TPAs gazetted nomination files submitted to Government | 5 TPAs management plans completed and under implementation |  | S | TPA Nomination files developed 100% (revised MT). |
|  | - Strengthened management of Temporal Protected Area (TPAs) covering 40 ha and Marine Protected Areas (MPAs) covering 1,421 ha, as measured by increased scores on GEF Management Effectiveness Tracking Tool (METT) | Turtle TPAs: 28 Baie Ternay / Port Launay MNP : 61 Curieuse MNP : 71 | 35 66 74 | 40 71 76 |  |  | 44.2 = 100% MT and End Target 71 = 100% MT and End 72 = 97% MT and 95% End |
|  | - Area (ha) of mangrove and other coastal forest ecosystems restored rehabilitated using native species | Mangrove : 0 Coastal Forest : 0 | 10 15 5 | 20 30 10 |  |  | 100% (15.5ha of 15 ha) of the revised MT target has been achieved. However, a concern about survival rate and real rehabilitated area remains. |
|  | - No. of KBAs with required technical documents and draft legal documents for gazetting presented to the Government | 0 | 2 | 6 / 5 (covering 2,235 ha) |  |  | 100% MT target and 60 % end target achieved with 5 instead of 6 KBAs having technical documents completed. 2 KBAs are merged into 1, with same Ha (2,235 Ha) as the initial 6 KBAs |
| Outcome 2: Strengthened management of upland KBAs and adjacent areas to enhance the flow of ecosystem services through the R2R approach | - Number of functioning Watershed Committees, with gender and age diversity | 1 Committee 4 committees set up under the GOS-AF-UNDP Ecosystem based Adaptation project | 4 committees with 30% women participation | 4, with 50% women and 15% youth participation |  | MS | 3 of the 4 (R2R site) Watershed Committees set up (75% of MT Target), with overall women participation 43% and youth 20%. Proposed shift from Grand Police to Caiman Watershed. |
|  | - Restoration Rehabilitation of areas critical for ecological functioning in priority watersheds / upland forests on Praslin | No. of ha of fire-degraded upland forest restored rehabilitated: 0 No. of ha cleared of IAS flora and replanted with native tree species and other non-native non-inavsive species: 0 | 4 40 10 | 10 60 20 |  |  | 100% (14.1of 14ha) of the revised mid-term target is achieved. |
|  | - No. of ha reforested within priority watersheds and in areas within / adjacent to target KBAs | 0 | 40 50 | 100 |  |  | 105% (52.4 of 50ha) of revised mid-term targets achieved. Here also concerns of survival rate and maintenance. Needs to be monitored. |
|  | - No. of ha of low-productivity land in the Val d’Endor, and Anse Royale Caiman and Praslin watersheds converted to agroforestry | 0 | 40 25 | 100 50 |  |  | 4% achieved based on revised mid-term target. |
|  | - Amount of tCO2eq GHG emissions avoided / sequestered through avoided deforestation and forest degradation, reforestation, agroforestry and conservation agriculture | 0 tCO2eq | 18,273 tCO2eq To be revised to: 7,070 tCO2eq, as recalculated by consultant with updated data | 43,853 tCO2eq To be revised to: 16,134tCO2eq, as recalculated by consultant with updated data |  |  | Targets recalculated by specialist with new data. Still only 17% of revised MT target achieved |
| Outcome 3: Promoting the ‘Ridge to Reef’ (R2R) approach through knowledge management, ecosystem health monitoring and inter-sectoral coordination | - Number of institutional partners using the online platform to share data, findings and other information generated by field interventions on Ridge to Reef approaches | 0 | 2 | 5 |  | MU – MS | Project Indicator target delayed: 5% achieved based on mid-term target. Now platform is underway |
|  | - Integrated ecosystem health monitoring at project sites institutionalised, with information management and dissemination coordinated by DOE, BERI and NISTI, to support the implementation of R2R approaches | No system exists | Ecosystem data being collected and consolidated | Data management system operating |  |  | Project indicator 50% achieved at midterm target. |
|  | - Policy recommendations to improve the effectiveness of R2R approaches, based on the integrated ecosystem health monitoring results, developed and submitted adopted by relevant ministries | 0 | 1 | 2 |  |  | Project Indicator target 5% achieved based on mid-term target. |
|  | - No. of local officials sensitised on R2R approaches and partnering with the project to facilitate community involvement in the management of KBAs, ecosystem monitoring, and undertaking sustainable agriculture and forest management interventions | Regional District Council members / staff: 0 District Administration members / staff: 0 | 4 6 | 8 12 |  |  | Project Indicator target 100% achieved based on mid-term target. |
| Outcome 4: Knowledge Management, M&E and Gender Mainstreaming | - No. of policies / strategies / programs supporting R2R approaches agreed with other national and international conservation programmes | 0 | 2 | 5 |  | MS - S | Project Indicator 100% achieved based on mid-term targets with 2 policies finalized. |
|  | - % of women among the project participants | 0 | >=30% | >= 50% |  |  | Project Indicator 100% achieved based on mid-term targets. |
|  | - Total number of direct project beneficiaries (m/f) | 0 | >= 270 (at least 40% are women) | >= 600 (at least 40% are women) |  |  | Project indicator target 52% achieved, based on mid-term target, with 140 of 270 beneficiaries (34%) being women. |

The indicators for the Project Objective are progressing Moderately Satisfactory to Satisfactory, with some (sub-)indicators already achieved their mid-term targets and even end of project targets (e.g. National Forest Policy, Lighting of Fires Act), or underway to reach mid- and end-targets (e.g. revision of State Land and Rivers Act into the three separate State Land Management, Water, and Forest & other Trees Bills, Regulations under the new Nature Reserves and Conservancy Act), despite the “heavy” concentration of several legislative indicators, which often falls outside the control of the project.. Some indicators are not on Track, e.g. the Regulatory amendments under the new Water Act are still in draft and under discussion with few outstanding matters to clarify. The finalization, approval and assenting / promulgation of the targeted laws should be monitored and followed, despite the fact that this formalization is nominally outside of the control of the Project. The indicator on “Capacity of national partners implementing integrated Ridge to Reef approaches, as measured by total scores on the UNDP Capacity Scorecard” has reached its mid-term target and seems well on its way to reach the end target.

Outcome 1 is progressing Satisfactory, with all indicators having reached their revised MT targets (as revised and agreed in the Inception Workshop). Nomination files for SPAs were finalized. The Management Effectiveness Tracking Tool (METT) scores for SPAs and Baie Ternay / Port Launay MNP have surpassed the MT target and reached the end Target, and Curieuse MNP is at 97% of MT target. All of the rehabilitation works on Praslin have reached their targets, although a concern remains of the survival rate and sustainability of some of the rehabilitated areas. This is in particular on Curieuse Island where the selected mangroves / coastal forests were indeed cleared and rehabilitated, but the Mangrove area at Baie Larie (La Saline / Anse Saline) most of the replanted species did not survive. This was apparently because of the time of planting (too late in / after the rainy season) that was done by an outside contractor. The SPGA that manages the island mentioned that it was not involved in this rehabilitation exercise and was unhappy with the final result. This mangrove and coastal forest area looks indeed “unfinished” and even desolate (cleared sandy area without many plants), which is also due to the destruction of the “causeway” in front of the old turtle pond during the tsunami of 2004, which caused a change of habitat where the original dark organic mangrove soil was covered with inorganic and much finer and infertile sand. The project mentioned that the other sites on Curieuse look better with a healthy survival rate, but this could not be verified by the consultant at all sites (e.g. Anse Badamier). Although the targets of “Rehabilitated Areas” were defined by the Steering Committee as “area with trees planted”, the reviewer recommends to monitor the survival rate and the final, real “rehabilitated areas”, either by the parties responsible for the area or the project itself.

In order to achieve the end of project targets, new sites for rehabilitation are being identified. These should preferably be sites in the Districts and watersheds where the project is already operating and where the R2R links can be established and shown. This could be in Baie  Lazare (potential site in Val d’en Dor already identified, where the watershed committee is active), but e.g. also in Anse Boileau (Caiman watershed), Port Launay / Baie Ternay (to link with on-going mangrove restoration and activties around the Marine Park, possibly in collaboration with the Ephelia Hotel and adjacent communities), or in Praslin (Anse Kerlan, Possession, Petit Coeur, where TRASS has already identified possible areas and watersheds).

The mid term target for the important indicator for the Key Biodiversity Areas (KBAs) has been reached with the delineation and descriptions presented to Cabinet (in September 2022). However this is for 5 instead of the foreseen 6 KBAs, as 2 KBAs have been merged but with the same final total Ha under KBAs (2,235Ha). The identified and delineated will now have to be verified through another round of consultation with the respective landowners before the final designation under the new National Reserves and Conservancy Act will be assigned and promulgated.

Outcome 2 is progressing Moderately Satisfactory. The number of Watersheds with functioning watershed committees is at MTR 3 instead of 4, with the targeted number of women participants achieved. These are the 3 watershed committees that have been set up by the predecessor UNDP – Adaptation Fund (AF) “Ecosystem based Adaptation (EbA)” Project that are now supported by the R2R project. A newly envisaged Watershed Committee in the area of Grand Police has not materialized, as there is on-going uncertainty and dispute of land ownership in this area, as well as an already approved large scale tourism development. MACCE therefore requested to halt any activities in that area. After discussions with stakeholders it is now recommended to shift the activities away from Grand Police to another sensitive watershed area (Caiman) adjacent to and within the Montagne Planneau KBA and with an already formed Watershed Committee. But because of the sensitive ecosystems at Grand Police, including the “Collines du Sud” KBA, wetlands and turtle nesting areas at the beaches, it is recommended to continue the on-going activities on the Seasonal Protected Areas (SPAs) at the several beaches in that area (these beaches do not form part of the disputed lands and are in any case not access restricted). The project will thereby still be involved and be able to keep an eye on this area and possible start activities when the land development issues have been solved (if feasible within the timeframe of the project).

The mid-term targets for reforested and rehabilitated areas have been achieved, although here also the survival rates and re-invasions will need to be monitored.

The target of area converted to Agroforestry is well below the mid-term target and hence “Unsatisfactory”. This has several reasons as explained by the project and pertinent stakeholders. It was found difficult to identify and convince smallholder farmers in the areas designated by the project document to convert to Agroforestry on “low productivity agricultural land” and “degraded forest areas”. As according to the prevailing Forest Law, forest land, even degraded, cannot be converted to (more) productive agroforestry land. Especially in the designated area of Anse Royale, no “low productivity land “ could be found where farmers are interested in converting to Agroforestry. It is recommended after discussion with all stakeholders (Department of Agriculture, Farmers Associations, individual farmers, Project Team) to change from the identified Anse Royale site to other areas where agroforestry is possible and farmers are interested, e.g. Baie Lazare (with already on -going agroforestry demonstrations), Caiman (where project activities are recommended to shift to anyway, cf. previous paragraph) and Praslin (where areas are available, and the project and responsible Partners (TRASS, SEYFA, Watershed Committee) are active in several watersheds).

The indicator under this Outcome related to “Amount of tCO2eq GHG emissions avoided / sequestered through avoided deforestation and forest degradation, reforestation, agroforestry and conservation agriculture” as measured through the Ex-Ante Carbon-Balance Tool (EX-ACT) is also progressing “unsatisfactory”. An international consultant was recruited to measure progress for this indicator, also because this tool is very complicated and no one so far in Seychelles has been able to use this tool. The expert looked at methodology, baselines and targets. The targets were revised by the expert, who found that outdated baseline data were used during project preparation, and the mitigation targets also didn’t consider revised rehabilitation and agroforestry (under Indicators 8 and 10). At time of measurement (August 2022) a calculated 1,195tCO2eq. was avoided / sequestered, which is only 17% of the revised MT Target. Some of this unsatisfactory achievement can be made up if especially the agroforestry activities gain momentum and will achieve their target. Nevertheless, it seems some of the selected sites still lose tree cover even when rehabilitated, which will need a more comprehensive and scientific approach to understand and mitigate this, in order to reach this carbon emissions  target.

Under Outcome 3, progress is moderately unsatisfactory to moderately satisfactory, with some of the activities slow to start or changed Responsible Partner. The ecosystem monitoring efforts were delayed but has now picked up under the leadership at BERI and UNISEY. The foreseen online platform to share data generated by the R2R project has not moved much yet. The National Institute of Science Technology and Innovation (NISTI) was envisaged as the responsible entity for developing such a platform, but they were not responsive. Through a new bidding process BERI/UNISEY came out as the sole partner to be able to undertake this. Together with other interested parties (SEYCATT, MACCE), BERI / UNISEY is now moving forward. The policy recommendations based on the ecosystem health monitoring results has not yet been implemented, despite a good and valuable gap analysis undertaken by a consultant. The project has been waiting for the results of the ecosystem monitoring systems in place (see Indicator 13) to implement the recommendations from the gap analysis. The MTR consultant recommends now in any case start with some pertinent recommendations from the report to revise the policy and legislative framework, without waiting for these monitoring results to come out (which may take another couple of years). This could especially be around agriculture, since this is central in the R2R approach in Seychelles, and food security has become a priority for government, but has an outdated legislative (Agriculture Act of 1966) and policy framework (Agriculture Policy expired in 2020). Especially developing a possible new “Agriculture Lands Protection Act” and a new Agricultural Policy (MACCE is working on a new policy since the previous Agriculture policy expired in 2020) as recommended in the “policy Gap Analysis” could be supported and influenced so that relevant R2R approaches are integrated (e.g. on agroforestry, organic agriculture and sustainable land management).

The Indicator: “number of officials trained” has reached its MT target.

Outcome 4 is progressing Moderately Satisfactory to Satisfactory. Some intended policies have been finalized and awareness and training programmes have picked up drastically by mid 2022 after the restrictions due to COVID-19 were mostly lifted, with total numbers of project participants and trainees approaching the targets and exceeding the targeted percentages of women trainees. The project has also shifted its focus to increase its women participants to now include also more youth. This is something that should be pursued further in the project by developing a project strategy and action plan to include more youth in the project, with at least gender parity, e.g. through more trainings for youth groups, employing part-time youth to assist on activities, directing some of the agriculture funds to Seychelles Institute for Agriculture and Horticulture (SIAH) and youth groups.

The project could also include all District Administrators (DAs) in their awareness and training programmes, as this is important for their work in the District and most DAs and policy and decision-makers  in the parent ministry of Local Government are interested. This will also help in reaching the total end targets of numbers of project beneficiaries and stakeholders and officials trained. Plus it may also help with the continuity of R2R programming in Districts, even when DAs change (as they often do), as they will then be better informed when shifting to other Districts. This will also improve the institutional memory around R2R, ecosystem integrity and sustainable management, including through the possible “district environmental profiles”. This could also be through more targeted training programmes, e.g. more general awareness programmes around R2R for all DAs and more specific trainings for those DAs directly involved in the project, e.g. when there are MPA, KBA, watershed or sustainable land management activities in their Districts.

The proposed changes at MTR to the indicators and targets are the following:

- The end target of Indicator 6. “No. of KBAs with required technical documents and draft legal documents for gazetting presented to the Government”, to be adjusted from 6 to 5, as 2 of the envisaged KBAs have now been merged, with the same coverage in Ha (2,235 ha).

- Indicator 10: Change in location for agroforestry sites from “Anse Royale Watershed” to “Caiman Watershed” and/or any suitable Watershed on Praslin (to be investigated).

- The targets of Indicator 11: “Amount of tCO2eq GHG emissions avoided / sequestered through avoided deforestation and forest degradation, reforestation, agroforestry and conservation agriculture”, adjusted from 18,273 tCO2eq to 7,070 tCO2eq at mid-term and from 43,853 tCO2eq to 16,134tCO2eq at end target, as this has been recalculated by an international expert with updated data.

Remaining barriers to achieving the project objective

Finalizing of Bills and their promulgation is crucial, also for starting and following up on further activities (e.g. implementation of standards and regulations, monitoring ecosystem quality, including water effluents following the promulgated standards, designations of PAs and KBAs, etc.). However, this is largely out of control of the project and in the hands of the Government, including parliament, pressure groups, the parliamentary and legislative calendar, etc. If there may be delays in promulgation of relevant laws and regulations this may slow down other activities. This may have e.g. consequences on the implementation of the KBA, SPA and Watershed Management plans that have already been developed.

Another barrier could be the final designations and status of the KBAs. This is as of now still under discussion and will depend on the final criteria for designation that are being developed under the NRCA. This is sensitive, not only because of the landownership in the KBAs but also because of the on-going debate in Seychelles seems to be shifting towards allowing of economic development vs. ecological integrity. As an important stakeholder mentioned, the country needs to be “smart” about the designation and monitoring of KBAs, to ensure the maximum buy in and ownership.

The development and appropriate use of the envisaged data platform is of importance for maintaining ecosystem integrity and allowing sustainable development in Seychelles. This will need to be pursued under the leadership of BERI - UNISEY, and the maximum amount of possible parties that may have relevant data will need to be approached and enticed to use the platform.

Clarity of implementation, ownership and full commitment of partners is important for achieving the desired results for the R2R project. This pertains e.g. to the uptake of Agroforestry, implementation of watershed and KBA Management Plan, etc. But also for development of policies and plans, that need to be “directional” (“what do we need, where are we going and who does what?”).

In order to achieve the results and overcome above mentioned barriers, the right approach and capacities are needed. Continued capacity development, advocacy, awareness and communication efforts are needed to achieve the desired result. In fact awareness, advocacy and communication around R2R concept, approach and implementation will need to speed up, which is expected with the recruitment of the dedicated communications officer for the project and for the PDCS.

## Project Implementation and Adaptive Management

Management Arrangements

The reviewer and all interviewed stakeholders find the project well managed with an experienced and dedicated Project Manager providing good leadership, a good (part-time) technical team and with solid and timely financial and administrative support. Relations with partners, project beneficiaries, members of PSC, implementing agencies (MACCE) and oversight bodies (UNDP) are appreciated. The project feels though that the Implementing Partner (MACCE) support is sometimes lacking (e.g. from Agriculture, Conservation and Biodiversity Department and others) and should be stepped up. Given the Technical Advisers and Community specialist are all part-time (some 90 working days/year) and that their input decreases over time, it may be worth it to see if these advisers can be kept for longer than anticipated in the budget until (almost?) the end of the project, as they may be surely needed to finalize, document and report on activities, results and recommendations.

The implementation of activities is in most cases organized through Responsible Parties (RPs, e.g.  SPGA, MCSS, BERI, Farmers Associations (FAs), with RPs responsible for $1,152,367 of the total budget. In some cases that works well, but the capacities, understanding and commitments of these RPs vary. Therefore, in order to still make meaningful progress and achieve the set targets, the Project has taken over some of the activities from RPs to implement these through own means, including through contractors. In most cases this was because of lack of capacity, e.g. an audit risk was raised for receiving cash advances by FAs, also because no proper capacity assessment was done at project preparation stage, and this was therefore stopped. The SPGA also had capacity challenges as it went through a period of transition (from SNPA to SPGA). Although this shift to implementation of some activities from RPs to the project  worked in terms of reaching some of the targets, this may have frustrated some of the RPs (e.g. SPGA) and may not have helped with capacity development and growing confidence so that these entities will be able to implement activities on their own in the future. These entities are nevertheless still involved in various preparatory and training activities by the project.

The overarching Programme Coordination Unit (PCU) that was established in 2008 and worked under an Aide Memoire between UNDP and the Ministry of Environment and where the project was housed under, has over the years lost its influence and direction. This was due to the many changes in personnel, departure of key staff and a vulnerable financial position of the PCU because of a decreasing portfolio of projects. The PCU also had to adapt its strategies based on the various Audit recommendations to adopt national policies and procedures. After further analysis and in discussion with main partners, notably MACCE and UNDP, and following earlier recommendations (e.g. from the final evaluation of the UNDP-AF EbA project), it was decided to revamp the PCU and turn it into an integral part of the Ministry. It has now transitioned in the Programme Development and Coordination Section (PDCS), under the office of the Principal Secretary for Climate Change under MACCE. The vision of the PDCS remained somewhat the same as for the PCU (provide coherent oversight and coordination amongst programmes and develop new relevant project – paraphrased by reviewer), but this will now be under the full responsibility of and funded under MACCE, with a new Chief Programme Coordinator (CPC, already in place since July 2022), M&E Officer, Communications Officer (both positions approved in September 2022 – though may only be recruited in 2023 and 2024) and administrative support and driver (already in place). At present the Standard Operational Procedures (SOPs) are being finalized with the help of a consultant, and with the full contingent in place this should improve oversight, coordination and support for the project. The project voiced a concern of the change in procurement, as this will fall now under the Procurement Oversight Unit (POU) of the Government, but officials and staff dealing with this entity already have assured that this can work smoothly when all preparation are done in line with requirements, though this may require some getting used to. The project is waiting for the final SOPs and instructions to start operating under this new regime.

UNDP as Implementing Partner has changed its involvement in the project. In previous projects, UNDP was more directly involved in the implementation and monitoring of the project, and it was even housed in the same premises. However, based on the most recent (November 2021) HACT Micro-Assessment and Audit of MACCE, which rated the Ministry as Low Risk and capable of such “Full NIM modality”, UNDP is now “stepping back” to provide oversight and quality assurance of projects through independent audits and midterm and terminal reviews in line with the UNDP Policy & Programming Policies & Procedures (POPP). GEF is insistent that project implementation should be led, where feasible, by the national counterparts such that the project results are fully integrated within the national system and to ensure sustainability. As a consequence, UNDP shall only be able to support cash advance or reimbursements, and requests for direct payment will no longer be in function. UNDP has also financial and personnel challenges, with no TRAC resources available for projects in Seychelles, and the departure of the Programme and Operations Specialist in the Seychelles office (end September 2022), with no immediate replacement in sight. The remaining staff member is 75% funded by the UNDP-AF Coral Restoration project as national project manager, with only 25% dedicated to programme and project oversight role. Given the current workload and constantly emerging new corporate reporting requirements, there may be a need in additional staff if the UNDP portfolio in Seychelles expands in the future.

Work planning

The project activities and implementation are very well planned. This was already apparent at the Inception Workshop which was organized and reported upon very timely and in relevant detail by the Project Manager who was already on board at that time (on part-time basis). This was important, as the Result Framework with the indicators with its targets and the Risk Log were discussed by the relevant participants, and some changes were agreed and Frameworks updated. This is considered good practice, however the changed indicators and targets were not recorded in the PIMS.

The project design and activities as described in the Project Document are followed in detail, taking into account some of the changes agreed at the Inception Workshop. This involved especially very elaborate and tedious planning with different RPs, founded on detailed Grant Agreements between RPs and the Project. As mentioned before, some of the RPs have lagged behind in implementation. This created challenges to the full project, as also the RPs financial reporting was often late or they could not expend the 80% which is needed for advance of the quarterly agreed budget, and therefore no funds for other RPs and the Project itself could be advanced. This was taken up in meetings with MACCE, UNDP and PSC, but no satisfactory and long-term solution has yet been found. The reviewer recommend to review the mechanism again and agree on a smoother way to advance and report on funds.

The project under the leadership of the Project Manager has a remarkable focus on Results Based Management (RBM), especially through its emphasis on the results indicators and their targets. This means that the whole project team and partners have a good eye on the results and targets and what needs to be achieved. Even with this focus, the project displays adequate adaptive management, by finding alternative ways to implement activities to achieve the targets when needed. This was the case during COVID when the planning concentrated on procurement and combining activities, instead of organizing community events or trainings (for instance) as per the workplan. The downside of such focus on targets and if applied too rigidly, could be that some of the partners could be left behind when the project implements activities that could be undertaken by partners themselves e.g. by the SPGA, Department of Agriculture and/or Farmers Associations. Implementing the activities through the project could then affect sustainability of project results, when targets and results are achieved, but there is no ownership and possibly little effort to sustain its results. The reviewer recommends to continue discussions with and attempts to implement new activities in close collaboration with the intended partners, even if this could potentially temporarily delay the timely achievement of targets, but this would enhance the sustainability of the results in the end.

Finance and co-finance

The disbursement of the funds for the project are slow, see also the financial delivery graph and table below.

| Component / Outcome | Total Budget | Expenditure (USD) |  |  |  | Balance |
| --- | --- | --- | --- | --- | --- | --- |
|  | (USD) | 2020 | 2021 | 2022 (June 2022) | Total |  |
| 1: Expansion of marine and terrestrial protected areas of the Seychelles’ Inner Islands | 1.106.249,00 | 91.745,54 | 245.955,35 | 101.363,21 | 437.689,39 | 668.559,61 |
| 2: Strengthened management of upland KBAs and adjacent areas to enhance the flow of ecosystem services through the R2R approach | 2.002.638,00 | 92.713,96 | 232.429,16 | 89.272,18 | 423.272,29 | 1.579.365,71 |
| 3: Promoting the R2R approach through knowledge management, ecosystem health monitoring, and inter-sectoral coordination to foster partnerships in the Seychelles and knowledge-sharing among SIDS | 200.000,00 | 2.848,84 | 12.821,83 | 648,08 | 16.318,75 | 183.681,25 |
| 4: Knowledge Management, M&E and Gender Mainstreaming | 413.500,00 | 23.597,97 | 43.578,67 | 17.475,69 | 84.652,33 | 328.847,67 |
| Project Management | 176.527,00 | 17.106,87 | 19.743,53 | 13.236,97 | 50.087,37 | 159.420,13 |
| PROJECT TOTAL | 3.898.914,00 | 228.013,18 | 554.528,54 | 221.996,13 | 1.012.020,13 | 2.919.874,37 |
|  |  |  |  |  | 26% |  |

This slow delivery is understandable because of COVID and other challenges (office housing problems, changes in Government, restructuring of PCU) already highlighted earlier. Another challenge is the capacity of some RPs to timely deliver and report, which also has negative consequences for disbursing the required advances. Partners need to know their limitations, identify bottlenecks, and capacities of RPs will need to be strengthened in this regard.

As this slow delivery can have more negative consequences further down the line and thereby affect timely implementation of activities and achievement of results and to ensure that the project catches up, a Delivery Action Plan may need to be put in place, as is already proposed by UNDP. This could entail:

(i)	Carry out joint combined budgeting and procurement planning with all project partners, to ensure better coordination and realize efficiencies wherever possible;

(ii)	Develop all TORS and activity concept notes under each AWP as a block in advance at the start of each quarter;

(iii)	Front load the budget with purchase of equipment and other larger-value items;

(iv)	Consolidate tenders or consultancies where possible and sensible;

(v)	Build the time required for procurement into the workplan and make sure that procurement processes are triggered well enough in advance of when the service/product is required, and in the right sequence;

(vi)	Explore the possibility of setting up partnerships with appropriately capacitated NGOs and/or other partners who are already active in the domain, to deliver clusters of related outputs.

The co-financing commitments and disbursements as recorded by the project are summarized here below and further detailed in Annex VII.

| Co-financing amount confirmed at CEO Endorsement / Approval | Materialized co-financing as of MTR |
| --- | --- |
| 27,279,946 | 9,204,574 |
|  | 33% |

There is confusion about the total committed co-financing, as this was recorded and detailed at CEO endorsement at USD27,279,946, but recorded on the cover page of the signed project document as USD27,204,946. After further inspection this proves to be an error, as inside the project document (page 110) this is detailed indeed as USD27,279,946. This should be corrected.

The seemingly low amount of co-financing disbursed may be due to the following:

- Unrealistically high amounts of co-financing commitments at project endorsement;

- Financial difficulties during COVID (esp. for NGOs)

- Lack of income generated through tourism led to partners, such as MCSS and SPGA.

- Ceasing of Corporate Social Responsibilities (CSR) from private sector that financed many NGOs

The shortfall in recorded co-financing disbursement could possibly be overcome by convening meetings with co-financiers to assess their current financial circumstances and future capacity to deliver the co-finance commitments, and explore solutions to any obstacles. It is nevertheless commendable that the project managed to increased the number of Co-Financiers with 12 new partners that have disbursed another USD1,270,146 (not included in the CF commitments at project start).

The audit that was undertaken on behalf of UNDP was unqualified, but identified some risk areas, e.g.:

- invoices from activity partners not being stamped paid;

- recommend for project to have an accounting software instead of excel;

- physical count and updating of the fixed asset register by all partners; and

- submission of all supporting documents.

These areas will need to be addressed.

Project-level monitoring and evaluation systems

The rather broad and complex project is well monitored by the project team, with the Project M&E systems concentrating mainly on the Indicators and Targets. Apart from the normal Quarterly Progress Reports that are based on the RPs progress reports, the project also produces “evidence based report” just prior to the Progress Implementation Reports (PIRs) that are used to inform and are attached to the PIRs (another innovative and “good practice”). The project staff, including PM and TAs regularly visit project sites and discuss with stakeholders, including RPs and project beneficiaries.

The PSC meetings are reasonably well attended and discuss pertinent issues and take decisions. Some PSC members that don’t regularly show up are reminded by the project to attend (though not always to good avail, e.g. the representative  of the Citizens Engagement Platform, Seychelles (CEPS) has never attended).

UNDP does no longer provide full operational support and project monitoring, e.g. UNDP is no longer involved in supporting or clarifying operational issues of the PDCS and does not partake in Technical Evaluation Committees. as before, as instructed by the GEF under the new “Full NIM” regime. UNDP does provide a quality control and oversight function, mainly through the PSC, visits occasionally project sites, and provides the usual cash advances to the project. The UNDP RTA normally provides support and comments during the PIRs.

The PDCS is still transiting from the earlier PCU and is putting in place its staff complement and SOPs. The recently newly appointed CPC has not yet visited the project yet, but promised to do so soon.

The PIMS monitoring and reporting system is rigid, and the mistakes recorded in there should be fixed, as they cause confusion and extra effort to report the right dates and indicators every year.

Stakeholder engagement

Stakeholder engagement in the development and implementation of the project is rated as adequate. Especially working relations with the responsible parties and direct stakeholders in the project are good, but some of the direct stakeholders and beneficiaries lack insight into the R2R concept. Community partnerships with e.g. the watershed committees are strong, especially with the addition of the Media, Community, Gender and Youth Officer in the Project (who was also instrumental in setting up and guiding the watershed communities in the predecessor EbA project). There have been trainings with women and youth that were beneficial and inspired some of the participants (especially the youth). However, some “outsiders” do not know much about the project, and there are only limited partnerships with entities that could benefit from and potentially invest in R2R approaches (e.g. SEYCATT, World Bank, FAO, Global Coral Reef Initiative, etc.). More can be done to create better awareness, especially with interested and affected parties like e.g. District Administrators, other farmers (those not directly involved in the project) and private land owners, but also potential donors and other interested parties.

Reporting

The reporting around the rather complex project is quite elaborate. RPs submit quarterly progress and financial reports. The quality of these vary between the RPs, and late or incomplete financial reporting from RPS can have consequences and cause delay for the entire project. This will need to be addressed (again). Apart from the normative reporting, the project also produces “evidence based reports” for their activities, focused on the indicators and targets, that inform and are attached to the PIRs. The PIRs are very comprehensive and of good quality. The reporting for the PIRs is made however extra tedious because the changes in some indicators and targets that were agreed in the Inception Workshop are not recorded in the PIMS system and hence the old indicators and targets still appear in the yearly PIR template, which needs to be corrected every year with justifications. All reports are tabled and presented to the PSC, where changes and recommendations are discussed and agreed. These PSC meetings are generally well attended and considered meaningful.

Communications

As mentioned above, the communication around the project in terms of creating awareness of the concept and visibility of results can be strengthened, especially with parties and stakeholders that are not intimately involved with the project. This is important from this point in the project going forward, as this will increase the sustainability of project results and may create attention with potential and future interested parties to continue with the concept and activities. The communication and awareness are expected to improve now that a dedicated Communication Officer for the project has come on board, and the PDCS will also recruit a new communication officer. A targeted communication strategy and action plan for the project from this point forward, possibly based on the existing “Public Awareness Strategy”, with clear distinction of roles between the project and the PDCS communication officers should be established.

Considering the above mentioned components and comments, the overall rating for Project Implementation and Adaptive Management is Satisfactory (Implementation of most of the seven components is leading to efficient and effective project implementation and adaptive management except for only few that are subject to remedial action).

## Sustainability

Sustainability is generally considered to be the likelihood of continued benefits after the project ends. Consequently the assessment of sustainability at midterm considers the risks that are likely to affect the continuation of project outcomes.

Financial risk to sustainability

The likelihood of financial and economic resources not being available once the GEF assistance ends is high. This has already been the experience with other projects, e.g. the recently completed UNDP-AF EbA project that ended in March 2022, and which is considered to be a predecessor to the R2R project. For instance, the Watershed Committees that were established through the EbA project and now receive continued support from the R2R project are doing well. One of the Watershed Committees established by the EbA project and that does not receive support from the R2R Project, the North East Point Watershed Committee, is struggling, as no government or other support is forthcoming. This is already visible in the cleared wetlands in the watershed, which were supposed to be maintained by the Government together with the Committee members (as also recommended in the Final Evaluation of the EbA project) but this has not materialized because of lack of funds and institutional support, with the wetland now dirty and clogging again and in need of cleaning.

Additional and sustained funding will need to be sourced to ensure sustainability after project completion, either from public or private sources. Government will need to find targeted funding for maintenance of the main project results that would need to be sustained. This financial support could be from the Government budget (esp. MACCE, in collaboration with Ministry of Finance), or from vertical or other donor funds, (E.g. GEF-8, AF, GCF, EU, bilateral donors, Global Coral Reef Initiative, others). Established local funding mechanisms available in Seychelles should also be explored, e.g. SEYCATT, UNDP-GEF SGP, Biodiversity Funds, or private sector initiatives, e.g. through (re-established) Corporate Social Responsibility (CRS) or other financing mechanisms (Payment for Ecosystem Services, Bonds, etc.). Some of the RPs to the project are self-sustaining, (e.g. the NGOS MCSS, TRASS, but now also the SPGA) and these could be assisted in exploring and sourcing funds to sustain project results. All this should be further detailed and made clear in a project Exit Strategy that should include firm commitments, responsibilities, financial mechanisms and identify funding streams, including from private sector (e.g. banks, other investors / financiers). Such an Exit Strategy should be developed as a priority and discussed in detail with government, UNDP and other stakeholders as early as possible, e.g. mid or end 2023.

The newly formed PDCS has also an instrumental role to play in sourcing and ensuring financing for priority activities that need to be sustained. The PDCS is working on a compendium of existing and completed projects, a Resource Mobilization Strategy and Donor Mapping, and plans to put a pipeline of priority project ideas and concepts in place. The M&E officer that will be recruited could play an important role in managing this, including follow up and reporting on projects MTR and Final Evaluation recommendations, especially around ensuring the sustainability of priority results, including possible integration of such recommendations in new projects.

Socio-economic risk to sustainability

The Seychelles, government and the project are still suffering from the still on-going COVID-19 pandemic. The pandemic directly (number of COVID cases) and indirectly (through the restrictions put in place) caused a delay in the project progress, although this was handled as well as possible by the project. The country witnessed an economic resurgence after lifting of the COVID-19 related restrictions with a rapidly increasing number of tourist visits, which is crucial for the economy and also for the financing of some of the environmental activities in the country (e.g. through park fees). Nevertheless, COVID-19 is still prevalent and it remains to be seen how this will develop and what restrictions might be put in place again in future, although the outlook looks promising with also the WHO declaring that the COVID-19 pandemic is largely under control and that “the end is in sight”.

However, new global geo-political and economic threats have surfaced, with the war in Ukraine leading to concomitant travel and energy access restrictions, as well as supply problems (e.g. food and fertilizers), thereby causing global economic hardship and inflation. This may well have consequences in Seychelles as well, through locally increasing energy prices, foreign exchange fluctuations and scarcity, and local inflationary pressures. This would mainly be linked to supply disruptions (energy, food, inputs), with also possibly again decreasing tourist entries (the important Russian and European tourist visitor markets will surely be affected). It is unclear what the government can and will do against these foreseen socio-economic hardships and how this may affect the project. Budgetary implications on the project may be felt with these inflation and "recessionary" trends, potentially hampering implementation of activities. Co-financing may be affected as well.

A potential risk from the above mentioned economic threats could be that Seychelles would opt for economic over sustainable development. This could be e.g. if large tourism developments or other investments in ecologically sensitive areas would be approved for immediate financial gains, thereby trumping environmental and sustainable development efforts. Or that food security and intensification is prioritized over sustainable agriculture, thereby potentially increasing the danger of further ecosystems degradation and pollution in some areas.

Institutional framework and governance risk to sustainability

Institutional and governance risks to sustainability are clearly present in Seychelles, putting the sustainability of some of the R2R achievements and results in danger. This is partly due to the required legislative framework for an appropriate R2R approach that may not be in place, monitored and/or enforced. The revision of laws and development of new Bill, Acts and Regulations envisaged by the project should be completed with urgency, and the capacity for its monitoring and enforcement will need to be put in pace.  It is understood that some of the articles in the new Bill and Acts + regulations may cause friction and/or opposition, especially when new designated protected areas or other restrictions on land ownership may come in place. This is already the case with the delineation and designation efforts of the KBAs, where different stakeholders, including nearby landowners, members of the general public and assembly warn against further restrictions to the right of ownership, access and use. This is the case in the Grand Police area, where project activities have been put to a halt because of unresolved land ownership and development claims. Such claims are even putting a burden on the Ministry of Land Use and Habitat (MLUH), as the policy is  to financially compensate or exchange for other land in such claims, which is both difficult for the country under current circumstances. Therefore these new designations need to be carefully managed, in a “smart way”, with new and different area designations and possibilities of (restricted) use by stakeholders or owners in different areas (e.g. for forestry, sustainable agriculture or other “low impact development”).

There is also a risk to effective implementation of the R2R approach because of the inadequate definitions and ineffective link between the different ecosystem (e.g. KBA, Green Corridor, watersheds, coasts and shorelines) and land use planning systems. Capacities for better and connected land use planning will need to be strengthened, although this may be difficult under the current R2R project.

Environmental risks to sustainability

The following environmental risks that could undermine and reverse the project’s outcomes and results are identified, that are also in relation to above mentioned institutional and governance risks:

- Non gazetting of necessary laws, regulations and designations.

- Push back on environmental / conservation gains, e.g. in name of Food Security or Economic Development, in order sustaining development and livelihoods.

- Constitutional rights vs. environmental assets, e.g. in terms of land ownership and use.

All of the above risks and threats to the sustainability of project results need to be captured in an Exit Strategy, produced and agreed in concurrence with participating and potential institutions and partners. This exit strategy should include clear commitments and responsibilities of the key partners in order to sustain the main project results and assets, as well as clear actions and monitoring mechanisms.

Given the above outlined risks to sustainability, the rating for the project sustainability is: Moderately Unlikely (“Significant risk that key outcomes will not carry on after project closure, although some outputs and activities should carry on”).

See further the updated risk log below:

Updated Risk Log, Updated 14th September 2022 (Summarized). See for Full Risk Log, ANNEX VIII

| No. | Description | Impact & Probability | Status |
| --- | --- | --- | --- |
| 1 | Continued introductions / spread of IAS minimize progress on reducing forest fires or increasing carbon sequestration | P=3,I=2 Moderate | National Biosecurity Agency closing down and being integrated into the Ministry of Agriculture, Climate Change and Environment. It remains uncertain how biosecurity functions will be implemented. Framework for IAS (Creeper) management developed. Economy (again) more open to IAS |
| 2 | NEW RISK: Disease in propagation of nursery Seedlings | Low | In the past there has been occurrence of hairy caterpillars and beetles in the nurseries. No further info |
| 3 | Many of the project’s field-based outcomes are vulnerable to the potential impacts of climate change. Most forest management, reforestation and agricultural activities can be negatively impacted by drought and/or extreme weather events, which may reduce vegetative cover and rates of recovery, and increase erosion/sedimentation problems. | P=3, I=3 Moderate | It was agreed that under the climate change risk, the forest and coastal component should be separated. The forest Risk is moderate. No further change |
| 4 | Coral reefs may be impacted by coral bleaching events, harmful algal blooms, and outbreaks of COTS | P=3,I=3 Moderate | This risk may possibly increase if climate change trends continue. |
| 5 | NEW RISK: Coastal Erosion due to high tide | I = High (4 or 5?), P=? | Under climate change risk, specific to coastal erosion, the rating should be raised to high as a lot of turtle nesting areas have gone this year alone through erosion, e.g. the MCSS turtle nesting sites in Grand Police area (SE monsoon) |
| 6 | NEW RISK: ocean acidification affecting corals should be included as a risk | Moderate | This risk may possibly increase if climate change trends continue Ocean 5 measures and collects data. National Observation system? |
| 7 | Opposition from landowners to designation of KBAs as protected areas. | P=3, I=2 Moderate | The risk should decline as project outreach to landowners and fishermen allows them to see the benefits accrued. However, Land ownership issues have come up under the Truth and Reconciliation and National Unity Commission hearings. Minister advised that there is a land ownership claim at Grand Police and any activities terrestrial sites need to be put on hold until this is clarified. Still pending. |
| 8 | Opposition from fishermen to new MPAs or strengthened MPA regulations; | P=3, I=2 Moderate | It was agreed that the Terrestrial and Marine risks should be separated. Project not really dealing with fishers |
| 9 | Socio-economic pressures (e.g. the importance of tourism development for the national economy) prevent effective implementation of development controls to protect coastal freshwater ecosystems | P=2, I=3 Moderate | Economic pressures and developments still occur. E.g. the “Grand Bwa Private Development project” has been put on hold, but EIA was approved. This will influence freshwater ecosystems and may affect the KBA around Montagne Planneau, of importance to R2R, also for the watershed committee at Caiman area. |
| 10 | Failure to enact the National Parks and Nature Conservancy Bill would limit the legal conservation status of the proposed KBAs and Turtle TPAs, and would reduce public awareness and support for protecting such areas | P=2, I=3 Moderate | No risk anymore since NRCA is approved and assented. Regulations will follow. |
| 11 | NEW RISK: Elections are being planned in 2020 and in 2025 and could, thus, pose a political risk as it could slow project implementation | Low | This had some impact on the project, but now after almost 2 years this is normalized. However, next elections in 2025 could impact project results in its final year. |
| 12 | The project may restrict access to the use of natural resources for certain groups, possibly and private landowners in upper elevation forest areas. Finally, the project will work to designate selected Key Biodiversity Areas as official protected areas; this could limit the ability of some private landowners who own land within the KBAs in terms of developing the land and/or in some uses of natural resources. | I=2, P=3 Moderate | Similar to Risk 7. Remove? |
| 13 | The project may restrict access to the use of natural resources for certain groups, possibly including fishermen. For example, the project will help to strengthen the management of existing Marine Protected Areas (MPAs), possibly including increased enforcement of restrictions on fishing in these areas. | I=2, P=3 Moderate | Project not working with fishers. Remove risk? |
| 14 | Alternative livelihoods in agriculture and forestry to be promoted by the project could reproduce existing discriminations against women. | Low | Contentious phrasing of Risk. It was earlier suggested that the risk should be lowered, but is still monitored. |
| 15 | NEW RISK: The disbursement of funds will be done only after 80% expenditure of previous tranche. This was identified as a risk whereby disbursement of the next tranche is usually late and partners run out of funds for activities. | Moderate | PCU has revised the overall budget for all responsible partners to be registered on separate budget lines in the combined budget and will liaise with partners for % expenditure when finalizing Grant Agreements. However, following audit of projects at PCU and a downgrade to Medium Risk for project implementation, all responsible partners were informed that PCU cannot organize Request for Direct Payment (RDP) to partners when they reach 80% expenditure during the quarter and it will now be part of the overall project’s cash advance. Should PCU, or a responsible partner, not spend their cash advance, there will be consequences on timeline for funds request and allocation to those who have spent 80%. |
| 16 | NEW RISK: Capacity issues to implement the activities | Moderate | Capacity challenges still exist, e.g. with Farmers Associations, and with some Government Agencies as Focal Points or key staff have changed (SPGA, Ag. Dept, CBDM) |
| 17 | NEW RISK: Global Corona Virus Pandemic | High Low | This has gravely affected implementation of project activities during 2020-2021. There are still surges of COVID cases, e.g. in early 2022 with Omicron variety, and even during MTR mission (September 2022) with several project staff testing positive and others isolating. Also the general socio-economic fall-out of the pandemic had an effect on the project, e.g. inflation and fluctuation of exchange rates. The project tentatively predicts the impact of COVID 19 has delayed project implementation for at least 6-8 months. Risk is now downgraded to low, though cases still exist and could temporarily increase. |
|  | NEW RISK (RTA): Slow delivery: This represents a risk to successful implementation, especially since the project has to make up for delays in activities to achieve end of project targets | Moderate | Develop a Delivery Acceleration Plan approved by the IP Ministry and PCU. |
|  | NEW RISK (Project Team): Transition PCU – PDCS may impact project implementation, especially Procurement | Low | Transition not yet finalized and new SOPs and instructions to e.g. change procurement through the Procurement Oversight Unit not yet issued to Project. Project team foresees delays, but government staff ensures that with the right preparation this will not be the case. Transition time is important to discuss and anticipate changes in procurement and financing. |
|  | NEW RISK (Project Team): UNDP’s new role vis-à-vis PDCS and Projects will mean less involvement, including less assistance in procurement and monitoring. This may affect project implementation | Low | UNDP will indeed be less involved in project implementation and focus only on oversight. With new SOPs for the PDCS in place this is supped to be overcome. |

Project Risk status is considered Low to Moderate (for some risks)

# CONCLUSIONS

The R2R concept with its ”whole island” approach and its focus on connections and sustainable management from the top of the mountains to the reefs is very relevant to the Seychelles. The UNDP-GEF R2R project in Seychelles is well designed and its content is well elaborated, with however some sections  less well developed (e.g. agriculture). The objective, outcomes, outputs are well designed and detailed, but some of the activities were found difficult to implement (e.g. in agriculture). The Results Framework is well detailed and fit for purpose. Some of the discussed and agreed changes to the Indicators at Inception have not been recorded by PIMS and still appear in UNDP reporting templates, which should be changed. The project end date should also be correctly recorded in PIMS: January 2026.

The progress towards results is varied. The Indicators and targets for the Project Objective are  progressing “Moderately Satisfactory” to “Satisfactory”, with some of the new policies and Bills / Laws in place, others still being worked on and not yet validated / assented, and some of the regulations needing more work. The “Capacity of national partners implementing integrated Ridge to Reef approaches” has improved significantly as measured by the UNDP score card and is well on its way to reach the end of project target.

Outcome 1 has progressed “satisfactory” with all its new to be designated areas (KBAs and SPAs) delineated and nomination files presented. A concern remains with the survival rate and sustainability of some of the rehabilitated areas in mangroves and coastal forests, and this should be monitored going forward.

Outcome 2 is progressing “moderately satisfactory”, with 3 functioning watershed committees in place and rehabilitation works on-going and having reached its mid-term targets, though these areas should also be monitored. The agroforestry work hasn’t reached its target (by far) and it is recommended to shift from Anse Royale (one of the 2 intended agroforestry sites) to another watershed. The CO2 mitigation targets have not been reached, even after recalculation.

Outcome 3 is progressing “moderately unsatisfactory” to “moderately satisfactory”, with work on the online platform only just starting and policy recommendations from the gap analysis not yet worked on. Efforts for these should be stepped up. The ecosystem monitoring has started and is progressing “moderately satisfactory”. The mid-term target for numbers of officials sensitized has been reached.

Outcome 4 is progressing “Moderately Satisfactory” to “Satisfactory” with the mid-term targets for number of policies / programmes supporting R2R approaches and % of women among project participants reached. But the Number of direct project beneficiaries has not reached the Mid-term target though is progressing well with many activities and trainings currently on-going and picking up after COVID restrictions have been lifted.

Overall progress towards results is “moderately satisfactory”, with some areas doing well and others in need to accelerate. This is a laudable achievement considering the challenges faced in its 1st 2 years with COVID-19 restrictions, destruction of the office and numerous changes in government and administration.

The project is well managed, monitored and reported upon, despite the early challenges. The overarching PCU where the project is housed transitioned into PDCS with the new Chief Programme Coordinator (CPC) already in place, and new officers being recruited and SOPs being finalized. This should help in support and oversight for the Project, although here is concern what this may mean for project operations, e.g. procurement. UNDP is “stepping back” some of its monitoring functions and will concentrate on quality assurance and cash advances, following the “full NIM” approach.

Project activities are well planned, but implementation varies with the different RPs. The project team has a remarkable focus on indicators and targets. However, some of the RP activities have been taken over by the project because of slow delivery due to capacity constraints. This can mean that some partners could be left behind, with possible consequences for sustainability. Financial disbursement and delivery is still slow, mainly caused by the slow start with the COVID-19 pandemic and its restrictions, as well as some of the RPs that are not delivering on time. Co-financing lags also behind the stated commitments, mainly because of financial constraints due to the effects of COVID-19; the project however managed to ensure new co-financing from some new partners. Stakeholder engagement of the project is good, although communication and awareness efforts can be stepped up.

Overall the project implementation is “Satisfactory”.

Sustainability of the project is questionable at this point, also taking consideration previous experiences of similar projects. The financial, institutional, socio-economic and environmental risks will need to be foreseen and managed through an elaborate exit strategy, that should contain clear commitments, responsibilities, actions and monitoring & reporting mechanisms. Socio-economic and environmentally related risks may also have consequences for project sustainability. The sustainability of the project is therefore considered moderately unlikely, that can be mitigated through the elaboration of a comprehensive and actionable exit strategy.

The overall rating of the project is Moderately Satisfactory. By following the recommendations of this MTR, most of the project end targets can be achieved, though the sustainability of the project needs extra and timely attention (through an elaborate exit strategy).

# RECOMMENDATIONS

| Rec. | Recommendation | Entity Responsible |
| --- | --- | --- |
| A | Project Strategy |  |
| A.1 | To correct in PIMS, before the next PIR (2023): - Project end date; - Changes in indicators and targets that were discussed and agreed at Inception; - Total committed co-financing from USD27,204,946 as mentioned on the ProDoc cover page, to USD27,279,946 as recorded and detailed at CEO endorsement. | UNDP |
| A.2 | No request for “project extension” at this early point in the project but continue to monitor the project progress and re-discuss this possible “extension” request after submission of the PIR in 2024 with all pertinent stakeholders and decide in the PSC, for possible submission to the GEF if needed and justified. | Project Team, UNDP, PSC, MACCE |
| A.3 | Record changes in the Results Framework at MTR, before next PIR (2023): - Indicator 6: End target of “No. of KBAs with required technical documents and draft legal documents for gazetting presented to the Government”, to be adjusted from 6 to 5, as 2 of the envisaged KBAs have now been merged, with the same coverage (2,235 ha). - Indicator 10: Change in location for agroforestry sites from “Anse Royale Watershed” to “Caiman Watershed” and/or any suitable Watershed on Praslin (to be identified). - Indicator 11 “Amount of tCO2eq GHG emissions avoided / sequestered through avoided deforestation and forest degradation, reforestation, agroforestry and conservation agriculture”: Adjust targets from 18,273 tCO2eq to 7,070 tCO2eq at mid-term and from 43,853 tCO2eq to 16,134tCO2eq at end target, as this has been recalculated by an international expert with updated data. | Project Team, UNDP |
| B | Project Objective |  |
| B.1 | Monitor and push for the finalization, approval and assenting / promulgation of the targeted laws + designation of KBAs, as well as the capacity for its monitoring and enforcement, by Project end (end 2025) | Project Team, MACCE |
| C | Outcome 1: Expansion of marine and terrestrial protected areas of the Seychelles’ Inner Islands |  |
| C.1 | Monitor periodically the survival rate and final area of “rehabilitated areas”, e.g. before each PIR through “evidence based reports”. | RPs, Project Team |
| C.2 | Identify new sites for rehabilitation, before the 2023 Workplan. These should preferably be sites in the Districts and watersheds where the project is already operating and where the R2R links can be established and shown, e.g. Caiman and Baie Lazare. | Project Team, MACCE |
| D | Outcome 2: Strengthened management of upland KBAs and adjacent areas to enhance the flow of ecosystem services through the R2R approach |  |
| D.1 | Shift activities under Indicator 7 away from Grand Police to the Caiman watershed, where there is a delineated KBA, wetlands and a watershed committee with watershed management plan, because of continuing uncertainty about claims of land ownership and possible tourism development in Grand Police. Include this in the 2023 Workplan. Continue the activities on SPAs in Grand Police, and monitor developments with the possibility to restart watershed management activities if feasible and when time allows, e.g. until end 2024. | Project Team, Caiman, Watershed Committee, MACCE |
| D.2 | Shift agroforestry activities from Anse Royale to other areas where agroforestry is possible and farmers are interested, e.g. Baie Lazare, Caiman watershed, Praslin or Montagne Pose (where the agriculture Department has AF sites). Identify and plan these activities in time to include in the 2023 Workplan. | Project, Agriculture Department (MACCE) |
| E | Outcome 3: Promoting the ‘Ridge to Reef’ (R2R) approach through knowledge management, ecosystem health monitoring and inter-sectoral coordination |  |
| E.1 | Support the policy revisions as recommended in the policy gap analysis report, especially on agriculture, i.e. developing a possible new “Agriculture Lands Protection Act” and a new “Agricultural Policy” (MACCE is working on a new policy since the previous Agriculture policy expired in 2020), so that relevant R2R approaches are integrated. This will need to be discussed and support further identified with the Agriculture Department, in time for the 2023 Workplan | Project, Agriculture Department (MACCE) |
| F | Outcome 4: Knowledge Management, M&E and Gender Mainstreaming |  |
| F.1 | Pursue the focus on achieving gender parity and to include more youth in project activities by developing a “Gender and Youth Strategy and Action Plan” for the project by end 2022, to inform the 2023 and future workplans | Project |
| F.2 | Include all District Administrators in relevant R2R awareness and training programmes, with continuation of specific trainings for those DAs directly involved in the project. This could start immediately and should be included in developing and organizing such new training programmes. | Project, RPs, DAs. MLGCA |
| G | Project Implementation & Adaptive Management |  |
| G.1 | Find and implement a solution to the delayed financial and activity reporting of some RPs, that endanger and delay the timely disbursement of advances to the project, before the end of 2022, so that an improved UNDP advance & reporting system can start in 2023. | Project, PDCS, UNDP |
| G.2 | Continue discussions with and renew attempts to implement activities in close collaboration with the intended partners, even if this could potentially temporarily delay the timely achievement of targets, as this may enhance the sustainability of the results in the long run. This should start immediately, with considerations given when new activities start, and with possible capacity assessments for new partners or partners that have undergone significant transitions in order to counter possible implementation delays. | Project, RPs |
| G.3 | In order to mitigate the slow financial disbursement and delivery, put in place a Delivery Action Plan by the end of 2022, in time for the 2023 Workplan, that could entail: (i) joint budgeting and procurement planning with all project partners, to ensure better coordination and realize efficiencies wherever possible; (ii) Develop all TORS and activity concept notes under each AWP as a block in advance at the start of each quarter; (iii) Frontload the budget with purchase of equipment and other larger-value items; (iv) Consolidate tenders or consultancies where possible and sensible; (v) Build the time required for procurement into the workplan and make sure that procurement processes are triggered well enough in advance of when the service/product is required, and in the right sequence; (vi) Explore the possibility of setting up partnerships with appropriately capacitated NGOs and/or other partners who are already active in the domain, to deliver clusters of related outputs | Project, PDCS, UNDP, RPs |
| G.4 | Review the Public Awareness Strategy for the project with the coming on board of the R2R Communication Officer, in order to come up with an updated and more targeted communication action plan to increase the awareness and disseminate the results and successes of the project. This could also take into consideration the future recruitment of an PDCS communications Officer, and should be one of the first tasks of the new R2R communication officer. | Project, PDCS |
| H | Sustainability |  |
| H.1 | Develop a project Exit Strategy in order to sustain priority project results and assets, including responsibilities, commitments, actions, financial and monitoring mechanisms of the main stakeholders, as early as possible, latest by mid 2023. This should be a “living” document to be reviewed yearly in PSC meetings and before PIRs, in order to cater for changes or new challenges. | Project, PDCS, MACCE, UNDP |

# ANNEXES

## Annex I: Mid Term Review Terms of Reference

BASIC CONTRACT INFORMATION:

| Location: | Seychelles / Home Based |
| --- | --- |
| Application Deadline: | 24TH June 2022 |
| Type of Contract: | Individual Contract |
| Post Level: | International Consultant |
| Languages Required: | English (French or Creole is advantage) |
| Starting Date: | 15th July 2022 |
| Duration of Initial Contract: | 30 Days |
| Expected Duration of Assignment: | 30 Days over 10-12 weeks |

BACKGROUND

A. Project Title : Mid Term Review of the UNDP-GEF Funded “A Ridge to Reef Approach for the Integrated Management of Marine, Coastal and Terrestrial Ecosystems in the Seychelles” (PIMS 5502)

B. Project Description

This is the Terms of Reference for the UNDP-GEF Midterm Review (MTR) of the full-sized project titled A Ridge to Reef Approach for the Integrated Management of Marine, Coastal and Terrestrial Ecosystems in the Seychelles (PIMS 5502) implemented through the Ministry of Agriculture, Climate Change and Environment (MACCE), which is to be undertaken in 2022. The project started on the 8th January 2020 and is in its 3rd year of implementation. This ToR sets out the expectations for this MTR. The MTR process must follow the guidance outlined in the document Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects.

The project was designed to undertake a comprehensive Ridge to Reef (R2R) approach that addresses the ‘whole island’ priorities of improved management and conservation of upland forest and agricultural ecosystems as well as coastal and marine ecosystems in the Seychelles to produce global benefits in terms of conservation of globally significant biodiversity and the effective management of large marine ecosystems (including coastal and near-shore marine ecosystems), and to arrest and reverse ecosystem degradation.

The project was designed to:

I. reduce threats to globally significant biodiversity by strengthening the country’s system of marine protected areas and reducing negative land-based impacts on those ecosystems, as well as strengthening the management of forested Key Biodiversity Areas and their surroundings;

II. reverse land degradation in areas outside of formally protected areas and in productive land through the promotion of SLM/SFM practices and agroforestry, leading to the restoration and sustainable flows of forest ecosystem services with positive impacts to communities as well as to adjacent coastal and marine ecosystems; and

III. strengthen capacity and partnerships to promote integrated ecosystem management based on the R2R approach.

By addressing a range of terrestrial threats to the marine environment, including flows of pollutants, nutrients and sediment, disrupted hydrological services, degradation of critical habitat, etc. that have significant negative impacts on important coastal/marine ecosystems including wetlands, mangroves, seagrass beds and coral reefs, the project will simultaneously improve the management of the terrestrial landscape, improve the effectiveness of integrated coastal management practices, and secure the integrity of existing and new marine protected areas in the Seychelles. At the policy and strategic level, the project will unite the three most important spatial and resource planning processes in the country, namely the Marine Spatial Plan (for the seascape), the Seychelles Strategic Plan (for the landscape), and national and district level Land Use Plans. The project will build on these baseline activities by providing strategic incremental funding to implement priority actions in each of the plans.

COVID 19 in Seychelles

The first recorded case of Covid-19 in Seychelles was on March 11th, 2020, and the Government of Seychelles undertook stringent measures including closure of borders to safeguard against the pandemic. However, by June 2020 the Seychelles undertook partial reopening of borders and tourism in Seychelles prompting a spike in the number of imported cases. By December In 2021, there was a spike in cases and the number of deaths due to various strains of the COVID-19 pandemic with the Government undertaking an aggressive vaccination campaign from the onset of 2021. As of May 1st 2022, the number of cases are in excess of 42,000 with 166 recorded deaths. More than 80% of the eligible population have been vaccinated with 2 doses and nearly 40% have had a booster. The Assessment of Socio-Economic impact of Covid-19 in Seychelles, prepared by UNDP in 2020, can be found on the link below:

https://www.mu.undp.org/content/mauritius_and_seychelles/en/home/library/an-assessment-of-the-socio-economic-impact-of-covid-19-in-seyche.html

C. MTR Purpose

The MTR will assess progress towards the achievement of the project objectives and outcomes as specified in the Project Document and assess early signs of project success or failure with the goal of identifying the necessary changes to be made in order to set the project on-track to achieve its intended results. The MTR will also review the project’s strategy and its risks to sustainability.

The MTR report will promote accountability and transparency, and assesses the extent of project accomplishments, bottlenecks and changes within the socio-environmental and political landscape. The recommendations will be used to a draft management response which will be taken up by the relevant stakeholders such as MACCE and other partners. The MTR will determine the necessity of long-term continuity through future initiatives and complementarity building on successes of past projects. The recommendations of the MTR will guide the of the project team in troubleshooting specific areas and adapting the course to ensure that project outcomes can be achieved in a changing national and global context.

The impact of COVID-19 on project activities and overall implementation should be assessed and documented including re-aligning some project activities or outputs that may have been significant in the project’s adaptation towards national challenges and in accordance with overall project outcomes and objectives.

DUTIES AND RESPONSIBILITIES

D. MTR Approach & Methodology

The MTR report must provide evidence-based information that is credible, reliable and useful.

The MTR will be conducted by an Independent Consultant who will review all relevant sources of information including documents prepared during the preparation phase (i.e. PIF, UNDP Initiation Plan, UNDP Social and Environmental Screening Procedure (SESP)), the Project Document, project reports including Annual Project Review/PIRs, project budget revisions, national strategic and legal documents, and any other materials that the team considers useful for this evidence-based review. The MTR Consultant will review the baseline GEF focal area Core Indicators/Tracking Tools submitted to the GEF at CEO endorsement, and the midterm GEF focal area Core Indicators/Tracking Tools that must be completed before the MTR field mission begins.

The MTR Consultant is expected to follow a collaborative and participatory approach ensuring close engagement with the Project Team, government counterparts (the GEF Operational Focal Point), the UNDP Country Office(s), the Nature, Climate and Energy (NCE) Regional Technical Advisor, direct beneficiaries, and other key stakeholders.

Engagement of stakeholders is vital to a successful MTR. Stakeholder involvement should include interviews with stakeholders who have project responsibilities, including but not limited to; executing agencies, senior officials and task team/ component leaders, key experts and consultants in the subject area, Project Board, project stakeholders, academia, local government and CSOs, etc.

Additionally, the MTR Consultant is expected to conduct field missions to Seychelles including the following project sites Marine Protected Areas (Curieuse, Baie Ternay, Port Launay), Watersheds (Val D’endor, Anse Royale, Petit Cours to Pointe Chevalier), Temporal Protected Areas (Anse Grand Police, Anse Bazzarca, Anse Intendance, Anse Petite Police, Anse Corail & Anse Cachee and Key Biodiversity Areas)

The specific design and methodology for the MTR should emerge from consultations between the MTR consultant and the above-mentioned parties regarding what is appropriate and feasible for meeting the MTR purpose and objectives and answering the evaluation questions, given limitations of budget, time and data.

The MTR Consultant must, however, use gender-responsive methodologies and tools and ensure that gender equality and women’s empowerment, as well as other cross-cutting issues and SDGs are incorporated into the MTR report.

The final methodological approach including interview schedule, field visits and data to be used in the MTR should be clearly outlined in the Inception Report and be fully discussed and agreed between UNDP, stakeholders and the MTR Consultant.

The final MTR report must describe the full MTR approach taken and the rationale for the approach making explicit the underlying assumptions, challenges, strengths and weaknesses about the methods and approach of the review.

As of 11 March 2020, the World Health Organization (WHO) declared COVID-19 a global pandemic as the new coronavirus rapidly spread to all regions of the world. At present, Travel to the Seychelles is currently permitted with proof of vaccination or a negative PCR test taken 72 hrs prior to travel. All travel to Seychelles must be authorized prior through Government website below:

https://seychelles.govtas.com/

The MTR mission will comprise a field mission, as the Seychelles is open to all visitors. It is recommended that the Consultant be fully vaccinated and take necessary precautions (such as wearing of masks or other) as prescribed by the local Health Authorities while in country for the mission.

No stakeholders, consultants or UNDP staff should be put in harm’s way and safety is the key priority at all times.

E. Detailed Scope of the MTR

The MTR Consultant will assess the following four categories of project progress. See the Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects for extended descriptions.

NOTE: Include below COVID-19 specific questions, as needed, and/or recognise the impact of COVID-19 and limitations on the project in the guiding evaluation questions.

1. Project Strategy

Project Design:

 Review the problem addressed by the project and the underlying assumptions. Review the effect of any incorrect assumptions or changes to the context to achieving the project results as outlined in the Project Document.

 Review the relevance of the project strategy and assess whether it provides the most effective route towards expected/intended results. Were lessons from other relevant projects properly incorporated into the project design?

 Review how the project addresses country priorities. Review country ownership. Was the project concept in line with the national sector development priorities and plans of the country (or of participating countries in the case of multi-country projects)? Review, the elements in project design that may respond to/support COVID-19 recovery

 Review decision-making processes: were perspectives of those who would be affected by project decisions, those who could affect the outcomes, and those who could contribute information or other resources to the process, taken into account during project design processes?

 Review the extent to which relevant gender issues were raised in the project design. See Annex 9 of Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects for further guidelines.

o Were relevant gender issues (e.g. the impact of the project on gender equality in the programme country, involvement of women’s groups, engaging women in project activities) raised in the Project Document?

 If there are major areas of concern, recommend areas for

Results Framework/Logframe:

 Undertake a critical analysis of the project’s logframe indicators and targets, assess how “SMART” the midterm and end-of-project targets are (Specific, Measurable, Attainable, Relevant, Time-bound), and suggest specific amendments/revisions to the targets and indicators as necessary.

 Are the project’s objectives and outcomes or components clear, practical, and feasible within its time frame?

 Examine if progress so far has led to, or could in the future catalyse beneficial development effects (i.e. income generation, gender equality and women’s empowerment, improved governance etc...) that should be included in the project results framework and monitored on an annual basis.

 Ensure broader development and gender aspects of the project are being monitored effectively. Develop and recommend SMART ‘development’ indicators, including sex-disaggregated indicators and indicators that capture development benefits.

2. Progress Towards Results

Progress Towards Outcomes Analysis:

 Review the logframe indicators against progress made towards the end-of-project targets; populate the Progress Towards Results Matrix, as described in the Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects; colour code progress in a “traffic light system” based on the level of progress achieved; assign a rating on progress for the project objective and each outcome; make recommendations from the areas marked as “not on target to be achieved” (red).

In addition to the progress towards outcomes analysis:

 Compare and analyse the GEF Tracking Tool/Core Indicators at the Baseline with the one completed right before the Midterm Review.

 Identify remaining barriers to achieving the project objective in the remainder of the project.

 By reviewing the aspects of the project that have already been successful, identify ways in which the project can further expand these benefits.

3. Project Implementation and Adaptive Management

Management Arrangements

 Review overall effectiveness of project management as outlined in the Project Document. Have changes been made and are they effective? Are responsibilities and reporting lines clear? Is decision-making transparent and undertaken in a timely manner? Recommend areas for improvement.

 Review the quality of execution of the Executing Agency/Implementing Partner(s) and recommend areas for improvement.

 Review the quality of support provided by the GEF Partner Agency (UNDP) and recommend areas for improvement.

 Do the Executing Agency/Implementing Partner and/or UNDP and other partners have the capacity to deliver benefits to or involve women? If yes, how?

 What is the gender balance of project staff? What steps have been taken to ensure gender balance in project staff?

 What is the gender balance of the Project Board? What steps have been taken to ensure gender balance in the Project Board?

Work Planning

 Review any delays in project start-up and implementation, identify the causes and examine if they have been resolved.

 Are work-planning processes results-based? If not, suggest ways to re-orientate work planning to focus on results?

 Examine the use of the project’s results framework/ logframe as a management tool and review any changes made to it since project start.

Finance and co-finance

 Consider the financial management of the project, with specific reference to the cost-effectiveness of interventions.

 Review the changes to fund allocations as a result of budget revisions and assess the appropriateness and relevance of such revisions.

 Does the project have the appropriate financial controls, including reporting and planning, that allow management to make informed decisions regarding the budget and allow for timely flow of funds?

 Informed by the co-financing monitoring table to be filled out by the Commissioning Unit and project team, provide commentary on co-financing: is co-financing being used strategically to help the objectives of the project? Is the Project Team meeting with all co-financing partners regularly in order to align financing priorities and annual work plans?

Project-level monitoring and evaluation systems

 Review the monitoring tools currently being used: Do they provide the necessary information? Do they involve key partners? Are they aligned or mainstreamed with national systems? Do they use existing information? Are they efficient? Are they cost-effective? Are additional tools required? How could they be made more participatory and inclusive?

 Examine the financial management of the project monitoring and evaluation budget. Are sufficient resources being allocated to monitoring and evaluation? Are these resources being allocated effectively?

 Review the extent to which relevant gender issues were incorporated in monitoring systems. See Annex 9 of Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects for further guidelines.

Stakeholder Engagement

 Project management: Has the project developed and leveraged the necessary and appropriate partnerships with direct and tangential stakeholders?

 Participation and country-driven processes: Do local and national government stakeholders support the objectives of the project? Do they continue to have an active role in project decision-making that supports efficient and effective project implementation?

 Participation and public awareness: To what extent has stakeholder involvement and public awareness contributed to the progress towards achievement of project objectives?

 How does the project engage women and girls? Is the project likely to have the same positive and/or negative effects on women and men, girls and boys? Identify, if possible, legal, cultural, or religious constraints on women’s participation in the project. What can the project do to enhance its gender benefits?

Social and Environmental Standards (Safeguards)

 Validate the risks identified in the project’s most current SESP, and those risks’ ratings; are any revisions needed?

 Summarize and assess the revisions made since CEO Endorsement/Approval (if any) to:

o The project’s overall safeguards risk categorization.

o The identified types of risks7 (in the SESP).

o The individual risk ratings (in the SESP) .

- Describe and assess progress made in the implementation of the project’s social and environmental management measures as outlined in the SESP submitted at CEO Endorsement/Approval (and prepared during implementation, if any), including any revisions to those measures. Such management measures might include Environmental and Social Management Plans (ESMPs) or other management plans, though can also include aspects of a project’s design; refer to Question 6 in the SESP template for a summary of the identified management measures.

A given project should be assessed against the version of UNDP’s safeguards policy that was in effect at the time of the project’s approval.

Reporting

 Assess how adaptive management changes have been reported by the project management and shared with the Project Board.

 Assess how well the Project Team and partners undertake and fulfil GEF reporting requirements (i.e. how have they addressed poorly-rated PIRs, if applicable?)

 Assess how lessons derived from the adaptive management process have been documented, shared with key partners and internalized by partners including COVID-19 lessons learned.

Communications & Knowledge Management

 Review internal project communication with stakeholders: Is communication regular and effective? Are there key stakeholders left out of communication? Are there feedback mechanisms when communication is received? Does this communication with stakeholders contribute to their awareness of project outcomes and activities and investment in the sustainability of project results?

 Review external project communication: Are proper means of communication established or being established to express the project progress and intended impact to the public (is there a web presence, for example? Or did the project implement appropriate outreach and public awareness campaigns?)

 For reporting purposes, write one half-page paragraph that summarizes the project’s progress towards results in terms of contribution to sustainable development benefits, as well as global environmental benefits.

 List knowledge activities/products developed (based on knowledge management approach approved at CEO Endorsement/Approval).

4. Sustainability

 Validate whether the risks identified in the Project Document, Annual Project Review/PIRs and the ATLAS Risk Register are the most important and whether the risk ratings applied are appropriate and up to date. If not, explain why.

 In addition, assess the following risks to sustainability:

Financial risks to sustainability:

 What is the likelihood of financial and economic resources not being available once the GEF assistance ends (consider potential resources can be from multiple sources, such as the public and private sectors, income generating activities, and other funding that will be adequate financial resources for sustaining project’s outcomes)?

Socio-economic risks to sustainability:

 Are there any social or political risks that may jeopardize sustainability of project outcomes? What is the risk that the level of stakeholder ownership (including ownership by governments and other key stakeholders) will be insufficient to allow for the project outcomes/benefits to be sustained? Do the various key stakeholders see that it is in their interest that the project benefits continue to flow? Is there sufficient public / stakeholder awareness in support of the long-term objectives of the project? Are lessons learned being documented by the Project Team on a continual basis and shared/ transferred to appropriate parties who could learn from the project and potentially replicate and/or scale it in the future?

Institutional Framework and Governance risks to sustainability:

 Do the legal frameworks, policies, governance structures and processes pose risks that may jeopardize sustenance of project benefits? While assessing this parameter, also consider if the required systems/ mechanisms for accountability, transparency, and technical knowledge transfer are in place.

Environmental risks to sustainability:

 Are there any environmental risks that may jeopardize sustenance of project outcomes?

 What are the risks brought on by COVID-19, if any to overall realization of project outcomes

Conclusions, Recommendations and Lessons Learned

The MTR consultant will include a section in the MTR report for evidence-based conclusions, in light of the findings.

Additionally, the MTR consultant is expected to make recommendations to the Project Team. Recommendations should be succinct suggestions for critical intervention that are specific, measurable, achievable, and relevant. A recommendation table should be put in the report’s executive summary. The MTR consultant should make no more than 15 recommendations total.

The MTR will also include a separate section with a concise and logically articulated set of lessons learned (new knowledge gained from the project, context, outcomes, even evaluation methods; failures/lost opportunities to date, what might have been done better or differently, etc.). Lessons should be based on specific evidence presented in the report and can be used to inform design, adapt and change plans and actions, as appropriate, and plan for scaling up.

The MTR report’s findings, conclusions, recommendations and lessons learned need to consider gender equality and women’s empowerment and other cross-cutting issues.

Ratings

The MTR consultant will include its ratings of the project’s results and brief descriptions of the associated achievements in a MTR Ratings & Achievement Summary Table in the Executive Summary of the MTR report. See the TOR Annexes for the Rating Table and ratings scales.

Expected Outputs and Deliverables

The MTR consultant shall prepare and submit:

 MTR Inception Report: MTR consultant clarifies objectives and methods of the Midterm Review no later than 2 weeks before the MTR mission. To be sent to the Commissioning Unit and project management. Completion date: (27th July 2022)

 Presentation: MTR consultant presents initial findings to project management and the Commissioning Unit at the end of the MTR mission. Completion date: (12th Aug 2022)

 Draft MTR Report: MTR consultant submits the draft full report with annexes within 3 weeks of the MTR mission. Completion date: (29th August 2022). Sent to the Commissioning Unit reviewed by RTA, Project Coordinating Unit, GEF OFP.

 Final Report*: MTR consultant submits the revised report with annexed and completed Audit Trail detailing how all received comments have (and have not) been addressed in the final MTR report. To be sent to the Commissioning Unit within 1 week of receiving UNDP comments on draft. Completion date: (9th Sept 2022)

*The final MTR report must be in English. If applicable, the Commissioning Unit may choose to arrange for a translation of the report into a language more widely shared by national stakeholders.

Institutional Arrangements

The principal responsibility for managing this MTR resides with the Commissioning Unit. The Commissioning Unit for this project’s MTR is the UNDP Country Office for Mauritius and Seychelles.

The Commissioning Unit will contract the consultants and ensure the timely provision of per diems and travel arrangements within the country for the MTR consultant and will provide an updated stakeholder list with contact details (phone and email). The Project Team will be responsible for liaising with the MTR consultant to provide all relevant documents, set up stakeholder interviews, and arrange field visits.

The Commissioning Unit will contract the consultant and ensure the timely provision of per diems and travel arrangements within the country for the MTR consultant. The Project Team will be responsible for liaising with the MTR consultant to provide all relevant documents, set up stakeholder interviews, and arrange field visits.

Duration of the Work

The total duration of the MTR will be approximately 30 days over a period of 10-12 weeks starting 20th June 2022 shall not exceed five months from when the consultant(s) are hired. The tentative MTR timeframe is as follows:

 (24th June 2022): Application closes

 (30th June 2022): Selection of MTR Consultant

 (15th July 2022): Prep the MTR Consultant (handover of project documents)

 (25th July 2022) 3 days (recommended 2-4): Document review and preparing MTR Inception Report

 (29th July )1 day: Finalization and Validation of MTR Inception Report- latest start of MTR mission

 (01-12th August 2022 )12 days (r: 7-15): MTR mission: stakeholder meetings, interviews, field visits

 (12th August 2022): Mission wrap-up meeting & presentation of initial findings- earliest end of MTR mission

 (26th August 2022)10 days (r: 5-10): Preparing draft report

 (1st Sep 2022): 1 day Concluding Stakeholder Workshop (virtual)

 (9th Sept 2022)3 days (r: 1-2): Incorporating audit trail on draft report/Finalization of MTR report(note: accommodate time delay in dates for circulation and review of the draft report)

 (20th Sep 2022): Preparation & Issue of Management Response

 (30th Sep 2022): Expected date of full MTR completion

 The date start of contract is 15th July 2022.

Duty Station:

The duty station is mostly home-based but the MTR Consultant will be expected to travel to Seychelles for a short field mission of 12 days to ensure robustness of the mid-term review processes. Some inter-island travel may be required.

Travel:

 International travel will be required to Seychelles during the MTR mission;

 The BSAFE training course must be successfully completed prior to commencement of travel; Herewith is the link to access this training: https://training.dss.un.org/courses/login/index.php . These training modules at this secure internet site is accessible to Consultants, which allows for registration with private email.

 Individual Consultants are responsible for ensuring they have vaccinations/inoculations when travelling to certain countries, as designated by the UN Medical Director.

 Consultants are required to comply with the UN security directives set forth under https://dss.un.org/dssweb/

 All related travel expenses will be covered and will be reimbursed as per UNDP rules and regulations upon submission of an F-10 claim form and supporting documents.

Travel to Seychelles

Travelers to Seychelles must be fully vaccinated or provide proof of negative PCR ahead of travel

24 hrs prior to travel,

Traveler’s must register on https://seychelles.govtas.com/ ; and obtain the necessary clearances to enter Seychelles. A fee is associated with this for all non-Seychellois travelers.

## Annex II: Evaluative Matrix

The evaluative matrix below specifies the main review criteria, and the indicators or benchmarks against which the criteria will be assessed. The “Evaluative Questions” are to be considered as “Guiding questions”. Not all of these questions need to be asked in every interview (some interviewees may be strategically, technically or more management oriented and hence only the relevant questions may be asked), and the wording can be adapted based on the interview circumstances.

| Evaluative Questions | Indicators | Sources | Methodology |
| --- | --- | --- | --- |
| Project Strategy: To what extent is the project strategy relevant to country priorities, country ownership, and the best route towards expected results? |  |  |  |
| Is the project relevant to Seychelles socio-economic and environment policies? | Relevant changes to Project design | Project Document, National Strategy documents; Interviews | Desk Reviews and analysis; interviews |
| Is the project relevant to the UN and UNDP’s Regional and corporate strategies? | Environmental and sustainable development challenges articulated | UN and other Regional / Pacific Strategies | Desk Reviews and expert interviews |
| In what ways is the project engaging stakeholder participation | Stakeholders awareness / engagement | Project Inception Report; Progress Reports; Stakeholder views; Project Briefs; media coverage | Desk / Document review; Media review; Interviews |
| In what ways is the project addressing targeted beneficiaries? | Activities undertaken; Beneficiaries engagement and participation + benefits | Project Inception Report; Progress Reports; Stakeholder / expert views Project Briefs | Desk / Document review; Interviews, site visits. |
| Is the project specifically addressing gender and youth issues ? | Gender Marker; Gender activities | Project Documents; Project Reports Progress reports / PIR Reviews ; stakeholder opinions | Desk Reviews, expert and stakeholder interviews |
| Are stakeholders actively supporting implementation of the project | Project activities undertaken with stakeholders; Stakeholder views and participation | Project Inception Report; Progress Reports; Interviews, Project Briefs, Communication & Advocacy materials | Desk / Document review; Interviews, Site visits |
| What changes could be made in project design to improve effectiveness? | Changes proposed / documented | Project Document Project Inception Report; Progress Reports / PIRs; Risk logs. Stakeholder / expert views Project Briefs | Document reviews; Expert opinions; Stakeholder interviews |
| What changes could be made within remainder of project to improve achievement of objectives? | Changes proposed to Logframe MTR Review | Project Document; Inception Report; PIRs Risk logs | Document reviews; Expert opinions; Stakeholder interviews |
| Progress Towards Results: To what extent have the expected outcomes and objectives of the project been achieved thus far? |  |  |  |
| Are activities and outputs of the project consistent with project goals and objectives? | Quality assurance report; SMART indicators Tracking Tools | PIF; Project Document; Inception Report; PIRs Tracking Tools | Desk review, document analysis; Stakeholder interviews |
| What is progress against indicators in terms of expected targets against outcomes? | PIR assessments | Project Document; PIRs Project monitoring Reports | Desk review; Document analysis; Stakeholder interviews |
| How was risk managed? | Changes in risk assessment and activities documented and actioned | Project Document; SESP; PIRs | Desk Review; Document analysis; Stakeholder and expert interviews |
| What lessons can be drawn in term of effectiveness? | Changes in project strategy and activities | PIRs Lessons Learned Reports Project Briefs Risk Logs | Desk Review; Document analysis; Stakeholder and expert interviews |
| How could the project be more effective in achieving results? | Stakeholder and expert opinions | PIRs; Lessons Learned Reports; Project Briefs; Reviews; Risk Logs | Desk Review; Document analysis; Stakeholder and expert interviews |
| What are remaining barriers to achieving the project objective in the remainder of the project? | Barriers Identified | Project Document, Project Inception Report, PIRs, Interviews | Analysis of Project Documents; PIRs; Progress Reports; PSC minutes; Expert and stakeholder views |
| What are ways in which the project can further expand results and benefits already achieved? | Recommendations for way forward identified and reported | Project Document, Project Inception Report, PIRs, Interviews | Analysis of Project Documents; Progress Reports; Expert and stakeholder views |
| Project Implementation and Adaptive Management: |  |  |  |
| Was the project logical framework, work plans and risk logs used as management tools during project implementation? Were there any changes applied to any of them? | Changes to Logframe and Risk Log documented | Project Document & Inception report, Project Workplans, Project progress reports, PIRs. | Analysis of Project Documents; PIRs; Progress Reports; PSC minutes; Expert and stakeholder views |
| Has the project been implemented efficiently, cost-effectively, and been able to adapt to any changing conditions thus far? | Timely workplans and progress reports; Non-qualified audits | Project Document & Inception report, Project Workplans, Project monitoring and progress reports, PIRs, Audits, spot checks. | Analysis of Project Documents; PIRs; Progress Reports; PSC minutes; Expert and stakeholder views |
| Was adaptive measures needed and used to ensure efficient use of resources? | Changes made and documented | Project Document & Inception report, Project Workplans, PSC minutes, Project monitoring and progress reports, PIRs, audits, spot checks | Analysis of Project Documents; Progress Reports; PSC minutes; Expert and stakeholder views |
| To what extent are project-level monitoring and evaluation systems, reporting, and project communications supporting the project’s implementation? | Quality of reports and implementation | Project Document & Inception report, Project Workplans, PSC minutes, Project monitoring and progress reports, PIRs, audits, spot checks | Analysis of Project Documents; Progress Reports; PSC minutes; Expert and stakeholder views |
| To what extent has progress been made in the implementation of social and environmental management measures? | Changes documented and made | SESP, PIRs, Risk Logs | Analysis of Project Documents, Progress Reports, Reviews |
| Were progress reports produced in a timely manner? | Dates of submission and approval | Progress Reports | Desk review, interviews PMU, UNDP |
| Have there been changes to the overall project risk rating and/or the identified types of risks? | Changes documented and followed | PIF, Project Document, SESP, Risk Logs | Analysis of Project Documents, Progress Reports, Reviews, Interviews |
| Was co-financing leveraged and to what extent? | Amount leveraged | PIRs, Progress Reports, Audits, Spot Checks, Interviews, CF Table | Analysis of Project Documents; Expert and stakeholder views |
| Is there a Stakeholder Engagement Plan and is it being implemented? If not what are the challenges? | Stakeholder engagement plan; Stakeholder aware and engaged. | Stakeholder Engagement Plan, Communication Plan, PIRs, Progress Reports, Interviews | Analysis of Stakeholder Engagement Plan, Progress Reports, Monitoring Reports |
| Were partnerships and networking facilitated amongst stakeholders? | Stakeholder engagement plan; Partners engaged | Stakeholder Engagement Plan, Communication Plan, PIRs, Progress Reports, Interviews | Analysis of Stakeholder Engagement Plan, Progress Reports, Monitoring Reports, Interviews |
| Sustainability: To what extent are there financial, institutional, socio-economic, and/or environmental risks to sustaining long-term project results? |  |  |  |
| What is the impact of the project in terms of awareness raising and participation in the project? | Stakeholders aware and participating | Stakeholder Engagement Plan, Communication Plan, PIRs, Progress Reports, Interviews | Analysis of Stakeholder Engagement Plan, Progress Reports, Monitoring Reports, Interviews |
| Was sustainability, including cross-cutting issues, adequately identified at project design? | Changes in project strategy and activities | PIF, Project Document, SESP,PIRs, Lessons Learned, Risk Log | Desk review, stakeholder opinions, interviews |
| What opportunities are there to maximizing partnership and enhancing project delivery? | Partners aware and participating | Stakeholder Engagement Plan, Communication Plan, PIRs, Progress Reports, Interviews | Analysis of Stakeholder Engagement Plan, Progress & Monitoring Reports, Interviews |
| What are the main risks to actions/interventions initiated by the project and how can/are they being addressed? | Risks documented and actioned | PIF, Project Document, SESP, Risk Logs | Analysis of Project Documents, Progress Reports, Reviews, Interviews |
| What is the level of influence and visibility of the project in terms of Environmental Management and Sustainable Development? | Targets achieved, documented and shared | PIRs, Risk Logs, Progress Reports, Policy Briefs, Press and awareness materials, media coverage, National Documents | Desk Reviews, media coverage, interviews |
| What is the level of stakeholder and general support and commitment towards the project and its results? | Partners aware and participating | Stakeholder Engagement Plan, Communication Plan, PIRs, Progress Reports, Interviews | Analysis of Stakeholder Engagement Plan, Progress Reports, Monitoring Reports, Interviews |

## Annex III: Ratings Scales

| Ratings for Progress Towards Results: (one rating for each outcome and for the objective) |  |  |
| --- | --- | --- |
| 6 | Highly Satisfactory (HS) | The objective/outcome is expected to achieve or exceed all its end-of-project targets, without major shortcomings. The progress towards the objective/outcome can be presented as “good practice”. |
| 5 | Satisfactory (S) | The objective/outcome is expected to achieve most of its end-of-project targets, with only minor shortcomings. |
| 4 | Moderately Satisfactory (MS) | The objective/outcome is expected to achieve most of its end-of-project targets but with significant shortcomings. |
| 3 | Moderately Unsatisfactory (MU) | The objective/outcome is expected to achieve its end-of-project targets with major shortcomings. |
| 2 | Unsatisfactory (U) | The objective/outcome is expected not to achieve most of its end-of-project targets. |
| 1 | Highly Unsatisfactory (HU) | The objective/outcome has failed to achieve its midterm targets, and is not expected to achieve any of its end-of-project targets. |
| Ratings for Project Implementation & Adaptive Management: (one overall rating) |  |  |
| 6 | Highly Satisfactory (HS) | Implementation of all seven components – management arrangements, work planning, finance and co- finance, project-level monitoring and evaluation systems, stakeholder engagement, reporting, and communications – is leading to efficient and effective project implementation and adaptive management. The project can be presented as “good practice”. |
| 5 | Satisfactory (S) | Implementation of most of the seven components is leading to efficient and effective project implementation and adaptive management except for only few that are subject to remedial action. |
| 4 | Moderately Satisfactory (MS) | Implementation of some of the seven components is leading to efficient and effective project implementation and adaptive management, with some components requiring remedial action. |
| 3 | Moderately Unsatisfactory (MU) | Implementation of some of the seven components is not leading to efficient and effective project implementation and adaptive, with most components requiring remedial action. |
| 2 | Unsatisfactory (U) | Implementation of most of the seven components is not leading to efficient and effective project implementation and adaptive management. |
| 1 | Highly Unsatisfactory (HU) | Implementation of none of the seven components is leading to efficient and effective project implementation and adaptive management. |
| Ratings for Sustainability: (one overall rating) |  |  |
| 4 | Likely (L) | Negligible risks to sustainability, with key outcomes on track to be achieved by the project’s closure and expected to continue into the foreseeable future |
| 3 | Moderately Likely (ML) | Moderate risks, but expectations that at least some outcomes will be sustained due to the progress towards results on outcomes at the Midterm Review |
| 2 | Moderately Unlikely (MU) | Significant risk that key outcomes will not carry on after project closure, although some outputs and activities should carry on |
| 1 | Unlikely (U) | Severe risks that project outcomes as well as key outputs will not be sustained |

## Annex IV: List of documents reviewed

- UNDP-GEF MTR Guidance

- IEO Guidance

- PIF

- CEO Endorsement Request

- UNDP Initiation Plan

- UNDP Project Document

- UNDP Country Programme Document (CPD)

- UNDP Seychelles Annual Report 2021

- UNDP Social and Environmental Screening Procedure (SESP) and Results

- Co-Financing Letters

- Risk Log updates

- Project Inception Report

- Project Implementation Reports (PIR's): 2021 and 2022

- Annual / Quarterly Workplans

- Quarterly / Annual progress reports

- Responsible Parties Report

- Audit report

- Finalized GEF focal area Tracking Tools at CEO endorsement and midterm

- Monitoring reports

- Evidence based Reports

- Project operational guidelines, manuals and systems

- Grant Agreements

- PDCS SOPs

- Minutes of Steering Committee meetings

- Project site location maps

- Project Communications and awareness brochures, posters, etc.

- Consultancy Reports (TORs, Inception, Technical, Final: Around 50 reports)

- Training Reports(around 10 reports)

- Financial Reports

- Other Project Reports (some 10 different projects, including MTR and Final Reports)

## Annex V: Interview Schedule

| Name: | Ridge to Reef Approach for the Integrated Management of Marine, Coastal and Terrestrial Ecosystems in the Seychelles |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Details: | MidTerm Review Mission Schedule 30th August to 16th September 2022 |  |  |  |  |
| Date | Time | Meeting / Activity | Organisation | Venue | Status |
| Tuesday 30th August 2022 | 09:00 | Consultant arrives |  |  |  |
|  | 18:00 | RTA Penny Stock | UNDP | PCU Meeting room- Virtual | Completed |
| Wednesday 31st August | 9.00 -12.00 | Joanna Prosper– R2R project Manager, Cindy Chang Leng Clair, Chief Programme Coordinator | Programme Coordination Unit | PCU Meeting room | Completed |
|  | 13:30-15:00 | Allen Cedras, Dainise Quatre | Seychelles Parks and Gardens Authority | SPGA Meeting Room | Completed |
|  | 15:30-17:00 | Ginnie Alexis | PUC | PCU Meeting room | Completed |
| Thursday 1st September | 11:00-12:30 | R2R- Technical Advisor Evelyn Drawec- Agriculture and Agroforestry | Programme Coordination Unit | PCU Meeting room | Completed |
|  | 15:30-17:00 | Islands Legal solutions- Consultant | Stefan Knights, Angelique Pouponneau | PCU Meeting Room- Virtual | Completed |
| Friday 2nd | 09:00-10:30 | R2R- Technical Advisor Didier Dogley- Forestry | Programme Coordination Unit | PCU Meeting room | Completed |
|  | 11:00-13:30 | Site visit Demonstration Farm Anse Royale TA Agriculture/ Agroforestry and Mont Plaisir with TA Forestry | Richard Felix Farm | Anse Royale. Mont Plaisir | Completed |
|  | 13:30: 14:00 | Danny Agathine | Val D'enDor Farmers Association | Val D'endor Community Centre | Completed |
|  | 13:30-17:00 | Site visit Demonstration Farm and Dan Sours with TA Agriculture/ Agroforestry and Mont Plaisir/Baie Lazare with TA Forestry | Mark Mothe Farm, Dan Sours | Anse Royale, Val D'endor, Dan Sours | Completed |
| Monday 5th | 09:00-10:30 | Vicky Athanase, Elvina Henriette | Terrestrial Restoration Action Society Seychelles -TRASS | PCU Meeting Room- Virtual | Completed |
|  | 11:00-12:30 | Terence Vel | Mont Plaisir Watershed Committee Chairperson | PCU Meeting Room- Virtual | Completed |
|  | 14.30-15.30 | Rajelle Barbe | Community, Gender and Youth | PCU Meeting Room- Virtual | Completed |
|  | 15:30-17:00 | Baie Lazare Watershed Committee Members | Baie Lazare Watershed Committee | Val D'endor Community Centre | Completed |
| Tuesday 6th | 09:00-10:30 | Nuette Gordon, Sylvanna Antat (including site visit) | Blue Economy Research Institute/ UNISEY | Anse Royale Campus- Site visit sampling sites | Completed |
|  | 11:00-12:30 |  |  |  | Completed |
|  | 13:30-15:00 | Rabia Somers, Christophe Mason Parker (including site visit) | Marine Conservation Society Seychelles | Seasonal Protected Areas Sites | Completed |
|  | 15:30-17:00 |  |  |  | Completed |
| Wednesday 7th | 09:00-10:30 | Preethi Sushil Nair, Oksana Vovk | UNDP Country Office | PCU Meeting Room | Completed |
|  | 11:00-12:30 |  |  |  |  |
|  | 13:30-15:00 | Denis Matatiken,Ashley Dias, John Quilindo, | NPD, Ag. DG Conservation, D Forestry | Botanical Gardens | Completed |
|  | 15:30-17:00 |  |  |  |  |
| Thursday 8th | 09:00-10:30 | Audrey Zelia | FAO | PCU Meeting Room | Completed |
|  | 11:00-12:30 | Andre Sopha- re organised for Friday |  |  |  |
|  | 13:30-15:00 | Jean Claude Labrosse | Department of Climate Change | PCU Meeting Room | Completed |
|  | 15:30-17:00 | Rachel Bristol, Gilberte Gendron, Bruno Senterre | KBA & Green Corridor | PCU Meeting Room | Completed |
| Friday 9th | 08:00 - 14:00 | Field Visit Praslin - SPGA (Curieuse) | Dainise Quatre, Anto Suzette | Curieuse | Completed |
|  | 14.00-15:30 | Seychelles Fire and Rescue Services Agency | Peter Cherry | SFRSA Praslin | Completed |
|  | 15:30 - 16:00 | Praslin Watershed Committee | Praslin Watershed Committee Members | SFRSA Praslin | Completed |
|  | 16:00 onwards | Andre Sopha | Seychelles Farmers Association | PCU Meeting Room | Completed |
| Saturday 10th | 09:00 – 11:00 | Field Visit Praslin - TRASS (Pasquiere) | Confirmed | Pasquire | Completed |
| Monday 12th | 09:00-10:30 | Mr Estico confirmed | Local Government- District Administration | Virtual | Completed |
|  | 11:00-12:30 | Emma Valentin | Finance Manager PCU | PCU Meeting Room | Completed |
|  | 15:30-17:00 | Nelson Renaud | Local Food Producers Association | Virtual | Completed |
| Tuesday 13th | 09:00-10:30 | Cindy Chang Leng Clair | Chief Programme Coordinator (PDCS) | Virtual | Completed |
|  | 11:00-12:30 | Roy Govinden, Linette Joubert, Bobb Petrousse | Department of Agriculture | Virtual | Completed |
|  | 13:30-17:00 | Prepare Working Session | Consultant | Virtual | Completed |
|  | 15:00-16:00 | Murial Morgan & Bernard Belle | Ministry of Lands and Housing | Virtual | Completed |
| Wednesday 14th | 09.00-12.30 | Working Session with Project Team | Project Team- JP, ED, DD, RB | Virtual | Completed |
|  | 13:30 - 17:00 | Prepare Debrief / Workshop | Consultant | PCU Meeting |  |
| Thursday 15th | 09:00-13:00 | Prepare Debrief / Workshop | Consultant | PCU Meeting |  |
|  | 14.30-16.00 | 1st debrief | UNDP, project team, PCU, NPD, RPs | PCU Meeting Room | Completed |
| Friday 16th |  | Writing Draft MTR |  |  |  |
| Monday 19th | 09:00 –10:00 | Meeting Markus, Ephelia Hotel, Port Launay |  |  | Completed |
|  | 11:00 – 13:00 | Meeting UNDP (Preethi, Oksana) |  |  | Completed |
| Tuesday 20th | 17:00 – 18:30 | Flavien Joubert | Minister of Agriculture, Climate Change and Environment | Minister’s Secretariat, unity House, Room 103 | Completed |
| Wednesday 21st |  | Consultant leaves |  |  |  |
| Wednesday 5th October | 13:00- 16:00 | Hybrid workshop- Present findings of MTR | All stakeholders | PCU Meeting Room + Virtual |  |

## Annex VI: Progress Towards Outcomes

| Indicator Assessment Key Green= Achieved | Yellow= On target to be achieved | Red= Not on target to be achieved |
| --- | --- | --- |

Red font, changes to original indicators and targets, at Inception Report, and at MTR (in yellow highlight)

| Project Strategy | Indicator | Baseline Level | Level in PIR 2022 | Mid-term Target | End-of- project Target | MT Level & Assess-ment | Rating | Justification for Rating |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: To manage and conserve the flow of marine, coastal and terrestrial ecosystem services in targeted islands of the Seychelles for multiple benefits through the Ridge-to-Reef approach | - Gender-responsive legal and regulatory frameworks, policies and institutions strengthened and solutions developed and submitted to address conservation, sustainable use and equitable benefit sharing of natural resources, in line with international conventions and national legislation | a) National Forestry Policy: being revised | 1. a) National Forest Policy- This sub-Indicator target is 100% achieved based on midterm and end of project targets. The National Forestry Policy has been completed and endorsed in December 2021. | - a) Revised and discussed with stakeholders in partnership with FAO Project | - a) Submitted to Govt. for approval in partnership with FAO Project |  | MS – S | 63.44% of the mid-term target has been achieved. Consultancy for 1.b. 1 Forest Mngt Bill signed. Status water regulations to check. ID gaps and drafting regulations |
|  |  | b) 1. Breadfruit and Other Trees Act (out of date), the Lighting of Fires Act, b 2. the State Lands and Rivers Act (1903): Out of Date | 1. b. 1) The Breadfruit and Other Trees Act- This sub-Indicator is 70% based on midterm targets. A Forest Management Bill, which will incorporate the Breadfruit and Others Trees Act, was being reviewed under the FAO TCP Project. First draft has been submitted unfortunately, the funds from FAO are not any more available. R2R project will support the completion of the Bill. TOR was approved by PSC, advertised and TEC held with selection of consultants completed. Completion work is scheduled to start in July 2022. 1.b. 2) The Lighting of Fires Act- The sub indicator is 100% achieved based on midterm and end of project target. No further action required by the project. 1.b. 3) The State Lands and Rivers Reserve Act (SLRRA) (1903)- This sub indicator is 25% achieved based on mid-term target. Consultant team recruited and started the review SLRRA in Q3 2021. Meeting held between MLH, MACCE, UNDP, R2R Team and Consultant team to discuss the SLRRA following submission of inception, report, gap analysis and a discussion paper. It was decided that there is no need to revise the SLRRA as other ongoing legislative works e.g Water Bill (EBA Project), Forests Bill (FAO) can cater for forest and water protection and resources management on State and private property. Discussions also suggested that a State Lands Management Bill is the preference of the Cabinet of Ministers; it would be obsolete to revise the SLRRA. Based on the above R2R management team sought approval from the R2R PSC for the R2R project to finance the State Lands and Management Bill in October 2021. Following approval by R2R PSC for the R2R project to finance the State Lands and Management Bill, the current was amended as such. The development of the Bill started in June 2022. | - b) Updated and discussed with stakeholders | - b) Submitted to Govt. for approval |  |  |  |
|  |  | c) Regulatory amendments under new Water Act to better conserve watersheds and wetland ecosystem services: None | c) The Regulatory amendments under new Water Act to better conserve watersheds and wetland ecosystem services- This sub indicator is 5% achieved based on midterm target. The new Water Resource Management Bill is being finalised by MACCE with support from GOS-AF-UNDP Ecosystem Based Adaptation (EBA) Project. The Integrated Water Resource Management Bill was presented in a validation workshop on 24th of March 2022 and although there are a few outstanding matters to clarify and sort out, in principle the Bill can soon be finalized and send to cabinet for endorsement. R2R will take up regulatory amendments once Bill is endorsed | - c) Drafted and discussed with stakeholders | c) Submitted to Govt. for approval |  |  |  |
|  |  | d) Water Quality and Effluent Standards and Codes of Practice: Outdated | d) The Water Quality and Effluent Standards and Codes of Practice- This sub indicator is 81 % overall achieved based on midterm target. The effluent standards and code of practice is 100 % end of project target achieved and the water quality standards 5% achieved for midterm target. Following several Technical Working Group meetings, a draft water effluent standards and Code of practice was presented at Validation workshop on 10th of March 2022 to representatives of government partners and stakeholders. Final deliverables were submitted end of March to DOE for endorsement. Water Quality Standards to be reviewed together with indicator 1c once Water Resource Management Bill is endorsed by Cabinet | - d) Drafted and discussed with stakeholders | - d) Submitted to Govt. for approval |  |  |  |
|  |  | Policies and/or regulations regarding compensation of landowners whose land uses are affected by PA designations: None | e) The Policies and/or regulations regarding compensation of landowners whose land uses are affected by PA designations- ‘Policy has been completed and approved by cabinet in February 2020'. Thus 100% achieved based on end of project targets. No further action required by the project. |  |  |  |  |  |
|  |  | f) Review and amend the Acquisition of land in Public Interest Act to include biodiversity value and criteria | f) Review and amend the Acquisition of land in Public Interest Act to include biodiversity value and criteria. This new sub-Indicator target is 10 % achieved based on midterm target. Consultancy for the review of the State Land Management Bill (see indicator 1.b.iii) is taking into account this indicator when developing the Bill. | f) drafted and discussed with stakeholders | f) Drafts sent to MEECC and Planning |  |  |  |
|  |  | g) Regulations for new Nature Reserve and Conservancy Bill | g) Regulations for new Nature Reserve and Conservancy Bill. This new sub-Indicator target is 80 % achieved based on midterm and end of project target. In March 2022, The Nature Reserves and Conservancy Bill was approved by National Assembly and assented. In June 2022, the draft of the proposed designation of protected areas regulations was submitted to the AG’s office | g) Draft (under the GOS-GEFUNDP Outer - Islands Project) | - g) Drafts sent to MEECC and Planning |  |  |  |
|  |  |  | - Although not an indicator, following Government request and approval by steering committee, the project also supported government in the revision of the Wild Animals and Bird Protection Bill with draft bill submitted in April 2022. |  |  |  |  |  |
|  | - Capacity of national partners implementing integrated Ridge to Reef approaches, as measured by total scores on the UNDP Capacity Scorecard | 71% (32/45) | The UNDP Scorecard was re-calculated on 8th June 2022 with score of 77% 35/45. Included in the calculation were Principal Secretary for Environment, Acting Principal Secretary for Climate Change, R2R Project Manager and R2R Technical Advisor for Agriculture/Agroforestry. Despite, some of the indicators going down in rating (resources lost from Covid, changes and restructuring in Government having an effect), there have also been beneficial gains in the project such as incorporation of technical knowledge, and adequate monitoring and evaluation. | - 76% (34/45) | - 82% (37/45) |  | S | The mid-term target has been 100 % (35/45) achieved. |
| Outcome 1: Strengthened management of upland KBAs and adjacent areas to enhance the flow of ecosystem services through the R2R approach | - 5 new Turtle Temporal Protected Areas (TPAs) encompassing 40 ha is strengthened formally established and supported by regulations to conserve biodiversity and maintain ecosystem goods and services (GEF Core Indicator - Marine protected areas newly created) | 0 | The revised mid-term target (5 TPAs ‘nomination files submitted to Government’) has been achieved and the project is on-track to meet the end of project target. The “Temporal Projected Areas” (TPA) nomination files were submitted to Department of Environment, MACCE on 21st April 2021. With the enactment of the Nature Reserves and Conservancy Act 2022, the terminology has changed and now makes provision for “Seasonal Protected Areas” (SPA). Turtle Seasonal Protected Areas management plan draft has been finalised, however, still requires clarification on the management modality from MACCE, as well as the management regulations. | 5 TPAs gazetted nomination files submitted to Government | 5 TPAs management plans completed and under implementation |  | S | 100% (revised MT). |
|  | - Strengthened management of Temporal Protected Area (TPAs) covering 40 ha and Marine Protected Areas (MPAs) covering 1,421 ha, as measured by increased scores on GEF Management Effectiveness Tracking Tool (METT) | Turtle TPAs: 28 Baie Ternay / Port Launay MNP : 61 Curieuse MNP : 71 | a) Turtle TPAs (average of the 5 sites) :44.2- Midterm and end of project target achieved . b) Baie Ternay / Port Launay MNP: 71- Midterm and end of project target achieved. c) Curieuse MNP: 72- Midterm target 97% achieved. | 35 66 74 | 40 71 76 |  | S | (100% MT and End Target) (100% MT and End) (97% MT and 95% End) |
|  | - Area (ha) of mangrove and other coastal forest ecosystems restored rehabilitated using native species | Mangrove : 0 Coastal Forest : 0 | Rehabilitation work on Curieuse focused on four targeted coastal forest areas being Anse Badamier, Grand Anse, Anse Patate and Anse Saline/ Mangrove area and consisted of removal of under canopy alien species including the removal of litter and waste from the sites and/or tree planting of 3752 native plants, spread over the four sites. Rehabilitation of a total area of 11 hectares was completed in February 2022. In additional Terrestrial Restoration Action Society of Seychelles (TRASS), a R2R Responsible Partner, has rehabilitating 4.5 ha of coastal forest which includes the beach crest, mangroves and riverine woodland at Pasquiere, in the Curieuse Marine National Park as part of their rehabilitation programme | 10 15 5 | 20 30 10 |  | S | 100% (15.5ha of 15 ha) of the revised MT target has been achieved. However, a concern about survival rate and impact maintains |
|  | - No. of KBAs with required technical documents and draft legal documents for gazetting presented to the Government | 0 | Consultancy ongoing to strengthened management capacity and assess the status for 6 key biodiversity areas (KBA) being: 1. Montagne Planneau 2. Montagne Corail – Collines du Sud and Grand Police 3. Montagne Brulee – Piton de l’Eboulis 4. Praslin National Park extension 5. Riviere Kerlan (Praslin) 6. Western coast (Curieuse) The following have been submitted - Identification of landowners in and abutting the KBAs -Stakeholder’s consultation report for the outreach to local land owners on KBA gazetting and management - Habitat maps showing interest features for each KBA including locations of KBA species, naturalness areas, and infrastructures as a GIS project and as maps. This report was further validated in May 2022. - Report on biodiversity assessments and ground-truthing including updates of KBAs using current survey methods. This report was further validated in May 2022. The management plans were submitted and reviewed internally by R2R team and Department of Environment officers in November 2021 In December 2021, Consultant team presented a brief for the Environment officers to present to the Cabinet of Ministers for clarification on designation procedures which will then follow with development of the Nomination files and presentation to the landowners and public. Six months delays from Department of Environment regarding seeking Cabinet of Ministers endorsement on queries rose about the process of declaring the KBA sites into legally protected areas. Senior Staff at DOE have confirmed in June 2022 that a Cabinet of Ministers paper is ready for submission and consideration. Cabinet presentation took place (September 2022) and concept was approved, though further consultations with all landowners was necessary. | 2 | 6 / 5 (covering 2,235 ha) |  | S | 100% MT target and 60 % end target achieved with 5 instead of 6 KBAs having technical documents completed. 2 KBAs are merged into 1, with same Ha (2,235 Ha) as the initial 6 KBAs |
| Outcome 2: Strengthened management of upland KBAs and adjacent areas to enhance the flow of ecosystem services through the R2R approach | - Number of functioning Watershed Committees, with gender and age diversity | 1 Committee 4 committees set up under the GOS-AFUNDP Ecosystem based Adaptation project | Working in collaboration with GOS-AF-UNDP Ecosystem Based Adaptation (EBA) Project 5 watershed committees (WSC), namely Baie Lazare, Anse Royale, Praslin, Anse Boileau and North East Point has been set up, the former 3 of which are at R2R project sites identified in the project document for watershed committees. The EBA project ended in March 2022, and the R2R project is providing support to the WSCs. The current composition of participation at the R2R project sites is: • Baie Lazare: 6 M (50%), 6F (50%) and 3Y (25%) • Anse Royale: 6M (64%), 5F (36%) and 2Y (14%) • Praslin: 5M (56%), 4F (44%) and 2Y (22%) The total composition of these three committees is 20M (57%), 15F (43%) and 7Y (20%) participation. Ownership of land at Grand Police has not been finalized since the project team has been informed to hold back on setting up the Grand Police Watershed committee. Awaiting the Midterm review for guidance on next step. Consensus is that the land ownership issue at Grand Police will not be solved anytime soon. It would be better to change areas, e.g. to Caiman, where a previous Watershed Committee already exists, and which is also an important KBA and watershed site. Nevertheless, being an important biodiversity area, the project should remain in Grand Police, e.g. through the MCSS managed SPAs, as these are anyway on beaches that are not under any claim, and monitor the situation and consider stepping in and forming a Watershed committees when appropriate and if there is still time within the project. | 4 committees with 30% women participation | 4, with 50% women and 15% youth participation |  | MS | 3 of the 4 (R2R site) Watershed Committees set up (75% of MT Target), with overall women participation 43% and youth 20%, ) Proposed shift from Grand Police to Caiman Watershed. |
|  | - Restoration Rehabilitation of areas critical for ecological functioning in priority watersheds / upland forests on Praslin | No. of ha of fire-degraded upland forest restored rehabilitated: 0 No. of ha cleared of IAS flora and replanted with native tree species and other non-native non-inavsive species: 0 | R2R responsible partner, Terrestrial Restoration Action Society Seychelles has reported rehabilitation of a total of 14.1 ha as follows 8 a) 4.6 ha of fire-degraded upland forest at Pasquiere (2.1 ha), Anse Possession (2ha) and Pte. Chevalier (0.5 ha). These are upland degraded areas where experimental trials are being incorporated into the rehabilitation. 8b) 9.5 ha are being cleared of IAS and undesirable native species and replanted with natives. This includes 9 ha at Pasquiere and 0.5 ha at Pte. Chevalier. | 4 40 10 | 10 60 20 |  | S | 100% (14.1of 14ha) of the revised mid-term target is achieved. |
|  | - No. of ha reforested within priority watersheds and in areas within / adjacent to target KBAs | 0 | Summary of achievements against mid-term targets are as follows a) 15.5 of 15 ha of coastal forest rehabilitated. See indicator 5 for more details. b) 14.1 of 14ha of areas critical for ecological functioning in priority watersheds / upland forests: See indicator 8 for more details. c) 22.8 of 21 ha of watershed on Mahe reforested. Work has completed in collaboration with the GOS-AF-UNDP Ecosystem Based Adaptation (EBA) project, as a part of a phase over of activities to R2R. Contractors have implemented rehabilitation on 2.9 ha of riverine forest in Mont Plaisir and 19.9ha of forest in Baie Lazare. | 40 50 | 100 |  | S | 105% (52.4 of 50ha) of revised mid-term targets achieved. |
|  | - No. of ha of low-productivity land in the Val d’Endor, and Anse Royale Caiman and Praslin watersheds converted to agroforestry | 0 | 1 ha at Val D’endor, Dans Sours, previously abandoned agricultural land, is being transitioned to agroforestry (AF)and is planned to be managed by the Baie Lazare watershed committee. Delays in achieving this indicator as the consultancy to review sites for AF in Val D’Endor and Anse Royale ended in March 2022 with unsuccessful results. The consultant was not able to submit completed maps and an assessment by the end of the consultancy and due to performance, the project did not extend the contract. Forestry land at the moment cannot have agricultural production per the Forestry Act. This Act is being updated under the project, and perhaps at the end of the project forest land can be used for agricultural purposes. As such, only abandoned agricultural land can be targeted. The TA Agri met with the Department of Agriculture on 21st June and 28th June 2022 to review suitable agricultural land for Agroforestry. There is no low productivity agricultural land in Anse Royale, this area has the most productive farm land. The project will focus on unproductive farmers in Val d’endor. The TA Agri will use the previous farm survey, personal farm surveys, and surveys during the trainings to identify farmers to work with to implement agroforestry. At the end of June 2022 a ToR was being reviewed by the Steering Committee to recruit a team of consultants to work directly with the farmers to implement Agroforestry systems. | 40 25 | 100 50 |  |  | 4% achieved based on revised mid-term target. |
|  | - Amount of tCO2eq GHG emissions avoided / sequestered through avoided deforestation and forest degradation, reforestation, agroforestry and conservation agriculture | 0 tCO2eq | Project has recruited an international consultant to assist with midterm calculations, at the end of Q2 2022, and has commenced work to provide the measurements before midterm review in August 2022. Consultant looked at methodology, baselines and targets. Targets were revised by expert, who found that outdated baseline date were used during project preparation, and also considered revised targets (e.g. under Indicators 8 and 10). At time of measurement (August 2022) a calculated 1,195tCO2eq. was avoided / sequestered. | 18,273 tCO2eq To be revised to: 7,070 tCO2eq | 43,853 tCO2eq To be revised to: 16,134tCO2eq |  |  | Only 17% of revised MT target achieved |
| Outcome 3: Promoting the ‘Ridge to Reef’ (R2R) approach through knowledge management, ecosystem health monitoring and inter-sectoral coordination | - Number of institutional partners using the online platform to share data, findings and other information generated by field interventions on Ridge to Reef approaches | 0 | Proposal for project to move forward with R2R responsible partner, Blue Economy Research Institute/University of Seychelles ( BERI/UNISEY) establishing the database via the ArcGIS platform in partnership with the Information Communication Technology Department at the University was discussed at 4th PSC meeting, July 2021. There was no objection to the proposal however The National Institute of Science Technology and Innovation (NISTI) was to be consulted for approval of this delegation of responsibility. A meeting was held in October 2021 whereby NISTI (Government Institute responsible to create and administer a centralized National Database System of all scientific research and activities) confirmed that a national database for water quality is not their priority. Following several discussions to follow the procurement procedure to ensure competitive bidding a TOR was advertised whereby BERI-UNISEY was the sole organization to apply. Amendment to the current Grant Agreement is being finalized for the activities to kickstart. Ministry of Agriculture, Climate Change and Environment, Waste Management and Standards Section and SeyCCAT Ocean 5 project collaborating with BERI/UNISEY to use the online platform once operational. | 2 | 5 |  |  | Project Indicator target 5% achieved based on mid-term target. |
|  | - Integrated ecosystem health monitoring at project sites institutionalised, with information management and dissemination coordinated by DOE, BERI and NISTI, to support the implementation of R2R approaches | No system exists | The University of Seychelles/Blue Economy Research Institute (UniSey-BERI) have finalised the water quality monitoring protocol in 2021. Protocol is currently being tested at the Anse Royale Watershed. The Protocol is formally part of UniSey BSc in Environmental Sciences curriculum (Course: SENV1106 – Research Methods & Skills) for last 3 years. Include practical field sampling & data analyses. The draft protocol has also been presented as part of the World Bank Short Course on Integrated Coastal Management (October 2021) and R2R Sustainable Watershed Management Training workshop (June 2022) | Ecosystem data being collected and consolidated | Data management system operating |  |  | Project indicator 50% achieved at midterm target. |
|  | - Policy recommendations to improve the effectiveness of R2R approaches, based on the integrated ecosystem health monitoring results, developed and submitted adopted by relevant ministries | 0 | Consultancy completed in February 2021 for an initial gap analysis of the existing government policy framework that limits the application of R2R approaches and a strategy to address these issues. Strategy recommendations is guiding projects next steps while we await the integrated ecosystem health monitoring system of project sites to set up, operate, data collected, consolidated and results obtained so further policy analysis and recommendations can be identified. | 1 | 2 |  |  | Project Indicator target 5% achieved based on mid-term target. |
|  | - No. of local officials sensitised on R2R approaches and partnering with the project to facilitate community involvement in the management of KBAs, ecosystem monitoring, and undertaking sustainable agriculture and forest management interventions | Regional District Council members / staff: 0 District Administration members / staff: 0 | Q1, 2021: 8 officials (District Administrators) were sensitized and assisted to locate landowners in management of KBAs Q1, 2021: 2 officials (District Administrator and Member of the National Assembly) were involved in the review of the nomination file for the Temporal Protected Areas Nomination file linked to ecosystem monitoring. Q4 2021: TA Agriculture gave an introduction to the R2R project, the timeline, main objective of the whole island approach to environmental conservation and management, main project outputs and indicators. The presentation was attended by 12 officials (District Administrators). Q1 2022: Part time consultants/officers recruited for media, community, gender and youth and communications. Both consultants/officers will work towards developing implementing the communication and engagement strategy with Local Government. Q2 2022: R2R Project Manager and Part time Community Officer met with 5 officials (District Administrators) for project sites; Baie Lazare, Takamaka, Anse Boileau and Anse Royale Presentation and discussions on the R2R project activities specific to their district and how they can involve community further. Next steps for assistance to be outlined in a communication and engagement strategy for District Administrators and development of communication tool kits. Q2, 2022: 1 officials (Member of the National Assembly) were involved in the Public meeting to discuss proposed Seasonal Protected Areas: status, threats, and solutions. | 4 6 | 8 12 |  |  | Project Indicator target 100% achieved based on mid-term target. |
| Outcome 4: Knowledge Management, M&E and Gender Mainstreaming | - No. of policies / strategies / programs supporting R2R approaches agreed with other national and international conservation programmes | 0 | The National Policy for Private Land Owners in Protected Areas of Seychelles was finalized in February 2020 and endorsed in December 2021. Agroforestry Policy finalised in 2021 and formally submitted to the Department of Agriculture for presentation to the Cabinet of Ministers. As per indicator 14, strategy recommendations are guiding projects next steps while we await the integrated ecosystem health monitoring system of project sites to set up, operate, data collected, consolidated and results obtained so further policy analysis and recommendations can be identified. | 2 | 5 |  |  | Project Indicator 100% achieved based on mid-term targets with 2 policies finalized. |
|  | - % of women among the project participants | 0 | The following has been recorded since project start in January 2020 till June 2022: - 67 contracts awarded to date of which 31 has been awarded to women (46%) - 55 recorded events (meetings, questionnaires, workshops and PSC) held to date, with 927 of 470 participants being women (51%) - As noted in indicator 7: The current composition of R2R site Watershed Committees is: • Baie Lazare: 6 M (50%), 6F (50%) and 3Y (25%) • Anse Royale: 6M (64%), 5F (36%) and 2Y (14%) • Praslin: 5M (56%), 4F (44%) and 2Y (22%) The total composition of these three committees is 20M (57%), 15F (43%) and 7Y (20%) participation. | >=30% | >= 50% |  |  | Project Indicator 100% achieved based on mid-term targets. |
|  | - Total number of direct project beneficiaries (m/f) | 0 | 18.a) Community members and government officials trained in SFM through the watershed management committees and community organizations (150/350): Sustainable Watershed Management capacity building held in June 2022, with 26 people trained, with 17 women. Sustainable Forest Management capacity building to be held in September 2022. Both training organized following the Capacity needs assessment in project planning, coordination, monitoring and information management to support Sustainable Forest Management and watershed management approaches for Forestry Division, Seychelles National Parks Authority, University of Seychelles, Terrestrial Restoration Action Society Seychelles (TRASS), Marine Conservation Society Seychelles (MCSS) and Community Based Groups (including Watershed Committees) finalised in July 2021. 18.b) Civil society members and government officials trained through forest fire fighting task forces (50/100); Forest fire fighting training was held in June, July, August, September and November 2021 with a total of 73 people trained, with 22 women. Training was organised jointly by R2R project and GOS-AF-UNDP Ecosystem Based Adaptation (EBA) project. Targeting members and officials from Seychelles Fire and Rescue Services Agency, District Emergency Brigades, Terrestrial Restoration Action Society Seychelles, Seychelles Parks and Gardens Authority, District Brigades, Seychelles Islands Foundation (Valle de Mai and Fond Ferdinand) and Forestry Section of Ministry of Agriculture, Climate Change and Environment. Upcoming training with district brigades planned in late 2022. 18 c) Farmers trained in Agroforestry, soil conservation, and other SLM practices (50/100); In October 2021, Soil Nutrient and Testing Training: 10 extension officers trained, with 3 women. In April 2022, Tree Felling Training: 9 extension officers trained, with 3 women. They will be able to pass this information along the farmers in each of their regions. In April 2022, Tree Felling Training: 13 Farmers, with 3 women. May 2022, Beekeeping Training: 6 farmers, no women. Upcoming Trainings on Compost and Mulching, Water Resources, Soil Fertility and Agroforestry for 2022. 18.d) Smallholder farmers practicing biodiversity-friendly SLM practices (20/50): With the selection of two demonstration sites, Mr. Felix and Mr. Monthe, these two farms are practicing sustainable land management. So far the project has helped with selective tree maintenance to mitigate erosion and has provided each with a wood chipper to help increase mulching and compost on farm (2 farmers). An additional wood chipper has been provide to Local Food Producers Association (LFPA) to utilize mulching and compost on farms (1 farmer). | >= 270 (at least 40% are women) | >= 600 (at least 40% are women) |  |  | Project indicator target 52% achieved, based on mid-term target, with 140 of 270 beneficiaries (34%) being women. |

## Annex VII:  Risk Log

Updated 18th June 2021 and 14th September 2022 (MTR) (revision in red)

| No | Description | Type | Impact & Probability | Mitigation Measures | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Continued introductions / spread of IAS minimize progress on reducing forest fires or increasing carbon sequestration | Environmental Terrestrial | P = 3 I=2 Moderate | Seychelles’ biosecurity system / protocols are expected to reduce introductions of new IAS, implemented through the new National Biosecurity Agency (NBA) that is tasked with monitoring and responding to any new introductions, and the existence of new emergency response protocols. | National Biosecurity Agency | Project Document: The risk of new IAS introductions is declining with the work of the NBA, but IAS spread may continue to be a risk. LPAC: 10thSeptember 2019 LPAC did not propose any changes 18th June 2021 See risk No. 11. 1st February 2021, the new President announced changes to the National Biosecurity Agency closing down and being integrated into the Ministry of Agriculture, Climate Change and Environment. It remains uncertain how biosecurity functions will be implemented. Technical studies being supported under GOS-AF-UNDP Ecosystems Based Adaptation (EBA) project to develop framework for IAS (Creeper) management – the consultancy will end on November 2021. MTR 14/09/22: IAS framework submitted to GOS. IAS priority More open to IAS (economy) |
| 2 | New Risk Disease in propagation of nursery Seedlings | Environmental Terrestrial | Low | Biosecurity protocols are expected to be followed by project partners in maintenance of nurseries | TRASS, SAA, SNPA, PCU | Inception Workshop: 28th February 2020 It was proposed that under the Invasive Alien Species, to add the risk of diseases in propagation of nursery seedlings as low risk though. In the past there has been occurrence of hairy caterpillars and beetles in the nurseries |
| 3 | Many of the project’s field-based outcomes are vulnerable to the potential impacts of climate change. Most forest management, reforestation and agricultural activities can be negatively impacted by drought and/or extreme weather events, which may reduce vegetative cover and rates of recovery, and increase erosion/sedimentation problems. | Environmental Terrestrial | P = 3 I=3 Moderate | The risk of climate change impacts on ecosystem conservation / restoration activities will be minimised with careful planning and mitigation strategies, as described in the ProDoc. For agriculture, agroforestry and reforestation activities, the project will seek to plant seedlings during seasons when extreme storm events or droughts are least likely, and to select species most likely to survive such events. | PCU, SNPA, TRASS, MCSS, SAA | Project Document: This risk may possibly increase if climate change trends continue LPAC: 10thSeptember 2019 It was noted that that PMU refers to PCU Inception Workshop: 28th February 2020 It was agreed that under the climate change risk, the forest and coastal component should be separated. The forest should be kept as moderate. (See risk No 3 for terrestrial component and Risk No. 4 for coastal component). |
| 4 | Coral reefs may be impacted by coral bleaching events, harmful algal blooms, and outbreaks of the Crown of Thorns starfish | Environmental Marine | P = 3 I=3 Moderate | The risk of climate change impacts on ecosystem conservation / restoration activities will be minimised with careful planning and mitigation strategies, as described in the ProDoc. For coral reefs, the project will focus on coral reef sites with the following characteristics that contribute to resilience to coral bleaching: (i) sites known to be less susceptible to bleaching; (ii) sites found downstream of large catchment areas where there is more freshwater input that helps to cool down the sea in these areas; (iii) sites where no phase shifts from coral domination to macro-algae or rubble domination have been observed; (iv) sites with low levels of anthropogenic disturbances (e.g. from boat anchor, pollution, land-based sedimentation) so that impacts are not cumulative with those from climate change; and (v) sites with reefs that have high rugosity, which seems to be more resilient. With regard to COTS, in the past outbreaks have been mainly concentrated on the northwest coast of Mahe, which are far from the areas selected by the R2R project. In addition, the project’s monitoring and surveys of marine environments will allow for early detection and control of COTS outbreaks. The project also will make use of citizen monitoring to report COTS presence and use civil society actions to control densities at more socio-economically important sites such as where there is regular diving and snorkelling by tourists. With regard to algal blooms, it is very difficult to mitigate as these blooms are caused by natural upwellings of nutrient rich waters that have been locked at depths off the Mahe Plateau. | PCU, SNPA, TRASS, MCSS, SAA | Project Document: This risk may possibly increase if climate change trends continue LPAC: 10thSeptember 2019 Risk 4 – it was noted that that PMU refers to PCU Inception Workshop: 28th February 2020 It was agreed that under the climate change risk, the forest and coastal component should be separated (see risk No 3 for terrestrial component and Risk No. 4 for coastal component). MTR 14/09/22: Maybe drop? |
| 5 | NEW RISK: Coastal Erosion due to high tide (to whom, in what way?) (MCSS, SPGS) CC with risk at extreme events (storm, high tide) | Environmental Marine | High I = High (4 or 5?)(MCSS) P = 4 or 5? | Another risk of climate change impacts on ecosystem conservation / restoration activities is coastal erosion, specifically the rise in high tide affecting turtles nesting sites in 2019/2020. Data from MCSS registered nests lost to erosion: 8, ESBOs (emergence stopped by obstacle) due to erosion cliffs: 16 and nests relocated due to erosion risk: 6 The project partners will follow turtle patrolling protocols to keep log of the impact of high tide to the nest and take mitigation measures to relocate nest that are prone be washed away. | MCSS, SNPA | Inception Workshop: 28th February 2020 Under climate change risk, specific to coastal erosion, the rating should be raised to high as a lot of turtle nesting areas have gone this year alone through erosion. 18th June 2021 Under a Grant Agreement with MCSS, responsible partner is rehabilitating degraded Turtle TPA nesting sites. Well-established ‘turtle-friendly’ native tree species were planted on Anse Bazarca, which is the most degraded TPA site in terms of beach crest vegetation, to allow the plants some months before the Southeast monsoon. 2 x ‘Bwadroz’ (Thespesia populnea) and 1 x ‘Takamaka’ (Calophyllum inophyllum) were planted where there were gaps in the vegetation though with consideration of the surrounding vegetation in order to provide some protection against erosion and weathering. MTR 14/09/22: MCSS destruction sites in South (SE monsoon). But phrasing and relevance to R2R? Only for SPAs? |
| 6 | NEW RISK: ocean acidification affecting corals should be included as a risk | Environmental Marine | Moderate | The project was designed as land centric approach, with the idea that if we're sustainable on land then it will have less impact on the ocean however the project is focusing on monitoring freshwater aquatic environment only. There is a need to also think of measuring the marine environment, which could be an additional co-financing activity, so as to have a holistic approach. Discussions need to be held with stakeholders to ensure the design of the monitoring strategies and indicators strengthens the link between freshwater aquatic and marine aquatic to determine the impact on the marine environment. | MCSS, SNPA, BERI | Inception Workshop: 28th February 2020 This risk may possibly increase if climate change trends continue MTR 14/09/22: Ocean 5 measures , collecting data. National Observation system? |
| 7 | Opposition from landowners to designation of KBAs as protected areas. | Political Terrestrial | P = 3 I=2 Moderate (High Risk?) | Regarding KBA sites, in those cases where at least part of the site is privately owned, any designation of a KBA site as an official protected area will not go forward until the Government of Seychelles has approved a compensation mechanism for private landowners; the Government is already working on a policy in this regard, and the proposed project will assist it in doing so. In addition, as described under Output 1.1.3, the first step in proposing any KBA sites for designation will be outreach and consultations with relevant private landowners. | SNPA MEECC MACCE | Project Document: The risk should decline as project outreach to landowners and fishermen allows them to see the benefits accrued. LPAC: 10thSeptember 2019 Ms Simms (SNPA Chair) and Mr Remy (SNPA CEO) queried why SNPA is being listed as responsible to mitigate risk of KBA from fishermen? Ms Simms (SNPA Chair) pointed out that SNPA is only responsible for National Parks, MACCE is responsible for other sites. It is proposed that the responsible parties be changed to MACCE. Mr Alcindor (UNDP co-chair) also suggested editing some of the text in the mitigation measures as it’s too long and to separate the marine and terrestrial risks. An additional risk was identified with regards to land ownership. land ownership issues may come up under the recently launched Truth and Reconciliation and National Unity Commission hearings. There was a query over what the mitigation measure to apply but there were no further discussions on the matter. Inception Workshop: 28th February 2020 It was agreed that the Terrestrial and Marine risks should be separated (see risk No 7 for terrestrial component and Risk No. 8 for marine component). 18th June 2021 Following Truth, Reconciliation and National Unity Commission (TRNUC) activities and discussions with the new Minister (Mr Flavien Joubert) on 24th November 2020, Government is advising that there is a claim by the Deltel family for Grand Police and any nomination files for terrestrial sites (for KBA or Watershed Management Plans) need to be put on hold until this is clarified. MTR, 14/09/22: Raise Risk? Areas will not be designated as “KBA”, but another category still to be decided under the new categories under the NRCA. This may also allow some measures of “sustainable Activities”? KBAs are also in not easily accessible and “disaster prone areas”. Development in these areas not straightforward and “easy”. See also Landownership claim at Grand Police. |
| 8 | Opposition from fishermen to new MPAs or strengthened MPA regulations; | Political Marine | P = 3 I=2 Moderate | In existing MPAs, the project will focus on strengthening the enforcement of existing regulations, rather than imposing new regulations. It is not anticipated that the strengthening of the existing network of MPAs will have any major negative impacts on fishermen's livelihoods, while it will have a major positive impact on the country's marine conservation efforts by showing that the Seychelles is not only interested in numbers like percentage of EEZ under protected status but also in the effectiveness of these protection designations. Most of the country’s MPAs have long been established and illegal fishing activities are already controlled, what the project will be doing will be increasing the level of compliance and increasing the level of respect of MPA stakeholders for these areas. In addition, the changes in access to marine resources are intended to increase the sustainability of these assets and produce a positive impact on livelihoods over the long-term. For example, the rehabilitation activities done by the project in coastal and mountain areas will reduce the level of sedimentation and improve health of coral reefs and coral reef associated fisheries, thereby producing net benefits for fishermen. The biodiversity surveys planned will also identify the characteristics of important/critical nursery areas for coral reef associated fish and make suggestions to improve their management, which will further benefit fishermen. The project approach is also in line with voluntary measures that fishermen on Praslin are taking to improve management of fisheries resources around this island; the project ensure effective consultations with fishers during implementation by having someone from the fishing industry on the project's steering committee. The project can also collaborate with on-going efforts to re-introduce Honorary Wardens (who can be fishermen) and how fishermen can otherwise be more actively involved in the management of natural marine resources. Finally, it is important to note that most fishermen are law abiding and would welcome better enforcement so that they do not lose out to those fishermen who do not follow the law. During the 1st year of project implementation, a Livelihoods Action Plan for fishermen will be developed for implementation during the remaining period of project implementation. With regard to the establishment of new MPAs, the project is only proposing to establish Turtle Temporal Protected Areas, which – because they are generally small in size and only seasonally in force – are not perceived by fishermen to be a threat to their livelihoods. In addition, the Turtle TPAs will not have any impact on fishing. The changes in access to marine resources from strengthening enforcement of existing regulations are intended to increase the sustainability of these assets and produce a positive impact on livelihoods over the long-term, which should mitigate opposition from fishermen. | SNPA MEECC MACCE | Project Document: The risk should decline as project outreach to landowners and fishermen allows them to see the benefits accrued. LPAC: 10thSeptember 2019 Ms Simms (SNPA Chair) and Mr Remy (SNPA CEO) queried why SNPA is being listed as responsible to mitigate risk of KBA from fishermen? Ms Simms (SNPA Chair) pointed out that SNPA is only responsible for National Parks, MEECC MACCE is responsible for other sites. It is proposed that the responsible parties be changed to MEECC MACCE. Inception Workshop: 28th February 2020 It was agreed that the Terrestrial and Marine risks should be separated. (see risk No 7 for terrestrial component and Risk No. 8 for marine component). MTR 14/09/22: No work with fishers in past years or foreseen in project (no funds). Mitigation measures have come from other project? Can leave in but will not be monitored. |
| 9 | Socio-economic pressures (e.g. the importance of tourism development for the national economy) prevent effective implementation of development controls to protect coastal freshwater ecosystems | Political Terrestrial & Marine | P = 2 I-3 Moderate | The Seychelles Planning Authority has previously given permission for development in sensitive areas, including KBAs, and current EIA processes are inadequate. Recent legal decisions have overturned Government land use planning designed to protect sensitive areas on constitutional grounds. However, EIA regulations are currently being revised and strengthened, including new regulations regarding wetlands, and this project will support these efforts as needed. In addition, the enactment of the proposed Nature Reserves and Conservancy Act is expected to greatly increase the visibility and support for effective protections of important natural ecosystems in the country | MEECC MACCE Planning Authority, AG’s Office | Project Document: This risk is projected to decline as new laws, regulations and policies are coming into place LPAC: 10thSeptember 2019 It was suggested that SNPA be removed as responsible party/owner and replaced by MEECC MACCE 18th June 2021 Controversial Tourism Development, namely the Grand Bwa Private Development project, is reportedly still progressing according to GOS-AF-UNDP EBA project. This will influence freshwater ecosystems, a GOS-AF-UNDP EBA project site but may affect Montagne Planneau the R2R KBA areas. This will be monitored as the KBA consultancy progresses. MTR 14/09/22: When projects shift to include Caiman site, above development may be monitored. |
| 10 | Failure to enact the National Parks and Nature Conservancy Bill would limit the legal conservation status of the proposed KBAs and Turtle TPAs, and would reduce public awareness and support for protecting such areas | Political Terrestrial & Marine | P = 2 I-3 Moderate | Project activities to carry out biodiversity assessments and create/refine nomination files for KBAs and TPAs will of themselves help to generate momentum and pressure to enact the proposed NRCA. In addition, active monitoring programs at these sites will help to conserve biodiversity (and in the case of KBAs, reduce land degradation) even if enactment of the NRCA is delayed for another year or two. | MEECC MACCE | Project Document This risk is expected to be eliminated in the 1st year of the project activities, and possibly even before the project starts. LPAC: 10thSeptember 2019 PS Decomarmond (NPD) advised that the NRCA (PA bill) has been approved by Cabinet and is waiting to be submitted to the National Assembly. The LPAC concurred that the risk will most likely be eliminated by the end of 2019, barring any negative input from the National Assembly. Additional risk – SNPA pointed out that project talks about KBA but it is not clear who will be responsible for these areas. National Parks will fall under the responsibility of SNPA while other categories could be managed by other agencies/organisation but in the interim it should be MEECC MACCE until power of delegation is determined 18th June 2021 See risk 11, On 6th January 2021, the new Cabinet approved and endorsed the final amendments to the Nature Reserves and Conservancy Bill, 2020. Cabinet Business - Wednesday 06th January 2021 - News - State House Seychelles ¦ Office of the President. Project awaits Government guidance on when this will be presented to the new National Assembly. MTR 14/09/22: No Risk anymore |
| 11 | NEW RISK Following LPAC and Inception workshop Elections are being planned in 2020 and in 2025 and could, thus, pose a political risk as it could slow project implementation | Political | Low | The new risk can come up at any time of implementation and risk log can be updated as and when needed. With regards to elections impacting implementation, Mr Alcindor (UNDP co-chair) proposed controlled disbursement of funds. Additionally, they can also consider direct payments to ensure funds do not sit in the account for more than 6 months. | PCU, MEECC MACCE | LPAC: 10thSeptember 2019 New risk identified in workshop Inception Workshop: 28th February 2020 New risk discussed in workshop 18th June 2021 On 5th June 2020, the Electoral Commission set dates for the 2020 presidential election for October 22, 23 and 24. 2020 presidential election -Seychelles Nation President Danny Faure proclaimed the dissolution of the National Assembly on 6th August 2020, President Faure proclaims the dissolution of the National Assembly - News - State House Seychelles ¦ Office of the President This has resulted in delays in review of documents (e.g. PA bill), delays in taking decisions prior to elections, restrictions on public consultation during the campaign period (Sep/Oct), possible Government restructuring post elections. 11th August 2020, The Electoral Commission of Seychelles confirmed October 22 to 24 as the island nation's dates for both presidential and legislative elections. Presidential, legislative election dates in Seychelles confirmed: Oct 22-24 - Seychelles News Agency The Seychelles Presidential and legislative election was held on 22nd to 24th October 2020 with ‘Linyon Demokratik Seselwa’ (LDS) being the majority winner in the legislative and a new president, Wavel Ramkalawan, being elected. In November 2020, the new cabinet of Ministers was announced, with Mr. Flavien Joubert being the Minister of the new Agriculture, Climate Change and Environment. The new President announced first phase of restructuring on 1st February 2021 President Ramkalawan announced first phase of Government restructuring - News - State House Seychelles ¦ Office of the President Changes to Seychelles National Parks Authority as follows ‘The National Botanical Gardens Foundation (NBGF) and Seychelles National Parks Authority (SNPA) will become the Seychelles Parks and Gardens Authority (SPGA) and a new commercial board will be appointed’. Project implementation for outcome 1.2 has significantly slowed down as new management is confirmed. The new CEO for the Authority commenced work in June 2021. The Seychelles Agricultural Agency (SAA) and National Biosecurity Agency will be phased out and will be merged within the Department of Agriculture as two divisions. Impact on project implementation have been minimum as PCU had already taken responsibility for SAA activities. The president also announced changes to NISTI as follows ‘The National Institute of Science Technology and Innovation (NISTI) will be restructured’. Impact on R2R project activities is still not clear though emails have been forwarded to all concerned for way forward. MTR 14/09/22: New government now almost 2 years in place and cannot be longer considered a “risk”. Remove? |
| 12 | The project may restrict access to the use of natural resources for certain groups, possibly and private landowners in upper elevation forest areas. Finally, the project will work to designate selected Key Biodiversity Areas as official protected areas; this could limit the ability of some private landowners who own land within the KBAs in terms of developing the land and/or in some uses of natural resources. | Social Terrestrial | I = 2 P = 3 Moderate | Regarding KBA sites, in those cases where at least part of the site is privately owned, any designation of a KBA site as an official protected area will not go forward until the Government of Seychelles has approved a compensation mechanism for private landowners; the Government is already working on a policy in this regard, and the proposed project will assist it in doing so. In addition, as described under Output 1.1.3, the first step in proposing any KBA sites for designation will be outreach and consultations with relevant private landowners. | MEECC MACCE SNPA | Project Document This risk is expected to be mitigated by Government policies that address land and natural resources usage rights LPAC: 10thSeptember 2019 PS Decomarmond (NPD) had a query over poverty criteria. Mr Alcindor (UNDP co-chair) pointed out that poverty studies done previously by UNDP and National Bureau of Statistics identified that poorest households consisted mostly of farmers and fishermen. It was felt there is better language that could be used e.g. “financially precarious”. Ms Sims (SNPA Chair) advised that from MSP context, there are other users who are affected who have not been singled out (land owners etc). Inception: 28th February 2020 It was agreed that the Terrestrial and Marine risks should be separated where applicable. MTR 14/09/22: Same as Risk 7. Remove here? Raise level to High? But what consequences may that have? |
| 13 | The project may restrict access to the use of natural resources for certain groups, possibly including fishermen. For example, the project will help to strengthen the management of existing Marine Protected Areas (MPAs), possibly including increased enforcement of restrictions on fishing in these areas. | Social Marine | I = 2 P = 3 Moderate | In existing MPAs, the project will focus on strengthening the enforcement of existing regulations, rather than imposing new regulations. It is not anticipated that the strengthening of the existing network of MPAs will have any major negative impacts on fishermen's livelihoods, while it will have a major positive impact on the country's marine conservation efforts by showing that the Seychelles is not only interested in numbers like percentage of EEZ under protected status but also in the effectiveness of these protection designations. Most of the country’s MPAs have long been established and illegal fishing activities are already controlled, what the project will be doing will be increasing the level of compliance and increasing the level of respect of MPA stakeholders for these areas. In addition, the changes in access to marine resources are intended to increase the sustainability of these assets and produce a positive impact on livelihoods over the long-term. For example, the rehabilitation activities done by the project in coastal and mountain areas will reduce the level of sedimentation and improve health of coral reefs and coral reef associated fisheries, thereby producing net benefits for fishermen. The biodiversity surveys planned will also identify the characteristics of important/critical nursery areas for coral reef associated fish and make suggestions to improve their management, which will further benefit fishermen. The project approach is also in line with voluntary measures that fishermen on Praslin are taking to improve management of fisheries resources around this island; the project ensure effective consultations with fishers during implementation by having someone from the fishing industry on the project's steering committee. The project can also collaborate with on-going efforts to re-introduce Honorary Wardens (who can be fishermen) and how fishermen can otherwise be more actively involved in the management of natural marine resources. Finally, it is important to note that most fishermen are law abiding and would welcome better enforcement so that they do not lose out to those fishermen who do not follow the law. During the 1st year of project implementation, a Livelihoods Action Plan for fishermen will be developed for implementation during the remaining period of project implementation. | MEECC MACCE, SNPA | Project Document This risk is expected to be mitigated by Government policies that address land and natural resources usage rights LPAC: 10thSeptember 2019 PS Decomarmond (NPD) had a query over poverty criteria. Mr Alcindor (UNDP co-chair) pointed out that poverty studies done previously by UNDP and National Bureau of Statistics identified that poorest households consisted mostly of farmers and fishermen. It was felt there is better language that could be used e.g. “financially precarious”. Ms Sims (SNPA Chair) advised that from MSP context, there are other users who are affected who have not been singled out (land owners etc). Inception: 28th February 2020 It was agreed that the Terrestrial and Marine risks should be separated where applicable. MTR 14/09/22: Same as Risk 8? No work with fishers. Remove? |
| 14 | Alternative livelihoods in agriculture and forestry to be promoted by the project could reproduce existing discriminations against women. | Social Marine/ Terrestrial | Low | During the development of the project, a Gender Analysis was undertaken, and a Gender Mainstreaming Plan was prepared based on that analysis. That Plan (in Annex N of the Prodoc), outlines the management measures that will be undertaken to address this risk and leverage it for multiple benefits. Opportunities for improving the lives of women and girls were identified in the Gender Analysis and built into the design of the project. With regard to the participation of women (and youth) in agriculture and forestry, proposed actions include: · Establish 50/50 policy for training and provide women friendly training facilities to build capacities for implementation and enforcement of sustainable forest and agriculture management · Ensure effective participation of women in resource management committees of target communities · Active involvement of women & youth in both trainings & extension activities · Target participation of 50% women / 15-30% youth in forestry and agriculture activities For full details of those measures, please see Annex N. | PCU SAA, MEECC MACCE | Project Document This risk is expected to be mitigated by project gender mainstreaming activities LPAC: 10thSeptember 2019 PS Decomarmond (NPD) queried on “discrimination against women”. Mr Alcindor (UNDP co-chair) pointed out that the ProDoc has gone through a series of stakeholder consultation and there were no objections to the wording. A gender analysis was also conducted and has been annexed with the ProDoc (to share with LPAC). It was felt that this needs to be reworded either before being submitted to GEF or at the Inception workshop. PS Decomarmond (NPD) felt that discrimination is very harsh language. Inception: 28th February 2020 It was agreed that the Terrestrial and Marine risks should be separated where applicable. It was noted that at the LPAC this risk was to be removed, as it does not apply to Seychelles, since there is no discrimination against women all are welcome to do the activity, but a precedence in that historically these sections were taken up by men. It was clarified that the risk maybe that the project will promoting jobs that are traditionally male orientated like foresters and farmers. It was recommended that there is a need to empower young men and women to take up these jobs. It was therefore suggested that the risk should be lowered and monitored. MTR 14/09/22: Risk indeed low, focus and monitoring shifted to Youth? Mitigation action may the development of women and yout policy? |
| 15 | NEW RISK The disbursement of funds will be done only after 80% expenditure of previous tranche. This was identified as a risk whereby disbursement of the next tranche is usually late and partners run out of funds for activities. | Financial | Moderate (elevate? No more DRDP) | The project has recommended that Grant agreements will be organised instead of Memorandum of Understanding (MOU) in order to have better control on budget to ensure 80% delivery at the end of each quarter. During the negotiation can be held n possibility of lowering the % down to 65% , similar to past projects with TRASS, which has mitigated the issue. Stakeholders were reminded that the same problem of disbursement from past projects, such as Protected Area, was due to how the budget was allocated per partner, whether all partners fall under one combined, which is not ideal or individually. It was recommended that all responsible partners should have their own budget registered in separate budget lines in the combined budget. | PCU, MEECC MACCE | Inception: 28th February 2020 New risk identified in workshop. PCU has revised the overall budget for all responsible partners to be registered on separate budget lines in the combined budget and will liaise with partners for % expenditure when finalising Grant Agreements. 18th June 2021 Following audit of projects at PCU and a downgrade to Medium Risk for project implementation and to comply with IPSAS principles, on 16th February 2021, all responsible partners were informed that PCU cannot organize Request for Direct Payment (RDP) to partners when they reach 80% expenditure during the quarter and it will now be part of the overall project’s cash advance. Should PCU, or a responsible partner, not spend their cash advance, there will be consequences on timeline for funds request and allocation to those who have spent 80%. MTR 14/09/22: Risk and challenge still there. May need to distinguish between the different RPs. Unclear how this may be under new PDCS SOPS? |
| 16 | NEW RISK Capacity issues to implement the activities | Institution and Capacity | Moderate | Specifically, for aquatic monitoring systems and outcome 3 whereby there are so many partners involved, the capacity issues and to ensure that it is sustainable. It was also pointed out that in this project there are many partners doing one component, such as component 2, it is important that it is properly organised so that there is clarity on roles and responsibilities. The Project Steering Committee should be used as a guiding body | PCU, MEECC MACCE BERI, MCSS, SNPA | Inception: 28th February 2020 New risk identified in workshop 18th June 2021 Additional capacity issues have been identified as Farmers Associations in general have limited experience in project development and implementation and requires much assistance in such. Consultants undertaking PPG stage should have carried out capacity assessment of Low Value Grants beneficiaries before allocating financing for activities that they cannot implement. This is significant as achievement of 3 indicators are tied to their activities. Technical Advisor and Project Manager giving additional support, diverting attention from their primary duties. Focal Point for R2R Project at SNPA resigned on 18th September 2020. SNPA has not recruited new staff to replace the acting Focal Point for R2R Project following her resignation. Capacity of SNPA to deliver on project activities has significantly reduced and it is unclear how the merger with NBGF will impact operations. On a positive note, the new CEO started in June 2021 and project expects positive implementation. MTR 14/09/22: Capacity challenges are still there, also with SPGA, though improvements are noted. The Farmers Associations also still have capacities issues, and their implementation roles are restricted, though coordination is sought and support from project provided. Capacity challenges and interest from DOE also apparent, e.g. with the Conservation and Biodiversity Department, LWMA and WEP. |
| 17 | NEW RISK Global Corona Virus Pandemic - Seychelles reported its first positive case of the pandemic CORONA Virus on 14th March 2020. On 17th March 2020, the MEECC Operations circular on the COVID-19 was released with a list of restrictions that affect the projects progress to achieve targets Since then, further measures have been imposed by the Government of Seychelles as the number of confirmed cases rose to 10 (http://www.statehouse.gov.sc/news/4789/speech-by-president-danny-faure-on-the-covid-19-situation). | Operational | High | The project is consulting with partners to revise the 2020 work plan and budget. The crisis has already started to impact on partners ability to meet co financing commitments, especially those relying on tourism like Seychelles National Parks Authority and Marine Conservation Society of Seychelles. The project tentatively predicts the impact of COVID 19 will delay project implementation for at least 6-8 months. It is recommend that one-year extension is considered at Mid Term Evaluation stage. The project with its numerous outputs supporting agriculture and agro-forestry, and as such food security, is now more than ever relevant at this time of crisis especially as we do not know how long this pandemic will last or its future consequences. Revision of project - Reallocation and mobilization of resources: The recruitment of national consultants will be brought forward, and the activities on agriculture and agro forestry to support food security. - Temporary suspension of certain projects or activities: The project has pushed back large scale consultation process, purchasing of overseas equipment orders and activities relating to recruitment of international consultants. - Rapid development of new bankable projects or activities - Donor/partner relations management: The GEF focal point to seek clarification from the Secretariat given that GEF’s Policy is to longer grant extensions. - Virtual and remote methods for working and implementation: Activities related work that can be carried out remotely has been brought forward. - Ensure a gender-responsive approach and engagement of women: Project will move forward in recruiting the local Gender expert. - Regular risk monitoring and assessment of changing local context: Project will update risk log on quarterly basis to undertake mitigation measures | All Partners | Updated April 2020- Inception Report Since then, further measures have been imposed by the Government of Seychelles as the number of confirmed cases rose to 10 (http://www.statehouse.gov.sc/news/4789/speech-by-president-danny-faure-on-the-covid-19-situation). The R2R current Project Risk log will be submitted to UNDP for uploading as part of the Inception Report. 18th June 2021 Seychelles reported its first positive case of the pandemic CORONA Virus on 14th March 2020. On 17th March 2020, the MEECC Operations circular on the COVID-19 restrictions was released. Below is a list of restrictions that will affect the projects progress to achieve targets identified in the inception workshop. All public meetings and theme days has been postponed. Internal and external face to face meetings should be minimized as much as possible to ensure minimum exposure (1m distance) in a confined space and restricted to those of emergency nature only). Communications can be done via email, WhatsApp, mobile phones, skype etc… Meetings at PCU restricted to no more than 6 people in the meeting room to ensure minimum exposure (1m distance), with other joining via skype as feasible. Contact with the members of the public is minimised with all communication must be done through means of telephone, video call or email. Only cases of Urgent or Emergency site visits will be allowed. For any visits scheduled with other entities, liaise and check with Heads of Departments. Overseas leave and mission will not be approved at such time. On 6th April 2020, Seychelles registered its 11th case which was regarded at the time as a potential community transmission, at which point, more restrictions were imposed. This included limitation on outdoor movements (partial lock down). See facebook links for more restrictions https://www.facebook.com/mohseychellesofficial/photos/a.666791056855362/1367314713469656 https://www.facebook.com/mohseychellesofficial/photos/a.666791056855362/1367314903469637 https://www.facebook.com/mohseychellesofficial/photos/a.666791056855362/1367314976802963 On 3rd May 2020, the schedule of opening of establishments and activities for May and June 2020 was released and followed by a Covid-19 (coronavirus disease) public health (infectious diseases) regulations orders. See link http://www.health.gov.sc/wp-content/uploads/schedule-of-opening-03-May-2020.pdf http://www.health.gov.sc/wp-content/uploads/Infectious-Disease-Prohibition-of-Public-Assemblies-03-May-2020.pdf http://www.health.gov.sc/wp-content/uploads/Activities-Allowed-June-2020.pdf On 29th December 2020, Seychelles President announced that evidence have shown that COVID-19 is being transmitting in our community. New measures are being taken by the Commissioner of Public Health, such as Prohibition of public assemblies and indoor public assemblies Restrict the opening and closing hours of offices establishments Restrict the movement of persons by vehicles and vessels On 30th December 2020, Seychelles COVID-19 active case account was 44, with 21 Seychellois and indication of an exponential increase. Since then, increases in active/confirmed case numbers has resulted in more severe measures in place to contain the pandemic. See Home - Ministry of Health - Seychelles. In March 2021, Seychelles started undertaking a vigorous vaccination campaign to obtain herd immunity. As of 14 June 2021, a total of 137,196 vaccine doses have been administered. Never the less, the cumulative number of cases remains high. Up to the 15th of June 2021 cumulative total of 14,123, active cases is at 1,562 and a total of 55 COVID-19 related deaths recorded. The pandemic has impacted on project implementation as follows: Communication with partners proved difficult at times due to limitation in internet connections when working from home, issues with email service providers, unavailability of partners. Most partners are formulating and implementing new Covid-19 strategic plans in order to sustain their organisations and thus project activities were not considered as priority to them. Some partners did not resume full time working hours or were sick which created delays in processing of documents and organizing activities. As a gender issue, female project partners with children were affected as the schools were closed or opened on rotation basis as per DOH guidelines. The care and home schooling of the children fell primarily on the mothers. The project has pushed back large-scale consultation process in favor of zoom meetings, public review of project outputs through individual consultation via email and telephone, google questionnaires, District Administration (KBA, strategies) however restrictions on organising face-to-face meetings & on number of partners in the meeting room has proven difficult for partners/stakeholders and public that are not technologically inclined. Restrictions in organising outdoor activities such as site visit with partners or watershed community meetings and activities halted and delayed project activities. Restrictions in organising capacity building to achieve indicators have halted or delayed. Project has organised Standard Operation Procedures and guidelines (SOP) for approval by DOH prior to organising activities however only “important” trainings (based on DoH criteria) have been approved to proceed. Overseas travel restrictions have affected recruitment of international consultants which are identified for consultancies to kick start some key activities under the project e.g. M&E System, Gender and Youth Action Plan. Project Steering Committee Members have approved for local consultants to be recruited instead with significant savings to the project. The fluctuations in the foreign exchange rates has impacted on project team’s ability to prepare realistic workplans and budgets for implementation. Seychelles Rupee ¦ 2008-2021 Data ¦ 2022-2023 Forecast ¦ Quote ¦ Chart ¦ Historical (tradingeconomics.com) (June 2020 1USD=SCR17, December 2020 1USD=SCR20, April 2021 1USD=SCR12, June 2021 1USD=SCR 15) The crisis has impacted on partners ability to meet co-financing commitments, especially those relying on tourism and CSR e.g. Seychelles National Parks Authority and Marine Conservation Society of Seychelles. The impact was raised at steering committee meeting, whereby partners were advised to report in the Progress Reports and Project Implementation Reports The project tentatively predicts the impact of COVID 19 has delayed project implementation for at least 6-8 months. Potential of extension to be considered by the Mid Term Evaluation consultant. MTR 14/09/22: Corona is still an issue, e.g. during visist of MTR consultant, several staff tested positive and had to quarantine. The MTR consultant also stayed mostly at home in his 2nd week, because of his close contact with positive tested cases, and conducted on-line interviews MTR, 14/09/22: At this time no “No cost extension”. Too early, premature. Not even midway project. Project doing well in catching up. Consider no-cost extension later, e.g. after PIR 2023 or 2024 (better still). That good review, + discussion, including PSC decision, + stakeholders including UNDP, GEF FP and RTA> |

|  | NEW RISK (RTA): Slow delivery: This represents a risk to successful implementation, especially since the project has to make up for delays in activities to achieve end of project targets |  | Develop a Delivery Acceleration Plan approved by the IP Ministry and PCU. |
| --- | --- | --- | --- |
|  | NEW RISK (Project Team): Transition PCU – PDCS may impact project implementation, especially Procurement |  | Transition not yet finalized and new SOPs and instructions to e.g. change procurement through the Procurement Oversight Unit not yet issued to Project. Project team foresees delays, but government staff ensures that with the right preparation this will not be the case. Transition time is important to discuss and anticipate changes in procurement and financing. |
|  | NEW RISK (Project Team): UNDP’s new role vis-à-vis PDCS and Projects will mean less involvement, including less assistance in procurement and monitoring. This may affect project implementation |  | UNDP will indeed be less involved in project implementation and focus only on oversight. With new SOPs for the PDCS in place this is supped to be overcome. |

## Annex VIII: Detailed Co-financing commitments

| Sources of Co-financing | Name of Co-financier | Type of Co-financing | Co-financing amount confirmed at CEO Endorsement / Approval | Materialized co-financing as of MTR |
| --- | --- | --- | --- | --- |
| Government | Ministry of Environment, Energy and Climate Change (MEECC) | Grants | 3,778,857 | 1,783,999 |
| Government | Ministry of Environment, Energy and Climate Change (MEECC) | In Kind | 57,857 | 255,659 |
| Government | Seychelles National Park Authority (SNPA) | Grants | 9,749,571 | 1,055,446 |
| Government | Seychelles Agricultural Agency (SAA) | Grants | 7,950,000 | 3,180,000 |
| CSO | University of Seychelles (UniSey) | Grants | 601,429 | 89,369 |
| CSO | University of Seychelles (UniSey) | In Kind | 278,571 | 18,720 |
| GEF Agency | UNDP: EU GCCA+ project (Component B) | Grants | 853,000 | 636,000 |
| GEF Agency | UNDP: COMESA project | Grants | 465,000 | 174,316 |
| GEF Agency | UNDP: Adaptation Fund project on Coral Reef Restoration | Grants | 1,500,000 | 200,000 |
| GEF Agency | UNDP: TRAC funding | Grants | 75,000 | 0 |
| GEF Agency | UNDP | In Kind | 75,000 | 20,000 |
| CSO | Marine Conservation Society Seychelles (MCSS) | Grants | 772,000 | 27,879 |
| CSO | Terrestrial Restoration Action Society of Seychelles (TRASS) | Grants | 27,857 | 466,934 |
| CSO | Terrestrial Restoration Action Society of Seychelles (TRASS) | In Kind | 1,095,804 | 26,105 |
| Donor Agency | IUCN-LEAP (Nature Seychelles) | Grants | (not set) | 24,331 |
| Recipient | MACCE- Agriculture Montagne Posse Agroforestry | Public Investment | (not set) | 0 |
| Donor Agency | IAEA SEY 5011 | Grants | (not set) | 337,998 |
| Donor Agency | IAEA SEY 5010 | Grants | (not set) | 203,433 |
| Donor Agency | INCIPE | Grants | (not set) | 12,248 |
| CSO | MCSS leverage counterpart funding- Apportioned administrative support | In Kind | (not set) | 154,146 |
| Donor Agency | FAO: TCP/SEY/3704 | Grants | (not set) | 194,510 |
| Donor Agency | SeyCATT | Grants | (not set) | 44,250 |
| Donor Agency | IAEA:SEY5013 | Grants | (not set) | 32,181 |
| Donor Agency | GERMINATION II | Grants | (not set) | 2,663 |
| Donor Agency | FED FOOD Sec Semence | Grants | (not set) | 3,978 |
| Donor Agency | TCP/SEY/3802 | Grants | (not set) | 260,408 |
| ∑ |  |  | 27,279,946 | 9,204,574 |
|  |  |  |  | 33% |

## Annex IX: Signed UNEG Code of Conduct form

## Annex X: Audit Trail for comments received

Comments received from 03/10/2022 to 11/10/2022 from the Midterm Review of “A Ridge to Reef Approach for the Integrated Management of Marine, Coastal and Terrestrial Ecosystems in the Seychelles” (PIMS 5502)

| Author | # | Para No./ location | Comment/Feedback on the draft MTR report | MTR team response and actions taken |
| --- | --- | --- | --- | --- |
| UNDP RTA | 1 | P.11, 4th Para | “No cost extension” never really comes at “no cost”; there are always costs involved, e.g. from extra efforts an time of staff, UNDP, administration, etc. Project should consider this and be careful to request such “no cost extension”. | The recommendation was already not to request a “no cost extension” at this point in time, as it is considered premature. A further qualification of the “no cost” nature has been added in the text (P.11, Para 4; P.12, Para 1), and further references in report are to “extension” instead of “no cost extension” |
|  | 2 | P33. Recommendations | Add further responsibilities and timelines to the recommendations | Done for all recommendations |
|  | 3 | P.26, 3rd Para | Clarify the changing role of UNDP (not mere “stepping back”), as mentioned in several areas of the report. Some extra text and explanation to add and specify further UNDP’s oversight role. | Paragraph amended |
| UNDP Country Office (during presentations of MTR Draft) | 4 | P. 11, 4th Para | Include justification for possible “no cost extension” | Already included in P. 11, 4th Para. No change. |
|  | 5 | P. 35, Recommendation G1 | The “disbursement challenge” has been discussed with the projects, especially the AF Coral Reef Restoration Project. Some examples for solutions provided. Need for further discussion and finding of real solutions. | This is further highlighted (P. 24, Para 1) and timeline for finding solution included in recommendation G.1. |
|  | 6 |  | - Project to develop Gender & Youth Policy? | This has changed to a “Project Strategy and Action Plan on Gender and Youth” (P.20, Para 2; Recommendation F.1) |
| UNDP (written comments) | 7 | P. 8, Para 1 | Formerly the Ministry of Environment Energy and Climate Change (MEECC) as at the time of project signature it was MEECC. | Reference to MEECC included |
|  | 8 | P. 21, Para 3. | Recommendation on building institutional memory at district level and capacity through digitalization of records/Website could be an element for consideration. | Although relevant, not included as project recommendation at this time (outside of scope and budget of Project) |
|  | 9 | P.21, Para 6 | It may be worth commenting that SPGA too has gone through a period of transition | Qualification on SPGA added. |
|  | 10 | P. 22, Para 1 | Perhaps to quantify and qualify the statement. | Have added sentence on PCU having to adapt its strategies. |
|  | 11 | P.23, 2nd Para | An interim solution has been proposed | Note added. |
|  | 12 | P. 26, Para 3 | Incorrect to state that UNDP is not involved in full project monitoring. | Paragraph amended |
|  | 13 | P.28, Para 4. | Budgetary implications on the project may be felt with inflation and "recessionary" trends hampering implementation of activities. Co-financing may be affected as well. | Included statement in “global economic threats”. |
|  | 14 | P.28, Para 5. | Don’t know if it is worth mentioning the deal with Adamantine on oil exploration as an example of economic gain over sustainability? | Good example, but not included in report, as no direct bearing on the R2R project. |
|  | 15 | P.30, Risk Log, Risk 4 | Since project is meant to cover coastal ecosystems in a whole island approach as well. Suggest revision to Low Risk P=2 I=2 | Kept the Risk and its rating (“Moderate”) |
|  | 16 | P30, Risk Log, Risk 11 | Would recommend leaving it as a risk in the event that decision making is hampered in the final year of project implementation due to elections. This has been a lesson learned from past project | Kept the Risk and qualified its status |
|  | 17 | P. 33 Recommendation A2 | Suggested Edit: Revisit/Assess the need for project extension in the 2024 PIR if the delays in implementation caused by COVID-19 have not been mitigated | Edited |
|  | 18 | P.35, Recommendation G.2 | Should the recommendation focus on Periodic Capacity Assessments such as HACT or other and/ document constraints where applicable. | Possible Capacity Assessments added (for new partners and/or partners that have undergone a significant transition) |
|  | 19 | Throughout | Typos (+tense + grammar) | Edited throughout document. Thank you. |
| Project Team | 20 | Results Framework | Record in Results Framework the recommended change in Agroforestry sites and shift from Grand Police to Caiman for new watershed area | Change in Agroforestry site included in Results Framework (P.16, Indicator 10; Annex VI, Indicator 10). Grand Police not specifically mentioned in Indicator, but comment added (P.15, Indicator 7; Annex VI, Indicator 7). |
|  | 21 | Page 13, Results Frame-work | Comments to Results Framework. E.g. (Sub-) Indicator Numbers, e.g. 1.b.2, 1.b.3, 1.e. Some further qualifications to be inserted, e.g. Indicator 11 (revised targets for tCO2eq avoided) and comments Indicator 12 (delayed but now on track). | The Results Framework in the MTR report follows the Results Framework as adopted at the Inception Workshop and documented in the Inception Report. Some number have been re-instated for ease of recognition and sequencing. Despite a comment, 1e is still considered removed, as this is documented in the Inception Report. All other comments (e.g. for indicators 11 and 12) adjusted |
|  | 22 | P. 17, Last but 1 Para | On the old Sate Land & Rivers Act and its separation. Comment: “This should be ‘State Lands Management Bills’. The Rivers and Waters will fall into forest and other trees bill and the integrated catchment act” | Edited, as per the explanation of the legal consultants |
|  | 23 | P. 17, Last but 1 Para | Confirm location of “Anse Saline” | Corrected to Baie Laraie (La Saline / Anse Saline), as appearing in the “Report on evidence-based rehabilitation of the coastal forest selected sites on Curieuse” from 01/06/22. |
|  | 24 | P. 18, 1st Para. | Sentence should be rephrased as it is false. | Sentence amended and note added. Next sentence on appearance of the area also amended, as some other reports were consulted. |
|  | 25 | P. 18, 1st Para. | Clarify the word “attention”. | Sentence changed and the word “monitor” now central. |
|  | 26 | P. 18, 3rd Para. | KBAs: The Nomination files were not submitted and are still being worked on. DOE wanted to submit the current deliverables to government before nomination files to confirm commitment of current GOS. | Sentence adjusted |
|  | 27 | P. 19, para 1. | Rehabilitated areas: “Funds not allocated for maintenance”. | Sentence adjusted, “maintenance” removed |
|  | 28 | p. 19, Last Para | “Grateful on suggestion of which recommendation in particular” (from the Gap Analysis) | Suggestions given, specifically around amending / influencing the agriculture legislative and policy framework. Also included in recommendation E.1 |
|  | 29 | p. 19, 1st Para | Need to include shift to other sites for agroforestry rehabilitation- indicator 10 in logical framework | Included in Recommendation A.3 and D.2 |
|  | 30 | p. 21, Last Para | There is a need to reword this paragraph. | Paragraph not reworded but (slightly) amended, and main message remains (as recorded from the RPs). |
|  | 31 | p. 22, 1st Para | We have been notified that these post will be recruited in 2023 &2024 due to budget constraints so the support to the project delayed even minimal. | Included in text |
|  | 32 | P. 22, 1st Para | A GEF Project under World Bank mentioned significant delays on their side because of going through GOS Procurement Oversight Unit. | Note included |
|  | 33 | P. 19 1st Para | The PDCU should be fully staffed before project starts using new SOP? | Sentence adjusted |
|  | 34 | P.23, 3rd Para | The example is not correct. | Example adjusted |
|  | 35 | P. 26, 2nd Para | Prefer another partner as example. | Another partner used as example in text |
|  | 36 | P. 33: Recommendations | Recommendations: Provide Timeline to action if possible | Timelines provided |
|  | 36 | P. 33, Rec. A.2 | To add UNDP, Project Steering Committee, Government | UNDP, PSC, Government added |

## Annex XI: Signed MTR final report clearance form

There is some confusion about the correct total amount of co-financing, this will be further detailed later in this MTR report

There has also been confusion about the project end date. This was recorded differently in the different documents (CEO approval, draft project Documents and PIRs, and also the records from PIMS). The signed Project Document mentions an end date of December 2025, which for the 72 months project signed and starting in January 2020 should be correct. This should be corrected in PIMS (end date of January 2025) and subsequent PIRs, as was already stipulated in the PIR of 2022 as well.

http://www.health.gov.sc/index.php/2022/08/16/covid-19-update-16-august-2022/

“Evaluation planning and implementation during Covid-19”, March 2020.

But also the Watershed Management Plans as developed by consultants for the Watershed Committees participating in the Project

The reviewer has understood that this may not be common practice and difficult to change in PIMS. Nevertheless, because of the confusion and extra efforts needed during reporting, the reviewer still maintains to amend this.

This statement is contested by the project, as the project mentions that the SPGA was involved in the selection of contractor and some of the monitoring, although the “SPGA support was low due to capacity and staff limitations” (staff limitations on Curieuse  is recognized by SPGA).

“Sedimentology of Coastal Deposits in the Seychelles Islands—Evidence of the Indian Ocean Tsunami 2004”. Nentwig et al., 2014.

Minutes of Project Steering Committee No. 3 of 21/01/2021.

Though another GEF Project has mentioned significant delays of going through the POU,  as reported by the R2R Project (not recorded by the reviewer).

For now partners are encouraged to improve Annual Work Planning esp in Q1 to ensure 80% thresholds can be met.

Already practiced in some instances

Also already practiced to some extent, e.g on Praslin

Already practiced in some instances