Final Evaluation of the Regional Project on “SDG Climate Facility: Climate Action for Human Security”

United Nations Development Programme – UNDP RBAS

July 30, 2024

Revised in September 2024

Prepared by: Arab World for Research and Development

# Acknowledgements

The Evaluation Team is grateful for UNDP-RBAS team for their support and guidance. The team would also like to thank UNDP-RBAS members for providing time and contributions to the evaluation, as well as supporting access to contacts and important data and documentation. Gratitude is also extended to the project partners, UNDP country offices and local partners who shared their insights and time with us.

# Project and Evaluation Information Details

#### Project Information

| Project title | SDG-Climate Facility: Climate Action for Human Security |  |
| --- | --- | --- |
| Atlas ID | Award: 00111749 – Outputs: 00113467 – 00122626 – 00122627 |  |
| Corporate outcome and output | Outcome 1 (Regional Programme Document (2018-2021)): Accelerate structural transformation of productive capacities in a sustainable and inclusive manner. Output 1.3.1 (Regional Programme Document (2018-2021)): Risk informed development policies and plans that incorporate integrated solutions to reduced disaster risk, enable climate change adaptation and mitigation. Outcome 3 (Regional Programme Document (2022-2025): Impact of climate change reduced, sound water management promoted, and access to sustainable energy improved. Output 3.1 (Regional Programme Document (2022-2025)): Public and private investment mechanisms mobilized for biodiversity, water, oceans, and climate solutions |  |
| Country | Broader Arab States. Resilience grants: Jordan, Egypt, Tunisia, Iraq, Palestine, and Yemen |  |
| Region | Arab States |  |
| Date project document signed | 03 Dec 2018 |  |
| Project dates | Start | Planned end |
|  | January 2019 | March 2024 |
| Total committed budget | 9,971,695 USD |  |
| Funding source | Sida – UNDP |  |
| Implementing party | UNDP |  |

#### Evaluation Information

| Evaluation type (project/ outcome/thematic/country programme, etc.) | Final Evaluation of the Regional Project: “SDG Climate Facility: Climate Action for Human Security” |  |
| --- | --- | --- |
| Final/midterm review/ other | Final |  |
| Period under evaluation | Start | End |
|  | January 2019 | March 2024 |
| Evaluators | Arab World for Research and Development (AWRAD) |  |
| Evaluator email address | awrad@awrad.org |  |
| Evaluation dates | Start | Planned Completion |
|  | January 2024 | July 2024 |

Contents

Acknowledgements	2

Project and Evaluation Information Details	3

Project Information	3

Evaluation Information	3

List of Acronyms	5

List of Tables	7

List of Figures	7

Executive Summary	8

1. Introduction	15

2. Evaluation Objectives, Approach and Methodology	18

3. Findings	23

4. Conclusions and Recommendations	66

Annexes (Attached in a Separate Document)	71

# List of Acronyms

| AA | Anticipatory Action |
| --- | --- |
| ACSAD | Arab Centre for Studies on Arid Zones and Dry Lands |
| ACSD | Arab Committee for Sustainable Development |
| AFEX | Arab Future Energy Index |
| AFSD | Arab Forum for Sustainable Development |
| AGIR | Arab Geographical Information Room |
| AIIB | Asian Infrastructure Investment Bank |
| AMWC | Arab Ministerial Water Council |
| AWC | Arab Water Council |
| AWRAD | Arab World for Research and Development |
| AWP | Annual Work Plan |
| CEBC | Clean Energy Business Council |
| CGIAR | Consortium of International Agricultural Research Centres |
| CIMA | Chartered Institute of Management Accountants |
| CNRS | National Council for Scientific Research |
| CoP | Community of Practice |
| COP | Conference of the Parties |
| CSO | Civil Society Organization |
| DRC | Desert Research Centre |
| DRR | Disaster Risk Reduction |
| EBRD | European Bank of Reconstruction and Development |
| EDF | Environment and Development Forum |
| EQ | Evaluation Question |
| ERRY | Enhanced Rural Resilience in Yemen |
| ET | Evaluation Team |
| FAO | Food and Agriculture Organization |
| FCDO | Foreign Commonwealth & Development Office |
| FDGs | Focus Group Discussions |
| GCC | Gulf Cooperation Council |
| GCF | Green Climate Fund |
| GEF | Global Environment Facility |
| GIS | Geographical Information System |
| IDPs | Internally Displaced Persons |
| IFRC | International Federation of Red Cross / Red Crescent Societies |
| IRCSF | Integrated Regional Climate Security Framework |
| JPO | Junior Professional Officer |
| JSB | Japanese Supplementary Budget |
| KfW | Kreditanstalt fur Wiederaufbau / Credit Institute for Reconstruction |
| KI | Key Informant |
| KII | Key Informant Interview |
| LAS | League of Arab States |
| LDCF | Least Developed Countries Fund |
| MENA | Middle East & North Africa |
| MIS | Management Information System |
| MSME | Micro, Small and Medium Enterprises |
| MSU | Management Support Unit |
| M&E | Monitoring and Evaluation |
| NAPs | National Adaptation Plans |
| NDC | Nationally Determined Contribution |
| NGO | Non-Governmental Organizations |
| OECD/DAC | Organisation for Economic Co-operation and Development/Development Assistance Committee |
| ODI | Overseas Development Institute |
| PB | Project Board |
| PENRA | Palestinian Energy and Natural Resources Authority |
| RCSN | Regional Climate Security Network |
| RHAS | Regional Hub for Arab States |
| RPD | Regional Programme Document |
| RPMT | Regional Programme Management Team |
| RSS | Royal Scientific Society |
| SDGs | Sustainable Development Goals |
| SDG-CF | SDG Climate Facility |
| Sida | Swedish International Development Cooperation Agency |
| ToC | Theory of Change |
| ToR | Terms of Reference |
| UAE | United Arab Emirates |
| UN | United Nations |
| UNDP | United Nations Development Programme |
| UNDRR | United Nations Office for Disaster Risk Reduction |
| UNEP FI | United Nations Environment Programme – Finance Initiative |
| UNESCO | United Nations Educational, Scientific and Cultural Organization |
| UNESCWA | United Nations Economic and Social Commission for Western Asia |
| UNFCCC | United Nations Framework Convention on Climate Change |
| UN HABITAT | United Nations Human Settlement Programme |
| UNHCR | United Nations High Commissioner for Refugees |
| UN OCHA | United Nations Office for the Coordination of Humanitarian Affairs |
| UN Women | The United Nations Entity for Gender Equality and the Empowerment of Women |
| WFP | World Food Programme |
| WtE | Waste to Energy |

# List of Tables

Table 1: Level of contribution of the resilience grants to beneficiaries lives	25

Table 2: Level of project achievement of sub-indicators under each outcome	35

Table 3: Views of UNDP country staff and partners on the achievements of the project results (N = 17);  figures in brackets in percentages	35

Table 4: Views of UNDP country staff and partners of project achievements at regional level (N = 17)	36

Table 5: Views of UNDP staff and partners of project contributions at country level (N = 17); figures in brackets in percentages	36

Table 6: Reported contribution of the projects to aspects of beneficiaries' lives (N = 42); figures in brackets in percentages	37

Table 7: Key supporting and constraining factors contributing to the results	38

Table 8: Number events SDG-CF organised and participated in	38

Table 9: Number of events by type	39

Table 10: Partner attendance at Steering Committee meetings	40

Table 11: Total beneficiaries disaggregated by gender Palestine solar pilot (sub-indicator xxx)*	43

Table 12: Beneficiaries reported contribution of the projects to equality between men and women (N = 42)	44

Table 13: Financial allocations across outputs and activities	48

Table 14: Analysis of the budget resources used to address climate issues in general directly	48

Table 15: Summary table of allocations of budget over project outcomes	50

Table 16: Summary table of the level of achievement indicators by outcome	50

Table 17: beneficiary answers to the question “the support/project will contribute to improving my/my family’s/my community’s living conditions in the long term”	58

# List of Figures

Figure 1: Rate of project participants who believe the project was…	24

Figure 2: Budget utilization rates over project period	49

# Executive Summary

Evaluation rationale: The United Nations Development Programme (UNDP) has commissioned the Arab World for Research and Development (AWRAD) to undertake a final evaluation of the project “SDG Climate Facility: Climate Action for Human Security Project”, hereafter referred to as the SDG Climate Facility Project, to assess the project performance and results and generate actionable recommendations and lessons learned for similar future projects. The project is a multi-partner, multi-year initiative, drawing on the expertise of key regional institutions, such as the League of Arab States (LAS), the Arab Water Council (AWC), with leading climate action United Nations (UN) Agencies such as UNDP, the United Nations Environmental Programme-Finance Initiative (UNEP FI), the United Nations Office for Disaster Risk Reduction (UNDRR), the World Food Programme (WFP), and the United Nations Human Settlements Programme (UN-Habitat) and funded by Swedish International Development Cooperation Agency (Sida).

The final evaluation aims to assess the relevance, coherence, efficiency, effectiveness, impact, and sustainability of the project and generate recommendations around them. In addition, the evaluation provides suggestions to develop lessons learned and good practices for implementing similar projects in the future. As this was designed as multi-partners project, it should assess the value added of joint implementation by UN and regional entities, including what worked and what could be done better.  Hence, it should be designed to assess the actual impact of the different types of implementation approaches used in the project. Such approaches were aimed to combine on-the-ground implementation in six countries in the region with the development and dissemination of knowledge products at the national, subregional, and regional levels, with the aim to influence the climate security agenda in the region.

Evaluation methodology: The evaluation team (ET) adopted a mixed-method and participatory approach, gathering and analysing quantitative and qualitative data from primary and secondary sources. Primary data was collected from key internal and external stakeholders, with a particular emphasis on engaging partners, policymakers, representatives from the private sector, and direct beneficiaries at the community level, allowing the ET to establish a deeper understanding of the project's impact on the climate and human security nexus of affected populations.  ET used a series of surveys to collect primary quantitative data from internal and external stakeholders across all countries involved, targeting 37 key stakeholders, of whom 17 completed the survey, resulting in a response rate of 46%. A beneficiary survey was also conducted with 42 beneficiaries (22 females, 20 males) of resilience grants to capture the impact of the grants on beneficiary lives. The ET also conducted interviews with 37 key informants, 10 interviews with multilateral regional institutions and UN agencies in the Arab region including LAS, AWC, UNEP-FI, UN-Habitat, UNDRR, WFP, CGIAR, Adelphi, and Sida. Nine interviews were conducted with the UNDP country offices, and four interviews were conducted with the UNDP-RBAS team. An additional 14 interviews were conducted with country-level actors and partners directly involved in the design and implementation of grant activities. Six focus group discussions were conducted with direct beneficiaries, local actors, and non-governmental organizations (NGOs) to understand their experience with project outcomes.

In addition, the ET conducted a systematic review of project documentation and examined other relevant key regional and national documents on climate change and human security. The team also reviewed specific project documents, including annual reports, work plans, and partnership agreements, to inform the design of evaluation tools and contrast findings with other primary data sources.

The evaluation encompasses the project's timeline from its initiation in January 2019 until March 31, 2024, accounting for the no-cost extension.  The project had an agreed no-cost extension until December 2023. The additional period, until March 31, 2024, is to make sure that the financial data and analysis are included in the report. The evaluation covered the Arab States, with a particular project outcome 3, under the UNDP responsibilities, focusing specifically on implementing on-the-ground solutions in Jordan, Egypt, Tunisia, Iraq, the State of Palestine, and Yemen. The evaluation covers all project outputs and outcomes.

The ET adhered to a human-rights-based approach across all the evaluation phases, ensuring inclusive and non-discriminatory engagement of key stakeholders, respecting the right of all relevant stakeholders to take part in the evaluation, as well as respecting the right of key stakeholders to express their opinions and viewpoints openly.  Gender and disability variables were explicitly incorporated in the study approach and tools. Wherever feasible, analysis of primary and secondary data was disaggregated by gender and disability. An intent to understand the gendered effects of the project was a key element in study design, integrating the insights and perspectives of female beneficiaries, males, and people with disabilities into the analysis.

The evaluation was conducted against the OECD criteria of relevance, coherence, effectiveness, efficiency, impact and sustainability. The ToR provided the key evaluation questions which were developed into a complete evaluation matrix to guide the development of data collection tools and analysis.

Main Findings: The following summarise the findings for each evaluation criteria.

Relevance: The project design aligns with UNDP commitments and the Sustainable Development Goals, presenting opportunities for future learning. While there is evidence of proper context analysis and identification of root causes, a complete Theory of Change (ToC) design is largely missing. In particular, the TOC did not clearly articulate core elements such as outputs, outcomes, impacts, and causality pathways critical for robust project development and monitoring.  An extensive consultative process was used in the project's design. Still, the design process lacked a designated pre-design assessment with a risk analysis to identify and evaluate potential risks and uncertainties in the regional and national context. Instead, the process relied on a review of existing literature, similar UN documents and consultative meetings, which proved insufficient to provide an in-depth understanding of the overall impact of the risks on resource allocations. The absence of a clearly structured ToC framework led to paradoxical results, such as flexibility for innovation and learning, while posing challenges in creating linkages between components. There is one reference to disability, aimed at ensuring non-discrimination. The original design was aligned with regional conditions, but there is no evidence of adjustments to the original design in response to the changes occurring over the project period. The project is highly relevant to the needs of communities and households. Despite a strong focus on women, the project had limited gender mainstreaming across all phases and activities. The regional and country teams exerted significant efforts to include women as partners and beneficiaries of the overall project and country grants.

Coherence: The project fostered extensive collaborative relationships at both regional, national and local levels, engaging local organizations and companies in sectors such as water management, agriculture, and green construction. This multi-partner approach facilitated the exploration of new systems and approaches, significantly benefiting the project's implementation and enhancing its alignment with national strategies and policies.

Effectiveness: Project activities achieved their expected outputs, but evidence of outcome achievement is limited. The envisioned SDG Climate Facility was not implemented, though most resilience grants successfully scaled up climate financing. While multiple knowledge products were produced to enhance cross-sectoral evidence, their late availability has – as yet - limited their intended influence. The lack of an active and integrated information-sharing platform hindered effective dissemination, though some information was available on partner-managed and new UNDP platforms. The project integrated the climate security nexus into regional discussion and awareness but has not yet shown clear evidence of impacting national or regional policies. Multiple partnerships characterized the program, with positive relationships between UNDP and partners but less effective collaboration among implementing partners at regional and national levels.

Efficiency: The implementation structures for the project are flat but geographically fragmented. UN partners reported that while their collaboration with UNDP was excellent, there was little facilitation by UNDP of cross-UN collaboration, which may have resulted in the strengthening of existing long-standing relationships between UN agencies over potentially new linkages with other UN partners involved in the project. The limited program coordination is also reflected in the lack of synergy in the follow-up of activities in one part of the program to understand their impact on regional policy change at another program level. Moreover, financial reimbursement systems did not embrace the efficiency of flexibility required for all partners, and decision-making processes, while generally very smooth, were challenged by limited communication and information-sharing at the overall level.  The M&E system needed an embedded learning process, limiting its ability to support efficient project management.

Impact: The project's positive indirect impacts were quite substantial, with strong sustainability elements, but with a limited and incidental linkage to the project objectives themselves. The project contributed to outputs, outcomes, and regional priorities, with beneficiaries reporting high confidence in the long-term benefits of the resilience grants. However, the intended impact has not yet been fully realized. Despite the cancellation of the SDG Climate Facility, there were positive direct results, including increased acceptance of climate security concepts and some limited regional policy integration. Substantial positive indirect impacts included aiding UN agencies in starting new climate-related initiatives and mobilizing significant funding for resilience projects.

Sustainability: At the regional level, sustainability prospects are mixed with more favourable prospects for multi-partner collaborative initiatives with strong collective ownership and less positive prospects where follow-up on results achieved was only moderate. At the local level, sustainability prospects are also mixed. They are impacted positively by strong project ownership, capacities, and resources, including the expansion of assets for beneficiaries, and negatively by weak ownership and limited integration of supporting services for female beneficiaries (childcare). There is evidence of continuing cultural and social resistance to the changing gender roles the project has engendered.

Conclusions

- Overall, the project’s design was innovative, in alignment with SDGs, yet in need of further articulation. The project vision and conceptual framing was pioneering, fully aligned to UNDP’s commitments to the SDGs, and intended to bring mutually reinforcing change through exchange of experience and building on lessons learned from implementation. However, the lack of a formal risk assessment during the design process gave staff a limited amount of preparedness to meet and mitigate emerging challenges. The utilization of diverse resources in a desk review on climate change, human security, gender assessments- while helpful in the project's design and accompanied by a consultative process, was not able to identify the needs and risks grounded in the current capacities and vulnerabilities of the region and its component countries.

- Evidence shows that women were core beneficiaries of the project; yet gender mainstreaming and inclusion was weakly achieved. The absence of a designated gender expertise at the design stage did not allow the design to take gender-mattering and women empowerment as integrative to the overall project and resilience grants, although opportunities for meetings of the CO’s were provided. As a result, the project placed great focus on including women in their activities to ensure that numerical targets were met.

- The effectiveness of implementation modalities was mixed. Collaborative partnerships added value to the overall project, but coordination mechanisms were not sufficiently able to fully capitalize on this approach's benefits. The limited integration of knowledge products into policy frameworks resulted partly from a limited focus on partnership building and multi-level dialogues. The multi-partner approach facilitated the integration of various initiatives, ensuring a comprehensive and effective response to climate security challenges. However, challenges in coordination and communication among partners were noted.

- While the project demonstrated complementarity at the local level, there were challenges in fully integrating and coordinating with other ongoing actions at the regional level. The integration of cross cutting issues in different country contexts has been well achieved and the project demonstrated strong coherence to UNDP’s corporate gender strategy and to the SDG’s selected. Overall, the project demonstrated coherence with UNDP's corporate gender strategy and the SDGs through its efforts to promote gender equality, women's empowerment, and address the interconnections between climate change, gender, and human security.

- Results achievement was overall effective, except for the cancellation of much of Outcome 1 activities. Overall, the levels of achievement of project results across activities and outputs were good but intended impact was sometimes weakened by late delivery of outputs. Moreover, implementation delays caused by the outbreak of the COVID-19 pandemic created inefficiencies over time. The project was granted a No Cost Extension to allow completion of activities.

- Management structures supported the achievement of project results. The flatness of the management structure created efficiencies which were, at times, challenged by the overlapping of executive and beneficiary roles and limited inclusion of civil society from the accountability framework. The non-hierarchical structure naturally leads to greater efficiencies in procedures, decision-making, and concentration of accountability. Moreover, there was a need for additional human resources to encompass the full range of competencies needed, including M&E, partnership management, and policy making.

- The project's M&E system was somewhat developed yet has some missing elements which undermined its efficiency in supporting project management and showcasing the true value of the project. The M&E system's ability to effectively and efficiently support project management was undermined by the lack of an embedded learning process, and also by the limited indicator definition, frequency of reporting, sources of verification, data collection, and dedicated staff.

- The communication and visibility strategy for the project knowledge products was well developed but cost-efficiency could have been improved. At the same time, implementation planning was efficient, and the results have justified how project resources have been allocated. The cost-efficiency of communication and advocacy work may have been improved with the involvement of UN agencies and CSOs as partners in advocacy for the project messages around the knowledge products. Implementation delays caused by the outbreak of the COVID pandemic created inefficiencies over time. The project was granted a No Cost Extension to allow completion of activities.

- Against this backdrop, the intended level of project impact was not sufficiently captured due to limitations regarding systematic evidence. There is some anecdotal evidence of direct impact, and evidence of substantial direct impact, which was not, however, proven to be directly linked to the project activities outlined in the projects Results Framework. While the extent of the impact was affected by internal and external factors, the intended level of impact has not been captured due to limitations in the M&E system as stipulated above. Limited evidence on impact suggests that the extent of impact is linked to four major factors:  implementation strategies, which were inadequate in terms of overall coordination for a project of such complexity, with so many implementing partners across multiple locations; weak community involvement and ownership; and limited funding.

- Prospects for the sustainability benefits of project are stronger at the country level, and more mixed at the regional level. Chances for sustaining project benefits are strongest where stakeholders have demonstrated increased capacity and ownership of project benefits and external funding has already been committed. Where project benefits require additional capacity and financial investments to be operationalizable, the chances of sustainability are quite weak. Several successes have been registered by the project in leveraging additional funds to sustain environmental and security benefits achieved at regional, national and sub national levels.

Recommendations

The recommendations below are informed by the conclusion that there is a need to continue support for the UNDP present efforts to protect investments already made and capitalize on lessons already learned.  The Evaluation Team argues that if the report’s recommendations were properly implemented, UNDP would be the appropriate mechanism for continuity. On the one hand, UNDP has historical experience and institutional comparative advantage as stated in other parts of the report. On the other hand, UNDP had accumulated rich experience during the past years with the SDG CF project and it would be more cost-effective to develop the SDG CF based on the recommendations rather than venturing into any other options. To guide future planning efforts that build upon the current project, AWRAD developed a series of action-oriented questions designed to prompt strategic thinking and drive meaningful outcomes.

| Recommendation # | Recommendation linkage to criteria | Recommendation for the use of |
| --- | --- | --- |
| 1 | Relevance, Sustainability | UNDP, Sida |
| 2 | Relevance, Effectiveness | UNDP, Sida |
| 3 | Relevance, Coherence, Sustainability | UNDP, Sida |
| 4 | Relevance, Coherence, Effectiveness Efficiency, Sustainability | UNDP, Sida |
| 5 | Relevance, Efficiency, Effectiveness | UNDP |
| 6 | Relevance, Coherence, Effectiveness, Efficiency and Sustainability | UNDP |
| 7 | Relevance, Coherence, Effectiveness, Efficiency and Sustainability | UNDP |
| 8 | Relevance, Coherence, Effectiveness, Efficiency and Sustainability | UNDP |
| 9 | Relevance, Coherence, Effectiveness and Impact | UNDP |
| 10 | Relevance, Effectiveness, Efficiency and Sustainability | UNDP |
| 11 | Effectiveness, and Efficiency | UNDP |

- Conclusions # 1, 5, and 8: Clarify/confirm overall project objectives and anticipated results at the output, outcome and impact levels. Using the project goal as a starting point, undertake a ToC process with stakeholders, working out at each level the pre-conditions needed for achieving the results anticipated (do you need more awareness, more knowledge, more access to finance, more capacity, more political will? How will you get it? How will you measure it?). Develop results chains which articulate clearly what is needed to get from inputs to outputs to outcomes, and then map the horizontal linkages between the results chains to articulate how all project elements can be mutually supporting to help align the project with other actors working on similar issues, and better identify areas of complementarity and collaboration.  Such a process will support chances of sustainability.

- Conclusions # 1, and 2: Bring in senior gender expertise to the ToC process considering that gender mainstreaming and inclusiveness is part of the package. Undertake a rapid gender audit of the resilience grants to identify the methodologies employed by implementing partners in implementing gender mainstreaming in the grants. This audit should consider the lived realities of men and women in the private and public sphere at sub national levels and identify points of entry for gender mainstreaming.  Audit results will help inform future gender mainstreaming strategies for project interventions and project design processes.

- Conclusions # 1, 3, 7, and 8: Undertake a needs and risk assessment which looks at the capacities and vulnerabilities of partner institutions and stakeholders relevant to project activities and goals in the region, identifying the capacity gaps and risks that will need to be mitigated or managed. This will also support chances of sustainability.

- Conclusions # 1, 4, and 8: Engage UN partners in the development of the ToC process and the risk and needs assessment. Based on regional plans, identify where complementarities lie with UNDP’s programmes and how a collaborative relationship with the project would add value to the output, or at least bring useful synergies to the process. Invest in the capacity-building of regional partners, as well as interested civil society organizations and groups to further popular awareness, engage in dialogue and advocacy, as well as policy formulation at the country and regional levels. The attention to capacity building, multi-level dialogue for policy formulation will also support changes of project sustainability.

- Conclusion # 3: Use detailed stakeholder mapping to identify and categorize project stakeholders according to their influence on, and interest in, the project to identify how to manage them in the interests of the project during implementation. Based on the stakeholder analysis, select a few proven implementation partners with the technical competence and experience needed to develop strong partnerships with inter and governmental institutions necessary for transforming knowledge products into policy and plans.

- Conclusion 3,4 and 5: Improve overall coordination of project activities through the establishment of a stronger coordination mechanism staffed by a full-time coordinator which tracks evolving opportunities for creating synergies in partner implementation practices, leveraging existing partnerships and emerging opportunities provided by the work of other partners so that all partners are aware of each other’s work and can build more effective collaborative partnerships across the region. This mechanism must include monthly - or at a minimum - quarterly mandatory check-ins with partners to identify areas of synergy and collaboration for action.

- Conclusion 3 and 4: Improve the implementation of multi-level dialogues around climate security issues by broadening the base from government and national partners to include non-governmental organisations and the private sector.

- Conclusion 8, 9 and 10: Engage in communications on the results of the SDG CG and advocacy based on the results from SDG CF implementation with and through the UN to accelerate action on climate security.

- Conclusion # 3: Expand project partnerships as implementation progress based on your stakeholder analysis, technical requirements and proven and efficient implementation modalities which are not challenged by overwhelming coordination requirements. A consolidation of the relationships with the LAS for future partnerships should also be prioritized.

- Conclusions # 7: Build a learning loop into the M&E implementation process to be managed by the CTO for periodic but regular review and reflection on progress achieved against targets at regional and sub national levels. To keep the results on track, a quarterly—or at least semi-annual—stock take of performance measures should be done.

- Conclusion # 6: Ensure PMU competencies include performance management skills, relationship building skills (a more structured approach is needed to policy integration), communication and advocacy skills at senior levels.

# 1. Introduction

This report presents the final evaluation results of the project SDG Climate Facility: Climate Action for Human Security. The project is a multi-partner, multi-year initiative, funded by the Swedish International Development Cooperation Agency (Sida), drawing on the expertise of key regional institutions such as the League of Arab States (LAS), the Arab Water Council (AWC), with leading climate action United Nations (UN) Agencies such as the United Nations Development Programme (UNDP), the United Nations Environmental Programme-Finance Initiative (UNEP FI), the United Nations Office for Disaster Risk Reduction (UNDRR), the World Food Programme (WFP), and the United nations Human Settlements Programme (UN-Habitat) .

The information contained in the report is structured to meet the purpose and information needs of UNDP and Sida by presenting the conclusions immediately after the findings across each criterion. The primary audience/users of the evaluation are UNDP and Sida. UNDP may use the report to when designing projects of a regional nature where there is intent to involve multiple partners and where strong regional coordination, and collaboration are required to achieve project objectives. The report may also be useful in supporting UNDP’s approaches to implementation modalities in general, learning cycles, and the use of partnership building and multi-level dialogues for transforming knowledge into policy formulation activities. Sida may find the recommendations helpful in providing an overall picture of the design and implementation of projects of this nature and may enable a pre-funding review of such projects to ensure that the design has all the elements in place to have the best chance of achieving project objectives.

#### Evaluation Rationale

The final evaluation covers the SDG-Climate Facility Climate Action for Human Security, hereafter referred to as SDG Climate Facility Project spanning the period of January 2019 until December 2023, and was designed as part of the Regional Programme of Arab States (2018-2021). The project is a multi-partner project funded by Sida and implemented by LAS, AWC, and leading UN partners active on climate actions in the region, including the UNDP, UNEP-FI, UN-Habitat, UNDRR, and WFP.

The project aimed at enhancing the capacity of regional and national institutions to effectively take climate action in a way that brings multiple benefits across SDGs in crisis prevention/recovery settings and support to scale up climate finance for innovative local solutions. The SDG Climate Facility focused on addressing two main priorities in the region that were identified during the formulation process: (1) to promote more integrated solutions for climate action that bring benefits across SDGs and for crisis prevention/recovery goals, and (2) to scale up local partnerships and finance to this end. The project, under its 3rd outcome, also focused on six pilot country resilience grants, which aimed to enhance local capacities, implement comprehensive on-site solutions, and support the expansion of climate financing: Egypt, Iraq, Palestine, Tunisia, Jordan, and two in Yemen.

#### Project Description

Climate change has become a significant and complex issue intensifying poverty and human insecurity in the Arab States. This issue has escalated social vulnerability, aggravated conflicts, and caused widespread displacement in the region. This is primarily because of pronounced water insecurity, diminished agriculture productivity, and amplified fragility of land and ecosystem services. Hence, adopting climate-resilient approaches to development is crucial for crisis prevention and effective recovery efforts in these high-risk regions.

The project has built on regional dialogues on priorities for SDG achievement and consultations among project partners and developed a set of priority SDG-climate nexus points for  the focus of activities in the programme. Through joint actions, the project addresses two main priorities in the region: to promote more integrated solutions for climate action that brings benefits across SDGs and for crisis prevention/recovery goals, considering the local contexts and scaling up local partnerships and finance to this end.

The project is implemented in the following countries of the Arab region: Yemen, Syria, Palestinian Territories, Lebanon, Jordan, Iraq, Egypt and Tunisia.

The project is a multi-year initiative that started in December 2018 and is planned to end on 31 March 2024. It is a  multi-partner project funded by  Swedish International Development Cooperation Agency (Sida) and implemented by League of Arab States (LAS) and the Arab Water Council (AWC), and leading UN partners active on climate actions in the region, including the UN Development Programme (UNDP), the UN Environment Finance Initiative (UNEP-FI), the UN Human Settlement Programme (UN-Habitat), the UN Office for Disaster Risk Reduction (UNDRR), and the World Food Programme (WFP).

Project beneficiaries (who are also implementing partners) include the League of Arab States (LAS), the Arab Water Council (AWC), national and sub national level governmental bodies in the implementation countries, local organisations and communities involved in implementation in the implementation countries, and direct beneficiaries at the community level who include women and men, some from marginalized and vulnerable communities.

The Theory of Change of the project assumes that by increasing awareness and understanding at the regional level of the benefits of a nexus approach to climate action for achieving SDGs, enhancing access to analysis, tools and strategies at the regional level to advance climate action across SDGs for prevention and recovery goals, strengthening national and local capacities to effectively integrate climate change into policies and scaling up climate finance among local initiatives, then more integrated solutions for climate action can be developed that bring benefits across SDGs and for crisis prevention/recovery goals, taking into consideration local contexts, and to scale up local partnerships and finance to this end. See Annex 3 for details of the Theory of Change (ToC).

#### Project Outcomes and Outputs

The project was designed as part of the Regional Programme for Arab States (2018-2021). It contributed to Outcome 1 of the Regional Programme Document: Accelerate the structural transformation of productive capacities in a sustainable and inclusive manner and contributes to Outcome 3 of the Regional Programme current cycle (2022-2025): Impact of climate change reduced, sound water management promoted, and access to sustainable energy improved.

The results framework has three main outcomes with several outputs under each.

Outcome 1: Enhanced knowledge and coordination on climate-security among key stakeholders at the regional level to achieve climate action with co-benefits across the SDGs, and crisis prevention/recovery goals.

- Output 1.1: Establishment of a SDG Climate Facility as a multi-partner regional platform for accelerating climate action in a way that generates benefits across SDGs and for crisis prevention/recovery goals.

- Output 1.2: Improved regional policies and actions that generate co-benefits from climate action for SDG achievement and crisis prevention/recovery goals.

- Output 1.3: Policy dialogues undertaken with regional and national stakeholders to highlight how policies and actions on climate change can contribute to SDG achievement and crisis prevention/recovery goals.

- Output 1.4: Advocacy and communication materials on the SDG-Climate-Security nexus to inform policy reforms and changes.

Outcome 2: Enhanced access to analysis, tools, and strategies at the regional level to support a climate nexus approach to achieving SDGs and prevention/recovery.

- Output 2.1: Better characterization of multi-dimensional risk, and baselines established on state of climate security, social vulnerability and adaptive capacity needs across the region.

- Output 2.2: Early warning services, tools and risk assessment strengthened for better decision making.

- Output 2.3: Strategic risk assessment produced on nexus of climate change to SDG achievement and crisis prevention/recovery goals to promote integrated SDG solutions at the regional level.

- Output 2.4: Regional analyses of opportunities to increase access to renewable energy in the Arab States, with a particular focus on crisis settings and fragile contexts completed.

Outcome 3: Strengthened national and local capacities to effectively integrate climate change considerations into development and crisis prevention/recovery policies and to scale-up climate finance for local innovative solutions with co-benefits across the SDGs.

- Output 3.1: Leadership and capacities of national and sub-national stakeholders enhanced to integrate climate change into development and crisis prevention/recovery policies and plans.

- Output 3.2: Resilience grants to advance integrated, country-driven solutions.

- Output 3.3: Access to innovative finance and private partnerships is facilitated and scaled up through market analyses, mechanisms like Climate Investment Forums and others.

- Output 3.4: Good practices, lessons-learned and models captured for replication and scale-up.

#### Budget

The SDG-Climate Facility project was agreed in December 2018 between Sida and the UNDP Regional Hub for Arab States, with an initial grant of 60,000,000 SEK from Sida. In early 2019, Sida contributed an additional 7,000,000 SEK to the project, and in June 2020, Sida further topped up the budget by 14,500,000 SEK. These different allocations amount to the equivalent of USD 8,945,415 contribution by Sida, and a USD 600,000 contribution by UNDP TRAC, resulting in an overall project budget of USD 9,545,415.

# 2. Evaluation Objectives, Approach and Methodology

The overall objective of the evaluation is to assess the project performance and results and generate actionable recommendations and lessons learned for similar future projects.

The more detailed objectives of the evaluation are to:

- Assess Project Performance: Evaluate Project Performance: Assess the project's performance and outcomes according to Organisation for Economic Co-operation and Development (OECD)/ Development Assistance Committee (DAC) criteria, encompassing relevance, coherence, effectiveness, efficiency, impact, and sustainability. This evaluation will scrutinize various aspects such as project design, governance structure, engagement modalities, contributions of project partners, financial efficiency, economic sustainability, measurable results, and the project’s influence on reducing inequality, with a notable emphasis on gender mainstreaming. The assessment will adhere closely to project documentation, agreements, and coordination with the donor, Sida, ensuring alignment with established objectives and expectations.

- Generate Recommendations and Lessons Learned: Extract and analyse the findings to craft precise, actionable, and evidence-based recommendations. These recommendations are designed to facilitate organizational learning and inform the development of future projects. The report will effectively communicate achievements, challenges encountered, rationales behind deviations from the original plan, and strategies for mitigating these challenges to drive future enhancements.

The evaluation is structured according to the Organisation for Economic Co-operation and Development’s (OECD) Development Assistance Committee (DAC) evaluation criteria and the UNDP evaluation guidelines. The ET has further refined and expanded upon these criteria, as detailed in the Evaluation Matrix in Annex 2.

#### Timeline

The evaluation encompasses the project's timeline from its initiation in January 2019 until March 31, 2024, accounting for the no-cost extension. The project had an agreed-upon no-cost extension until December 2023. The additional period until March 31, 2024, is to ensure that the financial data and analysis are included in the report.

The revised project document from 2020 will serve as the primary reference point for this assessment.

#### Geographical Coverage

The evaluation covered the Arab States, with a particular project outcome 3, under the UNDP responsibilities, focusing specifically on implementing on-the-ground solutions in Jordan, Egypt, Tunisia, Iraq, the State of Palestine, and Yemen.

#### Primary users

The primary users of the evaluation include Sida, UNDP, UN partner agencies, regional partners and other external key stakeholders such as local governments and authorities, and local NGOs.

#### Evaluation Approach and Methodology

The evaluation team (ET) carefully reviewed and scrutinised the evaluation questions for their logic, fit, coverage, and clarity and built on the existing questions in the ToR. To design the methodology, the ET reviewed key project documents, including the project document, annual reports, annual work plans, resilience grants proposals, partnership agreements, results framework (Annex 4), ToC (Annex 3), and evaluation matrix (Annex 2).

Mixed-method and participatory approach: The ET adopted a mixed-method and participatory approach. The team gathered and analysed quantitative and qualitative data from primary and secondary sources. Primary data was collected from key internal and external stakeholders, emphasising engaging partners staff, policymakers, representatives from the private sector, and direct beneficiaries at the community level.

Non-experimental theory-based approach: The ET followed a non-experimental theory-based approach, which allowed the team to assess the implementation and outcomes of the project and its various activities over time against a predefined set of indicators and results.

Rights-Based Approach (RBA): The ET followed this approach to assess the extent to which the project upholds human rights principles. This included evaluating the project's impact on the realisation of rights, equitable distribution of benefits, and ensuring that the project respects and protects the rights of all individuals.

Cross-cutting dimensions: The ET considered including cross-cutting themes to ensure adequate attention to gender considerations, disability inclusion, leaving no one behind (LNOB), and a do-no-harm perspective, as the project was focused on how climate-oriented solutions impact human security.

- Gender considerations: Gender dimensions were integrated into the evaluation approach, and analyses of primary and secondary data were disaggregated by gender whenever feasible to understand gender dynamics and impacts. The team navigated social norms sensitively, creating comfortable environments for women to express themselves, sometimes through women-only group discussions. The evaluation and data collection team were gender-balanced and assigned to gather data based on the primary gender of the groups involved.

- Leaning no one behind (LNOB): The ET has actively engaged marginalized or vulnerable communities in the data collection processes, aiming to capture the experiences and needs of those frequently overlooked or marginalized.

Ethical Considerations: The ET adhered to the UNEG Code of Conduct to ensure ethical integrity and protect the rights of informants. AWRAD's approach emphasises obtaining informed consent, safeguarding privacy, ensuring confidentiality, respecting cultural sensitivity, and upholding participants' autonomy to foster an environment free from pressure or harm, with a commitment to universal values and fairness for diverse groups. Annex 24 includes more details.

The detailed evaluation questions for each evaluation criterion are presented in Annex 5. It must be noted that these questions were tailored to fit the experiences of each stakeholder and were addressed through secondary and primary, qualitative and quantitative data sources.

### Data Collection Tools

The ET employed various qualitative and quantitative tools with a range of partners as shown in the table below.

|  | Regional and partner stakeholder interviews |  | Country level interviews |  | Online survey with stakeholders |  | Focus Group Discussions (FGDs) |  | In-depth interviews with beneficiaries |  | Survey with beneficiaries |  | Totals |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of beneficiaries targeted | 23 |  | 14 |  | 17 |  | 6 |  | 11 |  | 42 |  | 109 |  |
| Participation by sex |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Subtotal of participants | 12 | 17 | 11 | 10 | 10 | 7 | 17 | 28 | 2 | 9 | 22 | 20 | 68 | 99 |
| Grand total of participants | 29 |  | 16 |  | 17 |  | 45 |  | 11 |  | 42 |  | 167 |  |

#### In-depth Document Review

A systematic review of the project documentation was conducted using the evaluation matrix to guide the review. A list of the reviewed documents can be found in Annex 12. The ET conducted a comprehensive review of key regional and national documents and policies related to climate change and human security, and their impact on economic and social aspects and gender dynamics in the Arab Region in general and in the targeted countries in particular.

The ET also reviewed the projects’ documents, such as the project document, project inception report, annual reports, annual work plans, resilience grants proposals, partnership agreements, annual partners reports, the results framework, the ToC and knowledge products. The team used the different data sources to inform the design of the tools and evaluation matrix and contrast them with evidence extracted from other primary data sources. The desk review enabled the team to conduct a beneficiary mapping and stakeholder analysis to understand better the types, characteristics, and distribution of key stakeholders across the region. Moreover, it provided a large amount of qualitative and quantitative secondary data, which was then triangulated with the primary data garnered from KIIs, FGDs and surveys. This allowed the ET to validate and formulate evaluative judgements based on the comparison of the two sets of data.

#### Regional and Partner Stakeholder Interviews

These interviews included the donor (Sida), as well as the non-core organisations, CGIAR—a global research initiative focused on food security, land, and water systems under climate change—and Adelphi, a leading think tank specializing in climate, environment, and development - and Sida. Nine interviews were conducted with the UNDP country offices, and the other four were conducted with the UNDP-RBAS team. Annex 8 provides a detailed breakdown of regional and partner interviewees.

#### Online Survey

The ET collected quantitative data from both internal and external stakeholders across all countries involved, as well as from several representatives at the regional level. In consultation with the UNDP-RBAS team, and based on the stakeholder analysis, the ET prepared a list of key stakeholders composed of regional partners such as pan-Arab organizations, UN agencies, and research centres; UNDP country offices; local implementing partners, NGOs and consultants (purposive sample). The ET disseminated the online survey via email, which was self-administered by respondents. The team reached out to 37 key stakeholders, of whom 17 completed the survey, resulting in a response rate of 46%. The online survey included close and open-ended questions to ensure data validation and triangulation of data. The survey results can be found in Annex 10.

#### Country Level Interviews

These were with country-level actors and partners directly involved in designing and implementing grant activities. The ET has alternated some of the planned interviews with local partners and relevant NGOs into FGDs to promote active discussion between relevant actors in all the targeted countries expect Palestine. A total of 14 interviews were conducted, some of which were conducted online, while others were conducted in person. The list of country-level interviews can be found in Annex 8.

#### Focus Group Discussions (FGDs) and In-depth Interviews

The ET conducted FGDs with direct beneficiaries, local actors, and NGOs. Some of these were conducted online, while others were conducted in person. Initially, the team was supposed to conduct 13 FGDs. The team managed to conduct only six FGDs with a total of 45 participants (28 males, 17 females), and 11 in-depth interviews with Qat-to-Coffee beneficiaries from Yemen (9 males and 2 females) as illustrated in Annex 9, which also describes the challenges in implementing the FGDs.

#### Beneficiary Survey

A beneficiary survey was carried out in 5 countries where it was deemed relevant. Part of the surveys were self-administered; the team shared the survey link with the beneficiaries for them to fill out independently, while others were administered through CATI and CAPI data collection methods. The survey included closed and open-ended questions to ensure data validation and triangulation of data, and it was piloted before the data collection to ensure question and language clarity.  The sample of the beneficiaries’ survey was based on lists provided by UNDP country offices (Refer to Annex 11).

#### Limitations and Challenges

- Documentation gaps: It must be noted that the project was not completely finalised when the evaluation was initiated, resulting in some essential data and documents being unavailable.  For example, there was inadequate documentation and reports available for the resilience grants, which limited the ET's ability to understand what had been completed, what was ongoing, and the current status of each grant. Additionally, there was poor documentation regarding the net/final number of beneficiaries in each country. To address these gaps, the ET used interviews with UNDP country offices, local partners, and NGOs.

- Stakeholder availability: Stakeholder availability and willingness to participate posed a challenge during the data collection phase. Efforts were made to schedule interviews, focus groups, and fieldwork during appropriate times with support from the UNDP-RBAS team. Some interviews were not conducted, particularly with partners and NGOs at the country level, due to their full schedules and other commitments. The team attempted to follow up with those who did not respond to complete the online survey. Moreover, stakeholders were not highly responsive in filling out the online survey, resulting in a response rate of 46%. The team followed up with targeted stakeholders at different dates and times to ensure their participation in the online survey.

- Challenges in completing the agreed-upon FGDs due to the following reasons:

- Qat-to-coffee grant in Yemen: The benefited farmers (males or females) live in scattered areas due to the country's situation, which poses movement difficulties. As such, the team substituted the planned FGDs with phone in-depth interviews.

- Palestine: Community members in the two targeted villages are not directly beneficiaries; although they benefited from the project, they are unaware of its existence. As such, the team was not able to conduct FGDs with these groups.

- Tunisia: Social constraints and barriers prevented the team from conducting the planned FGD with female community members in Tunisia.

- Ecotourism component in the resilience grant developed for Iraq: This component in Iraq was designed but not implemented. As a result, there were no beneficiaries to reach out to.

- Waste to energy grant in Yemen: This grant was not completed/suspended, so the team was not able to contact its beneficiaries.

### Data Analysis and Reporting

Data analysis involved a series of steps using quantitative and qualitative investigation techniques to ensure comprehensive triangulation of evidence. The team analysed primary and secondary structured by evaluation questions. The ET compiled interview and field notes into a single compendium, allowing for easy searching by topic and enabling triangulation of different perspectives to validate and formulate evaluative judgements. Quantitative data was cleaned and checked to ensure the accuracy of responses; the percentages of questions were calculated from the responses in the survey. The ET conducted a thematic analysis of the KIIs, FGDs, and surveys.

### Quality Assurance

Quality control measures included verifying that the interview took place, that interview durations were feasible, and that the ET followed all guidelines and standards. AWRAD is committed to high ethical standards and preserves clients' confidentiality and privacy. The quality control of interviews was managed by monitoring their completion and reporting any issues encountered. Additionally, ET shared their experiences using the guides, discussed problems with questioning or participant engagement problems, and reviewed any necessary revisions. Qualitative data was recorded (after getting participants' consent) with either a recorder or MS Teams and transcribed after the interviews, with notes included to ensure maximum reliability in recall and interpretation. Once transcriptions were completed, the audio files were deleted to ensure confidentiality and protect participants' privacy.

# 3. Findings

### Relevance

### EQ1: To what extent were the SDG –Climate Facility Project approaches and expected outcomes justified and responsive to beneficiary needs, regional policies, and context, and donor priorities?

##### EQ 1.1: To what extent was the project in line with regional environmental and climate security priorities and priorities in the countries directly engaged in implementation?

Finding # 1: The project was envisioned during time of crisis, lending support the emerging consensus on the need to link climate security nexus agenda with a broader and integrative vision of human security

The project was developed during a critical period in the Arab region's recent history. At the time of its inception, half of the region's countries were in crisis due to conflict, poverty resurgence, and unprecedented displacement.  One regional KI involved in the project design shared that extreme groups like ISIL highlighted these challenges emphasizing the region's volatility and prompting policymakers to prioritize successful recovery processes to prevent such outcomes from recurring. There was a growing consensus among national, regional, and global policymakers about the role of climate change in exacerbating these challenges, making restoring previous systems and lifestyles impossible. Thus, the project offered an opportunity to reimagine the recovery from crisis by incorporating climate awareness, responsiveness, and resilience to “withstand future climate impacts…which may contribute to further instability.” In addition, the project design took into consideration the importance of mainstreaming climate-oriented solutions and policies for prevention, response, and recovery.

In this regard, the project was understood to be proof that climate-oriented solutions could “Illustrate and showcase the linkages between climate security and all other types of security, such as social, peace, and food security, and bring benefits across the SDGs’.” For one project, a KI mentioned consulting with psychology experts to incorporate mental health considerations into the project’s design, a novel approach in Arab reconstruction efforts. The 2020 Annual Report noted that the project had been “recognized as the only project exclusively dedicated to climate-security and SDGs in the Arab region.”

##### EQ 1.2: To what extent was the project in line with the UNDP regional programme outcomes and outputs, the UNDP Strategic Plan, and the SDGs?

Finding # 2: Project design aligns with UNDP commitments especially to the SDGs, with opportunities for learning to create even better linkages in the future

From its inception, the project was designed to align with several SDGs including No poverty (1), Zero hunger (2), gender equality and women’s empowerment (5), clean water and sanitation (6), affordable and clean energy (7), reduced inequalities (10), ecosystem (15) and partnerships (17).  At its most effective form, the project was able to synthesise other activities in each country and serve as a platform for added value and catalytic change. One KI identified Iraq as such an example, where the project drew on the experiences of other country-level UNDP activities and incorporated this knowledge in the National Climate Plan. The Resilience Grants, considered the cornerstone of the project by several KIs, were also believed to provide “a nexus between climate action, SDGs, and climate prevention and recovery.”

##### EQ 1.3: To what extent does the project’s ToC remain relevant for the regional, national and sub-national environmental and climate security priorities?

Finding # 3: While the project demonstrates a thorough context analysis and identifies root causes effectively, it needs critical elements of a comprehensive ToC design, such as clear overall goals, impacts, general outcomes, operational objectives, causality pathways, and vertical and horizontal linkages. Despite an extensive consultative process during project design, a designated pre-design assessment, including risk analysis was not conducted and the insufficient ToC framework led to paradoxical results: flexibility for innovation and learning, with weak linkages between components

The project launched with innovative intentions to employ the ToC as a framework for project design, which, at the time, was not yet a fully standardized programme design tool. However, relative to contemporary methodologies, the project's ToC appears incomplete. It fails to clearly articulate core elements such as outputs, outcomes, impacts, and causality pathways critical for robust project development and monitoring. Initially, the project prioritised outputs over outcomes, leading it to function more as a funding mechanism within the UN system, contrary to its original intent. However, a KI involved in project implementation highlighted that resilience grants effectively operationalized the ToC and incentivized community participation, which could inform future project designs. While the ToC effectively identifies climate change as “drivers” or “the exacerbating force” behind negative outcomes or realities across the Arab Region and identifies underlying “root causes” of “development challenges”, the project's role in addressing these issues remains ambiguous. The diagram outlines three “solution pathways” - later designated as “outcomes” - but fails to establish clear connections between these elements and broader impacts. This need for clarity is compounded by the absence of operationalized indicators for outcomes, which hinders an assessment of the project's transformative potential.

During the project's design phase, extensive consultations were conducted, reflecting a commitment to stakeholder engagement. However, a notable omission was made for a designated pre-design assessment and comprehensive risk analysis. KIs noted that ToCs were rarely developed at the time of project initiation, relying instead on “existing literature, similar UN documents, and consultation meetings”. The assumption that assessment materials from a predecessor project would suffice proved problematic, as it led to challenges in integrating core project pathways across different levels—community, governorate, country, and regional. This fragmentation hindered efforts to maximize synergies and achieve consistently impactful results. Despite producing knowledge products and technical deliverables described by a KI as “interesting”, they often remained disconnected from a clear pathway to translate into meaningful outcomes. One KI appreciated the flexibility it offered for innovation but noted the challenge of integrating these initiatives with broader project activities and external stakeholders' efforts. Efforts to address these challenges, such as proposed monthly meetings, were insufficient in fostering the necessary integration and alignment among the project stakeholders and components. The ET was informed by UNDP staff that a midterm review was not conducted as it was not a requirement for this type of project. As a result, no adjustments were made in the ToC to take account of changing regional circumstances.

##### EQ 1.4: To what extent were perspectives, needs, and priorities of men and women who could affect the outcomes considered during project design and implementation processes?

Finding # 4 The project showed high levels of relevance to the needs of communities and community members. Relevance for the family (household) is also established but at a lower level of consensus.

Surveys with project participants suggest that the projects they participated in were relevant to their needs and priorities. Among the key findings:

Figure 1: Rate of project participants who believe the project was…

Additionally, project participants believed the timing of the intervention was appropriate, either to a large extent (26 / 42) or some extent (16 / 42).

In many cases, project participants’ consistently highlight the projects' high relevance to their immediate needs. For example, in a project implemented in the State of Palestine, local participants emphasised that it addressed an urgent need identified in municipal strategy documents. However, while the generated products were well-targeted for municipal and local actors' needs, their immediate applicability remained unclear. One KI who worked on a specific output noted that this product was “not enough by itself. There should have been another part in the project [on] how to use it, operationalise, who the users are, and how we can build their capacity to understand it and use it efficiently.” The varied outcomes at the household level (as mentioned earlier) highlight additional challenges in integrating cross-cutting variables, particularly within households. While the design of resilience grants aligned with community and member needs, household-level analysis was less prominent in project documentation, omitting considerations of family members' diverse needs based on age, gender, and disability perspectives. According to one KI, "The community's immediate needs took precedence, and our approach to these cross-cutting issues was not fully developed or communicated." This approach, as noted by the same KI, "had implications for achieving anticipated results, particularly concerning gender, age, and disability." The survey results identified the level of contribution of the resilience grants to various aspects of the beneficiaries' lives, they mainly contributed to protecting the local community from the effects/problems resulting from environmental and climate decline.

Table 1: Level of contribution of the resilience grants to beneficiaries lives

| Statement | Egypt | Iraq | Yemen | Tunisia | Jordan | Male | Female | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Protecting the local community from the effects/problems resulting from environmental and climate decline | 67% | 79% | 78% | 100% | 100% | 85% | 82% | 83% |
| Improving the economic situation of the family | 100% | 84% | 89% | 0% | 67% | 65% | 82% | 74% |
| Protecting the local community from the effects of the lack of this service/support | 33% | 74% | 89% | 60% | 88% | 75% | 73% | 74% |
| Securing water among the local community | 100% | 79% | 78% | 0% | 83% | 65% | 77% | 72% |
| Promoting equality between men and women in the surrounding community | 100% | 69% | 89% | 0% | 100% | 70% | 73% | 72% |
| Reducing family living costs | 66% | 79% | 78% | 0% | 66% | 55% | 77% | 67% |
| Alleviating poverty in the local community | 100% | 73% | 89% | 0% | 50% | 60% | 72% | 66% |
| Increasing family production from agricultural sources | 33% | 63% | 67% | 0% | 84% | 50% | 64% | 57% |
| Improving the nutritional status of the family | 66% | 58% | 67% | 0% | 67% | 55% | 55% | 55% |

##### EQ 1.5: To what extent does the project contribute to gender equality, the empowerment of women, human security and the human rights-based approach?

Finding # 5: The design places great focus on women, but with limited gender mainstreaming in the design of all phases and activities

The project integrated multiple SDGs, emphasising gender empowerment, marginalised group recognition, and human security. SDG 5 on gender empowerment was a primary focus, while considerations for marginalised groups extended to SDGs addressing poverty (SDG 1), inequality (SDG 10), and resource access (SDG 6). The Results Framework assessed these elements, with specific indicators such as 1.3.2 measuring "women engaged in regional dialogues on climate action." Additional indicators like 1.2.3, 2.3.2, 3.2, and 3.3.2 also targeted gender issues. Further, with the 2020 top-up from Sida, the project added specific budget lines to “enable dedicated activities related to gender and climate security.” One of these was an assessment specifically focused on the role of climate change in exacerbating resource scarcity, displacement, and conflict and how these outcomes impacted women. UN Women was directly involved in the genesis of the project.

The extent to which these measures mainstreamed gender equality or empowerment as transformative notions is disputed. One KI stated, “a real mainstreaming exercise was not carried out,” highlighting that gender empowerment assessments were confined to quantitative figures mentioned earlier. Acknowledging that “the project talk[ed] about women and report[ed] on numbers,” this same expert believed the true impact on gender equality remained unclear. This approach was criticised as "gender-blind," reflecting a “limited understanding” of mainstreaming gender and its intersection with other marginalising factors like displacement and refugee status.

While the project has not yet concluded, its full impacts will remain unclear until its completion and the final report are available. Implementers emphasised women's participation as an end goal, believing it alone could achieve gender empowerment. Interviews also revealed challenges stemming from inadequate gender incorporation during the project's design phase. For instance, one KI noted unexpected conservative norms of the community they were working with would inhibit women’s potential participation, forcing the team to hire a private women-owned company with experience working with women in the area to help design a more inclusive approach.

Viewed from this perspective, the indicators identified above effectively illustrate these limitations. The indicators are concerned solely with the participation of women (e.g., adult females), but do not consider how girls might be impacted by climate challenges or uniquely reached by the project. Further, in considering gender, the project does not appear to have reflected on the status of men and boys and how their gender influences their daily lives and, perhaps more importantly, how this shapes their relationship with women and women’s roles more specifically. To several KI’s, this is mainly due to the absence of a pre-design gender analysis specific to the overall project, and to the resilience grants as well. In contrast, according to a UNDP KI, “the design consulted a wealth of other documents that cater to gender analysis”; still, the design was not sufficiently informed by a holistic analysis of gender needs, roles, power dynamics and varying impacts on men and women, ensuring no harm to both genders.

##### EQ 1.6: Were persons with disabilities consulted, considered among the project beneficiaries, and meaningfully involved in project planning and implementation?

Finding # 6: The project document contains one reference to disability in the project design as an overreaching criterion to ensure non-discrimination

##### The ET found no mention of mainstreaming disability in the project's design, beyond a general focus on non-discrimination. There were no specific activities addressing disability in the project proposal or resilience grants. Structured consultations with persons with disabilities regarding output indicators, data needs, disaggregation, and reporting were absent. Outcome statements also lacked consideration of progress among individuals with disabilities. Project documents and interviews did not indicate how the needs or engagement of people with disabilities were addressed in project activities.

##### EQ 1.7: To what extent has the project design been appropriately responsive to political, legal, economic, institutional, etc., changes in the region and the countries where activities were implemented?

Finding # 7: The original design was aligned with the conditions in the region; there was no evidence of design adjustments to respond to changes over the project period.

The project was initially conceptualized to address the intersection of climate change and human  security during a critical period in regional development. It aimed to pioneer effective approaches amid limited existing knowledge and successful practices in climate action within such contexts. The project's role as a pivotal pilot was underscored, aiming to establish a proof of concept for future, larger initiatives. Early in its implementation, the project capitalized on emerging synergies in sustainable finance, responding to expanding efforts in decarbonisation within Gulf region banks. This included capacity building for financial institutions to integrate climate and SDG objectives, marking a significant advancement. However, KIIs revealed shortcomings in anticipating and resolving varying priorities among LAS, UNDP, and AWC, particularly affecting the project's climate facility, which was subsequently abandoned for another activity launching a regional initiative in the same field. Although updates in the Regional Programme Document for Arab States (2022-2025) emphasised climate change and human security, the ET noted a gap in assessing how these updates were integrated into ongoing project activities.

### Coherence

##### EQ2: The extent to which other interventions supported or undermined the project.

##### EQ 2.1: To what extent did collaboration between UNDP and other agencies, and the multi-partner approach add value to the project?

Finding # 8: The value added through collaborative partnerships between implementing agencies was limited at the regional level but much more potent at national and sub-national levels.  The value added at the regional level would have been more significant with stronger coordination from UNDP. The multi-partner approach at regional level tended to undermine coordination efforts

The types of collaborative arrangements envisaged across this multi-partner mechanism were not defined during the project design process. As a result, different types of collaborative arrangements evolved, some of which added value to the project by enabling faster and more effective activity implementation, increasing the intervention's impact and value. This was particularly true of the resilience grants design and implementation. The resilience grant had a pre-investment screening committee meeting before the resilience grants were approved. This allowed for various agencies, including AWC/LAS to provide feedback to the projects before them being approved.

Other arrangements, primarily at the regional level, simply leveraged the expertise of different partners to achieve the activity output.

Collaboration was primarily between the UNDP Regional Hub and individual UN agencies, including AWC, UNEP FI, UN Habitat, WFP, and UNDP country offices, with additional collaborations between AWC and UN Women. The UNDP Regional Hub facilitated partnerships to ensure effective implementation of regional activities. The UNDP Regional Hub, UNDP country offices, LAS, and national offices worked together at the national level. Overall, the UNDP Regional Hub was central in coordinating with respective partners across regional and national levels to achieve project goals. UN partners felt that "UNDP was also very good in coordinating, bringing partners together sufficiently, having many discussions on how the things we were working on in the project could be scaled up or replicated or worked on outside the project context.” (KII).

Collaborative partnerships at regional level

At the regional level, synergetic collaborations were pivotal in designing initiatives like the Arab Geographical Information Room (AGIR), as described by a regional KI: "We conducted extensive meetings with key stakeholders, leveraging their expertise to develop the AGIR platform comprehensively." In another example, a female KI at the regional level explained how WFP and AWC used the synergy for a common objective: "In Jordan, the WFP conducted research on anticipatory action, while AWC focused on a social vulnerabilities study". Such synergies   enhanced knowledge sharing and operational effectiveness across North Africa, ultimately contributing to longer-term regional development outcomes.

UN partners reported that while their collaboration with UNDP was excellent, there was little facilitation by UNDP of cross-UN collaboration. The project board mandated some essential cross-linking between partners, but this did not happen as a regular project management function until the last 15 months of the project when additional emphasis was placed on partner coordination. Board minutes indicate that project partners made attempts to reach out to other implementers or suggested mechanisms for improved coordination (Brown bag lunches over informal presentations, ….), but the overall impression remains that connections between the field, implementing organizations, and stakeholders were not evident; they didn’t know about each other’s work.

The absence of coordination left partners feeling they were operating in their own bubble with no linkages to the work of other partners.  External consultants reported that there was ‘not enough’ formal and informal engagement with partners to link them together, and, as a result, opportunities emerging from implementation to consolidate output achievements and take them forward were lost.  For example, one of the UN partners reported that they had limited opportunity to make the connection with the resilience grants, which focused on public-private partnerships, to integrate their learnings into the knowledge products underway.

In the absence of a strong facilitation/coordination function, UN partners tended to focus on their own little silo of activities. They were able to devote time to supporting the development of their own regional missions. This helped partners to develop their own global programmes and advanced their own footprints in the region, allowing them to start new programmes integrated into their own country level strategy plans, and leverage additional resources. But these results were not linked directly to the SDG project.

“One of the important points I would like to mention is the need for better collaboration among partners in the project, which was not well-defined in the setup. Each partner knew their role and the studies they needed to accomplish to achieve the expected outcomes, but a component to ensure collaboration among partners was missing. This would have added a lot of strength to the project”. (KII).

In some UNDP country offices, limited regional integration of the resilience projects was noted: “In my opinion, the project felt like a standalone initiative in our country, with limited integration with other countries' projects. The primary coordination was with the SDG Climate Facility Project, funded by the regional office. There wasn't much opportunity for cross-country collaboration or sharing of experiences during the project. We hoped for more structured exchanges and learning opportunities, but these were not adequately facilitated”. (KII).

Collaborative partnerships at national and subnational level

At the local level, multiple collaborative partnerships were established with national and local governments and local organisations (NGOs and research centres) specialised in water management, community mobilization, agriculture, and green construction. These partnerships helped to ensure alignment with national and local policies and broader climate adaptation goals, efficient implementation based on previous joint implementation experience, effective income compensation for local communities impacted by climate change and created business models for private sector engagement.

For example, in Egypt, the project integrated seamlessly into a broader Green Climate Fund initiative to safeguard the Nile Delta from sea-level rise. The localised approach met community needs and aligned with broader climate adaptation goals. Partnerships with local organisations like Misr El Kheir Foundation and the Desert Research Centre (DRC) enhanced implementation through their localised expertise. A local KI highlighted the initial challenge of finding reliable partners in Kafr El Sheikh but praised the eventual collaboration, facilitating effective communication and project execution.

In Palestine, collaboration with the Energy Authority (PENRA) and the Ministry of Local Government streamlined project activities, strengthened alignment with national strategies bolstered the project's sustainability and effectiveness. Collaboration between UNDP and local agencies in Yemen added value despite coordination challenges. Partnerships, such as the Qat to Coffee initiative with agricultural foundations, facilitated effective communication and project execution at the community level. Similarly, in Tunisia, collaboration with multiple partners enhanced the project's impact at local and regional levels, aligning with national priorities. A male KI highlighted, "The project built on existing partnerships with key ministries and civil society organizations, ensuring efficient implementation and alignment with national priorities."

Multi-partner approach

While the multi-partner approach of the SDG-Climate Facility project brought substantial benefits, the implementation modality also posed coordination challenges, as highlighted by a female KI at the regional level who noted: "reaching consensus among all partners took longer than anticipated, which affected our timelines". Others noted the additional efforts required to ensure consistent implementation across different governorates and improve connectivity among implementing partners and UN sister organizations involved in resilience grants.

"Most of the partners if not all of the partners ended up just saying okay, well what's my own agency's work program and how can this funding contribute to that, essentially, that was, was rather opportunistic, I guess, most of the partners and I guess UNDP could have could have tried to manage that a little better. But I think just having seven partners in one project was also quite unwieldy”. (Male, KII).

"Partners were not clear or direct at times with reporting on problems or raising risks and mitigation measures; they are too late to inform; dealing with risks and mitigation without much information communicated– it was like a case of code of silence”. (KII).

The limitation regarding open dialogue and clear and comprehensive reporting hindered problem-solving and trust-building at some levels.

##### EQ 2.2: To what extent has the work of the different partners been mutually consistent, including in promoting climate security, gender equality, inclusion, and the respect for human rights

Finding # 9: Project initiatives show external coherence across projects at both regional and local levels, and project designs show a good level of harmonisation of approaches around cross-cutting issues.

At the regional level, efforts to improve gender equality and inclusion were consistently built into project approaches to foster women's participation in governance and decision-making. Regional initiatives have shown a commitment to gender equality and women’s empowerment through the design of gender-focused knowledge products.

At the national and sub-national level, gender equality and women’s empowerment were a common feature of project design, with female beneficiaries reporting significant levels of empowerment from training in income generating projects and the experience of successful water entrepreneurship. Resilience grants have also shown strong commitment to human rights considerations and inclusion of vulnerable and more marginalized communities   by promoting climate security, gender equality, and human rights at local and regional levels

##### EQ 2.3: Is there any overlap or complementarity with other ongoing/planned actions managed by UNDP, other implementing partners, other donors, or the civil society that need to be addressed/considered for future interventions

Finding # 10: The project and other development partners' ongoing/planned actions are significantly complementary.

The project was aligned with ongoing initiatives within UNDP’s regional, environmental, and livelihood portfolios so considerable levels of complementarity were expected. No obvious overlaps were noted.  An interviewee noted, "We have been integrating the nexus approach—water, food, and energy—within UNDP and with international institutions. This project covered water and food/agriculture segments, leveraging existing expertise." At the regional level, some challenges were reported by UNDP included aligning implementation timelines across regional and country levels, and navigating bureaucratic processes within governmental, UN, and donor entities with varying requirements and standards. At the level of local grants, In Jordan, the project synergized effectively with UNDP's environment and livelihood portfolio, with plans to replicate its success in the Jordan Valley and document lessons learned for broader dissemination. In Egypt, the project aligned with a larger Green Climate Fund initiative for the Nile Delta, documenting outcomes and planning phase two while negotiating a larger project with the European Investment Bank. In Palestine, the project integrated well with UNDP's programmatic framework and national climate change targets, focusing on renewable energy integration and improving service delivery at the community level. Locally in Tunisia, project results significantly contributed to the Ministry of Environment's Sustainable Cities Program in Kairouan, enhancing climate change adaptation efforts. Additionally, the project secured $1.5 million in grants from the Global Environment Facility (GEF) and the Ministry of Environment in Tunisia, reflecting its success and alignment with ongoing regional actions.

##### EQ 2.4:  How well was the project coherent to UNDP corporate gender strategy and SDGs?

Finding # 11: The project demonstrated coherence with the SDGs and UNDP's corporate gender strategy at the regional and local levels, with efforts to promote gender equality and women's empowerment.

At the regional level, the project aligned with SDGs by promoting gender equality, inclusion, and addressing the interconnected challenges of climate change, gender, and human security. It also addressed the gender-climate-migration nexus through research and partnerships, bringing together various UN agencies and regional organizations to address these issues in the Arab region. Furthermore, the project's efforts influenced other UN agencies like UN Women, UNHCR, and UNDP to advance research and action on the climate-displacement-women nexus, highlighting opportunities and addressing the need for data on displaced women and climate change in Arab States hosting large, displaced communities.

The project aimed to advance several SDGs, including SDG 1 (No Poverty), through initiatives in renewable energy, climate adaptation, income generation, and poverty reduction. SDG 5 (Gender Equality) was emphasized by integrating gender mainstreaming, women's empowerment, and gender-responsive climate action to enhance women's leadership in climate decision-making. Additionally, in Palestine, the project contributed to SDG 7 (Affordable and Clean Energy), SDG 13 (Climate Action), and SDG 8 (Decent Work and Economic Growth) by improving access to sustainable energy sources, thereby creating opportunities for livelihood diversification.

The project overall aligns closely with UNDP's Gender Equality Strategy 2022-2025, integrating gender-responsive approaches into climate action. The project prioritizes women's inclusion in climate finance and decision-making processes. According to the project document, "UNDP and Sida have prioritized integrating climate action with SDG 5 globally and within this regional project."

At national and sub-national levels, gender mainstreaming is used across project activities, with specific strategies including analysing regional gender trends, using sex-disaggregated data on climate risks, and ensuring women's engagement in decision-making processes.

In Jordan for example, gender integration was a priority throughout project activities, ensuring women's inclusion from the selection stage and conducting awareness sessions with 50% female attendance among communities and women-headed Community-Based Organizations (CBOs). In Egypt, the project focused on creating income opportunities for women affected by sea-level rise, with 90% of grants and loans directed towards youth and women, aligning with SDG 5 (Gender Equality) and SDG 8 (Decent Work and Economic Growth). In Tunisia, gender considerations were integrated across all project activities, notably in the waste-to-energy initiative, emphasizing the project's comprehensive gender mainstreaming plan. In Yemen, community committees involved in the project achieved 30% female representation, demonstrating ongoing gender integration efforts throughout the Enhanced Rural Resilience in Yemen (ERRYII).

### Effectiveness

EQ3: To what extent were the planned objectives and results achieved, including factors that contributed to or detracted from their achievement?

##### EQ3.1: Agenda 2030, The Sendai Framework, and NDC’s, which are at the heart of the Paris Agreement, with other international climate-related/Disaster Risk Reduction/Development frameworks, consider it paramount to work through integrated approaches, combining climate action with development solutions that bring benefits across several SDGs. To what extent has the project been effective in promoting integrated solutions?

Finding # 12: The overall effectiveness of the project in promoting integrated solutions is evaluated at weak to medium. While output effectiveness is strong at the regional and national levels, effectiveness at the regional level is quite limited with – as yet - scanty evidence of outcome achievement. Project effectiveness at national and sub-national levels is more robust.

All activities under the project were designed to promote integrated development solutions to managing the risks of climate change. The majority of project activities achieved their expected outputs, but evidence for the achievement of outcomes is, as yet, quite limited. At the time of this evaluation, the project was considered as ongoing, so additional evidence may come to light in the final reporting to enable a more complete assessment of project effectiveness.

The overall effectiveness of the project in promoting integrated solutions was undermined by the absence of a key project output -  the Climate Facility – as envisioned by UNDP and Sida. The project had to pivot from this plan, and there is no clear evidence of an articulated strategy to integrate the other components—knowledge products, sustainability, lessons learned from pilots, and advocacy with decision-makers—in the absence of the Facility. The revised approach included establishing AWC and UNEP FI knowledge platforms to promote climate security and climate finance knowledge products, respectively.

Effectiveness at regional level

While almost all other outputs at the regional level were fully achieved, evidence for the achievement of outcomes (project objectives) at the regional level is difficult to capture, undercutting the overall  effectiveness of the project, as well as its impact. Multiple knowledge products (16 in total) were produced and disseminated to improve levels of knowledge, awareness and information across various sectors. However, the majority of these were only made available in the last year of the project, limiting – at this point of project implementation - their influence on levels of knowledge acquisition, utilisation for informing regional and national policies and project design addressing climate security nexus, and achieving SDG-focused climate action. Some reports are yet to be published, and some have not yet been completed. At this point, there is no evidence that the products have resulted in improved decision-making at regional levels.

The project’s knowledge products reportedly reached many people through various in-person events and approximately 37,000 on digital platforms (UNDP 2023). However, at this point these numbers can’t be verified as no documentation on events registration lists or webpage hits and follow-through were seen by the ET.

The absence of an integrated information-sharing platform, has limited effective access to and dissemination of knowledge products and related project information; however, some information on the project and knowledge products is available on two partner-managed platforms and a recently created UNDP platform. No information on traffic to this Knowledge Platform was available in any documentation, so it is not possible to comment on the number of users reached or the platform's overall impact.  The project also used 18 global and regional events to showcase the knowledge products and disseminate the findings.

To support coordination on climate security among key stakeholders, one regional network – the Regional Climate Security Network - was established, and two existing regional network – Anticipatory Action Community of Practice and Disaster Risk Reduction Partners Forum– were strengthened. The RCSN was initially reported to comprise 29 member organizations, including UN agencies, academic institutions, government bodies, regional research centres, NGOs, Civil Society Organisations (CSOs), and climate funds. However, the current membership listed on the website shows only 12 members, including three country ministries from Yemen, Egypt, and Iraq, three UN agencies, and six international NGOs and research institutes. The reasons for this reduction in membership are unclear.

The latest update available on the RCSN website is a newsletter dated August 2021, suggesting potential issues with website maintenance. There is no evidence of the progress made to shape and steer the climate security agenda in the MENA region through this network, although several nexus dialogues have been held and a training has been conducted by AWC to improve the understanding of the impact of climate change in MENA region, strategies for climate mitigation and adaptation and climate advocacy.

One activity  - AFEX - did successfully build new  partnerships between regional stakeholders and International Finance Institutions , accelerating climate finance efforts. Other activities which were intended to build on coordinated action at the regional level (private sector roundtables; coalitions of finance ministers for climate action in the Arab states) have not yet been  completed due to lengthy approval processes, or only partially achieved due to the cancellation of regional event, but no pivot plans to carry the activity forward are evident.

Evidence for improved access to analysis, tools and strategies and better decision-making at the regional level is again not clear. While many of the tools, methodologies, policy briefs and data sets are now available – except for the digital library designed to support sustainable reconstruction and recovery in the region through knowledge exchange and research - there are no reports on levels of uptake, their utilization or their usefulness. In some cases, access is still limited by language considerations (the on- line courses designed for uptake of methodologies for quantifying social vulnerability is still in English). A White Paper on “Accelerating Private Finance for the Arab Renewable Energy Transition” produced could serve as a precursor to the development of regional or national policies. Other than this White Paper, there was no evidence of improved regional policies and actions because of project activities apart from some anecdotal reports. At the country level, one instance of an anticipated influence was provided from the Jordan resilience grant project.

At the national and subnational level, there is strong evidence of the improved capacities of national and sub national capacities to effectively integrate climate change considerations into development and crisis prevention/recovery initiatives in the resilience grant programming.  Scaling up climate financing was also a key outcome of the project, and six of the seven resilience grants achieved this. By showcasing tangible results and actively engaging local stakeholders, UNDP country offices were able to attract over USD 63 million additional funding from multilateral donors and the private and public sectors (UNDP Progress Report 2023). Findings are summarised in Annex 17. There is also strong evidence of the increasing capabilities of AWC to understand, research and advocate for climate security issues through the production of policy papers .

Efforts to build the capacities of national commercial partners were only partially successful. They were challenged by limited funding for smaller banks and by the lack of a pipeline of bankable investment projects, traditionally introduced and managed by national governments.

The impact of all the advocacy and communication materials cannot be empirically linked to changes in knowledge and awareness among regional stakeholders or to policy reforms and policy changes at regional level that would better support climate action, although anecdotal evidence shows that the materials were well produced and well received. The level of achievement of the sub-indicators per Outcome is provided in Table 2. Because the results framework only has indicators at the activity level, not at the output or outcome levels, the level of achievement per outcome is measured as the cumulative achievement of the output activity sub-indicators. Refer to Annex 16 for details.

Table 2: Level of project achievement of sub-indicators under each outcome

| Not Achieved |  | Partially Achieved |  | Fully Achieved |  | Output achievement per outcome |
| --- | --- | --- | --- | --- | --- | --- |
| % | # | % | # | % | # |  |
| 18.2% | 2 | 27.3% | 3 | 54.5% | 6 | Outcome 1 (n = 11) |
| - | 0 | - | 0 | 100% | 11 | Outcome 2 (n = 11) |
| - | 0 | 23.5% | 4 | 70.5% | 12 | Outcome 3 (n = 16) |
| 5.3% | 2 | 18.4% | 7 | 76.3% | 29 | Total (n = 38) |

Changes in partners perceptions because of project activities

The ET also looked at observable changes in the perceptions of various groups involved in the project activities as indicative measures of outcome achievement. When asked to rate the performance of the SDG-Climate Facility in achieving results in key areas, most respondents (64.7%) believed that there had been enhanced knowledge and coordination on climate security among key stakeholders at the regional level to a large extent, with 23.5% agreeing to some extent. In terms of enhanced access to climate nexus analysis, tools, and strategies at the regional level, only 29.4% saw significant progress. In comparison, 41.2% acknowledged some improvement, and 23.5% felt there had been little progress. Stronger national and local capacities to integrate climate change considerations into development and crisis prevention plans were recognized to a large extent by 35.3% of respondents and to some extent by 41.2%. Finally, 17.6% of respondents believed that there were stronger capacities to scale up climate finance for local innovative solutions to a large extent, with 41.2% seeing some extent of progress in this area. See Table 3.

Table 3: Views of UNDP country staff and partners on the achievements of the project results (N = 17);  figures in brackets in percentages

| Result | To a large extent | To some extent | No – not really | Don’t know/no answer |
| --- | --- | --- | --- | --- |
| Result: Enhanced knowledge and coordination on climate security among key stakeholders at regional level | 11 (64.7) | 4 (23.5) | 1 (5.9) | 1 (5.9) |
| Result: Enhanced access to climate nexus analysis, tools and strategies at the regional level | 5 (29.4) | 7 (41.2) | 4 (23.5) | 1 (5.9) |
| Result: Stronger national and local capacities to effectively integrate climate change considerations into development and crisis prevention plans and policies | 4 (35.3) | 7 (41.2) | 2 (11.8) | 2 (11.8) |
| Result: Stronger capacities to scale up climate finance for local innovative solutions | 3 (17.6) | 7 (41.2) | 5 (29.4) | 2 (11.8) |

The survey also explored partners' views on the value added by the SDG- Climate Facility Project at regional and country levels. At the regional level, notable contributions were made by the project in various aspects of climate security.  The project raised awareness among regional actors about the relevance of climate security, with 47.1% of respondents indicating this was achieved to a large extent and 29.4% to some extent. In addition, 47.1% of respondents felt the project effectively promoted the conviction that climate security deserves a place on the regional agenda, with another 47.1% agreeing to some extent. The project also provided skills and tools for analysing and assessing climate security issues, particularly in disaster risk assessment and mitigation, with 58.8% of respondents acknowledging this contribution to some extent and 29.4% to a large extent. See Table 4 for details.

Table 4: Views of UNDP country staff and partners of project achievements at regional level (N = 17)

| How would you assess the value of the SDG-CF programme at the regional level? Did it contribute to the following? | To a large extent | To some extent | To a limited extent | No-not really |
| --- | --- | --- | --- | --- |
| Raising awareness among regional actors of the relevance of the issue of climate security | 8 (47.1) | 5 (29.4) | 3 (17.6) | 1 (5.9) |
| Promoting a conviction that this is an issue that deserves to be on the regional agenda | 8 (47.1) | 8 (47.1) | 1 (5.9) | - |
| Providing skills/tools to analyse and assess climate security related issues (disaster risk assessment and mitigating) | 5 (29.4) | 10 (58.8) | 2 (11.8) | - |

At the national level, the findings from the partner survey indicate that the SDG –Climate Facility project has also made several noteworthy contributions. The project significantly increased awareness among involved institutions regarding climate security needs and requirements for their future work, with 64.7% of respondents indicating this was achieved to a large extent and 29.4% to some extent. Furthermore, 35.3% of respondents reported that the project introduced a systematic learning mechanism within their organisations to improve the design and implementation of similar projects, with another 41.2% acknowledging this to some extent. Raising awareness among national partners about the relevance of climate change was another key contribution, with 23.5% indicating this was achieved to a large extent and 70.6% to some extent. Introducing new national policies that tackle climate change was recognised by 17.6% of respondents to a large extent and 41.2% to some extent. However, 47.1% of respondents felt that the project introduced regulatory improvements at the national level to improve climate-related action to some extent. The project's impact on achieving gender equality and youth empowerment, particularly through employment generation, was noted by 35.3% of respondents to a large extent and 23.5% to some extent. See Table 5 for details.

Table 5: Views of UNDP staff and partners of project contributions at country level (N = 17); figures in brackets in percentages

| How would you assess the value of the project at the country level (if your focus was on more than one country, please answer about your overall assessment)? Did it contribute to the following: | To a large extent | To some extent | To a limited extent | No-not really | No answer/ Don’t know |
| --- | --- | --- | --- | --- | --- |
| The involved institutions are now more aware of climate security needs and requirements in their future work | 11 (64.7) | 4 (29.4) | - | - | 1 (5.9) |
| Introducing a systematic learning mechanism within our organization to improve our design and implementation of similar projects | 6 (35.3) | 7 (41.2) | 2 (11.8) | 1 (5.9) | 1 (5.9) |
| Raising awareness among national partners of the relevance of the issue of climate change | 4 (23.5) | 12 (70.6) | - | - | 1 (5.9) |
| Introducing new national policies that tackle the issue of climate change | 3 (17.6) | 7 (41.2) | 3 (17.6) | 1 (5.9) | 3 (17.61- |
| Introducing regulatory improvements at the national level to improve climate - related action | - | 8 (47.1) | 5 (29.4) | 1 (5.9) | 3 (17.6) |
| Helping achieves gender equality and youth empowerment (through employment generation) in the project implemented in your country/countries | 6 (35.3) | 4 (23.5) | 4 (23.5) | 1 (5.9) | 2 (11.8) |

The beneficiary survey reveals several indicative insights regarding the impact of the projects on various aspects of their lives. Firstly, over half the beneficiaries, 57%, reported that they have become significantly more aware of the concept of climate security due to the support provided by the projects, with an additional 33% acknowledging some improvement in this area. Only 4.8% felt this awareness was achieved to a limited extent or not at all. Secondly, the survey results indicate a strong positive impact on skills development, with 67% of respondents stating that they have greatly enhanced their skills to contribute to mitigating pollution and climate damage in their work and daily practices. However, the impact of the projects on promoting gender equality in the surrounding community was more varied. While 29% of beneficiaries believed that the projects significantly contributed to promoting equality between men and women, 43% felt that it achieved this to some extent. Conversely, 17% reported no achievement in this regard, and 4.8% felt it was achieved to a limited extent.

Table 6: Reported contribution of the projects to aspects of beneficiaries' lives (N = 42); figures in brackets in percentages

| Considering the following statements, do you think that this support has contributed to achieving these aspects in your life? | Achieved to a large extent | Achieved to some extent | Achieved to a limited extent | Not achieved at all | No answer/ Don’t know |
| --- | --- | --- | --- | --- | --- |
| I have become more aware of the concept of climate security | 24 (57) | 14 (33) | 2 (4.8) | 2 (4.8) |  |
| I have greater skills to contribute to mitigating pollution/climate damage in my work and daily practices | 28 (67) | 11 (26) | 1 (2.4) | 0 | 2 (4.8) |
| The project contributed to promoting equality between men and women in the surrounding community | 12 (29) | 18 (43) | 2 (4.8) | 7 (17) | 3 (7.1) |

Factors contributing to level of results achievement - Key supporting and constraining factors contributing to the results include the following:

Table 7: Key supporting and constraining factors contributing to the results

| Supporting factors | Constraining factors |
| --- | --- |
| - Technically robust knowledge products - Strong advocacy and communications materials - Excellent working relationships between UNDP and UN partners. - Flexibility in implementation where more impactful solutions could be prioritised over original activity design - Strong community and partner ownership of the final resilience grants output - Integration of the budgets of the resilience grants project into local authority budgets - Gender mainstreaming in the resilience grant project design - Involvement of diverse local community actors – local authorities, NGOs, and the private sector – in the design and implementation of the resilience grants | - Delays in implementation caused by the global COVID-19 pandemic. - Weak coordination of project partners across project activities at regional level - Political instability in certain countries, like Yemen and Iraq, complicated project implementation and engagement with local stakeholders. - Limited exchange and knowledge sharing between the different countries involved in the project - Limited work on related national policies and regulatory framework to enhance climate security at the national level - Limited joint programming between project partners - Lack of formal overall risk analysis of operating context leading to a level of unpreparedness in the face of evolving obstacles |

##### EQ 3.2: To what extent did the project contribute to the climate security nexus agenda in the Arab States region?

Finding # 13: The project effectively integrated climate security into regional discussions and high-level events, fostering a common understanding of the climate security nexus but could not effectively integrate that understanding into national or regional policies or plans.

From 2020 to 2023, the project organised and/or participated in over 18 global and regional events (information gleaned from what was mentioned in progress reports, KIIs, Board Meeting minutes).  Most events took place in 2022 (39%), with the fewest events (11%) in 2021.  Out of these 16 events, 10 (63%) were organised under the auspices of the SDG =Climate Facility Project or partners, and in 6 (37%) events SDG Climate Facility Project/partners participated.

Table 8: Number events SDG-CF organised and participated in

| Year | Number of events | Percentage |
| --- | --- | --- |
| 2023 | 5 | 28% |
| 2022 | 7 | 39% |
| 2021 | 2 | 11% |
| 2020 | 4 | 22% |
| Total | 18 | 100% |

The events SDG –Climate Facility project organised or participated in, included a mix of high-level global conferences (22%) such as COP28 and COP27; regional forums (56%) including MENA Climate Week; Arab Forum for Sustainable Development, and Arab Water Forum; and specialised workshops and webinars (22%). These events were reported to have enabled them to facilitate multi-stakeholder dialogues, promote practical solutions, and foster integrated approaches to sustainability and security across various levels and regions.

Table 9: Number of events by type

| Event Type | Number of Events | Percentage |
| --- | --- | --- |
| Global Conferences | 4 | 22% |
| Regional Forums | 10 | 56% |
| Specialised Workshops & Webinars | 4 | 22% |
| Total | 18 | 100% |

Limited information on the number and details of participants was available in the reports.  The most detailed information available was for the 1st Regional Stakeholder Dialogue on Climate Security Launch on 6 – 10 December 2020. The website provides details of the participants, of which there were 88, with an estimated 69 males (78%) and 19 females (22%). The event provided an opportunity to exchange views and information among the different stakeholders on how to integrate climate security considerations in planning and budgeting and how to generate agreed strategic priorities to act on climate security-related challenges in a more sustainable and coordinated manner (Information accessed from: https://climatechangedialogue.com).

Other than the 2021 White Paper: Accelerating Private Finance for the Arab Renewable Energy Transition discussion document, there was no evidence of a regional level policy or plan that provides a vision and objectives to combine climate action with development solutions.

The 2021 White Paper was, however, seen as an important advocacy tool, raising awareness of climate security: “(it has)" has helped to position climate security as an important subject in the region. Many partners are approaching LAS for cooperation opportunities due to the White Paper. Climate security is now a part of the LAS policy discussions and has been flagged by the LAS on many occasions as a “major challenge in the region that must be addressed” (Board Minutes June 2023).

One KII reported that while the Jordan resilience project did not directly develop new policies, it had supported regional policy initiatives related to climate change and displacement, indirectly benefiting women: "The project did not directly address policies but supported regional policy initiatives related to climate change, displacement and gender". However, a regional policy on this issue has yet to be developed.

In two instances, in Jordan and Iraq, resilience project's findings and experiences were used to inform and influence national programming on climate security.

##### EQ 3.3:  to what extent has partner’s engagement and partnership initiatives implemented throughout the project been appropriate and effective?

Finding # 14:  Project partners’ level of engagements has been consistently high throughout the project period.

Roles of the partners are described in the Terms of Reference (ToRs) for the project Steering Committee and all the project partners (except for UNDP country offices) were directly represented on the Project Steering Committee (ToR, October 2019). Board minute meeting minutes reflect this participation (see Table 10).  This consistent involvement indicates a high level of engagement with the project's purpose. This high level of engagement helped to compensate for the challenges regarding a strong coordination function within project management by collectively identifying areas where partner collaboration was needed and mandating action. Sida has noted that they were not invited to take part in the Steering Committee meetings except for the last meeting, where they were alerted too late to be able to participate.

Table 10: Partner attendance at Steering Committee meetings

| Date | AWC | LAS | Sida | UNDP Regional Hub | UNDRR | UNEP FI | UN Habitat** | WFP | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 - 2 October 2019 | 3 | 2 | - | 4 | 3 | 1 | 1 | 1 | 15 |
| 9 June 2020 | 3 | 2 | 1 | 3 | 2 | 1 | 1 | 2 | 15 |
| 5 July 2021 | 5 | 2 | - | 5 | 2 | 2 | 1 | 3 | 20 |
| 17 - 18 January 2022 | 4 | 2 | - | 6 | 2 | 2 | 1 | 1 | 16 |
| 19 June 2023 | 3 | 3 | - | 5 | - | 2 | - | 1 | 14 |

##### 3.5 to what extent has the project contributed to gender equality, the empowerment of women and the realization of human rights?

Finding # 15: Although some gender-level targets were achieved or surpassed, the lack of detailed results tracking, inconsistent reporting, and data gaps have hindered a proper assessment of the project's gender contributions.

The project allocated gender services to activities under Outcomes 1 and 3 and had a dedicated JPO for gender issues but had no project-level gender strategy. The project initially included a strong commitment to integrating gender considerations into its activities and across the different outcomes there is an explicit focus on the integration of gender considerations from the conceptualization phase and in most publications and knowledge products.  "A JPO was appointed specifically to ensure the integration of gender into the program" (Female, KII). At regional and country level, various workshops and training sessions aimed at raising awareness and building capacity on gender issues were conducted. These sessions were intended to ensure that gender considerations were integrated into climate resilience and adaptation activities.

Impact of gender-focused knowledge products on gender mainstreaming in interventions, policies and plans

The three Gender-focused knowledge products produced at the regional level highlight the differentiated impacts of climate change on men and women and propose gender-sensitive solutions, with a primary focus on displaced persons (see Annex 19). While efforts were made to disseminate these publications' findings and detailed recommendations through various events, conference sessions, and regional meetings, there is no evidence that these studies resulted in policy changes at the regional or national levels or specific programmatic interventions. The UNDP reports working on mainstreaming findings on the gendered impacts of climate change into global programmes, including the Climate Promise (UNDP 2023 Progress Report). The project views these knowledge products as crucial for gender mainstreaming in climate action and related policy and programming. However, the depth and reach of the dissemination efforts remain unclear. Reported synergies and complementary activities with other project partners appear promising. For instance, the joint Social Vulnerability Study between AWC and the WFP, supported by the UNDP Regional Hub in Amman, facilitated fieldwork and local policy dialogues. However, the impact and practical outcomes of these collaborations remain uncertain. Similarly, while the collaboration between the AWC and UN Women on the Climate-Gender-Migration nexus aims to contribute to UNDP's research on the impacts of climate change on displaced women and girls in the Arab States, the tangible benefits and integration of these findings into actionable policies need further evaluation.

Impact of resilience grants on gender equality, women’s empowerment and human rights

The resilience grant proposals all made some provision for monitoring and recording gender-related data to ensure men and women were equally benefitting from the project, and gender responsive activities such as gender analysis to understand different impacts on men and women, involving both genders in decision-making processes, ensuring that services were accessible and beneficial to all genders, and targeted activities with specific vocational opportunities directed at women (e.g. ecotourism in Iraq and food drying and preserving in Egypt).

While all proposals mentioned gender gap analyses, there was only evidence of two documented gender gap analysis. They were for the Jordan grant and for the Iraq pilot: Gender Analysis and Action Plan in Al Hwaizeh Project (August 2021). This gender analysis makes several recommendations including amongst others providing transportation options for women, such as group or solo transportation, and assess women's safety when sharing transportation with men; including men in gender discussions and ensuring women's participation throughout the project’s implementation; strengthening power relations within families and communities by creating diversified income-generating options, particularly in the ecotourism sector, and facilitate women's labour market participation. While these recommendations are actionable, they would benefit from more detailed guidance on implementation methods. This includes strategies for strengthening power relations within families and communities in ways that avoid increasing women's risk of gender-based violence resulting from shifting power relations.

In the Egypt project, the resilience proposal mentioned conducting a gender gap analysis “to assess the role of women in relevant sectors to make recommendations towards a fully gender-responsive project approach” (a supporting document provided but was dated 2017). The project included various activities to meet the needs of men and women, informed by social studies with men, women, and youth. Agricultural projects targeted men, while food drying and preservation projects were geared towards women, and honey beekeeping projects involved both youth (who could be male or female) and women: “This diversity ensured benefits were distributed fairly across different groups, not just one” (KII).

In Jordan, a consultant was reported to have been hired to conduct a gender gap analysis and develop an action plan to integrate gender and youth into activities "Actions included targeting male and female farmers and ensuring women were included in all training activities, emphasising maintaining a 50:50 gender balance" (Female, KII).

The Regional Office assisted country offices (possibly including the gender JPO) in developing their proposals, ensuring the inclusion of gender considerations.

Regional and national level gender targets

The project’s results framework includes one gender-related target at the regional and national level under Output 1.3.  This is measured by Sub-indicator 1.3.2. The UNDP Progress Report 2023 indicates that the target was achieved.

As mentioned earlier, an analysis of information on participants attending the Regional Stakeholder Dialogue on Climate Security held in December 2020 showed that of the 88 participants, an estimated 69 were male (78.4%) and 19 females (21.6%). This is less than the target of 30%. More male participants were in the task forces related to climate security, energy, and policy discussions. Female representation in the Climate Security, Social Cohesion, and Gender Equity Task Force was higher, with women making up about 63.6% of the participants

Local level gender targets

The UNDP draft Progress Report 2023 states that the project reached 79,329 beneficiaries across six countries, with 27,608 (35%) being women.  There are no consistent targets for each country, making it challenging to comment on the overall achievements.

Measurable local-level gender targets were set for one resilience grant indicator under Output 3.2: Sub-indicator 3.2.4, which tracks the number of country grants with at least one activity addressing gender inequality. The target was set at two country grants by Year 4. This target was surpassed, with all six grants addressing gender equality either directly or indirectly, exceeding the initial expectations set during project design. This result was achieved when the project team, in collaboration with UNDP country offices, developed the proposals for the resilience grants. They ensured that all six grants incorporated gender equality (see the previous section for a description of gender-related activities in resilience grants by country).

Output 2.3 has three other activities that mention co-benefits for women or emphasis on women’s empowerment (Yemen: Activity 3.2.1; State of Palestine: 3.3.2; Iraq: 3.3.3). None of these have indicators with measurable gender targets.

The State of Palestine activity sub-indicator (3.2.1) requires the number of people benefitting from increased access to energy through solar solutions in Palestine to be disaggregated by country and sex but did not provide a specific target. Data provided in the UNDP draft Progress Report 2023 on progress with this indicator demonstrated a balanced distribution of benefits between males and females. See Table 11.

Table 11: Total beneficiaries disaggregated by gender Palestine solar pilot (sub-indicator xxx)*

| Year | Location | Total beneficiaries | Female (%) | Male (%) |
| --- | --- | --- | --- | --- |
| 2022 | Arrabah | 12,356 | 49.3% | 50.7% |
|  | Qabalan | 8,771 | 48.6% | 51.4% |
| Total |  | 21,127 | 49% | 51% |

Source: Figures provided by the Palestinian Central Bureau of Statistics (UNDP Progress Report 2023)

The UNDP draft Progress Report 2023 provides an achievement of 51% male under the sub-indicator for Activity 3.2.3, however, it is unclear how this percentage relates to the target of 7 assessments and restoration measures. Specifically, it is ambiguous whether this percentage refers to male participation in the activities, beneficiaries, or another metric.

| Activity 3.2.3: Iraq: Deploy solar solutions to address sustainable energy needs for returnees of conflict in areas of Iraq liberated from IS, with emphasis on women empowerment, and technical assistance to mainstream solar solutions into broader crisis recovery policies and investments planning | Sub-indicator 3.2.3: Sub-indicator 3.2.3: Number of assessments and restoration measures for critical ecosystems implemented | Target: 7 | 2022/2023 Achievement: 51% male |
| --- | --- | --- | --- |

Some resilience grants projects established gender targets, but these are not reflected in the project results framework. The UNDP reports also provided some targets and achievements not reflected in the project results framework. There are gaps in reporting data against these targets which makes it difficult to provide conclusive findings. Annex 16 provides a summary of these findings.

Gender results of resilience grants

According to the partner survey findings the project's impact on gender equality and youth empowerment was mixed, with 38.5% recognising contributions, but with many seeing limited progress.

The beneficiary survey provides indicative findings on the impact of the projects in promoting gender equality within the surrounding community. According to the survey, 29% of respondents believe that the projects significantly contributed to promoting equality between men and women. An additional 43% felt that this objective was achieved to some extent. However, 17% of respondents reported no achievement in promoting gender equality, and 4.8% felt it was achieved to a limited extent.

Table 12: Beneficiaries reported contribution of the projects to equality between men and women (N = 42)

| Considering the following statements, do you think that this support has contributed to achieving these aspects in your life? | Achieved to a large extent | Achieved to some extent | Achieved to a limited extent | Not achieved at all | Don’t know |
| --- | --- | --- | --- | --- | --- |
| The project contributed to promoting equality between men and women in the surrounding community | 12 (29%) | 18 (43%) | 2 (4.8%) | 7 (17%) | 3 (7.1%) |

The UNDP annual progress reports for 2022 and 2023 indicate that the SDG Climate Facility Project engaged women’s associations and community leaders to ensure women's representation and participation in gender-responsive actions. Specific projects in the State of Palestine, Iraq, and Jordan involved significant numbers of women, with initiatives like solar PV plants and related training targeting substantial female participation. However, there is a lack of data or evidence on the outcomes of this type of participation for women.

Despite extensive involvement of women’s organisations in various activities, the results at the gender level remain unclear. For instance, the Warqa Organization, a women’s empowerment organisation in Iraq, hosted training sessions for women in Maysan Province and provided insights into entrepreneurship and small project ideas. They observed that women's attendance and engagement in these sessions had a positive impact, fostering a sense of empowerment and motivation to start their own projects. Anecdotal success stories (see Annex 20) provide some insight into the potential impact of these projects.

### Efficiency

##### EQ3: The extent to which SDG –Climate Facility resources (funds/human resources, time, etc.) were optimally used to achieve the intended results

##### EQ4.1: To what extent was the project management structure as outlined in the project document efficient in generating results?

Finding # 16: The management structure supported achievement of results well in terms of an effective accountability mechanism and decision-making process, but it was less successful in providing oversight to project coordination, consistency in quality assurance of technical assistance levels and financial reimbursements processes.

Management structure

The management structure is flat but somewhat fragmented, with the M&E and reporting function in Beirut, the day-to-day management in a non-co-located office in Amman, and the regional coordination housed within UNDP’s Regional Hub in Amman, while the main partner is in Cairo. The location of the Management Support Unit (MSU) outside of Egypt, the site of the programs’ most important regional implementing partners, and the projected location for the SDG Climate Facility Project is a little baffling. Jordan may indeed be a more stable country, but the optics of this choice may not be encouraging for the project's leading partner, the LAS.

The structure of implementation arrangements for the project are, in some respects, quite standard, comprising:

- A Project Board (PB) comprising Implementing Partners and UNDP to provide policy guidance and accountability.

- A Regional Programme Management Team co-located as an integral part of the UNDP’s Regional Hub for Arab States in Amman, Jordan.

- A MSU to manage the programme on a day-to-day basis.

- UNDP Country Offices in the region The UN Country Teams and UNDP Country Offices will support local implementation of individual country components of the project in concert with national partners.

Implementing partners included LAS, AWC, UNEP-FI, UN-Habitat, UNDRR, and WFP, who entered into partner agreements with UNDP to implement activities detailed in the Annual Work Plans (AWP). The RPMT provided technical and management oversight for all implementation to complement the competencies of the MSU through its own Management Support Unit (MSU) based in Beirut, which has particular responsibility for monitoring and reporting on project results, ensuring that all UNDP projects are aligned with the Regional RRF, and financial issues.  UNDP's technical advisory team - Climate Change, DRR, Energy, and Environment Team- provided programme and policy support to implementation for quality assurance of results. The UN Country Teams and UNDP Country Offices supported the local implementation of individual country components of the project in concert with national partners. For an organogram of the project, please refer to Annex 21.

Accountability for the achievement of project results

National partners or civil society organisations were not involved in Board meetings or discussions despite being allocated a place within the implementation/governance structure. Accountability was seen as a shared function between UNDP (which is both the Executing Agency and Implementer) and LAS (which is also the Implementing Agency and a prime beneficiary of the project's activities).

The second issue was the continuing concern to meet annual work plan targets and expenditures. The delays created by COVID for the first 18 months of the program were carried over to - and reflected in - the subsequent two years of implementation and annual budget utilization rates.

The risk register did not receive regular updates and analysing changes in risk and mitigation over the project period was undercut by the changing format and content of the registers. The register did, however, provide some useful data to support the analysis on implementation delays.

Project coordination

Two themes were common to all Board Meetings. First, the need, repeatedly and exhaustively expressed by all partners in all Board meetings from its very first meeting in 2019, was the continuing need to strengthen the understanding and collaboration between themselves as implementing partners, to create synergies in their implementation practices, to leverage existing partnerships and emerging opportunities provided by the work of other partners, and to share lessons learned to make project implementation more efficient, not only in a timely sense, but also in a making -best- use of -resources- sense. The Minutes of meetings show that collaborative discussions and exchange of documents were mandated at every meeting. Interviews with partners, as well as discussions in the Board meetings noted above in Coherence showed that there was a significant and general level of dissatisfaction with the coordination function of the project.

Project management

The efficiency of MSU was limited by its location and absence of a project management function for the last two years of the project.  The Project Management Unit, located in Amman, was not fully staffed until year 3 of the project and was without a project manager for the last 15 months of the project. The location of the MSU was established outside of Egypt when Egypt was the site of the programs’ most important regional implementing partners and the projected location for the Climate Facility.  Several of the UNDP Country Offices noted this as an impediment to smoother implementation, reflecting on some of the challenges faced in relationship building with LAS and AWC.

The MSU was formed during the project's inception phase to implement the project work plan and coordinate the activities of Implementing Partners. To do this effectively, the MSU was designed to include a team of professionals in areas of project management and administration, climate change and the nexus to SDG achievement and human security.

COVID-19 pandemic delayed staff recruitment. Although a project manager and project specialist were on board by the end of 2019, a communications specialist who could facilitate learning across the project between partners to improve synergies, linkages, and emerging collaborative opportunities was recruited in Year 3 of the project.

Work on project activities began in a very limited way in 2019 with UN sisters and regional partners undertaking preparatory work for their activities, signing agreement with UNDP, elaborating their first-year work plans, and requesting funds transfer for the first year of activities, which were delayed. An inception report, covering the first six months of project set up was submitted to Sida but the ET has not seen it.  Webinars were used to introduce the UNDP Country Offices to the program.

In 2021, Q1, the MSU staffing was expanded with a Communications Specialist, a Project Management Analyst and an Administrative Associate.  A Climate Mainstreaming Policy Analyst, JPO joined in Q4 of that year.  The communication specialist was recruited to try to reduce the friction generated between UNDP management and AWC over their reporting capacities. When the original project manager and project specialist left in September 2022, the communication specialist took on that role with support from the UNDP Regional Hub Programme Coordinator. The three-person team of the communications specialist, Climate Mainstreaming Policy Analyst (Junior Professional Officer), and administrative assistant continued into the NCE period. There was no dedicated project manager for the last two years of the project following the cancelation of the SDG Climate Facility structure establishment. The diagram in Annex 22 kindly produced by MSU staff shows all these changes over the project period.

Financial reimbursement systems

Non-UN implementing partner financial reporting systems are not aligned with Programme (UN) financial systems and processes. As a result, processing payments for these partners was sometimes delayed, and partners had to pre-finance payments to suppliers (mostly consultants). UN-HABITAT reported delays that required them to pre-finance to keep the activity going, a practice that would create conditions for an audit finding. Financial reports to the Steering Committee were often revised, and partner financial reports to UNDP did not match the UNDP reports.

Decision-making

As the executing agency and senior supplier, UNDP approves all procurements of goods (project materials and equipment) and services (external consultants) through an established decision-making process that is well understood by and accommodated for sister UN agencies and UN Country Offices. No issues were identified here, and no delays in decision-making on Annual Work Plans were noted.

Although the decision-making process is smooth, Sida did not always find the communication on decisions sufficient.  This was felt most acutely at the level of overall project accountability, where some partners and the donor felt keenly that the transparency and dialogue necessary between UNDP and stakeholders was not there.  For example, the reasons behind the decisions to abandon the central core of the project – the SDG Climate Facility Structure – were not clear to UN partners or donors and were not clarified to the ET beyond vague statements of legal issues and governance issues which could not be resolved.

The donor also felt that UNDP was not transparent enough in discussing implementation problems in general until it was too late to rectify them effectively. This is partly the result of the reporting process. The SDG Climate Facility and the lack of evidence for outcomes achieved are some examples.

Technical support to project activities was uneven across implementing partners and time

There was a division across and between UN partners on the issue of technical support provided by the UNDP Regional Hub and MSU staff to project activities, with some feeling that levels of UNDP technical was good, others less so.  MSU staff noted the bringing together of all Country Offices at the RG inception stage to help ensure that understandings of the purpose of grants were aligned as an example of good support.

Resilience grants partners reflect that support was strong during the inception period but felt that staff changes in the MSU and UNDP Regional Hub, reduced the support to an administrative rather than a technical function. Sida noted that, in their experience, UNDP Technical Assistance specialists were not sufficiently present in the field at country level and that the Resilience Grants were implemented with little technical support from the UNDP Regional Hub. All partners reported excellent coordination with UNDP, who helped to identify and gather other potential implementing partners for partner project activities and facilitated discussions on how to scale up.

Part of the explanation for the perceived weakness in the level of quality assurance for implementation through the UNDP Regional Hub technical support may be found in the 25% decrease in budget allocations to this function in the revised 2020 budget (from US$275,000 to US$205,000).

##### EQ4.2: To what extent were resources used to address climate security issues in general and related gender issues in general

Finding # 17:  The bulk of project funds - 78% - were used to address climate security issues, with only 1% allocated to gender-related issues.

Gender resources were allocated across outputs and activities but represented a very small proportion of the overall project budget. The original budget (2019) did not allocate funds for gender experts. In the revised budget for 2020, Sida provided an additional 120,000 specifically to be allocated to gender experts to provide gender mainstreaming services to project activities. The table below shows the allocations across outputs and activities. Gender allocations were just over 1% of the overall project budget.

Table 13: Financial allocations across outputs and activities

| Level of Result | Amount | Purpose of allocation |
| --- | --- | --- |
| Output 1.3, Activities 1.3.1 – 1.3.6 | US$20,000 | Gender mainstreaming services to provide support to policy dialogues with regional and national stakeholders, highlighting how policies and actions on climate change can contribute to SDG achievement and crisis-prevention/recovery goals. |
| Output 1.4, activities 1.4.1 – 1.4.3 | US$20,000 | Gender mainstreaming service to support the development of advocacy and communications materials, including policy briefs and infographics, to raise awareness on the special risks for gender inequality on the climate security nexus to inform policy reforms. This included support to the genderized development of capacity development training activities for media and CSO stakeholders at the regional and country level to advocate for the nexus approach. |
| Output 3.1, activities 3.1.1. – 3.1.3 | US20,000 | Gender mainstreaming services to the development of capacity development work with national and sub-national stakeholders to help them integrate climate change into development and crisis prevention/ recovery policies and plans |
| Output 3.2, activities 3.2.1 – 3.2.6 | US$50,000 | Gender mainstreaming services to support the integration of gender considerations into resilience grants. |
| Total | US$ 120,000 |  |

As noted in the Effectiveness section above, the gender resources allocated was limited, and not always adequate to ensure substantial impact.

Most project resources were allocated to addressing climate security issues in general.  The breakdown of the allocations is in the table below.

Table 14: Analysis of the budget resources used to address climate issues in general directly

| Budget Category | Budget 2019 | Revised budget 2020 |
| --- | --- | --- |
| Short term Technical Specialist/national experts | 1,108,000 | 1,559,000 |
| UNDP Regional Hub advisory service | 275,000 | 205,000 |
| MSU relevant staff | 1,467,000 | 2,063,649 |
| Workshop | 560,000 | 867,500 |
| Communications | 94,000 | 94,000 |
| Equipment and materials | 2,119,000 | 2,647,000 |
| Total | 5,623,000 | 7,436,149 |
| Percentage of total budget | 78 percent | 78 percent |

##### EQ4.3: To what extent has the project implementation strategy and execution been efficient and cost effective? Do the achieved results justify the way resources (funds, male and female staff time, expertise etc.) have been allocated?

Finding # 18:  Implementation became better aligned with annual work planning over the last three years of the projects’ life, and levels of results achievements align well with budget allocations.

The alignment between planning and implementation of activities was a little uneven over the project period. Implementation lagged behind schedule for the first 18 months of the project. This is clearly reflected in the budget utilization rates reported for this period. In subsequent years, implementation efficiency improved, achieving ever-increasing budget utilization rates year-on-year. However, the relative slowdown in activity rates after year 3 as the project began to move to close out also shows.

Figure 2: Budget utilization rates over project period

The COVID-19-related delays that impacted procurement and recruitment in the first 18 months of the project were compensated for over time, and staffing adjustments were made to accelerate the activity implementation rate. In 2021, MSU's capacity for this purpose was expanded by adding a program analyst, a policy analyst, and a communications specialist.

Apart from the first-year work plan, the project did not keep a running track of delays in planned against projected implementation, so our analysis has relied on comments provided in the Annual Reports, an analysis of the progress reports against indicators—which we have used as a rough proxy for progress—and from the partners themselves.

Alignment of levels of results achievement align with budget allocations

Much of the imbalance in budget allocations for outcome 3 is accounted for by the inclusion of procurement of equipment and materials for the resilience grants - 32% of the outcome allocation -and a component to produce best practices for the overall project. If these are considered, then budget allocations are more evenly distributed across the outcomes.

When the budget allocations and levels of results achievement figures are considered in the context of the project, the apparent misalignment is more easily explained.

The program agreed to cancel the establishment of the SDG Climate Facility Structure, and so two key results under Outcome 1 were cancelled – the establishment of the Climate facility and its first activity (indicators 1.1 and 1.3.5), reducing results achievement levels under Outcome 1. Other factors which influenced levels of achievement under this outcome were the challenges associated with regional relationship building. Under outcome 3, Lessons Learned and Best Practices are still being compiled.  Results under outcome 2, which comprised most of the technical work of UN partners, were fully achieved.

Table 15: Summary table of allocations of budget over project outcomes

| Result area | Budget allocation in US$ | Percentage of total allocation | Percentage of results fully achieved |
| --- | --- | --- | --- |
| Outcome 1 | 1,004,212 | 11 | 55 |
| Outcome 2 | 1,461,070 | 17 | 100 |
| Outcome 3 | 6,307,216 | 72 | 71 |
| Totals | 8,772,498 | 100 |  |

Table 16: Summary table of the level of achievement indicators by outcome

| Not Achieved |  |  | Partially Achieved |  | Fully Achieved |  | Output achievement per outcome |
| --- | --- | --- | --- | --- | --- | --- | --- |
| % | # |  | % | # | % | # |  |
| 18 |  | 2 | 27 | 3 | 55 | 6 | Outcome 1 |
| - |  | 0 | - | 0 | 100 | 11 | Outcome 2 |
| - |  | 0 | 24 | 4 | 71 | 12 | Outcome 3 |
| 5 |  | 2 | 18 | 7 | 77 | 29 | Totals |

##### EQ 4.4: To what extent have project funds and activities been delivered in a timely manner

Finding # 19:  Delivery of projects funds was overall timely but were sometimes delayed by inefficiencies and misalignments in financial reimbursement systems. Delivery of project activities were impacted by COVID-related delays in first two years of implementation but improved significantly in last 2 years of project life.

Financial support to project activities was not always efficient. There were times when project reimbursements were delayed to the point that implementing partners had to use their own funds to pre-finance payments so that activities could continue. As noted in Finding # 16, issues with the need for further alignment of UNDP’s financial reconciliation and reimbursement systems with regional partners caused some delays in payments for consultants hired.  This required some pre-financing by partners, which created problems within their own financial systems. UN Habitat also had to prefinance some activities as UNDP reimbursements were delayed.

Impact of COVID-19

Project activities were delayed by COVID-19 and the subsequent knock-on effects which affected overall activity scheduling. The timeliness of delivery of project activities varied by outcome due to the nature of the work (technical research versus physical implementation in a field context) and knock-on delays from COVID-19 impacts in the first 18 months (procurement and reversion to online modalities, which limited some aspects of relationship building). For example, in Year 4, significant delays against projected schedules were reported under the resilience grants, which were effectively remedied in Year 5. The 2021 Board minutes report that the overall midterm delivery was below 40%. Activities that were not completed on time (i.e., according to schedules projected in work plans) or whose results were not fully achieved were often those activities that depended on a large investment of time in relationship building. For example, the alliance of Climate Change champions drawn from regional member states and the convening of private sector roundtables on climate finance had not been completed by the date of completion of the draft 2023/2024 Annual Report.  The delay in the completion of the documentation on lessons learned and best practices was the result of delays in activity delivery and completion.

##### EQ4.5: To what extent has the project M&E system ensured effective and efficient project management

Finding # 20: The M&E system's ability to effectively and efficiently support project management was limited overall by the need for an embedded learning process, but also by the lack of indicator definition, operationalization, verification sources, frequency of reporting, and dedicated staff.

Missing elements in the M&E system

In terms of project design documents, the project does have a ToC, but it is unconventional in that sense that it does not show the results chains that link results at every level of the project, from output to outcome to impact, to allow a visual understanding of the changes created by the interventions. The outcomes are defined, but they are formulated as simply a mathematical accumulation of the outputs. No overall project goal is defined to which the outcomes were intended to link.

Most indicators were numerical counts of outputs achieved. Others, which had baselines, were more open to interpretation as the criteria for what constituted ‘low’, ‘medium’, ‘high’ was not defined. (For example, how would you assess whether the ‘level of enhanced understanding of nexus approach to climate action and SDG’s’ was low, medium or high. What evidence would you look for? Among which groups?). The Results Framework is well-developed, and the indicators are simple and well-defined. There is no overall M&E plan which integrates the indicators with the baseline figures, the annual targets, the data collection responsibilities (who collects the indicator data), and the frequency of data collection. The partner reporting template is well designed and fit for purpose, covering all essential aspects of the implementation. A risk log was developed at project start-up, and although a quarterly update was mandated, the ET only saw the Annual Updates in the Annual Reports.

Regarding process and systems, there was never a dedicated M&E focal point within the MSU. At project start-up, the project analyst had other functions, including M&E, and the communications officer also had two hats, M&E work and Communications. Discussions with the Beirut office revealed that there was no M&E function in the Beirut office, only a reporting function.  The staff members were responsible at the regional level for receiving the SDG Climate Facility reports and ensuring they complied with UDNP regional policies.  She had no role in developing the reporting, nor did she monitor and analyse the M&E indicators against targets.

The SDG Climate Facility is only one part of UNDP’s regional projects and is linked to the Regional UNDP Strategic Country Plan and Regional Results Framework. The SDG Climate Facility reports its results into UNDP’s regional level outcomes, which are at a higher level and are aligned to UNDP’s regional outputs and outcomes. The “outcomes” of the SDG Results Framework are in fact “outputs”, they are only called outcomes to satisfy some of the partner requirements.

Outputs of the Resilience Grants are very loosely aligned to SDG indicators. Each grant has its own M&E plan and indicators, limiting rollup into overall output achievements. No region-wide indicators were embedded into the pilot grants to enable the measurement and comparison of approaches across countries. UNEP-Fi had little opportunity to link with pilot projects, many of which focused on private-public partnerships, to share experience and learning.

No learning process was embedded at project level beyond the summaries of Lessons Learned, which were distilled into the Annual Report based on the partner reporting template.

In the absence of a dedicated M&E focal point, reporting on the achievement of progress against targets is accomplished by various parts of the project management function within the UNDP Regional Hub or within the MSU. For example, staff of the UNDP Regional Hub undertook reporting on progress achieved against the targets of the resilience grants. The reporting of lessons learned began in the first year of implementation, allowing sufficient time for these to be fed back into project implementation practice. Annual Project Quality Assurance is accomplished through the input of data showing the achievement of progress against targets. Reporting on project progress is done annually through the partner reporting template.

Impact of missing elements on support to results achievement

As almost all indicators were numerical and output-based, there was little room for discrepancies in data, even when performed by different staff members. Some of the indicators (those that had baselines) were more open to interpretation, leading to potential misstatements of the level of achievement of progress against targets.

There was no attempt at the overall project management level to align the SDG indicators with those being developed for the resilience grants. Each resilience grant has its own M&E plan and indicators, limiting rollup into overall output achievements.

According to WFP, the emerging results of all the activities at an overall level, the quantitative and qualitative changes underway, were never clear.

Annual reports provided regular updates on output progress but were limited in analytic content until the last two years. As a result, there was never a clear picture of how, and to what extent, activities were coming together. As noted under EQ1 above, partner coordination was often achieved or mandated during Board meetings.

The need for a learning process embedded at project level, which could enable the sharing of experience and approaches on a regular (quarterly) basis, undercut the potential for a more efficient project management.  This was felt particularly keenly by Country UNDP offices who were managing resilience grants, several of whom had expressed the hope for a more structured exchange of learning opportunities being facilitated. In the absence of a process for shared learning, the country level grant staff felt like they were ‘standalone’ efforts. This challenge regarding a seamless learning process also meant that course correction efforts were undercut.

Some country offices were not aware of the project-level indicators

A preponderance of output level indicators meant that stories of significant changes made in capacities, attitudes, perceptions because of project activities were not measured. As a result, all changes at outcomes level were in the form of anecdotal evidence. While the evaluation attempted to present higher level benefits of the project, the true value of the project at the level of outcomes might not be fully captured, which represent a lost opportunity.

##### EQ 4.6: Was the communication and visibility strategy for the project adopted? Was it cost effective in terms of promoting the project and its achievements?

Finding # 21: Although no overall project communication plan was developed, every knowledge product had its own well-developed unique plan and strategy. The involvement of CSOs as advocacy partner at the local and national level may have improved the cost-effectiveness of communications work overall, but its overall impact on promoting project achievements remains anecdotal and empirically unknown as no indicators were developed to measure its success.

While there was no overall communication strategy for the overall project, a KI informed the ET that UNDP had a three-phase quality assurance system for each of the knowledge products. Each product branded as UNDP requires its own communication strategy, even if it is not UNDP that is launching the product. So, when each knowledge product was launched, it had a set of social media cards or a communication, depending on its target audience. Each one of the products was launched at a different event, and the most significant products were launched at COPs, and MENA climate weeks. Gender knowledge products that were the product of several UNDP units/departments were/are launched together at different events, maybe even by partner organizations.

CSO involvement in project advocacy

CSO’s were not involved in project advocacy although they received advocacy training. The strategies originally employed for awareness/advocacy and sensitization were rather staid and conventional, including workshops, side platforms at regional events, etc., unsupported by local and national-level advocacy work on policy dialogue, which could have been effectively led by CSO’s, who – as noted above in finding # 21 - were not included in any strategic role in the project.  Leveraging social media for message dissemination was only developed when the communications specialist was brought on board after 27 months of project implementation.

### Impact

EQ 5:  The extent to which the SDG-CF project generated – or is likely to generate – directly or indirectly, positive and negative, intended or unintended higher-level effects.

##### EQ5.1: What is the overall direct and indirect impact of the project, considering positive and negative, intended or unintended effects of the project implementation?

Finding # 22:  The project has directly and positively impacted the acceptance of the notion of the climate security nexus in the region and its potential use in policy formulation and has contributed to the growing community of practice on integrated and innovative solutions to climate change. Indirectly, the project has accelerated climate security nexus financing and supported the development and launching of new regional climate security projects. The fact that the project is supporting such changes provides reassurance about the project's ultimate effectiveness.

No overall goal is defined for this project as explained in the Relevance section above. To assess impact therefore, we are taking as a proxy project goal the regional priorities narrated in the project document to which the project is designed to contribute to, namely:

- Delivering climate-oriented solutions that address climate challenges and bring co-benefits across the SDGs,

- Scaling up access to and delivery of climate finance, including through innovative partnerships with the private sector

Evidence of direct results beyond the outputs/outcomes

The extent of the impact can be attributed to four factors: the project's activities in the region, changes in the external context related to climate change, changes in regional and global perspectives on climate change issues, and new legislation and regulations in place in the region. These changes were not warranted to be significant enough for a revision of the Toc.

While there was a general belief that establishing the climate facility would lead to transformative outputs, the facility was ultimately cancelled as discussed in the effectiveness section above. Through interviews with partners, stakeholders, and UNDP program staff, and reviews of Annual Reports, we have identified several positive changes that the project has contributed to. These changes, which go beyond the project's outcomes, are related to the regional environmental and climate change priorities identified at project inception. Observing these changes during the project's implementation and towards the end of the project provides reassurance about the project's ultimate effectiveness.

The effectiveness section details the effects linked to outcomes. Going one step further, the project could reasonably claim to contribute to the following direct impacts.

- The concept of the climate security nexus agenda is now more widely accepted in the region. During project implementation, some partners felt that the terminology of Climate Security was inappropriate for the region due to the sensitivities of ‘security’ in countries with tense and volatile internal contexts. However, by the end of the program period, climate security was being used widely and freely in regional platforms.

- Arab states are considering nexus in their policy formulations. While some stakeholders felt that regional policy changes attributable to the project were anecdotal speculations, MSU staff, who attended discussions at COP and regional MENA platforms in the last year of the project and made multiple presentations of the projects Knowledge Products at these forums, were strongly convinced that the regional environment is changing towards an understanding of the integrated nature of regional climate challenges and that the project had played a part in this.

- The project has contributed to the growing community of practice on integrated and innovative approaches to the nexus between climate change and human security through the resilience grants.

Evidence of indirect impact

The project's positive indirect impacts were quite substantial with strong sustainability elements but with a limited and incidental linkage to the project objectives themselves.

Many UN partners felt - and MSU staff interviewed on this agreed - that the project had helped Partner UN agencies to start new Climate Security – related programmes and leverage new resources in the region and beyond. Annual Reports confirm this. The following are some examples:

- At the time of project inception, UNEP-Fi noted that the notion of sustainable finance was nascent, but by project end their regional staffing had expanded from 30-200 people. Project funding allowed them to expand outreach, helped them to develop UNEP-Fi global programmes to support banks in emerging markets and developing countries around de-carbonization

- WFP reported that the project helped them to start new programs and leverage new resources. In particular the project helped them build own fully fledged program in the region on Climate Security by using synergies with country counterparts, and the evidence they needed, to develop a multi-year global program integrated into WFPs existing country strategy plan, raising US2 million in the process. UN partners who took advantage of this notes that ‘although the project had not asked us to do these things, but we did because it made sense.’ (KII)

- As of April 2024, the project was able to mobilize USD17 million to scale up the country resilience pilot project that have been implemented in Jordan, Yemen, Iraq, Tunisia and the State of Palestine through partnerships with GEF, Canada, Japan, Germany and the private sector, with an additional USD27 million in the pipeline for Yemen through GEF and KfW. The longer-term replication of these grants was thereby assured.

Positive and negative effects of project

The impacts at various levels were affected by the same implementation and contextual factors, producing both positive and negative effects.

Implementation strategies around communication were strong in UNDP-sister UN Agency relationships and in the presentation of project outputs in regional forums and gatherings. This allowed for strong project advocacy at the regional level and good working relationships between UNDP and its sister implementers.

However, the LAS in particular, and other implementing partners in general, felt that while advocacy was essential to ensure that the project was well supported and understood at all levels, in all cases, dialogues must go beyond governmental partners to nongovernmental organisations and the private sector so that a real impact of activities can be seen on the ground in the form of tangible benefits to local communities. In their opinion, the project did not achieve this because of lack of funding and community involvement. A review of the documentation on the resilience grants shows that out of the 7 grants, only 43% (3) of them involved the private sector in partnership, 57% (4) involved the local authorities in implementation, and only29% (2) involved NGOs in implementation partnership. All seven of the grants, however, had extensive governmental involvement.

Implementation strategies in terms of overall coordination were too weak for a project of such complexity, with so many implementing partners across multiple locations. As a result, when the SDG Climate Facility Structure was cancelled, implementing UN partners felt that the program was further transformed into simply a funding mechanism for developing their own Climate Change country strategies and programs in the region.

As one UN agency KI pointed out, the regional operating context changed substantially over the project period.  These changes were reflected in the annual regional COP forums. Over the project period 2019 – 2023, the impact of COVID accelerated work on climate change, and a key COP milestone that impacted all states in the Arab region was the compensation fund set up to compensate those countries most affected by climate change. Over the same period, the GEF expanded its financial resources by 30% from 4.1 US$ billion to 5.33 US$ billion, and the GCF nearly doubled in size, and projects funded leapt from 5 to 11 billion by 2023. Although the Arab region lags significantly behind Africa, Asia, and Latin America in terms of projects, both funds, these past 4 years have shown that funds are more available, and a lot of innovative designs and technologies are being applied in the Climate security nexus approach.

##### EQ5.2: What could have been done differently to achieve a more transformational change

Finding # 23:  The transformational change envisaged would have been supported better with a project design which focused on comprehensive and current risk identification, the development of activities with a  gender-sensitive lens,   an embedded learning process, better allocations of staff time, and co-locating the MSU at least in Cairo, if not in the LAS.

The program was a unique and innovative regional endeavour with multiple partners involved in activities, the results of which were intended to be linked in a physical climate facility located in Cairo, Egypt, under the ownership of the LAS. Activity results were also intended to inform local, national and regional policies of partner countries in the region on linking climate security considerations with human security into their development and crisis recovery programming.

KIIs, project reporting, and partner and beneficiary surveys showed mixed results. The ET feels that the following overall actions may have supported more transformational change.

- Locating the MSU physically in Cairo with frequent visits from the program's regional coordinator would have promoted more effective relationship building with the program's main beneficiary, LAS, connecting daily with officials in the LAS sub-committees to identify and man issues and obstacles early. The optics of not having the MSU in the LAS's physical space may have led to challenges in the day-to-day joint dedication, communication and management that is acceptable to both UNDP and LAS.

- Such a complex set of activities requiring careful integration and connections for best impact, would be better implemented within a carefully phased approach, allowing for periodic reflection on progress through an embedded learning process. Many of the weaknesses in the implementation modalities detailed under effectiveness (limited activity synergies, mutually reinforcing elements) are a direct result of a closed-ended project design, which did not allow for a more flexible implementation strategy and regular learning across project activities.

- A more limited number of implementing UN partners at project outset (maybe first phase) would have allowed a more complete testing of the approach on the development of knowledge products and their practical integration into national, regional policy.

- Project design and ToC processes were not adequately linked to the reality on the ground including institutional capacities and vulnerabilities at regional and national levels and the presence of regional, national and local research institutes and non-governmental organisations.

- A  ground-truthed pre-assessment of regional, national and local capacities and vulnerabilities instead of a document review approach would have allowed for a better identification of some  of the gaps that only became apparent during the implementation period, such as the limited capacity in communications in the AWC, the need for gender expertise throughout, and the level of investment needed in relationship building and coordination required to ensure mutual complementarities and reinforcing elements between activities.

- The scheduling of the knowledge products should have allowed sufficient time for the discussion, input, reflection, and revision of the product at national and regional levels before its official launch at the regional level. This would have facilitated a better uptake of the substance of the knowledge products at the national and regional policy-making levels.

- Senior gender expertise should have been on board during the design process and the entire implementation period. Gender is a cross-cutting issue

- A dedicated M&E function should be housed with the MSU, so that lessons from project implementation can be used to immediately course-correct and improve the efficiency of project management.

##### EQ5.3: To what extent did the project achieve the intended impact as measured through the contribution to the identified outcomes and outputs, the SDG’s and regional and environmental climate security priorities

Finding # 24: While the project achieved most of its outputs, the key integrating output of the Climate Facility was not achieved. The project contributed to SDGs and regional and environmental climate security priorities, but evidence of outcome achievement remains limited. As a result, although there is evidence of both direct and indirect impact, the intended overall project impact was not realised at regional level but was well realised at national and sub-national levels.

Project contribution to outputs and outcomes

See the section on Effectiveness above.

Contribution to the SDGs at the regional level

According to the design summaries in the Interim Report, 2022, the combined resilience grants contributed to all 17 of the SDGs. All grants were designed to contribute to SDGs #5 (Gender Equality) and #13 (affordable, scalable solutions, low carbon economies, population displacement, mortality, instability, and conflict). A table with the full analysis is provided in Annex 13.  By the time of finalizing the evaluation report, we had not yet received any reporting on the resilience grants, so we have not been able to provide an aligned and in-depth analysis of how they contributed to the SDGs they were designed to link to, beyond data found in the Annual Reports, Interviews, and beneficiary surveys.

##### EQ5.4: What is the impact of the country's resilience grants?

Finding # 25:   According to beneficiaries, the resilience grants have been successful in providing high levels of confidence regarding longer term benefits.

The long-term impact of the resilience grants was assessed by the beneficiaries themselves across all countries except Palestine, indicating that beneficiaries had high levels of confidence in the long-term effects at the level of themselves, their families, and their communities. For details, see the table below.

Table 17: beneficiary answers to the question “the support/project will contribute to improving my/my family’s/my community’s living conditions in the long term”

| Dimension/Country | Egypt | Iraq | Yemen | Tunisia | Jordan | Average across dimension |
| --- | --- | --- | --- | --- | --- | --- |
|  | (All figures in percentages) |  |  |  |  |  |
| Benefit me | 100 | 95 | 78 | 100 | 100 | 95 |
| Benefit my family | 100 | 95 | 78 | 100 | 83 | 91 |
| Benefit my community | 100 | 95 | 78 | 100 | 100 | 95 |
| Average across country | 100 | 95 | 78 | 100 | 94 |  |

The project's impact on achieving gender equality and youth empowerment, particularly through employment generation, was noted by 38.5% of respondents to a large extent and 15.4% to some extent.

The resilience grants brought benefits across SGDs in delivering climate security solutions to human security problems using an approach that took account of local vulnerabilities across a range of socioeconomic dimensions.  The resilience grants were also able to scale up access to and delivery of climate finance through innovative partnership with the private sector. See Effectiveness section for the evidence of this.

The Interim Report of 2022 stated that this independent evaluation report was to include an in-depth analysis of the grants’ impacts on alleviating poverty, enhancing human security, and sustaining peace and conflict prevention. The 2022 Interim Report on the resilience grants explained that the grants themselves tackled interlinked challenges ranging from unsustainable natural resources management, youth unemployment, gender inequality, the impact of climate change on water resources, the increasing frequency and magnitude of climate-induced disasters, political volatility, and local insecurity and tensions,  at the local level in 7 countries in the region and were developed using cross-cutting approaches going beyond traditional siloed and sectoral development approaches.

As we have no reports from the projects beyond this, it has not been possible to assess the grants' impact usefully. Our brief comments here reflect information gleaned from the Country Office responsible for the implementation, document review, interviews, and surveys.

The Tunisia report detailed the very impressive scale-up of funding for the replication of the grants in  Tunisia, Iraq, Jordan and the State of Palestine for delivering climate-oriented solutions for human security as elaborated in the research conducted by UNEP FI, and in the context of the UNDP led Ministries of Finance for Climate Action initiative, which include lessons learned on leveraging multilateral and bilateral climate finance sources and removing barriers to expand the private sector engagement and investment in climate action to increase.  For the long-term impact on the project beneficiaries, see Section 5.3 above.

##### EQ5.5: What worked well and what can be done better in future similar interventions?

Finding # 26: The Project advocacy process at regional level, communications with project partners, inclusive national and sub-national level programming stand out as project processes that worked well and successfully supported the achievement of project objectives. Refer to section 5.2 above for a broad vision of what could be done better in future interventions.

Communication, project advocacy, and inclusive programming

Communication between and among UNDP and its partner organizations was excellent, as confirmed by all implementing UN partners. The design of resilience pilots proved was done in collaboration with the local communities, allowing each community's unique vulnerabilities to be identified. In addition, the communication/advocacy work done on the presentation of the Knowledge Product at the various regional events had a strong impact.

##### EQ5.6:  What have been the intended or unintended gender impacts of the SDG –Climate Facility Project? (access to control of resources, social norms change, gender practical and strategic needs, gender roles etc?) How were the impacts mitigated? What could be improved to ensure more effective contribution to gender equality and women’s empowerment? Effects on vulnerable and marginalized group

To avoid duplication of narratives, please find full details and analysis of gender impacts in   Effectiveness section, 3.5 above.

### Sustainability

##### EQ6: Analyse whether the benefits of project activities are likely to continue in the long-term after donor funding has been withdrawn.

##### EQ6.1:  What is the chance that the stakeholders’ capacities, resources and ownership will be sufficient to sustain the project benefits?

Finding # 27: Chances for sustaining project benefits are strongest where stakeholders have demonstrated increased capacity and ownership of project benefits and external funding has already been committed. Where project benefits require additional capacity and financial investments to be operationalizable, the chances of sustainability are quite weak.

At regional level, key sustainability challenges are availability of funding and ownership of project outputs, with stakeholder capacity issues being of less concern. At national and sub-national levels, the challenges are similar, but prospects for sustaining benefits for the longer term are overall more promising than at regional level as project activities have already attracted significant amounts of external funding.

Regional level

The stakeholders' capacities, resources, and ownership within the AWC and its partners appear to be well-aligned to sustain the project benefits beyond the program's duration. The project has established a multi-partner platform (RCSN) that includes LAS, UNDP, WFP, UNEP-FI, UNDRR, and UN-Habitat, which collectively work towards regional and national-level activities. This collaborative approach helps to ensures that the operational arrangements will continue beyond the program's duration.

AWC’s capacity in research and advocacy was built during the project with TA from UNDP and has made significant progress over the project period in its capabilities which are reflected in the research products completed around climate security issues and the role of private financing in the acceleration of climate action initiatives, and advocacy for the climate nexus approach in moving forward on climate action.  In the absence of the planned climate facility, the AWC could play a useful role in preparing climate security research and policy papers for high level regional forums.

AWS also has strong presence/role within the RCSN and could help energise its work around its mandate to guide and shape regional policy direction on climate security using the White Paper ‘Accelerating Private Finance for the Arab Renewable Energy Transition’ as one of the key reference policy documents. The more fluid communities of practices supported during the project period will continue without the need for additional resources and benefits will continue to flow to the organisations and institutions who use them. Benefits resulting from capacity building activities whose outputs/products have remained at the dissemination stage and require additional capacity building and funds to move forward are less likely to be sustained.

National and sub national levels

While significant capacity development activities have been provided at national and sub national levels in the region, access to finance remains a major constraint to sustaining project benefits. There are exceptions to this where external finance for scaling up has already been achieved. Examples of financial constraints include the capacity building assistance provided to national partners to mainstream climate security considerations into national plans and policies plans. This may have promise, but there is yet no data on how the methodology has been operationalised, how much it costs and what level of external funding is likely to support it.  Likewise, the guidelines produced by the UNEP-Fi on developing guidelines for commercial institutions to produce climate related financial products and services cannot be adopted by smaller commercial institutions without financial support.

The outstanding examples of sustainable project benefits are those of the resilience grants, almost all of which have been able to attract significant levels of funding for scaling up. Capacity building assistance has also been provided during grant design and implementation, and some of the grants demonstrate strong levels of local ownership.  For a detailed analysis of overall sustainability prospect of the project's resilience grants, see Annex 23.

##### EQ6.2: Was the project capable of leveraging additional resources to ensure that financial resources would be available to sustain the environmental and climate security benefits achieved by the project?

Finding # 28:  Several successes have been registered by the project in leveraging additional funds to sustain environmental and security benefits achieved at regional, national and sub national levels

Regional level

At the regional level, AWC demonstrated significant efforts in leveraging additional resources. The collaboration with various UN organizations and mentions of a possible phase 2 proposal indicates a strategic approach to scale up finance, reach more beneficiaries and continue to address climate security issues. AWC interviewee noted "The success of this study led to the development of a phase 2 proposal to continue the study in other countries and move from assessment to implementing solutions". This suggests that the project has laid the groundwork for future funding opportunities to sustain its benefits.

Like AWC, LAS also demonstrated success by attracting additional funding through its strategic partnerships. The Ambassador from LAS mentioned, "We emphasized maintaining this codeshare arrangement throughout because the university also had significant representation in the Arab region... enabling us to secure grants from UNDP for various national projects.”

The UNDP Regional Program for Arab States has a diversified funding base, with key donors including the governments of Sweden, Japan and Korea, the European Union, MBRF and CG. This diversified funding base is crucial for ensuring the continuation of project benefits beyond the program's duration.

National and sub national levels

At the local level, capacities to leverage additional resources are strongest where the project has strong buy-in both from the community and the implementing partners, and weakest where project management capacities are limited, local bureaucratic regulations are present, there is a lack of sovereignty over energy resources, and social tensions and political instability are prevalent.

In Egypt, local stakeholders, including community organizations and municipal authorities, played a pivotal role in mobilizing financial and in-kind contributions. Furthermore, the project in Iraq efforts to secure future funding through local government channels were mentioned: "We have opened the local government; the next budget will include some (allocation) that allow us to sustain this project". In Palestine the project secured co-financing from the Government of Japan for Palestine's COVID-19 response, nearly doubling the funds available from the SDG Climate Facility project. This additional funding ensures that the project can continue to deliver benefits even after the initial funding period ends. However, the local councils expressed uncertainty about the longer terms financial sustainability of the solar energy systems, citing risks such as the Israeli control of energy sources and the limitations imposed by the Paris Economic Agreement.

In Tunisia. The involvement of international donors and the success of previous projects related to climate change have positioned the municipality to seek further support. However, there are concerns about the continuity of funding. The FGD local government participants expressed frustration about the potential end of the project but emphasized the importance of employing the municipality workers' enthusiasm their strong desire to ensure its continuity.

The "Qat-to-Coffee" project in Yemen secured parallel co-financing from KfW for resilient water resources management, amounting to EUR 15 million jointly implemented by FAO and UNDP. The “Decentralized Renewable Energy Solutions” project has a clear strategy to attract private sector investment. The document mentions UNDP has secured the interest of a private sector company in each of the target locations for WtE co-ownership and operations, which indicates a proactive approach to leveraging additional financial resources to sustain the project's outcomes.

##### EQ6.3:  Are there any social, political or financial risks that may jeopardize the sustainability of the project contributions to the climate and climate security nexus at the regional level?

Finding # 29: Risks to the sustainability of project contributions to the climate and climate security nexus at the regional level are primarily political and financial.

Political risks include conflicts in the region that exacerbate existing challenges. Another key informant pointed out: "Our region faces particular challenges due to conflicts... ". The impacts of climate change exacerbate existing challenges—issues such as land degradation, desertification, variable rainfall, floods, and dust storms are prevalent. These ongoing conflicts pose significant risks to the project's sustainability. Political risks include the difficulty in engaging with government stakeholders. "There were some limitations to the degree to which we could reach the government stakeholders who I think we're very vital to the... utilization of this production of this product" (KI).

The AWC has identified several risks that could impact the sustainability of the project contributions, particularly political instability and conflict in the region. Political instability, conflict, and social and economic shocks have negatively affected the investment climate over the past decade. Additionally, financial risks are present, particularly in attracting investments and climate finance in conflict-affected areas. Climate Change, Conflict, and Fragility are intimately linked, one reinforcing the other, often in a complex systemic environment. Attracting investments and climate finance to climate actions in such contexts becomes riskier and more difficult.

Securing sufficient and regular funding is a long-term risk to sustainability The Ambassador from LAS expressed concerns about insufficient funding: "The progress has been slow, mainly due to insufficient funding and limited local community engagement" (KI).  In addition, social and cultural factors will continue to impact on the sustainability of project contributions including the continuing weak levels of access of women and the marginalised to land and other resources, weak involvement of women in general in public sector work in sub-national communities and continuing discriminatory practices to immigrant and minority communities.

##### EQ6.4: To what extent will target men, women and vulnerable groups benefit from the project interventions in the long term? What could be done to strengthen existing strategies and sustainability to support female and male project beneficiaries, as well as vulnerable/marginalized groups?

Finding # 30: Prospects for the sustainability of long-term benefits are mixed. Positive indicators are present but negative factors are very prevalent. Continued capacity building and improving levels of community engagement will help to sustain long terms benefits to project beneficiaries including vulnerable groups

Positive indications for longer term benefits to the projects’ target groups include improved employment opportunities, steps towards women’s empowerment and economic independence, but negative factors, including cultural barriers, need for stronger local project ownership, and lack of clarity on marketing strategies for products, remain challenging.

The project has made efforts to address the needs of vulnerable groups at the regional level. One KI mentioned the focus on social vulnerability and gender studies: "We worked on one of the important topics, which is social vulnerability in the Arab region under climate impacts... We also developed a training package ready to be used in different countries to support this idea". This indicates that the project has developed tools and methodologies to support vulnerable groups. However, one KI expressed concerns about the project's overall impact: "Honestly, if we look at the ground reality, the impact is minimal. The progress has been slow, mainly due to insufficient funding and limited local community engagement" suggesting that while the project has laid the groundwork for supporting vulnerable groups through a regionally developed process, more efforts are needed to ensure these benefits are sustained in the long term.

The resilience grants have demonstrated significant long-term benefits for men, women, and vulnerable groups locally. Men have seen improved employment opportunities through enhanced vocational training programs, women have gained economic empowerment and financial independence, particularly through microfinance initiatives, but still face cultural barriers and gender biases. Vulnerable groups, including people with disabilities and marginalized communities, have seen notable improvements in their quality of life due to the project's inclusive policies These changes have fostered a more inclusive environment, enhancing social cohesion.

A focus on water and energy solutions has been instrumental in addressing critical needs of vulnerable groups and the involvement of local women in training and awareness programs is a positive step, but the ability to maintain operations and secure ongoing support is crucial and the lack of a dedicated operational body (such as the Facility) pose risks to continuing long term benefits. Short project duration and lack of marketing opportunities are also factors which undermine sustainability. Projects which have been able to establish regular and significant revenue streams will continue to provide benefits to target groups.

Interventions which can strengthen existing strategies and sustainability

Community engagement, capacity building focused on women, support to project which seek to achieve transformational gender changes, the integration of strong cost-recovery components, building accountable private-public partnerships and the integration of pilots into pilots to demonstrate benefits of alternative use of resources.

The midterm review (MTR) of the UNDP Regional Programme for Arab States (2022-2025) highlights areas where sustainability is less certain due to insufficient follow-up and engagement. For example, while the SDG Climate Facility Project has made significant strides in launching a regional climate security agenda, the follow-up at the country level has been mixed.

##### EQ6.5: To what extent are lessons learned documented by the project team continually and shared with appropriate parties who could learn from the project?

Finding # 31: Documentation and sharing of lessons learned has not been consistent, systematic nor yet comprehensive, limiting the uptake of learning from the project.

The major challenges to learning within the project was the limited systematic learning cycle embedded in the project design which limited the ability to document and share lessons learned and insights effectively and support timely key project decision-making.

The limited regular connectivity and systematic exchange among the offices and partners implementing the resilience grants. One interviewee highlighted this issue: "More connectivity and systematic exchange/learning was needed among the offices/partners implementing the resilience grants, and also among UN sister organizations". There was also limited illustration or evidence of vertical linkages between the program activities under knowledge products and research and the resilience grants. This need for coordination has hindered the project's ability to leverage collective knowledge and experiences effectively.

# 4. Conclusions and Recommendations

### Conclusions

Conclusions

- Overall, the project’s design was innovative, in alignment with SDGs, yet in need of further articulation. The project vision and conceptual framing was pioneering, fully aligned to UNDP’s commitments to the SDGs, and intended to bring mutually reinforcing change through exchange of experience and building on lessons learned from implementation. However, the lack of a formal risk assessment during the design process gave staff a limited amount of preparedness to meet and mitigate emerging challenges. The utilization of diverse resources in a desk review on climate change, human security, gender assessments- while helpful in the project's design and accompanied by a consultative process, was not able to identify the needs and risks grounded in the current capacities and vulnerabilities of the region and its component countries.

- Evidence shows that women were core beneficiaries of the project; yet gender mainstreaming and inclusion was weakly achieved. The absence of a designated gender expertise at the design stage did not allow the design to take gender-mattering and women empowerment as integrative to the overall project and resilience grants, although opportunities for meetings of the CO’s were provided. As a result, the project placed great focus on including women in their activities to ensure that numerical targets were met.

- The effectiveness of implementation modalities was mixed. Collaborative partnerships added value to the overall project, but coordination mechanisms were not sufficiently able to fully capitalize on this approach's benefits. The limited integration of knowledge products into policy frameworks resulted partly from a limited focus on partnership building and multi-level dialogues. The multi-partner approach facilitated the integration of various initiatives, ensuring a comprehensive and effective response to climate security challenges. However, challenges in coordination and communication among partners were noted.

- While the project demonstrated complementarity at the local level, there were challenges in fully integrating and coordinating with other ongoing actions at the regional level. The integration of cross cutting issues in different country contexts has been well achieved and the project demonstrated strong coherence to UNDP’s corporate gender strategy and to the SDG’s selected. Overall, the project demonstrated coherence with UNDP's corporate gender strategy and the SDGs through its efforts to promote gender equality, women's empowerment, and address the interconnections between climate change, gender, and human security.

- Results achievement was overall effective, except for the cancellation of much of Outcome 1 activities. Overall, the levels of achievement of project results across activities and outputs were good but intended impact was sometimes weakened by late delivery of outputs. Moreover, implementation delays caused by the outbreak of the COVID-19 pandemic created inefficiencies over time. The project was granted a No Cost Extension to allow completion of activities.

- Management structures supported the achievement of project results. The flatness of the management structure created efficiencies which were, at times, challenged by the overlapping of executive and beneficiary roles and limited inclusion of civil society from the accountability framework. The non-hierarchical structure naturally leads to greater efficiencies in procedures, decision-making, and concentration of accountability. Moreover, there was a need for additional human resources to encompass the full range of competencies needed, including M&E, partnership management, and policy making.

- The project's M&E system was somewhat developed yet has some missing elements which undermined its efficiency in supporting project management and showcasing the true value of the project. The M&E system's ability to effectively and efficiently support project management was undermined by the lack of an embedded learning process, and also by the limited indicator definition, frequency of reporting, sources of verification, data collection, and dedicated staff.

- The communication and visibility strategy for the project knowledge products was well developed but cost-efficiency could have been improved. At the same time, implementation planning was efficient, and the results have justified how project resources have been allocated. The cost-efficiency of communication and advocacy work may have been improved with the involvement of UN agencies and CSOs as partners in advocacy for the project messages around the knowledge products. Implementation delays caused by the outbreak of the COVID pandemic created inefficiencies over time. The project was granted a No Cost Extension to allow completion of activities.

- Against this backdrop, the intended level of project impact was not sufficiently captured due to limitations regarding systematic evidence. There is some anecdotal evidence of direct impact, and evidence of substantial direct impact, which was not, however, proven to be directly linked to the project activities outlined in the projects Results Framework. While the extent of the impact was affected by internal and external factors, the intended level of impact has not been captured due to limitations in the M&E system as stipulated above. Limited evidence on impact suggests that the extent of impact is linked to four major factors:  implementation strategies, which were inadequate in terms of overall coordination for a project of such complexity, with so many implementing partners across multiple locations; weak community involvement and ownership; and limited funding.

- Prospects for the sustainability benefits of project are stronger at the country level, and more mixed at the regional level. Chances for sustaining project benefits are strongest where stakeholders have demonstrated increased capacity and ownership of project benefits and external funding has already been committed. Where project benefits require additional capacity and financial investments to be operationalizable, the chances of sustainability are quite weak. Several successes have been registered by the project in leveraging additional funds to sustain environmental and security benefits achieved at regional, national and sub national levels.

Recommendations

The recommendations below are informed by the conclusion that there is a need to continue support for the UNDP present efforts to protect investments already made and capitalize on lessons already learned.  The Evaluation Team argues that if the report’s recommendations were properly implemented, UNDP would be the appropriate mechanism for continuity. On the one hand, UNDP has historical experience and institutional comparative advantage as stated in other parts of the report. On the other hand, UNDP had accumulated rich experience during the past years with the SDG CF project and it would be more cost-effective to develop the SDG CF based on the recommendations rather than venturing into any other options. To guide future planning efforts that build upon the current project, AWRAD developed a series of action-oriented questions designed to prompt strategic thinking and drive meaningful outcomes.

| Recommendation # | Recommendation linkage to criteria | Recommendation for the use of |
| --- | --- | --- |
| 1 | Relevance, Sustainability | UNDP, Sida |
| 2 | Relevance, Effectiveness | UNDP, Sida |
| 3 | Relevance, Coherence, Sustainability | UNDP, Sida |
| 4 | Relevance, Coherence, Effectiveness Efficiency, Sustainability | UNDP, Sida |
| 5 | Relevance, Efficiency, Effectiveness | UNDP |
| 6 | Relevance, Coherence, Effectiveness, Efficiency and Sustainability | UNDP |
| 7 | Relevance, Coherence, Effectiveness, Efficiency and Sustainability | UNDP |
| 8 | Relevance, Coherence, Effectiveness, Efficiency and Sustainability | UNDP |
| 9 | Relevance, Coherence, Effectiveness and Impact | UNDP |
| 10 | Relevance, Effectiveness, Efficiency and Sustainability | UNDP |
| 11 | Effectiveness, and Efficiency | UNDP |

- Conclusions # 1, 5, and 8: Clarify/confirm overall project objectives and anticipated results at the output, outcome and impact levels. Using the project goal as a starting point, undertake a ToC process with stakeholders, working out at each level the pre-conditions needed for achieving the results anticipated (do you need more awareness, more knowledge, more access to finance, more capacity, more political will? How will you get it? How will you measure it?). Develop results chains which articulate clearly what is needed to get from inputs to outputs to outcomes, and then map the horizontal linkages between the results chains to articulate how all project elements can be mutually supporting to help align the project with other actors working on similar issues, and better identify areas of complementarity and collaboration.  Such a process will support chances of sustainability.

- Conclusions # 1, and 2: Bring in senior gender expertise to the ToC process considering that gender mainstreaming and inclusiveness is part of the package. Undertake a rapid gender audit of the resilience grants to identify the methodologies employed by implementing partners in implementing gender mainstreaming in the grants. This audit should consider the lived realities of men and women in the private and public sphere at sub national levels and identify points of entry for gender mainstreaming.  Audit results will help inform future gender mainstreaming strategies for project interventions and project design processes.

- Conclusions # 1, 3, 7, and 8: Undertake a needs and risk assessment which looks at the capacities and vulnerabilities of partner institutions and stakeholders relevant to project activities and goals in the region, identifying the capacity gaps and risks that will need to be mitigated or managed. This will also support chances of sustainability.

- Conclusions # 1, 4, and 8: Engage UN partners in the development of the ToC process and the risk and needs assessment. Based on regional plans, identify where complementarities lie with UNDP’s programmes and how a collaborative relationship with the project would add value to the output, or at least bring useful synergies to the process. Invest in the capacity-building of regional partners, as well as interested civil society organizations and groups to further popular awareness, engage in dialogue and advocacy, as well as policy formulation at the country and regional levels. The attention to capacity building, multi-level dialogue for policy formulation will also support changes of project sustainability.

- Conclusion # 3: Use detailed stakeholder mapping to identify and categorize project stakeholders according to their influence on, and interest in, the project to identify how to manage them in the interests of the project during implementation. Based on the stakeholder analysis, select a few proven implementation partners with the technical competence and experience needed to develop strong partnerships with inter and governmental institutions necessary for transforming knowledge products into policy and plans.

- Conclusion 3,4 and 5: Improve overall coordination of project activities through the establishment of a stronger coordination mechanism staffed by a full-time coordinator which tracks evolving opportunities for creating synergies in partner implementation practices, leveraging existing partnerships and emerging opportunities provided by the work of other partners so that all partners are aware of each other’s work and can build more effective collaborative partnerships across the region. This mechanism must include monthly - or at a minimum - quarterly mandatory check-ins with partners to identify areas of synergy and collaboration for action.

- Conclusion 3 and 4: Improve the implementation of multi-level dialogues around climate security issues by broadening the base from government and national partners to include non-governmental organisations and the private sector.

- Conclusion 8, 9 and 10: Engage in communications on the results of the SDG CG and advocacy based on the results from SDG CF implementation with and through the UN to accelerate action on climate security.

- Conclusion # 3: Expand project partnerships as implementation progress based on your stakeholder analysis, technical requirements and proven and efficient implementation modalities which are not challenged by overwhelming coordination requirements. A consolidation of the relationships with the LAS for future partnerships should also be prioritized.

- Conclusions # 7: Build a learning loop into the M&E implementation process to be managed by the CTO for periodic but regular review and reflection on progress achieved against targets at regional and sub national levels. To keep the results on track, a quarterly—or at least semi-annual—stock take of performance measures should be done.

- Conclusion # 6: Ensure PMU competencies include performance management skills, relationship building skills (a more structured approach is needed to policy integration), communication and advocacy skills at senior levels.

Annex 27 provides additional details on future planning recommendations.

# Annexes (Attached in a Separate Document)

#### Annex 1: TOR

#### Annex 2: Evaluation Matrix

#### Annex 3: Theory of change

#### Annex 4: Results Framework

#### Annex 5: Evaluation Questions and Key Performance Indicators

#### Annex 6: KIIs Guiding Questions

#### Annex 7: FGDs Guiding Questions

#### Annex 8: List of KIIs

#### Annex 9: List of FGDs and Number of Participants

#### Annex 10: Online Survey

#### Annex 11: Beneficiaries Survey

#### Annex 12: List of Consulted Documents

#### Annex 13: Summary of Country Resilience Project Targets and Achievements

#### Annex 14: Knowledge Products Produced by the SDG-Climate Facility Project

#### Annex 15: The Events and Involvement of the SDG-Climate Facility Project

#### Annex 16: Analysis of the Project Sub-Indicators and Level of Achievement

#### Annex 17:  Detailed Evidence of Achievement of Outputs and Outcomes

#### Annex 18: Summary of the Additional Fund Attracted to Resilience Grants

#### Annex 19: Gender Focused Knowledge Products Produced under the SDG Climate Facility Project

#### Annex 20: Anecdotal Success Stories Providing Some Insight into the Potential Gender Impact of Resilience Grants

#### Annex 21: Organogram of the Project

#### Annex 22: Staffing Arrangements for the Management of the Project over the Implementation Period

#### Annex 23: Analysis of Sustainability Prospects for Resilience Grants

#### Annex 24: Ethical Considerations

#### Annex 25: Background Information on Evaluators

#### Annex 26: Pledge of Ethical Conduct

#### Annex 27: Future Planning Recommendations

Climate Change in the Middle East and North Africa: Mitigating Vulnerabilities and Designing Effective policies, Carnegie Endowment for International Peace, October 2023 (unpublished draft); Addressing climate, peace and security in the Arab region, UN ESCWA policy brief, November 2023; Migration and Climate Changes in the Arab Region, UN ESCWA, policy brief, October 2022; The Climate Crisis is a Childs’ Rights Crisis, UNICEF, August 2021; Regional Assessment Report on disaster risk reduction in the Arab region, UNDRR, 2022; Climate Security Perceptions in Tunisia: Food Security as a dominant paradigm, in Climate Security in the Anthropocene, May 2023, Spring link; The Arab Spring and Climate change, Centre for American Progress, February 28, 2013.

Project staff pointed out that the impact of the Knowledge Products is yet to be fully determined as the project has technically not ended yet.

It is difficult for women with families to work outside the home without access to full time and stable childcare provision. These support services were not built into the projects.

Including a No Cost Extension that was approved. The project was signed in March 2019 and had a planned end date of December 31, 2022, however, a No-Cost Extension was requested and approved for 12 months until 31 December 2023.

Evaluation questions as per the TOR are presented in Annex 5.

For details on the core evaluation team’s background please refer to Annex 25.

These organisations were relevant for various outcomes of the project to contribute to the integration of climate in crisis/prevention. They contributed to project activities under Outcome 2 and 3.

In Palestine, key stakeholders participated in a FGD.

The ET received a total of 16 Qat-to-Coffee beneficiaries, the field team contacted all of them and reached to 11 beneficiaries.

The ET does not have the actual number of beneficiaries and, therefore, cannot assess the representativeness of the sample. The results of the survey reflected the perceptions and insights of the beneficiaries who were surveyed.

Beneficiaries in Palestine were not knowledgeable of the project and its impact, as much of the work was conducted in close partnership with the local councils.

Further details are found in Annex 9.

Islamic State of Iraq and the Levant (ISIL)

No social or environmental risks were identified for the programme according to the project document, Annex 1.

Identified in the ToC as: Increasing water insecurity, reduced agricultural productivity, growing land and ecosystem fragility, and low use of solar potential.

Cross country exchange of knowledge took place, but most often at a higher level than technical (with resident representatives) at COPs, who are not involved directly in the management of the resilience grants and would not be able to use the knowledge gained to help adjust implementation.

In Tunisia for example, the project integrated gender considerations, focusing on women's empowerment and participation in local governance structures." In Iraq, UNDP's collaboration with local organizations like the Warqa Organization for Skill Development empowered women in Maysan through training and skill development. In Jordan, UNDP collaborated with local agencies to promote climate security, gender equality, and youth entrepreneurship in water and agriculture sectors.

59% of the knowledge products were produced in the last year of the programme (2023/2024)

A report on the climate change, gender, and displacement nexus in the Arab States is still to be published (UNDP Progress Report 2023), as is an AWC study: Floods in Sudan: Disasters, impacts and risk management (ACW Progress Report 2022). Some have not yet been completed (Challenges facing datasets of climate change disasters in the MENA region; Impact of the Grand Ethiopian Renaissance Dam; Strategic plan for building community resilience for managing flood risks in Sudan

The cancellation of the Climate Facility resulted in the cancellation of the planned Climate Security Platform to be hosted in the facility.

The Regional Climate Security Network (RCSN) platform’s focuses mainly on RCSN activities. The Resources section provides access to the SDG Climate Facility flyer, 2019 and two SDG –Climate Facility knowledge products:  Climate Change and Social Vulnerability: Using multi-sectoral indicators to assess compound drought risk and Social Vulnerability in Jordan, March 2023, SDG-Climate Facility: Climate Action for Human Security Project: and Report on the Regional Climate Security Stakeholder Dialogue, 6 – 8 December 2020. (Webpage reviewed 19 June 2024). The Sustainable Finance Knowledge Platform provides detailed information with links to external resources on (1) Development in the MENA Region: how to finance the energy transition to mitigate climate change in the region; (2) Risks and opportunities: adaptation and transition risks and opportunities for finance institutions in the MENA region; and (3) Resources including access to UNEP-FI training opportunities and Climate Risk and TCDF Workshops conducted under the SDG-FI Project in Egypt and Tunisia in 2021. The Accelerating private finance for the Arab renewable energy transition. White Paper. March 2021 produced with support from the SDG –Climate Facility Project is available on the site. One SDG –Climate Facility knowledge product, namely Accelerating Finance for the Arab Renewable Energy Transition White Paper, 2021, was accessed on the Development in the Arab Region page (Webpage reviewed 19 June 2024). In 2023, the platform was reported to have been updated to be more user-friendly and continuously updated with the latest project-related publications on climate finance (UNDP Progress Report, 2023).

The UNDP 2023/2024 Progress Report, refers to the creation of a newly revamped webpage for the project: https://www.undp.org/arab-states/sdg-climate-facility-climate-action-human-security-0). The webpage provides information on the seven resilience grants, communication products, and eight knowledge products (accessed 19 June 2024).

The Regional Climate Security Network (RCSN) for the Arab Region was established in December 2020, under the framework of the SDG Climate Facility Project, by the AWC, LAS and UNDP Regional Office “as a think tank, and as a regional platform that enables institutions across the Arab world – including government institutions, organizations and NGOs, UN, private sector, academia, research institutions, donor agencies and other strategic partners – to develop an Integrated Regional Climate Security Framework (IRCSF) for the Arab Region” (RCSN Concept Note, https://rcsn.arabwatercouncil.org/#). The network was officially launched during a Regional Stakeholder Dialogue on Climate Security in December 2020, where a “regionally owned working definition of climate security” was agreed on (see: https://climatechangedialogue.com).

In 2023, UNDP launched the Arab Future Energy Index (AFEX) report, co-funded by the SDG-Climate Facility Project and the Regional Centre for Renewable Energy and Energy Efficiency (RCREE). This report assessed renewable energy and energy adoption trends towards 2030 and contributed to discussions on NDC progress in the Arab Region. The research accelerated climate finance efforts by enhancing partnerships between regional stakeholders and International Finance Institutions, such as the Asian Infrastructure Investment Bank (AIIB). The AFEX report tracked low-carbon sustainable energy trends, strengthened awareness, and facilitated replicating clean energy projects. It highlighted success stories, such as Jordan’s new policy frameworks de-risking climate investment and fed into UNDP’s global Climate Promise programme. The report’s findings also informed discussions at MENA Climate Week 2023 and COP28.

UNDP successfully completed a regional policy brief on Sustainable Energy for Displaced Communities in 2020. This brief elaborated on the challenges of achieving SDG7 (energy access) in crisis contexts, identifying opportunities to close the energy gap for crisis-impacted communities. It highlighted lessons learned from UNDP’s local projects in Yemen, Syria, Sudan, Somalia, Palestine, Libya, Lebanon, and Iraq, providing valuable insights for future initiatives. The development of project ideas and outlines stemming from the regional policy brief was partially achieved. Two project outlines for renewable energy investment in Lebanon and Libya were developed. However, the planned pitching event at the Arab Climate Resilience Investment Forum (ACRIF) in 2021 did not occur, hindering the progress of securing financial partners.

For example, there were no details of utilization or uptake of guidelines for mainstreaming climate change in recovery processes of cities in crisis (UN Habitat); no details or descriptions of scaling up national social protections and safety net proposals based on piloting climate services and EWS in Yemen and Iraq; no data on the number of crisis prevention and recovery plans using the approaches modelled in UNDP’s technical assistance

All the resilience grants have an explicit focus on gender, target youth unemployment and entrepreneurship, and focus on renewable energy access, eco-system revitalization, ecotourism livelihood opportunities, innovation for water saving technologies and rural community resilience, contributing to the objective of addressing underlying climate-security issues, to reduce potential climate-induced displacement, and contribute to resilience.

AWC presented a series of recommendations on climate nexus and climate security issues at several regional fora, and several AWC reports have been authored

Source: UNDP Progress Reports 2022 and 2023. No data available on indicator (3.2.2).

A White Paper serves as a comprehensive document that guides decision-making and policy formulation, aiming to foster sustainable development, address regional challenges, and promote collaboration among member states and other stakeholders. It is not a policy document so not binding of member states to specific commitments or objectives, however this White Paper could serve as a precursor to the development of regional or national policies.

In Jordan. the project was included as a priority in the NDC implementation. By prioritizing the project within the NDC framework, it gained significant visibility and recognition which helped attract attention and support from both the government and international donors, indicating that the project's objectives and activities were seen as valuable contributions to the country's broader climate strategy. (KII)

In Yemen, the findings of the Qat to Coffee resilience project were reported to have been integrated into national roadmaps for climate resilience. These roadmaps aim to incorporate climate security into national policies: "By working closely with ministries and other authorities, we ensured that the recommendations from the project were considered in broader policy development." (KII).

Sida's attendance was only at one meeting as an invitee.

The document "Annex XIII: Gender Assessment and Action Plan, Enhancing Climate Change Adaptation in the North Coast and Nile Delta Regions in Egypt" was prepared by the Green Climate Fund and the UNDP as part of the funding proposal for project FP053 and published on 28 September 2017. This document provides an overview of the gender situation in Egypt, suggesting that the pilot had drawn on the findings and recommendations of this study rather than conducting its own project-specific analysis.

This data refers to participation in the stakeholder dialogue. Data presented is what as available on the website

These are the percentages of planned annual budgets against actuals. They are presented against all outcomes every year.

Not all the gender related activities were in the budget. For example, when the project employed a "Gender JPO" this person was not reflected in the budget. When the project received in-house technical support from the gender team this was also not reflected in the budget.

All other costs including inception phase, evaluation and GMS cost are not included in these totals

No data available on indicator (3.2).

Two activities related to the establishment of the climate facility8 were cancelled in Year 3

UNHABITAT reported in December 2021 that “Another challenge is the lengthy internal procedures that delayed the receipt of the third tranche (USD 15,000 … Mobilizing resources from other on-going projects to partially fund the contract of the urban researcher (to develop the urban governance chapter)

SDG-CF annual Report, 2023/4

UNDP informed us that beneficiaries at the community level of this project would not be aware of any project details. As a result, we did not survey them.

Partner survey

The midterm review (MTR) of the UNDP Regional Program for Arab States (2022-2025) indicates a promising potential for the sustainability of project benefits, particularly in areas where regional institutions have shown ownership and engagement. But the MTR also highlighted that while the SDG Climate Facility has made significant strides in launching a regional climate security agenda, the follow-up at the country level has been mixed: While there is scope for improvement, Regional Programme follow-up, through the SDG Climate Facility team, with countries on climate security roadmaps was adequate and moderately successful.

For example, UN Habitats guidelines for mainstreaming climate resilient solutions into urban processes.

Grants in Iraq, Palestine, Yemen and Jordan for example.

However, the local councils expressed uncertainty about the longer terms financial sustainability of the solar energy systems, citing risks such as the Israeli control of energy sources and the limitations imposed by the Paris Economic Agreement.