Annex 2: Expenditure Management Capacity sub-programme report

# Background

The Expenditure Management Control Programme aims to improve expenditure management, and institutionalise medium term expenditure planning, across the civil service. In order to do this the programme firstly aims to establish a new legal framework for expenditure management and control. This is then implemented through the roll-out of budgeting, accounts and procurement reforms, development of medium-term planning systems, strengthening of internal and external audit, modernization of cash management, and the roll-out of financial management information systems.

The EMCP has been given a high priority by government, and has made good progress in achieving this objective. Until recently it was managed as a sub-component of the CSRP sub-programme, and from this year it has been established as a separate sub-programme, under the coordination of MOFED. MOFED takes overall responsibility for coordinating EMCP across the country, and the beneficiaries of the programme include all public institutions, including regional governments, and the Auditor General’s Office for external audit reform.

It is important to note that much of the ground work for the EMCP sub-programme has been laid by the Decentralisation Support Activity (DSA) project, funded by USAID, Irish Aid, the Netherlands and MOFED. This has included the work on budget, accounts and IT reforms. PSCAP funds were not used on the EMCP sub-programme until EFY 1999, and delays in procurement have meant the much of the impact of PSCAP has not yet been realised. In making the evaluation it is difficult to distinguish between these different programmes, as MOFED has used these different sources of donor funds to drive the same programme.

During October and November the evaluation team held meetings with the EMCP sub-programme, the CSRP sub-programme, the Auditor General, and the Centre for Leadership and Management Development. The beneficiaries of the EMCP programme include all public sector bodies, and meetings with a wide cross-section of public sector Ministries and agencies were held (see annexure xx to main report).

Key information on which the assessment was based included the sub-programme performance reports, legislation for expenditure management at federal and regional level, audit reports for federal and regional government, DSA project reports, and independent assessments of the state of public finance management across all tiers of government conducted for the PBS programme.

# Implementation of main components

The main components of the EMCP are creating the legal framework for expenditure management reform, building capacity for expenditure management and control, establishing the information systems to underpin proper financial management, improving property management, and building audit and oversight capacity. The EMCP programme has undertaken reforms initially at the federal level, and then rolled these out, first to established regions and woredas, and then to less developed regions. The first component that has been addressed is the enabling environment.

## Enabling environment

The legal framework for expenditure management and oversight at the federal level has been established, and it is governed by the following:

- Constitution of the Federal Democratic Republic of Ethiopia (1994)

- Proclamation on the definition of power and duties of the executive organs (04/1995).

- Federal Government of Ethiopia Financial Administration Proclamation no, 57/1996

- Council of Minister’s Financial Regulations No. 17/1997

- Federal Government of Ethiopia Proclamation Establishing the Office of the Auditor General No. 68/1997

- Proclamation on the establishment of Ethics and Anti-corruption Commission (235 – 2001)

- Federal Government of Ethiopia Proclamation Determining Procedures of Public Procurement and Establishing its Supervisory Agency Proclamation No. 430/2005

- Federal Public Procurement Directive, MOFED, July 2005

There are in addition a further 20 financial directives. The legal frameworks and regulations for the new public financial management systems are also in place in all regions. Somali has not yet implemented the accounts reforms.

The federal legal framework on financial administration and procurement has been revised in line with the new approach to decentralisation. This has been submitted to the Prime Minister’s office, but has not yet been approved by Parliament.

A procurement proclamation has been issued in 9 regions and cities, with two remaining.

## Capacity for expenditure management and control

The capacity for expenditure management and control has been built in all beneficiary institutions through a focus on budget reform, accounts reform, procurement reform, cash and disbursements management reform, and internal audit reform. Awareness creation workshops have been held for less developed regions, and a large amount of training has taken place at regional and federal level, and manuals and training modules have been prepared.

The training has largely been done in-house, although sometimes consultants have been brought in to assist with the training, using DSA funds. A training of trainers model has been used, especially for the accounts and budget reforms areas. The trainers have in turn organised training in each region, making use of the facilities of the regional Management Institutes. In this way training was organised for approximately 70 000 staff down to woreda level on areas such as account reforms and internal audit. The EMCP is now looking at making use of the civil service college for further continuous training purposes.

A new budget structure is in place - it has been implemented across all public institutions, and a large amount of training has been done on this. A new chart of accounts, cost centre based budgeting and single pool systems are being rolled out. The regional and woreda offices have been restructured.

The accounts reform process has assisted with some equipment such as computers, laptops and printers, much of which has been for less developed regions such as Gambella, Somali, Afar and Harar. The backlog of accounts has been cleared at federal and regional level, and partly at woreda level. Double entry accounting is now in place at federal level and in all regions except Somali.

Procurement training has been given to Tigray and Benishangul regions. A consultant has been hired to develop a training manual, and training module, and then to conduct further training of federal and regional procurement staff.

There has been reform of the cash and disbursement management systems, and training given to 51 trainees on the new system. The mode of effecting payments to public bodies has been changed, with institutions producing cash flow statements, 3 month projections of cash requirements, a zero balance drawing system in which the banks only pay for actual withdrawals. Arrangements also have been made to effect all salary payments through the banks.

## Financial information

The BDA and BIS computer systems previously used by Treasury have been upgraded to the web-based Integrated Budget and Expenditure (IBEX system), which has been installed in all regions except Somali, all national Ministries, most zones in regions, as well as in pilot woredas in each region. There are different modules within IBEX, namely accounts, budget and disbursement. However IBEX does not contain modules on debt management, revenue management or asset management. A large amount of equipment has been purchased as part of this exercise.

MOFED now plans to move to the integrated financial management and information system (IFMIS). It contains five modules, which include budgeting, accounting, fixed asset management, debt management and revenue management. The plan is to test IFMIS in a number of federal pilot bodies, and MOFED is waiting for the “no objection” letter from the World Bank before extending the system. MOFED estimates that the pilot phase will last 1 – 2 years, followed by a roll-out to other public bodies which will take 2 – 3 years. IBEX data will be migrated to IFMIS during this phase.

## Property management reforms

The property management system is also in the process of being reformed. This includes the management of government’s fixed assets – the sub-programme will investigate how to bring these on to the balance sheet of government. A fixed asset register is being prepared. Manuals and training on property management have been commissioned.

## Audit functions

The EMCP sub-programme has established internal audit across all federal institutions, and in all regions, thereby facilitating a move from pre-audit to post-audit. Manuals and training modules on internal audit have been prepared. Training has also been given to 108 trainees from Benishangul Gumuz.

The AGO confirmed that internal audit is in place in all federal institutions, and that they are reporting to heads of their institutions, with copies forwarded to MOFED.

There has also been substantial support to the AGO on external audit, which the AGO views as a success. This work was started with other donors such as CIDA, and has now been carried over to PSCAP. Work has been done on preparing audit standards and audit manuals jointly with the regional AGOs. A core group with federal and regional experts was established, which prepared documents and manuals. These were presented to the AGO assembly, which brings together the federal and regional AGOs, and comments were discussed before finalising the documents.

The AGO has also arranged training for trainers from each regional AGO, on the following topics:

- Financial audit

- Performance audits and standards

- Control audits and standards

- Environmental audits and standards

- Fraud awareness

- IT audit and standards.

Some senior managers have been sent for long term training with the US Government Accountability Office. The AGO is also receiving support with training from the African Organisation of Supreme Audit Institutions.

As a result the capacity of the AGO at federal and regional level has increased. They are now preparing for BPR, with PSCAP support.

# Overall assessment

There has been a substantial improvement across all institutions with respect to financial management, and there has been a major effort made to build capacity at woreda level. The AGO has confirmed the above mentioned changes in the public financial management system, including the implementation of double entry accounting at a federal level and in the larger regions.

The programme has been exemplary in taking responsibility for supporting reform initiatives at regional and woreda level, and in providing hand-on assistance to these institutions. The Auditor General’s Offices in the larger regions have confirmed that financial management is showing significant improvements in regions and woredas. Single finance pools have been established for each woreda. There was a move over to the modified cash basis for accounting four years ago. All woredas now use the double entry accounting system. Woreda finance staff have been upgraded to degree and diploma level. There is general compliance with the new laws and regulations for expenditure management.

A recently completed independent evaluation of Public Finance Management performance was undertaken in preparation for PBS (financed by CIDA and EU, released 23rd October 2007). The report is based on an international reference framework (PEFA) using high-level indicators and it looks into six dimensions, namely:

- Credibility of the budget

- Comprehensiveness and transparency

- Policy based budgeting

- Predictability and control in budget execution

- Accounting, recording and reporting

- External scrutiny and audit.

The main findings of the reports covering federal and regional systems are:

1. Credibility of the budget

The overall execution of expenditures at federal and regional level is good, with limited aggregate budget variance, although there are changes in the composition of primary expenditures. The system of fiscal federalism has been uniformly applied across the regions. Regional budget management has been good, and there are no regional fiscal deficits. However regions and woreda revenue forecasts are not fully realised.

2. Comprehensiveness and transparency

The federal and regional budgets are based on a functional classification and the information included in the budgets is of a good quality. However extra-budgetary expenditures exceed 10% of total expenditures, which weakens comprehensiveness and transparency.

There are transparent fiscal relations between the three levels of government. The comprehensiveness and transparency of the regional and woreda budgets has improved in recent years, but in some regions the year-end financial statements are delayed.

3. Policy based budgeting

There is a well ordered budget calendar, with a rolling three year Macroeconomic and Fiscal Framework, and a Public Investment Programme. Although there have been efforts to link the investment budget and forward recurrent estimates, in practice these remain separate processes.

Woreda budgets are almost entirely taken up with fixed recurrent expenditures, and there is therefore very little room for local initiatives and priorities to influence budgets.

4. Predictability and control in budget execution

Cash flow management is being implemented across all institutions, but is not yet fully established in some. Federal and regional institutions provide reliable monthly cash flow figures. Payroll controls are robust. Procurement reforms are being rolled out nationwide, although there is some concern that the thresholds are too restrictive. There is prompt reconciliation of bank accounts across all regions, but clearance of suspense accounts is not as timely. Internal audit has improved significantly over recent years, although its information is not shared with the AGOs at federal and regional level.

5. Accounting, recording and reporting

Reconciliation of all Treasury controlled accounts is carried out timeously, and the quality of in-year budget reports and annual financial statements is satisfactory. Delays in submitting annual financial statements to the AGO have been dramatically reduced. The EFY 1998 financial statements have been closed.

6. External scrutiny and audit

The audits of the AGO generally adhere to INTOSAI auditing standards and focus on significant issues. There is less than one year lag in auditing federal accounts. The Budget and Finance Standing Committee carries out a review of the recommended budget, and scrutinises the audit reports.

The reports on federal and regional Public Financial Management performance in general provide a very favourable assessment, and acknowledge the impact of the EMCP programme on the overall system.

The progress at woreda level is much more uneven, with many woredas not yet having automated financial systems, or indeed the computers and infrastructure to enable this. In looking at the differences between financial management in woredas, the DSA reports have identified some important issues for the attention of policy makers. A critical requirement is access to electricity, office computers and a telephone. Many woredas do not have office copies of financial regulations, and these should be provided routinely to all woredas. Another critical issue appears to be the staff complement assigned to the finance office – the top performing woredas tend to have a lower number of transactions per staff member per day in the finance sections, and a lower amount of non-salary operational and capital expenditure per staff member. Properly staffing woreda finance offices seems to be a priority. New woredas also appear to take some time to achieve adequate levels of performance, and the support that is provided to them needs to be maintained for longer.

# Programme management and support

## Institutional arrangements for PSCAP implementation

As indicated earlier, the sub-programme has recently been given the status of a separate sub-programme, and has been moved from CSRP to full time management by MOFED. A revised 3 year strategic plan has been finalised, and arrangements to move the programme over to MOFED have been completed. An EMCP coordinating office has been established and equipped with computers and communications infrastructure. MOFED has taken full responsibility for coordinating the programme at a national level, and is well placed to achieve the sub-programme targets.

## Coordination with MCB, other sub-programmes and regions

There is an effective mechanism for coordination between MOFED, BOFEDs and federal treasuries. A high level steering committee has been established to oversee implementation of the EMCP sub-programme. Chaired by the State Minister, it brings together all the reform programme offices at federal level, as well as the BOFED Bureau heads. The EMCP office head acts as the secretariat to the committee. The steering committee meets quarterly, evaluates progress, approves EMCP action plans for the coming year, and coordinates implementation of the sub-programme.

The Minister for Finance and Economic Development attends regular meetings convened by the Minister for Capacity Building to coordinate the overall transformation process.

The EMCP office convenes regular monthly meets with department heads from MOFED to coordinate the different elements of the sub-programme.

The AGO indicated that they had a good working relationship with CSRP regarding the coordination of PSCAP.

MOFED frequently visits regions and provides hands-on assistance and training. It also conducts workshops for woredas and zones where necessary, using its own budget.

## Compliance with eligibility criteria

The sub-programme has complied with all eligibility criteria, and a PPA for EFY 2000 has been signed.

## Planning and resource allocation

The sub-programme has produced a medium term strategic plan and annual action plan. MOFED indicated that the planning process is tedious, and that frequent revisions to the action plan, and then the procurement plan, are required.

## Sequencing and integration of reform initiatives

There do not appear to be any problems with the sequencing of reform initiatives.

## Financial management

The overall integrity of the financial management systems are good, but there has been serious under-expenditure of PSCAP funds, largely due to delays in procurement. Of the Birr31 million allocated last year, and Birr 7 m was spent, while the Birr 24m for hardware was not spent. Birr39,5m has been allocated for this year, mostly to cover the costs of IFMIS, but the delays in procurement could result in this also not being spent this year.

## Procurement

The main problems in procurement relate to the long delays in the approval process, and the centralisation of ICB procurement in MCB. There are multiple letters of no objection required from the World Bank for a single procurement exercise, and frequent queries are raised on a single procurement item. Approximately Birr 24m has not been spent as a result of these delays.

## Monitoring and evaluation

The sub-programme reports to the PPD on a regular basis on activities and spending. There does not appear to be a systematic approach to evaluating success with the programme. The reports of the federal and regional Auditors General are a regular and useful assessment of the overall state of expenditure management, but these are usually only available later in the financial year, and should not considered a substitute for proper evaluation processes within the sub-programme.

## Information, education and communication

It appears that there has been no progress made with this initiative.

# Cross-cutting issues

No information was provided regarding attention to cross-cutting initiatives.

## Key issues and challenges

The key issues arising out of the evaluation are:

- There is a low level of capacity and a high turnover of skilled professionals in the finance offices at woreda, regional and federal level. This requires a high level of repeat training. The incentive framework for civil servants needs to be addressed, and the higher education system must focus on producing more qualified personnel in public financial management.

- A key recommendation from the last review was that partnerships are formed with training institutions in order to scale up in a sustainable manner. A meeting with the Ethiopian Civil Service College and their Centre for Leadership and Management Development confirmed that they have a well developed public finance curriculum, but that to date MOFED and BOFEDs have not made use of this facility.

- The procurement of the IFMIS system has been unduly delayed. It is approximately 6 months since the submission was made to the World Bank, and there have been frequent no objection letters required, while queries from the WB are raised repeatedly rather than all at once. The final go-ahead on this has not yet been received.

- There are similar delays across the whole procurement system, resulting in the PSCAP budget not being spent.

# Lessons learnt and recommendations

- It is clear that MOFED have the capacity and systems in place to effectively manage complex procurement procedures. The procurement ceiling for PSCAP funds should be raised, and the procurement process decentralised to MOFED.

- The procurement of the IFMIS system must be expedited.

- The key priority for the next phase of EMCP must be those woredas that do not yet have basic infrastructure or adequately staffed finance offices – a major national effort is required to bring these woredas in line with the generally excellent progress that has been made at a federal and regional level.

- The system of internal audit is still in an establishment phase, and more effort is required to properly institutionalise this system, and take it down to woreda level.

- The JSM recommended that partnerships should be formed with training institutions in order to scale up in a sustainable manner. This should be implemented, and MOFED and BOFEDs should make use of the Centre for Leadership and Management Development at the Civil Service College in this regard.

- There should a proper evaluation system implemented for the sub-programme, with an annual assessment study commissioned to look at the state of expenditure management at federal, regional and woreda level. This study should be evaluated in a workshop that brings together regional BOFED heads, federal treasuries and MOFED to evaluate the report and decide on action.