Annex 3: Tax System Reform sub-programme report

# Background

The TSRP sub-programme aims to develop a modern tax administration through an overhaul of tax legislation, tax policy and administration, thereby improving revenue collection. At the same time TSRP aims to ensure equity and fairness in the tax system, and to encourage private sector investment and development. The programme originally was developed with six components for tax policy and administration, and later a customs reform component was added with three additional components.

An evaluation meeting with the TSRP sub-programme office in the Ministry of Revenue was held on 10 October. Meetings were held with the Federal Inland Revenue Authority and the Ethiopian Customs Authority on 30th October, and the Institute of Tax and Customs in the Ethiopian Civil Service College on 1st November. Input was also obtained from each of the regional TSRP offices, cities and woredas involved in tax collection, as well as from the Ethiopian Chamber of Commerce and regional Chambers of Commerce.

Information used for the assessment included data from MOFED on federal and regional government revenues, national surveys on the rates of growth, the MOFED report on “Macroeconomic Developments in Ethiopia 2005/06”, data on tax collection from FIRA and the Ethiopian Customs Authority, and the status of tax legislation at federal and regional level,

The Tax Systems Reform Programme (TSRP) was initiated five years ago, with bilateral donor support. PSCAP support to the TSRP only started in EFY 1997, and represented a scale up in the TSRP. PSCAP has been instrumental in achieving the reforms within the tax system. The tax authorities have been operating within a limited budget, and did not have the ability to finance the incremental costs associated with the reform process. These incremental costs have included office equipment and furniture, computers for the various tax offices, equipment to support the move to mobile anti-smuggling units, and a large investment in training for staff.

The TSRP sub-programme is coordinated by the Ministry of Revenue, and is implemented through two main beneficiary organisations, the Federal Inland Revenue Authority and the Ethiopian Customs Authority. The Institute of Tax and Customs in the Ethiopian Civil Service College also plays a key role in the training of tax personnel. The TSRP sub-programme consists of the following components:

- Tax policy and legislation

- Tax payer identification number (TIN)

- Presumptive taxation

- Value added tax (VAT)

- Operational programmes, systems, procedures and manuals

- Organisation and tax payers education

- Customs automation

- Customs enforcement

- Customs organisation and management.

Each of these components will be assessed in turn, with reference to the output indicators for the sub-programme as elaborated in the Project Implementation Plan.

# Evaluation of main components

The starting point for the TSRP is revising policy and legislation at federal and regional levels. The roll-out of the computerized Tax Payers’ Identification Number (TIN) system in 74 regional centers aims to lay the basis for future tax administration. The sub-programme aims to support implementation of presumptive and value-added taxes, strengthen the enforcement powers of tax collection bodies, and implement customs reform and modernization. Capacity is built in the relevant tax offices through establishing operation programme systems, procedures and manuals. At the same time the public acceptance of and compliance with the system is supported through taxpayers’ education.

The tax systems reform program is coordinated with plans to develop sub-national taxes as envisaged under the district level decentralisation and urban management subprograms.

## Tax policy and legislation

The TSRP sub-programme planned to overhaul the income tax laws and issue new proclamations for agriculture, income tax and land use fees in 9 regions. The division of tax powers between federal and regional government is governed by the Constitution of the Federal Democratic Republic of Ethiopia (1994) and the Proclamation on the definition of power and duties of the executive organs (04/1995). The Ministry of Revenue has assisted the regions to finalise their tax proclamations. To date legislation has been finalised in 8 regions, and the Somali region is in the process of finalising its Tax Law (89% complete). Tigray, Oromia, SNNPS, Gambella, Afar and Benishangul Gumuz have issued the Agricultural Income Tax law.

Revenue potential studies have been completed in Amahara, Tigray, Oromia, SNNPS, Afar, Benishangul Gumuz, Gambella and Harari. “No objection” has been obtained to undertake the revenue potential study at federal level.

## Tax payers identification number (TIN)

The TIN system assigns each taxpayer a unique tax number, and thus creates the basis for the sound administration of the taxation system. The TIN system has been applied across all tax authorities, and thus it cuts across the jurisdiction of federal, regional, woreda and city authorities. FIRA has overall responsibility for managing the system. The central system creates the TIN on application by any one of the authorities, and relays it back to regions, cities and woredas.

The TSRP sub-programme planned to register all potential tax payers, computerize 100% of the TIN database, and interface with 50%` of third parties. To date 327 585 tax payers have been registered, i.e. 90% of the total 365 000 tax payers. The system has been installed in 77 sites, and woredas that do not have the facilities for administering TIN send their forms to one of the sites that can. The registration effort has been complemented by a media sensitisation campaign. An additional inducement is that every trader applying for a license or certificate from government is required to be registered for TIN.

Engagement with the Ethiopian customs authority and the National Bank of Ethiopia on the system is underway.

## Presumptive taxation

Presumptive taxation is a regional competence, and FIRA and the Ministry of Revenue provide support to the regions for its administration. TSRP planned to issue a profitability rate directive, register all new taxpayers, and collect tax revenue from new registrants, new businesses and hard to tax groups. The national profitability rate has been issued for use by regions and the customs authority. Approximately 275 000 tax payers have been registered as presumptive tax payers. The tax revenue from these tax payers is not separately accounted for, but overall revenue has shown a significant increase.

## Value added tax (VAT)

The system of VAT replaced the earlier sales tax, and the introduction of the system was started prior to PSCAP, with donor support. In EFY 1997 the administration of VAT for sole proprietors was delegated to the regions and cities, while companies are administered by FIRA directly. The TSRP sub-programme planned to increase the total number of tax payers registered for VAT, and to increase tax revenues from VAT. To date 28 412 tax payers have been registered, compared with an original 3 500. The revenue from VAT has increase steadily to an amount of Birr 5,93 billion.

An invoice credited VAT system is utilised. FIRA assists taxpayers to understand the system, and to report properly. The system relies on self assessment, followed by reassessment by FIRA. Tax administration intervenes in cases where reporting is incorrect, by auditing accounts and cross-checking data with other sources e.g. the national bank, Customs and large distributors.

A national survey of revenue potential from VAT has not been done.

## Operational programmes, systems and manuals

The TSRP sub-programme planned to revise and restructure the organisation of the tax offices, train staff in customer service delivery, and overhaul the administration of tax across all tax authorities. This included implementing operational manuals in the four advanced regions, training 50% of the tax officers, integrating tax systems between the regions and the customs authority, and completing tax file management in all the advanced regions.

The tax office organisation is now fully restructured in all the advanced regions and contains nationally uniform tax administration functions. To date 4 operational manuals have been developed, and a prototype issued to regions and the customs authority. The manuals cover issues such as audit, correction enforcement, revenue accounting, investigation and intelligence.

A large automation exercise has been undertaken, using the Standard Integrated Tax Administration (SIGTAS) system, linking all the main tax systems and automating most tax offices. Tax integration is complete for the federal tax offices, and underway in the regions and customs authority.

A significant training effort has been undertaken for the staff of the federal tax office. Induction training and training on SIGTAS and BPR has been given to all staff. Last year 350 people were trained on SIGTAS, 124 in intelligence and investigation, 165 in tax laws and registration, and 132 in tax audit procedures.

## Organisation and taxpayers education

The education of taxpayers is central to raising revenue effectively, and the TSRP sub-programme therefore planned to educate tax payers regarding compliance, higher tax realisation and improved tax payer satisfaction. This has been done through a joint initiative of FIRA, the Customs Authority and the Ministry. Information is widely distributed to the public and taxpayers through the website, leaflets, brochures, and TV and radio advertisements. Workshops have been used to target the campaign, e.g. restaurant owners have been consulted regarding the benefits of having a cash register. The VAT system was introduced through an intensive workshop programme sector by sector.

There has not been a systematic evaluation of the impact of the media campaign, but FIRA indicated that the results are immediately observed in terms of registrations, and gaps are identified and addressed.

A bi-annual consultation forum and Annual Tax Conference has been set up to ensure tax harmony and consistency in administration. Special support is being given to emerging regions.

## Customs automation

The reform of the customs system has been based on the introduction of automated system in all customs offices. The aim is have all customs computerised and networked, enabling on-line input of data and tracking of performance. The system that is utilised was developed by UNCTAD, and is known as “Automation System for Customs Data” (Asycuda). The Customs Authority has completed the migration from Asycuda 2.7 to Asycuda++, and the system is in operation in 20 sites, including Dewele, Metema, Moyale, Humera, Togochale, Galafi, Mile, Gondar, Bahir Dar, Awash, Airport lagare, and Head Quarters. Computers have been supplied to all tax offices to enable automation and connectivity, increasing the number of computers from less than 20 to approximately 200.

## Customs enforcement

The TSRP sub-programme planned to develop an anti-smuggling strategy, and to increase public awareness and staff capacity in order to increase the incidence of interception and reduction of illegal trade. PSCAP resources were used to enable the anti-smuggling units to become mobile, including the purchase of radios and camping equipment. The anti-smuggling strategy manual has been developed and approved. Public awareness seminars were conducted and anti-contraband committees were established. Measures to mitigate contraband will be strengthened with the implementation of the anti-contraband strategy.

## Customs organisation and management

A survey was done on services and standards in customs at the start of the reform process, which revealed long clearance times, multiple steps (72 in all) required in processing goods, and multiple requirements (40 in all) for transit and clearance. The sub-programme set out to simplify procedures and facilitate legitimate trade. It planned to develop and implement operational manual in customs offices, and increase the capacity and skills of customs employees.

A new organisational structure was introduced, and 600 college graduates were recruited and trained for 2 months before being deployed to boost the customs effort.

Manuals have been prepared on transit, guarantees, time control, pre-requisites for transit and clearance, and pre-arrival release of goods. A draft intelligence manual has been prepared, and a manual on risk management is next in the pipeline. Training has been given to customs police and other staff on intelligence and customer care. Employees have received induction and BPR training.

The clearing office was relocated to Addis Ababa La Gare, and now has more spacious and conveniently located warehouses with reduced congestion. Reforms were initially focused on the airport office and La Gare.

There have been some noticeable improvements in the custom processing time as a result of these changes. The processing of transit permits has been reduced from 2 days to 1 hour. Clearance time has been reduced from 59 days to less than 2 days. This has been partly achieved by cutting the requirements for transit permits and clearance from 40 to 15. At the same time the different steps and sub-steps for transit and clearance were reduced from 72 to 9.

A preliminary survey of the current status of the reform was made at the end of the last budget year. The assessment has indicated that the results of the reform are tremendous, but that there still many problems with trade facilitation, procedures, valuation, enforcement, and integrity. As a result the sub-programme has decided to undertake BPR, with a focus on three core processes – import, export and enforcement, as well as support processes such as human resource development. The BPR teams have completed the identification of basic problems, and are now focusing on a benchmarking exercise.

The Customs Authority meets with the importers, exporters and transiters on a monthly basis to review progress and discuss issues. A business forum meets on an annual basis to review the process.

## Civil service college training programme

Although it is not listed as separate component of the TSRP, it is worth commenting on the Institute of Tax and Customs in the Ethiopian Civil Service College, as they are the main service provider for the training programme. They provide different forms of training, including short term courses on tax or customs administration, plus academic programmes which include diploma in tax administration, or elective courses as part of a BA or Masters degree. The Institute has provided all the bulk of the training for the TSRP programmes at federal level, as will as in Benishangul Gumuz and Addis Ababa city administration revenue agency. This year they will provide training for Afar and Oromia as well.

Last year was the first year for the tax programme at the college, and they managed 1766 trainees on courses lasting between 2 and 45 days (average 20 days). The Institute responds to requests from FIRA, the Customs Authority, Ministry of Revenue or regions and cities. Based on the request they prepare a training programme and materials, and collect trainees’ expectations for the programme. The teaching methodology includes presentations be trainers, sharing of trainees work experiences, case studies and group discussions. They have covered induction training, tax and customs intelligence, amongst others.

Their weaknesses are in the customs area, and in trainers with expertise in SIGTAS and Asycuda. For these purposes they usually bring experienced managers from the target institutions into the programme, although the organisations are reluctant to release people to do this training.

There has been evaluation of the impact of the training in the target institutions.

# Programme management and support

## Institutional arrangements

The TSRP sub-programme is coordinated by the Ministry of Revenue, and is implemented through two main beneficiary organisations, the Federal Inland Revenue Authority and the Ethiopian Customs Authority. The Customs Authority has a staff of 2800, and is headed by a Director General. The Institute of Tax and Customs in the Ethiopian Civil Service College also plays a key role in the training of tax personnel.

There has been a high level coordination of the tax reform process, with the Minister of Revenue chairing an inter-Ministerial task team, including the then State Minister for Capacity Building.

There is a lack of qualified project management staff within the programme. The executing capacity of beneficiary organisations has been weak. There are significant manpower constraints in regions, and negligence amongst some top managers in the regions.

## Coordination with MCB, other sub-programmes and regions

There is still a poor level of communication between the various role-players involved in the programme.

The TSRP provides support to regions through assisting them to implement new laws, providing capacity building for human resource development, and in planning, monitoring and evaluation. There is also a special support programme for emerging regions under the Ministry for Federal Affairs.

There are problems with obtaining regional plans and performance reports. MCB has been asked to share these, but to date no response has been received.

A coordination forum with the regions meets twice annually, bringing together the Ministers and State Ministers to discuss finance and tax issues, and harmonise these. This is not a specific PSCAP forum.

At a federal level there is a tax reform task force under the Ministry of Revenue that brings together the relevant federal institutions, plus representatives from Oromiya and Addis Abeba on behalf of the regions.

## Compliance with eligibility criteria

TSRP has complied with all eligibility criteria.

## Planning and resource allocation

Delays are experienced in preparing and submitting plans, as well as in obtaining approval of plans from MCB once submitted. There is a capacity constraint at all levels with preparing plans. The programme does not receive technical feedback from MCB on their action plans.

## Sequencing and integration of reform initiatives

TSRP has successfully managed to sequence reforms appropriately, largely due to a coherent plan at the outset.

## Financial management

The TSRP programme received a total budget of Birr 160 million for the years 2004 – 2008. To date Birr 76,1 million has been released – Birr 29,2 million for 2004/05, Birr 25,9 million for 2005/06, and Birr 21 million for 2006/07. Goods procurement has made up the largest share of the budget. Birr 5,2 million has been disbursed on in-house training and goods procurement. The programme is making good effort to utilise the funds as intended.

## Procurement

Significant delays are experienced in the procurement process due to lengthy and stringent rules and procedures. TSPR also does not have a proper action plan. MCB tends to lump together ICB requests, and processes them in batches. Initial delays with letters of no objection have now been largely resolved. Experts were brought in 6 months ago to address problems, and this has improved the situation, but it is felt that specialists are now needed to assist the experts.

## Monitoring and evaluation

The sub-programme submits monitoring reports to the PPD on a regular basis. A preliminary survey of the current status of the reform was made at the end of the last budget year. The assessment has indicated that the results of the reform are tremendous, but that there still many problems with trade facilitation, procedures, valuation, enforcement, and integrity.

The Customs Authority meets with the importers, exporters and transiters on a monthly basis to review progress and discuss issues. Once a year a business forum meets to undertake a full review of the process.

## Information, education and communication

The IEC activities of the sub-programme principally involve tax payers' education activities, where substantial effort is made to reach taxpayers through a media campaign, workshops with sectors of the business community, and engage with representative organisations such as the Chamber of Commerce.

# Assessment of cross-cutting issues

The Ministry of Revenue has a dedicated HIV/AIDS programme, although this is not specifically part of PSCAP. The do place emphasis on including women in the training programme, and there is training of all tax office staff on HIV/AIDS. The TSRP plays a supportive role in the gender programmes of the department of women’s affairs. Tax payers’ education also focuses on women tax payers.

There has been no attempt to integrate the cross cutting issues into tax policy in a substantive manner, e.g. assessing the potential impact of HIV/AIDS on future tax revenues, analysing impact of tax policy on women’s position in the economy, or looking at how to deal with environmental externalities in tax policy.

# Overall assessment

The progress with implementing TSRP has been impressive, and the planned activities have largely been undertaken effectively. There has been a total turnaround in the administration of taxation, and the system has been substantially modernised.

The tax authorities have received accolades from the business community, which indicated that the changes were “a miracle”. The Parliament Economic Committee has given an award to the Ethiopian Customs Authority for service improvement, and the IMF has indicated that the changes in the customs and tax system were beyond their expectations.

The federal Chamber of Commerce indicated that on the tax reform process, government has done a good job, that the system is much more transparent than it was, and that there are major improvements in the tax system. However the Chamber believes the changes are not sufficient, and that the improvements have not lived up to their expectations.

They indicated that the reforms do not match what has been promised in the media. The business community is divided into three categories of taxpayers, and, while the larger businesses have seen improvements, the small businesses have been most disadvantaged. As they do not keep their own books of account, government can use a large amount of arbitrary discretion.

There is also a level of arbitrariness in relation to other parts of the tax system. Government reserves the right to accept of reject the audited statements of companies, and this level of arbitrariness is a concern to the business community.

This has been partly offset by the inclusion of business representatives in the tax assessment committee, and on the tax appeal committee. In both cases the government representatives are in the majority and overrule the private representatives, but the move towards inclusiveness is nevertheless important.

In looking at the actual revenue data, the outcomes of the reform process are not as impressive as initial reports suggest. The Ministry of Revenue and FIRA have used year on year comparisons to measure performance with TSRP, which show substantial and steady annual growth. However the growth in tax collection needs to be compared with the growth in GDP measured in actual terms (i.e. unadjusted for inflation) in order to get a true assessment (alternatively one can use real GDP growth plus inflation as a comparator, it amounts to the same thing). Revenue growth in excess of actual GDP growth is the most accurate way of gauging the outcome of improved tax effort.

The table below shows actual federal, regional and total tax revenues for the last five years, and compares them with actual GDP figures, as released by MOFED.

Table 1: Tax revenues and GDP EFY 1995 – EFY 1999

| Tax revenue in Birr million | EFY 1995 | EFY 1996 | % growth | EFY 1997 | % growth | EFY 1998 | % growth | EFY 1999 | % growth |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Federal tax revenue | 6,678.4 | 8,741.7 | 30.9% | 9,711.8 | 11.1% | 11,303.7 | 16.4% | 13,637.3 | 20.6% |
| Income and profits tax | 1,681.6 | 1,632.1 | -2.9% | 1,792.1 | 9.8% | 2,182.8 | 21.8% | 2,784.9 | 27.6% |
| Domestic indirect taxes | 1,432.0 | 1,833.8 | 28.1% | 2,173.4 | 18.5% | 2,533.9 | 16.6% | 3,155.7 | 24.5% |
| Import duties & taxes | 3,563.7 | 5,275.9 | 48.0% | 5,746.2 | 8.9% | 6,587.0 | 14.6% | 7,696.7 | 16.8% |
| Regional tax revenue | 1,565.1 | 2,164.7 | 38.3% | 2,686.1 | 24.1% | 2,854.9 | 6.3% | 3,234.1 | 13.3% |
| Total tax revenue | 8,243.5 | 10,906.4 | 32.3% | 12,397.9 | 13.7% | 14,158.6 | 14.2% | 16,871.4 | 19.2% |
| Revenue variance (fed.) | 87.2% | 97.8% |  | 95.0% |  | - |  | 93.1% |  |
| GDP (actual for year) | 68,898.0 | 81,755.0 | 18.7% | 98,398.0 | 20.4% | 115,589.0 | 17.5% | 131,084.0 | 13.4% |
| Tax revenue / GDP | 12.0% | 13.3% |  | 12.6% |  | 12.2% |  | 12.9% |  |

Source: MOFED data on government finances, EFY 2000

The most significant increase in tax revenues came in EFY 1996, with a growth in federal tax revenues of 12,2% above GDP growth, and a growth in total tax revenues of 13,6% above GDP growth. In EFY 1997 and EFY 1998 the growth in tax revenues was below the GDP growth figures, suggesting a falloff in tax effort, although this was partly affected by a revision of tax assessment rates for regions in EFY 1998. There has been a recovery in EFY 1999, with a growth in federal tax revenues of 7,2% above GDP growth, and a growth in total tax revenues of 5,8% above GDP growth.

The growth in total tax revenues as a percentage of GDP has been disappointing, from 12% in 1995 to 12,9% in 1999. There is considerable room to manoeuvre here, and government should aim to increase this to at least 20% over the next decade.

Given that PSCAP support only started in EFY 1997, and that there have been significant delays in implementation of many of the PSCAP support modalities, it can be assumed that there would be lag in the output indicators. The EFY 1999 figures suggest that PSCAP is starting to have an effect on the overall tax revenues, but that there is still a long way to go. This is an important issue for the Ministry of Revenue and FIRA to take into account, and it is important to guard against complacency.

The other measure to note is the predictability of the revenues collected, i.e. the budget variance. Revenues that come in below 95% of budget are a sign of poor predictability, and as can be seen, this has shown some initial improvement, followed by deterioration in EFY 1999.

# Key issues and challenges

The assessment has identified a number of issues that are seriously affecting the performance of the sub-programme, and which are risks that need to be addressed. The most important of these relate to staff issues and include

- low staff morale

- shortage of manpower in basic areas such as intelligence, valuation and post-clearance audit

- lack of capacity and training in many of the basic tax and customs fields

- high turnover of staff due to comparatively poor pay and inadequate performance incentives, and

- a hostile customs working environment.

These problems are affecting the level of service delivery and customer focus, and could undermine the gains achieved by the sub-programme. For instance, despite some notable achievements, a few importers complained that the delays and poor communication from customs remained a serious problem. There is also a high degree of corruption in areas such as goods examination, tax assessment and valuation, and enforcement.

There have been other issues raised regarding practical challenges in the tax collection effort, such as under-invoicing by importers, and long prosecution times for offenders.

There are also a number issues that relate to the administration of PSCAP as a programme, including:

- The planning process for PSCAP is time consuming and tedious, and the planning and reporting formats received from MCB are not user friendly.

- The delays experienced with procurement procedures are a major headache for implementing agencies. Average delays for both goods and services are approximately 12 months. Consultants that are needed for critical tasks arrive a year later, and often their skills are no longer appropriate.

- There are long lines of communication with the Ministry of Revenue, MCB and the World Bank, with frequent delays.

- There are also challenges in coordination with the regions.

- There remains a poor level of capacity for implementation in the regions and beneficiary institutions.

- There is a general lack of communication and information sharing between stakeholders.

# Lessons learnt and recommendations

There are a number of recommendations regarding the implementation of the TSRP. These recommendations are made in addition to the generic set of recommendations for the overall programme.

- The political leadership behind the reform initiative has been crucial to its success, and this effort must be acknowledged and continued.

- However there is no room for complacency in the TSRP sub-programme, as the results to date are not as impressive as made out, and there is a long way to go in building the revenue base.

- The Ministry of Revenue should assess performance of tax effort based on revenue growth in excess of GDP growth, and compliance with revenue budget targets. This will provide a more accurate measure of the performance by the tax authorities.

- The staff in tax authorities dealing with the public need to focus more on the customer and service delivery – there are still widespread examples on inefficiency and carelessness that undermine the overall effort.

- The working environment of the staff in the tax authorities needs to be urgently improved, along with an incentive structure that rewards tax effort and retains top performers.

- Staff should be trained intensively in procurement management, project planning and monitoring and evaluation.

- There should be an annual exercise to evaluate the impact of training on target institutions, and to measure the appropriateness and success of the training programmes.

- Regions that are not making use of the Civil Service College for training on tax administration should be approached and invited to make use of its training expertise.

- The tax payers’ education campaign should be evaluated for effectiveness at least on an annual basis.

- Strong working relationships and communication between the stakeholders should be strengthened.

- It is crucial to find ways in which to ease the lengthy procurement procedures, and the lead time for obtaining no objection letters. Procurement for ICB should be delegated to the programme. The procurement office should also be strengthened with qualified and professional staff.