Annex 16: SNNPRS report

# 1.	Background

SNNPR Region was visited by Rob Mellors and Habtu Gebrehiwot between 14th and 19th October 2007. Meetings were held with all key stakeholders including the Bureau of Capacity Building, the 7 sub-programme managers, the Regional BOFED and a range of beneficiary organisations. Additional information was obtained from special reports produced by the sub-programmes, PSCAP 5 year and annual action plan, various statistics provided by sectoral bureaus and relevant secondary evaluation reports.  Three woredas were also consulted namely Daalle, Damot Gale and Alaba Special Woreda. Persons met are appended in Annex 22.

The Deputy Bureau Head of BCB, the staff of BCB and PPD, sub-programme coordinators and other officials generously made time available for interviews and helped by producing reports, presentations and collecting various data. Woreda and municipal personnel also gave of their time.  The evaluation team would like to thank all those in the region who contributed in any way.

# 2.	Overall Assessment

The Southern Nations, Nationalities and Peoples Regional State (SNNPRS) is one of the more developed regions of Ethiopia. Its population, estimated to be 15.3 million in 1999 EC is the most ethnically diverse of any region with 56 different groups. SNNPRS has 13 zones, 134 woredas (including 8 Special woredas) and 22 town administrations.

Overall implementation performance of government’s PSCAP reform programme in SNNP Region is impressive with the exception of procurement of goods and consultants. Many of the PSCAP sub-programmes were already initiated and funded by government and various bilateral agencies before the initiation of the pool funded programme in October 2004.  Some of these sub-programmes e.g. JSRP, EMCP have continued to be implemented with only minor recourse to PSCAP pooled funds.

PSCAP is much appreciated by the Regional government who feel it is making a significant contribution to transformation. BCB also believe however, that despite awareness training on the programme, many people do not really appreciate its intended integrated nature - rather they tend to see it as just budget support. The role of the Regional Technical Team (RTT) should therefore be very important although it does not meet regularly.

Generally the service users in SNNPRS acknowledge considerable improvement in government services over the past few years. These are attributed to decentralisation and public sector reforms. In particular, improvements are highlighted in the fairness and efficiency of the tax and licensing system, in the performance of the courts and aspects of the judicial system and overall, at regional level in terms of openness, transparency and participation. There are also considered to be significant improvements in education, health, agricultural and water services.

There are overwhelming complaints by participating bureaus and recipients about the special procedures set up to access PSCAP funds. These focus mainly on procurement systems and planning arrangements. Further details are elaborated throughout this report.

Most of the issues raised in the March 07 JSM are still relevant – more specifically the need to revamp the RTT, the strengthening of links between regional and federal sub-programmes, the need to recruit more procurement specialists.  MMAs are complete for all sub-programmes except DLDP and programme management.

# 3.	Assessment of Sub Programmes

## 3.1	Civil Service Reform Programme

### 3.1.1	Overview and Organisational Setup

The overall objective of the CSRP in SNNPR is to transform the civil service institutions and boost their capacity. This includes improving responsiveness, transparency and accountability. It also means increasing efficiency and effectiveness in service delivery. Implementation beneficiaries include all sector bureaus and public bodies at zonal and woreda levels, the Anti Corruption Commission and the Civil service Agency.

CSRP is managed by the BCB. It has CSRP Steering Committees at all levels and focal people in most bureaus and offices. The Regional Steering Committee is chaired by BCB.  The CSRP office at regional level suffers from high staff turnover. There are presently 2 vacant posts. The office has adequate IT equipment but lacks transport which is hampering M&E in particular.

Most training under CSRP is being conducted in house or through the Regional Management Institute which is the prime local training facility. The RMI has been strengthened through provision of computers and IT equipment although some orders are long overdue. It conducts training impact assessments immediately on completion of each course and then tries to do later evaluations through questionnaires. Overall the response of trainees is reported to be good. The RMI itself would like to further build its capacity so as to carry out more consultancies. Future plans include forming an association with another region. Virtually no use is being made of private sector institutions for training in SNNPRS.  Under the CSRP a training impact assessment has just been completed.

Subjectively the CSRP managers say that significant improvements are occurring especially in attitudes to customers, participation and service delivery.  Transparency is also increasing but the struggle against corruption however is regarded as critical.

### 3.1.2	Improving Governance of Human Resources Management and Control

The Civil Service Agency (CSA) has produced various manuals and directives on HRM including recruitment, promotion, HR planning, discipline, transfers, the strengthening of ethical merit based systems and Results Oriented Performance Evaluation (ROPE). Extensive training on HRM and ROPE has been carried out in all public bodies at all levels. The CSA has also tried to do job analysis and evaluation but find this generally beyond their capacity. CSA has received good assistance from PSCAP regarding IT equipment and copiers etc. but only 20% of CSA funding is through PSCAP. It works primarily with government resources and NGOs.

The ROPE system is gradually being accepted and introduced in all bureaus and offices. Many civil servants find it difficult to understand but resistance is said to have dropped by 70%. ROPE is reported to be having a significant impact on individual performance and is increasing employees’ understanding of the need for effectiveness. It is supposed to be tied into ‘Performance Agreements’ signed between each sector/zone/woreda and the regional BOFED.  Many interviewees however were not aware of what was in these performance agreements. Individual performance assessment will be more appropriate once the current round of BPR has been implemented. At that stage ROPE will be replaced by Balanced Score Card.

### 3.1.3	Improving Performance and public service delivery

All public bodies at Regional, Zonal and Woreda level have received training in strategic planning. Similarly most have been through one round of BPR training, however the region has decided that the BPR syllabus needed to be revamped and is now piloting intensive BPR with 8 major stakeholder sectors including Agriculture, Health, Education, Urban/Municipality.  The process is taking much time and energy - around 400 people are involved. Many find it difficult. The study process will take 6 months to 1 year and will be followed by implementation. Like the Strategic Planning before it, the BPR is taking a vertical approach, dealing with each sector from region down through zone and to the woreda. One hopes this takes into account the important horizontal coherence of woreda local governments. Under the leadership of the CSRP personnel these sectors are currently undertaking their studies with a view to implementation in due course.

All public bodies at all levels have produced strategic plans although they are of variable quality. At the Woreda level the plans tend to mainly sectoral and not fully integrated into overall Woreda Strategic Plans.

BPR Round 1 has had some impacts in Woreda OFEDs through changed structures and the shortening of time to complete functions.

In terms of service delivery many woredas now have public information boards displaying mission statements and service objectives. There are also public grievance procedures. The Education Bureau through its twice yearly evaluations notes improvement in woreda management of schools. Woreda cabinets are increasingly evaluating performance and allocating budgets more effectively.

### 3.1.4	Improving Transparency and Accountability

In addition to generalised training and distribution of regulations for civil servants on ethics and transparency, specific work is being done on corruption by the Anti-corruption Commission utilising PSCAP funds.  The ACC disseminates ethics education and generally tries to raise awareness of corruption throughout the general public. Working particularly with the women and the youth they have set up 42 anti corruption forums and groups which have been operating for over 3 years. These for a organise seminars and utilise the state media to educate people through 30 minute weekly radio programmes. They also use 3 community radio stations. At times they act as whistle blowers to the regional government when they spot corrupt practice. The Commission are members of both CSRP and JSRP Steering Committees as they also have a law enforcement branch.  The anti corruption survey in the region has been blocked for 3 years by World Bank insistence on it being done by a independent agency without involvement of the Commission.

The work of the Commission causes some tension within the civil service. Non corrupt people however welcome it. Generally the Commission sees minor but widespread corruption especially at woreda level.

### 3.1.5	Strengthening Top Management Systems

Managers and leaders have been through several rounds of training down to woreda level (including School directors) at the rate of 20,000 to 30,000 per year. The curriculum is developed by BCB and the 10 to 15 day courses include government policies, change management, leadership etc.

The CSRP and DLDP training programs in strategic planning, good governance, BPR, ROPE and Top management are having a significant impact on organisational systems.  Based on their own training woreda officials are attempting to cascade down their knowledge to councillors, lower level staff and kebeles.

### 3.1.6	Training evaluation

The CSRP has recently conducted an evaluation of some of its training programmes. Its findings reveal that most participants felt that the EMCP training on budgeting and accounts reforms has had major impact. Regional and zonal officials also saw significant change as a result of BPR and strategic planning whereas woredas were most positive about attitude and environment changes for service delivery. Least impact was observed on transparency and accountability. Main criticisms related to lack of training continuity/follow up, poor methodology and technique and inadequate time. There are serious concerns that poor leadership limits training impact and the ability to implement reforms.

Concerns were also expressed by different trainees during the evaluations as follows:

- No co-ordination re the woreda level. Courses are just cascaded onto people as and when the trainers are ready to provide them. There is little woreda input into need or design;

- TOTs and courses themselves are usually too short with inadequate selection of trainees;

- Training courses are often too short with too many subjects and no follow up;

- Training quality is often inadequate;

- Training fatigue.

## 3.2	District Level Decentralisation Programme

### 3.2.1	Overview and Organisational Setup

The District Level Decentralisation Programme is intended to strengthen decentralisation programmes at grass root level, thereby deepening the devolution of power, enhance grass roots participation, promote good governance and improve service delivery.

SNNPR’s 134 woredas have capacities covering a wide spectrum. Most woredas have developed a basic, though improving range of capacities to carry out their functions including planning, budgeting, financial management, revenue raising and public mobilisation. They are less proficient in terms of procurement, HRM, corporate management, making by-laws. During this evaluation we were only able to visit a small number of what are most likely to be the more capable woredas. The following statements derive from these visits plus previous visits to 8 other woredas earlier in the year.

Other than the Woreda Good Governance Package, most woredas know little about the content of the DLDP. This is perhaps not surprising since most DLDP initiatives are regional and are about creating an enabling environment for local government.

There are still some MMAs to be achieved by DLDP, notably the HR and Training Needs Assessments, the Participation and gender plan and manual and the region’s Decentralisation Strategy.

DLDP has relatively good horizontal and downward relationships, however its links with Federal DLDP are weak. Whilst it receives federal prototypes and reports, it complains of little support in terms of implementation and advice. With regard to IEC, DLDP has not produced any specialised material of its own either for the print or radio media.

DLDP has 4 staff at Regional level. In addition there are Capacity Building Officers in each Zone and in 50% of the woredas. Whilst adequately equipped with IT infrastructure, DLDP has no transport which makes travel to the woredas extremely difficult and seriously limits M&E activities.

### 3.2.2	Institutional and organisational arrangements

The Legal Framework and Functional Assignment documents are presently under scrutiny from Bureau of Justice and should soon be proclaimed.

Woreda officials have a generally good understanding of their main purpose and their governance and service delivery functions. This has improved significantly over the past 3 years. Further work is required with Councillors in this regard. Until the legal framework is published there remain numerous confusions over functional assignments.

Whilst the financial management structures in woredas have been unified, HR and equipment are still managed on a sectoral basis preventing the woredas making optimal allocation and use of their scarce human and physical resources. It is difficult for woredas to make major structural changes as their structures are modelled on guidelines from the Regional CSA. Structural guidelines can change every year.  Maybe when BPR takes root, woredas will have the power and understanding to develop their own structures although the sectoral orientation of this exercise may be limiting.

### 3.2.3	Manning and Training

The Human resource and Training needs assessment is currently being updated by a regional team following failure to procure a consultant.

Woredas in general are still significantly understaffed with less than 50% of all posts filled across the Region, even so most employ between 700 and 1200 personnel including teachers. Except in the favourable areas, there is a high staff turnover especially once people have received training. This is mainly due to low salaries and low incentives. Many woredas also still lack basic furniture and office equipment.  Around 25% of finance office staff have received training.

### 3.2.4	Grass roots participation

Preparation of a Participation manual with special emphasis on gender is currently under preparation in conjunction with the Bureau of Women’s Affairs.

### 3.2.5	Woreda fiscal transfer and own revenue enhancement

SNNPRS has pioneered different block grant formulae over the past 5 years and is generally regarded to be at the forefront of formula development in the country. Work on the formula is led by BOFED rather than DLDP. The present formula is complex and involves two main elements, one for the recurrent budget and one for a notional capital budget. The recurrent element is developed from needs based sub formulae involving the five main sectors plus administrative and general services.

The woreda block grants are now allocated by the Zones. This has significantly reduced the burden on Regional BOFED and has empowered the Zones who now have a significant allocation and management responsibility.

The more advanced woredas have introduced the TIN system and have run tax payer awareness programmes e.g. 480 out of 700  taxpayers are registered in Alaba.

Financially, most woredas still spend 80 – 90% of their annual budgets on salaries and recurrent costs. Some try to allocate a small capital budget e.g. Alaba has 2.9m Eth Birr in 2000 EFY. Whilst local revenue is generally perceived to be increasing, it still only contributes around 20 to 30% on average.

### 3.2.6	Woreda Planning and financial control

Little work has been done with regard to the planning part of this component. Federal DLDP has recently produced a study and a first draft manual which the region will examine in due course. The intention will be to produce a regional guideline. Ideally this should take account of the needs of the forthcoming Local Investment Grant (LIG) pilots.

Despite all the energy that has gone into woreda strategic planning, there is only limited development on the ground due to inadequate capital budgets.  By using a high level of community contribution however, woredas can make small capital budgets go a long way. Responsibilities for construction and procurement in relation to medium to large projects are handled at zonal level.

With regard to Expenditure management, all woredas operate a single pool treasury. Most have received training through EMCP and have implemented budget and accounts reforms. The better woredas have now computerised their accounts and payrolls and have introduced improved budget disbursement management.

### 3.2.7	Minimum service standards and performance assessment mechanisms

A study of service delivery mechanisms, standards and local government performance monitoring systems has been undertaken and a draft Minimum Service Standards Manual produced.  The Manual is now translated and is under examination by the Justice Bureau. It will also soon be passed by the Regional Council. Once the MSS are agreed, the challenge for the region will be to design an institutionalised woreda performance monitoring system to measure changes in service delivery.

Some woredas are involved in the sectoral BPR exercises which have been initiated at regional level. These should eventually result in improved efficiency and effectiveness in service delivery. The PSIP components of CSRP have already improved attitudes to public service provision.

### 3.2.8	Woreda Good Governance Package

Much recent attention has been given to cascading down the Woreda Good Governance Package through mass training. This has involved translating the federal manual and running TOT training programmes to take the document down to woreda and kebele levels. Many different officials and politicians have received training including 1,100 agriculture development agents based in kebeles.  Kebeles are also receiving basic training in expenditure management and model farmer selection. The training has already stimulated politicians to become more involved in planning.

Kebele capacities are being strengthened by employing cabinet members through the woredas. In progressive woredas, kebele executive committees have been increased in size from 3 to 7 members and kebeles are starting to plan on their own. They are starting to deal with service seekers and each has set up 4 special standing committees for education health, rural development and justice comprised of community members to mobilise people and deal with issues and problems.

Model farmers have been selected and given awards at woreda, regional and federal levels.

### 3.2.9	Woreda Equipment

Woredas remain seriously constrained in terms of transport resources and often depend on one or two vehicles run by the health, education or agriculture sectors. Some run a few motorbikes.  Whilst numbers of computers are increasing, there are usually less than 10 or 12 at a ratio of about 1 per 100 staff members.

## 3.3	Expenditure Management and Control Programme

### 3.3.1	Overview and Organisational Setup

The EMCP was previously part of the CSRP but is now a programme in its own right based in BOFED. There are 15 to 20 people involved in implementing the EMCP in the region. The sub-programme has set up special Woreda Support Units in each Zone to facilitate the reforms through training, on the job support and follow up.

Very few of the EMCP activities have been funded through PSCAP to date. Most use has been made of the DSA project which has provided excellent professional and technical support. DSA has Channel 3 funding systems which are more straight forward. The impending close of DCA will mean much greater use has to be made of PSCAP funds.

### 3.3.2	Improving governance of financial resources management and control

EMCP has run numerous technical training programmes to install new reforms including Budget Information Systems, Double Entry Accounting and Budget Disbursement Management including zero balance approaches. Through the CSRP guidelines and training manuals have been produced for internal auditors.

BOFED has also been very active in installing the new IBEX (Integrated budget and expenditure management) system across public bodies in the region. This integrated software replaces the previous BIS and BDA3 stand alone packages for managing and monitoring budgets and expenditure and is designed to be run on the web once all woredas and bureaus have established consistent and reliable internet access. It can generate a wide variety of analytical finance reports. BOFED also tries to operate a responsive capacity building service to woredas which is reported by the woredas to be highly effective in stimulating learning through doing.

EMCP carries out one impact assessment per year although these have not been formally written up. The Budget reform, cash management and accounts reforms have all had major impacts on financial management systems in the bureaus. Budgets can now be appropriated within 2 months of consolidation. Furthermore budget performance and accuracy is much improved in the executing agencies. Accounts backlogs have been significantly reduced. The region is now almost up to date and is closing 1999 accounts. Staff turnover is generally reported as a major problem leading to understaffing of key posts in WOFEDs which in turn can lead to accounts being a month or more out of date.

According to BOFED, woredas have wide variations in capacity - 30% are in a capable category, another 30% are moderate but 40% have serious capacity constraints. All categories however have shown marked improvements in efficiency with the one pool treasury system. On the whole WOFEDs are improving their capacities even though less than a quarter of the staff of WOFEDs have received training through EMCP.  There are often conflicts over new and old systems resulting from the partial staff training. Whilst EMCP impacts are high on both individuals and organisations, there are high levels of staff turnover especially in the less favourable woredas.

Accounting systems in most woredas are not yet computerised however there are exceptions where both accounts and payroll systems are now computer based. In more progressive woredas, WOFED staff now travel out to pay teachers and kebele staff thereby reducing the hours lost by crucial service providers taking time off to collect salaries etc.  The High Tech approach of the EMCP is considered appropriate despite capacity and equipment maintenance constraints.

## 3.4	ICT Sub Programme

### 3.4.1	Overview and Organisational Setup

PSCAP is a very important programme for the ICT reform with most ICT activities dependant on some level of PSCAP funds. The ICT sub-programme has 4 components, ICT for human resource development, ICT for public services delivery and good governance, ICT applications for sector development and ICT for community based information systems and services.

SNNPRS is regarded as one of the leading regions in developing the ICT sub-programme. Much creditable work has been done although the demands remain high. Staff turnover and the variable quality of equipment are posing serious maintenance problems. Negative lists preclude purchase of much needed small buildings to house ICT equipment in a number of woredas and for transport to facilitate maintenance and support.

In terms of IEC, the ICT sub-programme has produced a number a small leaflets on its own accord, however it would do more if a comprehensive IEC strategy was organised by BCB.

ICT is a well established sub-programme within BCB. At regional level it has 9 staff against an establishment of 12. In addition there are 2 operators and 1 ICT expert in each zone and 1 to 2 operators in each Woreda. This sub-programme has a very good record in terms of activities completed and under implementation.

### 3.4.2	ICT for human resource development

Activities carried out include:

- Establishment of a 60 unit training centre at the RMI and smaller centre at Jinka and  Mizan;

- Training of 2500 civil servants on basic computer applications and internet;

- Training of 200 Woreda Net operators;

- Training for 45 audit personnel on Peachtree accounting system;

- Training of 20 ICT experts on web page development, network administration and advanced PC maintenance.

ICT skills have been significantly increased and are in high demand in the Region. It is hardly surprising therefore that there is a reasonably high level of staff turnover – e.g. of 200 woreda and zonal operatives trained in 2005, 171 were still in post 2 years later.  Salaries are low at 600 Birr per month and the Region has so far refused to make any incentive payments to ICT trained people.  Woredas complain that although operators have been trained, they have limitations with regard to maintenance.

### 3.4.3	ICT for public services delivery and good governance

A Regional Data Centre has been established plus 104 woreda information centres.  A LAN has also been set up for various regional bureaus.

A great amount of IT hardware has been purchased for the region, zones and woredas including 600 computers, 75 heavy duty photocopy machines, 250 printers, 57 laptops, 2 sets of surveying equipment, video conferencing facilities for woredas and 8 cities. 11 different training manuals have been developed to support this hardware installation.

M & E is weak in terms of recording impact on structures, systems and individuals. The impacts are however reported to be high.  ICT equipment, LANs, WANs etc. have transformed the communication and data systems of most organisations in the Region. Impacts are reported to be particularly high in the Regional Courts.

At woreda level, there remain many technical problems with Woreda Net with numerous complaints about the quality of the PSCAP purchased ICT equipment.  Some woredas have suspended their internet. Instead of purchasing tried and tested Dell and Compaq machines, PSCAP has procured lower capacity Acer equipment which is also reported to be breaking down more frequently and with little back up. Similar reports have been received with regard to photocopying machines.  The Video Conferencing equipment in general has been little used so far and in some woredas is experiencing technical problems.

### 3.4.4	ICT applications for sector development

This component has provided:

- some support for School Net;

- a database for anticorruption commission;

- a Capacity Building website for the region;

- 11 different sets of training manuals.

It also covers operation and maintenance of photocopiers installed at region, zone and woreda levels. The establishment of e mail and the website has facilitated much improved ICT  linkages between bureaus in the region and with zones and woredas at lower levels.

School Net is reported to be working in approximately 50% of high schools. Programmes are produced at federal level by the Education Media Centre and are broadcast from a central transmission station. These programmes augment the classroom teacher. Whilst most parents and students appreciate the innovation, the slower children struggle to keep up with the programmes.

### 3.4.5	ICT for community based information systems and services

2 community computer centres have been established providing secretarial services and 3 community radio stations have been supported.

## 3.5	Justice Sector Reform Programme

### 3.5.1 	Overview and Organisational Setup

The objectives of the JSRP include promoting an efficient, accessible and accountable justice system with community participation, that protects human rights as enshrined in the Constitution.  There are 7 potential implementing agencies under the sub-programme – Courts, Justice bureau, Police, Prisons, Prosecutors, Nationality Council and Council of Peoples Representatives. Up to 2005 the JSRP was under the Justice Bureau but has since been moved to a department under BCB.  It is staffed by a sub-programme head and 1 expert. It should have a staff complement of 5. Additionally there should be an expert in each zone and in every woreda. There are focal persons in all implementing agencies.

The JSRP is guided by a Steering Committee at regional level chaired by the State President. There are JSRP Steering Committees at all other levels although most woreda and kebele committees are not very active.

JSRP also receives support from several agencies other than PSCAP. Many of the reforms under the JSRP especially those concerned with strengthening the courts, were initiated well before PSCAP. Activities under PSCAP have simply involved further roll out of existing reforms. Some agencies report that the programme worked better before it was taken over by PSCAP especially in terms of procurement. They would prefer not to become dependent on PSCAP.

Generally the JSRP officials appeared somewhat frustrated by staff turnover, lack of incentives, lack of transport and inadequate support for the 3 Ps. The sub-programme is also weighed down by all the bureaucracy and paperwork associated with PSCAP systems in particular managing the planning and coordination associated with 7 beneficiaries. Procurement of basic items such as colour coded files has been seriously delayed under PSCAP and the courts have had to get limited materials from the Federal Supreme Court.

PSCAP is regarded by some JSRP implementing beneficiaries as ‘not user friendly’. They have not received adequate training on how to access the resources and quite frankly would prefer not to get bogged down with the procedures if they can get support from elsewhere. Links between some beneficiaries and the JSRP are now quite weak.

In terms of MMAs, almost all activities are completed except for the court inputs in the 29 newly established woredas.

### 3.5.2	Strengthening the judiciary and the courts

Most activities have centred on the courts where achievements have been impressive. These have included:

- In service training for judges, lawyers and clerks on the new penal code, criminal law and the independence of the judiciary. Training activities have had clear objectives and have been complemented by distribution of 1,400 copies of promulgated criminal laws.

- Training for Woreda court judges on constitutional principles and fundamental rights. Training is also required on the interpretation and intention of the criminal law and penal code.

- Establishment of a computerised database in 25 regional high courts and the supreme courtso as to improve case management. The database is also being piloted in 7 woreda courts.

- Installation of colour coded files in all 104 woreda and 19 city courts.

- Information desks set up in all High, City and Woreda Courts,

- Upgrading of 200 prosecutors and 200 judges from certificate to diploma level through training.

Regarding future plans there are intentions to further improve the effectiveness of the woreda courts, to institute a regular court inspection programme, to further develop HR especially through pre-judicial training of lawyers to become judges, to improve the use of IEC and network the supreme and high courts and finally to enhance child friendly and other specialist courts.

Since the Justice situation in SNNPR was previously characterised by big backlogs in court case decisions, an acute shortage of trained professional judges and lawyers, (most judges having less than 6 months training), a lack of facilities and IT, poor record keeping and poor response to the people, the overall improvement resulting from these interventions has been high. Significant improvements have included:

- The computerised database and the standardised case forms have been immensely helpful for case management. The cases handled by the courts have doubled in the last 5 years and the backlog has been reduced by 10%,

- Overall numbers of cases opened and dealt with in a year has increased from 58 to 78%.

- The new transcribing equipment and the photocopiers have increased accountability, transparency and reduced workloads (mainly federal support rather than PSCAP),

- The information desks have markedly improved case access for clients and have been complemented by a 1 stop service arrangement.

Woredas acknowledge good training impact with woreda judges and other court officials. They confirm shorter time frames for decisions. Some have installed IT based recording and transcription. They also appreciate the ethics training with the police.

### 3.5.3	 Law revision and law reform

No specific activities were noted in the region relating to this component although this is an ongoing activity in the Justice Bureau.

### 3.5.4	Law enforcement organ capacity development

Police and prisons have only received PSCAP support for the last 2 years. These organisations have been precluded from obtaining hardware so far although they would much appreciate support with computers, furniture and further training. They have not been involved in BPR.

523 woreda, zonal and regional prosecutors have been trained on good governance and democracy, justice reform, new penal codes, human rights, fundamental rights of the accused.

The BCB/JSRP in conjunction with the Police Commission have run 2 week training programmes on good governance and democracy, JSRP awareness, community policing, human rights and prison handling laws for around 1,305 regional, zonal and woreda police management.

The police themselves report significant change in the attitudes and behaviour of their officers especially in terms of public service, case handling and awareness of human rights. Citizens acknowledge a general improvement but highlight issues of ‘nationality’ bias in terms of application of the law.

### 3.5.5	Legislative organ

Considerable work has been done through the sub-programme to build the capacity of the legislative organs. Training of members of the Regional Council and Nationalities Council has been conducted on roles and responsibilities, good governance, democratic systems and multi party systems. Special training has been given to 75 women members on women’s rights and the role of women in good governance and democracy. Training has also been provided to the Regional Council Standing Committees, Zones and Special Woredas on 8 relevant policies and strategies of government. There is an intention to train the incoming woreda councillors following the January 08 elections.

Members consider the impact of the training to be high.  The Regional Council now operates much more effectively and efficiently, makes more informed decisions and contributes with more in depth understanding on legislation. Councillors from Zones and Special Woredas are attempting to cascade down their training to Woreda Councillors.

## 3.6	Tax Systems Reform Programme

### 3.6.1	Overview and Organisational Setup

The Tax Systems Reform Programme began five years ago under the Bureau of Revenue.  Its objectives are to mitigate the problems of the tax system so as to attain macro economic stability and create a conducive environment for transformation of public goods and service delivery capacity for economic growth, good governance and poverty reduction.

TSRP is now  managed by an Implementation Unit within the Regional Tax Administration Authority.  Only 2 people in the Authority currently work with the PSCAP sub-programme – a focal management person and a planning officer.  Two more are required especially for M&E. The Manager has only been in post for 6 months and is still learning about PSCAP.

All MMAs have been completed. In general however, the sub programme is not progressing as well as expected due to the delays on procurement of goods and delays on receiving World Bank ‘no objection’ for consultancy activities.  As a result the main activities to have been carried out are training. No IEC strategy has yet been implemented.

The TSRP has facilitated an increase in tax revenues from 260m Birr in 2004/5 to 316m Birr in 2006/7. Most woredas have seen some level of increase in local revenue (some report 20% per year) which has contributed in a small way to their budget.

### 3.6.2	Tax policy and legislation

The TSRP has overseen the issuing of the income tax proclamation, business turnover tax proclamation, agricultural income tax and land use fee proclamation.  5520 copies of these instruments have been disseminated. Studies of the revenue potential of the region are yet to be conducted.

The public perceive that dated and complex tax laws are now much improved. There is better application of the tax laws at woreda level.

### 3.6.3	Tax payer identification number

The TIN has been introduced and awareness training programmes have been carried out with tax payers.

From a situation in which the tax office was unable to readily identify tax payers, 61.8% of the 34,018 tax payers are now registered with TIN. More progressive woredas have introduced the TIN system and have run tax payer awareness programmes. As yet the TIN is not fully computerised.

### 3.6.4	Presumptive taxation

Business turnover surveys have been completed and new more reasonable tax rates have been introduced.

Businesses paying presumptive tax have increased from 35,000 to 55,000 in the last 3 years. They  now volunteer their payments as this tax is seen to be fairer.

### 3.6.5	Value Added Tax

VAT is a newly introduced indirect tax aimed at broadening the tax base. The VAT system has been publicised in the media and 10 Regional and Zonal Tax officers have been trained on VAT administration and auditing. Receipts are increasing and have now reached 2.7m Eth Birr with 347 businesses now registered for VAT.

### 3.6.6	Operational Programmes systems, procedures and manuals

Under this component, it is intended to develop manuals on Business Turnover Surveys, and adapt guidelines for revenue transfers, reporting systems and refunds administration. 26 computers, a projector and a photocopier have been procured. Work has been initiated on LAN for a government tax administration system. Terms of reference have been developed for establishing the LAN and SIGTAS.

### 3.6.7	Organisation and tax payers education

Training needs assessments have been completed in all branch offices and training programmes conducted for revenue staff at all levels on a wide range of relevant topics including database operation, VAT, with-holding tax, tax auditing and tax assessment. Oracle and database training has also been provided to one tax officer. Awareness and skills of tax officers re tax law and procedures is significantly increased. The structure of the regional tax collection institutions has been revised twice.

Woreda and town staff  have been trained on strategic planning, ROPE and identifying revenue potential. Distance education is being provided for some branch staff. Taxpayer education has been improved through publicity campaigns raising awareness on tax laws.

Tax payers’ attitudes have certainly changed for the better and their level of awareness on taxation issues has been increased. This is indicated by an increase in the number of self declaring taxpayers.

## 3.7	Urban Management Capacity Building Programme

### 3.7.1 Overview and Organisational Setup

There are 22 cities in SNNPRS mandated to provide both municipal services and core state functions. In addition there are 77 towns mandated to provide municipal services only. Cities are presently run by transitional administrations with appointed councillors or advisory committees. Elections for the new administrations are due later this financial year.

The UMCBP is run by 5 staff. It receives funding through government as well as PSCAP. It sees its main functions as;

- Adoption of policies and strategies;

- Deepening the process of decentralisation and

- Local Government restructuring with capacity building.

Up to now most of the UMCBP reforms have been achieved without the use of PSCAP funds but now the sub-programme needs a good deal of support through PSCAP. Unfortunately it has experienced severe frustration with its PSCAP funding. Out of a planned 45.4m Eth Birr for the first 3 years it has only received 3.25m Eth Birr due to the regional PPD deleting its programmes ‘for duplication’ and to failed procurement. Most of the expenditures have been on training although some of its planned training expenditures have been utilised for other sub-programmes. The relationship between UMCBP and BCB is not cordial. UMCBP sees BCB as a controller rather than a co-ordinator. By contrast the sub-programme has good relationships with its federal counterpart, receiving support and advice. It copies all quarterly reports to the federal level.

### 3.7.2	Regional Urban Management Policy

The UMCBP has its own strategic plan and has produced an Urban Development Strategy using a consultant. It has enacted a decentralisation proclamation enabling 22 regional cities to have new autonomous powers.

22 Regional cities are now decentralised and have autonomy over a range of functions. These have been categorised into 4 grades. Awassa (the regional capital population approx. 200,000) and the larger cities are in grades 1 & 2 are not regarded by UMCBP to have made much progress. Much more improvement has been achieved in the 3rd and 4th category cities.

### 3.7.3	Deepening the process of decentralisation

The regional UMCBP has received a large number of guidance documents on urban land management, housing, planning, revenue, justice, accountability etc. and restructuring from the federal UMCBP. These were produced with support from GTZ consultants. It intends to produce these as regional manuals and circulate to all municipalities if it receives PPD approval. So far 4 cities are being piloted.

Municipalities are generally self financing although they have not adopted the TIN system promoted by Bureau of Revenue. Awassa had achieved impressive increases in revenue generation from 9m Eth Birr in 1997 to 29m in 1999. 40% of its budget its budget was allocated to capital development and this is set to increase to 60%.

### 3.7.4	Local government restructuring and capacity building

The cities have also been facilitated by UMCBP to participate in the training programmes of the CSRP including a first round of BPR. Municipal staff from all the cities are being trained on urban issues and are due to receive equipment support through PSCAP. All the regional activities are being repackaged under the ‘Urban Good Governance Package’ which will include a further round of BPR.

In terms of impact, Awassa was initially doing well but now seems to be overwhelmed by growing demand for land and services. It has however upgraded the market with support from UMCBP although not with PSCAP funds. The municipality itself believes that PSCAP has not been of any significant help – in fact it was unheard of until a year ago. It only acknowledges receiving some basic equipment but hopes for further support through ICT for networks and computers this year. The city has received little training and has not given attention to the UMCBP manuals although it would appreciate some financial support with implementing these. The staff conducted the first round of BPR 2 years ago but saw little benefit in it. More is hoped for from the current round. Awassa Municipality is criticised by many residents for a lack of responsiveness and transparency.

# 4	Programme Management and Support

Programme Management is provided through the Regional PPD in BCB and is led on a day to day basis by the Deputy Bureau Head in BCB.

## 4.1	Coordination with MCB, sub-programmes and woredas

IEC, TSRP and EMCP have good linkages in all directions. ICT consults the federal level programme on the technical aspects of its Annual Action Plan. All these three sub-programmes report to both BCB and their federal equivalent. DLDP and the JSRP have very weak relationships with the federal level. They sometimes try to copy their quarterly reports through but generally receive little support or feedback.

ICT, EMCP, UMCBP and more recently TSRP all acknowledge good relationships with their equivalent federal sub-programmes. They now all receive various levels of technical support, advice, and training from the federal level. In return they ensure their quarterly reports are copied to the federal sub-programmes as well as to BCB.  These sub-programmes also report that they meet at least twice per year with other regions and the federal level and in the case of ICT, the federal level appraises their annual action plan before it is sent to BCB. TSRP would appreciate more visits from the Ministry of Revenue.

## 4.2	Institutional arrangements for PSCAP in region

The prescribed structural arrangement for PSCAP management in BCB is summarised below:

- ICT has a Dept Head and 10 expert/tech posts, 3 of which are vacant

- CSRP has a Dept Head plus 4 expert posts, 2 of which are vacant

- JSRP has a Dept Head and 4 expert posts 3 of which are vacant

- PPD has a dept Head and 6 expert/specialist posts in Planning, M&E, and procurement. 2 posts are vacant in M&E and procurement.

Staff turnover is reported to be high.  The PPD Co-ordinator only joined 3 months ago.

DLDP has a Dept head and 4 expert posts 2 of which are vacant.

Figure 1. SNNPRS Bureau of Capacity Building PSCAP Organisation

PSCAP in SNNPR is led with great energy and commitment by the Deputy Bureau Head in BCB. He has been actively involved in driving the transformational agenda for over 5 years.

There are however frustrations and concerns expressed by some sub-programmes regarding aspects of programme management. Several implementing agencies complain of perceived arbitrary cuts or reallocations in sub-programme plans and budgets by BCB and the ad hoc nature of RTT meetings rather than a consistent agenda for co-ordination of planning, appraisal, budgeting and monitoring. BCB acknowledge that the RTT is not working as expected but see this as a reflection of the lack of incentives for members. RTT involves hard work and members tend to leave this to the PPD. BCB explains the changes they make to some sub-programme plans as the result of duplication and ‘substituting PSCAP funds for recurrent budgets’.

## 4.3	Compliance with eligibility criteria by region

The BCB compiles a Participation Agreement Matrix and this is signed by the BCB head and MCB. Preparation of the agreement is regarded as an excessively lengthy task. Evidently the format has been shorted recently by MCB.

## 4.4	Planning and resource allocation

Planning is largely carried out by the sub-programme heads and the implementing agencies. The PPD planners see their role as minor, however they do offer advice to those who can’t produce good plans. Recently revised standard planning formats have been introduced by MCB which have improved the consistency of the plan submissions. Planning procedures are perceived by several beneficiaries to be highly tedious and unpredictable. As noted above there were repeated complaints by PSCAP recipients of BCB interference in their plans and a lack of even handedness regarding incentives.

Planning follows the normal government timetable. All sub-programmes have 5 Year plans and each produces an annual action plan. PPD consolidates the action plans in March and revises the action plans after the budgets are allocated in June/July.

The Regional Technical Team is regarded as a useful arrangement but only meets to consider the consolidated annual plans and the revised budgets. Attendance is inconsistent and the meetings are called on an ad hoc basis. It is not being used as an intersectoral co-ordination, integration, management and monitoring committee. It is reported to have met twice in the last year.

## 4.5	Sequencing and integration of reform initiatives

Given the unpredictability of the planning and procurement systems, most sub-programmes state that it is almost impossible to carry out logically sequenced activities and integration. Most PSCAP expenditure goes on in house training, not only because the sub-programmes believe this is a critical area but because it is easy to implement in comparison with utilising the funding for consultancies or goods.

## 4.6	Financial management

PSCAP funds are managed by BOFED. Funding requests are made by each implementing agency and sent to PPD for checking. PPD then authorises BOFED to release funds. PPD consider the procedure to work reasonably well although it can be slow.  Several EAs however resent having to send applications through PPD.

PSCAP financial allocations to the Region have been much less than originally planned. Of the total 5 year planned budget only 40% will have been utilised after 3 years. It is therefore unlikely that the Region will get access to the original budget in the 2 years remaining. The budget for the 2000 financial year is however much increased at 103m Birr against a plan request for 174m Birr.

Table 1. 1997-99 EC allocated and utilised budget for PSCAP

Source: BOFED/PPD SNNPRS

After the first quarter’s advance, statements of expenditure are produced each month and forwarded to MCB to trigger further releases of funds to the Region. In terms of each year's annual budget there has never been a shortage of funds.  Looking at the disbursement profiles for funds replenishment, the SOE system does not appear to have been a constraint to spending in SNNPRS.

Utilisation rates for the first year were very low at 7% due to inexperience of systems and lack of preparedness. These have increased to around 70% for the last 2 years. The average over the period is 56%. DLDP has received by far the largest share of the PSCAP budget to date at almost 60% followed by CSRP at 15%. UMCBP has received the least at just 4%. It also has by far the lowest utilisation rate. This is because it had large plans for consultancies and hardware which could not be achieved. For most sub-programmes, local training is consuming well over 90% of the utilized funds each year.

## 4.7	Procurement

The Procurement Desk in PPD is presently staffed by a Junior Officer who joined the Department only 3 months ago. The Region has previously bulked up its goods orders and pushed these over the ICB threshold causing responsibility to be transferred to MCB.  It has also however also tried to implement two NCB procurements but both of these failed due to World Bank objections.

Procurement systems are almost universally regarded as severely problematic in the region. Every sub-programme complains of :

- Centralisation of procurement by BCB and bulking of orders,

- Cumbersome procedures,

- Long delays involved with ICB, up to 2 years,

- Delays with obtaining ‘No objections’ from the World Bank.

These problems have led most EAs to regard PSCAP as a fund of last resort. Procurement difficulties for hardware and consultants have resulted in virtually zero utilisation of PSCAP funds for these purposes.

A number of the items so far procured through ICB have been found to be substandard. In particular the Acer computers have a high breakdown rate and are reported to be of low quality. The Xerox copiers are also said to be over sophisticated and have limited back up in the region. Lack of trust and concern with bulk buying is seriously compromising the hardware components of PSCAP. Inadequate attention is being given to local support and maintenance issues and to allowing regions to buy the most robust locally available models.

## 4.8	Monitoring and evaluation

Monitoring and evaluation is the responsibility of the PPD, the sub-programmes themselves and the EAs.

The PPD focus is on activity monitoring, checking that the various activities are carried out in line with the plans and budget.  Sub-programme teams are said to meet at least quarterly to monitor the budget and prepare their quarterly reports. BCB can also call a conference to discuss reports. Woredas are monitored quarterly through trips organised by BCB. 3 or 4 teams go out in different directions to meet with the Zones Cities and some selected woredas.

Output or outcome monitoring and evaluation is limited. The CSRP has done 2 impact studies- one very useful one on training.  In some respects it is early days to measure serious changes in the wider objectives of PSCAP. Impact monitoring is seriously hampered by a lack of transport.

Whilst the RMI carries out immediate evaluations of the training courses it conducts, the evaluation of overall training impact receives needs more attention.

## 4.9	Information, education and communication.

Two or three brochures were published in 1997-8 EC. Until recently however there has been no formally organised IEC programme. 2 new people have been recruited into an IEC unit in BCB. A Regional PSCAP web site has been developed.

# 5.	Cross Cutting Issues

The cross cutting issues of Gender, HIV/AIDS and environment are acknowledged as important issues in their own right by almost all agencies interviewed during the evaluation. It is generally felt however that there are appropriate structures already established to address these not as cross cutting but as mainstream issues. Many of the training programmes funded by PSCAP in the region are provided on a gender proportionality basis e.g in ICT 50% of all trainees are female. Several bureaus have departments which promote gender mainstreaming. DLDP follows a similar approach wherever possible and gives specific attention to the questions of women’s participation in its participation manuals. Gender issues are mainstreamed in the CSA and are also addressed in police training.

Similarly it is reported that specific sessions are held on HIV/AIDS in most training programmes. A Gender end HIV/AIDS Unit has been established in BCB. The Anti-corruption Commission focuses much effort on the women and the youth and has a unit for Gender and HIV/AIDS. The CSA plans to produce a workplace guideline on HIV/AIDS if it can get PSCAP funding. EMCP does not really take into account cross cutting issues.

The environment receives less attention in PSCAP and most agencies see it as the concern of the agriculture and rural development bureaus and offices at all levels. There is meant to be one Development Agent in each kebele providing extension services on environment and conservation.

# 6.	Assessment of programme outcomes

Assessment of Programme outcomes through a short term exercise such as this is inevitably highly subjective and questionable. There are no specific PSCAP evaluation reports and there was no baseline. Comments have been derived from interview responses and secondary data. An appropriate assessment of progress against higher level indicators should be the subject of an in depth study. Outcomes are also difficult to attribute to PSCAP. Most of the innovative reform programmes were established before PSCAP funds were introduced.

Overall however the efforts made by all the sub-programmes in SNNPR and the commitment of the leadership appear to be having significant impact in the performance of government in terms of service delivery and good governance indicators across the region.  A strong start to transformation has been made.

The Woredas and Municipalities are the prime service providing agencies. The better ones are now becoming credible and competent and are winningthe support of their constituents. There remain others however who have a long way to go.

## 6.1	Enhanced predictability of financial resource flows in-year and across years

The Regional Budget increased from 1,239m Eth Birr to 1,510.5m between 1995 EFY and 1997 EFY as shown in the table. Federal transfers increased from 818.6m Birr in 1995 to 1,102.5m in 1997 and 1,780m in 1999 EFY. Average growth per annum of these transfers has been an impressive 34.7% - one of the highest rates in the country.

Table 2.Sources of income for SNNPRS budget, 2002 to 2005

| Sources | 2002/03 1995 EFY | % | 2003/04 1996 EFY | % | 2004/05 1997 EFY | % |
| --- | --- | --- | --- | --- | --- | --- |
| Federal | 818,600,000 | 66 | 1,001,960,000 | 73 | 1,102,550,000 | 73 |
| Loan | 129,700,000 | 10 | 92,070,000 | 7 | 41,290,000 | 3 |
| Assistance | 103,200,000 | 8 | 44,890,000 | 4 | 40,920,000 | 3 |
| Revenue | 187,578,779 | 16 | 216,296,000 | 16 | 314,734,100 | 21 |
| TOTAL | 1,239,098,779 | 100 | 1,366,241,082 | 100 | 1,510,534,100 | 100 |

Generally woreda block grants have also increased from year to year. From 1998 to 1999, the growth was 61.6% and between 1999 and 2000 just 5.3%. Salaries consume an average of 81.4% of the woreda grants. Revenue from regional and woreda taxation is generally predictable and has increased. The introduction of IBEX allows detailed financial analyses of budgets, revenues and expenditures from every perspective enabling the region to detect trends and potential problems. Budget variance has improved.

## 6.2	Greater inclusiveness and transparency of planning and prioritisation processes

As decentralisation has progressed, woredas are increasingly informing their constituents of plans, budgets and budget performance. Strategic plans have now been in use for several years and are available to the public. The planning process in most woredas is highly participative and involves inputs from kebeles. Public review meetings are held in some woredas.  The Woreda Good Governance package gives added impetus to participation and transparency in planning and monitoring. The region has made a huge investment in promoting the Package.

## 6.3	Improved quality and efficiency of government operations in priority sectors

Strategic planning, establishment of minimum service standards, increased information on service provision, BPR and other training initiatives are thought to be stimulating a significant improvement in service delivery across all sectors. Service delivery programmes in CSRP have resulted in grievance procedures being established.

A World Bank Study of decentralised service delivery carried out in SNNPR in 2006 confirms that the devolution of power and resources to woredas appears to have improved the delivery. Furthermore, decentralisation appears to have favoured the more remote and food insecure woredas e.g. education expenditure increased by 44% in remote woredas between 2001 and 2004 but by only 9 % in woredas close to major centres. Expenditure figures have mirrored improvements in key service indicators.

Each kebele now has a first cycle primary school. Text book availability is increasing. Educational inspectors report increased enrolment rates and improving pupil teacher ratios. Around 50% of schools now able to run School Net. Whilst School Net has obvious usage in linking schools with the region and with each other, one wonders however if the benefits of the VSat programme transmissions could not have been equally well or achieved through distribution of DVDs.

.

The Good Governance Package, with its creation of model farmers, is reported to be stimulating improved agricultural productivity – although the last three seasons have all had favourable climatic conditions for agriculture.  The Package’s  emphasis on developing kebele structures and systems has enabled more problems to be dealt with at kebele level rather than being sent up to the woreda.

The zero cash management system has raised efficiency in sector bureaus. In particular the health, education and agriculture bureaus have streamlined their systems and now do not need to waste time maintaining bank accounts and paper based financial management systems. More time and resources have thus been released for service delivery.  The EMCP reforms also enable woredas to make more efficient use of their block grants to improve services.

Municipal services are also generally seen to be improving against a background of high demands e.g. In Awassa, road infrastructure has been vastly improved in the last 2 years although this is not a product of PSCAP. The Awassa municipality believes its relationship with residents is generally positive although the residents complain of a lack of transparency especially in land lease allocation.  Generally the municipal managers are considered to be too inaccessible and unresponsive. As another example, Alaba Municipality has also undertaken a number of reforms and is upgrading water services, drainage and roads. It has received awards for its good performance.

In terms of Court services, impacts are acknowledged by beneficiaries in the Regional Courts especially in terms of efficiency, time taken to deliver judgements and general customer service. There is greater accessibility to information on cases through the computerised case management system. People can obtain updates on their cases by phone without having to make long journeys back to the courts. There was no evidence however that the quality of judgements is increasing.

At woreda level people report speedier and more competent case management in the courts although as yet only few woreda courts have computer data facilities. They also report shorter queues at police stations and at courts. Some woredas have set up a mobile court service.

## 6.4	Improved incentive environment for public servants (gender disaggregated)

Although there have been significant pay increases for civil servants during the last year, no progress has been made on introducing performance related pay, neither has any other form of performance related incentive package been devised. This remains a difficult area and is a major cause of the high levels of staff turnover.  Sadly, developing the skills of key staff especially those in high demand sectors such as ICT and accountancy, merely hastens the rate at which they move to greener pastures.

## 6.5	Enhanced revenue performance and fiscal autonomy

Regional revenues increased by 21% between 2004/5 and 2006/7.  The region transfers just over 70% of its budget to woredas.

Tax payers report significant improvements in the efficiency and fairness of the tax system. In particular they cite improvements in the system of presumptive tax with reduced rates. They also find government and the tax offices more helpful in providing information and in being open to discussion on problematic tax issues with the tax payers. Businessmen have concerns over inequalities caused by variable VAT registration requirements – small emerging businesses do not need to register and can therefore offer lower prices.

## 6.6	Improved transparency and accountability

The implementation of the Woreda Good Governance Package is having a significant impact on governance including attitude, accountability and transparency at woreda and kebele level.  Woredas experience fewer complaints and note that kebeles are responding to a higher proportion of public needs.

Woreda public information boards displaying budgets and financial reports are increasing transparency although more could be done in this regard.

BOFED has established what it calls key ‘performance objectives (outcome) indicators’ complemented by key ‘performance target (output/activity) indicators’ for each of the main sectors. It is intended that these be adopted by the woredas as part of their performance agreements with the Region. There appears to be little enforcement of this so far however. Generally there is limited knowledge and understanding of these performance agreements outside of BOFED and senior officials. The performance agreements established by the Sector Ministries in health and education appear to be having more significant impact.

# 7.	Key issues arising from assessment

a) 	Low salaries, lack of incentives and high staff turnover

The issue of incentives is keenly felt in SNNPRS. Presently no incentives or top ups are given for people working on PSCAP. The programme is creating a large amount of additional work for people involved with producing training manuals and running courses. PSCAP planning and reporting processes are also considered to be very time consuming and burdensome. Furthermore the Region receives numerous visitors from other regions and interested parties who all want to learn from the SNNPR experience.

The only way officials and employees can gain additional pay for these activities is to give up their jobs and be ‘procured’ as consultants. There is an undercurrent of discontent arising from rumours that some sub-programmes receive preferential treatment with regard to payment of incentives.

b)	 Weak monitoring of higher level indicators – output and wider objective levels

Throughout all PSCAP sub-programmes, relatively little attention has been given to monitoring of outputs and evaluation of higher level outcome indicators. This is partly the result of focusing all energies on activity implementation but is also due to the lack of institutionalised monitoring systems and confusions over indicators in the log frame – a good number of which are not clear or particularly relevant.

c)	Negative Lists re vehicles and buildings.

Most sub programmes have no transport and the lack of vehicles is a serious constraint especially in terms of monitoring and evaluation. Valuable ICT equipment cannot be installed in some woredas as there is no secure and appropriate building.  Some sub-programme officials also complain that PSCAP does not fund study visits to other countries although this does not seem to have been the case across the board and is likely to be a planning issue related to BCB cancelling the proposals.

d)	 Police Prisons and Prosecutors

JSRP managers strongly believe that improved justice cannot be delivered simply by addressing issues of the courts but must include capacity building of the police prosecutors and prisons. The exclusion of the ‘3Ps’ arises from rules forbidding the World Bank to fund security related sectors.  Arrangements have now been made through MCB to allow other funders of PSCAP to notionally fund 3 Ps activities. The region still believes however that more funding is necessary for capacity building of these sectors.

e)	 Training

In house supply driven training comprises the vast majority of PSCAP expenditure. Training is a high expenditure item partly because it requires no complicated procurement processes and is easy to implement using in house trainers. Whilst most training is legitimate, it is reported that some of the training simply focuses on ‘awareness issues for local leaders’ and is of questionable relevance to PSCAP objectives.  Training activities should be better justified on the basis of argued needs and should be clearly documented with precise learning objectives and syllabi. More attention should be given to evaluations.

f)	Planning and budgeting systems

The planning and budgeting systems of PSCAP are bureaucratic and take up a great deal of time of already overstretched officials. Much of the problem stems from the need to replan after budgets are cut by MOFED. There is need for greater predictability of available finance at the start of the planning process so that replanning is reduced to a minimum. There are also complaints of excessive interference in the plans and budgets of sub-programmes by BCB.

g)	 Procurement

Procurement is a major bottleneck especially for ICB and higher value consultancies. Most sub-programmes have failed to procure anything beyond ‘in house’ training. ICB thresholds are too low. The PPD have forced bulking up of hardware procurement pushing the value of orders over the ICB threshold and therefore causing major delays. ICB takes a minimum of 18 months if all goes well. It is reported that NCB and National Shopping can only be done once per year hence forcing the PPD to ‘bulk up’ orders. The World Bank are also causing resentment in some agencies through what is regarded as ill informed ‘no objection’ refusals.

h)	Equipment maintenance

Equipment maintenance is a big problem – 50% of the computers supplied under PSCAP are presently broken down. Remarkably the ICB procurement process has resulted in the selection of poorly performing models and manufacturers rather than equipment which is well supported in the Region.

# 8.	Lessons learnt and recommendations

a)	Serious streamlining of World Bank Rules on procurement is required. Ideally ICB procurement should be decentralised to the Region. Procurement thresholds should be raised significantly and multiple local shopping or NCB tenders should be allowed in any one financial year. Regional government procurement systems should be used to facilitate purchase of locally supported makes and models.

b)	The Planning system could be further streamlined if budget allocations were made more predictable. This would facilitate one major round of planning in each year rather than having to redo the exercise after final allocations are published.

c)	The BCB needs to promote increased co-operation, co-ordination and teamwork amongst PSCAP sub-programmes and implementers. It could use the RTT more extensively to ensure integration and transparency in the way plans and budgets are finally agreed thereby reducing the under current of suspicion and resentment over plan adjustments.

d)	There is need to decentralise the budget of PASCP to all implementing agencies at Regional Level instead of leaving it with BCB. In such a situation, BOFED would be solely responsible for fund release. BCB should be responsible for co-ordinating the planning and budgeting process and for monitoring the expenditure of the sub-programmes. Sub-programmes within BCB such as DLDP, JSRP could also be given a degree of budget autonomy once the annual budgets and programmes have been agreed.

e)	Consideration should be given to funding PSCAP through GoE systems for planning and procurement. PSCAP funds could simply be earmarked through a budget support type mechanism.

f)	The log frames for the programme need to be reviewed to improve the input, output, objective and goal linkages and define more precise performance indicators. This should be a participative exercise.

g)	An organisational development component could improve the effectiveness of DLDP especially in the zones and the more advanced woredas. This should include facilitators working from support units to facilitate the identification of organisational weaknesses and to develop practical internally driven solutions including structural reorganisation and training interventions. Decentralisation of some element of PSCAP funding – a woreda capacity building grant - would also stimulate woredas to develop their own meaningful capacity building plans based on self analysis of capacity strengths and weaknesses.

h)	Many woredas need enhanced block grants with special a capital element to provide meaning for the planning system and other organisational improvements. Scope for integrating the proposed Local Investment Grant (LIG)  and the existing Protecting Basic Services (PBS) programme with DLDP should be explored such that woredas have three grants available to them – a block grant covering recurrent costs and service operations, a capital grant for new infrastructure and a capacity building grant to build up staff capabilities to carry out their functions. They could also benefit from some kind of one off equipment grant which could be linked to establishing cost centres for equipment and vehicle maintenance.

i)	Attention should be given to developing a transparent system of incentives for carrying out specifically agreed PSCAP activities.  Similarly more flexibility is required in terms of supplying vehicles for specifically agreed functions provided that the recipients can guarantee adequate operation and maintenance budgets.

j)	The region needs to give increased attention to IEC strategies. These could provide a way to reduce the costs of mass awareness training.

k)	Thought might also be given to integrating some of the PSCAP sub-programmes into rural and urban local government capacity building programmes as has been done in Tigray and is being thought about in Oromia.

l)	The legal frameworks for urban and rural local governments may need to be updated to integrate elements of the Woreda Good Governance Package.

m)	The Region should pioneer the introduction of a local government performance monitoring system to provide an example to other regions. It might try to solicit funding from the Joint Government Donor Working Group who are interested to institutionalise the Woreda City Benchmarking Survey.

# References

CSRP, 2007. Training Evaluation Report.

Haile Melekot Tekle Giorgis, Gail Amare, 2007. Success Stories Public Sector Capacity Building In Ethiopia.

Draft Report 19 October 2007.

JSM, 2007. Southern Nations, Nationalities and Peoples Regional State. PSCAP Report 30-31. March 2007

SNNPRG Capacity Building Co-ordination Bureau, 2003. Consolidated Public Sector Capacity Building Programme (PSCAP). Final Action Plan Document (2004-2008) September, 2003 Awassa.

World Bank, 2006. Ethiopia: Enhancing Human Development Outcomes Through Decentralised Service Delivery. AFTH3 Human Development Department, Africa Region. Sept 2006 World Bank.