Annex 11: Benishangul Gumuz report

# Background

Steve Topham, assisted by Ato Eskinder Tesfaye, conducted the assessment of PSCAP progress in the Benishangul-Gumuz Regional State government (BGRS) over the period 13-20 October 2007. Meetings were held with the Regional Bureau of Capacity Building (BCB); sub-programme leaders; the Deputy President of the Regional Council; the Bureaux of Health, Women’s Affairs and Education; the Bureau of Finance & Economic Development (BOFED); the Civil Service Commission; Assosa Town Council; the woredas of Bambesi, Homosha and Assosa; the Supreme Court, representatives from the Police and Prison services; the Regional Council office; Assosa Secondary School and the Assosa Chamber of Commerce. A full list of interviewees is attached as Annexure One. The Regional BCB and other interviewees provided written and electronic documents, a list of which is attached as Annexure Two.

# Overall assessment

The BGRS faces great developmental challenges – the region is remote, runs along the Sudan border for around 400km, and is on average only 200-250km wide. Road connections are poor, due to mountainous inland topography and river systems. Roads are generally untarred, which hampers travel around the region during the rainy season. Telecommunications and electrification are improving, although coverage and capacity is still very patchy. The regional population is around 700 000, and the state capital is the town of Assosa. The town was accorded urban municipality status in 2005 (1997 EC) and has some 40 000 inhabitants. There are 3 zonal and 20 woreda administrations.

PSCAP progress in BGRS has improved since the latest Joint Supervision Mission (JSM) visit in April 2006 (1999 EC), although not all Minimum Mandatory Activities (MMAs) have been yet achieved. Financial management and budget reform, and the Justice Sector Reform Programme (JSRP) continue to make good progress, building on the foundations laid by previous projects and flows of assistance. Sector specific programmes are doing well in harnessing flows of funds from other agencies, as well as government resources, in delivering integrated programmes of capacity building at local level. Woredas report significant positive impacts in service delivery improvements, increased participation and citizen responses to reforms.

The regional government has taken seriously the challenge of improving coordination

requirements, and has instituted a Regional Technical Team (RTT) and Steering Committee (SC) that are performing well and providing strong leadership to the reform process.

# Assessment of implementation of each sub-programme

## Justice System Reform Programme (JSRP)

### General observations

The JSRP is performing well, building on a solid foundation established through the previous CIDA-funded Court Reform Programme. The JSRP coordinator has a clear understanding of the programme, and works closely with focal persons for its five implementing agencies – the Regional Council, the judiciary, Justice Bureau, Police service and Prisons administration. This group meets twice each month to assess progress, develops plans and coordinate activities. PSCAP has supported continued professional training, assistance in introducing new administration systems, and supplied various equipments, including computers, transcribers, office equipment and furniture.

There is a high level of attention paid to monitoring outputs, particularly in legal case processes, which provides valuable data in assessing performance. Training records are good. It is encouraging to see the steps being taken to monitor outcomes – institutional checks, direct observation and surveys are used to assess the improvement in the quality of law making and judicial judgements.

PSCAP budget constraints are a problem for the JSRP, given it has to spread resources across five implementing agencies. The Supreme Court, previously a direct beneficiary of the Court Reform Programme, registers this effect most vocally. Allied to its position on the independence of the judicial system, this has given rise to a proposal for increased budget and delegation of authority, which was recently submitted to the BCB. In addition, the ‘3Ps’ – police, prisons and prosecution service – remain comparatively under-funded, due in part to World Bank restrictions on application of its finances.

While coordination within the JSRP is of a high standard, there is a greater need for integration with the CSRP to strengthen its impact. The CSRP provides valuable training on ethics and accountability to the civil servants in the Bureau. However, this is not considered to be as important by the ‘main service’ of the judiciary and court administrators. Increased awareness is needed among beneficiaries and coordinators to maximise the impact of these two sub-programmes within the service as a whole.

### Minimum mandatory activities

The MMAs are partially complete. Court case management, case recording and transcribing have been installed in the regional supreme and high court.  The colour coded filing system has been set up at this level, but as yet is only in place in some woredas. In-service training has been initiated for judges, prosecutors and court clerks, and continues to be implemented at scale. Gender and HIV/AIDS issues have been included in the training programme, either as specific events (for example, 57 prosecutors from the Justice Bureau attended training on gender equality issues held in EC 1998-99) or as components in other training activities.

### Strengthening the judiciary

There has been an impressive improvement in the professional capacity of the judiciary and support staff (court administration and Bureau civil servants), with a wide range of training activities completed (see Table 1).

Table 1.JSRP training EY 1998-99

| Training subject | Participants | Trainees |
| --- | --- | --- |
| Annual judicial work evaluation | Judges | 51 |
| Continued professional development | Judges | 61 |
| New penal code | Prosecutors | 23 |
| Civil service reform and court practice | Registrars and clerks | 28 |
| Criminal and civil procedure | Judges | 57 |
| Gender equality | Prosecutors | 57 |
| Public legal awareness | Female prosecutors | 48 |

Source: JSRP Summary figures EY 1998-1999

Training activities involve a range of service providers, with specific legal training being provided by judges brought in from Federal level. Training events are held on a regular basis, timed to align with the court calendar, records are kept and feedback from participants is obtained at each event. In addition, there is a concerted effort to improve the formal qualifications of judges: over the recent period 28 judges have improved their qualification from Certificate to Diploma; six have improved from Diploma to Degree, while two have improved from Degree to Masters level.

There have been significant improvements in court performance and the speed in which cases are heard:

- The case clearance rate now stands at 96% across the region

- The conviction rate has increased from 24% to 86%

- All outstanding backlogs have been cleared from the court rolls, achieved by judges working through their holidays (and paid by funds from the Prison Fellowship)

- The average time for prosecutors deciding whether to bring a case forward following a police case report now stands at five to seven days, compared to the normal standard of 15 days

Field visits to woredas confirmed that these advances were consistent at local level, and that community attitudes to the improved operations of the courts were very positive. For example, at Bambasi, the average time for closure of cases had been reduced to an average of less than four weeks from a previous level of six to 12 months. Assosa reported that all three judges of the woreda court had received training that court procedures had been speeded up and the backlog of cases reduced.

Equally importantly, there is a concerted effort to measure performance and outcomes of training activities, and to institute an effective system of self-monitoring and performance evaluation. To illustrate:

- A system of reviewing judges’ performance has been instituted, including monitoring the number of cases that are passed through on appeal to higher courts and their subsequent judgements. A Disciplinary Committee can then report on these matters to the Judicial Council, which can issue sanctions on judges for low performance and poor quality of judgements, including reprimands, reduction in salary, or dismissal. Conversely, judges with consistently high performance are rewarded with commendations and opportunities for advancement.

- An Annual Prosecutors Forum has been put in place, which assesses individual and collective performance, again with powers of sanction

- Inspection tours are made to assess the workings of the high and woreda courts

### Law revision and law reform

The BGRS has promulgated a new Family Law. .

### Law enforcement capacity enhancement

Police have received training on a combination of practical and higher-level legal issues, covering control of drug abuse (11 participants), crime investigation (26), the new penal code (51), exhibit management (24) and crime prevention (24). PSCAP funds have also been used to supply new equipment including a photocopier and laptop computer.

The police service is under-funded, with its budget covering mostly salary and running costs, leading to a serious shortage of vehicles, radio and office equipment. The PSCAP programme has made a valuable contribution in strengthening local capacity, although more is needed for the future. In particular, it is anticipated that the current upgrading of the main road from Assosa to the Sudan will lead to increased pressure on the police to deal with contraband-related crime and narcotics.

The regional prison service administers three penitentiaries in three zones. Prison officers have received training in human rights (60 participants) while senior management staff has undergone leadership training. PSCAP funds have been used to equip training rooms.

The police and prison service representatives reported a constructive relationship with the PSCAP process, and that activities have taken place in a coordinated fashion in line with their strategic and annual plans. The JSRP coordinator plans and prioritises activities jointly with service focal persons.

### Regional Council and legislative bodies

The Regional Council office has played an active role in securing support from PSCAP, in line with the Council’s Strategic Plan (EY 1998-2003) and its annual operational plans. It has also been adept in aligning other sources of support in implementation – for example, a training needs analysis produced under a UNDP-funded consultancy was used as a basis to identify activities to be implemented under the JSRP.  Action Aid Ethiopia, under its support for good governance and the parliamentary system, has paid for the printing of proclamations, regulations and manuals used in JSRP training activities.

To ease logistics and reduce costs, training activities take place around February (the Council Assembly meeting) and May (when the seasonal rains have lessened and transport is easier from the remote woredas). To date, 99 members of Regional Council and woreda standing committees have been trained on their duties and responsibilities,

The Evaluation Team was pleased to note that efforts are being made to assess the qualitative effects of the capacity building programme. While progress on the quality of law-making may only be discernable after a long period, sample surveys are made (15% of woreda council participants, 40% of Regional Council participants) to obtain feedback on the use and impact of the training. The general perception reported to the Evaluation Team is that there has been a gradual improvement over the past three years, with the Regional and woreda councils operating in a more democratic fashion and more open to considering new ideas and issues.

Interestingly, the Regional Council Office also reported that there had been an improvement in the quality of training provided over this period – trainers were more up-to-date and professional, and were able to tailor modules (sort and focused) to catch the attention of this particular audience.

### Gender issues, HIV/AIDS and the environment

The Evaluation Team noted high awareness of gender issues among programme staff and implementing agencies, and that active steps have been taken to include such aspects in the sub-programme plans, to ensure women participation in training events and to hold specific training activities on gender issues. Currently 20 out of 67 prosecutors are women, with the same number in the total of 68 judges.  Most women judges are to found at woreda level, with relatively few in the high and supreme courts.

Chairs of woreda standing committees have received training on gender and HIV/AIDS awareness.  In addition, further awareness training on HIV/AIDS has been accessed via Action Aid Ethiopia.

There was no evidence of any mainstreaming of environmental issues in the JSRP.

### Public awareness

There has been a concerted effort to publicise legal rights among the public – 89 religious leaders, elders and woreda administrators have undergone training on raising public awareness.

## Urban Management Capacity Building Programme (UMCBP)

### General observations

The UMCBP has experienced several changes in respect of its institutional arrangements in BGRS. Initially, it was located in the Bureau of Trade & Industry, and then relocated to the Bureau of Works & Urban Development (BWUD). From there it was shifted to the Assosa Municipality. At the time, this was seen as a logical location, given that there were only two designated urban municipalities in BGRS – Assosa and Debre Zeit. However, a further 33 small and medium towns have been now recognised as urban municipalities, necessitating a relocation of the programme back to regional level. The UMCBP is currently located in the BWUD.

The programme is guided by the Urban Task Team, which includes the BWUD Head and Bureau experts, the sub-programme coordinator and a representative from Assosa Municipality. It has a clear set of coherent objectives:

- Developing management systems and tools for municipalities

- Strengthening municipal structures and capacity to enhance service delivery

- Developing legal and policy frameworks to support urban development

Progress has been made across all three objectives. The new legislation has created an institutional platform for urban development, which will be further strengthened by the strategies and policies now in progress. Regional and local level political leadership and officials are giving more attention to urban development and growth, while administrative capacity in this sector has been strengthened. Management of financial resources is improving – for example, Assosa has recently updated its 30-year old service tariff, while improved land registration should lead to better and more equitable collection of property taxes.

Local democracy is also being deepened. Municipal leaders, who are currently appointed by the regional government, will stand in open elections in January 2008 (EC 2001).

### Minimum mandatory activities

Progress against the four MMAs is as follows:

- Development and adoption of BGRS urban development policy and strategy.  Status: in progress, with target for adoption by March 2008 (EY 2001). A draft has been prepared, and will be put out for consultation and discussion with municipal leaders in November 2007 (EY 2000). Once finalised, it will be tabled for consideration at the Regional Council.

- Implementation of personnel management manuals for municipalities. Status: in progress, a first draft has been produced and the target for distribution to and adoption by municipalities is March 2008 (EY 2001)

- Development and adoption of municipal legislation, and urban land management policy. Status: partially complete. The Regional Council has adopted the municipal legislation, which gives a legal persona to the 35 medium and small towns in the region. A tender bid for consultants to provide support to the BGRS in developing the urban land management policy has been evaluated, and was forwarded to the World Bank for ‘no objection’ in August 2007 (EY 2000). At the time of writing a decision is still awaited.

- Provision of one round of bulk generic training to relevant municipal and regional staff. Status: in progress, with one batch of training complete, and another scheduled to start in November 2007 (EY 2000).

### Local government restructuring and capacity building

A total of 217 staff has been trained over the past two years, with generic courses given on municipal service delivery, planning and implementation, good governance, and management skills. Specific courses have included municipal finance (for finance managers), and Geographical and Land Information Systems (for land use planners). A five day-training event on Strategic Planning was held for 52 participants from the BGRS, three zonal offices and municipalities, and a further round of training is planned for November 2007 (EY 2000). In small municipalities, much of the training is directed to a few relevant individuals who are multi-tasking.

The Urban Task Team developed three training manuals on good governance tailored to meet the needs of smaller municipalities. This manual was adopted from documents supplied from federal level, but also drew on a needs analysis of a sample of small towns across three zones in the region.

All urban municipalities with 24-hour electricity have been supplied with a computer and printer, while zonal offices have received this plus a photocopier. Assosa municipality has received six computers, a photocopier as well as planning and survey equipment.

### Gender issues, HIV/AIDS and the environment

PSCAP has been used to strengthen management of urban environment issues. The training courses given to professional staff include sessions on sanitation and environmental protection. In addition, the Assosa municipality runs environmental awareness campaigns and has just purchased new rubbish containers (transportable by donkey cart, and financed by PSCAP). This initiative is successful and is being rolled out to other municipalities.

Gender awareness faces major challenges in this programme. There is only one woman senior official in the region’s municipalities (a financial manager from Assosa), but efforts have begun by specifying that at least 20% of participants in generic training courses must be women.

HIV/AIDS issues show slow progress in mainstreaming in the programme. It appears for the first time in the current work plan, in the form of training for HIV/AIDS in the workplace awareness.

### Next steps

The UMCBP has overcome its initial institutional disorders, and has established an effective foundation for the programme. However, it faces problems of increasing both the scale and depth of its activities. Scale has increased with the declaration of new urban municipalities, while more depth is required with the provision of more advanced technical training. The BCB and UMCBP need to pay attention to these aspects in their future planning exercises, with strong motivations for increased allocation of resources for training and consultancy assistance.

## District Level Decentralisation Programme (DLDP)

### General observations

The DLDP falls within the BCB, and so far shows relatively slow progress. It has been hampered by staff turnover in management – the original post-holder died, the replacement left after six months and the current acting head of DLDP has been in position for only four weeks. The DLDP unit head manages two other staff, both of which have other duties, organising capacity building support to NGOs and cooperatives. Field visits are limited due to a shortage of government vehicles in the BGRS, although each woreda is visited at least bi-annually.

Communications between the DLDP and the woredas could be improved, with closer efforts to integrate woredas into regional forward planning. However, the Evaluation Team acknowledge that regional difficulties of poor road networks and restricted telecommunications also have an impact in this regard.

Despite capacity, communications and logistical limitations, the DLDP has implemented training activities and purchased and distributed goods to woredas. After a very slow start (in line with the rest of the sub-programme activities in BGRS), it has shown progressively improved performance. Expenditure increased from a negligible amount in 2004 (EY 1997) to 45% of the programme’s allocated budget in 2005 (1998 EC), and then to 64% in 2006 (EY 1999). In addition, the DLDP coordinates other funding streams targeted at improving skills at woreda level; an estimated breakdown of financial contribution by source is PSCAP 40%, CIDA 40%, and UNDP 20%.

### Minimum mandatory activities

So far, only two MMAs have been completed, namely the human resource, training and equipment needs assessment for woredas; and the plan for community participation. Progress in other activities is as follows:

- Decentralisation legal framework: Draft legal framework document received from Federal DLDP, October 2007 (EY 2000). This will now be assessed and adopted for implementation by the BGRS government.

- Minimum service standards: Service standards and norms document received from Federal DLDP, October 2007 (EY 2000). This will now be assessed and adopted for implementation by the BGRS government.

In addition, further documents and prototypes have been received from Federal DLDP for review and adoption, including the woreda planning and budgeting manual, model fiscal transfer formula, and the system for participation of membership-based civil society organisations.

### Capacity building

The human resource needs assessment of woredas has formed the basis for capacity building, in addition to the package of essential services necessary for sound administration. Considerable effort has been applied to training woredas in strategic planning, funded via CIDA. All the woredas visited in the region had five-year strategic plans. CIDA support also provided for training in a package covering leadership and motivation, decision making, development planning, good governance and service delivery. PSCAP-funded training was supplied in resource management (70 participants) training needs assessment (30), service delivery (81), advanced computer training (8) and the participation framework (255).

### Planning and participation

The DLDP has a five-year Strategic Plan, which is updated on an annual basis. The Strategic Plan involved participation of woreda leaderships in its design, although not in the development of the annual operational plans.

Planning and participation are inter-linked at woreda level. Information from the DLDP and visits to woredas confirmed that annual planning and budgeting follows a participatory process, along the following broad lines:

- Woreda and kebele officials discuss development needs in community meetings at kebele level

- Sector officials lead discussions with special-interest focus groups to obtain specific perspectives on proposals, for example, women’s associations, youth associations and HIV/AIDS clubs

- These needs are summarised, and then assessed at the woreda council (which includes kebele representatives) and prioritised

- The council approves the overall development programme in line with the approved budget, with kebele representatives reporting back to their constituents.

### Woreda fiscal issues

The woreda block grant system has been introduced, and accounts for around 75-85% of woreda finances across the region. In general it mostly covers salaries and recurrent costs, with little capital allowance for development projects. Concern was raised in woreda visits that budget predictability would assist in development planning, with more advance notification of the budget allocation.

### Woreda financial administration

There has been a very positive improvement in financial planning and control at woreda level. All woredas visited had closed their annual accounts for 2006 (EY 1999) and had been audited. All maintained assets registers, which were checked by the external auditors, and all had received unqualified audits. The regional Bureau of Finance & Economic Development (BOFED) has played an excellent role through its outreach teams in strengthening financial administration at woreda level.

### Woreda office infrastructure and communications

There has been a substantial distribution of PSCAP-funded equipment, mainly computers, printers and furniture. Training in computer skills provided by the Information & Communications Technologies (ICT) programme has supported this. Video-conferencing has been installed in some woredas, but due to limitations in power and transmission tends to work only intermittently.

### Gender issues, HIV/AIDS and the environment

The DLDP annual plans include proposals for increasing focus on gender issues, and recommend that women are included in all training activities. Woredas reported that specific training courses had been presented on gender awareness, and that workshops had been held on tackling harmful traditional practices (HTPs), including female genital mutilation and abduction. While improvements cannot be solely attributed to PSCAP, there has certainly been an improvement in the status of and attention paid to gender issues at woreda level – instances reported include:

- An increase in the number of women staff, and the application of affirmative action in recruitment and promotion

- Encouragement of women staff, particularly teachers, to improve their qualifications

- An increase in the number of girl children in school enrolments

- The emergence of women in role model positions (albeit relatively small numbers at this stage) such as judges, prosecutors and members of woreda and kebele councils.

A similar level of recognition exists in respect of HIV/AIDS. Awareness training courses have been applied universally across woredas, and have been reinforced by major health-driven campaigns, including mass ‘know-your-status’ operations involving voluntary counselling and testing (VCT).

The overall DLDP programme appears to pay no attention to environmental issues. However, in the Evaluation Team noted a relatively high level of awareness in the woredas visited. This is given expression through practical programmes on reforestation (a number of woredas have established their own tree nurseries and woodlots), raising community awareness on sustainable forest use, and sustainable water usage.

## Tax and Customs Reform Programme (TSRP)

### General observations

The TSRP falls under the BGRS Revenue Authority, which was separated from the BOFED in 2005. PSCAP funds were used to support the establishment of the new office through the purchase and installation of computers, printers and office furniture. The BGRS state budget comprises 82% federal grants and 18% own revenues, and Revenue Authority officials are well aware of the need to increase local collections to reduce dependency of fiscal transfers.

However, tax collection performance has fluctuated, and although currently on an upward trend, has not met its targets for the last three years. The biggest variation was in 2005/06 (EY 1998), where Birr 22.4 million was brought in against a target of Birr 30 million. However, this was a year of crop failure, and collection demands for farmers were relaxed.

Table 2.Tax collection performance

| Year | Collection Target (Birr m) | Actual Collected (Birr m) |
| --- | --- | --- |
| 2003/04 (EY 1996) | - | 24.6 |
| 2004/05 (EY 1997) | 30 | 27.0 |
| 2005/06 (EY 1998) | 30 | 22.4 |
| 2006/07 (EY 1999) | 32 | 26.9 |

Source: TSRP Success Story Document, undated

From this measure it appears that although much effort has been put into building a professional and efficient tax service, it is not yet performing to its potential. There are combinations of reasons that help explain this, including peasant associations not passing tax on to collectors, tax collectors not covering their areas assiduously, and traders closing their businesses to avoid tax, and then re-opening elsewhere. Turnover of trained staff is also a problem.

Representatives of organised business in Assosa confirmed that there had been a relative improvement in the quality of the service. For example, making tax payments, which could previously take up to three days, can now be done immediately. However, it was also felt that the Revenue Authority could be making more efforts to communicate changes to tax laws and administration, and raise business awareness. The local Chamber of Commerce offered to call meetings of its 136 members (from an estimated 800 enterprises in the town) to assist in this respect.

### Capacity Building

The TSRP has put considerable effort into training at regional and woreda levels over the past three years:

- 74 regional tax collectors and administrators, 215 kebele tax assessors and administrators trained on new tax laws and management

- Government officials trained on tax laws, procedures, roles and responsibilities

- Revenue Authority staff trained on automation and Taxpayers Identification Number system

- Consultation and review sessions held between regional and woreda tax officials on system progress

- Tax education sessions held with traders, strengthening the shift to voluntary tax payment rather than coercion

This covers one of the MMAs, which can be considered completely achieved.

### Revenue Potential Study

The TORs for this study and the tender has been advertised. Unfortunately, only one bidder has come forward, rather than the three bids needed to make an appointment. The Revenue Authority is now re-advertising this contract, but the delays to the project now amount to around 12 months.

### Gender issues, HIV/AIDS and the environment

There have been no specific activities on HIV/AIDS, gender issues and the environment, although the Evaluation Team were told that the Revenue Authority intends to build HIV/AIDS issues into its next annual plan. The majority of tax collectors at all levels are men (an estimated 90%).

## Civil Service Reform Programme (CSRP)

### General observations

The CSRP is the responsibility of the eponymous office located in the BCB. The Expenditure Management Control Programme (EMCP) although falling within the CSRP is increasingly being dealt with by the BOFED, and is treated separately below. There has been a consistent improvement in performance of the CSRP since the last Joint Supervision Mission (JSM) in April 2006 (EY 1999). The programme office has an effective set of working partnerships with other bureaux and agencies, which collaborate in the delivery of specific aspects of the programme. These include BOFED (expenditure management); Office of the Auditor-General (financial accountability); Civil Service Commission (HRM procedures); Regional Management Institute (training provider); and the Bureau of Justice (ethics and accountability).

### Minimum Mandatory Activities

Progress against the CSRP MMAs is as follows:

- Training and adoption of Results Oriented Performance Evaluation (ROPE) in all regional bureaux and woredas. Status: not started. Apparently, information on the revised ROPE system is still awaited from Federal level.

- Completion of client score cards launched in 75% of regional bureaux. Status: no progress.

- Initiation of Business Process Re-engineering (BPR) in 75% of regional bureaux. Status: partially complete. BPR exercises are now underway in six regional bureaux.

- Completion of top management training for heads of 75% of bureaux. Status: exceeded. All regional bureaux heads have received training.

### Strengthening the capacity of CSR Coordinating Structures

The regional CSRP office has been established, with counterpart structures and focal persons in place across all regional bureaux, zones and woredas. All these experts have received training on the programme.  The CSRP manual has been produced in Amharic and distributed widely. The CSRP office is in the process of securing consultancy services to carry out an external impact evaluation of the programme this year

### Improving governance of human resources management and control

The Civil Service HRM proclamation, policy and regulations have been implemented in all regional bureaux, zonal and woreda offices. Awareness training has been conducted with 148 administrators and personnel officers (132 men, 16 women). The Civil Service Commission (CSC) has developed and provided training on manuals on the new regulations, as well as grievance and disciplinary procedures. The CSC’s Inspection Department conducts on-site assessments to check whether these manuals are in use and personnel officers are implementing their duties in line with the new arrangements.

### Improving performance and public service delivery

Manuals on the Performance & Service Delivery Improvement Programme (PSIP) and BPR have been developed. Training has been provided on general management for 20 regional experts (16 men, four women), and on BPR for 209 department, finance and administration heads and higher-level experts. BPR is currently being implemented in six pilot bureaux, before being rolled out further. The CSC conducted a BPR exercise on the civil service disciplinary procedures and was able to reduce the average number of steps from 20 to six.

### Improving accountability and transparency

The Bureau of Justice (BOJ) has conducted training on ethics principles and regulations for 26 higher-level experts (23 men, 3 women). In addition, the Office of the Auditor-General (OAG) has received training on civil service for its staff, and also led the following training activities:

- Internal audit and control, for 116 regional, zonal and woreda accountants and internal audit staff (95 men, 21 women)

- Conduct of investigation, environmental, financial and performance audits, for 31 regional staff

- Principles of auditing, for 64 auditors

In addition procurement processes are underway to secure consultancy services to identify the extent and causes of corruption in the BGRS civil service.

### Strengthening top management systems

The CSRP has invested considerable effort in rolling out training activities to strengthen top management systems – modules include strategic planning and management, performance and change management, decision making. All regional bureaux heads have been exposed to these modules, while training has also been provided for woreda higher-level officials.

### Gender issues, HIV/AIDS and the environment

Considerable effort is made at all levels to ensure a gender balanced trainee selection, but gender disparities in employment and management positions clearly affects the levels of female participation.

The CSRP office reported that all three cross-cutting issues were included as elements in the overall training programme.

### Next Steps

The Evaluation Team noted comments from the CSRP and its partners that while much has been achieved, the transformation is still in progress. The Team welcomed the CSRP Office’s commitment to carry out Training Impact Assessments six months after courses, and would emphasise that this should be part of a coordinated effort on monitoring and evaluation. The CSRP programme has a range of partners and implementing agencies, and all should be involved in developing and coordinating the collection of programme impact data. This should be gender-disaggregated wherever feasible. Some form of coordinating committee should be considered as an institutional mechanism to guide monitoring and evaluation efforts, and act as a first repository of institutional knowledge and transfer of experiences.

## Expenditure Management & Control Programme (EMCP)

### General observations

The EMCP programme was previously led by the CSRP until its transfer to BOFED in 2006 (EY 1999 ). The logic of giving clear management responsibility has been borne out by an impressive series of results and activities. PSCAP finance has only been used in the current year – activities have previously drawn on finance from the USAID Decentralised Support Activity (DSA) programme. This programme ends this year, and programme funding will switch substantially to PSCAP.

The single pool (treasury) function has been installed and is operational at regional, zonal and woreda level. There have been generally improvements in transparency, accountability and effectiveness across the board. The BOFED team is active and committed to expanding and improving the financial service, and has received generous improvements in PSCAP allocations as a result of good performance.

The Evaluation Team noted discrepancies between the information presented in documents by the CSRP and received in interviews with the BOFED. For example, the CSRP report dated July 2007 ‘PSCAP Physical and Financial Performance Report for the Year 1999 EC’ states under progress against MMAs that all backlog accounts have been eliminated at regional and local levels. This does not agree with information provided by BOFED that in fact the EY 1999 accounts have not all been closed. The Evaluation Team assumes that this may be due to a lack of clarity over information on financial years (for example, the EY 1997 and 1998 accounts had been cleared). The Team recommends that data is presented with more precision and describes the situation as exists at the time of writing.

### Minimum mandatory activities

Progress against the EMCP MMAs is as follows:

- Elimination of backlog accounts at regional and local levels. Status: almost complete, and very likely to be totally up to date this year with the closure of the 2006/07 (EY 2000) accounts.

- Installation and training in medium term expenditure management procedures manual, BIS and BDA3 systems in all regional and woreda institutions. Status: complete at regional level, and underway for woredas. The BDA3 system is being updated to the Integrated Budget & Expenditure System (IBEX).

### Budget reform

The new BIS has been established and computerised, cost centre budgeting introduced and new budget classification developed. Training has been provided on budget reform for all regional, zonal and woreda budget and finance officers.  The financial and procurement directives have been legislated, and issued to sector bureaux.

### Accounts Reform

Double entry bookkeeping and single pool accounting has been introduced at regional, zonal and woreda level. Performance improvements have been noted with more accurate reporting, reduction in costs of idle funds and transfer charges, and increased transparency in budget preparation and allocations.

### Capacity for expenditure management and control

There has been considerable training in the new financial management and budget reform processes, with effective use made of operational and training manuals. Over 300 accountants across the region have been trained, but the region has had to adopt a continuous approach to training due to high levels of staff turnover. The BOFED has set up an outreach team of eight accountants and two IT specialists to assist woredas on-site in budget and annual accounts preparation.

20 computers supplied under PSCAP have been provided to woredas, and this number will need to be increased once IBEX is rolled out more widely. The automated payroll system (which receives support from CIDA) is the next planned capacity improvement targeted at woreda level. 22 payroll printers have already been purchased in anticipation.

### Financial information

BIS and IBEX have been installed at the regional level, but not yet at woreda level. The Budget Calendar has been instituted, and the Budget Book prepared annually.

### Audit functions

Internal audit teams have been placed in each bureau, and woreda level training of 115 auditors has been conducted.

## Information & Communication Technologies (ICT)

### General observations

The ICT programme has a staff complement of five staff, based in the BCB. Unfortunately, the programme coordinator was unavailable at the time of the Evaluation Team’s visit, and this section is drawn from a printed presentation and interview with a member of the IT technical team. The programme has made substantial progress in delivering training courses, but faces logistical and staff limitations in providing outreach and mobile maintenance and monitoring support to woredas. Training is provided in most general office software programmes, as well as more advanced training in website design and operation.

Despite the training effort, ICT focal persons at woreda level have generally not yet attained advanced skills and there is relatively little maintenance and trouble shooting capacity outside the regional bureaux. (Even this is somewhat lacking; to illustrate, a CD of documents provided by the BCB for the Evaluation Team proved to be virus-infected and unusable)

Visits to woredas confirmed the valuable support provided by the ICT programme team. In future, ICT applications (for example, provided through the EMCP) and demands for training will increase, particularly as more staff becomes e-ready. There are hardly any private ICT companies in Assosa, which throws the burden of training, maintenance and installation onto the ICT team. BOFED concerns in this regard have prompted a proposal to establish its own technical team to support ICT applications in finance and expenditure administration at all levels. This proposal is to be considered by the Regional Council

### Minimum mandatory activities

Progress against the ICT MMAs is as follows:

- Establishment and strengthening of Regional Data Centres. Status: complete.

- Completion of technical training for Regional Data Centre staff. Status: complete.

- Initiate basic computer training for designated ICT focal persons from all woredas. Status: complete.

### Human resource development

The ICT section conducted a comprehensive training needs assessment, and has developed a training plan and manual. It has significantly increased its services and the amount of training it has provided over recent years:

Table 3. Computer training provision

| Training course | Number of participants |  |
| --- | --- | --- |
|  | 2005/06 (EY 1998) | 2006/07 (EY 1999) |
| Computer awareness | 220 | 500 |
| Basic Computer training | 40 | 375 |
| Advanced computer training | - | 13 |

Source: Presentation: ICT Success Stories with emphasis on PSCAP, October 2007

Training sessions are held for two hours every, and while this consistency is commendable, consideration will need to be given to establishing and expanding the regional ICT training function, as ICT demand increases.

### Public service delivery and good governance

Little information was available on this aspect. Reportedly, a study has been produced on regional ICT planning, and information is apparently available on a gender-disaggregated basis.  Woreda-net and school-net teleconferencing facilities have been rolled out in some woredas, but operations are patchy and intermittent.

### Applications for sector development

No information was supplied on this component of the programme.

### Community based information systems and services

Little information was supplied on this aspect. Reportedly, a study has been conducted on the establishment of a local community radio station.

### Gender issues, HIV/AIDS and the environment

Little information was supplied on this aspect, other than the availability of gender-disaggregated information as reported above.

# Programme management and support

## Institutional arrangements for PSCAP in region

The BGRS BCB is the lead bureau on PSCAP in the region, and is structured into five separate units:

- Planning & Programming Service (PPS) – which acts as the central administration office for BCB coordination, provides assistance to sub-programmes on planning, and support to the Regional Technical Team (RTT)

- Procurement Desk – responsible for PSCAP procurement, and accountable directly to the Bureau Head

- Monitoring & Evaluation – the third of the core coordination functions, collating information from and assessing progress of sub-programmes. This unit has dedicated technical assistance through the presence of a British Voluntary Service Overseas (VSO) placement.

- District Level Decentralisation Programme (DLDP) – a sub-programme of PSCAP, but housed within the BCB, its coordinator accounts directly to the Bureau Head.

- Information & Communication Technologies (ICT) – again, a PSCAP sub-programme, located within BCB and accountable to the Bureau Head.

Further support and Sub-Programme activities are located in various bureaux across the regional administration:

- CSRP is housed in a separate Sub-Programme Office

- TSRP is the responsibility of the Benishangul Gumuz Revenue Authority

- JSRP falls under the Bureau of Justice

- UMCBP is the responsibility the Bureau of Works and Urban Development

- Expenditure Management and Control falls under the BOFED, which also provides financial management support to the PSCAP programme at regional level.

In summary, responsible agencies for key programmes and activities are:

Table 4.Overview of responsible agencies for key programmes and activities

| Programme / Activity | Responsible agency |
| --- | --- |
| DLDP | BCB |
| ICT | BCB |
| JSRP | Justice Bureau |
| CSRP | CSRP Sub-Programme Office |
| EMCP | BOFED |
| TSRP | Benishangul-Gumuz Revenue Authority |
| UMCP | Works and Urban Development |
| Planning & Programme Service | BCB |
| BOFED (programme support) | BOFED |

Steering Committee: The BGRS established a PSCAP Steering Committee (SC) in mid-2006 as a high-level guidance and support structure to ensure effective implementation of PSCAP. It meets quarterly, and is chaired by the Regional President; other members include the Vice-President, Heads of Bureaux, the President’s Advisor on Capacity Building and relevant experts. The BCB is the SC Secretariat.

The SC has a range of functions, the most important of which are to:

- Monitor and assess PSCAP progress across all Bureaux

- Recommend actions to ensure timely and effective implementation of PSCAP, including assignment of tasks and deadlines to Bureaux

- Reviewing PSCAP documents including annual Action Plans and Quarterly Output Reports

- Providing support and advice to the RTT

The SC is a regional innovation, and has proved highly effective in raising awareness of the programme, securing high-level support across the BGRS government and building coordination, cooperation and unblocking obstacles to PSCAP delivery.

Regional Technical Team: The RTT is the central decision-making body for PSCAP in the BGRS, and is responsible for all major operational decisions, management and coordination. It is meeting regularly every month, and is chaired by the Head of the BCB. Its membership includes coordinators of the six PSCAP sub-programmes, Head of BOFED, Heads of Bureaux responsible for non-BCB sub-programmes, the Women’s Affairs Bureau and the Regional Management Institute.

Previously, the BGRS had been criticised in the Joint Supervision Mission (JSM) Aide-Memoire April 2006 for not having a functional RTT, which led to poor coordination and delivery among PSCAP sub-programmes. The Evaluation Team was pleased to note the establishment and successful functioning of the RTT, and much of the performance improvement in recent months is due to this institution.

## Coordination with MCB, federal sub-programmes, and woredas

Coordination with the MCB was reportedly effective, with the national body giving assistance to ensure timely and coherent plans. MCB has also provided advice on establishing and operating PSCAP procurement systems.

Sub-programme coordinators reported that coordination across PSCAP at regional level had greatly improved over the recent period, with the RTT playing an important role in this regard. All the region’s sub-programmes were provided to the BCB ahead of time, enabling prompt submission to the MCB.  In addition, certain sub-programmes have taken active steps to ensure effective coordination with their constituent implementing agencies.

Coordination with and assistance from Federal level PSCAP institutions varied. Some sub-programmes (notably JSRP and TSRP, as well as BOFED) reported good flows of information, guidance when requested and support on technical matters. DLDP reported that a form between federal and regional level structures had been established. However, other PSCAP areas reported a lack of support and response.

The woredas interviewed by the Evaluation Team reported that there was a good working relationship with the BCB and PSCAP programme coordinators. BCB officials had consulted with woreda officials to determine priority training areas before formulating the annual programme of PSCAP activities.

## Compliance with eligibility criteria by region

The BGRS has met the eligibility criteria. A Programme Performance Agreement (PPA) is negotiated annually, setting out a clear schedule of activities, outputs and deliverables, and budget against each sub-programme.

## Planning and resource allocation

The BCB provides central coordination and support for finalisation of annual action plans. These are then submitted to the MCB PPD, along with a proposed budget. Generally, plans are received in good time from the regional sub-programmes, and clearly the RTT plays an important role in driving this process.

However, the final plans approved and received from MCB are not matched by the allocated budgets from MOFED.   Comments received were that this process was ‘random’ and ‘unpredictable’. The RTT and BCB then have to embark on a process of reallocating budgets and reorganising action plans in conjunction with the sub-programmes. As a result, planning and budgeting is taking place twice – before and after the budget allocation, doubling effort and slowing down implementation.

## Procurement

The BCB has clearly paid much attention to improving procurement as part of the PSCAP process. It is managing those aspects of procurement processes within its remit professionally and effectively. For example, it secured 100% of its targets in its 2005/06 (EY 1999) procurement plan. The Evaluation Team rarely received negative comments about BCB’s activities on procurement. However, this should not be taken to imply general satisfaction – in fact complaints about the length of time to obtain procurement approvals was a consistent theme in the Team’s interviews with sub-programmes, implementation agencies and other bureaux. This criticism was  primarily directed at the MCB and World Bank.

These concerns relate to:

- Delays in approval of action and procurement plans from the federal PPD, and in obtaining ‘no objection’ letters from the World Bank;

- Delays in securing ‘no objection’ letters on TORs, tenders and appointments from the World Bank

## Expenditure and financial management

Expenditure and financial management for PSCAP is ably provided by BOFED for the BCB. There is a PSCAP dedicated team of two accountants in BOFED that pulls together consolidated statements and financial reports each month. Payments are approved by the BCB, and then made by BOFED.

## Monitoring and evaluation

The Evaluation Team noted that all programmes kept records of training events, participants, and amount of goods and services procured. However, this is generally not consolidated, and the over-riding focus is on quantitative assessment. There were isolated examples of proposed impact assessments at individual programme level, but key areas of information are still lacking (for example, citizen score cards). The Team feels that more resources need to be diverted to improving the quality of information supplied to management and the SC, particularly on assessment of outcomes.

## Information, education and communication (IEC)

The individual programmes and implementing agencies are undoubtedly making serious efforts to publicise, inform and educate stakeholders on PSCAP-related activities. Examples include:

- Public posting of woreda budgets (EMCP, financial accountability and transparency)

- Tax payer education sessions (TSRP, building awareness of tax reform, rights and responsibilities)

- Public posting of bureaux and woreda vision, mission and values (CSRP, accountability and transparency)

- A study into the establishment of a community radio station (ICT, community-based information services)

However, the Evaluation Team was not made aware of any consolidated IEC strategy for the region. This gap is unfortunate, and attention should be paid to developing such a strategy and programme, taking into account the current range of activities and identifying target groups and issues where programme messages should be reinforced.

## Sequencing and integration of reform initiatives

Overall the regional PSCAP plan is considered to be sequential and logical, and awareness across Bureaux is high. The Evaluation Team observed that in many programmes, activities have been introduced on a logical and sequential basis. For example, management training in strategic planning took place, followed introduction of the new planning process.  The strategic plans were then reviewed yearly and annual action plans produced, linked to budgets and procurement plans. The action plans form the framework for sector and departmental activities, in turn linked to individual responsibilities. This forms the foundation for the introduction of ROPE.

However, the Evaluation Team also notes that the transformation programme entails the introduction of a wide range of changes across many fronts. Some undoubtedly have taken root, and led to fundamental shifts in government processes, for example in expenditure management. The strength of the foundation provided through PSCAP is weakened by staff turnover and loss of institutional knowledge, as well as increased pressure on staff and managers, who have to take on change management and introduction of new processes as extra assignments. Without clear direction and coordination from the centre the transformation programme risks losing focus. On the other hand, the pressure to implement top-down directives quickly works against the time needed to consolidate and integrate reforms thoroughly into service delivery. The need to secure an effective balance requires adroit leadership and good flows of information to aid decision-making, as well as the right blend of leadership and delegation.

# Assessment of cross-cutting issues – gender, HIV/AIDS, and environment

There is undoubtedly great awareness on gender issues within the various PSCAP programmes. Most mentioned the provision of gender awareness training, and were able to provide some (but not always comprehensive) statistics on women participating in technical training courses at all government levels. Representation of women in managerial and technical positions is visibly an important issue - apart from administrative and secretarial staff, the single woman in a management position that the Evaluation Team met in all its interviews in the region was the head of the Women’s Affairs Bureau (WAB). The BGRS government has taken steps to address this question, and instituted affirmative action policies, but these will take time to ensure adequate representation of women in senior positions.

The WAB is a member of the RTT, and also comments on all PSCAP programme plans. It has relatively capacity for engagement beyond this, and relies on programme sources foe gender disaggregated data. Given this limitation, the submission of plans to the WAB at the earliest possible stage could help in generating more considered and effective inputs. Improved monitoring and evaluation, and particularly external research focusing on the transformation programme’s impact on women, could prove valuable in assessing and improving PSCAP outcomes.

HIV/AIDS issues showed similar features – high levels of awareness, and varying levels of prominence in programme activities. These were mostly confined to awareness training and discussion sessions among course participants, but are nonetheless valuable in reinforcing the government’s messages in tackling the pandemic. The PIP specifies inclusion of HIV/AIDS issues as part of the CSRP IEC strategy, and also refers to including these issues in training materials and sessions. In this respect, the BGRS is complying with this requirement.

Environmental issues featured the least in PSCAP programmes, and this raises the question of the validity of its inclusion without specific directions as to implementation. This appears to be a structural problem with PSCAP; the PIP makes no reference to mainstreaming environmental issues (and only a passing identification of the Environmental Protection Agency as an eligible beneficiary institution). The PSCAP Final Five Year Action Plan Vol 1 contains more detail on how cross-cutting issues could be mainstreamed, including references to environmental issues.

However, there are inconsistencies in how proposals are then to be translated into action. To illustrate, the ICT programme section contains a single reference to establishing an environmental information system. While this is obviously useful and has clear links with rural development as well as ICT usage, there is no further detail or justification on how this should be implemented, nor does it feature in the output indicators in the relevant sections in the PIP or Five Year Action Plan Vol 2 Matrix.

# Key lessons and limitations

The BGRS ‘turn-round’ since the JSM in April 2006 (1999 EC) can be attributed to:

- Improved institutional arrangements for managing and directing the programme, through the establishment of a functional RTT and the introduction of the SC as a critical link between PSCAP and the Regional Council. The RTT was consistently praised as an effective, democratic body and has done much to improve inter-programme coordination and information flows.

- Increased levels of staffing resources dedicated to PSCAP, although these are still inadequate for projected levels of increased activity

- Increasing familiarity with PSCAP planning, budget and procurement requirements, which has led to some improvements in efficiencies in the planning cycle

- Growing momentum of training and capacity building processes, which has led to real changes in service delivery. This in turn has increased confidence in the programme, and growing demands for more generic and specialised training.

The Evaluation Team was pleased to observe an increasing level of ownership of the programme among some stakeholders. Rather than being passive recipients, key managers are developing positions on how the programme can be improved. Ideas include delegation of PSCAP funds to improve implementation times.

Unfortunately, PSCAP also faces certain obstacles in BGRS that are limiting greater progress. These include:

  - Persistent shortages of skilled and experienced staff, and problems over staff retention, without improved remuneration, terms and conditions.

  - Delays in the planning process, and the difficulties of reconciling plans with final budget allocations, which necessarily lead to a second round of planning. This has a knock-on effect by increasing slippage in implementation, and under-spending in finance.

  - A lack of assistance and guidance from federal institutions on certain sub-programmes.

  - Relatively ‘thin’ institutional arrangements – while the RTT and SC are important drivers of the overall programme, it could also benefit from the establishment of sector or issue-specific working groups to provide advice, guidance and coordinated inputs to improve the quality of the programme.

  - Delays in procurement processes, notably relating to International Competitive Bidding (ICB) and receipt of ‘no objection’ letters from the World Bank.

  - Limitations on the types of the goods available to be purchased, as a result of the ‘negative list’. Clearly there should be careful control on purchase of capital goods, such as vehicles. However, a shortage of vehicles with off-road capability is definitely limiting communication, on-site inspection and monitoring of programme performance in the region’s more distant woredas.

  - Limitations in availability of consolidated programme data that measures outcomes as well as outputs and activities.

  - Shortage of external technical capacity, consultancy expertise and experienced training service providers.

This last issue is worth some consideration. PSCAP has a strong thread of state-generated expertise, self-evaluation and direct relationships with the beneficiary communities. This is the heart of the programme, and despite the operational limitations described above, is a sound foundation. It needs to be supplemented with external viewpoints - more independent evaluations (particularly on sector and issue specific issues, such as the impact of changes in service delivery on women) are important. The region should also consider developing stronger relationships with civil society structures (for example, the Chamber of Commerce, NGOs with operations in the region) to harness networks, information and expertise and help inform programme initiatives.

Acronyms and Abbreviations

3Ps		Police, Prison and Prosecution Services

BCB		Bureau of Capacity Building

BGRS		Benishangul Gumuz Regional State government

BOFED	Bureau of Finance and Economic Development

BOJ		Bureau of Justice

BPR		Business Process Re-engineering

BWUD		Bureau of Works & Urban Development

CIDA		Canadian International Development Agency

CSRP		Civil Service Reform Programme

DSA		Decentralised Support Activity

EC		Ethiopian Calendar

HRM		Human Resource Management

HTPs		Harmful Traditional Practices

IBEX		Integrated Budget & Expenditure System

ICB		International Competitive Bidding

ICT		Information & Communications Technologies

IEC		Information, Education and Communication

JSRP		Justice System Reform Programme

JSM		Joint Supervision Mission

MCB		Ministry of Capacity Building

MMA		Minimum Mandatory Activities

OAG		Office of the Auditor-General

PIP		Programme Implementation Plan

PSCAP		Public Sector Capacity Building Programme

PPA		Programme Performance Agreement

PPS		Planning & Programming Service (located within BCB)

PSIP 		Performance & Service Delivery Improvement Programme

RMI		Regional Management Institute

ROPE 		Results Oriented Performance Evaluation

RTT		Regional Technical Team

SC		Steering Committee

TORs		Terms of Reference

TSRP		Tax and Custom System Reform Programme

UMCBP	Urban Management Capacity Building Programme

UNDP		United Nations Development Programme

VCT		Voluntary Counselling and Testing

VSO		Voluntary Service Overseas