Annex 1: Civil Service Reform Sub-Programme Report

# Background

Steve Topham and Ato Eskinder Tesfaye assessed the operation and impacts of the CSRP in a series of meetings that took place between 10 October and 5 November 2007. Meetings were held with the representatives of the CSRP at federal level, and in Benishangul-Gumuz and Amahra regions. Visits were made to three woredas in each region to assess progress of the programme, and inputs were received from other members of the evaluation team who visited other regions and woredas, and met with the CSRP coordinators. Meetings were also held with CSRP implementing agencies, including the national and regional Civil Service Commissions, Ethiopian Civil Service College, Ethiopian Management Institute, and Regional Management Institutes.  The Team examined various programme documents and progress reports.

The Team would like to thank all the interviewees for their time and interest in sharing their information and insights.

# Evaluation of Main components

## Background

The CSRP started long before PSCAP, beginning in 1994 with a focus on five major streams of work:

- Top Management Systems

- Human resource management

- Service Delivery

- Expenditure Management & Control

- Ethics.

These areas still form the core components of PSCAP today. Through the late 1990s, a range of projects and institutions were set up to deliver on this programme, although it is fair to say that expectations exceeded the realities of reform.

PSCAP is intended to accelerate the rate of reform, and increase the scale of transformation in the civil service. The Civil Service Reform Sub-Programme (CSRP) is intended to build a fair, responsible, efficient, effective and transparent civil service and is considered a key task for all institutions at all administrative levels. The CSRP comprises the following components:

- Strengthening CSRP Coordinating Structures

- Improving Governance of Human Resource Management and Control

- Improving Performance and Service Delivery in entire Civil Service

- Improving Transparency and Accountability in Federal Civil Service

- Strengthening Top Management System of Federal Civil Service

- Building Policy and Institutional Governance Capacity in the Four Less Developed Regions (Afar, Benishangul-Gumuz, Gambella and Somali)

A final component, Improving Governance of Financial Resource Management and Control in Institutions, aims to strengthen civil service institutions for better expenditure management and control. This component has gained prominence over the past two years, and now has the status of a separate programme, the Expenditure Management Control Programme (EMCP), and falls under the leadership of MOFED.

The CSRP is the PSCAP flagship, and is central to its success. It is complex, and has a high degree of overlap with other programmes, which requires careful planning and integration. The CSRP is the lead agency on the introduction of Business Process Reengineering (BPR) and Results-Oriented Performance Evaluation (ROPE), and has also scored important successes with the introduction of service delivery frameworks, promotion of strategic planning, improved systems for Human Resource Management (HRM) and disseminating training on anti-corruption.

## Strengthening CSRP Coordinating Structures

The federal CSRP has to deal with coordination nationally, as well as driving activities through regional and sub-regional structures. The approach of developing initiatives and prototypes at federal level, to be then adopted and implemented in line with regional and sub-regional requirements, is generally sound. However, the Evaluation Team is concerned that although the existing staff are performing their duties very well, the office needs more skilled staff to meet the current and future workload.

The CSRP has a fairly effective infrastructure at regional and sub-regional levels. In its regional visits, the Evaluation Team observed that coordination arrangements are in place, with links across counterpart structures in the regional government and implementation agencies, as well as fairly regular communications with the capacity building desks at zonal, city and woreda level.

Implementation is underway, but needs to go faster. All aspects of the programme have been touched, but accomplishment is not deep enough. Capacity shortages lay behind this – much management and staff time was taken up with closing out the Capacity Building for Decentralised Service Delivery (CBDSD) programme, as well as dealing with the introduction of BPR. Consequently, PSCAP has only received full-time attention since 2006 (EY 1999), and for some implementing agencies full engagement came later – the federal CSC, for example, only really became fully involved from July 2007.

Reform is more than the introduction of new systems, although these are a central aspect of the CSRP. The programme seeks to bring about an attitudinal change in the civil service, inculcating values of customer service orientation, increased productivity, and an attitude of serving the nation. This requires leadership by example, good quality and efficient management, and commitment to build and sustain excellent performance. Such changes cannot be achieved by diktat from above. They require a concerted, integrated effort at all levels of government, with the CSRP providing guidance as well as direction. To this end, it is absolutely vital that the CSRP at federal level has a strong team of well-qualified staff, able to take initiative, and sufficiently resourced to handle all aspects of the programme.

## Improving Governance of Human Resource Management and Control

There has been some progress in this component. The Civil Service HRM proclamation has been enacted, with the policy and regulations adopted at regional levels and implemented in bureaus, zonal and woreda offices. Awareness training on the new HRM systems has been conducted widely, with the use of standard manuals and training materials.  There has been widespread use of training-of-trainers, usually drawn from HR staff at zonal, city and woreda level. There has been cooperation and coordination of varying degrees between the CSRP and DLDP at regional and sub-regional level, and this has led to an impressive range of activities – primarily training – at local government level. There is also a great deal of effort directed towards the strengthening of HR planning, and improving the system of job evaluation and grading.

Current projects underway in the HRM component are:

- Job evaluation and grading

- Performance appraisal system

- Recruitment, selection, transfer and promotion procedures

- Human resource planning

- Human resource development

- Human resource management information system

- Remuneration and conditions of service

- Civil service law, grievance system and procedures

- Records management.

Activity monitoring and to a lesser extent impact assessment has been carried out the CSC at national and regional levels. Impacts have not been evaluated consistently, but it was reported that there is a general reduction in the number of grievances, disciplinary actions and complaints in recruitment and promotion processes.

The Amhara CSC has also commissioned research on developing a motivation strategy for civil servants. The study involves research on the prevailing culture and work ethic of the civil service, and looks to develop ways of motivating staff to perform better. This study is underway currently, and should be monitored. Its findings could have wider application and relevance for the future development of the CSRP.

## Improving Performance and Service Delivery in entire Civil Service

There has been a significant effort to improve performance and service delivery capacity, with widespread training using the manuals on the Performance & Service Delivery Improvement Programme (PSIP). Strategic planning has become a feature of service departments at all levels, In addition, there have been many improvements to the interface between the civil service and the public – complaints desks and procedures have been established, information desks, office sign boards and personnel identification tags have been introduced.

Current projects underway include:

- Development of a service delivery policy

- Guidelines for handling customer complaints

- Development of service delivery standards

- Civil service award system.

Results Oriented Performance Evaluation Systems were introduced in the early 2000s, but was found to be too subjective, and was reworked into a more management based system – Performance-Based Management (PBM). However, before this could be consolidated and mainstreamed into line departments, it was overtaken by Business Process Reengineering (BPR). In 2005 (EY 1998) BPR exercises were piloted in six federal institutions, and has since been introduced on a wider scale across institutions at all levels. However, BPR did not bring rapid improvements in institutional performance, and a further round of BPR-related training activities took place.

More recently, PBM has been reformulated to incorporate the introduction of the Balanced Score System (BSC), which is due to be introduced on a pilot basis in 2007 (EY 2000).

The Evaluation Team noted a number of instances where BPR exercises have been translated into changes in procedures, leading to improvements in efficiency. However, it is concerned that there have been various system models introduced over the past five years that have not had the chance to be thoroughly tested and consolidated before being changed. This inconsistency and lack of continuity has affected confidence in the reform process at senior management levels. It has dented enthusiasm and undermined the value of long-term planning.

## Improving Transparency and Accountability in Federal Civil Service

The CSRP has coordinated this component with implementing agencies at federal, regional and local level, including the Offices of the Auditor-General, and Ethics & Anti-Corruption Commissions. While it is difficult to find a single summary of all activities, it is clear to the Evaluation Team that a wide range of actions have taken placed, with widespread awareness training programmes on ethics and accountability, audit processes and principles of transparent government.

Current projects in hand in this component include:

- Developing a Code of Conduct

- Capacity building of police, courts and prosecutors (in conjunction with the JSRP and DLDP)

- Ethics education

- Corruption survey

- Freedom Of Information Act

- Registration of Assets

- Protection of whistle blowers and witnesses.

## Strengthening Top Management System of Federal Civil Service

This element of the CSRP aims to improve the performance and productivity of top and middle managers by increasing their skills, improving the operational environment, and heightened awareness of gender issues leading to more gender equality within the civil service.

There has been considerable investment in rolling out training activities to strengthen top management systems – modules include strategic planning and management, performance and change management, decision-making and leadership. The Evaluation Team noted that training for top managers had taken place in all regions, usually involving head sand senior managers of all regional bureaus, as well as zonal, city and woreda higher-level officials.

Current projects underway include:

- Capacity building in strategic planning and management

- Top management development

- Policy development and management

- Performance management and evaluation

- Review and reorganisation of executive departments.

## Building Policy and Institutional Governance Capacity in the Four Less Developed Regions (Afar, Beneshangul-Gumuz, Gambella and Somali)

The CSRP has given support to strengthening policy and governance capacity by ensuring that the component packages of the programme are all delivered. While challenges in these regions are greater due to a shortage of skilled and experienced staff, the Evaluation Team noted activities are taking place across all elements, and that there are coordination arrangements in place with cities and woredas. Communication between federal and regional level is, unfortunately, still rather weak, and needs to improve, becoming more regular and responsive.

# Programme Management and Support

## Institutional Arrangements

The CSRP, which is led from the MCB, has relationships with five implementing agencies at federal level, shown in figure 1 below.

Figure 1. CSRP and Implementing Agencies.

CSRP

Federal Ethics Commission

Ethiopian Management Institute

Ethiopian Civil Service College

Office of Auditor-General

Civil Service Commission

These arrangements are in general replicated at regional level, with the Regional Management Institutes (RMIs) acting primarily as training providers. The RMIs are, at this stage, training providers of standard courses. They have relatively little research or management consultancy capacity. The Ethiopian Civil Service College (ECSC) provides professional training for regional and sub-regional government officials on courses at its centre in Addis Ababa.

The Ethiopian Management Institute (EMI) and ECSC are essential to the prospects of civil service transformation. They are key institutions in developing and deepening the capacity of civil servants, and should be at the forefront of professionalism in the civil service. Both organisations have mandates to carry out training, research and consultancy, but are having to strengthen their own capacity to deliver on all three elements.

The EMI provides a range of services to the CSRP, including training and coaching in human resource development and management, performance-based management and computer training. It has headquarters in Addis Ababa and a training facility in Debre Zeit. The EMI has a core staff of trainers who undertake training needs analysis, training programme design and courses, and is currently seeking to strengthen its resources on consultancy and applied research. The EMI has a mandate to develop the capacity of RMIs, which should be encouraged to continue. The EMI needs to work with the RMIs to improve benchmarking and cross-transfer of experiences, networking and development of common frameworks and approaches.

The ECSC provides training on a range of subjects linked to the civil service reform programme, including transformational management, performance management systems, human resource development, expenditure management and control, ethics and accountability. Like the EMI, the ECSC strives to be a centre of excellence and resource for the government’s transformation programme. Similarly, it is upgrading its own staff and knowledge resources to meet the increasingly complex and sophisticated demands that the CSRP is placing upon it. It has recently set up a working relationship with the UK Civil Service College, and established a fast-track training programme on the British model to train, retain and develop young and talented professional staff within the service.

The ECSC has supplied some 30 consultant ‘change agents’ to nine federal ministries and agencies to assist senior management in planning and reform programmes.

Continued close collaboration between the CSRP, ECSC, EMI and RMIs is vital. There needs to be common understanding and standards of capacity building on performance based systems, including the BSC. Without this, reform will be hampered and line managers confused by different interpretations of these new techniques and systems.

## Coordination with MCB, other sub-programmes and regions

Coordination between the CSRP and other programmes and departments is improving, and assisted by the functioning of the Federal and Regional Task Teams. However, it is under-resourced at federal programme level, where the staff post responsible for regional coordination remains unfilled.

## Planning and resource allocation

The CSRP produces an annual plan of activities, and attempts to coordinate this with needs and activities in the regions. The planning process is seen as generally sound, but hampered by delays in approvals once submitted.

## Sequencing and integration of reform initiatives

This is one of the key issues in the CSRP. The experience over the past seven years with the introduction of performance related systems and BPR points to the need for a coherent and consistent plan to avoid confusion and conflicting priorities during implementation. This aspect was identified previously in the Joint Supervision Mission reports of 2006 and 2007.

The CSRP has recently produced a discussion document – Ethiopian Civil Service Reform: Suggestions on Revised Civil Service Reform Programme Components, Projects, Sequence and Expected Outcomes. This is a useful start to the process for developing a plan, but is no substitute for developing a coherent strategic plan, and should not be used as such. The discussion document sets out a series of project outputs proposed for the years 2007-2010. The point of departure for these targets is not given and some seem over-ambitious; for example, implementing ISO 9000 management standards in selected institutions in 2009 is more likely a longer-term enterprise.

The Evaluation Team can only reinforce this point – there is a pressing need for a well-designed and coherent plan, setting out logically integrated and sequenced activities. This plan needs to be developed as a matter of urgency, and on the basis of wide consultation and participation to secure the necessary buy-in. The plan should also set out clearly the human resource requirements necessary to drive and support it at federal and regional level, The MCB should then ensure that the necessary resources are put in place.

## Procurement

The CSRP at federal and regional levels reported difficulties with the procurement process. It is experienced as complex and lengthy and causes debilitating delays for programme implementation and securing technical expertise.

## Monitoring and evaluation

Along with the lack of a coherent strategic plan and ‘road map’ for the CSRP, the weakness in monitoring and evaluation the impact of the programme should be a cause of great concern. The CSRP is critical to the process of reform and the lack of systematised, regular information to assess progress and guide decision-making is indefensible. There is no regular consolidated reporting, and clearly not enough skilled staff resources have been applied to deal with this problem. In the opinion of the Evaluation Team this problem must be addressed as a matter of urgency. Without accurate information it is impossible for politicians and senior managers to monitor and adjust the programme, build on its successes and direct resources to deal with its weaknesses.

## Information, education and communication

In line with most other components in the PSCAP, the CSRP does not appear to produced a practical strategy or programme for IEC. Efforts to recruit technical assistance for this process have so far not been successful.

## Technical support

The Evaluation Team noted that the process of securing international consultants to advise on key aspects of the CSRP had taken a long time. Consultants were sought for BPR, performance management systems, PSIP, ROPE, top management systems and IEC. The specialists to validate and improve the Top Management Development programme have been shortlisted and proposals being finalised. Unfortunately, no consultants have responded to requests to support the other areas.  The Team acknowledges the difficulties with this process, but can only urge continued effort to recruit experienced consultants. Discussions should be held with local bi- and multi-lateral donor agencies to explore alternative possibilities for fast-tracking these appointments.

# Assessment of cross-cutting issues

HIV/AIDS and gender awareness feature in CSRP training programmes at all levels. There is a generally consistent effort to ensure a gender balanced trainee selection, but disparate numbers of women in senior and professional positions has a negative impact on female participation. It is regrettable that the MCB’s recent discussion document on revising the CSRP makes no reference to gender mainstreaming in any of its proposals, apart from ‘proving greater opportunity for disadvantaged groups’ (MCB, 2007). This should be revised, and explicitly built into appropriate projects, such as the fast-track system for civil servants.

There are hardly any activities in relation to environmental issues.

# Overall assessment

The CSRP is the most important programme in PSCAP, affecting all the sectors within the programme. It is the latest manifestation in the reform programme that the government has been undertaking since 1994, and impacts at all levels of government. The CSRP has generated a very wide range of activities, and been responsible for the widespread introduction of new approaches to service provision and human resources in the civil service, most notably around linking management and delivery to performance. Unfortunately, these innovations – including ROPE, PBM, BPR and the current move towards the BSC approach – were introduced in rapid succession, generally less than two years apart. In addition, each new approach was introduced as a result of dissatisfaction with the previous method’s failure to deliver rapid improvements in institutional performance.

While BPR has demonstrated promise in increasing efficiency in certain procedures, a wide range of exercises is still underway. The CSRP and civil service management will have a deeper understanding of how and where BPR can be applied successfully only once these exercises have been evaluated. Similarly, the work in introducing BSC is still at an early stage, and its actual impact is yet to be assessed.

These rapid changes are not with effects on management and staff. On the one hand, the search for, and application of, best practice to improve service delivery is commendable, and shows that there is flexibility and a strong commitment to innovation within the CSRP. This is a programme has a leadership that is unafraid of promoting and driving change. On the other, too many changes in too short a time lead to confusion among management and staff, wearing away confidence and energy, and leading to cynicism about lasting change.

The CSRP is also hampered by a shortage of skilled staff and high workload pressure. Much time at federal level has been occupied by the close-out of one its predecessor programmes, Capacity Building for Decentralised Service Delivery (CBDSD). This has also meant that little attention has been paid to systematic collection and interpretation of programme performance data. Ironically, for a programme that promotes strategic planning, the CSRP still lacks its own plan and ‘road-map’ for the introduction of training and new initiatives in a logical and integrated sequence. At present, the MCB’s discussion paper on civil service reform appears to be serving as an interim plan (MCB, 2007), but is inadequate for this purpose.  In addition, there are shortages of capacity in CSRP implementing agencies, notably the Ethiopian Civil Service College (ECSC) and Ethiopian Management Institute (EMI), although these agencies are taking steps to strengthen their resources in key areas.

# Lessons learnt and recommendations

The key lessons from the performance of the CSRP so far highlight the difficulties of conducting a complex and far-reaching programme without strong capacity and leadership at federal level, and the introduction of new models of performance-related systems in too short a time, and without sufficient consolidation.

The Evaluation Team makes the following recommendations:

The MCB should determine a strategic plan for the CSRP as a matter of urgency. This should map out a logical sequence of interventions, against a careful assessment of resources available and extra capacity required. The MCB discussion document is a good starting point, but is also rapidly becoming dated. It also lacks detail and the timeframe for project outputs and timeframe for delivery is too truncated.  The finalisation and approval of the plan should be preceded by a thorough assessment, based on up-to-date evidence, of progress of all current performance and training related initiatives.

Redouble efforts to secure consultants for the main elements of the programme, and hold discussions with local bi- and multi-lateral donor agencies to explore alternative possibilities for fast-tracking these appointments.

The CSRP Monitoring and Evaluation system must be improved. Where necessary, increase the number of skilled staff assigned at federal to collect, analyse and report on programme activities, progress against targets and (this is increasingly important) impact. These staff must also take an outreach role, working in close collaboration with their regional counterparts to ensure consistent interpretation and systematic collection of information.

Increase numbers of skilled staff in the CSRP coordinating offices at federal and where necessary at regional levels

# References

Ministry of Capacity Building, May 2007. Ethiopian Civil Service Reform: Suggestions on Revised Civil Service Reform Programme Components, Projects, Sequence and Expected Outcomes.