Annex 14: Harari report

# Background

Harari is the smallest region in Ethiopia.  It covers an area not more than 40 square kilometres and is almost completely surrounded by Oromia.  It recently celebrated 1000 years of existence. It boasts one of the worlds oldest gated settlement, Jugol which is now a world heritage site.  Jugol is branded as a “Living Museum”.  The region has a population of 200 000.  The region has a parliament of 30 members and a Cabinet of 9.  The new constitution recognises Harari as a city and has afforded the President of the region the status as Mayor of Harari.  9 Bureaus under cabinet members support the Cabinet, while a City Manager is appointed to carry out the Municipal Functions.  The region is divided into 7 large Kebeles and 36 sub Kebeles, 17 of which are rural and 19 urban.  A number of Authorities such as the Water and Sewer and housing agency complete the institutional government arrangements.

The team made up of Pascal Moloi and Girma Shegute evaluated the region on 25 and 26 October 2007.

The itinerary in the region included:

- A briefing session led by the Capacity Building Bureau Head;

- One on One sessions with all the programmes;

- Inspection of the ICT sites including the Data Centre and the training centre;

- Visit to the Supreme Court;

- Visit to two Kebeles; and

- Meeting with the Chamber of Commerce.

# Overall assessment

An overall report on PSCAP was outlined at a meeting with the BCB head and attended by all the programme focal persons.  Despite challenges the region for the period under evaluation concentrated largely on in house training programmes, procurement of goods and services and attempts towards improving organisational effectiveness.

# Assessment of implementation of each sub-programme

## JSRP

### General observations.

The Justice System Reform Programme has fulfilled all it MMAs and could be in a position to move on to other programmes such as the establishment of information counters in all courts. It has introduced the case recording and transcribing system, three rounds of training for judges and has held workshops on the new penal code for prosecutors.  The team had an opportunity to inspect all the mentioned achievements at the Supreme Court and was satisfied that the colour-coded system is functioning well and understood by staff.  A demonstration of the database containing almost all the historical cases of the court was made. The recording system was demonstrated and all the tapes from the system were displayed.  The Courts in Harari deal largely with civil cases and very little with criminal cases.  The team was told that the Supreme Court dealt with only one felony case last year.   The court caseload and the impact the coded systems have had on the system were demonstrated by extracting out of the system comparative figures from 1998 to 1999(EC).  Staff interviewed are satisfied that the clients that use the system are satisfied.  Also demonstrated at the court was the information desk, which affords responses to all queries about case progress to clients within at least 24 hours.

The Chamber of Commerce acknowledged most of these achievements.  The only reservation expressed against the justice system was the decision to defer the decisions surrounding land and property to the banks.

Three focal persons manage the Programme.  A single person deals with Justice and prisons, while one deals with the courts and the other with the police.

### Minimum mandatory activities

Progress at the last supervision was recorded as:

1. Improved quality and efficiency of operations

- 66% Installation of court case management and case recording & transcribing systems in all regional supreme & high courts

- 66% Installation of colour coded filing system in all woreda courts

- 100% Initiation of in-service training and professional development of all judges, lawyers and court clerks

2. Improved transparency and accountability

- 100% Establishment of information counters in all regional high courts and woreda courts

A lot has been achieved since and includes:

### Strengthening the judiciary

- The court case management system is installed and operational in the Supreme Court and the High court. The balance of the courts is planned for 2000(EC).

- The colour-coded system is established in the Supreme Court and the woreda court, which is, located in the city centre and in the same premises as the Supreme Court.

- The Supreme Court is well equipped with a fully functional Information centre.

- Training across the board for judges has been included every year

- Awareness to the general public has been raised through the use of posters and publications and the local radio stations.

### Law revision and law reform

- 9 local judges and 10 randomly selected advocates have been provided with training on the new criminal code.

### Law enforcement capacity enhancement

- Materials which have been provided to the prison authorities include photocopiers and computers

- 24 000 birr is secured to provide staff and security officers with human rights training.  The trainees will be drawn from prisons, prosecutions and police

- The Programme also supported a project of allowing contact visits between prisoners and their families as a contribution to building human right awareness.

### Legislative organ

Not much was reported on the support for this component.

## UMCP

### General Observations

The Urban Management Programme has been assigned to the Harari Municipality to manage. The programme concentrated a lot of effort into building the capacity of the Harari City to exist as a separate entity with legal and constitutional rights and obligations.  The new city council legislation brings this desire into effect.  It gives the city council authority to make laws to enter into contracts as legal persona, higher staff and be responsible for its revenues and raise capital.  A five-year plan has been formulated at a regional level.  It applies to the whole region and has been developed by the regional Urban Management and works Bureau.  The City is producing a master plan, which is due in five months, which will cover only the borders of Harari city to give a spatial planning context to the Strategic Plan.

The City has completed and finalised a restructuring plan. The Plan has already been implemented.  The City is one of the BPR sites identified under the CSRP.  There is a potential risk of reopening processes that may not validate the organisational structure already being implemented?

The launch of PSCAP, according to the city focal person, has brought a new attitude and has given impetus to radical changes in the city from the regional government.   The Regional State is now taking more interest in the affairs of the city.  The entire approach to the transformation of the civil service and PSCAP has helped to bring attention to the need to develop the city.  The Constitutional amendments giving the regional president authority over the city has helped.  The Budget allocations have increased, and with the eminent passing of further regulations on Land Management and Financial Controls, the fundamental building blocks for building the ability of the city to run as a fairly autonomous organ of the state will have been in place.

The evaluation team was able to visit one of the Kebeles in the city.  The Kebeles are larger that usual in Harari. Shenkor has a population of 26 525.  It has 7 cabinet members responsible for Education, Health, Industry (SMME’s), Finance, Safety and Security, Municipal Administration (who also represents the city administration on the Kebele cabinet, and Social Mobilisation.  The new structure has been in place for two and a half years and has gained a bit of experience in servicing people and carrying out its responsibilities. The structure however is still fairly new and cannot always cope with all the demands.  Some of the key challenges include dealing with ever growing urban in-migration putting pressure on roads, health services, dealing with the remote parts of the city, and the demand for electricity.

It appears that the city has developed an elaborate mechanism and structure to involve the community in the planning processes.  The extent to which communities participate differs based on the organisational leadership and capacity from Kebele to Kebele.  There was a stark difference between the two Kebeles visited. The one Kebele, Shenkor appeared well organised and has been able to form consultative and planning structures.  It has broken the Kebele into three sub Kebeles, each with sub committees covering at least twelve villages per sub Kebele.  The participation in these structures is high.  Jugol (the world heritage sight) on the other hand has two Kebeles.  The one Kebele visited seems less capacitated and seems to lack the talent and leadership style demonstrated in Shenkor.  It appears that similar structures have been established but with little successes in getting the same level and quality of participation from the community.

The chamber of commerce while appreciating the strides made in turning the city around is critical on a number of aspects. It still has to come to grips with the changes and understand the different roles of the city administration and the Kebeles, the role of the President and the City Manager.  There was confusion about the role of the City Manager and that of a mayor.  The Chamber of Commerce and Industry recognises the reforms to lease management and the negotiations and auctions approaches being implemented.  It feels that it might be early to judge if the old system where government merely ratified private treaties was better or not.  It does hope that the evaluations will help.

The Chamber acknowledges that the willingness to change is evident everywhere in the civil services.  There is still a problem with individuals who corrupt and generally fail to take responsibility and account.  There is an old bureaucratic tradition that seems to hold back the civil reform programme from succeeding.  There is evidence, according to the chamber of instances where Political and Ethnic affiliations interfere with proper decision-making.

There is a sense that there is a need to still radically rationalise the number of administrative centres and government executing agencies in the region.  The fact that the region despite been so small and compact enjoys a region status which puts it in a strong position at a federal level.  The administrative separation between state and municipal, urban and rural can be rationalised to maximise impact and cut down red tape to service 200 000 people in with a 400 square kilometre area.

### Minimum mandatory activities

The programme had recorded a very low 34% percent achievement during the last supervision mission.

1.Greater inclusiveness and transparency of planning and prioritization processes

- 10% Training completed in key prototype manuals (to be designated) including fin mgt procurement, contract administration, etc.

- 100% Development and adoption of the following legislation and regulations:

  - Urban land legislation,

  - Municipal proclamation

2. Enhanced revenue performance and fiscal autonomy

- 25% Development and adoption of region's urban development policy and strategy

3. Improved quality and efficiency of operations

- 0% Completion of one round of bulk generic training to all relevant regional and municipality staff as well as local leaders

### Regional urban management policy

- Formulated legal and institutional framework that included, endorsement of legislation giving personality to the city council, endorsing city personnel regulations, endorsing and implementing city financial regulations, approving and implementing land lease legislation and regulations,

- Formulating Land development policy included the development and adoption of the regional urban development policy.  The process to procure consultants is underway.  Formulating urban land and Housing Policy (also awaiting procurement of consultants) and implementing an environmental protection strategy.

### Deepening the process of decentralisation

- Terms of reference have been completed to call for proposals for the development of a revenue generation scheme and inter governmental fiscal transfers

- Terms of reference completed to draft standard and operational manuals for personnel and financial management

- In the process of procuring goods and carrying out training on land management. Procuring software for land preparation.

### Local government restructuring and capacity building

- Completed and implemented restructuring and staffing plan

- In the process of establishing a municipal and building court to deal with municipal by law contraventions and building codes offenders.

- Establishing an information and documentation centre for the municipality

- Financial management and accounting system is adopted for implementation

- Awaiting the appointment of consultants to design a billing and collections system.  The City Council has collected 12 million birr and plans to collect 20 million this year.  The five year target is 40 million per annum.

- Revenue enhancement guidelines prepared and to be finalised in this financial year

- Issued TOR to develop procedures and manuals for internal management.

## District Level Decentralisation Programme

### General Observations

The DLDP in the region is responsible for 9 local woredas that include the 17 Kebeles that lie outside the Harari city council area.  The objectives are to facilitate the devolution of power to the woredas, Institutionalise decision making and promote good governance and service delivery in conjunction with the Civil Service Reform Programme (CSRP).

The activities have included preparing a legal framework for decentralisation to the 9 local administrations. The programme has prepared and disseminated manuals and materials to the 9 woredas. The programme has conducted training on good governance. Local woreda budgets have been decentralised, and the woredas are expected to prepare their own budgets in the future. Special training on strategic planning has been conducted. The DLDP programme has made further training assessments on deepening decentralisation of woreda fiscal transfers.

Some of the outcomes discussed include:

- The establishment of appropriate structures, which have enhanced the fiscal powers of the woredas.

- Greater transparency and awareness by committees, and the ability to hold leaders accountable.

- The quality and efficiency of operations has been improved through the dissemination of materials and equipment.

- Capital budget spending at Kebele level is evident. The evaluation team was able to see the new offices under construction in the Shenkor Kebele.

- There is an improvement in the education sector marked by the improvements in the student / teachers ratios and more parent and community involvement in school governance programmes.

There are challenges, which include delays in preparing documentation on time. 15 Manuals await adaptation to suit Harari requirements. There is not much best practice exchange with other regions, except for attending quarterly meetings at the Federal offices. Consulting services take too long to procure.

### Minimum mandatory activities

From the previous mission report the DLDP had achieved 36% of its MMAs. This was broken down as:

1. Greater inclusiveness and transparency of planning and prioritisation processes

- 100% finalisation of strategy and action plan for gender sensitised community planning

2. Enhanced revenue performance and fiscal autonomy

- 7% completion of review and preparation of decentralisation legal framework and structure

- 7% adoption of the regions decentralisation strategy document

- 0% contracted technical assistance for implementation of regions woredas decentralisation strategy and policy development, benchmarking and review plans.

- 25% development and adoption of regions urban development policy and strategy

### Enhanced incentive environment for public servants

- 66% completions of assessment of human resources and training needs for woredas, the required office infrastructure and equipment.

As of the 1st Quarter of 2000(EC) the following is recorded:

### Manning and training

- Training on good governance (Woredas, Kebele civil servants, officials etc.) – 760 of the planned 1600 persons.

- Planned training on monitoring and evaluation

### Grassroots participation

- Planned training to involve 250 persons on democratic participation and law making for enhancement of HHS and women.

### Programme development

- Planned sensitisation workshop for 250 officials

- Planned follow up and reporting the implementation of good governance in collaboration with (CSRP; JSRP and ICT)

- Planned conduct sensitisation workshop on DLDP for 300 participants including civil servants and community leaders.

No mention for this quarter was made of the woreda fiscal transfers and own revenue, the woreda planning and fiscal control and the minimum service standards components.

## TSRP

### General Observations

The programme is run alongside the Expenditure Management and Control Programme under BOFED.

There are improvements in the Regional Revenue figures. The region is recording a year on year growth of 20% since 1997(EC)

- 15 million birr collected in 1997(EC)

- 18 million birr collected in 1998(EC)

- 23 million birr collected in 1999(EC)

These have been from direct taxes, profit taxes and income tax. The collection constitutes 17% of the Regional State Budget.

The following achievements were recorded in the discussion.

- 100% achievement of TIN registration. It was however not very clear what the total was. The presenter gave a figure (645 000 which was for more than the population of the region). He may have meant 6450. The evaluation team has not been able to verify the figures. It is claimed that there could be a 100% registration if TIN is a prerequisite for trade and business licences, which means that the region has a lot of revenue that it is not collecting.

- The Chamber of Commerce and Trade is also sceptical of the radical introduction of modern instruments such as VAT and business turnover taxes which may be imposed in such a way that, overnight, they may render the non legal markets, which dominated the economy of the city and the region for years, illegal.

- Annual income tax – The region has completed the annual turnover survey, which shows an increase in the rate of tax paying. The survey is 99% completed.

- Proclamation and regulation – The organisational structure with BOFED has been revised and new procedures and guidelines are 75% complete.

- Training – greater awareness of tax administration staff has been facilitated, which has increased the ability to collect.

- Education of taxpayers – The results of the taxpayer education efforts are demonstrated through the increase in the tax revenue collected.

### Minimum mandatory activities

The programme had recorded a 46% achievement, which was above the regions average. It was broken down as follows:

1. Contribution to improved predictability of financial resources

- 0% completion of annual turnover survey in all regions

2. Contribution to enhanced revenue performance and fiscal autonomy

- 75% issue of TIN and adaptation of proclamations, regulations and directives

- 57% provision of training and education to relevant staff and taxpayers at regional and city administration level.

3. Contribution to enhanced incentives for Civil servants

- 100% proportion of computerised TIN coverage to be 50% in other regions

- 0% installation of tax file management system in 50% of the woredas.

The achievement and activities for the current quarter includes:

### Organisation and tax payer education

- Planned a workshop of  125 persons (30% of which have to be women)

- Planned 4 training session for staff on strategic planning

### Tax payer identification number

- Planned 4 training sessions for staff on MIS and TIN

### Value added tax

- Planned 4 training sessions for key personnel on VAT administration

- Planning to develop and produce VAT formats

## CSRP

### General Observations

The programme has achieved most of its MMAs and was also responsible until recently for the Expenditure Management and Control activities.  The EMCP has since been transferred to the BoFED.  The main activities since the launch of PSCAP have been the procurement of goods and materials. Work on good governance has included developing training manuals and adapting them for Harari, and carrying out training, developing rules and regulations and improving work systems. A lot of IT material through the assistance of the ICT programme has been distributed to Kebeles.  Training on ROPE and the distribution of manuals has been completed.

Good progress seems to have been made on the BPR programme. Training has been completed and six pilot sites have been prepared for implementation.  These include the Education Bureau, the Capacity Building Bureau, the Harari City administration, the Water and Sewer Authority, Health and the Justice Bureau.

There was initial training concluded for top management on Strategic Planning and Change Management.

Some of the challenges the programme faced in the initial stages was the lack of communication and poor coordination from the RTT.

### Minimum mandatory activities

The programme was the best performing with a 52% achievement of its MMA as contained in the Joint supervision report

1. Contribution to improved predictability and adequacy of financial resources flows (in year and across years)

- 80% Elimination of backlog accounts at regional and local level

2. Contribution to greater inclusiveness and transparency of planning and prioritization processes

- 75% Installation and training in medium term expenditure management procedures manual; BIS; and BDA3 systems in all institutions

3. Contribution to enhanced incentive environment for public servants

- 70% Completion of training in prototype regulations and policies for human resource management and development in all regional bureaus and woredas

- 50% Completion of training in and adoption of result oriented performance evaluation (ROPE) system in all regional bureaus and woredas

4. Contribution to improved quality and efficiency of operations

- 25% The following PSIP-related activities launched in 75% of regional bureaus: Completion of client score cards, initiation of business process re-engineering

- 10% Training in top management systems of agency heads of 75% of bureaus

The following activities are planned and/or implemented for the 1st quarter of 2000(EC).

### Strengthening the capacity of CSR Coordinating Structures

- Planned development of CSRP implementation guidelines

- Give bulk training to implementing institutions

- 50 computer training sessions planned

- Planned to start disseminating CSR related material through newsletters, periodicals (containing papers on HIV and AIDS, gender and environmental protection).

### Improving governance of human resources management and control

- Planned training on prototype regulations and policies for HRM and development in all regional bureaus and Kebeles for 5 days.  15% of the participants should be women

### Improving performance and public service delivery

- Improve on the past performance of the PSIP related activities launched in 75% of the regional bureaus and complete score cards and initiate business process reengineering over a 15 day session. There might be a sequencing problem here if the score cards are approved ahead of a BPR process?

### Improving accountability and transparency

- Intends to evaluate, follow up and identify problems and propose solutions on the implementation of the CSRP. (This activity sounds very week and not well thought through).

### Strengthening top management systems

- Will provide special and intensive training to women on empowerment and self-reliance for 15days.  (The curious question will be how many women are there in the Top Management?)

## EMCP

### General Observations

The programme was funded through the DSA and MoFED.  It has become a PSCAP project only from 1999(EC). The achievements shared indicate that there has been training on cash management, the passing of about 50 financial regulations and purchase of stationary.  11 Computers have been procured and 191 000 birr worth of goods procured.

The 1997(EC) accounts are closed and 1998(EC) in still in progress and are in the immigration to BIS process.  The programme is making progress with all the reform programmes with independent application at the municipal (Harari) level. Very little evidence on the reform programmes was shown.

The zero balance cash management system was implemented in 1998(EC).

The high turn over of IT staff in the Bureau presents a huge challenge.   The Bureau was critical of the parallel lines running in the way PSCAP is run outside “normal government programmes”. The bureau head is of the opinion that the responsibility for capacity building should be the responsibility of all bureaus.  The transition from Decentralised Support services (DSA) held up progress.  Most of the delays were caused by the need to adapt to the cumbersome PSCAP requirements.

### Minimum mandatory activities

As indicated the programme was run a CSRP until l999 (EC).

The following is achieved or planned for the current year:

1. Enabling environment

- Will conduct short term training for accounting staff (50% of whom should be women) for 20 days on the IBEX programme

- Intend purchasing 10 desktop computers.

2. Capacity for expenditure management and control

- The programme will conduct training on rules, regulations and guidelines and various financial administration and budget preparation manuals for sector bureaus, Kebeles, administrative accountants, auditors and material management personnel for 10 days.  - 45% of the participants are women.

- The programme will conduct training on rules, regulations and guidelines and various financial resource management manuals for sector bureaus, Kebeles, administrative accountants, auditors and material management personnel for 10 days.  - 35% of the participants are women.

(Not sure why the training is separate and why there is a difference in the women participation percentages). The plan does not indicate any activities under the financial information and Audit functions components.

## ICT

### General Observations

The ICT programme articulated its objective producing a critical mass of ICT literate civil servant force that can utilise infrastructure effectively and improve service delivery.

The programme spent its inception years raising awareness and preparing through among other methods, exchange visits to other regions.  The real accomplishments date back to 1999. The programme and the region in general seem to be unable to attract and keep IT skills.  The programme is hampered by insufficient access to communication infrastructure and facilities at woreda and Kebele levels.

### Minimum mandatory activities

The ICT programme achieved 12%.  It only slightly contributed to the improvement of the quality and efficiency of operations overall KPI.  20% completion of a regional ITC HR strategy and action plan and 15 % initiation of training for civil servants working in ICT.

### Human resource development

- Established a training centre.  The evaluation team visited the centre, which is conveniently located on the premises of a teacher training college. The set up is completed and the training should commence soon.

- The programme has prepared and published training materials on networking, access, excel, data base management, and MS word.

- Basic computer training for selected secretaries and civil servants has been conducted

### Public service delivery and good governance

- The ICT programme intended rolling out Wan and LAN in government institutions and set up a consultancy supervision service to manage the network across the region.  The plans were not implemented due to, as claimed by programme, the World Bank rejecting the proposal.

### Applications for sector development

The ICT programme plays a general support role in the implementation and development of programmes in these sectors by assisting in improving access to government information, assisting in aligning common ICT applications and improving the management of Government information

### Community based information systems and services

The ICT programme completed one project and has EICTDA for further funding

# Programme management and support

## Institutional arrangements for PSCAP in region

The Programme is run out of the Bureau of Building in the Region. The ICT, CSRP and the DLDP programme are run by the BCB. The BoFED runs both the TSRP and the ECMP. The Urban Management Capacity Building programme is run by the City of Harari administration.  There is an RTT, which meets regularly to consider programme plans and review progress.

## Coordination with MCB, federal sub-programmes, and woredas

There is a complaint about the lack of information and a calendar outlining reporting intervals, which often leads to delays in compilation, and submission of reports to the MCB.  There is still a problem with the understanding of reporting formats required by the MCB and the World Bank.  The BoFED Bureau Head found the PSCAP requirements as cumbersome as compared to the DSA requirements. The region itself concedes that it still needs to sort its own document and process management systems out.

Very few of the Bureaus and the programmes interviewed indicated a relationship with any of their federal counterparts. The DLDP, the UMCBP and the CSRP seem to be the key points of interaction with Kebeles on a programme/ project basis.

## Compliance with eligibility criteria by region

- The evaluation team has had sight of a signed “Participation and Performance Agreement” by the relevant minister responsible for federal subprogram or relevant cabinet member for region

- Established and appropriate governance and implementation arrangements are in place

- With regard to the completion of relevant capacity assessments across all participating sectors and levels of participating institutions, especially in the case of woreda and municipal strengthening.  The evaluation team is unable to give a definite view.  The individual programmes seem to have done some needs analysis or the other for training and capacity requirements. This seems to be the case for ITC and the civil service reform programme.  The Jugol Kebele suggest that there are instances were decentralised structures at Kebele levels are created even when there is no capacity to make them effective.  There are mandates without capacity.

- The comment earlier about clarity on a planning cycle and calendar addresses the issue of timely submission of endorsed costed medium-term rolling plans, as well as technically sound, feasible annual implementation/procurement plans in line with the financial calendar. Even though the financial time table is set, the comments from the PD suggests that this criteria needs attention

- With respect to the explicit provision for evaluation of annual performance including dissemination to the public of such evaluations, satisfaction score cards, etc, as part of the consultative planning process. It appears that the dissemination is appreciated at the level and among the participating agencies and bureaus the most.  From the comments made by the Chamber of commerce it appears like a lot of attention has to be invested in this area.

## Planning and resource allocation

The initial planning of PSCAP from what the PPD reported appears to have been an inclusive and consultative process with inputs from all key supply agencies and potential beneficiaries.  The RTT has since taken the full responsibility of the process.  BoFED and the PSCAP accountants and a gender focal point for Women’s Affairs Department play a significant role in processing the final submission to cabinet for approval. The meetings of the RTT happen every month and a half and are well attended by all Bureau Member and Focal Persons.

## Procurement

Procurement particularly the World Bank processes yet again is the single most complained about issue. The Harari region is no exception.

## Expenditure and financial management

BoFED and the PSCAP accountants are responsible for managing the PSCAP financial affairs.

## Monitoring and evaluation

The Region has a Monitoring and evaluation department, which works closely with the PPD and the Bureau Head.  The department has not had any impact yet on the quality of reporting.  The tracking system that is in place has not been modified to assist with the tracking of progress against PCSAP objectives.  The evaluation team views this as a step in the right direction

## Information, education and communication

The CSRP, the JSRP and the TSRP all mentioned a strong push and need to disseminate information and education packages for the public.  The comments from the Chamber again appear to suggest very superficial and little understanding of the reform programme.

## Sequencing and integration of reform initiatives

There may be sequencing issues and overlaps which appears to have already been achieved by the Harari city with regard to Structures, personnel management and the intended BPR processes.  The risks are that there may be a discord between what was approved as early as 2.5 years ago and the results of a BPR exercise.  The Jugol case presents a challenge for the DLDP programme about the broad-brush allocation of responsibilities and structures through proclamations even to areas that clearly do not have the capacity to call a village meeting.

# Cross-cutting issues

The mainstreaming of gender throughout most of the training and staff capacity building programmes across programmes is commendable.  The Evaluation team regrets not being able to meet with the Gender Focal Person.  It appears the effort to include targets in as many activities as possible is worth the effort.

There was very little mention of HIV and Aids in general.  Environmental issues also receive very little attention

# Assessment of programme outcomes

The region scored a low 45% during the last supervision mission. The evaluation team used the programme outcome as baseline to evaluate the current status and where possible make recommendations to fill the gaps

| Supervision assessment report |  | Evaluation Team Comments |
| --- | --- | --- |
| Improved predictability and adequacy of financial resources flows (in year and across years) | 40% | - With more elimination of backlogs and the completion of the turnover survey in all the woredas the regions is likely to achieve more in meeting this outcome |
| Greater inclusiveness and transparency of planning and prioritization processes | 71% | - The EMCP is already undertaking BDA3 systems and Training on prototype regulations is underway. - These set the basis for building capacity to be inclusive. The evaluation team would suggest a more robust attempt to include sub Kebele participation in areas like Jugol and others. |
| Enhanced revenue performance and fiscal autonomy | 28% | - This area is likely to grow very fast and beyond the 20% year on year growth reported by BoFED. - The evaluation team is of the opinion that the revenue base in the region is highly understated and would be wary to accept that all potential TIN registrations have been covered 100% as reported. The population, the number of businesses and the size of the economy appeared all understated. - The City may well be on its way to gain fiscal autonomy. |
| Enhanced incentive environment for public servants | 57% | - The current year’s plans do not give enough impetus to achieving this outcome. Most of the Plans are about the physical working environment and very little about direct employment remuneration and benefits to the city staff structure and the salary proposals may cause a risk to managing parity between the civil service and the new emerging municipal service. There was no indication on how this possible risk will be mitigated. - Nothing in the plans suggests programmes to address the wage differential and decompression issues as raised in the PIP. |
| Improved quality and efficiency of operations | 35% | - There are sequencing risks to PSIP related process for the BPR pilot sites. The BPR is likely to produce new or different processes to those that formed the basis of existing score cards - Chances of meeting this outcome are greatly enhanced by the Justice Service reform achievements, the ICT progress and the BoFED programmes. - Very little can be expected from the training of top Management. The training is not moving fast beyond the initial change management and strategic planning. |
| Improved transparency and accountability | 75% | - The outcome stand the risk of not been met if the transparency is not appreciated by key players such as the chamber of commerce - The success of the information counter in the supreme court should be transferred to the woredas as speedily as possible |

# Key issues and challenges

Harari’s overall approach and performance is impressive.   The evaluation team believes that the size should be a great asset in building a strong collective that should and can drive the transformation agenda. The key issue remains the rate of in- migration into the region and the ability of the region and the city to respond to the growing pressure to service the ever-growing demands on services.  Related to this is the Region’s and the City’s ability to establish an environment in which all forms of trade and commercial activities can thrive.  The criticism that the current approaches are not geared to build on the traditional forms of trade that have been at the core of the economy of the region for centuries. The evaluation team is not convinced that the TIN and VAT registration captures the full potential of the size of the economy and the form and amount of trade.  It would be interesting to evaluate the amount of collection as a factor of GDP growth in the region.  The role of the banks is growing and the fact that the state has given it right to deal with collateral is welcome.  It is however a challenge whether the banks will exercise this rights responsibly and in a way that does not undermine economic activity and growth especially in the property sector.  The region is the melting pot of trade and commercial activities that extend beyond its political borders. The way the civil service is organised and managed should take this into account.

# Lessons learnt and recommendations

The evaluation team would suggest that the region consider a consolidation of structures rather than further decentralisation.  The extent of devolution to the municipality is appreciated and the creation of an independent revenue stream from the region state is understood.  This will however require an extra bureaucracy to collect from an economy and base that is concentrated.  The region might well be advised to take a long-term view towards building a City State Region and direct current civil service reform objectives in that direction