Annex 17: Somali Report

# Background

Pascal Moloi assisted by Girma Shegute visited the region from 22 to 24 October. It became very obvious from the beginning that the level of organisation in the region would be substantially different from that enjoyed in Dire Dawa the week before.  None of the appointments arranged prior to arriving in the region were confirmed. It was not easy to draw up an itinerary, and the team hoped that the meetings would be held and that the relevant players would be available.  We have to remark upfront that the style of operation was too casual. The working day throughout started between 8h30 and 9h00.  There was usually a dead period between 11h30 and 14h30 when no formal engagements were entertained.  The last half of the day lasted to 17h00.  It was difficult within the time available to squeeze in all the engagements that were required.  The distance between woredas added to this problem.

It was however possible to conduct the following evaluation sessions:

- The Justice System Reform Programme;

- The Civil Service reform Programme;

- District Level Decentralisation Programme;

- The Urban Management Capacity Programme;

- The Tax Systems Reform Programme;

- The Expenditure Management and Control Programme and

- The Information Technology and Communications Programme

The Beneficiaries interviewed included:

- The Parliamentary Secretariat;

- The Women’s Affairs Bureau;

- The Kerbribeyah Woreda;

- The Jigjiga Municipality;

- The Jigjiga District Woreda;

- The State Revenue Bureau; and

- The Bureau of Finance and Expenditure Development.

A round up session was also held with the Programme Planning Department

Somali has a regional Parliament of about 118 members.  There is a Cabinet and a number of Bureaus headed by Cabinet members. The Deputy President of the region heads PSCAP. There are 52 Woredas in the region with Jigjiga and 6 others being urban municipalities.  The rest of the region is rural and pastoral.  It is the second largest region after Oromia but has a sparse population of 4 million.

The team took a lot of notes from meetings and perused a number of documents submitted at the meetings and received after the meetings. Where possible and time permitting, actual inspections of premises, equipment and training sessions in progress were made and observed.

# Overall assessment

In general Somali had a relatively slow start and was unable to get PSCAP off the ground during the first year of inception. The reasons are varied between capacity to implement, understanding and agreement of processes and procedures. The initial discussions on PSCAP PIP requirements from the point of view of BoFED caused delays in the initial implementation of the programme. Most of the programmes failed to meet the Minimum Mandatory Activities. The Civil Service Focal Person indicated that the region failed to match its PPAs with the Minimum Mandatory Activities in the first year, and thus caused a delay in justifying further allocations to the region.

# Assessment of implementation of each sub-programme

## JSRP

### General observations

The Justice Reform Programme in the region is largely still in the training and awareness building stage.  It seems to have not moved far beyond what was reported in the previous supervision mission.

Key gaps identified include the need for special training for focal persons in the handling of the contents of the JSRP and programme management.  The current personnel learn on the job and do not have any training or guidance.  They rely on their own legal backgrounds and general knowledge.  They express a need for Programme Management and implementation and Monitoring and evaluation expertise.

The Evaluation team was unfortunately not able to verify the offerings of the programme with any beneficiaries.

### Minimum mandatory activities

Progress during the last supervision on the MMAs was recorded as follows:

#### 1. Improved quality and efficiency of operations

- 10 % - Installation of court case management and case recording & transcribing systems in all regional supreme & high courts

- 100% Installation of colour coded filing system in all woreda courts

- 100% Initiation of in-service training and professional development of all judges, lawyers and court clerks.

#### 2. Improved transparency and accountability

  - 0% Establishment of information counters in all regional high courts and woreda courts.

During the evaluation the following progress was reported

### Strengthening the judiciary

- Conducted ongoing advanced diploma level training for 70 regional and woreda judges and court clerks

- Conducted training on managerial and leadership skills for 120 judges and support personnel;

- Conducted training on criminal law for 10 public defendants;

- Procured IT equipment and deployed to the Supreme and Zonal courts; and

- Conducted training on court case management software for 20 court staff and clerks.

The planned activities include a study on and implementation of case management and recording systems.

### Law revision and law reform

- Held HIV and AIDS and law awareness creation workshops for 100 prosecutors and office staff;

- Held a Human and democratic rights awareness workshop involving 300 traditional elders and women (at least 30% of the participants);

- One month legal training for 215 prosecutors including environmental law, the criminal code and anti corruption;

- 60 Prosecutors (including 30 sponsored via the treasury budget) are studying advanced law diploma as in service trainees.  They were two semesters to complete

- The translation and publication of the Ethiopian Penal code is in progress

Planned activities include preparing regulations for prosecutions and the roll out of filling and recording systems for the Justice Bureau.

### Law enforcement capacity enhancement

- 250 police personnel form 3 zones trained on community policing and fundamental rights;

- A study on crime prevention is underway

- Police files recording management system was implemented

- 180 prison officials trained on fundamental rights and rehabilitation of prisoners (20 of which were women)

- 27 prison staff trained to teach technical training, clinical nursing and sanitary science

- The establishment of a juvenile rehabilitation centre is underway

- The personnel and prison file recording management system is operational

### Legislative organ

- 45 standing committee members and 15 support staff have been trained on budgeting, drafting, the evaluation of bills and federalism;

- 10 members of the regional council (including the speaker of the house) have been for training on parliament administration and oversight control

- 20 proclamations drafted and enacted

- New IT equipment and office staff has been rolled out in the parliament offices

- The study on improving the rules and regulations governing oversights mechanisms is 70% complete.

## UMCP

### General Observations

The programme is run out of the Bureau of Urban Management and Works.  One person appointed by the Federal Bureau is responsible for the Consultancy, Training and goods components of the programme.

The programme has done well, in developing strategy and policy documents and is in a position to present them for approval.  It is however not yet in a position to implement. The discussion with the Jigjiga Municipality has not provided much insight on the potential for progress in implementation.  The evaluation team noted with concern that the capacity in the bureau to drive this process is questionable.  The work culture is said to be poor with high levels of absenteeism and generally low commitment to the programme.  Special mention has to be made with the parallels drawn with the Good governance programme run by the UNDP.  It appears that there are huge overlaps with PSCAP.  An attempt at federal level to fuse the two should be pursued. There appears to be a higher commitment to the good governance programme.  PSCAP is seen largely as a source of funding and not much as a programme.  Guidance on this issue is sought from the federal Bureaus of Capacity Building and Urban Management.  The discussion with Jigjiga gave an impression that the city still operates along the forms and structures of the old regime and still has to transform its policies, organisational structures and systems along the PSCAP objectives.

### Minimum mandatory activities

The programme reported 75% achievement of mandatory activities.  This is against a 40% performance recorded in the last report broken down as follows:

1. Greater inclusiveness and transparency of planning and prioritization processes

- 25% Training completed in key prototype manuals (to be designated) including fin mgt procurement, contract administration, etc.

- 100% Development and adoption of the following legislation and regulations: urban land legislation, municipal proclamation

2. Enhanced revenue performance and fiscal autonomy

- 0% Development and adoption of region's urban development policy and strategy

3. Improved quality and efficiency of operations

- 33% Completion of one round of bulk generic training to all relevant regional and municipal staff as well as local leaders

### Regional urban management policy

A number of strategies are completed and will be considered by cabinet.  These include:

- The Urban Land Development Strategy with regulations for Leasehold administration and Land administration

- Hosing Development Strategy

- An organisational development and appropriate staffing study.  The study suggests right sizing for municipalities

- Financial regulations

- Urban Grading report which categorises cities in the region

- Policy and legislation

- Approved powers and functions for cities

- Completed Intergovernmental and Communications manual for cities

### Deepening the process of decentralisation

- Will commence with the Powers and Functions proclamation

- Have completed a situational analysis of the seven major cities in the region, which assesses the state of infrastructure, the sectors and utilities providing services in these cities, and level of education.  The report should present a clearer picture of the state of the cities in the region

### Local government restructuring and capacity building

Produced a generic urban development strategy per category of cities

## DLDP

### General Observations

The DLDP discussion appeared to have achieved a lot and has continued from the good progress recorded in the last mission report.  DLDP is now run as a separate department with the Bureau of Capacity Building.  Until now it was run as a programme.  It has a direct reporting responsibility to the office of the Deputy President who is also the Head of the Bureau.  It is now called “Woreda Capacity Building (DLDP)”.  Four people including the Head of the department and two Focal Persons staff it.  One person is responsible for PSCAP and the other for UNDP decentralisation Programme.

The programme faced a lot of initial understanding of PSCAP.  The establishment of a dedicated department in the bureau to deal with woredas has helped.  Some challenges still remain, given the nature of the region, in building institutions in woredas. The programme had however managed to create awareness of the woreda roles and responsibilities. It has managed to redeploy civil servants to woredas and has been able to introduce systems in some woredas.  This has been done in at least 20 woredas that are more accessible such as the Jigjiga District and cash management issues have been dealt with.  The DLDP has structured itself to be a funnel of all PSCAP offerings to the woredas and has been greatly assisted by the authority of the office of the President.

The evaluation teams’ own assessment of the state of woredas from the Jigjiga district and the Kerbebribeyah woreda confirm that there are huge gaps to be filled. It is clear that the DLDP has only gone as far as doing a study on capacity and training needs assessments and has gone a long way in preparing manuals. Both woredas interviewed are still to enjoy the full benefits of the DLDP programme.

The feedback is limited to the comments received from the Jigjiga District woreda.  The district acknowledges the training received on good governance, which has changed the attitudes and conception of staff. It acknowledged the relevance and content of the manuals received.

### Minimum mandatory activities

The last mission report recorded the following:

1. Greater inclusiveness and transparency of planning and prioritisation processes

- 20% Finalisation of strategy and the action plan for gender sensitised community participation

2. Enhanced revenue performance and fiscal autonomy

- 100% Completion of review and preparation of decentralisation legal framework and structure

- 66% Adoption of region's decentralisation strategy document

- 0% Contracted technical assistance for implementation of region's woreda decentralisation strategy and policy development, benchmarking and review of plans

3. Enhanced incentive environment for public servants

- 17% Completion of assessments for: human resource and training needs for woredas, the required office infrastructure and equipment

### Institutional & organisational arrangements

- Prepared legal framework and functional assignments for woredas

- Prepared a woreda good governance package

- Ran a sensitisation programme for 300 people from woredas

- Produced a woreda working manual

### Manning and training

- Finalised woreda human resource training needs analysis

- Prepared woreda training manuals

- Rolling out Masters, 1st Degree and diplomas involving 220 woreda civil servants.  This is done in collaboration with universities

- Provided training for 739 Alternative Basic Education Facilitators from 50 woredas for 60 days.

- Completed six months training for 100 health extension workers from all woredas.

- Have advertised locally for 265 training opportunities on basic computer training

### Grassroots participation

- Preparing a grassroots training manual

- In the process of preparing a region wide training programme

### Programme development

The Woreda decentralisation manual is completed.

### Woreda fiscal transfer and own revenue enhancement

The alternative grant formula, which reviews the existing one based on population, revenue potential and state of development, is in first draft.

### Woreda planning and financial control

- Issued RFP to procure consultants to assist with the formulation of a monitoring and evaluation manuals

- Woreda expenditure management and control assessment is finalised.

### Minimum service standards

Currently evaluating proposals for the preparation of the minimum standards document

### Office infrastructure and development

- Procured 57 desktop computers, 52 filling cabinets, 102 double pedestal desks, and 204 swivel chairs;

- Training on the usage of new equipment is prepared.

## TSRP

### General observations

The programme is run out of the State Revenue Bureau.  A Focal Person and an assistant run the programme.  The two are responsible for goods, consultant services and the training activities of the programme

The programme is achieving its objective at the regional level. It is in the process of preparing itself to decentralise it operations to woredas.  It has established desks along side expenditure management in woredas.

The tax systems reform programme has shown a steady increase in revenues collected.  The Bureau raised 51 million in 1998(EC), 62 million in 1999(EC) and has a budgeted target of 75 million for 2000(EC).  It has already collected 90% of the first quarter target.

### Minimum mandatory activities

1. Improved predictability and adequacy of financial resources flows (in year and across years)

- 20% Completion of annual turnover survey in all regions

2. Enhanced revenue performance and fiscal autonomy

- 75% Issue/adopt/adapt proclamations, regulations and directives (to be designated)

- 100% Provision of training and education to relevant staff and tax payers at regional and city administration level

3. Enhanced incentive environment for public servants

- 95% Proportion of computerised tax payers identification number (TIN) coverage to be 50% in other regions

- 205 Installation of tax file management systems in 50% of woredas

The following progress was recorded per component of the programme:

### Tax policy and legislation

- Refined and adopted the proclamations and regulations (income, exercise, turnover and VAT) to suit the conditions of the region

- Conducted study, approved and issued the Agricultural Income Tax and Land Use fee Proclamation and directive;

### Tax payer identification number

- Conducted training on computerised TIN system to 60 revenue desks and Planning experts from 14 selected Woredas that generate over 700 000 Birr;

- Conducted training on TIN registration campaign.

### Presumptive taxation

A regional campaign for registration involving 85 tax personnel from 38 woredas was undertaken.

### Operational programmes systems, procedures and manuals

- Developed a strategy, systems and procedures manual peculiar to the region

- Engaged a local consultant to establish a tax file management system

### Organisation and tax payers education

- Conducted training on Tax systems, Procedures and Manuals;

- Conducted study tour on revenue administration to other regional states;

- Training on Tax policy and Legislation for 270 revenue desk tax assessment; collection and inspection and planning experts from all the 52 woredas;

- Conducted training on Tax assessment, auditing and tax payer service delivery;

- Conducted training on taxation and public finance.

- Conducted a study to develop a tax payers' education strategy and system.

## CSRP

### General observations

It appears that the region is achieving its planned activities.  Participation was very poor in the initial years of implementing the programme in the Region.  There was little understanding of PSCAP and thus no or little support was received from the bureaus.  The initial years saw very little match between what was planned, allocated and what eventually got to be implemented on the ground.  The programme had very little capacity and was unable to hold on to skilled personnel.  This resulted in the programme suffering a year’s setback. The Programme failed to meet its MMAs.  The Focal Person argues that some of the MMA could well have been met but were not included in the PPA

From the discussions with the Parliamentary Focal Person, the Bureaus of Revenue and BoFED, there appears to be satisfaction with the offerings received from the programme. The training on strategic Planning included Speakers and Deputy Speakers and there are plans to include woredas in the future. Parliamentarians benefited out of the Training Programmes given. 45 standing Committee members and 15 professionals were given training on Parliament Management, Petitions Management and office management.  The Focal person is happy that the Parliament secretariat was involved in the Training needs assessment and the actual preparation of the training sessions.  Both BoFED and the Revenue Bureaus were satisfied with the training received and the Revenue Bureau is one of the six BPR pilot sites.  The CSRP has established committees in these sites and is ready to roll out consultants to start with the processes.

The Jigjiga District Woreda was happy with the PSCAP support received.  It has been involved with the DLDP programme and ICT as will be shown below.  It anticipates CSRP roll out during this year.  The capacity building coordinator and the finance person are recipients of a long term diploma and a masters degree respectively.

The Parliamentary secretariat attributes the fact that there was a high turn over to the passing of proclamations to the training and exposure through exchange programmes it received form the CSRP.  BoFED acknowledged the impact the training provided for strategic planning. The State Revenue department is looking forward to the BPR process.  The BCB used the Strategic planning training as an opportunity to develop a strategic plan for the department.  The session included all key players including the deputy president.

### Minimum mandatory activities

From the last supervision assessment the programme had achieved 63% of its minimum mandatory activities broken down as follows:

1. Improved predictability and adequacy of financial resources flows (in year and across years)

- 66% Elimination of backlog accounts at regional and local level (Programme now transferred to BoFED)

2. Greater inclusiveness and transparency of planning and prioritization processes

- 45% Installation and training in medium term expenditure management procedures manual; BIS and BDA3 systems in all institutions (Programme now transferred to BoFED)

3. Enhanced incentive environment for public servants

- 66% Completion of training in prototype regulations and policies for human resource management and development in all regional bureaus and woredas

- 75% Completion of training in and adoption of result oriented performance evaluation (ROPE) system in all regional bureaus and woredas

4. Improved quality and efficiency of operations

- 25% The following PSIP-related activities launched in 75% of regional bureaus:

  - Completion of client score cards, and

  - Initiation of business process re-engineering

- 100% Training in top management systems of agency heads of 75% of bureaus

The following progress was recorded during the evaluation discussions:

### Strengthening the capacity of CSR Coordinating Structures

- Established the Programme as a fully-fledged department within the region.

- Used the Strategic planning training session to produce a 5 year strategic plan for civil service reform

### Improving governance of human resources management and control

- Provided training on ROPE, but have not implemented yet.

### Improving performance and public service delivery

- Raised awareness to 1200 woreda staff on the public service and good governance in a 10-day workshop. (Workshop coincided with the opening of a new hall).

- Trained 200 top officials on BPR

- Established committees to undertake BPR in 5 select pilot Executing Agencies including the Revenue Bureau, The Trade and Industry Bureau, the Civil Service Bureau and the Jigjiga Municipality.

### Improving accountability and transparency

- Not much was discussed on this component except for a comment that a lot of awareness has been achieved.

### Strengthening top management systems

- Conducted training for top management on strategic planning and change management

## EMCP

### General observations

The EMCP programme up to this year was run out of the CSRP in the Bureau of Capacity building.

The programme faces a lot of challenges in applying the PSCAP financial planning management guidelines. The Deputy Bureau head commented that the guidelines do not take into account the subjective conditions prevailing in the region and would be happy if there was room for modifications.  The closure of accounts is delayed by the inability of the bureaus to deal with accounting backlogs timorously. There has been a recurring shortage of PSCAP funds and the problem is even more peculiar this financial year.

BoFED confirmed that training on budget reforms and internal audit was conducted and that forms and manuals have been provided. Training and awareness programmes were confirmed with the Jigjiga District woreda and BoFED. The zero balance cash management system is been rolled out. The double entry system is been delayed to give priority to the accounting backlogs programme.  Double entry manuals are been translated and training is expected to resume this year.

### Minimum mandatory activities

(See the MMA under CSRP for the previous period when the EMCP was still run from there).

### Enabling environment

Held awareness workshops involving 16 woredas and section heads.  There was a deliberate attempt to avoid remote woredas because of security and logistical challenges.

### Capacity for expenditure management and control

- Training held at woreda level to implement budget, accounting, treasury and internal audit reforms,

- Provided forms and manuals

- Ready to implement reforms later in this financial year

### Financial information

- Closed accounts up to 1997,1998(EC) is ready for evaluation and 1999(EC) still a work in progress.

- Require assistance with BIS support.

- Implementing zero based cash management system

- Not implementing double entry system because of a decision to prioritise dealing with accounting backlogs first.

### Audit functions

Prepared for carrying out audits from BoFED

## ICT

### General observations

The ICT programme in Somali appears to be performing relatively well.  Like the DLDP and CSRP in the BCB, it is been elevated to department status.

### Minimum mandatory activities

The ICT programme had a high 97% achievement rate during the supervision assessment.

1. Improved quality and efficiency of operations

- 90% Completion of regional ICT human resource development strategy and action plan for public sector institutions

- 100% Contracting of technical assistance for review of human resource requirements for rolling out of Government systems and applications

- 100% Initiation of training for relevant civil servants working in ICT

### ICT Human Resource Development:

- Procured 150 ICT equipment including both hardware and software and distributed to bureaus

- Held more than 5 training sessions for PSCAP Focal Persons, data centre staff and civil servants in the region

- Modified the existing Regional Information Hub into a training centre

- Translated Video Conferencing Manuals into Somali

### ICT for public service delivery and good governance

- Preparatory work for the Regional Information Centre is underway;

- Developed five regional websites and these are running

- Woredanet equipment transportation and installation is underway

- Information Management Services for Health (HMIS) and Education (EMIS) was developed and operational

- Digitisation for the Jigjiga Municipality is underway

### ICT applications for sector development.

### Collected information for consolidation in two bureaus

- MIS requirements for the Education and Capacity Bureaus to integrate data bases is underway

- Network connectivity for three bureaus is underway and internet connection established for four bureaus

- LAN study was conducted for seven bureaus

### ICT for Community based information systems and services

- Community needs assessment is underway

- Community based information was compiled and is translated into local Somali language

- Community information centre establishment proposals submitted to ICTAD. ????

# Programme management and support

## Coordination with MCB, federal sub-programmes, and woredas;

Coordination with MCB in the region is largely funnelled through the BCB. Except for the Urban Management Capacity Building programme where the Focal Person is a deployee of the federal Bureau of Urban Management and Works, the rest of the programmes seemed content with the arrangement. The EMCP programme is now managed as a separate programme under BoFED.  The DLDP, ICT and CSRP all enjoy full department status in the BCB.  Generally the Region has full time personnel who are dedicated Focal Persons.  In total the region has Seven Focal Persons and the PPD.  There are two specialists rededicated to assisting with procurement.

## Institutional arrangements for PSCAP in region, and effectiveness of coordination within the region

PSCAP at the highest level is coordinated via a Steering Committee chaired by the President and made up of the six bureau heads.  The RTT is established and reports into the Steering committee.  Over the last 2.5 years of PSCAP there have been very infrequent irregular meetings of both structures. The RTT has for the evaluation period met only twice.  PSCAP has become a regular item on the cabinet agenda.  Since the arrival of the new PPD head, there have been a lot of frequent one to one meetings where the focal persons and the bureau head met with the PPD Head and the capacity Building Bureau Head (the deputy President) to talk about programme specific issues.  The discussion centres on planning implementation, procurement and general coaching on issues as they may have arisen

## Compliance with eligibility criteria by region

The region appears to have met all the eligibility criteria:

- “Submission of signed “Participation and Performance Agreement” by the relevant minister responsible for federal subprogram or relevant cabinet member for region “– The evacuation team was given a copy of the PPA

- “Establishment of appropriate governance and implementation arrangements”. – Somali Region has a very elaborate governance and implementation structure with 3 programmes in the BCB now made departments and full time Focal Persons for all programmes

- “Completion of relevant capacity assessments across all participating sectors and levels of participating institutions, especially in the case of woreda and municipal strengthening” – This is the one area that is suspect. There may be mitigating factors such as the vastness of the region, the inaccessibility of the remote woredas and the security and logistics challenges.

- “Timely submission of endorsed costed medium-term rolling plans, as well as technically sound, feasible annual implementation/procurement plans in line with financial calendar” – The Programme management team presented plans for the 2000(EC) year as presented.  The key concern is that the budget for this year, with a quarter gone, is not yet released.

- “Explicit provision for evaluation of annual performance including dissemination to the public of such evaluations, satisfaction score cards, etc, as part of the consultative planning process.” – The evaluation team was not presented with such evidence nor is it satisfied that this criteria has been met.  There is no evaluation and monitoring system in place let alone dissemination to the public.

## Planning and resource allocation

All programmes have issues with Planning and resource allocations.  There is always a gap between what is planned, requested in the form of budget proposals, what is approved and what is ultimately allocated to the programmes. Year on year bureaus have had to offer bridging finance to programmes.  This year the problem is compounded by the fact that there were delays in the release of the regular budget as well.  The PSCAP Budget is yet to be completed. The State Revenue Bureau head illustrated a difference in the responses received on the same submission from the World Bank, the MCB and MoFED.  That it was common for MoFED to even add new activities on the regions submission

## Sequencing and integration of reform initiatives

There was very little indication that there were sequencing problems experienced by any of the beneficiaries interviewed.  There seems to have been a sufficiently high level of materials rolled out.   A time lag in training and putting these to good use, especially IT equipment may be a risk.

## Financial management

BoFED has allocated two accountants to assist with all PSCAP financial Management requirements. This includes preparing budgets, responding to audit queries and accounting.

Table 1: Budget allocations and expenditure

| Programme | 1997 Budgeted | 1997 Spent | % | 1998 Budgeted | 1998 Spent | % | 1999 Budgeted | 1999 Spent | % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CSRP | 1,637000 | 22,740 | 1.4 | 5,130664 | 367,554 | 7 | 3,191100 | 2,498985 | 78.31 |
| JSRP | 195800 | 47,080 | 24 | 4,559300 | 2,563268 | 56.2 | 3,753048 | 3,753048 | 100 |
| TSRP | 908000 | 00,000 | 0 | 1,616164 | 1,014234 | 62.7 | 957100 | 671569 | 70.17 |
| UMCBP | 3,374600 | 00,000 | 0 | 3,003002 | 453,857 | 15.1 | 2,478920 | 1,028301 | 41.48 |
| ICT | 3,273100 | 24,770 | 0,75 | 6,413331 | 1,076059 | 16.8 | 3,512300 | 1,389766 | 39.56 |
| DLDP | 2,643000 | 329,998 | 12.5 | 4,913980 | 1,160289 | 23.6 | 3,017187 | 2,611422 | 86,5 |
| PSU | 424068 | 40,417 | 9,5 | 737549 | 625,814 | 84.9 | 655765 | 675765 | 100 |
| Total | 12,455568 | 465,005 | 3,7 | 26,373990 | 7,257074 | 27.5 | 17,565420 | 12,608856 | 73.72 |

## Procurement

Procurement and particularly the world ban processes and the treatment of ICB, emerged as a constant source of complaint from all programmes.  BoFED however feels the problem is not so much with the guidelines and the system but with capacity to implement at various levels of the chain.  It however contends that the ceiling may be unnecessarily high and can be lowered.  There may be limitations at BCB to prioritise procurement. The impression from the programmes is that BCB staff is too busy worrying about their own programmes to worry about prioritising procurement.  The Procurement committee ahs been reformed slightly to include the PPD Head (convenor), 2 specialists, one representative form the procuring programme and a person from BCB.  A lot of attention will be on dealing with the ICB procurement.

## Monitoring and evaluation

There was no indication that there is capacity in the region to implement Monitoring and Evaluation and the implementation of PIP guidelines.  Only the CSRP spoke about Monitoring and evaluation and the need to start giving attention to it given the increase I the number of activities.

## Information, education and communication

A few programmes seem to be dedicating an effort towards IEC.

# Cross-cutting issues

There are no clear programmes to deal with cross cutting issues.  It is unfortunate that the meeting with the Women’s Affaires Bureau did not bear any fruit.  The only feedback received was that the Cabinet had taken a decision to take 2% of working Capital for HIV and Aids programmes from every budget and imposed a 30% quota for all training to include women.  Some of the respondents complained that the quota is difficult to meet, as the existing employees do not include women at all.

# Assessment of programme outcomes

| ###### Supervision Mission Report |  | Evaluation Team Comments |
| --- | --- | --- |
| ##### Enhanced predictability of financial resource flows in-year and across years | 43% | - There is evidence of annual reviews of budget - The fact that the 2000 budget has not been released creates uncertainty. - The review mission reports are available and there is evidence of some of the recommendations been implemented. - Good progress has been made with the backlogs process since transferring to BoFED |
| ##### Greater inclusiveness and transparency of planning and prioritization processes | 48% | - Except for evidence received from the Jigjiga region, the team was unable to formulate an opinion on the inclusiveness of the planning process from the woredas and the municipalities. - There was no evidence of the involvement of civil society. |
| ##### Enhanced revenue performance and fiscal autonomy | 57% | - The revenue bureau has made a lot of progress in improving collection capacity - The capacity can be increased with the building of woreda and municipalities collection capabilities |
| ##### Enhanced incentive environment for public servants | 55% | - Except for the Training on ROPE as reported to the supervision mission there is no evidence of further work done and achieved in this area |
| ##### Improved quality and efficiency of operations | 78% | - The high achievement recorded in the last mission is attributed mainly to training and launching of a number of CSRP processes. There was a lot of ICT progress reported that achieved 100%. - There is still a need to place more emphasis on Education, Health, Agriculture, Water and Land Management. |
| ##### Improved transparency and accountability | 50% | - While there was no evidence of corruption and lack of accountability, the evaluation team was constrained by time, the absence of organised formations and the unavailability of people to formulate an opinion. Save for a mention on the production of brochures, the publication and posing of Woreda budgets on boards at their offices entrances, there does not appear to be a lot of government communication. |

# Key issues and challenges

While the effort relative to where the programme was a year ago is appreciated.  A lot of attention to should be given to building capacity to management to drive the reform programme in general in the region.  The fact that the region is investing in deploying full time personnel is appreciated.

The following need attention:

- Greater attention to changing the work ethic.  It may be a long shot, but the working hours and the long breaks present a risk for the programme in keeping up with the rest of the regions.

- The pace of decentralisation is questionable. While the evaluation from the Jigjiga District Municipality was encouraging the responses from the Jigjiga Municipality and the Kerbebribeyah Kebele may indicate that there is a lot of effort required to go beyond assessments and studies to begin with tangible institutional and structures building programmes.

- The high turn over of PPD Heads should be a concern.  The current head seems equipped to handle the task.  The PPD should consolidate coordination and management structures as speedily as possible to ensure the maximum support to programmes. The fact that the PSCAP budget is not yet released may be a serious draw back.

- The Urban Management Programme needs to be singled out as an area needing attention.  The comments made about the work ethic and culture in the Bureau needs to be taken seriously.  The region is largely rural and pastoral and the urban management programme can afford to be more focused on the few urban centres.  The Urban Good Governance Package and PSCAP programme overlaps have to be sorted out as a matter of urgency.

- All programmes complained about procurement delays.  It does however appear that the PIP guidelines and procedures are well understood. The complaints are more about the amount of time spent on the administration of the programme.  The PPD has to give greater attention to ensuring that the newly revamped committee is capacitated to process as speedily as possible.  The region makes a strong case for the review of the Procurement ceilings for ICB.