Annex 10: Amhara report

# Background

Steve Topham, assisted by Ato Eskinder Tesfaye, conducted the assessment of PSCAP progress in the Amhara National Regional State (ANRS) over the period 21-27 October 2007. Meetings were held with the Regional Bureau of Capacity Building (BCB); sub-programme leaders; the Civil Service Commission; the HIV/AIDS Secretariat; the Regional Management Institute; Bureaus of Justice, Women’s Affairs and Works & Urban Development; the Bureau of Finance & Economic Development (BOFED); Tana Haik Senior Secondary School; Bahir Dar City Council; the woredas of Bahir Dar Zunia, Woreta and Meket; the Supreme Court, representatives from the Police and Prison services; the Regional Council office; and the Amhara Chamber of Commerce. A full list of interviewees is attached as Annexure One. The Regional BCB and other interviewees provided written documents, a list of which is attached as Annexure Two.

# Overall assessment

Amhara is considered to be one of the more advanced regions of the country. Yet it has many development obstacles to overcome, including worrying levels in the incidence of HIV/AIDS and a literacy rate of 23%. The population is around 18.6 million people, and the state capital is the city of Bahir Dar. Amhara has 10 zones, 140 woredas and 3 082 kebeles, and, in the current year, an estimated 120 000 civil servants.

PSCAP is led by the BCB, which has around 40 staff. There is a Regional Technical Team (RTT) with membership drawn from the BCB, the Women’s Affairs Bureau, and PSCAP implementing organisations  - Bureau of Justice, Bureau of Works & Urban Development, and Amhara Revenue Authority.

The CSRP has made some important progress in the region – BPR exercises have been initiated in 16 government offices, while improved HRM procedures have been introduced into all zones and woredas. Local capacity building offices are responsible for monitoring the level and impact of these activities, and provide this data on a quarterly basis for consideration by the Amahra Civil Service Commission (ACSC).

The DLDP is also making progress in improving monitoring and evaluation. November 2007 (EY 2000) sees the DLDP unit making an intensive set of field visits to 38 selected woredas to conduct impact assessments of its activities.

The ICT programme has achieved notable progress in roiling out ICT to woredas – 114 have video-conferencing, all are connected to the Internet and currently 743 woreda offices and desks have e-mail addresses.

The JSRP continues to perform well, with advances in court administration and caseload management at all levels, as well as on-going professional development training for judges, prosecutors, legislators, prisons and police staff. Backlogs have largely diminished, and the time taken for cases to be presented and heard has been reduced.

Regional performance in PSCAP expenditure against allocated budget is improving – increasing from 75% in 2005/06 to 90% in 2006/07. However, expenditure categories are dominated by training, which consumes an estimated 93% of the total PSCAP budget compared to around 3% on procurement of goods and 0.1% on consultancy. While training is a priority activity within PSCAP, this expenditure pattern appears unbalanced. It is partly due to delays in procurement of goods and services, and difficulties in securing services of skilled consultants; but it also seems that training activities have become the ‘default’ setting for the programme, as they require no external approval and are under the region’s direct control. The EY 2000 (2007/08) Participation & Performance Agreement puts forward a more equitable programme (training 60%; goods 24%; and consultancy 16%), although only the final out-turn figures against approved budget will demonstrate whether a real shift has occurred.

Despite some activities to publicise the reform programme (including a weekly programme on regional radio) Amhara still lacks a coherent IEC strategy.

The Amhara RTT sees its role as a quality assurance and coordination body, focusing on the production of annual plans and receiving quarterly progress reports from sub-programmes. Apparently it meets on a quarterly rather than a regular monthly basis. This situation should be addressed – consistent, regular meetings build institutional knowledge, improve programme coordination and provide for consistent monitoring of RTT decisions and initiatives.

# Assessment of implementation of each sub-programme

## Justice System Reform Programme (JSRP)

### General observations

The JSRP is having a positive impact on court efficiency, and is benefiting from the foundation laid during the previous CIDA-funded Court Reform Programme. The region has one Supreme Court, 10 high courts and 173 woreda courts. There are 753 judges in total, of which 183 are women.

The JSRP has a very effective steering committee, chaired by the Regional President with the Vice-President (who also acts as Head of the BCB) as vice-chair). Other members are the Regional Council, the Supreme Court, Justice Bureau, Police service and Prisons administration. This group meets monthly to assess progress, develops plans and coordinate activities. The BCB Public Service Capacity Building Coordinator acts as secretary.

PSCAP has been successful in scaling up the processes of court reform – CIDA-supported innovations were introduced in 70 woreda courts, this now continues and has been increased to 101 under PSCAP. There was some loss of continuity and dislocation in the CIDA-PSCAP transition, primarily with the introduction of new administrative systems and procurement procedures, although this does not appear to have had a lasting effect.

PSCAP has supported continued professional training, assistance in introducing new administration systems, and supplied various equipments, including computers, transcribers, office equipment and furniture. Provision of equipment is critical to continued improvement in efficiency, and the Evaluation Team was disappointed to note that relatively high proportions of computers (18%) and photocopiers (40%) distributed under the programme were currently inoperable.

### Minimum mandatory activities

The MMAs are partially complete. Court case management, case recording and transcribing have been installed in the regional supreme and high courts, along with the colour coded filing system. This continues to be rolled out to woreda courts.

There has been substantial in-service training for judges, prosecutors and court clerks, and this programme of professional development continues.

### Strengthening the judiciary

There has been an impressive improvement in the professional capacity of the judiciary and support staff (court administration and Justice Bureau civil servants), with a wide range of training activities completed (see Table 1):

Table 1. JSRP trainees, EY 1998 and 1999

| Training subject | Trainees |
| --- | --- |
| Case management database system | 290 |
| Word processing and use of templates | 353 |
| Client awareness training | 542 |
| Court reform awareness | 178 |
| Computer maintenance | 25 |
| Gender awareness | 929 |

Source: Amhara PSCAP Physical & Financial Performance Reports EY 1998 and 1999

In addition, CSRP components have been incorporated into the training for management and staff. Training events have been held in human resource development (for top managers), financial accounts reform, client orientation, and ethics and accountability.

### Performance Indicators

There have been significant improvements in court performance in Amhara – figures for 2006 (EY 1999) show that:

- The case clearance rate now stands at 99.6% across the region

- 92% of cases are heard within six months

- Each judge handles on average 415 cases

- The backlog of 374 505 cases was reduced by 339 888 (90%)

- Only 34 617 cases – 9% of the annual total - were transferred forward into the new budget year; these cases were mainly those opened in June/July

- The average administrative cost of each court case is Birr 111.2. (This is one of the few measures of cost efficiency found by the Evaluation Team)

Minimum standards have been adopted which help explain the improvement in performance – regional supreme court judges are expected to deal with 25 cases per month; high court judges 30 cases; woreda court judges 35 cases.

Equally importantly, there is a strong effort to measure improvements in the ‘quality of justice’ provided. Judges’ performance is assessed through monitoring the number of cases that are passed through on appeal to higher courts and the Court of Cassation, and their subsequent judgements. The Judicial Council can take disciplinary measures in cases of inappropriate professional behaviour. For example, a woreda court judge was recently censured and fined two months salary for exercising poor judgement in sentencing a rape case.

### Law revision and law reform

The ANRS has promulgated the new Family Law, and conducted training on this subject among law-makers, judges, prosecutors and police.

### Law enforcement capacity enhancement

The prisons service has around 3 000 staff (prison police and administrators), and some 30% of these have undergone training in the past two years. Courses include human rights awareness, and HIV/AIDS. These activities have been the first training provided under PSCAP, and staff reaction has been very positive.

The police service has received training in community policing, crime prevention and investigation, and HIV/AIDS, with 3 391 participants since EY 1998. Community policing training has proved very effective, and the new approach has been introduced in 47 woredas and 346 kebeles. The target for EY 2000 is to roll this out to 50% of local structures – some 70 woredas and 1 500 kebeles.

Both services report a constructive relationship with the PSCAP process, through participation in planning and monitoring activities in the Steering Committee. However, final budget allocations are small, and the procurement process is tedious.

### Regional Council and legislative bodies

The Regional Council reports that PSCAP-supported training is paying dividends in the improved quality of law-making procedures, improved operations of oversight bodies and more efficient administration. In-house training has been provided in a range of modules: good governance, parliamentary system, oversight and accountability mechanisms, human rights, multi-party democracy, and the role of council members. Participants in EY 1998-99 were as follows:

- 200 Regional Council members (136 men, 64 women)

- 533 speakers, members and heads of standing committees from nationality zones, urban and woreda councils (490 men, 63 women)

The Regional Council secretariat pays careful attention to structuring the training programme and presentation of topics. Modules are adapted to take into account experience, education and literacy levels of participants. Feedback is obtained from all trainees at the end of each course, although there has been no external assessment on the impact of the training.

Capacity building activities for the Regional Council are supported mostly by PSCAP sub-programmes  – mainly from the JSRP while the remainder is secured from the CSRP. Anti-corruption and ethics training was provided by the federal agency.  The budget is allocated on time, and there is little variance from the Regional Council’s budget request.

Expenditure against budget allocation showed a decline in the last financial year (see Table 2); this was reported as being due to a high workload among Regional Council secretariat staff, which had to carry out other duties and responsibilities.

Table 2.Amhara Regional Council PSCAP-funded activities – Allocation and Expenditure

| Year | Budget Allocation Birr | Expenditure Birr | % Expenditure |
| --- | --- | --- | --- |
| EY 1998 / 1999 | 600 000 | 450 000 | 75% |
| EY 1999 / 2000 | 708 000 | 374 000 | 53% |

Source: Interview with Regional Council Secretariat Officials, 22 October 2007

### Cross-cutting issues

HIV/AIDS and gender issues feature consistently in the planning and training activities of the implementing agencies. Positive action has been taken to promote women participation in training events and to hold specific training activities on gender issues.

All Justice bureau staff has received training on HIV/AIDS awareness, and the department has its own HIV/AIDS action plan.

The police service has instituted a policy of positive recruitment for women in its traffic division, where they are considered to be good role models in a highly visible service and less open to temptations of corruption.

There was no evidence of any mainstreaming of environmental issues in the JSRP.

## Urban Management Capacity Building Programme (UMCBP)

### General observations

The UMCBP is currently located in the BWUD. Although the programme has been active officially for two years, in reality it has only become operational over the last 12 months. The Bureau Head reports that he and the Programme focal person are now more familiar with PSCAP processes, and are now engaged more actively. The focal person was not available for interview. The programme’s allocation for EY 2000 is Birr 26 million. There are 22 cities in Amhara – this includes 10 that were recently upgraded from municipality to city status.

### Minimum mandatory activities

All four MMAs have been completed:

- The Amhara Urban Development Policy and Strategy has been developed and adopted.

- Personnel management manuals have been developed and distributed to all cities.

- Both the urban land and municipal legislation have been developed and proclaimed.

- The first round of generic training to city, municipality and sub-municipality staff has been completed.

### Local government restructuring and capacity building

A total of 945 municipal and kebele councillors have been trained on urban development and management (which includes good governance, economic development and housing). In addition, generic training courses have been given to 800 city, municipality and sub-municipality staff on subjects including urban development and planning, land management and leasing, municipal finance, service delivery, project management, local economic development and community participation.

Over 4,000 participants took part in the conferences on future planning and responsibilities for the 10 newly upgraded cities.

### Gender issues, HIV/AIDS and the environment

PSCAP has been used to strengthen management of urban environment issues, and the UMCBP is currently developing terms of reference for designing an environmental protection system for urban centres.

There is little evidence of mainstreaming gender issues in this programme, beyond the target that 30% of participants in generic training courses must be women.

There is no evidence of HIV/AIDS mainstreaming.

### Next steps

The UMCBP has overcome its initial slow start, and has established an effective foundation for the programme. Strong engagement will be needed with PSCAP procurement procedures to secure timely and effective technical assistance to support the large number of cities in the region, and those newly upgraded municipalities in particular.

## District Level Decentralisation Programme (DLDP)

### General observations

The DLDP falls within the BCB, and accounts to one of the two Vice Bureau Heads. Following a BPR exercise in the BCB, the DLDP and CSRP are gradually being merged. Even though this exercise is supposed to improve operational efficiency, the staffing complement still seems low given the numbers of sub-regional structures it has to support. The DLDP unit comprises only three officials – a coordinator (in post) and two expert posts (one currently vacant).

The DLDP is making good progress, and is one of the highest spending programmes under PSCAP, no doubt because of the need to roll-out mass training exercises in capacitating woredas. Its annual expenditure on training over EC 1998 and 1999 is good, but its performance in securing goods and consultancy support over the same period is very poor (see Table 3 below). Goods and consultancy services amount to only 0.13% of total expenditure over the two years.

Programme staff report that while the planning and procurement processes are generally sound, obtaining approvals and no objection letters cause serious delays. Even so, this level of performance seems highly unbalanced.

Table 3. DLDP Expenditure EC 1997-1999

| Budget Year | Approved Budget Birr m | Expenditure by Category Birr m |  |  | ### Total Expenditure Birr m |
| --- | --- | --- | --- | --- | --- |
|  |  | Consultancy | Training | Goods |  |
| 1997 | 5.04 | 0.00 | 0.00 | 0.00 | 0.00 (0%) |
| 1998 | 26.26 | 0.00 | 25.02 | 0.06 | 25.08 (95%) |
| 1999 | 12.29 | 0.00 | 28.67 | 0.01 | 28.69 (233%) |
| Total | 43.58 | 0.00 | 53.69 | 0.07 | 53.76 (123%) |

Source: Amhara PSCAP Expenditure Summary EC 1997-1999

### Minimum mandatory activities

So far, only two MMAs have been completed, namely the human resource, training and equipment needs assessment for woredas; and the plan for community participation. Progress in other activities is as follows:

- Decentralisation legal framework: A zero draft Decentralisation Act was produced in EC 1998. A further draft legal framework document received from Federal DLDP in October 2007 (EC 2000). This will now be assessed and adopted for implementation by the ANRS government.

- Minimum service standards: Service standards and norms document received from Federal DLDP, October 2007 (EC 2000). This will now be assessed and adopted for implementation by the ANRS government.

In addition, further documents and prototypes have been received from Federal DLDP for review and adoption, including the woreda planning and budgeting manual, model fiscal transfer formula, and the system for participation of membership-based civil society organisations.

### Capacity building

The programme has carried out a major programme of training across zones, woredas and kebeles since EC 1997, and examples of the scale and performance are shown in Table 4. Main training modules include: Manning and Training; Planning and Control; Grass-roots Participation; Minimum Revenue Enhancement; Minimum Service Standards; and Good Governance.

In addition, 100,000 copies of the document ‘Questions on Good Governance in Rural Woredas and Kebeles’ have been printed and distributed to local officials.

Table 4.Examples of Training Performance in Amhara DLDP, EC 1997-1999

| Training Activity | Planned Number of Trainees | Actual Number Trained | Performance against Target | Percentage Women Participants |
| --- | --- | --- | --- | --- |
| Integrated planning and reporting for woreda and kebele officials | 1 204 | 1 103 | 92% | N/A |
| Gender analysis and project preparation for woreda and kebele officials | 700 | 644 | 92% | 60% |
| Woreda budget allocation and grant formula for data collectors | 296 | 259 | 88% | 16% |

Source: Amhara PSCAP Physical & Financial Performance Reports EY 1999

### Planning and participation

The DLDP has an annual plan, against which progress is assessed on a quarterly basis. Quarterly progress reports are collated by the PPD, for consideration by the RTT. DLDP procurement is done via the BCB’s Procurement Desk, and consolidated into the programme’s annual procurement request.

Participatory planning features strongly at woreda level. Information from the DLDP and visits to three woredas confirmed that annual plans are produced jointly between woreda administrations and communities, through a process of meetings and community identification of key projects.

### Woreda fiscal issues

The woreda block grant system has been introduced, and accounts for around 80-90% of woreda finances across the region. it is mainly used for salaries and recurrent costs; the balance plus own revenue raised means that there is little capital available for development projects.

### Woreda financial administration

The DLDP, along with BOFED and EMCP support, is assisting to strengthen financial planning and control at woreda level. According to BOFED, by October 2007 (EY 2000) 90% of the region’s woredas had closed their annual accounts for 2006 (1999 EC) and most had been audited. Previously, there were delays of up to three years in closing accounts, but now all woredas are up to date. All woredas have assets registers, which are checked as part of the external audit. This improvement in performance is due to increased capacity and expertise provided through the PSCAP and DSA programmes, and the outreach assistance given by the woreda support units located at zonal level.

### Communications and coordination

Coordination between the regional and federal DLDP was considered to be fairly loose, with joint planning and information sharing meetings taking place only bi-annually. Horizontal coordination was much stronger, with the DLDP working closely with BOFED and the CSRP to ensure effective alignment of training activities. The RTT plays a useful role here in helping coordination these programmes.

Communications between DLDP and woredas is more difficult, given the geographical spread of the region and poor road network. However, DLDP and other programme staff are undertaking a major assessment of progress and impact in 38 selected woredas in a 20-day field visit in November 2007 (EC 2000). ICT links with woredas are improving, although not always consistently functional. Around 114 woredas now have internet and e-mail connections (81% of the total), which is an impressive achievement. It is essential that DLDP staff have good computer skills, as this medium of communications will become more important in the future as more woredas and officials become e-ready.

### Cross-cutting issues

The Women’s Affairs Bureau assess DLDP annual plans for gender content, and advise accordingly. Gender disaggregated data is available for most training activities.

Women’s issues also feature strongly at woreda and kebele level, and there has been widespread provision of gender awareness training. Meetings are held with women’s associations as part of participatory planning processes. The best-performing woredas include gender perspectives in all sector operational plans.

There is also a high level of recognition of HIV/AIDS issues. Awareness training courses have been provided to all woredas, and HIV/AIDS is built into all sector operational plans. This increased awareness and planning contributes to the impressive performance of mass mobilisation campaigns for voluntary counselling and testing.

The DLDP programme so far has paid little attention to environmental issues, although is seeking to link up with the Environmental Protection Agency and relevant NGOs to develop course content on these issues. The Evaluation Team noted a high level of environmental awareness in the woredas visited, no doubt prompted by having to engage with practical issues on land rights, deforestation, soil depletion and water use.

## Tax and Customs Reform Programme (TSRP)

### General observations

The TSRP falls under the ANRS Revenue Authority, which was established in 2006 (EC 1998) The Deputy Head of the Revenue Authority is the TSRP focal person. There is no specific unit for the TSRP within the Authority; rather it is mainstreamed into the activities of line departments – Tax Assessment; Research & Systems; Tax Investigation & Intelligence; Finance & Administration; and Taxpayer Education & Public Relations.

The Authority has around 70 staff posts (40 for experts), of which 25 are currently vacant. This shortage of skilled staff – particularly accountants and economists – is replicated in the tax offices in all sub-regional government structures. Tax collection performance been good, exceeding its targets for three out of the last four years (see table 5 below).

Table 5. Amhara Tax Collection EY 1996-1999

| Year | Collection Target (Birr m) | Actual Collected (Birr m) |
| --- | --- | --- |
| 2003/04 (EY 1996) | 260 | 318.2 (122% of target) |
| 2004/05 (EY 1997) | 400 | 424.1 (106% 0f target) |
| 2005/06 (EY 1998) | 385 | 382.4 (99% of target) |
| 2006/07 (EY 1999) | 405 | 457.9 (113% of target) |

Source: Amhara Revenue Authority document: ‘Tax Reform Programme has launched to alleviate existing problem’ (undated).

In addition, the Authority has issued more than 65,700 Taxpayers Identification Numbers, 25,000 individuals have been identified as presumptive tax payers, and 606 businesses have been registered for VAT in EY 1999, compared to 403 in EY 1998. In EY 1999, Birr 21 million was collected from VAT.

The TSRP has consistently under spent its PSCAP allocation over the past two years. The low expenditure on goods and equipment is of concern, given the increasing importance of automation, electronic record-keeping and the introduction of ICT to improve the efficiency of the service. The Revenue Authority reported that this low level of spending was due to problems experienced with procurement procedures, which were found to be slow and inefficient.

Table 6. TSRP Expenditure EC 1997-1999

| Budget Year | Approved Budget Birr m | Expenditure by Category Birr m |  |  | ### Total Expenditure Birr m |
| --- | --- | --- | --- | --- | --- |
|  |  | Consultancy | Training | Goods |  |
| 1997 | 3.06 | 0.00 | 0.37 | 0.00 | 0.37 (12%) |
| 1998 | 3.63 | 0.00 | 1.72 | 0.50 | 2.23 (61%) |
| 1999 | 3.55 | 0.09 | 0.55 | 0.00 | 0.65 (18%) |
| Total | 10.24 | 0.10 | 2.64 | 0.50 | 3.24 (32%) |

Source: Amhara PSCAP Expenditure Summary EC 1997-1999

### Minimum Mandatory Activities

The TSRP does not have a document setting out its progress against the MMAs. However, the Evaluation Team noted the following progress:

- Tax reform and administration proclamations, regulations and directives have been issued and distributed to offices and users.

- Coverage of Tax Payers Identification Numbers has steadily increased from 47 400 in EY 1998 to 65 700 in EY 1999

- The revenue potential survey has been completed

- The training on tax laws for administrators at regional, woreda and city level has been completed.

### Business viewpoint

Amhara Chamber of Commerce is a regional representative business organisation, with 51 city and woreda chambers and around 38 000 registered members. The Chamber has welcomed the need for tax reform, and believes the new approach has improved clarity on the requirements for business. The Chamber agrees that that the system is improving, but raised concern about the lack of capacity in important centres, giving the Bahar Dar city taxation office as an example. Concern was also raised of moonlighting of revenue offices staff also providing services to private enterprises. The Chamber reported that it had had one meeting with the Revenue Authority to discuss the tax reform process, but that there had been no follow-ups. In this respect, the Evaluation Team feels that the Revenue Authority is missing an important opportunity to promote its message and build an effective partnership with organised business, and recommends that regular briefings are held with the Chamber, and that its membership network is used to communicate changes to tax laws and administration, and raise business awareness.

### Capacity Building

The TSRP has put considerable effort into training at regional and sub-regional levels over the past three years:

- 824 tax officers at zonal, woreda and city administration level have been trained on new tax laws and management

- 1 636 government officials have received training on tax reform, procedures, roles and responsibilities

- 314 officials have attended training on ethics and anti-corruption

- 681 staff have been trained in monitoring and evaluation

- 1 424 individuals have attended tax education sessions

### Cross-cutting issues

HIV/AIDS features in the Revenue Authority’s own business plan, although not in PSCAP supported activities. Data on the number of participants in training courses is partially gender disaggregated; women’s involvement in these activities ranges from 15-25%. There have been no specific activities on environmental issues.

## Civil Service Reform Programme (CSRP)

### General observations

The programme is the responsibility of the CSRP department located within the BCB, and accounts to one of the two Vice Bureau Heads. The Expenditure Management Control Programme (EMCP), which falls under the CSRP in the original PSCAP design, is increasingly being dealt with by the BOFED, and is treated separately below. The CSRP department has seven posts on its establishment, although only four are currently occupied (the programme coordinator and three experts).

The CSRP has working partnerships in place, led by focal persons in other collaborating Bureaus and agencies. These include BOFED (expenditure management); Office of the Auditor-General (financial accountability); Civil Service Commission (HRM procedures) and the Regional President’s Office (programme oversight). However, the EY 1999 Amhara PSCAP Physical and Financial Performance Report states that there is a lack of coordination among these agencies, particularly in a failure to follow through in implementation of annually planned activities.

CSRP expenditure performance has been good as shown in Table 7 below (which includes activities under the EMCP programme. Expenditure has exceeded approved budgets, with extra allocations being transferred from other programmes.

Table 7. Amhara CSRP and EMCP Expenditure EY 1997-1999

| Budget Year | Approved Budget Birr m | Expenditure by Category Birr m |  |  | ### Total Expenditure Birr m |
| --- | --- | --- | --- | --- | --- |
|  |  | Consultancy | Training | Goods |  |
| 1997 | 5.79 | 0.00 | 0.00 | 0.00 | 0.00 (0%) |
| 1998 | 25.68 | 0.00 | 25.67 | 0.42 | 26.10(102%) |
| 1999 | 11.84 | 0.00 | 22.33 | 0.48 | 22.81 (193%) |
| Total | 43.31 | 0.00 | 48.00 | 0.90 | 48.91 (113%) |

Source: Amhara PSCAP Expenditure Summary EC 1997-1999

However, 98% expenditure has been used on training, a similar proportion to the DLDP. This is a highly unbalanced pattern of expenditure, which even the well-known difficulties over PSCAP procurement procedures do not adequately explain.

### Minimum Mandatory Activities

The CSRP does not have a document setting out its latest progress against the MMAs. However, the Evaluation Team noted the following areas of progress

- Initiation of Business Process Re-engineering (BPR) in 75% of regional Bureaus. Status: Target exceeded. BPR exercises are now underway in 16 government offices, including the BCB. About six exercises have been completed. Training has also been provided to zonal and woreda officials on BPR.

- Completion of top management training for heads of 75% of Bureaus. Status: Target exceeded. All regional Bureaus heads have received training.

- Training and adoption of Results Oriented Performance Evaluation (ROPE) in all regional Bureaus and woredas. Status: Started. A workshop has been held on performance-based management for 141 government officials.

- Completion of client score cards launched in 75% of regional Bureaus. Status: no evidence of progress was provided to the Evaluation Team, in written form or in interviews.

### Strengthening the capacity of CSR Coordinating Structures

The CSRP department is in place, and works with focal persons in its counterpart structures in the regional government and implementation agencies, as well as linking to the capacity desks at zonal and woreda level. A recent BPR exercise in the BCB concluded that merging the CSRP and DLDP would improve efficiency in the delivery of both programmes. The Evaluation Team did not see any details about this process, or how this conclusion had been reached.

The CSRP department had raised concerns about lack of follow through on implementation by its programme partners, although it was felt that this was now gradually improving. It was also suggested to the Evaluation Team that more training on programme management was needed. This indeed may be valid, and should be considered seriously, but the effect of high workloads and extra responsibilities needs also to be taken into account.

### Improving governance of human resources management and control

There is still no HR Development Strategy for the region. It was reported that a framework was awaited from federal level, and also that the region felt it would need technical assistance to produce a regional version.

The CSRP has included a major training exercise on HRM, with awareness training conducted for 9 867 regional, zonal and woreda officials. The Civil Service Commission (CSC) has developed the proclamation and regulations on the Civil Service Legal Framework, and organises the training of trainers on HR issues. Generally, these are selected from HR staff at woreda level, and are prepared with the use of training manuals. This standardised approach is adopted to maintain consistency across the structures of sub-regional government. The trainers are then given a time-limited schedule to carry out training on HR issues in their home woredas, after which they must report on progress to the CSC. The CSC then follows up with on-site inspections.

Impact assessment on the effect of this training is still poorly developed, but the CSC generally reports positive improvements in a reduction of the number of grievances and a decline in complaints about recruitment and promotion.

The CSC has also commissioned research on developing a motivation strategy for civil servants. The study involves research on the prevailing culture and work ethic of the civil service, and looks to develop ways of motivating staff to perform better. The assignment is underway currently, and could produce interesting and potentially significant results.

### Improving performance and public service delivery

Training has been provided on improving service delivery to 586 woreda and zonal experts.

### Improving accountability and transparency

Training has been provided on ethics and accountability to woreda and zonal experts. I

### Strengthening top management systems

The CSRP has provided a considerable amount of training to senior mangers. In EY 1999 a total of 3,295 participants attended modules on strategic planning and management, performance and change management, and BPR.

### Cross-cutting issues

Considerable effort is made at all levels to ensure a gender balanced trainee selection, but gender disparities in employment and management positions clearly affects the levels of female participation. For example, only 12% of participants on senior management training were women.

The CSRP office reported that HIV/AIDS awareness and gender awareness were included as elements in the overall training programme, but that little attention had been paid to environmental issues.

## Expenditure Management & Control Programme (EMCP)

### General observations

The EMCP programme falls under the CSRP, although BOFED implements the relevant activities. Support is closely aligned to both the CSRP and DLDP programmes. The USAID Decentralised Support Activity (DSA) programme has provided the finance that covered the bulk of work on budget and accounts reform. This programme ends in November 2007 (EY 2000), and PSCAP will then form the bulk of finance. So far, PSCAP funds have been used for activities on strengthening procurement, internal audit and cash management.

The single accounts function has been widely adopted and is operational at regional, zonal and woreda level. Transparency, accountability and effectiveness have improved, with budget transfers now delegated from BOFED to sector Bureaus at regional level, to adjust according to need and demand.  The EY 1999 accounts for all regional Bureaus are due to closed by the end of November 2007 (EY 2000).

### Minimum mandatory activities

Progress against the EMCP MMAs is as follows:

- Elimination of backlog accounts at regional and local levels. Status: almost complete, with woreda backlogs cleared and 90% of woredas having already closed their EY 1999 accounts. All regional Bureaus will have closed their EY 1999 accounts by November 2007 (EY 2000).

- Installation and training in medium term expenditure management procedures manual, BIS and BDA3 systems in all regional and woreda institutions. Status: complete at regional level, and underway for woredas. The BDA3 system is being updated to the Integrated Budget & Expenditure System (IBEX).

### Budget reform

The new BIS has been established and computerised, and training provided on budget and accounts reform (DSA-funded).

### Accounts Reform

Double entry bookkeeping and single pool accounting has been introduced at regional, zonal and woreda level.

### Capacity building

PSCAP funds have been used for the following training activities:

- Procurement and supplies management: 1190 trainees, plus provision of 1 200 procurement procedures manuals

- Internal audit: 519 trainees, plus provision of 615 audit manuals

BOFED considers the provision of manuals from Federal level to be a useful contribution to the capacity building process, and a good example of federal-regional coordination. The prototype manuals are adopted to regional conditions, and usually only slight modifications are needed.

The finance departments of regional and sub-regional government structures are also hampered by high turnover in skilled staff. This has implications for training, requiring that it has to be done annually to update newcomers.

### Cross-cutting issues

Considerable effort is made at all levels to ensure a gender balanced trainee selection, but gender disparities in employment and management positions clearly affects the levels of female participation. For example, only 12% of participants on senior management training were women.

The CSRP office reported that HIV/AIDS awareness and gender awareness were included as elements in the overall training programme, but that little attention had been paid to environmental issues.

### Future Funding

The Amhara 2007-08 (EY 2000) Programme Performance Agreement (PPA) allocates Birr 600 000 to the EMCP. This seems low, given the importance of the programme in helping to create robust financial systems and fact that DSA financial support ends in November this year. The Evaluation Team recommends that this amount be kept under scrutiny by the RTT. Given effective EMCP performance, plans should be well in hand to increase this allocation by transfers from programmes performing less well.

## Information & Communication Technologies (ICT)

### General observations

The ICT unit is located in the BCB, and has a complement of nine staff (three government staff and six United Nations Volunteers). The programme has made very significant progress in providing infrastructure and delivering training courses, but has experienced logistical limitations in obtaining equipment via ICB in particular.

According to the PSCAP expenditure summary for EY 1997 to 1999, spending under the ICT programme has been very weak, and non-existent in 1999 (see Table 8 below). No other programme shows zero expenditure for 1999.

Table 8. ICT Expenditure EC 1997-1999

| Budget Year | Approved Budget Birr m | Expenditure by Category Birr m |  |  | Total Expenditure Birr m |
| --- | --- | --- | --- | --- | --- |
|  |  | Consultancy | Training | Goods |  |
| 1997 | 24.80 | 0.00 | 0.00 | 0.00 | 0.00 (0%) |
| 1998 | 8.86 | 0.00 | 2.26 | 0.00 | 2.26 (25%) |
| 1999 | 13.02 | 0.00 | 0.00 | 0.00 | 0.00 (0%) |
| Total | 46.69 | 0.00 | 2.26 | 0.00 | 2.27 (4.8%) |

Source: Amhara PSCAP Expenditure Summary EC 1997-1999

However, the Amhara PSCAP Physical and Financial Performance Report for EY 1999 tells a different story to the 1997-1999 Expenditure Summary. In the report, total ICT expenditure is shown as Birr 2.458 million (Training: Birr 1.252 million; Goods: Birr 1.206 million). There appears to be some confusion here, and these figures should be reconciled.

The ICT programme has its own coordinating body, the ICT Coordination and Technical committee. This was established in EY 1998, and comprises the ICT Unit and representatives of the Bureaus of Education, Health, Trade & Industry, Works & Urban Development, Agriculture and Rural Development, the Ethiopian Telecommunications Corporation and the Ethiopian Electric Power Corporation.

### Minimum mandatory activities

Progress against the ICT MMAs is as follows:

- Establishment and strengthening of Regional Data Centres. Status: complete. One regional and 114 woreda data centres have been established.

- Completion of technical training for Regional Data Centre staff. Status: complete.

- Initiate basic computer training for designated ICT focal persons from all woredas. Status: complete.

### Human resource development

There has been an impressive effort made to develop an ICT-literate workforce across the Amhara regional and sub-regional administrations. Training activities include:

- ICT awareness training given to 1 544 regional, zonal and woreda officials (EY 1998) and 1893 woreda officials and experts (EY 1999)

- Establishment of Regional ICT Training Centre, based within the BDB

- 228 Woreda-Net operators trained in video-conferencing and equipment management

- 466 woreda officials received basic ICT training

- Basic computer training (Windows office suite and internet) provided to 749 officials and 704 members of the judiciary

- Advanced computer training given to 973 civil servants

- Since 2005 Bahar Dar University has conducted distance learning with around 8 000 civil servants, using video-conferencing facilities in 10 zone towns

- Preparation, printing and distribution of 7 000 copies of the Regional ICT manual.

Training is provided in five regional centres (Debre Markos, Debre Birhan, Dessie, Bahar Dar and Gonder).

### Public service delivery and good governance

An ICT Regional Strategy document was developed in EY 1999, and 5,000 copies distributed. The ICT Unit has also commissioned the development of the following research and studies:

- Establishment of a public-private partnership to attract ICT investors

- Cost benefit analysis of Leased Line infrastructure

- Feasibility of adopting Open Source Software

- Feasibility of establishing e-kiosks for ICT services to farmers in remote areas.

In addition, the ICT Unit has implemented the following applications to assist in improving service delivery and communications:

- Establishment of LANs and inter-bureau and office connectivity in 36 Bureaus, offices and zones, plus training in network utilisation.

- Wireless network installed in Ethics and Anti-Corruption Commission

- Design and commencement of roll-out of Woreda-Net added services.

Internet access now covers 114 woredas, and 874 offices in 88 woredas have their own e-mail addresses.

### Applications for sector development

The ICT Unit has set up a task team to test the application of the Civil Service Information System (previously developed by private consultants). This will, if successful, be adopted and rolled out all Bureaus. Systems development for the Bahar Dar City Administration has been completed, and consultancy bids for systems development in the Gander City Administration have been evaluated.

A number of websites are in development, including the BCB (launched: www.amhcbb.gov.et), Bahar Dar City Administration, Bureau of Education and Amhara Mass Media Agency.

Library database systems have been developed for the Micro & Small Enterprise Trade & Industry Promotion Agency, the Bureau of Trade & Industry, Regional Investment Office, and Bureau of Water & Resources.

### Community-based information systems and services

In addition to the e-kiosk and farmers information project referred to 3.7.4 above, the ICT Unit has also been working on the following community-based information services projects:

- Identification of suitable rural market places for locating information kiosks

- Identification of 103 projects for community-based information services, with the first two chosen for more detailed investigation – the Awi community Tele-centre and the Amhara Region Youth Association Information Centre

### Cross-cutting issues

No information was available on the mainstreaming of the three cross-cutting issues in the ICT programme.

# Programme management and support

## Institutional arrangements for PSCAP in region

The ANRS BCB is the lead bureau on PSCAP in the region, and has the following structure (see figure 1 below):

- A Bureau Head (who is also the Regional Vice-President), and two Vice-Bureau Heads

- Planning & Programming Service (PPS) – which acts as the central administration office for PSCAP coordination, includes the Procurement and Monitoring & Evaluation functions, and acts as secretariat to the Regional Technical Team (RTT)

- Public Sector Capacity Building Department – which acts as coordinator for focal persons within the Justice Bureau (JSRP), Revenue Authority (TSRP) and Bureau of Works & Urban Development (UMCBP)

- The Civil Service Reform Programme (CSRP) department

- The District Level Decentralisation Programme (DLDP) department, which after a recent BPR exercise, is being merged with the CSRP

- Information & Communication Technologies (ICT) Unit – again, a PSCAP sub-programme, located within BCB and accountable to a Vice Bureau Head

- Education & Training Coordination experts, who provide support across all programmes on training issues

- Public Relations Officer, who accounts to the Bureau Head

Figure 1. Amhara Bureau of Capacity Building

Implementing Agencies and Partners, including:

Civil Service Commission

Amhara Regional Management Institute

Bureau Head

Public Relations Officer

Executive Secretary

Vice Bureau Head

Vice Bureau Head

DLDP Department

CSRP Department

Public Sector Capacity Building

Department:

JSRP

TSRP

UMCBP

Sector Bureaus

Planning & Programming Services

ICT Centre

Education & Training Coordination Experts

In addition, there is an important working relationship with the BOFED, which provides financial management services on PSCAP funds (through a dedicated programme accountant) as well as implementing the EMCP. However, according to information provided in documents and interviews to the Evaluation Team, the BOFED does not have a representative on the RTT.

The Women’s Affairs Bureau has a PSCAP focal person, who is responsible for assesses programme plans and outputs, and also sits on the RTT.

Regional Technical Team: The RTT is the coordinating body for PSCAP in the ANRS. It meets to consider annual plans, quarterly progress reports and other relevant documents (for example, reports from Joint Supervision Missions), and is chaired by the Head of the BCB. Its membership comprises the coordinators of the six PSCAP sub-programmes, the head of the PPS, PSCAP programme coordinators from the Bureaus of Justice, Works& Urban Development, and the Revenue Authority, and the PSCAP focal person from the Women’s Affairs Bureau.

The Evaluation Team was surprised to note that the BOFED was not a member of this committee, given its importance in handling programme finances and its lead role in the EMCP, and suggests that membership should be extended to include it.

The Evaluation Team notes that the RTT does not meet on a regular basis, other than (presumably) every three months to deal with quarterly progress reports. This issue was raised in a number of interviews with the Evaluation Team, and does seem to imply a lack of regular programmatic control and communication. The Evaluation Team notes that the EY 2000 (2007/08) Participation & Performance Agreement (PPA) includes a budget item under Programme Support for monthly meetings of the RTT, and recommends that this practice is implemented. The RTT should be chaired by one of the Vice Bureau Heads in cases where the BCB Bureau Head is absent.

## Coordination with MCB, federal sub-programmes, and woredas

Coordination with the MCB was reported to be adequate, although concern was raised about delays in securing approvals for programme plans.

PSCAP sub-programme coordinators reported that coordination with and assistance from federal level PSCAP institutions varied. CSRP reported that coordination was improving, while DLDP suggested that the relationship with its federal counterpart was not particularly close, with meetings take place only twice each year. The BOFED valued the assistance from federal level in providing manuals and frameworks for adoption. Meetings on the TSRP between regional and federal Revenue Authorities take place bi-annually, where experiences are shared and progress assessed on areas of common interest (for example, the pace of automation, collection of VAT and tax harmonisation across regions).

The Evaluation Team interviewed three woredas and the Bahar Dar City Administration, and it was generally reported that there was a good working relationship with the BCB and PSCAP programme coordinators.

## Compliance with eligibility criteria by region

The ANRS has met the eligibility criteria. A Programme Performance Agreement (PPA) is negotiated annually, setting out a schedule of activities, outputs and deliverables, and budget against each sub-programme.

## Planning and resource allocation

The BCB provides central coordination and support for finalisation of annual action plans, and reported no problems with the format for production. The main problem is the mismatch between plans submitted and the eventual allocation of budgets from MOFED. This necessitates a secondary round of planning and slippage in the programme timetable. It may also lead to inflation of initial budget submissions.

## Procurement

The lack of procurement capacity and awareness of procurement procedures in the BCB was criticised in the previous Joint Supervision Mission reports. The Evaluation Team was pleased to note that some steps had been taken to rectify this, with procurement staff having undergone thorough training to increase their understanding of procedures. However, the BCB insist that many problems in procurement are also due to the length of time to obtain procurement approvals from the federal PPD, and in obtaining ‘no objection’ letters from the World Bank. The quality of goods procured under ICB was also raised as an issue, and a number of examples given where the quality of computers and photocopiers supplied was not satisfactory and did not meet specifications.

## Expenditure and financial management

The BOFED provides expenditure and financial management services for PSCAP to the BCB, and has a dedicated accountant in the bureau for this purpose.

## Monitoring and evaluation

The previous Joint Supervision Mission reports criticised the BCB for not having enough capacity in its monitoring and evaluation unit, as well as restricting its focus to the MMAs. The Evaluation Team noted that the capacity issue has been addressed, with two staff now in this section.

There is still a focus on quantitative assessment, and the Evaluation Team noted inconsistencies in progress reports (see previous section 3.7.1 on ICT). Generally, the written reports are confusing, badly presented and uneven, although to be fair, this problem is not limited to the Amhara BCB but is a feature of PSCAP generally. The BCB have reportedly conducted an outcome evaluation of PSCAP’s impact so far, and have developed a first draft. The Evaluation Team were not able to obtain a copy, but recommend that this is followed up by future supervision or review missions, since it is a potentially important source of information.

## Information, education and communication (IEC)

The BCB still lacks an IEC strategy, even though this was identified in the JSM 2006 report as an issue to be addressed. Some activities are undertaken to publicise public sector reform, including a weekly short programme on ANRS radio, but there is a lack of consistent effort. The BCB reported itself unable to develop a strategy without technical assistance. The EY 2000 (2007/08) PPA includes provision of PSCAP T-shirts and continued coverage on radio. The Evaluation Team recommends that serious efforts be made to develop a consolidated IEC strategy for the region.

## Sequencing and integration of reform initiatives

The regional PSCAP programme appears to be sequential and logical, and awareness and engagement from participating Bureaus is high. This is welcome improvement after a relatively slow start, apart from those sectors that which benefited from previous initiatives supported by other donors. Strategic planning is a feature across all Bureaus and sub-regional government structures.

# Assessment of cross-cutting issues

Most PSCAP programmes build in gender-related issues into their activities, although there are some exceptions including EMCP. Some of the performance data available is gender-disaggregated, although this mainly relates to women participation on training courses. The WAB has a member on the RTT, and comments on all PSCAP programme plans and progress reports. Generally it was felt that PSCAP is assisting in creating a suitable environment in which engagement on gender issues is improved (for example through the involvement of women’s groups in preparation of woreda development plans), but more effort was needed to genuinely mainstream plans into implementation. The WAB has little capacity to engage across all sectors, and so must rely on heads of Bureaus and sub-regional governments to deliver. The WAB is currently developing gender-mainstreaming guidelines (including sectoral activity checklists) for Bureaus. The Evaluation Team recommends that these be examined and, where suitable, be incorporated into the PSCAP programme as a measure of progress on this cross-cutting issue.

There is generally a high level of inclusion of HIV/AIDS issues across the Amhara programmes. These usually involve awareness training and discussion sessions among course participants, but are a valuable reinforcement to the government’s overall campaign. Given the potential threat to civil service capacity (for example, national figures show a very high prevalence among teachers) this commitment in PSCAP should not be relaxed.

Environmental issues generally featured very little as a cross-cutting issue in PSCAP programmes, but there are some excellent examples of woredas taking action on promoting conservation and dealing with deforestation.

# Key lessons and limitations

The Amhara PSCAP programme is performing well generally, and in JSRP and ICT in particular. In common with other regions, Amhara faces serious challenges in the following areas:

  - Shortages in and high turnover of skilled and experienced staff

  - Mismatch between initial plans and final budget allocations, leading to a further round of planning, programme slippage and under-spending.

  - Delays in procurement processes, notably relating to International Competitive Bidding (ICB) and receipt of ‘no objection’ letters from the World Bank.

  - Shortage of external technical capacity, consultancy expertise and experienced training service providers.

There are specific areas that the BCB and its implementing agencies should consider to improve its own operations: The Evaluation Team recommends that:

- Effort is put into consolidating programme information and financial data into consistent and coherent formats. In particular, progress against the MMAs should be collected into a single document and assessed at least bi-annually.

- The region continues its current exercise on outcomes evaluation on a regular basis, and continues to improve its performance in monitoring and evaluation

- If it is not already the case, then the RTT membership should be extended to include BOFED

- The RTT should meet consistently every month

- A consolidated IEC strategy for the region should be developed as soon as possible

- The gender-mainstreaming guidelines being developed by the WAB are assessed, and if suitable, incorporated into the PSCAP programme as a performance measure

- The TSRP should build a stronger relationship with the Amhara Chamber of Commerce to improve communications with business tax payers

- Consideration should be given to programme and project management training for all relevant senior managers and coordinators involved in direct delivery of PSCAP

Acronyms

3Ps		Police, Prison and Prosecution Services

ACSC		Amahra Civil Service Commission

ANRS		Amhara National Regional State

BCB		Bureau of Capacity Building

BOFED	Bureau of Finance and Economic Development

BOJ		Bureau of Justice

BPR		Business Process Re-engineering

BWUD		Bureau of Works & Urban Development

CIDA		Canadian International Development Agency

DSA		Decentralised Support Activity

EY		Ethiopian Year

HRM		Human Resource Management

IBEX		Integrated Budget & Expenditure System

ICB		International Competitive Bidding

ICT		Information & Communications Technologies

IEC		Information, Education and Communication

JSRP		Justice System Reform Programme

JSM		Joint Supervision Mission

MCB		Ministry of Capacity Building

MMA		Minimum Mandatory Activities

OAG		Office of the Auditor-General

PIP		Programme Implementation Plan

PSCAP	Public Sector Capacity Building Programme

PPA		Programme Performance Agreement

PPS		Planning & Programming Service (located within BCB)

PSIP 		Performance & Service Delivery Improvement Programme

RMI		Regional Management Institute

ROPE 		Results Oriented Performance Evaluation

RTT		Regional Technical Team

TORs		Terms of Reference

TSRP		Tax and Custom System Reform Programme

UMCBP	Urban Management Capacity Building Programme

UNDP		United Nations Development Programme

VCT		Voluntary Counselling and Testing

WAB		Women’s Affairs Bureau