Annex 12: Dire Dawa Evaluation Report

# Background

Pascal Moloi assisted by Girma Shegute conducted the Dire Dawa evaluation from 15 October to 17 October 2007.

The meetings held included:

- An overall briefing meeting addressed by Herbi Bouch, the Bureau of Capacity Building Head and attended by the PPD head and Focal persons for the Sub programmes, CSRP and ICT

- A meeting with BoFED to evaluate the TSRP and the EMCP

- A meeting with City Urban Management to discuss the UMCB programme

- Meeting with the Justice Bureau to discuss the JSRP

The beneficiaries that were visited included:

- The Police Commission;

- The Women’s Affairs Bureau;

- The Office of the Auditor General;

- The Water and Sewer Authority; and

- The Chamber of Commerce

Dire Dawa does not have woredas. A number of kebeles (at least three or more) have been amalgamated to establish at least 7 kebeles. An average sized kebele has a population of about 35000. This is about the size of a woreda in other parts of the country. Evaluation meetings and visits were carried out in kebeles 02, 06 and 07.

The team took a lot of notes from these meeting and perused a number documents submitted at the meetings and received after the meetings. Where possible and time permitting, actual inspections of premises, equipment and training sessions in progress were made and observed. Live demonstrations of systems such as the tax collection and the website were entertained. This information is used in this evaluation report.

# Overall assessment

In general the programmes in Dire Dawa seem to be making good progress.  A quick check against the assessment made on the achievement of Minimum Mandatory Activities as found by the April Joint Supervision Mission seem to be accurate. PSCAP was seen as part of ongoing capacity building efforts aimed at a broader state transformation objective. The Region is 75% urbanised and is a chartered city with a City Administration and 7 kebeles.  Only five of the six federal programmes are run in the city region.  The District Level Decentralisation Programme does not apply in the region. A total of Birr 47 million is allocated, of which, Birr 44,7 Million is allocated to the Programmes and the balance to programme support.  The Bureau Head concedes that some of the targets may not have been met, but he is happy that noticeable progress has been made.

The achievements of the programmes can be summarised as follows:

## Civil Service Reform

The Programme reported on five of the six components of the programme as follows:

- Several training programmes in change management, BPR, and good governance among others have been delivered successfully

- A BPR study has been initiated and started in all 11 bureaus and offices

- Consequently – there are more skilled managers with more tools to carry out their duties and there is a change in civil servant attitudes towards development challenges and objectives and a greater commitment to translate these objectives into reality.

## Expenditure Management and Control

  - The financial administration, regulations and directives have been enacted;

  - A new chart of accounts, a single pool system and cost centre based budget structure has been rolled out;

  - The zero base treasury system has been implemented, the 1998(EC) accounts have been closed and at the time of interview the 1999(EC) accounts were on the verge of been closed; and

  - The double entry accounting system has been implemented

## The Tax Reform Programme

### Tax Policy and Administration

There has been an overhaul of income tax law and the issuance of new laws in the region.

### Tax Payers Identification Number

TIN has been automated, and training and awareness programmes have been rolled out. It can accommodate 5000 issues in one month. An automated system was used in 1999(EC).

### Value added Tax

The Vat collection systems have been automated, and training and awareness programmes have been rolled out.

### Operational programmes systems, procedures and manuals

Capacity and HR development includes an awareness creation programme. Progress on service delivery made:

  - Main goal 1997(EC) – 43 million

  - 1998(EC) – 47 million

  - 1999(EC) – 68 million

  - Budgeted 2000(EC) – 4.2 million per month to collect 89 million (IDP target 150 million p.a. by 2003) 23 million of the current year’s target already collected.

Achieving 50 minutes turn around time for transactions has been that previously took 3 days to complete.

### Organisation and Tax payers’ Education

Taxpayers’ education has been able to change behaviour.  At the end of 1998(EC) there was a high level of non-payment.  This has changed in 1999(EC) with more taxpayers meeting their obligations.

### Customs Automation

Not reported.

### Customs Organisation and Management

Not reported.

## The Justice System Reform Programme

### Strengthen the judiciary

- Strengthening the capacity of the Judiciary through regional experience sharing tours to SNNP, Addis Ababa and Oromia.  Use the experience to review how they operate and increase efficiencies.

- Training for Judges of the Social Court – (Different qualifications – certificated, diploma and traditional exit)

- Training included teaching on amending the criminal code for public prosecutors and advocates for a week.  This training acquainted the trainees with new codes of law.

- Has seen a lot of improvement in the administration of law

- Colour coded filing system about to be implemented

  - Training has been conducted without any clear signs of improvements in the social courts yet.

  - The only significant progress recorded seems to be the roll out of video conferencing, which has increased access to justice with limited costs.

### Law revision and law reform

- Law revision and reform and the drafting of new laws

- Reviewed a number of legal instrument of the system

- Identified some problems with some instruments in the region. This includes filling the legislative gaps, updating legislation, clearing ambiguities in the law, compiling and distributing the law in administrative law and disseminating these to the community.

### Law enforcement organisational capacity enhancement

- Most of the achievements have been in the area of training, Policemen in the area of legislation, human right and criminal law procedures of the country

- Some achievements can be traced by the high demand for more training, the decreased number of complaints about police efficiency from the public

- Improvements in the undertaking of investigations has improved

- Human rights – Has helped in changing the tactics and approaches they use to prevent crime. Fewer cases of police harassment and brutality reported

- Short term training of HR and Management, provides for 30 police officials working at different stations on office management – This has improved the way the offices are managed.  The opinions of the beneficiaries have been collected randomly through questionnaires and sometimes through information volunteered.  The amount of escalations from kebeles is a good indicator

- Institutional capacity building for the police included procurement training and roll out of computer and accessories.  The service has improved due to the availability of this new technology

- Training 120 police members on community policing concluded.

### Legislative organ

  - Remains a source of worry.  It is noted that it was a late starter with no funding in the first year. It is still difficult to trace notable improvements and performance remains below expectations.

  - There is good progress in the Bulk Train programme which appears to have increased the amount of awareness among the 10 000 participants. Anecdotal evidence suggests that in some kebeles there has been increased demand to fire so called corrupt officials as a result of increased awareness of rights and obligations.

## UMCB

The Urban Management Capacity Building programme although recording the highest level of meeting Regional MMAs is not easy to track in terms of the PIP objective and KPIs.  The reasons seem to be because of the overlap between DSA funded programmes, the regular budget funding and PSCAP.  The following was reported

### Regional urban management policy

- Seven Rules and procedures guidelines have been developed

- The urban land release legislation and urban proclamation are in place and have been applied

### Deepening the process of decentralisation

- Computers are been disseminated to kebeles as an attempt to deepen decentralisation and strengthen local authority access to services.

### Local government restructuring and capacity building

- The Regional IDP has been prepared, approved and disseminated.

- Land Management programme:

- Cadastral system developed which will contribute to fast tracking land release programmes

- Land released through negotiation, lottery, Auction and give-aways.

- Programme stalled by land invasions and existing informal settlement.

- Manages a programme to regularise and formalise some of the settlements

- The cadastral system for full computerisation of land and building information which will assist in the land management processes and revenue collection is in part used as a PSCAP programme

- Deals with Housing Backlogs

- 36000 houses to be provided as targeted

- 12 000 to be provided by the City administration and the balance by Housing Corporative

## ICT

### Human resource development

- Frontline capacity and general human resource is steadily on the increase.

- The ICT training centre is established and is functioning.  (The Evaluation team witnessed training examination sessions in progress at the time of the visits)

### Public service delivery and good governance

The programme has contributed to putting in technology in the Video conferencing centre, which is now used by the Administration and the general Public.  The centre hosts the video connected court system that has reduced the costs of access to justice

### Applications for sector development

The ICT programme is assisting in developing key requirements like GIS software and Land Use Management systems for the Land Authority.  There is ongoing installation of software and hardware

### Community based information systems and services

- The regional data centre is operating well (although the system was down at the time of inspection.)

- The regional website and portal is being completed and will be tested soon

- There is a general increase in public access to information using IT as a medium

# Assessment of implementation of each sub-programme

## Achievement of planned program activities

### The Civil Service Reform Programme

The programme has rolled out a good measure of its work per plan.  The is a lot of evidence supported by all the beneficiaries met by the team the Change Management and Leadership development Programme and the BPR programme were well provided and met the needs of all the participants.

The Auditor Generals office was critical on the roll out. While appreciating the need and relevance of the Change Management and Leadership course, the AG was unhappy with the way this office seems to have been left out generally by the Civil Reform effort.

### Tax Systems Reform Programme

The programme has been able to meet its planned activities to a great degree.

### Urban Management Capacity Programme

The Urban Management Programme seems to have achieved the meeting of the initial Mandatory Activities.  Beyond this point it is difficult to measure beyond the land development work being done.  All the kebeles interviewed were not aware of work done by the programme in their areas.  This may possibly mean that beyond the initial policy work and the proclamations developed, and the manuals produced, there has not been much interaction with kebeles. The kebeles themselves seem not to be aware of who the service providers are and tend to think that the computers received was part of the ICT programme.

### The Justice System Reform Programme

The programme after a slow start seems to have made good progress with respect to the training on Human Rights and legal awareness project.

### Information Communication Technology

The key programme included converting manual and traditional working environments to automation as far as possible.  The training mainly included Windows 2003.  The main beneficiaries are civil servants, women (a priority), teachers and Senior or high-level officials (including Cabinet Members) in kebeles

## Impact of these activities on institutional, organisational and individual capacities;

### The Civil Service Reform Programme

The Chamber of Commerce concedes that the general change in work environment and the attitude of government employees is indeed changing.  The police commission’s representatives remarked that as a result of the training received through this programme, the general attitude of the public towards the police is changing.  This is evidenced by reduced complaints directed towards the police on radio stations as compared to the past.  A sample of the Bureaus, Beneficiaries and kebeles that the team met suggests that the BPR effort is bearing fruit and should be encouraged.  It has been rolled out in at least one kebele.  Good reviews of the BPR process were also received from the Water Sewer Authority, kebele 6 and the Women’s Affairs Bureau.

Overall, service delivery in some institution like Dil Chora hospital and DD Water and Sewerage Authority has improved significantly. For example: The time required for the installation of HH lines was reduced to a day from 25 days on average. The institution also as part of the BPR process avails one stop shopping to provide its services. Similarly kebele 06 and Dil Chora Hospital has registered a success

Both the Water and Sewerage Authority and the AG raised a preference to less general training but to more technical and sector specific support.

The Chamber of Commerce while appreciating the need for the state to jerk its house up, felt that society would benefit more if there was a broader capacitating of key sectors of the region to ensure sustainable development and economic growth.

### Tax Systems Reform Programme

There has been a change of behaviour.  They are able to show how the tax money is used for developmental purposes.  The programme produced brochures.  There has been a big increase in the number of taxpayers from 1998(EC) to 1999(EC) (EC).  The change in employee and trained collectors behaviour is noticeable.  They have been trained to understand the use of taxes and as a result taxpayers get quicker service. The Chamber of commerce has confirmed this. The Chamber however warned that the underdeveloped privet sector and unskilled businessmen if not assisted will fail to comply with the new requirements.  The responsibility of keeping records and books of accounts in the private sector will require trained accountants.

On the Finance and Expenditure side the Bureau has been able to achieve a lot with little PSCAP funding.  Using mostly DSA money, the region has established multi year planning and budget reform in 1998(EC). They have completed the accounting reform and implemented, trained Internal Auditors. Zero balance cash management was introduced in September with the Bank of Ethiopia. All the beneficiaries interviewed were satisfied with the progress made and felt that it had improved their organisations and individuals.  Two of the three kebeles interviewed are familiar with the reforms and are implementing double entry accounting and zero base cash management systems

### Urban Management Capacity Programme

All the kebeles interviewed are familiar with local government legislation and understand their relative responsibilities with regard to the law.  There was however a mixed response to a checklist of the basis competencies between the three. One kebele scored full marks, the other was in between and the third lacked capacity completely. All seem to have been recipients of the same establishment and decentralisation process. The one probable explanation is the turnover in leadership and the “go-getter” tendency or lack of it displayed

Land Management seems to be making good strides with good progress made with the GIS project, the regularisation and management of informal settlements and the development of the cadastral system (which will contribute to fast tracking land release programmes). The team was able to observe work in the record automation centre were files were scanned into the new system. Land is being released through negotiation, lottery, and auction and give-aways. The land release programme has been stalled by land invasions and existing informal settlement.

A housing target of 36000 houses to be provided has been set.  12 000 of the houses are to be provided by the City administration and the balance by Housing Corporative.

### The Justice System Reform Programme

The police commission and the Women’s Affairs Bureau were particularly happy wit in the training received by women. The Police appreciated the value of teaching human right to law enforcers who in the past were culprits of violating rights. Some of the anecdotal evidence shared on impact was the fact that the 10000 mass training in some villages, which has caused an increased demand for alleged corrupt officials to be fired.

### Information Communication Technology

- Raised awareness of PSCAP by increasing access to justice records. Used IT and Video conferencing and general government information.

- Established a regional ICT centre which included a regional website and portal, and a data centre.  Conducted community needs assessment with a view of establishing a community based information management system. Ran this through community based workshops

## Impact of increased capacity vis-à-vis actual improvements in service delivery

### The Civil Service Reform Programme

The participants and beneficiaries agree that the Civil Service reform interventions have made a difference and have increased the capacity to deliver. There is however reservations about follow up and the ability to sustain the capacity developed. The higher expectations laid by the initial efforts from the public may not be followed through if procurement of further training and material will not be coming through. The BPR exercise requires qualified facilitators and when rolled out, some key turn around targets will require a bigger roll out of computers and equipment. The Police Commission stopped the BPR process because of the failure to attract qualified facilitators. The kebele has made good progress in mapping processes and creating two one stop centres. It has even gone to the extent of posting its commitment in the turn around times and processes on large boards on its premises for the public to hold it accountable. This is premised on the assumption that computers will be procured and that there will be an uninterrupted availability of quality staff.

### Tax Systems Reform Programme

The benefits of the TSRP and Expenditure Management are easy to measure. The collections have increased over the years as follows:

- Achieving 50 minutes turn around times for transaction that previously took 3 days to complete

- More transparency and accountability on the tax process

- Can accommodate 5000 in one month in 1999(EC) having used an automated system

- 1997(EC) – 43 million

- 1998(EC) – 47 million

- 1999(EC) – 68 million

- Budgeted 2000(EC) – 4.2 million per month to collect 89 million (IDP target 150 million pa by 2003) 23 million of the current years target already collected.  (NB. Property Taxes will be introduced for the first time this year)

### Urban Management Capacity Programme

The programme is hampered by highs levels of staff turnover at all levels. There are 10 000 urban informal settlements hindering the formal development of the city There is a plan, through consultation, to release and regularise these settlements. The big advantage is the migration patterns that seem to have slowed down over the last years.

All the kebeles consulted outlined a planning process that starts with village committees and is escalated to a level made up of representation from a number of villages within a Kebele.  There is a fair level of capacity to work through submissions at this level into a set of programmes that get submitted to the Kebele cabinet before they are submitted to the regional Local Development Agency.  The agency received such submissions from all the kebeles and used these as a basis for consolidating a regional plan. The plan is ultimately presented to BoFED for reworking and submission to the regional Cabinet.  The submissions from the Authorities and Bureaus are also included as the regional Plan.  The Plan through this Process has been able to produce an integrated development Plan (IDP)

The allocation of resources against these submissions and the ultimate approved plan is viewed as not transparent and accountable by a number of interviewees for a number of reasons.

The budget allocation methodology is not well understood by the kebeles.  The consultative and participatory process, it seems created expectations from kebele 6 that it would get a bigger slice of the allocation.  The kebele assumes population and consistently high in-migration factors to be key determinants.

### Justice System Reform Programme

The biggest service noticeable is the ability to bring procedures at social court to completion much quicker than it was the case before. With the collaboration between Justice and ICT, the video conferencing facility established has helped with the management of justice without having to fly in capacity. The training on the application of Sheri law in all Social courts has assisted.

### Information Communication Technology

There is a growing number of working environments that are now computer based. This has had a direct bearing on the reduction of paper, has improved record keeping and has helped with communication.  PSCAP coordination has benefited directly.

# Assessment of programme management and support

## Coordination with MCB, federal sub-programmes, and woredas;

Horizontal coordination is generally viewed as problematic. Without exception all the regional programmes expressed an unacceptable level of interaction with their Federal counterparts.  The fact that coordination of PSCAP is funnelled through BCB and MCB was found limiting to proper guidelines, advise and support of the regional effort. There is however evidence that outside PSCAP and what is described as regular work there is a level of interaction between regional Bureaus and their Federal counterparts.  There was no evidence at all of a cascading of coordination to kebeles

## Institutional arrangements for PSCAP in region, and effectiveness of coordination within the region;

The Regional Task Team (RTT) appears to be performing well in the City Administration. Regular meetings are been held.  It was a bit concerning that on request, attendance registers, and notes from these meetings were not available.  Through the assistance of the ICT programmes, it seems that there is relatively good coordination of information between programmes.  Most Focal Point personnel alluded to collaboration across Planning and Budgeting through the RTT.

There is a meeting of Bureau Heads in the region that is also used to provide coordination over PSCAP programmes in the region. The participants include at least BCB, BoFED and Urban Management.

## Compliance with eligibility criteria by region;

| Criteria | Comment |
| --- | --- |
| - Submission of signed “Participation and Performance Agreement” by the relevant minister responsible for federal subprogram or relevant cabinet member for region; | - The submissions have been made |
| - Establishment of appropriate governance and implementation arrangements; | - The RTT and Programme Heads are established and functioning |
| - Completion of relevant capacity assessments across all participating sectors and levels of participating institutions, especially in the case of woreda and municipal strengthening; | - Responses from Police commission and Kebele 06 suggested that needs analysis were carried out. Reservations were made by the Auditor General and Water Authority about training been too general and not been asked about specialised needs they may have. |
| - Timely submission of endorsed costed medium-term rolling plans, as well as technically sound, feasible annual implementation/procurement plans in line with financial calendar; | - Submissions seem to be made. The evaluation team cannot comment on whether these are made on time. |
| - Explicit provision for evaluation of annual performance including dissemination to the public of such evaluations, satisfaction scorecards, etc, as part of the consultative planning process. | - Not much evidence shown. The Chamber of commerce seem not to be informed about progress nor is it involved in the dissemination. The evaluation seems very ad hoc. Kebele 06 idea of publishing service preconditions, standards and turn around time commitment and placing a comment box under these posters is commendable |

## Planning and resource allocation

The RTT appears to be used effectively as a planning platform across programmes for PSCAP.  The AG expectations were raised when requested to prepare TORs against some of the plans included in its initial proposals. There appears to be a limited communication back to the kebeles once the plans are submitted.  The Division between PSCAP programmes requests and “regular Regional Budget processes is blurred.  This blurring of allocations and decision-making puts PCSAP at risk of failing to accurately account for its expenditure and impact against its Key Performance Indicators.

## Sequencing and integration of reform initiatives;

There were no major concerns raised against sequencing. It appears that most of the PSCAP efforts and inputs to date dealt with what most respondents described as addressing the basics, basics requirements for understanding change management and governance, basic understanding of human rights and the law, foundation appreciation of local government legislation and policy making, key and critical intervention to basic accounting and cash management and introduction to the office windows environment.  These initial efforts among others have been well accepted with a qualification that if no appropriate follow up is made it may be deemed as unsustainable.

The integration of efforts across programmes is evident, but appears ad hoc.  There is evidence of  a need by Urban Management to facilitate the settlement regularisation programme to allow tax reform to speed up the collection of property taxes.  Property taxes form a significant volume for meeting the IDP collection target.  The other example is the link between the cabinet determination for a 30% requirement of women participation in all training efforts and the 2% of working capital to be contributed towards HIV and AIDS programmes.  It has not been possible to track how this is enforced and reported.  Without a clear integration framework presented it is difficult to pin down evidence of integration

## Financial management

Most participants have been able to give clear statements of what was requested, what was allocated and what was actually given and spent.  The overall impression is that with the assistance of the BoFED roll out of the double entry system and the zero balance cash management programmes, the accounting and financial management environment has vastly improved.  The problem still remains for some programmes to account for PSCAP spend against the objectives and to separate this from other sources of resourcing either from other donors and/ or regular budgets.  The apparent absence of a PSCAP audit remains a threat and a risk.

## Procurement

All programmes and beneficiaries complained about procurement.  There is a chorus of complaints about procurement delays and the lack of transparency and accountability for PSCAP procurement processes.

The issues highlighted included:

- A failure to respond to TORs presented against requests made by PSCAP

- Under allocations against requests,

- The onerous process of reformulation and resubmission of requests

- The onerous MCB and World Bank requirements

- The absence of a known data base of preferred service providers

- The alleged ring fencing of functions by consultants even when there is internal capacity to perform such tasks

- Over centralisation of decision-making.

- Divide between regular procurement and PSCAP procurement processes.

## Monitoring and evaluation

There are no monitoring and evaluation systems in place.  The only mention of developing evaluation and monitoring was through ITC.  ICT intends developing a system in both Amharic and English. The relevance and quality of the system against KPI and impact is not known.

PSCAP programmes are well visible form the point of view of programmes and beneficiaries. Few, such as the Tax Systems reform programme have been able to present a before and after picture that is measurable and quantifiable in real and tangible terms.  PSCAP in the province is unable to measure impact and show a clear beginning of a set of measurements that could be used as future baselines.

## Information, education and communication

Most beneficiary respondents displayed a good knowledge and basic understanding of PSCAP and its objectives.  One extreme negative response came from a kebele representative.  The representative was not sure if PSCAP is a government programme or an NGO.  The biggest problem even from Focal Point PSCAP operatives is transparency from a programme management point of view.  There is also a gap in communicating the Programme to the general public.  Tax reform claim that it has a public communication approach that shows the taxpayers how their money contributes to the development of the region should be probed as a case study.

## Assessment of cross-cutting issues – HIV / AIDS, gender and environment

There is definitely no acceptable evidence of performance beyond the 30% women participation requirement and the 2% working capital allocation to HIV and AIDS efforts.  The constant request for mainstreaming guidelines should be serviced.

# Assessment of programme outcomes

## Enhanced predictability of financial resource flows in-year and across years

The region appears to be doing well in maintaining close monitoring and accounting of its budget processes. There is a gap between what is approved at federal level and what is released to the region. The Table below illustrates the year by year budget allocation and spending since 1997/ 98 to 1999/00(EC).

Table 1.Financial resource flows, 1997-200

| Year | Approved | Released | Spent |
| --- | --- | --- | --- |
| 1997/98 | 2,500 000 | 375 000 | 178 880 |
| 1998/99 | 7,615 000 | 2.920 000 | 1,549 410 |
| 1999/00 | 5,887 370 | 5,964 414 | 5,066 771 |
| Total | 16,002 370 | 9,259 414 | 6,742 956 |

## Greater inclusiveness and transparency of planning and prioritisation processes

The planning processes and the involvement of the kebeles in the putting together of their priorities up for ultimate consideration by the Cabinet and inclusion in the budget are commendable.  There was however no indication of the involvement of the public in the consideration of the overall city and/or region budget.  The City has put together an IDP.  The discussion with the Chamber of Commerce suggested very little, if any, involvement of the public in its formulation.

## Improved quality and efficiency of government operations in priority sectors

The process was well elaborated by the Water and Services sector and the Kebele 06.  It appears that the key sectors do have a chance to input into the process.  Their inputs seem to be well informed by community needs gathered through the kebele planning and consultation processes. The evaluation team was not able to check the details around cost efficiencies and responsiveness.  The Water Authority did however share some of the experiences with how efficiencies have been increased through changing work methods, materials and customer relation’s processes.  This they attribute to some of the benefits from the BPR processes.  They have cut out call out costs as an example and this has increased the amount of calls to the authority for repairs and thus has helped service the maintenance of the network.

## Improved incentive environment for public servants

The Evaluation team has not been able to ascertain this.  Although there is evidence of attempts to establish ROPE.  The general feeling expressed by top management involved in the interviews seems to display dissatisfaction with this aspect.

## Enhanced revenue performance and fiscal autonomy

As evidenced in the Tax sections above, there is very obvious and marked improvement in the regions’ revenue collections ability.  The same was not too clear from the two other kebeles outside Kebele 06.  The actual transfer figures between the region and kebele were also not clear.

## Improved transparency and accountability

The team has not picked up any feeling from the AG and the Chamber of commerce that there may be widespread acts of corruption.  The one area that still remains less transparent seems to be the decision or perceived decision with respect to land lease management and administration.

# Key issues arising from assessment, and obstacles to implementation of PSCAP

The Planning and Programme Management issues need to be resolved as a matter of urgency.  A lot of energy and effort is expended by key programme operatives on quibbling for resources at the expense of focusing on the key KPIs and objectives. The main culprits are procurement, the lack of transparency and the absence of a comprehensive measurement, monitoring and evaluation system.

PSCAP has to be embedded into regular government as soon as feasible.  The approach may be to decentralise and decongest to where there is obvious capacity to coordinate.

There is a real possibility to elevate PSCAP as a medium for developing a broader society capacity building programme that could benefit every key stakeholder critical for the social, and economic upliftment of the Dire Dawa region.

# Lessons learnt and recommendations for implementation

- The Civil Service reform Programme - Dire Dawa need to sustain the capacity developed. Procurement of further training and material is critical. The BPR exercises require qualified facilitators when rolled out, and some key turn around targets will require a bigger roll out of computers and equipment.

- Tax Systems Reform Programme – There is a need to be more transparent and accountable on revenue collection to the public in general and tax payers in particular.

- Urban Management Capacity Programme – The programme has done well in building decentralised institutions.  The capacity seems varied at kebele (NB the City is divided into large kebeles) levels to exercise the mandates and responsibilities assigned.  A lot still needs to be invested in building the capacity of the kebeles to carry out land management, housing and planning functions.  The high staff turn over has to be addressed.

- Coordination with MCB and federal sub-programmes have to be improved.  The City Administration has expressed a desire for more interaction with their Federal counterparts.  The fact that coordination of PSCAP is funnelled through BCB and MCB was found limiting to proper guidelines, advise and support of the regional effort.  More capacity to coordinate PSCAP programmes has to be built at kebele levels.

- The RTT while appearing to be well functioning still appears very loose in the way is approaches its business.  There has to be a record of meetings and decisions taken at RTT meetings. The RTT as a strategic planning and coordinating centre has to be improved. The Bureau Heads steering committee should be retained and supported. The communication gaps that seem to exist between kebeles and the Bureaus on the approval processes need to be closed.

- The “Blurred” allocation and accounting between the PSCAP budget and the regular budget needs to be ironed out. This will result in continued negative reports from the AG about the state of the City’s PSCAP accounts. This matter needs serious attention

- Sequencing and integration of reform initiatives – While there are no intra-programme sequencing issues raised, there is scope to improve on integration efforts across programmes.

- Financial management - The Problem still remains for some programmes to account for PSCAP spend against the objectives and separate from other sources of resourcing either from other donor’s and/ or regular budgets.  The apparent absence of a PSCAP audit remains a threat and a risk.

- The issues raised concerning procurement including a failure to respond to TOR presented against requests made by PSCAP; under allocations against requests, the onerous process of reformulation and resubmission of requests, the onerous MCB and World Bank requirements, the absence of a known data base of preferred service providers, the alleged ring fencing of functions by consultants even when there is internal capacity to perform such tasks; over centralisation of decision-making and divide between regular procurement and PSCAP procurement processes.

- There has to be an effort initiated to establish proper monitoring and evaluation systems.  The attempts by the ICT office should be encouraged.  The evaluation team would advise that the ICT could be key in developing the systems.  We would caution that the Evaluation and monitoring function not be developed as an ICT programme but that a proper office supported but ICT be considered.

- General communication to the public is poor and needs to be jerked up. The City should invest more in IEC activities.

- Assessment of crosscutting issues – HIV / AIDS, gender and environment.  There is no acceptable evidence of performance beyond the 30% women participation requirement and the 2% working capital allocation to HIV and AIDS efforts.  The constant request for mainstreaming guidelines should be serviced.