Annexure 7: District Level Decentralisation sub-programme report

# Background

Rob Mellors and Habtu Gebrehiwot explored the progress and impacts of the DLDP over a period from 10th to 31st October 2007. Two meetings were held with Ato Worku Yehualeshet, the Director of Federal DLDP. Meetings were also held with the Ministry of Federal Affairs, DLDP programme heads in Oromia, SNNP and Gambella Regions. Evaluative visits were made to 8 woredas. Inputs were received from other members of the evaluation team who visited all the other regions and some 14 woredas.   A wide range of documents were examined including all the studies, guidelines, packages and manuals produced by DLDP, the PBS and Local Investment Grant concept documents and mission aid memoirs.

We would like to thank Ato Worku for his time, generosity of spirit and interest in assisting us in this work plus all other interviewees who also provided much help.

# Overall assessment

## Progress with decentralisation

The objective of DLDP is to deepen the devolution of power to lower tiers of Regional Government, to institutionalise decision making processes at the grassroots level with a view to enhance local participation, to promote good governance and to improve decentralised service delivery.  DLDP presently has 8 components at federal level: Manning and Training, Grassroots Participation, Minimum Service Standards and Reporting mechanism, Fiscal Transfer and Own Revenue Enhancement, Woreda Planning System and Financial Control, Woreda Good Governance Package, Institutional and Organisational Arrangement, Programme Development.

After a slow start, DLDP has made good progress across most regions in terms of fulfilling its higher level objectives. Legal Frameworks (produced in 3 regions but only proclaimed so far in 1) are laying the basis for decentralised decision-making and have defined functions for tiers of local governments. Major progress has been made in decentralising budgets, transferring block grants and in establishing the physical and human resource base of Woredas. Vast amounts of training have been conducted for regional staff, woreda officials and councillors, kebele cabinets, teachers, agricultural DAs and peoples’ representatives in general. A significant proportion of woredas have now become credible organisations which are increasingly providing improved services to their constituents. Similarly attitudes, behaviours, and service delivery systems have become more transparent, participative and accountable and in line with the principles of good governance.  The scope of DLDP has also been increased by the introduction and promotion of MCB’s Woreda and Kebele Good Governance Package. This is now receiving high priority and is responsible for vast amounts of awareness training.

Much remains to be done however. Having established this sound base in a significant proportion of woredas, a major challenge for federal and regional governments is how to extend and sustain the capacity already developed and to allow woredas and kebeles to exercise real decision making and choices.  Devolution involves woredas having scope to set their own priorities, to make choices over allocating their resources between sectors, between salary, operational and maintenance costs and between different kebeles. At the present time the opportunity for woredas to make such choices is quite limited. Their structures are set by the Regions such that most of their budgets are consumed by salary costs. The lack of capital for new investment undermines the planning and priority setting processes. The lack of resources for maintenance means that their precious equipment and vehicles fall into disrepair.

Possible solutions are beginning to emerge:  BPR exercises may facilitate improved utilisation of manpower and reduce the ever growing salary bill. Increased levels of local revenue combined with newly proposed PBS and LIGs will provide resources for improved service delivery and capital investment. Enhanced capacity and participation at kebele levels will increase the efficiency of utilisation of capital and service funding.

## Federal DLDP

The Federal DLD Programme has made significant progress against its MMAs and programme components over the past year. After a very slow start a plethora of studies and manuals have been drafted and sent out to the regions.

The March 2007 JSM highlighted a number of challenges for DLDP at federal level and made recommendations for:

- A Review of Training undertaken to date,

- Delivery of prototypes to the regions,

- Strengthening co-ordination between federal and regional DLDP offices so as to stimulate experience sharing,

- Enhancing the skills of its own experts and employment of additional staff to manage DLDP at the federal level including the recruitment of a DLDP Advisor,

- Strengthening and using the on going Woreda City Benchmarking Survey and public opinion surveys as a means of determining PSCAP impact.

In response DLDP has made significant progress against item (b) by delivering numerous manuals and prototypes. It has also set up a quarterly forum for Regional and Federal DLDPs to share experience – now about to stage its second meeting. The other recommendations are not yet acted upon. The evaluation team has reservations about recommendation (e), preferring to see regional institutionalisation of the survey rather than a continuation of the present donor driven exercise.

# Assessment of implementation of main components

Most of the components of DLDP at federal level fall within the category of ‘Provision of Guidelines, packages, prototypes and manuals’. The following subsections summarise progress in these components. Within the last two years a new component has been added which is receiving priority attention – The Woreda Good Governance Package. This latest addition to the brief of DLDP creates opportunities to further refine the long term vision and policy for decentralisation in the country and to enhance capacity building at woreda and kebele level. At the same time it presents challenges to DLDP and MCB to ensure that the political priorities of the moment build on existing local government systems and do not create parallel processes which may undermine the fragile and slowly developing local government scenario.

## Manning and training

Using the consultancies budget, two Human Resource Studies have been conducted - one for the Afar, Somali, Benishangul Gumuz and Gambella Regions and the other for Amhara, Oromia, SNNPRS and Tigray.  Complementary Training Needs Assessments have been conducted alongside each study. Several regions are now also producing their own HR and training needs assessments.

These studies are useful to give an overall feel of the staffing and training-need status of woredas and for identifying key HR issues.  Frankly, however, in terms of planning detailed training responses, the situation on staff turnover is so fluid that the studies will rapidly become out of date. An evaluation of the quality of training provided for woredas and kebeles is planned for the current year.

## Grassroots participation

Despite a number of problems over TOR preparation and hiring of consultants, the following outputs have been achieved.

Manuals have been produced as follows:

- A system for the participation of local households and women in local councils,

- A Grass root participation Framework Manual for dominantly livestock farming regions,

- A Grass root Participation Manual for settled agricultural regions,

- A system for participation of Membership based Civil Societies at Rural Kebele.

Further manuals are planned on:

- Developing systems for consultation and access to information to civil societies at woreda and kebele levels,

- Developing systems for the Internal Governance of CSOs,

- A Comprehensive Kebele Capacity Building Manual.

The manuals are being sent to Regions who will then need the capacity to rationalise and simplify them and synthesise short clear and consistent guidelines which should enable woredas, kebeles and communities to participate according to their own will. DLDP is also trying to develop a methodology on public opinion surveys but is struggling with this exercise and is trying to hire a consultant.

## Minimum service standards and reporting mechanism

In conjunction with SNNP Region and DFID, a study on service standards and local government monitoring systems has been conducted by consultants. A prototype manual has been produced laying out suggested standards for service provision in agriculture, education, health, roads and water. The Manual also sets benchmarks for the generic functions of woredas e.g. administration, planning, budgeting, good governance etc. and proposes an institutionalised approach to monitoring progress against these standards. The Regions need to ensure that this Manual is consistent with their planning guidelines and their legal frameworks. Two regions have so far taken up the MSS Manual approach. Other regions are in need of facilitation or are hiring their own consultants.  The study and manual could provide a basis for institutionalising the Woreda City Benchmarking Survey at regional level.

## Fiscal transfer mechanism and revenue mobilisation capacity

A thorough and detailed study of Region Woreda Model Fiscal Transfer Formulae was undertaken by a consultant in 2007. This is a comprehensive compendium and an analysis of all transfer models and amounts in all the rural regions of the country.  The Study is complemented by two clearly written manuals (one for the less developed regions and one for the developing regions) each manual proposing two options for woreda grant formulae.

## Woreda planning system and financial control

A study and a planning manual have been produced by consultants. The Manual is a very useful resource document describing many processes and tools for planning and budgeting. It also provides standard designs and bills of quantity for basic woreda infrastructure. The Regions will need to adapt this resource manual into a short clear guideline for woredas which fits their chosen planning and budgeting system and is consistent with the regional Legal Framework and Minimum Service Standards manual.

This Manual is cited as an important operational guideline for the forthcoming Local Investment Grant. In this regard it will be reviewed at a special workshop involving government and donors. One would anticipate further work in this regard to derive a detailed operational manual from this document.

## Woreda Good Governance Package

MCB produced The Woreda Good Governance Package in January 2006 in response to feedback from the public, civil servants and the lower level leadership of woredas and kebeles.  The feedback suggested governance problems and serious limitations at the level of policy implementation in woredas. The package attempts to identify and categorize the problems and their causes and make recommendations for solutions. It enunciates 8 clear principles of good governance and suggests that the best way to promote these is through practical approaches of demonstration and constant participation.  The principles are:

- Increasing participation

- Promoting consensus and cohesion,

- Increasing the responsiveness of Woredas

- Transparent governance,

- Accountable Government

- Fair, equitable and inclusive government,

- Promotion and adherence to the rule of law,

- Efficiency, effectiveness and value for money in government operations and service delivery.

- For each principle, detailed actions are recommended involving new structures, systems and activities.

Responsibility for implementation of the Woreda Good Governance Package has been ascribed to DLDP and has high priority. In this context DLDP has:

- Promoted massive training programmes on the package throughout most of the regions;

- Started to prepare additional laws and guidelines to complement the package;

- Started to prepare over 20 special Kebele guidelines along with 12 formats on such issues as complaints, incentives etc.;

- Established 3 Inspection Teams with members from the regions and the federal government to inspect woredas and kebeles at the rate of 6 woredas and 36 kebeles per month;

- Obtained no objection to carry out translation of the package into different languages;

- Prepared and introduced of manuals on kebele inspection and woreda plan supervision. This has been introduced in 6 regions;

- Developed a methodology for implementation of public response surveys. This is under preparation;

- Made plans for the review of criteria for model villages.  Yet to be done.

## Institutional and organisational arrangement

Under this component, DLDP has produced:

- Federal Prototype Local Government Policy;

- Regional prototype local government policy (included with the above); and

- Prototype Legal Framework for Regional Local Governments.

These documents were produced following a workshop in March 2006 attended by all regions. Initial work especially by Tigray was used to inform the content of the legal framework prototype. Most regions have either adapted these prototypes or are in the process of doing so.  DLDP has not however promoted discussion of the Federal Policy document amongst key political and civil service stakeholders. This is important in producing a coherent overall vision for local government.

DLDP produced standardised woreda organisational structures in 2002. These have been adapted and changed by regions at frequent intervals over subsequent years often creating frustration and anxiety amongst employees.  DLDP is currently conducting a review and developing proposals for new local government organisational structures, however the final structures of woredas should depend on BPR activities which are being carried out sectorally. It is also attempting to hire a consultant to refine the legislative framework and functional assignments of woredas. It has published an interesting Study on the Effectiveness of Rural Woreda Public Bodies Organisational Structure (Part 1).

## Program development

This component mostly seems to relate to the procurement of equipment for the DLDP Office. Despite placing orders some time ago through PPD, no equipment has yet been delivered.

In general this component seems a little unclear. Its indicators relate to strategy documents, benchmarking and training measures all of which are covered by other components.

# Programme management and support

Unlike several other PSCAP sub-programmes, DLDP formed in 2001, only really achieved momentum under PSCAP. As a federal agency promoting decentralisation, its role is somewhat difficult as it is one step removed from the regions who are the key players in promoting, regulating and supporting the development of local government in their respective areas.

## Coordination with MCB, other sub-programmes and the regions;

Co-ordination has not been DLDP’s strong point. It feels there is a lack of support from PPD regarding planning, budgeting and procurement issues.  It does not have strong links with other federal sub-programmes.  In terms of common interest, there should be close links with the Ministry of Federal Affairs who are responsible for the facilitation of development in the 4 less developed regions. According to MFA, DLDP has made some contact in this regard but much more co-operation and joint enterprise is necessary. MFA on the whole feels marginalised by MCB and the PPD.

DLDP has not been receiving regional DLDP progress reports which seem to get stuck in PPD and in general it has weak operational linkages with the regions. Some of the regions see federal DLDP simply as a purveyor of manuals and documents rather than a co-ordinator or facilitator. Very recently DLDP has responded to this situation by deciding to hold quarterly review meetings involving all the regions. This is an encouraging change.

## Institutional arrangements for PSCAP

Federal DLDP is located in Ministry of Capacity Building and now reports directly to the Minister Ato Tafara. In earlier years it reported through a Minister of State. It has a Director plus 6 graduate experts and 2 support staff. For several years it has been dogged by staff shortages, high staff turnover and inexperienced personnel.  This situation appears to be improving. From the start of PSCAP, there was provision for the appointment of a special advisor; however, this has so far not been taken up although it remains in the plan.

## Compliance with eligibility criteria

DLDP has complied with eligibility criteria for PSCAP funding requirements and has prepared and signed the necessary participation agreements.

## Planning and resource allocation

Despite finding the PSCAP planning processes frustrating and time consuming federal DLDP has improved the quality of its plans and successfully prepared its 2007-8 Action Plan by early March 2007.

## Sequencing and integration of reform activities

DLDP has not followed any specific sequence in the provision of its guidelines. Rather this has been dictated by the availability of consultants and the vagaries of the procurement system.

## Financial management

As a sub-programme within MCB, DLDP reported no significant problems with the PSCAP financial arrangements, other than those related to the overall delays in disbursements which are beyond its control.

Financially, DLDP at federal level is a low spender of PSCAP resources as illustrated by the following table. Its budget for the first 3 years of PSCAP was less than 2% of the federal PSACP budget.

| Eth Birr | 1997 EFY | 1998 EFY | 1999 EFY | 2000 EFY |
| --- | --- | --- | --- | --- |
| Budget | 2,007,700 | 3,127,960 | 2,171,530 | 6,813,100 |
| Actual Expenditure | 155,151 | 774,588 |  |  |
| % | 7.7% | 24.8% |  |  |

At regional level however the DLDP programmes are the largest spenders as they are funding the mass training programmes of the Woreda Good Governance Package.

## Procurement

DLDP has struggled to hire appropriate consultants during the early stages of PSCAP. This situation is now improving and several contracts have been awarded in the last year. In terms of goods and equipment, it expresses a great deal of frustration as its orders for basic computers and office equipment have remained stuck in PPD’s bulked up backlog.

## Monitoring and evaluation

At the present time DLDP has no institutionalised monitoring and evaluation system, however it has now recognised the need to undertake regular visits to the regions and has set up two teams for this following its own BPR exercise. Federal DLDP appears to be peripheral to the PSCAP quarterly reporting channels from the regional DLDPs to the PPD in MCB. It has however initiated and been involved in ad hoc evaluations of decentralisation conducted with DFID support. It has also commented on and taken interest in the Woreda Benchmarking Survey run through the Joint Government Donor Working Group on PSCAP although it has no wish to take over responsibility for this exercise.  The current initiative involving the training and deployment of ‘woreda inspection teams’ as part of the implementation of the Woreda Good Governance Package could also be regarded as part fulfilment of its evaluation brief.

## Information, education and communication

As yet Federal DLDP does not have an IEC strategy.

# Cross-cutting issues

DLDP encourages the regions to address cross cutting issues through its various studies and manuals. Participation manuals in particular include recommendations on gender involvement in local government activities.  The draft prototype local government policy espouses gender sensitive principles on the recruitment and promotion of woreda staff.

# Key issues arising from assessment

DLDP has experienced a range of problems at the federal level some of which have been beyond its control including high levels of staff turnover, inexperienced staff, low budgets, difficult working relationships within MCB and lack of equipment etc due to delayed procurement.

It has also received adverse reports and reviews during supervision and evaluation missions relating to inadequate co-ordination, not being proactive enough, delays in achieving its outputs etc. Regions have also tended to have low expectations of federal DLDP and have in some cases largely carried on with their own initiatives not bothering to report or consult.

Given the difficulties of its federal level role, we have taken a somewhat hypothetical perspective in identifying key issues for federal DLDP. This is to try to stimulate further thought as to how federal DLDP might evolve to create a meaningful role for itself and to command more respect as a useful agency from its political masters and the regions as a whole. Essentially federal DLDP needs to become a ‘centre of excellence’ for knowledge and support to regions on decentralisation and local government, if it is to increase its relevance in the current environment. Therefore we see this federal sub programme as having 6 major groups of activities;

- Promoting a clear overall decentralisation policy and vision from the perspective of the federal government. Continuing to explore potential for advancement of decentralisation in the country;

- Providing technical and administrative guidelines to the regions in line with government’s political vision. This would include providing prototypes, packages, manuals and studies for regional adaptation;

- Supporting more directly the implementation of DLDP in the regions through provision of advice, facilitation of information and best practice sharing, facilitation of technical innovation, providing specific support to the emerging regions;

- Co-ordinating government, donor and non government initiatives which aim to support the implementation of the decentralisation vision such that they are complementary and serve to build capacity rather than undermine it;

- Monitoring and evaluation of DLDP PSCAP activities and establishment of an institutionalised local government performance monitoring system which generates standard data for measuring decentralisation progress and impact;

- Publicising DLDP and decentralisation through a clear IEC strategy which enunciates the Vision of decentralisation and governments efforts to implement it.

a) 	DLDP in MCB is the agency responsible for promoting the federal government’s vision on decentralisation. Whilst there is no question about the core direction and intention, the details of this vision have not been presented through a clear policy document which is widely available to all actors. The Regions, in terms of the constitution, are responsible for local government operated through their own constitutions and legal frameworks but this responsibility could be better informed if DLDP provided a policy statement on the federal government’s vision for decentralisation and local government.

DDLP has already prepared a prototype legal framework for local government and a prototype policy document for further elaboration and adaptation by each region. Within these prototypes are draft sections relating to a possible federal policy statement. To date DLDP has yet to promote federal level discussion of its draft prototype local government policy. The new Woreda Good Governance Package has also introduced new elements, which need to be incorporated into this policy and vision.

b)	Seven of DLDPs 8 components comprise the preparation of studies, packages, manuals and prototypes. The studies have been undertaken by various consultants and DLDP itself. Each represents a significant piece of work.  It has taken 3 years to make significant progress on these studies. Some of them have been somewhat late and overtaken by events in the regions.

In terms of the content of the studies, there are questions of consistency, duplication, over elaboration and detail, partly as a result of a lack of precision in the overall vision. Woredas could become overwhelmed by all these guidelines especially those woredas with limited capacity in the first place. The onus will be on regional DLDP’s to adapt and simplify all this information to produce clear, simple and consistent manuals. Somewhat surprisingly there is no manual on different capacity building strategies including guidance on what capacity development involves and how it can best be brought about.

c)	Federal DLDP is very cautious about its potential role in supporting CB in the regions. It does not want to be accused of dictating or interfering in regional responsibilities beyond providing guidelines and manuals accompanied by limited training which regions can ‘take or leave’ or adapt for themselves. Whilst this approach is in line with the federal constitution and policy, there is considerable scope to do more to support and influence the regions through organising learning events, facilitating experience sharing activities, promoting study tours, assisting regions to hire consultants and simply responding when invited to assist. DLDP complains of missing out on regional reports (which seem to end at PPD). It has however recently instituted a quarterly meeting of regional DLDPs which will go some way to fulfilling its facilitator/coordinator role. The emerging regions in particular require additional support for their DLDPs - a challenge for both Federal DLDP and the Ministry of Federal Affairs. They need to design appropriate support mechanisms and co-ordinate their implementation.

d) 	Co-ordination of government, donor and non government initiatives in relation to decentralisation and woreda capacity building is an essential role for DLPP, ensuring such initiatives operate in line with the local government policies. DLDP could do more in this regard. As a custodian of MCBs decentralisation vision, Federal DLDP should actively engage with important initiatives by providing design inputs and monitoring impact.  Examples include the attempts by Ministry of Federal Affairs to build decentralisation capacity in the emerging regions; the operation of the Protecting Basic Services, the design of EPBS, and the design and piloting of Local Investment Grant proposals.

e)	Monitoring and evaluation of rural decentralisation policy implementation (including local government performance) and regional DLDP capacity building performance is another important role for federal DLDP. This area needs much more attention. At best, federal DLDP receives patchy reports on the activities of regional DLDPs. There is little regular output or outcome monitoring. The Woreda City Benchmarking Survey is a donor driven initiative to obtain regular information on woreda capacities and performance. It provides some limited data but its indicators could be improved and it needs to be institutionalised within the GoE bureaucracy. MCB, through federal DLDP has established Good Governance ‘Inspection Teams’ which again will provide insight into the performance of some woredas however this initiative also needs to be properly integrated and institutionalised. No regions have yet established comprehensive woreda monitoring and regulation arrangements.

f)	At a regional level, responsibilities for local government promotion, support, regulation and monitoring are disbursed between several bureaus or not being fully taken up. DLDP at federal level should encourage regions to study this institutional architecture. It may be better to establish a bureau of local government in each region.

g)	Federal DLDP is yet to prepare a clear IEC strategy to promote rural local government policy and vision or to support the regions in undertaking this requirement.

# Lessons learnt and recommendations

Federal DLDP will soon have completed most of its initial batch of assignments involving the production of manuals and studies. This should make more room for its promotional, support and monitoring roles. In particular DLDP should:

a)	Facilitate clarity in MCB and Government as a whole on the long term policy and vision for decentralisation and rural local government. This should involve promoting administrative and political debate around integrating the Woreda Good Governance Package and the prototype decentralisation policy which has already been prepared.

b)	Review some of its various manuals and guidelines to make these short, clear, and consistent with each other and with Federal decentralisation policy. Likewise encourage regions to make their own versions consistent, especially with good government and decentralisation legal frameworks.

c)	Facilitate review of local government capacity building strategies being used in the country and elsewhere, including different forms of training, organisation development, learning by doing, study tours, woreda support units, incentives etc. and provide the results to the regions so as to encourage further innovation beyond bulk training.

d)	Facilitate greater experience sharing between regions and woredas so as to promote best practice.

e)	Facilitate the development of institutionalised performance monitoring systems for rural local governments at regional and federal levels. It is recommended in particular that DLDP promotes regional institutionalisation of Woreda Benchmarking Survey rather than allow it to continue as an expanding donor driven exercise. The funds presently expended on the survey could be used to finance pilot performance exercises in different regions based on the Minimum Service Standards manuals of DLDP.

f)	Encourage regional analysis of the advantages and disadvantages of setting up bureaus for local government so as to integrate promotion, support, regulation and monitoring activities.

g)	Work with other agencies and ministries particularly the Ministry of Federal Affairs to devise specific strategies to provide additional support to the four less developed regions.

h)	Develop and implement an IEC strategy for decentralisation and local government policy.

i)	Explore possibilities for establishing some form of Rural Local Government Association(s) or a Forum for the purposes of sharing experiences, lobbying for improvements etc.

# References

Amha Diana, 2007. Assessment of Planning and Budgeting System at Woreda and Kebele Level. DLDP July 2007.

Amha Diana, 2007. Woreda Planning and Budgeting Manual. DLDP July 2007.

Development in Practice Ltd, 2007. A Performance Monitoring System for Local Government in SNNPRS including Minimum Service Standards - Second Draft. SNNPRS BCB, DLDP, DFID April 2007.

DLDP MCB, 2006. Draft Local Government Legal Framework for development by Regional States. March 2006.

DLDP MCB, 2007. Human Resource Planning Survey in selected rural woredas of Afar, Somali, Gambella and Beneshangul Gumuz Regions. Final Report June 2007.

DLDP MCB, 2007. Training Need Assessment in Emerging Regions. Draft Report May 2007.

DLDP, 2007. Annual PSCAP DLDP Action Plan. DLDP March 2007.

DLDP, 2007. Annual PSCAP Participation and Performance Agreement. DLDP September 2007.

DLDP, 2007. Annual PSCAP Performance Report. DLDP August 2007.

DLDP, 2007. A system for the participation of local households and women in local councils.

DLDP, 2007. Grassroot participation Framework Manual for dominantly livestock farming regions.

DLDP, 2007. A Grassroot Participation Manual for settled agricultural regions,

A system for participation of Membership based Civil Societies at Rural Kebele.

DLDP, BCB SNNPRS, DFID, 2007. Draft Manual – Minimum Service Standards, Norms and Reporting Mechanisms for Rural Woreda Local Governments. April 2007

DLDP, MCB, 2006. Draft Local Government Policy of the FDRE. MCB March 2006.

Ludovick Leon Shirima, 2007, Model Regional Transfer Formula Development – Field Visit Reports and Manuals Volume 1 Reforming Regions, Volume 2 Less Developing Regions. DLDP2007

DLDP, MCB, 2005. Mid Term Implementation Directions for District Level Decentralisation and Capacity Building – DLDP. MCB June 2005.

DLDP, MCB 2004. Rural Woreda Capacity Building Program (DLDP), Federal PSCAP Action Plan (2004 – 2008). MCB 2004.

Yohannes L., Mussa, M., 2005. Synthesis Report on Assessment of District Level Decentralisation and Capacity Building in Tigray, Amhara, Oromiya and SNNPRS. DLDP MCB Dec 2005.