Annex 13: Gambella report

# Background

Gambella Region was visited by Rob Mellors and Habtu Gebrehiwot between 21st and 24th October 2007. Meetings were held with The Deputy Speaker of the Regional Council, the Regional President, the Bureau of Capacity Building, the 7 sub-programme managers, the Regional BOFED and a range of beneficiary organisations. Additional information was obtained from special reports produced by the sub-programmes, PSCAP 5 year and annual action plans, various statistics provided by sectoral bureaus and relevant secondary evaluation reports.  Two woredas were also consulted namely Abobo and Gambella. Persons met are appended.

The Evaluation Team would like to thank The Deputy Speaker of the Gambella State Council, The President of the Region, the Bureau Head of BCB, the staff of BCB and PPD, sub-programme coordinators and other officials and individuals who generously made time available for interviews and helped by producing reports, presentations and collecting various data. Woreda and municipal personnel also gave of their time.

# Overall assessment

Gambella Region has rich potential but is one of the four less developed regions. It has made steady development progress as a Region since the first round of decentralisation in 1994.  Gambella has come from a very low base in capacity terms and has experienced intermittent periods of insecurity when development programmes have been interrupted. It remains seriously challenged in implementing PSCAP and in achieving demonstrable impact. Implementation has really only started over the last 18 months since the previous period of insecurity. Its struggling performance results from a combination of serious skilled manpower shortages, frequent turnover of staff - both experts and appointees - underlying nationality tensions within government and in the society at large, a late start and the difficulties with the PSCAP design and implementation in terms of procurement and availability of funding.

Awareness of the programme is far from comprehensive amongst key some of the key stakeholders e.g. the Regional Legislature confirmed through the Deputy Speaker that they have only started to become informed about PSCAP in the last few months.   Conversely, the Regional President is familiar with the Programme and considers it very important, “if only its overburdening bureaucracy can be overcome”. In essence, the present PSCAP arrangements require adjustment and augmentation if they are to be appropriate to Gambella’s needs.

Performance is quite variable between sub-programmes. Most of the MMAs are well behind those of other regions. Slowly but surely however one gets the impression that progress is being made with implementation accelerating in the past year. This could be significantly enhanced it the Region was given some special support and facilitation.  Sadly the present financial year has started badly with virtually no funds being released to the Region in the first quarter thus eroding the momentum that was being built.

It is not possible to assess follow up of previous JSM recommendations as the region has been omitted so far from JSM visits. Given the pressing needs of the region, such a situation is unfortunate and every effort should be made during future JSMs to give the region some extra attention.

It is generally too early to assess impact against the higher level ‘service delivery and good governance indicators’, other than to say that the general consensus is that small gains are being achieved here and there. Woredas note greater cohesion between the Woreda administration and the people and also highlight service delivery improvements in education, water and security. Half the woredas now have electricity and telephones. They are aware of their capacity needs which include infrastructure, furniture, training on good governance, further training for cabinet members and councillors and upgrading of their staff.

It is more realistic in this report to assess the Region’s early PSCAP activities and to make some assessment of the outputs or intermediate objectives relating to improved systems and structures, financial flows, justice and civil service conditions.

As in other regions there are numerous complaints by sub-programmes and some beneficiaries about the special procedures set up to access PSCAP funds. These focus mainly on procurement systems, shortage of funds and delays in release. At the same time the programme is much appreciated by a number of bureaus for the support that it has brought so far to a region that is desperate for assistance.

# Progress with Sub-programmes

  - Civil Service Reform Programme

    - Overview and Organisational Setup

The objectives of the CSRP in Gambella are the same as those of other regions namely, to enhance the policy and strategy implementation capacity of the civil service transforming it into an efficient, transparent, accountable and result oriented body. The components comprise:

- Strengthening the CSRP co-ordinating bodies at all levels,

- Improving Governance of Human Resources Management and Control

- Improving Performance and public service delivery,

- Improving Transparency and Accountability and

- Strengthening Top Management Systems.

    - Strengthening the CSRP co-ordinating bodies at all levels,

PSCAP activities hardly started until 2006 as the focal people in CSRP kept leaving and there was little equipment. Staff turnover is still a major problem e.g. from 8 people involved in implementing the programme last month, only 5 remain this month. CSRP and JSRP have also only been part of BCB since June 2006.  MMAs are around 25 to 35% achieved.

Initial efforts have gone into building up the CSRP Office.

Training:

Training activities have been quite limited. There are serious problems getting trainers so training has to be done by the BCB officials and other bureau staff. Training equipment has also not arrived so there are no projectors or training aids. Training conducted so far includes:

- 20 for CSRP and associated staff on computers;

### Study Tour for 5 CSRP staff to SNNPRS.

Equipment:

The CSRP was previously supported by UNDP and the sub-programme received a vehicle and IT equipment. It now feels let down in terms of procurement under PSCAP. So far it has only received and distributed 2 computers, 4 laptops and furniture. Training equipment, computers, photocopiers and laptops have all been ordered but have not been delivered.

    - Improving Governance of Human Resources Management and Control

A start has been made with this component. Manuals have been, and are still being produced on HRM and various civil service working systems. Training has been conducted for 160 officials from all levels on good governance, accountability, transparency, ethics, change management, civil service proclamations, principles and directives by CSA.

Results oriented performance evaluation (ROPE) has been included as a subject in the training course but there has been no follow up. The Civil Service Agency (CSA) intends to produce a rules manual, however so far it has not received any budget for work this financial year.

Consultancies:

No consultancies have been carried out. There is an intention to do an assessment of human resources and develop an HR database but funds for this year are not released. Proposals have been drawn up to hire trainers but these have remained unfunded.

    - Improving Performance and Public Service Delivery

CSRP has produced local manuals on Strategic Planning and has run training courses for:

- 128 officials on the basic elements of PSIP;

- 118 officials from all levels on the basic principles and activities of Strategic Planning, BPR and ROPE by SNNPRS trainers – 8 day course.

    - Improving Transparency and Accountability

No specific activities were reported under this component, however these governance issues have been covered in various multi faceted training courses

    - Strengthening Top Management Systems

52 focal officials have been trained on gender policy, gender development and equality issues in the civil service.

    - Impacts on institutional, organisational and individual capacities

Most sector bureaus have limited knowledge about PSCAP although they are familiar with the CSRP.  They acknowledge receiving training on Strategic Planning, BPR and ROPE and have all recently produced their 5 year Strategic plans following the helpful training from the SNNPRS team in October 2006. So far however there has been no implementation of the training received on BPR or ROPE although woreda staff members all have job descriptions.

The Bureau of Education claims that it has been informed that it is not a PSCAP beneficiary and has therefore never submitted any plans for training or equipment.

Woredas have received guidelines on their structures from the Civil Service Agency and each year new offices are being opened. Most have also prepared strategic plans but they question the value of these when they have virtually no capital budget with which to implement anything. Woreda staff members have not generally been able to put their service delivery training into effect as again there are no funds available.

Woredas acknowledge the training on civil service principles, ethics, transparency etc. which they feel was useful. They believe they are becoming better managers, decision makers and planners. Some are trying to carry the training down to their kebeles.

  - District Level Decentralisation Programme

    - Overview and Organisational Setup

Gambella region has 12 rural and 1 urban woreda divided between 3 Zones based on nationality. During this evaluation we were only able to visit 2 woredas which are likely to be the more capable. The comments below are based on these visits.  Woreda populations average between 20 and 40,000 which are small by comparison with the larger regions. Their councils are appointed by the Zones. Elections should be held in 2008. The woredas are generally short staffed even so they employ 500 to 1000 staff including teachers. They have limited transport resources, maybe 1 vehicle and 3 to 6 motorbikes some of which were supplied earlier through UNDP.

Woreda staff members have not heard much of PSCAP although they have heard of some of the reform programmes. Some have heard of the Woreda Good Governance Package, but most woredas know little about the content of the DLDP. This is perhaps not surprising since most DLDP initiatives are regional and are about creating an enabling environment for local government.

The objectives of DLDP in Gambella are to strengthen the decentralisation programme at grassroots level and thereby deepen devolution of power in decision making and promote good governance so as to ensure sustainable development and service delivery.

DLDP has 2 staff working at regional level although one has recently disappeared and the other is newly in post. The Deputy Bureau Head has a good understanding of the sub-programme however, and there seems to be a good team approach in the BCB to try to handle the main issues. A small amount of office infrastructure has been provided including 1 computer. In each of the13 woredas there is also a Capacity Building Officer plus additional staff to cover CSRP, ICT and DLDP.

Overall achievement of MMAs is between 10 to 20%. The Local Government Legal Framework is the only MMA which has almost been achieved, most have not been started.

As in other regions DLDP has good horizontal and downward relationships but its links with Federal DLDP are weak. It receives federal prototypes and reports but complains of little support in terms of implementation and advice. Most support comes from SNNPRS.

    - Institutional and organisational arrangements

The Region has made good progress in developing a Local Government Legal Framework utilising examples from prototypes and other regions. The Framework has been passed by the Regional Cabinet and is awaiting final endorsement by the Council.

There is no institutionalised woreda monitoring system from a local government perspective. DLDP has not carried out any evaluation of activities. Woredas however, report that decentralisation has had impact on participation and public relationships.

    - Manning and Training

Woreda organisational structures have been designed and established along with job descriptions for each post. DLDP is planning a human resources and training needs assessment this financial year if it can procure suitable consultants or get the assistance of the CSA.

Numerous training programmes have been conducted in strategic planning; roles and responsibilities of cabinets, officials and councillors; financial management. These have involved 10 to 20 day workshops run by the Ethiopian Management Institute (EMI).

Woredas have appreciated the training by DLDP in decentralisation and on the draft legal framework. They found the work on functional assignments especially useful and have now started to implement the legal framework. There is little awareness of decentralisation in the kebeles.

    - Grass roots participation

No participation manuals have been produced as yet by DLDP.

    - Woreda fiscal transfer and own revenue enhancement

There appears to be no specific grant formula in use in Gambella.  Block grants to woredas are distributed on a needs basis in relation to staff salaries and the remaining amount is disbursed based on sectoral plans from the woredas. In per capita terms Gambella receives the highest level of block grant in the Country – the figure being around 600 Birr per head in 2006. (In Amhara, Oromia, Tigray and SNNPR the figure is around 100 Birr per head).  Block grants to woredas in Gambella have risen by 30% in the last year.  Local revenue comprises on average 11 to 11.6 % of the budget and is also projected to rise by 36% between 1999 and 2000 EFY.

Table 1. Gambella Regional State - Zone budgets for the 2000EC (2007/08) BOFED

| Zone | Recurrent |  | Block grant for Capital | Total | % |
| --- | --- | --- | --- | --- | --- |
|  | Block grant | From Zone (local)revenue |  |  |  |
| Agnwak | 3,006,322 | 180,563 |  | 3,186,885 | 34.07 |
| Nuwer | 2,371,506 | 186,869 | 500,000 | 3,058,375 | 32.7 |
| Mejenger | 2,905,172 | 203,425 |  | 3,108,597 | 33.23 |
| Total | 8,283,000 | 570,857 | 500,000 | 9,353,875 | 100 |

Table 2. Zones Budgets 1999E.C (2006/07) BOFED

| Zone | Recurrent |  | Block grant for Capital | Total | % |
| --- | --- | --- | --- | --- | --- |
|  | Block grant | From Zone (local)revenue |  |  |  |
| Agnwak | 3,003,455 | 217,230 |  | 3,220,685 | 35.72 |
| Nuwer | 2,300,640 | 236,251 | 1,000,000 | 3,536,891 | 39.22 |
| Mejenger | 2,100,305 | 159,061 |  | 2,259,366 | 5.06 |
| Total | 7,404,100 | 612,542 | 1,000,000 | 9,016,942 | 100 |

Table 3. Woreda Budgets 2000EC (2007/08) budget BOFED

| No | Woreda | Recurrent |  | Total | % |
| --- | --- | --- | --- | --- | --- |
|  |  | Block grant | Local Revenue |  |  |
| 1 | Abebo | 11,538,361 | 78,272 | 12,916,634 | 13.00 |
| 2 | Dima | 5,309,647 | 1,246,426 | 6,556,074 | 6.60 |
| 3 | Gambella Zuria | 6,763,750 | 1,171,980 | 7,935,730 | 7.99 |
| 4 | Gog | 8,819,638 | 664,636 | 9,484,274 | 9.55 |
| 5 | Jor | 4,138,655 | 303,901 | 4,442,556 | 4.47 |
| 6 | Akobo | 5,023,533 | 376,404 | 5,399,937 | 5.44 |
| 7 | Jikawo | 6,068,676 | 504,656 | 6,573,332 | 6.62 |
| 8 | Lare | 11,026,322 | 764,787 | 11,791,110 | 11.87 |
| 9 | Wantuwa | 5,361,176 | 577,671 | 5,938,847 | 5.98 |
| 10 | Godere | 7,372,431 | 1,693,083 | 9,065,514 | 9.12 |
| 11 | Mengiesh | 5,598,715 | 877,914 | 6,476,629 | 6.53 |
| 12 | Itang | 5,339,877 | 734,525 | 6,074,402 | 6.11 |
| 13 | Gambella town Admin Council | 5,469,217 | 1,229,806 | 6,699,023 | 6.74 |
|  | Total | 87,830,000 | 11,524,060 | 99,354,060 | 100.00 |

Table 4.Woreda Budgets 1999 E.C (2006/07) BOFED

| No | Woreda | Recurrent |  | Total | % |
| --- | --- | --- | --- | --- | --- |
|  |  | Block grant | Local revenue |  |  |
| 1 | Gambella town admin council | 7,066,167 | 920,858 | 7,987,025 | 10.44 |
| 2 | Itang | 5,972,750 | 550,000 | 6,522,750 | 8.53 |
| 3 | Gambella | 4,867,655 | 877,559 | 5,745,214 | 7.51 |
| 4 | Abebo | 5,734,957 | 950,000 | 6,684,957 | 8.74 |
| 5 | Gog | 5,008,843 | 497,660 | 5,506,503 | 7.20 |
| 6 | Jor | 4,639,063 | 227,556 | 4,866,619 | 6.40 |
| 7 | Dima | 5,983,719 | 933,303 | 6,917,022 | 9.04 |
| 8 | Jikawo | 4,746,636 | 281,551 | 5,028,187 | 6.60 |
| 9 | Lare | 5,640,832 | 572,660 | 6,213,492 | 8.13 |
| 10 | Wantuwa | 5,002,120 | 432,550 | 5,434,670 | 7.10 |
| 11 | Akobo | 4,975,227 | 281,845 | 5,257,072 | 7.22 |
| 12 | Godere | 8,094,831 | 1,918,255 | 10,013,056 | 13.09 |
|  | Total | 67,732,800 | 8,443,767 | 76,176,567 | 100.00 |

    - Woreda Planning and financial control

Woredas have received training in Strategic Planning under the CSRP. They have also been supported with some training in budgeting and accounts by the EMCP. There have been no significant inputs by DLDP in this area as yet.

    - Minimum service standards and performance assessment mechanisms

Some work has been done on service standards, badges, name plates, service information boards etc. through the CSRP but much more is required through adaptation of the MSS federal prototype.

    - Woreda Good Governance Package

A Good Governance Steering Committee has been established at regional level chaired by the Regional President with BCB as the Secretary. This will oversee capacity development in the woredas and the good governance training programme based on the Manual that the Region has only just received.

    - Woreda Equipment

Some Woredas have received limited amounts of IT equipment. The computers and photocopiers received through PSCAP are very useful and so far are all in working order. Previously woredas were supported by the UNDP programme and given vehicles and computers. Most of these are now broken down and unserviceable.

  - Expenditure Management and Control Programme

    - Overview and Organisational Setup

It was not clear if EMCP is still part of the CSRP or if it is to be run separately however whatever the location institutionally, the programme is presently being run by BOFED personnel.

Most woreda budgets are of the order of 5 to 13 m Eth Birr and between 85 and 100% of this is for salaries and recurrent costs. Budgets have increased over the past 2 years. Capital budgets are virtually nil. There are complaints that the budgets are inadequate to even pay the present staff.

In terms of MMAs, BOFED reports that only some woreda accounts are up to date as of end of 1999 financial year, in others there is a small accounting backlog.  Some basic training in BIS and BDA3 has been carried out. Subjectively this would give an MMA score of around 50% - the highest for any sub-programme in Gambella.

The BOFED staff involved with EMCP are very appreciative of assistance they receive from federal level MOFED.

    - Improving governance of financial resources management and control

EMCP activities in the Region have so far consisted of two rounds of training in 2007 each lasting 12 days. The training is done in house using manuals from MOFED. The course details are as follows:

- 70 regional, zonal and woreda officials have been trained on new financial legislation and working systems;

- 195 officials have received training on Budget reforms/formats, expenditure management including double entry accounts and reporting.

A new course is about to be run to train internal auditors - the trainers have been invited to come down from federal level.

    - Impacts on institutional, organisational and individual capacities.

The accounting and budget reforms were due to be implemented this financial year 2000 EFY. Orders have recently been sent out to all bureaus to start double entry accounts straight away.

All woredas have now been introduced to the single pool treasury system which in some cases is still being implemented. In woredas where the process is complete, a WOFED would typically be manned by around 40 to 55 personnel.

Woredas submit financial reports to the region monthly and to the Woreda Administrator and cabinet quarterly. Some woredas are slow to submit their accounts and require assistance. Overall woredas have problems producing and managing their budgets. Only 2 or 3 are using computers. WOFED staff acknowledge a great need for training but complain that the course they received so far was of poor quality and too short. The regional trainers however, also had concerns about training impact as some participants were unable to cope with the materials. There is some impact from the training but a long way to go.

In an attempt to expedite end of year accounts, BOFED is trying to install internal auditors in all public bodies. They will finalise the accounts with the accounts staff and then the auditor general will do the final audit.

  - ICT Sub-programme

    - Overview and Organisational Setup

ICT has 4 key components which are intended to address the overall objective of improving governance and service delivery. These are:

- Developing an ICT skilled labour force in government;

- Developing computerised working systems for service delivery;

- Developing special sectoral applications;

- Developing community based ICT services.

Limited progress has been made with the ICT sub-programme in Gambella partly due to an overall lack of implementation capacity but more importantly due to the major constraints in the procurement system which have severely limited the availability of equipment.  There are 2 ICT personnel located within BCB, one who is very newly in post.

9 out of 12 rural woredas have received video conferencing equipment. Only 7 however have been able to install the equipment as 2 do not have appropriate buildings in which to house it – the buildings are on the PSCAP negative list. A further 3 woredas are still awaiting procurement.

    - ICT for human resource development

3 representatives from each woreda have been trained in Addis on the installation, operation and maintenance of Woreda Net equipment and video conferencing equipment. 126 civil servants from the regional bureaus and council have received basic computer training over a 45 day period in the last year in anticipation of the arrival of a large procurement order of computers. The training was conducted by private sector trainers.

    - ICT for public services delivery and good governance

School net has been established by the Bureau of Education without any PSCAP input. There are intentions now to collaborate with the ICT sub-programme in BCB.

    - ICT applications for sector development

The Region is attempting to purchase 20 computers to establish its regional data centre but again it has not received funding. It seems there are also problems with adapting the main server which evidently has been installed but is not familiar to available technicians.

Attempts to establish a LAN for 6 main regional bureaus are presently in suspense.  The system was planned by outsiders and the personnel in the region do not have the knowledge and experience to implement the plan. In trying to hire a consultant to assist them, the region finds itself unable to prepare adequate TORs. There is also a plan to prepare sets of training manuals in the local language but again this is proving too challenging an exercise for regional capacity.

    - ICT for community based information systems and services

No activities have been undertaken under this component as yet.

    - Impact on institutional, organisational and individual capacities;

The 3 ICT trainees from each woreda have had mixed fortunes since their training. Some are now fully engaged by their woredas on ICT, others work part time and some are not applying their training at all as their woredas have no equipment. The training for civil servants has also had a mixed impact again due to the non arrival of computers. Most bureaus have one or two computers purchased by government and so only a proportion of the trainees have had any opportunity to apply the acquired knowledge. For others it has been a wasted exercise.

Overall this sub-programme has been dogged by procurement delays and lack of experienced ICT manpower. Furthermore the equipment (Acer) that has been delivered through PSCAP has been found to be of low quality and subject to a high failure rate. The technological challenge of such a programme in a remote environment like Gambella is large. Much more support is required alongside the supply of more tried and tested hardware if significant impact is to be achieved.

The woredas have recently received some computers and photocopiers which are all continuing to operate.  ICT staff members have increased capacities as a result of training in Addis.  There are problems in getting the video conferencing systems to work.

School Net has been established in 6 High Schools with 18 Plasma Screens.  There are now 2 teachers in each school who have received training in Addis as operator/technicians. Lack of finance for generator fuel, the occasional problem of theft, a shortage of trained maintenance technicians and high staff turnover have presented the Education Bureau with significant challenges to keep the system running. They themselves have a few well trained staff who can provide back up and at the time of the visit only 14 out of the18 plasmas were functional. Overall the budgets are too small to run the system optimally.

With the exception of School Net the ICT programme is having little or no impact on service delivery.

  - Justice Sector Reform Programme

    - Overview and Organisational Setup

The JSRP has 6 specific objectives:

- Building the capacity of the courts to increase efficiency in processing cases,

- Achieving greater equity and effectiveness in judicial service,

- Strengthening independence and accountability of the judiciary,

- Ensuring wider accessibility of courts to the public and ensuring predictability of court decisions,

- Strengthening law making capacity of Gambella’s legislative organ,

- Establishing a modern legal framework compatible with the constitution, socio economic and political interests of society.

- Creating an enabling environment for the transformation of law enforcement agencies so they become more effective and efficient.

The JRSP has been running in Gambella for 3 to 4 years and is now based in BCB having previously been in the Justice Bureau. It is run by one person who has been in post for 1 month. Overall achievement of MMAs  is around 20%. Most activities have centred on the courts where there have been some tangible achievements.

    - Strengthening the judiciary and the courts

In terms of the court system Gambella has a Supreme Court, 4 High Courts and 12 woreda courts. Only one of the High Courts deals with criminal cases and is seriously overloaded.

There are also plans to undertake a study visit to SNNPR to gain information on how to restructure the whole court set up for greater efficiency. In Service training for some 90 judges and prosecutors has been conducted at Federal level on the new penal code, revised criminal law, hearing and deciding of cases and the independence of the judiciary. Various court staff have also been trained on court organisational structure, filing, introduction to computers, court case management, budget and project planning.

Installation of the Colour coded filing system has been completed in the Supreme Court and one High Court only. Introduction of transcribing machines in the Supreme Court and into 1 High Court is also complete.  The programme has facilitated improved case management through a computerised database in the Supreme Court and in one High court. It is planned to extend this to the other High courts in due course. New file folders have been introduced in all courts in the region except one woreda court. No Information Desks have been set up as yet.

In terms of equipment, the courts have received 2 computers, 1 laptop, 3 printers and furniture through PSCAP. There are quality problems with the equipment especially the printers. Overall there is considerable frustration about delays in the PSCAP planning system and in particular the budget release for the current financial year plus the backlog of unsupplied equipment. The Supreme Court President is aware of the ICB constraint and feels it is unnecessary as the equipment could be procured through NCB or local shopping.

    - Law revision and law reform

No activities were reported under this component.

    - Law enforcement organ capacity development

The Police produce an Annual Action Plan for PSCAP but have not received the support or materials as planned. They have received one computer, a printer and photocopier against an order of 10. They are also having technical problems with the equipment.

In terms of training the police have attended various courses and have included amongst their trainees, representatives from regional, zonal and woreda levels. They have received training in crime investigation, traffic and criminal statistics at the Federal Police Commission and Police College. 51 force members have also done a 10 day course on Human Rights. Others have done various types of management training at EMI.

    - Legislative organ

To date there has been no training for the 82 Regional Council members  (including 14 women) due to the Council having little understanding of JSRP or PSCAP. The situation is set to change this year with training planned in constitutional law making and principles of law. The administrative staff of the Council and Executive have received some basic office training.  The Regional Council has received 1 computer. Many more are on order for 2007.

    - Impacts on institutional, organisational and individual capacities

PSCAP is regarded by the courts as a beneficial programme despite the problems with procurement. The colour coded files have been very effective in improving the effectiveness and efficiency of case management.

At Supreme and High court level the training has had some limited impact on the performance of the judges. Most judges in Gambella however are category 2 and 3. Only one has a Masters degree. There is a reluctance of people to enter the judiciary. Some judges also complain of ‘pressures’ applied on their judgements.

The Court President also notes some small improvements in police case handling but the more noticeable improvements have been with the prosecutors. Fewer cases now have to be sent back due to poor preparation.

At Woreda level there are few improvements as most judges are unqualified and have capacity limitations in terms of training impact.

The Police have developed a much improved structure in conjunction with PSCAP funded support from SNNPRS. They are also introducing job descriptions based on lessons learned from Amhara.

So far the JSRP has had no impact on the Regional Council. The council has members from 3 parties and has had little information on PSCAP until this year.

  - Tax Systems Reform Programme

    - Overview and Organisational Setup

The objectives of the TSRP in Gambella are to increase revenue, broaden the tax base, improve equity and efficiency and promote investment through:

- updating tax policy and legislation,

- improving and rationalising presumptive tax,

- introducing TIN,

- introducing VAT,

- preparing and distributing operational manuals,

- educating the tax payers.

Responsibility for implementing the TSRP is spread across the 4 working teams in the Bureau of Revenue. The Bureau has 1 broken down vehicle and states that it can no longer access the woredas. 4 Laptop and 4 Desktop computers, a fax machine plus various pieces of office furniture have been received though PSCAP however the IT equipment has been subject to numerous breakdowns. The TSRP staff complain of the poor quality of the equipment and delays in the release of funds by PSCAP.

A limited amount of implementation progress been made with this sub programme. MMAs are still largely incomplete. The progress with each of the components is as follows:

    - Tax policy and legislation

Two proclamations – Agricultural Income Tax and Rural Land Use Fee have been issued.

    - Tax payer identification number

Four staff have been trained on TIN and VAT registration although it is unclear if any people have been registered for TIN. This component is really only just getting underway.

    - Presumptive taxation

TORs have been drafted to carry out a study of revenue potential although there is presently no money to hire the consultant.

    - Value Added Tax

VAT has not yet been started in the region. Businessmen who are VAT registered settle their affairs in other regions.

    - Operational Programmes systems, procedures and manuals

50 staff have been trained on contraband and illegal trade; 78 on gender and HIV/AIDS.

A further 18 staff have been trained on tax assessment and auditing.

    - Organisation and tax payers education

Awareness training has been given on cost sharing fee collection, withholding tax and VAT for up to 200 people.

    - Impacts on institutional, organisational and individual capacities

The Bureau reports many problems regarding the collection of tax, the main one being a lack of awareness on tax use, types of tax and the need to pay by the public at large. In the past tax collectors have frequently misused taxes for their own purposes, which has further alienated people from the system. Despite this there is an increasing trend in total regional collections from 12m Eth Birr in 1998, 17.9m Eth Birr in 1999 and a projected 19m Eth Birr for 2000. Most of this however comes from income tax on salaried workers.

Tax Officials are anxious for more national level training of their experts. They would especially like more training for woredas on tax issues. Collection of agricultural income tax is a big problem particularly with regard to un-receipted collections and embezzlement by tax collectors. The woredas local revenue is projected to rise however, from 8.44m in 1999 to 11.52m Eth Birr in 2000. It makes an average contribution of 11 - 13% towards woreda budgets. Woredas complain of never having had any training on revenue collection.

The approach to IEC is through meetings but they have not tried the print media or radio.

Table 5 Gambella Local Revenue Mobilisation 1999 E.C - All sources

| No | Location |  | Achieved Performance |  |  | Total |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Planned | Direct Tax | Indirect Tax | Non taxable items |  |
| 1 | Regional Level | 5,859,741.00 | 7,558,295.19 | 659,959.87 | 811,891.17 | 9,030,146.23 |
| 2 | Agnwak Zone | 217,230.00 | 156,960.98 | - | 27,782.15 | 184,743.13 |
| 3 | Nuwer Zone | 236,251.00 | 158,145.61 | 8,616.51 | 1,380.50 | 168,142.62 |
| 4 | Mejenger Zone | 159,061.00 | 177,784.90 | - | 4,552.95 | 182,337.85 |
| 5 | Dima Woreda | 933,303.00 | 724,064.21 | 239,337.51 | 48,867.75 | 1,012,269.47 |
| 6 | Godere Woreda | 1,918,225.00 | 1,484,452.92 | 117,384.00 | 218,192.44 | 1,820,029.36 |
| 7 | Gog Woreda | 497,660.00 | 697,362.28 | 29,156.48 | 63,490.93 | 790,009.69 |
| 8 | Gambella Woreda | 877,559.00 | 443,185.11 | - | 297,607.22 | 740,792.33 |
| 9 | Aluwero Apeno | 950,000.00 | 801,460.84 | 9,902.55 | 120,900.06 | 932,263.45 |
| 10 | Jikawo Woreda | 281,551.00 | 277,842.19 | 1,435.90 | 6,095.15 | 285,373.24 |
| 11 | Akobo Woreda | 281,845.00 | 182,296.81 | - |  | 182,296.81 |
| 12 | Wantuwa woreda | 432,550.00 | 411,879.35 | 30,867.00 | 22,597.44 | 465,343.79 |
| 13 | Lare Woreda | 572,660.00 | 463,186.44 | 26,132.70 | 147,359.92 | 636,679.06 |
| 14 | Jor Woreda | 227,556.00 | 363,790.64 | - | 7,222.90 | 371,013.54 |
| 15 | Itang Woreda | 550,000.00 | 482,761.95 | 20,237.17 | 28,406.75 | 531,405.87 |
| 16 | Gambella Town administration | 920,858.00 | 527,836.71 | - | 30,014.18 | 557,850.89 |
|  | Grand Total | 14,916,050.00 | 14,911,306.13 | 1,143,029.69 | 1,836,361.51 | 17,890,697.33 |

Source: Gambella Bureau of Revenue

  - Urban Management Capacity Building Programme

    - Overview and Organisational Setup

There are four beneficiaries of the UMCBP in Gambella – the Bureau of Works and Urban Development, Gambella Municipality, Meti Municipality and Gambella Town Administrative Council. The UMCBP is overseen by the Deputy Bureau Head in the BWUD although he has only been in post for 1 month. Substantive activities are driven by an energetic special consultant from the Ministry of Works and Urban Development who is facilitating implementation of the sub-programme.  The UMCBP comprises three components: Regional Urban Management Policy, Deepening the process of decentralisation and Local government restructuring and capacity building.

UMCBP is one of the few regional PSACP sub-programmes which gets technical input into its annual plan from the federal level. It does not yet seem to have received the various GTZ sponsored urban management and development manuals. The sub-programme has put in requests for furniture and office equipment. BCB has only managed to procure some of the furniture so far which has been distributed to beneficiaries. UMCBP complains that it has not been invited to the Regional Technical Team. Although it reports to BCB quarterly as required by the PIP, its relationships are better with the Ministry in Addis.

The UMCBP is now picking up after a relatively slow start due to a lack of co-ordination between itself and BCB. It has really only made significant progress with the training component of the MMAs – one could subjectively say there is around a 10 to 20% achievement overall.

UMCBP’s main activities to date focus on consultancies and goods procurement as follows:

    - Regional Urban Management Policy

Much effort has gone into the preparation of a number of TORs and draft advertisements. Due to financial constraints only the first two are being progressed -  the Regional Urban Development Policy and the Financial systems and restructuring  for Gambella. The TORs have been handed to PPD in BCB to undertake procurement. In both cases BCB has been unable to procure the consultants even though the TORs have been prepared to a high standard. This is reported to be due to a lack of capacity to advertise.

    - Deepening the process of decentralisation

No activities were reported under this component.

    - Local government restructuring and capacity building

All training in BWUD is carried out in Addis and has included BPR. There have been study tours to Addis and Amhara and some basic training on computers for office staff.  Municipality personnel have received training on performance budgeting, customer service, project planning & implementation, basic accounting, human resource management and gender development. In cases where PSCAP funding has not been forthcoming, the sub-programme has used government funds alone.

6 staff members have also undertaken a gender course at EMI. PSCAP failed to fund this programme and so it was eventually financed from the government budget.

    - Impacts on institutional, organisational and individual capacities

Although it has not done any formal evaluation, the UMCBP subjectively believes that the training has had some impact on municipal and bureau efficiency. Secretaries are more proficient with IT and the accounts departments are becoming also more efficient.

Gambella Municipality has 44 employees, 20 of which have received some sort of training. It raises its own revenue, which is slowly increasing annually although it has had no help from the TSRP. 90% of its small annual budget of only 800,000 Eth Birr goes to salaries. It struggles to find and retain good staff but has some energetic and well-oriented personnel. The Municipality has had no help from CSRP. It struggles to fulfil its core functions, e.g. it has no garbage vehicle, the fire engine is only capable of being used as a ‘run around’ and the abattoir does not function.

There is a problem over land allocation, which has been suspended for the last 4 years pending the finalisation of the operational manual for the recently approved Master Plan. The Municipality appreciates the help it gets from UMCBP including furniture and 2 computers and photocopier.  It is desperately seeking further help in procuring vehicles, equipment and to get its abattoir going.

A major road building programme is currently underway in the town – maintenance of the new roads will eventually become a municipality function. Quite how the municipality will afford to do it looks very difficult with its present budget. The public complain seriously about the delays in implementing the Master Plan and the lack of garbage collection.

# Programme Management and Support

Programme Management is provided through the Regional PPD in BCB and is led on a day to day basis by the Deputy Bureau Head in BCB.

  - Coordination with MCB, sub-programmes and woredas

As in other regions the ICT, TSRP, UMCBP and EMCP have better linkages with their federal counterparts than do the DLDP, CSRP and JSRP. ICT makes calls quarterly to the Region to discuss progress and problems. In the UMCBP, the federal level comments on and supports preparation of  the regional plan before it is submitted to BCB. DLDP at federal level simply sends down masses of documents. In contracts the EMCP staff  receive good support from MOFED. No comment was made about support from Ministry of Federal Affairs.

Co-ordination at the regional level appears to be quite weak. The RTT rarely meets, however the Regional President has set up a Regional Steering Committee to promote Good Governance and this may promote enhanced focus and co-ordination.

Other than federal PPD assistance to the regional BCB, Gambella sub-programmes have rarely received visits for monitoring or support from federal sub-programmes. Generally, the federal level simply summons people to Addis Ababa. The BCB Bureau Head attends quarterly meetings in Addis Ababa at MCB to discuss progress based on the quarterly progress reports submitted by the Region.

  - Institutional arrangements for PSCAP in Gambella region

Programme management is provided through the Regional PPD in BCB, The Head of the PPD is directly accountable to the Bureau Head and is government salaried. Under him are 3 accountants and 2 Procurement experts. The procurement staff members are employed through the PSCAP budget. The Bureau is seriously stretched in terms of capacity – it has no planning or M&E expert. Some sub-programmes feel that they would be better served if the functions were transferred to BOFED. The BCB is also limited in its operations by a lack of transport. It has access to 2 vehicles – one provided to the CSRP by UNDP and one for DLDP.

Alongside the PPD are two Deputy Bureau Heads – one responsible for DLDP and ICT and the other responsible for CSRP and JSRP. In each of the 12 woredas there are 4 capacity building officers, one each for ICT, CSRP and DLDP under the CB Office and one other for JSRP.

  - Compliance with eligibility criteria by region

The region has signed Participation Agreements with the Federal PPD.

  - Planning and resource allocation

Planning for PSCAP follows the government calendar. Annual Action Plans are prepared by the sub-programmes in February March after receiving submissions from the various beneficiary agencies.  After compilation they are sent to the Federal PPD. In response to the Region’s request, the Federal PPD has come down this year to assist the Gambella BCB to compile their plan according to the PSCAP requirements.

The Regional Technical Team, chaired by the BCB Bureau Head meets on an ad hoc basis to co-ordinate the planning process – some sub-programme heads say they have never been to any meeting at all. It does not seem to be used to appraise and integrate the plans.

  - Sequencing and integration of reform initiatives

Sequencing of PSACP activities has not really been an issue in Gambella. Progress is at an early stage with most sub programmes. In DLDP the Region has given primary attention to setting up woreda organisational structures and systems, arranging basic training and drafting the legal framework. This is an entirely logical approach.  Under CSRP again, the first initiatives have been on strategic planning which is appropriate.

  - Financial management

The regional BOFED is responsible for financial management. It reports monthly to the Federal PPD. The programme is badly affected by high staff turnover. There are presently 2 accountants responsible for managing PSCAP budgets although these have only received training in double entry book keeping in Addis. The accountants have complained of low salaries and are not stable in their jobs.

Of the 39.1m Eth Birr originally allocated to Gambella in the PSACP 5 Year Action Plan, the region had received 8.35m by the end of 2006/7 and accounted for 7,215,118 Eth Birr (or 86.42%) through SOEs.

Expenditure in Year 1 (1997 EFY) was exceptionally low at only 0.9% of the 5.47m Birr budget allocated. This picked up in year 2 (1998) to 49.5% of the 6.47m Birr budget allocated.  Last year’s expenditure figures are much improved and are shown by sub-programme are shown in the table below. Encouragingly there is reasonably good correlation of these figures with those provided by PPD in MCB.

Table 6. PSCAP Funds by Sub-programme 2006/7, EFY 1999

| Sub-Programme | Budget 2006/7 | Spent | % |
| --- | --- | --- | --- |
| CSRP | 815,900 | 716,985 | 88 |
| DLDP | 979,410 | 580,461 | 59 |
| ICT | 897,200 | 823,378 | 92 |
| JSRP | 747,500 | 1,619,456 | 217 |
| TSRP | 245,300 | 188,345 | 77 |
| UMCBP | 714,540 | 320,028 | 45 |
| PSS | 208,400 | 238,763 | 115 |
| TOTAL | 4,608,250 | 4,487,418 | 97 |

Source: BOFED PSCAP Accounts Section

Gambella has been allocated approx 8m Eth Birr this year but so far only 449,000 Eth Birr has been released.

  - Procurement

Performance with procurement has been a source of great frustration for Gambella Region. The PPD has been financed to employ 2 procurement officers. Despite this there are complaints from some sub-programmes about procurement capacity in the PPD. In 2005/6, the region planned to acquire 86 desktop computers and 36 laptops. It eventually received 41 desktops and 25 laptops.  In 2006/7 it did not receive any equipment despite sending up 3 plans. The balance of the original order has never arrived.

Performance with office furniture procurement appears to have been better as it was achieved through ‘local shopping’ and many bureaus are very appreciative of the furniture they have received.

There are serious issues with regard to the appropriateness of the IT equipment sent to the region.  All bureaus made reports on the inferior quality, especially of the PSCAP supplied computers and in some cases the printers as well. Many of the units have broken down once or several times and many are now out of action. One wonders whether or not it is simply a question of the equipment not being robust enough for the Gambella environment or if the issue relates to inadequate use of UPS units etc.  By contrast, Dell equipment, procured for various bureaus by government seems to be subject to much fewer failures.

At woreda level only 6 of the 12 woredas have electricity, the rest have generators. Those woredas with electricity have all been allocated 1 or more computers.

  - Monitoring and evaluation

There is one person for M&E in the PPD although there have been periods when the post was unfilled. This seems a relatively weak area. The PPD states that it tries to monitor the activities of all training programmes to ensure they take place as planned and funded. They also say they have a training evaluation study in progress.

As in other regions the need for much increased effort in M&E is obvious. The region could begin to install a basic local government monitoring performance system using some standard forms covering a limited number of service and generic indicators.

  - Information, education and communication

There seems to be no formally organised IEC strategy in the region. Most sub-programmes say that information is extended during meetings and trainings but so far no one has produced brochures or radio programmes. Outside those directly involved with the programme many members of the public, CSOs, NGOs and even Regional Council members have relatively little knowledge of the PSCAP or most of the sub programmes.

# Cross Cutting Issues

Many of the training programmes in the region include gender and HIV/AIDS sessions especially those conducted by EMI. Some officials have been funded to attend gender mainstreaming training. Environmental issues are addressed in various sectoral strategic plans concerned with agriculture, rural development and municipalities. There is no real consideration of environment in terms of PSCAP however. The CSRP has invited proposals for material assistance from HIV/AIDS clubs in schools but have received no response.

Woredas have established Gender Desks and assigned gender focal persons in other offices. Similarly they also have HIV/AIDS desks which try to give support to AIDS orphans and promote awareness in schools and at kebele level.

# Assessment of programme outcomes

  - Enhanced predictability of financial resource flows in-year and across years

This is a very difficult indicator and hardly applicable in the Gambella political situation which has been somewhat unstable over past years. Having said that, federal regional subsidies have shown consistent and steady growth (annual rate of 8.6%) over the past 4 years. There was a drop in actual disbursement in EFY 1997 however.

As stated earlier in the report, the woredas in Gambella are receiving block grants although these are not formula driven and are hence potentially less predictable. Year on year increases are high however and the Region receives the highest level of subsidy per capita (around 600 Birr) in the country.

  - Greater inclusiveness and transparency of planning and prioritisation processes

The introduction of strategic planning has had significant impact on this indicator although there are virtually no capital funds available after payment of salaries and recurrent costs at woreda level to implement the projects which are planned. One of the woredas visited displayed a range of photographs of its recent public annual plan meeting.

  - Improved quality and efficiency of government operations in priority sectors

Some sectoral services are improving as a result of CSRP e.g. it is now possible to get a licence from the Bureau of Trade and Investment in 2 to 3 days instead of the previous 2 to 3 months. Lack of capacity, local jealousies and a lack of merit based appointments however remain as fundamental challenges still to be overcome. Service blockages also create opportunities for corrupt practice.

In education, pupil teacher ratios vary enormously from 18:1 in rural Kebeles to 120:1 in the small towns. Enrolments are said to be increasing in the towns but decreasing elsewhere. In agriculture there is only 1 Development Agent per kebele against a target of 3.

School Net is much appreciated by the people. Running for the past 2 to 3 years in 6 out of the Region’s 7 High schools, it is helping to overcome the shortage of qualified teachers – only 28% have degrees and are appropriately qualified. The equipment provides programmes for 7 study periods through each day.

  - Improved incentive environment for public servants (gender disaggregated)

As in all other regions salaries for public servants are relatively low and staff turnover is high especially at regional level.

  - Enhanced revenue performance and fiscal autonomy

Although the revenue figures provided by the Bureau of Revenue and BOFED are somewhat inconsistent, it does seem that there is an upward trend. As the TSRP gets more fully into operation, this trend is expected to continue.

Taxpayers so far have noted little improvement in the tax system, however the Chamber of Commerce did not see tax issues as a major problem e.g. in the case of Presumption Tax.

  - Improved transparency and accountability

One woreda visited was making moves towards openness and accountability by holding public conferences on their Annual Plan. Others are setting up grievance handling facilities in each office.

The introduction of Urban and Rural legal frameworks will go some way towards establishing clearer roles and responsibilities but these are not yet proclaimed. Once training begins on the Good Governance Package, the region expects to see further improvements in transparency and accountability.

There has been little overall improvement in the time taken to process cases by the judiciary as the main constraint is an absolute shortage of judges – there were only reported to be 4 for the High Court but this has recently been increased to 6.  Cases still take 2 to 3 or more years to be decided.

The police believe in some areas they are offering a better service to the public and are treating people better in terms of their human rights. They recognise continuing weaknesses in their capacity to carry out criminal investigations. Some citizens also report bias in treatment based on ethnicity.

# Key issues arising from assessment

- Gambella made a late start in PSCAP and is only now getting fully engaged in the programme. The late release of funds for the current financial year has undermined the momentum that was building in 1999 EC or 2006-7.

- The Programme is appreciated by the Region as very important for its development. PSCAP has the support of the Regional President but more needs to be done to create awareness and understanding of the programme at Regional, Zonal and Woreda level.

- There is no Regional IEC strategy.

- Gambella is making progress in building capacity and but from a low capacity base.

- Staff turnover and transfers are exceptionally high. Many bureau heads and deputy heads have been in post less than a year.

- Earlier insecurity in the region and nationality tensions within the regional administration have hindered capacity building.

- There is a serious shortage of qualified personnel in Gambella. Low salaries, lack of incentives, the hot climate and the politics of the region deter retention and in-migration and of high calibre personnel.

- There are few training facilities or high calibre trainers. Much of the training has been conducted at outside venues or by bringing in trainers from EMI or other regions.

- There is very little monitoring of outputs or outcomes at the present time. All energies are being focused on getting the activities of the sub-programmes moving.

- The Bureaus managing PSCAP, mainly BCB and BOFED, require further strengthening in terms of qualified/trained staff to provide greater momentum for the programme.

- Procurement delays have undermined the credibility of PSCAP. Many items from the 2005-6 order have still not arrived. In a region lacking many basic items of equipment this has been a serious handicap.

- There are serious questions regarding the quality and suitability of the equipment provided through the first round of ICB. Many computers are breaking down or are not up to the required standard.

- The capacity of the region to sustain a system as technically sophisticated as Woreda Net given the harsh environment and the difficulties of qualified staff retention should be re-evaluated.

- Negative lists especially the exclusion of vehicles is limiting the mobility of the regional staff in terms of facilitating PSCAP programmes in the Woredas.

- No consultancies of consequence have been procured in Gambella. The UMCBP complains of the BCB not following up on the comprehensive procurement documents provided to them.

- It is more practical for the Region to inject technical content into its sub-programmes by importing facilitators either from other regions or from outside to work with its own task teams.

- Training comprises the vast majority of PSCAP expenditure. It is the most easily organised activity given the PSCAP implementation arrangements. Some of the training was reported to be of questionable quality.

- Despite the various limitations and issues listed above, Gambella is making gradual progress with reported improvements at both the output and service level.  Relationships between the government and the people are reported to be improving. Financial flows through block grants and local revenue are slowly increasing.

# Lessons learnt and recommendations

- Gambella Region requires additional technical support with regard to overall programme management, PSCAP financial management and to help it develop and run most of the PSCAP sub-programmes. This could take the form of a temporary facilitation unit staffed with experienced officials perhaps drawn from other regions or from MFA. The facilitators should aim to build the capacity of the Gambellan officials in post by provoking improved programme content and speedier implementation and by providing training.

- An alternative approach would be to follow the example of the UMCBP and provide facilitators for each sub-programme. Again, it is important that external support is provided with sensitivity and an emphasis on building local capacity rather than simply ‘getting the job done’.

- More attention and support could be provided to the Region by the federal sub programmes. This could be reinforced by the JSMs.

- Study Tours could be used more frequently to other regions to increase exposure to ideas and more dynamic work practises. They could also develop linkages which would help to energise the sub-programmes and bring in external trainers etc.

- There are some well organised NGOs and other donor agencies in Gambella. It might be useful to explore their scope to support some of the sub-programme activities.

- Procurement delays require urgent attention by BCB. More local procurement of higher quality and locally serviceable equipment is required.

- Regular meetings of the Regional Technical Team should be established to co-ordinate and monitor the PSCAP sub-programmes as well as appraise and advise on PSCAP plans.

- Gambella, like all other regions would benefit from streamlining of the PSCAP planning procedures proposed in this report. In a region where capacity limitations are so critical, it is highly inappropriate that the capacity that does exist should be absorbed by such bureaucratic requirements.