Annex 5: Justice Systems Reform sub-programme report

# Background

Steve Topham and Ato Eskinder Tesfaye assessed the operation and impacts of the JSRP in a series of meetings that took place between 10 October and 5 November 2007. Meetings were held with the representatives of the JSRP at federal level, and in Benishangul-Gumuz and Amhara regions. Visits were made to three woredas in each region to assess progress of the programme, and inputs were received from other members of the evaluation team who visited other regions and woredas, and met with the JSRP coordinators. Meetings were also held with JSRP implementing agencies, including the Justice System & Legal Research Institute, federal and regional supreme courts, the House of Federation, and representatives of the police and prison services. The Team also met with representatives of the legal profession and civil society organisations active in the fields of access to justice and women’s legal rights. The Team examined various programme documents and progress reports.

The Team would like to thank all the interviewees for their time and interest in sharing their information and insights.

# Evaluation of main components

## Background

The Justice System Reform Sub-Programme (JSRP) aims to strengthen the functions of the justice system, increasing its efficiency and effectiveness to deepen democracy and the rule of law. The JSRP is coordinated by the Justice & Legal System Research Institute (JLSRI), which accounts to the JSRP National Steering Committee and the Ministry of Capacity Building (MCB). PSCAP is intended to build on the achievements of previous programmes of support to this sector, and roll out capacity building, equipment and technical improvements at a national scale

This sub-programme has four components:

- Strengthening the capacity and institutional arrangements (now falling under the JLSRI) to carry out sub-programme responsibilities, including production of materials, design and packaging of training events, M&E systems, and knowledge and information dissemination

- Law reform and revision of legislation, which covers the review and improvement of existing legislation, drafting of new laws, publication of laws and legal research. This component draws on legal and technical consultancy services to support GOE staff and the judiciary.

- Strengthening the judiciary, through improved professional development of judges and clerks of the court, improving the quality of legal training and academic courses, identification of actions to improve access to justice, and design and installation of new systems to manage case loads and court records.

- Strengthening law-making processes through capacity building for political office bearers in federal and regional legislatures, covering legislative processes, principles of good governance, and specific focus issues including gender aspects and HIV/AIDS.

In addition to the training for legislators mentioned above, this sub-programme includes an explicit focus on gender issues, with a special focus on the training of female judges and the increase of women in the legal professions.

## Strengthening the capacity and institutional arrangements to carry out sub-programme responsibilities

The JLRI has had the responsibility for management the JSRP since December 2006, after it had been transferred from the MCB. The JLSRI reports that it has a solid working relationship with the MCB, and it also accounts to its Board of Directors. The Institute has become more familiar with PSCAP procedures over the past year, but although the disruption caused by the incorporation of the CIDA-supported Court Reform Programme, and the reassignment of management responsibilities has been largely overcome, there are still some aspects of coordination that are being strengthened.

Coordination is a particular issue in this programme. The overall objective is to promote improved access to justice, which requires a ‘joined-up’ system involving the courts, the justice administrations, the 3Ps of police, prisons and prosecutors, and federal and regional law-makers. However, there is an institutional tendency for these organisations to operate in parallel, rather than cooperate to improve integration.

To this end, the Institute is establishing a monthly technical committee with its regional counterparts, to help in annual planning of the programme, assess and assist in requests for technical assistance, and to share experiences and best practice.

## Law reform and revision of legislation

Prior to PSCAP there had been revisions to the existing criminal law, and a new Family Law has recently been developed and adopted at federal and regional levels. Copies of this law, and training in its implications have formed part of various PSCAP capacity building activities at federal, regional and sub-regional government level. It is beyond the scope of this evaluation to comment in detail on the quality of this law, but it is seen overall as a positive step in promoting gender-equality in a male-dominated culture. Academic research has identified potential problems in its implementation, and recommends that the Supreme Court clarify certain vague provisions within the new law (Demissie, 2007).

The JLSRI is providing technical assistance on the drafting of new legislation, and a further 19 new laws are due to promulgated in EY 2000.

## Strengthening the judiciary

This component has achieved some of the most impressive results of the whole PSCAP programme, and clearly befitted from a very strong foundation laid down by the CIDA-supported Court Reform Programme. The lessons, innovations and activities under this programme are being applied on a much wider scale, and with a great deal of confidence and purpose.

There has been a remarkable improvement in the professional capacity of the judiciary and support staff (court administration and Bureau civil servants), with a wide range of training activities completed. These include:

- Court reform awareness

- Professional development, including briefing on new laws

- Client awareness training

- Ethics and accountability

- Administrative and technical skills, including word processing and computer skills, and using the case management database system,

There is a concerted effort to improve the formal qualifications of judges, with significant numbers studying and obtaining upgrades in their qualifications at diploma and degree level.

This increase in professional skills of court staff and the judiciary has been complemented by improvements in the operations of the courts themselves. The colour-coded case management system has been widely instituted, and there are progressive innovations to improve efficiency and the targeting of justice, such as the introduction of family courts, secluded areas for breast-feeding mothers, and more welcoming court layouts and waiting areas. Information desks are in place at federal level courts and being rolled out at regional and sub-regional level

As a result there have been remarkable gains in court efficiency – clearance rates have increased and backlogs almost eliminated, and there has been a reduction in the average time for cases to be heard and judged. Minimum standards have been adopted which help explain the improvement in performance – there are targets set for the number of cases to be heard each month by judges in regional supreme courts, high courts and woreda courts.

Equally importantly, there is a concerted effort to measure performance and outcomes of training activities, and to institute an effective system of self-monitoring and performance evaluation. Regions have instituted a system of reviewing judges’ performance, including monitoring the number of cases that are passed through on appeal to higher courts and their subsequent judgements. A Disciplinary Committee can then report on these matters to the Judicial Council, which can issue sanctions on judges for low performance and poor quality of judgements, including reprimands, reduction in salary, or dismissal. Conversely, judges with consistently high performance are rewarded with commendations and opportunities for advancement.

The Evaluation Team noted that in Amhara, senior court administrators estimated that the average cost of handling each case in the judicial system was Birr 111. This is one of the very few cost efficiency measures identified in the PSCAP programme.

The current plan for the programme (JLSRI, 2007) includes proposed actions to strengthen the National Judges and Prosecutors Training Centre. It also addresses the issue of improving the nature of legal higher education, through a major set of activities to improve graduate and post-graduate academic courses. This is a logical intercession that seeks to improve the training of legal professionals, and challenge the outdated and overly pedagogic nature of law schools in the country. It is a welcome and holistic longer-term intervention to improve the overall quality of legal practitioners, and should be pursued actively.

## Strengthening law-making processes through capacity building for political office bearers

PSCAP-supported training is delivering positive results in the improved quality of law-making procedures and more efficient administration of Regional Councils and sub-regional government structures. A wide range of training has been supplied on topics including:

- Good governance

- Workings of the parliamentary system, and multi-party democracy

- Ethics, oversight and accountability mechanisms

- Human rights and the Constitution

- The roles of council members in governance and law-making.

The House of Federation has played an important leadership role in helping raise Constitutional awareness, and that copies of the Constitution have been printed and distributed widely.  The Evaluation Team noted that care is taken at regional level to structure training programmes to take into account experience, education and literacy levels of participants. Similarly, some attention is paid to assessing the impact of the capacity building programme. While progress on the quality of law-making may only be discernable after a long period, the general perception reported to the Evaluation Team is that there has been a gradual improvement over the past three years, with the Regional and woreda councils operating in a more democratic fashion and more open to considering new ideas and issues.

## Law enforcement capacity enhancement

The PSCAP programme is making a valuable contribution to strengthening law enforcement capacity, although this needs to be expanded in the future. Police and prison officers have been given generic training at federal and regional on human rights awareness, the penal code, HIV/AIDS and leadership training. In addition, police officers have received training in specialist subjects including community policing, control of drug abuse, crime investigation, exhibit management and forensic investigation.

Both services are under-funded, and the PSCAP programme has made also been important is supplying computers and equipping training rooms.

The training on community policing is particularly important, as the new approach is being disseminated from federal to regional level, and gradually instituted in woredas and urban municipalities.

Both prison and police services reported a constructive relationship with the PSCAP process, and had been involved in planning and programme coordination through the various coordination structures at federal and regional levels. However, final budget allocations are small, and the procurement process is tedious.

PSCAP budget allocations for the 3Ps (police, prisons and prosecutions) are a structural issue within the programme. IDA rules forbid the use of its funds for activities to support these services, requiring any shortfall to be made up from other programme resources. Given increasing of constitutional and human rights within the country, and the introduction of community policing at local level, it is important to ensure that sufficient funds are provided to support these activities.

# Programme Management and Support

## Institutional Arrangements

The JLSRI was the original designer and coordinator of this programme, which began in 2003, and led to revisions of the criminal law, and increased professional training for judges and prosecutors. With the introduction of PSCAP in 2005, this programme was transferred to the control of the MCB. A subsequent review of PSCAP progress and implementation arrangements led to this responsibility being transferred back to the JLSRI in December 2006. The JLSRI reports to its Board of Directors and the National Steering Committee, as well as the MCB.

It also has to coordinate and plan the programme with nine partner institutions involved in legislation, law enforcement, human rights and justice. These are:

- The Supreme Court, and the Judges and Prosecutors Training Centre

- The House of Parliament and the House of Federation

- The Human Rights Commission

- The Office of the Ombudsman

- The Ministry of Justice

- The Federal Police Commission

- The Federal Prison Administration

- The Federal Anti-Corruption commission.

Given this range of agencies involved, it is unsurprising that coordination is a challenge in the programme, and the Evaluation Team noted reports of disconnection between the court reform process and other components. The monthly technical committee that is to be established by the JRSLI with its federal and regional counterparts should assist in developing a more integrated approach to programme planning and delivery.

The programme action plan for EY 2000 includes a proposal to strengthen the management capacity of the JRSLI with extra professional staff in the areas of planning, financial management, procurement, monitoring and evaluation, and programme management. This seems necessary for the effective running of the programme as activities continue to expand and become more sophisticated.

## Planning and resource allocation

Planning of the JSRP has improved over the three years of PSCAP. The JRSLI has coordinated inputs from its partners and implementing agencies into an action plan for EY 2000, which includes projects carried over from previous years, new initiatives, and proposals to strengthen JRSLI capacity.

Previous supervision and review missions have noted complaints about inadequate allocation of financial resources against planned activities. The current plan sets out an explicit budget against the programme, with a total request of Birr 242 million split between new projects (67%) and ongoing commitments (33%).

The EY 2000 action plan has a fairly clear structure with actions bundled together under the implementing institution. The plan can be improved by a synthesis of activities under the various programme objectives they are meant to achieve, which would allow for a better understanding of the balance of resources and prioritisation. Activities that support cross-cutting issues should also be clearly separated.

## Sequencing and integration of reform initiatives

The Evaluation Team is of the opinion that there are no major issues in respect of sequencing of reform initiatives. Integration should improve through the workings of the new technical committee to be established by the JRSLI.

## Procurement

Procurement has proved to be a constant source of frustration in the programme. The Evaluation Team received reports of difficulties with the operation of procedures at federal, regional and sub-regional level. The 2000 procurement plan had been awaiting a no objection letter for four months at the time of this evaluation. The slowness of the process and delays in receiving approvals for purchase and no objections has a serious impact on programme management and leads to slippage. Most of the projects in the ‘ongoing’ category of the EY 2000 programme action plan are for procurement of goods and consultancy services, and it seems likely that their carry-over from the previous year is at least partly due to delays in the procurement process.

## Monitoring and evaluation

Monitoring and evaluation is an area of the JSRP where there needs to substantial improvement. No progress reports have been submitted to the MCB PPD since December 2006 (EY 1999), and many of the implementing and regional agencies are less than diligent in providing coherent information on a regular basis. For example, a consolidated list of new laws passed is only available for the Federal level; the regions do not automatically passed on this information to the JRSLI or MCB.

The dynamics between federal and regional level government has an influence on this issue. The MCB is taking steps to address this by calling a conference of all regional JSRP representatives to explain the purpose of and reinforce the need for more efficient flows of information. Hopefully once there is agreement on this a regular system of data flow can be instituted.

In addition, the programme will establish a new documentation centre in November 2007. This will act as a central repository for information, and should greatly improve central collection and analysis of data.

However, most information collected so far relates to the quantitative aspects of the programme. There have been few, if any, evaluations of the programme impact on the quality of justice provided. After three years of PSCAP, and its predecessor programmes, there really should be assessments of whether it is increasing access to justice for the poor and other disadvantaged groups. The effect on women is another serious gap to be addressed. The PIP makes specific reference to the need for periodic studies on these aspects. There are specialist groups and civil society organisations with the experience and resources to carry out this type of qualitative and social research, and it strongly recommended that specific studies be commissioned on these areas.

## Information, education and communication

The Evaluation Team were not made aware of any effective IEC strategy for this programme, although specific public awareness activities are taking place at federal and regional level. The EY 2000 action plan sets out proposals for leasing air time on TV and radio for public education on legal and human rights, and ethics and anti-corruption awareness, as well as printing and distributing brochures, posters and pamphlets. These activities are valuable, but should be consolidated within the framework of a medium term IEC strategy to ensure that there is consistent messaging and targeting of specific communities of interest.

# Assessment of cross-cutting issues

The JSRP is one of the few PSCAP programmes with a professional training component targeted explicitly at women. The focus on improving skills, qualifications and competency for women judges and prosecutors is highly commendable. The EY 2000 Action Plan also includes:

- In-house training to upgrade the skills and competencies of women support staff in the Ministry of Justice

- In-house training for justice sector professionals in prevention of trafficking in women and children

- In-house training for justice and health sector professionals in integrated rape case management

- Gender policy and mainstreaming awareness training for representatives in the House of Parliament.

Gender awareness training is a widespread activity in the programme at federal, regional and sub-regional levels.

The Evaluation Team noted that training activity data is collected on a gender-disaggregated basis, but that few impact assessments have been conducted on its effect on women. Possible longitudinal studies could include assessing the total number of women judges, broken down by level of qualifications, and the status of courts within which they serve. Measured over a period of years this would give some idea of whether the judiciary was beginning to match the profile of the community it serves, and whether professional advancement for women professionals was actually being achieved. Reference has already been made to the need for external evaluation on the impact of reforms through assessing the experiences of women as clients within the justice system.

PSCAP is assisting to mainstream HIV/AIDS issues in the justice sector through widespread awareness training.

There was no evidence of any mainstreaming of environmental issues in the JSRP at any level.

# Overall assessment

The JSRP is progressing very well and expanding its scope to support and strengthen the various organisations that act as watchdogs on the operations of the civil service and justice systems, including the Office of the Ombudsman and the Anti-Corruption Commission. Activities to improve the quality of legal education are welcome, and should lay a base for the longer-term prospect of better-trained professionals. The 3Ps are still somewhat the Cinderella component of the programme, and need to have more resources directed at them. Gender issues are well mainstreamed, and the programme’s activities on improving the status of women professionals must continue and be expanded. Programme management under the JRSLI is improving, but the extra staff and professional resources requested should be approved if the improvement is to continue.

# Lessons learnt and recommendations

The key lessons from the performance of the JSRP so far are to highlight the need for strong programme management to handle a complex programme that involves a very wide range of institutions, which in themselves have very different natures. The uniformed services are completely different from the democratic organs of government, while the independent judiciary has a different status and constitutional role. Yet all must be integrated to create the joined-up system of justice that is essential to achieve the objectives of reform.

The Evaluation Team makes the following recommendations:

- The JLSRI must be given more staff and professional capacity dedicated to programme management

- There must be a concerted effort by all JSRP partners to improve the regularity and consistency of progress reporting, data collection and analysis. The proposed JSRP Documentation Centre must be established and brought on-line without delay.

- The JSRP should commission qualitative and social research on the impact of the programme and the experiences of those using the justice system. The studies should be independent, and specialist civil society organisations with experience in these areas are likely service providers.

- The JSRP should develop an IEC strategy to accompany its action plan

- The JSRP action plan should be improved by the inclusion of a synthesis of activities set against the programme objectives they are designed to achieve. The plan should also identify clearly activities that address cross-cutting issues.

# References

Demissie W, 2007. ‘Implementation Problems of the Revised Family Code’, in Berchi: Annual Journal of the Ethiopian Women’s Lawyers Association, Issue 6.

Justice & Legal Research Institute, April 2007. Justice Reform Programme Action Plan for 2000 EFY.