Annex 18: Tigray report

# Background

Crispian Olver, assisted by Atto Birhanu Seboka, visited the Tigray region from 22nd to 26th October 2007 and met with the BCB head and PPD, BOFED, the Bureaux for Justice and for Works and Urban Development, various sub-programme coordinators, the Supreme court, the Police Commission, the Prison Administration, the Auditor General, the Ethics and Anti-corruption Commission, the Mekele and Wukro municipalities, and five woredas (see annexure 22 for full list of persons). A large number of documents were collected as part of the assessment, and these are listed in annexure 23. The evaluation is based on interviews with key informants, previous PSCAP reports and documents collected from the different sub-programmes.

The PPD Director, sub-programme coordinators and Bureau heads generously made time available for interviews and participated in the evaluation process. The evaluation team would like to thank the various organisations and people who assisted with the evaluation and made their time available to participate in the assessment.

There are a number of discrepancies that were found between information from interviewees and the report of the JRM in April 2007. It was not possible within the time available to clarify each of these issues, and in general the information from interviewees has been relied upon in this report, except in a few instances where the context suggested otherwise.

# Overall assessment

Tigray is an established region with a well developed regional government administration. It is the northern most region of Ethiopia, with an estimated population of 4,3 million. 81% of the population are rural. The regional capital is located at Mekele.

The reform programme in Tigray is well established, and has been ongoing for the last 6 years – well before PSCAP. The programme consists of a thorough going decentralisation process designed to devolve decision making and service delivery to woreda and kebele level. At the same time there is a total overhaul of the civil service structures at all levels, with a focus on service delivery, accountability and participation. The scale of the reform programme is impressive, and it has been backed up by a clear political commitment and leadership, as well as by the decentralisation of finances. Approximately 70% of the region’s budget is transferred to woreda level through a system of block grants.

The PSCAP programme has been laid on top of this reform programme, and has functioned to provide much needed support to back up or deepen the reforms. PSCAP has therefore played a critical role in entrenching an existing reform agenda, and making it credible. However it is difficult to separate out PSCAP as a separate programme, particularly for the purpose of evaluating outcomes. Changes in service delivery on the ground have taken place as a direct result of PSCAP spending, but this has built upon prior work whose outcomes are indistinguishable from PSCAP itself.

The implementation arrangements in the region are coordinated by the Bureau of Capacity Building (BCB), which has taken overall charge of managing the programme in the region. BCB seems to have moved away from a distinct separation of programmes, and rather concentrated on an integrated roll-out of the different elements of the programme within the framework of the region’s reform programme as a whole.

In terms of progress with PSCAP implementation, Tigray has done well. The decentralisation process and focus on participation, performance and service delivery have resulted in significant changes at levels of the regional government, and established a large number of best practice examples.

Most minimum mandatory activities in Tigray region were completed by the time of the JSM in April 2006, and all were confirmed completed by the JSM in April 2007. This evaluation has in fact identified a few instances where the MMAs have not been completed, but mainly in areas where the MMA is no longer relevant to the way the sub-programme is being implemented. There is significant progress with each of the sub-programmes, which is described in more detail below.

# Assessment of implementation of each sub-programme

## JSRP

### General observations

There have been very significant achievements by most of the beneficiaries of the JSRP sub-programme, and there are a large number of best practice cases which have developed. This is partly the result of the high level political support and coordination provided by the regional government, and partly the solid basis laid for the sub-programme by the pre-existing programme funded by CIDA. The region has embraced the concept of “joined up justice”, and there is a high level steering committee, chaired by the President of the High Court, which brings together the heads of the Justice Bureau, the Prison Administration, the Anti-corruption Commission, the Security and Administration Affairs Bureau, and BCB. The steering committee drives the overall reform of the justice system in the region, and is not specific to PSCAP. BCB acts as secretariat to the committee.

The JSRP sub-programme itself is coordinated by BCB, although the JSRP coordinator is overloaded with other responsibilities (see DLDP report) and is not able to play an effective coordination role. It appears there is no coherent JSRP coordination, and rather a set of discrete initiatives within the different beneficiaries, which are guided by the overall approach to “joined up justice”.

### Strengthening the judiciary

There have substantial reforms and improvements within the court system, and this is one of the areas of highest achievement both within the sub-programme and the regional programme as a whole. There has been a significant effort to build a decentralised justice system, with strengthening of the woreda courts, at the same time as improving the overall level of service delivery. There are now 90 woreda courts, and 6 zonal courts (this is currently being extended to 7), in addition to the high court and supreme courts. All the judges now have degrees or diplomas, as a result of systematic upgrading of judges’ skills done with PSCAP funds. At the same time the level of participation by women in the judiciary has increased significantly, with 45 women overall in the judiciary, including 3 women in the high court and 3 in the supreme court. This is approximately 20% of the judiciary.

A large amount of training has been done, both for the judges and the court civil servants, on criminal procedures, standardising sentencing between courts, the “joined up justice” approach, strategic planning for the courts, and performance evaluation of judges. A training centre for judges has been established at Wukro using PSCAP resources, and federal trainers have been linked to the trainees using video-conferencing. Last year 136 judges and prosecutors were trained, and 8 judges went to the federal training centre. This has resulted in a complete change of mindset within the judiciary, towards a culture of service and accountability to the public.

There have been a number of specific interventions to improve administration and efficiency. The courts have been equipped with a heavy duty photocopier, computers and a plasma screen, linked into the woredanet system. This has allowed the remote hearing of appeal cases referred from the woredas, which is much more convenient for the individuals involved in the cases. At the same time the jurisdiction of the woreda courts has been increased, thus decreasing the load on the supreme and high courts.

Recording and transcribing machines have been installed in the supreme court, zonal courts and 8 woreda courts. The colour coded filing system has been introduced in the supreme and high courts and 8 woreda courts, together with a database filing system.  A manual on filing has been compiled. There has been a massive improvement in the filing system, with cases no longer being lost, and files easily found. An information counter has also been installed in the supreme court.

Alongside these changes there has been a focus on the court management systems, with the introduction of strategic planning, performance standards and measurement, and assessment of individual judges’ performance. A manual has been prepared indicating the maximum time that can be taken for different types of cases. The courts have also introduced a community outreach programme, including meetings with the public twice a year.

The results of these reforms have been significant. The courts are now clear of backlogs and congestion of cases. There was a commitment from the courts to dispose of cases prior to the new millennium, and in the end the supreme court carried over 60 cases to the new year, and the 90 woreda courts carried over a total of 400 cases. The courts have introduced a tool known as the court performance standard and performance assessment system, together with a manual. All the courts now assess themselves in terms of access, speed, efficiency, equity, integrity, fairness, independence and public trust. The average score across the courts was 76%, and on the efficiency score only the figure was 89%.

### Law revision and law reform

The legal framework for the new approach to justice, linked to the overall decentralisation process, has been created. A new Criminal Law was passed in EFY 1997, which has significantly improved the legal framework for criminal matters and their processing by the courts. An amendment has been passed to the Proclamation for the Establishment of Courts to increase the jurisdiction of woreda courts, by, for example, increasing the threshold amount to Birr 10 000 for civil disputes.

The supreme court has now compiled all the proclamations issued by the regional council since its formation, and circulated these as a legal reference to all courts. This has significantly assisted the administration of justice, as previously many woreda judges were not able to reference legislation. A similar exercise is being undertaken for all federal proclamations, which will be compiled and circulated this year.

### Law enforcement capacity enhancement

The region has put a lot of effort into building the capacity of the 3Ps – police, prosecutors and prisons, and the focus on service delivery, accountability and performance has been effectively carried through to the 3 Ps. This is critical in order to ensure the reforms are sequenced across the different components of the criminal justice system, and therefore to create equivalence between the different components, and hence build the overall effectiveness of the criminal justice system. A frequently raised concern in the region was that the World Bank does not finance the 3Ps, and that these components are under-funded as a result.

The police have transformed from a low base, in which their members had little or no accountability to the community, no commitment to community service, and little contact with remote areas. The police have been refocused towards community policing, and working at a grassroots level through kebeles. Manuals have been prepared on community policing, and the new approach has been communicated through workshops and exchanges between police in different locations. These exchanges were found to be particularly useful, as they have built a common language between the police, enabling effective communication from top to bottom.

A large training effort has been undertaken - there has been training in crime prevention, investigators have received technical and tactical training, radio operators have been trained on communications and radio. Training and exchange of experiences has been arranged for finance and human resource managers within the police, with practical mentoring of trainees. 100 police were recruited and trained in road safety and traffic policing.

There have been major changes on the ground, that reflect this new approach to policing. The core focus of policing is now service delivery. There is an attitude change in the police, with some police doing community service, such as arranging for street lights to be fixed. Communities are increasingly holding local police accountable, and police are attending community forums at which security issues are discussed. Communities have taken the initiative in some areas, set up community police stations, and recruited community police teams to assist the police.

The speed of processing cases has increased, and cases are handled within the framework of the law, which protects the rights of citizens and the accused. Investigators are critically evaluated in terms of their compliance with benchmarks, and breaches of the code of conduct are treated seriously. There is a process of open evaluation of performance of police by communities. There is also a process of reporting to parliament on progress, the handling of cases, and discipline. Police are all aware of human rights issues in policing.

Similar changes have happened with the prosecutors, who fall under the Justice Bureau. The Bureau did a situational analysis, which highlighted service delivery, efficiency and accountability as weak points. The justice system did not have the public’s trust or confidence. The Bureau produced a policy paper on reform of the prosecutorial service, which introduced the concept of a community based prosecution system. People’s participation is seen as key, both as witnesses and as victims of crime. Accountability has been introduced as a new concept for prosecutors, and this has been clarified in terms of ethics and a code of conduct. Manuals on service delivery, performance and evaluation were produced. Professional capacity has been addressed through training for 250 prosecutors in case flow management, skills to prosecute cases, and trial and advocacy techniques.

The outcome has been an attitudinal change in prosecutors. The Wukro prosecutors’ office is a shining example or the new approach. The office has adopted a customer focus, and publicly displays its statistics with regard to case management. Customers are informed of what services they can expect and the standards for each service,  they are treated with courtesy and their issues addressed promptly. The conviction rate has increased significantly over the last five years, resulting in a drop of crime from 815 cases in 1995 to 233 in EFY 1999. The office has also pioneered a focus on domestic violence and crimes against women, with a special service for gender violence and family cases.

There have also been significant changes in the prison administration, with a large amount of training done through the police training centre on human rights, the handling of prisoners, counselling and rehabilitation of prisoners, and finance and resource management. The results have been better leadership within the prison team, observable changes in behaviour towards prisoners, the establishment of rehabilitation programmes for prisoners, and better service delivery for prisoners’ families and friends. Trainees, prisoners and their families have been involved in assessing the changes, and ratings between 80 and 90% have been given for performance.

### Legislative organ

Training was done for all regional council members on parliamentary democracy, human rights, ethics and monitoring and evaluation. Two important manuals were prepared on the parliamentary oversight role, and the monitoring and evaluation of the executive and legislative bodies. Five different standing committees of the regional council were also trained in the above topics.

This training was also taken down to the woreda level, with training given to woreda council speakers and their assistants.

As a consequence the legislature has been able to exercise more effective oversight over the regional government, critically assess the progress with reform, oversee sound expenditure management, and hence build accountability.

## UMCP

The urban management sub-programme is managed by the Bureau of Works and Urban Development, and started in EFY1997. Its main effort has been around policy and strategy development, which has been translated into legislation, manuals and rolled out through a large number of training activities. The CBDS programme under the World Bank laid the basis for much of the work, which has then been incorporated into the PSCAP initiative.

The urban good governance initiative is the framework for coordination of the urban reform agenda in the region. The regional President chairs a steering for urban good governance, which brings together 7 Bureau heads, and meets quarterly. The Bureau of Works and Urban Development chairs a technical committee which meets monthly to oversee implementation. The PSCAP sub-programme does not appear to have a separate coordination mechanism outside of this arrangement, and PSCAP resources are increasingly used to support the urban good governance programme.

### Regional urban management policy

The region has established the legal framework for urban local government with the EFY 1995 Cities Proclamation, which was revised in EFY 1999. 12 cities have been recognised in terms of this legislation, which sets out their powers and functions, establishes their councils and committee structure, and creates two layers within the cities – the city and tabias. The region has finalised its urban development policy and strategy, and this has been translated into a five year action plan. Two further strategies, on infrastructure development and housing development, will be undertaken this year. The region has also developed and adopted urban land legislation, which has been translated into municipal proclamations.

### Deepening the process of decentralisation

A number of measures have been implemented in order to assist the process of decentralisation. Most significantly, the fiscal framework has been decentralised, and regional government finance offices have been merged with city treasuries into a single municipal treasury. This has totally changed the previous structure, and has implemented the region’s policy of “one vision, one city, one finance”. The cities now collect the tax revenues that previously accrued to the region, and there is a formula for the division of tax revenues between the cities and the region. There are no block grants from the region to the cities, but the new system gives them substantial fiscal autonomy.

A municipal organisational structure has been created for 47 municipalities. 12 have been designated as cities, and the remainder are categorised as emerging and placed in one of three categories. The structure is centred around the creation of committees to oversee key functions and ensure the implementation of integrated development plans.

The main thrust of the changes is around a bottom up process of participation and planning, which has been in operation for over a year. Participation at kebele level is designed to include interest groups such as investors and civil society associations. Kebele representatives attend a city wide representative forum for planning that develops the IDP for the city and translates it into a budget and annual action plan. There is an annual public conference to evaluate progress against plan.

Meetings with the Mekele and Wukro municipalities confirmed the restructuring that has taken place, with administrative capacity largely devolved to kebele level. In Mekele most municipal services are now provided through the 7 kebeles, which have equivalent status to woredas. Each kebele has a development committee, and is allocated a capital budget to deal with local priorities. Communities set priorities for infrastructure provision, land delivery and release. Politicians and civil servants are held accountable for performance through kebele and municipal councils.

Physical planning units have been created in each city, supported by the Regional Urban Planning Institute. The Institute services all cities with capacity building for planning, and preparation of urban development plans. It also maintains a database of urban plans.

The region is planning to establish a regional municipal association next year.

### Local government restructuring and capacity building

A human resource strategy for municipalities was developed two years ago, and then handed over to BCB for implementation. A wide variety of manuals (22 in all) have been prepared to assist municipalities in areas such as urban design, project management, service delivery, kebele upgrading and housing cooperatives. Specific initiatives worth mentioning are:

- The financial procedures, systems and implementation manual.

- A prototype computerised system for financial management.

- Manuals with procedures and guidelines for urban land lease hold.

- Establishment of personnel management authorities and improved municipal service delivery systems.

- A strategic plan for municipal infrastructure and financial planning.

These have been followed up by a large amount of training of municipal personnel and managers in areas such as strategic planning, IDPs, financial management, housing development, land management, good governance, project implementation, and urban industrial development. BPR has been undertaken on a pilot basis in some of the municipalities, including Mekele.

There has been a gender focus in some of the training. Gender issues are taken up in IDPs, and specific efforts are made to involve women in the planning exercise. There have been gender offices set up in all municipalities. It was estimated that approximately 10% of the participants in training programmes were women. Environmental issues are addressed in the programme through a focus on greening the cities, solid waste management, urban pollution and environmental degradation.

There have been some noticeable improvements as a result of these reforms. In both municipalities visited there has a visible attempt to focus on service delivery. Signage in municipal offices indicates the services that are provided, and the standards that can be expected. Municipal staff wear name tags, and their offices indicate their functions and delegated responsibilities. A number of municipal services have shown dramatic increases. For example, in Mekele the time taken for processing of industrial land applications has improved from approximately a year to less that a day. Subdivisions of land have improved from one year to approximately one month. Mekele has set a target of 85% customer satisfaction for this year, and are implementing a systematic approach to evaluating this.

However some of the municipal managers interviewed did not believe that the capacity building provided was efficient. The regional initiatives were at times viewed as hierarchical and bureaucratic, and the region itself lacked the capacity to implement the ambitious reforms it proposed. Weaknesses in leadership prevented implementation of many reforms, and the municipalities are still focusing on getting their day to day activities done.

A systematic evaluation process has been instituted in some cities and towns. Comprehensive pilot evaluations were done in two towns last year, and other municipalities are copying the approach. There is also a monthly system of evaluation established for the urban good governance programme. The Bureau of Works and Urban Development meets with cities twice a year to evaluate progress, and best practice experiences are shared through visits to model cities.

## DLDP

The DLDP programme is managed directly by BCB, although the DLDP coordinator has multiple other tasks, and there does not appear to be a discrete DLDP programme separate from the broader tasks of implementing the rural good governance package. The DLDP office has three staff, but they all have multiple other responsibilities. The PPD indicated that DLDP has accomplished two main tasks, namely the development of human resources in woredas, and supporting the implementation of the rural good governance package.

The region has a high level mechanism for the coordination of the rural good governance programme. A steering committee, chaired by the regional President, brings together the relevant Bureau heads to integrate plans, review progress and drive implementation.

Training on the good governance package has been rolled out in a comprehensive manner, dealing with restructuring, participation and planning aspects. First the regional Cabinet was trained, then leaders of each woreda and their executives, and then each of the 628 kebele executives (consisting of 13 persons each). The scale of the training, and the commitment to implementation of the new model, are impressive.

The programme aims to take decentralisation right down to kebele level, and indeed to the level of the individual farmer. The package includes a description of the model peasant. The chair of each kebele is meant to be a model peasant, and therefore to spend most of his time in the fields. Kebeles are therefore run by full time managers who are civil servants.

### Institutional & organisational arrangements

The legal and policy framework to support the decentralisation programme has been finalised. The Decentralisation Proclamation which decentralises power and functions to woreda and kebele level was passed by the Regional Council 6 months ago. A few additional proclamations on kebeles are in the process of being prepared and will be submitted to the Council this year.

The legal framework has been followed up with the preparation of a number of manuals which have been distributed to all woredas and kebeles. Four manuals, dealing with service delivery, information desks, complaints mechanism, and the model peasant have been finalised. Further manuals on revenue-raising, and supervision and control, are being prepared.

The systems have then been taken to local managers through a cascaded system of training, starting with Kebele managers, who have in turn trained their staff.

### Manning and training

A comprehensive assessment of the human resource requirements of all woredas was undertaken by Mekelle university, and a new structure for woredas developed. This structure was then implemented across all woredas, and a massive redeployment of personnel from the region to woredas took place. Over 8000 new recruits with diplomas, certificates or degrees were recruited and deployed to woredas. As a consequence the overall staff complement of woredas has grown from approximately 30 000 to over 51 000. At the same time an aggressive programme of training has aimed to ensure that skills in all the critical areas required by the woredas are given to staff. BCB is now of the opinion that woredas have the necessary human resource capacity to implement the functions assigned to them.

### Grassroots participation

A bottom up system of planning and participation has now been established in most woredas and kebeles across the region. A large amount of effort has gone into preparing a detailed manual entitled “Integrated Community Based Participatory Planning Approach: Practical Considerations for Local Governments and Communities at Woreda and Kebele Levels”. The manual was first tested in a few pilot woredas, and then rolled out on a massive scale. A strong emphasis was placed on gender sensitive planning approaches. In all approximately 50 000 participants were trained in the procedures through local workshops.

People participate in the planning process in the first month of the year, through kebele councils, and through their delegates to woreda councils. The medium term plan, and the annual action plan for the woreda, are discussed, as well as the budget. The progress with the implementation of the plan is also reviewed twice a year.

In terms of a new decree, the number of participants in the kebele council has been increased, so that there is one representative for every 1000 peasants. As a consequence kebele (tabia) councils have increased from between 60 and 80 members previously, to between 200 and 300 members. Woreda councils have increased from between 80 and 120 members, to between 150 and 324 members. Provision has also been made for representation of civil society on kebele councils, and representatives from trade unions, the women, youth etc made up 30% of the councils.

### Programme development

The decentralisation strategy has been guided by the Legal Decentralisation Framework Policy and Strategy Concept Paper, which was based on an in depth study of the appropriate legal framework. A regional workshop assessed the outputs of the study and reviewed possible alternatives. On the basis of the policy the legal framework was created with proclamation no. 99/98 and the functional assignment was done with proclamation no. 100/98.

The woreda benchmarking tool is not being used by the region.

### Woreda fiscal transfer and own revenue enhancement

The DLDP sub-programme does not deal with fiscal transfer issues or appear to take an active interest in such issues, and the information for this section was obtained from BOFED.

The system of block grants to woredas was established in EFY 1994, and the formula is based on population (65%), development gap (25%), and revenue capacity (10%). Approximately 70% of the regions funds are transferred directly to woreda level, which is a significant fiscal commitment to decentralisation. The percentage of the region’s budget transferred to woredas has remained fairly constant, between 67% and 70%, and is approximately Birr 800m. Approximately 70% of woredas depend solely on block grants for their revenues and do not collect any revenues themselves. Last year the formula was reviewed, some new indicators were developed, and it has been decided to move onto a needs based, unit cost approach. This revised system will be implemented next year.

The revenue collection system in the region has decentralised many tax functions to woreda level, and the region has now prepared a revenue sharing formula to apportion tax revenues between woredas and the region. This has been approved by the executive, and is ready to be issued as a proclamation. Again this represents a significant commitment to the decentralisation process.

### Woreda planning and financial control

The woreda planning system is a bottom up process designed to maximise community participation. The woredas have all been trained in the process of preparing medium term (five year) plans, which are linked to medium term financial plans or budgets. These are in turn translated into annual plans and budget. A large amount of training has taken place, and the system appears to now be entrenched across all woredas, although it is not possible to say how well the system is working in more remote woredas.

The systems of expenditure management and financial control at woreda level are managed by BOFED, and have not been incorporated in the DLDP programme (see EMCP for further detail).

### Minimum service standards

Service delivery policies and manuals have been prepared and distributed to all woredas. The include policy regarding service standards. Training on this has been done for all woreda staff. Woredas have now installed signage informing customers of the services they can expect, the time it will take for particular services to be performed, and who to contact for particular services. The application of this was certainly proved in the woredas visited, and the evaluators were informed that the system exists across all woredas.

### Office infrastructure and development

The DLDP sub-programme has provided a minimum infrastructure in each woreda, including 7 computers (this tends to vary between 5 and 13 computers, linked to the ICT training centre and woredanet), printers, a fax machine and a photocopier. PSCAP support has in addition provided internet access, e-mail facilities and hence ensured connectivity services for all woredas. This is a significant achievement.

However the lack of proper infrastructure remains a large problem for the majority of woredas – many of the woredas visited as part of this assessment raised problems regarding the lack of available offices, the lack of telephones and electricity, problems with connectivity through woredanet, and the lack of capacity to manage the technologies installed.

## TSRP

The tax systems reform programme was started five years ago, initially funded by the Ministry of Revenue. The current PSCAP sub-programme has therefore been laid on a solid foundation, and has consequently been able to produce some solid results. The sub-programme is coordinated by BOFED, who feel that tax reform is not given sufficient priority by PSCAP. Their budgets are inadequate, their action plans and procurement requests are not approved timeously, and the previous focal person in BOFED refuses to work with PSCAP, indicating serious issues with its coordination. Nevertheless the sub-programme has made some significant gains.

### Tax policy and legislation

The previous proclamation on tax was 40 years old, and did not match the new economic policy of the government. There was also very little awareness of the interests of tax payers, and a mentality that “the tax collector is king”. Consequently there was a large amount of evasion, and no understanding of the value of annual tax payments. The Bureau has sought to turn this situation around by promulgating new tax legislation, overhauling the tax collection system, and reaching out to tax payers and educating them about the new system.

### Tax payer identification number

There has been a large drive to make sure that all tax payers have an identification number. Woreda finance offices have been used to make sure that all people are registered. This has been augmented by introducing TIN as a requirement for individuals taking out a bank loan, or receiving certain services from government. The region has previously estimated a total of 20 000 taxpayers, but this year revised its estimate to 24 000. To date the region has registered 24 049 tax payers for TIN, therefore reaching over 100% registration.

The next step is for the region to expand the use that can be made of the TIN, as well as build on the benefits that tax payers can expect from TIN.

### Presumptive taxation

The region estimates that 90% of taxpayers cannot maintain books of account, and therefore the region is required to estimate annual sales to determine the tax payable. Previously there have been problems with the assessment of presumptive tax, with large fluctuations between years. The region has introduced door to door assessments for most areas, although there are some delays in the larger cities. The system has been operational for three years now. There are some residual problems with the guidelines, which have been revised for EFY 2000. There is a committee that oversees the assessment process, and representatives of the Chamber of Commerce sit on the committee. However there remain concerns that some of the assessments are arbitrary. In all about 80% of the tax payers fall the below the threshold and do not pay profit tax.

### Value added tax

VAT is collected by FIRA, but the region plays a role in registering traders for VAT. To date the region has registered 519 tax payers for VAT, in addition to the 676 registered by the federal level, making a total of 1195 VAT payers in the region. There was a significant change in 1998, during which a large body of taxpayers were moved from the category “sales turnover tax on locally manufactured goods” to VAT. The region has retained this component of VAT, and in 1998 an amount of Birr 26,5m was registered as income. Persons that are not registered for VAT fall under the presumptive tax system. The region is now considering how best to undertake a VAT audit, which is presenting them with some challenges.

### Operational programmes systems, procedures and manuals

The new tax system has been put in place through a series of proclamations, regulations and directives dealing with income tax, turnover tax, agricultural income tax, land use tax, excise tax and stamp duty. These in turn have been translated into a set of guidelines and manuals for staff at woreda level. There are three guidelines in place at woreda level, and a further three will be developed this year.

Training for tax collectors has been done through a “training of trainers” approach, with the region taking 200 tax collectors through a training programme. This has been cascaded down to woreda level.

Revenue planning was found to be a problem, and a manual has been distributed to all woredas in this regard. The region has not assessed the full revenue potential of the region for three years, and they are now planning a new study.

### Organisation and tax payers education

There is a systematic approach to communicating with taxpayers. In the large cities, approximately 500 taxpayers attended educational sessions. Every woreda has a programme for communicating with local taxpayers. In addition there has been a large amount of communication through the radio. Organisations such as the Chamber of Commerce have also been involved in the outreach programme.

The results of these reforms have been demonstrated in the revenues collected. Figures were provided up to the EFY 1998 financial year, and they show a significant and steady increase in total tax revenues for the region from Birr 105m in EFY 1996 to Birr 157,1m in EFY 1998. A large driver of this increase has been the tax on “income, profit and capital gain, which has increased from Birr 69m in EFY 1996 to Birr 96,2m in EFY 1998.

Tax evasion has been substantially reduced. It is now very limited in rural areas, and in urban areas the numbers of A and B category tax payers are very small and easy to follow up.

## CSRP

The CSRP sub-programme is managed directly by the BCB and forms part of the broader task of the Bureau to drive reform across the civil service. There does not appear to be a separate PSCAP CSRP coordinator, or indeed a separate PSCAP sub-programme. The CSRP programme was started in EFY 1995, with six different components. The programme was severely limited by financial constraints, and its incorporation under PSCAP was given it a significant boost. The CSRP work to date has consisted of two main elements, namely the performance management and evaluation process, and more recently, the focus on BPR.

The region has established a high level coordination mechanism for BPR – the regional President chairs a steering committee of Bureau heads, which coordinate the roll-out of BPR across the civil service.

### Strengthening the capacity of CSR Coordinating Structures

CSRP offices have been established in all regional bureaux and woredas. Meetings were held with two regional CSRPOs and two woreda CSRPOs, which confirmed that the structures are in place and functioning.

### Improving governance of human resources management and control

The management of human resources in the public service has been boosted through the training of 575 HRM officers, personnel and CSRP focal persons. At the same time a large number of HR manuals have been prepared, covering issues such as service delivery, strategic planning, performance appraisal, training, and recruitment.

The region initially implemented Results Orientated Performance Appraisal (ROPA) across the civil service, but encountered difficulties because of the lack of strategic and annual plans as a basis for determining individual performance targets, which in turn lay the basis for performance appraisal. The programme encountered resistance, first from the leadership, then from staff. The basis for a proper appraisal system has now been laid. The region has promulgated a regulation on performance appraisal last year. Employees are now putting pressure on their managers to implement the system. The CSRP sub-programme is now shifting its attention to the quality of the performance appraisal process. They plan to move onto the balanced score card method of appraisal next year, initially on a pilot basis.

### Improving performance and public service delivery

The CSRP sub-programme has set out to change the focus of each bureau and woreda with respect to service delivery, customer focus, accountability and performance. This has been done through the distribution of manuals and guidelines, and a massive training effort in target institutions, starting with the leadership and management.

The approach has taken different forms in different sectors. For example, the education bureau CSRPO has mobilised teachers around the “school improvement programme”, and focused their training and workshops on principals, vice principals, woreda education heads, inspectors and training officials. They estimate that they have trained over 3 000 managers and educators with PSCAP funds, and this has been rolled out through a cascaded approach at regional, woreda and school level. This is being translated into school improvement initiatives, which have resulted in a progressive improvement in the quality of education.

The performance improvement programme has now been overtaken by a focus on Business Process Reengineering (BPR), which is being piloted in 10 regional bureaux. It is being done vertically, i.e. the BPR is being implemented in pilot woredas in the same functional areas. There is significant investment of time and political capital in this exercise – in addition to the regional steering committee led by the President, there is a core team chaired by the BCB head, supported by a BPR technical team.

### Improving accountability and transparency

The sub-programme has set out to change the values of politicians and civil servants through training and the development of prototype guidelines on ethics. This enhanced  by a number of actions at office level - the values of service delivery, accountability and performance are prominently displayed in all offices, and civil servants now all wear badges displaying their names, designation and function.

A large community training exercise has been undertaken on grassroots level participation and the civil service reform agenda, reaching approximately 20 500 people.

The regional Ethics and Anti-corruption Commission has been established two years ago, with the aim of creating public awareness, as well as investigating and prosecuting cases of corruption. They acknowledge that they have done limited work on ethics, as this is largely addressed by the CSRP. They appear to be facing capacity problems, and acknowledged that there have been no new corruption cases in the last two years. The PPD is planning to provide them with some support from PSCAP.

As part of the commitment to accountability for performance, an annual survey on the performance of the civil service is undertaken. 22 000 forms have been distributed to customers, and an analysis is done of the customer survey. The results are published regardless of the nature of the assessment.

### Strengthening top management systems

The CSRP sub-programme has targeted regional and woreda political appointees and managers with training on strategic planning, change management and performance management, amongst others. The goal has been to enable the leadership to drive change in their institutions. A 6 volume book on performance management has been drawn up and circulated. The scale of the training effort has been enormous – 2180 persons attended awareness creation workshops on the overall civil service reform agenda, 1650 managers have been trained in ROPA, 1480 managers have been trained in service delivery and customer satisfaction.

## EMCP

The EMCP programme was started in EFY 1996, initially focusing on budget reform and accounts reform, linked to the process of fiscal decentralisation to woredas. This has laid a solid basis for the further development of the programme under PSCAP. Until this year the EMCP sub-programme fell under the CSRP sub-programme coordinated by BCB, but it has now been established as a separate sub-programme managed directly by BOFED.

### Enabling environment

The legislation that has driven the expenditure management reform process was enacted with a proclamation in EFY 1989 and regulations in EFY 1993.

A proclamation on cash management was enacted in EFY 1999.

### Capacity for expenditure management and control

The sub-programme has built capacity through creating the right legal framework, including proclamations and regulations, then translating these into manuals and guidelines. This has been followed by a large scale roll-out of training to accountants, budget experts, woreda and sector heads, and followed up with technical support from BOFED to the management of each institution at regional and woreda level.

Training was arranged for approximately 100 experts from woredas on linking strategic planning and medium term budgeting to operational planning. BOFED indicates that 100% of woredas now have proper financial management systems in place, although these are not yet computerised.

The auditor general confirmed that financial management is showing significant improvements in woredas. Single finance pools have been established for each woreda. There was a move over to the modified cash basis for accounting four years ago. All woredas now use the double entry accounting system. A large amount of training in financial management has taken place, and woreda finance staff  have been upgraded to degree and diploma level. There is general compliance with the new laws and regulations for expenditure management. The Auditor General did express concern regarding the high turnover of staff in the finance sections of the woredas.

### Financial information

The previous BDA and BIS programmes have been incorporated into IBEX, which computerises all budget and financial information. This was implemented in 1998 at a regional level, and is being implemented in 5 woredas on a pilot basis. It is planned to extend this to 34 rural woredas and 12 urban woredas in the coming year.

### Audit functions

This is the first year of implementing internal audit systems in regional bureaux. The Auditor General indicated that internal audit bodies report to BOFED and that they have no direct means of assessing their effectiveness. However they can confirm that each Bureau is hiring internal auditors, that there are internal audit manuals in place, and that the system is being installed. It is however still in its infancy as a system.

The regional Auditor General’s office was established 12 years ago, initially only doing financial audits, but they have now developed a performance audit capacity. Each year the AGO audits 60 offices, with three to four offices receiving performance audits. They plan to add resource control, environment audit and IT audit functions over time.

The auditors hold exit meetings with the top management in each institution they audit, sign a minute with the head, and submit their report both to the organisation and the appropriate oversight body – either the woreda council, regional council or BOFED. Ultimately audit reports are tabled to parliament, where the audit and budget committee is strong. Members of the committee visit each woreda and hold discussions on the audit findings. In this manner the system of accountability has been strengthened.

## ICT

The ICT sub-programme has made significant progress with implementation, and has laid the basis for a common IT platform across the region. Previously there were very few government offices, even at regional level, with IT facilities. Only the large departments such as BCB and Agriculture had computers. Now almost all woredas and regional bureaux are equipped with IT facilities. This has been made possible through an initial investment in awareness creation, a large amount of basic training, a cascaded system of IT support and training for woreda staff, and the strategic provision of IT infrastructure.

The ICT component consists of 6 permanent staff and 5 UN volunteers, who coordinate all ICT programmes in the region, in addition to PSCAP. The PSCAP resources are an essential support to their overall efforts, but are not the only input. It is difficult to assess the specific impact of PSCAP in isolation, although the components listed below are all supported by PSCAP directly. The region coordinates closely with federal ICTDA, submits quarterly reports to them and attends coordinating meetings at least twice a year. The ICTDA does all the configuration changes to the network.

### Human resource development

The ICT sub-programme has done extensive training at a regional and local level. A regional training centre has been established with 16 terminals. This is linked to a regional data centre with another 4 terminals. The key to success however has been the establishment of training centres at woreda level – there are now 34 woreda training centres, each with 6 computers. 35 woreda ICT experts were initially trained at the regional level for two weeks. They in turn have rolled out an aggressive training programme at local level. In the first wave 500 regional staff were trained in basic IT literacy, followed by 500 civil servants from woredas. Most of this training was done by woredas themselves.

The sub-programme has also delivered 477 computers to beneficiaries last year, approximately 100 to regional bureaux and the remainder to woredas. There have been problems with the quality and after sales service for the Acer computers, and a large percentage of the computers have power supplies that have burnt out.

### Public service delivery and good governance

Single server networks have been established in each woreda, which allows for optimum communication. Woredanet is working in all woredas, but there are problems with the configuration of VSAT and delays in trafficking which make the use of the system difficult.

There is an IT expert assigned to each woreda, who takes responsibility for running the woreda IT training centre, as well as the whole process of ICT communications for the woreda.

The financial systems in woredas are not yet automated or electronic. It is planned to start working on this in urban areas this year, and then to roll this out to rural woredas.

### Applications for sector development

In BCB 200 computers have been connected via an expanded LAN. The regional data centre is now promoting an e-government focus. The network infrastructure to support this was requested from PSCAP two years ago, and has still not been received. Due to the delays the specifications for the tender are now out of date and need to be redrawn, adding further costs and delays to the process.

In the mean time the sub-programme has developed database software for six regional bureaux, and are planning to install this in all woredas as well. The Information and Communication System Network Engineering Design has been completed for all the regional bureaux and woreda offices.

There has been progress with developing websites for departments such as BCB, Health, Agriculture and Tourism. These Bureaux have developed the content of the websites, but have not yet posted them due to budget constraints.

### Community based information systems and services

Woreda training centres have offered training in IT literacy to local communities, and there are plans to open up internet cafés next to each woreda training centre. As part of this effort there are plans to upgrade woredanet nationally to allow for public users to access the system.

These reforms will pose increased challenges for security of the IT system, especially the regional data centre. There is an ICT policy in place, from a national level, and the region is planning to customise it for their purposes.

The ICT sub-programme indicated that new needs (in addition to the much delayed network infrastructure mentioned above) include upgrades to the regional data centre, including the server, to allow on-line IT support.

# Programme management and support

## Institutional arrangements for PSCAP in region

The management of PSCAP in Tigray is centralised within BCB. In general the sub-programmes are not managed as distinct entities, and do not have dedicated full time coordinators responsible for sub-programme coordination. For example, the DLDP coordinator in BCB is also the JSRP coordinator, in addition to managing his full time job as head of research and policy for BCB. There was no CSRP coordinator, and we were eventually referred to the Bureau head for a proper briefing on the programme. UMCP, located in the Bureau for Works and Urban Development, is charged with many but not all of the sub-programme elements, with the fiscal issues being handled entirely by BOFED. There was no single person within the Bureau who could give a coherent explanation of the whole programme. The only examples of clear sub-programme coordination and responsibility were in BOFED, where the EMCP and TSRP sub-programmes are quite distinct and well managed.

In addition, there is no effective coordination taking place between different sub-programmes, other than through the PPD. The RTT does not meet on a regular basis, and there is no collective effort to integrate or coordinate the different activities of sub-programmes. The PPD’s view is that the RTT is “useless”.

However there is a high level well organised system for coordinating the overall reform programme in the region. The regional President chairs four committees which impact on this area, namely the committees for rural good governance, urban good governance, business process reengineering, and “joined up justice”. Each committee functions like a Cabinet committee, and brings together the relevant Bureau heads to coordinate the reform agenda, review progress and decide on actions in the focus area. BCB functions as the secretariat to each of these structures. The steering committees are duplicated at zonal and woreda level.

BCB is therefore positioned at the centre of the reform process, and has a large responsibility for its overall coordination. PSCAP is increasingly being used as a resource to support this broader reform initiative, rather than a discreet programme on its own utilising its own coordination mechanisms.

BCB shares offices with the President’s office and BOFED, and the three bureaux use a common accounts pool for financial management purposes.

The conclusion of the evaluation is that the management of PSCAP within the region is highly centralised. The programme has now been deployed as a budget support mechanism for the overall reform agenda. This has allowed the region to attain some impressive results in the reform process, both in terms of the scale of the reform process, and in terms of the quality and depth of best practice cases. This level of centralisation is therefore not necessarily a bad thing, and in the early stages of the reform process was indeed necessary and unavoidable. The crucial question is rather whether this management model will remain appropriate for the next phase of the programme.

The PPD consists of one full time coordinator, who is key to driving and coordinating PSCAP in the region. For the first two years this was the sole human resource for the PPD, which is amazing considering the outputs achieved. The other staff are a M&E expert, a planning expert, and three procurement officers.

The region raised the split in responsibilities with BOFED as a serious problem. Currently all the planning, programming and procurement functions sit with the PPD in BCB. BOFED makes an annual budget allocation to BCB, which submits the procurement documentation to BOFED for payment once the procurement process has been completed. This split in responsibilities has led to serious delays in the processing of payments, as BOFED does not understand the PSCAP procurement procedures.

Instead BOFED tends to apply the regions own procurement criteria, which have different cut-offs for decision making. At the very least BOFED needs a clear letter of instruction, requiring them to adhere to the PSCAP procurement procedures. Ideally BCB would like to have the processing of the financial transactions handed over to them, so that the overall coordination vests with BCB.

## Coordination with MCB, regional and federal sub-programmes, and woredas

There seems to be very little support from federal level PPD or sub-programmes to the region. ICT has a good relationship with ICTDA, with whom it cooperates closely. JSRP receives some training from the federal supreme court, although there has been no coordination federal JSRP for the last three years.

The region did not see much value in the role played by MCB PPD, and saw them more as a rubber stamp function and a brake on the process. The region would be happy to engage with the World Bank and other donors directly. It seems that there is little value placed on lesson sharing with the federal level and other regions.

The region has an extensive system of coordination with woredas which is highly developed. As indicated above, the four main committees for coordinating the reform agenda at federal level are duplicated at zonal and woreda level. The zones play an important role in coordinating activities amongst the woredas. The region frequently brings together zonal coordinators for two way communication with woredas and kebeles.

## Compliance with eligibility criteria by region

The region has complied with eligibility criteria, and there is a detailed PPA negotiated each year for the region which sets out programme activities, deliverables and budget allocations per sub-programme.

## Planning and resource allocation

The annual action plan is compiled by the PDD from inputs received from each of the sub-programmes or beneficiaries. There is a widespread disaffection with PSCAP planning, as it is considered tedious and over-designed. As a consequence, sub-programmes tend to submit their inputs late. The plans from the region are therefore submitted late to MCB, and MOFED complains about this – they usually require their inputs into the budget process by March of each year.

Following the allocation of budgets, action plans need to be revised, because the amounts allocated are significantly less than the indicative allocations used for planning purposes. The final allocations differ substantially from indicative allocations, and are approximately 30% of the original amounts.  The revised plans are then submitted to the Cabinet for approval, which frequently overturns plans and gives revised instructions about what priorities need to be addressed. As a consequence action plans need to be revised for the third time.

Regional leaders have indicated that they would prefer not to have allocations made to specific sub-programmes, and would rather use PSCAP as a resource to support the overall reform programme.

There are reallocations made between sub-programmes on an annual basis, but no 6 monthly mid-year reallocations are made.

## Procurement

The procurement of goods and services is managed by the PPD, except for ICB. There are the usual delays in procurement of goods and consultants, with most sub-programmes complaining about the excessive time taken – usually between 9 months to a year. The PPD indicated that the procurement which falls under their responsibility is delayed because of the following:

- Budget approvals are given late by MOFED;

- There is a delay in approval of action plans from PPD, and in obtaining “no objection” letters from the World Bank;

- There is a further delay in the actual transfer of funds from MOFED to BOFED, as a consequence procurement usually does not start until the second or third quarter;

- There is a further delay in getting “no objection” letters from the World Bank on the procurement plan;

- Once procurement has been done, all the tender documents need to be resubmitted to PPD and World Bank for a further letter of no objection;

- Thereafter the documentation is submitted to BOFED, which usually disputes the procedures because they don’t match the region’s own procurement procedures.

The process with ICB procurement is even worse. Requests for ICB procurement are sent to MCB, which then goes through a process of “bulking up” contracts from different regions. The goods procured through the ICB process take up to two years to arrive, and the quality of the goods is inferior, while the prices are higher than the region would have been able to obtain locally. In addition, the selected manufacturers often do not have after sales service facilities in the region, let alone the woredas.

For example the computers bought for woredas were Acer, which seemed to have defects with the power adaptors. These frequently burnt out in rural areas. The region was able to organise for one round of repairs to be done, but the problem has recurred. The region is currently sitting with 28 computers that are not functioning, and no Acer technicians available to correct the problems. The region also indicated that the prices paid for the Acer terminals was approximately Birr 2 000 more expensive than they were able to obtain locally.

The Xerox copiers procured for woredas also have no after-sales service, and the only available technicians have been flown up from Addis Ababa.

A further problem raised by the region relates to the negative list, which excludes vehicles and other capital goods from PSCAP expenditure. The original agreement allowed for the PPD to have two vehicles with drivers included in the budget, but the MCB PPD subsequently decided that the regions must supply this themselves. As a consequence, the PPD has to make ad hoc arrangements to travel to woredas, and is forced to beg vehicles from other programmes and implementing agencies in order to get around. The region has also has problems with many woreda courts which are in dilapidated buildings, and urgently need upgrading. The police indicated the need for forensic equipment and riot control apparatus.

## Expenditure and financial management

The pattern of expenditure by each of the sub-programmes and for the programme as a whole is summarised in the table below. The table confirms a general pattern of under-expenditure, starting from a very low 5,1% in EFY 1997. The overall expenditure last year of 55,4% is indicative of persistent problems with procurement, which the ICT record lows of 0,1% in EFY 1997, and 6,3% last year illustrate.

Table 1. Budget allocation and expenditure, 1997 to 1999

|  | 1997 budget | 1997 actual | % | 1998 budget | 1998 actual | % | 1999 budget | 1999 actual | % |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CSRP | 4,168,100 | 1,233,740 | 29.6% | 13,738,833 | 9,813,603 | 71.4% | 12,432,725 | 7,996,064 | 64.3% |
| JSRP | 312,600 | 120,387 | 38.5% | 3,332,900 | 993,099 | 29.8% | 6,162,042 | 1,931,365 | 31.3% |
| TSRP | 837,000 | 208,043 | 24.9% | 640,000 | 286,244 | 44.7% | 853,010 | 346,107 | 40.6% |
| UMCP | 4,962,100 | 88,734 | 1.8% | 3,895,300 | 218,394 | 5.6% | 5,042,460 | 2,148,368 | 42.6% |
| ICT | 25,757,900 | 24,448 | 0.1% | 3,000,000 | 1,779,838 | 59.3% | 2,650,000 | 166,413 | 6.3% |
| DLDP | 2,195,700 | 182,963 | 8.3% | 15,104,084 | 12,746,797 | 84.4% | 9,490,175 | 7,739,823 | 81.6% |
| Prog support | 242,806 | 98,510 | 40.6% | 910,490 | 341,779 | 37.5% | 700,728 | 367,548 | 52.5% |
| TOTAL. | 38,476,206 | 1,956,825 | 5.1% | 40,621,607 | 26,179,754 | 64.4% | 37,331,140 | 20,695,688 | 55.4% |

The region has mainly used PSCAP funds for training purposes. This is partly because of the emphasis they have placed on large scale roll out of training, and partly because of the crippling delays in the procurement processes for consultants and goods. As a consequence, the region has already reach the 40% limit for spending on training, and are concerned that they will not be able to finance further training activities from PSCAP resources. The PPD commented that “PSCAP is now crippled” as a result.

There seems to be a general move away from using consultants, partly because of the capacity that already exists in the region, and partly because of the problems with procurement. A number of sub-programmes expressed the desire to shift funds away from the consultancy component.

Due to the delays in the transfer of funds into the region’s PSCAP account, the BCB frequently takes advances out of the pool account to pay for PSCAP expenditure.

## Monitoring and evaluation

There is partial success with monitoring and evaluation. There is an M&E expert in the PPD who inspects all training activities, and produces an annual detailed monitoring report on all programme activities and targets – this is finalised in March of each year. The PPD undertakes all the monitoring itself, and this is not done by sub-programmes.  The monitoring of activities is done thoroughly, and the system is working well.

There is no systematic evaluation of sub-programme outputs or programme outcomes. The PPD indicated that it needed to boost its capacity in order to be able to undertake evaluations.

There is a cultural system of peer review and evaluation which the region referred to as “gem gam”. This is applied to managers in the civil service, including PSCAP coordinators, and they consider it a highly effective way of giving individual performance assessments.

At woreda level monitoring and evaluation structures have recently been set up in all woredas. Professionals have been hired to assist woredas with the evaluation process.

The PPD indicated that the evaluation of certain activities is difficult because of their political character, and that it would be hard to criticise some of the Minister or Bureau head’s policies – for this purpose it was suggested that the M&E function might be better located in the President or Deputy President’s office.

4.8 Information, education and communication

There has been little progress with IEC. A fortnightly column in a local newspaper has been started by the PPD, highlighting progress with PSCAP. The paper goes to every farmer and 200 copies are distributed to each tabia. The articles highlight good governance best practice. The second issue has recently been produced.

The region agrees that this area needs more attention, particularly now that best practice cases have emerged. They blame the delay partly on the federal PPD, which had originally agreed to coordinate all IEC activities. A manual on IEC was produced by the PPD, but due to the turnover in staff, no further action was taken.

## Sequencing and integration of reform initiatives

There are a number of activities where the region has followed a clear sequencing of reforms. For example, medium term strategic planning was introduced first, in order to lay the basis for medium term budgeting. These were in turn translated into annual action plans, which in turn were translated into plans and targets for each office, before individual performance targets were set for employees. This has now laid the basis for the results orientated performance evaluation system. Most woredas appear to be following the reforms in this sequence.

This logical sequence has been learnt after some initial examples of poor sequencing, in which performance assessments of staff failed because of the lack of proper plans against which to set performance standards.

However the region has introduced many reforms at the same time, for example, in addition to the above, budget and account reforms, IT systems reforms, service delivery focus, and good governance have been introduced simultaneously in many woredas. The region has an understandable haste to implement the reform agenda, especially after the last election. However there is a danger that less capacitated institutions will become overwhelmed and confused, and ultimately disheartened and demobilised.

# Cross-cutting issues

The PSCAP sub-programmes do not include HIV/AIDS as a cross-cutting issue as there is a separate fund which finances the HIV/AIDS activities. There is little attention being given to environmental issues in PSCAP programmes, partly because it is not seem as a priority, and partly because sub-programmes do not know how to take it up in their areas of work. When examples such as integrating environmental resource issues into woreda strategic plans were mentioned, there was a good response.

Gender is taken up well in most sub-programmes, and coordinators all referred to gender mainstreaming. There are women’s affairs offices in most bureaux and woredas, and the CSRP and DLDP programmes have made the best progress with this issue. Under the DLDP sub-programme a regional assessment was done on gender issues and women in civil society. Gender focal persons in all the regional bureaux and woredas have been trained. A policy framework on gender mainstreaming is in the process of being finalised by BCB. UMCP has done a study on how to support women in urban centres. JSRP has a few shining examples, such as the Wukro prosecutors office, which has made huge strides in addressing domestic violence and the abuse of women. The JSRP needs to look at replicating this approach more widely. The women in the regional council have also received training on how to improve their participation in parliament, as well as boost women’s role in society more broadly.

The representation of women in the regional council is 505, and in kebele and woreda councils is 13%. It is planned to increase this to between 20% and 30% in the next election.

# Assessment of programme outcomes

The Tigray region has made impressive gains in the reform and decentralisation process, with a strong political commitment to drive the change process, backed up by the financial resources and dedicated work within the public service. This has paid off, in that there are now tangible outcomes at the community level. There are a number of best practice examples of reform and service delivery improvement, and the change process has been initiated across a very broad front of institutions. However it is clearly uneven in its application, and there are a number of woredas and other institutions where the change remains at a superficial level. While the reform process still has a long way to go, especially in ensuring their application across all woredas, a firm basis has been laid, and the system has been shown to work.

## Enhanced predictability of financial resource flows in-year and across years

The introduction of medium term strategic plans and budgets in all regional bureaux, municipalities and woredas has significantly improved the predictability of financial resources. This predictability has been backed up by the largely fixed percentage of regional revenues that are transferred to the woredas through the block grant system. The predictability of tax revenues has also been addressed through building capacity to do revenue planning at a woreda level, and this will be further enhanced by the formula for the division of tax revenues between woreda and region, which will be implemented next year.

These changes have been reflected in the progressive improvement in budget variance for regional bureaux and woredas, a trend confirmed by both BOFED and the Auditor General.

## Greater inclusiveness and transparency of planning and prioritisation processes

The bottom up system of prioritisation, planning and budgeting introduced in all kebeles across the region is a huge improvement in inclusiveness and transparency. The evaluation was not able to confirm the uniformity of this approach across all kebeles, but it is certainly working well in the woredas and municipalities that were visited. The Auditor General and the Chamber of Commerce both confirmed the changes that have taken place.

The expansion of the number of participants in the kebele council to one representative for every 1000 peasants has also significantly increased the level of local participation. Kebele (tabia) councils have increased from between 60 and 80 members previously, to between 200 and 300 members. Woreda councils have increased from between 80 and 120 members, to between 150 and 324 members. Provision has also been made for representation of civil society on kebele councils, and representatives from trade unions, the women, youth etc made up 30% of the councils.

## Improved quality and efficiency of government operations in priority sectors

There are a large number of examples of significant improvements in service delivery at woreda and regional level. The Tigray Chamber of Commerce confirmed that processing of land applications and subdivisions by Mekele municipality has indeed improved significantly. In general government is much more responsive to issues raised by the Chamber, and consults them regularly on key issues.

The Chamber of Commerce indicated that the court reforms were of little benefit for civil cases, and that they generally avoided the courts and resorted to mediation to settle disputes. The Chamber is establishing an arbitration unit for this purpose.

## Improved incentive environment for public servants (gender disaggregated)

There has been no progress made on introducing performance related pay, or addressing the broader incentive package for public servants.  This is seen as a critical gap in the reform agenda, and was raised as an issue by a number of offices at regional and woreda level. Unless the reforms are followed through with changes in the incentive regime for civil servants and managers, the entire reform agenda stands at risk of losing momentum and support, and ultimately failing.

## Enhanced revenue performance and fiscal autonomy

There has been a significant and steady increase in total tax revenues for the region from Birr 105m in EFY 1996 to Birr 157,1m in EFY 1998. Tax evasion has been substantially reduced. Approximately 70% of the region’s funds are transferred directly to woreda level, which is a significant fiscal commitment to decentralisation. The percentage of the region’s budget transferred to woredas has remained fairly constant, between 67% and 70%, and is approximately Birr 800m. The revenue collection system in the region has decentralised many tax functions to woreda level, and the region has now prepared a revenue sharing formula to apportion tax revenues between woredas and the region. Again this represents a significant commitment to the decentralisation process.

## Improved transparency and accountability

Accountability has been strengthened through the system of auditing under the AGO. Audit reports are tabled to parliament, and the audit and budget committee visit each bureau and woreda and hold discussions on the audit findings.

The Tigray Chamber of Commerce indicated that government has significantly improved the transparency of the taxation system, and that there are clearer rules governing the imposition of taxes. The chamber now participates on the tax committee. However the presumptive tax remains arbitrary, with many traders complaining of inequitable treatment.

Corruption in the region is viewed by the Chamber as much better than other regions, mainly because the community is very sensitive to the abuse of administrative power. For instance communities frequently elevate concerns about improper land allocation to a regional and even a federal level.

The independence of the judiciary is growing steadily as a result of the massive improvement in capacity of the courts.

# Key issues and challenges

Many of the challenges raised by sub-programmes and beneficiaries are common across all the programmes. These include:

  - The overcentralisation of PSCAP in the region, with all decision making vested in BCB and the PPD. Some sub-programmes viewed the PPD and BCB staff as arrogant, and had difficulty working with them.

  - The time-consuming nature of the planning process, and the lack of indicative budget ceilings which match actual allocations, requiring revision of plans.

  - Delays in procurement and problems with the quality of goods procured through ICB, which have been canvassed above.

  - Inadequate budget allocations, especially for TSRP, DLDP and the 3Ps in JSRP.

  - Insufficient budget allocations for goods, as well as the negative list which precludes the procurement of certain critical capital items.

  - Problems with shifting funds between PSCAP categories for training, consultants and goods.

  - Delays in the release of funds from MOFED, with the bulk of the funds usually only received in the last quarter of the year.

  - The long chains of decision making which make it extremely time consuming to obtain even simple things – most beneficiaries expressed the desire to have PSCAP funds allocated directly and placed on their own budgets, with direct responsibility for procuring goods and services.

  - Lack of skilled manpower in many critical areas with each sub-programme, especially in woredas and kebeles.

  - High turnover of key staff in the programme and more broadly within coordinating and beneficiary institutions.

  - The lack of performance incentives for the civil service, with no means of rewarding personnel who go beyond the call of duty, and put in long hours to meet service delivery standards.

The region is encountering specific problems with the training programme arising out of PSCAP conditions. The bulk of the training is delivered in-house, and the region uses trainers that are drawn from universities, NGOs, licensed private providers and government institutions. The best trainers are in government, and are highly sought after. Generally they need some sort of incentive in order to be able to attract them to participate in the training, but PSCAP does not allow any payment to government employees other than per diems. As a result the training programmes tend not to attract the right quality of trainers.

# Lessons learnt and recommendations

The above evaluation has raised a number of issues that need to be resolved in order to speed up implementation of PSCAP and improve its overall effectiveness. Many of these issues need to be addressed at the level of the overall PSCAP programme. Central to these changes should be a change in PSCAP approach. Unlike the decentralised system that it is meant to be supporting, PSCAP as a programme is a more centralised programme, with multiple levels of control that delay decision making and the flow of resources. The following recommendations are preliminary, and are subject to the final report coming out of this evaluation exercise:

- There should be a substantial decentralisation of decision making within the programme, at three levels:

  - From federal to regional level, with the region handling all of its own procurement procedures, and a reduction in the number of approvals and letters of no objection required for each sub-programme.

  - From regional to sub-programme level, with budget allocations being made directly to bureaux with the capacity to manage their own procurement processes.

  - From regional to woreda level, with pilot woredas being allowed to have dedicated PSCAP allocations that are placed on their budgets.

- The processes of PSCAP should be better integrated with the governments overall planning, budgeting and procurement systems. This should include a move towards budget support, the establishment of a single planning and budgeting cycle, the use of a common set of procurement criteria, and a move away from bulking up procurement contracts or the management of ICB procurement at federal level.

- The cut-off levels for procurement should be reviewed, and the system of “no objection” streamlined.

- Budget allocations should be aligned with indicative medium term planning allocations, so that sub-programmes have certainty about future finances, and are able to plan within a clear envelope.

- Sub-programme coordinators must submit action plans and procurement plans timeously to BCB, which in turn should submit inputs timeously up to federal level.

- Greater flexibility needs to be introduced regarding expenditure between the training, consultants and goods categories, as well as between sub-programmes.

- The PPD’s role should be focused more on planning, advising BOFED about budget allocations for sub-programmes, and monitoring and evaluation. Procurement and administration of sub-programmes should be done by implementing agencies.

- The coordination of PSCAP in the region needs to be undertaken at a senior level, led by the BCB Bureau head, meeting together with Bureau heads responsible for sub-programmes, and support by the RTT. The RTT needs to meet on a regular basis to coordinate the PSCAP planning and budgeting process, to integrate and sequence reform initiatives, to share lessons, and plan monitoring and evaluation.

- Each sub-programme should be managed by a clearly designated coordinator who is able to devote substantial amounts of their time to management of the sub-programme.

- The region needs to conduct an annual evaluation of sub-programmes based on outcome indicators, and discuss this evaluation at an annual assessment workshop which brings together all executing agencies and beneficiaries.

- A systematic approach to IEC must be coordinated by the PDD, aiming to popularise emerging best practice and deepen reforms.

- The region must make sure that cross-cutting issues such as HIV/AIDS, gender the environment are taken up in strategic plans for bureaux and woredas.

- The incentive framework for civil servants is a crucial missing element of the overall reform programme that needs urgent attention.