Annex 15: Oromiya report

# Background

Oromia Region was visited by Rob Mellors and Habtu Gebrehiwot between 19th and 31st October 2007. Meetings were held with all key stakeholders including the Bureau of Capacity Building, the 7 sub programme managers, the regional BOFED and a range of beneficiary organisations. Additional information was obtained from special reports produced by the sub-programmes, PSCAP 5 year and annual action plan, various statistics provided by sectoral bureaus and relevant secondary evaluation reports. Visits were made to view the reforms in action at the Supreme Court and BOFED at regional level.  Three woredas – Ada’aa, Adama, and Adamitulu Jido Kombolcha -  and 2 Municipalities – Adama and Burayu - were also visited and consulted. Persons met are shown in Annex 22.

The Regional BCB went to great lengths to prepare for the evaluation with each sub-programme making detailed presentations. The evaluation team would like to thank the staff of the PPD for their enthusiastic efforts to arrange meetings. We also thank the various organisations and people who generously made their time available to participate in the assessment.

# Overall assessment

Oromia is the largest region in Ethiopia with a population of 27 to 35 million people. It is organised into 17 Zones, 254 Woredas and 337 Municipalities. The region has a wide range of agricultural environments including highland plateau, rift valley and more semi arid/arid areas in the south east. It has a strong economic base. Oromia is regarded as one of the 4 more developed regions.

Regional government in Oromia has to grapple with huge distances to its extremities and thus has to rely on Zones as outposts of the regional government to support and monitor all the woredas. The number of zones and woredas was increased from 12 to17 and 198 to 257 in 2005-6. The capital of the region is in Adama although most of the administrative offices are in Addis. The region has some highly competent civil servants in the higher levels of government but the more remote or newly formed woredas suffer low staffing levels and high staff turnover.

Oromia has made remarkable progress in implementing government’s PSCAP reform program over the past three years. There is a strong sense of commitment, interest and team-work amongst all the main implementing agencies. Similarly most of the beneficiary agencies are well informed about the programme and the various planning, budgeting and implementation arrangements. Many of the PSCAP sub-programmes were already initiated and funded by government and various bilateral agencies before the initiation of the PSCAP pool funded programme in October 2004.

The Region regards PSCAP as a very important programme for improving service delivery and despite the problems believes that financial utilisation is higher than with other externally financed programmes. It has helped to introduce new systems and to empower people at all levels especially the grass roots.  There is need now to update the original plans and to look at redesign of some elements the programme. The BCB believes that PSCAP should be at least a 10 year intervention given that the first 1 or 2 years were largely lost in learning the ropes.

The region has completed Minimum Mandatory Activities in all sub-programmes except DLDP. The main constraint for DLDP has been the region’s inability to secure suitable consultants to undertake the required studies. A new strategy based on internal task forces, inter regional learning and facilitation is now being adopted and much better progress is anticipated.

In addition to the MMAs, a vast number of capacity building activities have been undertaken across all sub-programmes. The region is now trying to restructure its activities around the Woreda and Urban Good Governance Packages.

Awareness of PSACP sub-programmes is high in almost every zone and woreda – a PSCAP information brochure has recently been produced. The planning, budgeting and co-ordination processes for PSCAP are competently handled by BCB and PPD. Most M&E to date has centred on activity monitoring but an impact assessment is soon to be published.  There have been serious delays in the procurement processes due to the complexities of the system, however the PPD has gone to great lengths to establish appropriate organisational arrangements and is currently processing 12 different procurement packages.

Gender and HIV/AIDS issues are addressed in most training programmes and there are dedicated offices for both these at woreda and regional level.

# Assessment of implementation of each sub-programme

## CSRP

### Overview and organisational set up

Transforming the civil service is a core component of PSCAP in the Region. This involves changing hierarchical, inflexible attitudes and bureaucratic systems, increasing responsiveness, improving pay and morale, increasing skills and weeding out corruption. To date there has been some overall improvement although there are still problems with ‘control oriented attitudes’, a lack of transparency, a failure to appreciate performance management systems, lack of concern for public assets and a desire for more pay without improvements in productivity.

The specific objectives of the CSRP in Oromia are to ensure responsiveness, transparency and accountability in the civil service, to ensure efficient service delivery, better uitilisation of scarce resources and to create civil servants with zero tolerance of corruption. The CSRP has until recently included both HR and Expenditure Management objectives. The latter are now dealt with under the EMCP section of this report.

The CSRP is having little impact on staff turnover which continues to plague the regional civil service due to low salaries. Average woredas remain short of skilled personnel and are on average 60 to 80% staffed against their prescribed structures. The CSRP has plans to send out 360 new graduates to different sectors throughout the region.

The CSRP is part of BCB and is staffed by a Department Head, 2 Team Leaders and an Expert. It is implemented through the Oromia Civil Service Commission and The Ethics and Anti- corruption Commission with the expenditure management elements run by BOFED and the Auditor General.

In terms of activities, the CSRP has been introducing strategic planning, PSIP, BPR and ROPE to the region. It has also conducted Service delivery surveys, benchmarking and several ‘quick win’ initiatives.  All Minimum Mandatory Activities were reported as complete during year 1 of PSCAP.

### Strengthening the capacity of CSR Coordinating Structures

A Study Tour focusing on CSRP issues has been conducted to South Africa and Canada for 5 regional professionals. 4 people have also been to Swaziland for training on project planning.

A range of 144 computers and IT equipment has been procured and delivered to key implementers. Basic computer training has been provided to the 322 personnel from the Civil Service Commission, the Auditor General’s Office and the Bureau of Capacity Building.

These initiatives have increased professionalism in the management of the CSRP. There is further scope to improve co-ordination and relationships with the various  CSRP implementing agencies however.

### Improving governance of human resources management and control

Extensive training in prototype regulations and policies has been conducted, in particular training on HRM guidelines and ROPE has been run for 1600 woreda and municipal personnel. A further 1100 staff have been given awareness training on HIV/AIDS and gender.

This training is reported to have had reasonable impact on attitudes and working practices. Woredas are starting to implement systems of ROPE and they note that previous levels of resistance from staff are now subsiding. All woreda staff now have job descriptions and some have set specific work standards.

### Improving performance and public service delivery

Considerable effort is going into the introduction of Business Process Re-engineering.  Previously 28 Bureau Heads and 2,100 employees were trained and BPR was implemented in 55% of regional institutions. However since it was decided to introduce a new round of BPR approximately 1,800 people have been trained and an evaluation workshop conducted.

Generally the CSRP has had most impact in terms of service delivery.  There are significant changes in attitude towards a customer orientation. BPR is making good progress and a new implementation phase involving 20 bureaus will soon begin. There have already been numerous reductions in processing times for key services and decisions. The more progressive woredas are instituting their own BPR processes based on earlier models. They are setting maximum times to carry out key service functions and introducing 1 stop shops in specific service areas.

Earlier PSIP activities resulted in public notice boards, information leaflets, badges, suggestion boxes etc in most woredas. These have been reinforced now through the Good Governance Packages.

### Improving accountability and transparency

Specific activities in relation to this component are run by the Anti Corruption Commission which is two years old in the region. A workshop has been run for 1600 personnel on ethics and the operations of the Anti Corruption Commission. There have been further workshops and training on corruption and ethics for approx 1500 people. 117 Audit workers have received training on fraud detection and a baseline survey is currently being conducted to assess the extent of corruption in the civil service.

Subjectively the region perceives greater openness and awareness on corruption issues. Whilst the training has had some impact, there is still some way to go in improving transparency and accountability.

### Strengthening top management systems

CSRP has worked on promoting strategic planning throughout most regional and local government institutions. It has conducted training on leadership, change management, strategic planning and BPR for all bureau heads. This training has been cascaded down to 480 other top managers with a focus on change management, leadership skills, M&E.

All managers now have a much sharper awareness of the reform agenda. They better understand the role of a manager and the respective roles and responsibilities within their organisations.

## DLDP

### Overview and organisational set up

Within the scope of its overall objective to deepen decentralisation and enhance democratic participation and service delivery, the specific objectives of DLDP in Oromia are to strengthen the capacity of local government bodies, institutionalise decision making closer to the people, ensure responsiveness and efficiency in service delivery, ensure transparency and accountability and promote increased awareness of decentralisation policies with enhanced grassroot participation.

DLDP in Oromia is run from within BCB. It has a Programme Head, 4 experts and a secretary. All senior staff have Masters Degrees. It works closely with the Regional Civil Service Agency, the Public Service College and the sub regional CB Offices.

Given the 254 woredas and 17 zones in Oromia, DLDP has a huge task. Much training has been carried out, however the region is still some way from completing its MMAs due to problems in hiring consultants. In particular it has yet to complete its decentralisation legal framework with refined functional assignments and is now doing this through a special task team using the experience of other regions. The picture is similar in terms of the Minimum Service Standards although a consultant has just been selected for this.  Progress is yet to be made on the decentralisation policy and strategy document and the community participation strategy. The human resource and training needs assessments have been conducted through the Regional Civil Service College and the re-assessment of the block grant formula is in progress.

Massive training on the Woreda Good Governance Package has been conducted. 1.7m people have attended awareness training events.

Generally woredas have good awareness of reform programmes though they may not be familiar with the word PSCAP.

### Institutional & organisational arrangements

The legal framework for decentralisation and functional assignments is still under preparation through the special task force.

### Manning and training

The HR needs assessment of woredas has been completed by RCSCO.  Large numbers of training courses have been conducted including:

- Gender sensitized community participation and cross cutting issues at all levels;

- Planning and financial management for zone and woreda professionals;

- HRD concepts, responsibilities under decentralisation for woreda executives;

- In service training of several thousand agriculture, education, health and water officials from woreda and kebele levels following a needs assessment exercise – part of this was orientation in terms of the Good Governance Package and included over 50,000 teachers plus agriculture DAs.

- Longer term distance education courses are being supported by government both for MAs (90 people), for remote woreda personnel (4970 people) and for other civil servants (4316).

- Democratic participation, leadership training for various women affairs groups and staff of the Youth and Sports Affairs Bureau.

### Grassroots participation

Participation has been the subject of a limited amount of training although more generally it is covered by the Good Governance Package training. The region notes increased awareness on participation, gender issues and rights on service delivery.

### Setting minimum service standards

A consultant has been appointed to study MSS in the region and develop an MSS manual.

### Woreda fiscal transfer and own revenue enhancement

Re-assessment of the Woreda block grant transfer is in progress and a tender procedure is underway for consultants to assess and develop revenue generation improvements.

Woreda Block Grant transfers in Oromia have been increasing significantly over the past two years by 26 and 48% respectively. These have been much increased by the PBS budget support. The region has identified some 30 woredas to take part in a pilot of the Local Investment Grant. It is anticipated they will share around 70m Birr.

### Woreda multiyear planning, budgeting and financial control

Proposals have been received from consultants to assess the introduction of a multi year financial framework and reporting system. Woredas have benefited enormously from the support provided by woreda support units under the EMCP/DSA programme.

Most woredas are seriously understaffed in their WOFEDs e.g. 50% in their accounts sections and 95% in their budget sections. In some woredas the budget sections have no staff at all. Despite this, acceptable reports and budgets are produced although the staff work long hours – inducing more turnover. The workload in the accounts sections is way beyond the existing manpower. According to the recent DSA evaluation average staff turnover in WOFEDs is 37%. WOFEDs do not get adequate priority in terms of the woreda budget overall.

Almost all woredas follow the standard budget and accounts procedures but are ill supplied with forms, regulations and guidelines.

### Equipment support

IT equipment has been purchased to support the implementation capacity of 153 woredas. On the whole however, they are generally poorly equipped and furnished.

### Programme development

No activities were recorded under this component.

### Capacity building for lead implementing agencies

Books are being purchased for the Public Service College.

### Good Governance Package

Massive amounts of training have been conducted on the principles and contents of Woreda Good Governance package including;

- 530 Cabinet members and leaders of the region and zonal administration;

- 4,017 Selected woreda and zonal officials;

- 42,500 kebele administrators;

- 60,000 civil servants from all levels.

Linked with the package training has also been conducted for thousands of woreda and kebele officials on public complaint handling, customer care, exemplary models and model villages.

Over 100,00 copies of the package have been printed and distributed and follow up M&E activities have been conducted.

As a result of the training there is much greater awareness of government policies and political and economic reform strategies. Service providers and customers are more aware of their respective rights and responsibilities. Attitudes of service providers are improving. The costs of all this training have been high.

## EMCP

### Overview and Organisational setup

The objective of the EMCP sub programme in Oromia is essentially to improve overall governance of finances including expenditure management and control. It is managed by BOFED although it still fell under the CSRP until this year. In the March 2007 JSM report all MMAs are said to be complete i.e. the elimination of backlog accounts up to 1999 E.C. and the installation and training in medium term manuals BIS and BDA3, however BOFED and auditor general state that only 75% of institutions have closed their accounts.

Very good progress has been made with this sub programme. It has benefited substantially from the DSA project which has been working in the region but is now unfortunately about to close.

60% of the Regional Budget is now going towards block grants for woredas. In value terms these have risen from 1,621 m Eth Birr in 1998 E.C. to budgeted figures of 2,056m and 3,054m Birr in 1999 and 2000 E.C. respectively. These figures represent 26% and 48% increases on an annual basis. The region has been using a needs based formula for determining the block grant for the past 3 years and is quite satisfied with it.

The region is now planning to introduce Local Investment Grants (LIG) to some 33 woredas on a pilot basis in 2001 E.C. through disbursing around 70m Birr between them.

### Improving governance of financial resources, management and control

In terms of activities, the new financial proclamations have been adopted and distributed to most bureaus, zones and woredas. A cash management manual has been adapted and translated and circulated at all levels with training for 248 BOFED staff. 75% of public bodies have been sensitized on these proclamations. 6,289 finance officers from all levels have been trained on accounts reforms, implementation of the double entry accounts system and the new budget structure in all public bodies.  Training of 653 personnel has also been conducted on procurement with a further 1180 trained on financial audit and accounting systems. Most woredas are now implementing double entry accounts and revised budget procedures.

The Zero Cash management system has also been introduced at regional level. 38 different institutions have been trained in its operation and it will be fully implemented during 2000 E.C.

Woredas use the regional 5 Year Development Plan which is based on PASDEP as an indicative plan to guide their own woreda strategic plans. BOFED has trained and placed specialised planning and monitoring officers to strengthen all financial bodies going down to all levels. These officers should also improve the planning and monitoring systems and improve reporting to regional level. Overall BOFED is trying to give more attention to M&E. In addition to receiving quarterly reports, they are attempting to conduct field visits utilising 4 teams to visit selected zones and woredas. There is still no institutionalised woreda performance monitoring system.

Under the DSA project, much energy was given to building the capacities of the zonal and woreda OFEDS. Special Woreda Support Units (WSUs) were established in all Zones to provide support and on the job training to the WOFEDS.  A special DSA evaluation of 18 woredas in 6 zones conducted this year showed that the WSUs have been very successful however they have had to contend with serious staff shortages and high levels of staff turnover, especially in newly established woredas. Therefore while substantial achievements have been made, there is still need for much more strengthening of WOFEDs at grassroots level.

The introduction of IBEX (Integrated Budget and Expenditure) software is well advanced in Oromia. It is installed at regional level and in all 17 Zones. This system replaces BIS and BDA3. It provides a huge amount of analytical flexibility and is capable of generating a wide range of integrated financial reports and summaries. Ultimately it is intended that the system operates on the web using Woreda Net however at the present time a more manual approach has to be followed. Paper based woreda budgets and financial reports are taken to ZOFEDs who enter them into the IBEX software which is then brought to the Regional Server on a CD.

Auditing of public bodies in the region is the responsibility of the Auditor General’s Office. It has 117 professionals against an establishment of 285 and suffers high staff turnover due to low salaries and budget constraints. It is presently responsible for auditing 25% of the regional proclaimed budget (although the future target is 35%) and sends quarterly reports to the Oromia Public Accounts Standing Committee. The office has prepared an External Audit Manual with CIDA and Irish support and has received training costs from PSCAP to run courses on this. PSCAP has also provided the office some few items of IT and copying equipment but is seriously hampered by a lack of transport. Otherwise it receives relatively few resources from PSCAP. More computers and training are urgently required. It would also like to be networked to the other key regional bureaus. PSCAP is also supporting the training of internal auditors by BOFED.

Woreda audit functions are run from 4 centres in the region. In each year they are capable of auditing 80 to 100 woredas, thus it takes 3 years to get round all the woredas, at which time they have to do 3 lots of accounts.

Audit reports usually note lack of experienced accounts staff in the woredas with high staff turnover and poor management of public property. Generally however they discern a marked improvement in woreda PFM performance. In many woredas accounts are being closed on time and they are coping with the double entry system. The weaker woredas however fail completely to close their accounts, report very late and in the worst cases the accounts cannot be audited.

## ICT

### Overview and organisational setup

Oromia regard the ICT sub programme as a very important tool in meeting the development challenges of the region.. ICT has 4 key components which try to address the overall objective of improving governance and service delivery. These are:

- Developing an ICT skilled labour force in government;

- Developing computerised working systems for service delivery;

- Developing special sectoral applications;

- And developing community based ICT services.

The ICT component is run by a department within BCB and all MMAs have been completed but overall ICT development in the region is still at an early stage. Initial expenditure has been low under this sub programme. Some 800 desktop and 35 laptop computers have been distributed across public bodies in the region. A good if slow start has been made but there are some major challenges confronting this sub programme:

- Major delays in procurement of equipment – preventing the establishment of 5 training centres and numerous community centres,

- Lack of vehicles for maintenance and M&E,

- Problems in pre qualifying consultants,

- Stability of CISCO devices re video conferencing,

- Shear lack of skilled IT manpower in such a vast region.

### ICT Human resource development

Training manuals have been developed for all the basic computer applications e.g. Word, Excel etc. and much hardware installed throughout the region. The establishment of Regional Training Centres is in progress with classrooms being prepared at 3 centres. A limited amount of training has also been carried out under this component including:

- 364 woreda operators and the staff of 4 regional data centres,

- 318 woreda civil servants on basic computer applications – a further 800 will be trained shortly as will 45 ICT experts on an advanced package.

- Advanced training for 4 experts in CISCO routing and servers, 10 experts on web page development, 15 experts on maintenance of Woreda Net.

In terms of impact, most woreda and sector offices now have e mail addresses and some woredas are now sending reports to the region by e mail. Many staff are also using applications for written reports, presentations and spreadsheets. They are also able to carry out basic equipment maintenance.  There is however a long way to go here. The number of computers per head of workforce is still very low and there are serious issues of computer maintenance especially in the more remote woredas.

### Public service delivery and good governance

The regional data centre is established and operational. It can provide internet services and videoconferencing. A consultancy is under negotiation to develop websites for 10 Bureaus. Some specific customised applications are being developed (esp. MIS) for 6 bureaus. These applications will be linked up through a LAN.

Anticipated impacts include reduction of training costs through the use of videoconference facilities and reduced time loss on training courses. The evaluation team were informed that several workshops and meetings are being conducted using video conferencing.

### Applications for sector development

As yet no tangible progress has been made with this component. Consultancies are planned to develop sector specific management and information systems (MIS) at the regional data centre.

### Community based information systems and services

Again there is limited progress being reported under this component. An awareness creation workshop for 300 community representatives has been held. Five centres have been chosen for community information establishments including a community radio station and 4 farmer information centres.

## JSRP

### Overview and organisational setup

As part of its overall goal to build an efficient, fair, transparent and accountable justice system in Oromia, the JSRP has 6 specific objectives:

- Building the capacity of the courts to increase efficiency in processing cases,

- Achieving greater equity and effectiveness in judicial service,

- Strengthening independence and accountability of the judiciary,

- Ensuring wider accessibility of courts to the public and ensuring predictability of court decisions,

- Strengthening law making capacity of Oromia’s legislative organ,

- Establishing a modern legal framework compatible with the constitution, socio economic and political interests of society,

- Creating an enabling environment for the transformation of law enforcement agencies so they become more effective and efficient.

This sub-programme is the most advanced in the region as much work had been done in terms of the court reforms before PSCAP began. The fruits of all the effort put in are now starting to be realised with significant gains in impact in almost all areas. The challenges remaining are still large however. A crucial issue is the quality of judgements in the lower courts especially. If this can be further improved, the burden on the Supreme Court will be reduced.

JSRP is located within the BCB and involves the Oromia Supreme Court and the Bureau of Justice as implementing agencies. There are JSRP Steering Committees at all levels. Relationships with BCB are good and JSRP produces quarterly and annual reports on time. M&E is assisted by the automated case management systems supplemented by field trips and customer responses.

Procurement problems for equipment and stationery have been a major impediment to greater progress. JSRP managers believe more long term training is essential in this sector but is not encouraged by PSCAP or the systems involved in procuring it. They also believe there are gains to be achieved by study tours which are also discouraged. Negative lists preclude procurement of vehicles and upgrading of court facilities.

### Strengthening the judiciary

Much effort has gone into this component which was initiated well before PSCAP. The evaluation team was highly impressed with the level of reporting and data which was presented reflecting very effective MIS. The organisational structure of the courts has been reviewed and reforms developed. 27 photocopiers and 45 computers and printers plus new furniture have been distributed to the Supreme Court and the Zonal courts. Over 150,000 file folders and cards have been distributed to zonal and woreda courts.

Numerous training programmes have been conducted for around 3,740 judges and support staff including:

- Court reform, service delivery and case handling awareness to 1,032 judges and support staff;

- Various management, policy planning and HR skills to senior and junior court officials and leadership staff:

- Management and secretarial training to court secretaries;

- Numerous short term in service training courses for judges on substantive and procedural law and judicial ethics, judicial codes of conduct, judicial independence;

- Longer term in service training for judges including 252 woreda judges at diploma level, 130 zonal and woreda judges at LLB level, 30 support staff at diploma level;

- Filing systems and case management for 292 court clerks and registrars;

- Courses for public defenders on judicial ethics, procedural law and independence of the judiciary.

The colour coded filing system is under implementation in all district courts across the region although procurement problems have delayed the accompanying improved file folders which are only now just being delivered. File cabinets are now the outstanding deficiency. An impressive automated court case management system is in operation at the Supreme Court, in 15 Zonal High Courts and in 2 district courts in the cities of Shashamane and Adama.

Information counters have been established along with telephones, computers, database facilities, TVs and new furniture in the Supreme Court and in zonal high courts.  They are in the process of also being set up in some woredas but are so far poorly equipped.

In terms of impact there have been major achievements on the completion of court cases, although backlogs are again increasing as can be seen from the following table:

Table 1: Status of processing of court cases, 1994 to 1999

| Year | Pending | ###### Decided | Transferred | % transferred |
| --- | --- | --- | --- | --- |
| 1994 | 295,427 | 200,262 | 95,145 | 32% |
| 1995 | 334,709 | 230,340 | 104,369 | 31% |
| 1996 | 437,744 | 356,988 | 80,756 | 19% |
| 1997 | 452,627 | 375,958 | 76,669 | 17% |
| 1998 | 396,768 | 311,023 | 85,745 | 22% |
| 1999 | 408,634 | 315,190 | 103,204 | 25% |

The average time to dispose cases has declined very significantly and is now 1 year at the Supreme Court, 4 months at high courts and 3 months at woreda courts. In terms of criminal cases over 80% of cases are now disposed within a year - up from 40% 6 years ago.

Whilst the speed to deal with cases is much improved, law professionals outside of government say there are still significant questions regarding the quality of judgements. The fundamental training of judges is constrained by outdated attitudes and curricula for the legal profession right up through to university level.

Some woredas are also now taking court reform down to kebele level by providing training to Social Courts and running awareness programmes.

### Law revision and law reform

Regional laws enacted by the State Council have been published and distributed to woredas.

### Law enforcement capacity enhancement

Initially the 3 Ps (police, prosecutors, prisons) were not eligible for PSCAP funding but this has now changed and a considerable amount of procurement of computers, furniture and photocopiers plus training has been carried out to build capacity.  Training has included:

1. Prosecutors

- Short term prosecutor training on investigation techniques, making charges, complaint handling, human rights, gender mainstreaming, criminal and family law and good governance, computers, personnel management and management skills;

- Longer term prosecutor training through Diplomas and LLB for 250 candidates;

- Prosecutor induction training was carried out for 102 new recruits;

- 428 prosecution support personnel from all levels  plus have been trained in document registration;

- Bulk training of 5885 community leaders, women, farmers etc on constitutional principles, human rights and good governance.

2. Police

Numerous courses have been provided for many hundreds of members of the police from all levels and for durations of up to 6 months on subjects such as investigation tactics, traffic accident investigation, crime prevention, radio operation, leadership, mob prevention, good governance and democratisation, modified cash accounting, criminal statistical records, collection of criminal evidence, HIV/AIDS.

3. Prisons

Around 88 Prison Officers have received training on good governance, human rights, rehabilitation of prisoners and 16 others on vocational skills training.

Impacts of all this training are reported to be significant with conviction rates up from 50% to 65%. Prosecutors are also reported to be handling more cases up from 60,189 in 1997 E.Y to 70,386 in 1999 E.Y. Accountability and transparency are said to be improving as are the skills and knowledge of the police force resulting in a reduction of crime rates. It was not possible in the time available to independently verify these statistics.

### Legislative organ

JSRP has also upgraded the capacity of the Regional Council and the Aanaa (Woreda) Councils. Internal structures of the councils have been reviewed to improve performance. 2 computers have been provided to the Regional Council.  350 parliamentarians and 37 standing committee members have been trained on principles of democratic constitutions, separation of powers, human rights, roles and responsibilities of councillors and executives, role of opposition parties, planning and budgeting, law making and procedures, democracy and good governance including state policies on agriculture, education, health, and urban areas..

349 Speakers and their deputies have had similar relevant training but with particular reference to their chairmanship role.

244 Experts from woreda councils have received training on democratic constitutions, planning and budgeting, minute taking and documentation, HIV/AIDS and environment so they can better support the councils.

The Region reports significant impact as a result of these efforts. The quality of legislation is improving and the Standing Committees are now more aware and better able to provide checks and balances on the activities of the regional executive and other government organs. Similarly there is some improvement in the capacity of woreda councillors. Much still remains to be done in these areas such that councillors become more effective links for representating the interests of their constituents. At the moment many councillors still remain as passive ‘rubber stampers’.

## TSRP

### Overview and organisational setup

Oromia has been reforming tax administration for the last 6 years. 2 years ago it established the Oromia Bureau of Revenue to oversee all regional tax issues and run the TSRP. The objectives of the TSRP in Oromia are to increase revenue, broaden the tax base, improve equity and efficiency and promote investment through:

- updating tax policy and legislation,

- improving and rationalising presumptive tax,

- introducing TIN,

- introducing VAT,

- preparing and distributing operational manuals,

- educating the tax payers.

All minimum mandatory activities for the TSRP have been completed and the programme has good relationships with the BCB.  Relationships within the various levels of the Revenue Bureau are said to be good. There have been very significant achievements under the TSRP with growing increases in total revenue collected and an extension of the tax base as illustrated in the following table. There is no room for complacency however as average % increases through to 1998 did not keep up with annual GDP growth. Only in 1999 has there been a significant net increase in total tax revenue – something of a rebound since the significant drop during the period of the last elections and the change in profitability rate used to compute turnover tax. Over the total period 1994 – 1999 the average increase in revenue was 11%.

Table 2. Tax revenue, 1994 to1999

| Year EFY | Total Revenue collected Eth Birr | % change | Including VAT collected |
| --- | --- | --- | --- |
| 1994 | 480,361,000 |  |  |
| 1995 | 502,676,000 | 4.6 |  |
| 1996 | 590,572,000 | 1.7 |  |
| 1997 | 662,910,650 | 12.2 |  |
| 1998 | 624,310,608 | -5.8 | 20,210,000 |
| 1999 | 809,346,078 | 29.6 | 84,195,350 |

At woreda and municipal level average local revenue over the 284 local authorities was 1.29m Eth Birr in 1999 EFY. This represented and average 17.8% of their total budgets. This was projected to rise to 1.66m Eth Birr in 2000 EFY – an increase of 29%.

From our few opportunities to consult with tax payers there is a general perception of increased fairness and efficiency and a greater willingness to pay taxes due.  The Bureau also reports that taxpayers feel that corruption has been minimised.

### Tax policy and legislation

Tax proclamations and regulations covering income tax, excise tax and stamp duty have been adopted and distributed across the region and this has been followed up with training workshops for bureau and woreda staff followed by an impact assessment.

### Tax payer identification number

A total of 63,451 tax payers (approx 62% of taxpayers) have been registered for TIN and 32 user/administrators trained on the application of TIN systems. This has been accompanied by the procurement of 40 computers and accessories which have been distributed to woredas, zones and city administrations.

### Presumptive taxation

To assist in raising revenue from the informal sector, an annual income survey in two phases has been conducted. In 1996 EFY the survey netted 76,740 taxpayers. The EFY 1999 survey however achieved a 34% increase to almost 103,000 taxpayers. Working manuals and directives on the operation of this tax have been issued and training on their application conducted for 852 woreda and city administration staff.  The tax has been made fairer by reducing the profitability rate to 7.5 – 10% used in the computation of tax due.

### Value added tax

Oromia is delegated by the federal government to collect VAT. This new tax has been introduced through adopting the operational systems developed at federal level followed by training on VAT laws and regulations for bureau, zone, and woreda and city administration staff. The VAT applications within the SIGTAS IT software are being used to manage and enforce VAT and this has again involved training for bureau staff.  So far 642 taxpayers have been registered for VAT and 94.4 m Eth Birr collected.

### Operational programmes systems, procedures and manuals

The regional tax offices were in need of much reform at the start of the TSRP in 1994 EY. Unskilled staff and outdated practices predominated. New operational strategies and procedures manuals on tax collection, enforcement, accounting and auditing had to be prepared and distributed to implementing agencies. This has been followed up with continuous annual rounds of staff training at the rate of 450 to 600 staff per year. In the last year specialised training on the operation of SIGTAS has been conducted for a small number of officers.

### Organisation and tax payers education

Over 70,000 information manuals have been distributed and various training activities conducted for over 44,000 taxpayers.

Tax payers at woreda and municipal levels are now more willing to pay taxes following the awareness training.

## UMCBP

### Overview and organisational setup

Oromia has the highest number of city administrations in the country and thus has a big challenge to move them forward and get beyond the neglect of the past. There are 27 grade 1 and 12 grade 2 City administrations which have the hierarchical status of woredas and thus can provide state functions. There are a further 55 grade 3 and 243 grade 4 municipalities which fall under woredas with the status of kebeles. All these administrations are defined and covered by the Municipalities Proclamation 65/2003.

The objectives of the UMCBP in Oromia are numerous and include:

- Provide an effective policy environment for the effective functioning on ULGs,

- Provide specific policy and strategy for land management and housing development,

- Capacity Building of ULGs so they can deliver services and create a conducive environment for economic development,

- Empower ULGs to support micro and small scale enterprises,

- Promote good governance, transparency and accountability in ULGs,

- Promote economic integration between ULGs and with the agriculture sector,

- Provide regulatory system for ULGs,

- Promote awareness on safe and clean environments in ULGs.

The Oromia UMCBP programme under PSCAP in now in its third year. All MMAs have been achieved. Good progress has been made with improving legislation, distributing manuals on urban management and various types of training. UMCBP has used consultants to help develop and deliver training materials. There are impressive rates of development and improved services in many of the ULGs.

### Regional urban management policy framework

The region developed and adopted its regional urban development policy and strategy through the CBDSD TA fund and then used PSCAP funds to run 8 rounds of familiarisation workshops for 4,000 people. These comprised government employees, civil societies, religious groups and prominent elders. This process was participative and enhanced transparency.  The policy and strategy also included a housing strategy.

The Municipality Proclamation 65/2003 and associated regulations have brought real decentralisation to the urban areas. Municipalities now have significant responsibilities for finance and revenue collection, HRM, service delivery/infrastructure and good governance. Crucially important (and different from woredas) they can determine their own basic organisational structure.  Key services include land provision, licences, registrations, housing facilitation, water, roads, health and education. There is a varied picture with regard to further decentralisation to urban kebele and sub kebele levels. Most municipalities still have some way to go in this regard, limitations being due to lack of facilities, trained manpower, vehicles and communication.

The region has developed urban land legislation focusing on land lease and rent, real estate development, house plot sizes and the grading of urban lands. This has greatly assisted transparency and fairness in land allocation and development.

### Deepening the process of decentralisation

The Municipalities are still in a transitional phase without elected Councillors. Councils will be elected during 2000. Grade 1 and 2 Municipalities are subdivided into Urban Kebeles and have dual administrations – municipal infrastructure and state functions. State functions such as health and education are largely financed by the block grant transfer with some complementary own revenue whereas municipal functions are entirely financed from own source revenues e.g. school buildings and equipment are paid for by the Municipality whilst teachers salaries and books by the regional subsidy. The City Administration are run by the Mayor and the Mayoral committee whilst the Municipal functions are managed under the mayor by a Municipal Services Manager.

The Municipalities have received a range of manuals and packages from UMCBP which they are using for their day to day management e.g. Urban Good Governance Package, House development, Youth, Micro-enterprises etc. These are considered to be helpful and comprehensive.

With regard to finance, the Municipalities have achieved remarkable increases in own revenue collection partly as a result of training of officials and tax payers on the Tax Reform Programme e.g. Burayu Municipality collected 8.9m EB in 1998, 19.4m in 1999 and expects 65m in 2000. Adama’s revenue has increased from 11m 5 years ago to 37m Eth Birr last year. (Note these figures do not tally with BOFED summaries).

Housing is a big problem throughout the Municipalities. Following a demand assessment,

they are attempting to deal with this in line with the Regional Government’s housing policy by:

- Providing land to prospective home-owners to construct their own houses,

- Providing land to housing co-operatives,

- Facilitating the construction of condominiums for the poorer populace by the Regional BWUD. This involves providing land, supporting small industries to supply building materials, allocating the units etc. Allocation criteria for land and condominiums are ‘reasonably developed.

### Local government restructuring and capacity building

Some municipalities have prepared strategic plans, others are working on the basis of Annual plans only. Strategic plans were prepared without PSCAP support.

As part of its MMAs, the regional UMCBP completed training programmes on key prototype manuals including financial management, urban management, procurement and contract administration. It has also provided bulk generic training to municipal staff and local leaders. 900 relevant participants have received training on the Urban Good Governance Package which has provided the framework for participation and is being publicised to the people through meetings. The Municipalities themselves however don’t seem to have a formal IEC strategy for this. The package includes participation, transparency, inclusiveness and accountability as well as HRM, legal frameworks, financial management, land and infrastructure management, Business Development, Entrepreneurship, Credit and Savings, BPR and Leadership.

Other training organised through the UMCBP has included detailed BPR, Leadership, Gender Mainstreaming, Mass awareness training on health and environmental issues for 50,000 people in 6 main cities. BPR is yet to be fully operationalised in most municipalities however physical and organisational changes are already being planned in anticipation. Once BPR is in place municipalities will implement ROPE.  Municipalities say they have not received any training in Budgeting or financial management. Despite this they are implementing the basic budget and accounting reform recommendations.

Specific attention is being given to training in facilitation of Business Development, entrepreneurship and how to improve strategies for SMEs including credit and savings procedures.

In addition to the short-term training, 143 urban sector employees are studying an urban management MA program. A further 168 will follow.

Priorities for further capacity development would centre on training of cabinets and councillors (once elected) and for the kebeles so that they can take on decentralised functions. Further technical training for workers is also required along with policy awareness and mobilisation skills for community leaders.

Municipalities have received various computer packages and photocopiers through the first round of PSCAP procurement. There was no proper needs assessment done. The equipment is reported to be sub standard and in some cases over sophisticated and difficult to maintain. Most of the equipment is bought using municipalities’ own funds and procurement systems. Municipalities also have the capacity to procure for building contracts and other small to medium infrastructure projects.  The UMCBP office itself has received key IT equipment and furniture. Consultancies have been procured to prepare training materials and carry out training needs assessments.

Many Municipalities now have Master Plans and are starting to implement these. In particular, they are facilitating the release of land for industrial, commercial and domestic purposes. Land leases are the major source of revenue for the Municipalities.

BPR has had some major impacts in Adama e.g. property right transfer time reduced from 150 days to 1 day. Land certificate issue now takes 1 day instead of 35 days, marriage and birth certificates half a day instead of 13 days etc.

# Programme management and support

## Institutional arrangements for PSCAP in the region

Overall management and coordination of the PSCAP in the region is performed by the Oromia BCB. In addition, management of 4 of the sub programmes has been established in OBCB namely CSRP, ICT, DLDP and JSRP. TSRP and UMCB are managed by the Oromia Bureau of Revenues and the Oromia Bureau of Works and Urban Development respectively.  OBCB has established an effective PPD which reports to the Deputy Bureau Head and has the following staff:

- Planning Team – Head and 2 Senior Experts, work with focal persons in each EA

- M & E Team –  One officer at present

- Procurement Desks – Two local procurement specialists

A Regional Technical Team of 12 high and mid level officials has been established to oversee and co-ordinate the programme. It meets at least quarterly to consider plans and progress reports.  In addition a 5 person Bid Evaluation Committee and a Technical Evaluation Committee have been established to handle procurement.

OBCB and the PPD appear to be efficient and well respected by all players. They have some high calibre and motivated staff and have developed strong linkages with BOFED and the other implementing Bureaus.

## Coordination with MCB, federal sub-programmes, and woredas

The PPD in the Region co-ordinates and submits plans, progress reports etc to the PPD in MCB. The relationship is cordial and business like. Linkages between the Regional sub programmes and their federal counterparts are very variable. EMCP, ICT, UMCBP have good relationships and exchange information on plans and progress. DLDP, JRSP have weak contacts with their federal equivalents.

## Compliance with eligibility criteria by region

The region complies with the eligibility criteria and signs a detailed PPA each year with MCB. This sets out a matrix of programme activities, deliverables and budget allocations per sub-programme.

## Planning and resource allocation

The planning process now presents no significant problems to the Region.  As with all other regions it is subject to the up and down process of submitting plans to MCB and MOFED, and having to re-plan once its final budget allocation is known. This is time wasting and inefficient. The Region is also frustrated by the late release of funds especially for this financial year. So far PSCAP activities are being financed through advances from government rather than PSCAP funds.

## Procurement

The Region has gone to great lengths to improve its procurement capacity. Its procurement specialists and the Procurement Committees have all been trained twice on IDA procurement procedures and guidelines. They handle all NCB and national shopping procurement except for in house training courses. They also complete all the requirements re ICB processes that are then handed on to MCB PPD. To date Oromia has received 60m Eth Birr worth of ICB equipment for various beneficiaries. Out of 29 Procurement packages embarked upon by the PPD, 7 have been successfully completed, 4 have been aborted due to lack of capable consultants, and the remaining 18 are at various stages of invitation, bidding or evaluation.

The region seriously complains about the delays over procurement and previous orders.   It also considers that much of the procured IT equipment is of a lower quality and a higher price than could have been obtained in the local market. There are also problems of appropriateness.  In terms of consultancies its experience has been one of struggling to find capable firms willing and able to take on the more complex assignments especially with regards to DLDP.

## Expenditure and financial management

Control of PSCAP expenditure in managed by the PPD although the BOFED disburses funds against budgets and keeps accounts. Figures on budgets and transfers have been obtained from both the PPD in Oromia and the PPD in MCB and surprisingly there are significant differences.  According to the regional PPD the figures budgeted and disbursed for the past three years are as follows – MCB comparatives are shown in brackets.

Table 3. Budget and expenditure, 1997 to 2000

| Birr EFY | 1997 | 1998 | 1999 | 2000 |
| --- | --- | --- | --- | --- |
| Budget allotment | 125,972,774 | 234,836,289 | 226,473,765 | 178,261,424 |
| Adjusted Budget | 78,196,506 (98,647,700) | 134,772,832 (137,141,832) | 93,523,960 (109,191,800) | 132,244,357 |
| Actual expenditure | 11,398,101 (11,454,639) | 45,322,427 (45,465,600) | 72,112,391 (51,908,549) | 21,472,496 |

As can be seen from the figures final adjusted budgets are sometimes less than 50% of original allotments. Actual expenditure was very low in the first year at only 14.6% of the adjusted budget. Fund utilisation has however improved progressively as management and procurement capacities within the BCB have increased but still only averages 32% for 1997 – 99 EFY - the lowest of the more developed regions.

The highest spending sub-programme by far is the DLDP which utilised 48m Birr out of the regional total of 72m last year. Much of this can be attributed to massive training conducted on the Good Governance package. The region needs to evaluate training impact in this area and also explore other IEC strategies for this type of awareness training. The lowest spending sub programmes have been the TSRP and the ICT – the latter spent nothing at all in 1997 and 1998.

There is considerable proportional variation between the planned and approved budgets for the different sub-programmes – they bear little relationship to each other - suggesting perhaps that MCB submitted plans on the region’s behalf before the regional plans were received.

External  audit on PSCAP funds was generally good with only minor points to address.

## Monitoring and evaluation

The monitoring of programme activities and targets is being coordinated by the PPD. Each sub programme also has its own monitoring and evaluation officials. The PPD monitors the activities and budgets of the various sub programmes. Evaluation has tended to be a weak area. Recently however a PSACP Impact evaluation has been conducted which is in the process of being written up.

## Information, education and communication

The PPD has recently produced a brochure on PSCAP objectives and activities which has been widely circulated throughout the Region. Awareness of PSACP is generally high.

## Sequencing and integration of reform initiatives

Generally the sequencing of activities does not appear to have been a problem except where consultancies have been required. DLDP has been worst affected by these delays - its legal frameworks, minimum standards and training needs assessments should have all been conducted early in the programme.  The lack of a clear Local Government policy statement and the delayed legal framework mean that there could eventually be contradictions or at least a lack of focus with some of the training programmes that have already gone ahead.

Conversely one should always view capacity building as a learning process and the fact that some aspects are delayed has heightened peoples understanding of the need for them.

# Cross-cutting issues

Many PSCAP funded training activities have specific quotas for women and include sessions on gender and HIV/AIDS. There are line departments dealing with gender and HIV issues at all levels of government.

Despite all the training, increased awareness has not yet fed through into increased numbers of women in key posts in government or adequate numbers of women councillors. E.g. in the woredas visited, women councillors generally numbered around 5%.

There is no attention being given to environmental issues in PSCAP sub-programmes.

# Assessment of programme outcomes

Impact of sub-programmes outcomes is difficult to assess quantitatively.  The following comments are based on anecdotal information and discussions with programme beneficiaries and service users at different levels.

## Enhanced predictability of financial resource flows in-year and across years

Predictability of regional subsidies has increased through 3 year block grant estimates. Woreda block grants showed a 26% average rise from 1998 to 1999 and are budgeted to rise a further 48% in 2000. Local revenues are also showing steady increases – averaging 11% for the region over the past 5 years.

## Greater inclusiveness and transparency of planning and prioritisation processes

All woredas and most municipalities have followed participative processes in producing strategic plans which they believe have been very helpful in focusing development activities. The Municipalities Proclamation creates the framework for public participation in plans, budget reviews, prioritisation and M&E. DLDP reports that participatory budgeting and public involvement in reviews is now being implemented.

Woredas are also encouraging kebeles to improve and implement their own plans. Through the Good Governance Package, kebeles have been given additional training and resources. Each kebele now has a secretary and some paid staff. The community through their kebeles are participating in quarterly plan reviews giving feedback to the woredas on performance.

## Improved quality and efficiency of government operations in priority sectors

Service delivery by local governments in general is reported to be improving. The table below shows this to be a general trend throughout the country. PSCAP is a contributor to this improvement.

Table 4. Progress on selected Human Development Indicators and Spending on Poverty Sectors, 1995/96 – 2004/05

| Sector | Indicator | Years |  |  |  | %Change 2004/1996 | %Change 2004/2000 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 1995/96 | 1997/98 | 1999/00 | 2004/05 |  |  |
| Education | Primary (1-8) Gross Enrolment Rate (%) | 37.4 | 52.3 | 61.1 | 74.2 | 98.4 | 21.4 |
|  | Literacy Rate (%) | 25.8 | 26.6 | 29.2 | 37.9 | 46.9 | 29.8 |
| Health | U5 Child Immunization Measles (%) BCG (%) | 39.1 40.1 | 46.9 50.9 | 48.1 49.1 | 56.8 54.9 | 45.3 49.6 | 18.1 14.4 |
| Water | Access to Safe Drinking Water (%) | 19.1 | 23.7 | 27.9 | 35.9 | 88.0 | 28.7 |
| Poverty Sectors1 | Spending on Poverty Sectors as % of Total Expenditure | 1999/00 | 2000/01 | 2001/02 | 2002/03 | 2003/04 | 2004/05 |
|  |  | 27.9%2 | 35.9% | 44.8% | 43.3% | 50.3% | 57.1% |

Notes: 1 These are the education, health, agriculture and natural resources, and rural road sectors, as defined by the government.

2 This was a year of war between Ethiopia and Eritrea.

##### Source:  SDPRP APR 2, July 2005, MOFED; and World Bank staff estimates

Municipalities have shown significant improvements in terms of land administration, urban planning, housing, slum upgrading and revenue administration. They have also have made good progress on roads, waste management, electricity and water provision, urban greenery and afforestation. Further achievements include kebele led neighbourhood improvements, support to small and medium scale enterprises, and facilitation of LED.

Woredas stress that some services are improving significantly. In education student teacher ratios are reducing (e.g. 1st and 2nd cycle 70:1 down to 55:1 in last 3 years in Adama woreda) as are textbook student ratios now at 1:1. In agriculture there is increased use of improved seeds and fertilizers and the DA farmer ratio is slowly improving as is the provision of animal health centres. Adama woreda has even conducted household income surveys and last year farm incomes averaged around 10,000 birr per household.

## Improved incentive environment for public servants (gender disaggregated)

Incentives for civil servants remain low despite recent salary increases. Distance learning courses for additional qualifications are an incentive for some however. Staff turnover is generally high e.g. in some WOFED planning departments it ranges from 33 to 200%.  The DSA programme evaluation estimates the need to train and replace 2,000 woreda finance staff every year just to maintain current levels of capacity.

## Enhanced revenue performance and fiscal autonomy

Revenue performance has increased by an average of 11 % in the region over five years. There were dips during the elections. This is a good achievement and slightly better than GDP growth but there is no room for complacency.

Revenue performance in municipalities is particularly encouraging rising by over 100% through the past 3 years in the municipalities visited (although figures from the municipalities do not always correspond with those of the regional BOFED). Woreda revenue increases are also generally ahead of GDP growth rates.

Block grants have also increased well above inflation and GDP growth as a result of donor contributions to the PBS programme as well as increases from the federal government.

## Improved transparency and accountability

Transparency and accountability have improved through the participatory planning and budgeting processes of the region, municipalities and woredas. The urban and rural Good Governance Packages further reinforce this. The devolution of power to woredas, municipalities and kebeles has initiated a bottom up system of accountability. Various municipal laws provide for transparent processes re land and other services. Access to justice has also increased and there is generally more awareness of government programmes and performance.

# Key issues and challenges

Key issues across sub-programmes in the region are as follows:

- PSCAP is generally too centralised and top down. This is causing delays and frustration. There is no trust in the system. It is also inhibiting learning by doing.

- Allied to centralisation PSCAP is not responsive to needs. Training and procurement have generally been supply driven.

- Woredas are getting tired of simply being passive recipients of PSCAP activities. They want to be able to express their own needs and for the programme to be more responsive instead of top down.

- There is a lack of qualified consulting firms and consultants to handle the more complex assignments. This compounds the problem of the long drawn out consultancy procurement procedures.

- The procurement process is extremely cumbersome. Thresholds are too low and the number of WB ‘no objection’ requirements is too high.

- There have been major delays in deliveries for ICB procurement handled by MCB e.g. out of 2,000 computers ordered 2 years ago only 811 have arrived. Much of the problem has been caused by the insistence on ‘bulking up’ by MCB both in terms of the regional action plan goods components and by bulking regional plans together. This has pushed orders beyond the ICB threshold.

- The quality of goods received under ICB has been poor especially the Acer Computers. Linked to this the brands chosen have limited back up in the areas where they are used e.g. the Xerox copiers are over sophisticated and have little back up.

- The region should be concerned about equipment maintenance especially expensive IT equipment. More attention should be given to training people on proper utilisation and ensuring there are adequate budgets for maintenance.

- Lack of vehicles is a serious impediment especially for monitoring and evaluation of the programme.

- PSCAP mainly facilitates short term training but there is also need for long term training and more study tours especially in key professional areas.

- High staff turnover and lack of incentives is making it difficult to sustain capacity gains. e.g. in the field of accounts staff alone, Oromia needs to train nearly 2,000 per year to maintain staffing levels in WOFEDs.

- Linked to this, major skills gaps continue to exist at the different levels of government but especially in woredas.

- The DLDP in particular reports weak linkages with federal DLDP.

- Full implementation of BPR followed by ROPE/Balanced score Card will seriously challenge the region and the civil service in particular.

# Lessons learnt and recommendations

The main recommendations arising out of the evaluation are summarised below.

- PSCAP needs to be more responsive and needs based. Plans should derive from beneficiary structures e.g. the woredas and municipalities rather than being decided on their behalf by sub programmes.

- Overall the PSCAP systems should be based on principles of trust and decentralisation. This significantly assists capacity building through learning by doing.

- PSCAP budgets should be decentralised both to implementing agents at regional level and eventually to the woreda level.  Pilot exercises with woreda PSCAP budgets could be tried alongside the forthcoming LIG pilots.

- Procurement processes for PSCAP goods and services should be decentralised wherever possible matching responsibilities with budget holders. The Region can now handle ICB processes.

- The insistence on bulking up orders should be relaxed and the procurement criterion of local maintenance and serviceability should be given higher prominence. There is need for more procurement training.

- The allocations for training, consultancies and goods in the PAD should be made more flexible.

- A level of flexibility regarding procurement of vehicles should be introduced.

- The original Regional PSCAP 5 Year Plan is now out of date and needs to be redone. There is also need to look at the whole log frame and the various KP Indicators.  This should be a participative exercise.

- More long term training should be financed by PSCAP, even distance learning. This could be a useful incentive to assist staff retention.

- Much more attention is required on M&E. It is recommended that the region explores how to implement an institutionalised local government performance monitoring system once it has completed its study on Minimum Service Standards.

- Linked to this, the region needs to decide which bureaus should be responsible for performance monitoring and for the regulation and oversight of local governments once the woreda legal framework has been proclaimed. The Region needs to consider whether or not it needs a dedicated bureau for local government combining all the functions of promotion, regulation, support and M&E. It might also consider if is there potential to combine the issues of rural and urban local government in one bureau?

- The success of Zonal based Woreda Support Units providing on the job support to Woredas indicates the value of facilitation approaches to capacity building. Generally there is now a need for much more facilitation in various areas of the programme to complement the mass training that has been provided. E.g. the region’s approach to overcoming problems in hiring consultants has been to set up task teams although these could benefit from supportive facilitation.

- More effort and innovation is required on the issue of incentives. Even if there are constraints on financial rewards, other incentive mechanisms must be explored.

- The Regional brochure on PSCAP is a good step forward in IEC. There is still scope however for much more IEC activity rather than expensive awareness training exercises.

- Woredas need increased capital budgets. They are generally getting good value by utilising community contributions to projects.

- If woredas had their own CB budgets their priorities would be to increase decentralisation down to kebele and to build kebele capacities in planning and service delivery. They would also increase the drive towards computerisation.