#### Annex 6: Urban Management Capacity Building sub-programme report

# Background

The Urban Management Capacity Building Programme (UMCBP) is one of the six Public Sector Capacity Building Programmes’ sub programmes in Ethiopia. Its main focus is to enhance the capacity of municipalities in the delivery of services; and to enable urban centres to play a more effective role in social and economic development. Three key activities have been identified to achieve the objective. They are:

- To provide technical assistance for the development of federal and regional policies related to urban development, housing, urban land, municipal structures and the formation of municipal associations.

- To provide technical assistance for the deepening of municipal decentralisation through the preparation of manuals governing resource management, reviews and the organisation of training and human resource needs, the establishment of regional planning units and the development of fiscal transfers and revenue mobilisation mechanisms.

- To support local government restructuring and capacity building efforts including restructuring of water and sanitation, urban land and other services, the development and roll-out of financial, human resources and land systems and related organisation reviews.

The evaluation team met the Ministry of Works and Urban Development (MWUD), which through the Urban Development Capacity Building Office is responsible for the management of the site programme. The meeting was held on the 10th October 2007. A follow up meeting was held on 05 November 2007. An evaluation relies on material provided including the PSCAP programme implementation plan, the inputs collected from the regional visits, discussions with key institutions such as the Ministry of Capacity Building and the Ethiopian Civil Service College (which is responsible for the bulk of the training programmes), interviews with independent bodies )such as the Chamber of Commerce (including some of the regional chambers)) and professionals and practitioners.

The UMCBP, for a variety of reasons mostly funding related, started off only 18 months ago as PSCAP programme. Most of its activities were funded and ran as part of a Good Governance Reform Programme through the CBDSD programme. From the very onset, the Director General of the Ministry saw PSCAP as a means of achieving the broader objectives of the Urban Good Governance package. This fact became very apparent in most of the urban centres visited by the evaluation team.

The MWUD explained the Urban Good Governance Package as a package of seven programmes aimed at accelerating reform and decentralisation. The seven include:

- Land reform

- Justice reform

- Urban Planning

- Organisation and Good Governance

- Finance Reform

- Infrastructure Governance reform; and

- Participation reform.

The urban good governance reform programme, alongside the rural good governance reform programme, was developed as a direct response to government’s consultation process after the last elections.  The ministry’s mandate is informed by this programme and links this to their mandate of formulating an urban National strategy.  The initial activities linked to the Urban Good governance and the Ministry’s mandate have to date and up to the end of December 2007(EC) been funded out of the Capacity Building for Decentralised Service Delivery programme (CBDSD), a World Bank Funded Programme.  The Ministry has applied to extend funding up to 2008(EC) to allow the programme to complete some of the infrastructure development projects.  PSCAP funding is used largely to assist the Ministry in meeting the objectives of the Urban Good Governance Program through, among other ways, meeting the shortfalls of the CBDSD programme.

# Evaluation of the main activities / components of the sub-programmes

The evaluation team was provided with a copy of a Quarterly progress report prepared by the UDCBO. The key point of departure in the report is the two-year delay. The programme was not funded for the years 1997(EC) and 1998(EC). The 1998(EC) request was for Birr 9 million. No expenditure was incurred in that year, mainly because of the failure to receive approval from IDA. The one reason for the refusal was that the requests were not contained in the procurement plans. The other reason was a failure to obtain no objections for the ICB requests. Birr 60 million was requested for the 1999(EC) financial year and only Birr 13 million was approved. The key 1999(EC) requests related to materials (including beds, mattresses and pillows), furniture and office machinery. It appears from studying the spreadsheet commitments and actual payments under PSCAP for 1999(EC) that Birr 2,5 million was for material, 7 million for a Master Degree at the College (ECSC) and the balance for training. Birr 91 million was requested for the EFY 2000(EC).  As of the 5th November, when the evaluation team met with the UDCBO, no money had been released and it appears that the Federal UMCBP will be on hold yet again.

The Ministry raised the lack of monitoring and evaluation systems as an issue. There is currently a process of collecting project outputs and monitoring activities to establish a basis for an evaluation that will be rolled out at mid-term. The monitoring and evaluation will have to measure the impact of the entire offering since 1997(EC) irrespective of the source of funding. The evaluation team is of the opinion that it may be possible to measure the impact of all the activities in the municipalities on the basis of their impact on service delivery and social and economic development.

# The status of minimum mandatory activities:

The UDCBO collated reports received from the regions via the BCBs and the MCB and has been able to piece the following report together.  Its own activities are those that relate to the ECSC procurement of goods, training and consultancy services.  The evaluation team was unable to get more details behind the statement “Urban Good Governance Package Completed”, posted at the end of most KPIs.

## Key Performance Indicator 1: Greater inclusiveness and transparency of planning and prioritisation processes

- Established practice of participatory budgeting and public reporting on budgets and performance at all levels;

- Regular involvement of civil society in planning and policymaking, budgeting, and review processes.

### Key Contribution outputs

Horizontal accountability mechanism or checks and balances established.

### Actual outputs reported in progress report

- Restructuring and Performance Improvement Plans prepared for 18 towns and some being implemented through PSCAP as from EFY 1999(EC).

- Studies on municipal finance, revenue mobilisation and collection, human resource management, training needs assessment, completed. Draft Revenue Improvement Plans prepared in 9 towns.

- 16 generic manuals on service delivery completed and awaiting adaptation by regions / municipalities.

- Manuals completed on financial management, revenue enhancement, grading system, Kebele upgrading, housing and infrastructure financing.

- Urban Good Governance Package completed.

## Key Performance Indicator 2: Enhanced fiscal autonomy and improved revenue administration at all levels

- Increased own revenues and unconditional transfers as a share of total expenditures at sub-national levels.

- Increased tax efforts at all levels.

### Key contributing outputs

- Legal and policy framework strengthened.

- Expenditure Management System reform.

- Intergovernmental fiscal and revenue mobilisation mechanisms.

### Actual Outputs Reported in Progress Report

- National Urban Development Policy completed & approved in March 2005(EC).

- PASDEP strategy document with “Emerging Urban Agenda” completed.

- Draft Regional Urban Development Strategies and Implementation Plans completed and being implemented in the four major regions.

- TOR for Housing Policy finalised and Task Force set up.

- Regional Housing Strategies completed and being implemented in the four major regions.

- Draft NATIONAL Urban Training Strategy developed.

- Report and recommendations on regional fiscal and grant system for municipalities prepared.

- 16 service delivery manuals and other manuals/handbooks prepared.

- Municipal proclamations in 4 regions; AA and DD established as chartered cities.

- Draft Legal and Institutional Framework Study for the 4 Emerging Regions and Harari. Draft Proclamations completed and given to the regions to review and implement.

- Prototype financial regulations implemented in one region.

- Infrastructure delivery and Financing Strategies and Implementation Plans completed for the 4 major regions.

- Urban Good Governance Package completed.

## Key Performance Indicator 3: Enhanced incentive environment for public servants

(Gender – disaggregated)

- Increased average civil service salary as percentage of living wage.

- Private-public wage comparison.

- Wage decompression ratios.

### Key Contributing outputs

- Restructuring and performance improvements.

- Personnel management systems reform and roll-out.

### Actual Outputs Reported in Progress Report

- Situation analysis completed in 18 towns.

- Restructuring and Performance Improvement Plans prepared for 18 towns and some are being implemented through PSCAP as from EFY 1999(EC).

- Organisational structures established in 16 towns in the four major regions. Harari, Dire Dawa and Addis Ababa.

- Personnel management manuals and systems developed and implemented in the 4 major regions. Addis Ababa and Dire Dawa.

- Computerised Financial Management and Accounting System developed and implemented in Addis Ababa and Dire Dawa.

- Prototype Computerised Financial Management and Accounting System developed for other towns and to be implemented through PSCAP.

- 16 service delivery manuals prepared and other operational manuals/handbooks prepared and ready for publication, dissemination and implementation at city level.

- Infrastructure Assessment and Infrastructure Inventories completed in 18 towns.

- Five year municipal infrastructure investment plans prepared for 18 towns.

- Urban Good Governance Package completed.

## Key Performance Indicator 4: Improved quality and efficiency of operations

- Improved service levels in terms of access, responsiveness and cost efficiency in priority sectors.

- Reduced unit costs and processing time for essential rural, urban, social, and legal services in priority sectors.

### Key Contribution Outputs

- Restructuring and performance improvements.

- Vertical accountability mechanisms established.

### Actual Outputs Reported in Progress Report

- Situation analysis completed in 18 towns.

- Restructuring and Performance Improvement Plans prepared for 18 towns and some being implemented through PSCAP as from EFY 1999(EC).

- Organisational structures established in 16 towns in the four major regions, Harar, Dire Dawa and Addis Ababa.

- Personnel management manuals and systems developed and implemented in the 4 major regions, Addis Ababa and Dire Dawa.

- Computerised Financial Management and Accounting System developed and implemented in Addis Ababa and Dire Dawa.

- Prototype Computerised Financial Management and Accounting System developed for other towns and to be implemented through PSCAP

- 16 service delivery manuals prepared and other operational manuals/handbooks were prepared, and are ready for publication, dissemination and implementation at city level.

- Infrastructure Assessment and Infrastructure Inventories completed in 18 towns.

- Five year municipal infrastructure investment plans (MHPs) prepared for 18 towns.

- Centre for Urban Management established at the ECSC and to be equipped through PSCAP.

- New Ministry (MWUD) with new departments and an increased urban focus, established as part of the Restructuring of Government Ministries in October 2005(EC).

- A study on municipal finance, revenue mobilisation and collection, human resource management and training needs assessment completed. Draft Revenue Improvement Plans prepared in 9 towns.

- 16 generic manuals on service delivery completed and awaiting adaptation by regions/municipalities.

- Manuals completed on financial management, revenue enhancement, grading system, Kebele upgrading, housing and infrastructure financing.

- HANDBOOK ON Housing Cooperatives and Condominiums completed and ready for use by regions/municipalities.

- Regional urban planning units established in the four major regions. Vehicles, equipment, trading and urban planning manuals provided to the units.

- Final Report and Recommendations for establishment of Integrated Urban LAND Information Systems completed.

- Training conducted in the entire four major regions, Dire Dawa, Addis Ababa and planned for emerging regions.

- Translation into Amharic of 14 UN Habitat manuals on training of councillors and council management completed.

- Urban Good Governance package completed.

## Key Performance Indicator 5: Improved transparency and accountability

- Reduced incidence of corruption and arbitrariness in rule enforcement (as judged by economic agents).

- Increased access to justice, recourse and redress.

- Enhanced independence of the judiciary.

- Increased access to government information.

### Key Contributing outputs

- Legal and policy framework strengthened.

- Horizontal accountability mechanism or checks and balances established.

- Restructuring and performance improvements.

### Actual Outputs Reported in Progress Report

- Municipal proclamations in 4 regions; AA and DD established as chartered cities.

- Draft legal and Institutional Framework study for the 4 emerging regions and Harari. Draft proclamations completed and given to the regions to review and implement.

- Prototype financial regulations implemented in one region.

- New ministry (MWUD) with new departments and an increased urban focus, established as part of the restructuring of Government Ministries in October 2005(EC).

- Urban Good Governance Package completed.

# Programme Management and support

## Institutional Arrangements

The UMCBP is co-ordinated by the Ministry of Works and Urban Development. The direct responsibility falls with the Urban Development Capacity Building Office.

## Coordination with MCB, other sub-programmes and regions

The coordination seems to have improved only recently. The Bureau has raised misgivings about the level of coordination provided by MCB in the past. The FTT now meets and has met at least twice over the last financial year. The DG was delayed for the meeting because of an FTT meeting. There is, however, still a problem with submissions and responses to requests from regions. There is no direct submission and reporting channel between the UDCBO and the regions. The reports are funnelled through MCB. There is however a good relationship, built over the years largely through the roll out of the outgoing CBDSD programme. The Ministry has established a support system through the deployment of technical experts funded by the GTZ to the emerging regions. The intention is to deploy at least three persons per region.

## Compliance with eligibility criteria

Despite the fact that the programme has not been fully funded over the last three years, the Ministry seems to have met all the eligibility criteria.

## Sequencing and integration of reform activities

The Ministry appears to have succeeded in ensuring continuity of the reform agenda across the CBDSD and the PSCAP funded programmes.  It appears that the broader intention of driving through the urban good Governance package is maintained.  The report card shows good reform momentum building in at least the 16 towns in the four regions and the three cities, Addis, Dire Dawa and Harar.  The logical sequence includes policy and legislative reform, followed by building capacity by creating institutions through systems, manuals and guidelines and procedures and lastly building structures.

## Planning and Resource allocation

The approved process has improved since 1999(EC). There is still poor communication with the emerging regions. The Ministry holds periodic consultative workshops with the regions. This has been confirmed with the cities, Addis, Dire Dawa. The Ministry has suggested to MCB that reports submitted by provinces should be passed on to the sub programmes. There has to be improvement in adhering to timetables set up in the PIP.

## Financial Management

The programme received no funding for 1997(EC) and 1998(EC). It has received Birr 13 million for 1999(EC).  The programme has spent 75% of its allocation.  A total of Birr 91,6 million was planned for 2000(EC) and none of the 2000(EC) amount has been released to date. (The 1st quarter is gone and we are already into the 1st week of the second quarter.)

## Procurement

The UDCBO has experienced problems with the procurement process. The problem seems so stems from the uncertainty about the availability of funds, and is compounded by the procurement process. Judging by the quality of the procurement plan contained as an annexure to the Quarterly report (4th quarter ending July 2000(EC)), the UDCBO has sufficient capacity and therefore the problem cannot lie simply with the capacity to understand the process as may be the case with some of the regions visited. A suggestion to decentralise ICB procurement has been made to MCB.

## Monitoring and Evaluation

The focus to date has been to report on activities and output indicators and no weighting and evaluation has been conducted. This means that there is no comprehensive set of information that can make a statement about outcomes. The UDCBO identified this as an issue and intends commissioning studies similar to the Woreda City Benchmarking survey.

## Information, education and communication

The UMCBP has established the practice of participatory budgeting and performance at all levels. It was not very clear how this is monitored. From the regions visited the experience has been very limited in terms of reporting on performance. The public participation in collecting priorities and contributing to formulating budgets was explained in most municipalities. The use of committees at Kebele and sub Kebele levels and how the information gets cascaded upward to eventually formulate City Budget was also well explained.

The programme however, was still not clear on how the rest of the IEC intentions are addressed. The evaluation team has not been able to formulate a view on how the UMCBP manages risks. The risk, especially in the Urban Centres, has been the transfer of authority from the caretaker administration to elected representatives after the next elections. The experience in Addis following the last elections, illustrates how disruptive an election can be to PSCAP and other reform initiatives.

There is no visible set of IEC activities that have a clear trail of delegation from the Federal programmes to the regions and the cities.

# Assessment of cross cutting issues

The interaction with various regions and cities revealed that women quotas were set and have improved in most training opportunities. The UMCBO has ensured that in every city, there is at least a desk dealing with HIV and AIDS issues. Various obligations are been imposed through legislation and codes to ensure environmental management and protection are in place. These issues are still to be subjected to evaluation to check if the desired effects and outcomes are achieved.

# Key issues and challenges

The attempts and efforts of the UDCBO and the Ministry in addressing the PSCAP objectives and, in particular, contributing to the overall transformation of the state and public service, are appreciated. It is very apparent that a lot of activities have been entertained since 1997 to 2000 (EC).  In the case of the UMCBP PSCAP, other programmes may have directly funded these. The main issue is whether there is an improvement in service delivery in the cities, and whether these cities are contributing to social and economic growth. The challenge is in monitoring and evaluating the impact of the activities on outcomes.

The urban decentralisation effort is commendable. The amount of policies, proclamations and regulations passed to foster the creation of responsible sub regional structures is commendable. Two key issues however remain to be addressed. The first is the capacity to exercise these responsibilities at sub regional level. An evaluation needs to be made if all the structures created have been acquired.

The second key issue is to guard against over decentralisation. Harar city is the case in question. There may be a case of over governance brought about by following similar types of decentralisation across the country. Harar is a very small and compact geographic space (less than 400 km square), with a population of under 300 000. It is governed by a regional cabinet (with 10 regional bureaus), a city administration with municipal departments, 7 Kebele cabinets as well as a water and sanitation authority and a Housing Agency. The evaluation team, while sensitive to the special nature of political challenges in Harar and other regions, feels that a much more coherent centralized form of Governance and management can be maintained. This may allow for better distribution of resources and cohesive executive decision-making.

The management of the programme at Federal level should be maintained. The key challenge remains coordination. The UMCBP can benefit greatly if there was a much more coordinated programmatic approach between the regions, the cities and the Bureau directly. The evaluation team believes there is sufficient capacity at federal and regional or city administration level to manage output and out comes. The MCB should maintain responsibility for managing planning and strategic support and alignment with other sub programmes. This may mean a form of decentralisation of Federal PSCAP urban management output and outcomes to the Ministry of Works and Urban Development.

The Ministry has already made representation on the procurement process and the request to decentralise ICB decision making to the UDCBO. A further decentralisation to advanced regions and cities such as Addis Ababa, Dire Dawa, Harar and the 16 towns where capacity is displayed, should be considered.

There is now an opportunity for the Urban Sector in the country to create and strengthen Local Government and Municipal Management institutions. Some of the key questions and key institutions to consider may include:

- The establishment of a distinct Local Government Ministry at regional level. It may be possible to separate local / municipal government competencies out of the Works and Urban Development and the Federal Affairs Ministry and include them into a mandate of a new local government responsibility at regional level?

- A much stronger push is required in building an association of Local Government. This is a statutory organised local government body that can be useful to support, advise and provide an advocacy platform for municipalities. There is an immediate opportunity, and need, at regional level where there are a number of municipal structures established. The case may not be that strong at some of the regions where there are fewer municipalities (Dire Dawa and Harar).

- The Associations can also be used as cross municipal or joined up association that use economies of members for procurement of skills, goods and infrastructure to deliver services.

- There is a strong and emerging number of Urban Management professional institutes and bodies. It may be worth supporting the establishment of a distinct municipal managers' institute. This could be a member based body that recruits all senior / top management in municipalities as its members.

- Affiliation to African or international bodies is critical.

- The idea of beefing up the ECSC by the creation of an Urban Management Centre should still be pursued.

- Lastly, the creation of an incentive package for key personnel is important. Managing reform and transformation in cities is burdensome. The efforts of men and women deployed to carry out these tasks, needs to be rewarded.