Annex 8: Addis Ababa Report

# Background

The evaluation team, made up of Pascal Moloi and Girma Shegute, visited Addis Ababa from 29 to 31 October 2007.  Addis Ababa is the capital of the country.  It has a population of roughly 4 million and is surrounded completely by the Oromia region. Addis is a chartered city and enjoys full regional status as well as being a municipality.  The City has been divided into 10 sub cities each with at least 9 to 11 kebeles.  The city has 8 bureaus that are responsible for the running of state functions, on the one hand, and has 9 departments responsible for the execution of municipal functions.  Members of the Mayor’s cabinet head the bureaus. The City Manager is responsible for all the Municipal Functions and reports to the Mayor.  The Mayor enjoys the same status as a regional President.

The visit kicked off with a full morning briefing chaired by the Bureau Head.  The session was well attended by all Programme heads and the Deputy Bureau Head.  Further visits included:

- Follow up sessions with the TSRP.

- Follow up session with the Urban Management Capacity Building Programme.

- A Visit to the Bole Sub City which included:

  - A briefing by the Capacity Building Lead person,

  - A discussion with the City Manager,

  - An inspection of the Vat, TIN and Land registration systems, and

  - A visit to the 04/06/07 Kebele administration system.

- A visit to the Nifas Silk Lafto Sub City which covered:

  - An inspection of the Vat, TIN and Land management offices and systems,

  - A inspection on the housing and lease management issues followed by a discussion.

- A visit to the Lideta Subcity First Instance Court.

- A Visit to the Gulele sub-city where the team

  - Conducted a capacity audit interview; and

  - Inspected the Tax system management premises.

# Overall assessment

## General overview

The Reform and Transformation story pre-dates PSCAP in the City. The City initiated the reform process around 1995(EC), before PSCAP was launched.  From the discussions with the team, the city’s reform took a serious knock with the events around the elections. The programme was stalled, and PSCAP has now been driven along by a caretaker administration. The city feels constrained in driving a full transformation and reform programme, given the temporary nature and the mandate of the current administration. It appears that the Administration concentrates on building institutions and the capacity of these institutions to function effectively. Despite the impact of the election issues, the city in general seems to be making huge strides in undertaking PSCAP activities and pushing a decentralisation of powers and capacity to sub-cities and kebeles.

A presentation on the city’s performance against its mandatory activities to date was made.  This presentation seems to be an improvement from the last supervision mission, when, it appears from the notes, it was presented in a format that the mission was not happy with.  Relevant references will be made in the individual programme assessments below.

# Assessment of implementation of each sub-programme

## JSRP

### General observations

The programme appears to be running fairly well in the region and this seems to have been the case for a while. The comments from the Chamber of Commerce and from an independent practitioner, although made roughly about the state across the country, will probably impact Addis more.  These respondents made two comments.  Firstly, the courts still remain preoccupied with criminal cases and are not the obvious point of recourse for commercial and civil disputes.  Secondly, the courts have raised the bar in terms of pushing and administering the court process. This, without the full backing of a revamped, trained and prepared judiciary on human rights, democracy, the constitution and modern jurisprudence, means that the courts may still not be delivering fair judgements.

There may also be some problems in the roll-out of the accompanying equipment, stationery and machinery to sustain the new approaches to court process administration.  The court visited by the evaluation team was sadly lacking in the basic infrastructure to make the colour-coded systems succeed.  There were not enough files with the correct colour coding, no storage facilities to hang the files, the printer had run out of cartridge and it seemed like this had been the case for a while. As a result, the court was only achieving half of the potential case management turn around given its capacity. The President and the Registrar are very articulate and appeared very capable but are being let down by the facilities. The building and premises also doe not give a sense that justice will be prosecuted in those surroundings. The information desk operates under severely constrained physical conditions.

### Minimum mandatory activities

The following presentation of the city’s performance against its minimum mandatory activities was presented:

- Installation of court case management and case recording & transcribing systems in the Appellate (regional supreme) & First Instance (high courts)

  - Installation of ICT

- Installation of colour-coded filing system in all First Instance (woredas courts), establishment of information counters in the Appellate (regional supreme) & First Instance (high courts)

  - Installation of ICT

  - Office equipment procured and Information counters established

  - Computers and related facilities accessed at different first instant courts

- Initiation of in-service training and professional development of all judges, lawyers and court clerks

  - Short term training for the prosecutors

  - Training on capacity building for judges

  - 15 days professional training has been given to all judges

### Strengthening the judiciary

- Fifteen days professional training has been given to all Judges

- Information counters established

- Computers and related facilities accessed at different first Instant courts

### Law revision and law reform

#### Law enforcement capacity enhancement

- A 4 days workshop on Gender has been conducted.  In the workshop different issues were discussed including: Differences between sex & gender, the basic gender terminologies, definitions & concepts and the basic concept & approaches of gender and development

- Computers and related facilities have been installed

- One day training on ICT has been given

#### Legislative organ

The planned activities include:

- Development of  Mechanism of communication by members of the council to their constituents.

- Develop system for recording, documenting, retraining and distributing council proceedings.

- Provide materials and office equipment for the secretary of the council.

These activities have not been implemented because there is no council in Addis.

## UMCP

### General Observations

The main objective of the sub-program is to enhance the capacity of municipalities in the delivery of services and enable urban centres to play a more effective role in social and economic development.

Responsible bodies of UMCBP - Implementing offices:

- City Manager Office

- Housing Agency (Housing Development Project Office)

- Fire and Emergency Services

- Land Administration and Development Authority

- Environment Development Office

- Sanitation, Beautification, and Parks Development Agency

- Infrastructure Coordination and Building Permit Authority

Since 2004(EC) the Urban Management Institute (UMI) has acted as the main body responsible for implementing UMCBP both as an implementing office and an office to support other implementing offices.  Regulation No 13/1998(EC)  Addis Negarit Gazeta established the Urban Management Institute of Addis Ababa (UMI) as a legal entity in 1998(EC) (EC).  The UMI was re-established again in February 2003(EC) as the Urban Management Institute in line with the restructuring of the City Administration of Addis Ababa. The mission of UMI is to offer training, research and consultancy services to the city Administration staff.

The 2000(EC) Plan proposes changes to the management of the programme.  A number of challenges and difficulties have been encountered with the current arrangements.  These include a lack of a clear coordinating structure given the long list of eight responsible agencies (as shown above) the lack of skilled experts, low commitment from some of the stakeholders, etc.  The proposal is to rationalise the implementing agencies into four. These are:

1. Urban Planning Department

  - Refinement and Development of LDP, Eco-system, and Urban Renewal

  - Implementation Guideline Establishing the Urban Development Plan in the decentralised Urban Management System

  - Establishing Urban Development Plan in the Decentralised Urban Management System

2. Fire and Emergency Services

  - Formulation of Fire Code

  - Formulation of Fire Services Standard

  - Preparation of an Organisational Structure and HRM Strategies development, salary scale, incentive mechanisms system design for Fire and Emergency Services.

3. Housing Development Project Office

  - Refining the Urban Housing Policy

  - System Development towards Strengthening the Housing Development Project Office

4. Urban Management Institute (UMI)

  - Refining the organisational structure of the Institute

  - Developing working manuals for training, research and consultancy services

  - Developing a well-designed HRM manual

  - Developing a capacity development strategy for the city

  - Developing a HRM Strategy and Policy for the city

  - Provision of First round bulk generic training to all concerned staff of CGAA

The programme, in the case of Addis, is different. The activities were almost all completed in 1997(EC) almost all before the current phase of PSCAP.  The current processes seem to largely be about implementation and refining some of them.  As will be shown in the MMAs, all the activities have been achieved.

### Performance against minimum mandatory activities

#### Development and adoption of region's urban development policy and strategy

- 100% Five years Strategic Plan: 1996(EC) -2000(EC)

- 100% Urban Development Strategy (focusing on Five components: Micro and Small Scale Industries, Housing)

#### Development and adaptation for implementation of personnel management manuals for local government authorities

- 100% Preparation of Organisational Structure and HRM Strategies

- 100% refining the organisational structure of the Institute

#### Development and adoption of urban land legislation and municipal proclamation

- 100% Proclamation 16/96: Addis Ababa City Master Plan Preparation, Issuance, and Implementation Proclamation

- 100% Regulation 17/96: Regulation for the Approval and Implementation of the Addis Ababa City Government Structural Plan

- 40% Regulation: Cemetery Regulation

- 100% Regulation x/96: Regulation to protect the expansion of illegal Land Occupation and illegal Land Tenure.

- 100% Regulation x/96: Building Permit Regulation

- 100% Directive 1/97: Building Permit Directive Miazia/97

- 40% Regulation: Infrastructure Coordination

- 40% Regulation: Advertisement (Billboard) Services Regulation

- 40% Regulation: Parking and Green Area development and Protection Regulation

- 40% Guideline: Real Estate Design and Implementation Guideline

Completion of one round of bulk generic training to all relevant regional and municipal staff.

- 100% First round bulk generic training

The evaluation team found it difficult to box the achievements to date into the usual pigeonholes used for other regions.

## TSRP

### General Observations

The organogram below is of the Revenue Agency in the BoFED.

The main objective of the program is to enhance the city Government’s revenue and to improve the revenue and tax administration. The city’s revenue increased from Birr 815,67 million in 2002/03(EC) to Birr 2,4 billion in 2006/07(EC). The Head of the agency was very reluctant to commit to a figure after the 5-year strategy term.  When pushed she estimated that the city could be collecting as much as Birr 6.3 billion by 2002(EC).

There are critical problems, which require additional finance and would be covered by an external fund.

These are:

- Procurement of 109 generators for the continuation of service delivery when the electricity goes down.

- Procurement of fingerprinting equipment to solve the problem of duplicating TIN.

- Procurement of ICT materials to facilitate operational functioning of the Agency

The evaluation team inspected the systems in the agency (after walking eight storys, and reaching an altitude of more that 2000m above sea level).  The systems are fully automated and live.  Also on the same floor is a fully equipped training centre that services new recruits and is used as a refresher centre for everyone.  The team interacted with the Public Relations team which boasts a number of mass communication materials including posters, flyers, brochures and a fully functional website which has online application capabilities.

The team visited the agency premises in all the sub cities and was happy with the rollout at these centres. There was however no clarity from one sub city about the involvement of representatives of the public on the assessment and the appeals committees.  They were insistent that this is not allowed and were surprised that the chamber is involved at the city level.  The visit at the Kebele contradicted the 24-hour TIN certificate turn around time claimed by the sub city.  The deputy administrator of the Kebele raised a concern that the failure to meet the turn around time is a disincentive for potential business.  The TIN is a prerequisite for issuing business licences.

Overall the system is functioning exceptionally well. The City is a recipient of a TIGA (Technology in Government in Africa) award. This was in recognition of the cities employment of technology in enhancing its revenue and tax collection. The walk up the stairs was worth the effort.

### Performance against minimum mandatory activities

#### 100% Adoption of Proclamations, regulations and directives for income, TOT and VAT

- Income tax and TOT Proclamations, Regulations and directives are implemented

- Revenue assessment and collection directives have been adopted

#### 100% Completion of 50% coverage for computerised Taxpayers Identification Number (TIN)

- In case of Addis Ababa, we can say completion of 100% coverage has been achieved.

- Currently daily registration and computerisation is a regular activity of the city revenue administration

- The infrastructure setup is networked from federal to city and from city to sub-cities- so TIN is 100% computerised and more than 152000 taxpayers TIN certificate have been issued.

#### 100% Completion of annual turnover survey

- The committees in each of the Kebeles surveys the city taxpayers through door to door visits and submitted the daily turnover reports now used for official assessments since 1997(EC).

#### 100% Completion of training on laws for tax administrators at regional and city administration levels in case of Addis Ababa

- All staff was trained on tax laws and regulations and the working manual for each employee was distributed.

- Moreover, to introduce new directives the employees participated in discussions on clear implementation

- Awareness creation on tax laws and regulations was undertaken through the media. This included conducting taxpayer education, through the development of booklets, posters, brochures etc.

## CSRP (Including EMCP)

### General Observations

The CSRP was presented and discussed.  The presentation included feedback on expenditure management and control.  There in no backlog in the closing of accounts and the city appears to have rolled out the financial management reform programmes. The city carries out Audit Assignments but finds it difficult to meet all the recommendations contained in the findings due largely to the lack of capacity.  Most of the EMCP appeared to have been installed and funded out of DSA funding before PSCAP.

The one obvious omission in the presentation and discussion the lack of was reference to Strategic Planning.  As already mentioned, the explanation given was that given the nature of the transition administration, there was more emphasis on dealing with building the capacity of operations and staff and implementation of the already existing five year strategic plan.

There was however a bit of BPR training and roll out of quick wins in Kebeles and Sub cities.

The general impression the evaluation team got from the field visits was that there are basic approaches to dealing with office layouts, customer reception and service areas either in housing, Tax, SME centre and land administration.  Most have the basic set of conditions posted at entrances, and directions and basic information is given.  There was no commitment to turn around time and service standards visibly displayed for the public. The look and feel and the conditions of the facilities differed from premises to premises with some of them (Inherited from previous authorities like roads in the Nifas Silk Lafto Sub city) looking relatively posh.

### Performance against minimum mandatory activities

#### 100% Elimination of backlog accounts at City and Sub city level.

#### 90% Installation and training in medium term expenditure management procedures manual, BIS, and BDA3 systems in all regional and Sub city institutions

- Accounts manual, module and Chart &Account are printed and distributed during the training session and 1050 Accountants and auditors are trained

- BDA (3B) program has installed by DSA Project and the 1996(EC) , 1997(EC) accounts have been closed. For 1999EFY more updated software, i.e. IBEX was installed and accordingly 1998(EC)  accounts were closed.

#### 100% Completion of training in and adoption of result oriented performance evaluation (ROPE) system in all regional bureaus and Sub city

- TOT on ROPE system has been given to trainers from regional and sub city offices

- A guiding manual of ROPE has been adopted and distributed to all offices at region and sub city level.

- Bulk training to all supervisors has been undertaken

- A 1-day consultation workshop for 150 supervisors was undertaken and comments from all institutions on ROPE collected and analysed.

#### 100% The following PSIP-related activities launched in 75% of regional bureaus and Sub cities:

- Completion of client scorecards

- Initiation of Business Process Re-engineering

- BPR-quick wins implemented in 90% of regional bureaus to Kebele levels

- Guidelines to implement BPR have been prepared

- Baseline, impact assessment and customer satisfaction surveys were conducted

- One stop shopping service centres were established

#### 100% Completion of top management training in Strategic Planning Management, Change Management, Performance Management, and Leadership Development for Agency heads of 75% of bureaus

## ICT

### General Observations

The ICT PSCAP coordination is currently in the Capacity building Bureau.

There was approval given recently to establish a separate ICT agency.   The new agency will have the following mandate:

- Coordinating ICT activities at city level

- Proceeding with setting up standard and protocols

- Establishing and operating a city data exchange

- Creating easy to access city information (including the creation of a web portal)

- Establishing, operating and maintaining a city wide data centre

- Capacity Building

- Establishing an e-government environment.

The ICT team shared with the evaluation team other non-PSCAP projects that are paid for out of the normal government budget. These include a WAN project to connect 5 public offices through WANICT policy for the city and the acquisition of a City Orthophoto and digital line map.

### Performance against minimum mandatory activities

#### Human resource development

- 45% completion of training programme on application packages, database design, system development, GIS and network technology for civil servants;

- A planned workshop for creation of awareness of ICT

- A planned experience sharing tour of South Africa or Namibia

- 10% completion of awareness creation in the use of ICT for the community

- Prepared TOR to conduct advanced training for ICT experts

#### Public service delivery and good governance

- 70% adoption/customisation of national ICT policy

- 20% Implementation of city wide network for public institutions at all levels

- 10% Preparation of proclamation governing the registration of city residents

- System development and implementation for the 13 public offices is planned

- 15% procurement of hardware and software

- A workshop on implementation of modalities of PSCAP was held

- 30% City wide residential data capturing and encoding.

#### 100 % design of applications for sector development including:

- Budget and disbursements

- Human Resource Management

- Archives and file tracking

- Procurement Management

- Property Management

- Vehicle and Fuel Management

- Project Monitoring, Evaluation and Reporting.

#### Community based information systems and services

- 20% systems study and development complete

- 10% customisation of common applications programmes completed.

# Programme management and support

## Institutional arrangements for PSCAP in region

The disturbing point raised by the previous mission about lack of buy in by Addis Leadership and Bureau Heads was not evident.

The Head of the Capacity Building Bureau heads up PSCAP in the City.  The Bureau is divided into two main Departments, the Monitoring and Evaluations and Decentralisation Department, and the Programmes Coordination Department.  The latter serves as the PSCAP PPD and fulfils all the PIP responsibilities. The Programmes Coordination Department is responsible for the over all coordination and Management of PSCAP.  It is staffed by a Head, two senior Planning, M&E experts, one Procurement Specialist, one Procurement Officer, and one Secretary.

An Attendees committee has been established and meets as and when required and is structured as illustrated below:

| Organisation | Title | Responsibility |
| --- | --- | --- |
| Capacity Building Bureau | Program Coordination Department Head | Chairman |
| Urban Management Institute | Institute deputy Manager | Member |
| City Information and Documentation Department | Department Head | Member |
| Finance and Economic Development Bureau | Legal Department | Member |
| Capacity Building Bureau | Procurement Specialist | Member and Secretary |
| Implementing agency | Representative of Implementing agency | Conditional Member |

## Coordination with MCB, federal sub-programmes, and sub-cities

There was no evidence at all of coordination between the city programmes and Federal Offices.  There was, at the level of technical assistance and sharing, possible relations between Bureaus.  Formal coordination is managed through the BCB.

There is a capacity building Head at Sub city level responsible for PSCAP coordination.  The Revenue Agency, as well as other agencies of the city, have a presence in the Sub cities.

## Compliance with eligibility criteria by region

| Criteria | Comment |
| --- | --- |
| - Submission of signed “Participation and Performance Agreement” by the relevant minister responsible for the federal subprogram or relevant cabinet member for region; | - The city meets the criteria |
| - Establishment of appropriate governance and implementation arrangements; | - The structures are in place |
| - Completion of relevant capacity assessments across all participating sectors and levels of participating institutions, especially in the case of Sub city and municipal strengthening; | - It is assumed that these have been made, as there was no evidence to the contrary. - Individual programmes including CSRP and the ICT programme made reference to needs analysis |
| - Timely submission of endorsed costed medium-term rolling plans, as well as technically sound, feasible annual implementation/procurement plans in line with the financial calendar; | - Addis seems to have improved a lot in meeting the requirements as compared to the comments in the last mission report. |
| - Explicit provision for evaluation of annual performance including dissemination to the public of such evaluations, satisfaction scorecards, etc, as part of the consultative planning process. | - The Deputy Head of BCB outlined attempts to use the media as much as possible in general to dealing with city matters. There was no direct mention of activities and/or programmes that suggest that there is specific PSCAP communication and dissemination of information |

## Planning and resource allocation

The Regional Technical Team Chaired by the Head of the Programme Coordinating Department is responsible for the planning and resource allocation for PSCAP in the City.  The Team made up of programme coordinators also includes the Head of the Monitoring and Evaluation and Decentralisation Department.

## Procurement

The lengthy World Bank procurement system was singled out as a problem.

## Expenditure and financial management

Addis has enjoyed 144 million Birr over the last five years.  This amount does not include the estimated 50 million Birr the city contends it spent out of its pocket that is PSCAP related but was incurred even before PSCAP was launched in 1997(EC).

Expenditure and Budget tables are attached at the end of the report.

## Monitoring and evaluation

Addis seems to have a very strong monitoring and evaluation Department. It is however still working on adapting its tracking system to meet PSCAP PIP requirements. In the meantime there is very little monitoring and evaluation happening.  Programme Coordinators have been requested to supply information that the evaluation team is beginning to organise into a compressive data set that could be used for measurements and baselines for the future evaluation exercises.

## Information, education and communication

There was no presentation specific on IEC and the evaluation team chose to make the following comments against the PIP guidelines:

Targeting Risks.  The fact that Addis was a “leading” transformation and reform site in Ethiopia and was disrupted by the last elections is worth mentioning as a risk.  There was no direct mention by the leadership of the programme, nor was there any IEC details given.  The Evaluation team is satisfied that the Addis team is aware of these risks.

Delegating to Mandated Institutions. Because the IEC activities were not discussed the Evaluation team was unable to check if the appropriate delegations are in place.

Scaling Up.  The ICT attempts at assisting with presenting platforms are a good example of scaling up potential. The evaluation team found a whole lot of activities, e.g. The TSRP website that is run separately without a link to the city website and the collection efforts and messages to tax payers that are not shared with service payments for housing water and other municipal fees.

Quality Control and Assurance. It is not clear if the RTT is geared to be the quality assurance-clearing house.

Public Disclosure.   The Addis team pointed out attempts through IEC to change perceptions, which include collecting public opinion, the use of local radio and TV, commissioned Theatrical productions and publications.  The comments from the non-government sources that the evaluation team had the opportunity to interact with, (including the chamber, a legal practitioner and a media practitioner) are a good sample about the government’s performance in general.  All of them are residents of the city and their comments are shaped by their own personal experiences, which are in fact Addis experiences.  From their comments it is safe to deduce that the City lags far behind in terms of disclosures generated from surveys.  There is general awareness from the respondents about PSCAP, but this is not drawn from the city’s direct and deliberate efforts.

## Sequencing and integration of reform initiatives

There were no obvious problems with sequencing.

# Cross-cutting issues

Women’s issues are handled by the Women’s Affairs Department.  There was no obvious mainstreaming that the evaluation team was able to pick up. The same could be said of HIV and Aids and Environment.  HIV and AIDS are left to the desks dealing with such matters at various levels and is not a mainstreaming subject.  Environmental issues are in legislation, in the mandate of the parks and cemeteries mandate, etc.

# Assessment of programme outcomes

## Autonomy, greater inclusiveness and adequacy of financial resources flows (in-year and across years)

- Exercise of local self- government

- Devolution of political, fiscal, and Administrative power to local government

- (Devolution of power to exercise their Authority, to levy  and collect Revenue, to use their resources and to deliver public services at lower level)

- Enhanced public participation.

## Enhanced revenue performance and fiscal autonomy

- Raise in revenue (Addis Ababa collected ETB 815 million in 2003, ETB 1.6 Billion in 2004, ETB 2.1 billion in 2005, ETB 2.6 billion in 2006 and ETB 2.4 fiscal year)

- Automated / computerised / tax Administrative system

- Improving revenue performance and enhancing transparency, quality and efficiency of tax collection.

## Improved quality and efficiency of operations

- Introduce and Set service standards and improve efficiencies of services

- Bring together related (interdependent) service under one umbrella (one Stop shopping)

- Public-private partnership (out-sourcing)

- Automation and computerisation

- Reduce Excessive Bureaucracy

- Minimising the workload and complication of the public offices

- Optimal utilisation of resources.

## Improved transparency and accountability

- Issuing different Guidelines, operational manual leaflets, brochures and website.

- Ease of access to services and information.

- Defined authority and Responsibility at all levels.

- Hold public hearings and advice.

- Automation and computerisation.

# Key issues and challenges

The following were identified as key challenges:

- The high turn over and lack of skilled manpower.

- Lack of motivation (This point was motivated along the lines of a lack of an incentive scheme generally for public servants.  It appears that even the annual inflation adjustments have not been done in a long time.  There maybe a bit of transformation fatigue if too much is pushed without direct gains for staff.

- Considering PSCAP as additional assignment. This relates mostly to staff requests from time to time to assist with PSCAP assignments without extra allowances and/or compensation.

- Lack of coordination between Federal and Regional sub programs. There was a strong preference expressed for such a need, especially given the location of the city as the capital and living side by side with federal authorities.

- Lengthy World Bank procurement process (this point is repeated here for emphasis).

## Issues that need special attention

The Addis presentation to the evaluation team ended with the following issues highlighted by the PSCAP as matters needing special attention.

- Introduce incentive mechanism and motivation for key PSCAP professionals.

- Delegation of the PSCAP procurement activities to implementing agencies.

- Delegation of procurement of ICB to regions.

# Lessons learnt and recommendations

The key lesson to be learnt form the Addis Ababa experience is the importance of a stable political environment to a successful and sustained transformation and reform effort.  Addis had committed a lot of resources and energy to the transformation programme before the elections.  The disruptions after the elections usurped some of the energy and caused a lot of delays in the roll out of the programme.  The current caretaker administration is putting a lot of effort into rebuilding momentum and energy but is concerned that the previous levels of energy, particularly among staff, may not be achieved.

Addis as a City Region is well positioned to run a decentralised civil service reform programme.  With the appropriate resources, the City is well equipped to manage PSCAP.  There appears to be massive growth and development happening in the city at the moment. Addis being the capital of the country cannot afford to have a civil service that cannot cope with the increasing demands on its services and infrastructure.  The special role and place the city holds in African politics today, by virtue of being the seat of the African Union, has to be taken more into account.  This fact was not obvious in the deliberations with the city.  The relations with the AU although federal in nature has to translate to the City facilitation transactions relating to land management, the provision of services and the maintenance of a healthy and clean environment around the many sites and embassies that are now a huge feature of the Addis economic and social make up.

Some specific recommendations:

- The BCB capacity to monitor and evaluate impact should be beefed up.  It is commendable that the city already has a Monitoring and Evaluation Office in the Bureau.  The office has to gear up its ability to monitor impact and to find gaps that should be addressed in the future.

- Most of the municipal reform and transformation efforts hinge on the UMCBP.  The fact that there is no single bureau taking responsibility for this is still a bit of a worry.  While it is appreciated that the responsibility has been narrowed from eight to four agencies, the evaluation team would still want to recommend that the office of the City Manager be seen as the Executing Authority.

- Where feasible and where there is capacity, as demonstrated in the Revenue Agency the city should consider devolving further responsibilities for civil service reform.  This should be the case for Health, Trade and Industry, Education, Water and Sewer and other key sectors.

- The Bole Nifas Silk Lafto and sub cities displayed greater potential to run mandates assigned to them.  This probably makes a case for further devolution of PSCAP responsibilities to this level.  This recommendation is made with great caution that it should not be applied across the board without an assessment of capacity.  The Gulele sub- city did not display the same level of capacity as the other two and may need to be assisted centrally.

- The Evaluation Team is aware of the effort to revise aspects of the 5-year Plan adopted in 1996(EC) and the risks associated with the massive investment in the exercise ahead of the next election.  It may however be possible to review and suggest aspects on the spatial plans, the transportation aspects, and the land and housing sector plans. The review could take the form of developing baseline data that could be used by the future leadership as the basis for setting targets.

- The normalisation of the human resource environment is critical. The management of remuneration and payroll automation, increased communication to staff and the efforts towards wellness and occupational safety will go a long way in building staff confidence.  A lot of caution should be taken in sequencing ROPE, the establishment of new structures and the BPR exercises and aligning these to strategic planning.

#### Annex A: Budget and Expenditure Tables

| FIVE YEAR BUDGET ALLOCATION FOR PSCAP |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Programme | Budget Share % | Budget Allocated for 5 years | 1997(EC)/1998(EC) | 1998(EC) /1999 | 1999/2000 | 2000/2001 | 2001/2002 | TOTAL |
| CSRP and IEC | 14.01 | 16087.54 | 5860.7 | 3273.9 | 2741.9 | 2573.9 | 1634.9 | 32186.85 |
| ICT | 50.74 | 58252 | 34200 | 18781.6 | 3584.2 | 790.6 | 895.6 | 116554.7 |
| JSRP | 5.64 | 6474.95 | 2267.5 | 1999.3 | 1632.1 | 331.3 | 248.8 | 12959.59 |
| TSRP | 10.14 | 11641.5 | 4880.2 | 2485.1 | 2034.5 | 1449.2 | 792.38 | 23293.02 |
| UMCBP | 16.97 | 19480.79 | 3944.2 | 10023.4 | 2751.5 | 1568.2 | 1193.2 | 38978.26 |
| TOTAL | 97.5 | 111936.78 | 51152.6 | 36563.3 | 12744.2 | 6713.2 | 4764.88 | 223972.5 |
| PS and M&E | 2.5 | 2798.4195 | 1278.815 | 914.0825 | 318.605 | 167.83 | 119.122 | 5599.312 |
| TOTAL | 100 | 114735.2 | 52431.415 | 37477.3825 | 13062.805 | 6881.03 | 4884.002 | 229571.8 |

| APPROVED BUDGET AND UTILISATION BY PROGRAME JANUARY 1998(EC) TO JULY 1999 |  |  |  | APPROVED BUDGET AND UTILISATION BY PROGRAMME JULY 1999 TO JULY 2000 |  |  |  | THREE MONTH FINANCILA PERFORAMNCE JULY 2000 TO SEPTEMBER 2000 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PROGRAMME | APPROVED BUDGET | EXPENDITURE | % UTILISATION | APPROVED BUDGET | EXPENDITURE | % UTILISATION |  | APPROVED BUDGET | EXPENDITURE | % UTILISATION |
| CSRP | 8019769 | 2510279.79 | 31.30 | 2610400 | 2066653.5 | 79.17 |  | 1472100 | 0 | 0.00 |
| TSRP | 7046439 | 896470.71 | 12.72 | 823800 | 865496.61 | 105.06 |  | 1852900 | 0 | 0.00 |
| UMCBP | 7181522 | 341317.27 | 4.75 | 2329220 | 341317.27 | 14.65 |  | 4832470 | 1771691.74 | 36.66 |
| ICT | 25107733 | 180086.8 | 0.72 | 3248900 | 180086.8 | 5.54 |  | 8684900 | 9170.16 | 0.11 |
| JSRP | 6175900 | 126478.1 | 2.05 | 2348600 | 70546.7 | 3.00 |  | 314000 | 470839.64 | 149.95 |
| PS and M&E | 1230938 | 307666.93 | 24.99 | 374100 | 146116.93 | 39.06 |  | 506600 | 150667.55 | 29.74 |
| EMCP | 0 | 0 | 0 | 0 | 0 | 0 |  | 930900 | 0 | 0.00 |
| TOTAL | 54762301 | 4362299.6 | 7.97 | 11735020 | 3670217.81 | 31.28 |  | 18593870 | 2402369.09 | 12.92 |