Annex 9: Afar report

# Background

Crispian Olver, assisted by Atto Birhanu, visited the region from 15th to 19th October 2007 and met with the BCB, MOFED, all sub-programme Bureaux and coordinators, two woredas (Awash Water Bureau and Mille woreda), one municipality (Awash), the Supreme court, and the local police station in Awash (see annexure 22 for full list of persons met). A large number of documents were collected as part of the assessment, and these are listed in annexure 23. The evaluation was constrained by the large distances between centres, the general lack of output and outcome indicator information, and the majority of respondents not being available in the afternoons. This was partly offset by the sub-programme coordinators and Bureau heads making a significant effort to prepare information and to participate in the evaluation process. The evaluation team would like to thank the various organisations and people who generously made their time available to participate in the assessment.

# Overall assessment

Afar is an emerging region with an estimated population of 1.4 million people. The region is arid with a limited economic base, and large nomadic component to the population. Regional government in Afar has only been operating for a decade and a half, so the structures of government are in some cases still embryonic. The capital of the region has recently been moved from Asayita to Semera. The civil service remains severely constrained by the lack of basic infrastructure and facilities, and the generally poor level of skills available in the region.

The implementation of PSCAP in the region has been understandably slow. The region has completed approximately two thirds of the Minimum Mandatory Activities, and hopes to complete the remainder of them this financial year. The region is struggling with the complexity of planning, budgeting and procurement processes for PSCAP. There have been serious delays in the procurement process, and consequently only the training component of PSCAP has been utilised to date. Almost no expenditure on goods or consultants has taken place. This threatens to undermine the credibility of the programme.

There have nevertheless been some significant achievements, considering the environment in which the region has to operate. The region has embraced PSCAP, and has appointed regional counterpart agencies responsible for each sub-programme. PSCAP has been integrated into the region’s five year action plan, which maps out three phases for the programme. Currently the region is in the preparatory phase, and hence the majority of its activities are focused on creating the enabling environment for the full scale roll out of the programme.

There is a widespread level of awareness amongst beneficiaries about the focus on service delivery, about the main components of the training programme, and about the good governance package for woredas and municipalities. Strategic planning has been institutionalised across regional and woreda institutions. A large amount of training activities have taken place, and some sub-programmes have developed very useful models of facilitating capacity development. The PPD has established a project tracking and monitoring system that lays a solid basis for future regional coordination. Gender and HIV/AIDS issues have been taken up very widely in training programmes, facilitated by dedicated offices for both these issues at woreda and regional level.

# Assessment of implementation of each sub-programme

## JSRP

### General observations

Given the overall stage of implementation of PSCAP in the region, JSRP is doing well. Despite a slow start, there are tangible improvements resulting from the JSRP. The Justice Bureau head and the JSRP coordinator appear to have a clear understanding of the programme, are well motivated, and gave cogent explanations of progress with the programme. They have taken the initiative with aspects of the programme without any guidance from federal JSRP. The Bureau is not effectively structured at the moment, and a new structure has been proposed to the civil service commission. There is a lack of attention to monitoring outputs, and the information required to report on outputs for each component of the programme was not available.

The coordination with federal, regional and woreda institutions appears to be weak. There is a quarterly meeting of the justice sector coalition at federal level with brings together all the relevant JSRP actors and beneficiaries.

### Minimum mandatory activities

The MMAs are partially complete. Court case management is in place in the high court, but not the supreme court. Work has started in all the courts on the colour coded filing system, and it has been completed in the supreme court. Information desks have been set up in the high court, but not the woreda courts. Initiation of in-service training has been done.

Awareness creation and orientation workshops have been held with all beneficiaries on the JSRP programme. The region did this on their own initiative, without any pre-training from the federal level. Gender and HIV/AIDS issues were included in the programme.

### Strengthening the judiciary

The professional capacity of the judiciary (judges and attorneys) has been upgraded through distance education. Coming from a low base (with no diplomas or degrees) 26 prosecutors have been upgraded to diploma level, and 13 promoted to degree level. Other training initiatives include orientation and training for judges by Federal JSRP experts in service delivery, training in case flow management for judges and supreme court managers, and an exposure visit for judges to the federal institutions. All courts have benefited from the training effort, including most court staff.

The colour coded filing system has been implemented in 15 woreda courts, 5 zones and the supreme court. A recording, transcribing and data base system has been established in the supreme court and 2 zones.

There has been some improvement in the speed of processing cases, and in the number of cases settled each year, although no overall statistics for the region were available to back this up. The supreme court registrar indicated that the speed of processing cases had improved by 11.7%. No files are being lost (previously this was an enormous problem), and beneficiaries can now phone the court and request information directly, without needing to physically visit the court.

### Law revision and law reform

An exposure visit and exchange of ideas was arranged with Tigray, Amhara and SNNP regions, which was very useful. The regional delegates came back with a number of regulations and laws which they have adapted to their own requirements. There is a new criminal law. A manual has been prepared regarding the issuing of certificates for contracts, births, marriages etc.

### Law enforcement capacity enhancement

Police have received training in human rights, complaint management, community policing. A visit to a woreda police station confirmed that training had taken place, and that there now was a different approach to policing, including a larger number of criminals being brought in by distant communities. Police are now according prisoners rights such as release after 24 hours unless prosecuted. The main capacity constraints seem to be the lack of basic equipment and infrastructure such as a vehicle, radio and office computer.

213 prison administrators have been trained in prison administration and management. A similar number of police have been trained in criminal investigation in partnership with the Tigray and Amhara police institutions.

### Legislative organ

85 parliamentarians have been sent to the civil service college, and trained in parliamentary procedures, roles and responsibilities of MPs, and dealing with public concerns. This has brought about a shift in attitude and output from parliament in terms of developing legislation. The speakers from all the woredas were also trained regarding their roles and responsibilities. An existing partnership with Amhara has been invaluable in this regard, but PSCAP resources played an important role in augmenting this support.

### Next steps

A study into the strengths and weaknesses of the regional justice system has been conducted in collaboration with the Amhara Regional Bureau. A stakeholders workshop is being planned to present the findings, and plan a systematic programme – this will be important for the next phase of implementing PSCAP.

## UMCP

The UMCP programme has suffered from a high staff turnover, a lack of commitment to the programme from senior management, and a general lack of skills and staff in the Bureau of Works and Urban Management. As a consequence the UMCP is seriously underperforming. This situation is compounded by the urban development challenges. As it is a newly established region, the urban municipalities of Afar are being established from scratch. Decentralisation in Afar was only on paper until 2 years ago.

### Regional urban management policy

An urban development policy and land structuring workshop has been held with stakeholders, but the urban development policy for the region has not yet been completed. A proclamation has been prepared on small towns. Currently 4 municipalities have been proclaimed, and it is planned to increase this to 15. The 4 current municipalities suffer from serious capacity problems, both in terms of human resources and infrastructure.

### Deepening the process of decentralisation

The proclaimed municipalities currently remain sub-structures of the woredas within which they fall, and do not have their own elected councils. Key functions such as health and education remain under the woreda. There is a critical need for basic infrastructures, but the provision of goods under PSCAP has not happened, and this is a high priority for these municipalities.

The main programme of UMCP seems to centre around the urban governance package, which has been adapted from the federal package. Training in the package has been done for leaders and top managers from the municipalities. The package includes community participation, infrastructure services, the use and administration of land, democracy at a local level, and the generation of own revenues. It is important that PSCAP support is now focused around the elements of the urban governance package.

### Local government restructuring and capacity building

The municipalities have prepared strategic plans, but not with PSCAP support. The municipalities participated in the preparation of the latest UMCP action plan, and their needs were incorporated into the plan. A total of Birr 7m was allocated to the 4 municipalities, of which Birr4m has been spent. From time to time the municipalities submit proposals to UMCP for specific assistance, but have received no feedback on these. They feel demotivated as a result.

Specific training that has been received by the municipalities includes performance management, change management, budgets and accounting, surveying and works management, and solid waste management. Experts have also given assistance to municipalities on land surveying and GIS.

Work has begun on tariff collection, with some short term training done and a draft policy document circulated for comment. A TOR has been prepared on urban financial guidelines, and a proposal submitted to federal level.

There have been some consequent changes in municipal service delivery, especially in terms of improved accessibility and accountability of municipal staff and politicians. The Mayor of Awash municipality indicated that his door is never closed to members of the local community. There has been a change of mindset regarding service delivery. However there remains a critical gap in basic equipment and infrastructure, including vehicles such as dump trucks, landfill sites, surveying equipment etc. There is also a critical gap in terms of financial capacity, including tariff structuring, and modern accounting methods. Any further improvements need these basic capacity needs to be met.

## DLDP

The DLDP programme has made reasonable progress in the light of the organisational challenges it faces. The DLDP programme falls under BCB, and is managed by 3 people (two of whom are seconded from the People Participation Bureau and BOFED). The coordinator has been on 2 years study leave, and has only been back for 6 months. The programme has no vehicle, one desktop computer, and no admin budget. Coordination with federal DLDP is poor – they do not visit the region, and do not provide any assistance. There are no coordination meetings with woredas, as the programme does not have the infrastructure for convening such meetings.

There are 29 established woredas in the region, and another 3 have recently been established. Woredas in the region face enormous capacity challenges, with lack of skilled staff, weak administrative and financial management systems, technology gap, and lack of logistics infrastructure.

Regarding the MMAs, the majority are completed:

- The programme has completed the decentralisation legal framework and functional assignments.

- The assessment of HR and training needs, and infrastructure needs, of woredas has been done, but the HR assessment is not yet published.

- The strategy document is underway – DLDP has a five year strategy and action plans that already outline a strategic approach.

- Manuals have been prepared for community participation.

- Technical assistance has been provided to woredas for decentralisation process.

- The prototype minimum service standards are not done – a technical person is required to assist with this task.

### Institutional & organisational arrangements

The legal framework for decentralisation has been completed. The programme has produced manuals and guidelines to assist woredas in implementing the legislation. The main task now is to complete the functional assignment – BOFED is assisting with this task. Cooperation with SNNP has been very useful in this regard. A draft guideline has been developed, and this will be revised this year.

### Manning and training

The HR needs assessment of woredas has been completed. 75 civil servants have been sent on distance education diploma courses, the majority of whom are women. Training has also taken place on planning and strategy development.

### Grassroots participation

Work on the grassroots approach to participation was initiated in 1998 with an exchange of experiences from different regions. As a consequence 4 manuals were prepared, dealing with community participation, integration between rural development policy and community participation, participatory rural appraisal, and the formation of kebele development committees. Training of community leaders has been done in zones 2 and 4, and this year the training will be extended to the other zones.

In the woredas visited, the view was that the mindset of staff towards service delivery has not yet been fundamentally changed. Commitment is currently at the level of political leaders and senior management. Requests have been made to establish a public complaints office, but this has not yet been actioned.

### Programme development

The decentralisation strategy document is being prepared, but has not yet been finalised. This is an important priority for the coming year. The woreda benchmarking tool is not being used by the region.

### Woreda fiscal transfer and own revenue enhancement

From the end of 1996 Afar has adopted the SNNP block grant system, using the criteria of population index, capacity to collect revenue, and the infrastructure development index. The actual transfers of block grants have been taking place for 2 years now. The system was revised in 1998, again drawing on experience from SNNP and Oromiya. The region now uses the “needs based expenditure grant formula”, which is based on the real expenditure needs of each woreda. The formula has been workshopped with all woredas and is generally accepted.

Woredas are also collecting their own revenue to supplement the block grant, and there has been a steady increase in these revenues over the last three years.

### Woreda planning and financial control

The training provided under this component has been exemplary, and has understandably produced the best results across the whole region. In each instance training was carefully targeted at the responsible officials, who were then supervised during implementation, with a strong “learning through doing” approach, and follow up technical support was provided. In conjunction with BOFED, visits were conducted to each woreda, and hands on training was done, first to prepare annual plans (1997), followed by budget reform (1997), then short term training on strategic planning (1998). Training manuals on participatory planning, monitoring and evaluation were prepared, and training given to 290 woreda experts. This year training will be given on annual budget planning.

As a consequence, each woreda has now prepared a 5 year strategic plan, followed by annual plans. Budget reform and zero balance account reform have been fully implemented. DLDP are understandably very happy with the results.

### Minimum service standards

The work on prototype minimum service standards has not been done, and the region is awaiting technical support in this area.

### Office infrastructure and development

Due to the delays in the PSCAP procurement process, this component has not been delivered. Most woredas have a standard set of buildings, built to the same design, for the woreda administration, WOFED and woreda court. In most of the woredas, Woredanet has been installed but is not functional. The communication functionalities of this investment are not being exploited. There is a critical lack of computers, and most systems are run on a manual basis.

## TSRP

The TSRP falls under BOFED and is generally making good progress. It has completed all MMAs. The region’s tax revenues are showing steady growth, from Birr 34m in 1997, Birr42m in 1998. to Birr 45m in 1999. An amount of Birr 51m is projected for 2000. The main complaint from the sub-programme is that they are under funded compared to the other regional sub-programmes, although the PPD has indicated that the allocation of Birr7m can be topped up from reallocations from other underperforming sub-programmes.

### Tax policy and legislation

Two types of revenue laws, dealing with income tax and turnover tax, have been issued. Legislation dealing with excise and stamp duty have been prepared and submitted to the legislature. Guidelines on the legislation have been prepared and distributed to implementing agencies. The remaining legislation requiring attention deals with the rules relating to revenue generation.

### Tax payer identification number

A total of 2 500 tax payers have been registered for TIN, out of an estimated total of 3000 potential tax payers.

### Presumptive taxation

Presumptive tax payers make up 95% of all tax payers in the region, and they are not expected to produce accounts. An annual turnover survey is completed each year.

### Value added tax

Previously the region simply registered the VAT payers and sent the information to the federal level for administration. Now the region processes all individual VAT payers, and retains the revenue. For companies the information is collected by the region and sent to the federal level, which collect the tax and hand over 30% of the taxes collected to the region.

### Operational programmes systems, procedures and manuals

Manuals have been prepared and distributed to implementing agencies. Distance education has been used to upgrade the qualifications of finance staff at the regional and woreda level (almost 50% of whom were women). Short term training has been done on customer service delivery, tax auditing, control of contraband, encoding and integrated tax administration.

### Organisation and tax payers education

Education was conducted for 300 tax payers at woreda level in 1998. Awareness regarding the new tax system has been promoted through the use of radio broadcasts and seminars.

## CSRP

The CSRP has completed 75% of its MMAs, and will complete the remainder this year. Thereafter it plans to align its activities with the regional strategic plan. The CSRP has not yet touched the woreda level. In general the CSRP programme seems to be well organised, and the Bureau highly motivated around its delivery. Its main achievements to date are:

### Strengthening the capacity of CSR Coordinating Structures

The regional CSRP office has been established, with two working teams – service delivery and HRM improvement team, and ethics and expenditure management team. The team has been establishing CSRP coordinating structures at regional and woreda level, with 50% of regional bureaux and 20% of local structures having functioning CSRP coordination offices.

### Improving governance of human resources management and control

The governance of human resource management has been addressed through a Civil Service Proclamation, policy and regulations, which have been implemented in all institutions, along with an awareness creation workshop and training for 40% of core civil servants. Human resource managers are in general aware of the new approach and making changes, but HR systems are still paper based. An incentive package for civil servants has been proposed, and will be implemented in the next year.

### Improving performance and public service delivery

A service delivery policy and complaint handling manual have been drafted, and guidelines have been implemented in 8 model bureaux. Training and workshops on service delivery have been held for over 300 service providers. Top managers and experts have been trained in the Public Service Improvement Programme and Business Process Reengineering. BPR is being introduced in the 8 model bureaux first before being rolled out to the rest of the civil service.

### Improving accountability and transparency

A code of ethics has been drafted and workshopped with 185 political leaders, judges and civil servants. It is estimated that 50% of these target groups have been trained in accountability and transparency. There appears to be a widespread understanding of the importance of this for government, but this has not yet been translated into concrete interventions such as information and help desks etc.

### Strengthening top management systems

CSRP has worked on strengthening top management at regional and local level, with training of 80% and 60% of personnel, respectively, in leadership development, performance management and change management. Interviews with beneficiaries indicate that there has been some improvement in top management, especially in terms of the new focus on service delivery and accountability.

## EMCP

The EMCP programme has until now been managed under the CSRP, and the transfer to BOFED has only taken place this year. BOFED sees this programme as relating to its core activities, which are expenditure management, budget reform and internal audit. The programme has made quite substantial achievements using channel 3 resources from USAID, DFID and Irish Aid. The MMAs are largely complete. Backlog accounts have been cleared for 1997 and 1998, and the region is only left with 1999. A single treasury function has been created at regional and woreda level. The budget reform is completed and the accounting reform will take place this year. The main achievements in relation to each component are:

### Enabling environment

The legal framework for accounting and expenditure management has been passed into law, and guidelines for implementation have been prepared. A draft procurement law has been prepared and submitted to the legislature.

### Capacity for expenditure management and control

90% of finance experts and 100% of audit bureau staff have been trained in the new budget manual, accounting reform and auditing.

The budget reform process has been done over the last two years.

The reform of accounting systems will take place this year.

### Financial information

BIS and IBEX have been installed at the regional level, but not yet at woreda level.

### Audit functions

Internal audit has been previously very weak or non-existent in the region and woredas. It has now been established as a department for each regional Bureau and as a desk for each woreda. A manual on internal audit has been prepared. BOFED has an inspection office which complements these structures.

## ICT

The ICT component consists of 6 staff, including a secondment from UNDP. It has made little progress due to the delays in procurement, and the lack of IT facilities in beneficiaries. This is a major obstacle, as training in the absence of IT equipment in the beneficiaries is wasted. The region is also coming from a very low base, with no familiarity with the concept of IT until 2 years ago.

### Human resource development

Awareness has been created regarding ICT and woredanet amongst regional and woreda civil servants – 130 people, half of them women, participated. The region plans to repeat the awareness session as they feel they had an inadequate response from the first session. This was followed by a study tour for 9 experts to neighbouring regions.  A study has been initiated into the ICT human resource requirements and training needs for the region and woredas. The region is also in the process of producing 10 000 training manuals and software in the Afarigna language.

The main problem faced by the region is a lack of a regional ICT training centre. The available private centres have a maximum capacity of 8 persons. A centre with 25 terminals used in two shifts can take 50 trainees per day, which will be adequate for initial needs.

### Public service delivery and good governance

The regional data centre is operational, and has been doing training on the woredanet and schoolnet teleconference facilities. The region has started work on the first website for BCB, which is 70% complete. This will be subsequently extended to other regional Bureaux. No work has been done on an information portal. The information systems for woredas and municipalities are not computerised, the LAN and WAN have not yet been developed.

### Applications for sector development

No progress has been made with this component.

### Community based information systems and services

No progress has been made with this component.

# Programme management and support

## Institutional arrangements for PSCAP in region

PSCAP coordinating bodies are now in place for each sub-programme, and for the region as a whole. The region has on the whole embraced the programme and attempted to set up the structures and systems to deliver on its objectives.

The overall coordination of the programme in the region is managed by BCB. BCB appears to be seriously under-capacitated in relation to its coordination function. The PPD, located within BCB, consists of four staff, including the PPD coordinator, the DLDP coordinator, an M&E expert and a procurement expert. The procurement experts are volunteers, and only available part time. BCB directly manages the DLDP and ICT programmes. There is no vehicle for the PPD, despite their obvious need to travel widely across the region. The PPD indicated that they need an additional planning expert and a procurement expert. They also need additional training and support in programme coordination and management.

The PPD has established a project management system that tracks each activity, budget request, budget allocation and expenditure.

The majority of the Bureaux have not yet taken full ownership of the sub-programmes. BCB has convened two workshops with Bureaux and beneficiaries to initiate the PSCAP planning process, but BCB is of the opinion that the Bureau heads did not carry the process through sufficiently. The following table gives an overview of the responsible agencies for each sub-programme, and a rough estimate of the degree of management buy-in and political leadership provided for each sub-programme (programmes were rated from 1 to 6, with 1 being the lowest level of buy-in or leadership).

Table 1.Management buy-in and leadership effectiveness

|  | Responsible agency | Management buy-in | Leadership effectiveness |
| --- | --- | --- | --- |
| DLDP | BCB | 6 | 4 |
| ICT | BCB | 4 | 4 |
| JSRP | Justice Bureau | 4 | 6 |
| CSRP | CSRPO | 5 | 3 |
| EMCP | BOFED | 4 | 4 |
| TSRP | BOFED | 5 | 5 |
| UMCP | Works and Urban Development | 1 | 2 |
| PPD (programme support) | BCB | 4 | 4 |
| BOFED (programme support) | BOFED | 3 | 2 |

There is serious problem regarding coordination between BOFED and BCB, and neither institution seems properly capacitated to undertake their roles. The bigger picture of speeding up service delivery has become lost in interagency rivalry.

## Coordination with MCB, federal sub-programmes, and woredas

According to BCB, coordination with MCB only takes place when the region is called to meetings in Addis Abeba. MCB does not visit the region. There is a similar situation regarding each sub-programme, with most sub-programme coordinators indicating that there is generally poor coordination and support given to sub-programmes from the federal level. The exception was CSRP, which indicated a good level of cooperation and support from federal level.

The regional technical team has been established on paper, but it appears to meet only on an ad hoc basis. The FTT is not playing a significant coordinating role, and the integration and sequencing of sub-programme activities is not taking place. There is also no coordination mechanism for woredas, neither for PSCAP in the region as a whole, nor for key sub-programmes such as DLDP.

## Compliance with eligibility criteria by region

The region has complied with eligibility criteria, and there is a detailed PPA negotiated each year for the region which sets out programme activities, deliverables and budget allocations per sub-programme.

## Planning and resource allocation

There have been delays in the planning process, and the region’s action plans were submitted late to MCB for approval in 1998 and 1999. The 2000 action plan was however submitted on time. The delays are partly due to lack of ownership of the programme by Bureaux. Coordinators are overwhelmed by their regular tasks in the civil service, and, because they are not evaluated against PSCSAP outputs, these are often accorded second place in terms of priorities.

One of the main problems in the planning process is that the action plans are based on indicative budget figures that bear no relation to the final budgets allocated by BOFED. Different interpretations were given to this by the PPD and BOFED, and at the time of writing it is not clear whether sub-programmes are planning expenditures that are way beyond the indicative medium term allocations for PSCAP, or whether the problem is a mismatch between indicative and final budget allocations.

As a consequence of the mismatch between plans and allocations, each sub-programme has to redo its action plan based on the final budget allocations, effectively duplicating the planning process. The final release of the budget is also late – for instance the budget for 2000 has not yet been released for the region.

In general the action planning process is considered tedious, and dominated by “red pen” and amendments.

Reallocations between performing and underperforming sub-programmes were done for the first time in 1999, with significant cuts made to ICT and UMCP, and to a lesser extent CSRP. DLDP was the major beneficiary of the reallocations.

## Procurement

Delays in procurement are a major issue affecting every programme in the region, and this threatens to undermine the credibility of the programme. The primary responsibility for procurement rests with BCB. No goods have been procured except under ICB. The BCB indicated that the goods procured under ICB were of an inferior quality and higher price than they would have been able to obtain locally. The region is in the process of procuring local goods.

There is a general lack of capacity and knowledge regarding procurement procedures. Sector Bureaux do not have proper skills to prepare TORs. BCB is slow in advertising and processing the bids. BOFED is also having problems in processing payment for tenders that have been awarded. The bidding committee has been established, and has received some training, and procurement experts have been hired to speed up processes. The main problem seems to be poor communication between BCB and BOFED regarding procurement procedures. It appears that the PSCAP procurement requirements do not match those used by the region, and that PSCAP compliant procurement has been held up by BOFED for not complying with the regions own criteria. For example a large consignment of goods has been sitting in the BCB offices for 4 months with BOFED refusing to release funds due to the goods value exceeding the regional cut-off requirement. In addition to the confusion, no serious effort is being made to resolve the problem, and BOFED is taking a risk averse rules based approach. BOFED also alleges that BCB does not inform them when processing bids, and does not provide proper proof of procedures followed in the bidding process.

## Expenditure and financial management

To date a total of Birr 20 963 089 has been transferred from MOFED, of which R11 978 312 has been spent, leaving a closing balance of Birr 8 984 777. The budget allocations and expenditure over the last three years are as follows:

Table 2. Budget allocations and expenditure 1997 to 1999

|  | 1997 | 1998 | 1999 |
| --- | --- | --- | --- |
| Budget allotment | ? | Birr 12 703 123 | Birr 9 705 170 |
| Adjusted Budget | ? | Birr 12 703 123 | Birr 9 705 170 |
| Actual expenditure | Birr 670 027 | Birr 5 002 433 | Birr 6 305 852 |
| Variance | ? | Birr 7 700 691 | Birr 3 399 318 |

The most significant underspending has been from UMCP (16% of budget spent), ICT (42%), PPD (47%), and TSRP (64%), although in actual amounts DLDP is the largest with Birr1,032,890 unspent (71%).

Two audits have been done on PSCAP by the Auditor General, but the region has not received feedback on either of these. There are functioning internal audit offices in all Bureaux, which keep track of PSCAP expenditure and procedures.

## Monitoring and evaluation

The monitoring of programme activities and targets is being coordinated by the PPD, and in general seems to be working well. The PPD monitoring and evaluation expert only started work 9 months ago. She visits each sub-programme, compares activities to plan, consolidates the information, and reports to the PPD on performance against targets. Training was received from CIDA in conjunction with MCB.

The region has not yet conducted an evaluation of outcomes. This has been included in the action plan for 2000. The open culture of the region assists in the work, and there is the ability to honestly share information about the strengths and weaknesses of sub-programmes. However sub-programmes tend to see the M&E expert as an inspector rather than an important source of feedback. It was indicated that management and leadership need to be more supportive of the M&E process.

## Information, education and communication

Information sharing has to date consisted of workshops and awareness-raising in regional workshops. There seems to be no overall IEC strategy. However the “dagu” cultural system of sharing information in the region plays a strong role. Operating through the clan leaders, this system allows for rapid dissemination of information. More systematic use of this system will be important for taking PSCAP further in the region.

## Sequencing and integration of reform initiatives

Generally the sequencing of activities does not appear to be a problem. The CSRP for instance has a clear sequence of introducing strategic planning and management, followed by business process reengineering, then performance management system.  Woredas receive training in strategic planning, followed by expenditure management and accounting reform.

# Cross-cutting issues

In general the cross cutting issues of HIV/AIDS and gender have been taken up by all programmes, largely driven by the established of offices or bureaux for these at regional and local level. The woredas have appointed gender officers, but they are often in a junior position in the administration and have extremely limited resources. Afar region has a deeply ingrained culture that views education of women to be undesirable. The practice of female circumcision is still widespread. The region has focused initially on awareness creation of gender issues. Training programmes include approximately 30% of women. The appointment of women to senior management positions is hampered by the lack of educational qualifications amongst women. At a political level there is also progress, with 8 women in parliament (compared to one previously), the deputy speakers of most woredas are women, and women are taking up portfolios other than the traditional women’s affairs portfolios.

One of the problems stemming from budget cuts to programmes is that the HIV/AIDS and gender components are often dropped.

There is no attention being given to environmental issues in PSCAP programmes.

# Assessment of programme outcomes

Impact of the above sub-programmes on programme outcomes is difficult to assess due to the lack of statistics and data collected regarding the high level indicators. The following assessment is therefore based on anecdotal information, and impressions gained from discussions with programme beneficiaries.

## Enhanced predictability of financial resource flows in-year and across years

According to BOFED predictability of regional and woreda revenues has significantly improved. Rolling three year estimates of block grant allocations are received from federal government, and once received the block grant is passed on to woredas. This predictability does not extend to PSCAP funding, in which annual budget allocations bear little relation to indicative medium term budget allocations.

BOFED indicates that there has been a significant improvement in budget variance for Bureaux, although figures were not available to back this up.

## Greater inclusiveness and transparency of planning and prioritisation processes

A bottom up process of planning and budgeting has at least on paper been established for the region, and seems to be in practice in the more capacitated woredas. The structures for public participation have been created in woredas, but key facilities such as complaints offices and information centres have not yet been established.

## Improved quality and efficiency of government operations in priority sectors

Some examples of improvement in services, such as speedier processing of court cases, were obtained, but no statistical information on improvement in services was available. Given the previous absence of regional government, any service provision should count as an improvement.

There has been a behavioural change in the top management of the civil service, with a growing trend towards modern management practices.

## Improved incentive environment for public servants (gender disaggregated)

The region suffers from a serious shortage in skilled manpower. It has difficulty in recruiting skilled personnel to work, in particular at woreda level. There is a high staff turnover. Recently the regional government has endorsed an incentive package to retain civil servants, including increasing salary grades, paying a hardship allowance and building houses for civil servants. This has not yet been implemented. The civil service is severely constrained in terms of infrastructure, including offices, computers, communication facilities, transport.

## Enhanced revenue performance and fiscal autonomy

The region’s tax revenues make up approximately 10% of the overall budget. They are showing steady growth, from Birr 34m in 1997, Birr42m in 1998. to Birr 45m in 1999. An amount of Birr 51m is projected for 2000.

The block grant to the region is over Birr 500m, and has shown some growth over the last few years, but not significantly. Federal government has indicated that the block grant will slowly decrease over the next few years. The region is consequently looking at maximising savings and efficiencies.

## Improved transparency and accountability

Transparency and accountability have been boosted through the participatory planning and budgeting processes for the region and woredas. The devolution of power to woredas and kebeles has assisted in building a bottom up system of accountability. However these structures are still at an early stage of establishment, and are severely limited in effectiveness through infrastructure, technology and skills gaps.

# Key issues and challenges

The sub-programmes in the region all suffer from a common set of challenges that impact on the implementation of the programme as a whole. These include:

- Institutions are generally at an early stage of formation and development, and the capacity, systems and procedures for managing a complex programme are still being developed.

- A general lack of skills in the fields of strategic planning, project management, procurement management, ICT, and output evaluation.

- High staff turnover and the inability to attract or retain competent staff.

- Lack of basic infrastructure such as vehicles, IT especially computers and connectivity, offices and telecommunications facilities.

- Serious delays in the procurement of goods and consultants.

- Problems with coordination with the federal level, with other regional sub-programmes and with woredas.

Given that training has constituted the bulk of PSCAP activities to date, it is important to note a few deficiencies regarding the training programme. Training to date has focused on bulk training exercises for managers and staff, which is seeking to communicated a set of generic skills identified at the inception of PSCAP. There appears to be no prior training needs assessment conducted in target institutions. This may not be a problem in the early stages of PSCAP, but in the subsequent phases a more nuanced and targeted approach seems to be needed. There have been a number of instances in which training participants were poorly selected, and the trainees were not in fact the people responsible for implementing the learned activities. In general feedback from participants on the content of the training provided is that it was appropriate. However there was no follow up of the training exercise. Participants were left to implement the lessons they had learnt without any assistance or mentoring. There was also no assessment of the effectiveness of the training. For a programme of the scale of PSCAP this is a major deficiency, as without a feedback loop there is no way of learning and improving on the training provided.

# Lessons learnt and recommendations

The Afar region has established the basic infrastructure and control mechanisms to manage the programme effectively. The long lines of communication, and delays in approvals of plans and letters of no objection, mean that federal and donor oversight of the regional programme act to slow down programme implementation, undermine local initiative, and ultimately undermine the overall intent of decentralisation. Given the problems encountered with coordination between regional and federal level, as far as possible the decision making with regard to the programme, including planning, procurement and expenditure, should be decentralised to the region.

The main recommendations arising out of the evaluation are summarised below.

- There is an urgent need to strengthen the PPD, both in terms of staff and basic infrastructure such as a vehicle. If the PPD retains the procurement function, a procurement specialist needs to be urgently assigned to assist the team, and a major overhaul of procurement procedures undertaken.

- The Regional Technical Team needs to meet on a regular (at least quarterly) basis, and develop a strategic ability to look at the big picture regarding the overall reform programme, and the coordination of various capacity building initiatives.

- Bureau heads need to take full ownership of their respective programmes, and be held accountable for performance on these programmes. Sub-programme coordinators in each Bureau should be assigned full time responsibility for coordinating sub-programmes, and should not be loaded with other responsibilities.

- Urgent steps must be taken to retain the core management staff involved in coordinating sub-programmes and programme support. In the absence of a broader incentive framework for public servants, specific measures for PSCAP management should be instituted as an interim measure.

- The preparation of annual action plans by sub-programmes should be done within clear indicative budget allocations set at the start of the planning process, that are closely related to final budget allocations.

- The crisis regarding delays in the procurement process needs urgent attention. A number of steps are required, including decentralising ICB procurement to the region, recruiting a procurement specialist for the region, establishing fast track procurement procedures for consultants and goods, including developing a list of pre-approved consultants and firms that the region can chose from, allowing budget roll-overs at least as a transitional measure, and improving BCB and BOFED coordination.

- The provision of ICT goods and training is a critical intervention that will enable the region and woredas to move onto a modern public service footing. A regional training centre needs to be established, procurement of IT infrastructure fast tracked, and woredanet made operational and capable of full connectivity functions.

- Training in the region needs to move beyond the mass training approach used to date, with a focus on learning through doing and in-service training and mentoring. Proper needs assessments should be done and participants selected more carefully to ensure better targeting of efforts. Post training evaluation should be done to improve training effectiveness.

- The monitoring and evaluation system must focus on evaluating sub-programme and programme level outputs and outcomes, and provide timely feedback to role-players.

- Cross-cutting issues must be protected from budget cuts, and all sub-programmes need to consider how the environment can be addressed.

- The IEC component of the programme needs to be implemented, with use made of the dagu system in the region for rapid spread of information.