ATE TABLES

Table: Status of objective / outcome delivery as per measurable indicators

| OBJECTIVE | MEASURABLE INDICATORS FROM PROJECT LOGFRAME | END-OF-PROJECT TARGET | STATUS OF DELIVERY* | RATING** |
| --- | --- | --- | --- | --- |
| Objective: To enhance coverage and management effectiveness of the Forest Protected Areas (FPAs) through demonstrating cost-effective approaches for effective conservation and sustainable resource management at Küre Mountains National Park and taking initial steps towards the replication of this model at the remaining eight forest hot spots | Surface of globally significant habitats (grasslands, old growth forests) under conservation management (either legal protection or under sustainable forest management) | 600,000 ha | ongoing | S |
|  | Proportion of 9 forest hot spots under legal protection | 100% | red | U |
|  | Forest management performance at the 9 forest hot spots, as measured with METT | Performance score increased by 15% | ongoing | MS |
|  | Number of local women producing traditional products and their total income | Income rate: increase by 10% in 3 years. No. of participating women: increase by 5% in 3 years | ongoing | S |
|  | The overall performance of the national PA system (specially forest PA) using WWF’s Rapid Assessment and Prioritization of PA Management Methodology (RAPPAM) which is based on the WCPA framework | Performance score increased by 10% at the end of the project | ongoing | S |
| OUTCOMES | MEASURABLE INDICATORS FROM PROJECT LOGFRAME | END-OF-PROJECT TARGET | STATUS OF DELIVERY | RATING |
| Outcome 1: Cost-effective conservation management approaches for forest protected areas are implemented at Küre Mountains National Park (KMNP) | - Use of business methods at Küre MNP level and existence of a PA performance monitoring system | Business planning is an integral part of PA management, supported by an M&E system at the park level | ongoing | S |
|  | Available funds are in line with management requirements | Management costs are being covered through national funding sources in line with a financial plan | ongoing | S |
| Outcome 2: Sustainable natural resource management is demonstrated in the buffer area of Küre Mountain National Park | Use of sustainable forest management approaches in the buffer area of KMNP is institutionalized by the Department of Forestry as a tool for sustainable natural resource management to be used in all forest PAs | Business planning is an integral part of PA management, supported by an M&E system at the park level | ongoing | S |
|  | Extent and percentage of forest area under comprehensive sustainable forest management plan | Management costs are being covered through national funding sources in line with a financial plan | ongoing | S |
|  | Female participation percentage in training programmes related to productive and conservation activities | Sustainable forest management guidelines developed and implemented at KMNP and institutionalized by the Department of Forestry as a tool for sustainable natural resource management to be used in all forest PAs | ongoing | S |
|  | Area of degraded forest land | 40% of forest area is under SFM | ongoing | S |
|  | Local population percentage generating income from alternative livelihoods | At least 20% females at the end of project | ongoing | S |
|  | Local population percentage meeting fuel needs from renewable energy resources | 5% decline in degraded forest areas | ongoing | S |
| Outcome 3: Lessons learned from demonstration work at KMNP are disseminated to the other forest hot spots in Turkey, contributing to the maturation of the national protected area system | Capacity increase rate for the staff working in the nine forest sites | The capacity is increased by 60% | ongoing | S |
|  | Instances of “methodology replication” at other sites | By project end, 3 recorded instances of ‘methodology replication’ at GttE sites or elsewhere (supported through leveraged co-financing) | ongoing | S |

###### * Status of delivery colouring codes:

Green / completed – indicator shows successful achievement

Yellow – indicator shows expected completion by the end of the project

Red – Indicator show poor achievement - unlikely to be complete by end of Project

** Ratings code as are detailed in Annex 2.