Mid Term Evaluation: Inception Report and Methodology

Enhancing Coverage and Management Effectiveness of the Subsystem of Forest Protected Areas in Turkey’s National System of Protected Areas

PIMS Number: 1988

# Mid Term Evaluation

The Mid-term Evaluation (MTE) is initiated and commissioned by UNDP Turkey country office as the Implementing Agency for this project. The objectives of the MTE is to evaluate the progress towards the attainment of global environmental objectives, project objectives and outcomes, capture lessons learned and suggest recommendations on major improvements and if found necessary, on changes in the project. The Mid-term Evaluation serves as an agent of change and plays a critical role in supporting accountability.  To this end, the MTE will serve to:

- Strengthen the adaptive management and monitoring functions of the project;

- Enhance the likelihood of achievement of the project and GEF objectives through analyzing project strengths and weaknesses and suggesting measures for improvement;

- Enhance organizational and development learning;

- Enable informed decision-making;

- Create the basis of replication of successful project outcomes achieved so far.

Particular emphasis will be put on the current project results and the possibility of achieving all the objectives in the given timeframe, taking into consideration the speed, at which the project is proceeding. More specifically, the evaluation should assess:

- The project concept and design.

- Implementation.

- Project Outcomes, Outputs and Impacts

Evaluation is an integral part of the UNDP-GEF project cycle management. The MTE is guided by the MTE Terms of Reference and UNDP-GEF Project Monitoring and Evaluation Policies and Procedures. The evaluation process is independent of both UNDP and GEF and the opinions and recommendations in this report and the subsequent Final Report are those of the Consultants and do not necessarily reflect the position of the GEF, UNDP, the Ministry of Environment and Forestry (the Executing Agency) or WWF Turkey, however, once accepted the MTE becomes a recognised component of the project’s documentation. In the case of unresolved difference of opinions between any of the parties, UNDP may request the evaluation team to set out the differences in an annex to the final report.

# Inception Phase and Methodology

The inception period can be considered a point in the process of evaluation to consolidate the evaluation team and define the current and near-future status of the evaluation. This inception report therefore represents the MTE’s understanding of the project prior to the field visit. Following the Inception Report the MTE will:

- Continue to examine documentation, reports and other materials developed during the project

- Carry out interviews with stakeholders

- Carry out field visits

- Present the interim findings of the MTE to key project stakeholders

- Produce an Aide Memoire of the key findings prior to producing the draft MTE Report

- Produce a draft MTE Report for circulation to project stakeholders

- Incorporate relevant comments and correct any factual inaccuracies

- Produce a Final MTE Report for submission including annexes and verified Tracking Tool.

# Proposed Methodology

The Mid Term Evaluation (MTE) will follow the methodology outlined in the ToR (Annex 1 and 2). This will include focused interviews and round table meetings with key stakeholders, examination of the projects documentation and analysis of the projects progress and effectiveness in achieving the objective set out in the Project Document and log frame matrix (LFM). In particular the MTE will consider:

### Project Cycle Management

The evaluation will consider the project’s development from the PDF stage and follow this through to the present. The objective of this would be to examine how the project was designed and subsequently developed, and if and when critical changes were made. As projects don’t occur in a vacuum, the project development, decisions and assumptions should be considered against the prevailing situation, at the time they were taken, in order to understand the context of why such decisions were made.

### Log Frame Matrix and Overall Strategy

Particular attention will be placed upon the project’s log frame matrix to examine the rationale behind the project’s design and consider how the strategy – the various outcomes – contributed to the project’s strategy for achieving the objective and overall GEF goal.

The MTE will examine the indicators developed in the Project Document LFM to see if these are the best measures of the progress of work and the effectiveness and impact of the various activities in achieving the objective.

If necessary the MTE will develop new or additional indicators in order to measure the effectiveness of the various interventions.

### Adaptive Management Framework

The MTE will examine the overall project strategy, objective, outcomes and activities and consider whether and the original strategy represented the best scenario at that time and to examine the project’s adaptive management framework, that is, how the project has responded to new information, changes in variables, etc.

The MTE will examine the risks and assumptions that the project had based its strategy upon and assess their validity and the way in which the project, as a whole has responded and managed these risks.

### Project Performance

The MTE will review the project’s performance to date. This will consider what the impacts of the project are and how it is contributing to the GEF objectives. Therefore the MTE will be:

- Assessing the effectiveness of the individual activities (monitoring performance);

- Assessing the effectiveness of the various activities in achieving the Outcome (monitoring the impact), and;

- Assessing the effectiveness of the various Outcomes on achieving the Objective (monitoring the change).

The analysis of this will allow the MTE to comment on the:

- Implementation – is the project doing what it planned to do (i.e. is the plan still untested because the implementation is poor);

- Effectiveness – is the plan meeting the predicted objectives (i.e. has the plan been tested and found to have flaws), and;

- Validation of the model’s parameters and relationships (i.e. which assumptions, variables and interactions were correct).

### Specific Issues

Prior to commencing the field visits the MTE has identified a number of issues. These are listed here, however, their significance to the MTE may change in light of the field visit and the MTE will not limit itself to these issues if necessary. These issues are, inter alia:

- Were the risks and assumption correctly identified during the critical point of the project cycle (project development, inception phase, etc.)? Have new or different risks been identified during the project.

- Do the indicators set out in the LFM reflect a good measure of performance and effectiveness?

- Has the project had a significant impact upon the conservation management of the protected areas?

- What has been the impact on the project where risks have been realised and assumptions found to be incorrect?

- What has been the impact of the socio-economic interventions?

- Has the project had significant impact upon the enabling environment in terms of influencing policies and events both inside and outside of the immediate project area?

- Given the large number of rural villages (60 within the KMNP Buffer Zone) and the high dependence upon forest resources (70%) of local communities are the alternative livelihood strategies sufficient to absorb the opportunity costs?

- Given that modern protected areas management is as much about governance as it is about science and regulation/enforcement, is the local community of resource users sufficiently involved in the decision-making process of both the project and the future management of the national park and buffer zone or does more need to be done to develop collaborative systems of resource management?

- How is the experience gained from the project being internalised and mainstreamed through policy development?

- How effective are the institutional coordination arrangements established by the project?

- What are the risks of relying too heavily on alternative livelihoods and particularly eco-tourism as a means to offset local community opportunity costs resulting from conservation management?

- What are the implications for replication in the other project “hotspots” given the diversity of issues and the importance of building capacity of stakeholders to effectively manage resources (i.e. how valid is a “model” for sustainable conservation management versus a process?

- What should the UNDP-GEF, Ministry of Environment and forestry and WWF Turkey’s future response be to ensure that the benefits of the project are internalised and made sustainable after the end of the GEF funding?

### Overall Approach to the Mid Term Evaluation

The MTE has a number of audiences and needs to provide a basic evaluation service for these different players (GEF, UNDP, Ministry of Environment and Forestry, Provincial Governorates, WWF Turkey, Forest Villages, etc.). The MTE provides an opportunity for external evaluators to ask the difficult questions of the project’s stakeholders and challenge the decisions, activities and assumptions of those involved in the project. However, very little is achieved by adopting a combative approach to project evaluation. Rather, the MTE should work alongside the project management team, WWF, UNDP Country Office and other partners to look critically at the projects progress against the stated objective, outputs and indicators contained in the log frame matrix and identify the strengths and any weaknesses that may exist and map out any future interventions.

Therefore, the evaluation will provide feedback at all points of the evaluation; explain the findings of the evaluation to the project team prior to the presentation; provide a final feedback power point presentation and submit an aide memoire before the Team Leader leaves Turkey.

# Agenda and Issues to be discussed with Project Stakeholders

In order to map out the agenda for the MTE a preliminary list of issues that will be discussed with the stakeholders has been added to the Inception Report. The MTE notes that the evaluation process is an iterative process and with a multi-stakeholder project (particularly when local communities are involved) the same question can have a multiplicity of answers and the task of the evaluation team is to decipher the answers, analyse the results and draw conclusions based upon the evidence or reasoned arguments. The MTE, according to the ToR need not limit their inquiries to these areas; however, the following provides a broad outline for the topics to be covered.

UNDP CO and PMU– project design, inception, strategy, relevance of project, selection of indicators for the project’s impact on protected areas management, implementation, project management arrangements, National Execution modality, project log frame, adaptive management framework, fit to national environment and UNDP-GEF objectives, project performance, effectiveness of interventions, sustainability and way forward and project exit strategy. Budget execution and co-financing. METT.

WWF - project design, inception, strategy, relevance of project, selection of indicators for the project’s impact on protected areas management, implementation, project management arrangements, project log frame, adaptive management framework, project performance, effectiveness of interventions, sustainability and way forward.

Ministry of Environment and Forestry- (GDNCNP, GDF, Orkoy, GDA, etc.) - fit to national environment and GoT objectives national and local environmental objectives and policies, relationship with project, UNDP-GEF and WWF, institutional participation, project strategy, community development, cost and benefit relationships, sustainability and way forwards.

Steering Committee - project strategy, relevance of project, implementation, project management arrangements, National Execution modality, adaptive management framework, fit to national objectives, project performance, effectiveness of interventions, sustainability and way forward.

Provincial government and local community representatives – local development plans and goals, local development aspirations, cost and benefit relationships, tenure and access to forest resources, sustainability and way forwards, national forest park concept.

The MTE also provides an opportunity to for feedback from stakeholders outside of the normal project channels and therefore all stakeholders will be given an equal opportunity to discuss issues other than the above with the MTE Team.

# Preliminary agenda for MTE

| Date | Morning | Afternoon | Comments |
| --- | --- | --- | --- |
| 30/10/10 | TL travel to Ankara | Study documentation |  |
| 31/10/10 | TL meeting NC | TL & NC planning & strategy meeting |  |
| 01/11/10 | MTE meetings with PMU, MFE | Meeting with UNDP.....& arrangements for field trip Field trip |  |
| 02/11/10 | MTE Meet with GDF | MTE Meet with GDA, Orkoy. Travel to Kastamonu and Bartin |  |
| 03/11/10 | Field | Field |  |
| 04/11/10 | Field | Field |  |
| 05/11/10 | Field | Field |  |
| 06/11/10 | Field | Travel to Ankara |  |
| 07/11/10 | Analysis & feedback presentation preparation | MTE feedback presentation preparation |  |
| 08/11/10 | MTE feedback presentation preparation | Feedback Presentation and finalise Aide Memoire |  |
| 09/11/10 | TL return to home base |  |  |
| Date to decided |  | First Draft MTE Report |  |
| 26/11/10 |  | Final MTE Report due |  |

Interpretation during Feedback Workshop

Due to language difficulties and the importance of expressing various concepts and technical terms clearly so that they are understood by all participants the MTE requests that there an interpreter is made available during the Feedback Workshop. This is important because the National Consultant will be participating in the workshop as a technical expert and evaluator and the additional task of interpretation will be a distraction.

The following ratings will be applied by the MTE.

| General ratings: - Highly Satisfactory (HS): no shortcomings - Satisfactory (S): minor - Moderately Satisfactory (MS):moderate - Moderately Unsatisfactory (MU): significant - Unsatisfactory (U): major - Highly Unsatisfactory (HU): severe - Not applicable (N/A) - Unable to assess (U/A) | Project sustainability ratings: - Likely (L): negligible risks to sustainability - Moderately Likely (ML) : moderate risks - Moderately Unlikely (MU): significant risks - Unlikely (U): severe risks - Highly Unlikely (HU) - Not Applicable (N/A) - Unable to Assess (U/A) |
| --- | --- |

The MTE Team

Francis Hurst (Team Leader) has a BSc. in Zoology and a MSc. in Conservation. He has worked in biodiversity conservation, protected areas management and natural resource management for over 20 years with practical experience of managing protected areas. For the past 15 years he has worked as an independent consultant in more than 20 countries including UNDP-GEF and EU midterm and final evaluations in Uzbekistan, Georgia, Egypt, Russia, Jordan, Kazakhstan and Botswana. Of particular relevance was a recent assignment as the Forest Conservation Management technical expert on the EU-funded Yildiz Mountains Biosphere Project in northwest Turkey and experience in collaborative management systems, adaptive management approaches.

Koray Abaci (National Consultant) has a BSc. in International Relations. He has worked in public consultation, environmental permitting issues in international projects for last 10 years. Till 2007 he has worked as a Monitoring and Evaluation Expert in EU and MDG funded Projects during this period he prepared and assist on Grant Monitoring and Implementation Guidelines and lessons learned booklet. His recent assignments were in different parts of Turkey such as Adana, Kayseri, Nigde, Erzurum and Izmir.

http://thegef.org/MonitoringandEvaluation/MEPoliciesProcedures/mepoliciesprocedures.html

Terms of Reference, Mid Term Evaluation – Enhancing Coverage and Management Effectiveness of the Subsystem of Forest Protected Areas in Turkey’s National System of Protected Areas.

METT

Given the time constraints it is not advisable to try and produce any form of questionnaire

The MTE notes that it will not be able to produce a full LFM for the project but can reorganise and rationalise Objectives, Outcomes, Indicators and Targets (Outputs) if necessary. But if the project needs drastic revisions to the LFM this is requires the input of all the project stakeholders and further period of consultation.

The ratings are supposed to be included in each of the MTEs, based from GEF guidance.  Shortcomings relate to achievement of objectives in terms of relevance, effectiveness or efficiency, as well as the quality of M&E systems. This same scale should be used to rate shortcomings in the terminal evaluation report.