### TERMS OF REFERENCES FOR CONSULTANCY SERVICES

### FOR MID-TERM EVALUATION OF UNDP-GEF PROJECT

### ENHANCING COVERAGE AND MANAGEMENT EFFECTIVENESS OF THE SUBSYSTEM OF FOREST PROTECTED AREAS IN TURKEY’S NATIONAL SYSTEM OF PROTECTED AREAS

Project Title:	PIMS 1988: Enhancing Coverage and Management Effectiveness of the Subsystem of Forest Protected Areas in Turkey’s National System of Protected Areas Project

Vacancy Type: 	One (1) External Vacancy

Location: 	Turkey (Ankara and visit to Kastamonu and Bartın

Provinces)

Category: 	Environment and Sustainable Development (ESD)

Type of contract: 	SSA (Special Service Agreement)

Reporting Language: 	English

Application Deadline:	01 September 2010

Starting Date: 	15 September 2010

Expected duration of Assignment: 20 man/days throughout the contract validity (non-consecutive)

- Duration of Contract:	15 September – 30 October 2010

Reference Code:	PIMS 1988 – MTE_LOCAL

# INTRODUCTION

This Mid Term Evaluation (MTE) is initiated by the UNDP Turkey as the Implementation Agency for this project and it aims to provide managers (at the Project Implementation Unit, UNDP Turkey Country Office and UNDP-GEF levels) with strategy and policy options for more effectively and efficiently achieving the project’s expected results and for replicating the results. It also provides the basis for learning and accountability for managers and stakeholders.

This evaluation is to be undertaken taking into consideration the GEF Monitoring and Evaluation policy (http://thegef.org/MonitoringandEvaluation/MEPoliciesProcedures/mepoliciesprocedures.html) and the UNDP-GEF Monitoring and Evaluation Policy (http://www.undp.org/gef/05/monitoring/policies.html).

The MTE is intended to identify potential project design problems, assess progress towards the achievement of objective, identify and document lessons learned (including lessons that might improve design and implementation of other UNDP-GEF projects), and to make recommendations regarding specific actions that might be taken to improve the project. It is expected to serve as a tool of validating or filling the gaps in the initial assessment of relevance, effectiveness and efficiency obtained from monitoring. The MTE provides the opportunity to assess early signs of project success or failure and prompt necessary adjustments.

The evaluation will play a critical role in the future implementation of the project by providing advice on: (i) how to strengthen the adaptive management and monitoring function of the project; (ii) how to ensure accountability for the achievement of the GEF objective; (iii) how to enhance organizational and development learning; and (iv) how to enable informed decision - making.

The evaluation will have to provide to the GEF Secretariat with complete and convincing evidence to support its findings/ratings. The evaluator should use the evaluation methodology and prepare specific ratings on specific aspects of the project, as described in Annex 2 of this Terms of Reference. Particular emphasis should be put on the current project results and the possibility of achieving the objective and outcomes in the established timeframe, taking into consideration the speed, at which the project is proceeding.

# Project overview

PIMS 1988: Enhancing Coverage and Management Effectiveness of the Subsystem of Forest Protected Areas in Turkey’s National System of Protected Areas Project was approved by GEF in March 2008 and signed by UNDP and Government in May 2008. The Inception workshop was organized in August 2008. By that time the project team was hired and the project offices were established. The project life time is 3 years. The updated total budget is 2,650,000 USD (GEF contribution is 972,000, Government (in cash) – 160,000 USD, Government (in kind) – 1,435,000 USD, and WWF-Turkey (in kind) – 83.000 USD).

The project aims to enhance coverage and management effectiveness within the Forest Protected Areas sub system by demonstrating cost-effective management approaches in Küre Mountains National Park (KMNP) and then replicating to the remaining 8 forest hot spots. KMNP has been chosen as a demonstration site because: (i) it represents the best remaining example of the ‘deciduous and coniferous forests of North Anatolia’ ecoregion as well as the best remaining example of the highly endangered karstic mountain areas of the “Black Sea Humid Forests” ecotype; (ii) it is broadly representative of different socioeconomic, ecological and institutional conditions at the other intended forest PAs, implying that the management paradigm developed there can easily be adapted for employment at the other sites once it has been tried and tested; and (iii) GoT has already taken several important steps in the recent past to secure the PA, including by establishing an on-site management presence.

The project will contribute to achieving global environmental benefits by enhancing the management effectiveness and sustainability in 37,000 ha of Küre Mountains National Park and its buffer zone (80.000 ha) in Turkey and indirectly influencing approximately an additional 1,400,000 ha of future forest protected areas covering globally significant forest ecosystems, through up-scaling and replication of best management practices. Expected project outcomes are as follows:

Outcome 1: Cost-effective conservation management approaches for forest protected areas are designed, piloted and adopted;

Outcome 2: Sustainable natural resource management approaches demonstrated in buffer areas; and

Outcome 3: Lessons learned from demonstration work in the first established forest Pas are disseminated to the other forest hot spots in Turkey, contributing to the maturation of the PA system of Turkey.

# OBJECTIVE(S) OF THE ASSIGNMENT

The objective of this assignment is to carry out Mid Term Evaluation for PIMS 1988: Enhancing Coverage and Management Effectiveness of the Subsystem of Forest Protected Areas in Turkey’s National System of Protected Areas Project.

The Mid Term Evaluation is initiated by UNDP Country Office in Turkey in line with the UNDP-GEF M&E guidelines in order to assess the overall project progress, make sure the project is on track to deliver the agreed outcomes, and produce recommendations on any adjustments needed.

The purposes of the MTE are:

- To assess overall performance against the project objective and outcomes as set out in the Project Document, Project’s Logical Framework, and other related documents;

- To assess the effectiveness and efficiency of the project;

- To analyze critically the implementation and management arrangements of the project;

- To assess the progress to date towards achievement of the outcomes;

- To review planned strategies and plans for achieving the overall objective of the project within the timeframe;

- To assess the sustainability of the project’s interventions;

- To list and document initial lessons concerning project design, implementation and management;

- To assess project relevance to national priorities;

- To provide guidance for the future project activities and, if necessary, for the implementation and management arrangements;

In particular, this evaluation will assess progress in establishing the information baseline, reducing threats, and identifying any difficulties in project implementation and their causes, and recommend corrective course of action. Effective action to rectify any identified issues hindering implementation will be a requirement prior to determining whether implementation should proceed.

Project performance will be measured based on Project’s Logical Framework Matrix (see Annex 5, which provides clear performance and impact indicators for project implementation along with their corresponding means of verification. Success and failure will be determined in part by monitoring changes in baseline conditions.

The evaluation will be undertaken by a team composed of an International Consultant (Evaluation Team Leader) and a Local Consultant. As the member of the evaluation team, the local consultant is expected to work with key project stakeholders, including UNDP Country Office in Turkey, related central and local departments of Ministry of Environment and Forestry, WWF- Turkey, local universities and ENGOs.

# DUTIES AND RESPONSIBILITIES

The evaluation will be undertaken by a team composed of an International Consultant (Evaluation Team Leader) and a Local Consultant. They will receive the support of UNDP Country Office and Project Management Team, and will be assisted by a translator/interpreter (when needed).

The local consultant will work under coordination of international consultant (Evaluation Team Leader). The local consultant will provide input in reviewing all the project-relevant documentation and provide the International Consultant (Evaluation Team Leader) with a compilation of information prior to the evaluation mission. Specifically, the Local Consultant will perform the following tasks:

- Review the original documents;

- Participate in the design of the evaluation methodology;

- Organize the mission program, arrange and facilitate meetings with key stakeholders;

- Provide regular translation/interpretation as necessary;

- Draft related parts of the evaluation report, as relevant;

- Assist the International Team Leader in finalizing the draft report by incorporating inputs received;

- Provide other support services for the International Team Leader.

- TIME-FRAME OF WORK

The duration of the assignment will be 45 days upon the signature of the Contract.

The work will be undertaken during a period of 20 man/day throughout the time-frame below;

Contract Start Date:  15 September 2010

Contract Completion Date:  30 October 2010

- DELIVERABLES AND REPORTING

The core product of the Mid-Term Evaluation will be the Mid-Term Evaluation Report that includes:

- Findings with the rating on performance;

- Conclusions drawn;

- Recommendations for improving delivery of project outputs;

- Lessons learned concerning best and worst practices in producing outputs;

- A rating on progress towards outputs.

The Report will be supplemented by Rate Tables, attached in Annex 6 of this TOR

The Report will include a table of planned vs. actual project financial disbursements, and planned co-financing vs. actual co-financing in this project, according the table attached in Annex 7 of this TOR.

The Mid-Term Evaluation Report structure and details are given in Annex 3.

As the member of the evaluation team, the consultant will be responsible to submit following deliverables.

| Date | Estimated Number of Professional Days to be invested* | Milestone/Deliverables |
| --- | --- | --- |
| 20 September 2010 | 3 | Inception Report: Desk review, development of methodology, updating time table, drafting mission programme |
| 01 October 2010 | 7 | In-country field visits, interviews |
| 15 October 2010 | 3 | Drafting report |
| 20 October 2010 | 5 | Draft report circulation |
| 28 October r 2010 | 2 | Finalization of report |
| Total Number of days | 20 |  |

* The number of day may change among different activities and deliverables but the total days to be invested cannot exceed 20 days for the content of this TOR. UNDP has the right to request from the Consultant additional number of days to be invested for additional activities, based on the needs of the project.

The final version of the evaluation report should be submitted in electronic format (MS Word) to UNDP Country Office in Turkey no later than October 30, 2010.

- Reporting Line

The local consultant will work under coordination of international consultant (Evaluation Team Leader). However, the local consultant will be responsible to the PIMS 1988: Enhancing Coverage and Management Effectiveness of the Subsystem of Forest Protected Areas in Turkey’s National System of Protected Areas Project Deputy Project Manager for the completion of the tasks and duties assigned in Article-D. The deliverables shall be submitted to the Deputy Project Manager and UNDP Environment and Sustainable Development (ESD) Programme Manager for final approval. All of the deliverables are subject to approval from UNDP ESD Programme Manager in order to realize the payments to the consultant. He/she will work in close collaboration with Ministry of Environment and Forestry General Directorate of Nature Conservation and National Parks, and other project partners.

- Reporting Language

The reporting language should be in English.

- Title Rights

The title rights, copyrights and all other rights whatsoever nature in any material produced under the provisions of this TORs will be vested exclusively in UNDP.

- G. DUTY STATION

Duty station of the Consultant will be his/her home base. If the consultant’s home base is outside of Ankara, the costs of the transportation to Ankara and other costs such as accommodation etc. will be covered from the project budget. The individual contractor might also be required to travel outside the duty station, to the project sites including Kastamonu and Bartın. The costs of the transportation to project sites and other costs such as accommodation etc. will be covered from the project budget.

- H. TERMS AND PAYMENT

The consultant will be paid in TL (UN monthly exchange ratio will be used as official conversation rate from USD to TL)

- Contracting Authority

Contracting Authority for this ToR is UNDP, and the contract amount will be provided through UNDP-GEF budget under “PIMS 1988: Enhancing Coverage and Management Effectiveness of the Subsystem of Forest Protected Areas in Turkey’s National System of Protected Areas” Project.

- Contracting Modality

SSA-Special Service Agreement of UNDP.

- Payment schedule

The local consultant shall be paid upon submission and approval of deliverables specified in Section-F- DELIVERABLES and REPORTING of this ToR, by UNDP, following successful completion of the tasks listed throughout this ToR and assigned by UNDP.

The payments for each deliverable will be based on the number of days to be invested for the respective deliverable. The payments shall be effected only if the deliverables required in this ToR are submitted to UNDP within the time frames stipulated in the TOR and they are approved by UNDP. Without submission and approval of the deliverables, the consultant shall not receive any payment even if he/she invests time for this assignment.

The amount paid to local consultant shall be gross and inclusive of all associated costs such as social security, pension and income tax etc.

| Name of the Report | Expected Delivery Date of the Reports | Estimated Number of days to be invested |
| --- | --- | --- |
| - Inception Report | 20 September 2010 | 3 |
| - Draft Report | 15 October 2010 | 10 |
| - Final Report | 30 October 2010 | 7 |
| - Total Number of Days | 20 |  |

Tax obligation

The subscriber is solely responsible for all taxation or other assessments on any income derived from UNDP. UNDP will not make any withholding from payments for the purposes of income tax. UNDP is exempt from any liabilities regarding taxation and will not reimburse any such taxation to the subscriber.

- I. SERVICES AND FACILITIES PROVIDED BY UNDP/MOEF

The principal responsibility for managing this evaluation lies with UNDP Country Office in Turkey. It will be responsible for liaising with the project team to set up the stakeholder interviews, arrange the field visits, coordinate with the Government and WWF-Turkey

These Terms of Reference follow the UNDP-GEF policies and procedures, and together with the final agenda will be agreed upon by the UNDP-GEF Regional Coordinating Unit, UNDP Country Office in Turkey, Ministry of Environment and Forestry, and WWF-Turkey. These four parties will receive a draft of the final evaluation report and provide comments on it prior to its completion.

If requested, the Consultant will be provided with an office space located in Ankara and project site with an access to the Internet and a local telephone line.

- J. QUALIFICATIONS AND SKILLS

The evaluators selected should not have participated in the project preparation and/or implementation and should not have conflict of interest with project related activities.

| General Qualifications | - University degree in environmental sciences or social sciences. - Excellent command in written and spoken English and Turkish. |
| --- | --- |
| Professional Experience | - Minimum 4 years relevant experience in project development in environment field; - Minimum 2 years of experience in monitoring and evaluation in environment field. - Proven ability and practical experience in monitoring and evaluation of international projects. |
| Specific Experience | - Excellent analytical and report writing skills. - Excellent computer literacy. - Excellent time-management skills. - Strong interpersonal and communication skills, strong cultural sensitivity and ability to work in multi-cultural environments. - Ability to work in a team, under pressure and ability to meet deadlines. - Prior experience with UNDP would be an asset. |

- K. Evaluation of Applicants

Applicants meeting the minimum qualifications listed in the Terms of Reference will be short-listed and asked for price proposals.  The selection of the Consultant will be made in accordance with the quality-cost based selection method (70 % technical component and 30% price component).

- L. Application Information

Interested candidates should submit the following application – women candidates are encouraged to apply – documents by stating the reference code PIMS 1988 – MTE_LOCAL [SURNAME OF APPLICANT] as the subject of the e-mail:

- A cover letter stating an expression of interest with a possible starting date for the entire duration of the contract;

- Most updated CV;

- UN Personal History Form (P11 Form);

- Proof of his/her recent work in monitoring and evaluation (web links, summary of produced reports, etc) along with at least three professional references who can confirm or familiar with your work.

Applicants should submit their CVs and the UN Personal History Form (http://www.undp.org.tr/jobDocuments/Personal_History_Form_SC_SSA.doc)

to ssa.proposal@undp.org.tr  address no later than 01 September 2010, 17:00 pm local time.

Women candidates are encouraged to apply.

# M. Annexes

Annex 1: GEF Terminology and Project Review Criteria

Annex 2: Scope and Methodology of Evaluation

Annex 3: Mid Term Evaluation Report Structure

Annex 4: List of Documents to be Reviewed by the Evaluators

Annex 5: Revised Project Logical Framework

Annex 6: Rate Tables

Annex 7: Co-financing Tables

# Annex 1. GEF terminology and project review criteria

Implementation Approach includes an analysis of the project’s logical framework, adaptation to changing conditions (adaptive management), partnerships in implementation arrangements, changes in project design, and overall project management.

Some elements of an effective implementation approach may include:

- The logical framework used during implementation as a management and M&E tool

- Effective partnerships arrangements established for implementation of the project with relevant stakeholders involved in the country/region

- Lessons from other relevant projects (e.g., same focal area) incorporated into project implementation

- Feedback from M&E activities used for adaptive management.

Country Ownership/Driveness is the relevance of the project to national development and environmental agendas, recipient country commitment, and regional and international agreements where applicable. Project Concept has its origin within the national sectoral and development plans

Some elements of effective country ownership/driveness may include:

- Project Concept has its origin within the national sectoral and development plans

- Outcomes (or potential outcomes) from the project have been incorporated into the national sectoral and development plans

- Relevant country representatives (e.g., governmental official, civil society, etc.) are actively involved in project identification, planning and/or implementation

- The recipient government has maintained financial commitment to the project

- The government has approved policies and/or modified regulatory frameworks in line with the project’s objectives

For projects whose main focus and actors are in the private-sector rather than public-sector (e.g., IFC projects), elements of effective country ownership/driveness that demonstrate the interest and commitment of the local private sector to the project may include:

- The number of companies that participated in the project by: receiving technical assistance, applying for financing, attending dissemination events, adopting environmental standards promoted by the project, etc.

- Amount contributed by participating companies to achieve the environmental benefits promoted by the project, including: equity invested, guarantees provided, co-funding of project activities, in-kind contributions, etc.

- Project’s collaboration with industry associations

Stakeholder Participation/Public Involvement consist of three related, and often overlapping processes: information dissemination, consultation, and “stakeholder” participation. Stakeholders are the individuals, groups, institutions, or other bodies that have an interest or stake in the outcome of the GEF-financed project. The term also applies to those potentially adversely affected by a project.

Examples of effective public involvement include:

Information dissemination

- Implementation of appropriate outreach/public awareness campaigns

Consultation and stakeholder participation

- Consulting and making use of the skills, experiences and knowledge of NGOs, community and local groups, the private and public sectors, and academic institutions in the design, implementation, and evaluation of project activities

Stakeholder participation

- Project institutional networks well placed within the overall national or community organizational structures, for example, by building on the local decision making structures, incorporating local knowledge, and devolving project management responsibilities to the local organizations or communities as the project approaches closure

- Building partnerships among different project stakeholders

- Fulfillment of commitments to local stakeholders and stakeholders considered to be adequately involved.

Sustainability measures the extent to which benefits continue, within or outside the project domain, from a particular project or program after GEF assistance/external assistance has come to an end.  Relevant factors to improve the sustainability of project outcomes include:

- Development and implementation of a sustainability strategy.

- Establishment of the financial and economic instruments and mechanisms to ensure the ongoing flow of benefits once the GEF assistance ends (from the public and private sectors, income generating activities, and market transformations to promote the project’s objectives).

- Development of suitable organizational arrangements by public and/or private sector.

- Development of policy and regulatory frameworks that further the project objectives.

- Incorporation of environmental and ecological factors affecting future flow of benefits.

- Development of appropriate institutional capacity (systems, structures, staff, expertise, etc.) .

- Identification and involvement of champions (i.e. individuals in government and civil society who can promote sustainability of project outcomes).

- Achieving social sustainability, for example, by mainstreaming project activities into the economy or community production activities.

- Achieving stakeholders consensus regarding courses of action on project activities.

Replication approach, in the context of GEF projects, is defined as lessons and experiences coming out of the project that are replicated or scaled up in the design and implementation of other projects. Replication can have two aspects, replication proper (lessons and experiences are replicated in different geographic area) or scaling up (lessons and experiences are replicated within the same geographic area but funded by other sources). Examples of replication approaches include:

- Knowledge transfer (i.e., dissemination of lessons through project result documents, training workshops, information exchange, a national and regional forum, etc).

- Expansion of demonstration projects.

- Capacity building and training of individuals, and institutions to expand the project’s achievements in the country or other regions.

- Use of project-trained individuals, institutions or companies to replicate the project’s outcomes in other regions.

Financial Planning includes actual project cost by activity, financial management (including disbursement issues), and co-financing. If a financial audit has been conducted the major findings should be presented in the TE.

Effective financial plans include:

- Identification of potential sources of co-financing as well as leveraged and associated financing.

- Strong financial controls, including reporting, and planning that allow the project management to make informed decisions regarding the budget at any time, allows for a proper and timely flow of funds, and for the payment of satisfactory project deliverables

- Due diligence due diligence in the management of funds and financial audits.

Co-financing includes: grants, loans/concessional (compared to market rate), credits, equity investments, in-kind support, other contributions mobilized for the project from other multilateral agencies, bilateral development cooperation agencies, NGOs, the private sector and beneficiaries. Please refer to Council documents on co-financing for definitions, such as GEF/C.20/6.

Leveraged resources are additional resources—beyond those committed to the project itself at the time of approval—that are mobilized later as a direct result of the project. Leveraged resources can be financial or in-kind and they may be from other donors, NGO’s, foundations, governments, communities or the private sector. Please briefly describe the resources the project has leveraged since inception and indicate how these resources are contributing to the project’s ultimate objective.

Cost-effectiveness assesses the achievement of the environmental and developmental objectives as well as the project’s outputs in relation to the inputs, costs, and implementing time. It also examines the project’s compliance with the application of the incremental cost concept. Cost-effective factors include:

- Compliance with the incremental cost criteria (e.g. GEF funds are used to finance a component of a project that would not have taken place without GEF funding.) and securing co-funding and associated funding.

- The project completed the planned activities and met or exceeded the expected outcomes in terms of achievement of Global Environmental and Development Objectives according to schedule, and as cost-effective as initially planned.

- The project used either a benchmark approach or a comparison approach (did not exceed the costs levels of similar projects in similar contexts)

Monitoring & Evaluation. Monitoring is the periodic oversight of a process, or the implementation of an activity, which seeks to establish the extent to which inputs, work schedules, other required actions and outputs are proceeding according to plan, so that timely action can be taken to correct the deficiencies detected. Evaluation is a process by which program inputs, activities and results are analyzed and judged explicitly against benchmarks or baseline conditions using performance indicators. This will allow project managers and planners to make decisions based on the evidence of information on the project implementation stage, performance indicators, level of funding still available, etc, building on the project’s logical framework.

Monitoring and Evaluation includes activities to measure the project’s achievements such as identification of performance indicators, measurement procedures, and determination of baseline conditions.  Projects are required to implement plans for monitoring and evaluation with adequate funding and appropriate staff and include activities such as description of data sources and methods for data collection, collection of baseline data, and stakeholder participation.  Given the long-term nature of many GEF projects, projects are also encouraged to include long-term monitoring plans that are sustainable after project completion.

Financial Planning - Cofinancing

| Cofinancing (Type/Source) | IA own Financing (mill US$) |  | Government (mill US$) |  | Other* (mill US$) |  | Total (mill US$) |  | Total Disbursement (mill US$) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual | Planned | Actual |
| - Grants |  |  |  |  |  |  |  |  |  |  |
| - Loans/Concessional (compared to market rate) |  |  |  |  |  |  |  |  |  |  |
| - Credits |  |  |  |  |  |  |  |  |  |  |
| - Equity investments |  |  |  |  |  |  |  |  |  |  |
| - In-kind support |  |  |  |  |  |  |  |  |  |  |
| - Other (*) |  |  |  |  |  |  |  |  |  |  |
| # Totals |  |  |  |  |  |  |  |  |  |  |

* Other is referred to contributions mobilized for the project from other multilateral agencies, bilateral development cooperation agencies, NGOs, the private sector and beneficiaries.

## Leveraged Resources

Leveraged resources are additional resources—beyond those committed to the project itself at the time of approval—that are mobilized later as a direct result of the project. Leveraged resources can be financial or in-kind and they may be from other donors, NGO’s, foundations, governments, communities or the private sector. Please briefly describe the resources the project has leveraged since inception and indicate how these resources are contributing to the project’s ultimate objective.

# ANNEX 2: SCOPE AND METHODOLOGY OF EVALUATION

# SCOPE OF EVALUTION

The evaluation will focus on the range of aspects described below. In addition to a descriptive assessment, all criteria marked with (R) should be rated using the following divisions: Highly Satisfactory, Satisfactory, Marginally Satisfactory, Marginally Unsatisfactory, Unsatisfactory, Highly Unsatisfactory. All ratings given should be properly substantiated:

1. Project concept/design, relevance and strategy

1.1 Project relevance, country ownership/drivenness (R): the extent to which the project is suited to local and national development priorities and organizational policies, including changes over time as well as the extent the activities contribute towards attainment of global environmental benefits:

- Is the project concept in line with the sectoral and development priorities and plans of the country?

- Are project outcomes contributing to national development priorities and plans?

- How and why project outcomes and strategies contribute to the achievement of the expected results.

- Examine their relevance and whether they provide the most effective way towards results.

- Do the outcomes developed during the inception phase still represent the best project strategy for achieving the project objectives (in light of updated underlying factors)?  Consider alternatives.

- Were the relevant country representatives, from government and civil society, involved in the project preparation?

- Does the recipient government maintain its financial commitment to the project? Has the government approved policies or regulatory frameworks in line with the project’s objectives?

1.2 Preparation and readiness:

- Are the project’s objective and components clear, practicable and feasible within its timeframe?

- Were the capacities of executing institution and counterparts properly considered when the project was designed?

- Were lessons from other relevant projects properly incorporated in the project design?

- Were the partnership arrangements properly identified and the roles and responsibilities negotiated prior to project approval?

- Were counterpart resources (funding, staff, and facilities), enabling legislation, and adequate project management arrangements in place at project entry?

1.3 Stakeholder involvement (R):

- Did the project involve the relevant stakeholders through information-sharing, consultation and by seeking their participation in the project’s design?

- Did the project consult and make use of the skills, experience and knowledge of the appropriate government entities, NGOs, community groups, private sector, local governments and academic institutions in the design of project activities?

1.4 Underlying factors/assumptions:

- Assess the underlying factors beyond the project’s immediate control that influence outcomes and results.  Consider the appropriateness and effectiveness of the project’s management strategies for these factors.

- Re-test the assumptions made by the project management and identify new assumptions that should be made.

- Assess the effect of any incorrect assumptions made by the project.

1.5 Management arrangements (R):

- Were the project roles properly assigned during the project design?

- Are the project roles in line with UNDP and GEF programming guidelines?

- Can the management arrangement model suggested by the project be considered as an optimum model? If no, please come up with suggestions and recommendations.

1.6 Project budget and duration (R):

- Assess if the project budget and duration were planned in a cost-effective way?

1.7 Design of project M&E system (R):

- Examine whether or not the project has a sound M&E plan to monitor results and track progress towards achieving project objectives.

- Examine whether or not the M&E plan includes a baseline (including data, methodology, etc.), SMART indicators and data analysis systems, and evaluation studies at specific times to assess results and adequate funding for M&E activities.

- Examine whether or not the time frame for various M&E activities and standards for outputs are specified.

1.8 Sustainability:

- Assess if project sustainability strategy was developed during the project design?

- Assess the relevance of project sustainability strategy

2. Project implementation

2.1 Project’s adaptive management (R):

- Monitoring systems

  - Assess the monitoring tools currently being used:

- Do they provide the necessary information?

- Do they involve key partners?

- Are they efficient?

- Are additional tools required?

  - Assess the use of the logical framework as a management tool during implementation and any changes made to it.

  - What impact did the retro-fitting of impact indicators have on project management, if such?

  - Assess whether or not M&E system facilitates timely tracking of progress towards project’s objectives by collecting information on chosen indicators continually; annual project reports are complete, accurate and with well justified ratings; the information provided by the M&E system is used to improve project performance and to adapt to changing needs.

- Risk Management

  - Validate whether the risks identified in the project document and PIRs are the most important and whether the risk ratings applied are appropriate.  If not, explain why.

  - Describe any additional risks identified and suggest risk ratings and possible risk management strategies to be adopted.

  - Assess the project’s risk identification and management systems:

- Is the UNDP-GEF Risk Management System appropriately applied?

- How can the UNDP-GEF Risk Management System be used to strengthen the project management?

- Work Planning

  - Assess the use of routinely updated work plans.

  - Assess the use of electronic information technologies to support implementation, participation and monitoring, as well as other project activities.

  - Are work planning processes result-based? If not, suggest ways to re-orientate work planning.

- Financial management

  - Consider the financial management of the project, with specific reference to the cost-effectiveness of interventions.  (Cost-effectiveness: the extent to which results have been delivered with the least costly resources possible.). Any irregularities must be noted.

  - Is there due diligence in the management of funds and financial audits?

  - Did promised co-financing materialize (please fill out the co-financing form provided in Annex 1)?

- Reporting

  - Assess how adaptive management changes have been reported by the project management.

  - Assess how lessons derived from the adaptive management process have been documented, shared with key partners and internalized by partners.

- Delays

  - Assess if there were delays in project implementation and what were the reasons.

  - Did the delay affect the achievement of project’s outcomes and/or sustainability, and if it did then in what ways and through what causal linkages?

  - Contribution of Implementing and Executing Agencies:

- Assess the role of UNDP and Ministry of Environment and Forestry against the requirements set out in the UNDP Programme and Operations Policies and Procedures. Consider:

  - Field visits

  - Participation in Steering Committees

  - Project reviews, PIR preparation and follow-up

  - GEF guidance

  - Operational support

- Consider the new UNDP requirements outlined in the UNDP Programme and Operations Policies and Procedures, especially the Project Assurance role, and ensure they are incorporated into the project’s adaptive management framework.

- Assess the contribution to the project from UNDP and Ministry of Environment and Forestry in terms of “soft” assistance (i.e. policy advice & dialogue, advocacy, and coordination).

- Suggest measures to strengthen UNDP’s soft assistance to the project management.

2.3 Stakeholder participation, partnership strategy (R):

- Assess whether or not and how local stakeholders participate in project management and decision-making.  Include an analysis of the strengths and weaknesses of the approach adopted by the project and suggestions for improvement if necessary.

- Does the project consult and make use of the skills, experience and knowledge of the appropriate government entities, NGOs, community groups, private sector, local governments and academic institutions in the implementation and evaluation of project activities?

- Consider the dissemination of project information to partners and stakeholders and if necessary suggest more appropriate mechanisms.

- Identify opportunities for stronger partnerships.

2.4 Sustainability:

- Assess the extent to which the benefits of the project will continue, within or outside the project scope, after it has come to an end; commitment of the government to support the initiative beyond the project.

- The evaluators may look at factors such as mainstreaming project objectives into the broader development policies and sectoral plans and economies.

The sustainability assessment will give special attention to analysis of the risks that are likely to affect the persistence of project outcomes. The sustainability assessment should also explain how other important contextual factors that are not outcomes of the project will affect sustainability. The following four dimensions or aspects of sustainability will be addressed:

  - Financial resources: Are there any financial risks that may jeopardize sustenance of project outcomes? What is the likelihood of financial and economic resources not being available once the GEF assistance ends (resources can be from multiple sources, such as the public and private sectors, income generating activities, and trends that may indicate that it is likely that in future there will be adequate financial resources for sustaining project’s outcomes)?

  - Socio-political: Are there any social or political risks that may jeopardize sustenance of project outcomes? What is the risk that the level of stakeholder ownership (including ownership by governments and other key stakeholders) will be insufficient to allow for the project outcomes/benefits to be sustained? Do the various key stakeholders see that it is in their interest that the project benefits continue to flow? Is there sufficient public / stakeholder awareness in support of the long term objectives of the project?

  - Institutional framework and governance: Do the legal frameworks, policies and governance structures and processes pose risks that may jeopardize sustenance of project benefits? While assessing this parameter, also consider if the required systems for accountability and transparency, and the required technical know-how are in place.

  - Environmental: Are there any environmental risks that may jeopardize sustenance of project outcomes? The terminal evaluation should assess whether certain activities will pose a threat to the sustainability of the project outcomes.

On each of the dimensions of sustainability of the project outcomes will be rated as follows:

  - Likely (L): There are no or negligible risks that affect this dimension of sustainability.

  - Moderately Likely (ML): There are moderate risks that affect this dimension of sustainability.

  - Moderately Unlikely (MU): There are significant risks that affect this dimension of sustainability

  - Unlikely (U): There are severe risks that affect this dimension of sustainability.

3. Project results (outputs, outcomes and objectives)

3.1 Progress towards achievement of intended outputs, outcomes/measurement of change:

Progress towards results should be based on a comparison of indicators before and after (so far) the project intervention.

To determine the level of achievement of project outcomes and objectives following three criteria should be assessed:

- Relevance: Are the project’s outcomes consistent with the focal areas/operational program strategies and country priorities?

- Effectiveness: Are the actual project outcomes commensurate with the original or modified project objectives? In case the original or modified expected results are merely outputs/inputs then the evaluators should assess if there are any real outcomes of the project and if yes then whether these are commensurate with the realistic expectations from such a project.

- Efficiency: Is the project cost effective? Is the project the least cost option? Is the project implementation delayed and if it is, then does that affect cost-effectiveness? Wherever possible, the evaluator should also compare the cost-time vs. outcomes relationship of the project with that of other similar projects.

Outcomes and the  whole project should be rated as follows for relevance, effectiveness, efficiency:

- Highly Satisfactory (HS): The project has no shortcomings in the achievement of its objectives.

- Satisfactory (S): The project has minor shortcomings in the achievement of its objectives.

- Marginally Satisfactory (MS): The project has moderate shortcomings in the achievement of its objectives.

- Marginally Unsatisfactory (MU): The project has significant shortcomings in the achievement of its objectives.

- Unsatisfactory (U): The project has major shortcomings in the achievement of its objectives.

- Highly Unsatisfactory (HU): The project has severe shortcomings in the achievement of its objectives.

# EVALUATION METHODOLOGY

An outline of an evaluation approach is provided below; however it should be made clear that the evaluation team is responsible for revising the approach as necessary.  Any changes should be in-line with international criteria and professional norms and standards (as adopted by the UN Evaluation Group).  They must be also cleared by UNDP before being applied by the evaluation team.

The evaluation must provide evidence-based information that is credible, reliable and useful.  It must be easily understood by project partners and applicable to the remaining period of project duration.

Evaluators should seek guidance for their work in the following materials, which could be found at (www.undp.org/gef):

- UNDP Handbook on Monitoring and Evaluation for Results

- UNDP/GEF M&E Resource Kit

- Measuring Results of the GEF Biodiversity Programme

It is recommended that the evaluation methodology include the following:

- Documentation review (desk study), to include Project Document, Project CEO Approval Document, Inception Report, GEF Project Implementation Reviews, Minutes of the Project Steering Committee meetings, GEF quarterly project updates;

- Interviews with Project Management Unit and key project stakeholders, including UNDP Country Office in Turkey, GEF Regional Coordination Unit in Bratislava, Ministry of Environment and Forestry in Turkey, WWF-Turkey, project local management unit and other stakeholders, as necessary;

- In-country field visits.

ANNEX 3: Mid-Term Evaluation Report Structure

The core product of the Mid-Term Evaluation will be the Mid-Term Evaluation Report that includes:

- Findings with the rating on performance;

- Conclusions drawn;

- Recommendations for improving delivery of project outputs;

- Lessons learned concerning best and worst practices in producing outputs;

- A rating on progress towards outputs.

The report is proposed to adhere to the following basic structure:

- Executive summary

- Brief description of project

- Context and purpose of the evaluation

- Main conclusions, recommendations and lessons learned

- Introduction

- Project background

- Purpose of the evaluation

- Key issues to be addressed

- The outputs of the evaluation and how will they be used

- Methodology of the evaluation

- Structure of the evaluation

- The project and its development context

- Project start and its duration

- Implementation status

- Problems that the project seeks to address

- Immediate and development objectives of the project

- Main stakeholders

- Results expected

- Analysis of the situation with regard to outcomes, outputs and partnership strategy

- Findings and Conclusions

4.1 Project formulation

    - Project relevance

    - Implementation approach

    - Country ownership/Driveness

    - Stakeholder participation

    - Replication approach

    - Cost-effectiveness

    - Sustainability

    - Linkages between project and other interventions within the sector

    - Management arrangements

4.2 Project implementation

    - Financial management

    - Monitoring and evaluation

    - Management and coordination

    - Identification and management of risks (adaptive management)

4.3 Results

    - Attainment of outputs, outcomes and objectives

    - Project Impact

    - Prospects of sustainability

- Conclusions and recommendations

- Findings

- Corrective actions for the design, duration, implementation, monitoring and evaluation of the project

- Actions to strengthen or reinforce benefits from the project

- Proposals for future directions underlining main objectives

- Suggestions for strengthening ownership, management of potential risks

- Lessons learned

- Good practices and lessons learned in addressing issues relating to effectiveness, efficiency and relevance

- Annexes

- Evaluation TOR

- Itinerary

- List of persons interviewed

- Summary of field visits

- List of documents reviewed

- Questionnaire used (if any) and summary of results

- Comments by stakeholders (only in case of discrepancies with evaluation findings and conclusions)

- Management Effectiveness Tracking Tool

The Report will be supplemented by Rate Tables, attached in Annex 6 of this TOR.

The Report will include a table of planned vs. actual project financial disbursements, and planned co-financing vs. actual co-financing in this project, according the table attached in Annex 7 of this TOR.

The expected length of the report is around 50 pages in total. The first draft of the report is expected to be submitted to the UNDP Country Office in Turkey within 2 weeks of the in-country mission for subsequent circulation to the key project stakeholders for comments. Any discrepancies between the interpretations and findings of the evaluator and the key project stakeholders will be explained in an annex to the final report.

annex 4. List of documents to be reviewed by the evaluators

General Documentation

- UNDP Programme and Operations Policies and Procedures

- UNDP Handbook for Monitoring and Evaluating for Results

- GEF Monitoring and Evaluation Policy

Project Documentation

- Project Document

- Project CEO Approval Document

- Inception Report

- Annual Project Reports

- Project Implementation Review

- Quarterly Reports

- Steering Committee Meeting Minutes

- Management Effectiveness Tracking Tool (METT midterm)

Annex 5: revısed Project Logical Framework

| Project Goal | Long-term conservation of the most representative range of globally significant biodiversity in Turkey by strengthening the national system of protected areas |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Indicator | Baseline | Target |  | Source of Verification | Risks and Assumptions |  |
| Project objective: To enhance coverage and management effectiveness of the Forest Protected Areas (FPAs) through demonstrating cost-effective approaches for effective conservation and sustainable resource management at Küre Mountains National Park and taking initial steps towards the replication of this model at the remaining eight forest hot spots | Surface of globally significant habitats (grasslands, old growth forests) under conservation management (either legal protection or under sustainable forest management) | 37,000 ha | 600,000 ha |  | Meeting Pan Parks requirements Monitoring surveys Biodiversity monitoring reports | National political and economic stability ensure that GoT remains committed to conservation objectives The strength of other sectors and interest groups causing threats is not more than conservation efforts; or they are open to cooperate. The agencies responsible for the management of the forest sites continue to be open to apply the new tracking systems for performance and cost-effectiveness. Local women have continuous willingness on participating training and productive activities. |  |
|  | Proportion of 9 forest hot spots under legal protection | 10% | 100% |  | Official Gazette |  |  |
|  | Forest management performance at the 9 forest hot spots, as measured with METT | The baseline will be assessed at the beginning of implementation phase | Performance score increased by 15% |  | METT data sheets |  |  |
|  | Number of local women producing traditional products and their total income | Baseline data will be assessed at the beginning of implementation | Income rate: increase by 10% in 3 years. No. of participating women: increase by 5% in 3 years |  | Surveys |  |  |
|  | The overall performance of the national PA system (specially forest PA) using WWF’s Rapid Assessment and Prioritization of PA Management Methodology (RAPPAM) which is based on the WCPA framework | The baseline will be assessed within in the first year. |  | Performance score increased by 10% at the end of the project | RAPPAM reports |  |  |
| Outcome 1: Cost-effective conservation management approaches for forest protected areas are implemented at Küre Mountains National Park (KMNP) | - Use of business methods at Küre MNP level and existence of a PA performance monitoring system | There is no business planning at Küre MNP level and no institutionalized PA performance monitoring system |  | Business planning is an integral part of PA management, supported by an M&E system at the park level | Business plan Monitoring plan | The project receives required co-operation from relevant local people Government financing is not jeopardized by political and economic instability No irresolvable difficulties are encountered in drafting of management plan; conflict resolution mechanism can successful resolve serious conflicts |  |
|  | Available funds are in line with management requirements | Available funds cannot cover management costs of effective protection |  | Management costs are being covered through national funding sources in line with a financial plan | Financial records of KMNP management authority |  |  |
| Outcome 2: Sustainable natural resource management is demonstrated in the buffer area of Küre Mountain National Park Outcome 2: Sustainable natural resource management is demonstrated in the buffer area of Küre Mountain National Park | Use of sustainable forest management approaches in the buffer area of KMNP is institutionalized by the Department of Forestry as a tool for sustainable natural resource management to be used in all forest PAs | No sustainable forest management guidelines applied in Küre and other forest hotspots |  | Sustainable forest management guidelines developed and implemented at KMNP and institutionalized by the Department of Forestry as a tool for sustainable natural resource management to be used in all forest PAs | Records from the Forest & National Parks departments and court | Socio-economic and human development priorities of local communities can be addressed in a sustainable manner while conserving the biodiversity of the project area The project receives all required co-operation from relevant Government, municipalities, NGOs, local villagers |  |
|  | Extent and percentage of forest area under comprehensive sustainable forest management plan | 0 hectares of forest in the buffer zone is under SFM |  | 40% of forest area is under SFM | Records from Forest Department |  |  |
|  | Female participation percentage in training programmes related to productive and conservation activities | 5% participation |  | At least 20% females at the end of project | Activity reports by the project |  |  |
|  | Area of degraded forest land | 40,000 hectares |  | 5% decline in degraded forest areas | Records from Forest Department |  |  |
|  | Local population percentage generating income from alternative livelihoods | 70% of local population depends on resource harvest from the forest to generate income |  | At least 5% of local population is generating income from alternative livelihoods | Records from the Forest & National Parks departments |  |  |
|  | Local population percentage meeting fuel needs from renewable energy resources | 70% local populations rely on the forest to meet fuel needs |  | At least 2% of local population meets fuel needs from non-forest sources | Records from the Forest department |  |  |
| Outcome 3: Lessons learned from demonstration work at KMNP are disseminated to the other forest hot spots in Turkey, contributing to the maturation of the national protected area system | Capacity increase rate for the staff working in the nine forest sites | The conservation management capacity of the staff responsible for forest sites is very low |  | The capacity is increased by 60% | Institutional Assessment scorecard Personnel records and TORs of staff | Government remains committed to bringing all 9 forest hot spots under an effective conservation regime |  |
|  | Instances of “methodology replication” at other sites | 0 |  | By project end, 3 recorded instances of ‘methodology replication’ at GttE sites or elsewhere (supported through leveraged co-financing) | Official Gazette Project progress reports |  |  |

ANNEX 6:  RATE TABLES

Table: Status of objective / outcome delivery as per measurable indicators

| OBJECTIVE | MEASURABLE INDICATORS FROM PROJECT LOGFRAME | END-OF-PROJECT TARGET | STATUS OF DELIVERY* | RATING** |
| --- | --- | --- | --- | --- |
| Objective: |  |  |  |  |
| OUTCOMES | MEASURABLE INDICATORS FROM PROJECT LOGFRAME | END-OF-PROJECT TARGET | STATUS OF DELIVERY | RATING |
| Outcome 1: |  |  |  |  |
| Outcome 3: |  |  |  |  |
| Outcome 3: |  |  |  |  |

###### * Status of delivery colouring codes:

Green / completed – indicator shows successful achievement

Yellow – indicator shows expected completion by the end of the project

Red – Indicator show poor achievement - unlikely to be complete by end of Project

** Ratings codeas are detailed in Annex 2.

ANNEX 7: CO-FINANCING

| Cofinancing (Type/Source) | IA own Financing (mill US$) |  | Government (mill US$) |  | Other Sources (mill US$) |  | Total Financing (mill US$) |  | Total Disbursement (mill US$) |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Proposed | Actual | Proposed | Actual | Proposed | Actual | Proposed | Actual | Proposed | Actual |
| Grants |  |  |  |  |  |  |  |  |  |  |
| Loans |  |  |  |  |  |  |  |  |  |  |
| Credits |  |  |  |  |  |  |  |  |  |  |
| Equity |  |  |  |  |  |  |  |  |  |  |
| In-kind |  |  |  |  |  |  |  |  |  |  |
| Non-grant Instruments |  |  |  |  |  |  |  |  |  |  |
| Other Types |  |  |  |  |  |  |  |  |  |  |
| # Totals |  |  |  |  |  |  |  |  |  |  |

* Other Sources refer to contributions mobilized for the project from other multilateral agencies,

bilateral development cooperation agencies, NGOs, the private sector etc.

* “Proposed” co-financing refers to co-financing proposed at CEO endorsement.

* Describe “Non-grant Instruments” (such as guarantees, contingent grants, etc):

Source/amount/in-kind or cash/purpose

* Explain “Other Sources of Co-financing”:

Source/amount/in-kind or cash

Please refer to Council documents on co-financing for definitions, such as GEF/C.20/6. The following page presents a table to be used for reporting co-financing.

UNDP-GEF’s system is based on the Atlas Risk Module.  See the UNDP-GEF Risk Management Strategy resource kit, available as Annex XII at http://www.undp.org/gef/05/monitoring/policies.html

RBM Support documents are available at http://www.undp.org/eo/methodologies.htm

Available at http://content.undp.org/go/userguide/results/project/

See http://www.uneval.org/