Final Evaluation Report: Objective 3 of the GFATM Round 4 addressing provision of treatment, care and support to people living with HIV/AIDS (PLHIV)

United Nations Development Programme (UNDP) Tajikistan

7-7-2010

DRAFT REPORT

Submitted by Sara Van Rompaey and Mansour Dodarbekov

- Background and purpose

Background

Objectives of the Final Evaluation

Evaluation of Objective 3, to ‘Scale up the access of people living with HIV/AIDS to effective treatment’ of the GFATM Round 4 grant on “Reducing the Burden of the HIV/AIDS in Tajikistan”, addressing provision of treatment, care and support to people living with HIV/AIDS (PLWH) will be a component of the combined final evaluation of the Round 4 GFATM grant

Main objective

- Measure the effectiveness and efficiency of objective 3 of GATM Round 4 HIV

- access to treatment, care and support for PLWH,  including ARV

- PMTCT services

- care for people with HIV

- capacity building of health care providers

- social workers

- NGOs working with PWLH

- Assess implementation and achievement of results against the project targets and indicators

- Define lessons learnt and produce plausible recommendations on project management practices for the consolidated Round 6/8 grant (started in 2009)

In compliance with the project document the final evaluation of Objective 3 should assess:

- Project concept and design, reviewing problems/issues addressed by the project and the project strategy, considering appropriateness of the objectives, planned outputs, activities and inputs as compared to cost-effective alternatives.

- Implementation of the project in terms of progress towards project results, quality and timeliness of inputs and efficiency and effectiveness of activities carried out.

- Project outputs, outcomes and impacts achieved by the project as well as the likely sustainability of project results. This should encompass an assessment of the achievement of the outcomes and the contribution to attaining the overall objective of the project, inclusion of relevant stakeholders.

Description of main activities of objective 3 of GTAM Round 4

Workshops on ARVT and monitoring will be conducted for health care professionals. Clinical guidelines on ARVT for health care professionals will be developed and published. Two sets of CD-4 counting laboratory equipment and reagents for 5 years will be procured through proposal. Annual national conference for sharing experience in the implementation of HIV/AIDS treatment will be implemented from the 2 year. NGOs and CBOs representatives will be trained in supporting PLHIVA psychologically and in helping them to comply with the treatment. Procurement of antiretrovirals, other drugs and methadone will be implemented. The government will ensure the availability of the other essential drugs to provide treatment of opportunistic infections.

- Scope, methodology and limitations

Scope of Evaluation

1) ARV treatment, care and support to PLWHIV under round 4 GFATM grant and, where appropriate, in collaboration with other development partners that have contributed to the achievement of the outcomes. The evaluation is expected to generate lessons learnt, findings, conclusions and recommendations and cover the following specific issues: SWOT analysis of the national management arrangements and working modalities between key stakeholders for treatment, care and support for PLWH

Evaluate national management arrangements existing in the country for provision of ARV therapy and treatment of opportunistic infections and conduct Strength, Weaknesses, Opportunities and Threats (SWOT) analysis of working modalities between UNDP and AIDS centers, AIDS centers and health care provider and AIDS centers and NGOs/CBOs providing support to PLWH through conducting site-visits, observations, and individual interview with the health care providers, people affected by disease, NGOs representing PLWH, social workers and other stakeholders. 

2) Review the quality and efficacy of ARV therapy and its compliance to the national guidelines and international quality standards, through review of patient records and treatment protocols. Evaluation of ARV efficacy should be focused on the following direction:

- Access to ARV treatment for eligible patients;
- Accessibility of ARV drugs;
- Accessibility and quality of lab diagnostic;
- Assess main difficulties for ARV introduction and implementation in the country and provide recommendations for improvement/amendment given the prevailing circumstances. 
- Evaluate effectiveness of trainings and capacity building activities targeting to ARV providers organized by UNDP and AIDS centers.
- Assess capacities of responsible health care providers for ARV therapy and management of opportunistic infections 

3) Review and evaluate national arrangements for prevention of mother-to-child transmission for HIV-positive pregnant women and newborns, achieved results within the period of programme implementation as opposed to target set and provide recommendations for ongoing GFATM-funded programme for support of PMTCT –related activities. Review and assess efficiency of VCT practices targeting pregnant women within the framework of PMTCT program implementation. 

4) Review and evaluate programs targeting PLWH to improve adherence to treatment and provide social care and support, including review of small grant provided to NGOs involved in PLWH care and support, results achieved and recommendations for further expansion of involvement of communities/families of PLWH to support and care.

5) Review of partnership and sectoral coordination system

- Review of sectoral coordination system and mechanisms between stakeholders exists in the country level and its effectiveness and contribution to better promotion of ARV treatment and creating positive attitude (environment) of community towards PLWHIV. 

- Analyze established partnerships of UNDP with governmental structures, health care sectors and providers, civil society and people affected by disease and other clusters to coordinate, cooperate and enhance implementation of treatment, care and support programme and provide recommendations for possible expansion of partnership with relevant stakeholders in and outside the country for the purpose of ongoing program.

Methodology

Following methods were used during the final evaluation:

Desk review of following documents:

- Projet document GFATM round 4 and GFATM round 4 grant proposal

- Budget plan round 4

- Performance framework GFATM round 4 indicators

- UNDP Midyear semi-annual report 2009 GFATM round 4

- Global fund performance report round 4

- Final Outcome evaluation report GFATM round 4, 14 January 2007

- GFATM round 6 proposal

- Monitoring and Evaluation Plan gfatm round 6

- UNDP Monitoring and evaluation round 6 year 1 and 2

- UNDP Annual project report 2007 GFATM round 4 and 6

- annual report 2008 “Reducing the Burden of  HIV/AIDS in Tajikistan”  TAJ-404-G03-H (ATLAS Project ID 00041567);“Support to National AIDS  Response to Scale up   HIV/AIDS   Prevention and Care Services in Tajikistan” TAJ-607-G05-H (ATLAS Project ID 00056191)

- Mid-term evaluation round 6 by external consultants

- Operational research on ARV treatment effectiveness by invited international consultant. March 2008

- HIV/AIDS TREATMENT AND CARE Clinical protocols for the WHO European Region 2007

- National training modules on PMTCT, ART and multidisciplinary approach

- Strategic plan of response to the epidemic of HIV in the Republic of Tajikistan, 2006-2010, Dushanbe 2006

- Ungass report march 2009

- Health Sector Fiduciary Capacity Assessment ReporT, World Bank June 12, 2008

- National surveys of republican AIDS centre

Meetings with representatives of:

- UNDP PIU

- UNICEF

- MoH department of Safe Motherhood and Family Planning

Field visits and in-depth interviews with responsible staff of:

- National AIDS Centre

- Hospital of infectious diseases of Dushanbe and Isfarafstan

- regional AIDS centre of Kurgan-tyube and Kulyab

- regional AIDS centre of Khujand

- inter-district AIDS centre of Isfarafstan

- Reproductive Health Care centre number 3 in Dushanbe

- Maternity House number 3 in Dushanbe and

- NGO Guli surkh

- Medical department of prison number 4 in Dushanbe

Focus group discussions with PLHIV of:

- Republican AIDS centre

- Regional AIDS centres of Kurgan-Tyube and Kulyab

- PLHIV association Guli Surkh

Limitations

The evaluator team consisted of an external international consultant, and a national consultant who is the head of the dispensary department and the key responsible in implementing training activities and HIV care nationally. This conflict of interest presented an obstacle to a neutral and objective approach of the evaluation.

- Findings

- People with advanced HIV infection receiving ART combination therapy

| Coverage indicator GFATM round 4 |  | Baseline (2004) | Year 1 achieved | Year 2 achieved | Year 3 achieved | Year 4 achieved | Year 5 achieved | Year 5 target |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Number of people with advanced HIV infection receiving ART combination therapy | 0 | 0 | 73 | pending | 231 | 424 | 500 |

According the national AIDS centre, on the 1st January 2010, 424 patients are recorded as having initiated ART. 310 are men, 114 women and 10 of them are children.

AREAS OF PROGRESS:

- General Coverage

No ART was available before the start of round four GFATM.

According estimations made by WHO, 1300 people in Tajikistan needed ARV therapy in 2008. This means that by the end of 2009, about 33% of people in need for ART have initiated treatment.

As of December 31, 2009 1,853 cases of HIV infection were officially registered in the country.

Thanks to all mechanisms put in place during GFATM round 4, the targets set for scaling-up ART in GFATM round 8 are within reach:

| Indicator GFATM round 8 |  | 31.Dec.09 target | 31.Mar.10 target | 30.Jun.10 target | 30.Sep.10 target | 31.Dec.10 target |
| --- | --- | --- | --- | --- | --- | --- |
|  | Number and percentage of people with advance HIV infection receiving ARVT |  | N: 500 D: 1,020 P: 49% | N: 550 D: 1,019 P: 54% | N: 591 D: 1,019 P: 58% | N: 620 D: 1,016 P: 61% |

- Geographical distribution

Graph 1: Breakdown of HIV +, covered by ARV Therapy, as of location (N=424)

ART coverage respects equity towards PLHIV living in different oblasts.

- Coverage of Age groups

Graph 2: Breakdown of HIV +, covered by ARV Therapy, as of age profile (N=424)

Coverage of the ART follows national AIDS trends: HIV prevalence is highest among young people less than 29 years old and it takes on average about 3 to 7 years to become eligible to ART

- Coverage of Risk groups

235 patients who initiated HAART were intravenous drug users ( 56%) and 188 were not (44%). 23 PLHIV received ARV therapy in prison. There are no data about ART in sex workers and MSM.

Coverage of the ART programme corresponds to the relative size of the risk group of IDUs.

- Outcomes in adults receiving ART

Percentages of treatment interruption and PLHIV who left the country are relatively low.

Graph 3: Outcomes of ART

- Outcomes in Children receiving ART

13 children have initiated ART. Only 1 child died (8%) because diagnosis was made in a final stage of the disease at the age of 18 months. Death occurred soon after treatment initiation.

Most children were 3 to 4 years old at ART initiation. The pediatrician of the Republican health centre initiated all children on ART. Treatment was continued by the service staff of regional AIDS centres for the children living in Soghd and GBAO oblasts.

Children on ART 2007 – 1/4/2010

| № | districts | 2007 |  | 2009 |  | First 3 months 2010 |  | Total |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | М | F | М | F | M | F | М | F | all |
| 1 | Dushanbe | 1 | 1 | 2 | 1 |  | 1 | 3 | 4 | 7 |
| 2 | Soghd |  | 1 | 1 | - |  |  | 1 | 1 | 2 |
| 3 | GBAO | 1 | 1 | 1 | - |  |  | 2 | 1 | 3 |
| 4 | RRS |  |  |  |  |  | 1 |  |  | 1 |
| total |  | 2 | 3 | 4 | 1 |  | 2 | 3 | 4 | 13 |

- Introduction of latest eligibility criteria

Successful implementation of immunological eligibility criteria of latest WHO guidelines (2006), with CD4 cell cut-off is lower than 350 kl/mcl.

- Availability and use of ART regimens

Availability of antiretroviral medicines is generally good and no shortages have been reported.

For adults, preferred regimens for treatment of HIV/HBV (eg Tenofovir and Tenofovir/Emitrabicine combination) and HIV/TB co-infected are available.

No lethal cases caused by side-effects have been reported in Tajikistan so far. Possible side-effects are well monitored with laboratory examinations and clinically. Social workers have been trained to recognize side-effects.

ROOM FOR IMPROVEMENT

- Mortality in adults

Round 8 impact indicator: % of adults and children with HIV known to be on treatment 12 months after initiation of ART:

Year 1              Year 2    Year 3    Year 4    Year 5

Target 70%        75%      80%        80%        80%

Causes of mortality

As ART treatment is still relatively new in the country, most HIV-related deaths occur in the first 3-6 months of treatment. This early death rate showed the late presentation of the patients to the clinic with overwhelming opportunistic infections or early immune reconstitution syndrome induction.

In the next 5 years, more cases of ‘late mortality’ are to be expected, caused by suboptimal adherence, treatment failure and late side-effects of lactic acidosis. Viral load measurements help to identify early treatment failure.

Tuberculosis (held responsible in about 50% of lethal cases)

Identified obstacles:

- Vertical TB and HIV services with little interaction on management of co-infection.

- Poor diagnostic capacities of extrapulmonary and pulmonary smear-negative pulmonary TB

- Suboptimal efforts on preventive measures to lower TB incidence in PLHIV

End-stage hepatitis: (25% - 40 %)

Almost 40% of the PLHIV mortality results from liver cirrhosis.  HCV prevalence among IDU is reported as 61.3% . The national AIDS centre recorded a Hepatitis C prevalence of 30 % amongst IDU living with HIV.

Identified obstacles:

- Poor access of PLHIV to Hepatitis screening.

- Hepatitis treatment is not available and neither affordable: Test phase of a treatment programme is scheduled for the end of July 2010. The cost to treat one patient is estimated at 20 000 $.

Kaposi sarcoma:

Identified obstacles:

- Poor access to treatment. Treatment in Oncology centre is unaffordable to the vast majority of PLHIV

- Poor approach of health service providers of oncology centre towards PLHIV

Late presentation and bad adherence

Late presentation is often recorded in labour migrants who travel back to Tajikistan because of health problems, in a late stage of the HIV infection

Bad adherence is often reported in active IDUs, who represent 60% of PLHIV

Identified obstacles:

- Stigma

- No availability of substance replacement therapy. Provision of substitution therapy is now in a test phase

- No plans for integration of provision of ART and substitution in the future

- No availability of viral load measurements to detect adherence problems in an early stage

Overdose?

Other OI’s?

Opportunistic infections, held responsible in other rich or resource-limited countries for an important number of deaths, as Pneumocystis jiroveci pneumonia, cerebral toxoplasmosis and cryptococcal meningitis were never recorded in Tajikistan. It is probable that some diagnosis are missed.

Identified obstacles:

- ART prescribers don’t possess necessary tools to diagnose and to manage these opportunistic infections. As of today, they are still in the initial learning period. In industrialised countries, the positive impact of sites’ and physicians’ experience on HIV-infected patients’ outcomes has been reported for a long time.

- vertical, fragmented health system with poor access for PLHIV to general health care services due to stigma and discrimination

(Indicator round 8: % of health professionals who demonstrate readiness to provide health services to PLHIV and Vulnerable Population Groups at the same quality level and with the

same attitude as to all other people)

Side-effects?

Lactic acidosis is a lethal long-term side-effect of ART, which presents insidious and non-specific signs and symptoms which has never been diagnosed in Tajikistan. No laboratory tests are available to measure lactic acid levels. In the next few years, there should be maximal awareness for this complication.

Use and availability of ART regimens

For children, only one regimen is available in oral solution: Zidovudine – Lamivudine – Nevirapine. However, in HIV-infected infants who were exposed to NVP during PMTCT, evidence supports the use of PI-regimens (Lopinavir-ritonavir) if ART is started before the age of 1 year. Abacavir and Stavudine in oral solution form are suitable options to replace Zidovudine in case of severe anemia.

For second line regimens, alternative NRTIs are missing. Didanosine and Abacavir should be made available in the country.

22% of patients are on a first-line treatment including Stavudine. WHO recommends to give priority to Zidovudine because of its association with fewer and better manageable side-effects. The national AIDS centre has included this recommendation in its planning for future procurements and all patients taking Stavudine will be switched to Zidovudine when ran out of stock.

Some patients receive Liponavir/ritonavir (Kaletra) as a first-line regimen when no contra-indications for Efavirenz or Nevirapine as first-line treatment are present. All 12 patients who are receiving Liponavir/ritonavir, (3%) are not on a proper second-line treatment.

Three-drug regimens, comprising two NRTIs plus a boosted PI, are used for Prophylactic treatment of occupational exposure. WHO recommends in its latest guidelines  that a two-NRTI regimen is preferred (Zidovudine – Lamivudine) and that a three-drug regimen can be considered in situations where antiretroviral therapy resistance is known or suspected.

- Number of people receiving treatment for opportunistic infections

| Coverage indicator | Baseline (2004) | Year 1 achieved | Year 2 achieved | Year 3 achieved | Year 4 achieved | Year 5 achieved | Year 5 target |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Number of people receiving treatment for opportunistic infections | 0 | 0 | 49 | pending | 132 | 248 | 220 |  |

No treatment for severe opportunistic infections was available before the round four GFATM.

ROOM FOR IMPROVEMENT

Coverage and Estimated outcomes

The target of 220 patients at who receive treatment for opportunistic infections is low. Any registered PLHIV, whether or not receiving ART should be screened on a routinely basis for opportunistic infections and be treated accordingly. Eligibility criterion for Cotrimoxazole prphylaxis should be checked for at every occasion.

The indicator should be reformulated as: number of PLHIV “seen for care” (seen at least once in the previous 12 months)

Monitoring and evaluation of the cohort of PLHIV who have not yet initiated ART is poor.

1853 PLHIV have been detected since the start of the programme.

According the data of the national AIDS centre, 15.9% of people with a confirmed test result (278 PLHIV) never registered at the HIV care programme.

1575 PLHIV who registered at the AIDS centres have not yet initiated ART. The Global Fund evaluation report reported only 248 patients who were receiving treatment for opportunistic infections. In cohorts of HIV care programs in other countries, the number of PLHIV not yet eligible is higher than the number of PLHIV receiving ART.

The 296 detected patients did probably not register at the dispensary because they have to overcome different hurdles in the fragmentized VCT process, without assurance of qualified post test counseling.

National data of mortality of PLHIV who are not receiving ART are lacking.

In  Khujand oblast only, 488 patients were detected from the start of the programme. Of those, 125 patients have initiated ART. (26%). Of all registered deaths, 32 patients died while on ART, and 68 patients died before ART initiation.

Graph 4: enrolment of detected PLHIV

Analyses performed in South-Africa also found that most early in-programme deaths occurred among patients with advanced immunodeficiency who had not yet initiated ART. Researchers conclude that programme evaluations using on-treatment analyzes may have greatly underestimated early in-programme mortality. Actions to retain these vulnerable patients not yet on ART, like minimising unnecessary in-programme delays in treatment initiation and maybe defaulter tracing, should be initiated by the health structure.

Identified obstacles:

- Fragmentized VCT process

- Poor clinical follow-up by routine appointments on a two-yearly basis (for CD4 count measurements)

- Poor diagnostic and management capacity of opportunistic infections with many referrals to other vertical services for diagnosis and/or treatment

- Necessity of visits to multiple service providers who have little to no communication amongst themselves

- Stigma towards vulnerable groups in the medical services providing OI diagnosis and/or treatment

- Repeated shortages in medicines for opportunistic infections

- Poor monitoring

- Training of health care deliverers

| Coverage indicator |  | Baseline (2004) | Year 1 achieved | Year 2 achieved | Year 3 achieved | Year 4 achieved | Year 5 achieved | Year 5 target |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3 | Number of service deliverers trained (package HAART, PMTCT, PEP, treatment of opportunistic infections and palliative care) | 4 | 93 | 173 | pending | 357 | 357 | 357 |

Most of the physicians trained on ART under GFATM support were not active in ART although some physicians received training abroad funded by other international donors as WHO, Soros Foundation and Central Asia AIDS Project (CAAP), funded by the World Bank and DFID.

Generally, service staff from all AIDS centres received at least 3 days of ART training organized by the republican AIDS centre. The national supervisory team performs in-service training on a quarterly or yearly basis, depending on the location. Supervision of the AIDS centres on district level is performed by the supervisory team of the oblast AIDS centres, at times organized as joint visits with supervisors of national level.

ART prescribers can call the head of dispensary at any time by phone for specific advice upon complex cases in order take a joint therapeutic decision. Complex cases can physically be referred to national level for expert advice.

AREAS OF PROGRESS

- Training of multidisciplinary teams of different AIDS centres. The 5-day course on multidisciplinary approach of HIV care allows a good introduction on all aspects of care for PLHIV receiving ART

- Trained service deliverers in Reproductive Health care centres and Maternity Houses in 22 districts. The 3-day course on PMTCT treats all components of the programme in a well-balanced way.

- Doctors and social workers are trained on aspects of providing psychological support to HIV patients.

- Service staff was sufficiently aware about the importance of good adherence and some of them were able to mention some tools to monitor adherence systematically.

- Training of Post-exposure Prophylaxis for health staff with distribution of a clear manual

ROOM FOR IMPROVEMENT

- Some ART prescribers in AIDS centres have not followed any training on HIV/AIDS.

- Service staff of ART dispensaries in prison did not receive ART training

- Training on PMTCT: The number of health staff in antenatal and reproductive health facilities who received training on pre-test counseling of pregnant women and PMTCT interventions is still low.

- Training on pediatric HIV care: Only 3 pediatricians in the country received training on care and treatment of exposed and infected children, in Uzbekistan, funded by Central Asia AIDS Project (CAAP). Only one trained pediatrician is active in the field of pediatric HIV care and works at the republican AIDS centre. ART prescribers in the oblast did not receive training on pediatric HIV care.

- Training of ART prescribers: The 3-day course on ART is too short and superficial to provide prescribers all the necessary tools for autonomous clinical management of PLHIV, particularly at regional/provincial and district levelsIssues on treatment failure, second line therapy and diagnosis and treatment of opportunistic infections were not well covered. ART prescribers miss clinical experience. Poor decision making skills: ART prescribers in the regions and districts are highly dependent from interventions and advice from the head of dispensary department.

- The quality of monitoring varied among the different sites. The head of the dispensary department, who received training abroad on the Drug Management Information System, stated that this system is not sufficiently user-friendly in order to implement it in Tajikistan on a large scale.

- Poor knowledge on HIV and ART in health staff of general health services.

Activities planned for the round 8 GATM partially respond to the identified needs of capacity building by integrating HIV and ARV training in the general curriculums:

Activity 4.1.5: Conduct five-day annual training on HIV and ARV treatment for 30 professors of postgraduate courses and 30 participants from the Medical University.

Activity 4.1.6: Develop curriculum and educational module for the Post-graduate Institute and update curriculum for the Medical University on ARV treatment.

Activity 4.1.7: Develop and print education manual on HIV and ARV therapy for the Medical University, Post-graduate Medical Institute and Medical College.

Activity 4.1.8: Establish, repair and fully equip a National HIV Training Center for medical specialists. Training of ARV providers on M&E and DMIS.

Activity 4.5.2: Develop capacities of national, regional and district health department to plan, implement, and monitor and evaluate mass interventions.

- Health facilities offering HIV care

| Coverage indicator | Baseline (2004) | Year 1 achieved | Year 2 achieved | Year 3 achieved | Year 4 achieved | Year 5 achieved | Year 5 target |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Number of health facilities capable of providing advanced interventions for prevention and medical treatment for HIV | 0 | 20 (target 5) |  |  |  |  |  |  |

Patients can freely choose upon the AIDS centre they want to receive care from.

Areas of progress:

- The national hospital for infectious diseases reserved a ward of 20 beds for treatment of complex cases of PLHIV with good conditions to ensure confidentiality.

- 21 AIDS centres are established throughout the country, although some AIDS centres at district level are not yet fully operational.

- Efforts to decentralize HIV care to district level by inter-district AIDS centres and integration of HIV care in the general district hospital for the hard-to-reach districts.

- CD4 count measurements are available in the 4 oblasts.

Room for improvement:

- For children living with HIV, no separate ward is available in the country.

- Most AIDS centres are not adapted to outpatient clinical care: they suffer from lack of staff and appropriate equipment, do not have a waiting room and neither child-friendly areas.

- The setting of the district hospital of infectious diseases did not allow for clinical care with respect of privacy and confidentiality.

- Insufficient funding does not permit rehabilitation of existing buildings or construction of new ones.

- PMTCT

| Coverage indicator GFATM round 4 | Baseline (2004) | Year 1 achieved | Year 2 achieved | Year 3 achieved | Year 4 achieved | Year 5 achieved | Year 5 target |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Percentage of HIV-infected pregnant women receiving ARV prophylaxis | 0 % | 66% | 100 % (4/4) | Pending | 71% (35/49) | ? | 100 % |  |

The indicator of GF has not been used appropriately in the monitoring of Round 4: To measure the real coverage of the programme, we should monitor the percentage of all estimated pregnant HIV + women who received prophylaxis, and not the percentage of known cases of HIV positive pregnant women.

The indicators proposed for monitoring of PMTCT coverage in Round 8 are more appropriate:

| Indicator GFATM round 8: Number and percentage of pregnant women receiving HIV tests, results and post-testing counseling | 31.Dec.09 | 31.Mar. 10 | 30.Jun. 10 | 30.Sep.10 | 31.Dec.10 |
| --- | --- | --- | --- | --- | --- |
| Target | N: 104,000 D: 140,541 P: 74% |  | N: 128,000 D: 139,130 P: 92% |  | N: 133,000 D: 140,000 P: 95% |
| result | N: 76,297 D: 140,540 P: 54% |  |  |  |  |

UNICEF set its target of VCT coverage in pregnant women only at 80% because screening all HIV-infected women is not regarded as cost-effective: Due to the specific dynamics of the HIV/AIDS epidemic in the general populations and risk groups in Tajikistan, prevalence in pregnant women is very low. (estimated as 0.0009%) The goal is to cover all pregnant women who are household keepers and wives of labour migrants.

| Indicator GFTAM round 8: HIV-positive pregnant women receiving a complete course of ARV prophylaxis to reduce MTCT in accordance with nationally approved treatment protocol | 31.Dec.09 | 31.Mar.10 | 30.Jun.10 | 30.Sep.10 | 31.Dec.10 |
| --- | --- | --- | --- | --- | --- |
| target |  | N: 25 D: 260 P: 10% |  |  | N: 60 D: 261 P: 23% |
| result |  |  |  |  |  |

The target of prophylactic treatment coverage of pregnant women living with HIV of Round 8 is set too low in order to have considerable impact on vertical transmission.

- HIV testing of pregnant women

In Reproductive Health Centres without rapid test possibilities, pregnant women are referred to the closest HIV centre for testing. In case of a positive rapid test result, a blood sample is sent to the national laboratory for confirmation by Western blotting.

260 pregnant women are estimated to live with HIV in the country at any given time.

In one regional AIDS centre, 12 000 pregnant women were tested in 2009. 130 women were tested positively with a rapid test, but in only 7 women, confirmation was obtained by Western blotting.

120 HIV positive pregnant women were detected in the country between 2001 and September 2009.

Graph 4: Number of detected HIV + pregnant women (N-100)

The majority of HIV positive pregnant women were sexual partners of labour migrants and a smaller number were sexual partners of IDUs.

Graph 5: Breakdown of HIV + pregnant women as of risk category

There is a good geographical distribution in the detection rates of HIV positive pregnant women

Graph 6: Breakdown of HIV + pregnant women as of  location profile (N-100)

In 2008 and 2009 together, 367532 women were registered at reproductive health care centres, 116297 (32 %) women were tested for HIV and 57 (0.0005% prevalence) women had a confirmed positive test result, which shows prevalence comparable with the estimated national HIV prevalence of women > 25 years in the country.

From the 100 pregnant women who were tested positive on the first screening test before September 2009, only 69 cases were confirmed by a second test before delivery.

ROOM FOR IMPROVEMENT

- Low level of public awareness on HIV/AIDS aspects

- Inefficient testing procedures

- Discrimination of HIV positive pregnant women by service staff in reproductive health care centres and maternity houses

- Low number of doctors in antenatal and reproductive health facilities who received training on pre-test counseling of pregnant women

- Weak referral system between AIDS centres, reproductive health care centres and maternity houses

- Low level of access for Pre-test counseling for pregnant women living in remote areas (according the MoH department of safe motherhood and family planning, up to 70% of women in remote areas deliver at home)

LATEST PROGRESS

- Since 2009, gynaecologists in reproductive health care centres and maternities in 22 districts have been trained on VCT and PMTCT interventions and rapid tests are available in the centres. Women are tested for HIV with rapid tests during the first trimester and the third trimester. HIV status is confirmed in the AIDS centres.

- This strategy is now implemented in all districts of Dushanbe.

- Good availability of rapid tests

- It has made case detection of HIV positive pregnant women scale-up in the year 2010. E.g. in Reproductive Health centre number 3 of Dushanbe a HIV testing coverage of 96% was reached in women who come for their first ante-natal consultation.

- The PMTCT training and direct involvement of service deliverers in Reproductive Health Care Centres and Maternity houses raises awareness amongst health staff and reduces discrimination against HIV positive women

- In Dushanbe, a pilot phase to test a strategy of ‘package of guaranteed services’ is run, to reimburse the cost of ante-natal services at the 5th antenatal visit.

- Within a short delay, PMTCT guidelines will be published and distributed with a clear policy on integration in reproductive health care

- The PMTCT working group is developing a consistent monitoring system.

- Coverage of PMTCT interventions

Graph 7: Total number of HIV + women detected during pregnancy  and receiving ARVP

Only 55 cases received any form of ARV prophylaxis. 28 women delivered by caesarian section. The majority of exposed children were breastfed and a minority received artificial feeding.

Reasons for poor coverage of PMTCT interventions are the following:

- Lack of social workers to provide social services

- Inappropriate VCT procedures with late confirmation of HIV test result, inducing a missed opportunity to prevent vertical transmission

- Discrimination of HIV positive pregnant women by service staff in reproductive health care centres and maternity houses

- Low number of doctors who received training on PMTCT interventions

- Poor referral system between AIDS centres, reproductive health care centres and maternity houses

- Unavailability of formula feeding preparations

- Lack of financial means for HIV positive women to buy formula feeding preparations

- Follow-up of HIV exposed children

Consistent data are collected nationally to evaluate outcomes of HIV-exposed children.

Graph 8: Number of children delivered by HIV + women (N81)

Graph 9: Breakdown of children delivered by HIV + women, as of status profile (N81)

By only considering the cases with known infection status, 42% of exposed children is HIV infected, an infection rate equal to exposed breastfed children, without any PMTCT interventions. When considering all deceased children as HIV infected, the infection rate is 54%. When considering the 41 cases under care and all deceased children as not infected, the infection rate of 17% (13/ 76), is still considerably high.

Graph 10: Analysis of PMTCT interventions in HIV-infected children

The most important risk factor for vertical HIV transmission is the lack of ARV prophylaxis.

Breast feeding plays the second greatest role, followed by natural delivery.

Mortality of exposed children

Eight exposed children died cumulatively, which corresponds to 10% of all registered exposed children. HIV infection was held responsible in 2 children. In most other children, HIV infection has not been confirmed.

Roughly 33% of untreated HIV-infected infants in the developing world die during the first year of life, and >50% die by the age of 2 years. As stated above, HIV infection rate of about 40% is recorded in HIV-exposed children in Tajikistan. By making the projections of 33% mortality for the 81 exposed children, we would expect to lose 12 children by lack of early diagnosis.

Graph 11: Possible factors led to mortality of children, delivered by HIV + pregnant women  (N-8)

Graph 11: Breakdown of deceased children, as of age profile (N-8)

Graph 13: Reasons for exposed children’s mortality

Out of the total number of 81 exposed children, 61 did not receive cotrimoxazole prophylaxis, due to shortages of this medicine in its suspension form. Cotrimoxazole prophylaxis might have prevented some of the reported severe bacterial infections.

According WHO guidelines, all children younger than one year with confirmed HIV infection should receive ART in order to reduce mortality. The European guidelines recommend to use a virological test (like PCR) after birth and at the age of 6 weeks to make an early diagnosis of HIV infection.

As virological testing is still lacking in the country, for the time being, diagnosis should be made on a clinical basis, according the WHO guidelines for resource-limited countries : Infants and children aged under 18 months where access to virological testing is not yet available but where there are symptoms suggestive of HIV infection, accompanied by positive HIV antibody testing, a presumptive clinical diagnosis of severe HIV infection may be necessary in order to permit decision-making on the need for the initiation of potentially life-saving ART

Causes of high transmission rate and high mortality are the following:

- Lack of PCR testing for early laboratory diagnosis of HIV infection.

- Poor coverage of PMTCT interventions in detected HIV positive pregnant women

- Poor capacity to make an early diagnosis of HIV infection on a clinical basis in the  oblast and district levels

- Poor diagnostic and management capacity of opportunistic infections in HIV exposed children in oblast and district levels

- Poor capacity in prescribing ART in children in oblast and district levels

- Appointments are too much spaced in time to allow good clinical follow-up of exposed children in oblast and district levels

- Lack of Cotrimoxazole suspension to prevent opportunistic infections

- Lack of social workers to provide social services

Improving the coverage of PMTCT and making PCR available and systematic prophylactic treatment in all HIV exposed children, would have the greatest impact in reducing mortality in this vulnerable group.

- Health facilities offering PMTCT

| Coverage indicator |  | Baseline (2004) | Year 1 achieved | Year 2 achieved | Year 3 achieved | Year 4 achieved | Year 5 achieved | Year 5 target |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 6. | Number of health facilities offering a minimum package of PMTCT | 0 | 10 (target 5) |  |  |  |  |  |

As of today, 22 facilities in the country are offering PMTCT package, with complete coverage of Dushanbe, but small coverage in the provinces. The facilities possess the necessary tools, equipment and infrastructure to perform VCT and provide Antiretroviral prophylaxis during labour and delivery.

Protective material for safe deliveries is missing in the maternity houses

- Networks/partnership

| Coverage indicator |  | Baseline (2004) | Year 1 achieved | Year 2 achieved | Year 3 achieved | Year 4 achieved | Year 5 achieved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 7. | Number of networks/partnerships involved in scaling up the access of people living with HIV/AIDS to effective treatment | 0 | 30 (target 15) |  |  |  |  |

The GFATM R8 is the only source of expanding the PMTCT programme, improving the system of monitoring and evaluation and providing treatment for ARV therapy and opportunistic infections.

The fact that HIV care and ART are only implemented by State Health Services and not by the private sector (who is not well developed in Tajikistan) is an important strength of the programme. It avoids fragmentation and inequalities in the provision of care.

UNICEF is the technical supporter of policy development and implementation of PMTCT interventions.

The NGO’s Gulit Surkh and SPIN+ deal with defaulter tracing, accompaniment of patients to overcome the barrier to come to the dispensary, provide food support and have focal points in the community. In Dushanbe, a lawyer, a psychologist, a gynaecologist and a pulmonologist dedicate 20% of their time to patients who are referred from Gulit Surkh.

Central Asia AIDS Project (CAAP), funded by the World Bank and DFID (2005-2009); is designed to strengthen the region’s capacity to fight HIV/AIDS by improving regional

coordination, policy development, and capacity strengthening

The World Food Programme provides nutrition packages with oil, salt, floor and chick peas for every patient on ART, that are distributed by NGO’s. There are no defined criteria to stop nutrition support, but criteria on food support initiation are strict: only patients who are treated with ART for at least 3 months can be subscribed to the programme.

It is noted that patients groups with higher mortality rates (before ART initiation and within the first 3 months of ART), are not receiving any form of food support.

The Central Asian Program on AIDS Control in Vulnerable Populations (CAPACITY

Project) funded by USAID (2005-2009); aims to advocate the government to take steps in

the response to HIV/AIDS.

The Access Project sponsored by the Dutch Ministry of International Affairs and carried out by AIDS Foundation East-West (AFEW). AFEW’s Access strives to improve access to HIV and TB, treatment, care and support to IDUs, SWs, prisoners, communities of PLHIV and TB patients by increasing accessibility to and sustainability of preventive services and professional care.

- Adherence support

| Coverage indicator |  | Baseline (2004) | Year 1 achieved | Year 2 achieved | Year 3 achieved | Year 4 achieved | Year 5 achieved |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 8. | Number of NGO/CBOs staff trained to support the adherence of PLHIVA to treatment | 0 | 50 (target 60) |  |  |  |  |

Area of progress

- leaflets, on such aspects like: ART

- Multidisciplinary team approach of adherence and social problems

- Trained peer social workers attached to AIDS centres  increase access and adherence

- Pill count performed by dispensary nurse to monitor adherence during the first month after ART initiation is a practice applied in some regional centres

- Systematic phone calls to remind patients about medicines intake and dispensary appointments

- Pill boxes provided by NGO’s

- High satisfaction by individual and confidential approach from Doctors in the AIDS centres

- High satisfaction on support provided by PIN+ and Guli Surkh.

- PLHIV associations have regular meetings to give peer support

- seminars for PLHIV organized by “Guli Surkh” organised which covered HIV issues, including the importance of adherence to ARV therapy with high satisfaction rates of patients.

- home visits for defaulters and occasionally for delivering medicines or food support

- Phone call system by social workers according with preference of the patients

- pilot project on substitution therapy, in Dushanbe

Room for improvement

- most patients living outside of Dushanbe prefer the social assistants not to visit their homes, because of stigma

- Some patients preferred the social assistants to be peers

- identified need of patients for a professional psychologist at AIDS centre level.

- poor access to substitution therapy

- substitution therapy based in narcology centre, associated with psychiatric diseases, an association which is not advised by WHO.

- Patients who are adherent and clinically stable on ART would like to have quarterly instead of monthly appointments at the AIDS centre, to avoid stigma to a maximal degree and to have less interference with their daily life activities.

- need for more systematic adherence monitoring system

More social aspects:

According to PLHIV associations, PLHIV are still afraid to defend their rights because this would imply disclosure to the community.

Reports of discrimination and refusal of care have in reproductive health centres and maternity houses, TB dispensaries and other health services.

Patients complained about the practice of employers in Tajikistan, and universities and employers abroad to ask for a medical certificate that states seronegativity. This certificate can only be obtained at oblast level or nationally and is not free of charge. PLHIV are fired when their status is discovered. Many PLHIV are unemployed as a result of that.

Service deliverers in hospitals reported the obligation of HIV screening 3 times a year.

Gender: In one district AIDS centre, service staff tested a migrant worker and his wife and reported the result of both tests to the husband, leaving his wife ignorant about her serostatus. They are eligible to ART, but the husband denies treatment for himself and his wife. Similar cases have been reported by staff of Guli Surkh.

Recommendations

- Improve prevention, diagnosis and treatment of TB/HIV co-infection

Round 8 proposes to improve the referral system between TB and AIDS centres.

From a clinical point of view, it is better to provide diagnosis and treatment of both infections in the same site, with follow-up by the same clinician.

In one regional AIDS centre, inserting a TB specialist in the AIDS centre seemed beneficial for adherence of the patient and quality of clinical monitoring. Another option would be to insert ART prescribers in TB dispensaries.

The threshold for making the diagnosis of smear-negative and extra pulmonary TB should be kept very low in HIV-infected patients.

Isoniazid Preventive Therapy (IPT)is only implemented for people who have household contacts with TB. It is not implemented in the prisons of Tajikistan.

IPT can safely be given to people living with HIV without TB disease, reducing the risk of developing TB by 33–67% for up to 48 months.

It is currently recommended for all people living with HIV in areas with a prevalence of latent TB infection >30%, and for all people living with HIV with documented latent TB infection or exposure to an infectious TB case, regardless of where they live. More recently, evidence has shown that the combined use of Isoniazid preventive therapy and antiretroviral therapy among people living with HIV significantly reduces the incidence of TB; and the use of IPT in patients who have successfully completed a course of TB therapy has been shown to markedly reduce the risk of subsequent TB cases.

In April 2008, the HIV Department of the

WHO clearly stated that it is the responsibility of National Aids Programmes to deliver this package to PLHIV within the context of general health systems.

Intensified Case Finding (ICF), Isoniazid Preventive Therapy (IPT) and TB Infection Control (IC) for people living with HIV

The coordinating body for TB-HIV activities should:

• Carry out joint TB-HIV planning

• Conduct monitoring and evaluation

Reduce the burden of TB in people living with HIV/AIDS

• Establish intensified tuberculosis case-finding

• Study the possibility of introducing Isoniazid preventive therapy for PLHIV and develop national policies

• Ensure tuberculosis infection control in health care and congregate settings

- Provide Opiate Substitution Therapy with emphasis on DOT in conjunction with ART and provision in prisons

The introduction of low threshold OST was already planned in Round 4 and today is only in a test phase.

OST has been identified as one of the most effective treatment options for opiate dependence. Internationally endorsed, OST can decrease the high cost of opiate dependence to individuals, their families and society in general by reducing heroin use, associated deaths, HIV risk behaviours, and criminal activity.

WHO recommends that at least 60% of IDUs have access to drug dependence treatment and harm-reduction programmes in order to have an impact on the epidemic among this group.

Where substitution therapy is available, consideration should be given to offering HIV/AIDS medical care and providing ART at the same site from which drug substitution therapy is provided.

There is evidence that DOT is an effective strategy in the provision of ART with treatment for substance dependence. Using DOT to provide ART in conjunction with methadone maintenance is recommended because it:

• results in significant numbers of patients achieving maximum viral suppression

• achieves higher levels of viral suppression than either standard care or treatment adherence support and

• minimizes the impact of HAART on the IDU’s daily routine.

There are several models for effectively combining HIV prevention, treatment and care with substance dependence treatment, including:

• a single site for both HIV/AIDS care and substance dependence treatment:

° on-site HIV/AIDS medical care in substance dependence treatment facilities or

° substance dependence treatment in HIV/AIDS services;

• separate HIV/AIDS and substance dependence treatment services in close proximity with good coordination and liaising, including referrals to other services; and

• primary care services for both drug dependence management and HIV/AIDS care through general practitioners or office-based practice.

IDUs are three times as likely not to receive HAART if they are not enrolled in such a programme

IDUs receiving stable care from experienced staff with adequate support can adhere to ART and have clinical outcomes equivalent to those of HIV patients who do not use drugs

In Tajikistan, drug dependence treatment will be offered in a separate centre, which implies the risk of bad monitoring and coordination of treatment, similarly to what is observed in the management of other co-pathologies. (TB/HIV, HIV/HCV, PMTCT)

As OST is still newly implemented in the country, it is a good opportunity to advocate and lobby for integrated care from the start, although integrated care is not mentioned in the national policy on OST.

According the national policy on OST, the Ministry of Justice as has the task to develop, together with MoH, agreements, memorandums of understanding and any other agreement of political aspect, to implement substitute therapy on the basis of prisons.

- Hepatitis diagnosis and treatment

In European countries, end-stage liver disease is the predominant cause of death in patients coinfected by HCV and HIV, as well as in hepatitis B virus (HBV)/HIV-coinfected patients.

Being the second cause of PLHIV in Tajikistan, non-availability of treatment of end-stage liver disease (ESLD) represents a considerable obstacle in mortality reduction in PLHIV. Due to the high burden of the disease and the high cost of treatment (HCV prevalence among IDU is 61.3% and a minority is HIV positive), assuring equity amongst HIV infected and HIV non-infected patients with ESLD represents an enormous challenge.

Experiences and conclusions from the pilot project of HIV/HCV infected patients in Dushanbe, should be used for lobbying and advocacy of scale-up of treatment coverage.

A general complaint of patients was the non-gratuity of diagnosis of hepatitis and laboratory tests for evaluation of severity of disease and the stigmatizing approach in the health services of hepatitis diagnosis. Strategies should be studied to take blood samples for Hepatitis screening and liver tests in the AIDS centre, to be sent to the laboratory.

- Chemotherapy for Kaposi’s sarcoma

This treatment is costly and refusal of care and discriminative approach of service deliverers in the oncology department have been reported.  Efforts should be made to improve this attitude (e.g. by training on HIV/AIDS aspects, psychosocial approach of PLHIV) and to make treatment of Kaposi’s sarcoma financially accessible to patients.

- Nutrition support

Review criteria of eligibility for food support. Patients who are taking ART since at least 6 weeks, show optimal adherence and good clinical evolution may be less in need than some patients prior to the start of HAART. Suggestions for criteria should be moderate and severe malnutrition, tuberculosis and other severe OI’s, economic difficulties and unemployment.

- PLHIV in care not receiving ART

More frequent consultations are required to monitor and treat opportunistic infections and other health needs and check eligibility status. The multidisciplinary team should focus maximally on this vulnerable group with high mortality and implement defaulter tracing, psycho-social support and eventually nutritional support.

- Improve testing procedures and referral system to HIV care programme

Develop a policy that reduces the number of interventions of different persons and waiting time to obtain the test result to a minimum between the first pre-test counseling and the first HIV consultation. Prioritize, where possible, the strategy of 2 rapid tests of different types for screening and confirmation, especially for pregnant women.

- PMTCT programme

Scale up of testing of pregnant women in the regions and districts. Prioritize strengthening of the PMCT mechanism including providing rapid HIV testing and counseling at maternity hospitals, and ensuring prompt confirmatory testing and communication.

Develop a consistent referral system and coordination mechanisms between AIDS centres, reproductive health centres and maternity houses

Aim at integration of all components of PMTCT in the general health care system.

Recruit and train social workers to give psycho-social support to HIV positive pregnant women and assure the link between different health services.

Develop strategies to reduce stigma and discrimination aganst HIV positive pregnant women.

Make Protective material for safe deliveries available in the maternity houses

- Safe feeding practices in exposed children

The provision of formula replacement feeding was initially accepted in Round 8, but its budget was eventually reduced.

Although the impact of replacement feeding has been documented in rich countries, hygienic living conditions in rural areas in Tajikistan might make formula feeding unsafe. Strategies to reduce HIV transmission rate in exclusively breastfed children should be developed, like prolonged ARV prophylaxis in lactating women or breastfed children.

Health care deliverers in Reproductive Health care centres, Maternity houses and AIDS centres should be trained in counseling about the risks and advantages of replacement feeding versus exclusive breastfeeding, leaving the final decision to the mother.

In women who choose to breastfeed exclusively, the possibility of prolonged ART prophylaxis in mothers or exposed children should be studied.

UNICEF is developing a strategy to give financial support to mothers of exposed children. (50$ per month)

The NGO Gulit Surkh provides alternative support and care and can help up to 35 to 40 families with some cash to buy formula milk.

- Improve pediatric HIV care

Close clinical follow up of exposed children by monthly consultations

Monitoring and follow-up of growth, neurologic development and opportunistic infections

By actual lack of PCR: make early clinical diagnosis and start ART early

Find solution for PCR testing in other countries.The advantage of dry spot techniques are small required volumes of blood, ease of sample collection, storage and shipment, noninfectious transport medium, safe handling, stability of sample (stable in room temperature > 1 month), allows for centralization of testing facilities and facilitates systemic and unbiased surveillance

UNICEF aims at developing a policy to train pediatricians in district hospitals in pediatric HIV care and treat children accordingly in these structures.

- Use and Management of Medicines

A mechanism for sustainable provision of ARV drugs needs to be developed.

Improve procurement for medicines of opportunistic infections in order to avoid shortages.

Prioritize Cotrimoxazole suspension for OI prophylaxis in exposed children

Antiretroviral medicines: Procure Didanosine and Abacavir tablets for adults and abacavir, stavudine and Lopinavir/ritonavir in suspension form for children

If both Efavirenz and Nevirapine have serious side-effects in a patient on first line, consider using a triple nukes regimen (eg Zidovudine – Lamivudine- Abacavir)

Reserve Lopinavir/ritonavir as a second- line treatment in case of failure of first line therapy.

Implement the use of two-NRTI regimen (Zidovudine – Lamivudine) for Post-Exposure Prophylaxis and reserve the three-drug regimen in situations where antiretroviral therapy resistance is known or suspected.

- Laboratory tests

PCR, Indian Ink and cryptococcal antigen tests, viral load, lactic acid measurements

- Adherence monitoring

Implement a tool for routine monitoring of adherence. Methods that can be used systematically are a standard questionnaire, pill count, respect of appointments…

The grade of adherence should systematically be noted in the patient’s records and in case of suboptimal adherence, the multidisciplinary team should implement intensive adherence counseling.

For patients receiving ART since at least 6 months, with optimal adherence and good clinical evolutions, 2- or 3-monthly appointments can be planned.

Augment the input of Gulit Surkh and PIN + in maximizing adherence and improve coordination and referral system between AIDS centres and NGO’s

- Monitoring and evaluation

Introduce a specialized ambulatory record that contains systematic tracks on psychosocial, economic, clinical and laboratory information, data on adherence monitoring, and on prescriber regimens.

All these data can be compiled in the future Access database in the center of Medical Statistics.

Develop a consistent Monitoring and evaluation strategy with improved reporting forms.

The following data should be collected at each clinical facility on a regular basis (e.g. monthly,

quarterly or semi-annually):

- number of HIV patients “seen for care” (seen at least once in the previous 12 months)

- number of HIV patients seen for care who are eligible for ART (CD4 <350 cells/mm3)

- number of HIV patients seen for care initiating ART

- number of HIV patients seen for care receiving first-line ART

- number of HIV patients on ART changing from first-line ART to second-line ART

- number of HIV patients on ART changing from second-line ART to salvage ART

- number of HIV patients interrupting ART treatment, including the reason (e.g. death, toxicity,side effects, loss to follow-up, ARVs not available, etc.)

- number of patients who died while on ART, including cause of death (e.g. HIV/AIDS related mortality or non-HIV/AIDS related mortality such as accident, overdose or suicide)

- number of HIV patients who died within the first 12 months of initiating HAART

- number of deaths among all HIV patients including cause of death (e.g. HIV/AIDS related mortality or non-HIV/AIDS related mortality such as accident, overdose or suicide).

- number of IDUs among all HIV patients

- number of HIV-infected active IDUs (having injected in the past four weeks)

- number of HIV-infected former IDUs (not having injected in past the four weeks)

- number of HIV-infected IDUs on OST

- number of HIV patients coinfected with HCV

- number of HCV/HIV-coinfected patients with chronic hepatitis C

- number of HCV/HIV-coinfected patients with chronic hepatitis C receiving:

° only HCV treatment

° only ART

- number of HIV patients coinfected with HBV (HbsAg-positive)

- number of HIV-positive patients with active hepatitis;

- number of HIV-positive patients with active hepatitis receiving:

- HAART with 3TC and/or TDF;

° ART without 3TC and/or TDF;

° exclusively on hepatitis B treatment (e.g. IFN or ADF);

- operational research

Document experiences of HIV care in different risk groups and develop adapted approaches for detainees, intravenous drug users, detainees, sex workers, labour migrants, pregnant women and men having sex with men

- Training

Develop of a capacity building plan, including a training calendar

Implement an information system that provides regular updates of all service deliverers on latest evidence on HIV/AIDS related subjects

Develop checklists of signs and symptoms that are suspicious of HIV infection and that indicate HIV testing. E.g. in children: chronic ear infection, chronic parotitis, sepsis, oropharyngeal mycosis, failure to thrive, oral warts,…, in adults: oropharyngeal mycosis, chronic diarrhea, Sexually transmitted infections, herpes zoster, seborrheic dermatitis

Distribute checklists to all different health care providers of the general health system (family doctors, Specialists in medicine and infectious diseases, pediatricians, neurologists, dermatologists…)

Training priorities identified during the evaluation:

- Intensive training on PMTCT counseling and feeding options for HIV positive mothers for service deliverers in Reproductive health centres, Maternity houses and AIDS centres.

- Training of social workers on PMTCT

- Training of social workers, nurses and/or psychologists on counseling and psychosocial support of PLHIV

- diagnosis and treatment of opportunistic infections , clinical staging and IRIS for ART prescribers

- management of TB/HIV co-infection, with emphasis on diagnosis of smear negative pulmonary TB and extrapulmonary TB for ART prescribers in AIDS centres and prisons

- pediatric HIV care for ART prescribers

- treatment failure/second line therapy for ART prescribers

- adherence monitoring and monitoring of viral load for the multidisciplinary teams

- side effects with emphasis on lactic acidosis for ART prescribers

- Capacity building on ART initiation and management: make ART prescribers able to initiate HAART and choose correct ART regimen.

Due to the amount of required trainings, development of a team of master trainers who regularly refresh and build upon existing skills is necessary. Carefully select future trainers who will be maximally dedicated to the training activities. Training of trainers would have to be organized In Dushanbe or abroad with important international input.

Most trainings can be organized in the country and given by national trainers.

For the trainings on pediatric HIV care, second line therapy and side effects, an international input would be more than welcome

Emphasis should be put on interactive training methods as case-based learning, exchange experiences, practical (clinical) training and bed-side teaching with maximal efforts to increase medical decision-making skills

- Awareness raising and Lobbying and advocacy in workplaces, community and health services

Unfavourable local or legislative environments have contributed to poor service implementation, utilization and community acceptance. Stigmatization and discrimination of PLHIV is widespread, also among health service providers.

As no PLHIV are ready to disclose their status in public, involve health care deliverers, religious leaders, politicians, journalists and celebrities to take the lead in the fight against stigma

Lobbying and advocacy are required to:

- Fight against stigma

- Empowerment of PLHIV and defend human rights

- Adoption of workplace legislation defending the rights of PLHIV and protecting workers who may be at risk.

- Defend the rights of university students

- Diminish gender-based inequality

Activity 6.4.1: Review national legislation related to HIV/AIDS and the workplace to identify existing gaps and develop an updated strategy.

WHO progress report 2008 ‘Towards Universal Access’

Global Fund Evaluation sheet of Round 8 Grant Performance Report

ARV THERAPY Achievements, weaknesses and Future Plans, DODARBEKOV M.D. – HEAD OF DISPENSARY DEPARTMENT, OF REPUBLICAN CENTER ON HIV PREVENTION AND CONTROL

ARV THERAPY Achievements, weaknesses and Future Plans, DODARBEKOV M.D. – HEAD OF DISPENSARY DEPARTMENT, OF REPUBLICAN CENTER ON HIV PREVENTION AND CONTROL

Global Fund Evaluation sheet Round 8 Grant Performance Report

Immune restoration disease after antiretroviral therapy. MA French et al, AIDS 2004; 18: 1615–27.

Estimations of national AIDS centre

Estimations of national AIDS centre

GFATM PROPOSAL FORM – ROUND 8 2008

AIDS, Aceijas, 2004

Physicians’ experience with the acquired immunodeficiency syndrome as a factor in patients’ survival. MM Kitahata et al, N Eng J Med 1996; 334:701-706

Global Fund Evaluation sheet of Round 8 Grant Performance Report

Post-exposure prophylaxis to prevent HIV infection, WHO 2008

HIV treatment and care, Clinical Protocols for the WHO European Region, WHO 2007

Global fund Grant Performance Report Tajikistan 2010

Effectiveness of antiretroviral treatment in a South African Program. R. Lara et al, Arch Intern Med, Vol 168 no. 1, January 2008

Early mortality among adults accessing a community-based antiretroviral service in South Africa: implications for programme design. SD Lawn et al, AIDS Volume 19(18), December 2005, p 2141-2148

Global Fund Evaluation sheet of Round 8 Grant Performance Report

National estimation in SPECTRUM Program 2007

Situation review on HIV + pregnant women and children in Tajikistan, Hamidova Mohira, obstetrician – gynecologist and Madjitova Tatyana, pediatrician, Republican HIV center

Situation review on HIV + pregnant women and children in Tajikistan, Hamidova Mohira, obstetrician – gynecologist and Madjitova Tatyana, pediatrician, Republican HIV center

Situation review on HIV + pregnant women and children in Tajikistan, Hamidova Mohira, obstetrician – gynecologist and Madjitova Tatyana, pediatrician, Republican HIV center

HIV prevalence of target populations, PROPOSAL FORM – ROUND 8 GAFTM 2008

Situation review on HIV + pregnant women and children in Tajikistan, Hamidova Mohira, obstetrician – gynecologist and Madjitova Tatyana, pediatrician, Republican HIV center

Situation review on HIV + pregnant women and children in Tajikistan, Hamidova Mohira, obstetrician – gynecologist and Madjitova Tatyana, pediatrician, Republican HIV center

Situation review on HIV + pregnant women and children in Tajikistan, Hamidova Mohira, obstetrician – gynecologist and Madjitova Tatyana, pediatrician, Republican HIV center

Situation review on HIV + pregnant women and children in Tajikistan, Hamidova Mohira, obstetrician – gynecologist and Madjitova Tatyana, pediatrician, Republican HIV center

Newell, M. L.et al. Mortality of infected and uninfected infants born to HIV-infected mothers in Africa: a pooled analysis. Lancet364, 1236–1243 (2004).

Situation review on HIV + pregnant women and children in Tajikistan, Hamidova Mohira, obstetrician – gynecologist and Madjitova Tatyana, pediatrician, Republican HIV center

Situation review on HIV + pregnant women and children in Tajikistan, Hamidova Mohira, obstetrician – gynecologist and Madjitova Tatyana, pediatrician, Republican HIV center

ANTIRETROVIRAL THERAPY FOR HIV INFECTION IN INFANTS AND CHILDREN: TOWARDS UNIVERSAL ACCESS Recommendations for a public health approach, WHO 2006

HIV treatment and care, Clinical Protocols for the WHO European Region, WHO 2007

WHO Three I’s Meeting Intensified Case Finding (ICF), Isoniazid Preventive Therapy (IPT)

and TB Infection Control (IC) for people living with HIV Report of a Joint World Health Organization HIV/aids and TB Department Meeting 2-4 April, 2008, Geneva , Switzerland

Isoniazid preventive therapy for people living with HIV: public health challenges and implementation issues

N. Aït-Khaled, E. Alarcon, K. Bissell et Al, International Union Against Tuberculosis and Lung Disease, Paris, France

Isoniazid preventive therapy for people living with HIV: public health challenges and implementation issues

N. Aït-Khaled, E. Alarcon, K. Bissell et Al, International Union Against Tuberculosis and Lung Disease, Paris, France

National Operating guidelines on substitute therapy by methadone for Opiate Addiction Syndrome, Dushanbe 2009