## Sheet1
Annual Review Report to UNDP
Africa Adaptation Plan Programme (AAP) Supporting Climate Resilient Sustainable Development in Ethiopia
Narrative Description of Physical and Financial Performance Report
1. Basic Information
· Component: AAP
· Lead Agency: EPA
· Implementing Partner: EPA
· Program Period: October 2010- December 2012
· Reporting period: October 2010 to December 2012
CP Outputs | Indicators Including Annual Targets/ Baselines | Planned Activities | Narrative description of Progress against Activity results by refering to Planned Activities | Budget Allocated 1ST INSTALLMENT | Budget Allocated 2ND Installment | Budget Allocated | Budget Allocated | Budget Allocated 5 th installment | Expenditure for the Same Activities | [7 empty] | total installment | [8 empty] | 1st | 2nd | 3RD | 4TH |  |  |  | Budget Allocation | Expenditure for the Same Activity | Expenditure Taken for Demonstration Project from the total Expenditure | Total Expenditure to Date in (Birr) | Budget Balance
Output 1: Dynamic, long-term planning mechanisms to manage the inherent uncertainties of climate change introduced
| Target Year 1- Baseline study completed and informs preparation of PADSEP II by end Year 1. | Activity Result 1: National Planning frameworks are designed to operationalise the agreed strategies for creating a carbon netural and Climate Resilient Green Economy in Ethiopia | As part of the national planning framework to climate change, National Adaptation Programme called the Ethiopian Programme of Adaptation to Climate Change (EPACC) is prepared after several national consultation processes. A Guideline to mainstream Climate Change into policies, programmes, plans and projects at regional, district and local levels is prepared. Sectoral Technical Working Groups (TWGs) are established in 11 National Regional Units and 12 key sectoral institutions of which all of the Regional TWGs and 8 of the sectoral TWGs have prepared their respective adaptation programmes.
|  | Action 1.1.a Elaborate on the implications of the national climate change strategy and, specifically, CNCR to all concerned line Ministries and relevant stakeholders, so that these implications are fully understood and internalised. | [30 empty] | 577023.3 | 577023.3 |  | 577023.3 | 0
|  |  | AAP has fully supported the preparation of the 8 sectoral adaptation Progrmmes and supported the sensitization and training programme of the TWGs which contributed to the capacity building in the preparation of EPACC and Adaptation Programmes. The 8 sectoral and the 11 Regional Units’ adaptation plans are completed, edited and are currently being used by the concerned bodies. The TWGs’ duty is mainly to spearhead the mainstreaming of Ethiopian Programme of Adaptation to Climate Change (EPACC) and the implementation of associated regional and sectoral adaptation plans into sectors’ and Regional policies, rogrammes and projects. As a result of this intervention, currently mainstreaming climate change in policies, programmes and plans has been given top priority. | [28 empty] | 1st face
|  |  | The eight sectoral ministries which have prepared their respective Sectoral Climate Change Adaptation Programme are: The Ministry of health, the Ministry of Water and Energy, the Ministry of Mines, the Ministry of Urban Development & Construction, he Ministry of Agriculture, the Ethiopian Wildlife Conservation Authority, the Ministry of Transport, and the Refugees and Returnees Affairs. | 163600 | 167600 | [11 empty] | 331200 | [8 empty] | 30000 | 78034.54 |  | 448908.76 |  | 20080 | [5 empty] | 0
| - Baseline study completed and informs preparation of PADSEP II by end Year 1. | Action 1.1.b Undertake consultation on Carbon Resilient Green Economy (CRGE) for concersned stakeholders and key sectors at national and regional level; support with technical expertise so that its implications are fully understood and internalised in their holistic planning approaches. | One of the significant out put produced by contribution of AAP is the preparation of the Ethiopian Climate Resilient Green Economy (CRGE) Strategy document. AAP has played a great role in building the capacity of Sectoral and Regional Experts through continuous training workshops and seminars starting from the initial concept of “Carbon Neutral Climate Resilient Economy (CNCRE)” which later evolved to CRGE. CRGE envisioned to 2025 goal of becoming Ethiopia a middle income country with zero net carbon emission by following green growth path. The following are training workshops and seminars conducted for the Regional and Sectoral TWGs, federal and Regional represented staffs, delegates from higher learning institutions, The seminars and workshop conducted for parlimantarians is shown in Table 1 attached in Annex 1. | [13 empty] | 0 | [6 empty] | 12374.72 | [8 empty] | 12374.72 | 12374.72 |  | 12374.72 | 0
| Targets (year 2) | Action 1.1.c As part of supporting policy interventions with evidence base in renewable energy, enhance capacity of the AAP supported biofuel project to avoid environmental pollutatnts by converting them into useful commodities. | AAP has also financed the consultation process of the Draft CRGE Strategy. The draft strategy was enriched by stakeholders and partners from all regions and sectors. The three consultative workshops on the strategy were conducted at Mekele on July 25 to 26, 2011; at Addis Ababa on August 1 to 2, 2011 and Harar on 5 to 6, 2011, each for two days. Representatives from different federal and regional stakeholders participated on the workshops. The objectives of the workshops were a) to check the credibility and reliability of data used in the draft CRGE document, assumptions and feasibility assessment; b) to validate the existing initiatives with the proposed green economy initiatives; and c) to identify more green economy initiatives. Discussions were focused on the 7 pillars of CRGE (power, green cities, industry, livestock, agriculture, transport and forest). The technical teams participated in the CRGE preparation process led the process of consultation. See consultation workshops held in Table 2 of Annex I. | [13 empty] | 0 | [19 empty] | 0
| - Local Level adaptation planning Capacity Building Plan implemented. | Action 1.2.a Gain agreement with, and support for, newly defined / re-defined accountabilities within relevant Ministries relating to climate change planning, mitigation, adaptation and integration under the overall high level programme of CNCR. Provide specialised expertise to support each ministry as appropriate. | The technical study titled, “Assessment of Drought and Flood Prone Areas of Ethiopia” is prepared. The content of the document refers drought in terms of Metrological Drought, Agricultural Drought, Hydrological and Socio-economic Drought; areas of Annual Probability of Drought are mapped in the document; vulnerability to flood, areas of flood hazard frequency in Ethiopia are identified and mapped. In addition, likely future condition of flood and drought are also predicted. The Study was based mainly on secondary documents. The document is helpful in future dynamic planning. to adapt to climate change. | 163600 | 251400 | [11 empty] | 415000 | [8 empty] | 65085.48 | 90174.19 |  | 149971.96 |  |  |  | 305231.63 | 305231.63 |  | 305231.63 | 0
0
| Multi-sector climate change strategy developed by end Year 2. | Action 1.2.b Provide specialised expertise to support each ministry as appropriate on the refinment and finalization of CRGE. | As a continuous process of improving the EPACC the consolidation and synthesizaiton of Regional and Sectoral adaptation Programmes was carried out by a team of experts. This consolidated programme helps in updating the national one (the EPACC). In addition, from the synthesized document fundable project proposals consisting of selected adaptation technologies and practices are prepared. Some of the technologies selected are the one learnt from the implementation of adaptation learning demonstration projects funded by AAP (See Annex IV) | [13 empty] | 0 |  |  |  | 2240 |  |  |  | 32875.93 | [7 empty] | 35115.93 | 35115.93 |  | 35115.93 | 0
|  | Action 1.3.a Align all plans for the development of key documents and strategies (including, but not limited to PASDEP II, national plans for adaptation and mitigation, plans for CDM initiatives and adaptation projects) | Africa Adaptation Programme (AAP) National Steering Committee meetings were held five times within the average of three to four months interval. The Steering Committee has consistently assisted the project implementation through project report review, monitoring and providing programme level and technical direction. Table 3 shows the Steering Committee meetings held during the project implementation period. | 81800 | 83800 | [11 empty] | 165600 |  |  | 402714 | [12 empty] | 339838.07 | 339838.07 |  | 339838.07 | 0
|  | Action 1.3.b Engage the private sector, particularly the industrial sector (manufacturing and service), in developing appropriate long-term strategies and near-term solutions and pilot implementation for tackling environmental pollution and climate change adaptation measures | The impact of climate change reaches across almost all aspects of social and economic activities. It is, therefore, vital to recognize that the implication of climate change and the steps required for an effective response go well beyond environmental management. Climate change must not be considered as a narrow sectoral issue, rather a multi and cross-sectoral response is essential. The response will require cooperation planning and action across government sectoral ministries and agencies, from finance to agriculture, from education to foreign affairs; regional government and woreda administrations and outside government, by civil society, religious groups, the private sector, communities, academic and research institutions, international and national NGOs and development partners. | [13 empty] | 0 | [7 empty] | 30000 | [7 empty] | 30000 | 30000 |  | 30000 | 0
|  | Action 1.4.a Engage the private sector, particularly the industrial sector, in developing appropriate long-term strategies and near-term solutions for tackling environmental pollution and climate change adaptation measures | With so much complexity, and the need for so many different actors, the response needs strategic leadership. Leadership can be defined as the capacity to inspire others to behave in such a way that the desired outcomes are achieved. It involves personal commitment as well as concrete action. A key principle is that leadership can reside in anyone regardless of job title, seniority or social status. That is why under AAP intervention, EPA in collaboration with UNDP, UNICEF and WFP has conducted Leadership for result Program (LRP) programme which built the leadership capacity of key sectors in managing issues related with climate change adaptation (see the detail about the programme under Out put 2, Activity result 2) | 490800 | 838000 | [11 empty] | 1328800 | [15 empty] | 200000 | 200000 |  | 200000 | 0
|  |  | HIV-AIDS harms the development of the nation by killing the productive force and loosening the social structure and increasing vulnerability to climate change. To reduce the effect of it training and capacity building is mandatory. Therefore, Federal environmental protection Authority conducted training on the prevention of HIV AIDS for 73 FEPA staffs from 10 to11 October 2011. | [33 empty] | 0
|  |  | The Socialist republic of China government’s delegation to Ethiopia has made discussion with Federal Environmental Protection Authority and representatives from sector ministries of Ethiopia, from 11 to 14 March 2012. The main objective of the delegation was to assist Ethiopia to enhance the competitive and leadership capacity to the world climate change negotiations and to develop bilateral cooperation between the two countries on climate change agenda. This bilateral cooperation is believed to benefit and create an opportunity to Ethiopia in the implementation of Climate Resilient Green Economy Strategy and the five year’s Growth and Transformation Plan (GTP). | [33 empty] | 0
|  |  | The members of the Ethiopian House of Federation comprising of 135 members were given one day training on Climate Resilient Green Economy Strategy on 10 October 2012 at Addis Ababa. Among the participants 23 were females and 112 were males. | [33 empty] | 0
|  |  | A Guide Line for Student's environmental club establishment in schools and Environmental Groups establishment in Government institutions was developed and the evaluation of it by stakeholders was conducted on 19-22 November 2012 in Ziway town. Currently, the document is prepared in final form. | [33 empty] | 0
|  |  | EPA staffs from public relation directorate made a visit to Renaissance Hydroelectric power dam on 28 November to 03 December 2012 to provide technical support and to report to EPA’s staff on the need for additional support. | [33 empty] | 0
|  |  | Staffs from Monitoring and Evaluation Directorate conduct field visit on evaluating environmental impact of road construction projects of Jimma-Mizan-Bonga and report is submitted to EPA. The evaluation was made based on the EIA study report prepared before the commencement of the project. | [33 empty] | 0
|  | Activity Result 2: National Planning frameworks reflect sector plans for managing climate change. | In addition to the training workshops held to capacitate the Federal and Regional sectoral institution on climate change issues, the TWGs established at sectoral level have worked with technical support given by EPA on baseline review of key documents within their respective ministries under the support of AAP. This enabled them to prepare their sectoral adaptation programme. They mapped current activities relating to climate change and designed future adaptation cost and adaptation capacities. As part of this processs, key ministries concerned with National Planning, including MoFED have taken consecutive training workshops on the initial concept of CNCRE all the way till its evolvement to CRGE. | [13 empty] | 0 | [19 empty] | 0
|  | Action 2.1.a Undertake a Baseline Study of climate change planning in key Ministries; to include mapping of current activities relating to climate change matters(see Action 1.3 above); an initial assessment of climate change adaptation costs; and a preliminary assessment of strategic strengths and capacities. (linked with 1.1, 1.2 and 1.3) | In support of sectoral and regional agencies in climate change adaptation and mainstreaming, three teams comprised of 34 professional staff from EPA and environmental NGOs having diverse professional background were setup and worked on separate areas each but by cross-fertilizing the concepts. The areas worked and the products of the teams’ work were: 1. Reviewed sectoral governmental entities’ and the regional states’ “Climate Change Adaptation Programme” documents, and prepared a consolidated and synthesized national document, 2. Reviewed other secondary documents, different from climate change adaptation documents mentioned above in item No. 1, and worked on climate vulnerability, adaptive capacity and response measures, and prepared a separate document. The output of this work has been used to enrich the consolidated and synthesized national document. 3. Prepared project proposals on climate change adaptation and mitigation technology needs and reformulated them into fundable project proposals. | 327200 | 335200 | [11 empty] | 662400 |  |  | 16553.3 | [5 empty] | 3054.48 | 26917.5 | [5 empty] | 246525.28 | 246525.28 |  | 246525.28 | 0
|  | Action 2.1.b Undertake a baseline study and prepare climate change adaptation programme in 5 key Ministries that inclues thier respective sectors' climate change vulnerability, adaptation capacity, adaptation options and their costs. | One of the activities planned under AAP is Climate Action Intelligence (CAI). CAI is a mechanism in which mapping of different national actors working on Climate Change will be registered and information on what type of effort, by whom and where will be obtained. It is a software supported mapping action conducted by national consultant. Trainings were given to participating key sector’s experts and the national consultants. Based on the training a "Assessment Design Proposal for Establishment and Maintenance of Climate Action Intelligence and National CRGE Registry System is prepared by the national consultants with close support given by the recruited international consultant. Materials needed for this activity are procured namely: 10 Computers, 1 high speed Server and 5 GPS. | [13 empty] | 0 | [6 empty] | 14779.41 | [8 empty] | 14779.41 | 14779.41 |  | 14779.41 | 0
|  | Action 2.1.c Edit, publish and dessiminate Sectoral and Regional Adaptation Programmes. | Total of 1,096 participants from federal sector institutions, regional units, parliamentarians, women & youth affairs institutions, civil societies, chamber of commerce and community organizations participated on trainings, sensitization workshops, field visits, dialogue forums on climate change adaptation. Climate change mitigation topics were also integrated in the programmes. Field level observation and monitoring activities showed that capacity building activities being undertaken by the support of AAP are bringing meaningful changes in enhancing adaptation capacity. |  |  |  |  | 527700 | [8 empty] | 527700 | [15 empty] | 527699.77 | 527699.77 |  | 527699.77 | 0
|  | Action 2.2.a Provide specialised technical expertise to further develop the capacity of EPA, MoFED, MoARD and other relevant agencies in terms of their ability to adopt holistic planning approaches relating to climate change. | Training on Gender Climate Mainstreaming Seminar was given to Federal and District representatives as well as to Sectoral and EPA Experts on 1-2 December 2011 and 27 December 2012. A total of 82 participants have participated on the Seminar and of which 20 are Females and 62 are Males. | 654400 | 670000 | [11 empty] | 1324400 | [15 empty] | 150000 | 150000 |  | 150000 | 0
|  | Action 2.2.b Consolidate sectoral and Regional adaptation plans to reflect national perspective; prepare package of fundable projects to their implementation and support publishing and dessimination. | Assessment on Gender Mainstreaming status is conducted by Gender, Youth and Children Directorate of EPA and the document is prepared. The Assessment was conducted with the involvement of experts from Sectors and Regions. | [13 empty] | 0 |  |  | 190520.33 | [12 empty] | 190520.33 | 190520.33 |  | 190520.33 | 0
|  | Action 2.2.c 11 National Regional States investement plans prepared based on lessons learned from the design, execution and evaluation of the demonstration activities that support the realisation of the Climate Resilient Green Economy: | Regional implementation of “Enhancing the Adaptive Capacity of Major infrastructures Contributing to the Eradication of Poverty and to the Achievement Climate Resilient Green Economy (CRGE) strategy”, under the Mechanism to Motivate, Support and Reward Results (mMSRr) was launched nationwide. The launching workshop was held at three different cities namely Addis Ababa, Adama and Bahir Dar. The participants were delegated from the 97 woredas which are targeted as 30% of the Growth and Transformation Plan (GTP) woredas. See the mMSRr launching workshops in Table 4. |  |  |  |  | 1846950 | [8 empty] | 1846950 | [15 empty] | 1846949.98 | 1846949.98 |  | 1846949.98 | 0
|  | Action 2.3.a Conduct an analysis of current budget plans within key sector Ministries in light of likely adaptation costs To be linked with 2.1 | A task team of professionals delegated from the 9 regional states and 2 city administrations were trained on data collection for preparation of climate resilient green economy building investment plan/proposal at woreda level. The training was held at Addis Ababa for 3 days on 3 rounds. A total of 193 professionals participated and among these 12 were females. After the training, the participants carried out assessment of climate change vulnerability in their respective pilot woredas, identified technologies relevant to cope up with the impacts and wrote report for each woredas. The assessment was technically supported on the field by EPA professionals. | [13 empty] | 0 | [19 empty] | 0
|  | Action 2.3.b Drawing on knowladge base (Output 5). Impact assessments (Output 4) and action learning experience (Output 3) develop long term climate chsnge actions and budgets that fully align with the governments stated strategy and policies.Prepare long term climate change strategic plan. | [14 empty] | 0 | [15 empty] | 200000 | 200000 |  | 200000 | 0
|  | Action 2.3.c A single consolidated long-term regionally appropriate climate resilient green growth plan will be prepared based on regional investment plans and with the objective of informing the national budgeting process, mobilizing or leveraging non traditional finance. | [5 empty] | 1085400 | [8 empty] | 1085400 | [15 empty] | 1085400 | 1085400 |  | 1085400 | 0
|  | Action 2.4.a Develop planning mechanisms with sector Ministries which will enable the incorporation of climate change adaptation and mitigation issues into their planning processes. |  | 163600 | 335200 | [11 empty] | 498800 | [15 empty] | 250000 | 250000 |  | 250000 | 0
|  | Action 2.4.c Elligible entities in 4 Regional States prepare their respecitve investment project proposals to deploy prioritized technologies on building Climate Resilient Green Economy. | [5 empty] | 263850 | [8 empty] | 263850 | [15 empty] | 263850 | 263850 |  | 263850 | 0
|  | Action 2.5.a Drawing on knowledge base (Output 5), financial impact assessments (Output 4) and action-learning experience (Output 3) develop long-term climate change actions and budgets that fully align with the Government’s stated strategy and policies . Prepare long term climate chanage strategic action plan | [14 empty] | 0 | [15 empty] | 450550 | 450550 |  | 450550 | 0
|  | Activity Result 3: a Key sectors engaged in co-ordinated regional and national climate change response. | Specialized and sustained technical support was given for sectoral representatives and Regional EPAs experts including through field technical assistance in the 9 regions and 2 city administrations. The field mission was supported by AAP and it was with the aim of providing technical advice on the implementation of adaptation learning projects and in identification and documentation of good lessons. Currently coordinated mechanism is established under CRGE technical team being lead by EPA and above that to provide policy direction there is Interministerial Committee lead by His Excellency the advisor of the Prime Minister. The CRGE technical team includes TWGs selected from the 7 CRGE pillar sectors (Crop and livestock, power, transport, forest, green cities and industry). | [13 empty] | 0 | [19 empty] | 0
|  | Activity Result 3: b&c Key sectors engaged in co-ordinated regional and national climate change response based on CRGE. | The initiative on the analysis of current budget plans within key ministries and Regions is started under the CRGE and the preparation of investment plan and sectoral reduction mechanism in the key pillar sector is being carried out. At sectoral level also, under the umbrella Mainstreaming Guideline, based on consecutive training workshop given to the TWGs and the Environment and Natural Resources Standing Committee members of the House of Peoples Representatives, sectoral budget consideration and sustained evaluation to incorporate climate change has become priority issue. | [13 empty] | 0 | [19 empty] | 0
|  | Action 3.1.a Provide specialised technical expertise to build capacity of planning units at sector Ministries at Federal and regional level. | EPA staffs had participated on the inauguration of Adama wind generated electric power project on 30 October 2012 which is one of the largest project in the country in response to climate change to generates clean and renewable resource. | 327200 | 502800 | [11 empty] | 830000 | [9 empty] | 29947.34 | [5 empty] | 29947.34 | 29947.34 |  | 29947.34 | 0
|  | Action 3.1 b&c Provide technical expertise support to build capacity of planning units at sector Ministries at Federal and regional level to enable them incorporate climate change in their sectoral planning as stipulated under CRGE | Monitoring and Evaluation team of EPA conducted a two days workshop to enhance the Regional and sectoral capacity to verify climate resilient green economy performance measurement on the five environmental laws. On the workshop two representatives from each of the nine regional states and two city administrations participated. |  |  |  |  | 175900 | [8 empty] | 175900 | [15 empty] | 175900 | 175900 |  | 175900 | 0
|  | Action 3.2.a Building on findings of baseline study, support federal and regional sector agencies to engage in joint climate impact assessment exercises to incorporate climate change into sector planning. |  | 327200 | 670400 | [11 empty] | 997600 | [8 empty] | 4893.95 | [6 empty] | 54893.95 | 54893.95 |  | 54893.95 | 0
|  | Action 3.2.b Drowing on Output 5, Output 4 and output 3, develop more refined sector-level long term climate change actions and budgets for regional implimentation based on the regional addaptation programmes. | [14 empty] | 0 |  |  | 30000 | [12 empty] | 30000 | 30000 |  | 30000 | 0
|  | Action 3.2.c Technical assistance support for CAI | [14 empty] | 0 | [19 empty] | 0
|  | Action 3.3.a Drawing on Output 5, Output 4 and Output 3, develop sector-level long-term climate change actions and budgets for regional implementation. | [14 empty] | 0 | [19 empty] | 0
|  | Action 3.3.b Establish a mechanism and system that enables coordinate and support climate change interventions by various stake holders through the establishment of a system of Climate Action Intelligence (CAI). | [14 empty] | 0 |  |  | 505600 | [12 empty] | 505600 | 505600 |  | 505600 | 0
|  | ACTIVITY RESULT 4: Capacity built for managing climate change risks and opportunities at local level. | [14 empty] | 0 | [19 empty] | 0
|  | Action 4.1.a&b As part of the base-line survey, identify vulnerable groups that should be eligible to construct, and should benefit from, a carbon neutral, climate resilient economy. (Conduct vulnerability assessment and identify beneficiary households with in the selected woredas) | [14 empty] | 0 | [15 empty] | 355200 | 355200 |  | 355200 | 0
|  | Action 4.1.c Generate awareness of implications of climate change in local leadership in target areas | [14 empty] | 0 | [19 empty] | 0
|  | Action 4.2.a Generate awareness of implications of climate change in local leadership in target areas | A video documentary showing good practices in environmental protection efforts by school-communities in the target regions has been approved by AAP partners - EPA and UNDP, and produced in Amharic and English. This video is being broadcast to all regions using equipment available at secondary school level. The development of a gender-sensitive climate change communication strategy as well as knowledge management for climate change has been concluded. For knowledge management, a template for selection of best practices was jointly developed with EPA and the Knowledge Management platforms are finalized. | [13 empty] | 0 | [15 empty] | 55800 | 55800 |  | 55800 | 0
|  | Action 4.2.b Identify capacity constraints for climate change addaptation planning at woreda level and impliment demo projects. | Financial and Technical support was given to demonstration projects and scaling up of the best practices obtained in the implementaiton of demo projects. the up front support was givent under the programme Mechanism to Motivate Support and Rewared Results (mMSRr). |  | 419000 | [11 empty] | 419000 | [15 empty] | 419000 | 419000 |  | 419000 | 0
|  | Action 4.3.a Identify capacity constraints for climate change planning at woreda level and implement building capacity plan. Conduct werda level climate change impact assessment (impact of climate change on temperature, precipitation and drought, flood and other extreme events) in selected woredas . identify capacity gaps (needs assessment) and conduct conduct training) | The districts which obtained up front support under this component are Embalage, Seharti/Samre, Southern Tenben, Hentalo Wajrat, tankua Abergel, Kola Tenben, NaderAdet, Weri Leke, Tahtay Maichew, Medebay Zana, Tselemti , Mekele of the Tigray National RegionalState; Districts located under Eastern Gojjam of the Amhara National Regional State namely, Gozamen, Senan, Bibugne, Machakel, Debre Elias, Anedad, Basoliben, Awabel, Dejen Zuria, Enemaye, Gonecha Sisoenese, Hulet Eje Enese, Shebel Berenta, Enebse Sarmeder, Enarge Enawga, Debay Telat, Debre Markos City, Debremarkos, Dejen, and Bichena and Mota | [13 empty] | 0 | [19 empty] | 0
|  | Action 4.3.b Prepare local level environmental management plans and establish woreda level LEAP in a sellected sample of woredas and impliment demo projects that fully align with the strategy for the construction of a climate resilient economy. |  |  | 3686710.6 | [11 empty] | 3686710.6 | [15 empty] | 3686710.6 | 3686710.6 |  | 3686710.6 | 0
|  | Action 4.4.a Prepare local-level environmental management plans in a selected sample of woredas that fully align with the strategy for the construction of a climate resilient economy | [14 empty] | 0 | [15 empty] | 342479.05 | 342479.05 |  | 342479.05 | 0
|  | Action 4.4.b Generate awarness of implications of climate change in local leadership in target areas. | [14 empty] | 0 | [19 empty] | 0
|  | Action 4.5.a Establish woreda-level LEAP (Link to Output 3). | [14 empty] | 0 | [19 empty] | 0
|  | Action 4.5.b Explore and analyse impacts of climate change on food security in sellected sample woredas using VAM tools |  |  | 427750 | [11 empty] | 427750 | [15 empty] | 427750 | 427750 |  | 427750 | 0
Total Output 1 |  |  |  | 2699400 | 8387860.6 | 0 | 0 | 3899800 | [8 empty] | 14987060.6 |  |  | 1145387.63 | 2240 | 0 | 0 | 27154.13 |  | 103033.91 | 225073.57 | 0 | 598880.72 | 0 | 20080 |  | 12809139.36 | 12809139.36 |  | 12809139.36 | 0
Output 2: Leadership and institutional frameworks to manage climate change risks and opportunities in an integrated manner at the local and national levels built
| Targets (year 1) - Technical Working Group established and advice to EC and NRE members of the Parlimantarins initiated, environmental Units streangthened in key sectoral institutions. | ACTIVITY RESULT 1: a &b Environment Council strengthened to take on leadership role for CCA. | It is believed that there are a lot of local good practices within Ethiopia with regard to climate change adaptation. Some of the activities have to be tested by adaptation learning demonstration projects. Climate change adaptation demonstration projects have been implemented in all regions for the last two years. About 45 adaptation learning projects were successfully implemented in different climatic zones of the country and lessons are documented. The demo projects can be categorized in the thematic groups of Infrastructural and Water Sensitive Industries adaptation, Lakes and Rivers ecosystem adaptation and rehabilitation, Community Based Adaptation through alternative livelihood development and Primary Solid Waste Management and clean and alternative energy development. | [33 empty] | 0
| - Technical Working Group established and advice to EC initiated. | ACTIVITY RESULT 1: c Parliamentarians, Sectoral Environmental Units and/or CRGE Units, Regional EPAs, Regional and local Councils as well as small scale enterptises strengthened to take on leadership role for CCA. | A lot of lessons are drawn from the demonstration projects. The lesson are documented in booklets, printed and disseminated to the public. In addition, a 45 minutes documentary film on lessons learnt and good practices and green technologies identified is prepared and disseminated. | [33 empty] | 0
|  | Action 1.1.a Special seminars & visit series to motivate and enhance actions on climate change adaptation. | As the intervention of enhancing the leadership capacity of decision makers, several capacity buildings for Parliamentarians, Heads of Environment Bureaus of Regional Governments, Department Heads of Sector Institutions in CC mainstreaming activities were carried out through workshops and seminars and study tours. See seminars conducted for parliamentarians in Table 5. | 163600 | 502800 | [11 empty] | 666400 | [15 empty] | 150000 | 150000 |  | 150000 | 0
| Targets (year 2) Agreement reached in EC and NRE Standing Committes of the parlimentarians to mainstream adaptation through integrated actions. | Action 1.1: b Organize Special seminars & visit series to EC and/or Sectoral Envioronmantal Units, Regional EPAs & Council members to motivate and enhance actions on climate change adaptation and up to date them in international Climate Change negotiation positions. | EPA as the Environmental Council Secretariat is expected to carry out responsibilities in coordinating the efforts of CC at national level. To perform the task, self capacity as well as Regional EPAs’ capacity building is essential. The gap can be explained in terms of material and human capacity building. To respond to the material capacity gap, the purchase of office equipment and furniture is conducted. The procured items were 94 desktop computers, 27 laptop computers, 5 printers, 11 LCD projectors, 12 digital cameras, and office furniture both for Regional institutions and for Federal EPA is conducted and distributed. | [13 empty] | 0 | [15 empty] | 168500 | 168500 |  | 168500 | 0
| Agreement reached in EC to mainstream adaptation through integrated actions. | Action 1.1:c Effective and appropriate engagement with the proposed Mechanism to Motivate Support and Reward (mMSRr) will be assured through the creation, publication and widespread communication of a National Operations Manual. | Accordingly, to enhance the administrative capacity of EPA and provide technical assistance to regions on the implementation of AAP, one IT expert one procurement expert, two assistant project coordinators and 1 accountant was recruited. |  |  |  |  | 87950 | [8 empty] | 87950 | [15 empty] | 87950 | 87950 |  | 87950 | 0
| Policy Position Papers Prepared by EC to advise country Leadership on international climate change negotiations. | Action 1.2: a Keep EC/NRE members up to date with international climate change policy and implications and support preparation of policy positions for international negotiations. | AAP has also financed human resource development activities.The technical and support staff of EPA have been given consecutive training workshops mainly focusing on improving the business process and the service giving capacity of EPA. The objectives of the trainings were: * To increase awareness of the staff on the national development policies and strategies; • To familiarize the staff with the newly introduced business process; and • To acquaint the staff with the result focused Balanced Score Card (BSC), and task and output measurement mechanism. A total of 130 staff members of the Federal EPA have participated in the training-workshops. Resource persons from private consultants and trainers from other experienced organizations were involved in the training. The following are capacity building training workshops conducted for internal staff. For the capacity building training for EPA see Table 6. | 327200 | 502800 | [11 empty] | 830000 | [11 empty] | 390883.72 | 136316.98 | 69137.4 |  | 596338.1 | 596338.1 |  | 596338.1 | 0
| Local leadership in selected Woredas understand climate change and the risks and opportunities it brings for local development. | Action1.2. b Strengthen the technical and administrative function of EC and TWGs secretariat; and the climate change National Focal Institution. | Besides the above mentioned training which has accommodated the whole staff, there were also trainings targeting individual staff members on their area of expertise. Accordingly, one staff of the EPA from Information Technology stream has participated in a training organized by the Ministry of Communication and Information Technology with the theme “Auditing, Securing Enterprise Level Network” by the support of AAP. The training was conducted for 15 consecutive days. | [13 empty] | 0 |  |  | 200000 | 62762.11 | 161275.22 | [10 empty] | 424037.33 | 424037.33 |  | 424037.33 | 0
|  | Action 1.2:c Criteria developed and issued on the selection and entry into a register of qualified champions that provide service on the preparation and implementation of climate resilient green economic growth intitiatives. | As working environment is essential for the productivity of workers; AAP has supported the greening of EPA’s compound through procurement of flower and grass seedlings and associated hand tools. |  |  |  |  | 87950 | [8 empty] | 87950 | [15 empty] | 87950 | 87950 |  | 87950 | 0
|  | Action1.3.a Strengthen the technical and administrative function of EC secretariat. | Federal Environment Protection Authority in collaboration with the Oromia Environmental Protection & Rural Land Administration Office conducted evaluation mission on pollution caused by Cement factory established around Modjo town, Oromya National Regional State. | 1390600 | 1089400 | [11 empty] | 2480000 |  |  | 150213.89 | 37213.89 |  |  |  | 151486.88 | 1210928.29 | 170375.52 | 48686.67 |  |  |  |  | 1600405.14 | 1600405.14 |  | 1600405.14 | 0
|  | Action 1.3:c Conduct 25 hands on training forums at federal and regional levels to assist the establishment and operation of green enterprises, community organizations and public agencies in the area of adaptation or mitigation. | A chemical owned by BAB & transported by Orcid Business Group from Djibouti to Dallol was subject to car accident. Therefore, technical team from EPA went there to evaluate and report the state of threat of the chemical accident and prepared the report. |  |  |  |  | 351800 | [8 empty] | 351800 | [15 empty] | 351800 | 351800 |  | 351800 | 0
|  | Action 1.4:c Organize Special seminars & visit series to parliamentarians, Regional EPAs and or Council members to motivate and enhance actions on climate change adaptation and up to date them in international Climate Change negotiation positions. | Technical experts from Federal EPA have provided training to Benishangul Gumuz National Regional State’s experts on the implementation of Environmental Impact Assessment and other regulations, environmental auditing and climate change adaptation from 20 to 30 June 2012. The training has also included skill training on the utilization of solar panel implanted to the pilot communities by the support of AAP. |  |  |  |  | 264300 | [8 empty] | 264300 | [15 empty] | 264300 | 264300 |  | 264300 | 0
|  | Action1.5:c Strengthen the technical and administrative function of EC, Regional and Federal TWGs. | The vision of the Ethiopian Climate Resilient Green Economy Strategy was advertised on ‘Dagu Special Development and Goodwill Magazine” which have huge coverage over the country. |  |  |  |  | 1247729.06 | [8 empty] | 1247729.06 | [15 empty] | 1247728.66 | 1247728.66 |  | 1247728.66 | 0
|  |  | AAP has also supported EPA’s General Director supervision mission at Lalibela and Tigray Region on 14 to19 August 2012. | [33 empty] | 0
|  |  | A Convention of African Federation of Alumni Societies and Ethiopians who studied in Japan Association was sponsored. The sponsorship included propagating Ethiopia’s effort in climate change adaptation and the magazine was published on the occasion of the convention held from 1 to 2 October 2012. | [33 empty] | 0
|  |  | In order to enhance the monitoring and regulatory capacity of EPA, it has become important to upgrade the field vehicles. With this objective, 50 piece of tires were procured for field vehicles. | [33 empty] | 0
|  | ACTIVITY RESULT 2: c Multi-sector technical group established to support the Environment Councils secretariat and climate change focal point on the leadreship on CC Actions | The Sectoral and Regional Technical working groups (TWGs) are established as explained in Out put 1. To support the Environmental Council’s Secretariat (EPA) on the implementation of AAP, a Steering Committee comprising of 17 members represented from sectoral ministries, civil societies and UN Agencies has been operational. The members of the steering committee have also been active in providing technical leadership within their respective sectors in relation to CC adaptation matters and on the implementation of AAP’s activities. | [13 empty] | 0 | [19 empty] | 0
|  | ACTIVITY RESULT 2:a&b Multi-sector technical group established to support the Environment. Council | To enhance the institutional capacity of EPA and to look for better institutional programme on CC related issues, an initial project proposal document entitled “Strategic Climate Institutions Programme (SCIP”) was prepared, commented by stakeholders and submitted to DFID (UK aid). The proposal have been accepted for the funding of 482,000 Pound. | [13 empty] | 0 | [19 empty] | 0
|  | Action 2.1.a Establish multi-sector technical working group to provide technical leadership in climate change adaptation. | Adaptation learning project were also implemented under the financial support of AAP, in some projects with co-financing of UNDP’s Climate Change and Environmental Sustainability (CCV) Project. The implementation of the projects is located in all Regions with thematic focus on Infrastructural and Water Sensitive Industries adaptation, Lakes and Rivers, Community Based Adaptation and Primary Solid Waste Management projects. The implementers of the projects were Regions, civil societies, community organizations and Academia. The implementation of the project helped to identify best lessons in CC adaptation as well as those having mitigation component, and inform policy level interventions (see the full information on the demonstration project in in Annex III). | 572600 | 502800 | [11 empty] | 1075400 | [9 empty] | 8433.2 | [5 empty] | 8433.2 | 8433.2 |  | 8433.2 | 0
|  | Action 2.1.b Strengthen the capacity of Technical working (TWGs) through seminars, workshopa and study tours to provide technical leadership in climate change adaptation. | Field monitoring and backstopping visits to the demonstration project sites by EPA, accompanied by Regional counterparts, were conducted in 2 rounds and reports were prepared. Besides, all the project holders have submitted the quarterly physical activity and the quarterly financial reports of their respective projects regularly. Based on the reports of the project holders, and those of the field monitoring visits, desk review of each of the projects has been undertaken and consolidated review report prepared. |  | 91050.61 | [11 empty] | 91050.61 |  |  | 70705.35 | 2520 |  |  | 125837.65 | [8 empty] | 199063 | 199063 |  | 199063 | 0
|  | Action 2.1:c The strategic contributions of the Inter-ministerial Committee for the Climate Resilient Green Economy to the federal CRGE strategy at all levels of the economy, and its operational effectiveness, will be optimised through the creation and publication of appropriate Rules of Procedure. | A 2 days review workshop of the AAP funded demonstration projects was organized on which project holders and the Heads of the regional EPAs involved. The review workshop was conducted from 16 to 17 May 2011. Consecutive field level monitoring and evaluation with the objective of providing technical support was also conducted to the project sites by groups of EPA’s experts collaborated with Regional Expert and report prepared. |  |  |  |  | 17590 | [8 empty] | 17590 | [19 empty] | 0
|  | Action 2.2.a Strengthen technical and administrative function of the TWG secretariat and leadership with technical advisory support. | Following the review workshop, a monthly joint meeting of the heads of the regional EPA’s and officials of the FEPA was undertaken. The role of the regional EPAs in monitoring of and providing backstopping support to the climate change adaptation learning projects and supports needed to properly discharge their responsibilities was discussed on the meeting. The consecutive monitoring and evaluation process has contributed to the success of the demonstration projects. | 981600 | 670400 | [11 empty] | 1652000 |  |  |  | 22947.91 | [5 empty] | 518152.67 |  | 122123.48 |  | 44070.89 |  | 707294.95 | 707294.95 |  | 707294.95 | 0
|  | Action 2.2.b Support sector Ministry contributions with relevant technical expertise, provide Leadership for result programme (LRP) training as well as other relevant seminars for priority sectors. | In collaboration with the Addis Ababa University and the Eastern Gojjam Zone Administration, a two days national workshop has been organized in Debre Markos town from May 21 to 22/2011 under the theme of “Building Climate Resilient Green Economy on the Mt. Chocke Catchment”. The Mt. Chocke Catchment is located under the catchments of the Blue Nile basin draining about 22 woredas of mostly the East and few in the West Gojjam Zones, where significant amount of the water discharges to the Blue Nile. The objective of the workshop was to discuss mechanism on implementing the CRGE in the Mt. Chocke Catchment based on lessons leant from the demonstration projects implemented under AAP and on the findings of multiples of academic researches undertaken on the catchment. On the workshop About 250 participants, represented from federal, regional, zonal and woreda level government offices, universities, grass-root communities, UN agencies and NGOs were parties. The workshop has ended by reaching consensus on the strategy devised to realize the CRGE initiatives in the Mt. Choke Catchment and a steering committee was formed to devise follow-up plans. | 3146420.64 | 1676000 | [11 empty] | 4822420.64 |  |  | 178095.48 |  |  |  | 18124 | [8 empty] | 196219.48 | 196219.48 |  | 196219.48 | 0
|  | Action 2.2.c Support the elaboration and implementation of 3 breakthrough projects prepared under LRP. | In collaboration with UNDP Country Office, training on Leadership for Result Program (LRP) on climate change which rolled out over a course of six months was launched in collaboration with UNDP, UNICEF and WFP for participants selected from key sectors. The key sectors involved were Ministry of Agriculture, Federal Environmental Protection Authority, Ministry of Industry, Ministry of Health, Ministry of Women, Children and Youth Affairs, Ministry of Transport, the House of Peoples Representatives (Parliament) , Ministry of Water and Energy, Forum for Environment, and Ministry of Finance and Economic Development. |  |  |  |  | 527700 | [8 empty] | 527700 | [15 empty] | 527700.5 | 527700.5 |  | 527700.5 | 0
|  | Action 2.3.a Support sector Ministry contributions to TWG with sector-relevant technical expertise for priority sectors. | The objectives of the Leadership for Result Programs were:-  To build capacity of the involved organizations in addressing complex issues that are currently faced in climate change adaptation;  To design, launch and implement breakthrough projects that contribute to more effective organizational and national climate change adaptation;  To strengthen leadership capacity within key organizations in terms of their ability to address the impact of climate change; and  To create community of teams committed to being the catalyst for nationwide action on climate change | [13 empty] | 0 |  | 1030648.68 | [7 empty] | 518247.89 |  | 2479169.58 |  |  |  | 4028066.15 | 4028066.15 |  | 4028066.15 | 0
|  | Action 2.3.b Undertake demonstration projects, monitoring and action learning visits and provide technical and financial support for Regional & woreda leadership. . | The intended overall outcome of LRP is to develop multi-stakeholder leadership that is powerful and effective in responding to the immediate and long term challenges of climate change impacts in the country. There were three consecutive workshops scheduled over a period of six months time frame. As critical component of the programme, participants had designed and conducted special breakthrough projects to advance organizational climate goals, while developing the leadership effectiveness. Coaching support for the participants in their effort of developing break through projects on climate change was given from Dakar, the regional office of AAP and by recruited international consultants. All the round trainings had been organized for 5 days each, lead by 3 facilitators and training coordinators assigned from the AAP African Regional Office. The number of participants attended the three workshops are listed under Table 7. |  | 2281534 | [11 empty] | 2281534 |  |  | 102517.57 | 3541275.05 |  |  | 1612609.97 | 1291218.73 | [7 empty] | 6547621.32 | 6547621.32 |  | 6547621.32 | 0
|  | Action 2.3.c Undertake demonstration projects, monitoring and action learning visits and provide technical and financial support for Regional & woreda leadership. . | As part of the establishment of multi sectoral technical working groups the establishment of technical working groups in the 12 key Sector institutions which their mandate is to prepare their respective CC Adaptation Programmes, and to closely ensure follow up of mainstreaming CC in sector policies, programmes, plans and projects is to be mentioned. The second is the establishment of CRGE Technical Team which was involved in the preparation of the 7 CRGE pillars and its finalization as a CRGE strategy document as well as the one that follows CRGE implementation at sectoral level is to be mentioned. Third is the establishment of the Inter- ministerial committee chaired by his Excellency the Advisor of the Prime Minster, which gives policy direction and followed up the process of CRGE formulation and implementation at national level. |  |  |  |  | 38028.39 | [8 empty] | 38028.39 | [15 empty] | 4578230.57 | 4578230.57 |  | 4578230.57 | 0
|  | Action 2.4.a Undertake demonstration project monitoring and action learning visits and provide technical mentorship for woreda leadership. (Linked with 2.3) . | Ethiopian Electric Power Corporation conducted a one day workshopheld on 15 June 2012 at Assosa Town, Benishngul Gumuz Regional State. The workshop was to publicize the environmental and social impact assessment result of the Renascence Dam. The participation on the workshop from the EPA side was financed by AAP. | [13 empty] | 0 | 605288.42 |  | 1840326.07 | [6 empty] | 2132616.08 | [9 empty] | 0
|  | Action 2.5.a Support TWG to oversee development of CCA knowledge base. Merge with 2.3 | Result based system (BSC) training was provided to 44 EPA support staffs on 13 to 14 June 2012. Of the total trainee 30 were women and 14 were men. | [13 empty] | 0 | [19 empty] | 0
|  |  | EPA’s Director General participated on celebration made at Konso from 5 to10 June 2012 to commemorate its registration of the Konso terracing as world’s cultural heritage site. | [33 empty] | 0
|  |  | The participation of two EPA staffs on the Seminar organized in Hawass on 5 July 2012, regarding the conservation and restoration of Lake Hawasa was financed by AAP. On the seminar, presentation was made by EPA on best practices obtained during intervention made by demonstration projects on around Hawassa Lake | [33 empty] | 0
|  |  | A Documentary film of best adaptation practices and green technologies identified by the implementation of AAP supported demonstration projects is prepared and disseminated. The procurement of the identified green technologies is finalized and the technologies are being disseminated to other districts for scaling up. | [33 empty] | 0
|  |  | An evaluation team of EPA conducted an evaluation field visit at demonstration project site of Gilgel Gibe I hydro power buffer zone rehabilitation site and Tendaho irrigation dam buffer zone rehabilitation site, which were implemented by the financial support of AAP from July 28 to August 2, and from December 6 to 11, 2012. The objective of the evaluation is evaluate the work done by the 70% financial support previously released for SANRM and release the last 30% fund release. Based on the field report it is confirmed that the job has been found good and by the last amount released all the jobs planned have now completed and terminal report is submitted to EPA. | [33 empty] | 0
|  |  | EPA made second level sponsorship agreement with Weyen news paper and financial support was given from AAP project. Weyen Magazine has agreed to post Ethiopia’s vision in achieving climate resilient green economy by 2025 and role played by the late Prime Minster of Ethiopia in climate negotiations by representing African nations. | [33 empty] | 0
|  |  | All EAP staffs were given two days training on code of conducts of environmental service providers by external expert from 19 to 20 November 2012 at Addis Ababa and it was financed by AAP. | [33 empty] | 0
|  |  | 16 Technology profiles which was developed in Amharic by EPA were translated to English version by team of experts to prepare a compendium of technologies document. | [33 empty] | 0
|  | ACTIVITY RESULT 3: Parliamentary NRE sub-committee able to effectively articulate CC issues at parliamentary and constituency level. | Seminar to the Parliamentarians focussing on the members of the Environment and Natural Resources (NRM) Standing Committee was conducted on Feb 5 to 6, 2011; June 22, 2011 and April 29 to May 1, 2011. On the seminar, papers prepared on climate change adaptation, impacts expected due to climate change in Ethiopia and possible intervention options were presented and discussed. In addition, familiarization of EPACC and that of the draft Mainstreaming Guideline as well as what is expected from the members of the House of Peoples Representatives were widely discussed and agreed. At the end of the workshop commitment was reached by the members of the House of Peoples Representatives to support the efforts of adaptation to climate change at different levels. | [13 empty] | 0 | [19 empty] | 0
|  | Action 3.1.a&b Facilitate links with international parliamentary groups on climate change. |  | 81800 | 167600 | [11 empty] | 249400 |  |  |  | 1260 | 35098.56 | 35723.34 |  |  |  |  | 94937.46 |  |  |  |  | 167019.36 | 167019.36 |  | 167019.36 | 0
|  | Action 3.2.a&b Keep NRE members’ up to date with international & national climate change policy and their implications.(to be Linked with 1.2 of output 2 above) | [14 empty] | 0 |  |  |  |  | 14170.66 | [5 empty] | 1398.16 | 148434.34 |  |  |  | 164003.16 | 164003.16 |  | 164003.16 | 0
|  | Action 3.3.a Technical support to strengthen interpretation and use of adaptation knowledge |  | 32720 | 33920 | [11 empty] | 66640 | [10 empty] | 12729.02 |  |  |  |  | 12729.02 | 12729.02 |  | 12729.02 | 0
|  | Action 3.4.a Special parliamentary seminars convened. • Prepare and conduct parliamentary seminar |  | 81800 | [12 empty] | 81800 | [9 empty] | 80705.15 | [5 empty] | 80705.15 | 80705.15 |  | 80705.15 | 0
Total Output 2 |  |  |  | 6778340.64 | 7518304.61 | 0 | 0 | 2623047.45 | [8 empty] | 16919692.7 | 605288.42 | 1030648.68 | 2541858.36 | 3672458.96 | 210544.44 | 35723.34 | 1810879.88 | 1505581.54 | 1210928.29 | 3428530.51 | 157751.31 | 3140611.12 | 136316.98 | 113208.29 |  | 22196095.09 | 22196095.09 |  | 22196095.09 | 0
Output 3: Climate-resilient policies and measures implemented in priority sectors
| Targets (year 1) Target 2011 | ACTIVITY RESULT 1: Identify available technologies & best practices on climate change adaptation. | In order to meet the Growth and Transformation Plan (GTP) target of building climate resilient green economy in 30% of the districts of the Nation up to the first planning period (2010-14), up-front support was given to participating districts to deploy green technologies. The districts which are included in the first planning period are located in the basins of Gibe Hydro Power Dam, Tekeze Hydro Power Dam, the Reinessance Dam and important Biodiverisity areas of the Rift Valley System of Ethiopia. | [33 empty] | 0
| Results based M&E system implemented. | Action 1.1.a&b Identify technologies from national and international sources, evaluate them, prioritise and prepare a portfolio of appropriate technologies and good practices needed for the implementation of concrete projects validated for the construction of a climate resilient economy | With the above objective green technologies have been identified from the implementation and support of demonstration and quick win projects; best practices identifed from local sources and the one identified from international sources. Base on these sources portfolio of appropariate technologies prepared and the document is published in Amharic language. The technologies have been started to be scalled up in 86 districts. Inorder to identify district specific appropriate green technologies from portfolio document, stakeholders' consultation was conducted with represntatives from the Regional EPAs, zonal and district administrators and relevant experts. Based on consultation at least 5 appropriate technologies were selected. The technologies identifed are based on priority sectors relevant in builidng climate resilient economy. | [29 empty] | 1000000 | 1000000 |  | 1000000 | 0
Action 1.1: c Identify technologies from national and international sources, based on local adaptation capacity needs evaluate them, prioritize and prepare a portfolio of appropriate technologies and good practices needed for implementation of concrete projects validated for the construction of a climate resilient economy, and as appropriate implement resilience building measures like income generation activities; degraded ecosystem rehabilitation in a maximum of 50 selected woredas with regular early warning system established by NMSA.
|  |  | Financial Support was also given to the 86 woredas to procure green technologies idntified to building climate resilient green economy. Some of the green technologies were procured by EPA under the delegation of the woredas and most of them have already disburesed to the woredas. The woredas included in the scaling up of the green technoloiges are: Buma, Marka, Genabusa, Knota, Kendo Dadeya, Humbo, Deguna Fago, Tembaro, Merab Abaya, Arba Minch Zuria, Boreda, Derashe, Dila Zuria, Loka Abaya, Dara, Konta Special Woreda, and Yem Special Woreda in Southern Nations and Nationalities and Peoples Regions; Embalage, Seharti/Samre, Southern Tenben, Hentalo Wajrat, tankua Abergel, Kola Tenben, NaderAdet, Weri Leke, Tahtay Maichew, Medebay Zana, Tselemti , Mekele of the Tigray National RegionalState; Limu Seka, Limu Kosa, Goma, Mana, Kersa, Seka Chekorsa, Sekoru, Tiro Afeta, Omo Nada, Dedo, Arsi Negele, Adame Tulu Jido Combolcha, Adama Town, Adama Woreda, Ada, and Lume districts of the Oromya National Regional State; Mekdela, Woreilu, Tenta, Borena, Legambo, Wegdi, Saint, Mehel Saint, Kelala, Jamma, Dese Zuria, Legehida, Semada, Tach Gaint, Merab Este, Mesrak Este, Dera , Fogera, Farta, Kemkem district, Gozamen, Senan, Bibugne, Machakel, Debre Elias, Anedad, Basoliben, Awabel, Dejen Zuria, Enemaye, Gonecha Sisoenese, Hulet Eje Enese, Shebel Berenta, Enebse Sarmeder, Enarge Enawga, Debay Telat, Debre Markos City, Debremarkos, Dejen, and Bichena, Mota of the Amhara National Regional State. In this suport green enterprises and community organizations have got up-front support to adapt to climate change and build green economy. Vulnerable groups of the society such as women, youth have been given due consideration and attention. | [29 empty] | 21381311.77 | 21381311.77 |  | 21381311.77 | 0
| Action learning for integrated policy measures established in a maximum of 50 woredas, in line with the national strategies. |  |  | 13124566 | 2092022.59 | [11 empty] | 15216588.59 | [15 empty] | 65100 | 65100 |  | 65100 | 0
|  |  | A report on “Africa Adaptation Programme (AAP) Identification of Climate-Resilient Water and Sanitation Technological Options for Schools in Ethiopia” has been prepared and reviewed by the EPA, MOWE, MOH, MOE and participating Regional Bureaus. This report reviews climate change-resilient technologies and practices appropriate for Ethiopian schools, such as solar pump kits, which will be introduced to schools to help them develop resilience to climate change. | [33 empty] | 0
|  | Action 1.2.a&b Assessment of technology needs and local adaptation capacity needs and identify suitable demonstration interventions in priority sectors in a maximum of 50 selected woredas(WFP mplement resilient building measures like income generation activities; degraded ecosystem rehabilitation) | Climate change-resilient technologies and practices suitable for application in Ethiopian schools have been reviewed. Field trial of these approaches has been carried out and linked to the MOE Environmental Education initiative. A School WASH Facility Guideline has been developed in line with the AAP and endorsed by the Ministries of Education, Health and Water and Energy. | [13 empty] | 0 | [15 empty] | 428365.96 | 428365.96 |  | 428365.96 | 0
|  |  | Twelve (12) solar pumps procured for schools were received and distributed to regions, and the boreholes have been dug. The installation of solar pumps and subsequent follow up activities has been delayed due to scarcity of qualified expertise. However, an expert has now been brought on board from the Science and Technology Agency, who will develop a solar pump installation manual. The manual will be ready and installation completed by February 2013, in line with the School WASH guidelines. | [33 empty] | 0
| Process for linking CCA programme results to Development planning in priority sectors agreed with MoFED |  | A total of 20 WASH Staff (ten from UNICEF and ten from the Regional Governments of Tigray, Amhara, Oromia and SNNPR) have been trained in Solar Pump installation and maintenances. These trained staff will be able to use the manual on installation and maintenance of solar-powered pumps and are expected to cascade the training. | [33 empty] | 0
| Targets (year 2) | Action 1.3.a&b In conjunction with relevant sectors of industry and private enterprise, create a portfolio of appropriate technologies and good practices that will support the creation of a CNCR economy |  |  | 1011549.8 | [11 empty] | 1011549.8 | [15 empty] | 1011549.8 | 1011549.8 |  | 1011549.8 | 0
| Two project learning cycles completed by month 24. | Action 1.3:c Identify vulnerable economic sectors and seek to define and implement quick-win projects that adequately demonstrate social, economic and ecological benefits arising from the construction of a carbon neutral, climate-resilient economy. (focusing on the agricultural sector, implement resilient building measures like watershed management and income generation activities) |  | 6276406 | [12 empty] | 6276406 | [15 empty] | 111823.38 | 111823.38 |  | 111823.38 | 0
| Evidence from projects generated, analysed and presented to TWG by end of 2011 | Action 1.4.a&b Identify and map communication pathways for delivery of and feedback on early warning information for improved seasonal responsiveness at local (Woreda) level (Strengthen the existing early warning system with DRMFSS) |  |  | 171100 | [11 empty] | 171100 | [15 empty] | 171000 | 171000 |  | 171000 | 0
| Evidence from evaluation of Action Learning projects used to finalise CCA Strategy by project end. | Action 1.5.a&b Identify vulnerable economic sectors and seek to define quick-win projects that adequately demonstrate social, economic and ecological benefits arising from the construction of a carbon neutral , climate-resilient economy.(Focusing on the agricultural sector, implement resilient building measures like watershed management and income generation activities) |  |  | 1711000 | [11 empty] | 1711000 | [15 empty] | 603117.37 | 603117.37 |  | 603117.37 | 0
| Evidence from projects generated, analysed and presented to TWG by end of 2012 | Action 1.6.a&b Based on the identified vulnerable groups and proposed projects, develop a multi-sectoral action learning programme and agree an integrated action plan with priority sectors. |  |  | 1508400 | [11 empty] | 1508400 | [15 empty] | 1508400 | 1508400 |  | 1508400 | 0
|  | Activity result 2: Identification of the economic potential of adaptation measures that support the attainment of a carbon neutral, climate resilient economy | The support under the scaling up of green technologies are targeting the vulnerable groups of the society mainly jobless youth and women and encourages the flourishig of green enterprises which aim at creating market chain with other sectors. | [13 empty] | 0 | [19 empty] | 0
|  | Action 2.1.a,b,&c Complete a market chain analysis and design market systems in order to establish entrepreneurship and to foster a market for goods and services produced through the implementation of suitable projects in the course of constructing a climate resilient economy | Support was given financially to the consultancy study work of enhancing the eco-tourism potential of Tabor Hill located in Hawasa town of the Southern Nations Nationalities and Peoples Region. The study document is completed and ready for intervention. The study is also aimed at enhancing the enterprenurship of green enterprises and community organizations by enhancing the service giving capacity of the Hill. | 527666 | [12 empty] | #VALUE! | [15 empty] | 990000 | 990000 |  | 990000 | 0
|  | ACTIVITY RESULT 3: A set of integrated policy measures (adaptation approaches) tested in specific AEZ to deliver learning & best practice. | Capacity of EPA is built through workshops, seminars, material support interms of office equipment, and field logistic support. In addition, support was also given to Regional EPA's interms of provision of office equipments and suppoting action learning projects. | [13 empty] | 0 | [19 empty] | 0
|  | Action 3.1.a&b In selected sites integrate top-down climate (early warning) information with local level environmental planning to deliver climate resilient environmental and agricultural practices. | Financial up front support was given to Tigray and Oromya National State to procure green technologies that help in builidng climate resilint economy as well as that enhance the building of green economy. The woredas covered in this upfornt support were Embalage, Seharti/Samre, Southern Tenben, Hentalo Wajrat, tankua Abergel, Kola Tenben, NaderAdet, Weri Leke, Tahtay Maichew, Medebay Zana, Tselemti , Mekele of the Tigray National RegionalState; Limu Seka, Limu Kosa, Goma, Mana, Kersa, Seka Chekorsa, Sekoru, Tiro Afeta, Omo Nada, Dedo, Arsi Negele, Adame Tulu Jido Combolcha, Adama Town, Adama Woreda, Ada, and Lume districts of the Oromya National Regional State. The support was mainly focused on builidng green entrprises and community orgnaizations which will actively particpate in adaptation activities. |  | 598850 | [11 empty] | 598850 | [15 empty] | 598850 | 598850 |  | 598850 | 0
|  | Action 3.1.c Build capacity of EPA to provide support to actors at lower administerative units and communities in environmental planning. | The up front suport has also included districts located under Eastern Gojjam of the Amhara National Regional State namely, Gozamen, Senan, Bibugne, Machakel, Debre Elias, Anedad, Basoliben, Awabel, Dejen Zuria, Enemaye, Gonecha Sisoenese, Hulet Eje Enese, Shebel Berenta, Enebse Sarmeder, Enarge Enawga, Debay Telat, Debre Markos City, Debremarkos, Dejen, and Bichena and Mota. | 2356937 | [12 empty] | 2870237 | [15 empty] | 39220.5 | 39220.5 |  | 39220.5 | 0
|  | Action 3.2.a Use demonstration sites as sample observational network by feeding back ground level weather and impact observation to NMSA to improve downscaling capacity and impact assessments. | The upfront suport and the implemention of those project is aimed at building the adaptive capacity at local level through creating job opportunity and generting income at house hold level as well as to enhance the adaptive capacity of the Great Reinessance Dam, the Gibe Hydropower Plant and the Tekezze Hydro Power Plant, which are key to building green economy, by rehabiliatating the upper catchment of the basins. | [13 empty] | 527666 | [19 empty] | 0
|  | Action 3.2.b Build capacity of EPA to provide support to actors at lower administration units and communities in environmental planning and strengthen documentation of wether impact observations in sellected administration sites |  |  | 513300 | [11 empty] | #VALUE! | [15 empty] | 2045553.39 | 2045553.39 |  | 2045553.39 | 0
|  | Action 3.2:c Establish environmental clubs in schools in action learning areas and support local clubs to contribute to local environmental planning and action. | [14 empty] | 0 | [19 empty] | 0
|  | Action 3.3.a Assess local knowledge systems for environmental management in selected Woredas and integrate with best practices and climate information. | [14 empty] | 0 | [19 empty] | 0
|  | Action3.3.b Assess local knowledge systems for environmental management in sellected woredas and integrate with best practice and impliment demonstration projects that promote local knowledge |  |  | 3283950 | [11 empty] | 3283950 | [15 empty] | 2619689.61 | 2619689.61 |  | 2619689.61 | 0
|  | Action 3.3:c Train teachers to train club members to monitor local environmental plans and action research. | [14 empty] | 0 | [19 empty] | 0
|  | Action 3.4.a&b Empower local communities, working with the industrial sector and private enterprise, to develop their environmental action plan. |  |  | 838000 | [11 empty] | 838000 | [15 empty] | 838000 | 838000 |  | 838000 | 0
|  | Action 3.5.a Set up and apply suitable criteria for assessing project eligibility and install reporting procedures for all selected projects | [14 empty] | 0 | [15 empty] | 200000 | 200000 |  | 200000 | 0
|  | Action 3.5.b Immpliment demo projects and set up and apply suitable criteria for assessing project eligibility and initial reporting procedures for all sellected projects |  |  | 335200 | [11 empty] | 335200 | [15 empty] | 335200 | 335200 |  | 335200 | 0
|  | Action 3.6.a&b Establish environmental clubs in schools in action learning areas and support local clubs to contribute to local environmental planning and action. | Environmental school clubs play a critical role in raising awareness on environmental education and climate change. Supporting this educational practice can provide the means for expanding good practices in CCEE, as well as reaching a broad audience on environment-related issues. Funds were provided to Addis Ababa, Benishangul-Gumuz, SNNP, Somali and Tigray in support of school club activities. |  | 427750 | [11 empty] | 427750 | [15 empty] | 312100.16 | 312100.16 |  | 312100.16 | 0
|  |  | Innovations in schools served as preliminary data for the development of a platform for sharing good practices on school based activities. However, learners’ participation in school clubs varies. For example, out of a sample of 21 schools in four regions, a total of 3,163 club members were identified but the number of members per school club varied from 42 to 1,033 members. | [13 empty] | 0 | [19 empty] | 0
|  |  | The Climate Change and Environmental Education Manual developed in 2011 complements the content of the “Environmental Science” classes and serves to guide the co-curricular learning activities of the Environmental Protection Clubs in schools (grades 5-12). The manual provides a key resource for environmental clubs as virtually all surveyed schools reported the lack of focused materials on CCEE as a major challenge in running environmental club activities. | [33 empty] | 0
|  |  | The initiation of a platform for documenting and disseminating model school-based activities has been established (http://www.ccee-ethiopia.org) and will be periodically updated by the CCEE focal persons in woredas and regions. | [33 empty] | 0
|  |  | The use of school learners to extend the lessons of climate change adaptation to their parents and caregivers is gaining momentum (See School Projects List on Annex VI). | [33 empty] | 0
|  | Action3.7.a&b Train teachers to train club members to monitor local environmental plans and action research. | Addis Ababa, Benishangul-Gumuz, SNNP, Somali and Tigray have been involved in training of teachers and club members in project schools and clusters to develop, implement and monitor local action plans. To date, 2,812 professionals (38% of them female) who are teachers in cluster schools and experts at woreda and regional levels have been trained to facilitate scale up to cover all cluster schools and their satellites. | [13 empty] | 0 | [15 empty] | 361975.24 | 361975.24 |  | 361975.24 | 0
|  | Action 3.8.a,b&c In the selected sites, use school learners to extend the lessons of climate change adaptation to their parents and carers | Throughout the project, a series of training workshops were undertaken for mini-media clubs in AAP schools in Amhara, Oromia, Somali and Addis Ababa. The objective of the training was to build the capacity of club members and teachers to lead mini-media clubs in programme production, including environmental protection, using modern communication equipment. Each school was represented in the training by two students (mini-media club members) and one teacher (heading the club). | [13 empty] | 0 | [15 empty] | 41850 | 34875 |  | 34875 | 6975
|  |  | Funds provided to Addis Ababa-based AAP schools to strengthen community-school linkages on climate change adaptation have been used by learners in community awareness and mobilization, using mini-media equipment including microphones, radios and cassettes for awareness and mobilization activities. (See Annex VI) | [33 empty] | 0
|  | ACTIVITY RESULT 4: Generate an evidence base for refining policy measures and informing long-term planning. | [14 empty] | 0 | [19 empty] | 0
|  | Action 4.1.a,b&c Local Environmental clubs mobilise the youth to monitor local level adaptation practices to build awareness of climate change. | This activity was not undertaken in this phase of the project. There was need to energize environmental clubs first, and then conduct community awareness and mobilization activities prior to engaging the youth to participate in monitoring of climate change in their localities. The schools have already started doing outreach activities with the community and out-of school youth. This component will be incorporated into 2013 plans. | [13 empty] | 0 | [15 empty] | 55800 | 46499 |  | 46499 | 9301
|  | Action 4.2.a Using action learning evidence base: | [14 empty] | 0 | [19 empty] | 0
|  | · Produce a detailed and budgeted programme plan to upscale early warning system to improve adaptive capacity. | [14 empty] | 0 | [19 empty] | 0
|  | · Draw adaptation lessons and produce/revise best practice recommendations. | [14 empty] | 0 | [19 empty] | 0
|  | · Draw out evidence for informing long-term planning processes | [14 empty] | 0 | [19 empty] | 0
Total Output 3 |  |  |  | 22285575 | 12491122.39 | 0 | 0 | 0 | [8 empty] | 34776697.39 |  |  | 0 | 0 | 0 | 0 | [9 empty] | 34718907.18 | 34702631.18 |  | 34702631.18 | 16276
Output 4: Financing options to meet national adaptation costs expanded at the local, national, sub-regional and regional levels
| Targets (year 1) Climate change costs on key development sector budget identified by end year 1. | ACTIVITY RESULT 1: National budgeting systems incorporate climate-related implications on spending priorities. | As a starting point to establish national investment facility a concept paper is prepared to Nordic Climate Facility (NCF). This concept paper was prepared in collaboration with GAIA Association to secure additional funding. Fund was also mobilized from UK Government under the SCIP programme amounting to 482,000 Pounds. Other funds are also being mobilized like the one form UNDP Core Fund for CRGE strategy implementation amounting 5.2million USD in which four sectors are involved in the implementation. | [33 empty] | 0
| Initial assessment of climate change costs on key development sectors by end year 1. | Action 1.1.a Undertake financial risk assessments of climate change for priority sectors. | Because of the continuous sensitization and consultation process conducted by AAP support on the need for having climate financing option, currently, a dynamic funding mechanism called Ethiopian Climate Resilient Green Economy Facility has been established and has become operation which was evolved from the concept of establishing “multi-stakeholders trust fund”. The Facility is hosted under Ministry of Finance and Economic Development and the mechanism to access the fund is being developed under continuous process. | [33 empty] | 0
| Targets (year 2) | Action 1.1.b Budget implications of climate change on priority sectors assessed and guidelines to mainstream climate change at regional and local level prepared | A guide on mainstreaming climate change issues in budget system is treated under the Climate Change Mainstreaming Guideline prepared by the AAP intervention. The Guideline threats the mechanism of incorporation budgeting issues to climate change at different level: Programme, Project and local plan level. | [13 empty] | 0 | [19 empty] | 0
| Guidelines and procedures established for accessing international climate change funding mechanisms prepared. Guidelines and procedures established for including climate change budgeting and Mechanism to Motivate and Support, Reward Results (mMSRr) prepared; options for accessing international climate change funding mechanisms identified. | Action 1.1:c Finalize the guideline to mainstream climate change at regional and local budget and expenditure and edit and make ready for use. | [5 empty] | 17590 | [8 empty] | 17590 | [19 empty] | 0
| Targets (year 3) | Action 1.2.a Climate change budget implications for priority sectors assessed and tradeoffs measured. |  |  | 167600 | [11 empty] | 167600 | [19 empty] | 0
| regulatory options on the establishment of national environmental finanial mechanism prepared and presented to Env Council by end Yr 3. | Action 1.2.bundertake training wokshops on the application of the guidelines mentioned under aciton 1.1 above. | [14 empty] | 0 | [19 empty] | 0
| A set of options for meeting adaptation costs agreed and implementation plans prepared by MoFED.Regulatory options on the establishment of national environmental finanial mechanism (CRGE Facility) prepared and presented to Env Council by end Yr 3. | Action 1.2:c The national capacity to leverage finance from the private sector, financial institutions or insurance companies will be enhanced through the development of a national system for the greater engagement of micro-finance institutions in area of climate change. | [5 empty] | 263850 | [8 empty] | 263850 | [15 empty] | 263850 | 263850 |  | 263850 | 0
|  | Action 1.3.a Develop options for adjusting domestic national budgets to accommodate CC adaptation needs, including trade-off scenarios. |  |  | 167600 | [11 empty] | 167600 | [19 empty] | 0
|  | Action 1.4.a Development of a national investment facility for mobilising and managing funds for cross-sectoral climate change adaptation responses supported. |  | 81800 | [12 empty] | 81800 | [9 empty] | 1575 | [5 empty] | 1575 | 1575 |  | 1575 | 0
|  | ACTIVITY RESULT 2: Local Fiscal Regulatory options for financing and incentivising climate change adaptation assessed. | As mechanism of addressing financing and incentivising climate change adaptation effort, a concept of Mechanism to Motivate, Support and Reward Results on Building Climate Resilient Green Economy (mMSRr) is developed by EPA. The design of this system will address the issue of enhancing the efforts of building Climate Resilient Green Economy at different level, especially at grass root community level through providing support and providing reward for good results. The launching of this mechanism was launched at 4 sites by AAP Support (in Adama, Oromya National Regional State; in Hawassa, Southern Nations, Nationalities and Peoples Region, in Bahir Dar and Dessie in Amhara National Regional State. | [13 empty] | 0 | [19 empty] | 0
|  | ACTIVITY RESULT 2: Prepare a local fisical regulatory approach and mechanisim to motivate support, and reward results achieved in building a Climate Reselinet Green Economy (CRGE) in priority sectors. | [14 empty] | 0 | [19 empty] | 0
|  | ACTIVITY RESULT 2: Approaches to accessing international CC fund identified, tested and exploited successfully. | [14 empty] | 0 | [19 empty] | 0
|  | Action 2.1.a Assess current regulatory framework, regulatory capacity and relevance of international best practices with the support of specialist technical expertise. |  | 163600 | 167600 | [11 empty] | 331200 | [19 empty] | 0
0
0
|  | Action2.1.b Rules of proceure on the operation of mMSRr prepared |  |  | 496746.34 | [11 empty] | 496746.34 |  |  | 32047.01 | 80689.36 | 49271.65 |  | 308884.32 | [8 empty] | 315642.34 | 315642.34 |  | 315642.34 | 0
|  | Action 2.1:c Finalizing and convening 3 consultation forums with donors on the national system to operationalize a result based payment system in order to up-scale the technologies and good practices obtained during the life span of AAP and continues beyond 2012. | [5 empty] | 52770 | [8 empty] | 52770 | [19 empty] | 0
|  | Action 2.2.a Develop options for ‘green taxes’ and assess cost-benefit and capacity trade offs of options with the support of specialist technical expertise. |  | 163600 | 335200 | [11 empty] | 498800 | [19 empty] | 0
0
|  | Action 2.2.b Financial mechanism (CRGE Facility) to solicit and channel resources in support of actions under the mMSRr agreement establishd | [14 empty] | 0 |  |  |  | 9620 | [11 empty] | 9620 | 9620 |  | 9620 | 0
|  | Action 2.3.a Enhance the access to carbon trading mechanisms in different sectors for low-carbon climate change adaptation with the support of specialist technical expertise |  | 327200 | 167600 | [11 empty] | 494800 | [19 empty] | 0
|  | Action2.3.b Governance arrangment for the implementation of mMSRr prepared |  |  | 502800 | [11 empty] | 502800 |  |  |  | 16234.9 | [11 empty] | 16234.9 | 16234.9 |  | 16234.9 | 0
|  | Action 2.4.b Trainning on the determination of gographic, sectoral, coverage of actors | [14 empty] | 0 | [19 empty] | 0
|  | Action 2.5.b Training on preparation of Readiness Plan to participate under mMSRr | [14 empty] | 0 | [19 empty] | 0
|  | Action 2.6.b Training on how to determine the Baseline for the Provision of Reward (BPR) | [14 empty] | 0 | [19 empty] | 0
|  | Action 2.7.b Training on the peparation and approval of local investment plan to build CRGE | [14 empty] | 0 | [19 empty] | 0
|  | Action 2.8.b Trainnig on verification and issuance of Reward | [14 empty] | 0 | [19 empty] | 0
|  | ACTIVITY RESULT 3: Approaches to accessing international CC fund identified, tested and exploited successfully. | One approach to accessing international CC fund is through establishing CRGE Facility which is established in 2012. AAP has supported the establishment of this facility through continuous sensitization of different forums on climate change adaptation to different stakeholders at different times. Currently the Facility has got a seed money from Austrian Government and various international funding agencies have shown to support the national implementation of the Green Economy Strategy through the Climate Facility. | [13 empty] | 0 | [19 empty] | 0
|  | Action 3.1.a&b Increase awareness amongst public agencies, community organizations, financial planners, sector project developers and civil society networks to international adaptation funds and their accessibility, |  | 163600 | [12 empty] | 163600 | [15 empty] | 155250 | 155250 |  | 155250 | 0
0
|  | Action 3.2.a&b Train sector institutions in the methods for developing projects for international climate change funding. |  |  | 83800 | [11 empty] | 83800 | [19 empty] | 0
|  | Action 3.3.a Prepare projects based on action research sites and pilots that meet the standards of public or private technology / finance providers (to be linked action 2.3 of output 2) | [14 empty] | 0 | [19 empty] | 0
|  | Action 3.3.b Enhance access to carbon trading mechanisms in different sectors for building Cargon Resilient Green Economy (CRGE) with the support of specialist technical expertise | [14 empty] | 0 | [19 empty] | 0
|  | Action 3.4.a&b Apply for funding from targeted sources with the objective of mobilising significant funds from existing financial mechanisms (or from new ones to be established pursuant to the Copenhagen accord). |  |  | 117320 | [11 empty] | 117320 | [19 empty] | 0
Total Output 4 |  |  |  | 899800 | 2206266.34 | 0 | 0 | 334210 | [8 empty] | 3440276.34 |  |  | 32047.01 | 106544.26 | 49271.65 | 0 | 308884.32 |  | 0 | 1575 | 0 | 0 | 0 | 0 |  | 762172.24 | 762172.24 |  | 762172.24 | 0
Output 5: Knowledge on adjusting national development processes to fully incorporate climate change risks and opportunities generated and shared across all levels
| Targets (year 1) | ACTIVITY RESULT 1: Build a detailed knowledge base on climate change impacts in priority sectors. | [34 empty] | 0
| Communication Strategy produced by end month 6. | Action 1.1.a&b Knowledge management system established with advice of knowledge management specialists and shared with the ALM. | Stakeholders analysis and interview in relation with best practices of Managing Environmtnal Resources to Enable Transition to More Sustainable Livelihood (MERET) that are contributing to building resilience and reducing greenhouse gases from the atmosphere, field level analysis of the best practices including discussion with the relevant experts in the field, beneficiary community members and management committee, field observation in relation with the results achieved and documentation. |  | 171000 | [27 empty] | 171100 | 171100 |  | 171100 | 0
| Knowledge management system in place by end year 1. Knowledge Management system established by the end of 2012. Communication and knowledge mangment strtaegy developed by the end of 2012. | Action 1.1:c Criteria development, analysis, prioritization and documentation of best practices for building a climate resilient green economy. | [30 empty] | 174320 | 174320 |  | 174320 | 0
| Targets (year 2) | Action 1.2 Establish databank of all CCA projects and initiatives in Ethiopia. | Financial and technical suport were given to Limu Seka, Limu Kosa, Goma, Mana, Kersa, Seka Chekorsa, Sekoru, Tiro Afeta, Omo Nada, Dedo, Arsi Negele, Adame Tulu Jido Combolcha, Adama Town, Adama Woreda, Ada, and Lume districts of the Oromya National Regional State to implement projects that enhance the adaptaive capacity at local level. The focus in those districtes was also to enhance the adatptive capacity of Gibe Hydropower Generation Plant which significantly contribute to the building of green economy by conserving the upper catchment of the Gibe River Basen. | [13 empty] | 0 | [19 empty] | 0
| Information generated shared with relevant stakeholders through appropriate fora from beginning in year 2. | Action 1.2.b Impliment demo projects and establish data banks of all CCA projects and initiatives in Ethiopia. Using action learning evidence based produce a detail and budgeted program plan toupscale early warning system to improve addaptive capacity. Drow addaptation lessons and produce/revise best practice recomendations. Drow output evidence for informing long term planning. | The up front suport under this component has also included districts located under Eastern Gojjam of the Amhara National Regional State namely, Gozamen, Senan, Bibugne, Machakel, Debre Elias, Anedad, Basoliben, Awabel, Dejen Zuria, Enemaye, Gonecha Sisoenese, Hulet Eje Enese, Shebel Berenta, Enebse Sarmeder, Enarge Enawga, Debay Telat, Debre Markos City, Debremarkos, Dejen, and Bichena and Mota which are districts located under the Great Reinessance Dam. |  | 3994600 | [11 empty] | 3994600 | [15 empty] | 5102442.63 | 5102442.63 |  | 5102442.63 | 0
| In depth case studies from action learning sites completed, results fed into knowledge base and disseminated | Action 1.2.c Review and develop minimum criteria for documentaiton of best practices and document 5 to 7 selected best action learning projects (soil, livestock, energy, forest west, water and transport) | The lessons learnt from the implementaion of those projects are being documented. The lesson learnt has contributed in informing long term planning in building the adaptive capaicty of key infrastructures. | [13 empty] | 0
| Set of best practices prepared and disseminated for adaptation approaches | Action 1.3.a Technical and financial support for the generation of evidence from target demonstration areas for assessing the: vulnerability of communities in different agro-ecological zones and climate variability and risk assessments. |  |  | 171100 | [11 empty] | 171100 | [15 empty] | 102139.5 | 102139.5 |  | 102139.5 | 0
|  | Action 1.3.b Technical and financial support for the generation of evidence from target demonstration areas for assessing the vulnerability of communities in different agro-ecological zone and climate variability and risk assessment. | [14 empty] | 0 | [19 empty] | 0
|  | Action 1.3.c Review existing knowledge management systems/platforms and develop Knowledge Management Strategy (platform) | [14 empty] | 0 | [19 empty] | 0
|  | Action 1.4.a Assess and Extract adaptation learning for key sectors. | [14 empty] | 0 | [19 empty] | 0
|  | Action 1.4.b Document best practices developed from action learning in output 3 and (where relevant) minimum standards developed | [14 empty] | 0 | [19 empty] | 0
|  | 1.4.c Participate in knowldeger management workshop and support national workshops | [14 empty] | 0 | [19 empty] | 0
|  | Action 1.5.a Document best practices developed from action learning in Output 3 and (where relevant) minimum standards developed. | Package of print and video documentaries has been developed using seven demonstration projects as Climate Adaptation good practices, which were selected in collaboration with EPA based on agreed criteria. This documentation package will be shared with key stakeholders during the dissemination workshop. Moreover, EPA will be taking the lead to pursue further media dissemination of the video documentaries to support its advocacy efforts for the replication of the demonstration projects. | [13 empty] | 0 | [15 empty] | 37200 | 37200 |  | 37200 | 0
|  | 1.5.c Review selected AAP communication strateges and develop communciation strategy | [14 empty] | 0 | [19 empty] | 0
|  | 1.6.c Develope guide book for dessemination of information and organize national/regional dialogue forums for journalists. | [14 empty] | 0 | [19 empty] | 0
|  | 1.7.c Dessimination of best practice documentaions during jounalist training and knowledge management workshop and shared to relevant stakeholders. | [14 empty] | 0 | [19 empty] | 0
|  | ACTIVITY RESULT 2: Climate Change Information Strategy established and implemented | [14 empty] | 0 | [19 empty] | 0
|  | Action 2.1.a&b Develop gender sensitive climate change Communication Strategy. | The AAP Communication and Knowledge Management strategies underwent a thorough review by partners from selected sectors on 19 December 2012. The partners will participate in a full day review meeting to finalize the strategy during the month of January 2013. These partners include the GCAO, MOE, MOH, MOA, MOWE, MOWCYA, and from Civil Society organizations the Forum for Environment and Lem Ethiopia, as well as teams from EPA, UNDP, WFP and UNICEF. The final strategy will be presented during the dissemination workshop planned to take place at the end of January 2013. | [13 empty] | 0 | [15 empty] | 30782.91 | 30782.91 |  | 30782.91 | 0
|  |  | A multi-function interactive web-based knowledge management and A multi-function interactive web-based knowledge management and sharing platform was developed with the aim of supporting EPA to sustainably promote knowledge sharing among its national and regional partners, even beyond the AAP. Training on the management of the platform is planned towards the end of January 2013 for EPA’s Information Technology (IT) team, directorate focal persons and regional EPA offices. The platform can be temporarily accessed through the following link: sharing platform was developed with the aim of supporting EPA to sustainably promote knowledge sharing among its national and regional partners, even beyond the AAP. Training on the management of the platform is planned towards the end of January 2013 for EPA’s Information Technology (IT) team, directorate focal persons and regional EPA offices. The platform can be temporarily accessed through the following link: ://www.yesakor.com/eccf/index.php | [33 empty] | 0
|  | Action 2.2.a&b Prepare CCA Information management guidelines to ensure consistent messages disseminated. | Information Management Guidelines for journalists and producers have been drafted, aimed at ensuring consistent dissemination of messages. A desk review was undertaken to review Information Management Guidelines from other AAP countries and the Nairobi AAP team shared experiences in developing these guidelines and training of journalists. Trainingon these guidelines will be delivered jointly with EPA in January 2013. GCAO has been provided with funding to organize further guideline familiarization sessions, followed by a series of audio-visual documentation and dissemination of key CCA issues in the coming six months. | [13 empty] | 0 | [15 empty] | 25652.42 | 25652.42 |  | 25652.42 | 0
|  | Action 2.3.a&b Disseminate Best Practice and Learning from the programme and sister programmes. | By the end of January 2013, EPA and AAP partners will organize a dissemination workshop to share seven best practice products featuring seven demonstration projects identified from selected AAP partner implementation sites in Tigray, Addis Ababa and Amhara. For each of these projects, the documentation package includes a narrative report, a 12 minute audiovisual documentary and a brochure. The AAP regional team provided technical guidance to the process, particularly the selection criteria for the best practices, documentation templates and documentation process tools. The documentaries are expected to support EPA’s advocacy efforts to replicate the demonstration projects | [13 empty] | 0 | [15 empty] | 20521.94 | 20521.94 |  | 20521.94 | 0
|  | Action 2.4.a&b Building on enhanced climate capacity, disseminate Climate Information to inform planning and investment programmes. | Training of EPA team and regional focal persons on Knowledge Management strategy roll-out and platform management is planned during the final dissemination workshop in January 2013. Three key activities are planned:  Dissemination workshop for key stakeholders both at federal and regional level;  An information management guideline for journalists aimed at ensuring consistent message dissemination is finalized and training of journalists will be carried out in January 2013 as part of the final events;  An interactive web-based knowledge sharing platform is developed, and platform management training for EPA’s regional and federal level teams will be provided. | [13 empty] | 0 | [15 empty] | 25652.42 | 25652.42 |  | 25652.42 | 0
Total Output 5 |  |  |  | 0 | 4336700 | 0 | 0 | 0 | [8 empty] | 4336700 | [15 empty] | 5689811.82 | 5689811.82 |  | 5689811.82 | 0
Output 6: Project management and Governance
| Target of 2012: Effective management of AAP activities. Outputs and targets set by AAP achieved. | CTIVITY RESULT 1: Effectiveness and efficiency of project management is optimised through the use of experienced national and international resources | A full time project coordiantor is assigned starting June 2012 and was funcitonal until February 2013. As a result the implemtnaiton of AAP activities have become more effective. | [33 empty] | 0
|  | Action 1.1.c Implementation of the AAP project is made more effective and efficient by appointing a full time Project Manager (EPA) | The project management unit is supported by the recruitment of 1 assistant project coordinator and 1 accountant |  |  |  | 26190 | 211080 | [8 empty] | 237270 | [14 empty] | 52770 | 158310 | 158310 |  | 158310 | 0
|  | Action 1.2:c Support provided to the PMU with the 2 local assistant project coordinators and the 2 local accountants. | 8 Regional Assistant Project Coordiantors were emplyed in 7 Regional States and 1 City Administrations starting July 2012 and the implemtnation of AAP at Regional level has became effective |  |  |  |  | 114335 | [8 empty] | 114335 | [15 empty] | 61750 | 61750 |  | 61750 | 0
|  | Action 1.3:c Recruit 11 full time expers to support and speed up Regional Implementaion of AAP | AAP implementation has been supported by the assignment t of 1 short time international consultant based at UNDP. |  |  |  | 87300 | 703600 | [8 empty] | 790900 | [15 empty] | 703600 | 703600 |  | 703600 | 0
|  | Action 1.4:c Support is provided to the AAP Project Management team by the use of 2 "Implementation support consultants" working as part of the AAP PMU (EPA) | AAP implementation has become effective by the support givenby the high level expert from Regional AAP Coordination Office |  |  |  |  | 562880 | [8 empty] | 562880 | [15 empty] | 562880 | 562880 |  | 562880 | 0
|  | Action 1.5:c Support is provided to the AAP Project Management team by the use of 1 "Implementation support consultant" working as part of the AAP at UNDP for 2 months period | Two steering committee meetings have been conducted since the revision of the last annual workplan. On the meeting the steering committee has passed major decisions that helped the effectiveness of AAP implementation. |  |  |  |  | 299030 | [8 empty] | 299030 | [15 empty] | 299030 | 299030 |  | 299030 | 0
|  | Action 1.6:c Liason and oversight misson (from Regional Office) | [14 empty] | 0 | [19 empty] | 0
|  | Action 1.7:c Set up ad hoc Management Committee to provide hands-on leadership | [5 empty] | 31662 | [8 empty] | 31662 | [19 empty] | 0
|  | Action 1.8:c Executive Task Force to meet every 2 weeks in Q1 and monthly thereafter | [5 empty] | 31662 | [8 empty] | 31662 | [19 empty] | 0
|  | Action 1.9:c Support the establishment and conduct of Project Steering Committee meetings: monthly in Q2 and then once per quarter to the end of the year | [5 empty] | 87950 | [8 empty] | 87950 | [15 empty] | 6294 | 6294 |  | 6294 | 0
Total Output 6 |  |  |  | 0 | 0 | 0 | 113490 | 2042199 | [8 empty] | 2155689 | [14 empty] | 52770 | 1791864 | 1791864 |  | 1791864 | 0
Output 7: Knowledge management
| Target of 2012: Knowledge and best practices across eastern Afria shared. | Action 1.1:c Technical assistant and oversight on knowledge management |  | 0
|  | Action 1.2:c Major Eastern African Knowledge Management Confrernce |  | 0
Total Output 7 |  |  |  | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 | [15 empty] | 0 | 0
Grand Total |  |  |  | 32663115.64 | 34940253.94 | 0 | 113490 | 8899256.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76616116.03 | 605288.42 | 1030648.68 | 3719293 | 3781243.22 | 259816.09 | 35723.34 | 2146918.33 | 1505581.54 | 1313962.2 | 3655179.08 | 157751.31 | 3739491.84 | 136316.98 | 133288.29 | 52770 | 77967989.69 | 77951713.69 | 0 | 77951713.69 | 16276 | 0
NB: Actity codes refers to different repogramming periods.
Prepared by: _____________________
Date:______________________________
Signature:_________________________________
176009563.37