Strengthening the Marine and Coastal Protected Areas of Russia

Russian Federation

GEF Agency: United Nations Development Programme

Executing Agency: Federal Ministry of Natural Resources and Environment

GEF Biodiversity Focal Area, Operational Program 1, 2

Strategic Objective BD-1

Full-sized Project: GEF ID: 3518, UNDP PIMS: 4051

UNDP Atlas Award 00056530; Atlas Project ID 00069210

Mid-term Evaluation

November 5, 2012

Josh Brann, International Consultant, Brann.Evaluation@gmail.com

Table of Contents

I. Executive Summary	IV

II. Introduction: Evaluation Scope and Methodology	1

III. Project Overview and Development Context	2

A.	Development Context	2

B.	Concept Development and Project Description	4

i.	Concept Background	4

ii.	Project Description	4

iii.	Project Timing and Milestones	7

C.	Russia MCPAs Project Relevance	8

i.	Relevance at the National Level	8

ii.	Relevance to Multilateral Environmental Agreements	9

iii.	Relevance to GEF Strategies, Priorities and Principles	10

IV. Project Design and Implementation	10

A.	Elements of Project Design, Planning and Development	10

i.	Key Aspects of Project Design	10

B.	Project Management and Cost Effectiveness (Efficiency)	12

i.	Russia MCPAs Project Implementation Arrangements	12

ii.	Project Management and Implementation	15

iii.	Russia MCPAs Financial Planning by Component and Delivery	16

iv.	Russia MCPAs Planned and Actual Co-financing	19

v.	Flexibility and Adaptive Management	20

vi.	UNDP Project Oversight	21

V. Russia MCPAs Project Performance and Results (Effectiveness)	22

A.	Progress Toward Achievement of Anticipated Outcomes	22

i.	Outcome 1: Improved MCPA system and Institutional-level capacity enables the expansion of the MCPA system	24

ii.	Outcome 2: MCPA management know-how is demonstrated, expanded and reinforced	31

iii.	Outcome 3: Strengthened MCPA system effectively captures knowledge and enables replication of best practice	36

B.	Additional Results	37

C.	Progress Toward the Objective by Logframe Indicators and Targets	37

VI. Key GEF Performance Parameters	42

A.	Stakeholder Participation in Development and Implementation	42

B.	Sustainability	46

i.	Financial Risks to Sustainability	47

ii.	Sociopolitical Risks to Sustainability	47

iii.	Institutional Framework and Governance Risks to Sustainability	47

iv.	Environmental Risks to Sustainability	48

C.	Catalytic Role: Replication and Scaling-up	48

D.	Project Monitoring, Reporting and Evaluation	48

E.	Project Impacts, and Global Environmental Benefits	50

VII. Main Lessons Learned and Recommendations	51

A.	Lessons from the Experience of the Russia MCPAs Project	51

B.	Russia MCPAs MTE Recommendations	53

C.	Russia MCPAs Project Mid-term Evaluation Ratings	56

VIII. Annexes	60

Acronyms

APR	Annual project review

CBD	Convention on Biological Diversity

CEO	Chief Executive Officer

GEF	Global Environment Facility

GIS	Geographical Information System

ha	Hectares

IAS	Invasive alien species

Km	Kilometers

M&E	Monitoring and evaluation

MSP	Medium-sized Project

N/A	Not applicable

N/S	Not specified

NGO	Non-governmental organization

PA	Protected area

PIR	Project implementation Review

PMIS	Project Management Information System

PMU	Project Management Unit

PSC	Project Steering Committee

ROtI	Review of Outcomes to Impacts

UA	Unable to assess

UNDP	United Nations Development Programme

USD	United States dollars

# Executive Summary

- PROJECT DESCRIPTION AND OVERVIEW

| Project Title: | Strengthening the Marine and Coastal Protected Areas of Russia |  |  |  |
| --- | --- | --- | --- | --- |
| GEF Project ID: | 3518 |  | At endorsement (million US$) | At completion (million US$) |
| UNDP Project ID: | 4051 | GEF financing: | $4.00 | N/A |
| Country: | Russian Federation | IA/EA own: | $0.00 | N/A |
| Region: | ECA | Government: | $8.93 | N/A |
| Focal Area: | Biodiversity | Other: | $0.47 | N/A |
| FA Objectives, (OP/SP): | SP-1 | Total co-financing: | $8.50 | N/A |
| Executing Agency: | Russian Federal Ministry for Natural Resources and Environmental Protection | Total Project Cost: | $13.40 | N/A |
| Other Partners Involved: | Multiple relevant stakeholders not directly responsible for execution. | ProDoc Signature (date project began): |  | June 8, 2009 |
|  |  | (Operational) Closing Date: | Proposed: December 31, 2013 | Actual: N/A |

The Russia MCPAs project is classified as a Global Environment Facility (GEF) Full-sized Project (FSP), with total GEF support of $4.00 million (not including $0.07 in project development funding), and originally proposed co-financing is $9.40 million United States dollars (USD), for a total project budget of $13.40 million USD. The United Nations Development Programme (UNDP) is the GEF Agency, and the project is executed under UNDP’s national execution (NEX) modality, with the Russian Federal Ministry of Natural Resources and Environment (MNRE) as the national executing partner.

According to the project document, the overall project goal is “Conservation and sustainable use of globally significant coastal and marine biodiversity.” The project objective is “To facilitate expansion of the national system of marine and coastal protected areas and improve its management effectiveness.” The project objective is planned to be achieved through three main outcomes:

Outcome 1: Improved MCPA system and Institutional-level capacity enables the expansion of the MCPA system

Outcome 2: MCPA management know-how is demonstrated, expanded and reinforced

Outcome 3: Strengthened MCPA system effectively captures knowledge and enables replication of best practice

According to GEF and UNDP evaluation policies, mid-term evaluations are required practice for GEF funded FSPs, and the mid-term evaluation was a planned activity of the monitoring and evaluation plan of the Russia MCPAs project. This mid-term evaluation reviews the actual performance and progress toward results of the project against the planned project activities and outputs, based on the standard evaluation criteria: relevance, efficiency, effectiveness, results and sustainability. The evaluation assesses project results based on expected outcomes and objectives, as well as any unanticipated results. The evaluation identifies relevant lessons for other similar projects in the future in Russia and elsewhere, and provides recommendations as necessary and appropriate. The evaluation methodology was based on a participatory mixed-methods approach, which included two primary elements: a) a desk review of project documentation and other relevant documents; and b) interviews with key project participants and stakeholders. The evaluation is based on evaluative evidence from the start of project implementation (October 2009) through July 2012 (with expected project closure in December 2013), and includes an assessment of issues prior to approval, such the project development process, overall design, risk assessment and monitoring and evaluation (M&E) planning. The desk review was begun in July 2012, and the evaluation mission was carried out from July 30 – August 3, 2012.

- MAIN EVALUATION CRITERIA

At the mid-point the project is progressing with execution of the project workplan, and positive results have been achieved under multiple specific project outputs. At the same time, the project has faced some challenges, progress is slower on some fronts than expected, and meaningful work needs to be done in the second half of implementation to make significant progress toward the objective. Based on the evaluative evidence collected throughout the mid-term evaluation process, the project’s Progress Toward Overall Project Results is rated moderately satisfactory. Additional work is required toward catalyzing a broad MCPAs constituency of government institutions, which is critical in the context of overlapping and conflicting institutional mandates related to the management of marine and coastal resources. In particular, strengthened cooperation with the Federal Agency of Fisheries (FAF) is of utmost importance for further implementation of multiple project activities. Generally speaking, the project faces the difficult situation found in many countries of unclear, competing, and contradictory government institution mandates in the realm of marine and coastal resources. There are also opportunities for enhanced engagement with other sectors, such as transportation and energy, with both public and private stakeholders.

The overall project concept and objective is considered relevant. Russia’s system of MCPAs continues to develop, with multiple new MCPAs planned for establishment. Strengthening the capacity of the government to manage this system, and engaging other relevant stakeholders in the process, is vital to effective conservation of Russia’s globally significant marine and coastal biodiversity. This is especially the case in the face of expected increasing threats from oil and gas development, unsustainable fishing practices, climate change, and other issues. Generally speaking, the project supports implementation of relevant Russian laws and policies related to the conservation of marine and coastal biodiversity, and supports Russia’s implementation of the Convention on Biological Diversity. The project is also clearly relevant to the GEF’s biodiversity focal area strategic objective on protected areas. While the project objective is relevant, the actual design of project activities could have been strengthened through improved structure, an explicit theory-of-change analysis, increased input and ownership from stakeholders, and increased relevance to the current and practical realities of strengthening Russia’s system of MCPAs.

Based on all aspects of project implementation and financial management, project efficiency is rated moderately satisfactory. There has been slow progress but no critical efficiency issues thus far, although as of June 30, 2012 only a little more than 40% of the GEF resources had been delivered over approximately 63% of the planned project implementation period. To reach the project objective, the second half of project implementation will need to be more active, dynamic, adaptive and participatory. All project financial management aspects are in-line with UNDP policies and procedures, Russian legal requirements, and comparable norms and standards for multilateral projects in Russia. Budgeted project management costs are at the GEF-stipulated maximum threshold of 10% of GEF resources. UNDP has provided the appropriate project financial management support, and consistently worked to ensure the project remains focused on results. There are also opportunities for strengthening the implementation approach going forward; the current implementation arrangements for the project are not fully meeting the needs for project implementation, and the project mid-term presents a good opportunity for further adaptive measures. The project is executed by a project team staffed by UNDP-contracted individuals; the MNRE (the national executing agency) is working well with the project team and UNDP, but may need to play a more active role in integrating the project objective and resources with national priorities related to the development of the full system of MCPAs.

The Overall Project Outcome Rating is considered moderately satisfactory, while progress toward the overall project objective (effectiveness) is considered moderately unsatisfactory. Key results produced thus far include:

- Strengthening management effectiveness of the Commander Islands Zapovednik on multiple fronts, including conducting a management audit that facilitated increased financial resources allocated for the reserve from the MNRE, and design of a nationally unprecedented environmental monitoring program;

- Initiation and development of management plans for multiple MCPAs, including the Far Eastern Marine Reserve and Russian Arctic National Park;

- Training on hazardous material spill response in Gulf of Finland;

- Support for key steps toward establishment of Ingermanland Reserve in the Gulf of Finland, including development of required technical documentation for government approval;

- Assessment of the situation with respect to invasive alien species in the Far Eastern Marine Reserve;

- Support for collaboration and cooperation among marine research stations and MCPAs;

- Progress toward development of a system-wide approach to the assessment of management effectiveness for MCPAs.

The results achieved thus far have been valuable, but overall results are limited relative to the expected end-of-project status. A key result, the establishment of the Ingermanland Reserve remains an ongoing process, though there is recent positive progress on this issue; establishment of the reserve is a lynchpin for multiple additional project activities in the Gulf of Finland. At this stage of implementation the project has not yet generated significant progress toward incremental results at the systemic level. To make significant progress toward the project objective and generate Global Environmental Benefits the project will need to achieve much more during the second half of the project than it has in the first half.

Mid-term evaluations are not well placed to provide ratings on sustainability, as many more activities that may positively or negatively influence sustainability remain to be implemented, but a rating on sustainability is provided here as required. Overall sustainability is considered moderately unlikely. At this stage of project implementation it is unclear what financial resources will be required to sustain eventual project results, and therefore not possible to assess financial risks to sustainability. There is a need to strengthen stakeholder ownership and buy-in among the full range of stakeholders, especially the critical government stakeholders, without which the project’s lasting impact will be limited. There are legal and policy challenges for effective MCPA management, and government institutional mandates are not fully in-sync. There is currently not adequate national political will to institute effective mechanisms for coordinated government management of marine and coastal resources. Nonetheless, the eventual project results should be able to continue positively contributing to improved management of MCPAs in Russia. The project results on the ground thus far are limited, and therefore are not subject to specific environmental risks. At the same time, the key environmental risks to Russia’s MCPAs (as outlined in the project document) remain pertinent, particularly in the three primary project pilot sites.

- PRIORITIES AND RECOMMENDATIONS FOR THE REMAINING IMPLEMENTATION PERIOD

The project design did not serve the project well in facilitating a results-based approach for undertaking specific activities, and the project needs to consciously avoid developing a “Christmas tree” type approach where many small “priorities” are supported but do not result in a whole greater than the sum of its parts. If it is well-focused, a project of this size and scope has the potential to deliver significant results at least at the outcome level. Some priorities for the second half of implementation include:

- Increase the strategic approach by focusing on activities that have potential catalytic effects at the systemic level, such as piloting implementation of national standards and guidelines for effective MCPA management; establishment, testing, and sharing of tools and templates (such as development of monitoring systems and management plans); significant capacity development efforts at the individual, institutional and systemic levels; and building the constituency for MCPAs through networks, partnerships, etc.

- Expand the approach for engaging the full range of stakeholders, with particular attention to the FAF, which is the most critical partner for achieving multiple project goals;

- Carry out at least a brief theory-of-change analysis exercise for the project, to identify and facilitate clear justification for the project activities that are critical for achieving the project objective and will allow the project to stay focused;

- Take a proactive and dynamic approach to implementation of project activities by making things happen, not just waiting to see if they will happen (within the confines of standard Russian governmental bureaucracy, of course); persistence is key. This should also serve to accelerate project implementation.

The following are the key recommendations of this evaluation report, with the primary audience for the recommendation in brackets at the end of each. Lessons and additional recommendations are also documented in the final section of the evaluation report.

Key Recommendation 1: The project should not allow the delay in the establishment of the Ingermanland Reserve to significantly derail project activities in the Gulf of Finland. As establishment of the reserve is ongoing, there is an opportunity to focus on the overall system of MCPAs PAs in the Gulf of Finland, including the five regional level MCPAs that need significant strengthening, particularly considering that there is a capable potential partner in the Leningrad regional PAs directorate, which could also use further support from the federal MNRE. At the same time, ongoing advocacy efforts should be made to reach approval of the Ingermanland reserve as quickly as possible. [MNRE, with support as appropriate from UNDP]

Key Recommendation 2: The project needs to intensify implementation efforts in each of the project sites, and the current implementation structure is not highly efficient in this regard considering the geographic spread of the project. There are multiple active partners in the Leningrad region, and the project should assess the possibility of delegating a significant portion of planned activities in the region to a capable partner organization in the region, such as the Baltic Fund for Nature, as a kind of sub-PIU for project activities in the region. There are multiple successful examples throughout the GEF portfolio of high-capacity civil society organizations executing all or a portion of a UNDP-GEF project. This would leave the project team in Moscow to focus efforts at the central systemic level in collaboration with the MNRE, and in the Far East where there are also capable partners at the two project pilot MCPAs. Within the scope of intensifying the project activities in the Leningrad region, there are multiple opportunities to partner with regional stakeholders to strategically strengthen the entire system of MCPAs in the Gulf of Finland. [MNRE, PSC]

Key Recommendation 3: Although the concept of multi-stakeholder cooperation and coordination in the management of marine and coastal resources is broadly considered in the project document, the project needs a stronger concrete focus on this aspect. With the MNRE’s leadership and leveraging whatever means possible, there is an urgent need for the project, to specifically and proactively strengthen cooperation with the FAF; there are also opportunities for additional stakeholder engagement. This could include drawing on UNDP’s power as a third-party, independent convening organization to bring institutions together to discuss common issues, promoting mechanisms for information exchange, sharing international best practices, creating linkages among professional staff at the technical level (through conferences, workshops, etc.), or any other number of activities. A major result for the project would be to help catalyze an effective multi-stakeholder coordination mechanism for the management of marine and coastal resources (including highlighting the role of MCPAs). This type of model could also be piloted starting at the regional level, for example in the Gulf of Finland where informal communication channels, or more formal mechanisms, could be established involving stakeholders such as the port authorities, the ministry of transportation, and others. Establishing the Ingermanland Reserve would be an excellent result, but the conservation and sustainable use of biodiversity in the Gulf of Finland requires an integrated and comprehensive approach to natural resource management, bringing together all relevant stakeholders. There are some linkages established between the border patrol and MCPAs in the Gulf of Finland and in the Commander Islands, but a broader constituency is required. [MNRE, with support as appropriate from UNDP]

Key Recommendation 4: Experience has shown that UNDP-GEF projects with micro-grant/finance components are most successful when the target stakeholders have the capacity to develop and implement appropriate micro-grant proposals. The project document foresees a micro-grant program in the Commander Islands, but it is not clear that this would be an effective tool in the context of the Commander Islands. At the same time, there is a need to more constructively and pro-actively engage the local community in the Commander Islands through a community development approach. This mid-term evaluation recommends the project stakeholders re-assess the potential value of a micro-grant program in the Commander Islands, and identify alternative development-focused approaches to strengthen engagement with the local community, with the overall goal of strengthening management effectiveness of the Commander Islands reserve. Identifying good practices in Russia and elsewhere for community engagement with MCPAs could be a starting point. The community development priorities need to be clearly identified, whether related to health, education, improved communication and transportation infrastructure, etc.; then synergies between management of the reserve can be identified and pursued. In addition, it may be determined that the PA administration can gain community buy-in by making specific community investments that may not be directly linked to PA management actions, but which generate the necessary community support to enable effective PA management. In a context such as the Commander Islands the community must be seen as an integral part of the overall socio-ecological complex comprised within the reserve and that is within the sphere of responsibility of the PA administration. [Project Steering Committee, The Commander Islands Reserve, and MNRE]

Key Recommendation 5: To strengthen the project’s implementation approach and increase sustainability, it would be beneficial to establish stronger working relationships with some MCPAs in Russia that have the best capacity within the system. The project could work with these MCPAs to help establish and maintain a national network of MCPAs, including biological research stations, etc. This would also be useful to support some active models for partnership and collaboration between MCPAs and research stations for environmental monitoring and research on issues such as issuance of permits, research collaboration, and strengthening monitoring capacity. Some initial efforts have begun with the Kronotsky Biosphere Reserve (in Kamchatka) and the White Sea Biological Research Station (in the Karelia Republic). [PIU]

Key Recommendation 6: There are multiple opportunities for the project to have a valuable influence on oil spill response preparation and training in the Gulf of Finland, and the project should consider strengthening the focus on this issue, particularly given the potential negative scope of the threat. According to project stakeholders, there is no comprehensive oil spill response plan for the Gulf of Finland, and there is a current opportunity to address the issue of marine wildlife rescue in the new version of the regional oil spill response plan, which should be pursued under the project. Additional valuable activities could include, workshops/seminars on coordinated oil spill response, international best practices in the Baltic Sea (Finland, Sweden, Norway, Germany, etc.), and additional training or workshops on dealing with affected wildlife and birds. There are also suggestions for establishment of a wildlife rehabilitation center as a facility that could be available in case of oil spills or other hazardous waste incidents, but if such an investment is considered, a feasibility study for such a center should be carried out first, with particular attention to financial sustainability. Direct support from the project would need to be reviewed within the strategic context of the project outcomes and objective. [Project Steering Committee]

- Russia MCPAs Project Mid-term Evaluation Rating Summary

| - Criteria | - Rating |
| --- | --- |
| - Project Formulation |  |
| - Relevance | - R |
| - Conceptualization / design | - MU |
| - Country-drivenness | - MS |
| - Stakeholder involvement in design | - S |
| - IA & EA Execution |  |
| - Quality of UNDP Implementation | - MS |
| - Quality of Execution – Executing Agency | - MS |
| - Overall Quality of Implementation / Execution - (Efficiency) | - MS |
| - Use of the logical framework | - S |
| - Financial planning and management | - S |
| - Adaptive management | - MS |
| - Use and establishment of information technologies | - MU |
| - Operational relationships between the institutions involved | - MU |
| - Technical capacities | - S |
| - Monitoring and Evaluation |  |
| - M&E Design at Entry | - MU |
| - M&E Plan Implementation | - S |
| - Overall Quality of M&E | - MS |
| - Stakeholder Participation |  |
| - Production and dissemination of information | - S |
| - Local resource users and civil society participation | - MS |
| - Establishment of partnerships | - MS |
| - Involvement and support of governmental institutions | - MU |
| - Assessment of Outcomes |  |
| - Outcome 1: Improved MCPA system and Institutional-level capacity enables the expansion of the MCPA system | - MU |
| - Outcome 2: MCPA management know-how is demonstrated, expanded and reinforced | - MS |
| - Outcome 3: Strengthened MCPA system effectively captures knowledge and enables replication of best practice | - MS |
| - Overall Project Outcome Rating | - MS |
| - Progress Toward Project Objective (“To facilitate expansion of the national system of marine and coastal protected areas and improve its management effectiveness”) (Effectiveness) | - MU |
| - Sustainability |  |
| - Financial Resources | - U/A |
| - Socio-political | - MU |
| - Institutional Framework and Governance | - ML |
| - Environmental | - N/A - ML |
| - Overall Likelihood of Sustainability | - MU |
| - Progress Toward Impact |  |
| - Environmental Status Improvement | - U/A |
| - Environmental Stress Reduction | - U/A |
| - Progress Towards Stress/Status Change | - U/A |
| - Progress Toward Overall Project Results | - MS |

| Ratings for Outcomes, Effectiveness, Efficiency, M&E, Implementation and Execution 6: Highly Satisfactory (HS): no shortcomings 5: Satisfactory (S): minor shortcomings 4: Moderately Satisfactory (MS): moderate shortcomings 3. Moderately Unsatisfactory (MU): significant shortcomings 2. Unsatisfactory (U): major problems 1. Highly Unsatisfactory (HU): severe problems | Sustainability Ratings 4. Likely (L): negligible risks to sustainability 3. Moderately Likely (ML): moderate risks 2. Moderately Unlikely (MU): significant risks 1. Unlikely (U): severe risks | Relevance Ratings 2. Relevant (R) 1. Not relevant (NR) Impact Ratings 3. Significant (S): Large-scale impacts 2. Minimal (M): Site-based impacts 1. Negligible (N): Little or no impacts |
| --- | --- | --- |
| Additional ratings where appropriate Not Applicable (N/A) Unable to Assess (U/A) |  |  |

# Introduction: Evaluation Scope and Methodology

According to GEF and UNDP evaluation policies, mid-term evaluations are required practice for GEF funded FSPs, and the mid-term evaluation was a planned activity of the monitoring and evaluation plan of the Russia MCPAs project. The UNDP Russia Project Support Office initiated the mid-term evaluation approximately 3/5ths of the way through project’s planned four-year implementation period, with the post mid-point timing being primarily due to the initial slow implementation of the project. This mid-term evaluation reviews the actual performance and progress toward results of the project against the planned project activities and outputs, based on the standard evaluation criteria: relevance, efficiency, effectiveness, results and sustainability. The evaluation assesses project results based on expected outcomes and objectives, as well as any unanticipated results. The evaluation identifies relevant lessons for other similar projects in the future in Russia and elsewhere, and provides recommendations as necessary and appropriate.

In addition to assessing the main GEF evaluation criteria, the evaluation provides the required ratings on key elements of project design and implementation. Further, the evaluation will, when possible and relevant, assess the project in the context of the key GEF operational principles such as country-drivenness, and stakeholder ownership, as summarized in Annex 2.

The evaluation methodology was based on a participatory mixed-methods approach, which included two primary elements: a.) a desk review of project documentation and other relevant documents, and b.) interviews with key project participants and stakeholders. The evaluation is based on evaluative evidence from the start of project implementation (October 2009) through July 2012, and includes an assessment of issues prior to approval, such the project development process, overall design, risk assessment and monitoring and evaluation planning. The desk review was begun in July 2012, and the evaluation mission was carried out from July 30 – August 3, 2012. The list of stakeholders interviewed is included as Annex 4 to this evaluation report.

All evaluations face limitations in terms of the time and resources available to adequately collect and analyze evaluative evidence. Also, as is understandable, some documents were available only in Russian language, although all key documents were available in English, and the composition of the evaluation team, with an expert interpreter, ensured that language was not a barrier to the collection of evaluative evidence. Altogether the evaluation challenges were not significant, and the evaluation is believed to represent a fair and accurate assessment of the project.

The evaluation was conducted in accordance with UNDP and GEF monitoring and evaluation policies and procedures, and in-line with United Nations Evaluation Group norms and standards.

The intended users of this terminal evaluation are the MNRE as the project executive organization (including the project team), the UNDP Russia Project Support Office, UNDP Bratislava regional office, and UNDP-GEF Headquarters office. As relevant, the mid-term evaluation report may be disseminated more widely with additional stakeholders to share lessons and recommendations.

# Project Overview and Development Context

## Development Context

Ringing Russia's vast territory is the longest coastline of any country in the world. Russia governs more than 20% of the world’s ocean shelf and has shoreline in 13 seas.  The sheer geographic scope of Russia’s marine and coastal zone stretches across eleven time zones, from the Caspian Sea to the White Sea in the West to the Barents, Kara, Laptev and Chukchi Seas in the North, to the Seas of Japan, Okhotsk, and Bering in the East. Russia’s coastal and marine waters harbor a striking variety of marine habitats and species -- some of the most significant “cold-spot” biological diversity in the world.

Eleven Global 200 Ecoregions are represented in Russia’s coastal and marine areas. Russia’s coastal and marine environment is comprised of a multitude of unique coastal mosaics: river deltas, embayments, lagoons, islands and archipelagoes, shallow submarine shelves, sand spits, cliffs and extensive lowlands of intertidal grassland. These mosaics provide habitat for an extraordinary array of biological diversity. Some biotopes such as shallow water hydrotherms, cold seeps and mud volcanoes are unique and host fascinating biota of global importance. In the offshore areas recurrent phenomena as fronts, upwellings and stationary Arctic polynyas are of particular importance for maintaining marine productivity and biodiversity.

Fish and invertebrate diversity in Russian waters exceeds eight thousand species. Among these is the world’s greatest diversity of sturgeon, salmonid and coregonid fishes. The coastal waters of the Russian Far East and Northwest are critically important for some of the most important populations and genetic diversity of Atlantic and Pacific salmon species. Russia’s coastal and marine habitats support millions of nesting, wintering and migrating waterfowl, fish, mammals, and marine mammals. For example, approximately thirteen million seabirds nest along Russia’s arctic coastline and more than eighty species of seabirds can be found in Russia’s coastal areas, greater than in any other country in the northern hemisphere.

At the time of project development there were 35 MCPAs within Russia’s national system of PAs: 19 zapovedniks (strict protected areas); two national parks; and ten zakazniks (wildlife refuges), or approximately 14% of Russia’s entire national system of protected areas. The total area of Russian marine territory under protection (excluding buffer zones) is 91,000 km2 or 1.8% of the total shelf area under Russian jurisdiction (the total area of marine and coastal PA in Russia is over 24.4 million ha).

Russia’s constitution places the country’s internal marine waters, territorial seas, the EEZ and the continental shelf under federal jurisdiction. Therefore, marine protected areas must have federal status. However, in reality the protection regime of several regional protected areas extends to marine areas as well. These are, in particular, regional-level nature reserves (zakazniks) that are also Ramsar sites, as well as local protected areas covering marine lagoons or semi-closed inlets. This means that other agencies have jurisdiction over resources or territory of central importance to the ability of Russia’s 35 MCPA to protect the biological diversity within their borders. Despite of some inconsistencies in their legal status, these areas are recognized de facto by the authorities and economic actors. Some of the zakazniks are extremely well organized and advanced in their management practices.

The national MCPA system is also complemented by other “specially designated or managed” areas that fit the IUCN criteria of particular types of marine protected areas. First are the so-called marine mammal protection zones (MMPZ) that surround important marine mammal colonies and coastal haulout sites (i.e. walruses, Steller sea lions, fur seals) in the Russian Far East and the Chukotka Peninsula in the Chukchi Sea. Historically some of these areas preceded the establishment of a zapovednik. The MMPZ in the Commander Islands was created to allow and manage subsistence hunting of the fur seal by the local population. In fact, this MMPZ constitutes the nature use zone of the Commander Islands Zapovednik (CIZ). These marine mammal protection zones (MMPZ) correspond to the IUCN category IV or V. The new Fishing Regulations for the RFE and adjacent parts of the Arctic Ocean adopted according to the Law on Fisheries of 2004 confirm the no-fishing status of the important MMPZ but do not specify objectives of management and do not regulate the non-fishing impacts. The total area of these MMPZ areas is 2,800,000 ha.

The socio-economic context of Russia’s MCPA is characterized overall by an extremely low population density. Over 50% of the 35 MCPA occur in districts with a population density under 1 person/km2 and over 90% of the MCPA occur in districts with a population density under 10 persons/km2; six MCPA districts have a population density over 10 persons/km2. In general there is an apparent trend for further decrease of permanent population on the coasts of the Russian Arctic and Far Eastern Seas. A remarkably different situation is on the Caspian, Black/ Azov and especially Baltic Sea coast where MCPAs are surrounded by densely populated areas with developed industrial, agricultural and tourism infrastructure. Two coastal national parks occupy the most populated areas (>100 persons/km2). However even in remote and scarcely populated areas the MCPAs may have local communities close or even within the protected area such as the Commander Islands.

Twenty-three (75%) of the MCPA are located in districts where hunting and fishing are primary economic activities involving the local population (and the MCPA). The importance of fishery sector’s contribution to the Russian Gross Domestic Product (0.3% in 2006) is tiny compared to the importance of the fishery sector to local communities and coastal areas, where it takes on significance for small businesses and subsistence purposes.  Russian fisheries are divided into three main categories, namely the industrial, the recreational, and the subsistence fishery for indigenous people. There is also a small category for scientific, educational and replenishment purposes. Russia’s coastal and marine areas support some of the world’s richest fisheries. Russia is among the top ten countries in the world with respect to marine and inland capture fisheries, and a significant player in terms of processing and trade.  According to the Ministry of Economic Development and Trade, the government set a goal for fish production at 4.7 million metric tons in 2010, 50% above [2008] production levels, with most of the gains coming from aquaculture.

Russian wild fish catch in 2007 declined by approximately 3% from 2006 levels. The Federal Agency of Fisheries (FAF) has placed a high priority in improving the efficiency and profitability of the Russian fishery sector, including changes in the quota distribution system, renovation of the fishing infrastructure, and combating poaching. The FAF’s goal is to double Russia’s total catch from the current 3.4 million tons to 6.58 million tons. To spur investment in new fishing vessels and equipment and to promote long-term sustainable fishing practices, the Government recently announced a doubling in the time period from 5 to 10 years for which fishing quotas will be issued to fishing entities. The important contributions of MCPA to the health and sustainability of coastal fisheries have been repeatedly recognized.

## Concept Development and Project Description

### Concept Background

According to project stakeholders, the project concept originated as an offshoot from a previous GEF FSP, the project “Demonstrating Sustainable Conservation of Biological Diversity in Four Protected Areas in Russia’s Kamchatka Oblast, Phase I” (GEF ID #932). This previous FSP had succeeded in significantly strengthening the capacity of the four targeted PAs, and had raised their profile in Russia’s national PA system, with increased attention (and resources) from the central government. Thus the initial idea for the current project was to have a medium-sized project that would achieve something similar for another marine reserve in the Kamchatka region, the Commander Islands. However, around the time that the project concept was initiated, the GEF strategy for the biodiversity focal areas shifted to emphasize a systemic approach for PAs, which did not allow the development of a single site-based project proposal. Therefore UNDP and the government agreed to expand the concept to a system-wide approach, including the Commander Islands capacity strengthening as one of the activities of a larger overall project. The project development phase was also affected by the fact that the position of the National Project Director (NPD) changed during the development phase, so there was a difference of emphasis on different aspects of the project design over time.

### Project Description

The Russia MCPAs project was developed to contribute to addressing the main threats to Russia’s marine biodiversity. Given the geographic range and diversity of Russia’s marine ecosystems, there are numerous specific threats; the project document identifies the main threats as: i.) unsustainable exploitation of animal and plant resources (including illegal, unregulated and unreported fishing); ii.) invasive species; iii.) chronic and catastrophic oil and hazardous material spills; and iv.) unregulated tourism development. In addition, climate change presents an overarching threat to Russia’s marine ecosystems, particularly in the sensitive arctic zone. As stated in the project document, “The project is designed to complement the governmental efforts to expand the marine protected area system and strengthen its management effectiveness.” The desired long-term status is an MCPA system that is ecologically representative, resilient to climate change, and effectively managed. However, the barriers to the normative status are i.) systemic capacity barriers (e.g. lack of multi-sectoral, multi-agency approach); ii.) institutional capacity barriers (e.g. inadequate communication and cooperation); iii.) individual capacity barriers, including knowledge barriers

The project is classified as a GEF FSP, since the funding received from the GEF is more than $1 million USD. Total GEF support is $4.00 million (not including $0.07 in project development funding), and originally proposed co-financing is $9.40 million USD, for a total project budget of $13.40 million. The project is executed under UNDP’s NEX modality, with the Russian Federal Ministry of Natural Resources as the national executing partner.

The overall project goal is not explicitly stated in the project document, but could be summarized as the conservation and sustainable use of Russia’s globally significant marine and coastal biodiversity, particularly at the species and ecosystem level. The project objective is “To facilitate expansion of the national system of marine and coastal protected areas and improve its management effectiveness.” The project objective was planned to be achieved through three main outcomes:

Outcome 1: Improved MCPA system and Institutional-level capacity enables the expansion of the MCPA system

Outcome 2: MCPA management know-how is demonstrated, expanded and reinforced

Outcome 3: Strengthened MCPA system effectively captures knowledge and enables replication of best practice

A key part of the project’s design is to demonstrate improved practices related to overcoming significant barriers and mitigating the main threats in three pilot MCPA sites: the Commander Islands Zapovednik or (CIZ); the Far East Marine Zapovednik (FEZ) and the still-to-be established Ingermanland Zapovednik (IZ). These three areas were chosen as pilot sites based upon a variety of criteria, as outlined in the project document.

Basic information on these sites is provided in Table 1 below, and maps showing the location of the sites are shown in Figure 1 and Figure 2 below. In addition, the project aims to support Russia’s full system of MCPAs, which at the time of project development included 35 federal-level sites. The project has also provided lower levels of support to some other individual MCPAs such as the organization of trainings at Kronotsky Zapovednik, and support for development of the management plan for the newly created Russian Arctic National Park.

Table 1 Demonstration Site Characteristics

| - Site | - Area (ha) | - Year of Establishment | - IUCN Category |
| --- | --- | --- | --- |
| - Commander Islands Zapovednik | - 185,379 (terrestrial); 3,463,300 (marine) | - 1993 | - I (Zapovednik) |
| - Far East Marine Zapovednik | - 1,316 (terrestrial) - 63,000 (marine) | - 1978 | - I (Zapovednik) |
| - Ingermanland Zapovednik | - 14,200 (terrestrial and marine) | - Not yet established | - I (Zapovednik) |

Figure 1 Project Pilot Sites: Commander Islands (top) and Far East (bottom) Zapovedniks

Figure 2 Project Pilot Site: Proposed Ingermanland Zapovednik in the Gulf of Finland

### Project Timing and Milestones

The project’s key milestone dates are shown in Table 2 below. The development period from PIF Approval to CEO Endorsement was 15.5 months, and more than six additional months were required to reach implementation start at the inception workshop. The project inception workshop was held in Moscow in October 2009. The project’s planned implementation is 48 months (four years). As further outlined in Section IV.B on project management, although the inception workshop was held in October 2009, the original project manager resigned and a new project manager was not in place until May 2010; as a result, an official workplan was not approved by the Project Steering Committee until October 2010, although some initial project activities were started in early 2010. Thus, practically speaking, project implementation did not really begin until the 2nd half of 2010. Pipeline entry to project operational closing is expected for a total of 73 months (~6 years), but due to the slow project start-up additional time may be required – the mid-term evaluation is being conducted approximately 36 months after project start-up instead of 24 months. The project team is currently planning to request a no-cost project extension.

Table 2 Project Key Milestone Dates

| Milestone | Expected date [A] | Actual date [B] | Months (total) |
| --- | --- | --- | --- |
| 1. Pipeline Entry / PIF Submission | Not Applicable | Not Specified |  |
| 2. PIF Approval | Not Specified | December 12, 2007 | 0 (0) |
| 3. PPG Approval | Not Specified | January 9, 2008 | 1 (1) |
| 4. CEO Endorsement Submission | May 9, 2009 | January 12, 2009 | 12 (13) |
| 5. GEF Secretariat Technical Clearance | January 22, 2009 | February 22, 2009 | 1.5 (14.5) |
| 6. CEO Endorsement | March 22, 2009 | March 24, 2009 | 1 (15.5) |
| 7. Agency Approval | April 2009 | June 8, 2009 | 1.5 (17) |
| 8. Implementation Start (first disbursement) | September 2009 | October 2009 | 5 (22) |
| 9. Mid-term Evaluation | July 2011 | July 2012 | 32 (54) |
| 10. Project Operational Completion | December 31, 2013 | Not Applicable | 19 (73) |
| 11. Terminal Evaluation | November 2013 | Not Applicable | N/A |
| 12. Project Financial Closing | December 31, 2014 | Not Applicable | 12 (85) |

## Russia MCPAs Project Relevance

Based on the assessment of project relevance to local and national priorities and policies, priorities related to relevant international conventions, and to the GEF’s strategic priorities and objectives, overall the Russia MCPAs project concept and objective is considered relevant.

### Relevance at the National Level

Russia’s system of MCPAs continues to develop, with multiple new MCPAs planned for establishment. Strengthening the capacity of the government to manage this system, and engaging other relevant stakeholders in the process, is vital to effective conservation of Russia’s globally significant marine and coastal biodiversity. This is especially the case in the face of expected increasing threats from oil and gas development, unsustainable fishing practices, climate change, and other issues. The project supports Russia’s national biodiversity strategies and priorities, as outlined in its 2001 National Biodiversity Strategy and Action Plan (NBSAP). The NBSAP emphasizes the importance of the establishment and effective management of protected areas as mechanisms for biodiversity conservation, and the NBSAP identifies coastal and marine ecosystems as a national conservation priority. The project supports national legislation related to marine and coastal biodiversity conservation, including the Ecological Doctrine of the Russian Federation (2002), Federal Law “On Protected Areas” (1995) (including its revisions in 2001, 2004, and 2005), Law on Fisheries and Protecting Biological Resources of the Seas (2004), and the Water Code (2006). In December 2011, after project approval, the MNRE adopted the program of expansion of protected areas from 2012-2020, including multiple MCPAs. The project is directly supporting the establishment and operationalization of the MCPAs identified in this plan.

### Relevance to Multilateral Environmental Agreements

The GEF is a designated financial mechanism for the United Nations CBD, and as such, projects funded by the GEF must be relevant to and support the implementation of this convention. Russia is a party to the CBD, having ratified the agreement on April 5, 1995. The Russia MCPAs project is relevant to the CBD on multiple fronts, most notably in supporting the CBD’s protected areas program of work. The project also meets CBD objectives by supporting the Convention's Articles 6 (General Measures for Conservation and Sustainable Use), 7 (Identification and Monitoring), 8 (In-situ Conservation), 10 (Sustainable Use of Components of Biological Diversity), 11 (Incentive Measures), 12 (Research and Training), 13 (Education and Awareness), and 17 (Exchange of Information).

At the 10th Conference of Parties to the CBD, in 2010, in decision X/2, member nations of the convention adopted the Strategic Plan for Biodiversity 2011-2020, which included the Aichi Biodiversity Targets. The Russia MCPAs project is broadly supportive of most, if not all of the targets, but is specifically relevant to the following targets:

- Target 6: By 2020 all fish and invertebrate stocks and aquatic plants are managed and harvested sustainably, legally and applying ecosystem based approaches, so that overfishing is avoided, recovery plans and measures are in place for all depleted species, fisheries have no significant adverse impacts on threatened species and vulnerable ecosystems and the impacts of fisheries on stocks, species and ecosystems are within safe ecological limits.

- Target 9: By 2020, invasive alien species and pathways are identified and prioritized, priority species are controlled or eradicated, and measures are in place to manage pathways to prevent their introduction and establishment.

- Target 10: By 2015, the multiple anthropogenic pressures on coral reefs, and other vulnerable ecosystems impacted by climate change or ocean acidification are minimized, so as to maintain their integrity and functioning.

- Target 11: By 2020, at least 17 per cent of terrestrial and inland water, and 10 per cent of coastal and marine areas, especially areas of particular importance for biodiversity and ecosystem services, are conserved through effectively and equitably managed, ecologically representative and well connected systems of protected areas and other effective area-based conservation measures, and integrated into the wider landscapes and seascapes.

- Target 19: By 2020, knowledge, the science base and technologies relating to biodiversity, its values, functioning, status and trends, and the consequences of its loss, are improved, widely shared and transferred, and applied.

The project is relevant to numerous other multilateral environmental agreements to which Russia is a party. Notably, the project activities in the Gulf of Finland are supportive of the “Convention on the Protection of the Marine Environment of the Baltic Sea Area” (also known as the Helsinki Convention). Other relevant MEAs include the Ramsar Convention (as some of Russia’s MCPAs include Ramsar sites), and the project could be considered supportive of Russia’s implementation of the Convention on International Trade in Endangered Species. In addition, by supporting Russia’s system of MCPAs, the project supports Wrangel Island Reserve, which is a World Heritage site, and thus the project supports the World Heritage Convention. The project also supports the Convention on Migratory Species, which aims to conserve terrestrial, aquatic and avian migratory species throughout their range. The project is contributing to the objectives of the convention since the project area includes migration routes for multiple bird species that cross international boundaries. However, Russia is not a signatory to the convention. Another relevant MEA that Russia is not a party to is the Convention on the Conservation of European Wildlife and Natural Habitats (i.e. “Bern Convention”). Also relevant is the United Nations Convention on the Law of the Sea.

### Relevance to GEF Strategies, Priorities and Principles

The GEF strategic priorities for each of its thematic focal areas (biodiversity, climate change, etc.) have evolved from one GEF phase to the next, but overall these priorities have remained roughly focused on the same broad areas of intervention. The project was approved under the strategic priorities for GEF-4 (July 2006 – June 2010),and is being implemented under the strategic priorities for GEF-5 (July 2010 – June 2014). The project is aligned under the first GEF-4 Strategic Objective for the biodiversity focal area: “Catalyzing the Sustainability of Protected Areas”, and under this objective, it is focused on the second Strategic Program: “Increasing representation of effectively managed marine PAs in PA systems.” The overall objective of the Russia MCPAs project is directly relevant to and supportive of this GEF strategic objective. Although data gaps currently limit the ability to fully analyze the representativeness of Russia’s MCPA network, it is safe to say that there is a need for increased coverage and representation. The project is also supporting the strengthening of management effectiveness of Russia’s MCPAs at the systemic level, and specifically for a few particular sites.

# Project Design and Implementation

## Elements of Project Design, Planning and Development

### Key Aspects of Project Design

The project document is comprehensive, and includes relevant and necessary elements, such as stakeholder analysis and participation plan, threat analysis, risk assessment, monitoring and evaluation plan, sustainability analysis, replication plan, etc. At the same time the design of many project outcomes and outputs is vague and abstract, and in some ways the project does not appear to be connected to the practical realities and current situation of the management of Russia’s PA system, particularly in marine and coastal areas.

In some cases, particularly in describing plans under Outcome 1, the project document proposes multiple activities and initiatives that do not appear to be clearly grounded in relevant data and concrete descriptions of the practical realities of MCPA management in Russia. At the very least, the project document is full of unnecessary and complex jargon, making it difficult for project stakeholders and implementers to understand certain aspects of the project approach. Although the three outcomes articulated in the project document do have a logical complementarity, the outputs do not fully support the outcome they are under, are not clear, and are sometimes redundant. Output 1.4, expansion of the MCPA network, is a significant large-scale task, and rather distinct from the other outputs under Outcome 1. Under Output 1.1 the project document plans a “Strategic Conservation Plan (SCP)” for MCPAs, when the Russian government and other stakeholders already had an alternate process under implementation, which resulted in the December 2011 government decision on the strategic plan for PAs to 2020. Under Output 1.2 the project document plans an institutional “Effectiveness Improvement Program (EIP)” and under Output 1.3 the document proposes an “Institutional Effectiveness Task Team (IETT)”. Outputs 1.2, 1.3, 2.1, and 3.1 all relate to systemic and individual capacity development without logical, practical distinction of activities among them.

The project document includes an analysis ranking the main threats on a scale of 0-3 for each of the 35 MCPAs in Russia at the time of project development (though the methodology for the assignment of the rankings is not clear). This is a useful analysis for linking specific threats to specific PAs, as the characteristics of Russia’s MCPAs are varied, and the MCPAs have diverse contexts. The project document does not provide a clear threat matrix showing how each of the project activities are designed to address the threats highlighted (as well as the barriers to achieving the normative status), though the multiple specific pilot activities under Outcome 2 do obviously correspond closely with the identified threats.

The project’s risk assessment analysis is included under section II.3 of the project document. The risk analysis includes six specific risks, including a risk related to climate change, as required. Although this is an above average number of risks identified compared to a majority of UNDP-GEF projects, the risk analysis was still not adequate in some respects. The risk analysis did not include perhaps the most significant risk to the project objective, which is the willing cooperation of all necessary stakeholders. This is a standard issue for most projects, but for projects dealing with marine and coastal ecosystems it is especially pertinent as there are typically multiple government institutions with mandates related to the management of these resources. The project document specifically lists 23 different stakeholder institutions or groups from the local to international levels that have relevant roles to play in relation to MCPAs (see Table 7 in Section VI.A on stakeholder participation). At the inception phase the risk assessment was updated with five additional risks not previously covered in the project document, but these still do not address the issue of effective stakeholder engagement. The inclusion of a significant number of new risks at the inception phase of a project can also be an indicator of inadequate risk assessment during the project development phase, though it is important to recognize that new risks do emerge in the sometimes extended period between project development and implementation. Inadequate risk assessment is a quality at entry issue commonly found in the GEF portfolio.

Aspects of stakeholder involvement in the project design are further discussed in Section VI.A on stakeholder participation. During the project development process a range of stakeholders were consulted, particularly individuals involved in the project pilot sites. Nonetheless it does not appear that the full range of stakeholder institutions were fully engaged in project development, as indicated by the fact that the only planned project co-financing from the government comes from the MNRE. One hypothesis is that some projects may have a condensed project development process partially driven by the GEF project cycle milestone time and funding limits; in the case of FSPs, projects have a maximum of 18 months to go from PIF approval to CEO Endorsement, and the Project Preparation Grant (PPG) funding for the Russia MCPAs project was only $70,000 – less than 2% of the total expected GEF funding. In earlier times when project development funding was called “PDF-B” in GEF lingo, it was not uncommon for development phase budgets to be up to $350,000 for FSPs. The current limits do not necessarily allow for an extensive process of stakeholder engagement that would be required for a project with the scope and breadth of the Russia MCPAs project (although the Russia MCPAs project development process was only conducted over ~11 of the available 17 months); analysis of a larger sample of the GEF’s biodiversity portfolio would be required to draw any conclusions on this issue. Given the range in scope of project objectives and differences in national contexts, it seems likely that a limited one-size-fits-all approach to project development timing and funding does not work well in all cases.

## Project Management and Cost Effectiveness (Efficiency)

Overall the efficiency of the project is rated moderately satisfactory. Key aspects of project management and cost-effectiveness are further discussed in the sections below.

### Russia MCPAs Project Implementation Arrangements

UNDP is the project GEF Agency, and the project is implemented under UNDP’s NEX approach, with the Russian Federal Ministry of Natural Resources and Environment (MNRE) as the national executing organization. Initially the project was overseen by the Department of International Cooperation within the MNRE, rather than the department responsible for PAs, but oversight was switched to the current arrangement in late May 2011, and the National Project Director (NPD) position was taken up by the Deputy Director of the Department of State Policy and Regulations of Environmental Protection and Safety of the MNRE, which includes the management of PAs within its responsibilities. As stated in the project document, the NPD is the chair of the Project Steering Committee, and is responsible for ensuring the proper implementation of the project on behalf of the government, and “in doing so, the NPD is responsible for project delivery, reporting, accounting, monitoring and evaluation, and for the proper management and audit of project resources.”

There are multiple other elements to the project management and oversight arrangements:

- Project Management and Coordination Unit (further referred to as the PIU), consisting of the project manager and Chief Technical Advisor, based in Moscow. According to the project document, “The PM’s time, as well as that of the Project Site Managers, will be split 30% for management and 70% for technical input.” The project document envisioned site managers for the project pilot sites, but a cost-effective alternative has been implemented in which the key staff operating in these sites have been adequately supporting project activities. For the Commander Islands Zapovednik this is the director of the reserve, and for the Far East Marine Zapovednik, a member of the expert council associated with the Russian Academy of Sciences, which manages the reserve. In the Leningrad region a leading local NGO serves as a focal point as the Ingermanland reserve is not yet established.

- Project Steering Committee: Monitors project implementation to ensure timely progress in attaining the desired results, and efficient coordination with other projects. The steering committee membership was confirmed at the project inception workshop, and is shown in Box 1 below, with representation of 15 stakeholder organizations. Following the inception workshop on October 6, 2009, the steering committee met in October 2010 to approve the first official project workplan, and again November 25, 2011. Participation in the steering committee meetings has not always been complete, with the administration of the Leningrad region missing the 2011 meeting, and the administration of Primorskiy krai missing the 2010 and 2011 meetings.

- National Implementing Organization: NGO “Ecology and Business” located in St. Petersburg, selected through a competitive open tender process, is the transacting body for financial management. Ecology and Business is responsible for contracting and procurement according to UNDP and Russian procedures, policies, laws and requirements, and is responsible for a separate bank account used for project transactions. UNDP transfers quarterly advances of the project budget based on the quarterly project workplan and projected expenses. Requests for financial advances are signed by the NPD. Procurement is handled according to standard UNDP National Execution practices in Russia. For example, for procurement of equipment for an MCPA, the project team prepares detailed procurement specifications, with full agreement from the beneficiary and MNRE, both of which verify the specification. Justification for the purchase is signed off by the NPD, signaling that the purchase is in-line with the project activities and objective. The verification by the beneficiary entity also contains assurances related to the maintenance and operation of the equipment. The project team or beneficiary then proceeds with the solicitation, but there are measures in place so that no funds for purchases are released until the project team and UNDP verify the transaction. The procurement contract is structured so that ownership of the equipment is transferred to the beneficiary upon purchase, so it is never UNDP property. According to standard UNDP practices for the Russia Project Support Office, each project under implementation is audited each year. This organization is not responsible for any aspects of technical implementation of the project, but simply serves as the “Local Responsible Party” (in UNDP terminology) for legal project implementation processes, since the project financial management is not done through the MNRE. By engaging the implementing entity, the MNRE, and beneficiaries in financial management procedures, the administrative burden on UNDP is reduced, increasing management efficiency. The detailed financial management procedures are also designed to ensure cost-effectiveness in procurement for the project.

- Project Expert Scientific Council: This body was not foreseen in the project document, but was established after project start-up following the suggestion of the initial NPD. The body is a 16 member expert panel that provides advice and insight on relevant technical issues related to project implementation. The council communicates and discusses issues virtually (online), as members are spread across different regions of Russia. Panel membership includes leading members of Russia’s scientific community related to MCPAs, including representation from organizations such as the Russian Institute of Marine Biology, Arctic and Antarctic Research Institute, Murmansk Marine Biological Institute, White Sea Biological Research Station of Moscow State University, Russian Academy of Sciences Institute of Oceanology, Russian Zoological Institute, Klaipeda University, and WWF Russia.

To intensify project implementation in the second half of the project (see further discussion in Section IV.B.ii below), particularly in the Gulf of Finland pilot area (Leningrad region), it would be useful to modify the implementation arrangements to strengthen, expand and further delegate a majority of project activities in this region. There are multiple active partners in the Leningrad region, and even before the Ingermanland Reserve is established there are multiple opportunities to strengthen MCPAs in the region, within the framework of the planned outcomes and outputs of the project. This evaluation recommends the project assess the possibility of delegating planned activities in the Leningrad region to a capable partner organization in the region, such as the Baltic Fund for Nature, as a kind of sub-PIU for project activities in the region. There is a need to increase information among stakeholders in the Gulf of Finland about the overall project’s objective, the aims of the project in this region, and the general understanding of the project approach. There are multiple successful examples throughout the GEF portfolio of high-capacity civil society organizations executing all or a portion of a UNDP-GEF project. This would leave the project team in Moscow to focus efforts at the central level in collaboration with the MNRE, and in the Far East where there are also capable partners at the two project pilot MCPAs.

Box 1 Project Steering Committee Membership

- Russian Association of Indigenous People Of the North, Siberia and Far East

- Border Agency of the Federal Security Service of the Russian Federation

- Department Economy and Finance, Federal Ministry of Natural Resources and Ecology

- Department of International Cooperation, Federal Ministry of Natural Resources and Ecology

- Border Agency of the Federal Security Service of the Russian Federation

- Ministry of Transport, Russian Federation

- Federal Agency of Fishery, Russian Federation

- Far Eastern branch of the Russian Academy of Sciences

- Administration of Primorskiy Krai

- United Nations Development Programme

- Baltic Fund of Nature

- Department of State Policy and Regulations of Environmental Protection and Safety, Ministry of Natural Resources and Ecology of the Russian Federation

- World Wide Fund for Nature, Russia

- Administration of Leningrad region

### Project Management and Implementation

The scope and geographic breadth of the Russia MCPAs project has presented some challenges for the project implementation arrangements. Project implementation has been slower than planned, with approximately 41% of the GEF resources delivered by June 30, 2012, a period representing approximately 63% of the planned project implementation period. Management costs are generally on track, with approximately 43% of the project management budget spent, roughly equal to the disbursement of the non-management budget.

There are multiple reasons for the slower than anticipated pace of implementation thus far. To start with, the project suffered from staff turnover in the position of project manager at the beginning of the project, resulting in an approximately six-month period (the first half of 2010) with no project manager. The current project manager started work in May 2010, approximately one year after UNDP Prodoc signature.

One further issue that did not contribute to a rapid start-up was the initial arrangement with the NPD within the MNRE’s Department for International Cooperation, which did not instigate a priority for project implementation. This initial arrangement was apparently because of the project’s relevance in the Gulf of Finland, on which Russia cooperates through the Helsinki Commission (HELCOM) of the Helsinki Convention on environmental protection of the Baltic Sea. Once the role of NPD was transferred to the more relevant department of the MNRE there was a greater priority on project implementation and urgency for completion of activities.

Another factor contributing to some activities not yet being carried out is that the government has not yet been approved the Ingermanland Reserve, and multiple project activities in the Gulf of Finland region are dependent on the reserve being in existence.

Once the current project manager was in place, the original draft workplan was revised and actively discussed with the key stakeholders, and eventually adopted at the October 2010 Project Steering Committee meeting. Subsequent annual workplans have been prepared by the project team and adopted by the steering committee. Although the first comprehensive project workplan was not adopted until October 2010, the project did initiate some key activities in early 2010 based an approval from the MNRE as executing agency. These included:

- Support for Financial and Material Justification of the Operation of the Ingermanland Reserve (e.g. drafting of staffing requirements, equipment requirements, infrastructure requirements and planning, requirements for management planning)

- Development of program and action plan for ecological monitoring in the Commander Islands

- Aerial census of the Baltic ringed seal in the Russian waters of the Gulf of Finland

- Strategic conservation plan for strengthening and expansion of MCPAs

- Gap analysis: identification of gaps in the bio-geographical and ecosystem coverage of the MCPA system and key species protection

- Development of a management plan for the Far East Marine Reserve

- Analysis of tourism potential and development of a sustainable tourism strategy for the Commander Islands

The UNDP office and project team have comprehensively completed the Project Implementation Review (PIR) form, and complete quarterly progress reports. UNDP and the project management team complete workplan revisions, and develop corresponding budget revisions for approval by UNDP, the MNRE, and the Project Steering Committee. Through the annual PIR the project team tracks project results against the results framework indicators and targets to maintain a results-based approach; however, unfortunately not all of the results framework indicators and targets are adequately results-focused (see further discussion in Section VI.D on project monitoring and evaluation).

While the multiple factors above contributed to a reduced rate of implementation during the first half of the project, now that the project has been up and running for some time, and the project team and government partners have a clear vision for successful project results, it is necessary to accelerate implementation in the second half of the project. The MNRE and the PIU will need to take a proactive and dynamic approach to executing project activities by making things happen, not just waiting to see if they will happen (within the confines of standard Russian governmental bureaucracy); persistence is key.

### Russia MCPAs Financial Planning by Component and Delivery

The total project budget from GEF resources is $4.00 million USD, not including $0.07 million USD in PPG financing. Table 3 below provides an overview of proposed and actual expenditures by component, including project management. The largest portion of the project budget is slated for Outcome 2, with 46.1% of GEF resources. Outcome 1 is planned for a little more than one quarter of GEF resources, and Outcome 3 is planned for less than 20% of GEF resources. The project management budget is slated for 10% of GEF resources, with $0.40 million USD, which is at the GEF threshold. The project has made some budget revisions from the originally planned workplan, but these have primarily been in rolling unspent funds forward from the first two years of implementation, rather than significant shifts between activities, though there have been some minor revisions in this regard as well.

Figure 3 below shows planned expenditure by outcome, and Figure 4 shows actual expenditure by outcome thus far. As previously mentioned, 41.2% of the budget had been delivered as of June 30, 2012. Figure 5 shows total actual disbursement relative to planned disbursement over time.

Table 3 Project Planned Budget and Actual Expenditure Through June 30, 2012 (millions USD)

|  | Planned GEF funding | % of GEF planned | Total planned | % of total planned | GEF amount actual | Actual % of GEF planned |
| --- | --- | --- | --- | --- | --- | --- |
| Outcome 1: Improved MCPA system and Institutional-level capacity enables the expansion of the MCPA system | 1.05 | 26.1% | 3.65 | 27.2% | 0.52 | 49.9% |
| Outcome 2: MCPA management know-how is demonstrated, expanded and reinforced | 1.85 | 46.1% | 6.71 | 50.1% | 0.78 | 42.2% |
| Outcome 3: Strengthened MCPA system effectively captures knowledge and enables replication of best practice | 0.71 | 17.8% | 1.79 | 13.4% | 0.18 | 24.9% |
| Monitoring and evaluation* | 0.37 | N/S | N/S | N/A | N/A | N/A |
| Project coordination and management | 0.40 | 10.0% | 1.25 | 9.3% | 0.17 | 43.2% |
| Total | 4.00 |  | 13.40 |  | 1.65 | 41.2% |

Sources: Project Document for planned amount; UNDP Combined Delivery Reports and 2012 Budget Revision for actual GEF amounts.

*The M&E budget is drawn from all components of the project budget, and is not additional to the amounts shown for project components and management.

| Figure 3 Russia MCPAs Planned Expenditure by Outcome | Figure 4 Russia MCPAs Actual Delivery by Outcome to June 30, 2012 |
| --- | --- |

| Figure 5 Russia MCPAs Planned vs. Actual Delivery | - * In the project document planned expenditure for “Year 1” equates the start of a calendar year, when in fact the project began implementation in October 2009. Therefore Year 1 of “planned” and Year 1 of “actual” delivery are not directly comparable. Nonetheless, actual delivery for Year 1 was only 6.6% of planned delivery, not the ~25% that would be expected for three (out of 12) months of implementation, assuming a roughly even rate of delivery throughout the year. - ‡ To get an approximation of the full year of delivery for 2012, actual Year 4 delivery is projected here as double the delivery through June 30, 2012; this is based on the simplistic assumption that delivery in the 2nd half of the year will be similar to the first half. |
| --- | --- |

Table 4 Project Planned and Actual Co-financing Through August 2012 (millions USD)

| Co-financing (Type/Source) | UN Agency |  | Central Government |  | NGOs* |  | Other Sources‡ |  | Total Co-financing |  | Percent of Expected co-financing |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Proposed | Actual | Proposed | Actual | Proposed | Actual | Proposed | Actual | Proposed | Actual | % of proposed |
| Grant |  |  | 8.93 | 6.38 | 0.30 | 0.09 | 0.17 | 0.15 | 9.40 | 6.62 | 70.4% |
| Credits |  |  |  |  |  |  |  |  |  |  |  |
| Loans |  |  |  |  |  |  |  |  |  |  |  |
| Equity |  |  |  |  |  |  |  |  |  |  |  |
| In-kind |  |  |  |  |  |  |  |  |  |  |  |
| Non-grant instruments |  |  |  |  |  |  |  |  |  |  |  |
| Other types |  |  |  |  |  |  |  |  |  |  |  |
| Total |  |  | 8.93 | 6.38 | 0.30 | 0.09 | 0.17 | 0.15 | 9.40 | 6.62 | 70.4% |

Source: Project document for planned amount; Actual amounts from data provided by project.

*Planned NGO funding was from WWF and the Baltic Fund for Nature. $0.09 has been implemented by WWF Sweden, and the Baltic Fund for Nature has carried out multiple other relevant projects and activities with various donor funding. There is no data available on co-financing from WWF Russia.

‡ The planned “other” source was bilateral funding from Sweden. Actual “other” sources include $0.14 from the private sector company Nord Stream AG.

### Russia MCPAs Planned and Actual Co-financing

Project planned and the actual co-financing is shown in Table 4 above. The total expected co-financing planned at project approval was $9.40 million USD, for a co-financing ratio of 1 : 2.4. The majority of this co-financing was planned to come from the federal government – from the MNRE – in the form of support to MCPAs, in-line with the project objective. Other planned co-financing partners were WWF, the Baltic Fund for Nature, and the Swedish Environmental Protection Agency. Funding from the MNRE has in fact been a significant source of the co-financing received by the project thus far, a total of $6.62 million USD. This equates to 70.4% of the expected co-financing, which is a positive sign for the project as it is a higher percentage than either the project budget disbursed thus far, or the percentage of time passed for the planned implementation period.

One positive aspect of the co-financing received thus far has been the support received from the private sector, specifically, from Nord Stream AG, the company involved in constructing the undersea gas pipeline from Russia to Germany, through the Gulf of Finland and Baltic Sea. There are requirements for monitoring environmental impact during the course of pipeline construction and operation, so it is not clear that Nord Stream’s contributions have been incremental due to the project, but the fact that the project has established communication and cooperation with Nord Stream on environmental monitoring is a positive step for biodiversity conservation in the Gulf of Finland. Hopefully this partnership can build on the example found in another UNDP-GEF project in Russia, in the Komi Republic (GEF ID #2035); in this case a partnership has been established between the firm Gazprom and Yugyd va National Park owing to the fact that a major Gazprom pipeline transverses the national park territory, as the pipeline was constructed prior to establishment of the national park. Gazprom provides various forms of financial support to the national park administration, as well as sharing environmental monitoring data. If the Ingermanland Reserve is established in the Gulf of Finland, Nord Stream may be a strategic partner for effective management of the reserve.

Co-financing is an important indicator of stakeholder ownership, and the significant co-financing received from the MNRE thus far implies that the MNRE does support the project, and is contributing to reaching the project objective. At the same time, considering the number of stakeholders relevant for the management of marine and coastal resources there are relatively few co-financing partners, particularly other government partners, which may be an indication of limited ownership by a range of stakeholders during the project development phase. In particular, the fact that the FAF was not a co-financing organization hinted at the challenges the project has faced in engaging the FAF during implementation.

The project has also not received specific information on co-financing by WWF Russia, one of the originally planned sources of co-financing. WWF-Russia has likely contributed significant in-kind financing – partially through attendance and participation in project meetings and activities, but also through WWF Russia’s significant contributions to the establishment of new MCPAs in Russia. WWF Russia has financed the preparation of documentation for various new MCPAs in Russia, which is within the overall objective of the project, and without this support the project might have to provide additional support in this regard. .

### Flexibility and Adaptive Management

Flexibility is one of the GEF’s ten operational principles, and all projects must be implemented in a flexible manner to maximize efficiency and effectiveness, and to ensure results-based, rather than output-based approach. Thus, during project implementation adaptive management must be employed to adjust to changing circumstances. So far the Russia MCPAs project is generally being implemented in a flexible manner, and the project team and main implementation partners have made a number of minor adjustments to the project workplan to respond to changes in context or circumstances. While positive adjustments have been made, a more significant adaptive approach is required to increase the engagement of key stakeholders and intensify the rate of implementation in the second half of the project.

At the inception workshop some initial adjustments to the project implementation plans were made. As previously mentioned, the risk assessment analysis for the project was updated, with the addition of a number of new risks. Taking a broad perspective the project inception report provides a detailed analysis of changes in the project context related to MCPA system development, policy and legislative context, socio-economic context, and institutional context. The report provides an update of the table with data on the status and area of federal MCPAs. In discussing the MNRE’s strategic plan for PA system development, crucially the inception report notes: “The scheme developed by the MNRE does not include declaration of intent for establishing zakazniks and nature monuments. This basically means that once the relevant organizations forward agreed with stakeholders and justified according to the national standards proposals they may be considered for implementation. Thus several zakazniks may be proposed in the course of the project to reach the project target of 7,680,000 ha of additional area protected with facilitation of the project. Development of the marine mammal protection zones as proposed in the Project Document remains an important resource which can provide even greater extension” (emphasis added). The inception report also contains a table highlighting changes in government plans for establishment of new MCPAs (see table 12 of the inception report).

Multiple revisions to the project results framework indicators and targets were also made at the inception phase, particularly with respect to the impact level species-based indicators. The changes are described in detail in the inception report. This evaluation relies on the updated, current version of the results framework for assessing project progress.

One notable adaptive management feature was the addition of the Scientific Council, previously mentioned in Section IV.B.i on implementation arrangements. This body was not foreseen in the project document, but is a valuable innovation to provide the project and partners with necessary scientific and technical advice related to MCPA management issues.

During implementation a key adjustment to the project workplan was related to the planned “Elaboration of Strategic Conservation Plan for MCPA Network Strengthening and Expansion under Output 1.1. Following the issuance of the Strategic Concept for the Development of the federal Protected Areas till 2020 by the Ministry of Natural Resources of Russia, work under the Output 1.1 of the Project was stopped by the decision of the Project Steering Committee in October 2011. In another example, the project halted further development of the online MCPA database portal after initial discussions with stakeholders about assuming ownership for this tool were not positive.

### UNDP Project Oversight

UNDP is the responsible GEF Agency for the project, and carries general backstopping and oversight responsibilities, as well as handling the financial accounts. As outlined in the project document, “The UNDP Country Office will support the project’s implementation by maintaining the project budget and project expenditures, contracting project personnel, experts and subcontractors, carrying out procurement, and providing other assistance upon request of the National Executing Agency. The UNDP Country Office will also monitor the project’s implementation and achievement of the project outputs and ensure the proper use of UNDP/GEF funds.  Financial transactions, reporting and auditing will be carried out in compliance with the national regulations and UNDP rules and procedures for national execution.  The UNDP Country Office will ensure the implementation of the day-to-day management and monitoring of the project operations through the appointed official in the UNDP Environment Unit and Project Officer based in Moscow.”

The UNDP Russia Project Support Office staff carry out project monitoring, as well as the designated UNDP Regional Technical Advisor for biodiversity in Bratislava. UNDP closely tracks project progress and implementation, and has worked to ensure an efficient and results-based approach for the project. Data gathered during the mid-term evaluation indicates that UNDP is fulfilling its oversight and implementation duties in a responsible manner, with particular attention to project reporting, cost-effective financial management, and the project’s added value. The project has benefited from a consistent personnel presence in the UNDP Russia Project Support Office.

There are some areas of potential strengthening as UNDP continues as a key GEF partner in Russia. A number of the shortcomings in the Russia MCPAs project relate to the project design (see Section IV.A), and as the GEF Agency, UNDP bears primary responsibility for shepherding a participatory, comprehensive, and technically sound project development process, which should result in a well-designed and implementable project. Along with the national executing agency, UNDP is also responsible for getting the project up and running, including successful project staff recruitment. As implementation continues, the Russia MCPAs project would benefit from UNDP working to continue enhancing the management capacity of the project team, and enabling and empowering the project team and stakeholders to proactively address the challenges the project faces.

# Russia MCPAs Project Performance and Results (Effectiveness)

## Progress Toward Achievement of Anticipated Outcomes

Each of the project outcomes was implemented through a series of outputs and specific actions, as outlined in the annual project workplans. Under each of the outcomes below, the primary outputs are listed, and key results highlighted. The project logframe includes indicators and targets for each of the outcomes, which are assessed in Table 6 at the end of this section. As seen in this table, a majority of project indicators have not reached 50% or more of the target level.

Key results thus far include:

- Development of monitoring program for Commander Islands

- Other individual and technical capacity development support for the Commander Islands (management effectiveness audit, trainings, provision of equipment, tourism assessment)

- Training on hazardous material spill response in Gulf of Finland

- Support for key steps toward establishment of Ingermanland Reserve in the Gulf of Finland

- Development of a management plan for Far East Marine Reserve

- Work on IAS in Far East Marine Reserve

- Support for collaboration and cooperation among marine research stations and MCPAs

- Progress toward development of a system-wide approach to the assessment of management effectiveness for MCPAs

Overall progress toward achievement of the project outcomes is considered moderately satisfactory, while overall progress toward the project objective (effectiveness) is considered moderately unsatisfactory. The project has produced a number of valuable outputs thus far, and is making progress in implementation of the project workplan; thus the results produced to date are moving the project toward the three planned outcomes, though at a slower pace than expected. At the objective level, the project has yet to make a significant contribution at the systemic level for the management of MCPAs in Russia, and it is not clear that the current trajectory of results will reach the systemic level.

There are three main project objective level indicators: a.) Area of expansion of the MCPAs network (8.7 million new ha of MCPAs directly or indirectly influenced); b.) Average 20% increase in management effectiveness of MCPAs as measured by the METT; c.) Various species-level impact indicators.

With respect to the expansion of the MCPA network, the project also has yet to make a significant incremental contribution, as the Russian Federal government had separately developed an official program for expansion of PA system in the early stages of the project. The project’s contributions toward creation of the Ingermanland Reserve have been critical, but the reserve is yet to be established and it is not clear when it will be. It is expected that the project will be able to make important contributions to the start-up and management strengthening of the new MCPAs that have been or will be established in 2012 and 2013, but it appears that the government would establish any new MCPAs with or without any influence of the project (other than the Ingermanland Reserve). As discussed in Annex 3 covering suggestions and revisions to the results framework, the relevance of this indicator as a measure of project results has been reduced by the independent government plan for PA expansion to 2020.

The METT score indicator is key for assessing system-wide progress among Russia’s MCPAs. As discussed in Section VI.D on project monitoring and evaluation, the use of this indicator allows the linkage of the Russia MCPAs project results with the global GEF biodiversity focal area results framework. For this indicator, the baseline METT score was calculated during project development for each of the 35 national level MCPAs in existence at that time. The project target is an average 20% increase in the METT scores system-wide. For the annual PIR, METT scores are only calculated for those MCPAs directly impacted by the project. For the mid-term evaluation, more detailed METT assessments were completed, which indicated that the most recent PIR METT scores remain valid, and the overall increase was calculated as 7.2%. The scores for some MCPAs have not increased, due to particular circumstances relating to external factors, such as the influence of local legislation. The project is not providing direct support for increased METT scores in individual MCPAs, but is providing support to the overall system through trainings, seminars, developing environmental monitoring programs, contributing to examples of management plans, study tours, etc. Catalyzing a 20% increase in the METT score on average for all MCPAs in Russia may be an ambitious goal, but a project of this size and scope is expected to generate results at the systemic level; the final evaluation will need to assess the extent of various ways the project may have strengthened Russia’s system of MCPAs, of which the METT may be only one limited measure.

The species-level impact indicators are relevant for assessing the long-term contributions of Russia MCPAs to biodiversity conservation, but are not particularly useful for assessing project results as there are few project activities directly focused on these populations, and there are many factors that contribute to the status of these species’ populations. It is useful to identify impact level indicators related to the overall project goal, but in most cases it is not realistic to expect projects to reach results of this level within the life of the project. For further discussion see Section VI.E on impact and Global Environmental Benefits.

Although the concept of multi-stakeholder cooperation and coordination in the management of marine and coastal resources is broadly considered in the project document, the project needs a stronger concrete focus on this aspect. This is a broader issue related to institutional coordination at the federal level, and as one stakeholder put it, “the major obstacle is that there is no strong political will at the high level,” that this is a “systemic problem”, not just something for individual regions in Russia, and that this is something “to be resolved at the all-Russia level.”

Though it is not expressly identified in the project document as a planned project result, a significant objective-level result for the project would be to contribute to catalyzing an effective multi-stakeholder coordination mechanism for the management of marine and coastal resources in relation to MCPAs. This type of model could be piloted starting at the regional level, for example in the Gulf of Finland where informal communication channels, or more formal mechanisms, could be established involving stakeholders such as the port authorities, the Ministry of Transportation, and others. Establishing the Ingermanland Reserve would be an excellent result, but the conservation and sustainable use of biodiversity in the Gulf of Finland requires an integrated and comprehensive approach to natural resource management, bringing together all relevant stakeholders.

To make further progress toward reaching the project objective, this evaluation recommends that under the MNRE the project take a small but specific and proactive focus on this issue, leveraging whatever external means possible. This could include drawing on UNDP’s power as an independent third-party convening organization to bring institutions together to discuss common issues, promoting mechanisms for information exchange, creating linkages among professional staff at the technical level, providing information on international best practices, or any other number of activities.

Although the project has not achieved as much at the mid-point as was planned, there is still the full potential for the project to reach a satisfactory or highly satisfactory rating by the end of the project. For example, some results expected by the end of the project include establishment of the Ingermanland Reserve, significant capacity strengthening of the project pilot MCPAs and of the MCPAs established during the project, and some changes in the systemic level in the way the MNRE monitors, assesses, and supports management of MCPAs. To reach a highly satisfactory rating it is expected that the project would produce the planned results with no major shortcomings, and produce some results above and beyond what was originally planned – for example, the piloting of a multi-stakeholder coordination mechanism for management of coastal and marine resources at the regional or national level. Ultimately the project results framework indicators and targets should be used to assess project results and progress toward the overall objective, though some revisions to the indicators and targets may be appropriate to strengthen the ability to use this tool to assess results. Some suggestions for revisions of the logframe are included in Annex 3 of this evaluation report.

### Outcome 1: Improved MCPA system and Institutional-level capacity enables the expansion of the MCPA system

Some important outputs have been produced under Outcome 1, but there have been some challenges as well under Output 1.4, which focuses on expansion of the MCPA network. The Strategic Conservation Plan under Output 1.1 was canceled as the government had already approved a separate program of MCPA establishment for the 2012-2020 period. In sum, Outcome 1 is rated moderately unsatisfactory.

Output 1.1 Strategic Conservation Plan for MCPA network strengthening and expansion

This activity was initiated, but later discontinued due to changes in circumstances. An initial gap analysis of MCPA network coverage in Russia was carried out, with holes in biogeographic and ecosystem coverage and key species protection identified. However, it was also identified that there is not comprehensive data on landscape and biological diversity for most Russian MCPAs, which makes it challenging to assess the representativeness of the current network. Recommendations on strengthening Russia’s MCPA network were made to federal and regional authorities, based on the analysis performed.

It had been anticipated that the project would produce a strategic conservation plan for expansion and development of the MCPA network. As discussed in Section IV.B.v on adaptive management, at the November 2011 Project Steering Committee meeting it was decided that this activity would be discontinued, as the MNRE was going to adopt in December 2011 an official plan for expansion and development of Russia’s PA network, including MCPAs, from 2011-2020. Thus the project’s work on this would have been unnecessary and redundant. According to project documentation, it is expected that the project will focus resources on Output 1.2 instead.

Also under this output a web-based information and analytical system was developed. This information portal (viewable in test mode at http://oopt.aari.ru/) is intended to allow PA managing authorities and other stakeholders to access information and carry out analysis on Russia’s MCPA system. Some of the targeted stakeholders believe elements of this system are potentially useful, but at present no organization or institution has the interest or capacity to assume responsibility for maintenance and operation of the full system. This is partly because few stakeholders have interest in information about the entire MCPA network; the exception is the MNRE, but the ministry has limited capacity to manage this type of tool.

Output 1.2 System-level MCPA management effectiveness measuring and monitoring program

The project document foresaw under this output the development and implementation of an institutional “Effectiveness Improvement Program (EIP)”, building on the work of Output 1.1, to “maximize the impact on MCPA institutional effectiveness”, focusing on key capacities.

Also under this output the project aims to:

- Develop recommendations for inter-departmental interaction between the MNRE and FAF concerning MCPA marine biodiversity conservation;

- Conduct and audit of MCPA management effectiveness;

- Assess MCPA management effectiveness at the systemic level; and

- Develop a program for improving the management of federal MCPAs.

Under this output the project developed an agreement to develop indicators for measuring system-level MCPA management effectiveness, and to draft methodological recommendations to assess individual MCPA and MCPA system management effectiveness. The management audit of the Commander Islands reserve can also be considered as a demonstration exercise for the use of this tool in the overall system, as few protected areas in Russia’s national system have undergone such a management audit; each audit conducted thereby strengthens the process. Further substantive systemic level results under this output are anticipated. Achievements toward putting building blocks in place for strengthening of Russia’s MCPAs at the systemic level would be one of the most important contributions of the project to aim for before its completion.

Output 1.3 Elaborated policy and guidelines on MCPA collaboration with stakeholders for more effective management of current and emerging threats

The project document’s description of this output is vague, and does not appear to be particularly distinct from other project activities. The project document proposes an “Institutional Effectiveness Task Team (IETT)” that would hold meetings to share experiences and find an approach to effective MCPA collaboration with other government agencies, with “senior representatives of other relevant sectors (e.g. fisheries, transport, and the border guards)” invited to the meetings. Within the project workplan for 2012, there is one activity planned for this output: Development of recommendations on the use of remote instrument information and on the mechanisms of MCPA cooperation with organizations receiving and processing satellite information. Under this activity the priority task is to prepare a draft agreement on granting MCPAs quick access to data on ship monitoring carried out by the Centre for Fishery Monitoring and Communications with respect to ships passing through nature reserves’ marine zones buffer zones, and to submit the agreement to FAF. The project has made some progress on this activity, but more concrete and sustainable results remain to be achieved.

Overall under this output the project is supporting various forms of stakeholder cooperation and communication for MCPA management. The project carried out an analysis and review of MCPA best practices of partnership on monitoring and research of marine biodiversity, and on cooperation in protection of marine and coastal areas. A forum on opportunities for cooperation on MCPAs was organized under the conference “Cooperation between Marine and Coastal Protected Areas, business and science in the regions of implementation of large-scale industrial projects,” held in St. Petersburg on Baltic Sea Day in March 2011.

The project is also supporting models of cooperation on research between MCPAs and educational and research institutions. Following requests from the Far Eastern Marine Reserve, Kronotsky Nature Reserve, and Commander Islands Nature Reserve the project supported fieldwork by students, with the goal of increased cooperation between MCPAs and educational institutions. Other such research partnerships may be developed, and for example one such study on the dependence of coastal ecosystems on salmon is underway in Kronotsky Nature Reserve, involving Kronotsky Nature Reserve, the Kamchatka Research Institute of Fisheries and Oceanography, and Moscow State University. The involvement of the Commander Islands Nature Reserve and an MCPA on Sakhalin Island is anticipated.

One interesting activity under this output is the initiation of a potential national association or network of MCPAs with marine research stations and centers, with the goal of coordinating large-scale inventory and monitoring of coastal biodiversity, and to integrate the Russian network into the European network of marine research stations. The project is receiving support for this initiative from the White Sea Biological State of the Moscow State University, and the Institute of Marine Biology of the Far Eastern Department of the Russian Academy of Sciences.

Output 1.4 Expanded network of MCPAs

This output covers multiple key activities and initiatives expected to produce results in the expansion and strengthening of Russia’s MCPA network. These include:

- Various forms of support to the MNRE for the establishment of Ingermanland Nature Reserve in the Gulf of Finland;

- Various forms of support to the MNRE for establishment or expansion of eight other MCPAs;

- Strengthening the legal status of existing marine mammal protection zones;

- Creating an enabling environment for the protection of an additional 1,006,000 hectares of priority marine and coastal habitats.

The establishment of the Ingermanland Reserve is the primary site in which it was anticipated the project would provide extensive direct support for the establishment of an MCPA. The project has supported preparation of the financial and technical justification for operations of the Ingermanland Reserve, which was an important step toward the establishment of the reserve. The overall package of documents comprising the justification for creation of the reserve passed the state environmental review, and was provided to the MNRE to support the overall government approval process to establish the reserve.

The establishment of the Ingermanland Reserve is one of the priorities for the project, and while it has not yet been established as originally planned, there has been important recent progress. The process had been stalled due to bureaucratic issues between the MNRE and FAF, which currently oversees the marine territory proposed to be included in the MCPA; the establishment of an MCPA requires approval from all government ministries. According to project stakeholders, local fishermen in the Gulf of Finland do not actively use the area proposed for the reserve, but do not wish to see this area removed from potential future use. However, in July of 2012 the Ministry of Agriculture, which currently oversees the FAF, issued a non-objection statement on the establishment of the reserve, allowing the process to move ahead. There are additional government approval steps required before the reserve is officially established, but the recent breakthrough should allow the process to move forward, with establishment anticipated in late 2012 or 2013. Once officially established additional time will be required to set up the management administration.

In the Gulf of Finland region, the establishment of the Ingermanland Reserve has been the project’s primary focus, along with the activities under Output 2.5 below on training for oil spill response. Multiple other project activities in the Gulf of Finland are dependent on the establishment of the reserve, which was to be one of the primary pilot sites for multiple project activities (e.g. PA management capacity strengthening under Output 2.1). The project should not allow the delay in the establishment of the Ingermanland reserve to significantly derail project activities in the Gulf of Finland. While the process for establishment of the Ingermanland reserve is ongoing, the project should broaden its focus on supporting MCPAs in the Gulf of Finland by working with and providing support to the Leningrad Regional PAs Directorate, which is tasked with managing the network of regional MCPAs in the Gulf of Finland (see Figure 2 and Figure 6). As establishment of the reserve is ongoing, there is a need to focus on the overall system of MCPAs PAs in the Gulf of Finland, including the five regional level MCPAs that need significant strengthening. There is a significant opportunity, considering that there is a capable potential partner in the Leningrad regional PAs directorate, which could also use further support from the federal MNRE. At the same time, it ongoing lobbying efforts should be made to reach approval of the Ingermanland reserve as quickly as possible. Stakeholders interviewed during the mid-term evaluation identified the following activities as high priority for supporting the regional network of MCPAs in the Gulf of Finland:

- Strengthening coordination with MNRE to engage federal and regional fisheries institutions to revise fishing regulations, including amendment to rule on fishing in the region, and the establishment of no-fishing areas;

- Strengthening coordination with MNRE to establish agreements with Ministry of Transport on dredging and hazardous spill preparedness;

- Strengthening enforcement capacity of federal and regional environmental management authorities;

- Establish contacts and working relationships with the Visotsk and Ostluga port authorities;

- Conduct research and assessments of sustainable subsistence catch for local resource users in the Kurgalski Peninsula MCPA, and identify species at risk;

- Management audit of regional MCPAs, particularly Berzovie Islands, to identify weaknesses;

- Identify opportunities for local fishermen to access resources to support switching to fishing gear that reduces by-catch;

- Environmental education and awareness activities for local populations and resource users, particularly to familiarize local communities with the planned Ingermanland reserve;

- Development of recreational use facilities (campsites, trails, picnic sites, etc.) in regional MCPAs to support sustainable use;

Box 2 Regional MCPAs in the Gulf of Finland

The Leningrad region contains 46 PAs covering 6.7% of the territory under three types of protection – municipal PAs (generally small individual sites), zakazniks, and nature monuments. 39 sites are of regional importance, two sites are federal importance, and four sites are of local importance. There are five zakazniks in the marine zone in the Gulf of Finland, three of which are recognized as Ramsar sites. These are: Kurgalski Peninsula zakaznik (#1 in Figure 6) (38,400 ha of marine area); Lebyazhi zakaznik (#3 in Figure 6) (5,298 ha of marine area); and Berezovie (“Birch”) Islands zakaznik (#11 in Figure 6) (47,020 ha of marine area). Non-Ramsar designated MCPAs in the region are Vyborgsky zakaznik (#10 in Figure 6) (6,940 ha of marine area) and Kotelsky zakaznik (#2 in Figure 6)(302 ha of marine area).

Because all marine area in Russia is legally under federal jurisdiction, the Leningrad Regional PAs Directorate does not technically have jurisdiction over the marine area of these MCPAs. The marine area of these regional zakazniks is therefore not officially protected, from a legal perspective. However, for the three sites designated as Ramsar sites, there is an agreement that allows the regional PAs authority to enforce protection in these internationally recognized sites. However, the capacity of the Leningrad Regional PAs Directorate is limited, with four technical staff in the central office, and 26 administrative and ranger staff stationed in the field.

Figure 6 Regional MCPAs in the Gulf of Finland

(Source: Ovcherenko, Vera. 2011. “Russian National Report Concerning the Baltic Green Belt,” Green World.)

In addition to establishment of the Ingermanland Reserve, it was anticipated the project would support the MNRE in the establishment of eight additional MCPAs. The specifics for these activities, as shown in Table 5 below, replicated from the project document.

Table 5 Proposed MCPAs for Support from the Russia MCPAs Project

| Location | Type/ Name | Area (ha) | Description | Current Status & Next Steps |
| --- | --- | --- | --- | --- |
| Baltic Sea | “Ingermanlandsky” Zapovednik | 14,200 | Islands and marine area in the Gulf of Finland in the eastern Baltic Sea. Global 200 Ecoregion #: 85: Northeastern Atlantic Shelf. | a) All justifications completed. Council of Ministers issued internal document creating zapovednik. b) Finalizing gazetting procedure by enabling the Russian Government to issue special order introducing IZ creating legal entity of Zapovednik and legally confirm budget for Reserve. c) Operationalize reserve w/staff, modest facilities and equipment. |
| Barents & Kara Seas | Novaya zemlya Zapovednik | 2,000,000 | Large Arctic Island. Breeding areas of Polar bear and Atlantic walrus. Characteristic seabed, pelagic and sea ice communities. | a). Revise the Russian Arctic National Park proposal. - Draft documentation describing area and justification for marine area to ensure clear land use rights, economic and budgetary justifications. - Convene new state ecological panel review; - Secure Council of Ministers endorsement. |
| Sea of Okhotsk | “Shantarskie Ostrova” National Park (SONP) | 512,000 | Shantar archipelago island and marine ecosystem, Sea of Okhotsk. Extensive tidal flats with high tidal amplitude. Bowhead whale feeding area. Global 200 Ecoregion #: 204: Sea of Okhotsk & #71 Russian Far East Temperate Forests. | a) NP documents prepared for State Ecological Expert Panel Review. Khabarovsk Krai Governor established regional -federal interagency working group to establish the SONP. b) Organize public hearings. - Convene state expert panel. - Elaborate management arrangements and business plan for innovative financing. - Secure Council of Ministers endorsement. |
| Sea of Okhotsk | Sakhainsky Marine Reserve (Zakaznik) | 168,000 | Shallow lagoons (Piltuna, Astokh Bays) and coastal waters off NE Sakhalin. Unique benthic community supports most important feeding ground of Western Pacific Gray whale. Lagoon is important water bird biotope. | a) Documents in process of agreements with regional authorities. b) Ongoing consultations with Sakhalin Oblast and oil interests. |
| Circum-Russia | Marine Mammal Protection Zones | 2,800,000 | Special management areas of varying size reserved for priority use by marine mammals. They are regulatory-based areas, not legally based. | - Currently these are set aside based upon fishery regulations. - Need to increase status from regulatory to legal. Involves consultations with fishery agency and MNRE and legal reviews & recommendations. To reach agreement between FAF and MNRE about MMPZ through Memo of Agreement; and Conversion of areas into Nature Monument (IUCN #3). |
| Pacific Ocean | Extension of the marine zone of the Kronotsky biosphere reserve | 200,000 | Representative biotopes of the Pacific shelf of Kamchatka. Recently discovered feeding ground of the Western Pacific Gray whales | a) Consultations with the administration of zapovednik and preparation of the proposal; b) Develop the proposal - Organize public hearings. - Convene state expert panel. - Elaborate management arrangements and business plan for innovative financing. - Secure Council of Ministers endorsement. |
| Sea of Okhotsk | Zapadno-Kamchatsky zakaznik | 500,000 | Representative shelf and coastal biotopes, lagoons and estuaries, seal rookeries, feeding areas of young salmon, breeding and nursery areas of Kamchatka crab. | a). Proposal is at final stage of preparation; c). Apply to authorities. - Consult with stakeholders. - Organize public hearings. - Convene state expert panel. - Elaborate management arrangements. - Secure Council of Ministers endorsement. |
| Kara Sea | Extension of the buffer zone of biosphere polygon of Gydansky Zapovednik | 1,000,000 | Recurrent polynya – important wintering place and migration route of seabird and marine mammals | Process not yet began but may be successful due coinciding of some natural and political circumstances. a). Consult the Gydansky zapovednik and prepare the proposal; b). - Develop the proposal - Organize public hearings. - Convene state expert panel. - Elaborate management arrangements. - Secure Council of Ministers endorsement. |
| Black Sea | Tamano-Zaporozhsky zakaznik | 500,000 | Unique extensive shallow water marine non-tidal bay with underwater mud volcanoes; largest seagrass meadows in the Russian Black Sea; wetland in the Ramsar shadow list, important water bird area; | a). Preparation of the proposal and the letter to the MNRE regarding the execution of the order of Prime Minister Chernomyrdin of 1996; b). As a federal zakaznik will require special funding from the federal budget. c). Development of the zoning, management concept, working with stakeholders, preparation of the documents for State Ecological Expert Panel Review, legal approval. |

As foreseen in the official government plan adopted in December 2011, at least five MCPAs are in the process of establishment. The MNRE announced in early 2012 that four areas would be established in 2012 – Ingermanland Reserve, and three national parks – “Beringia” (Chukotka Autonomous area), “Onega seaboard” (Arkhangelsk region), and “Land of the Leopard” (maritime territory). Two of the eight targeted project areas were not included in the government plan, the Sakhalinsky Marine Reserve, and the Zapadno-Kamchatsky Reserve.

With respect to the plans for the establishment of new MCPAs, the MNRE should further focus on integration of the project’s support into strengthening the management of MCPAs that have been recently established, or will be established during the project. The government’s adoption in December 2011 of the plan for PA expansion to 2020 appears to have made obsolete the project’s original plans for supporting MCPA expansion, and a majority of the MCPAs planned in the project document are included in the government policy, and will be established even without project support.

Also under this output, the project has agreed to support drafting of the documents necessary for justification of establishment of the East Sakhalin natural marine site. However, this site was not included in the government plan for PA expansion, and based on information from project stakeholders, formal government approval of this site is not likely unless management arrangements can be identified that do not require additional funding from the MNRE.

Additionally, WWF Russia is taking efforts to support the official procedure for creation of the Beringia and Shantar Islands National Parks. The draft documents passed the state environmental review and are at the final stage of approval by different agencies and regional administrations.

The project’s work on strengthening the current marine mammal protection zones has met with minimal success thus far, primarily due to the lack of cooperation and communication with the FAF. The current marine mammal protection zones are within the purview of the FAF, and strengthening these areas depends on further cooperation with the FAF.

### Outcome 2: MCPA management know-how is demonstrated, expanded and reinforced

The achievement of Outcome 2 is considered moderately satisfactory.  Some of the most valuable project results thus far have been through the activities under this outcome, including support for the Commander Islands, and multiple activities in the Gulf of Finland under Output 2.5 related to hazardous spill response. The project results framework includes only one indicator for Outcome 2, the METT scores for the three project pilot sites, and a positive indication of progress is the (limited) increase in management effectiveness for two of the project’s three main pilot sites. For the Commander Islands the METT has increased from the baseline of 53 to 67, more than 50% toward the target of 75. For the Far East Marine Reserve the METT has increased from the baseline of 63 to 67, less than 50% toward the target of 80. For the Ingermanland Reserve the METT remains at the baseline level of 13, with an end-of-project target of 60. Much more work remains to be done under this outcome, which has been partially slowed by the lack of establishment of the Ingermanland Reserve thus far. Given the range of activities under this outcome, the project would benefit from additional results-focused outcome-level indicators in the project results framework that would facilitate capturing the range of positive results under this outcome at the end of the project. Suggestions for revisions to the results framework indicators are included in Annex 3.

Output 2.1 Pilot I - Management and field conservation capacity building programme.

Under this output the project document foresaw the establishment and operationalization of “Community Working Groups (CWG)” in each of the three primary pilot areas of the project – Ingermanland Reserve, Commander Islands Reserve, and Far Eastern Marine Reserve. In addition, the project document anticipated various individual level capacity development activities for PA staff (training, professional development courses, study tours, etc.) on a semi-annual, based on a training needs assessment to be conducted in each site. In addition, “support under this output will provide for adequate facilities, equipment, and the ability to maintain them,” including “at least three zodiac-type boats for each MCPA to enable safe and efficient monitoring and enforcement work by reserve personnel.”

The project has initiated a number of important activities under this output. A management plan for the Far Eastern Marine Reserve was drafted and approved, and a draft management plan for the Commander Islands Reserve was developed. Initial work on the management plan for the newly established Russian Arctic National Park is also underway. Actual implementation of the plans will be the next step, and the project is supporting the MCPAs in seeking resources for management activities beyond the baseline level of staff salaries. The Commander Islands Reserve management plan will be further revised and refined as the management capacity at the reserve continues to develop. A training needs assessment was conducted in the second half of 2012.

A management effectiveness audit of the Commander Islands Reserve was carried out, with recommendations provided to improve the management effectiveness of the reserve. The approach of a “management audit” for PAs is a relatively new practice in Russia, and is envisaged to extend to other MCPAs within the framework of the project in accordance with a schedule approved by the MNRE. Based on the recommendations of the Commander Islands Reserve management audit a funding request was made to the MNRE for the 2012-14 period and funds were earmarked for the reserve. In 2012, central government funding for the Commander Islands increased significantly compared to 2011, from 36 million RUB (~1.14 million USD) to 57 million RUB (~$1.81 million USD).

A review of the Commander Islands Reserve security service was included in the management audit, and although no major problems were noted, the project has provided some additional support for equipment to strengthen the security service, and a training for strengthening MCPA security service operations was carried out in Kronotsky Reserve in October 2012.

It is envisioned that the project will support the procurement of additional equipment to strengthen the reserve’s technical capacity. Under particular consideration at the time of the mid-term evaluation is the question of the project’s support for procurement of a large marine vessel that would serve as the key technical resource for the reserve. The expected cost of the vessel is $260,000. The mid-term evaluation sees no issue with procurement of this vessel using project resources, as long as all appropriate measures have been taken to ensure the maintenance and ongoing operational costs of the vessel. According to the director of the Commander Islands Reserve, the reserve has renovated a building to be used as a garage for the vessel, and has the necessary technical skills within the MCPA staff to ensure maintenance of the vessel. The mid-term evaluation recommends that procurement of the vessel should proceed once a detailed plan has been written and agreed by the reserve regarding all specific points about the ongoing maintenance and operation of the vessel, including where expected fuel costs will come from over time.

It is also planned that the project will implement a small grants program in the Commander Islands through the reserve’s Public Council, which includes members of the local community. Experience has shown that UNDP-GEF projects with micro-grant/finance components are most successful when the target stakeholders have the capacity to develop and implement appropriate micro-grant proposals. It is not clear that the planned micro-grant program would be an effective tool in the context of the Commander Islands. At the same time, there is a need to more constructively and pro-actively engage the local community in the Commander Islands through a community development approach. This mid-term evaluation recommends the project stakeholders re-assess the potential value of a micro-grant program in the Commander Islands, and identify alternative development-focused approaches to strengthen engagement with the local community, with the overall goal of strengthening management effectiveness of the Commander Islands reserve.

Output 2.2 Pilot II - Strengthened enforcement & monitoring partnerships among MCPA and key stakeholder institutions.

Another key activity in the Commander Islands Reserve has been the development of an environmental monitoring program. The reserve is seeking diverse methods for implementing the monitoring program, and the project provided support for monitoring equipment. Over time improved monitoring data should contribute to more effective management of the reserve. The monitoring program is further replicated to the other MCPAs in the system, such as Kronotsky Reserve, with similar conditions and requirements in terms of environmental monitoring.

In the Gulf of Finland efforts were made in 2010 and 2012 to conduct a census of the Baltic ringed seal (one of the project’s impact indicators). The seal census was carried out through remote methods to serve as an example of innovative methodology to be recommended for use in MCPAs as part of environmental monitoring.

In March 2012 a conference was held on “The Gulf of Finland PA: Problems and Achievements. Ways of Cooperation Between Interested Parties.” The conference brought forward the main problems of regional MCPAs, which could be considerably eased through creation of the Ingermanland Natural Reserve. The workshop participants highlighted the need for cooperation between regional and federal MCPAs. A decision was made to conduct an audit of regional MCPAs, with the goal of developing a specific action plan to improve their operations and develop their cooperation with interested parties. Additional proposals were made at the conference, including i.) Establishing a regional environmental network of MPCAs, including the Ingermanland Reserve, once established; ii.) Assess the pollution loads in terrestrial and marine areas of the Gulf of Finland to identify threats that can be addressed; iii.) Create a rehabilitation center for animals affected by oil spills in the Gulf of Finland.

Output 2.3 Pilot III - Sustainable tourism management.

The project document foresaw that this pilot activity would be conducted in the Far Eastern Marine Reserve, but at the inception phase this was switched to focus on the Commander Islands based on emerging tourism opportunities for this MCPA. Although the islands are relatively remote, there is recent stated interest from cruise tour operators to potentially include the Commander Islands in tour itineraries in the region. In the Commander Islands Reserve the project supported the development of an eco-tourism strategy, and provided support to publish informational brochures and produce souvenirs. Some activities were carried out in the Far Eastern Marine Reserve, with an analysis of the tourism carrying capacity for the reserve.

In March 2011 a roundtable discussion was held on the development of eco-tourism in MCPAs as part of the Baltic Sea Day International Forum in St. Petersburg. A training was held on local participation in development of environmentally friendly tourism in Poronaysk Reserve.

It was also planned for MCPA staff to develop capacity in eco-tourism development through study tours to Alaska (September 2012) and the Galapagos Islands (March 2013), with the goal of familiarizing MCPA staff with best practices in protection of marine and coastal zones in conjunction with the organization of eco-tourism and scientific research and monitoring.

Output 2.4 Pilot IV - Integrated invasive species management.

The project activities on invasive alien species (IAS) management were originally planned for the Commander Islands Reserve, but following discussion at the inception workshop this was refocused for the Far Eastern Marine Reserve, which has a more significant issue with IAS. Experts working with the project analyzed the situation in the Far Eastern Marine Reserve to assess the experience and requirements for monitoring and control of IAS. In addition, a review of international and Russian experience in monitoring and control of IAS in MCPAs was prepared and circulated to the MCPAs involved in the project to inform their ongoing work. The review found that research and control of IAS in Russia is extremely limited.

Output 2.5 Pilot V - Demonstration for MCPA contingency planning & response to hazardous materials/contaminants spill.

A review was conducted on contingencies for spills of oil and other hazardous materials near MCPAs, and the experience with planning and response. Based on the review, recommendations were prepared for the reduction of oil spill impacts around protected sites.

In the Gulf of Finland the project worked with Baltic Salvage and Towing Company (a public entity) and the Baltic Fund for Nature (an NGO) to carry out training exercises for a range of stakeholders who would be prepared to respond to environmental and wildlife impacts from oil spills, such as veterinarians, ornithologists, and citizen volunteers (see Figure 7). A training course for PA staff in the Gulf of Finland was also scheduled. The trainings have been particularly helpful in familiarizing the Baltic Salvage and Towing Company and other stakeholders with the main oil spill response regulations, and also identifying areas for strengthening for environmental clean, such as increasing equipment on-board response boats for cleaning birds and animals.

There are multiple opportunities for the project to have a valuable influence on oil spill response preparation and training in the Gulf of Finland, and the project should consider strengthening the focus on this issue, particularly given the potential negative scope of the threat. In 2011 105 tankers of volume 50,000 and 100,000 tons transported 6.5 million tons of heavy fuel through this sensitive ecological environment, and this volume of transport is expected to continue growing over time. Both of the main ports have challenging navigational situations, with numerous islands, reefs, rocks and shallows. An oil spill in either the spring or fall bird migration season would be particularly catastrophic.

The Baltic Salvage and Towing Company is the designated authority for hazardous spill response, so work on these issues needs to be closely coordinated with them. According to project stakeholders, the current oil spill response plans for the Gulf of Finland have little information focusing on the environmental effects of oil spills, particularly the plans of specific institutions such as the port authorities, which do not address birds and animals. The plans provide no guidance on ecosystem clean-up and response methodology, including the identification of relevant facilities, response resources, delegation of organizational and institutional responsibilities, plans for managing the safety and transportation of volunteer clean-up personnel. Oil spill response plans can be improved and strengthened over time to address biodiversity resources – organizational plans are revised every three years, regional plans are revised every four years, and the federal response plan is revised every five years.

There are also currently regulatory and bureaucratic barriers to the effective and rapid deployment of trained volunteer environmental clean-up experts because of the region being a border region, and therefore passengers on ships going into the border areas need permits from the border control service, and need to be carrying their passport. Passengers also need to be certified in basic maritime safety. In the case of oil spills rapid response can be important to reducing the potential negative impact of the spill, and all of these factors reduce the ability of stakeholders to respond quickly to any reported spills. The region also needs improved technical capacity and facilities to test and identify sources of spilled oil, which is not always reported by perpetrators for small spills.

Additional valuable activities could include additional joint workshops/seminars on coordinated oil spill response, international best practices in the Baltic Sea (Finland, Sweden, Norway, Germany, etc.), and additional training or workshops on dealing with affected wildlife and birds. There are also suggestions for establishment of a wildlife rehabilitation center as a facility that could be available in case of oil spills or other hazardous waste incidents, but a feasibility study for such a center should be carried out first, with particular attention to financial sustainability.

Figure 7 Hazardous Waste Spill Response Training

### Outcome 3: Strengthened MCPA system effectively captures knowledge and enables replication of best practice

Overall, achievement of this outcome is rated moderately satisfactory. More of the work under this outcome will be carried out in the later stages of the project when there is more experience from the earlier project activities. Activities thus far have been slower than anticipated, and are marginally on track to reach end of project targets; a majority of the indicator targets for this outcome are below 50% achievement as of the mid-term.

Output 3.1 System-Level MCPA Management Effectiveness Measuring and Monitoring

This output overlaps with Output 1.2 as described above. According to project documentation, an agreement with MNRE on monitoring and assessment of efficiency for PA management and operations was concluded for 2012-13.

Output 3.2 National MCPA Knowledge Management and Development Program

Various individual level capacity development activities are being implemented, including the multiple training courses mentioned under previous outputs, such as trainings on MCPA security and enforcement, eco-tourism, and accident response. Also, the study tours mentioned under Output 2.3 were planned. In 2011-12 a competitive selection process was carried out for university and post-graduate students research projects in MCPAs, as part of a process of searching for talented and active young scientists to be involved in MCPA work. In addition, as part of the environmental monitoring work, the project sponsored students’ summer fieldwork in the Commander Islands Reserve and Kronotsky Reserve, in participation with research and educational institutions.

To strengthen the project’s implementation approach and increase sustainability, it would be beneficial to establish stronger working relationships with some MCPAs in Russia that have the best capacity within the system. The project could work with these MCPAs to help establish and maintain a national network of MCPAs, including biological research stations, etc. This would also be useful to support some active models for partnership and collaboration between MCPAs and research stations for environmental monitoring and research on issues such as issuance of permits, research collaboration, and strengthening monitoring capacity. Some initial efforts have begun with the Kronotsky Reserve (in Kamchatka) and the White Sea Biological Research Station (in the Karelia Republic).

Output 3.3 Strengthened Replication Policies At National MCPA Level

This output focuses on promoting replication of experiences and lessons learned from the project activities within the national MCPA network. As stated in the project document, under this output the project would develop a policy mandate and incentives to use training modules and apply best practices, with the MNRE mandating the use of best practices and knowledge tools by regulatory or policy means. This included the establishment of a “knowledge network.” It was also foreseen that study tours for MCPA staff would be conducted by the MNRE to the project pilot sites within Russia. A project website has been established (http://mpa-russia.ru/) though it is unclear how much it is used as a resource by project stakeholders. The website documents the main project output reports and analyses, and provides information such as the composition of the steering committee, expert council, and project workplan. Experts involved with the project authored the publication “Spiridonov V., Gavrilo M., Krasnov Y., Makarov A., Nikolaeva N., Popov A., Sergienko L., Krasnova E. 2012. Towards the new role of marine and coastal protected areas in the Arctic: the Russian case. In: F. Huettmann (ed.) Protection of Three Poles. Tokyo, Springer, pp. 171-202.” The project also contributed to the publication by WWF of the Atlas of Biodiversity of the Seas and Coasts of the Russian Arctic, available at http://www.wwf.ru/resources/publ/book/eng/500.

## Additional Results

The mid-term evaluation did not identify any significant results yet produced beyond the originally anticipated scope of the project. There are some promising potential avenues for additional results, but this aspect will need to be further assessed at the terminal evaluation.

## Progress Toward the Objective by Logframe Indicators and Targets

Table 6 below shows the project’s progress toward the logframe indicators and targets, according to the below color-coded key. As further discussed in Section VI.D below on monitoring and evaluation, the logframe targets and indicators do not provide a good basis for assessing project results, and this mid-term evaluation report recommends a revision to logframe indicators and targets, as further described in Annex 3.

Note that the first two objective level indicators link directly to the GEF-5 biodiversity focal area results framework, as indicators supporting Expected Outcome 1.1 of the results framework: Improved management effectiveness of existing and new protected areas (Indicator 1.1: Protected area management effectiveness score as recorded by Management Effectiveness Tracking Tool), and Core Output 1: New protected areas (number) and coverage (hectares) of unprotected ecosystems.

Table 6 Russia MCPAs Logframe Indicators and Progress Toward Targets

| - Red = Limited or no progress | - Yellow = Progress less than 50% | - Green = Progress greater than 50% | - Gray = Unable to assess due to inconclusive data or data not available, and indicator not relevant for assessing short-term project results |
| --- | --- | --- | --- |

| Description | Description of Indicator | Baseline Level | Target Level at end of project | MTE Status |
| --- | --- | --- | --- | --- |
| Objective: To facilitate expansion of the national system of marine and coastal protected areas and improve its management effectiveness. | Area of coastal and marine area under protection expanded. | 24,577,651 ha | Additional area protected with direct influence of project: +14,000 ha; Additional area protected with facilitation of the project + 7,680,000 ha; Enabling environment created for establishment of additional 1,006,000 million ha; New total area under protection: 33,277,651 ha | The project’s actual contribution to the establishment of new MCPAs is limited, but the project is supporting the capacity development for management of newly established areas. The project supported the production of important documents for establishment of the Ingermanland Reserve, though this MCPA is yet to be established. The project also supported work on the management plan for the newly established Russian Arctic National Park. Since the beginning of the project, approximately 1,608,500 hectares of MCPAs have been newly established or strengthened thanks to the efforts of project partners and MNRE: 1,426,000 hectares as part of the Russian Arctic National Park, 10,000 hectares as part of Utrish Zapovednik (Black Sea), and 172,500 hectares in East Sakhalin with increased protection for Pacific gray whales. |
|  | Indirect impact on improved management effectiveness in 24 million hectares of MCPA through METT Score. (see (a) through (f) below) | (see data below) | +20% | + 7.2% The project is not providing direct support for increased METT scores in individual MCPAs, but is providing support to the overall system through trainings, seminars, developing environmental monitoring programs, management plans, study tours, etc. |
|  | (a) Zapovedniks - Arctic Bolshoi Arktichesky Gydansky Kandalakshsky Kandalakshsky Nenetsky U-Lensky Taimyrsky Wrangel Island | Zapovedniks - Arctic Bolshoi Arktichesky - 29 Gydansky - 40 Kandalakshsky - 37 Kandalakshsky - 42 Nenetsky - 36 U-Lensky - 42 Taimyrsky - 50 Wrangel Island - 47 Russian Arctic - 0 | Zapovedniks - Arctic Bolshoi Arktichesky - 41 Gydansky - 56 Kandalakshsky - 52 Kandalakshsky - 58 Nenetsky - 50 U-Lensky - 69 Taimyrsky - 70 Wrangel Island - 65 Russian Arctic - to be determined | Zapovedniks - Arctic Bolshoi Arktichesky - 40 Gydansky - 40 Kandalakshsky - 38 Kandalakshsky - 41 Nenetsky - 38 U-Lensky - 46 Taimyrsky - 55 Wrangel Island - 51 Russian Arctic - 41 |
|  | (b) Far East Botchinsky Dzhugdzhursky Kronotsky Koryaksky Kurilsky Lazovsky Magadansky Poronaisky Sikhote-Alinsky | Far East Botchinsky - 37 Dzhugdzhursky - 35 Kronotsky – 58 Koryaksky - 42 Kurilsky - 55 Lazovsky – 54 Magadansky – 51 Poronaisky – 43 Sikhote-Alinsky – 56 | Far East Botchinsky - 52 Dzhugdzhursky - 49 Kronotsky – 80 Koryaksky - 58 Kurilsky - 76 Lazovsky – 75 Magadansky – 72 Poronaisky – 59 Sikhote-Alinsky – 78 | Far East Botchinsky - 40 Dzhugdzhursky - 36 Kronotsky – 63 Koryaksky - 42 Kurilsky - 55 Lazovsky – 57 Magadansky – 52 Poronaisky – 43 Sikhote-Alinsky – 56 |
|  | (c) Caspian Sea Astrakhansky Dagestansky | Caspian Sea Astrakhansky – 62 Dagestansky – 44 | Caspian Sea Astrakhansky – 87 Dagestansky – 62 | Caspian Sea Astrakhansky – 62 Dagestansky – 44 |
|  | (d) Baltic Regional zakazniks | Baltic Regional zakazniks - 30 | Baltic Regional zakazniks - 42 | Baltic Regional zakazniks - 30 |
|  | (e) National Parks Kurshskaya Kosa Sochinsky | National Parks Kurshskaya Kosa - 63 Sochinsky - 59 | National Parks Kurshskaya Kosa - 87 Sochinsky – 83 | National Parks Kurshskaya Kosa - 63 Sochinsky - 63 |
|  | (f) Federal Zakazniks Franz-Josef Land Nenetsky Nizhne-Obskiy Severnaya Zemlya Yuzhno-Kamchatsky Malye Kurily Tumninskiy Agrakhansky Priazovsky Samursky | Federal Zakazniks Franz-Josef Land - 29 Nenetsky -- 28 Nizhne-Obskiy - 13 Severnaya Zemlya - 13 Yuzhno-Kamchatsky - 28 Malye Kurily - 34 Tumninskiy - 13 Agrakhansky - 41 Priazovsky - 19 Samursky - 13 | Federal Zakazniks Franz-Josef Land - 41 Nenetsky -- 39 Nizhne-Obskiy - 19 Severnaya Zemlya - 19 Yuzhno-Kamchatsky - 39 Malye Kurily - 48 Tumninskiy - 19 Agrakhansky - 57 Priazovsky - 27 Samursky – 19 | Federal Zakazniks Franz-Josef Land - 35 Nenetsky -- 28 Nizhne-Obskiy - 13 Severnaya Zemlya - 13 Yuzhno-Kamchatsky - 28 Malye Kurily - 35 Tumninskiy - 13 Agrakhansky - 39 Priazovsky - 19 Samursky - 13 |
|  | Populations of two globally threatened seabird species at CIZ: Red-legged Kittiwake | Red-legged kittiwake Toporkov Island: 22 pairs; Ariy Kamen’: 223 pairs (2008 survey) | Pop #s within natural range of variation | No comparable data for the reporting period. Monitoring data is provided by the MCPA administration, which includes an ornithologist on staff. |
|  | Steller sea lion populations on Mediny Island; - # of adult/juveniles - # of pups - # of breeding males | Medny: 88 adult males, 105 subadult males, 295 females, 182 1year + specimens, 231 pups | Stable pop or within +/- 20% of Long-Term Mean (LTM). | Data provided by Commander Islands MCPA staff: 71 adult males, 67 subadult males, 262 females, 40 1year specimens, 176 pups The slight decrease in number is within the range of multi-year fluctuations. The project is not carrying out work that directly affects the population. |
|  | # and distribution of sea cucumbers in Reserve. | 0.02 – 0.03 m2 | Stable or increasing. | No census done during the reporting period. |
|  | Baltic seal population - Ringed seals [Per Inception Report, this indicator no longer measures Grey seals, and only the Russian part of the Gulf is being monitored] | Based upon 2010 spring aerial survey : 40-45 | Stable pop or within +/- 20% of LTM. | The LTM cannot be conclusively established based on one year’s census. 2012 spring aerial census: 100. The population increased compared to the 2010 census, however, expert opinion is that the long-term trend is negative due to increased threats from climate change (warm summers, lack of ice cover preventing breeding). |
|  | Larga seal breeding population in the Far Eastern Marine Reserve | 2100 adults 380 pups (census of 2008) | Stable pop or within +/- 20% of LTM. | No census conducted from mid-2011 to mid-2012. The Larga seal census is conducted in winter. The previous census was conducted in the winter season 2008-2009. The most recent census was conducted in the 2012-2013 winter; hence the data will only be available for the 2013 PIR. |
| Outcome 1: Improved MPA system and institutional-level capacity enables the expansion of the MCPA system. | Area of MCPA in the process of establishment. | 14,000 | 2,500,000 hectares | The Ingermanland Reserve is still in the process of establishment. The MNRE had previously announced that four MCPAs would be created in 2012, including: Ingermanland Reserve (14,000 ha) (direct project support), Beringia National Park (2,300,000 ha), Onega Seaboard (Arkhangelsk region), and “Land of the Leopard” (maritime territory). In addition, the Shantar Islands National Park (500,000 ha) is also in the process of establishment. Other than the status of Ingermanland Reserve it is not clear to what extent this indicator is useful for assessing the project’s contributions to expansion of the MCPA system. |
|  | # of new policies and guidelines developed and adopted by MNRE to strengthen effectiveness. | 0 | At least 4 in total | The December 2011 plan adopted by the MNRE for expansion of the PA system includes foreseen measures for improvement of management effectiveness. To the MTE the project has directly contributed to one set of guidelines – the monitoring program for the Commander Islands. The project is contributing to the development of other guidelines and policies that will be proposed for the MNRE. Other site-specific activities, such as the management effectiveness audit carried out for the Commander Islands Reserve, may be generalized into a replicable approach that may be applied at a broader level. |
|  | # of marine mammal zones with strengthened protection. | 0 | At least 10. | No project influence; this is within the mandate of the FAF, with which there is yet no established cooperation. Two sites have changed status since the start of the project (no permissions issued for catching young walruses; more strict control of authorities in the no-take zones on Serdtse-Kamen' Cape). |
|  | MNRE MCPA Capacity Scorecard (see (a) through (e) below) | (Baseline data below) | (EoP Targets below) | No mid-term assessment conducted; planned for project completion. |
|  | (a) Policy formulation Systemic Institutional | Policy Formulation 3/out of 6 1/out of 3 | Policy Formulation 5/out of 6 2/out of 3 |  |
|  | (b) Implementation Systemic Institutional Individual | Implementation 3/out of 9 7/out of 27 4/out of 12 | Implementation 7/out of 9 20/out of 27 8/out of 12 |  |
|  | (c) Engagement & consensus Systemic Institutional Individual | Eng. & consensus 3/out of 6 3/out of 6 1/out of 3 | Eng. & consensus 5/out of 6 5/out of 6 2/out of 3 |  |
|  | (d) Info & knowledge Systemic Institutional Individual | Info & knowledge 2/out of 3 3/out of 3 1/out of 3 | Info & knowledge 3/out of 3 3/out of 3 2/out of 3 |  |
|  | (e) Monitoring Systemic Institutional Individual | Monitoring 2/out of 6 3/out of 6 1/out of 3 | Monitoring 4/out of 6 4/out of 6 2/out of 3 |  |
| Outcome 2: MPA management know-how is demonstrated, expanded and reinforced. | Direct impact on improved effectiveness in pilot sites = improved management in 6 million ha though METT Score. | CIZ: 57 FEMZ: 63 IZ: 13 | CIMPCA: 75 FEMZ: 80 IZ: 60 | CIZ - 67 (+4) FEMZ - 67 (+4) IZ – 13 |
| Outcome 3: Strengthened MCPA system effectively captures knowledge and enables replication of best practice. | # of MCPA adopting invasive species management plans. | 0 | 3 (FEMZ, IZ, and probably Kurshskaya Kosa) | 1 in progress in FEMZ |
|  | # of MCPA adopting contingency plans for hazardous material spills. | 0 | 4 (TBD) | 0 |
|  | # of official partnerships (monitoring, enforcement) formed by MCPA nationwide. | Monitoring marine and coastal ecosystems agreements - 14 Cooperation agreement with other MCPA - 2 Cooperation agreement with tourism companies - 2 Written agreement for cooperation in enforcement – 0 | At least 20 monitoring agreements. At least 10 cooperation agreements. At least 7 tourism management and promotion agreements. At least 5 written agreements in cooperation on enforcement. | MCPA directors are in fact responsible for signing cooperation agreements with potential partners, while the project can provide suggestions and identify potential areas for cooperation. Monitoring of marine and coastal environment agreements – 20; Cooperation agreements with other MCPA – 2; cooperation agreements with tourism companies -5 Agreements for cooperation in enforcement – 2 |
|  | # of Russia’s MCPAs included in the North Pacific monitoring network (indicator introduced by the Inception Report) | 0 | 3 | 2 (CIZ & Kronotsky Reserve) CIZ is working according to the agreed North Pacific monitoring standards with regard to marine colonial birds and Stellar sea lions; Kronotsky Reserve participates in the North Pacific monitoring network of sea lion colonies. |

# Key GEF Performance Parameters

## Stakeholder Participation in Development and Implementation

The project document includes a list of key project stakeholders, summarized in Table 7 below. Given the scope of the project targeting Russia’s system of MCPAs, there are a large number of relevant stakeholders at the federal, regional, and local levels – at least 23 different institutions or groups. As described in Section IV.B.i on implementation arrangements, the Project Steering Committee includes representatives from the key stakeholders among the federal and regional government institutions, as well as civil society organizations.

Table 7 Russia MCPAs Project Stakeholders and Relevant Roles and Responsibilities

| Stakeholders | Roles and responsibilities relevant to MCPA |
| --- | --- |
| Ministry of Natural Resources & Ecology (MNRE) | Develops policy, prepares and issues regulation, coordinates the process of planning, establishing and operating new MCPA. |
| Federal Agency of Fisheries (FAF) | Develops fish management policy; approves fishing and hunting rules which may influence MCPA; proposes Total Allowable Catch, which includes catch in those parts of MCPA system where fishing is allowed. Important stakeholder (among other governmental institutions) in approving proposals for new MCPA and extension of existing PA. |
| Regional Administrations / Governments | Oversee resource use in on local and regional lands. Have authority to establish coastal PA and approve the designation and regulation of buffer zones. Often are involved in supporting MPA management by providing communication services or office space. May support federal MCPAs. Administer regional MCPAs through relevant institutions. More developed regions have Committees of Environment (e.g. Leningrad Oblast’) or directorates of specially protected areas (e.g. Murmansk Oblast’ and Nenets Autonomous District) with staff and budget. |
| -Kamchatka Krai - Committee for Natural Resources and Environmental Protection | Responsible for managing all regional protected areas that are potential partners for the federal MCPA in Kamchatka, including CIZ. |
| - Kamchatka Pacific Institute of Geography | Academic institute with experts in a range of ecological and environmental disciplines. Provides expert support to regional and federal conservation efforts and resource management. |
| -Leningrad Oblast -Committee for Natural Resources and Environment Protection | Responsible for managing all regional protected areas that are potential partners for the federal MCPA in Leningrad Oblast, including the newly established IZ. |
| - State Organization “Sevmorgeo” | Responsible for geo-ecological marine monitoring. |
| - State Institute of Lake and River Fishery (Gosniorkh) | Responsible for management of and applied research for lake and river fisheries in Leningrad Oblast. Is a potential important partner for regional and federal level MCPA. |
| -Primorsky Krai - Committee for Natural Resources and Environmental Protection | Responsible for managing all regional protected areas that are potential partners for the federal MCPA in Primorsky, including FEMZ. |
| Local Municipalities and Towns. - Nikolskoye, Aleutian Municipal District; Kamchatka Krai - Vladivoskok/Kasansky District Posiet and Slavianka towns. Primorsky Krai. - Kingissep and the Vyborg Districts, Vysotsk, Primorsk, Leningrad Oblast. | Local municipalities and towns are the homes of local resource users and local politicians interested in livelihood and resource management issues central to many MCPA. Often very much involved with MCPA and enter into partnerships of one sort or another with MCPA. |
| Russian Academy of Sciences | Responsible for management of Far Eastern Marine Zapovednik. Several institutes have agreements with particular federal PAs, conduct joint research and are involved in planning new MCPAs. |
| National and Regional-level Universities | Several universities (Moscow University, St. Petersburg University, Far Eastern University, Kirov and Irkutsk Agricultural Academies (with departments of game management) have long-term relationships with particular zapovedniks, maintain scientific cooperation with them and their graduates work there. MGU has a marine biological station on the White Sea that contributed to the organization of the Polyarnyi Krug Zakaznik and is factually managing its part. St. Petersburg University is an important stakeholder in designing the new Ingermanlandsky Zapovednik. |
| WWF Russia | Gathers, analyses and publishes information on MCPAs; maintains long-term cooperation with particular MCPAs (CIZ, FEMZ, Kurilsky Zapovednik, Koryaksky Zapovednik, Nentsky Zapovednik) searching for funds and providing them material support and expertise. Participates in planning and establishing new MCPAs. Prepared proposal and justification for the Shantar Island National Park, Utrish Zapovednik, and Sakhalin Grey Whale Reserve in 2008. Also in 2008 WWF Russia funded a visit centre in Koryaksky Zapovednik, monitoring work on CIZ and helped the Nenetsky Zapovednik to solve the problem of abandoned oil wells in the area. |
| Wetlands International, Russia office | Maintains a database on the important wetlands that are within either existing or planned MCPAs. |
| Biodiversity Conservation Centre (NGO) | Maintains a web-based resource on federal strictly protected nature areas in Russia. Kola Branch is involved in design of new coastal nature monuments. |
| Local NGOs | A growing number of local NGOs and community-based organizations are participating in conservation related initiatives across Russia. Environmental NGOs are relatively new to Russia, having first started their work in the mid-1980s. The number of NGOs has increased in recent years. NGOs play an active role in the planning of regional coastal PAs in Leningrad, Murmansk and Sakhalin Oblasts and Kamchatka Krai. |
| Kamchatka Krai - Aleutian district Society of Hunters - Kamchatka League of Independent Experts - Kamchatka office of RAIPON | Currently, there are over 15 Kamchatka and Sakhalin NGOs concerned with PA or biodiversity conservation issues. The Hunting Society is a crucial constituency for the CIZ’s management work with the local community. Two regional NGOs serve as advocates for MCPA and watchdogs over its management and enforcement work. Also often contribute to MCPA monitoring and research work and lobby local officials on behalf of the MCPA. RAIPON’s regional offices work to ensure their indigenous members are involved, contributing to and benefiting from MCPA. |
| Leningrad Oblast Baltic Fund for Nature and St. Petersburg KE Association. | Two regional NGOs very much involved in the planning and management of the MCPA in the Bay of Finland. The KE Association of St Petersburg is a league of independent experts that provides input to key conservation and environmental challenges. |
| Fisheries companies | Several fisheries companies have permits to fish in the buffer zones of Kurilsky Zapovednik, Poronaisky Zapovednik and in the Zakaznik Malye Kurily (managed by Kurilsky Zapovednik). They are obliged to have scientific observers onboard and submit the fishing survey reports to the Zapovednik. A company involved in fur seal hunting is organizing fur seal hunt in the area of nature use on Commander Island. Another such company is factually managing the Tyuleniy Island marine mammal protection zone (Terpenia Bay, Sakhalin). In general the role of fishing companies is limited. |
| Port Management Authorities: - Primorsk Specialized Sea Oil-Loading Port Joint Stock Company - Vysotsk Port Authority, Leningrad Oblast | Key stakeholders in terms of planning to mitigate impact of increasing volumes of shipping on the IZ. Also potentially key stakeholders in terms of long-term support for the IZ as part of the shipping terminal companies’ environmental mitigation efforts. |
| Tourism companies | Several tourism companies have agreements with the administrations of the federal protected areas and organise limited number of visits for marine mammals watching (Commander Islands and more occasionally others in the Russian Far East) and diving (Far Eastern Marine Zapovednik, Kandalakshsky Zapovednik). In general the role of tourism companies is limited. |
| International Stakeholders: |  |
| Metsahallitus Natural Heritage Services. | Manages PA of Finland and has long-term cooperation with the Russian federal and regional level PA. Among current initiatives there is potential for cooperation on tri-lateral level in the Eastern Gulf of Finland between MCPA of Finland, Estonia and the planned IZ. Considered will be scientific cooperation, change of methodology and information, development of management, capacity building, training programs and international networking. |
| The Finnish Inventory Programme for the Marine Environment - VELMU. | Cooperates with Russian organizations on marine and coastal biodiversity issues. |
| Finnish Institute of Marine Research | Focuses on invasive species research and control in the Baltic. |
| Alaska National Marine Wildlife Refuge of the U.S. National Fish and Wildlife Service | “Sister reserve” to Commander Islands Zapovednik. Engages in staff exchanges, joint training seminars, wildlife surveys, and invasive species control efforts. |

According to the project document, the project development phase “placed strong emphasis on various forms of stakeholder involvement, including the direct involvement of federal and regional government agencies in regional meetings and workshops.” In addition, there was “a strong emphasis on the involvement of local stakeholders active in the pilot areas.” Further, the “Project objective and envisioned full-scale project outcomes and outputs were discussed in a series of meetings with relevant representatives from the fisheries and other sectors.” Although details of the above referenced meetings and workshops were not included in the project document, there is no reason to doubt that meetings were held with stakeholders during the project development phase, and there are indications of the consultative process carried out. For example, individuals involved in the management of the project pilot sites were extensively consulted. The MNRE was the main government partner involved in project development.

One of the principles the project document attempts to convey, but does not adequately translate into a practical approach, is that effective management of marine and coastal resources requires broad involvement and effective cooperation between many different stakeholders. According to national legislation and policy multiple government agencies at the local, regional and federal levels have mandates that relate to the conservation and sustainable use of marine and coastal ecosystems. In some cases these mandates are not exactly complementary, and can be unclear, or in conflict. One notable example found in many countries is the linkage between the fishing industry and the conservation of marine mammals and other marine resources, including fish stocks as they relate to the conservation of biodiversity. This array of mandates has led countries to pursue integrated national approaches to managing these resources, such as Integrated Coastal Zone Management. According to project stakeholders, Russian legislation does provide some useful mechanisms for integrated management approaches, but these are not effectively implemented. In some aspects the project document of the Russia MCPAs project highlights the importance of coordination and cooperation among all stakeholders, but the project development and implementation process has not yet stimulated a dynamic multi-stakeholder national approach to the management of marine resources. It is not realistic to expect a single $4.0 million USD project to actively engage all relevant stakeholders in all regions of Russia related to the management and conservation of marine and coastal biodiversity, but the development of multi-stakeholder coordination mechanisms is something to which the project could contribute.

National Executing Agency: The project has strong overall support from the MNRE, which is a significant positive situation, and does not go without saying for all GEF projects. At the same time, the MNRE is part of the Russian government’s bureaucratic status quo, limited in action by political parameters and resources, and having limited appetite for risk. In other words, the MNRE is unable or unwilling to push through all of the initiatives sought by project stakeholders, such as the establishment of MCPAs not already included in the government-approved policy. As previously highlighted in Section V.A.i, under Output 1.4, there is a need for the project to be more specifically integrated with the government plans for expanding the network of MCPAs in terms of supporting the strengthening of new MCPAs.

Key Federal Stakeholder - Federal Agency of Fisheries: As is referenced throughout this evaluation, the most pressing issues for the project is for the MNRE to establish a good working relationship with the FAF at the national level. The FAF is included as a member of the Project Steering Committee, and according to project stakeholders representatives of the FAF and of the Russian fisheries science institutions were extensively consulted during the project development phase, which contributed to the development of the project activities related to fisheries refugia zones and marine mammal protection zones. The establishment of new MCPAs, such as the Ingermanland Reserve, also typically requires agreement from the FAF as Russian policy processes require the sign-off of all ministries for the establishment of PAs. Another critical issue is the sharing of satellite/GPS data on ship traffic with MCPA administrations, and cooperation on enforcement of protected zone boundaries.

Though the FAF was consulted during project development, the present institutional restructuring of the FAF under the Ministry of Agriculture has complicated the implementation of these activities, as it has created uncertainty within the FAF regarding roles and responsibilities. According to the project team and other project stakeholders, at present there is little communication and coordination between the FAF and the MNRE. The institutional restructuring has raised concerns in the Russian fisheries sector beyond this project as well - according to some sources, following the initiation of this institutional re-organization “a number of fishing and seafood producing organizations sent a letter to Prime Minister Dmitry Medvedev expressing displeasure with the move, which they say will impede the development of Russia’s fisheries. According to the letter the FAF has been restructured 15 times in the past 20 years, and has been part of the Ministry of Agriculture four times.” To provide an example of the challenges faced in this respect (which are not limited to this project): according to Russia MCPAs project stakeholders, under the Helsinki Commission a project “Managing Fisheries in Baltic Marine Protected Areas” was launched in January 2012, and despite significant efforts from the HELCOM project team, no critical stakeholders from the fishing industry in Russia attended the inception meeting.

It appears that the FAF did not feel a sense of “ownership” in the eventual Russia MCPAs project proposal, which has continued to the present; notably, there was no planned co-financing from the FAF (or any other government institutions other than the MNRE). The lack of buy-in of the FAF has contributed to the challenges on the FAF-relevant issues during implementation. During the mid-term evaluation mission the evaluator was not able to meet with FAF representatives despite some initial promising communications.

During the second half of implementation, it is clear that broader and more concrete communication and cooperation with the FAF will be necessary for the project to achieve large-scale sustainable outcome level results. There are no easy answers for establishing this dialogue, but the project must work to engage the FAF on issues that relate to and support the FAF’s mandate as well. Ultimately, a well-managed and sustainable fishing industry is good for both fishermen and biodiversity conservation. Identifying inter-dependencies and linkages between the health of fish stocks and other elements of marine and coastal ecosystems is likely to be an important step in this direction, moving on to shared goals in environmental monitoring.

Other Federal Government Institutions: A highlight of stakeholder participation within the project has been the involvement of the border patrol service in the Leningrad region and in the Commander Islands. There has been regular communication and a positive working relationship between the MCPA administrations, and the border patrol has participated in steering committee and other project meetings.

Academic and Scientific Organizations: Multiple research institutes and universities are involved in project activities in one way or another, including the Moscow State University and the National Academy of Sciences.

Civil Society: The project has successfully worked with the Baltic Fund for Nature, and WWF is an important project partner.

Private Sector: In the Leningrad region the project has cooperated on environmental monitoring with Nord Stream AG the entity responsible for construction and management of the undersea natural gas pipeline through the Gulf of Finland from Russia to Europe.

Given the range of issues involved in the management of marine and coastal resources, there are many opportunities to engage or at least actively inform additional stakeholders. Just in the Leningrad region for example, there are prime opportunities to engage the transportation sector on issues related to ship traffic and ports. Particularly in the Leningrad region the project could also work more closely with regional environmental protection authorities, and with local resource user communities (fishermen, coastal dwellers near MCPAs). According to project stakeholders, in the Commander Islands the reserve administration is making progress in cooperation with the local community, but relations between the reserve and the community are still uneven. Further, in multiple geographic areas long-term effective management of MCPAs and conservation of marine and coastal biodiversity will require a positive working relationship with the oil and gas industry.

## Sustainability

Sustainability is a temporal and dynamic state that is influenced by a broad range of constantly shifting factors. It should be kept in mind that the important aspect of sustainability for GEF projects is the sustainability of results, not necessarily the sustainability of activities that produced results. In the context of GEF projects there is no clearly defined timeframe for which results should be sustained, although it is implied that they should be sustained indefinitely. When evaluating sustainability, the greater the time horizon, the lower the degree of certainty possible. In addition, over time the results achieved by GEF projects in a given context may become diffuse, and diluted by the continued and additional efforts of stakeholders and other funding partners, thus reducing the relevance of a long-term assessment of sustainability specifically of activities supported by the GEF.

In addition, by definition, mid-term evaluations are not well-positioned to provide ratings on sustainability considering that many more activities will be undertaken before project end that may positively or negatively affect the likelihood of sustainability – especially in the case of the Russia MCPAs project. Nonetheless, ratings on sustainability are provided here as required. Based on GEF evaluation policies and procedures, the overall rating for sustainability cannot be higher than the lowest rating for any of the individual components. Therefore the overall sustainability rating for the Russia MCPAs project for this mid-term evaluation is moderately unlikely.

### Financial Risks to Sustainability

It is not possible to assess financial risks to sustainability at this stage as it is unclear what aspects of the project results will require financial resources to be sustained once the project reaches completion; this aspect of sustainability is currently considered unable to assess. Many aspects of the project are focused on capacity development at all three levels – individual, institutional and systemic. By their nature, gains in strengthening capacity are mostly self-sustaining. Financial resources will be required for management of Russia’s MCPAs, but the issue of MCPA financing is beyond the scope of this project, which is not specifically focused on this issue (in contrast to some GEF-funded projects that specifically target PA financing). The project activities and results, at least thus far, are diffuse and relatively small scale. Thus there are some small aspects that may require financial resources in the future. These may include, for example, the implementation of any comprehensive hazardous spill response plans in the Gulf of Finland, implementation of the management plans for the Far East Marine Reserve and other MCPAs (such as the Russian Arctic National Park), ongoing management effectiveness strengthening in multiple MCPAs (particularly the Commander Islands Reserve, which is receiving a significant investment from project resources), and follow-up efforts on the research on invasive alien species in the Far East Marine Reserve.

### Sociopolitical Risks to Sustainability

Sociopolitical risks to sustainability are the most significant for the project at this stage, and in this respect sustainability is currently considered moderately unlikely. This aspect of sustainability is primarily considered to relate to stakeholder ownership, which is primarily discussed in Section VI.A above. Without ownership and active engagement of the critical partners such as the FAF the project’s lasting impact will be limited. On the positive side, the MNRE is strongly supportive, and is taking ownership of the project. The complex and multi-sectoral nature of managing marine and coastal resources however requires the engagement of a range of government institutions. In addition, although many MCPAs are not in densely populated areas, long-term effective management requires establishing a functioning model of community engagement in the management of MCPAs for those areas that do have nearby local populations, and such a model has not been fully established in the areas targeted by the project – notably in the Commander Islands.

### Institutional Framework and Governance Risks to Sustainability

There are not significant institutional and governance risks to the sustainability of the project’s support for MCPAs, other than the previously discussed lack of a functioning multi-stakeholder coordination mechanism for management of marine and coastal resources. According to project stakeholders, the legislative and policy framework in Russia does include adequate provisions for multi-sectoral coordination, but it is not implemented in reality, and there is currently not adequate national political will to institute effective mechanisms for coordinated government management of marine and coastal resources. Even if legislation does have some useful provisions, there are still many legal and policy challenges with respect to conflicting or unclear institutional mandates for managing marine and coastal resources. For example, one remaining important issue is the fact that all marine territory is under federal jurisdiction, so there is no possibility to have regional-level (or any other non-federal) MCPAs, except in some unique site-based circumstances.

The project has plans to strengthen the MNRE’s overall institutional capacity to manage MCPAs effectively, and successful completion of these efforts should influence the end-of-project status of institutional risks to sustainability. At present, institutional and governance aspects of sustainability are considered moderately likely.

### Environmental Risks to Sustainability

The project results on the ground thus far are limited, and therefore are not subject to specific environmental risks. At the same time, the key environmental risks to Russia’s MCPAs remain pertinent, particularly in the three primary project pilot sites. As one small example, according to project stakeholders, among the most significant risks to the Baltic ringed seal population in the Gulf of Finland is climate change, as in many years the warming wintertime temperatures do not allow adequate levels of sea ice to form to meet the seal’s breeding requirements. To the extent that it is relevant to the project’s work thus far, sustainability in this regard is considered moderately likely.

## Catalytic Role: Replication and Scaling-up

The project includes a number of elements that are expected to contribute to the project’s catalytic effects. Some of the specifically designed replication elements are planned under Outcome 3, as discussed in Section V.A.iii.

## Project Monitoring, Reporting and Evaluation

The Russia MCPAs project document includes a full description of the project M&E plan and activities in Part IV. This section includes the summarized budgeted M&E plan, as per the standard UNDP approach. The summary table includes the planned M&E activities, responsible parties, budget, and expected timeframe. The M&E plan conforms to standard UNDP and GEF M&E procedures and norms. Foreseen M&E activities include the inception workshop and report, APR/PIR, PSC meetings, quarterly progress reports, mid-term and final external independent evaluations, terminal report, lessons learned, and audit. The total indicative M&E budget is given as $365,000 – excluding project team staff time. This is relatively high (9.1% of GEF resources) even for a GEF FSP, though the M&E budget does not specifically indicate if the costs will be fully covered by GEF resources or partially covered with co-financing. The project’s geographic spread (from the Ingermanland site in the Gulf of Finland to the remote Commander Islands on the edge of the Bering Sea) may contribute to expected higher than average monitoring and evaluation costs, including relatively high travel costs for UNDP staff, project staff, independent evaluation consultants, project steering committee members, etc.

Overall, the M&E plan is being implemented as envisioned, with comprehensive (though slightly delayed) reporting in the PIR, and Project Steering Committee meetings held annually. This mid-term evaluation is being conducted later than planned in the original project implementation schedule, but as the project is slightly behind in implementation (~41% of resources delivered over ~62% of the implementation period), the timing of this mid-term evaluation is appropriate. The establishment of the expert technical panel has been a valuable addition to the project M&E activities, and there is opportunity to even further leverage this panel for increased project effectiveness through contributions to national policy making and management decisions.

The key element of the project M&E system for a results-based approach is the project logframe, with indicators, baseline data, and targets. To meet GEF and UNDP M&E minimum standard, project logframe indicators must meet SMART criteria. The Russia MCPAs project logframe is based on the standard UNDP logframe structure and approach. The logframe was further adjusted and updated at the inception phase, with changes to the logframe outlined the inception report. The logframe indicators and targets do not fully meet SMART criteria, on multiple accounts, but especially because many of the indicators do not facilitate assessment of project results because they are not related to issues that will be influenced by the project, or will only be influenced in a very indirect manner. In addition, some indicators are output-based, which tend to have a lower relevance for results-based management. This evaluation recommends the project logframe indicators and targets be revised to more adequately reflect SMART criteria, as per suggestions included in Annex 3.

The project logframe includes indicators applying two scorecard/tracking tool mechanisms. Foremost, the project is using the protected areas Management Effectiveness Tracking Tool (METT) to track management effectiveness scores for all federal MCPAs in Russia, and specifically the three project pilot MCPA sites – Ingermanland Reserve, Far East Marine Reserve, and Commander Islands Reserve. For the non-pilot MCPAs the project target value is an average increase of 20% in the METT score. The three pilot sites have targets specific to their respective situations. The application of the METT is a critical element of the project logframe because it a.) Is one of the most widely accepted means of tracking the effectiveness of protected areas, which is a primary planned project outcome; and b.) It facilitates the linkage of the project’s results within the full GEF biodiversity focal area portfolio. There is one opportunity for strengthening however, as currently the project chief technical expert solely calculates METT scores – a methodology that is likely to be consistent, but not necessarily the most robust approach for calculating the METT scores of 35+ MCPAs in Russia. The METT is most useful when calculated using a triangulation approach with multiple sources of data, for example through a consultative process with PA staff and a limited number of other relevant and informed stakeholders (e.g. local government, civil society organizations, community members), with data verified by external experts.

The GEF-5 biodiversity focal area results framework also has expected core outputs relevant for the project: the number and coverage (ha) of new protected areas. The coverage of new PAs is also included in the project logframe, with a target of 14,000 ha directly influenced by the project, 7.68 million ha indirectly influenced by the project, and 1.01 million ha further facilitated by the project. See further discussion on mid-term achievement of these indicators in the previous Table 6.

The project logframe also includes use of the Capacity Assessment Scorecard. Many other UNDP-GEF projects utilizing this indicator have found its relevance mixed in terms of a tool to assess project results, as compared to just assessing the overall capacity levels within a country. This is because multiple elements measured by the scorecard are beyond the scope of any individual project, especially in a country the size of Russia.

## Project Impacts, and Global Environmental Benefits

For the GEF biodiversity focal area project impacts are defined as documented changes in environmental status of species, ecosystems or genetic biodiversity resources. Global Environmental Benefits in the biodiversity focal area have not been explicitly defined, but are generally considered to involve sustained impact level results of a certain scale or significance. The project document specifically highlights the expected global environmental benefits of this project under four main aspects:

- Contribution to the indicators, outcomes, and expected long-term impacts under the GEF’s biodiversity strategic objective 1;

- Contribution to conservation of the globally significant ecoregional context of Russia’s marine and coastal areas, including representation in five of 11 WWF Global 200 marine and coastal ecoregions in Russia;

- Contribution to the global body of experience and best practice on conservation of marine and coastal biodiversity;

- Conservation of a vast number of species (including Red List species) representing a globally significant biodiversity asset, particularly in the project’s three pilot sites.

The project logframe includes a number of impact level indicators in an attempt to ensure a results-focus for the project activities. The impact indicators are species-based, focusing on the population status of the following species: Red-legged Kittiwake (Commander Islands); Steller’s sea lion (on one of the Commander Islands); sea cucumbers (Far Eastern Marine Reserve); Baltic ringed seal (Gulf of Finland); and Larga seal (Far Eastern Marine Reserve). However, these impact indicators not directly linked with the project activities, which are by and large focused on expanding the MCPA system and strengthening capacity for effective MCPA management. Both of these intervention approaches will take years to have measurable effects on Russia’s marine and coastal ecosystems. To facilitate the long-term assessment of impacts, the project may wish to identify relevant sources of environmental monitoring data that will be collected without project resources once the project is completed, such as the environmental data collected by the MCPA administrations, the Russian Academy of Sciences, or other sources such as Nord Stream AG monitoring in the Gulf of Finland.

The project is collecting monitoring data on impact indicators when possible. The project supported a census of the Baltic ringed seal in 2010 and 2012. On the other indicators the project takes a positive approach of leveraging monitoring data from project partners and other sources, rather than trying to finance a new monitoring program. The project receives monitoring data on species in the Commander Islands from the reserve’s current environmental monitoring program. In the Gulf of Finland there is environmental monitoring carried out in association with the construction of the Nord Stream undersea gas pipeline from Russia through the Gulf of Finland and Baltic Sea to Germany; however the Nord Stream environmental program focuses on specific impacts related to the pipeline and does not constitute a comprehensive environmental monitoring program for the Gulf of Finland. There is little or no other regular Russian federal environmental monitoring as the Ingermanland Reserve has not yet been established.

In fact it is extremely difficult for GEF projects to demonstrate significant impact level results by the end of the project, as ecosystems and species populations can take years to measurably respond to conservation measures. In addition, environmental monitoring data is often inadequate to make these assessments. Ultimately the Russia MCPA project’s impact will need to be assessed years in the future to appropriately consider how the activities supporting Russia’s MCPAs may have positively contributed to the conservation of biodiversity, particularly in the project pilot sites. Making such an assessment at the systemic level, beyond the project sites, would be impossible given the dynamic nature of a large and diverse system of protected areas that are positively and negatively influenced by many factors.

# Main Lessons Learned and Recommendations

## Lessons from the Experience of the Russia MCPAs Project

Below are lessons considered by the evaluation team to be some of the more significant lessons drawn from the project experience, but should not necessarily be considered comprehensive. The project team and stakeholders should continue analyzing and drawing on the project experience to identify additional or more comprehensive lessons, and support dissemination of these lessons through documentation in knowledge products.

Lesson 1: It has been stated innumerable times in international development literature, but it bears repeating given that it still inadequately heeded: Stakeholder ownership by all relevant stakeholders is critical for project progress and ultimate success. For the Russia MCPAs project strengthened stakeholder buy-in and support for the project objective and strategy during project development and throughout implementation would have increased the progress toward key results. In the situation of marine and coastal ecosystems there are many relevant stakeholders, particularly including the FAF, which is responsible for fisheries management. The implementation experience of the project thus far has confirmed what many other projects have also discovered – without full support from key stakeholders, reaching primary goals is challenging. In this case, the establishment of the Ingermanland Reserve (among other efforts) was slowed, which affects multiple other project activities in the project site focusing on the Gulf of Finland.

Lesson 2: In a country as large as Russia, attempting to carry-out site-specific or field based activities on opposite sides of the country is challenging for a single project, as completely different sets of stakeholders are involved. The project might have been designed as a phased approach focusing on one general region at a time, or implemented through a more decentralized structure with greater autonomy for designated partners in each of the pilot regions.

Lesson 3: The project design is also ambitious, covering many different types of pilot activities across large geographic spaces, as well as focusing on systemic capacity development. Although the Russia MCPAs project budget is relatively large at $4.0 million USD, Russia’s MCPA system covers vast territory, geographically and from a technical management perspective. A project design that was strategically based on a logic chain analysis might have served the project better.

Lesson 4: When possible, it is most cost-effective for projects to focus on impact level indicators that can be monitored through data provided in the framework of regular monitoring programs already in place by project partners or other stakeholders. The Russia MCPAs project logframe includes impact level indicators that are monitored by the respective MCPA administrations, and in the Gulf of Finland by the private sector (Nord Stream pipeline). This is an approach that should be shared with other UNDP-GEF projects to help address the important issue of the ability to measure environmental impacts over time, including after project completion.

Lesson 5: There remains a need to strengthen the design of UNDP-GEF project results frameworks to improve alignment of indicators and targets with SMART criteria and to strengthen their results-focus. In addition, there is a need to find a more realistic and relevant approach to project impact tracking than simply including species-based indicators in results frameworks, as these are not likely to reflect project results in a meaningful way before the end of the project.

Lesson 6: A technical advisory body, when appropriately constituted and convened, can serve as a valuable resource for projects with technical elements, as well as providing political grounding through science. The Russia MCPAs project Expert Scientific Council includes numerous highly technically qualified individuals from a range of scientific and research institutions. The expert council made invaluable contributions to the design of an environmental monitoring system for the Commander Islands, a system that may be replicated in other MCPAs.

Lesson 7: Effective management of marine and coastal resources requires the involvement of a wide range of stakeholders that are typically more numerous and diverse than those involved effective management of terrestrial protected areas. There are many reasons for this, including the fact that marine and coastal ecosystems often have strategic national importance, and governments are organized in a sectoral manner covering multiple aspects of the management of coastal and marine resources. The Russia MCPAs project document identifies 23 different stakeholder organizations and institutions, but this is only scratching the surface at the national level. Even at the regional level in the Gulf of Finland there more relevant stakeholders than can be easily summarized.

Lesson 8: Among the important risks faced in successful implementation are operational risks related to bureaucracy for project start-up, implementation arrangements, and human resources. For the Russia MCPAs project, implementation was initially slowed by turnover in project staff, and the project’s placement in the international cooperation department of the MNRE. Operational risks were not included in the project’s original risk analysis (though they were added at the inception phase), and the original project workplan and disbursement schedule assumed that the project would quickly be started and operating at full capacity.

Lesson 9: Although operational and start-up issues are frequently encountered in GEF projects, project designs often plan for the first years of the project to have the greatest delivery of the project budget, rather than building activities over time toward the end of the project. The current approach of front-loading planned project implementation frequently does not correspond to on-the-ground realities. For the Russia MCPAs project, the project did not come close to matching the planned annual disbursement level until the second full year of implementation.

Lesson 10: Civil society organizations that have well-developed project management and technical capacities can be valuable partners. In the Russia MCPAs project the Baltic Fund for Nature has been an important partner in the Gulf of Finland region for project activities thus far, but there is an opportunity to further leverage the BFN’s capacity and experience to further the project’s aims in this region. When potential partners such as this are identified during the project development phase it is useful to maximize their potential contribution to project implementation.

## Russia MCPAs MTE Recommendations

The recommendations from this mid-term evaluation are provided below, with the targeted primary audience for the recommendation in brackets immediately following.

Key Recommendation 1: The project should not allow the delay in the establishment of the Ingermanland Reserve to significantly derail project activities in the Gulf of Finland. As establishment of the reserve is ongoing, there is an opportunity to focus on the overall system of MCPAs PAs in the Gulf of Finland, including the five regional level MCPAs that need significant strengthening, particularly considering that there is a capable potential partner in the Leningrad regional PAs directorate, which could also use further support from the federal MNRE. At the same time, it ongoing lobbying efforts should be made to reach approval of the Ingermanland Reserve as quickly as possible. [MNRE, with support as appropriate from UNDP]

Key Recommendation 2: The project needs to intensify implementation efforts in each of the project sites, and the current implementation structure is not highly efficient in this regard considering the geographic spread of the project. There are multiple active partners in the Leningrad region, and the project should assess the possibility of delegating a significant portion of planned activities in the region to a capable partner organization in the region, such as the Baltic Fund for Nature, as a kind of sub-PIU for project activities in the region. There are multiple successful examples throughout the GEF portfolio of high-capacity civil society organizations executing all or a portion of a UNDP-GEF project. This would leave the project team in Moscow to focus efforts at the central systemic level in collaboration with the MNRE, and in the Far East where there are also capable partners at the two project pilot MCPAs. Within the scope of intensifying the project activities in the Leningrad region, there are multiple opportunities to partner with regional stakeholders to strategically strengthen the entire system of MCPAs in the Gulf of Finland. [MNRE, PSC]

Key Recommendation 3: Although the concept of multi-stakeholder cooperation and coordination in the management of marine and coastal resources is broadly considered in the project document, the project needs a stronger concrete focus on this aspect. With the MNRE’s leadership and leveraging whatever means possible, there is an urgent need for the project, to specifically and proactively strengthen cooperation with the FAF; there are also opportunities for additional stakeholder engagement. This could include drawing on UNDP’s power as a third-party, independent convening organization to bring institutions together to discuss common issues, promoting mechanisms for information exchange, sharing international best practices, creating linkages among professional staff at the technical level (through conferences, workshops, etc.), or any other number of activities. A major result for the project would be to help catalyze an effective multi-stakeholder coordination mechanism for the management of marine and coastal resources (including highlighting the role of MCPAs). This type of model could also be piloted starting at the regional level, for example in the Gulf of Finland where informal communication channels, or more formal mechanisms, could be established involving stakeholders such as the port authorities, the ministry of transportation, and others. Establishing the Ingermanland Reserve would be an excellent result, but the conservation and sustainable use of biodiversity in the Gulf of Finland requires an integrated and comprehensive approach to natural resource management, bringing together all relevant stakeholders. There are some linkages established between the border patrol and MCPAs in the Gulf of Finland and in the Commander Islands, but a broader constituency is required. [MNRE, with support as appropriate from UNDP]

Key Recommendation 4: Experience has shown that UNDP-GEF projects with micro-grant/finance components are most successful when the target stakeholders have the capacity to develop and implement appropriate micro-grant proposals. The project document foresees a micro-grant program in the Commander Islands, but it is not clear that this would be an effective tool in the context of the Commander Islands. At the same time, there is a need to more constructively and pro-actively engage the local community in the Commander Islands through a community development approach. This mid-term evaluation recommends the project stakeholders re-assess the potential value of a micro-grant program in the Commander Islands, and identify alternative development-focused approaches to strengthen engagement with the local community, with the overall goal of strengthening management effectiveness of the Commander Islands reserve. Identifying good practices in Russia and elsewhere for community engagement with MCPAs could be a starting point. The community development priorities need to be clearly identified, whether related to health, education, improved communication and transportation infrastructure, etc.; then synergies between management of the reserve can be identified and pursued. In addition, it may be determined that the PA administration can gain community buy-in by making specific community investments that may not be directly linked to PA management actions, but which generate the necessary community support to enable effective PA management. In a context such as the Commander Islands the community must be seen as an integral part of the overall socio-ecological complex comprised within the reserve and that is within the sphere of responsibility of the PA administration. [Project Steering Committee, The Commander Islands Reserve, and MNRE]

Key Recommendation 5: To strengthen the project’s implementation approach and increase sustainability, it would be beneficial to establish stronger working relationships with some MCPAs in Russia that have the best capacity within the system. The project could work with these MCPAs to help establish and maintain a national network of MCPAs, including biological research stations, etc. This would also be useful to support some active models for partnership and collaboration between MCPAs and research stations for environmental monitoring and research on issues such as issuance of permits, research collaboration, and strengthening monitoring capacity. Some initial efforts have begun with the Kronotsky Reserve (in Kamchatka) and the White Sea Biological Research Station (in the Karelia Republic). [PIU]

- Key Recommendation 6: There are multiple opportunities for the project to have a valuable influence on oil spill response preparation and training in the Gulf of Finland, and the project should consider strengthening the focus on this issue, particularly given the potential negative scope of the threat. According to project stakeholders, there is no comprehensive oil spill response plan for the Gulf of Finland, and there is a current opportunity to address the issue of marine wildlife rescue in the new version of the regional oil spill response plan, which should be pursued under the project Additional valuable activities could include, workshops/seminars on coordinated oil spill response, international best practices in the Baltic Sea (Finland, Sweden, Norway, Germany, etc.), and additional training or workshops on dealing with affected wildlife and birds. There are also suggestions for establishment of a wildlife rehabilitation center as a facility that could be available in case of oil spills or other hazardous waste incidents, but if such an investment is considered a feasibility study for such a center should be carried out first, with particular attention to financial sustainability. Direct support from the project would need to be reviewed within the strategic context of the project outcomes and objective. [Project Steering Committee]

Recommendation 7:  To enhance the control of general compliance of maritime operators with a regime of protected marine zones within MCPAs, the use of a satellite monitoring data is essential. To enable the reserves to track fishing boats at sea, as well as vessels carrying hydrocarbon fuel and chemical substances in the MCPA waters, it is recommended to facilitate negotiations between MNR and the FAF on the options of providing access to the fishery Vessel Monitoring System to the MCPA management, thus enabling their use of data for the remote control of vessels operations in the area. Dissemination of experience of such Vessel Monitoring System use is of significant value in wider contexts. [MNRE]

Recommendation 8: Under particular consideration at the time of the mid-term evaluation is the question of the project’s support for procurement of a large marine vessel that would serve as the key technical resource for the reserve. The mid-term evaluation sees no issue with procurement of this vessel using project resources, as long as all appropriate measures have been taken to ensure the maintenance and ongoing operational costs of the vessel. The mid-term evaluation recommends that procurement of the vessel should proceed once a detailed plan has been written and agreed by the reserve regarding all specific points about the ongoing maintenance and operation of the vessel, including where expected fuel costs will come from over time. [MNRE, PIU, Commander Islands Zapovednik]

Recommendation 9: There is a need to strengthen online presence and resources for Russian MCPA stakeholders. In particular, options for formation of the web-based platform supporting cooperation between marine research stations within MCPAs and scientific stakeholders should be explored. Such a resource may build a basis for broader partnership between MCPAs and marine biological stations and relevant academic institutes. [PSC and PIU]

## Russia MCPAs Project Mid-term Evaluation Ratings

| - Criteria | - Rating | - Qualitative Summary |
| --- | --- | --- |
| - Project Formulation |  |  |
| - Relevance | - R | - Strengthening Russia’s network of MCPAs is highly relevant to the country’s biodiversity conservation priorities and policies, contributes to implementation of the CBD, and is in-line with the GEF biodiversity focal area strategic objectives. |
| - Conceptualization / design | - MU | - The project design is not well-structured, and is abstract and unclear in some aspects. Some descriptions of planned project activities lack concrete and clear linkages to actual circumstances and practical realities in the Russian system of PA management. . |
| - Country-drivenness | - MS | - The MNRE was the primary point of government contact during the project development phase. The project would have been strengthened with increased stakeholder ownership among other government institutions, particularly the FAF, which is a critical partner. |
| - Stakeholder involvement in design | - S | - According to project stakeholders all key institutions and organizations were consulted during the project design phase. The MNRE is the only government institution that committed co-financing prior to approval. The stakeholder consultation process did not lead to a fully well structured project design. |
| - IA & EA Execution |  |  |
| - Quality of UNDP Implementation | - MS | - UNDP has provided the appropriate project financial management support, and consistently worked to ensure the project remains focused on results. There are opportunities for strengthening going forward. The current implementation arrangements for the project are not fully meeting the needs for project implementation, and the project mid-term presents a good opportunity for further adaptive measures. |
| - Quality of Execution – Executing Agency | - MS | - The project is executed by a project team staffed by UNDP-contracted individuals. The MNRE is working well with the project team and UNDP, but may need to play a more active role in integrating the project objective and resources into national priorities related to the development of the system of MCPAs. In addition, much depends on the MNRE for engaging other government institutional stakeholders. |
| - Overall Quality of Implementation / Execution - (Efficiency) | - MS | - There has been slow progress but no critical issues thus far, but to reach the project objective the second half of project implementation will need to be more active, dynamic, adaptive and participatory. |
| - Use of the logical framework | - S | - Through the annual PIR the project team and UNDP regularly reference the logframe to assess project progress. Unfortunately the logframe does not provide a good basis for assessing project results. |
| - Financial planning and management | - S | - All project financial management aspects are in-line with UNDP policies and procedures, Russian legal requirements, and comparable norms and standards for multilateral projects in Russia. Budgeted project management costs are at the GEF-stipulated maximum threshold of 10% of GEF resources. UNDP has provided the appropriate project financial management support. |
| - Adaptive management | - MS | - A number of appropriate small-scale adaptive measures have been taken, but there is a need for a more intensive approach to address the main challenges facing the project in order to meet the results expected by the end of the project. |
| - Use and establishment of information technologies | - MU | - The project has a website used to disseminate documents and information about the project; though the website appears to be regularly updated, it does not appear to be a dynamic resource that is actively used by stakeholders. The project also has attempted to develop an online tool for analyzing the MCPA system, which is in test form, but this resource does not appear to be demand driven and may not be actively used. |
| - Operational relationships between the institutions involved | - MU | - The working relationship between UNDP and the MNRE is good, but other stakeholders, particularly the FAF, need to be more actively and directly involved in project implementation. The project faces the difficult situation found in many countries of competing and contradictory government institution mandates in the realm of marine and coastal resources. |
| - Technical capacities | - S | - The project is drawing on personnel with strong technical capacities related to MCPAs, and the project expert council is a great technical resource for the project. |
| - Monitoring and Evaluation |  |  |
| - M&E Design at Entry | - MU | - The project M&E plan meets UNDP and GEF minimum standards, with the exception of the logframe indicators and targets, which do not adequately meet SMART criteria. |
| - M&E Plan Implementation | - S | - The project M&E plan is being implemented as envisioned, with some minor exceptions. Part of the project oversight mechanisms, such as the Project Steering Committee, have the goal of building broad stakeholder engagement and support for the project objective, which has so far not been the case. |
| - Overall Quality of M&E | - MS | - The project logframe indicators and targets require revision to be able to adequately assess project results. |
| - Stakeholder Participation |  |  |
| - Production and dissemination of information | - S | - The project is providing the key outputs and other information through the project website. The project does not have a significant public education and awareness raising component. |
| - Local resource users and civil society participation | - MS | - The project activities are spread across huge territories, and at least some efforts have been made to engage stakeholders in the main project pilot sites. However, it appears that there remain opportunities for strengthening engagement from the fishing and transportation industries in the Gulf of Finland, and a need for continued progress in involvement of the local community in the Commander Islands. |
| - Establishment of partnerships | - MS | - There are some positive examples of partnerships implemented under the project, particularly with educational and research institutions, and civil society organizations in the Gulf of Finland. There remain important opportunities for building broad-based partnerships in the transportation, oil and gas, and fisheries sectors. |
| - Involvement and support of governmental institutions | - MU | - The FAF is a key government stakeholder that has not been adequately engaged in project implementation. The engagement with the national border security service has been a positive aspect. |
| - Assessment of Outcomes |  |  |
| - Outcome 1: Improved MCPA system and Institutional-level capacity enables the expansion of the MCPA system | - MU | - The results achieved thus far have been valuable, but overall results have been limited relative to the expected end-of-project status. There has been progress toward establishment of the Ingermanland Reserve, but the process is still ongoing, and has delayed other project activities in this region. Slow progress on other key results reflects overall lagging results under this outcome. |
| - Outcome 2: MCPA management know-how is demonstrated, expanded and reinforced | - MS | - Some of the most valuable project results thus far have been through the activities under this outcome, including support for the Commander Islands, and multiple initiatives in the Gulf of Finland. A positive indication of progress is the (limited) increase in management effectiveness for two of the project’s three main pilot sites. Much more work remains to be done under this outcome, which has been partially slowed by the lack of establishment of the Ingermanland Reserve thus far. |
| - Outcome 3: Strengthened MCPA system effectively captures knowledge and enables replication of best practice | - MS | - More of the work under this outcome will be carried out in the later stages of the project when there is more experience from the earlier project activities. Activities thus far have been slower than anticipated, and are marginally on track to reach end of project targets. |
| - Overall Project Outcome Rating | - MS | - Some positive results have been achieved thus far, but to have fully reach the outcomes the project will need to achieve much more during the second half of the project than it has done in the first half. |
| - Progress Toward Project Objective (“To facilitate expansion of the national system of marine and coastal protected areas and improve its management effectiveness”) (Effectiveness) | - MU | - At this stage of implementation the project has not yet generated significant progress toward incremental results at the systemic level. Improvements in METT scores for all MCPA for which scores were calculated average 6% increase, with the project target at 20% (though instituting a more robust approach for calculating METT scores would be useful.) The project design created an unclear project approach, without adequate stakeholder input and ownership. |
| - Sustainability |  |  |
| - Financial Resources | - U/A | - At this stage of project implementation it is unclear what financial resources will be required to sustain eventual project results, and therefore not possible to assess financial risks to sustainability. |
| - Socio-political | - MU | - There is a need to strengthen stakeholder ownership and buy-in among the full range of stakeholders, particularly the FAF. Without ownership and active engagement of the critical partners the project’s lasting impact will be limited. |
| - Institutional Framework and Governance | - ML | - There are legal and policy challenges for effective MCPA management, and government institutional mandates that are not fully in-sync. There is currently not adequate national political will to institute effective mechanisms for coordinated government management of marine and coastal resources. Nonetheless, the eventual project results should be able to continue positively contributing to improved management of MCPAs in Russia. |
| - Environmental | - N/A - ML | - The project results on the ground thus far are limited, and therefore are not subject to specific environmental risks. At the same time, the key environmental risks to Russia’s MCPAs remain pertinent, particularly in the three primary project pilot sites. |
| - Overall Likelihood of Sustainability | - MU | - Based on the lowest rating from the above main criteria for sustainability. |
| - Progress Toward Impact |  |  |
| - Environmental Status Improvement | - U/A | - It is too early to assess the project’s progress toward impact. |
| - Environmental Stress Reduction | - U/A | - It is too early to assess the project’s progress toward impact. |
| - Progress Towards Stress/Status Change | - U/A | - It is too early to assess the project’s progress toward impact. There has been some progress on this aspect – for example, through increasing the management effectiveness of the Commander Islands reserve administration, and |
| - Progress Toward Overall Project Results | - MS | - The project is producing some valuable results, and implementation of the work plan progressing. However, a project of this size and scope is expected to produce significant results by the end of the project, and much greater progress is required in the second half of implementation to make a significant incremental contribution toward reaching the overall project objective and generating Global Environmental Benefits. |

# Annexes

- Annex 1: Evaluation Terms of Reference

- Annex 2: GEF Operational Principles

- Annex 3: Logframe With Suggested Revisions

- Annex 4: Theory-of-Change Review of Outcomes to Impacts Framework

- Annex 5: List of Persons Interviewed

- Annex 6: Field Visit Schedule

- Annex 7: Interview Guide

- Annex 8: Evaluation Matrix

- Annex 1: Mid-term Evaluation Terms of Reference

- Note: For space considerations the annexes of the TORs have not been included.

Terms of Reference

for the terminal evaluation of the UNDP/GEF Project

“Strengthening the Marine and Coastal Protected Areas of Russia”

00069210

I. INTRODUCTION

Standard UNDP/GEF Monitoring and Evaluation requirements

The Monitoring and Evaluation (M&E) policy at the project level in UNDP/GEF has four objectives: i) to monitor and evaluate results and impacts; ii) to provide a basis for decision making on necessary amendments and improvements; iii) to promote accountability for resource use; and iv) to document, provide feedback on, and disseminate lessons learned. A combination of tools should be used to ensure effective project M&E. These might be applied continuously throughout the lifetime of the project – e.g.periodic monitoring of indicators -, or as specific time-bound exercises such as mid-term review, audit reports and independent evaluations.

In accordance with UNDP/GEF M&E policies and procedures, all projects with long implementation period are strongly encouraged to conduct mid-term evaluations. In addition to providing an independent in-depth review of implementation progress, this type of evaluation is responsive to GEF Council decisions on transparency and better access to information during implementation.

Mid-term evaluations are intended to identify potential project design problems, assess progress towards the achievement of objectives, identify and document lessons learned (including lessons that might improve design and implementation of other UNDP/GEF projects), and to make recommendations regarding specific actions that might be taken to improve the project. It is expected to serve as a mean of validating or filling the gaps in the initial assessment of relevance, effectiveness and efficiency obtained from monitoring. The mid-term evaluation provides the opportunity to assess early signs of project success or failure and prompt necessary adjustments.

This evaluation is to be undertaken taking into consideration the GEF Monitoring and Evaluation policy (http://www.thegef.org/gef/node/4184 ) and the UNDP/GEF Monitoring and Evaluation Policy (http://www.undp.org/gef/monitoring/policies.html ).

Project objectives

In 2009, with funding from the Global Environment Facility, UNDP launched a project targeting conservation and sustainable use of globally significant coastal and marine biodiversity of Russia. This project is designed to complement the governmental efforts to expand the marine protected area system and strengthen its management effectiveness.

The Project Objective is therefore to facilitate expansion of the national system of marine and coastal protected areas and improve its management effectiveness as reflected in design issues relating to both individual sites and protected area systems and adequacy and appropriateness of management systems and processes, and the delivery of protected area objectives. The three main outcomes of the project are: (i) Improved MCPA system-level capacity enables the expansion of marine and coastal protected areas; (ii) MCPA management know-how is demonstrated, expanded and reinforced; and (iii) Strengthened MCPA system effectively captures knowledge and enables replication of best practice. The project is supposed to improve the coverage of marine and coastal ecosystems by 8.7 million hectares by: a) finalizing the protection of the new 14,000 ha Ingermanland Zapovednik, b) facilitating the expansion or establishment of additional eight MCPA covering 7,680,000 hectares; and c) creating the enabling environment for the protection of an additional 1,006,000 million ha of marine and coastal ecosystems.  The project is also designed to improve management effectiveness of a network of 35 MCPA across Russia covering over 24 million ha. This is believed to be an important step in securing the long-term conservation of globally significant coastal and marine biodiversity sheltered in the longest coastline in the world.

Project location: Russian Federation

Project pilot sites:  Commander Islands, Primorsky Krai, Leningrad Oblast

The implementation of project activities are coordinated by the Project implementation Unit m based in Moscow. The overall management of the project is the responsibility of Project Manager, who is a full time employee of the project, stationed in the UNDP Project Support Office in Moscow.

The project was launched late in 2009 and was supposed to be implemented within four years. However, due to the late project start and delays in project operationalisation the mid-term evaluation is taking place later than originally supposed. The project funding provided by the GEF amounts to USD 4,000,000. Pledged cofinancing is estimated at USD 9,396,000.

The project is implemented by the Government of Russia (GOR) represented by the federal Ministry of Natural Resources & Ecology (MNRE) and operates according to UNDP National Implementation Modality (NIM).

Project website: http://www.mpa-russia.ru/

II. OBJECTIVES OF THE EVALUATION

This Mid Term Evaluation is initiated by the UNDP Project Support Office in Russia and it aims to provide managers (at the Project Implementation Unit, UNDP Russia Country Office and UNDP/GEF levels) with strategy and policy options for more effectively and efficiently achieving the project’s expected results and for replicating the results. It also provides the basis for learning and accountability for managers and stakeholders.

The evaluation will play a critical role in the future implementation of the project by providing advice on: (i) how to strengthen the adaptative management and monitoring function of the project; (ii) how to ensure accountability for the achievement of the GEF objective; (iii) how to enhance organizational and development learning; and (iv) how to enable informed decision – making.

The evaluation will have to provide to the GEF Secretariat complete and convincing evidence to support its findings/ratings. The consultant should prepare specific ratings on seven aspects of the project, as described in the 'Reporting' section of this Terms of Reference. Particular emphasis should be put on the current project results and the possibility of achieving the objective and outcomes in the established timeframe, taking into consideration the speed, at which the project is proceeding.

The evaluation is intended to provide a comprehensive overall assessment of the project and provides an opportunity to critically assess administrative and technical strategies issues and constrains associated with large international and multi-partner initiatives. The evaluation should also provide recommendations for strategies, approaches and/or activities to improve the potential of the Project to achieve expected outcomes and meet the objective within the Project timeframe. Findings of this evaluation will be incorporated as recommendations for enhanced implementation of the current project phase in the future years.

The purpose of the Mid-Term Evaluation is:

- To assess overall performance against the Project objective and outcomes as set out in Project Document and other related documents

- To assess the effectiveness and efficiency of the Project

- To analyze critically the implementation and management arrangements of the Project

- To assess the progress to date towards achievement of the outcomes;

- To review planned strategies and plans for achieving the overall objective of the Project within the timeframe;

- To assess the sustainability of the project’s interventions.

- To list and document initial lessons concerning Project design, implementation and management

- To assess Project relevance to national priorities

- To provide guidance for the future Project activities and, if necessary, for the implementation and management arrangements.

In particular, this evaluation will assess progress in establishing the information baseline, reducing threats, and identifying any difficulties in project implementation and their causes, and recommend corrective course of action.  Effective action to rectify any identify issues hindering implementation will be a requirement prior to determining whether implementation should proceed.

Project performance will be assessed based on Project’s Logical Framework Matrix (see Annex 2), which provides clear performance and impact indicators for project implementation along with their corresponding means of verification. Success and failure should be determined in part by monitoring changes in baseline conditions.

The Report of the Mid-Term Evaluation will be stand-alone document that substantiates its recommendations and conclusions.

# 3. EVALUATION

The evaluation should assess:

Project concept and design: The evaluators will assess the project concept and design. He/she should review the problem addressed by the project and the project strategy, encompassing an assessment of the appropriateness of the objectives, planned outputs, activities and inputs as compared to cost-effective alternatives. The executing modality and managerial arrangements should also be judged. The evaluator will assess the progress in achievement of indicators and review the work plan, planned duration and budget of the project.

Implementation: The evaluation will assess the implementation of the project in terms of quality and timeliness of inputs and efficiency and effectiveness of activities carried out. Also, the effectiveness of management as well as the quality and timeliness of monitoring and backstopping by all parties to the project should be evaluated. In particular, the evaluation is to assess the Project team’s use of adaptive management in project implementation.

Project outputs, outcomes and impact: The evaluation will assess the outputs, outcomes and impact achieved by the project as well as the likely sustainability of project results. This should encompass an assessment of the achievement of the immediate objectives and the contribution to attaining the overall objective of the project. The evaluation should also assess the extent to which the implementation of the project has been inclusive of relevant stakeholders and to which it has been able to create collaboration between different partners. The evaluation will also examine if the project has had significant unexpected effects, whether of beneficial or detrimental character.

The Mid-term Evaluation will also cover the following aspects:

3.1.	Progress towards Results

Changes in development conditions. Address the following questions, with a focus on the perception of change among stakeholders:

- Have critically endangered species been properly and adequately protected within the marine and coastal protected areas within the Project sites in Russia?

- Have there been changes in local stakeholder behavior (i.e. threats…) that have contributed to improved conservation? If not, why not?

- Is there distinct improvement in biodiversity information turnover and use in decision making among MCPA related stakeholders?

- Has awareness on biodiversity conservation and subsequent public participation in biodiversity monitoring and management increased as a result of the project?

- Is there adequate territorial planning in place, or in progress, ensuring long-term conservation of biodiversity and cultural values?

Measurement of change: Progress towards results should be based on a comparison of indicators before and after (so far) the project intervention. Progress can also be assessed by comparing conditions in the project site to conditions in similar unmanaged sites.

Project strategy: how and why outcomes (listed as outputs in the project document) and strategies contribute to the achievement of the expected results. Examine their relevance and whether they provide the most effective route towards results.

Sustainability: Extent to which the benefits of the project will continue, within or outside the project domain, after it has come to an end. Relevant factors include for example: development of a sustainability strategy, establishment of financial and economic instruments and mechanisms, mainstreaming project objectives into the local economy, etc.

3.2. Project’s Adaptive Management Framework

Monitoring Systems

- Assess the monitoring tools currently being used:

    - Do they provide the necessary information?

    - Do they involve key partners?

    - Are they efficient?

    - Are additional tools required?

- Reconstruct baseline data if necessary.  Reconstruction should follow participatory processes and could be achieved in conjunction with a learning exercise

- Ensure the monitoring system, including performance indicators, at least meets GEF minimum requirements.  Apply SMART indicators as necessary.

- Apply the GEF Tracking Tool and provide a description of comparison with initial application of the tool.

Risk Management

- Validate whether the risks identified in the project document, PIRs and the ATLAS Risk Management module are the most important and whether the risk ratings applied are appropriate. If not, explain why.  Describe any additional risks identified and suggest risk ratings and possible risk management strategies to be adopted.

- Assess the project’s risk identification and management systems:

  - Is the UNDP/GEF Risk Management System appropriately applied?

  - How can the UNDP/GEF Risk Management System be used to strengthen project management?

Work Planning

- Assess the use of the logical framework as a management tool during implementation and any changes made to it: (i) Ensure the logical framework meets UNDP/GEF requirements in terms of format and content; and (ii) What impact did the retro-fitting of impact indicators have on project management?

- Assess the use of routinely updated workplans.

- Assess the use of electronic information technologies to support implementation, participation and monitoring, as well as other project activities

- Are work planning processes result-based?  If not, suggest ways to re-orientate work planning.

- Consider the financial management of the project, with specific reference to the cost-effectiveness of interventions.  Any irregularities must be noted.

Reporting

- Assess how adaptive management changes have been reported by the project management

- Assess how lessons derived from the adaptive management process have been documented, shared with key partners and internalized by partners.

3.3.	Underlying Factors

- Assess the underlying factors beyond the project’s immediate control that influence outcomes and results.  Consider the appropriateness and effectiveness of the project’s management strategies for these factors.

- Re-test the assumptions made by the project management and identify new assumptions that should be made

- Assess the effect of any incorrect assumptions made by the project

3.4.	UNDP Contribution

- Assess the role of UNDP against the requirements set out in the UNDP Handbook on Monitoring and Evaluating for Results.  Consider: Field visits; Steering Committee/TOR follow-up and analysis; PIR preparation and follow-up; GEF guidance;

- Consider the new UNDP requirements outlined in the UNDP Programme and Operations Policies and Procedures (POPP), especially the Project Assurance role, and ensure they are incorporated into the project’s adaptive management framework

- Assess the contribution to the project from UNDP “soft” assistance (i.e. policy advice & dialogue, advocacy, and coordination).  Suggest measures to strengthen UNDP’s soft assistance to the project management.

3.5.	Partnership Strategy

- Assess how partners are involved in the project’s adaptive management framework: (i) Involving partners and stakeholders in the selection of indicators and other measures of performance; (ii) Using already existing data and statistics; and (iii) Analyzing progress towards results and determining project strategies.

- Identify opportunities for stronger substantive partnerships;

- Assess how local stakeholders participate in project management and decision-making.  Include an analysis of the strengths and weaknesses of the approach adopted by the project and suggestions for improvement if necessary.

- Consider the dissemination of project information to partners and stakeholders and if necessary suggest more appropriate mechanisms;

- Assessment of collaboration between governments, intergovernmental and non-governmental organizations.

- Assessment of collaboration between implementation units of other related projects.

- Assessment of local partnerships

- Transfer of capacity to the national institutions;

3.6. Project Finance:

- Review the changes to fund allocations as a result of budget revisions and provide an opinion on the appropriateness and relevance of such revisions, taking into account the project activity timeframe;

- Review the effectiveness of financial coordinating mechanisms

# 4. METHODOLOGY FOR EVALUATION APPROACH

The mid-term Evaluation will be done through a combination of processes including a desk study, site visit and interviews with Project Stakeholders.

Evaluator should seek guidance for his/her work in the following materials:

GEF Monitoring and Evaluation policy (http://www.thegef.org/gef/node/4184 ) and the UNDP/GEF Monitoring and Evaluation Policy (http://www.undp.org/gef/monitoring/policies.html ).

The methodology for the evaluation is envisaged to cover the following areas:

- Desk study review of all relevant Project documentation

- Consultations with MNRE, UNDP

- Field site visit  within project territories

- Interviews with stakeholders

In preparation for the evaluation mission, the project manager, with assistance from UNDP project support office, will arrange for the completion of the Management Effectiveness Tracking Tool (METT). The tracking tool will be completed / endorsed by the  relevant implementing agency or a qualified national research /scientific institution, and not by the international consultant or UNDP staff. The tracking tool (METT) will be submitted to the evaluation specialist, who will need to provide his/her comments on it. Upon incorporation of the comments from the evaluation specialist to the tracking tool, it will be finalized and attached as a mandatory annex to the final evaluation report.

5. PRODUCTS

The core product of the Mid-Term Evaluation will be a Mid-Term Evaluation Report.

The Mid-Term Evaluation report will include:

- Executive summary

- Introduction

- Findings and conclusions in relation to issues to be addressed identified under the Evaluation section of this TOR

- Recommendations

- Lessons Learned

- Annexes

The draft and final report will be written in the format outlined in ANNEX 1 of this TOR. The draft report will be submitted to UNDP/GEF and the Ministry of Natural Resources and Ecology no later than August 20th 2012. Based on the feedback received from stakeholders a final report will be prepared by 20st of September 2012.

The report will be submitted electronically in English.

The report will be supplemented by rate tables (ANNEX 3).

# 6. EVALUATOR  QUALITIES:

The Mid-term evaluation will be carried by an individual consultant. Evaluator shall possess the following qualifications:

- Recent experience with result-based management evaluation methodologies;

- Experience applying participatory monitoring approaches;

- Experience applying SMART indicators and reconstructing or validating baseline scenarios;

- Recent knowledge of the GEF Monitoring and Evaluation Policy;

- Recent knowledge of UNDP’s results-based evaluation policies and procedures

- Competence in Adaptive Management, as applied to conservation or natural resource management projects;

- Familiarity with protected area policies and management structures in Eastern Europe/CIS/Russia;

- Demonstrable analytical skills;

- Work experience in relevant areas for at least 10 years;

- Experience with multilateral or bilateral supported conservation projects;

- Project evaluation experiences within United Nations system will be considered an asset;

- Excellent English communication skills.

# 7. IMPLEMENTATION ARRANGEMENTS

## Evaluation management arrangements

- Role of Project Manager (located in Moscow)

  - Coordination of evaluation activities and logistics

  - Arrangement of field site visits

  - Organization of meetings with selected stakeholders

- Role of UNDP

  - Coordination of evaluation activities in Moscow

  - Administrative and logistical support for the evaluator in Moscow

## 8.	Tentative timeframe

- Selection of evaluator					May 2012

- Briefings for evaluator					June 2012 (precise dates tbc)

- Desk review 						July 2012 (precise dates tbc)

- Debriefings in Moscow   	 			end of July 2012 (precise dates tbc)

- Trip to the field sites (including allocation for travel), interviews with

local stakeholders					 (planned for 1-15 August 2012, tbc))

- Circulation of draft evaluation report for comments	 end of August 2012

- Preparation of final evaluation report 			by 20 September 2012

- Annex 2. GEF Operational Principles

http://www.gefweb.org/public/opstrat/ch1.htm

TEN OPERATIONAL PRINCIPLES FOR DEVELOPMENT

AND IMPLEMENTATIONOF THE GEF'S WORK PROGRAM

1. For purposes of the financial mechanisms for the implementation of the Convention on Biological Diversity and the United Nations Framework Convention on Climate Change, the GEF will function under the guidance of, and be accountable to, the Conference of the Parties (COPs).  For purposes of financing activities in the focal area of ozone layer depletion, GEF operational policies will be consistent with those of the Montreal Protocol on Substances that Deplete the Ozone Layer and its amendments.

2. The GEF will provide new, and additional, grant and concessional funding to meet the agreed incremental costs of measures to achieve agreed global environmental benefits.

3. The GEF will ensure the cost-effectiveness of its activities to maximize global environmental benefits.

4. The GEF will fund projects that are country-driven and based on national priorities designed to support sustainable development, as identified within the context of national programs.

5. The GEF will maintain sufficient flexibility to respond to changing circumstances, including evolving guidance of the Conference of the Parties and experience gained from monitoring and evaluation activities.

6. GEF projects will provide for full disclosure of all non-confidential information.

7. GEF projects will provide for consultation with, and participation as appropriate of, the beneficiaries and affected groups of people.

8. GEF projects will conform to the eligibility requirements set forth in paragraph 9 of the GEF Instrument.

9. In seeking to maximize global environmental benefits, the GEF will emphasize its catalytic role and leverage additional financing from other sources.

10. The GEF will ensure that its programs and projects are monitored and evaluated on a regular basis.

- Annex 3: Project Status of Objective and Outcome Indicators Target Delivery (from the 2011 PIR)

| Description | Description of Indicator | Baseline Level | Target Level at end of project | Suggestions for Revisions |
| --- | --- | --- | --- | --- |
| Objective: To facilitate expansion of the national system of marine and coastal protected areas and improve its management effectiveness. | Area of coastal and marine area under protection expanded. | 24,577,651 ha | Additional area protected with direct influence of project: +14,000 ha; Additional area protected with facilitation of the project + 7,680,000 ha; Enabling environment created for establishment of additional 1,006,000 million ha; New total area under protection: 33,277,651 ha | The relevance of this indicator as a measure of project results has been reduced by the adoption of the independent federal government plan for PA expansion in Russia through 2020, which mandates the specific MCPAs the government is planning to establish through this period. During the project development phase it had been anticipated that the project would be able to have a greater influence on the establishment of new MCPAs. Nonetheless the project is well-positioned to provide support to strengthening the management of MCPAs newly established according to the government plan. This evaluation recommends this indicator be revised to only focus on the project’s direct influence on the establishment of Ingermanland Reserve (14,000 ha), and to include a new indicator on the project’s influence on strengthening management of other newly established MCPAs: “Hectares of MCPAs established from project initiation through 2013 with increased management effectiveness”, with an end-of-project target of an increases METT score of 20% over the baseline at the time of establishment of the respective MCPAs. |
|  | Indirect impact on improved management effectiveness in 24 million hectares of MCPA through METT Score. (see (a) through (f) below) | (see data below) | +20% | This is one of the critical indicators for the project and no specific suggestions are made for revision of the indicator. However, it is recommended that the METT scores for the five regional MCPAs in the Gulf of Finland be added amongst the PAs for which METT scores are calculated, as an additional measure for documenting project results in this region. It would be useful for the project team to clearly specify which project activities are expected to have contributed to increasing the average METT score within the system of MCPAs. This would facilitate increased understanding of the project’s contribution, as opposed to any significant changes in METT scores that had nothing to do with project activities, or that occurred despite project activities due to other factors. Further, it would be useful to implement a more robust approach to generating METT scores, through a process engaging the staff and administration of the respective MCPAs, as well as possibly other external stakeholders. |
|  | (a) Zapovedniks - Arctic Bolshoi Arktichesky Gydansky Kandalakshsky Kandalakshsky Nenetsky U-Lensky Taimyrsky Wrangel Island | Zapovedniks - Arctic Bolshoi Arktichesky - 29 Gydansky - 40 Kandalakshsky - 37 Kandalakshsky - 42 Nenetsky - 36 U-Lensky - 42 Taimyrsky - 50 Wrangel Island - 47 Russian Arktic - 0 | Zapovedniks - Arctic Bolshoi Arktichesky - 41 Gydansky - 56 Kandalakshsky - 52 Kandalakshsky - 58 Nenetsky - 50 U-Lensky - 69 Taimyrsky - 70 Wrangel Island - 65 Russian Arktic - to be determined |  |
|  | (b) Far East Botchinsky Dzhugdzhursky Kronotsky Koryaksky Kurilsky Lazovsky Magadansky Poronaisky Sikhote-Alinsky | Far East Botchinsky - 37 Dzhugdzhursky - 35 Kronotsky – 58 Koryaksky - 42 Kurilsky - 55 Lazovsky – 54 Magadansky – 51 Poronaisky – 43 Sikhote-Alinsky – 56 | Far East Botchinsky - 52 Dzhugdzhursky - 49 Kronotsky – 80 Koryaksky - 58 Kurilsky - 76 Lazovsky – 75 Magadansky – 72 Poronaisky – 59 Sikhote-Alinsky – 78 |  |
|  | (c) Caspian Sea Astrakhansky Dagestansky | Caspian Sea Astrakhansky – 62 Dagestansky – 44 | Caspian Sea Astrakhansky – 87 Dagestansky – 62 |  |
|  | (d) Baltic Regional zakazniks | Baltic Regional zakazniks - 30 | Baltic Regional zakazniks - 42 |  |
|  | (e) National Parks Kurshskaya Kosa Sochinsky | National Parks Kurshskaya Kosa - 63 Sochinsky - 59 | National Parks Kurshskaya Kosa - 87 Sochinsky - 83 |  |
|  | (f) Federal Zakazniks Franz-Josef Land Nenetsky Nizhne-Obskiy Severnaya Zemlya Yuzhno-Kamchatsky Malye Kurily Tumninskiy Agrakhansky Priazovsky Samursky | Federal Zakazniks Franz-Josef Land - 29 Nenetsky -- 28 Nizhne-Obskiy - 13 Severnaya Zemlya - 13 Yuzhno-Kamchatsky - 28 Malye Kurily - 34 Tumninskiy - 13 Agrakhansky - 41 Priazovsky - 19 Samursky - 13 | Federal Zakazniks Franz-Josef Land - 41 Nenetsky -- 39 Nizhne-Obskiy - 19 Severnaya Zemlya - 19 Yuzhno-Kamchatsky - 39 Malye Kurily - 48 Tumninskiy - 19 Agrakhansky - 57 Priazovsky - 27 Samursky – 19 |  |
|  | Populations of two globally threatened seabird species at CIZ: Red-legged Kittiwake | Red-legged kittiwake Toporkov Island: 22 pairs; Ariy Kamen’: 223 pairs (2008 survey) | Pop #s within natural range of variation | As outlined in the evaluation report, species-based impact level indicators are useful to maintain focus on project results, and to identify some indicators of the Global Environmental Benefits the project is seeking to generate. At the same time, except in cases where projects have on-the-ground activities targeting specific species, the project’s contributions are unlikely to have any significant effect on species’ population trends before the end of the project. This evaluation recommends that these impact level indicators be maintained in the project results framework, but with a clear understanding that it is not expected that the target values will be achieved as a result of project activities by the end of the project. If desired, sometime after project completion an ex-post impact evaluation could use these indicators to conduct an assessment of the project’s long-term impacts. On the whole these impact indicator targets do a good job of focusing on long-term population trends rather than a specific point-in-time value. However it would be useful for the long-term trend targets to be clearly rationalized – on what basis is the target for three of the indicators within +/- “20%” of LTM – does this value represent a population size that can be sustained in the long-term? For a population with as few individuals in the target area as the Baltic ringed seal it could be argued that a much larger population base would be required to sustain this species in perpetuity. |
|  | Steller sea lion populations on Mediny Island; - # of adult/juveniles - # of Pups - # of breeding males | Medny: 88 adult males, 105 subadult males, 295 females, 182 1year + specimens, 231 pups | Stable pop or within +/- 20% of Long-Term Mean (LTM). |  |
|  | # and distribution of sea cucumbers in Reserve. | 0.02 – 0.03 m2 | Stable or increasing. |  |
|  | Baltic seal population - Ringed seals [Per Inception Report, this indicator no longer measures Grey seals, and only the Russian part of the Gulf is being monitored] | Based upon 2010 spring aerial survey: 40-45 | Stable pop or within +/- 20% of LTM. |  |
|  | Larga seal breeding population in the Far Eastern Marine Reserve | 2100 adults 380 pups (census of 2008) | Stable pop or within +/- 20% of LTM. |  |
| Outcome 1: Improved MPA system and institutional-level capacity enables the expansion of the MCPA system. | Area of MCPA in the process of establishment. | 14,000 | 2,500,000 hectares | This indicator faces the same issue as the first indicator at the objective level above. With the adoption of the government plan for PA expansion to 2020 this indicator has reduced relevance for assessing results of the Russia MCPAs project, as the area of newly established MCPAs will not be a result of the project’s contribution, with the exception of the Ingermanland Reserve. However, as highlighted in the evaluation report, there is an excellent opportunity for the project to directly support the establishment and strengthening of the management regimes for the MCPAs newly established under the government plan. It would have been useful to include as an indicator the representative coverage of Russia’s MCPA system in terms of the types and extent of ecosystems and species under protection – however, as shown in the project there is currently not adequate data to make this level of assessment. This evaluation recommends that this indicator be reframed as hectares of newly established MCPAs with strengthened management effectiveness (as measured by the METT) resulting from project support. This would facilitate assessment of the project’s contributions to newly established MCPAs such as Russian Arctic National Park and Beringia National Park. |
|  | # of new policies and guidelines developed and adopted by MNRE to strengthen effectiveness. | 0 | At least 4 in total | No specific revision suggested. However, the indicator (and target) does not fully meet SMART criteria – particularly with regard to specificity and relevance. What is the threshold to define which policies and guidelines “strengthen effectiveness”? It would also be helpful for the indicator target to be clearly rationalized through a results-oriented focus – why is it necessary for the project to achieve four policies and guidelines? Does this number relate to four specific policy barriers or deficiencies that the project is targeting, Or is this just a value that “seemed reasonable” for the project to achieve? Or is this a “supply-driven” indicator target based simply on the planned project activities? Further, the indicator and target are at the output level, which have reduced relevance for tracking project results. Ultimately it is not really the number of policies adopted that lead to results, but the actual effect of those polices when implemented – a result that should be captured under the METT indicator at the objective level. |
|  | # of marine mammal zones with strengthened protection. | 0 | At least 10. | No specific revision suggested. However, see comments above with respect to specificity, a clearly rationalized target, supply vs. demand driven target, and output level indicators. |
|  | MNRE MCPA Capacity Scorecard (see (a) through (e) below) | (Baseline data below) | (EoP Targets below) | No specific revision suggested. However, other UNDP-GEF projects have found the capacity scorecard to have limitations for effectively tracking project results, as the scope of the scorecard covers many factors that are not addressed by projects. This should be kept in mind during the terminal evaluation, and appropriate analysis carried out to identify the project’s particular contributions to increases (or decreases) in capacity scores documented through the scorecard. |
|  | (a) Policy formulation Systemic Institutional | Policy Formulation 3/out of 6 1/out of 3 | Policy Formulation 5/out of 6 2/out of 3 |  |
|  | (b) Implementation Systemic Institutional Individual | Implementation 3/out of 9 7/out of 27 4/out of 12 | Implementation 7/out of 9 20/out of 27 8/out of 12 |  |
|  | (c) Engagement & consensus Systemic Institutional Individual | Eng. & consensus 3/out of 6 3/out of 6 1/out of 3 | Eng. & consensus 5/out of 6 5/out of 6 2/out of 3 |  |
|  | (d) Info & knowledge Systemic Institutional Individual | Info & knowledge 2/out of 3 3/out of 3 1/out of 3 | Info & knowledge 3/out of 3 3/out of 3 2/out of 3 |  |
|  | (e) Monitoring Systemic Institutional Individual | Monitoring 2/out of 6 3/out of 6 1/out of 3 | Monitoring 4/out of 6 4/out of 6 2/out of 3 |  |
| Outcome 2: MPA management know-how is demonstrated, expanded and reinforced. | Direct impact on improved effectiveness in pilot sites = improved management in 6 million ha though METT Score. | CIZ: 57 FEMZ: 63 IZ: 13 | CIMPCA: 75 FEMZ: 80 IZ: 60 | No specific revision recommended, but it would be helpful to have an understanding of the rationale for the target score to allow an improved assessment of the results indicated by the increased score. |
|  | Proposed new indicators Under Outcome 2 the project is undertaking a number of different types of pilot or demonstration activities in the three pilot sites. These activities are ultimately leading toward the goal of strengthened management effectiveness in each of these areas, and thus the above indicator on management effectiveness of the three sites is useful. However, this indicator does not allow a more in-depth documentation and assessment of the project results under each of the outputs under Outcome 2.5. It is not necessary to include indicators for all the different project activities conducted, but it would be helpful to have some expanded measures of the project results for assessment at the final evaluation. This evaluation proposes additional indicators below intended to support further documentation of the project results under Outcome 2. |  |  |  |
|  | Output 2.1 – Percentage of Commander Islands reserve PA staff participating in specific individual-level capacity development activities on an annual basis | 0%? | 80% | A significant focus of the activities under Output 2.1 relates to capacity strengthening for the Commander Islands reserve. Activities include the management audit that was conducted, development of a training needs assessment, exchanges between MCPAs, and study tours – all of which include individual level capacity strengthening approaches. With the desired overall outcome level result of increasing management effectiveness of the reserve, strengthening individual-level capacity will be an important element. A target of 80% is proposed as representing a minimum ideal for the percentage of staff involved in capacity development activities on an annual basis. The ideal normative status would be 100%, but from a practical point of view it may not be possible to have all staff participating in specific capacity development activities every year. The baseline would need to be determined retroactively, but the target is expected to be valid without a confirmed baseline figure – assuming the baseline value is not already very close to the proposed target. Other important project results under this output that are not captured by this indicator are the increased government budget allocation for the reserve that is linked with the project’s support, and the planned increases in technical capacity for the reserve. However, both factors should translate to an increase in the overall METT score for the reserve which is already included as an indicator. |
|  | Output 2.2 – Percentage of bird and mammal species in the Commander Islands monitored annually with identified estimated population sizes and overall trends | ? | 50%? | One of the main results of the project under this output is the development of the monitoring program for the Commander Islands. There are approximately 203 bird species identified in the Commander Islands, of which 58 are nesting, and 32 species of mammals. A target of 50% is proposed as a figure that should allow a picture of the overall status of the Commander Islands ecosystem, and facilitate management decision-making, but this target value should be validated or revised according to input from the Commander Islands MCPA staff, the project technical expert council, or the Project Steering Committee. The baseline value would also need to be retroactively established. |
|  | Output 2.3 – Negative ecosystem and social impacts from tourism | ? non-existent? | No significant impacts negatively affecting species populations; No significant negative social impacts (“Significant” = any impact compromising the ecological or social integrity representing the global significance of the Commander Islands) | The project has supported development of a tourism strategy, and tourism is increasing in the PA. The reserve administration is developing tourism infrastructure, and it is anticipated that tourism will play an increasingly important role for revenue collection for the reserve. The project is anticipated to continue working with the reserve to promote tourism and increase its value for strengthening management of the reserve. Through this process the environmental tourism carrying capacity needs to be carefully established, and it should be ensured over time that tourism does not negatively affect the ecological integrity of the reserve. The value proposition of tourism for the Commander Islands is primarily a financial one, but there is no defined specific expected total monetary value that tourism may provide – in this case the biodiversity-focused result indicator proposed relates to avoided negative impacts rather than trying to track the as yet undefined potential positive outcomes from tourism. The baseline would need to be retroactively established. |
|  | Output 2.4 – Number of invasive species for which ecosystem and financial impacts are assessed for the geographic area targeted under the project (Far Eastern Marine Reserve and surrounding area) | 0? | 30 | Under this output the project is supporting monitoring and research of invasive species in the Far Eastern Marine Reserve. According to project stakeholders, there are more than 50 species of tropic and sub-tropic origin that have successfully adapted to the area, including 20 species that are considered serious bio-fouling organisms. While continued research to understand trends is important, it is necessary to translate knowledge into actionable management proposals – therefore this proposed indicator focuses on the assessment of ecological and financial impacts of invasive species. A target of 30 is proposed as covering the 20 species considered to have significant bio-fouling effects, plus a few additional species that may have other negative impacts. The baseline would need to be retroactively established. |
|  | Output 2.5 – Status of regional preparation to handle wildlife impacts of hazardous waste spills | Regional hazardous response plans do not include any substantive information on methodologies and plans for addressing wildlife impacts of spills | Regional hazardous spill response plans include detailed information on preparation for and methodology to address wildlife impacts from hazardous spills, and at least two trainings or simulations have been conducted to test response preparedness | The project has supported activities for strengthening hazardous spill response in the Gulf of Finland, and it is anticipated that additional activities will be carried out in the remaining period. |
| Outcome 3: Strengthened MCPA system effectively captures knowledge and enables replication of best practice. | # of MCPA adopting invasive species management plans. | 0 | 3 (FEMZ, IZ, and probably Kurshskaya Kosa) | No specific revisions proposed. However, it would be helpful for the normative situation to be clarified (i.e. how many MCPAs require invasive species management plans?), and the rationale for the target made explicit. |
|  | # of MCPA adopting contingency plans for hazardous material spills. | 0 | 4 (TBD) | No specific revisions proposed. However, it would be helpful for the normative situation to be clarified (i.e. how many MCPAs require contingency plans for hazardous material spills?), and the rationale for the target made explicit. |
|  | # of official partnerships (monitoring, enforcement) formed by MCPA nationwide. | Monitoring marine and coastal ecosystems agreements - 14 Cooperation agreement with other MCPA - 2 Cooperation agreement with tourism companies - 2 Written agreement for cooperation in enforcement – 0 | At least 20 monitoring agreements. At least 10 cooperation agreements. At least 7 tourism management and promotion agreements. At least 5 written agreements in cooperation on enforcement. | No specific revisions proposed. However, it would be helpful for the target rationale to be explained – i.e. in the case of monitoring: What do the target values represent in terms of results for improving the status of biodiversity? How many monitoring agreements should there be? Are more agreements inherently better? Or are 20 agreements only an insignificant fraction of what is really needed? What do these agreements represent for strengthening management of MCPAs? Similar brief explanations should be provided with respect to agreements on cooperation, tourism management, and enforcement. It is necessary for the project stakeholders to have a clear understanding of the results-based rationale for the outputs produced. |
|  | # of Russia’s MCPAs included in the North Pacific monitoring network (indicator introduced by the Inception Report) | 0 | 3 | No specific revisions proposed. However, it would be helpful for the target rationale to be explained. |
|  | # of presentations or knowledge documents produced and actively presented to MCPAs not directly involved in project activities, or presented in other relevant fora | 0 | Knowledge documents or presentations produced on at least five project good practices or lessons (e.g. development of monitoring schemes, development of management plans, establishment of multi-stakeholder partnerships, hazardous spill response preparedness, invasive species management plans, sustainable tourism for MCPAs, etc. | Proposed additional indicator: The project is undertaking multiple pilot or demonstration activities in divergent regions of the country. The catalytic value of such activities is that the experience is shared with others who can draw on the lessons and good practices to adapt and strengthen management in their own circumstances. |

- Annex 4: Theory-of-Change Review of Outcomes to Impacts Framework

- A project’s logical intervention approach, or theory of change, is the expression of the strategy chosen to achieve the objective. Based on the objective and strategy chosen, the project inputs and activities are designed to produce the outputs and outcomes required to eventually achieve impact level results. This “logic chain” defines the outcomes-impacts pathway. Figure 8 below indicates a generic project logic chain pathway.

Figure 8 Generic Theory of Change for Outcome-Impacts Pathways

- Articulating and understanding a project’s theory of change can be a valuable step toward later assessment of the potential results. This is particularly true for a project such as the Russia MCPAs project, which has an extended theory of change – that is, there are multiple steps in the process between the outcomes produced by the project and the intended results. To assess the likelihood of impact, the GEF Evaluation Office applies the Review of Outcomes to Impacts (ROtI) methodology.

- The ROtI methodology acknowledges and recognizes that time is required following completion of most GEF projects for sustained execution of the conditions processes leading to eventual changes in threats to or improved management of environmental resources. This is particularly true in the case of biodiversity conservation projects, as species populations and ecosystems take time to respond to project interventions to the extent that changes in environmental status can be identified and documented.

- For the Russia MCPAs project it was expected that during the project lifetime there would be progress toward improving the management effectiveness of Russia’s network of MCPAs, toward the overall required intermediate state of ongoing effective management of these protected areas. Effective management over time corresponds by reduced threats and improved environmental status.

- The Review of Outcomes to Impacts methodology is an approach designed to assist in identifying potential and likely project impacts from a theory-based perspective. The key elements of this analysis are the assumptions, impact drivers, and intermediate states (defined in Table 8 below) required to move from outcomes to impacts.

Table 8 Theory of Change Definitions

| - Theory of Change Terms | - Definition |
| --- | --- |
| - Assumptions | - The significant factors that, if present, are expected to contribute to the ultimate realization of project impacts, but that are largely beyond the power of the project to influence or address |
| - Impact Drivers | - The significant factors that, if present, are expected to contribute to the ultimate realization of project impacts, and that are within the ability of the project to influence |
| - Intermediate States | - The transitional conditions and processes between the project’s outcomes and impacts that must be achieved in order to deliver the intended impacts |

- A draft Russia MCPAs project theory of change is summarized in Table 9, below. This proposed theory of change builds on the different outcomes and outputs, but does not directly correspond to the project design, as different strategies are represented within the different project outcomes. The below theory of change includes elements based on the actual project activities, as well as some identified gaps that are not included in the project design. It is not necessary for a single project to attempt to address all necessary strategies, but it should be recognized that without required improvements in all necessary aspects of the system the project alone may not be able to achieve the overall objective. In this sense the project may represent necessary, but not necessarily sufficient, contributions to conserving Russia’s marine and coastal biodiversity.

Table 9 Russia MCPAs Project Theory of Change

OUTCOMES TO IMPACTS OVER TIME

| - Strategy | - Outcomes | - Assumptions and Impact Drivers | - Intermediate States | - Impact |
| --- | --- | --- | --- | --- |
| - Institutional and systemic capacity strengthening of the MCPA system at the central level | - National institutions and MCPA management authorities have the necessary tools and knowledge to effective manage the system of MCPAs | - ID: Tools and information to effectively manage the system of MCPAs - ID: Supportive national institutional frameworks - A: Adequate institutional and systemic capacity is a key barrier to effective management of the system of MCPAs - A: Human resources are adequate for implementing effective management approaches - A: Financial resources are adequate for implementing effective management approaches | - Ongoing effective management of a representative system of MCPAs | - Reduced threats to and improved status of Russia’s globally significant marine and coastal biodiversity |
| - Expansion of MCPA geographic coverage | - A representative extract of marine and coastal biodiversity is covered by protected status | - ID: Implementation of biodiversity conservation management measures in areas under protected status - A: Adequate data to identify under-represented ecosystems or species - A: Political will to increase coverage of protected resources | - A representative system of MCPAs is maintained, with necessary ecosystem and species coverage to sustain marine and coastal biodiversity |  |
| - Institutional and individual capacity strengthening at the site level | - PA management authorities have the knowledge and technical capacity for effective management | - ID: Adequate technical capacity to perform necessary management functions - ID: Adequate individual ability to perform necessary management functions - A: Available human resources are able to uptake knowledge and training at the level required to perform required management duties | - Ongoing effective management of a representative system of MCPAs |  |
| - Demonstration and pilot activities to address specific threats (hazardous spills, invasive species) and opportunities (tourism) related to MCPAs | - Increased knowledge and experience to address key threats and leverage opportunities for MCPAs | - ID: Implementation of pilot and demonstration (successful or not) - ID: Dissemination of experiences from pilot and demonstration activities - A: Implementation of pilot and demonstration activities provides necessary insights on lessons and good practices for improved management | - Ongoing effective management of a representative system of MCPAs |  |
| - Knowledge sharing and dissemination | - Increased knowledge about effective MCPA management among MCPAs | - ID: Identification and documentation of knowledge about effective management of MCPAs - ID: Dissemination of knowledge - A: Uptake and use of knowledge by other parties - A: Knowledge about good practices and lessons in one MCPA is relevant to other MCPAs | - Ongoing effective management of a representative system of MCPAs |  |
| - Establishment of partnerships to support key MCPA functional requirements, such as enforcement, environmental monitoring, and knowledge sharing | - Improved management beyond what individual MCPA administrations would be able to support on their own | - ID: Availability of resources from partners - ID: Effective communication among partners - A: Potential for synergies among partners catalyzes establishment of partnership, or legislative/policy mandates compel establishment of partnerships - A: Adequate financial and other resources to implement partnership agreements | - Ongoing effective management of a representative system of MCPAs |  |
| - PROJECT GAP: Revision and updating of legal and policy framework to provide necessary mandates and division of responsibilities among government institutions and other stakeholders | - Outcome: No significant legislative or policy barriers to effective management of marine and coastal resources | - ID: Adequate data and knowledge to support the development of appropriate legislation and policy for effective management of coastal and marine resources - A: Political will to adopt legislation and policies supporting effective management of coastal and marine resources | - Ongoing effective management of coastal and marine resources, supporting a well-managed system of MCPAs |  |
| - PROJECT GAP: Multi-stakeholder coordination mechanisms operational for effective management of marine and coastal resources | - Outcome: Roles and responsibilities are agreed between all relevant stakeholders | - ID: Effective management actions undertaken by all stakeholders - ID: Adequate knowledge to make appropriate decisions supporting sustainable management of resources - A: Stakeholders interests are complementary for the sustainable management of national coastal and marine resources - A: Legislation and policy supports coordinated multi-stakeholder approaches | - Ongoing effective management of coastal and marine resources, supporting a well-managed system of MCPAs |  |
|  | - Outcome: Knowledge is effectively shared among stakeholders |  |  |  |
|  | - Outcome: Stakeholders share technical and human resources to support shared management goals |  |  |  |
|  | - Outcome: A nationally unified vision of sustainable management of coastal and marine resources |  |  |  |

- Annex 5. List of Persons Met and Interviewed During Mid-term Evaluation Mission

- Ms. Irina Bredneva, Programme Officer, Environment Unit, UNDP Russia Project Support Office

- Ms. Natalya Olofinskaya, Head of Environment Unit, UNDP Russia Project Support Office

- Mr. Dmitry Kryukov, Project Manager, Russia MCPAs Project

- Mr. Vasily Spiridonov, Chief Technical Advisor, Russia MCPAs Project

- Mr. Sergei F. Titov, State Research Institute for Fisheries, Leningrad Region

- Mr. Alexander Glinkin, Head of Russian Federal Border Guard Security Service to St. Petersburg and Leningrad Region

- Dr. Rustam A. Sagitov, Director, Baltic Fund for Nature

- Mr. Sergey P. Rezvy, Project Coordinator, Baltic Fund for Nature

- Mr. Andrei Andrianov, Director of Far Eastern Marine Reserve, Far Eastern Branch of Russian Academy of Sciences

- Mr. Valentin F. Kovalev, General Director, Baltic Salvage and Towing Company

- Mr. Dmitriy S. Smirnov, General Director, Baltic Salvage and Towing Company

- Mr. Alexey V. Orekhov, Deputy Director, Makarov Training Centre, Admiral Makarov State Maritime Academy

- Mr. Fedor N. Stulov, Head of PA Division, Leningrad Oblast Committee for Natural Resources and Environment

- Mr. Alexander N. Siluyanov, Programme Officer, Leningrad Regional Protected Areas Directorate

- Ms. Nadezhda M. Alexeeva, Programme Officer, PA Division, Leningrad Oblast Committee for Natural Resources and Environment

- Mr. Vsevolod B. Stepanitskiy, National Project Director, Deputy Director of the State Policy and Regulation for Environment Protection and Safety, Russian Federal Ministry of Natural Resources and Environment

- Mr. Dmitry Lisitsyn, Sakhalin Environment Watch

- Mr. Alexander Tsetlin, Professor Moscow State University, Director of the White Sea Biological Station

- Ms. Anastasia V. Kuznetsova, Director, Komandorsky Nature Reserve

- Ms. Natalia I. Troitskaya, Independent Expert, Protected Area Management Effectiveness

- Mr. Johan Robinson, Regional Technical Advisor, UNDP Bratislava Regional Centre

Mr. Jeff Griffin, former independent project development consultant

- Annex 6. Evaluation Field Visit Schedule

- Monday, July 30, Saint Petersburg

- Morning: Meeting with multiple stakeholders of the Leningrad Region at the offices of the Baltic Fund for Nature

- Afternoon: Meeting at the offices of the Baltic Salvage and Towing Company

- Tuesday, July 31, Saint Petersburg

- Morning: Meeting at the offices of the Leningrad Regional Protected Areas Directorate

- Wednesday, August 1st, Moscow

- Afternoon: Meeting with the PIU staff at UNDP offices, and phone interviews with project stakeholders in Russian Far East

- Thursday, August 2nd, Moscow

- Morning: Phone interviews with Director of White Sea Biological Station, and Director of Commander Islands Reserve

- Afternoon: Meeting with National Project Director and project experts

- Friday, August 3rd, Moscow

- Evaluation Wrap-up with Project Team and UNDP

- Annex 7. Interview Guide

Overview: The questions under each topic area are intended to assist in focusing discussion to ensure consistent topic coverage and to structure data collection, and are not intended as verbatim questions to be posed to interviewees. When using the interview guide, the interviewer should be sure to target questions at a level appropriate to the interviewee. The interview guide is one of multiple tools for gathering evaluative evidence, to complement evidence collected through document reviews and other data collection methods; in other words, the interview guide does not cover all evaluative questions relevant to the evaluation.

Key

Bold = GEF Evaluation Criteria

Italic = GEF Operational Principles

- PLANNING / PRE-IMPLEMENTATION

- Relevance

  - Did the project’s objectives fit within the priorities of the local government and local communities?

  - Did the project’s objectives fit within national priorities?

  - Did the project’s objectives fit GEF strategic priorities?

  - Did the project’s objectives support implementation of the relevant multi-lateral environmental agreement?

- Incremental cost

- Did the project create environmental benefits that would not have otherwise taken place?

- Does the project area represent an example of a globally significant environmental resource?

- Country-drivenness / Participation

- How did the project concept originate?

- How did the project stakeholders contribute to the project development?

- Do local and national government stakeholders support the objectives of the project?

- Do the local communities support the objectives of the project?

- Are the project objectives in conflict with any national level policies?

- Monitoring and Evaluation Plan / Design (M&E)

- Were monitoring and reporting roles clearly defined?

- Was there either an environmental or socio-economic baseline of data collected before the project began?

- MANAGEMENT / OVERSIGHT

- Project management

- What were the implementation arrangements?

- Was the management effective?

- Were workplans prepared as required to achieve the anticipated outputs on the required timeframes?

- Did the project develop and leverage the necessary and appropriate partnerships with direct and tangential stakeholders?

- Were there any particular challenges with the management process?

- If there was a steering or oversight body, did it meet as planned and provide the anticipated input and support to project management?

- Were risks adequately assessed during implementation?

- Did assumptions made during project design hold true?

- Were assessed risks adequately dealt with?

- Was the level of communication and support from the implementing agency adequate and appropriate?

- Flexibility

- Did the project have to undertake any adaptive management measures based on feedback received from the M&E process?

- Were there other ways in which the project demonstrated flexibility?

- Were there any challenges faced in this area?

- Efficiency (cost-effectiveness)

- Was the project cost-effective?

- Were expenditures in line with international standards and norms?

- Was the project implementation delayed?

- If so, did that affect cost-effectiveness?

- What was the contribution of cash and in-kind co-financing to project implementation?

- To what extent did the project leverage additional resources?

- Financial Management

- Was the project financing (from the GEF and other partners) at the level foreseen in the project document?

- Where there any problems with disbursements between implementing and executing agencies?

- Were financial audits conducted with the regularity and rigor required by the implementing agency?

- Was financial reporting regularly completed at the required standards and level of detail?

- Did the project face any particular financial challenges such as unforeseen tax liabilities, management costs, or currency devaluation?

- Co-financing (catalytic role)

- Was the in-kind co-financing received at the level anticipated in the project document?

- Was the cash co-financing received at the level anticipated in the project document?

- Did the project receive any additional unanticipated cash support after approval?

- Did the project receive any additional unanticipated in-kind support after approval?

- Monitoring and Evaluation (M&E)

- Project implementation M&E

- Was the M&E plan adequate and implemented sufficiently to allow the project to recognize and address challenges?

- Were any unplanned M&E measures undertaken to meet unforeseen shortcomings?

- Was there a mid-term evaluation?

- How were project reporting and monitoring tools used to support adaptive management?

- Environmental and socio-economic monitoring

- Did the project implement a monitoring system, or leverage a system already in place, for environmental monitoring?

- What are the environmental or socio-economic monitoring mechanisms?

- Have any community-based monitoring mechanisms been used?

- Is there a long-term M&E component to track environmental changes?

- If so, what provisions have been made to ensure this is carried out?

- Full disclosure

- Did the project meet this requirement?

- Did the project face any challenges in this area?

- ACTIVITIES / IMPLEMENTATION

- Effectiveness

- How have the stated project objectives been met?

- To what extent have the project objectives been met?

- What were the key factors that contributed to project success or underachievement?

- Can positive key factors be replicated in other situations, and could negative key factors have been anticipated?

- Stakeholder involvement and public awareness (participation)

- What were the achievements in this area?

- What were the challenges in this area?

- How did stakeholder involvement and public awareness contribute to the achievement of project objectives?

- RESULTS

- Outputs

- Did the project achieve the planned outputs?

- Did the outputs contribute to the project outcomes and objectives?

- Outcomes

- Were the anticipated outcomes achieved?

- Were the outcomes relevant to the planned project impacts?

- Impacts

- Was there a logical flow of inputs and activities to outputs, from outputs to outcomes, and then to impacts?

- Did the project achieve its anticipated/planned impacts?

- Why or why not?

- If impacts were achieved, were they at a scale sufficient to be considered Global Environmental Benefits?

- If impacts or Global Environmental Benefits have not yet been achieved, are the conditions (enabling environment) in place so that they are likely to eventually be achieved?

- Replication strategy, and documented replication or scaling-up (catalytic role)

- Did the project have a replication plan?

- Was the replication plan “passive” or “active”?

- Is there evidence that replication or scaling-up occurred within the country?

- Did replication or scaling-up occur in other countries?

- LESSONS LEARNED

  - What were the key lessons learned in each project stage?

  - In retrospect, would the project participants have done anything differently?

- SUSTAINABILITY

- Financial

- To what extent are the project results dependent on continued financial support?

- What is the likelihood that any required financial resources will be available to sustain the project results once the GEF assistance ends?

- Was the project successful in identifying and leveraging co-financing?

- What are the key financial risks to sustainability?

- Socio-Political

- To what extent are the project results dependent on socio-political factors?

- What is the likelihood that the level of stakeholder ownership will allow for the project results to be sustained?

- Is there sufficient public/stakeholder awareness in support of the long-term objectives of the project?

- What are the key socio-political risks to sustainability?

- Institutions and Governance

- To what extent are the project results dependent on issues relating to institutional frameworks and governance?

- What is the likelihood that institutional and technical achievements, legal frameworks, policies and governance structures and processes will allow for the project results to be sustained?

- Are the required systems for accountability and transparency and the required technical know-how in place?

- What are the key institutional and governance risks to sustainability?

- Ecological

- Are there any environmental risks that can undermine the future flow of project impacts and Global Environmental Benefits?

- Annex 8. Evaluation Matrix

| Evaluation Questions | Indicators | Sources | Data Collection Method |
| --- | --- | --- | --- |
| Evaluation Criteria: Relevance |  |  |  |
| - Does the Russia MCPAs project’s objective fit within the priorities of the local government and local communities? | - Level of coherence between project objective and stated priorities of local stakeholders | - Local government stakeholders - Local community stakeholders - Local private sector stakeholders - Relevant regional and local planning documents | - Local level field visit interviews - Desk review |
| - Does the Russia MCPAs project’s objective fit within national priorities? | - Level of coherence between project objective and national policy priorities and strategies, as stated in official documents | - National policy documents, such as National Biodiversity Strategy and Action Plan, National Capacity Self-Assessment, etc. - National legislation such as National Forest Code, etc. | - Desk review - National level interviews |
| - Did the Russia MCPAs project concept originate from local or national stakeholders, and/or were relevant stakeholders sufficiently involved in project development? | - Level of involvement of local and national stakeholders in project origination and development as indicated by number of planning meetings held, representation of stakeholders in planning meetings, and level of incorporation of stakeholder feedback in project planning | - Project staff - Local and national stakeholders - Project documents | - Field visit interviews - Desk review |
| - Does the Russia MCPAs project’s objective fit GEF strategic priorities and operational principles? | - Level of coherence between project objective and GEF strategic priorities - Level of conformity with GEF operational principles | - GEF strategic priority documents for period when project was approved - Current GEF strategic priority documents - GEF operational principles | - Desk review - Field visit interviews |
| - Does the Russia MCPAs project’s objective support implementation of the Convention on Biological Diversity? Other MEAs? | - Linkages between project objective and elements of the CBD, such as key articles and programs of work | - CBD website - National Biodiversity Strategy and Action Plan | - Desk review |
| Evaluation Criteria: Efficiency |  |  |  |
| - Is the Russia MCPAs project cost-effective? | - Quality and comprehensiveness of financial management procedures - Project management costs share of total budget | - Project documents - Project staff | - Desk review - Interviews with project staff |
| - Are expenditures in line with international standards and norms for development projects? | - Cost of project inputs and outputs relative to norms and standards for donor projects in the country or region | - Project documents (budget files, audit, etc.) - Project staff - National stakeholders | - Desk review - Interviews with project staff |
| - Are management and implementation arrangements efficient in delivering the outputs necessary to achieve outcomes? | - Appropriateness of structure of management arrangements - Extent of necessary partnership arrangements - Level of participation of relevant stakeholders | - Project documents - Project staff - Local, regional and national stakeholders | - Desk review - Interviews with project staff - Field visit interviews |
| - Was the Russia MCPAs project implementation delayed? If so, did that affect cost-effectiveness? | - Project milestones in time - Required project adaptive management measures related to delays | - Project documents - Project staff | - Desk review - Interviews with project staff |
| - What is the contribution of cash and in-kind co-financing to project implementation? | - Level of cash and in-kind co-financing relative to expected level | - Project documents - Project staff | - Desk review - Interviews with project staff |
| - To what extent is the Russia MCPAs project leveraging additional resources? | - Amount of resources leveraged relative to project budget | - Project documents - Project staff | - Desk review - Interviews with project staff |
| Evaluation Criteria: Effectiveness |  |  |  |
| - Is the project objective likely to be met? To what extent and in what timeframe? | - Level of progress toward project indicator targets relative to expected level at current point of implementation | - Project documents - Project staff - Project stakeholders | - Field visit interviews - Desk review |
| - What are the key factors contributing to project success or underachievement? | - Level of documentation of and preparation for project risks, assumptions and impact drivers | - Project documents - Project staff - Project stakeholders | - Field visit interviews - Desk review |
| - What are the key risks and priorities for the remainder of the implementation period? | - Presence, assessment of, and preparation for expected risks, assumptions and impact drivers | - Project documents - Project staff - Project stakeholders | - Field visit interviews - Desk review |
| - Is adaptive management being applied to ensure effectiveness? | - Identified modifications to project plans, as necessary in response to changing assumptions or conditions | - Project documents - Project staff - Project stakeholders | - Field visit interviews - Desk review |
| - Is monitoring and evaluation used to ensure effective decision-making? | - Quality of M&E plan in terms of meeting minimum standards, conforming to best practices, and adequate budgeting - Consistency of implementation of M&E compared to plan, quality of M&E products - Use of M&E products in project management and implementation decision-making | - Project documents - Project staff - Project stakeholders | - Field visit interviews - Desk review |
| Evaluation Criteria: Results |  |  |  |
| - Are the planned outputs being produced? Are they likely to contribute to the expected project outcomes and objective? | - Level of project implementation progress relative to expected level at current stage of implementation - Existence of logical linkages between project outputs and outcomes/impacts | - Project documents - Project staff - Project stakeholders | - Field visit interviews - Desk review |
| - Are the anticipated outcomes likely to be achieved? Are the outcomes likely to contribute to the achievement of the project objective? | - Existence of logical linkages between project outcomes and impacts | - Project documents - Project staff - Project stakeholders | - Field visit interviews - Desk review |
| - Are the key assumptions and impact drivers relevant to the achievement of Global Environmental Benefits likely to be met? | - Actions undertaken to address key assumptions and target impact drivers | - Project documents - Project staff - Project stakeholders | - Field visit interviews - Desk review |
| - Are impact level results likely to be achieved? Are the likely to be at the scale sufficient to be considered Global Environmental Benefits? | - Environmental indicators | - Project documents - Project staff - Project stakeholders | - Field visit interviews - Desk review |
| Evaluation Criteria: Sustainability |  |  |  |
| - To what extent are project results likely to be dependent on continued financial support? What is the likelihood that any required financial resources will be available to sustain the project results once the GEF assistance ends? | - Financial requirements for maintenance of project benefits - Level of expected financial resources available to support maintenance of project benefits - Potential for additional financial resources to support maintenance of project benefits | - Project documents - Project staff - Project stakeholders | - Field visit interviews - Desk review |
| - Do relevant stakeholders have or are likely to achieve an adequate level of “ownership” of results, to have the interest in ensuring that project benefits are maintained? | - Level of initiative and engagement of relevant stakeholders in project activities and results | - Project documents - Project staff - Project stakeholders | - Field visit interviews - Desk review |
| - Do relevant stakeholders have the necessary technical capacity to ensure that project benefits are maintained? | - Level of technical capacity of relevant stakeholders relative to level required to sustain project benefits | - Project documents - Project staff - Project stakeholders | - Field visit interviews - Desk review |
| - To what extent are the project results dependent on socio-political factors? | - Existence of socio-political risks to project benefits | - Project documents - Project staff - Project stakeholders | - Field visit interviews - Desk review |
| - To what extent are the project results dependent on issues relating to institutional frameworks and governance? | - Existence of institutional and governance risks to project benefits | - Project documents - Project staff - Project stakeholders | - Field visit interviews - Desk review |
| - Are there any environmental risks that can undermine the future flow of project impacts and Global Environmental Benefits? | - Existence of environmental risks to project benefits | - Project documents - Project staff - Project stakeholders | - Field visit interviews - Desk review |

The data in this section is drawn directly from the corresponding section of the project document, which includes all relevant information. For additional details on the development context, see the project document.

The details for these sites (i.e. name, international status, region, hectares) are included in Table 1 of the project document.

Map source: Project MCPAs gap analysis.

Map source: Google Maps.

Sources: 1.A. N/A; 1.B. N/S; 2.A. GEF project cycle business standards; 2.B. GEF online database; 3.A. GEF project cycle business standards; 3.B. GEF online database; 4.A. As per requirements of GEF project cycle business standards (18 months less 1 month for time for CEO Endorsement review); 4.B. Submission date on CEO Endorsement Request; 5.A GEF project cycle business standards; 5.B. Date of final review sheet / GEF online database; 6.A. GEF project cycle business standards; 6.B. GEF online database; 7.A. CEO Endorsement Request milestones; 7.B. 2012 PIR; 8.A. CEO Endorsement Request milestones; 8.B. Date of inception workshop; 9.A. 2011 PIR; 9.B. Start of mid-term evaluation data collection; 10.A. CEO Endorsement Request milestones, and 2012 PIR ; 10.B. N/A; 11.A. Within the three months prior to completion; 11.B. N/A; 12.A. As per standard UNDP operational procedures; 12.B. N/A.

See http://www.cbd.int/decision/cop/?id=12268 for the full text of the decision, including the Aichi Targets.

For the focal area strategic approach for GEF-4, see GEF Council document GEF/C.31/1, “Focal Area Strategic and Strategic Programming for GEF-4,” July 16, 2007.

For the focal area strategic priorities for GEF-5, see GEF Council document GEF/R.5/31, “GEF-5 Programming Document,” May 3, 2010.

Source: Project Document Workplan.

Source: Project Budget Revision and CDR documents.

Sources: Planned amounts from project document workplan; actual amounts from project financial records.

This plan approves the creation over eight years of 11 new nature reserves, 20 national parks, and three refuges.

Source: Project documentation from the project website.

Source: Project Document.

At the time of project development the Federal Agency of Fisheries operated as an independent government entity, separate from any ministries. In 2012 the FAF was integrated under the Ministry of Agriculture. As outlined elsewhere in this report, according to project stakeholders, this institutional restructuring put a temporary hold on any constructive activity related to interagency coordination (with the Ministry of Environment and Natural Resources), as responsibilities and reporting lines in the new institutional structure were to be determined.

Seafoodsource.com, “Concern surfaces over Russia’s Fishery Agency,” June 6, 2012.

The GEF Evaluation Office defines SMART indicators as those that are: Specific, Measureable, Achievable and Attributable, Relevant and Realistic, Timebound, Timely, Trackable and Targeted. See http://www.gefcountrysupport.org/report_detail.cfm?projectId=232 for additional information.

The project logical framework analysis is oddly included immediately following the project document’s incremental cost analysis, on pg. 80 of the project document.

See pg. 16 of the project inception report.

RBM Support documents are available at http://www.undp.org/eo/methodologies.htm

The UNDP POPP is currently only available on UNDP’s intranet.  However UNDP can provide the necessary section on roles and responsibility from http://content.undp.org/go/userguide/

Source: GEF Evaluation Review of Outcomes to Impacts Handbook.