Evaluation of UNDP’s support to mobile courts arrangements in post-conflict situations

INCEPTION REPORT

Table of contents

Introduction ……………………………………………………………………………………………………………	p. 2

SECTION 1 : GENERAL FRAMEWORK

1. Purpose and objectives …………………………………………………………………………………….	p. 2

2. Scope …………………………………………………………………………………………………………………	p. 3

3  Target audiences ……………………………………………………………………………………………….	p. 4

4. Limitations …………………………………………………………………………………………………………	p. 4

5. Status of the evaluation process  ………………………………………………………………………	p. 5

SECTION 2: EVALUATION METHODOLOGY

1. Overview of the methodological approach ………………………………………………………	p. 6

2. Evaluation matrix ……………………………………………………………………………………………… 	p. 7

3. Evaluation activities ………………………………………………………………………………………….	p. 7

► Phase 1 (desk review, inception report, mission to New York) ……………………………	p. 7

► Phase 2 (Field visits) …………………………………………………………………………………………	p. 8

► Phase 3 (Final report drafting and dissemination) …………………………………………….	p. 9

5. Work plan and time schedule ……………………………………………………………………………	p. 9

6. Expected Deliverables ………………………………………………………………………………………	p. 9

7. Structure of the final report ………………………………………………………………………………	p. 9

ANNEXES …………………………………………………………………………………………………………………	p.12

1. Evaluation Matrix

2. Framework for good practices in mobile court interventions

3. Statistics required from mobile courts case records

4. Sample questionnaire for Mobile Court users

5. Query on Mobile Court interventions for UNDP knowledge networks

6. TOR

17 December 2102 (Revised version)

By Monica Rispo (BCPR consultant)

Introduction

The present document represents the inception report developed for the “Evaluation of UNDP support to mobile courts arrangements in post-conflict situations”, commissioned by UNDP/BCPR to one international consultant (Ms Monica Rispo), as per TOR attached in Annex 6.

The inception report provides an update on the set of activities conducted in the preliminary phase of the evaluation (15 November -15 December), and contains some methodological and practical suggestions for the next phases of the evaluation.

SECTION 1 : GENERAL FRAMEWORK

§ 1.1. Purpose and objectives

As mentioned in the TOR, the purpose of the evaluation is to “assess the progress, achievements and lessons learned, including challenges faced with regard to the support to mobile courts’ systems in the framework of UNDP RoL programmes”.

The evaluation focuses on both accountability and learning purposes and more specifically aims to achieve the following objectives:

- Building knowledge for better and eventually wider application of mobile courts interventions across BCPR’s Global ROL programme.

The desk review and preliminary discussions with UNDP staff, have pointed out that comprehensive studies specifically dedicated to mobile courts have not yet been conducted, neither at national nor international level.

The only exception is the DRC experience with the “gender mobile courts”, which has produced a number of interesting reports which are however specific to the DRC context and limit their focus on SBGV. Occasionally general reports on the justice sector have dedicated a few paragraphs to mobile courts, but without offering a detailed analysis of the topic.

There is therefore a need for more specific analysis of the functioning and impact of mobile courts interventions and how UNDP supports these initiatives in order to identify best practices, lessons learned and eventually promote a debate on some key issues. Such needs are confirmed by UNDP staff in county offices, who would welcome further guidance in supporting mobile courts.

At BCPR level there might be a need to have a clearer overview of the different mobile courts models that have been implemented in the different country offices, eventually with the objective to identify some common basic standards for future mobile courts interventions across the Global ROL programme.

To this end the evaluation will, whenever possible, take a comparative approach in order to explore how different political and institutional contexts (e.g. status of conflict, level of judicial reform) and legal systems (common law/civil law/ pluralistic) might hinder or facilitate mobile courts arrangements.

- Promoting joint accountability of UNDP and the national government, respectively in supporting  and implementing mobile courts interventions.

The accountability component of the evaluation aims to ascertain results of mobile courts interventions in the light of the 5 criteria of relevance, effectiveness, efficiency, sustainability and impact.

The accountability component will have a different focus for UNDP and the national partner in accordance to their respective roles with regards to mobile courts.

For UNDP the main focus will be on its programmatic accountability for providing adequate policy and technical support to governments in an approach aimed at strengthening national capacity and promoting national ownership and gender equality. In particular the evaluation will assess the impact UNDP’s support to facilitate mobile courts sessions, promote capacity development to bring justice closer to conflict-affected population and facilitate the (re-)establishment of a justice system and thus grant access to justice for vulnerable groups in a sustainable manner.

The accountability of the national government derives from its primary responsibility for the provision of qualitative and accessible justice and the fact that mobile courts are in principle implemented autonomously by the Judiciary (or military judiciary, as in DRC) in the light of the principle of administrative independence of the judiciary. In this regards the evaluation will focus on aspects that include assessing if mobile courts are implemented in respect of fair trial rights and ensuring that the intervention does not generate practices affecting the independence of the judges.

In order to facilitate the assessment of these two, strictly interlinked, forms of accountability and promote national ownership of the evaluation results, the field visits will be structured as joint UNDP/Judiciary missions, as illustrated in § 1.4.

In the light of the principle of complementarity in prosecuting crimes under the jurisdiction of the ICC and BCPR’s engagement to support transitional justice processes, the BCPR Global ROL Programme recognizes that “the process of facing past atrocities should be initiated and driven locally to have a long term impact” and promotes activities that strengthen national capacities in prosecuting Rome Statute crimes.

Accordingly, in specific transitional justice settings (e.g DRC, Sierra Leone) the evaluation will assess the impact of UNDP supported mobile courts on transitional justice processes, with a focus on the opportunity for conflict-affected population to seek redress for human rights violations and the capacity of mobile courts to address impunity and eventually offer reparations for human rights abuses.

As per TOR, specific objectives of the evaluation are:

- To assess the extent to which mobile courts interventions met their intended objectives and contributed to the achievement of outcomes/outputs;

- To systematically review the implementation modalities, capacity development efforts, knowledge management and considerations for access to justice for vulnerable groups including women and in particular survivors of sexual violence;

- To determine the extent to which support to mobile courts has contributed to increasing access to or decentralizing provision of justice services; and restoration of state-authority in conflict-affected areas

- The extent to which mobile courts contribute towards developing and strengthening long term national capacities and strategies for increased A2J;

- Assess the exit strategy for UNDP’s support to the mobile courts given their temporary nature;

- To present key findings, generate lessons learned, and provide a set of clear and forward-looking recommendations for enhancing the quality of future engagement of UNDP and its partners in supporting mobile courts’ arrangements.

The above mentioned evaluation objectives will be further defined by the evaluation criteria, which represent the standards against which the initiatives will be assessed, and are illustrated in § 2.2 (evaluation matrix)

§ 1.2. Scope

The evaluation will cover 3 mobile courts interventions implemented within the framework of broader ROL programmes/projects funded under the BCPR Global ROL programme, as indicated in the table below. A number of additional country offices will be identified to participate in the desk study.

The period covered by the evaluation will vary according to the different status of project implementation in each country, but the reference document for the evaluation will be the latest results framework.

| country | title of UNDP projet or programme under which mobile courts are implemented | project/ programme duration | Year when UNDP started to support mobile courts |
| --- | --- | --- | --- |
| Central Africa | Stratégie de Développement des Capacités pour le Renforcement de l’Etat de droit ? | 2012 – 2016 | ? |
| Sierra Leone | Improving Access to Justice Programme | 2010 – 2011 | ? |
| Somalia | Governance and rule of law programme | 2012-2015 | 2008 |
| Additional countries will be identified for the desk study and will include Guinea Bissau, DRC and Timor Leste |  |  |  |

§ 1.3 Target audiences

The identification of the target audiences for the evaluation is interlinked with 2 main purposes of the evaluation:

- The accountability component responds to the information needs of the following users:

- BCPR and UNDP staff in the 5 Country Offices;

- national partner ( Judiciary or Ministry of Justice) and/or implementing partner (NGO,CSO);

- eventual UN partners (e.g. DPKO) in case of joint interventions;

- eventual donors contributing to the initiative.

The report will be used to improve programme delivery, make informed and evidence-based decisions and plan strategically the activities to be implemented.

- The lesson learned component has a broader audience: in addition to the above-mentioned users, the evaluation could also be of interest for the following users:

- development partners (INGOs, donors, international organisations….)

- UN sister agencies,

- academic and research institutions,

- national institutions as Police, Prison system, Bar Associations…

The report will be used to inform programming, generate knowledge, promote guidance and disseminate BCPR’s achievements in supporting mobile courts across its Global ROL programme.

Considered the different information needs of the 2 above mentioned target audiences, it will be suggested to disseminate the evaluation in the form of two different documents, one for each target group (see § 7)

§ 1.4. Limitations

As illustrated below, the desk review phase allowed to point out some limitations that might hamper the presentation of clear and accurate evaluation findings (particularly with regards to the accountability component). In order to address these issues in a timely manner, some suggestions are proposed to identify appropriate solutions.

1) Lack of detailed resource-frameworks specifically related to mobile courts interventions

The lack of detailed resource-frameworks is inherent to the way mobile courts interventions are planned within UNDP programmes.

In the 5 pilot countries, mobile courts are a small component of broader ROL programmes. Consequently specific resource-frameworks for mobile courts interventions are not available: such interventions are only mentioned as an “activity result” of the general ROL project result framework.

This means that indicators, targets, baseline and activities for mobile courts interventions are not presented with sufficient details to allow a consistent evaluation.  For example in the Sierra Leone Project Document, mobile courts fall under activity 1.1.5 ,which is framed as “Funding for Magistrates or  mobile courts in under or un-serviced areas” and is measured with the indicator “Number of new magistrates/mobile courts assigned to under or un-serviced areas”.

Conversely the same limitation applies to monitoring tools: there is a lack of detailed progress reports to illustrate specifically the achievements for the mobile courts intervention.  For the same reasons it is likely that specific quantitative data (statistics) will be difficult to collect.

A proposed solution would be to develop an additional reference document for the evaluation, which would identify the standard activities and respective indicators required for mobile courts intervention on the basis of the international standard for fair trial and the practices developed by UNDP country offices. The “framework for good practices in mobile court interventions” described in § 4.1.2. has been designed, inter alia, for this purpose.

2) Issues related to the administrative independence of the Judiciary

In the light of the principle of administrative independence of the Judiciary, mobile courts interventions are generally implemented autonomously by the national partner (Judiciary/MOJ) with involvement of UNDP limited to the planning/monitoring phase and mainly focused on providing financial support. In some contexts there is therefore a risk that the evaluation exercise might be perceived by the local judicial authorities as an interference in their administrative independence.

A proposed solution would be to structure the evaluation as a joint UNDP/Judiciary initiative and ensure that a representative of the MOJ/judiciary takes part in the evaluation mission in loco. This approach would enhance the national ownership and promote the capacity building of national partners, in addition to facilitating access to court records and statistics required for the evaluation. In addition, the presence of a representative of the Judiciary would facilitate and give a stronger legitimacy to the assessment of accountability aspects more directly linked with the national government.

The joint approach would be proposed only those countries where the institutional context would be conducive to these kinds of arrangements (e.g. Sierra Leone).

3) Limited availability of court statistics

Discussions with Sierra Leone and CAR Country Offices have pointed out that the national case management system is weak, particularly with regards to mobile courts sessions.

To fill this gap and adequately prepare the field missions, the country offices will give a special attention to ensure that judicial authorities will make available the quantitative data related to each mobile court session.

Annex 3 (mobile courts case records) will give country offices an indication of the basic statistical information that would be needed in order to provide an overview of mobile courts workload in the evaluation report.

§ 1.5. Status of the evaluation process

In the process leading up to the present inception report, the consultant conducted the following activities:

- Desk and literature review to collect the basic documentation that will inform the evaluation (general and country specific material described in § 2.4.1). The online research is concluded, but the documentation from the Country Offices is not yet complete. The material is available on a shared Dropbox folder, as mentioned in § 2.4.1.

- 3 phone interviews: UNDP Sierra Leone (Mr James Nunan and Ms Rakel Larsen); BCPR (Ms Isabelle Tschan); UNDP Central African Republic (Mr Appolinaire Fotso)

- emails exchanges with BCPR staff (how to conduct the desk review phase, introductions to UNDP staff in the country offices, suggestions for evaluation tools…) and UNDP field staff to collect feedback on the Evaluation Matrix.

Given some constraints related to the end of the year festivities and some recent security concerns in some of the evaluated countries (DRC and Guinea Bissau), it was agreed that the field missions and the mission to New York would only take place starting from mid January 2013.

The country offices that will participate in the evaluation process are still being defined. It is likely that missions will take place in Sierra Leone, Central Africa and Somalia; other countries (e.g. DRC, Guinea Bissau) will participate by contributing to the desk study.

SECTION 2: EVALUATION METHODOLOGY

§ 2.1. Overview of the methodological approach

The evaluation process will be conducted in the light of the guiding principles and quality standards defined for UNDP evaluations

Special attention will be given to ensure the involvement of all stakeholders and partners in order to ensure local ownership and enhance the credibility and transparency of the evaluation exercise. Mixed methods of collecting data will be used, in particular to triangulate evidence from once source (e.g. interviews) with other source (e.g monitoring reports). The evaluation will reflect UNDP’s commitment to human rights based approaches and gender equality.

The proposed methodology consists of a mixture of qualitative and quantitative research methods. Quantitative methods will be used to elicit information such as the functioning of mobile courts, the effectiveness and efficiency of UNDP’s support.

The following quantitative data will be collected:

- Court records analysis. (Country Offices will ensure that the minimum required information will be available, if possible prior to the field missions. See Annex 3)

- Performance indicators derived from UNDP planning and monitoring documentation

- Query and Survey for UNDP Country Offices participating in the desk study (see Annex 5)

Qualitative methods will offer greater insight into the process, the perceptions and the impact of the interventions.

The following qualitative data will be collected:

- Focus groups with beneficiaries

- Eventual “mobile court user perception survey” (on the model of the initiative currently piloted in Sierra Leone. See Annex 4)

- Individual semi-structured interviews

- Case study methods, to develop informative stories that are notable either for their frequency or their uniqueness;

- Documentary evidence (UNDP monitoring reports, past evaluations, research papers, donor reports…)

- If possible, on-site observation of a mobile court in action

Quantitative data will be analyzed by cleaning the surveys and creating tables, graphs that illustrate the findings.

Qualitative data will be analyzed by summarizing the information collected during interviews or focus groups.

§ 2.2. Evaluation matrix

The Evaluation Matrix is based on the evaluation questions listed in the TOR and specifies further each key question by articulating sub-questions, data sources and data collection methods.

An additional criterion (impact) was added in order to assess the impact of mobile courts interventions on the population and the judicial system. In some cases, the questions contained in the matrix have been modified from those in the TOR, in order to reflect additional information or eliminate duplicative questions.

The Evaluation Matrix is presented in Annex 1.

2.3. Evaluation activities

The evaluation will be conducted in a three phase approach and will consist of the key steps described below.

Phase 1 (desk review, inception report, mission to New York)

► Desk and literature review

The desk and literature review consists in collecting and analyzing existing documentation related to mobile courts interventions, available both online and at UNDP offices.

Specific UNDP documents to be reviewed include: UNDP Project Documents with related resource frameworks and Annual Workplans; UNDP strategic documents (e.g. UNDAF, CPAP), UNDP monitoring tools (e.g. quarterly and annual reports, databases…); past UNDP evaluations of ROL projects in the relevant Country offices; UNDP financial documents (e.g. Atlas reports, budgets); eventual partnership agreements with other organizations or judicial authorities to support mobile courts.

General documents to be reviewed include: samples of legislation on mobile courts, research studies, articles, court statistics, justice sector strategies, national development plans and poverty reduction strategies, material from other development partners, justice sector assessments in relevant Country Offices….

To facilitate the collection of relevant documentation a folder was set up on Dropbox and was shared among focal points for the mobile courts evaluation in CO/HQ and the consultant.

The objective is that each team member will be able to easily upload files related to the mobile courts evaluation and at the same time be updated about the material available in other Country Offices.

► Desk study on additional Country Offices

In addition to the 3 evaluated Country Offices, other UNDP Country Offices are running mobile courts under the BCPR Global ROL programme, (e.g. Chad) or under the UNDP BDP Global A2J programme (e.g. Djibouti, Pakistan).

In order to complement the information from the 3 evaluated CO and promote a greater participation in terms of lessons learned at the global level, additional information will be collected on how such additional Country Offices support mobile courts.

As illustrated in Annex 5, the data collection method will be a survey (via SurveyMonkey) and a query posted on UNDP’s  communities of practice (e.g. CRPnet and Huritalk).

► Framework for good practices in mobile courts interventions

Considered the lack of a specific resource framework for mobile courts interventions, it is suggested to develop some solid indicators combined with indicative activities/good practices in order to guide the evaluation.

To this end a “Framework for good practices in mobile courts interventions” has been designed on the basis of the international standards for fair trial and the practices developed by UNDP country offices. A draft is annexed to the present report and will be discussed and validated by UNDP staff in Country Offices and BCPR (Annex 2)

The added value of this tool would also be to make available a framework for eventual future guidelines or basic standards for mobile courts interventions across UNDP programmes.

►Inception Report (present document)

A draft inception report was submitted on the 7th of December 2012. Feedback from BCPR was consolidated and a revised version was submitted on 17th of December.

Due to time constraints it has been agreed that further feedback from BCPR will be given in January during the first mission to New York.

► First mission to New York

The mission to New York will take place in the second week of January and will have the following objectives:

- Collect feedback on the inception report and validate the document.

- Discuss and eventually adopt the Checklist for mobile court interventions.

- Organize the field missions.

- Meet key BCPR staff in ROL Unit

- Meet key development partners supporting mobile courts interventions (American Bar Association, OSJI, UN sister agencies, DPKO, World Bank…)

Phase 2 (Field visits)

The programme for each field mission will be defined jointly with the Country Offices.

The missions will mainly consist in conducting interviews, focus groups with relevant stakeholders and key informants, arranged by UNDP CO in advance. Preliminary finding will be presented by the evaluator to UNDP office representatives at the end of each field visit.

Key informants to be met during field missions will be identified jointly with the CO.

It will be ensured that the following actors are included: national judicial authorities (judges, prosecutors, ministry of justice), UNDP staff, donors, UN system, INGOs, human rights CSO, representatives of the police and prison system, lawyers and Bar Association, traditional authorities; beneficiaries/users of mobile courts.

Phase 3 (Final report drafting and dissemination)

The last phase of the evaluation will include the submission of a draft report to BCPR and the CO in order to collect comments and feedback.

A final report will be submitted after consolidating the feedback received and will be presented to the Evaluation Reference Group during a second mission to New York, that could take place in May 2013.

A strategy to disseminate the evaluation results internally and externally will be identified with BCPR during the first mission to New York.

§ 5. Work-plan

| ACTIVITY | TIMESCHEDULE 2012 / 2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Nov |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |
| Literature & desk review |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Desk study on additional CO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Submission Inception Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| First mission to NY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Field mission to Sierra Leone |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Field mission to CAR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Field mission to Somalia |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Draft evaluation report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Second mission to NY (TBD) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

§ 6. Expected Deliverables

The following deliverables will be submitted to BCPR:

- Inception report (present document);

- Country-specific evaluation report.  (for internal dissemination  and with focus on accountability);

- Thematic evaluation report.  (for external dissemination and with focus on learning );

- Presentation to illustrate the evaluation findings in New York to the Evaluation Reference Group.

In addition to these deliverables, the consultant will provide BCPR with regular progress updates throughout the course of the assignment.

§ 7. Structure of the final report

Considered the two folded purpose of the evaluation (accountability and learning) and that the respective target audiences have different information needs, it is suggested to structure the evaluation in 2 separate documents, as follows:

- A country-specific evaluation report. This document will focus on the accountability component of the evaluation by applying the 5 evaluation criteria for each country office, which will allow to present recommendations specific to each context.

The report will be disseminated only among UNDP/BCPR staff, Judiciary and other implementing partners and eventual donors.

- Thematic evaluation report. This document will focus on learning component and will present the findings and best practices in a comparative approach by following the outline of the “framework for good practices in mobile court interventions”

The report will be widely disseminated to generate knowledge, promote guidance and disseminate BCPR’s achievements in supporting mobile courts across its Global ROL programme.

The table of content for the country-specific report is outlined below:

- Executive summary

- Part 1: Context and Methodology

- Part 2: Evaluation findings presented by criteria: relevance, effectiveness, efficiency, sustainability, impact

- Part 3: Conclusions, Recommendations, Lessons Learned

- Annexes

Part 2 and 3 will be repeated for each evaluated country.

The table of content for the thematic report is outlined below:

- Executive summary

- Part 1: Context and Methodology

- Part 2: Best practices, lessons learned, case studies presented by mobile court phases (as identified in the Framework for good practices): i) planning and assessment ii) before mobile courts sessions ii) during mobile courts sessions iii) after mobile courts sessions iv) monitoring activities v) crosscutting issues

- Part 3: Conclusions, Recommendations

- Annexes

§ 8. Annexes

- Annex 1: Evaluation Matrix

- Annex 2: Framework for good practices in mobile courts interventions

- Annex 3: Mobile courts case records

- Annex 4: Sample questionnaire for Mobile Court users

- Annex 5: Query on Mobile Court interventions for UNDP knowledge networks

- Annex 6 : TOR

ANNEX 1: Evaluation Matrix

| Evaluation of UNDP support to mobile courts arrangements in post-conflict situations EVALUATION MATRIX |  |  |  |  |
| --- | --- | --- | --- | --- |
| 1. RELEVANCE Relevance concerns the extent to which a development initiative and its intended outputs or outcomes are consistent with national and local policies and priorities and the needs of intended beneficiaries. Relevance also considers the extent to which the initiative is responsive to UNDP corporate plan and human development priorities of empowerment and gender equality issues. Relevance concerns the congruency between the perception of what is needed as envisioned by the initiative planners and the reality of what is needed from the perspective of intended beneficiaries. It also incorporates the concept of responsiveness—that is, the extent to which UNDP was able to respond to changing and emerging development priorities and needs in a responsive manner. An essential sub-category of relevance is the criteria of appropriateness, which concerns the cultural acceptance as well as feasibility of the activities or method of delivery of a development initiative. |  |  |  |  |
| questions & sub-questions |  | data sources |  | data collection method |
| Q.1.1. To what extent do the mobile courts’ support interventions respond to the priorities outlined in national strategies? - What is the legal basis for implementing mobile courts? - Are a national strategy and a national budget available for MC? - Is there an MOU between UNDP and the Judiciary/MOJ to support mobile courts? - Has the Judiciary implemented MC without the support of international donors? If so, what were the results? - How does the country legal system (civil/common law, pluralistic..) influence mobile courts arrangements? |  | - National legislation - National Justice Sector strategies - MOU between UNDP and Judiciary |  | - Online research - Request CO/HQ - Interviews: judicial authorities.. |
| Q.1.2. How well do programming and implementation modalities match the needs of the population and national partners? - What influenced UNDP’s decisions on where, how and to what extent to engage in supporting mobile courts? Was the decision discussed with relevant stakeholders? - Was a needs assessment conducted before launching the mobile court intervention? Was the Judiciary involved? - Which are the most vulnerable groups in the country? Are they targeted by mobile courts interventions? - To what extent were issues related to the restorative v. retributive conception of justice in remote areas taken into consideration? |  | - Needs assessment or baseline analysis reports (by UNDP, Judiciary or other actors) - research reports - reported opinions from key informants |  | - Online research - Request CO/HQ - Interviews: MOJ, judicial authorities, UNDP staff.. |
| Q.1.3. What was the relevance of mobile courts assistance for other priorities of UNDP Rule of Law programmes and the cross-cutting areas of gender equality, capacity building and national ownership? - Were synergies established between MC and other components of UNDP Rule of law programmes? (Legal aid, Paralegalism, Policing, …), If so, what was the added value of a mobile court component? - How was gender mainstreamed across the mobile court intervention? - Have mobile courts interventions utilized existing local capacities of rights holders and duty bearers to achieve their results? How were their capacities strengthened? |  | - UNDP documents: CPAP/UNDP project documents /BCPR field visits reports/ BCPR integrated projects/ evaluation reports… - reported opinions from key informants |  | - Request CO/HQ - Interviews: UNDP staff.. |
| 2. EFFECTIVENESS Effectiveness is a measure of the extent to which the initiative’s intended results (outputs or outcomes) have been achieved or the extent to which progress toward outputs or outcomes has been achieved5 |  |  |  |  |
| questions & sub-questions | data sources |  | data collection method |  |
| Q.2.1: What model of MC emerges from the CO practice? - What is the composition of the MC? How are the judges/prosecutors/lawyers selected to participate? - What is the jurisdiction of mobile courts with regards to subject matters, litigants and geographical coverage? - What is the average distance between the permanent tribunal and the mobile court? - How long does the mobile court session last and how often does it visit the same area per year? - To what extent have interventions addressed transitional justice process and impunity of international crimes? | - Databases /statistics - Map of the judiciary - project document - Reported opinions from key informants |  | - Interviews: UNDP staff, Ministry of Justice… - Request CO/HQ |  |
| Q.2.2: What results (quantitative and qualitative) were achieved in each phase of mobile court interventions? phase 1: before mobile court sessions - What support did UNDP ensure to the logistical aspects of mobile courts (transport, courtroom, accommodation, office and legal material for judges on circuit)? - Were the population and local authorities informed about the arrival of the mobile court in an appropriate and timely manner? - Were investigations in criminal cases effectively conducted? Were eventual pretrial detention issues addressed? Were linkages between Prosecutors and Police promoted? - Were notifications of procedural acts issued and communicated in a timely manner? - Were specific trainings for mobile court staff organized? (knowledge of the local culture and traditional law practices, gender/child rights…) phase 2: during mobile court sessions - How many and what cases received free legal aid from a lawyer? Was the Bar Association involved? - How many witnesses appeared before the mobile court? Which measures were in place to protect witnesses and victims, and in particular SGBV victims? Is there a “travel cost reimbursement program” to assist witnesses and victims to appear in court? - Were hearings translated into local languages? - How many people participated in the public hearings? Were they assisted in better understanding the hearings? - Were mechanisms in place to ensure the security of mobile court staff? - Were the proceedings adequately recorded? Are there higher rates of adjournment for MC proceedings? phase 3: after mobile court sessions - How many judgments were enforced (criminal/civil)? - Were mechanisms in place to enforce prison sentences in the absence of local prison facilities? - What is the rate of appeal of MC decisions? - Are there mechanisms in place to ensure the communication of MC decisions to the rest of the justice chain to ensure decision enforcement and information sharing? - Were parties assisted to collect eventual financial compensation that they were awarded? - If alternative sanctions to imprisonment were applied (community services), was a follow up ensured? | - Project performance indicators - Databases/ statistics - UNDP quarterly and annual reports - MC reports - Judiciary reports - Research studies - Reported opinions from key informants |  | - Request CO/HQ - Interviews: Ministry of Justice, judicial authorities, police, prison staff, traditional authorities, lawyers, other implementing partners, UNDP staff.. - Focus group with beneficiaries |  |
| Q.2.3: Were planning and monitoring procedures appropriate to achieve results and ensure accountability? - Is a clear results framework with SMART indicators, targets and risks analysis available? - What monitoring tools are available? Are court statistics available? - Are national partners involved in monitoring activities? - Is there a system in place for trial observation? - Is feedback from mobile court users collected to assess needs and adjust services accordingly? - How is the quality of mobile court judgments assessed? - Are landmark cases identified and disseminated? | - Project document and results framework - UNDP quarterly and annual reports - evaluation reports of broader ROL projects - reports drafted by MC staff |  | - Interviews: UNDP staff, Ministry of Justice… |  |
| Q.2.4: What were the reasons for achievement and non-achievement of results and the factors contributing or hindering their achievement? - How can UNDP build upon or replicate the achievements? - How can the shortcomings be overcome? - What are the lessons learned? - Were there any unanticipated events, opportunities or constraints? - What could be done differently in the future? - What were the unintended results (positive/negative) | - Reported opinions from key informants - UNDP quarterly and annual reports - Judiciary reports |  | - Interviews: UNDP staff, Ministry of Justice, Mobile court staff… |  |
| 3. EFFICIENCY Efficiency measures how economically resources or inputs (such as funds, expertise and time) are converted to results. An initiative is efficient when it uses resources appropriately and economically to produce the desired outputs. (…)It is also important to assess how the partnership strategy has influenced the efficiency of UNDP initiatives through cost-sharing measures and complementary activities. 5 |  |  |  |  |
| questions & sub-questions | data sources |  | data collection method |  |
| Q.3.1: Has the MC intervention been implemented within its cost estimates and is it cost-effective? - Were sufficient resources allocated for mobile courts’ support interventions? Is the national government contributing to the budget for MC? - Are the expenditures for MC proportionate to the number of cases and broader indicators as the number of participants in public hearings? - What are the costs per trial? would it be cheaper to build court rooms and provide staff in remote areas? - Are perdiems for judges and MC staff in line with local market? | - Resource frameworks, budgets, AWP, - Reported opinions from key informants - UNDP quarterly and annual reports - MOJ reports |  | - Interviews: UNDP staff, Ministry of Justice.. - Request CO/HQ |  |
| Q.3.2: Has UNDP promoted a partnership strategy at the global, regional and national level to implement MC interventions? If so, was it effective and appropriate? - What was the nature and added value of these partnerships? - Did such partnerships promote an integrated approach aiming at addressing complementary aspects of mobile courts interventions (legal awareness for the population; support to police and prisons; linkages with traditional justice …) - Were UNDP’s comparative advantages perceived/ interpreted and were these reflected in the division of responsibilities? - If the Judiciary received specific support for mobile courts interventions from several donors, were the initiatives efficiently coordinated? | - UNDAF - partnership agreements/MOU - Reported opinions from key informants |  | - Interviews: UNDP staff, Ministry of Justice, Protection cluster, UN agencies and INGOs, civil society organisations, universities… - Request CO/HQ |  |
| Q.3.3: What effect did UNDP technical assistance and management arrangements have on the quality of mobile courts interventions in terms of programming, delivery and monitoring for results? - Were the project management structure and the administrative modalities appropriate and effective? - Was the support from UNDP staff effective and timely? | - Project document and monitoring reports - Reported opinions from key informants |  | - Interviews: UNDP staff, Ministry of Justice, Mobile court staff… |  |
| Q.3.4: Did mobile courts interventions focus on the set of activities that were expected to produce significant results? - Are all the planned activities implemented? Should additional activities be planned? - Are mobile courts ensuring the implementation of the international standards of fair trial? Would some of the fair trial rights need more attention? | - Project document - Reported opinions from key informants - international standards on fair trial |  | - Interviews: UNDP staff, Ministry of Justice, other implementing partners… |  |
| 4. SUSTAINABILITY Sustainability measures the extent to which benefits of initiatives continue after external development assistance has come to an end. Assessing sustainability involves evaluating the extent to which relevant social, economic, political, institutional and other conditions are present and, based on that assessment, making projections about the national capacity to maintain, manage and ensure the development results in the future. 5 |  |  |  |  |
| questions & sub-questions | data sources |  | data collection method |  |
| Q.4.1: To what extent were sustainability considerations taken into account in the design and implementation of interventions? - Were exit strategies for mobile courts interventions appropriately defined and implemented? - What steps were taken to ensure that the effects of the intervention would continue beyond UNDP’s support? - Has the development of partnerships contributed to the sustainability of results? | - Project document - annual reports - Reported opinions from key informants |  | - Interviews: UNDP staff, Ministry of Justice, Judiciary other implementing partners… |  |
| Q.4.2: How were different stakeholders engaged designing, monitoring and implementing mobile courts interventions? - Has UNDP promoted and facilitated the coordination among local justice and security actors (Police, Prisons, Traditional justice, local authorities…) ? - Have linkages been established between mobile courts and ADR mechanisms? (for example to establish mandatory court annexed mediations). | - Project document - annual reports - Reported opinions from key informants |  | - Interviews: UNDP staff, Judiciary, Ministry of Justice, Police, Prison staff, traditional authorities, local authorities… |  |
| 5. IMPACT Impact measures changes in human development and people’s well-being that are brought about by development initiatives, directly or indirectly, intended or unintended. 5 |  |  |  |  |
| questions & sub-questions | data sources |  | data collection method |  |
| Q.5.1: What changes did mobile courts interventions bring for rights holders in terms of making justice more accessible to them? - Have MC interventions promoted a better confidence in the justice system? Is there a perception that impunity is being addressed? - Are vulnerable groups in remote areas more aware of their rights and do they have a better understanding of the formal justice system? - Do MC provide an alternative to traditional justice? | Reported opinions from key informants |  | Focus groups with beneficiaries and interviews with their lawyers / Eventual users perception survey |  |
| Q.5.2: What changes did mobile courts interventions bring for duty bearers in terms of making them more effective in responding to justice need of conflict affected populations in remote/underserved areas? - What is the impact of MCs on ordinary courts? (in terms of case backlog, promoting case management systems, costs) - What was the impact on ordinary courts of assigning judges and other judicial staff to mobile courts? - Have MC interventions led to the re-establishment of the justice system eventually in conflict-affected areas? - Have MC interventions promoted closer coordination among the different actors in the justice chain? - Have judicial authorities acquired additional skills and knowledge in terms of managing a MC intervention? | Reported opinions from key informants |  | Interviews: Judicial authorities and Ministry of Justice, Police, Prison staff, traditional authorities |  |

ANNEX 2: Framework for good practices in mobile courts interventions

| GOOD PRACTICES for MOBILE COURT interventions |  |
| --- | --- |
| good practice statement | indicator |
| 1. Planning and assessment |  |
| The context is assessed and needs are identified | Clear baseline available; eventual study conducted |
| A MC model (composition, jurisdiction, geographical coverage…) is identified |  |
| UNDP has established a partnership with the Judiciary to support MC interventions | MOU signed |
| UNDP has promoted partnerships with other donors/development partners to ensure that all components of MC interventions are covered (e.g. awareness raising for population / training for police) | Joint project drafted / agreements to define areas and modalities of interventions in place |
| Linkages among national justice/security actors / traditional authorities are established | Meetings, discussion fora, protocols for coordinated interventions in place |
| Linkages with other UNDP projects in the same area are established | Linkages identified in Project Documents |
| The MC intervention is adequately designed and roles are clearly defined | Specific results framework (SMART indicators) available |
| 2. Before MC sessions (logistics & investigations) |  |
| The arrival of MC is communicated to the population and relevant authorities in an adequate and timely manner | Information sessions for the population & meetings with local authorities organised |
| The logistical aspects of MC interventions are ensured in a timely and efficient manner | MC staff transported and accommodated. Legal resources, courtroom and office equipment available. |
| Investigations are conducted by the police and eventual pre-trial detentions issued are identified | Statistics on investigations/pre-trial detention available |
| Court clerks deliver notifications in a timely manner | ≠ of notifications of procedural acts delivered |
| MC staff participate in trainings to better serve in remote areas (knowledge of local culture and traditional law practices, gender/child rights ….) | ≠ of trainings for MC staff conducted |
| 3. During MC sessions |  |
| MC deliver final decision in respect of fair trial rights | Statistics on MC caseload available |
| Witnesses and victims are financially assisted to appear in court | ≠ of victims/witnesses financially assisted to appear in court |
| Interpreters translate the hearings into local languages | An interpreter is part of the MC staff |
| A legal aid policy for MC is available and free legal aid is provided | ≠ of legal aid cases taken up by lawyers |
| Witnesses and victims (in particular SGBV survivors) are protected | ≠ and type of special measure in place to protect witnesses and victims |
| The population participates and understands MC hearings | ≠ of participants to public hearings; mechanisms in place to facilitate understanding of MC procedures (e.g. community paralegals) |
| The physical security of MC staff is ensured | ≠ of police officers/private guards protecting MC staff |
| 4. After MC sessions (enforcement & reparations) |  |
| MC judgements are enforced | ≠ of MC judgements enforced (civil/criminal) |
| Detainees are transferred to the nearest prison | ≠ detainees transferred to nearest prisons |
| Alternative sentences to imprisonment are followed up | A mechanism is in place to ensure the follow up |
| Victims are assisted to obtain reparations/ compensation | ≠ of victims who have obtained reparations |
| Opportunities to appeal MC decisions are available and accessible | ≠ of appeals |
| 5. Monitoring activities |  |
| MC activities are regularly monitored | ≠ of monitoring tools developed (database, reports…) |
| A trial observation system is in place | ≠ of trial observed & outcome analysed |
| MC users have the opportunity to express their views on how the intervention is delivered | Surveys conducted |
| The quality of MC judgements is regularly assessed | Outcome of periodical analysis of judgements |
| Court records are regularly registered | Court management systems in place |
| 6. Crosscutting issues |  |
| Safeguards are applied in cases involving children | In camera hearings, best interest of the child…. |
| Mechanisms to control corruption are in place |  |
| Gender is mainstreamed across the MC activities | ≠ female staff in MC; indicators disaggregated by gender |

ANNEX 3: Statistics required from Mobile Courts case records

(in black: minimum required information; in blue: desired information)

| 1. Statistics related to cases |  |
| --- | --- |
| Type of case | ≠ of criminal cases ≠ of civil cases |
| Nature of case | ≠ of criminal cases disaggregated by type of crime ≠ of civil cases disaggregated by type of dispute |
| Result of the case | ≠ of final decisions ≠ of cases adjourned ≠ of cases abandoned/settled outside court |
| Outcome of the case (if court disposed of the case) | ≠ of convictions (and details of sentence) ≠ of acquittals ≠ of dismissals ≠ of settlements of civil cases (and details of conditions) |
| Case summary | Description of the facts |
| 2. Statistics related to parties |  |
| Position in case | ≠ of plaintiffs/complainants (disaggregated by age/sex) ≠ defendant/accused (disaggregated by age/sex) ≠ civil party (if applicable) ≠ of witnesses who testified ≠ of people who participated in the public hearings |
| Occupation/Status | Specify occupation or position in the community |
| Legal representation | ≠ of parties represented by a lawyer in court |
| Fees paid to court by parties | Amount of fees paid to court per case |

ANNEX 4: Sample questionnaire for Mobile Court users

Evaluation of MCs from a user perspective:

Questions for survey/interview with parties to MC cases

| Age: …….. Sex: F ¦ M Marital status: Single ¦ Married ¦ Divorced ¦ Widowed ¦ Other Employment: No ¦ Full time ¦ Self-employed ¦ Student ¦ Retired ¦ Other Position in case: claimant ¦defendant ¦ witness¦ victim/survivor ¦ (civil party) Type of case: civil ¦ criminal Nature of case: SGBV ¦ land ¦divorce ¦inheritance ¦theft ¦physical assault ¦other …………………….. |  |
| --- | --- |
| 1 | When did you start the procedure? …………………(month, year) When did you receive an outcome? ………………. (month, year) □ I did not receive an outcome yet. Are you satisfied with the overall time of the MC procedure? (from start to final decision) □ Yes □ No □ Don’t know |
| 2 | Was the process of opening your case before the MC easy and straightforward? □ Yes □ No □ Don’t know Who did you first contact to file your case before the MC (authorities, NGOs, etc..) ? ……………………… |
| 3 | Were you informed in a timely and adequate manner about your case throughout the procedure? □ Yes □ No □ Don’t know Have you received general information about the MC (role, objectives…)? □ Yes. Please specify by whom …………………………………………………………………………………. □ No □ Don’t know |
| 4 | Were you granted legal aid from a lawyer or a paralegal? □ Yes. Please specify if: □ lawyer or □ paralegal □ No □ Don’t know Was the assistance of the lawyer/paralegal useful? □ Yes □ No □ Don’t know |
| 5 | Was the final decision fair? □ Yes □ No □ Don’t know Was the final decision in accordance with the traditions and culture of your community? □ Yes □ No □ Don’t know Was the final decision explained and eventually translated to you? □ Yes □ No □ Don’t know |
| 6 | Was your problem solved by the decision of the MC? □ Yes □ No □ Don’t know |
| 7 | Were traditional authorities involved in the procedure? □ Yes □ No □ Don’t know If so, did they facilitate the procedure? □ Yes □ No □ Don’t know |
| 8 | How much money did you eventually spend for the procedure (court fees, lawyer etc)? Please specify: …………………………. Did you have to pay bribes? □ Yes □ No □ Don’t know |
| 9 | Did your participation in the MC trial have an impact on your social relationships? □ Yes, a positive impact □ Yes, a negative impact □ No □ Don’t know Did your participation in the MC trial affect your personal security at any stage of the procedure? □ Yes. Please specify ………………………………………………………. □ No □ Don’t know |
| 10 | For eventual future disputes would you refer your case to the MC again? □ Yes □ No. Please specify why: ……………………………………………………………………….. □ Don’t know If not, to whom would you refer the case? …..………………………………………….. |
| 11 | Would you have any suggestions to improve the MC service? |

ANNEX 5: Query on Mobile Court interventions for UNDP knowledge networks (CPRnet and Governance)

For the purpose of the present query, Mobile Courts are defined as “formal courts that conduct proceedings in locations other than their home courts, usually in remote areas where no justice services are available”. Trials are organized closer to the population by transferring the required justice actors (judge, prosecutor, court clerk, police officer…) to remote locations with the main objective to facilitate access to justice, in particularly for vulnerable groups who would not otherwise have the possibility to bring their cases before a formal court, often located miles away from their villages.

The growing number of UNDP Country Offices that are supporting Mobile Courts interventions and the lack of comprehensive studies specifically dedicated to this topic, suggest that further analysis of the functioning and impact of mobile courts interventions and how UNDP supports these initiatives would be needed.

Within this framework, BCPR is conducting an evaluation to assess results, identify good practices and lessons learned in supporting mobile courts interventions across UNDP RoL programmes in post-conflict settings. The evaluation includes a field visit of an international consultant in 3 selected Country Offices (Sierra Leone, Central Africa and Somalia) and a desk study on additional Country Offices that are supporting Mobile Courts.

If your Country Office is supporting or planning to support Mobile Courts and you would be available to participate in the Desk Study, we would appreciate if you could share your experience by using one (or both) of the following data collection methods:

- Send a general reply to the query, addressing the following aspects: 1) brief presentation of the Mobile Court that your CO is supporting 2) Which are the greatest challenges in supporting Mobile Courts? 3) Which are the main lessons learned? 4) Are there any replicable “good practices” developed within the Mobile Court intervention that you are supporting?

- Fill out the brief survey on Mobile Court interventions available on SurveyMonkey. (Add link)

In addition to the above-mentioned contributions we would very much welcome any documentation related to Mobile Courts that have been developed by your Country Office. (National legislation specific on Mobile Courts, UNDP reports and general research papers related to Mobile Courts , MOU between UNDP and the national judiciary, landmark cases disposed by Mobile Courts…). The objective is to better understand the Mobile Court intervention that you are supporting, and also to gauge the potential for further use or adaptation throughout UNDP.

The query and survey results will be used to inform the learning component of the evaluation report, which aims at consolidating good practices, lessons learned and identify common methodological approaches across UNDP ROL programmes..

General replies to the query and relevant documentation should be sent to Mr Serdar Bayriyev (serdar.bayriyev@undp.org)

The deadline to submit your contribution is ……..

Thank you in advance for taking the time to share your experience.

| SURVEY ON MOBILE COURTS INTERVENTIONS ACROSS UNDP COUNTRY OFFICES |  |
| --- | --- |
| 1 | General information Country office: ………………………… UNDP focal point for Mobile Courts: ……………………………….. (name) ………………………………………….. (email address) National implementing partner: □ Ministry of Justice □ Judiciary □ the Country Office started supporting Mobile Courts in …………………………. (year, month). Please indicate the 2013 programme/project under which Mobile Courts are supported: …………………………………………… □ the Country Office is planning to support Mobile Courts in the future |
| 2 | What is the legal basis for implementing Mobile Courts in your country of intervention? □ specific national legislation on Mobile Courts □ criminal/civil procedure code □ other. Please specify ………………………………………………………………………………………………………………………………………. Is there a national strategy that makes direct reference to Mobile Courts (e.g. Justice sector strategic plan…)? □ Yes . Please specify ………………………………………………………………………………………………………………………………………. □ No |
| 3 | What is the jurisdiction of mobile courts with regards to subject matters? □ Civil □ Criminal □ Only specific matters (e.g. transitional justice, SGBV, civil registration….). Please specify: ……………………………… What is the jurisdiction of mobile courts with regards to litigants? □ All persons living in the area of intervention of the MC □ Only persons belonging to specific groups ( e.g. indigents, SGBV survivors…). Please specify ………………………. What type of Mobile Court do you support: □ Civil □ Military What is the composition of the Mobile Court team? 1. The court: □ Judge □ Prosecutor □ Registrar □ court clerk 2. Legal aid: □ Lawyer, □ Paralegal 3. Security: □ Police □ private guards 4. Other (e.g. mediator, driver...) : …………………………………………………………………………………………………………………… How many cases are referred to the Mobile Court system per year? ………………………………………………………………. How many final decisions are issued by the Mobile Court system per year? …………………………………………………… |
| 4 | If available, could you specify the annual budget that the UNDP CO will allocate to Mobile Courts in 2013? ……………….. Will the national government contribute to the budget? □ Yes. If possible, please specify for what amount: ……………………………………………………………………………… □ No |
| 5 | Are Mobile Courts implemented in cooperation with other international partners? □ Yes. Please specify: □ INGO □ UN agency □ DPKO □ other □ No |
| 6 | Which are the greatest challenges in supporting Mobile Courts? |
| 7 | Could you please share a “good practice” developed within the Mobile Court intervention that you are supporting? (we are particularly interested in initiatives that offer practical solutions to common challenges to Mobile Courts interventions, e.g. improving participation of the local population, enhancing monitoring mechanisms, strengthening investigation procedures, promoting coordination with police/traditional authorities….) |
| 8 | Which are the main lessons learned? What would you do differently in the future? |

ANNEX 6: Terms of Reference

| ### EVALUATION CONSULTANT: SUPPORT TO MOBILE COURT ARRANGEMENTS IN POST-CONFLICT SITUATIONS |  |
| --- | --- |
| Location : | Home-based with travel to selected countries |
| Application Deadline : | 22-Aug-12 |
| Type of Contract : | Individual Contract |
| Post Level : | International Consultant |
| Languages Required : | English |
| Starting Date : (date when the selected candidate is expected to start) | 24-Sep-2012 |
| Expected Duration of Assignment : | 50 working days spread over 3 months |
| Refer a Friend Apply Now |  |
| ### Background |  |
| Background and Context: UNDP provides rule of law support to over 100 countries, including 37 crisis-affected and fragile situations. Particular attention is paid to 21 priority countries supported through the Global Rule of Law Programme (2008-2011) which provides support to the implementation justice and security programmes in those countries. Recently, UNDP launched the second phase (2012-2015) of the Global Programme (GP) “Strengthening the rule of law in crisis-affected and fragile situations”. The rule of law programmes in countries supported by the GP are focusing on enhancing access to justice and improved justice and security service delivery, tackling impunity for sexual and gender-based violence (SGBV), strengthening security sector governance, and supporting transitional justice processes. This assistance responds to urgent needs for justice and security, and simultaneously lays the foundations for recovery and long term development. The GP also provides support to joint programmes with DPKO, UNHCR, UNODC and UN Women which continue to deepen impact on the ground where it is most needed, particularly in UN mission areas such as Haiti, Liberia, South Sudan and Timor-Leste. Barriers to access justice exist in many societies but they are especially pervasive in conflict and post-conflict contexts. The administration of justice system might have been disrupted and the population displaced as a consequence of the conflict. Consequently, for many people the formal justice system is too far away. UNDP programmes assist people to find their through the justice system by supporting legal aid and by bringing justice closer to conflict-affected populations through the establishment of mobile courts. Support to mobile courts is provided in the aftermath of conflict to provide population to access to justice and seek redress for their grievances. In some countries, support to mobile courts arrangements is provided in the context of the UN’s support to transitional justice processes. UNDP provided support to mobile courts in several countries, including in DRC, Central African Republic, Sierra Leone, Guinea-Bissau and Timor-Leste. In some countries this support was provided jointly with DPKO, OHCHR as well as civil society organizations. UNDP is now conducting a study to evaluate the impact of the UNDP support provided to mobile court arrangements in countries supported by the Global Programme. Evaluation Purpose: The purpose of this evaluation is to assess the progress, achievements and lessons learned, including challenges faced with regard to the support to mobile courts’ systems in the framework of UNDP RoL programmes. The evaluation will review the impact of such activities and interventions at the sub-regional and national levels within the wider context of the technical and financial assistance provided by UNDP and its partners on RoL. In particular, the evaluation will measure the impact UNDP’s support regarding the facilitation of mobile court sessions and capacity development to bring justice closer to conflict-affected population and increase the access to justice of vulnerable people. In a second step, the evaluation will assess the impact of UNDP supported mobile court system for conflict-affected population to seek redress for their grievances and the consequences this might have for transitional justice and peace building and reconciliation efforts. The findings and conclusions of this evaluation will help generate lessons learned and identify best practices and strategies for UNDP’s (and its partners) RoL programming in post conflict-countries and for the continued engagement of UNDP in supporting development of mobile court’s systems and their relevance for legal/justice programming post conflict transitions.. Evaluation Scope and Objectives: The evaluation will review components of RoL programmes supporting mobile courts project components in DRC, Central African Republic, Sierra Leone, Guinea-Bissau and Timor-Leste in terms of their contributions to improve access to justice for the conflict-affected population and increased justice service delivery at the sub-regional and national level in these countries. The evaluation will specifically focus on the mobile courts’ impact for the population i) to seek redress for their grievances and ii) the consequences this might have for transitional justice processes and iii) for peace building and reconciliation efforts. The evaluation will examine the relevance of mobile courts project components in the context of their contributions towards improved justice service delivery and capacity development of justice institutions. Specific objectives of the evaluation are as follows: - To assess the extent to which the mobile courts’ assistance interventions met their intended objectives and contributed to the achievement of outcomes/outputs; - To systematically review the implementation modalities, capacity development efforts, knowledge management and considerations for access to justice for vulnerable groups including women and in particular survivors of sexual violence; - To determine the extent to which support to mobile courts has contributed to increasing access to or decentralizing provision of justice services; - The extent to which mobile courts contribute towards developing and strengthening long term national capacities and strategies; - Assess the exit strategy for UNDP’s support to the mobile courts given their temporary nature; - To present key findings, generate lessons learned, and provide a set of clear and forward-looking recommendations for enhancing the quality of future engagement of UNDP and its partners in supporting mobile courts’ arrangements. The evaluation will assess programme performance against the following criteria: relevance, effectiveness, efficiency and sustainability. Evaluation Questions: This paragraph includes suggested evaluation questions against the 5 criteria listed below: Relevance - To what extent do the mobile courts’ support interventions respond to the priorities outlined in the national development strategies (or similar plans/strategies)? - How does the support for mobile courts’ arrangements contribute to the longer term development results in terms of approaches, capacities, policies and strategies in the Rule of Law/Justice provision. - How well do programming mix and support modalities match the needs of the population and national partners? - What has influenced UNDP’s decisions on where, how and to what extent to engage in supporting decentralization of justice service delivery through mobile courts assistance? - What was the relevance of and possible synergies between mobile courts assistance and other priorities identified in the Rule of Law programmes and the cross-cutting areas of gender equality, capacity building and national ownership? Efficiency - Has the programme been implemented within its deadline and cost estimates? - Did the mobile courts’ support interventions focus on the set of activities that were expected to produce significant results? - Was there any identified synergy between UNDP-funded mobile courts’ support interventions and other similar interventions that contributed to reducing costs while supporting results? - Has there been over expenditure or under expenditure of the mobile courts’ support interventions? - Were there any unanticipated events, opportunities or constraints? Were the anticipated policy influences achieved? Did alternative ones emerge? What could be done differently in the future? - Were there sufficient resources allocated towards achievement of the objectives of the mobile courts’ support interventions? How well did the mobile courts’ support interventions leverage non-core resources towards achievement of results? - What effect did management and institutional arrangements have on the quality of mobile courts’ support interventions in terms of programming, delivery and monitoring for results? What measures were taken to assure the quality of development results and management practices, both in relation to process and products, and to partnership strategies? What monitoring and evaluation procedures were applied by UNDP and partners to ensure greater accountability? Effectiveness - Have the expected development (quantitative and qualitative) results been achieved and what were the supporting or impeding factors? - Were the approaches, resources, models and conceptual frameworks relevant to achieve intended outcomes and outputs? - What are the main lessons learned from the partnership strategies and what are the possibilities of replication? - Were UNDP’s comparative advantages perceived/interpreted and were these reflected in the division of responsibilities? - To what extent have interventions addressed transitional justice process and impunity of international crimes? - Which aspects of the interventions had the greatest achievements? What have been the supporting factors? How can UNDP build upon or replicate these achievements? - In which areas does the project component have the least achievements? What have been the constraining factors and why? How can they be overcome? - Were the approaches, resources, models and conceptual frameworks used for mobile courts support relevant to the achievement of planned outcomes/outputs? - What were the unintended results (positive/negative) of mobile courts assistance interventions? Sustainability - To what extent was the timeframe/timeline of support to mobile courts as an immediate measure to improve access to justice of the conflict-affected population taken into account? - To what extent were sustainability considerations were taken into account in the design and implementation of interventions? How was this concern reflected in the design of the project component, in the implementation of activities at different levels, in the delivery of outputs and the achievement of outcomes? - Were exit strategies for mobile courts’ support interventions appropriately defined and implemented, and what steps have been taken to ensure sustainability of results? - How the development of partnerships at the global, regional and national level contributed to sustainability of the results? - How different stakeholders been engaged in the design and implementation of mobile courts’ support interventions? Have interventions been implemented with appropriate and effective inter-agency and partnership strategies? What has been the nature and added value of these partnerships? |  |
| ### Duties and Responsibilities |  |
| Inception: Based on the indicative questions listed in the above section, project component and content specific questions will be elaborated further by the evaluation consultant in the inception report. The inception report should contain an evaluation matrix that displays for each of the evaluation criteria the questions and sub-questions that the evaluation will answer, and for each question, the primary and secondary data that will be collected. Data collection: In view of the complexity of the evaluation, the consultant will seek to obtain data from a range of sources, including desk reviews and document analyses, surveys and questionnaires, stakeholder consultations, interviews and focus group discussions at UNDP Headquarters and in a range of programme countries, UN agencies, international organizations, and other relevant institutions. The rationale for using a range of data sources (data, perceptions, evidence) is to triangulate findings in a situation where much of the data, due to the very complex nature of interventions, is qualitative, and its interpretation thus critically dependent on the evaluators’ judgment. Triangulation provides an important tool in filtering evidence by using different data sources to inform the analysis of specific issues. The evaluators will provide empirical evidence to support all conclusions and recommendations, and the evidence will be validated from multiple sources. Where possible and appropriate, the evaluation should seek to obtain evidence as to what might or might not have occurred in the absence of these interventions. A three-phased approach will be adopted in conducting the evaluation: First phase (Initial briefings/ meetings in New York and desk reviews): During this phase, the Evaluation consultant will conduct a desk review of relevant project documents and related documentation such as routine monitoring reports, project progress reports, and relevant review and evaluation reports, other analytical studies. The desk review will enable the consultant to: i) examine the quality of results baselines and indicators established for the projects; ii) assess the adequacy of the response strategies as reflected in the results framework; iii) review the quality of project baselines and indicators as well as existing monitoring mechanisms and resources (financial and human), and iv) conduct an initial assessment of progress towards results and/or impact as reflected in available progress reports. During the first two weeks of this phase the Evaluation Consultant will participate in briefings and meetings in UNDP and other UN agencies based in New York and interviews with the members of the Evaluation Reference Group. Within the first two weeks of the assignment the Evaluation Consultant will submit the inception report, describing the methodological/analytical framework for the evaluation and overall timeframe. The second phase (country visits): The in-country evaluations will require extensive review of existing documentation with particular attention to evaluations and studies, consultations with senior and operational managers and field staff, as well as consultations/interviews with a sample of beneficiaries. This will also include review of existing UNDP programme evaluations and assessments, studies, research and evaluations conducted by other development partners, and other relevant documentation. The Evaluation Consultant will conduct individual country visits to validate the documentary data against actual results on the ground. The focus will be to triangulate information from documents and interviews by gathering objective data on key achievements and areas for improvement. At the end of each country visit, the Evaluation Consultant is expected to present initial findings to the concerned country offices for validation of factual information and findings. The third phase (finalizing reports): The third phase of the evaluation will include finalization of the evaluation report, presentation of its findings to the Evaluation Reference Group and dissemination of lessons learned through existing UNDP mechanisms. The report should specifically highlight key lessons learned and good practices that could be replicated in future programs. Evaluation Products / Deliverables: - Inception report— detailing the evaluators’ understanding of what is being evaluated and why, showing how each evaluation question will be answered by way of: proposed methods, proposed sources of data and data collection procedures. The inception report will also include a proposed schedule of tasks, activities and deliverables, designating a team member with the lead responsibility for each task or product; - Draft evaluation report; and - Final evaluation report. Evaluatiuon Ethics: The evaluation will be conducted in accordance with the principles outlined in the UNEG “Ethical Guidelines for Evaluation” and evaluators must address, in the design and implementation of the evaluation critical issues, critical issues including evaluation ethics and procedures to safeguard the rights and confidentiality of information providers, such for example: measures to ensure compliance with legal codes governing areas such as provisions to collect and report data, particularly permissions needed to interview or obtain information about children and young people; provisions to store and maintain security of collected information; and protocols to ensure anonymity and confidentiality. Implementation Arrangements: The ROL Team and the Monitoring and Evaluation team (M&E) of the Bureau for Crisis Prevention and Recovery (BCPR) will jointly manage the evaluation process and ensure the coordination and liaison with concerned agencies at the headquarter level as well as the country level. An Evaluation Reference Group will be established at the outset of the evaluation, consisting of key stakeholders and partners, i.e. focal points/representative from UN agencies, multilateral development banks (the World Bank), academia, as well as client countries’ representatives and implementing partners. The Reference Group will play an important role in providing strategic, methodological and substantive inputs into the evaluation process, as well as feedback on the inception and final evaluation report. In addition, the reference group will ensure that the evaluation results are appropriately disseminated and discussed within their respective organizations. |  |
| ### Competencies |  |
| - Superior leadership and strategic management skills with an excellent understanding of international development issues and knowledge of the UN system; - Strong written and verbal communication skills, in a multi-cultural setting; ability to conduct results-based management and reporting, objectivity and ability to analyze large multi-country data sets in short period; - Experience working collaboratively in small teams with tight deadlines. |  |
| ### Required Skills and Experience |  |
| Education: - Masters or PhD in law or other relevant fields. Experience: - At least 7 years of international development experience or well established and well-functioning organization with at least 5 years of experience in project/programme design and implementation; - Relevant professional experience in evaluation of rule of law or other relevant programmes – at national, regional, and global levels; - Strong monitoring and evaluation background, sound methodological skills and knowledge of evaluation methods and techniques; - Extensive experience in working with the UN/multilateral development agencies, UNDP country offices and/or regional centres is an asset. |  |

UNDP supported mobile courts interventions

evaluation report

Local Court police officers in Moyamba

Country report n.1

The circuit courts of Sierra Leone

Commissioned by: UNDP/Bureau for Crisis Prevention and Recovery (BCPR)

Conducted by: Monica Rispo

February 2013

Contents

Acronyms and abbreviations …………………………………………………………………………………………..	p. 4

Executive Summary ………………………………………………………………………………………………………..	p. 5

PART I: INTRODUCTION

1.	Introduction …………………………………………………………………………………………………………	p. 8

2. 	Purpose and scope of work …………………………………………………………………………………..	p. 8

3. 	Methodology and limitations ……………………………………………………………………………….  	p. 9

4. 	Description of the evaluated intervention...…………………………………………………………..	p. 9

5. 	Overview of the judicial system in Sierra Leone ……………………………………………………	p. 10

6. 	Critical background factors ……………………………………………………………………………………	p. 10

PART II: EVALUATION FINDINGS

# 1.  	relevance

1.1. The Sierra Leonean mobile court model …………………………………………………........	p. 12

1.2. Relevance to national justice sector strategies ………………………………………………	p. 13

1.3. Relevance to the needs of the population ……………………………………………………….	p. 15

1.4. Relevance to gender and national ownership …………………………………………………	p. 16

# 2.  	effectiveness

2.1. Planning and monitoring …………………………………………………………………………………	p. 17

2.2. The achieved results ……………………………………………………………………………………….	p. 19

2.3. The quality of the achieved results …………………………………………………………………. 	p. 21

2.4. Observation of mobile court sessions ……………………………………………………………..	p. 31

# 3.  	efficiency

3.1. Cost-effectiveness …………………………………………………………………………………………..	p. 32

3.2. Coordination with international partners ……………………………………………………….	p. 34

3.3. Coordination between national justice and security institutions ……………………	p. 35

3.4. Challenges ……………………………………………………………………………………………………..	p. 37

3.5. Good practices ……………………………………………………………………………………………….	p. 38

3.6. Lessons learned ……………………………………………………………………………………………..	p. 39

# 4.  	sustainability …………………………………………………………………………………………………………	p. 39

# 5.  	impact

5.1. Changes for the population and the justice actors ……………………………………………	p. 40

5.2. The impact of mobile courts on the prosecution of international crimes  …………	p. 41

PART II: CONCLUSIONS AND RECCOMANDATIONS

6. 	conclusions ………………………………………………………………………………………………………….	p. 42

7. 	reccomandations …………………………………………………………………………………………………	p. 43

ANNEXES

- 1. List of reviewed literature

- 2. List of interviewed persons

- 3. Map of circuit courts

- 4. Chief Justice Order for the appointment of High Court circuit sessions, 2011

- 5. Evaluation matrix

- 6. TOR

Acronyms and abbreviations

A2J: Access to justice

ASJP: Access to security and justice programme

AWP: Annual work-plan

BCPR: Bureau for crisis prevention and recovery

CARL: Center for accountability and rule of law

CO: Country office

CPA: Criminal procedure act

CSO: Civil society organization

DFID: United Kingdom Department for International Development

FGM: Female genital mutilation

FSU: Family support unit

GBV: Gender based violence

GIZ: Deutsche Gesellschaft für Internationale Zusammenarbeit

IRC: The International Rescue Committee

JP: Justices of the peace

JSDP: Justice sector development programme

LOA: Letter of agreement

MOU: Memorandum of understanding

NHRC: national human rights commission

PBF: peace building fund

PI: preliminary investigation

SGBV: sexual and gender violence

SMART: Specific, Measurable, Achievable, Relevant, Time-bound

UNDP: United Nations development programme

UNIPSIL: United Nations Integrated Peacebuilding Office in Sierra Leone

UNSCR: United Nations Security Council resolution

UPR: Universal periodic review

Acknowledgments

It is with sincere gratitude that the consultant acknowledges the contributions of all the persons met during the evaluation process. Thanks are due to the UNDP staff in Sierra Leone and in BCPR for their support and the valuable comments and clarifications provided; most grateful appreciation is extended to the Sierra Leonean partners and interviewees for their hospitality and for sharing their experiences.

Executive Summary

The present report is part of a broader evaluation commissioned by UNDP/BCPR to assess results, identify good practices and lessons learned in supporting mobile courts interventions across UNDP RoL programmes in post-conflict settings. In this framework mobile courts are defined as “formal courts that conduct proceedings in locations other than their home offices, usually in remote areas where no justice services are available”.

As set forth in the TOR and further detailed in the Inception Report, the evaluation includes a field visit of an international consultant to 3 selected COs (Sierra Leone, DRC and Somalia) and a desk study on additional COs that are supporting Mobile Courts (Timor Leste and Central Africa).

The present report presents the findings of the field visit to Sierra Leone.

The legal background for Sierra Leonean circuit courts is article 7 of the 1963 Courts Act stating that “courts should be held at such places as the chief justice may direct”; the principle is reaffirmed in article 131.3 of the Constitution and further specified by a yearly Chief Justice order.

The mobile court system in Sierra Leone is jointly supported by 3 international partners, under a framework that covers the whole territory of the country by geographically dividing the respective area of intervention: UNDP supports the Southern province; GIZ the Eastern and DFID the Northern province. Similar models of intervention are applied, mainly consisting in providing financial support to the Judiciary to implement the circuit courts, in complementarity with other activities.

UNDP is supporting circuit courts in the Southern province since 2010; 2 Letters of Agreement have been signed between UNDP and the Judiciary for a total amount of 45.496 USD.

2 typologies of courts are travelling on circuit: Magistrate courts and High Courts. While on circuit the jurisdiction of the latter is limited to criminal cases, whereas Magistrates can also hear civil cases.

In the Southern province UNDP supports 2 resident Magistrates to cover 8 stations and 1 resident High Court judge to travel on circuit 4 times per year, in the locations identified by the Chief Justice order.

The initiative has developed some good practices; to be noted the growing network of community-based court monitors, the adequate and commonsensical budget and the effective use of courtrooms.

The most cited challenge was the absence of witnesses in court and the related issue of high adjournment rates, followed by the difficulties that court users have in understanding the procedures due to language barriers and lack of rights awareness.

Key lessons learned include: 1) mobile courts have been an efficient stop-gap mechanism to assist the government in reestablishing the formal justice system after the civil war and temporarily respond to the chronic shortage of magistrates 2) some of the challenges faced by mobile courts are a reflection of those affecting more generally the justice system, so eventual solutions would require a more comprehensive justice sector reform intervention 3) supporting mobile courts should not be limited to the supply side of justice (allowances, fuel and stationary for circuit courts) but should also target the demand side of justice (raising awareness among the population about the role and objectives of a mobile court and establish mechanisms to assist vulnerable groups to claim their rights  and understand the legal procedures).

Acknowledging the difficulties of intervening in a country where the traditional legal system is strongly prevalent, the evaluation concludes that UNDP’s support to mobile courts in Sierra Leone is achieving results that are progressively improving.

The main findings for each evaluation criteria are summarized below.

relevance

Mobile courts are aligned with national justice sector strategies; they have been supported in full respect of the principle of national ownership and were found to be relevant by partners and other key stakeholders.  Circuit courts should be more responsive to the needs of the population, inter alia by ensuring that language is not a barrier to the adequate participation of litigants in the proceedings and that people receive timely information about the arrival of the mobile court in their village. Mobile courts are gradually contributing to translate into practice the recently adopted laws on the protection of SGBV victims, although these procedures still need to be improved.

effectiveness

There is clear evidence of improvement in the planning of the initiative, but monitoring remains a major concern, mainly due to the lack of court statistics and a shared vision on monitoring approaches between donors and the Judiciary. There is however a definite commitment from the Judiciary to define jointly with the 3 international partners a common monitoring framework.

Magistrate Courts on circuit record an approximate number of 972 received and 568 disposed cases under the support of UNDP, which indicates an acceptable 58% rate of case disposal and a successful 12% increase in the number of cases received during the reporting period. The High Court on circuit achieved a disposal rate of 52% with 375 received cases and 198 disposed cases.

The quantitative results appear satisfactory in a context where traditional system is strongly prevalent, but the quality of the mobile court services could be improved, in particular with regards to the following aspects:1) illegal pre-trial detention for remandees waiting for circuit courts to arrive; 2) lack of lawyers and interpreters to assist court users; 3) high adjournment rates due to the absence of witnesses in court; 4) special measures to protect SGBV survivors in court proceedings; and 5) logistical improvements, such as the prompt communication of the arrival of circuit courts and the regularity of its schedule, transportation for the mobile court team.

efficiency

The mobile court system is dependent on international donors for 80% of its budget, the remaining 20% being an in kind contribution from the Judiciary. Allowances (the highest budget line), are aligned with the local marked and perceived as fair.

The coordination with other international partners has achieved the exemplary result of ensuring circuit courts on the whole territory of Sierra Leone. The coordination is being strengthened with the development of common monitoring tools and a harmonized allowance policy.

Conversely coordination among justice and security actors appear weak and no formal mechanism to promote linkages seems in place.

sustainabilty

Some of the preconditions for the MC to continue without international support are in place: they are implemented independently under the lead of the Judiciary and having recourse to only local capacities.

The lack of financial and human resources remains a strong obstacle and allows concluding that the Judiciary’s reliance on donor support will continue for some time. An exit strategy should be defined in cooperation with the Judiciary. Meanwhile the Judiciary should advocate for additional funds in the national budget and UNDP should provide assistance to improve key aspects of the intervention, with a particular focus on monitoring activities.

impact

Key informants reported reduced crime rates in the villages where circuit courts travel and pointed out that litigants and their families are relieved from the economic burden of travelling to courts. Due to the lack of specific measures to assist court users in claiming their rights (legal aid, interpretation), the impact of mobile courts on the population has not been as significant as it could have been. Mobile courts have yet had a limited, although growing, impact on increasing legal awareness among the rural population.

The impact of mobile courts has been positive for the Judiciary.  The role of the formal justice system in remote areas has been strengthened, in particular by making the courts known to the population, which is a successful achievement in a country where traditional justice is strongly prevalent. Circuit courts have indirectly addressed the issue of the chronic shortage of Magistrates and backlogs in the districts have been cleared.

Due to legal and political obstacles, no war-related prosecutions were initiated by the national justice system, so circuit courts did not have the opportunity to impact on transitional justice.

Key recommendations directed at UNDP and the Judiciary are detailed in the body of the report and include:

- Strengthen gender and SGBV mainstreaming

- Improve monitoring aspects

- Ensure the accountability of mobile courts for illegal pre-trial detentions

- Promote complementary activities targeting the demand side of justice

- Continue to promote international partnerships

- Improve communication

- Reduce adjournment rates and promote the presence of witnesses in court

- Continue to support court monitors

- Support the Judiciary’s strategy to complete the institutionalization of circuit courts

PART I: INTRODUCTION

§ 1. Background and rationale for the evaluation

The present report is part of a wider evaluation exercise titled “UNDP’s support to mobile courts arrangements in post-conflict situations”

For the purpose of the evaluation Mobile Courts are defined as “formal courts that conduct proceedings in locations other than their home courts, usually in remote areas where no justice services are available”. Trials are organized closer to the population by transferring the required justice actors (judge, prosecutor, court clerk, police officer…) to remote locations with the main objective to facilitate access to justice, in particularly for vulnerable groups who would not otherwise have the possibility to bring their cases before a formal court, often located miles away from their villages.

The growing number of UNDP Country Offices (COs) that are supporting Mobile Courts interventions and the lack of comprehensive studies specifically dedicated to this topic, suggest that further analysis of the functioning and impact of mobile courts interventions and how UNDP supports these initiatives would be needed. Within this framework, BCPR is conducting an evaluation to assess results, identify good practices and lessons learned in supporting mobile courts interventions across UNDP RoL programmes in post-conflict settings.

As set forth in the TOR and further detailed in the Inception Report, the evaluation includes a field visit of an international consultant to 3 selected COs (Sierra Leone, DRC and Somalia) and a comprehensive desk study on additional COs that are supporting Mobile Courts.

The present report presents the findings of the field visit to Sierra Leone.

The terms “Mobile Court”, “Itinerant Court” and “Circuit court” are interchangeable; the latter is commonly used by Sierra Leoneans legal practitioners.

§ 2. Purpose and scope of work

The present report is directed to UNDP/BCPR staff, the Judiciary, international partners and donors (DFID, GIZ and Irish aid) and has two overarching objectives:

- Promoting joint accountability of the UNDP Country Office and the Sierra Leonean government, respectively in supporting and implementing mobile courts interventions.

- Building knowledge to improve mobile courts interventions across BCPR’s Global ROL programme.

The report is structured in 3 parts: the first part presents a description of the methodology and a brief overview of the context; the second part assesses the interventions against the criteria of relevance, effectiveness, efficiency, sustainability and impact; the third part presents the conclusions and the recommendations.

§ 3. Methodology and limitations

The evaluation was conducted by an international consultant and consisted in a desk review phase followed by a mission to Sierra Leone from 30/01/2013 to 10/02/2013.

The desk review included an analysis of relevant documentation and discussions with the UNDP Project Manager to define the evaluation tools. (see list of consulted literature in Annex 1)

During the country visit, the consultant conducted interviews with about 40 key informants, including representatives of the Judiciary, police and prison system, civil society organizations, international partners, mobile court users and UNDP staff. (see list of consulted persons in Annex 2)

The mission included a 3 days visit to Moyamba and Gbangbatok to observe 2 circuit courts sessions.

A draft report was submitted to the CO and BCPR for comments.

The methodology of the evaluation was set out in the Inception Report and consisted in a mixture of qualitative and quantitative research methods.

The evaluation questions and sub-questions are defined in the Evaluation Matrix (see Annex 5) on the basis of the TOR and reflect the 5 criteria of relevance, effectiveness, efficiency, sustainability and impact.

Some constraints, mainly related to the planning and monitoring aspects of the intervention, have prevented a detailed analysis of the project results. In particular court statistics provided by the Judiciary were not detailed enough to allow a comprehensive analysis of the results and the reporting was not continuous throughout the duration of the agreement with UNDP.

§ 4. Description of the evaluated intervention

UNDP is supporting circuit courts in Sierra Leone since 2010. The intervention was developed on the basis of the 2005-2008 “JSDP pilot project in Mombaya”, a sector wide Justice and Security programme funded by DFID, which included a mobile court component.

The support to mobile courts is part of the broader UNDP “A2J in Sierra Leone programme”, and falls under Output 1 (strengthen state capacity for efficient justice service delivery) and activity result 5 (formal justice services extended to deprived rural areas) for the 2012 UNDP AWP.

The intervention is further described in 2 Letters of Agreement (LoA) signed between UNDP and the Judiciary, respectively in 2010 and 2012, for a total amount of 45.496 USD. The 2012 LoA has been extended to April 2013.

The scope of the present evaluation focuses on the specific activities identified under the 2 LoAs and summarized as follows:

- UNDP will deliver the funds required to implement circuit courts in the Southern province.

- The Judiciary will ensure the implementation of circuit courts as follows:

-  The Magistrate court based in Bo will cover monthly/bi-monthly circuits to 3 stations (Pujehun,

Zimmi, Mongere)

-  The Magistrate court based in Moyamba will cover monthly/bi-monthly circuits to 5 stations

(Mattru-Jong, Rotifunk, Taiama, Bonthe Island, Gbangatok). The four lasts stations were added in

the 2012 LoA.

-  The High Court based in Bo will ensure circuits to Moyamba 4 times per year.

- The Judiciary will provide UNDP with financial and narrative reporting

The map in Annex 3 provides an overview of the locations served by mobile courts.

§ 5. Overview of the judicial system in Sierra Leone

Below is a brief overview of the structure of the Judiciary and the hierarchy of courts in Sierra Leone, with a special focus on the Magistrate Courts and the High Courts in the provinces, which are the ones that travel on circuit and fall under the scope of the present report.

- Local Courts are part of the Judiciary only since August 2011, when the revision of the Local Courts Act established that they no longer reported to the executive branch of the government (Ministry of Internal affairs).

Local courts are hybrid in the sense that they apply traditional laws but are officially part of the formal judicial system. The 292 local courts of Sierra Leone have jurisdiction over community and domestic issues, including land, inheritance, divorce, maintenance, and minor debt disputes as well as “criminal offenses punishable by a fine not exceeding 50.000 Leones or a term of imprisonment not exceeding 6 months”

In addition to these formally recognized traditional courts, there are a range of unlawful informal structures at community level that are run by Paramount chiefs and secret societies.

- Magistrate Courts have original jurisdiction to try minor criminal and civil cases and appellate jurisdiction over Local Courts within each judicial district. Magistrate courts do not have jurisdiction over more serious offences such as murder and rape, but they hear these cases on preliminary investigation to determine whether there is sufficient evidence to warrant a committal to the High Court.

The Magistrates are assisted by two Justices of the Peace (JP), usually retired civil servants.

- High Courts have original jurisdiction over all criminal and civil matters and exercise appellate and supervisory jurisdiction over all inferior courts. In the provinces there are 3 High Courts based in the each provincial headquarters (Bo, Makeni and Kenema).

- A Court of Appeal sits in Freetown and the Supreme Court is at the highest level of the court hierarchy.

§ 6. Critical background factors

The judicial system of Sierra Leone has been described and assessed in several reports, to which reference is made for further information.

The box at the end of the paragraph provides a situational analysis and the points listed below present a summary of key contextual issues that are affecting the mobile court system and should therefore be taken into consideration while reading the present report.

- Sierra Leone has a dual legal system, incorporating both a formal system rooted in British common law and a customary system based on traditional law. Numerous reports refer that 70% of the disputes in Sierra Leone are handled by the traditional legal system: it remains unclear if this percentage is referred to the illegal courts or the Local Courts, however it indicates that a very low number of cases reach the Magistrate and High Court level.

According to the JSDP “Justice sector survey” in 2007 the total caseload for Magistrate Courts in Sierra Leone was 7,500 (4000 criminal cases and 3,500 civil cases) and the total caseload for High Courts was 1,308 (75 criminal cases and 1233 civil cases).

- The Sierra Leonean legal framework is outdated, for example both the Criminal Procedure Act and the Courts Act date back to the 60’s and reflect the strong formalism of court proceedings in the colonial era.

It is however to be recognized that in the past few years some innovative laws were passed (e.g. the Legal Aid Act, the Sexual Offenses Act and the ‘3 Gender Acts’  ) and some key laws were revised (e.g. the Local Courts Act).  These legislative changes represent an important opportunity for the Mobile Court system as they can play a key role in implementing the new laws and ensuring that the rural population is granted the new rights that have been recognized.

- Courtrooms have been rehabilitated after the war with the support of the international community, but there is still a serious shortage of legal practitioners in Sierra Leone. According to the draft “Agenda for Prosperity” the country has 21 Judges, 20 Magistrates, along with 23 Prosecutors. The number of lawyers was estimated to about one hundred in 2011.

- The country is addressing urgent gaps in other sectors, so there is limited funding available for the Judiciary to improve the justice services:  “In 2011 the Ministry of Finance awards the justice sector – including police, prisons, and courts –well below 1% of its annual budget”.

SITUATIONAL ANALYSIS

(Abstract from the UNDP access to justice project document – 2013/2014)

“Sierra Leone has made significant progress in building stability after more than a decade of civil war, which ended in 2002. During the immediate years following the end of the conflict the government prioritized rebuilding state institutions as well as basic infrastructure as part of the peace consolidation effort. Peaceful elections were held in 2002, 2007 and most recently in November 2012. Nevertheless, despite progress Sierra Leone is ranked 180 out of 187 countries in the 2011 Human Development Index; 60% of the population lives below the poverty line and a gender inequality index value of 0.662 ranks the country at 137 out of 146 countries in 2011.[...]

The lack of access to justice was identified by the Sierra Leonean Truth and Reconciliation Commission (TRC) in 2004 as a key cause of Sierra Leone’s 11-year civil war. In the aftermath of the conflict, lack of trained staff and damaged infrastructure hampered the administration of justice and threatened the consolidation of peace.  In the recovery phase therefore, donors provided logistical and infrastructure support to restore justice sector institutions severely destroyed or degraded during the war. The TRC findings led to a national consensus that reform of the justice sector is central to peace consolidation, and ultimately a vital ingredient for sustainable development in post-conflict Sierra Leone.

Despite 10 years of development assistance, the Government recognizes the problems that continue to confront the justice sector as a whole. Only 21 Judges and 20 Magistrates, along with 23 Ministry of Justice Prosecutors serve the entire country with a population of more than 6 million. Magistrates Courts are present in all Districts- 5 serviced only through donor supported mobile courts- however most criminal cases are prosecuted by untrained Police Prosecutors and long delays in both criminal and civil cases are common. Prisons are reported as overpopulated and arbitrary detention, due to delays in case processing, is the norm;

PART II: EVALUATION FINDINGS

In accordance with UNEG standards and as detailed in the TOR and the Inception Report, the evaluation findings are structured around the criteria of “relevance, effectiveness, efficiency, sustainability and impact”, as illustrated in the following paragraphs.

RELEVANCE

Relevance concerns the extent to which a development initiative and its intended outputs or outcomes are consistent with national and local policies and priorities and the needs of intended beneficiaries.

§ 1.1. The Sierra Leonean mobile court model

The notion of mobile justice is rooted in the Sierra Leonean judicial system: circuit courts are established in article 7 of the 1963 Courts Act stating that “magistrate courts should be held at such places as the chief justice may direct” and the principle is reaffirmed in article 131.3 of the Constitution.

Several key informants confirmed that circuit courts were organized in the provinces before the civil war, but specific material on this experience was not available. It’s only in 2008 that circuit courts were revamped with the support of the international community.

Holding circuit hearings in remote underserved areas is considered part of the duties of the magistrates and judges resident in the provinces. Therefore the issue of the selection of the mobile court team, which can be problematic in other countries, does not arise in Sierra Leone as the judges and magistrates appointed in the provinces will be the ones to travel on circuit. The areas and schedule for the High Court judges are identified every year by the Chief Justice, whereas Magistrate Courts have more flexibility in identifying their areas of intervention.

There are 2 typologies of mobile courts, with distinct jurisdictions and procedural rules.

a) Magistrate court circuit hearings

The Court Act establishes that a resident Magistrate should be present in each of the 12 districts of Sierra Leone, however as of February 2013, only 6 magistrates are operational in the provinces (2 in each of the three provinces).

The recruitment of 2 additional Magistrates is ongoing and the Master and Registrar clarified that they will be based respectively in the Northern and Eastern province.  In total the 6 magistrates are ensuring circuit hearings in 21 stations (8 in the South, 10 in the North and 3 in the East) with the support of the international community.

The jurisdiction of the Magistrate Court on circuit is the same as for permanent sittings. To be noted that in 1981 an amendment of the CPA extended the criminal jurisdiction of the Magistrate to “try summarily any offence punishable by sentence of imprisonment for a term not exceeding 5 years” (previously 3 years). In specific cases and “with the consent of the accused but not otherwise” the jurisdiction is increased to 7 years.

Concerning the UNDP supported Mobile Courts in the Southern province, it was referred that the Moyamba Magistrate sits in his home court every Friday and Saturday and the rest of the week he travels on circuit to 5 stations located in 3 judicial districts. Two Justices of Peace are supposed to ensure the ordinary activities of the home-court when the Magistrate is on circuit, but they are currently not operational in Moyamba.

The Moyamba magistrate court on circuit is indicatively composed of the following 7 team members: the magistrate, 1 court clerk/registrar, 3 police prosecutors, 2 prison officers, 1 driver. The court clerk also serves as interpreter. Police prosecutors ensure the prosecutorial function in all Magistrate Courts due to the shortage of State Counsels and prison officers are in charge of transferring prisoners on remand and the sentenced persons.

The Magistrate Court on circuit uses the Local Courts’ courtrooms and locks-up, which in the Southern provinces have all been recently rehabilitated, inter alia with the support of UNDP/PBF.

b) High Court circuit hearings.

In the provinces there are 3 High Courts based in the each provincial headquarters (Bo, Makeni and Kenema). In accordance with the Courts Act, they must travel on circuit 4 times per year (although for a variety of reasons the courts do not seem to have achieved this target for a long time, anywhere in the country). Their schedule is established every year by a Chief Justice order published on the Gazette.

In the Southern province the High Court sessions are held in Moyamba, a station that according to the Consultant Master and Registrar was chosen because of the high number of cases and the availability of facilities, such as the presence of a prison and availability of accommodation for the judge.

The 2012 Chief Justice order limits the jurisdiction of the High Court on circuit to criminal cases. To be noted that for most serious cases as rape and murder, the High Court intervenes only after the magistrate has conducted the preliminary investigation.

The High Court on circuit is composed of a judge and the support staff and convenes a jury of 12 persons; the prosecution is always ensured by a State Counsel.

Finally it is worth mentioning that across the 3 provinces, UNDP is supporting, since 2011, a network of CSOs that provide court monitoring services for mobile courts and local courts.

§ 1.2. Relevance to national justice sector strategies

Circuit courts are mentioned in the “Justice Sector Reform Strategy and Investment Plan I (2008-2010)” and bringing justice closer to the population is recognized as a priority in subsequent national justice sector strategies.

In particular Outcome 1 of the “Justice sector reform strategy and implement plan II / 2011-2014” aims at ensuring that “Justice is easily accessible locally” by building additional courtrooms and promoting ADR and paralegalism to unclog courts.

Similarly the “Poverty Reduction strategy 2013-2016” (Agenda for prosperity) plans to improve the conditions of service for the judges and to build additional courtrooms.

The Judiciary recognises that circuit courts have been a cost-efficient solution to the problem of the shortage of magistrates in Sierra Leone as the system has allowed the few resident magistrates posted in the provinces to covers additional judicial districts.

The main reason mentioned for the chronic shortage of magistrates in Sierra Leone is the fact that the salary of a Magistrate is significantly lower than the fees a lawyer can earn in Freetown, particularly in the commercial or mining sector.

The Consultant Master and Registrar summarized the current position of the Judiciary on mobile courts by defining them as “a permanent measure, but not to the scale as it is today”. The Judiciary is aiming at reducing the number of circuit sessions per Magistrate by ensuring the presence of one Magistrate per district who will continue to travel on circuit, but only within the judicial district of his or her competence.

Numerous key informants shared this position and viewed circuit courts as “temporary” or “stop-gap”  or “interim measure”; it was strongly advised to continue supporting the mobile court system but with the objective to develop them into a more permanent framework, which should be reflected in a clear engagement of the Judiciary to build new courtrooms and recruit additional resident magistrates.

More lawyers are expected to enter the profession in the coming years, and new Magistrates are in the process of being recruited. These changes in the justice sector should be seen as an opportunity for UNDP to support the strategy of the Judiciary to transform mobile courts into a permanent institution, with more resident magistrates covering a reduced number of circuit stations. To this end UNDP should extend its support to develop the legal profession and continue to assist the Judiciary in improving the conditions of service for magistrates and recruit additional ones.

Some of interviewed persons expressed the opinion that in some judicial districts the caseload would not be sufficient to justify a resident magistrate (indicatively 30 cases per year), and other suggested that in some cases a district court should have 2 magistrates so than one would be able to follow the cases of the home court while the other is on circuit. In this light it might be useful to conduct an analysis aimed at mapping justice services and needs to establish where additional magistrates would be needed.

Concerning the High Court circuit sessions, the Judiciary has a different vision for the coming years, which is mainly related to the fact the these courts are more costly in terms of allowances and salaries and their caseload is less compared to magistrate courts.

The interviewed High Court judge and the Master and Registrar believe that High Court circuit sessions should be considered as a permanent institution as there are currently not enough cases to justify an additional resident judge in the province.

Most interviewed persons (e.g. prison staff, NHRC, Namati ) suggested however that the High Court circuit sessions should be more frequent and respect the schedule of 4 times per year established by law. The main reason adduced by this group of interviewees is the pretrial-detention issues that arise while waiting for the MC to arrive.

§ 1.3. Relevance to the needs of the population

A comprehensive and systematic assessment of the needs of the population does not seem to have been undertaken prior to signing the LoA with the Judiciary to support mobile courts. Some material is available from the JSDP project, but in general the justice sector assessments conducted in the past mainly focus on the supply side of justice and contain limited information on the needs of the population.

The UNDP Project Manager explained that UNDP’s approach was to first ensure that institutional support would start and then conduct in parallel assessments into the needs and perceptions of the population. UNDP piloted such assessments in 2012 and will further expand them in 2013.

It is unanimously recognized that the presence of MC is relevant to the population in terms of offering a service that is physically more accessible and represents an alternative forum to local courts and traditional courts, as well as a strong deterrent to reduce crime rate in the communities.

The observation of two circuit courts and the opinion of key informants have however suggested that mobile courts are not prioritizing a people-centered approach, despite some magistrates are making efforts in this direction. One of the interviewed CSO representatives believes that “the victim is at the mercy of the court and the justice system seems to be there to support the institutions and not the people”.

It was observed, as further discussed in § 2.3, that all the services that would assist court users in understanding the legal procedures and in claiming their rights (as interpretation, legal representation, paralegal assistance, court fees exemption) were not available in any of the mobile courts.

UNDP court monitors are playing an important role in ensuring that mobile courts are more respondent to the needs of the population; being members of the communities where mobile courts travel, they are facilitated in understanding and giving voice to the needs of the justice users.

Several reports and the majority of the interviewed persons identified the most vulnerable groups in Sierra Leone as follows: rural women and children, persons living with disabilities (amputees) and persons living in detention .

Among the above-mentioned vulnerable groups, circuit courts only adopt special measures to ensure the rights of juveniles during trial. As observed during a magistrate circuit session and confirmed by key informants, the anonymity and privacy of juveniles during hearings is ensured, as all proceedings are held in camera as provided for by article 206 of the CPA.

The protection of women is analyzed in the next section.

Further information on the needs and expectations of the population in rural areas with regards to the formal system would represent an important baseline for eventual interventions aimed at promoting a more people-centered mobile court service. In 2012 UNDP and its partner-CSOs have piloted (and are currently collating the results) a court user survey, which will certainly contribute to address the above discussed issue.

1.4. Relevance to gender equality and national ownership

The situation of women’s rights in Sierra Leone is strongly influenced by customary traditions as illustrated in the following abstract from a Friede report:  “customary authorities have had responsibility for all decision-making over domestic and community matters and therefore over those issues most relevant to women’s lives such as marriage, inheritance, property, land and family rights. The fact that the state in Sierra Leone has traditionally relegated those issues of most importance to women to the “private” sphere and the control of customary authorities has had profound implications for women’s rights and participation in governance.”

Sierra Leone is gradually bringing some key domestic issues under the jurisdiction of the formal judicial system.  In 2007 the “3 Gender Acts” have increased State authority in areas of marriage, divorce, inheritance and domestic violence and, together with the 2012 Sexual Offenses Act, are offering a more effective legal framework for the protection of women’s rights.

In practice, changes for Sierra Leonean women are slow to become effective. In addition to the resistance from traditional chiefs, women who bring a male family member before a formal court are stigmatized by the community and can be abandoned by their families.

Mobile courts should be encouraged to play a more active role in implementing these new laws especially because the presence of magistrate circuit hearings in remote areas is particularly relevant to rural women. For example appeals of Local Court decisions before Magistrate Courts on circuit could represent an important tool to challenge local courts decisions that are discriminating against women.  Another recent tool available to Magistrates to protect women’s rights are protection orders for women victims of domestic violence.

In order to claim the rights that are recognized in the gender laws before a mobile court, women must be empowered to understand the procedures and assisted in bringing their cases before a court. UNDP is doing considerable work on raising women’s awareness both on SGBV and Gender Laws and also property rights; unfortunately, due to the lack of detailed court statistics, there is no evidence showing that women are accessing justice services more regularly since awareness activities have started.

Specific SGBV issues are addressed in § 2.3.

UNDP’s support to the mobile court system reflects the principles of national ownership.

As illustrated in § 1.2, the intervention is grounded in national justice sector strategies and is nationally driven and owned: for example the first LoA was drafted by the Judiciary and the second was written by UNDP in consultation with the Master and Registrar. In addition, the intervention fully relies on national expertise and capacities as mobile courts are entirely run and managed by the Judiciary.

The Judiciary, both in Freetown and in the districts, found UNDP’s support to be relevant. Relations between UNDP staff and the Judiciary are good and respectful of the independence of the judiciary. The Consultant Master and Registrar has engaged to make additional efforts to adopt a more rigorous monitoring framework, in compliance with UNDP rules and regulations. UNDP will support a monitoring and reporting officer who will be seconded to the Judiciary for a period of 6 months in order to improve the monitoring system and eventually develop a case management system.

UNDP is committed to develop national capacities within the Judiciary and has organized in the past, within the framework of other UNDP initiatives, trainings for judges and magistrates. In addition UNDP is planning to further strengthen the capacities of court monitors by supporting them to become fully accredited paralegals.

EFFECTIVENESS

Effectiveness is a measure of the extent to which the initiative’s intended results (outputs or outcomes) have been achieved or the extent to which progress toward outputs or outcomes has been achieved.

§ 2.1 Planning and monitoring

Planning

The main planning tools to guide UNDP and the Judiciary in the implementation of mobile courts are the 2 Letters of Agreement (LoA) signed between UNDP and the Judiciary in 2010 and 2012 and the UNDP Annual Work Plans (AWP) from 2010 to 2012, with reference to Activity result 5.

The LoA is described in § 4 and an abstract of the UNDP AWP is presented below.

| Abstract of UNDP AWP (2010 to 2012): activity result 5 (support to mobile courts) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity result 5 | Activity 1 | baseline | indicator | Target |
| Formal justice services extended to deprived rural areas | Funding for mobile courts for under or sub services areas | n/a | n/a | Four additional mobile courts supported in the Eastern province |

The planning of mobile courts activities under the 2012 LoA is more rigorous compared to the previous years and reflects UNDP’s results based management principles; a results framework is available as well as a clear budget and activities are detailed.

The following aspects of the LoA could be further improved:

Baseline:  a summary of the results achieved under the previous LoA (number of cases referred and disposed, number of circuit courts sessions, typology of mobile court users… ) as well as a brief analysis of the needs of the population with a special focus on the vulnerable groups should be included in the LoA (the results of the ongoing court user perception survey will provide this kind of information, which will be reflected in the 3rd LoA/2013).

Indicators: It is suggested to add quality indicators (e.g. adjournment rate), eventually impact indicators and to ensure that indicators are SMART and disaggregated by gender. In addition indicators should be harmonized with the court statistics provided by the judiciary on quarterly basis.

Targets: In line with the Judiciary’ strategy to institutionalize circuit courts and in view of a UNDP exit strategy, the targets for new LoA should have a stronger focus on the quality of the implemented activities (e.g. reduction of adjournments and pretrial detention…). UNDP is already working on these improvements in view of drafting the 3rd LoA.

A good practice to improve the quality of court decisions is to carry out regular cases-audits. Such practices are for example well established in DRC where UNDP publishes a yearly report in the framework of its “court monitoring project”, which includes an analysis of selected GBV cases; Avocats sans Frontières has a similar initiative focused on international crimes cases handled by MC. Such reports have proved to offer the judges useful tools to improve their practice without interfering with their independence.

Additional recommendations would include a brief reference to the criteria for identifying the geographical areas of intervention to allow a better understanding of the initiative.

Finally the format of the quarterly and annual narrative report complied by the Judiciary should be tailored to the mobile court intervention and reflect data collected on the basis of the identified indicators and targets.

Monitoring

The main monitoring tools identified in the LoA are the annual and quarterly narrative reports indicating: 1) dates and location of circuits, 2) case statistics: number of cases reported and disposed of for each location.

Monitoring has been weak throughout the intervention and is major concern for all three international partners supporting circuit courts (UNDP/GIZ/DFID).  The limited availability of court statistics has not allowed to consistently measure progress towards set targets and is raising serious doubts among donors about the opportunity to continue supporting circuit courts.

Annual reports are structured with reference to different reporting periods so it is not possible to analyze the results in a comparative approach; the quantitative data is occasionally missing and is too limited (only number of referred and disposed cases); finally the number of circuits courts and their dates are not detailed, as requested in the LoA.

The consultant experienced serious difficulties in collecting the basic data to assess the initiative.

Several reasons can be mentioned to explain these shortcomings.

UNDP and other international partners bear the responsibility for not having elaborated a detailed monitoring framework which would have guided the Judiciary in selecting the courts statistics and other data required to deliver a reporting compliant to UNDP standards.

The main weakness at the Judiciary level is the lack of an efficient case management system and a computerized database to follow up on court outcomes. This was confirmed in a recent report by the Auditor General which documented “poor management and maintenance of magisterial returns” in several judicial districts included at Bo magistrate court.

The Master and Registrar confirmed that all courts send their returns to Freetown every month and insisted that statistics are disaggregated by nature and typology of cases.

It seems therefore that a solution to the monitoring issues should focus on 1) establishing a common understanding of the monitoring framework; and 2) promote activities directed at improving the court management system.

Fruitful discussions with the Judiciary led to an agreement on the points listed below. (which are recommended to be regarded as essential preconditions to the signature of the new  LoA):

- a standard template to collect basic court statistics and eventually a database will be developed;

- the standard template will be discussed and adopted by all three international partners (GIZ/UNDP/ASJP);

- UNDP will ensure that personal data of court users will not be collected (specifically the name of the client);

- the Judiciary will provide the missing court statistics (e.g the 6 last months of 2012)

- the Judiciary confirmed availably to host a UNDP supported Monitoring and Reporting officer for a period of 6 months.

§ 2.2. The achieved results

For the reasons illustrated in the previous paragraph, it is difficult to assess the mobile court intervention from a quantitative perspective.

The tables below represent however a tentative effort to produce some quantitative information about the results achieved by the mobile court system in the Southern province. Bearing in mind that some statistics were missing and other data was deduced from financial reports, the figures can be considered indicative.

| High Court of BO (circuits in the Southern Province from 2010 to 2012) |  |  |  |
| --- | --- | --- | --- |
|  | 2010 | 2011 | 2012 |
| Locations visited by MC | Moyamba | Moyamba | Moyamba |
| ≠ of MC sessions | 2 (august and October) | 2 ( June and November) | 1 (June) |
| ≠ of days on circuit | 20 | 20 | 10 |
| ≠ of cases received | n/a | 182 | 193 |
| ≠ of cases disposed | n/a | 112 | 86 |

| Circuit sessions for the Magistrate Court based in Moyamba * |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ≠ of MC sessions |  | ≠ of days on circuit |  | ≠ of cases received |  | ≠ of cases disposed |  |
|  | 1st LoA (09.2010 to 09.2011) | 2nd LoA (10.2011 to 07.2012) | 1st LoA (09.2010 to 09.2011) | 2nd LoA (10.2011 to 07.2012) | 1st LoA (09.2010 to 09.2011) | 2nd LoA (10.2011 to 07.2012) | 1st LoA (09.2010 to 09.2011) | 2nd LoA (10.2011 to 07.2012) |
| Rotifunk | n/a | 0 | n/a | 0 | 76 | 74 | 38 | 43 |
| Taiama | n/a | 2 | n/a | 3 | 72 | 88 | 41 | 59 |
| MattruJong | 6 | 6 | 18 | 14 | 44 | 59 | 23 | 33 |
| Bonthe | 1 | 2 | 6 | 8 | 51 | 47 | 21 | 28 |
| Gbangatok | n/a | 3 | n/a | 5 | 88 | 102 | 43 | 76 |
| TOTAL | 7 | 16 | 24 | 38 | 331 | 370 | 166 | 239 |
| Moyamba permanent Magistrate Court |  |  |  |  | 121 | 112 | 66 | 75 |

| Circuit sessions for the Magistrate Court based in Bo* |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | ≠ of MC sessions |  | ≠ of days on circuit |  | ≠ of cases received |  | ≠ of cases disposed |  |
|  | 1st LoA (08.2010 to 09.2011) | 2nd LoA (10.2011 to 06.2012) | 1st LoA (08.2010 to 09.2011) | 2nd LoA (10.2011 to 06.2012) | 1st LoA (08.2010 to 09.2011) | 2nd LoA (10.2011 to 06.2012) | 1st LoA (08.2010 to 09.2011) | 2nd LoA (10.2011 to 06.2012) |
| Pujehun | 3 | 3 | 5 | 10 | 72 | 98 | 44 | 56 |
| Zimmi | 4 | 2 | 8 | 1 | 14 | 23 | 6 | 19 |
| Mongere | 9 | 3 | 12 | 9 | 38 | 26 | 21 | 17 |
| TOTAL | 16 | 8 | 25 | 20 | 124 | 147 | 71 | 92 |

* Data from 8/2012 to 04/2013 is still being processed, but it can be anticipated that during this period the Magistrate Courts of Moyamba and Bo reported 160 received cases and 168 disposed cases. This is in line with the previous period and indicates an excellent disposal rate of 95%. It is also worth noting that the number of cases received per month rose from 27 in 2010 to 37 in 2012 and the number of disposed cases increased from 14 to 28 per month.

---------------------

According to the 2012 LoA, UNDP should support an estimated number of 50 circuit sessions for two magistrate courts and 4 circuit sessions for the High Court.  These targets were not achieved as of June 2012: the table indicates by that date 24 circuit hearings were organized for the Magistrate Courts and only 1 for the High Court. It is however to be noted that the Judiciary has been granted an extension of the LoA to April 2013. Also it must be recalled that the death of the High Court Judge in Bo, as well as the 2012 general elections, caused justified delays in the organization of the circuit courts.

For the 2 magistrate courts the total number of cases received on circuit from 08/2010 to 06/2012 is 972, of which 568 cases were disposed: the initiative records an acceptable 58% rate of case disposal.

The total number of cases received under the 1st and 2nd LoA has increased by 12%, which is a successful result if we consider the strong prevalence of the informal/traditional system in Sierra Leone. Both the interviewed Magistrate and Judge confirmed the positive impact of mobile courts in terms of increasing the number of cases.

To be noted that the total number of cases received during the JSDP/DFID pilot project in Moyamba (from 2006 to 2008) was 364. Gbangbatok (a targeted location in both JSDP and UNDP projects) reported 7 cases disposed in 2006 under the JSDP project and 76 disposed cases under the 2nd UNDP LoA.

For the Magistrate Court in Moyamba the number of cases disposed on circuit (405) is higher than the ones received in permanent sitting (141), which confirms that the magistrate spends most of his time on circuit but also raises some issues about the limited number of cases disposed in his home court.

The High Court in Bo is not travelling on circuit as regularly as prescribed by the LoA (4 times per year): in 2012 there was only one session in June, which took place as long as 8 months after the previous session.

From 08/2010 to 06/2012 the High Court on circuit achieved a disposal rate of 52% with 375 received cases and 198 disposed cases. The results are surprisingly high if compared to the findings of the interviews, which repeatedly pointed out that the court should travel more often, had huge backlogs and adjourned cases constantly.

An attempt was made to compare the results achieved by the mobile court system in the South with the other provinces (East and North) but it has not been possible because of gaps in statistical data made available by the Judiciary.

2.3 The quality of the achieved results

The mobile courts initiative is well received by the judiciary authorities and the population and as illustrated in the previous paragraph is achieving results that are progressively improving.

The objective of the present evaluation is also to assess the quality of the provided justice services and to apprise that they are not producing negative side effects.

To this end the achieved results will be analysed in the light of the basic human rights standards for fair trial, as provided for by the Sierra Leonean Constitution of 1991. In addition the quality of the MC system will be assessed against UNDP’s mandate, with a particular focus on the promotion of gender and legal empowerment.

Some of the findings address key issues that would need an immediate attention and would require complementing the MC intervention with additional activities (e.g. the provision of legal representation and interpretation during MC trials); other findings are indicated as opportunities for improvements.

Finally it must be recalled that most of the issues highlighted below are not specific to the MC system but are common to the justice system as a whole. It must however be recognized that these issues are usually aggravated when occurring in remote areas where courts travel on circuit and would therefore need an urgent attention.

■ Pretrial detention and bail

Section 17(3) of the Sierra Leone Constitution states that an arrested person shall be brought before a court “within ten days from the date of arrest in cases of capital offences, offences carrying life imprisonment and economic and environmental offences; and within seventy-two hours of his arrest in case of other offences”.

The provision is however not respected in the legal practice: a high number of interviewed persons and published reports have highlighted that pre-trial detention is one of the most alarming problems of the Sierra Leonean judicial system.

A recent study by UNIPSIL on the situation of detention in the 17 prisons of Sierra Leone concluded that “the majority of prisoners (57.5% as of March 2012) are not serving sentence, but are rather on remand or trial” . Human Rights Watch reported, in the 2011 UPR review, that “insufficient access to legal representation and the slow pace of cases before the courts had resulted in an alarming number of prisoners being held in prolonged pre-trial detention”.

Given the lack of detailed data, it is not possible to assess the impact of mobile courts on pretrial detention.

The interviews revealed however a general perception that the absence of a resident magistrate/judge has an important impact on the high pretrial detention rates in the provinces, because “detainees on remand are waiting for the MC to arrive”. The problem highlighted by most interviewed people was not the MC per se, but the fact that its schedule was not regular and that it was often delayed and its arrival unpredictable. The problem is particularly alarming for serious case like murder, for which magistrates do not have power to grant bail.

The Moyamba Deputy Prison Director referred that out of the 53 inmates, 15 were on remand waiting for the High Court to arrive in Moyamba. He further specified that “Some of these 15 inmates are waiting since 6 months and maybe a year for the arrival of the HC”.

Similar observations were made by the High Court jurors who observed that “the itinerant court is good but should be more frequent, at least 3 times per year. Some people spend more than 2 years in prison, waiting for the HC”. On the same note CARL highlights that “For detainees who are usually held on remand, it sometimes takes weeks or months before the circuit court sits in their jurisdiction”

The pre-trial situation is aggravated by the fact that judges are not granting bail easily: both the interviewed Magistrate and Judge expressed the valid concern that if bail is granted, there are strong chances that the case will be closed, because the accused will move to another part of the country and disappear. Accordingly, for serious cases it is common to grant bail only under very strict conditions.

For example during one of the observed High Court trials, the judge granted bail to a man accused of rape until the victim would appear in court. However he set a bail to 20 million Leones and requested 2 sureties, one of which should be resident in Moyamba and own property. Such strict conditions are not commensurate to the living conditions in rural areas and mean in practice to deny bail.

An additional point of concern was highlighted by the FSU police officer who reported that sometimes, although bail is granted, nobody shows up to stand for surety.  Considered that the CPA does not allow for the imposition of cash payment conditions to secure bail, sureties in Sierra Leone are just required to give a picture, their name and place of residence. However people are afraid of getting involved with the judicial system or they do not understand what their role should be, so they prefer not to show up.

Finally the UNDP court monitors mentioned the conditions to stand for surety should be revised so that women can also play this role. Currently most women are unable to meet the conditions set out by the magistrate: for example in the above mentioned rape case, a woman would not have been able to stand for surety because most women in rural areas do not own property, according to local traditions.

An interview with one of the remandees awaiting the High Court trial illustrates some of the above-described issues. The interviewed detainee was a 25 years old woman, married with 5 children, accused of murdering a child she was taking care of. She has been detained in Moyamba prison for 1 year and 4 months waiting for trial and given birth to her 5th child in detention. She never received any explanations about her rights or the legal procedures and her case was adjourned already once by the High Court, without bail being granted.

The following recommendations are proposed to improve the impact of MC on pre-trial detention issues:

- MC should follow a more regular schedule which should be communicated to relevant authorities well in advance.  The High Court should travel on circuit 4 times per year, as provided by the Criminal Procedure Act.

- MC should be more focussed on pre-trial detention, on the model of UNDP supported mobile courts in Central African Republic.  The current linkages between MC and the prison system appear weak: while describing such linkages the HC judge only referred that “the prison director hands over the list of persons on remand”. On the role of the judicial authorities in pre-trial detention, a report by ….. noted that “the Judges interviewed declined to accept any responsibility for detentions beyond the constitutional limit and the denial of bail, declaring that they were matters where the accused should exercise their own rights”.

In this context efforts should be promoted to ensure the accountability of MC for illegal detentions, for example by encouraging police prosecutors and State Counsel (or eventual lawyer) travelling with the MC to visit the police and local courts locks-up and the 4 prisons of the Southern province and follow up on eventual pre-trial detention cases.

- The new LoA UNDP/Judiciary should include specific indicators to measure the impact of MC on pre-trial detention.

- Detainees should be sensitised on their pre-trail rights for example by awareness raising sessions delivered by paralegals in prisons, which seems to be among UNDP’s priorities for the next programmatic cycle.

■  Legal representation and interpretation

Two main obstacles to an adequate participation of the parties to the hearings before the circuit courts were observed: the absence of a lawyer and of an interpreter. These issues have a disruptive impact on the rural population, where illiteracy and lack of understanding of legal procedures are common.

1. Legal aid and legal representation

Sierra Leone has recently ensured its compliance to international standards that set an obligation to provide legal representation to the indigent where the interests of justice so require.

In May 2012 the parliament passed the Legal Aid Act, which has been recognised as one of the most progressive legal aid laws in Africa, in particular for the inclusion of certified paralegals as legal aid providers.

Its implementation has not yet started so, despite the progressive legal framework, the right to legal representation is still seriously curtailed in Sierra Leone particularly in the provinces, where the majority of the population can not afford to pay a private lawyer.

The few lawyers practising in Sierra Leone  prefer to work in Freetown rather than in the provinces and those appointed by the State accept the task reluctantly because they know that their fees will be low and paid with delays.

The lack of legal representation affects mostly poor defendants: “Without adequate representation to build and fight a case for them, most defendants end up being convicted”

All interviewed persons unanimously confirmed that circuit hearings at both Magistrate and High Court level are often held without the presence of lawyers. In accordance with the CPA, the State only appoints a defence counsel in cases involving capital offences, namely treason, murder and serious economic crimes.

The High Court judge clarified that the current practice is to suspend capital cases unless the accused is represented by a lawyer. This occurred for example during one of the observed trials, which was adjourned because the defence lawyer for a woman accused of murder was expected the next day. To be noted that the JSDP report on legal aid questions this practice and states that “In the provinces outside Freetown, those who are charged with capital offences do not appear to be represented”.

A paradoxical impact of the absence of lawyers on the justice system was noted in a 2002 report:  “the preponderance of undefended cases, especially in the heavily overloaded magistrates’ courts, has prevented the complete collapse of the system. With capacity stretched to the limit, time is at a premium. As one magistrate explained, undefended cases are easier and quicker to hear, and if not for them, his own court would be crippled with backlogs”.

The observed circuit trials reflect this opinion as some of the hearings were extremely speedy and consisted in a dialogue between the police prosecutor/state counsel and the magistrate/judge, without any opportunity for the accused to participate in the trial.

This perception might also show through the bailiff’s opinion that “lawyers who come from Freetown cause unnecessary delays” and the jurors statement that “when a defense lawyer comes from Freetown there are lots of discussions between the state counsel and the lawyer”.

A common opinion among legal practitioners is that the intervention of a lawyer should occur as early as possible in the process, ideally during arrest and before the case enters the judicial system in order to get the detainee bailed. It is therefore important that legal aid lawyers are made available at the magistrate level and not only before the High Court. This is evident for serious cases under preliminary investigation (PI) at the magistrate level: the PI can last for months and when the case arrives before the High Court the detainee has maybe been on remand for several months, if not years.

Lawyers before circuit courts often face challenges to adequately prepare the litigation strategy as the arrival of the court is usually communicated at the last moment and often delayed.

Finally it’s worth considering if an effective way to strengthen the capacities of Police Prosecutors in Magistrate Courts, would be to ensure that a legal aid lawyer is present in addition to the Police Prosecutor to better protect the interests of the victim, on the model of the civil law system.

2. Assistance of an interpreter

The second aspect that hinders an adequate participation of the parties to the cases originates from article 78 of the Courts Act which stipulates: “the language of the Court established under the Constitution and this act shall be English”.

The provision places Magistrates is a difficult position:  they are only authorised to use English during the trial, although they speak local languages and most likely Krio, which is Sierra Leone’s lingua franca.

Asked if Magistrates could use the local language to facilitate the understanding of justice users, most interviewed persons (including judicial staff) replied that “this is the system and it can not be changed: judges must speak in English”. It is however common practice at magistrate level to grant police prosecutors and eventual lawyers to either lead or cross-examine witnesses in the local language. In addition the Constitution grants the parties to the case the right to use the language in which they are confident.

The consultant observed that trials appear very confusing and are difficult to follow due to the overlapping of these different languages; during one of the hearings an accused person was derided because, according to the Police Prosecutor, was pretending not to speak English.

Many interviewed persons reported that a lot of information gets lost or wrongly interpreted in the translation, as there are few professional interpreters. A common practice is that translations are conducted by court clerks, police prosecutors or by people from the public asked to volunteer to serve as interpreter. Court monitors added that “if you don’t want your matter to go the wrong way, you pay an interpreter”.

It appears however that only the questions to the accused or witness are translated, not the rest of the proceedings, which, combined with the absence of a lawyer who can explain the procedures, curtails the constitutional right to be tried in a language the accused understands.

The Moyamba Magistrate reported that he always ensured that the parties to the cases would have the opportunity the express themselves in the language of their choice; in addition he would spend additional time explaining legal procedures. This was the case in one of the observed trials, during which he clarified some important legal aspects related to domestic violence. Notwithstanding the parties to the case officially confirmed that they spoke English, when they were later interviewed by the consultant it was clear that their level of English was too poor to have understood the informative speech of the Magistrate.

Asked to suggest a solution, most interviewed people referred to international human rights standards and Section 23(5) of the Constitution to recommend that courts should provide interpreters.

While this might be appropriate for the High Court, several persons proposed a more people-centred solution at the Magistrate level.  Namati and DFID suggested advocating for a change in the legal practice aiming at authorising the use of Krio or other local language during trials before Magistrate Courts.

Such changes would require advocating for a legislative reform and could be then implemented by introducing new SOPs for justice officials, eventually building on existing documents as the JSDP “Criminal case management handbook”.

The lack of legal representation combined with the absence of an interpreter as well as the strong formalism of Sierra Leonean court procedures, seriously curtails the right of case parties to participate in MC trials and confines them to an isolated and weak position.

Recalling the centrality of legal empowerment and access to justice approaches to UNDP programming, it is recommended to complement the support to MC with additional interventions aiming at ensuring an adequate participation of the parties to the cases in the circuit trials. Some suggestions are illustrated below.

- UNDP should actively contribute to the debate on the implementation of the recently adopted Legal Aid Act , for example by continuing to participate in the related working group to inter alia advocate for the application of the future free legal aid scheme to the MC system.

- Explore the opportunity of re-establishing a UNDP funded legal aid scheme (as in 2012), at least for SGBV cases and in coordination with the planned ASJP initiative to provide legal aid for capital cases. If several donors are involved it might be worth to explore the possibility of promoting a UNDP managed Basket Fund for the activities falling under the Legal Aid Act, including legal representation in MC hearings.

- The option of including a salaried lawyer in the MC team was discussed, but found not ideal by most interviewed. The main reason was that the lawyer would not have time to ensure an adequate representation as it would not be possible to meet the client in advance.

A preferred solution was to support some lawyers to establish their practice in a few key districts. Supporting lawyers could indirectly address the issue of shortage of magistrates: considered that in Sierra Leone becoming a magistrate requires a minimum of 3 years of practice as a lawyer, legal aid lawyers could be encouraged to establish their practice in the provinces in  the prospect of serving as magistrates in the future.

- NGO representatives, in particular Timap and Namati, pointed out that for a free legal aid scheme to be effective, lawyers should be supported by a network of community based paralegals.  The Moyamba magistrate welcomed this suggestion and referred that he “has never seen paralegals in his court”, except occasionally when they came to follow up on a personal case.

Paralegals would play a key role in increasing the participation of MC users in the justice system by explaining legal procedures and making the MC services closer to the communities. Best practices in using paralegal services to complement a MC intervention can be drawn from the DRC experience, where paralegals meet with the community before and after the MC hearing to prepare the parties to the case and discuss the verdict. Paralegals would also play a key role in preparing the files before the arrival of the lawyer for example by collecting in advance the required documents or identifying eventual sureties and witnesses.

Timap developed a best practice in the Eastern province with the organization of joint trainings for paralegals, court staff and magistrates; the initiative had a positive impact in terms of increasing mutual confidence, strengthening the relationships and understanding respective roles.

The UNDP project manager explained that UNDP will support the court monitors working under the CSO network to attend the additional TIMAP training required to become certified paralegals, as provided for by the legal aid bill. In addition, from 1st of April 2013, court monitors will start providing paralegal assistance in support to mobile courts.

The innovative Sierra Leonean framework that recognizes paralegals as legal aid providers should be seen as a unique opportunity the UNDP CO to promote paralegalism and establish best practices that could be replicated elsewhere in Africa.

■ Procedural issues and the right to be tried without undue delay

The legal framework for both civil and criminal court procedures is outdated and has been often cited as one of the reasons for delays in MC trials.

The Consultant Master and Registrar confirmed that the draft of the revised Criminal Procedure Act (CPA) has been finalized and is planned to be discussed in Parliament in the coming months. Some of the main criminal procedure issues subject to revision include the preliminary investigation and High Court jury, which have important implications on MC as illustrated below.

A) Preliminary investigations

In accordance with Article 108 of the CPA, for cases that fall under the jurisdiction of the High Court “the Magistrate shall conduct a preliminary investigation into the charge alleged”. The rationale for this procedure is to rapidly ascertain if there is sufficient evidence to commit the case to the High Court. In practice, as mentioned by CARL, a Sierra Leonean legal NGO, the PI is so lengthy that it “has become a whole trial in itself”. For example, for the political violence which occurred in Bo in 2011, the ruling of the magistrate was issued one year after the beginning of the PI.

The High Court judge shared the opinion that PIs can cause unnecessary delays, with a particularly negative impact on witnesses, namely, when the case arrives before the High Court so much time has elapsed that the witnesses are not available any more.  The Moyamba magistrate confirmed that more PIs were conducted by his court compared to the previous year. (15 PI cases in 2012).

PI procedures conducted by circuit courts can be particularly problematic in terms of timing also because they require the coordination of 2 circuit courts.  It is therefore recommended that UNDP supports the current debate to revise the CPA and the NGOs that are advocating for changes in the PI procedures.

b) The High Court Jury

In accordance with the 1965 CPA the High Court must include 12 jurors. Jurors are volunteers without legal background who are annually selected from the communities for their probity and good character.

A group interview with 6 jurors (5 men and 1 woman) allowed a better understanding of their needs and role in the MC system. All the jurors were farmers and came from remote villages; most of them were retired civil servants (one was 103 years old and had served in the British army). They strongly complained about the limited amount of their perdiem (35.000 Leones for the entire 10 days High Court session) which they claimed was not enough to cover accommodation, food and the fact that they had to suspend their farming activities.

As explained by the Master and Registrar accepting to serve as a Juror is considered as a national service, so should not be paid. In Freetown a bench warrant can be issued if an appointed juror does not show up. The arrangements for the circuit courts jurors are therefore exceptional and have not the same rationale as the perdiem for the court staff.

Jurors also complained that they were informed only at 10.00 PM via the community radio that they had to be present at the High Court hearing the following morning.

The Master and Registrar believes that Jurors are a problematic and anachronistic institution and supports the ongoing discussion about reducing them to 8 (instead of 12). She also believes that in the provinces jurors do not have the required education level to participate in trial, so they can not adequately contribute. On the contrary they are causing delays, because if the Jury is not complete the hearing is adjourned. In practice (as observed during the field mission) if a juror is absent the court clerk will ask a person in the public to volunteer as replacement.

c) Witnesses and adjournments

One of the main challenges faced by the MC system is the high adjournment rate of the hearings.  As critically pointed out by one of the interviewed persons “mobile courts are not about going to the field and adjourning cases: it’s about delivering the service”.

The court statistics available to UNDP are not detailed enough to allow an analysis of the adjournment rate in the MC system, however a recent court survey by CSAE presents an interesting review of the matter. The survey concluded that  “from August to October 2010 in 10 up-country magistrates’ courts, 89% of criminal cases were adjourned”, but without specifying the number of adjournments per case.  The reasons for adjournments are indicated, out of a sample of 4.553 adjourned cases, as follows: 33% absence of witness; 14% absence of complainant; 11% absence of accused; 7% magistrate refuses the case; 7% lack of evidence; 28% other reasons.

These data are reflected in a recent report by Timap which summarises as follows the reasons for frequent adjournments in criminal cases:  “For a detainee’s case to be heard at the given date requires five things to perfectly coincide. First, the Magistrate must arrive to town on the pre-determined date. Second, all witnesses who will testify must be present for the case to be heard. Third, the prosecuting police officer must be present. Fourth, the detainee must be present. And fifth, the preceding court cases must not take longer than anticipated”.

The interviewed persons (included the magistrate, the judge and State Counsel) unanimously confirmed that the main reason for frequent adjournments of MC sessions is the fact that witnesses fail to attend court: this is not only due to the costs involved but also a consequence of the pressure to settle the case out of court that victims and witnesses receive from the family of the accused and other community members.

Other reasons for court adjournments were mentioned in the interviews. The jurors highlighted that the resident magistrate is on circuit most of the week and only sits in Moyamba on Friday and Saturday. Others reported that Magistrates were not attending court or being late.

UNDP is engaged in addressing the causes for adjournments and has developed a programme to reimburse travel expenses for witnesses.  The initiative falls under the Saturday courts programme, but is it was agreed with the Judiciary to extend it to MC, although the field mission confirmed that to date no witnesses were reimbursed for their travel expanses. To be noted that the costs are in line with the local market.

The effectiveness of the witness transportation programme could be strengthened if a paralegal network was in place in order to ensure witness tracking services.

It is recommended to ensure that future statistics from the Judiciary will include more specific information about adjournments, in order to i) be able to assess if the adjournment rate is too high to justify the MC intervention ii) to take corrective measures to address the reasons for high adjournment rates .

Such recommendations should also apply to court monitors who should not limit their reporting to indicating that “There are frequent and long adjournments of cases”, but also specify the reasons and the number of adjournments”.

■ The prosecution of SGBV crimes

The adoption of the Sexual Offenses Act in August 2012 marked the achievement of a comprehensive legal framework for the protection of Sierra Leonean women from SGBV crimes. The process started in 2007 with the adoption of the 3 Gender Bills and the National Action Plan on UNSCR 1325 and 1820.

The prosecution of SGBV crimes in areas where circuit courts are operational is facilitated by the presence of Police Family Support Units (FSU), specifically mandated to deal with gender-based violence. However specific data on SGBV cases disposed by circuit courts is not available as the statistics available to UNDP are not disaggregated by nature of the case.

The FSU in Moyamba mentioned that the number of cases reported to the police is increasing: 31 cases, out of which 3 rape cases were reported in 2012. According to the Judge his court handled about 5 or 6 rape cases in 2012. To be noted that Magistrate Courts only deal with rape cases as a preliminary investigation.

Numerous reports have analyzed the obstacles to prosecuting SGBV crimes in Sierra Leone, focusing for example on the difficulties women face in accessing free medical certification required for the trial or on the fact that most GBV cases are settled outside court, sometimes by the police.

An issue repeatedly mentioned during the interviews is that rape cases should be handled in camera, which appears to be the case before Magistrate Courts, but not before the High Court. This affects the right to privacy of the victims, especially in a culture where rape is very stigmatizing.  Court monitors reported that in some rape trials the public would laugh during the hearing and mentioned an FGM case that was openly explained into the most private details.

The Judge confirmed that his court treats juveniles in camera but not women victims of rape and he added that upon request of the party he could discretionally grant in camera hearings.

The solution to this issue is provided for in article 40 of the recent Sexual Offenses Act which establishes that when adult victims of sexual offenses are testifying, the court can decide “the adjournment of the proceedings to chambers or some other premises; the exclusion from the court, while the witness is giving evidence, of all or any persons without a direct interest in the proceedings”

The consultant found that this provision is not yet known and consequently applied in the provinces, so its dissemination should require some additional attention from the Judiciary.

UNDP will contribute to this objective by ensuring, in 2013, training activities for justice actors on the new Sexual Offense Act and other GBV laws, as the Domestic Violence Act.

IRC suggested topics aiming at strengthening the capacities of judicial actors to interview GBV survivors and promote the application of protection orders in domestic violence cases.

At this stage it is essential to support the Judiciary to translate the comprehensive legislative framework into practice and circuit courts, if adequately supported and trained, can play a key role in ensuring that Sierra Leoneans living in the provinces are granted the protection that they are entitled in the laws.

UNDP is supporting since 2012 the so-called Saturday courts in Bo and Freetown, which have specific jurisdiction over SGVB crimes.

The issue of linkages between the circuit courts and the Saturday court in Bo was discussed during the interviews. The solution of transferring all rape cases to the Saturday court was not considered realistic because PIs would still be conducted by Magistrates in the districts. However, if the abolishment of the PI will be achieved with the new CPA this option could be further explored.

Meanwhile it is recommended that best practices and landmark cases from the Saturday Courts are disseminated as widely as possible in the legal community. UNDP is planning to contribute to this objective in 2013 by supporting the publication of Law Reports.

■ Communication

Community radios are the communication means adopted by the Judiciary to inform the population about the arrival of a mobile court. It’s been recognized as an efficient and cost effective means, as it has a wide coverage and is free of charge.

Court monitors mentioned however that the community radio signal does not reach certain remote locations, and Timap believes that radio broadcast of the MC is irregular and only happens in few areas, for example in the Northern provinces. The High Court jurors complained that the information is released at the last moment. Advocaid also pointed out that their paralegals are particularly affected by the delays in communicating the arrival of the court, as they would need more time to visit the communities and track witnesses and sureties.

Given the obstacles faced by police process servers to inform the witnesses of the arrival of the court, it seems that sometimes community radios are used to inform parties to the case to appear in court. A lawyer expressed some concerns in terms of respecting the privacy of the parties to the cases because sometimes the names of the complainant, defendant and witnesses are publicly announced on the radio.

Being understood that the responsibility to communicate the arrival of MC lies with the Judiciary, eventual paralegals would play an important role in complementing radio messages and informing the population about the arrival of mobile courts.

■ Logistical issues

Some positive findings can be highlighted with regards to the logistical aspects of the MC system. Courtrooms have been rehabilitated, with inter alia the support of UNDP/PBF, so they are adequate and have spacious areas reserved to the public. Magistrate courts on circuit use the court room and detention cells of the Local Courts and High Courts on circuit sit in the premises of the magistrate court.

The security of MC staff is provided by the police and, as reported by the FSU officer, there have not been security incidents during the hearings.

Mobile courts could be more effective if some additional basic needs were ensured. Among suggested improvements are: the introduction of stenographers or modern transcription facilities; the creation of

a library with basic laws; the improvement of accommodation for judges and magistrates on circuit. The Moyamba registrar complained about the lack of stationary and claimed that he has to personally pay for these expanses. Considered that UNDP funds the stationary for MC, it is recommended to look into this issue further.

The observation of the circuit hearings, suggested that a microphone would allow the public to better hear the debate, although lack of electricity might be a factor to consider.

Transportation represents a major issue for the MC system. Vehicles are provided for by the Judiciary as an in kind contribution to the project. The Magistrate complains that only one car is available and given the state of the roads in the provinces it is often stationed in Freetown for repairs.

The deputy prison director highlighted the difficulties in transferring the detainees without a vehicle; it was indeed observed during the High Court circuit hearing, that the 12 prisoners on remand were escorted to the court by foot (1 mile). The police prosecutor added that when prisoners are transferred for a circuit court they are accommodated in the vehicle of the Magistrate, which raises issues of security and impartiality.

§ 2.4 Observation of mobile court sessions

The consultant had the opportunity to observe 2 circuit sessions in Moyamba (High Court) and in Gbangbatok (Magistrate Court).

In Gbangbatok the Magistrate Court was on its 3rd day of hearings and the observed session lasted from 10.00 to 13.00. The circuit court team was composed of the magistrate, 2 police prosecutors, 2 prison officers and the registrar. 50 persons were present among the public (16 women), most of which were involved in the case.

7 cases were handled during the observed session, as detailed in the table below. 3 parties to the cases (2 male, 1 female) were interviewed and shared their experience with the MC.

In none of the 7 cases observed a lawyer was present. There were 2 adjournments due to lack of witnesses.

Two cases of interest are highlighted below.

A domestic violence case reported by a woman against her husband who had beaten her and caused injuries requiring 500.000 Leones of medical treatment. The sentence was mild (a fine of 100.000 Leones) but considered proportionate as the wife pleaded for her husband and she was pregnant. This hearing was an important opportunity to disseminate the message that wife-beating is a crime and the Magistrate spent some minutes explaining this to the public in the courtroom.

The second case was an appeal from the Local Court. The object of the complaint was not known but it is worth noting it in the light of the new supervision role of Magistrate Courts over Local Courts. The case was however adjourned because the 2 assessors from the Local Courts who must integrate Magistrate Courts in these cases were not available.

Below is a summary of the cases observed before the Magistrate circuit court in Gbangbatok.

| 5/02/2013 - Magistrate Court of Moyamba on circuit in Gbangbatok |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Type and nature of case | Parties to the case | Outcome of the case | Legal representation |
| Case 1 | Criminal Burglary and theft (2 chicken valued at 70.000 le) | Accused: male, 18 yrs Defendant: male | Adjourned to next day (absence of witness) | No |
| Case 2 | Criminal (PI) Burglary | Accused: male | Adjourned to next day (absence of witness) | No |
| Case 3 | Criminal Unlawful possession | Accused: male | Conviction (3 years of prison) | No |
| Case 4 | Criminal Domestic violence | Accused: male Defendant: female (wife of the accused) | Conviction (Fine of 100.000 leones) | No |
| Case 5 | Civil (appeal from Local Court) | n/a | Adjourned to next day (absence of assessors from Local Court) | No |
| Case 6 | Criminal Burglary and theft (bag with personal belongings) | Accused: male (pleaded guilty and is a prison escapee) | Conviction (5 years of prison) | No |
| Case 7 | Criminal Battery (stones thrown at teacher) | Accused: male, 17 yrs | The court retired in camera. | No |

EFFICIENCY

Efficiency measures how economically resources or inputs (such as funds, expertise and time) are converted to results and assesses assess how the partnership strategy has influenced the efficiency of the initiatives through cost-sharing measures and complementary activities.

§ 3.1. Cost effectiveness

The Mobile Court system in Sierra Leone is strongly dependant on international donors: 80% of the budget for mobile courts is funded by UNDP, GIZ and DFID.

The donors are funding: i) allowances of judges, magistrates and support staff (court clerk, registrar, driver), ii) fuel, iii) stationary, and  iv) transportation for witnesses.

The Judiciary contributes with, i) allocation and maintenance of vehicles, motorbikes, and  ii) salaries for judges, magistrates and support staff.

The table below tentatively compares the MC budgets of the 3 international partners, which are intervening in 3 different geographical areas (UNDP in the South, GIZ in the East and DIFID in the North)

| The financial contribution of international partners to Sierra Leone Mobile Courts (2012) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| UNDP (south) 12 months N. of itinerant Magistrate Courts: 54 N. of itinerant High Courts: 4 |  | GIZ (east) 12 months N. of itinerant Magistrate Courts: n/a N. of itinerant High Courts: n/a |  | ASJP/DFID (north) 6 months N. of itinerant Magistrate Courts: 66 n. of itinerant High Courts:2 |  |
| Activity | USD | Activity | USD | Activity | USD |
| 1. Allowances (leones) |  | 1. Allowances (leones) |  | 1. Allowances (leones) |  |
| 1.1 Magistrate Courts - 2 Magistrate@ 150.000/night - 9 support staff @100.000/night (1 court clerk, 1 registrar, 1 driver, 2 police officer, 4 prison officer) | 8.163 | 1. 1 Magistrate courts - 1 Magistrate @ 150.000/night - 3 support staff@ 50.000/night (1 clerk, 1 police prosecutor, 1 driver) | 2.506 | 1. 1 Magistrate courts - 2 Magistrate @ 200.000/night - 2 to 4 support staff@ 50.000/night ( clerk, police prosecutor, prison officer, driver) | 8.079 |
| 1.2 High Court - 1 judge @ 250.000/night - 3 support staff @100.000/night (1 court clerk, 1 registrar, 1 driver) | 2.558 | 1.2 High Court - 1 judge @ 350.000/night - 1 registrar@ 100.000/night - 2 support staff @50.000/night - 1 deputy registr@200.000/night (1 court clerk, 1 driver) | 8.358 | 1.2 High Court - 1 judge @ 300.000/night - 1 registrar@ 100.000/night - 1 clerk @50.000/night - 1 driver@50.000/night | 3.484 |
| 1.3 Coordination (5 months) - 1 coordinator@ 500.000/month - 1 driver @100.000/month | 698 | 1.3 Coordination (6 months) - 1 coordinator@ 500.000/month | 1.042 | 1.3 Coordination 3 coordinator@ 500.000/month | 2.298 |
| 1.4 JP & High Court Jurors - 6 JP@ 250.00/month. 6 months - 18 jurors@40.000/2 sittings | 2.074 | 1.4 JP - 4 JP@600.000/month | 1.251 | 1.4 JP - 6 JP@150.000/month | 1.253 |
| Subtotal Allowances: 13.493 USD |  | Subtotal Allowances: 13.157 USD |  | Subtotal Allowances: 15.114 USD |  |
| 2. Fuel | 2.673 |  | 1.333 |  | 4.800 |
| 3. Stationary and equipment | 7.658 |  | 0 |  | 2.066 |
| TOTAL BUDGET FOR UNDP | 23.824 | TOTAL BUDGET FOR GIZ | 14.490 | TOTAL BUDGET FOR ASJP/DFID | 21.980 |

It emerges from the table above that international partners should promote a better coordination of the financial aspects of their support to the MC system.  In particular the following budget lines should be given a special attention:

- Allowances for magistrates, judges, JPs and support staff are not harmonised across the country, (e.g. a JP is currently paid 600.000 in the East and only 150.00 in the South).

- The typology of support staff is not the same in the 3 provinces (e.g prison officers are only supported in the South and in the North). UNDP could further explore if 4 prison officers are required.

- Jurors are only supported in the South.

The 3 international partners agreed to harmonise allowance rates and eventual other budget lines in their respective MOUs with the Judiciary (all planned for signature in the first quarter of 2013) with the objective to ensure a stronger coordination in supporting the Judiciary, inter alia to facilitate reporting activities and promote transparency.

It appears that the Magistrate Court support staff in Moyamba (except the registrar) is not receiving their allowances in cash. The police prosecutor expressed sincere gratitude to the Magistrate for providing food and accommodation for all support staff as well as food and transport for the prisoners, so it is assumed that the amount of the perdiem for support staff is allocated to the Magistrate who then manages the funds according to the needs.

This system would need to be discussed with the Master and Registrar as it might be more appropriate, inter alia in terms of independence of the Magistrate that support staff receive their perdiem directly in cash, as is the practice in the other provinces supported by DFID and GIZ.

The consultant did not receive any complaints about the amount of the allowances, so it can be assumed that they are appropriate (except for the jurors, but this particular case is discussed in § 2.3. The Master and Registrar confirmed that circuit court perdiems were raised in 2006, because they were so low that staff refused to go on circuit and the UNDP Project Manager added that allowances were increased from the 1st to the 2nd LoA. The Moyamba Magistrate suggested that the perdiem should be paid in advance instead of upon return from a circuit session.

§ 3.2 Coordination with international partners

Circuit courts are implemented in Sierra Leone with the assistance of 3 international partners: UNDP supports the South; GIZ the East and DFID the North. Such arrangements have resulted in an effective set up that covers the whole territory of Sierra Leone. This is one of the best practices that have been developed in Sierra Leone and should be encouraged in other countries.

The different areas of intervention have similar A2J needs with some regional differences in terms of context: for example the South presents additional challenges for the lack of adequate infrastructures but is more open with regards to women rights.

The 3 international partners apply very similar models of intervention which consist in providing financial support to the Judiciary to implement the circuit courts. Out of a total of 6 magistrates who are operational in Sierra Leone to date, DFID supports 3 resident magistrates covering 10 stations, UNDP supports 2 resident magistrates covering 8 stations and GIZ supports 2 magistrates covering 4 stations.

All partners support the 3 High Court sessions on circuit (See map in annex 3).

All 3 donors are also supporting the JP (Justice for Peace), but only UNDP is supporting the jurors.

DFID is planning to support State Counsels for Mobile High Courts in the whole country and a modest legal aid fund for capital offenses.

The Southern province was the first attempt of the international community to support circuit courts. In 2006 JSDP/DFID launched the Moyamba pilot project which included a MC component and was later replicated in other provinces.

Considering that UNDP’s support to MC in the South builds on this project, it would have been expected to find stronger references to lessons learned and best practices developed during the Moyamba pilot, which were on the contrary surprisingly limited. Only one report was available from the Moyamba pilot period, which is unfortunate because such material could have been useful to establish a strong baseline.

Asked about the quality of the coordination among the 3 international partners, the Consultant Master and Registrar expressed satisfaction and confidence that “everyone knows what others are doing”.

The 3 partners have indeed established cordial and fruitful relationships and have regular individual exchanges with the Master and Registrar, but official mechanisms for the coordination of the initiative have not been created.  This set up has weakened the position of the international partners vis á vis the judiciary and hindered an harmonized approach in the support to circuit courts.

As suggested by the Irish Aid representative and the UNDP Country Director, for future initiatives to support the MC system it is advised to draft a joint strategy of intervention in the 3 provinces. Such document could inform the MOUs that each international partner will sign with the judiciary and consist in a brief description of common project management objectives and tools (e.g. baseline, indicators, amount for allowances…).

The coordination mechanism could be completed by an annual meeting to officially share and discuss with the Judiciary the results of the respective interventions.

Such a meeting could also be a starting point to engage in disseminating more widely the results achieved by the circuit courts. It has been noted that there is, particularly within the international community, some confusion and not enough awareness about the role of circuit courts in the legal system. Some persons were confused by the term mobile court, others were not aware of the existence of such initiatives.

It is therefore recommended to further engage in disseminating information about the objectives and role of mobile courts among the international community and the population.

§ 3.3 Coordination between national justice and security institutions

A special attention was given to explore how justice and security actors coordinate for an efficient implementation of circuit courts and if UNDP, or other donors, have established mechanisms to facilitate such linkages.

Police and prisons

Several key informants raised the issue that police officers represent an obstacle to the prosecution of cases because they often settle cases before they reach the court.  The Moyamba Magistrate confirmed this practice and revealed that in 2012 his court received more civil cases than criminal ones because most criminal cases are mediated by what is ironically referred to as “police courts”. For example the magistrate is aware that there are numerous traffic matters in Moyamba (cars without plates etc), but in the last 3 months he has not received a single traffic court case.

The situation is aggravated by the widespread corruption of police officers. Court Monitors reported cases of Police Prosecutors who take statements and make them disappear in order to settle the case for a bribe.

The presence of the Police Family Support Unit (FSU) is gradually increasing the rate of GBV prosecution in Sierra Leone: in Moyamba 3 rape cases were referred to the Magistrate Court in 2012.

Given the limited, although growing, number of State Counsels in Sierra Leone, the police steps in to prosecute cases before Magistrate courts. 60 police prosecutors have been trained, inter alia with the support of UNDP, and are currently serving in the whole territory.

There is a common perception that “Police prosecutors lack adequate skills and training on how to prosecute matters, they fail to perform their tasks well. Reports state that they often come to court unprepared”. This was not the case before the circuit court observed by the consultant, however improving the skills of police prosecutors remains a priority as well as increasing the number of State Counsel, which is inter alia one of the objectives of the new ASJP/DFID programme.

It is strongly recommended to set up coordination mechanisms aiming at identifying prisoners detained for long time and make recommendations for their release from custody. Such mechanisms are currently not in place: asked how his court coordinates with the Prison in Moyamba the Judge replied “we receive the list of prisoners on remand on the day of the trial”.

Police prosecutors who travel with the MC team could be encouraged to visit the police and local courts detention cells and prisons in remote locations to follow up on pretrial detention issues.

Justices of the Peace

The “Justices of the Peace” (JP) are lay persons established in article 13 of the 1965 Courts Act and repeatedly trained by UNDP in the past, who perform a role of assistance to the magistrate. They play a key role in ensuring the basic court activities while the magistrate is on circuit.

In Moyamba, JPs don’t seem to be operational: when the consultant arrived, the court was closed because the Magistrate was on circuit and it was not possible to meet any of the JPs (one died in 2012 and the second has allegedly never taken up his functions).

A discussion with the Master and Registrar should clarify the issue considered that UNDP has funding available for the salaries of the 2 JPs.

As suggested by Advocaid and Timap, it would be important to have an efficient network of JPs in the provinces to avoid the suspension of all court services when the Magistrate is on circuit. It is therefore recommended to support the re-establishment of JPs in Moyamba and ensure their training.

Local courts

The legal framework for Local Courts has been recently revised and a new Local Court act was passed in 2012, inter alia with the support of UNDP. Under the new law, Local Courts are not part of the Ministry of Internal Affairs but fall under the Judiciary, so Magistrate Courts have become in all effects their superior courts (e.g. local courts will send their monthly returns the resident magistrate).

The current interaction between the two institutions is however limited to the following aspects:

- The magistrate court decides upon appeals from the Local Courts

- When on circuit, the Magistrate uses the Local Courts courtrooms and locks-up.

Appeals to Magistrate circuit courts should be seen as important opportunities to improve the practice and jurisprudence of Local Courts, and a tool to supervise some of the common challenges of Local Courts as exorbitant fines, discrimination of women, overstepping of their jurisdiction.

Appeals are still very few although the Magistrate reported that after his court became mobile, the number of appeals from the Local Court increased.

In 2012 only 2 Local Court cases were appealed to the Magistrate in Moyamba. One is a case of abusive language that has been pending before the Magistrate for almost a year. The magistrate explained that the main reason for this delay is that the court has to be integrated by 2 Local Court assessors, which is often problematic as they are not paid. The Local Court supervisor added that sometimes appealing to a Magistrate Court is a strategy to delay the case for parties who do not want to pay the local courts fees and fines.

Finally some issues were highlighted with regards to the limitations of the two jurisdictions and in particular the fact that Local Courts occasionally, and in contravention of the law, decide upon rape cases instead of referring them to the Magistrate Court. It appears however that these cases have become less frequent after an intensive awareness raising campaign.

UNDP has allocated a consistent budget to support Local Courts until 2014; within this framework it is recommended to include a special focus on promoting coordination mechanisms and a better communication between Local Courts and Magistrate Courts on circuit.

§ 3.4 Challenges

All interviewed persons were asked to identify the main challenges for the Mobile Court system; most answers have been illustrated in the previous paragraphs, but are summarised in the table below for easy reference.

The majority of the challenges (legal representation, number of magistrates, case management system, adjournments) are common to the entire justice system in Sierra Leone. A second group of challenges is also recurrent across Sierra Leoneans jurisdictions, but is exacerbated in remote areas where mobile courts intervene (interpretation, witnesses, out of court settlements). The remaining challenges (in bold) are specific to the mobile court system and are mainly related to logistical matters (MC schedule, transportation).

The most cited challenge was the absence of witnesses in court and the related issue of high adjournment rates, followed by the difficulties that court users have in understanding the procedures due to language barriers and lack of rights awareness.

Some of the identified challenges are currently being addressed by UNDP (witness transportation programme and Saturday Courts); by the Judiciary (recruitment of 3 new magistrates) and by DFID (support to recruit additional State Counsels)

| CHALLENGE | MENTIONED BY |
| --- | --- |
| Witnesses do not appear in court | Advocaid, DFID, GIZ, State counsel, FSU, police prosecutor, court monitors, HC judge, magistrate, IRC, CARL |
| Interpreters are not available/court users do not understand legal procedures | Advocaid, DFID, TIMAP, OHCHR, Irish aid, FSU, Moyamba HR committee, Police prosecutor, court monitors, Namati |
| Legal representation is not available | Advocaid, Master and Registrar, OHCHR, bailiff, Moyamba HR committee, judge, magistrate |
| Insufficient number of magistrates/ magistrates on circuit are overloaded | Master and Registrar, DFID, FSU, Mombaya HR committee, court monitors, CARL, magistrate |
| The MC schedule is unpredictable | Advocaid, Timap, FSU, HC jurors, MC user, court monitors, |
| Cases are settled outside court (by police/traditional chiefs) | UNDP, State counsel, Magistrate, Police prosecutor, judge HC, court monitors |
| Vehicles for prison/magistrate/police prosecutors on circuit are not available and roads are in bad conditions | Master and Registrar, HR committee Moyamba, magistrate, Prison director, police prosecutor |
| Frequent adjournments | Advcoaid, DFID, CARL, Namati |
| Court statistics are not available | DFID, GIZ, UNDP |
| Lack of skills to deal with SGBV cases | IRC, Namati |
| Corruption of police | Court monitors, lawyer |
| Political interference | Court monitors, lawyer |
| Complex and outdated legal procedures | CARL, lawyer |
| MC are not frequent enough (pretrail detention issues) | NHRC, Namati |
| Jurisdiction of Local Courts and magistrates is not respected | DFID, Timap |
| Sureties to stand for bail are not available | FSU, court monitors |
| Stationary and legal documentation for MC are not available | Registrar Moyamba |
| Insufficient number of State Counsels | Judge HC |

§ 3.5. Good practices

The support to MC in Sierra Leone has developed a series of best practices that are described below as suggestions for eventual replication in other UNDP County Offices.

An extended network of court monitors

UNDP is supporting a network of court monitors active in the 3 provinces and structured under a coalition of CSO. The consultant met with 7 court monitors representing some of the 19 CSO active in the Southern province. They are monitoring local courts, magistrate courts and High Courts. Quarterly reports are sent to UNDP with indication of the number and typology of monitored cases as well standard indicators on the fairness of trials. Court Monitors are members of the local communities and therefore facilitated in assisting litigants to understand legal procedures. To be noted that UNDP is planning to support selected court monitors to attend the TIMAP training to become certified paralegals.

This is an excellent initiative that, although still in its pilot phase, encourages the civil society to play an important oversight role on the judicial system and contributes with useful information on the court caseload, which is particularly important in a context where official statistics are limited.

Courts monitoring reports are being improved while UNDP is building the reporting capacities of the monitors: one of the objectives of 2013 is to ensure that data from courts on circuit will be disaggregated (currently it is unclear if case was observed in a circuit or home court).

As an influence of the practices introduced by the Special Court for Sierra Leone, court monitoring is quite developed in Sierra Leone so several NGOs (e.g. CARL and Namati) are engaged in this activity. A greater coordination among these different actors could eventually be promoted by UNDP with the objective to share best practices, harmonize approaches and better advocate for changes in the judicial system.

A good coordination among international partners

As illustrated in § 3.2, circuit courts are implemented in Sierra Leone with the assistance of 3 international partners. Such arrangements have resulted in an effective set up that covers the whole territory of Sierra Leone.

The international partners are in the process of strengthening the coordination by harmonizing approaches in particular with regards to allowances and performance indicators.

An adequate and commonsensical budget

As illustrated in § 3.1, UNDP supports the payment of allowances for judges and court staff that are in line with the market and perceived as fair. The same observation can be made for the witness transportation programme.  This is an effective approach that avoids the negative side effects observed in other countries, where travelling on circuit has become a business for witnesses and judges. In addition it is important to continue ensuring that the Judiciary contributes to the budget by providing vehicles for the circuit courts and additional Magistrates.

The ongoing harmonization of allowance rates among international partners supporting MC, will be an additional added value.

An efficient use of courtrooms for circuit hearings

As illustrated in § 1.1, when on circuit, the Magistrate uses the Local Courts’ courtrooms and locks-up, and the High Court used the Magistrate Courts’ premises, which in the Southern provinces have all been recently rehabilitated. Lower courts are accommodated in alternative premises, such as the community hall, during the session of the superior court. This set up offers a cost effective solution for courts on circuit to have an adequate working space without interrupting the ordinary activities of residential courts.

§ 3.6. Lessons learned

The following lessons learned can be drawn from the mobile court experience in Sierra Leone:

- Supporting MC should not be limited to the supply side of justice (allowances, fuel and stationary for circuit courts) but should include interventions targeting the demand side of justice. Such interventions should aim at raising awareness among the population about the role and objectives of a MC and establish mechanisms to assist vulnerable groups to claim their rights before MC and understand the legal procedures.

- Some of the challenges faced by MC are a reflection of those that affect more generally the justice system, so eventual solutions would require a more comprehensive justice sector reform intervention (e.g. outdated legal framework, lengthy preliminary investigations…).

- Mobile courts have been an efficient stop-gap mechanism to assist the government in reestablishing the formal justice system after the civil war and temporarily respond to the chronic shortage of magistrates.

- The weak monitoring system (lack of SMART indicators and court statistics) has not allowed measuring progress towards set targets and was a missed opportunity to take eventual corrective measures.

SUSTAINABILTY

Sustainability measures the extent to which benefits of initiatives continue after external development assistance has come to an end.

The evaluation findings suggest that some of the conditions for the MC system to continue without the support of the international community are in place, in particular:

- The MC system in Sierra Leone is rooted in the judicial system and exists since 1965. The Master and Registrar considers MC as priority and specified that they are “a permanent measure, but not on the scale as it is today”

- Since 2006, when the international partners started to support MC, they have been implemented independently under the lead of the Judiciary: running MC is therefore an institutionalised process that is entirely implemented with local capacities.

- The financial support provided by the international community for court staff allowances is in line with the local market, which increases the chances that the initiative will continue.

The lack of financial and human resources remains however the main obstacle to the continuation of the initiative by the Judiciary; which is further complicated by the fact the government is currently giving priority to address urgent issues in other areas, as health. Some international partners have expressed concern that the Judiciary is becoming dependent on international aid to organize the MC. For example in the Northern province, circuit court sessions were suspended during the gap period between the closure of the JSDP project and new ASJP project.

Another aspect that should be considered in identifying the moment for withdrawal of international support, is that a consistent M&E framework is not yet in place and there has been a lack of joint ownership of M&E processes between the Judiciary and donors. The new LoA between UNDP and the Judiciary should be an opportunity to strengthen the monitoring component in addition to further building the capacities of judicial authorities and staff in specific areas, such as the prosecution of SGBV crimes.

Considered that all 3 international partners are in the process of renewing their MOU with the Judiciary to support MC and that UNDP is entering the 4th year of support to the MC system, it would be an appropriate moment to promote a discussion about how long the support should continue and define an exit strategy.  The outcomes of such consultations could be reflected in the joint strategy to support MC, described in § 2.1.

Finally it’s worth mentioning that some NGOs as Namati are promoting the sustainably of their interventions by encouraging the participation of rural communities in building the premises needed for project activities.

This approach was also suggested in a JSDP-commissioned report, which stated “There was overwhelming agreement among the communities that because of the great benefit the communities are deriving from the itinerant court, they too should bear some of the responsibilities. They suggested providing accommodation and feeding for the court team, and a building to house the chamber of the magistrate”.

These community based approaches could be explored, but to succeed they would need to be complemented by activities aimed at bringing circuit courts and their clients closer and improving the confidence of the population in the justice system.

IMPACT

Impact measures changes in human development and people’s well-being that are brought about by development initiatives, directly or indirectly, intended or unintended

The absence of impact indicators and the limited scope of the present evaluation, makes if difficult to illustrate the changes produced by the MC system for the population (rights holders) and the judicial authorities (duty bearers). Some indicative findings based on the opinions of a limited number of interviewed persons will however be presented below.

§ 5.1. Changes for the population and the justice actors

Changes for the population

It is widely recognized that MC are an opportunity to increase access to justice for the rural population because, as often mentioned during interviews, “MC bring justice to your doorstep”. Court monitors further emphasized that people from remote villages don’t have to experience, as in the past, the bewilderment of arriving in a big city as Moyamba to sort out their disputes. In addition the economic burden of going to court is reduced for litigants.

According to the Moyamba Human Rights Committee and the Magistrate, the presence of MC has reduced the crime rate in the district, as sentences are a powerful deterrent for potential offenders: “people fear the formal court, so they commit fewer crimes”.

The Principal State Counsel and the Timap representative recalled that with the presence of MC “people get to see justice in action” and they have the opportunity to better understand what a formal court is.

However, the interviews with 5 parties to the cases and the observation of Magistrate and High Court sessions, revealed that all court users had extremely limited awareness of their rights and understanding of court procedures, also because of strong language barriers. The Moyamba Magistrate is making efforts to explain court procedures to the population, but for a significant impact his efforts should be complemented by paralegals and lawyers.

Despite the Magistrate reported that court users are less intimidated and have more confidence in MC than in the past, this was not observed by the consultant while interviewing some of the parties to the cases.

Changes for justice actors

The presence of MC has strengthened the role of the formal justice system in the provinces where traditional justice is prevalent. Mobile courts have been an efficient stop-gap mechanism to assist the government in reestablishing the formal justice system after the civil war and temporarily address the chronic shortage of magistrates.  Several informants referred that the number of cases has increased since the courts are travelling on circuit; in addition according to the Master and Registrar the backlogs in the districts have been greatly reduced.

The Magistrate mentioned that the prosecution is currently facilitated in accessing the witnesses and processes have become speedier.

Finally it’s worth noting that court monitors have contributed to improve the impact of MC as their presence has reduced arbitrary behaviors by the judges, which were common in the past. The presence of court monitors in courts is now accepted and their position is stronger: for example they are allowed to take notes, which was not the case in the past.

§ 5.2 The impact of mobile courts on the prosecution of international crimes

One of the objectives of the present evaluation is to analyze eventual contributions of the MC system to transitional justice mechanisms in the light of UNDP’s integrated approach to transitional justice, which focuses on developing the capacities of national institutions to investigate and prosecute international crimes in complementarity with the ICC.

The Special Court for Sierra Leone is currently concluding its mandate and has achieved the prosecution of 8 high ranking officials.

Several legal and political obstacles have precluded the national justice system and eventually the circuit courts to complement the Special Court in prosecuting atrocities committee during the conflict. Firstly the amnesty granted by the Lomé Peace Agreement for the crimes committed during the conflict was a bar to prosecution before the national courts.  Secondly the Special Court was not designed to be complemented by national courts as the process was fully international; on the contrary some authors believe that “it may have even had a discouraging effect on national war-related prosecutions in Sierra Leone”. One of the reasons for limiting national prosecutions was that the national justice system was not considered able to deliver fair trials and had no experience in handling international crimes and gross human rights violations.

Representatives of the Special Court pointed out that the dualist nature of Sierra Leone’s legal system implies that international norms have to be domesticated before application in national jurisdictions; considered that the country has ratified but not yet incorporated into domestic law the Rome Statue, it appears that Sierra Leonean courts are not yet enabled to prosecute war crimes, crimes against humanity and genocide.

PART III: CONCLUSIONS AND RECOMMENDATIONS

6. CONCLUSIONS

Despite the difficulties of intervening in a country where the traditional legal system is strongly prevalent, UNDP’s support to mobile courts in Sierra Leone is achieving results that are progressively improving.

The main findings for each evaluation criteria are summarized below.

relevance

Mobile courts are aligned with national justice sector strategies and have been an efficient stop-gap mechanism to assist the government in reestablishing the formal justice system after the civil war and temporarily respond to the chronic shortage of magistrates.  Now that the country is entering a development phase the process of institutionalizing mobile courts should continue with a stronger focus on the quality of justice services and in complementary with a network of resident magistrates in each district.

Circuit courts should be more responsive to the needs of the population, inter alia by ensuring that language is not a barrier to the adequate participation of litigants in the proceedings and that people receive timely information about the arrival of the mobile court in their village. Mobile courts are gradually contributing to translate into practice the recently adopted laws on the protection of GBV victims, although these procedures still need to be improved. Special measures to protect vulnerable groups during court proceedings are only in place for juveniles.

Mobile courts have been supported in full respect of the principle of national ownership and were found to be relevant by partners and other key stakeholders.

effectiveness

There is clear evidence of improvement in the planning of the initiative, but monitoring remains a major concern, mainly due to the lack of court statistics and a shared vision on monitoring approaches between donors and the Judiciary. There is however a definite commitment from the Judiciary to define jointly with the 3 international partners a common monitoring framework, with a particular focus on the improvement of court statistics.

The target of 50 Magistrate and 4 High Court circuit sessions in the south has not yet been achieved. The Magistrate Courts on circuit record an indicative number of 972 received and 568 disposed cases during the support of UNDP, which indicates an acceptable 58% rate of case disposal and a successful 12% increase in the number of cases received under the 1st and 2nd LoA. The High Court on circuit achieved a disposal rate of 52% with 375 received cases and 198 disposed cases.

The quantitative results appear satisfactory in a context where traditional system is strongly prevalent, but the quality of the mobile court services could be improved, in particular with regards to the following aspects:1) illegal pre-trial detention for remandees waiting for circuit courts to arrive; 2) lack of lawyers and interpreters to assist court users; 3) high adjournment rates due to the absence of witnesses in court; 4) special measures to protect SGBV survivors in court proceedings; and  5)  logistical

improvements, such as the prompt communication of the arrival of circuit courts and the regularity of its schedule, transportation for the MC team.

efficiency

The mobile court system is dependent on international donors for 80% of its budget, the remaining 20% being an in kind contribution from the Judiciary. Allowances (the highest budget line), are aligned with the local marked and perceived as fair.

The coordination with other international partners (GIZ and DFID) has achieved the exemplary result of ensuring circuit court on the whole territory of Sierra Leone. The coordination is being strengthened with the development of common monitoring tools and a harmonized allowance policy. On the contrary coordination among justice and security actors appear weak and no formal mechanism to promote linkages seems in place.

The initiative has developed some best practices, in particular a growing network of court monitors and an effective use of courtrooms.

sustainabilty

Some of the preconditions for the MC to continue without international support are in place, in particular the fact that they are implemented independently under the lead of the Judiciary and having recourse to only local capacities.

The lack of financial and human resources remains a strong obstacle and allows to conclude that the Judiciary’s reliance on donor support will continue for some time. Considering that UNDP has been supporting the initiative since 2010, an exit strategy should be defined in cooperation with the Judiciary. Meanwhile the Judiciary should advocate for additional funds in the national budget and UNDP should provide assistance to improve key aspects of the intervention, with a particular focus on monitoring activities.

impact

Key informants reported reduced crime rates in the villages where circuit courts travel and pointed out the fact that litigants and their families are relieved from the economic burden of travelling to courts.

However, due to the lack of specific measures to assist court users in claiming their rights (legal aid, interpretation), the impact of mobile courts on the population has not been as significant as it could have been. Mobile courts have yet had a limited, although growing, impact on increasing legal awareness among the rural population and reestablishing the confidence in the formal justice system.

The impact of mobile courts has been positive for the Judiciary.  The role of the formal justice system in remote areas has been strengthened, in particular by making the courts known to the population, which is a successful achievement in a country where traditional justice is strongly prevalent. Circuit courts have indirectly addressed the issue of the chronic shortage of Magistrates and backlogs in the districts have been cleared.

Due to legal and political obstacles, no war-related prosecutions were initiated by the national justice system, so circuit courts did not have the opportunity to impact on transitional justice.

7. RECOMMMANDATIONS

The following recommendations stem from the findings illustrated in the previous paragraphs and are directed at UNDP and the Judiciary.

► Strengthen gender and SGBV mainstreaming

- Encourage mobile courts to play a more active role in implementing the recently adopted laws on the protection of GBV victims;

- Ensure that mobile court hearings of GBV cases are held in camera, as provided for by the 2012 Sexual Offenses Act;

- Organize trainings for judicial actors aiming at strengthening the capacities to interview GBV survivors and promote the application of protection orders in domestic violence cases;

- Disseminate best practices and landmark cases from the Saturday Courts as widely as possible within the legal community and establish linkages between the circuit courts and the Saturday Court in Bo.

► Improve planning and monitoring

- Ensure that all planning tools include SMART indicators that are disaggregated by gender and harmonized with the court statistics provided by the judiciary on quarterly basis;

- Improve baseline information, in particular with regards to the needs of the population;

- Adopt, jointly with GIZ and ASJP/DFID, a standard template to collect basic court statistics and eventually a case management database;

- Ensure the planned recruitment of a UNDP supported Monitoring and Reporting officer at the Judiciary for a period of 6 months.

► Reduce pre-trial detention rates

- Ensure that the High Court travels on circuit 4 times per year, as provided by the Criminal Procedure Act.

- Ensure the accountability of mobile courts for illegal detentions, for example by encouraging police prosecutors and State Counsel travelling on circuit to visit the detention centres/prisons and follow up on pre-trial detention cases.

- Include in the planning tools a specific indicator to measure the impact of mobile courts on pre-trial detention.

► Promote complementary activities targeting the demand side of justice

- Continue to contribute to the debate on the implementation of the recently adopted Legal Aid bill, to inter alia advocate for the application of the future free legal aid scheme to the mobile court system;

- Explore the opportunity of re-establishing a UNDP funded legal aid scheme and/or support a few lawyers to establish their practice in some key districts, with the specific objective to support courts on circuit and within the framework that is being developed by the Legal Aid Board;

- Support a network of community-based paralegals to raise awareness among the population about the role and objectives of circuit courts and assist lawyers with witness tracking services.

- Advocate for the use of Krio in Magistrate Courts and/or the provision of additional interpreters

► Reduce adjournment rates and promote the presence of witnesses in court

- Continue to support the UNDP programme to reimburse travel expenses for witnesses of the Saturday Court and clarify the modalities and the criteria to extend the service to circuit courts.

- Include in future statistics from the Judiciary and planning tools a specific indicator about court adjournment rates.

► Improve communication

- Ensure that the population and the parties to the cases are informed in a timely manner about the arrival of the circuit court and ensure that the schedule is respected.

- Engage in disseminating information about the objectives, role and achievements of mobile courts among the international community.

► Continue to promote the international partnership

- Agree to a joint UNDP/GIZ/DFID strategy for the support of mobile courts in the 3 provinces;

- Finalise the harmonisation of allowance policies among the 3 international partners

- Disseminate jointly the results achieved in the 3 provinces in order to illustrate regional trends.

► Continue to support court monitors

- Promote a closer coordination among the different national NGOs that provide court monitoring services with the objective to share best practices, harmonize approaches and better advocate for changes in the judicial system.

- Ensure that court monitors reports present disaggregated data about courts on circuit and eventually extend their mandate to High Courts.

- Continue to explore the possibility of supporting UNDP Court monitors to attend the training required to become certified paralegals, as provided for by the legal aid bill.

► Support the Judiciary’s strategy to complete the institutionalization of circuit courts

- Support the strategy of the Judiciary to develop Magistrate circuit courts into a permanent institution, (more resident Magistrates covering a reduced number of circuit stations) by providing assistance to promote the legal profession, sustainably improve the conditions of service for Magistrates and recruit additional ones.

- Promote a discussion about the timeline for withdrawal of international support and define an exit strategy.

► Additional Areas

- Improve the logistical aspects of the initiative, such as the introduction of stenographers or modern transcription facilities; the creation of a library with basic laws; the improvement of transportation and accommodation for judges and magistrates on circuit

- Re-establish the 2 JPs in Moyamba and ensure their training.

- Continue to support Local Courts and  add a special focus on promoting coordination mechanisms and a better communication between Local Courts and Magistrate Courts on circuit.

ANNEX 1: Reviewed literature

Consulted documents are available on the shared folder created on Dropbox for the present evaluation:

https://www.dropbox.com/sh/kn177z4dddfvgyp/AbtqXNN4Ai

1. Articles

- Betty Alimamy Sesay, “Filling the Gaps in the Justice Sector: More Resident Magistrates Needed in Sierra Leone”, CARL, 2011

- Braima Koroma “A cost benefit analysis of itinerant courts in the Moyamba district”, 2008

- Caroline Roseveare “Sierra Leone access to justice for survivors of sexual and domestic violence” IRC/Timap,  2012

- Centre for the Study of African Economies, Oxford University “Timap Criminal Justice Pilot: Baseline Evaluation Report”, 2010

- Clare Castillejo, “Building Accountable Justice in Sierra Leone”, Friede 2009

- Clare Castillejo, “Strengthening women’s citizenship in the context of state-building: the experience of Sierra Leone”, Friede 2008

- Commonwealth Human rights Initiative, “In pursuit of justice: a report on the Judiciary in Sierra leone”,2002

- Namvula Rennie, JSPD, “Silenced Injustices in Moyamba District”, 2006

- Pamela Dale  “Access to Justice in Sierra Leone: A Review of the Literature” World Bank’s Justice for the Poor program , May 2008

- Peter Albrecht “Betwixt and between – chiefs and reform of Sierra Leone’s justice sector” DIIS Working Paper, 2010

- Resolve Group “ The feasibility of a legal aid system in Sierra Leone”, 2007

- Sheku Koroma and John Shangai Koroma “Addressing the Issue of Interpretation in District Magistrate Court in Sierra Leones”, CARL, 2006

- Sigall Horovits “Sierra Leone: interaction between national and international responses to the mass atrocities”, 2009

- Varvaloucas, Koroma, Turay and Siddiqi “Improving the justice sector: law and institution building in Sierra Leone”, 2012

- World Bank, “Sierra Leone: legal and judicial sector assessment”, 2004

- UNIPSIL/OHCHR, “The situation of detention in Sierra Leone”, 2012

2. Legislation and other documents

- ASJP/DFID, Loa for itinerant courts, 2011

- Auditor General report, 2013

- JSDP, Inception Report, 2005

- JSDP, Justice sector survey, 2008

- JSDP, “Criminal case management handbook” 2006

- Judiciary of Sierra Leone, Annual reports on itinerant courts, 2010, 2011

- Judiciary of Sierra Leone, Justice Sector Reform Strategy and investment plan II,  2011-2014

- The courts Act, 1965

- The criminal procedure Act, 1965

- The domestic violence Act, 2007

- The sexual offences Act, 2012

- UNDP Project document “Access to justice is Sierra Leone”, 2011

- UNDP, annual report, 2011

- UNDP, court monitors reports, 3rd quarter, 2012

- UNDP, LoA to support mobile courts, 2010 and 2012

- Universal Periodic Review - Sierra Leone (Compilation of UN information), 2011

ANNEX 2: List of interviewed persons

- Abdul Tucker, Bailiff - Magistrate court of Moyamba

- Alie B. Sesay, Rule of Law Officer - UNDP

- Andrew Mondeh, Investigator -  Police Family Support Unit (FSU).

- Charles Nbowe, Executive director - Dignity now (court monitoring CSO)

- Christopher Will Project Manager, Rule of Law and Justice Programme - GIZ

- Daniel Harding, Chairman - Human Rights committee of Moyamba

- Deanne Evans, GBV programme coordinator - IRC

- Emmanuel S. Cole - head of High Court jurors ( meeting attended by 5 jurors)

- Fabundeh Ansumana, Human rights Officer – National Human Rights Commission

- George Amorat, Deputy prison director - Prison of Moyamba

- George Harding, Local Court supervisor – Local Court

- George Thomson, judge – High Court on circuit in Moyamba (meeting attended by the State Counsel and Registrar)

- Ibrahim Tommy, Executive director - Centre for accountability and the rule of law (CARL) .

- Interview with 5 parties to cases (3 women and 2 men)

- James Nunan, A2J Project manager - UNDP

- Julia Sarkodie-Mensah, Master and Registrar - Judiciary

- Lars Andersen, Chief of Outreach and Public Affairs - Special Court for Sierra Leone

- Lebbie Human Rights Officer - UNIPSIL/OHCHR

- Mark Aiken Justice Advisor, ASJP - DFID

- Matilda Anthoney, Line Manager - Police FSU

- Meeting with 5 Court Monitors

- Mia Seppo, UNDP Country Director

- Michal Kahn, Chairman – Local Court

- Mohammad Abchir, DCDP - UNDP

- Monfred Sesay Principal State Counsel - Ministry of Justice

- Patrik Johnbull, Legal Aid lawyer – Center for access to justice and human rights

- Prince K. Kallon, Coordinator - Human rights Youth Coalition (court monitoring CSO)

- Rakel Larsen, ROL officer - UNDP

- Rosina M’balu Mahoi, child protection specialist - UNICEF

- Sabrina Mathani, Executive Director - AdvocAid

- Sahr Kekura, Magistrate on circuit in Gbangbatok (meeting attended by registrar, police prosecutor and prison officer) – Moyamba Magistrate Court

- Simeon Koroma,  Director - TiMAP for Justice

- Sinead Walsh, Charge d’affaires, Irish aid, Embassy of Ireland

- Sonkita Conteh, Director - Namati

ANNEX 3: Map of circuit courts in Sierra Leone

ANNEX 4: Chief Justice Order for the appointment of High Court circuit sessions

ANNEX 5: Evaluation Matrix

| Evaluation of UNDP support to mobile courts arrangements in post-conflict situations EVALUATION MATRIX |  |  |  |  |
| --- | --- | --- | --- | --- |
| 1. RELEVANCE |  |  |  |  |
| questions & sub-questions |  | data sources |  | data collection method |
| Q.1.1. To what extent do the mobile courts’ support interventions respond to the priorities outlined in national strategies? - What is the legal basis for implementing mobile courts? - Are a national strategy and a national budget available for MC? - Is there an MOU between UNDP and the Judiciary/MOJ to support mobile courts? - Has the Judiciary implemented MC without the support of international donors? If so, what were the results? - How does the country legal system (civil/common law, pluralistic..) influence mobile courts arrangements? |  | - National legislation - National Justice Sector strategies - MOU between UNDP and Judiciary |  | - Online research - Request CO/HQ - Interviews: judicial authorities.. |
| Q.1.2. How well do programming and implementation modalities match the needs of the population and national partners? - What influenced UNDP’s decisions on where, how and to what extent to engage in supporting mobile courts? Was the decision discussed with relevant stakeholders? - Was a needs assessment conducted before launching the mobile court intervention? Was the Judiciary involved? - Which are the most vulnerable groups in the country? Are they targeted by mobile courts interventions? - To what extent were issues related to the restorative v. retributive conception of justice in remote areas taken into consideration? |  | - Needs assessment or baseline analysis reports (by UNDP, Judiciary or other actors) - research reports - reported opinions from key informants |  | - Online research - Request CO/HQ - Interviews: MOJ, judicial authorities, UNDP staff.. |
| Q.1.3. What was the relevance of mobile courts assistance for other priorities of UNDP Rule of Law programmes and the cross-cutting areas of gender equality, capacity building and national ownership? - Were synergies established between MC and other components of UNDP Rule of law programmes? (Legal aid, Paralegalism, Policing, …), If so, what was the added value of a mobile court component? - How was gender mainstreamed across the mobile court intervention? - Have mobile courts interventions utilized existing local capacities of rights holders and duty bearers to achieve their results? How were their capacities strengthened? |  | - UNDP documents: CPAP/UNDP project documents /BCPR field visits reports/ BCPR integrated projects/ evaluation reports… - reported opinions from key informants |  | - Request CO/HQ - Interviews: UNDP staff.. |
| 2. EFFECTIVENESS |  |  |  |  |
| questions & sub-questions | data sources |  | data collection method |  |
| Q.2.1: What model of MC emerges from the CO practice? - What is the composition of the MC? How are the judges/prosecutors/lawyers selected to participate? - What is the jurisdiction of mobile courts with regards to subject matters, litigants and geographical coverage? - What is the average distance between the permanent tribunal and the mobile court? - How long does the mobile court session last and how often does it visit the same area per year? - To what extent have interventions addressed transitional justice process and impunity of international crimes? | - Databases /statistics - Map of the judiciary - project document - Reported opinions from key informants |  | - Interviews: UNDP staff, Ministry of Justice… - Request CO/HQ |  |
| Q.2.2: What results (quantitative and qualitative) were achieved in each phase of mobile court interventions? phase 1: before mobile court sessions - What support did UNDP ensure to the logistical aspects of mobile courts (transport, courtroom, accommodation, office and legal material for judges on circuit)? - Were the population and local authorities informed about the arrival of the mobile court in an appropriate and timely manner? - Were investigations in criminal cases effectively conducted? Were eventual pretrial detention issues addressed? Were linkages between Prosecutors and Police promoted? - Were notifications of procedural acts issued and communicated in a timely manner? - Were specific trainings for mobile court staff organized? (knowledge of the local culture and traditional law practices, gender/child rights…) phase 2: during mobile court sessions - How many and what cases received free legal aid from a lawyer? Was the Bar Association involved? - How many witnesses appeared before the mobile court? Which measures were in place to protect witnesses and victims, and in particular SGBV victims? Is there a “travel cost reimbursement program” to assist witnesses and victims to appear in court? - Were hearings translated into local languages? - How many people participated in the public hearings? Were they assisted in better understanding the hearings? - Were mechanisms in place to ensure the security of mobile court staff? - Were the proceedings adequately recorded? Are there higher rates of adjournment for MC proceedings? phase 3: after mobile court sessions - How many judgments were enforced (criminal/civil)? - Were mechanisms in place to enforce prison sentences in the absence of local prison facilities? - What is the rate of appeal of MC decisions? - Are there mechanisms in place to ensure the communication of MC decisions to the rest of the justice chain to ensure decision enforcement and information sharing? - Were parties assisted to collect eventual financial compensation that they were awarded? - If alternative sanctions to imprisonment were applied (community services), was a follow up ensured? | - Project performance indicators - Databases/ statistics - UNDP quarterly and annual reports - MC reports - Judiciary reports - Research studies - Reported opinions from key informants |  | - Request CO/HQ - Interviews: Ministry of Justice, judicial authorities, police, prison staff, traditional authorities, lawyers, other implementing partners, UNDP staff.. - Focus group with beneficiaries |  |
| Q.2.3: Were planning and monitoring procedures appropriate to achieve results and ensure accountability? - Is a clear results framework with SMART indicators, targets and risks analysis available? - What monitoring tools are available? Are court statistics available? - Are national partners involved in monitoring activities? - Is there a system in place for trial observation? - Is feedback from mobile court users collected to assess needs and adjust services accordingly? - How is the quality of mobile court judgments assessed? - Are landmark cases identified and disseminated? | - Project document and results framework - UNDP quarterly and annual reports - evaluation reports of broader ROL projects - reports drafted by MC staff |  | - Interviews: UNDP staff, Ministry of Justice… |  |
| Q.2.4: What were the reasons for achievement and non-achievement of results and the factors contributing or hindering their achievement? - How can UNDP build upon or replicate the achievements? - How can the shortcomings be overcome? - What are the lessons learned? - Were there any unanticipated events, opportunities or constraints? - What could be done differently in the future? - What were the unintended results (positive/negative) | - Reported opinions from key informants - UNDP quarterly and annual reports - Judiciary reports |  | - Interviews: UNDP staff, Ministry of Justice, Mobile court staff… |  |
| 3. EFFICIENCY |  |  |  |  |
| questions & sub-questions | data sources |  | data collection method |  |
| Q.3.1: Has the MC intervention been implemented within its cost estimates and is it cost-effective? - Were sufficient resources allocated for mobile courts’ support interventions? Is the national government contributing to the budget for MC? - Are the expenditures for MC proportionate to the number of cases and broader indicators as the number of participants in public hearings? - What are the costs per trial? would it be cheaper to build court rooms and provide staff in remote areas? - Are perdiems for judges and MC staff in line with local market? | - Resource frameworks, budgets, AWP, - Reported opinions from key informants - UNDP quarterly and annual reports - MOJ reports |  | - Interviews: UNDP staff, Ministry of Justice.. - Request CO/HQ |  |
| Q.3.2: Has UNDP promoted a partnership strategy at the global, regional and national level to implement MC interventions? If so, was it effective and appropriate? - What was the nature and added value of these partnerships? - Did such partnerships promote an integrated approach aiming at addressing complementary aspects of mobile courts interventions (legal awareness for the population; support to police and prisons; linkages with traditional justice …) - Were UNDP’s comparative advantages perceived/ interpreted and were these reflected in the division of responsibilities? - If the Judiciary received specific support for mobile courts interventions from several donors, were the initiatives efficiently coordinated? | - UNDAF - partnership agreements/MOU - Reported opinions from key informants |  | - Interviews: UNDP staff, Ministry of Justice, Protection cluster, UN agencies and INGOs, civil society organisations, universities… - Request CO/HQ |  |
| Q.3.3: What effect did UNDP technical assistance and management arrangements have on the quality of mobile courts interventions in terms of programming, delivery and monitoring for results? - Were the project management structure and the administrative modalities appropriate and effective? - Was the support from UNDP staff effective and timely? | - Project document and monitoring reports - Reported opinions from key informants |  | - Interviews: UNDP staff, Ministry of Justice, Mobile court staff… |  |
| Q.3.4: Did mobile courts interventions focus on the set of activities that were expected to produce significant results? - Are all the planned activities implemented? Should additional activities be planned? - Are mobile courts ensuring the implementation of the international standards of fair trial? Would some of the fair trial rights need more attention? | - Project document - Reported opinions from key informants - international standards on fair trial |  | - Interviews: UNDP staff, Ministry of Justice, other implementing partners… |  |
| 4. SUSTAINABILITY |  |  |  |  |
| questions & sub-questions | data sources |  | data collection method |  |
| Q.4.1: To what extent were sustainability considerations taken into account in the design and implementation of interventions? - Were exit strategies for mobile courts interventions appropriately defined and implemented? - What steps were taken to ensure that the effects of the intervention would continue beyond UNDP’s support? - Has the development of partnerships contributed to the sustainability of results? | - Project document - annual reports - Reported opinions from key informants |  | - Interviews: UNDP staff, Ministry of Justice, Judiciary other implementing partners… |  |
| Q.4.2: How were different stakeholders engaged designing, monitoring and implementing mobile courts interventions? - Has UNDP promoted and facilitated the coordination among local justice and security actors (Police, Prisons, Traditional justice, local authorities…) ? - Have linkages been established between mobile courts and ADR mechanisms? (for example to establish mandatory court annexed mediations). | - Project document - annual reports - Reported opinions from key informants |  | - Interviews: UNDP staff, Judiciary, Ministry of Justice, Police, Prison staff, traditional authorities, local authorities… |  |
| 5. IMPACT |  |  |  |  |
| questions & sub-questions | data sources |  | data collection method |  |
| Q.5.1: What changes did mobile courts interventions bring for rights holders in terms of making justice more accessible to them? - Have MC interventions promoted a better confidence in the justice system? Is there a perception that impunity is being addressed? - Are vulnerable groups in remote areas more aware of their rights and do they have a better understanding of the formal justice system? - Do MC provide an alternative to traditional justice? | Reported opinions from key informants |  | Focus groups with beneficiaries and interviews with their lawyers / Eventual users perception survey |  |
| Q.5.2: What changes did mobile courts interventions bring for duty bearers in terms of making them more effective in responding to justice need of conflict affected populations in remote/underserved areas? - What is the impact of MCs on ordinary courts? (in terms of case backlog, promoting case management systems, costs) - What was the impact on ordinary courts of assigning judges and other judicial staff to mobile courts? - Have MC interventions led to the re-establishment of the justice system eventually in conflict-affected areas? - Have MC interventions promoted closer coordination among the different actors in the justice chain? - Have judicial authorities acquired additional skills and knowledge in terms of managing a MC intervention? | Reported opinions from key informants |  | Interviews: Judicial authorities and Ministry of Justice, Police, Prison staff, traditional authorities |  |

ANNEX 6 Terms of reference

| ### EVALUATION CONSULTANT: SUPPORT TO MOBILE COURT ARRANGEMENTS IN POST-CONFLICT SITUATIONS |  |
| --- | --- |
| Location : | Home-based with travel to selected countries |
| Application Deadline : | 22-Aug-12 |
| Type of Contract : | Individual Contract |
| Post Level : | International Consultant |
| Languages Required : | English |
| Starting Date : (date when the selected candidate is expected to start) | 24-Sep-2012 |
| Expected Duration of Assignment : | 50 working days spread over 3 months |
| Refer a Friend Apply Now |  |
| ### Background |  |
| Background and Context: UNDP provides rule of law support to over 100 countries, including 37 crisis-affected and fragile situations. Particular attention is paid to 21 priority countries supported through the Global Rule of Law Programme (2008-2011) which provides support to the implementation justice and security programmes in those countries. Recently, UNDP launched the second phase (2012-2015) of the Global Programme (GP) “Strengthening the rule of law in crisis-affected and fragile situations”. The rule of law programmes in countries supported by the GP are focusing on enhancing access to justice and improved justice and security service delivery, tackling impunity for sexual and gender-based violence (SGBV), strengthening security sector governance, and supporting transitional justice processes. This assistance responds to urgent needs for justice and security, and simultaneously lays the foundations for recovery and long term development. The GP also provides support to joint programmes with DPKO, UNHCR, UNODC and UN Women which continue to deepen impact on the ground where it is most needed, particularly in UN mission areas such as Haiti, Liberia, South Sudan and Timor-Leste. Barriers to access justice exist in many societies but they are especially pervasive in conflict and post-conflict contexts. The administration of justice system might have been disrupted and the population displaced as a consequence of the conflict. Consequently, for many people the formal justice system is too far away. UNDP programmes assist people to find their through the justice system by supporting legal aid and by bringing justice closer to conflict-affected populations through the establishment of mobile courts. Support to mobile courts is provided in the aftermath of conflict to provide population to access to justice and seek redress for their grievances. In some countries, support to mobile courts arrangements is provided in the context of the UN’s support to transitional justice processes. UNDP provided support to mobile courts in several countries, including in DRC, Central African Republic, Sierra Leone, Guinea-Bissau and Timor-Leste. In some countries this support was provided jointly with DPKO, OHCHR as well as civil society organizations. UNDP is now conducting a study to evaluate the impact of the UNDP support provided to mobile court arrangements in countries supported by the Global Programme. Evaluation Purpose: The purpose of this evaluation is to assess the progress, achievements and lessons learned, including challenges faced with regard to the support to mobile courts’ systems in the framework of UNDP RoL programmes. The evaluation will review the impact of such activities and interventions at the sub-regional and national levels within the wider context of the technical and financial assistance provided by UNDP and its partners on RoL. In particular, the evaluation will measure the impact UNDP’s support regarding the facilitation of mobile court sessions and capacity development to bring justice closer to conflict-affected population and increase the access to justice of vulnerable people. In a second step, the evaluation will assess the impact of UNDP supported mobile court system for conflict-affected population to seek redress for their grievances and the consequences this might have for transitional justice and peace building and reconciliation efforts. The findings and conclusions of this evaluation will help generate lessons learned and identify best practices and strategies for UNDP’s (and its partners) RoL programming in post conflict-countries and for the continued engagement of UNDP in supporting development of mobile court’s systems and their relevance for legal/justice programming post conflict transitions.. Evaluation Scope and Objectives: The evaluation will review components of RoL programmes supporting mobile courts project components in DRC, Central African Republic, Sierra Leone, Guinea-Bissau and Timor-Leste in terms of their contributions to improve access to justice for the conflict-affected population and increased justice service delivery at the sub-regional and national level in these countries. The evaluation will specifically focus on the mobile courts’ impact for the population i) to seek redress for their grievances and ii) the consequences this might have for transitional justice processes and iii) for peace building and reconciliation efforts. The evaluation will examine the relevance of mobile courts project components in the context of their contributions towards improved justice service delivery and capacity development of justice institutions. Specific objectives of the evaluation are as follows: - To assess the extent to which the mobile courts’ assistance interventions met their intended objectives and contributed to the achievement of outcomes/outputs; - To systematically review the implementation modalities, capacity development efforts, knowledge management and considerations for access to justice for vulnerable groups including women and in particular survivors of sexual violence; - To determine the extent to which support to mobile courts has contributed to increasing access to or decentralizing provision of justice services; - The extent to which mobile courts contribute towards developing and strengthening long term national capacities and strategies; - Assess the exit strategy for UNDP’s support to the mobile courts given their temporary nature; - To present key findings, generate lessons learned, and provide a set of clear and forward-looking recommendations for enhancing the quality of future engagement of UNDP and its partners in supporting mobile courts’ arrangements. The evaluation will assess programme performance against the following criteria: relevance, effectiveness, efficiency and sustainability. Evaluation Questions: This paragraph includes suggested evaluation questions against the 5 criteria listed below: Relevance - To what extent do the mobile courts’ support interventions respond to the priorities outlined in the national development strategies (or similar plans/strategies)? - How does the support for mobile courts’ arrangements contribute to the longer term development results in terms of approaches, capacities, policies and strategies in the Rule of Law/Justice provision. - How well do programming mix and support modalities match the needs of the population and national partners? - What has influenced UNDP’s decisions on where, how and to what extent to engage in supporting decentralization of justice service delivery through mobile courts assistance? - What was the relevance of and possible synergies between mobile courts assistance and other priorities identified in the Rule of Law programmes and the cross-cutting areas of gender equality, capacity building and national ownership? Efficiency - Has the programme been implemented within its deadline and cost estimates? - Did the mobile courts’ support interventions focus on the set of activities that were expected to produce significant results? - Was there any identified synergy between UNDP-funded mobile courts’ support interventions and other similar interventions that contributed to reducing costs while supporting results? - Has there been over expenditure or under expenditure of the mobile courts’ support interventions? - Were there any unanticipated events, opportunities or constraints? Were the anticipated policy influences achieved? Did alternative ones emerge? What could be done differently in the future? - Were there sufficient resources allocated towards achievement of the objectives of the mobile courts’ support interventions? How well did the mobile courts’ support interventions leverage non-core resources towards achievement of results? - What effect did management and institutional arrangements have on the quality of mobile courts’ support interventions in terms of programming, delivery and monitoring for results? What measures were taken to assure the quality of development results and management practices, both in relation to process and products, and to partnership strategies? What monitoring and evaluation procedures were applied by UNDP and partners to ensure greater accountability? Effectiveness - Have the expected development (quantitative and qualitative) results been achieved and what were the supporting or impeding factors? - Were the approaches, resources, models and conceptual frameworks relevant to achieve intended outcomes and outputs? - What are the main lessons learned from the partnership strategies and what are the possibilities of replication? - Were UNDP’s comparative advantages perceived/interpreted and were these reflected in the division of responsibilities? - To what extent have interventions addressed transitional justice process and impunity of international crimes? - Which aspects of the interventions had the greatest achievements? What have been the supporting factors? How can UNDP build upon or replicate these achievements? - In which areas does the project component have the least achievements? What have been the constraining factors and why? How can they be overcome? - Were the approaches, resources, models and conceptual frameworks used for mobile courts support relevant to the achievement of planned outcomes/outputs? - What were the unintended results (positive/negative) of mobile courts assistance interventions? Sustainability - To what extent was the timeframe/timeline of support to mobile courts as an immediate measure to improve access to justice of the conflict-affected population taken into account? - To what extent were sustainability considerations were taken into account in the design and implementation of interventions? How was this concern reflected in the design of the project component, in the implementation of activities at different levels, in the delivery of outputs and the achievement of outcomes? - Were exit strategies for mobile courts’ support interventions appropriately defined and implemented, and what steps have been taken to ensure sustainability of results? - How the development of partnerships at the global, regional and national level contributed to sustainability of the results? - How different stakeholders been engaged in the design and implementation of mobile courts’ support interventions? Have interventions been implemented with appropriate and effective inter-agency and partnership strategies? What has been the nature and added value of these partnerships? |  |
| ### Duties and Responsibilities |  |
| Inception: Based on the indicative questions listed in the above section, project component and content specific questions will be elaborated further by the evaluation consultant in the inception report. The inception report should contain an evaluation matrix that displays for each of the evaluation criteria the questions and sub-questions that the evaluation will answer, and for each question, the primary and secondary data that will be collected. Data collection: In view of the complexity of the evaluation, the consultant will seek to obtain data from a range of sources, including desk reviews and document analyses, surveys and questionnaires, stakeholder consultations, interviews and focus group discussions at UNDP Headquarters and in a range of programme countries, UN agencies, international organizations, and other relevant institutions. The rationale for using a range of data sources (data, perceptions, evidence) is to triangulate findings in a situation where much of the data, due to the very complex nature of interventions, is qualitative, and its interpretation thus critically dependent on the evaluators’ judgment. Triangulation provides an important tool in filtering evidence by using different data sources to inform the analysis of specific issues. The evaluators will provide empirical evidence to support all conclusions and recommendations, and the evidence will be validated from multiple sources. Where possible and appropriate, the evaluation should seek to obtain evidence as to what might or might not have occurred in the absence of these interventions. A three-phased approach will be adopted in conducting the evaluation: First phase (Initial briefings/ meetings in New York and desk reviews): During this phase, the Evaluation consultant will conduct a desk review of relevant project documents and related documentation such as routine monitoring reports, project progress reports, and relevant review and evaluation reports, other analytical studies. The desk review will enable the consultant to: i) examine the quality of results baselines and indicators established for the projects; ii) assess the adequacy of the response strategies as reflected in the results framework; iii) review the quality of project baselines and indicators as well as existing monitoring mechanisms and resources (financial and human), and iv) conduct an initial assessment of progress towards results and/or impact as reflected in available progress reports. During the first two weeks of this phase the Evaluation Consultant will participate in briefings and meetings in UNDP and other UN agencies based in New York and interviews with the members of the Evaluation Reference Group. Within the first two weeks of the assignment the Evaluation Consultant will submit the inception report, describing the methodological/analytical framework for the evaluation and overall timeframe. The second phase (country visits): The in-country evaluations will require extensive review of existing documentation with particular attention to evaluations and studies, consultations with senior and operational managers and field staff, as well as consultations/interviews with a sample of beneficiaries. This will also include review of existing UNDP programme evaluations and assessments, studies, research and evaluations conducted by other development partners, and other relevant documentation. The Evaluation Consultant will conduct individual country visits to validate the documentary data against actual results on the ground. The focus will be to triangulate information from documents and interviews by gathering objective data on key achievements and areas for improvement. At the end of each country visit, the Evaluation Consultant is expected to present initial findings to the concerned country offices for validation of factual information and findings. The third phase (finalizing reports): The third phase of the evaluation will include finalization of the evaluation report, presentation of its findings to the Evaluation Reference Group and dissemination of lessons learned through existing UNDP mechanisms. The report should specifically highlight key lessons learned and good practices that could be replicated in future programs. Evaluation Products / Deliverables: - Inception report— detailing the evaluators’ understanding of what is being evaluated and why, showing how each evaluation question will be answered by way of: proposed methods, proposed sources of data and data collection procedures. The inception report will also include a proposed schedule of tasks, activities and deliverables, designating a team member with the lead responsibility for each task or product; - Draft evaluation report; and - Final evaluation report. Evaluatiuon Ethics: The evaluation will be conducted in accordance with the principles outlined in the UNEG “Ethical Guidelines for Evaluation” and evaluators must address, in the design and implementation of the evaluation critical issues, critical issues including evaluation ethics and procedures to safeguard the rights and confidentiality of information providers, such for example: measures to ensure compliance with legal codes governing areas such as provisions to collect and report data, particularly permissions needed to interview or obtain information about children and young people; provisions to store and maintain security of collected information; and protocols to ensure anonymity and confidentiality. Implementation Arrangements: The ROL Team and the Monitoring and Evaluation team (M&E) of the Bureau for Crisis Prevention and Recovery (BCPR) will jointly manage the evaluation process and ensure the coordination and liaison with concerned agencies at the headquarter level as well as the country level. An Evaluation Reference Group will be established at the outset of the evaluation, consisting of key stakeholders and partners, i.e. focal points/representative from UN agencies, multilateral development banks (the World Bank), academia, as well as client countries’ representatives and implementing partners. The Reference Group will play an important role in providing strategic, methodological and substantive inputs into the evaluation process, as well as feedback on the inception and final evaluation report. In addition, the reference group will ensure that the evaluation results are appropriately disseminated and discussed within their respective organizations. |  |
| ### Competencies |  |
| - Superior leadership and strategic management skills with an excellent understanding of international development issues and knowledge of the UN system; - Strong written and verbal communication skills, in a multi-cultural setting; ability to conduct results-based management and reporting, objectivity and ability to analyze large multi-country data sets in short period; - Experience working collaboratively in small teams with tight deadlines. |  |
| ### Required Skills and Experience |  |
| Education: - Masters or PhD in law or other relevant fields. Experience: - At least 7 years of international development experience or well established and well-functioning organization with at least 5 years of experience in project/programme design and implementation; - Relevant professional experience in evaluation of rule of law or other relevant programmes – at national, regional, and global levels; - Strong monitoring and evaluation background, sound methodological skills and knowledge of evaluation methods and techniques; - Extensive experience in working with the UN/multilateral development agencies, UNDP country offices and/or regional centres is an asset. |  |

Watch the video produced by UNDP on Mobile Courts in Somalia

UNDP supported mobile courts interventions

evaluation report

Country report n.3

Mobile Courts in Somaliland

Commissioned by: UNDP/Bureau for Crisis Prevention and Recovery (BCPR)

Conducted by: Monica Rispo

June 2013

Contents

Acronyms and abbreviations ……………………………………………………………………………………………..		p. 3

Executive summary …………………………………………………………………………………………………………….		p. 4

PART I: INTRODUCTION

1. 	Background and rationale ………………………………………………………………………………………  	p.7

2. 	Purpose and scope of work ……………………………………………………………………………………	p.7

3. 	Methodology and limitations …………………………………………………………………………………..	p.7

4. 	Description of the evaluated intervention...…………………………………………………………….. 	p.8

5. 	The structure of the formal court system in Somaliland ………………………………………….. 	p.9

6. 	Critical background factors ……………………………………………………………………………………….	p.9

PART II: EVALUATION FINDINGS

# 1.  	relevance

1.1. The Somaliland mobile court model ……………………………………………………………………….	p.11

1.2. Relevance to national justice sector strategies and national ownership ………………..	p.13

1.3. Relevance to the needs of the population, with a particular focus on women ……….	p.14

# 2.  	effectiveness

2.1. Planning and monitoring …………………………………………………………………………………………	p.17

2.2. The achieved results ……………………………………………………………………………………………….	p.24

2.3. Challenges in the implementation of a fair trial ………………………………………………………	p.28

2.4. Observation of mobile court sessions …………………………………………………………………….	p.32

# 3.  	efficiency

3.1. Cost-effectiveness …………………………………………………………………………………………………	p.33

3.2. Internal coordination and synergies among justice and security actors ………………..	p.35	3.3. Challenges …………………………………………………………………………………………………………….	p.36

3.4. Best practices ……………………………………………………………………………………………………….	p.37

# 4.  	sustainability ………………………………………………………………………………………………………………. 	p.37

# 5.  	impact

5.1. Changes for the population and the justice system ………………………………………………	p.38

5.2. Impact on the prosecution of international crimes ………………………………………………	p.39

PART II: CONCLUSIONS AND RECCOMANDATIONS

6. 	conclusions ……………………………………………………………………………………………………………	p.42

7. 	reccomandations …………………………………………………………………………………………………...	p.43

ANNEXES:

- 1. List of reviewed literature

- 2. List of interviewed persons

- 3. Map of Somaliland Courts

- 4. Evaluation matrix

- 5. TOR

Acronyms and abbreviations

A2J Access to Justice

BCPR Bureau for Crisis Prevention and recovery

CESVI Cooperazione e Sviluppo

CO Country Office

DRC Democratic Republic of Congo

GBV Gender Based Violence
AWP Annual Workplan

HRW Human Rights Watch

ICC International Criminal Court

IDP Internally Displaced Persons

LOA Letter of Agreement

MC Mobile Court

MOJ Ministry of Justice

RBM Result Based Management

ROL Rule of Law

SGBV Sexual and Gender Based Violence
CSO Civil Society Organization

SMART Specific, Measurable, Achievable, Relevant and Time-bound

SOLLA Somaliland Lawyers Association
SOMSAT Somali Satelite TV
UNODC UN Office for Drugs and Crime

SPU Special Police Unit

SWLA Somaliland Women Lawyers Association

UNDP United Nations Development Programme

Acknowledgments

It is with sincere gratitude that the consultant acknowledges the contributions of all the persons met during the evaluation process. Thanks are due to the UNDP Somalia staff for their support, commitment, good humor and the valuable comments and clarifications provided; most grateful appreciation is extended to the Somaliland partners and interviewees for their warm hospitality and for sharing their experiences.

Executive Summary

The present report is part of a broader evaluation commissioned by UNDP/BCPR to assess results, identify good practices and lessons learned in supporting mobile courts interventions across UNDP RoL programmes in post-conflict settings. In this framework mobile courts are defined as “formal courts that conduct proceedings in locations other than their home offices, usually in remote areas where no justice services are available”.

As set forth in the TOR and further detailed in the Inception Report, the evaluation includes a field visit of an international consultant to 3 selected COs (Sierra Leone, DRC and Somalia) and a desk study on additional COs that are supporting Mobile Courts (Timor Leste and Central Africa).

The present report presents the findings of the field visit to Somaliland.

The 2003 “Law on the organization of the Judiciary” represents the legal basis for mobile courts in Somaliland: it gives authority to the Supreme Court, the 6 Appeal Courts and the 6 Regional Courts to “hear cases in any place with in its territorial jurisdiction”. The legal basis could be strengthened by further detailing the modalities of the intervention on the model of the DRC 2013 “law on the organization of the Judiciary” that dedicates an entire Section to mobile courts.

UNDP is supporting mobile courts in 5 of the 6 regions of Somaliland and has to this end signed 4 Letters of Agreement (LoA) with the national partner (initially the Ministry of Justice and subsequently the Supreme Court). The total amount specifically allocated for mobile justice during the period 2008 -2012 is 321.000 USD.

Mobile courts in Somaliland are not following a regular and pre-established circuit of places to visit as in Sierra Leone, but are organized on an ad hoc basis, as a response to specific needs. Mobile courts hear in priority criminal cases (indicatively 80% of the caseload), but civil cases are also adjudicated, in particular land disputes.

UNDP is the only international partner supporting mobile courts in Somaliland.

The initiative has developed some good practices; to be noted the strong focus on monitoring activities, the good cooperation with the informal justice system (Xeer) and the excellent synergy with other UNDP A2J project components.

Challenges to the implementation of mobile courts include the lack of a national strategy as well as financial contribution from the Somaliland government; the frequent lack of legal representation and weak legal awareness of court users; the occasional interference of the elders in court decisions.

Key lessons learned include: 1) Mobile courts contribute to promote the development the formal justice system in remote areas where traditional justice is strongly prevalent; key to this achievement is the close cooperation with traditional leaders 2) Mobile trials are opportunities to introduce formal justice mechanisms to the communities and to offer an alternative to the traditional justice system 3) the inclusion of  female staff among mobile court teams encourages women to access mobile courts and inspires changes in the cultural norms that restrict the participation of Somali women in public life and decision making  4) annual “mobile court review workshop” where justice actors operating in different Regions meet and share experiences are effective fora to strengthen coordination within the Judiciary.

The evaluation concludes that UNDP’s support to mobile courts in Somaliland is contributing to gradually improve decentralized justice service delivery, although the focus on activities targeting mobile court users to better understand their rights and legal procedures could be reinforced in a stronger access to justice approach.

The main findings for each evaluation criteria are summarized below.

relevance

Mobile courts are aligned with national justice sector strategies and they are rooted in the Somaliland legal system; the legal basis could be further detailed. Mobile courts have been supported in full respect of the principle of national ownership and were found to be relevant by partners and other key stakeholders.

The context in which MC operate seems to gradually become more responsive to women needs; the role of women in accessing MC and the presence of female legal professionals is still to be strengthened. For SGBV cases the biggest challenge is the withdrawal from the courts in order to be settled by the elders outside the formal system; the option of establishing gender mobile courts does not seem to be appropriate for the Somali context.

effectiveness

MC are supported by UNDP since 2008 and have been planned in the framework of 4 consecutive Letters of Agreement (LoA). The current MC model “on demand” has not allowed to plan the initiative as effectively as in “circuit court” models. Important efforts were undertaken in monitoring the system; the lack of a database to consolidate the collected information remains a challenge to measure progress towards set targets.

Satisfactory results have been achieved. 1.579 cases were filed by the MC system since the beginning of the project in 2008 and the total number of cases heard by mobile courts in the five regions increased by 57% from 2009 to 2012. In 2010 the MC caseload represented 6.5 % of the total caseload for the formal justice system in Somaliland.

The campaign conducted by the University of Hargeisa (4 sessions of 7 days each in 2012) is to be noted as an exemplary coordination among the different components of the A2J project.

The following aspects of the MC procedures could be improved: i) presence of defense lawyers ii) legal awareness of court users iii) coordination with police and prisons iv) policy for court fees exemption

efficiency

Despite a clear engagement from the Somaliland government to financially contribute to the MC initiative, the system is currently dependent on UNDP for 90% of its budget. The MC initiative is cost- effective, although the financial resources could be allocated in a more effective way, in particular with regards to fuel, which represents 75% (241.000 USD) of the total UNDP contribution.. Notable efforts were undertaken to build the capacities of the Judiciary in financial reporting.

UNDP is the only international partner that is supporting MC in Somalia. Exemplary coordination is in place among the different components of the UNDP A2J project. Coordination among justice and security actors appears weak and no formal mechanism to promote linkages seems in place.

Synergies and mutual cooperation with the elders have been promoted by MC teams and should be noted, in terms of coordination, as one of the best practices of the Somaliland experience.

sustanablity

Some of the preconditions for the MC system to continue without international support are in place, in particular the fact that they are implemented independently under the lead of the Judiciary and having recourse to only local capacities; in addition MC are well accepted by the elders and rooted in the Somali traditions.

MCs are gradually evolving towards a sustainable initiative from a technical point of view; however in practice, due to the lack of financial contributions from the government, it is unlikely that MC will continue independently from UNDP’s support in the coming years, at least to the same extent as the current system.

impact

MC have fostered positive changes for the population, included: reduced conflict in the communities, reduced costs of travelling to courts, possibility of an alternative to the dispute resolution mechanisms overseen by the elders. Mobile courts have yet had a limited, although growing, impact on increasing legal awareness among the rural population.

The technical competences of the MC team members have improved and MC review workshops were important opportunities for the Judicial staff to meet as a group. The role of the formal justice system in remote areas has been strengthened.

The contribution of MCs to the prosecution of international crimes is limited as the issue is not relevant for Somaliland and currently at a very early stage in South Central.

Key recommendations directed at UNDP and the Judiciary are further detailed in the body of the report and include:

- Strengthen the legal basis for MC

- Improve the planning of MC, gradually shaping them as a circuit court model

- Complete the monitoring framework

- Promote legal awareness and understating of MC procedures for the population

- Improve the quality of MC services

- Continue to promote the sustainability of the MC system

- Strengthen the prosecution of SGBV cases and gender/child mainstreaming

- Assess the role of MCs in prosecuting international crimes

PART I: INTRODUCTION

§ 1. Background and rationale

Mobile Courts are defined for the purpose of the present report as “formal courts that conduct proceedings in locations other than their home offices, usually in remote areas where no justice services are available”. Trials are organized closer to the population by transferring the required justice actors (judge, prosecutor, court clerk, police officer and eventually legal aid lawyers) to remote locations with the main objective to facilitate access to justice, particularly for vulnerable groups who would not otherwise have the possibility to bring their cases before a formal court, often located miles away from their villages.

The growing number of UNDP Country Offices (COs) that are supporting Mobile Courts interventions and the lack of comprehensive studies specifically dedicated to this topic, suggest that further analysis of the functioning and impact of mobile courts interventions and how UNDP supports these initiatives would be needed.

Within this framework, BCPR is conducting an evaluation to assess results, identify good practices and lessons learned in supporting mobile courts interventions across UNDP RoL programmes in post-conflict settings.

As set forth in the TOR and further detailed in the Inception Report, the evaluation includes a field visit of an international consultant to 3 selected COs (Sierra Leone, DRC and Somalia) and a comprehensive desk study on additional COs that are supporting Mobile Courts.

The present report presents the findings of the field visit to Somaliland.

§ 2. Purpose and scope of work

The present report is directed to UNDP/BCPR staff, the Judiciary, donors and has two main objectives:

- Promoting joint accountability of the UNDP Country Office and the Somaliland government, respectively in supporting and implementing mobile courts interventions.

- Building knowledge for better application of mobile courts interventions across BCPR’s Global ROL programme.

The report is structured in 3 parts: the first part presents a description of the methodology and a brief overview of the context; the second part assesses the interventions against the criteria of relevance, effectiveness, efficiency, sustainability and impact; the third part presents the conclusions and the recommendations.

§ 3. Methodology and limitations

The evaluation was conducted by an international consultant and consisted in a desk review phase followed by a mission to Somaliland from 06/05/2013 to 12/05/2013.

The desk review included an analysis of relevant documentation and discussions with the UNDP Project Manager to define the evaluation tools. (see list of reviewed literature in Annex 1)

During the country visit, the consultant conducted interviews with about 20 key informants, including representatives of the Judiciary, Police and prison system, civil society organizations, international partners, mobile court users and UNDP staff. (see list of consulted persons in Annex 2)

The mission included a 1 day visit to Gabiley and Wajaale districts to observe 3 mobile court sessions.

A draft report was submitted to the CO and BCPR for comments.

The methodology of the evaluation was set out the Inception Report and consisted in a mixture of qualitative and quantitative research methods.

The evaluation questions and sub-questions are defined in the Evaluation Matrix (see Annex 4) on the basis of the TOR and reflect the 5 criteria of relevance, effectiveness, efficiency, sustainability and impact.

Some constraints have affected the analysis of the project results, in particular:

- Despite a strong engagement of both UNDP and the Supreme Court in monitoring activities, a tool to consolidate court statistics is not yet available, so a detailed analysis of project results has not been possible for all project components.

- Capacities in Somaliland are limited, although growing. A younger generation of legal practitioners is developing (inter alia as a result of UNDP’s activities in the legal education field), but is yet still building its technical and management skills. In 2010 “only 4% of the judiciary staff has received a formal legal education”

§ 4. Description of the evaluated intervention

UNDP’s support to mobile courts in Somalia is developed under the framework of the current “Governance and rule of law programme in Somalia”, and falls under the project “Improving access to justice and the judicial system”.

Mobile Courts have been implemented since 2008 with the support of UNDP in all three regions in Somalia, with distinct approaches that reflect the particular context of each region.

In Somaliland, where the context is most stable, MCs are implemented in the framework of a permanent court system established across the whole territory and under a National Justice Strategy.

In Puntland UNDP supports MC in a more fragile institutional framework as the basic justice structures are still being established and the security context is unstable.

In South Central MCs were successfully piloted in 2012 and are currently expanding as a stop-gap mechanism, meanwhile permanent courts are rehabilitated.

The scope of the present evaluation is limited to Somaliland and focuses on the specific activities identified under Letters of Agreement (LoA) signed between UNDP and the national partner (initially the Ministry of Justice and then the Supreme Court).

4 LoA were signed between 2008 and 2012 for a total amount of 321.000 USD specifically allocated for MC.

The main activities performed under the LoAs are summarized below.

- The Supreme Court, 5 Appeal Courts and 5 Regional Courts ensure the implementation of Mobile Courts in their respective jurisdictions.

- UNDP delivers the required funds and technical assistance.

- The Somaliland government contributes to the MC budget

- The Supreme Court (MOJ during the first 2 LoAs) ensures the financial and narrative reporting.

§ 5.  The structure of the formal court system in Somaliland

Below is a brief overview of the structure of the Judiciary and the hierarchy of Courts in Somaliland. The judicial institutions supported to organise MC are highlighted in blue; District Courts are well represented on the territory, but they are currently not organizing MC sessions and fall therefore outside the scope of the present report.

A map of the justice institution in Somaliland is available in Annex 3.

The current Somaliland judiciary is structured as follows:

- 37 District Courts

- 6 Regional Courts

- 6 Appeal Courts

- 1 Supreme Court (also serving as Constitutional Court)

District Courts

These are first instance courts and deal with the following legal matters:

1. All claims based on Sharia, which are primarily matters relating to family matters and succession

2. Civil litigation concerning suits for amounts up to 3 million Somaliland Shillings

3. Criminal cases punishable by imprisonment for up to 3 years or fines up to 3 million Shillings

Regional Courts

Regional Courts are also first instance courts and deal with:

1. All civil and criminal matters above the jurisdiction of the District Court

3. All labour or employment law claims

4. Any claims arising out of local district council government elections

Appeal Courts

Appeal Courts deal with all appeals from District and Regional Courts. The President of the Appeal Court in each region acts as the head of the Courts  in the region.

Supreme Court

The Supreme Court is the highest judicial body in the country and is composed of the Chairman and at least four judges. The Supreme Court deals with appeals from the Appeal Courts, electoral matters, administrative issues related to the final decisions of public bodies and acts as a Constitutional Court.

§ 6. Critical background factors

The judicial system of Somaliland has been described and assessed in several reports, to which reference is made for further information.

Below is a summary of key contextual issues that are affecting the mobile court system and should therefore be taken into consideration while reading the present report.

A) Strong prevalence of a traditional/clan-based justice system overseen by the elders (Xeer)

The Somali legal framework has developed into a combination of three distinct legal traditions: statutory law, sharia law and customary law (Xeer). The latter is prevalently applied in Somaliland where it is reported that 90% of the disputes are settled by the elders according to Xeer practices and only a limited number of cases reach the formal system (only 6.520 cases were filed by formal courts in 2010 in the whole country).

The importance of customary law in the Somali context is indisputable; it’s worth noting that it has not developed into a separate legal system, but the Xeer system “instead of competing with the formal system actually shapes its performance, including in urban centres notwithstanding the presence of courts and lawyers”.

This peculiar framework is clearly reflected in the MC system, where judges have established strong inter-linkages with the traditional clan-based system and are allowed to apply Xeer principles in their decisions. This set-up has generated some interesting best practices, but also occasionally created contradictory and inconsistent outcomes, in particular with regards to sentencing policies.

MC Judges also apply Sharia law as this is the primary source when it comes to personal status issues (marriage, divorce, and succession); according to article 5 of Constitution “The laws of the nation shall be grounded on and shall not be contrary to Islamic Sharia”.

B) Gradual and recent development of the formal justice sector

After the adoption of its first National Justice Strategy in 2008, Somaliland has achieved, inter alia with the support of UNDP, remarkable achievements in the development of the formal justice sector. To be noted for the impact on the MC system, the establishment of permanent Courts across the whole territory of the country, the training of judges and judicial staff, the establishment of a court case management system and a legal aid scheme.

The system is however still developing: the legal framework is outdated, capacities of justice actor are still weak and the Judiciary has not yet achieved an independent status, but is under the control of the Executive.

It’s worth noting that recent years have marked a strong focus on institutional reform, but less on the demand side of justice, so the population, especially in the rural areas where MC intervene, is not aware of its rights and has limited understanding of how the formal justice system works.

PART II: EVALUATION FINDINGS

# 1. RELEVANCE

§ 1.1. The Somaliland mobile court model

Several key informants confirmed that MCs are not a new institution to the Somali context, but were already organized in the past, although it is only in 2008 that mobile courts were revamped with the support of UNDP.

Articles 12(2), 11(2) and 8 (3) of the “Somaliland organisation of the Judiciary Law” represent the legal basis for MC as they give authority to respectively the Supreme Court, the Appeal Court and the Regional Court to “hear cases in any place with in its territorial jurisdiction”.

One of the interviewed lawyers criticized the weak legal framework on the basis of which MC operate and believed that in some cases there were grounds to argue that a MC would not have territorial jurisdiction over a specific case.

The legal basis for MC could be strengthened by further detailing the modalities of the intervention. This is for example the solution adopted in Sierra Leone where circuit courts are mentioned in the Constitution as well as in specific legislation and further integrated by a Chief Justice order published on the Gazette every year to identify the locations included in the circuit. In DRC the 2013 law on the re-organisation of the Judiciary dedicates a whole section to MC.

The MC model developed in Somaliland functions “on demand”: MC are not following a regular and pre-established circuit of places to visit, but are organised as a response to specific requests.

As mentioned above, the Courts organising mobile sessions are the Appeal Court, the Regional Court and the Supreme Court; the latter has an oversight role of MC the system and, since January 2013, has appointed a dedicated staff (the MC Coordinator) mainly tasked to coordinate and consolidate the MC reporting.

When a case that would need the intervention of a MC arises (for example if a District Court is addressed for a case that is above its jurisdiction), a wide range of actors can contact the competent Court and request a MC. Such actors include District Courts, prison staff, elders, High Judicial Council inspection team, and even the victim can request a MC by directly calling the judicial authorities.

The president of the Appeal Court in Hargeisa agreed it would be more effective to have an internal mechanism to receive and coordinate case referrals.

The interviewed judges reported that if additional and non-scheduled cases arise during the MC session, they tend not to hear them, but ask the District Court to assign the case and eventually come back.

The composition of a MC depends on the type of bench: General Sections of Regional and Appeal Courts only require one judge, but for Assize sections a panel of 3 or more judges is required, including one or more assessor. Registrars, prosecutors and legal aid lawyers complete the MC team.

Security is ensured by a number of police officers and eventually a Special Police Unit (SPU) escort, if a UNDP monitoring team is present.

It is common that several judges travel on a MC, but individually hear different cases so that several mobile court sessions are in operation simultaneously in the same location.

The President of the Hargeisa Appeal Court confirmed that when judges are on mission the permanent court continues to hear cases, “as there are enough judges in the system” and explained that specific judges are not assigned for MC, but the President of the Court assigns the case to any of the judges of the jurisdiction and fixes a date for the MC hearing.

A clear policy identifying the areas of intervention or the criteria to prioritise the cases that trigger a request for a MC is not available; however both the Chief Justice and the acting Attorney General mentioned that the following criteria are taken into consideration:

- Cases that involve vulnerable groups;

- Cases from particularly remote areas;

- Cases of serious crimes, like rape and murder.

In addition the MC LoA specifies that “in delivering MC services criminal cases shall be prioritized over civil cases and particularly cases related to women and children”

Not all 6 Somaliland Regions are covered by MC: due to the unstable security situation, MC are not supported in the region of Sool, on the border with Puntland. The President of Sanaag Court of Appeal added that “there are certain parts of East of Erigavo, which are not safe.  The mobile courts can only go to closest and safest areas”

“Nagaad Network” highlighted that most justice and security institutions are present in the western areas of Somaliland, although it’s in the eastern areas where justice needs are most urgent.

The Somali culture facilitates the communication of court procedures to the parties to the cases. The interviewed judges explained that they have different means to reach the court users (a letter given to the elders, a telephone call), but they rarely face the issue of the absence of the accused in court as “Somalis know each other and the information reaches the parties in time”

Support to MC only covers the trial phase, so investigations are conducted by the police and the Prosecution Office independently.

On the contrary a complementary activity that is occasionally carried out by the MC team is to hold awareness raising sessions with the communities or eventually provide legal advice to persons other than the parties to the cases.

Finally it is worth noting that 90% of the MC supported in Somaliland are structured as one-day missions; only in Saanag region are MCs organised for longer periods, in any case not exceeding 7 days.

§ 1.2. Relevance to national justice sector strategies and national ownership

Mobile courts are expressly mentioned in the 2008 “National Justice Reform Strategy” and the 2009 “Action Plan for implementation”.

Point 7.10 of the Action Plan aims at “Strengthening and expanding the Mobile Court modality” and point 7.11 recommends including a sexual violence specialist on Mobile Court Teams.

Similarly the 2012 “Somaliland National Development Plan” highlights that increasing the mobile courts services is “among the most important planned projects and programs to be implemented for improving the justice delivery system in Somaliland”

The Chief Justice is strongly committed to bringing justice closer to the population but, while recognizing that MC are a priority for the development of the formal justice sector, he explains that so far a specific strategy for MC has not been developed.

The Chief Justice and the highest judicial authorities are highly supportive of UNDP’s activities and always present at the workshops organized by UNDP, in the framework of the MC initiative and other projects.

A positive development, particularly in terms of independence of the judges, has been the transfer of the MC project from the Minister of Justice to the Judiciary (Supreme Court) in 2011. In addition UNDP is assisting the relevant institutions to draft a MOU aimed at institutionalising the management of all courts by the Judiciary, because currently the lower courts are managed by the Ministry of Justice.

It is expected that this change, coupled with the strong political will of the current Chief Justice, will favour a positive development of the MC system.

One aspect that remains problematic is that, despite the strong political will and the increased independence of the Judiciary in managing the MC system, the financial aspects of the initiative are still under the responsibility of the MOJ. The Supreme Court is organising the MC, but the MOJ is managing the budget and paying the related costs, with subsequent frustrations among the judges due to the delays in the reimbursement of their mission expenses.

Finally it is worth noting that despite the Chief Justice has clearly committed in the last two LoAs to ensure that the Somaliland government would start contributing to the MC budget, in practice such contributions are not yet significant enough: 80% of the MC budget is still provided for by UNDP and the funds for the expanses that the Judiciary engaged to cover (perdiems and stationary) are too limited to have an impact, as detailed in § 3.1.

The UNDP Project Manager explained that the above mentioned MOU currently under discussion could be an opportunity to address these issues and further the debate on the transfer of the MC initiative to the national partner.

UNDP’s support to the mobile court system reflects the principles of national ownership.

The intervention is grounded in national justice sector strategies and is nationally driven and owned: the intervention fully relies on national expertise and capacities as mobile courts are entirely run and managed by Somali judges.

UNDP is committed to develop national capacities within the Judiciary and has organized in the past, within the framework of other UNDP initiatives, trainings for judges and magistrates: 3 of the interviewed judges had participated in the 9 months training for judicial staff supported by UNDP.

§ 1.3. Relevance to the needs of the population, with a particular focus on women

A baseline study was conducted by the University of Hargeisa and UNDP in July 2012 (hereafter Baseline study) to assess different aspects of the formal justice system, included the public perception and level of user satisfaction of the justice services, as well as community understanding of available judicial mechanisms.

Reference will therefore be made to this document to assess the relevance of MC with regards to the needs of the population.

The most common legal issues identified by the respondents to the Baseline study were: 1) Fight (assault) 2) Inheritance disputes 3) Land disputes  4) Domestic violence.

Detailed MC statistics are not available, but it is confirmed that MC have heard both criminal and civil cases, and evaluation interviews reported that MC are often solving land disputes that the elders can not agree upon. Two of the interviewed beneficiaries (a man and a woman) were parties to a land case and were waiting the Regional MC to measure and demarcate their property.

There seems to be a clear understanding among justice actors and UNDP staff that the MC “shall benefit in priority vulnerable groups, including IDPs, women, juvenile offenders, minorities and the disabled, and those on remand or in police custody”.

MC statistics are not reporting information on the status of the parties to the cases, so it is difficult to assess if MC are targeting marginalised groups; data is only available for cases filed by women: in 2012 an indicative number of 150 women have brought their cases before a MC.

One of the most urgent gap unanimously highlighted during the interviews, is the limited awareness of the population about their rights and the mechanisms available to seek redress.

The interviewed MC users had little understanding of the court proceedings and all the interviewed judges recommended to increase the activities aimed at addressing this gap. One judge reported that due to the frequent questions from the communities the MC team ensures that some time is dedicated to explain their role.

The UNDP monitoring reports demonstrate the attention that UNDP staff dedicates to include the point of view of the population. Observations tend however to be quite general and repeated over time, so it is recommended to focus on more detailed information and deepen the analysis to better understand the needs of the population. For example in addition to concluding that “mobile courts saved time and money for our community”  it could be interesting to explore the following issues: how much money was spent? To whom was it given? In general are MC perceived as free of charge? If not, are they more expensive or less expensive than the dispute mechanisms overseen by elders?

The issue of discrimination against minority clans deserves particular attention, as it is reported that across Somalia such groups are not offered any protection under the Xeer system and are also discriminated by the formal system inter alia “because police, who tend to be from the majority clans, side with stronger clans”.

The situation in Somaliland is not as alarming as in South Central, but special attention should be given to the group known as Gaboye, comprising of people practicing specific non-pastoralist occupations such as market-selling, domestic work, cooking and tea-selling, which is the biggest minority in Somaliland. The UNDP A2J team leader in Hargeisa confirmed that the Gaboye group is among the MC priority target groups.

Introducing an indicator specifying the clan belonging of MC users would facilitate the follow up of this issue, however further discussions might be need with the judicial authorities: an indicator to assess the status of the parties to the cases was suggested during one of the MC workshops but rejected by most participants as too sensitive.

Internally Displaced Persons represent another group that would need special legal protection. It is estimated that 85,000 IDPs are currently living in Somaliland; those of them who come from South Central Somalia are out of their clan areas and can therefore not rely on their usual clan protection.

With regards to gender, the evaluation mission confirmed the findings of the Baseline Study that concluded “Above all, it is the perception and attitudes of men holding influential positions within the community, including elders, judges and police, which appear to be the biggest challenges to women’s access to justice”.

The male-dominated power structures are discouraging women to address formal courts; some respondents reported that elders can pressure women to withdraw their cases.

Some reports indicate that a woman can file a case to the courts but only if she is represented by male family member who speaks on her behalf. In addition customary practices are not adequately protecting of women’s rights, for example “widows may be forced to marry a relative of the deceased husband; sisters of a deceased wife may be passed for marriage to the widower; and girls may be given into an aggrieved clan as part of a conflict resolution agreement. While, in the social order, these measures provide women with continued economic security, or guarantee peace between social units in conflict, from the perspective of a ‘modern’ human rights paradigm, these are clear violations”

On the other hand it’s worth noting that, according to a UNDP Survey assessing the perception of safety and security in the districts, level of trust in the Courts is higher amongst women than men: for example in Las Canood respondents indicating high trust were 46.8% women and only 23% men. It might be surmised that women prefer the Courts to the Elders given the decisions in Xeer that seem to favour men over women.

Despite these difficulties, the context in which MC operate seems to gradually become more open to women needs: the total number of women accessing MC has increased from 127 in 2011 to 150 in 2012. Although there are yet no female Judges in Somaliland, some female Registrars and 10 female Prosecutors are in post and a growing number of female lawyers and paralegals are participating in the MCs missions.

Most of the interviewed persons recommended including more female staff in the MC to make them more easily approachable by women.

The issue of SGBV is particularly sensitive, considered the stigma that is associated with rape in the Somali culture and the consequent reluctance of victims to report rape cases as well as the uneasiness of judges in hearing such cases. An additional factor hindering the adjudication of SGBV cases is the lack of technical expertise (e.g. how to interview a rape survivors and how to collect evidence to prove sexual offences).

One of most cited challenges for the prosecution of SGBV cases is that judges allow such cases to be withdrawn from the courts in order to be settled by the elders outside the formal system, which under some versions of Xeer can lead to the outcome that the raped woman is forced to marry the perpetrator.

To address the issue the Chief Justice issued a directive in 2011 stating that elders have no jurisdiction over rape cases, and accordingly they should not intervene in such cases once the adjudication has begun by a formal court. The UNDP Team Leader in Hargeisa reported that since 2013, as a result of trainings for court staff, the number of rape cases withdrawn from the formal courts is gradually decreasing.

MCs can be a powerful tool to challenge decisions taken by the elders that are discriminating against women and promote a gradual change in the Xeer practice, so it is recommended to continue to encourage MC judges to apply the 2011 Chief Justice directive.

The President of the Appeal Court of Hargeisa confirmed that the courts under his jurisdiction are applying measures to ensure the confidentiality of the victim; if the case is heard under a tree the judges will ask police to move the public.

Consistent statistics on the number of SGBV cases handled by MC are not available, however it can be noted that in the first quarter of 2012, out of 131 cases, 31 were SGBV cases.

Nagaad Network, one of the most active CSO in the women’s rights field did not seem to be aware that MC deal with rape cases “as these are dealt with at the level of traditional leaders”, so it would be important to further disseminate to the legal community the results achieved by MC in adjudicating SGBV cases.

Finally it might be worth mentioning a brief comment on the option of establishing gender mobile courts, which is recommended in both the in Justice Strategy and the UNDP project document.

Lessons learned from the UNDP supported MCs in the Democratic Republic of Congo, where the notion of gender mobile courts was originally developed, show that these MCs are effective in increasing the number of SGBV cases, but also have negative side effects that should be considered.

From a general Human Rights perspective, gender MC may discriminate the right to access justice of non-GBV victims in remote areas where formal courts are not present and consequently create a two-tier justice system. More specifically to the DRC context, it can be noted that such courts proved to have negative implications on the independence of the judges as donor policies pressured the judges to take up in priority GBV cases with the additional consequence of producing exceptionally high conviction rates.

Moreover in a context like Somalia where the stigma for rape is much stronger than in DRC due to religious and cultural factors, a gender MC might not be the most appropriate measure to effectively fight impunity for rape.

Other less explicit mechanisms might be more suitable to promote the prosecution of SGBV in rural areas, where the focus should be on gradually changing the cultural and social behaviours and avoid quick-fixes as justice mechanisms that might be misperceived by the communities.

MC should indeed continue to take up SGBV cases, but along with other cases, in an unostentatious approach and in complementarity with a massive awareness raising campaign.

The increased presence of female staff (as lawyers, registrars and prosecutors) among MC staff is a commendable result that will gradually facilitate women’s access to justice.  Given the difficulties that women legal practitioners still face in having their role recognised, male judges and judicial staff should continue to be trained on promoting women’s rights and how to handle SGBV cases.

Finally special attention should be dedicated to monitor how MC handle cases involving minors; and verify that measures are taken to ensure their privacy (in camera hearings) and to take into consideration the best interest of the child.

MC can play a key role in implementing the law on juvenile justice that was approved in Somaliland in 2007 and in discouraging the common practice of the so-called “discipline cases” (parents who believe their children are disobedient request the justice and security services to incarcerate their children as a way of instilling discipline).

# 2. EFFECTIVNESS

§ 2.1. Planning and monitoring

Project planning

The main planning tools to guide UNDP and the Judiciary in the implementation of mobile courts are the Letters of Agreement (LoA) signed between UNDP and the MOJ/Supreme Court.

The UNDP 2012 Annual Work Plan (AWP) includes a specific output (2.4.2) on mobile courts, resulting from the following activities: “Agreement on an exit strategy (year 2 of 3). Includes sponsoring of quarterly coordination meetings with mobile court teams”.

The LoAs are described in § 2.4, whereas the table below summarizes the intended results for the MC component and will be the reference framework for the present evaluation.

| Abstract of UNDP/Supreme Court LoA for 2012-2013 |  |  |  |
| --- | --- | --- | --- |
| Activity/output | Baseline | Indicator | Target |
| 1. Increased access to justice for residents of districts and rural areas in Somaliland | Total n. of cases in 2011: 459 | n. of cases filed by MC | At least 50 monthly cases in Somaliland |
|  | n/a | increase in the n. of serious cases filed by MCs | 10% yearly increase in serious cases filed by MC |
| 2. Increased awareness of legal rights by the civilians as well as the traditional leaders | n/a | n. of legal awareness raising sessions carried out by the MC team | 8 legal awareness sessions per month in Somaliland |

The LoA captures the basic info in a RBM approach; however the following aspects could be improved:

- Baseline:  Considered that the MC initiative is entering its 4th year, the baseline for the new LoA could be more detailed and not limited to the total number of cases filed by MC under the previous LoA. The new reporting system that is being implemented will eventually contribute to this objective by providing additional information, as the disposal rate or the number of MC sessions.

- Indicators: It is suggested to add a few quality indicators (e.g. disposal rate) and to ensure that indicators are SMART and disaggregated by gender. For example instead of “serious cases” a more specific indicator could be “criminal cases involving a sentence of 5 years or above”. Indicators should be harmonized with the court statistics provided by the Judiciary in the quarterly reports. An indicator to assess the presence of defense lawyers should be included, as this one of the obligations of the Judiciary under the LoA.

- Targets: In view of a UNDP exit strategy, the targets for new LoA should have a stronger focus on the quality of the implemented activities (e.g. reduction of pretrial detention and adjournment rates, improvement of quality of the court decisions).

UNDP and the Judiciary have issued “procedural guidelines” to discipline the implementation of the Mobile Court project in Somaliland, indicating the roles of each actor and establishing information flow and reporting mechanisms: this is a valid initiative that has contributed to ensure that the system is clear and transparent.

MC planning

As illustrated in § 1.1, MC are organized “on demand”, when case arises and there is a request.

This approach is justified according to the interviewed judges because there are not enough cases to allow a systematic planning of the initiative. The President of Sanaag Regional Court confirms this challenge: “It is not possible to design a quarterly work plan by the appeal court because for the coming three months the cases to be handled or pending are not known” . Another reason is that given the lack of Per diem, judges only travel on daily MC missions.

While the challenges are recognised, it must also be noted that the current “model on demand” presents some shortcomings in both financial and logistical terms. Organising a MC places a lot of burden on the judicial authorities and the lack of planning obliges them to micromanage the initiative.  The Chairman of Hargeisa Appeal Court complains that “There was one day three judges came to me and said they were going to three different locations - I cannot manage this way.  Every court must organize its own team before it goes”

Practices from other UNDP CO, indicate that MC systems have developed into two MC models, eventually implemented jointly, as illustrated below.

- The “circuit court ”model  - A permanent court organizes mobile courts within its territorial jurisdiction, in pre-identified locations and according to a yearly schedule, with the objective to: i) hear appeal cases ii) hear cases for which lower courts do not have jurisdiction, iii) to sit in substitution of a court that is established by law, but not yet in place. This approach is applicable in contexts (as Somaliland and Sierra Leone) where mobile courts can be implemented in complementarity with a system of permanent courts that are either functioning or in the process of being established and is suited to hear ordinary criminal and civil cases.

- The “ad hoc mobile court” model  - Mobile courts are organized to address specific one-time justice needs which arise in remote locations  (e.g. in DRC  mobile courts are often deployed to hear cases of serious human rights violations committed in remote conflict affected areas). This model is best suited to address serious criminal cases (eventually international crimes) in insecure conflict-settings where justice institutions are not present.

With regards to the Somaliland context it would be recommended to improve the planning of MC by gradually shaping them as a circuit court model (as in Sierra Leone).

UNDP staff is aware that measures should be taken to ensure a more systematic approach to MC and shift to a model that is structured around regular circuit courts.

As illustrated in § 2.2, in South Central Somalia, where MC follow a pre-established schedule and a clear referral mechanism, stronger results have been achieved: in only 4 months they filed more than 70% of the cases filed in Somaliland in a year.

The current ROL Project document also suggests this approach: “the programme will increase the reach of mobile courts by instituting a more proactive and regular circuit for district courts to reach villages.”

A first step to shift towards a circuit court model is to assist the Judiciary in identifying the locations included in the circuit and receiving a regular visit of MC. Some criteria to achieve this objective are suggested below.

- 1)  Identify the locations where MC travel most frequently

The statistics for 2011 and 2012 consolidated by the MC coordinator indicate that some towns/villages are visited regularly by MCs, which could represent a first indicator that justice needs are relevant and therefore MC should continue to give priority to these areas.

The table below gives a preliminary indication of the localities that were most visited by MC in 2011 and 2012. More detailed analysis is being developed by UNDP staff.

| Location visited by MC | n. of one-day MC |
| --- | --- |
| Madheera (Hargeisa Region) | 108 |
| Gebiley (Hargeisa Region) | 57 |
| Ceel Afweyn (Sanaag Region) | 54 |
| Gubro Libaax | 23 |
| Garadan (Sanaag Region) | 21 |
| Cali Cise | 21 |

It’s interesting to note that in several of the most visited locations there is a prison (in bold in the table).

Considered the sensitiveness of incarceration in the Somali context (where restorative justice is prevalent), as well as the concerns related to illegal pre-trial detentions, it might be worth to explore the possibility of setting up a special MC component for prisons. To this end it would be important to clarify if the MC currently visiting the prisons are only validating pre-trial detentions or also conducting hearings.

- 2) Map  available justice and security actors in each region of Somaliland

The second step to establish a circuit court model requires a clear mapping of the justice and security actors available in Somaliland, with a particular focus on the rural areas.

The reason is that circuit courts should be prioritized, at least in an initial phase, in areas where the first level of justice and security actors is present: District police stations and District Courts. This is particularly relevant in Somaliland where MCs are only implemented by higher Courts as Appeal Courts, Regional Courts and the Supreme Court. The police will ensure adequate investigations, eventual transfer of the accused to prison, the security of MC teams; the District Court will play a key role in preparing the MC sessions (e.g. by informing the parties to the cases and offering an adequate space where hearings can be held).

As illustrated in the map in Annex 3, District courts and Police stations are well represented across Somaliland (37 District Courts and 65 Police stations).

The MC caseload and the opinion of several respondents indicate that District Court decisions are very often appealed before the Regional or Appeal Court. Conversely some respondents reported that Police stations are not respecting the statutory 48 hours for pre-trial detentions.  MC could therefore play an important supervisory role: in DRC for example, MC judges also inspect the lower courts and in Central Africa MC Prosecutors visit police or prison detention centres to verify pre-trial detention cases.

Several interviewed persons suggested that “district courts should be a part of the plan for the Mobile Courts” . An assessment of the District courts could be carried out to evaluate if they would have the capacities to conduct MC in their jurisdictions, eventually as a long term objective.

The table below suggests a list of potential locations that could be included in the regular MC circuits, based on the criteria of the presence of first level justice and security actors.

The UNDP Team Leader in Hargeisa pointed out that most prisons in the Districts would not be suitable to support the MC system because of poor detention conditions and lack of capacities. UNODC has carried out several assessments of the prison system in Somaliland, so might provide further information on this point.

| Suggested priority locations for MC circuits | Available justice and security actors |
| --- | --- |
| HARGEISA Regional Court & Appeal court |  |
| 1. Gabiley | 2 District courts, 1 Prison, 1 Police station, 1 SOLLA Office, 1 SWLA office |
| 2. Daaraslam | 1 District Court, 1 Police station |
| 3. Bali Gubadle | 1 District Court, 1 Police station, 1 Prison |
| 4. Saba Wanaag | 1 District Court, 1 Police station |
| 5. Cadaadlay | 1 District Court, 1 Police station |
| 6. Salaxley | 1 District Court, 1 Police station, 1 Prison |
| 7. Alay Badey | 1 District Court, 1 Police station |
| 8. Mandheera | 1 Prison, 1 SOLLA office, 1 SWLA office |
| BOROMA Regional Court & Appeal Court |  |
| 1. Baki | 1 District Court, 1 Police station |
| 2. Dil | 1 District Court, 1 Police station |
| 3. Saylac | 1 District Court, 1 Police station |
| 4. Xariirad | 1 District Court, 1 Police station |
| 5. Garba Dadar | 1 District Court, 1 Police station |
| 6. Lughaya | 1 District Court, 1 Police station |
| BERBERA Regional Court & Court of Appeal |  |
| 1. Sheekh | 1 District Court, 1 Police station, |
| 2. Xagal | 1 District Court, 1 Police station |
| BURAO Regional Court & Court of Appeal |  |
| 1. Buuhoodle | 1 District Court, 1 Police station |
| 2. Balidhiig | 1 District Court, 1 Police station |
| 3. Oodwayne | 1 District Court, 1 Police station, 1 prison |
| 4. Ooryaale | 1 District Court, 1 Police station |
| 5. Duruqsi | 1 District Court, 1 Police station |
| ERIGABO Regional Court & Court of Appeal |  |
| 1. Badhan | 1 District Court, 1 Police station |
| 2. Dhahar | 1 District Court, 1 Police station |
| 3. Ceel Afwayn | 1 District Court, 1 Police station, 1 Prison |
| 4. Laas Ooray | 1 District Court, 1 Police station |
| 5. Maydh | 1 District Court, 1 Police station |
| 6. Figifulye | 1 District Court, 1 Police station |
| 7. Gar Adag | 1 District Court, 1 Police station, 1 Prison |
| 8. Xiis | 1 District Court, 1 Police station |

- 3) Assess the caseload and the prevalence of crimes and civil disputes

Finally setting up a MC circuit would require further assessment of justice needs in the relevant areas. The Baseline Study offers a comprehensive general reference, but more specific analysis would be useful with regards to the geographical context of intervention, for example: where are land-disputes most recurrent?  Are there areas where minority groups requiring special protection are concentrated? Which are the most recurrent crimes and disputes?

In addition to MC on regular circuits, a limited number of “MC on demand” could continue to be supported, in locations where justice and security actors are not available and planning is not possible.

It is important to consider that in order to be successful, this model of MC require additional efforts in terms of financial resources and preliminary arrangements: mobile investigation teams and lawyers should be sent in advance, arrested persons should be transferred to a prison in a timely manner, parties to the case should be appropriately informed about the court proceedings, an adequate location for the hearing should be identified. Without appropriate mechanisms in place to ensure that these basic aspects of a fair trial are respected, it is not recommended to support MCs on demand, at least for serious criminal cases.

The Sool region, where the justice institutions are few, the security situation is unstable and serious crimes are committed, is an area where MC on demand could play a key role.

Project Monitoring

UNDP has undertaken significant efforts to improve the monitoring aspects of the MC initiative, as illustrated below.

► UNDP Access to Justice Staff has regularly participated in MC missions in all 5 regions of intervention in order to monitor the MC sessions and follow up on other aspects of the A2J project.

Consolidated statistics on this activity are not available, but the number of monitoring missions for the A2J project in 2011 and 2012 can be estimated to 60 missions. From April to July 2012, 18 monitoring visits to MC have been organized in the framework of the Baseline study in order to specifically collect information of the community perception of MC.

In addition the Supreme Court has been conducting monitoring missions via the High Judicial Inspection Council, but data related to this activity is not available either.

► Since January 2013 a MC Coordinator has been recruited by the Supreme Court with the support of UNDP to improve the quality of the MC reporting, in complementary with the court management system that is being implemented in Somaliland. The MC Coordinator has the main task of overseeing the reporting activities for the MC system.

► Adequate reporting tools have been designed, in an exemplary participative approach: the reporting forms have been validated during a 5 days workshop with the Judiciary in Boroma in 2012.

The following monitoring tools have bee identified for the Mobile Court system and are consolidated by the MC Coordinator:

- Daily movements report (indicating the locations visited by the MC; it’s compiled at MC level, signed by the judges on mission and approved by Regional or Appeal court)

- Monthly report (indicating number and type of cases and information on the parties to the cases; it’s compiled by the regional/appeal court and sent to the MC Coordinator on a monthly basis)

- Quarterly report (compiled by the Coordinator and sent to UNDP)

► Knowledge management products, such as lessons learned reports, have been developed in close synergy with the Judiciary.

The following MC workshops have been organised in Somaliland with an average participation of 45 Mobile Court team members (Judges and court clerks, prosecutors, legal aid providers):

- 1st Mobile Courts review workshop, 10th to 14th September 2011, Hargeisa, Somaliland

- 2nd Mobile Courts review workshop, 14th to 18th July 2012, Burao, Somaliland

- Training Workshop on the improvement of Mobile Court Services and Court Case Management system 30th Sept. to 3rd Oct. 2012, Borama, Somaliland ,

The above described MC monitoring framework would need a few additional inputs in order to fully develop into a system allowing to measure progress towards set targets and to adequately inform programmatic decisions.

To be noted that the MC Coordinator is in post only since 6 months and the UNDP team is engaged in building his capacities, so the system is expected to improve in the coming months.

The most urgent issue to address is to conceive a database to consolidate the information collected in the reports compiled by the Courts. Basic information on MC seems to be available, but it is not possible to access it in a neither speedy nor effective way. The consultant experienced serious difficulties in collecting the basic quantitative data needed for the evaluation.

UNDP Quarterly reports are not filling this gap as they do not follow a harmonized structure: for example the number of minors is indicated only in Q1 report; Q3 indicates the total number of cases, but only Q1 disaggregates the sexual assault cases. The current framework does therefore not allow a comparative analysis nor to draw conclusions on annual trends.

To fill this gap it is strongly recommended to establish an Excel database to consolidate the statistics from the quarterly reports compiled by the Judiciary.

A sample database was developed by the consultant and shared with the CO as a first tool be further adapted to the programmatic needs in Somaliland. The suggested format includes the basic information needed to monitor MC and reflects the monitoring tools developed so far; the database is structured with dropdown menus to promote a harmonized encoding and includes a filtering system allowing to rapidly sort information.

It would be suggested to dedicate some time to input all the statistics from the previous years into the new Database.

As discussed with the MC Coordinator, the following additional data could be included in the monthly reports in order to offer a more comprehensive overview of the MC system:

- Add a column for the outcome of the case (conviction, acquittal, or settlement out of court)

- Include additional information on parties to the cases. (status, clan of MC user, if appropriate)

- Add a column indicating the number of lawyers present at the MC hearing.

- Adopt a harmonised terminology to identify the typology of cases (e.g. decide if the report should mention rape or sexual assault)

The different documents shared by the MC Coordinator and the UNDP staff also indicate that knowledge in basic Excel skills and statistics could be improved. (cases are double counted, discrepancies among different documents are evident, the presentation of the results can be confusing).

The MC Coordinator also mentioned that the lack of computers and weak internet connection in the most remote regions, creates additional challenges for the Courts that rarely manage to send the monitoring reports on time. Normally the reports are given to someone reliable and send by car, or public transport, when available.

A best practice developed by UNDP in DRC could represent an alternative that might be worth exploring:  in the framework of the court monitoring project, UNDP has successfully implemented data-collection methodologies that run on Smart-phones.

It is understood that collecting the required data can be time consuming and could put too much burden on the already overloaded Court Registrars. To this end it is recommended to keep the information to the minimum and request only what is strictly necessary; for example for statistical purposes it is not necessary to indicate the names of the parties to the case.

Another option for reducing the monitoring burden on court staff is to explore the possibility of broadening the number of actors who collect information on the results achieved by the MC.

A best practice developed in Sierra Leone is to support a network of community based paralegals specifically trained to monitor courts, included MC; in DRC, UNDP introduced a MC court monitoring component carried out by 8 UNDP staff, whereas Avocats sans Frontieres works with community-based court monitors.

The presence of community based court monitors would offer the possibility to triangulate the information received from the Judiciary; assist the work of the UNDP staff that travel on mission to monitor the MC and ensure the point of view of the communities is taken into consideration in monitoring the MC system.

An interesting possibility for implementing this option in Somaliland are the so-called “District and Village Safety Committees”, supported by UNDP in the framework of the Community Policing project. Such Committees are composed of 12 persons representing all sectors of the community, included formal courts.

Another option would be to establish linkages with the “Community Safety Programme” supported by the Danish Demining Group, which has established community based security structures at village level, as for example the Community- Police Partnerships Committee

The development of community based paralegals is inter alia in line with the objectives of the current UNDP ROL project to “conduct more community case‐by‐case (court observation) analyses of the use of each (legal) system”

Finally, considered that the Inspection Services at MOJ also conduct MC monitoring missions, it would be advised to improve the coordination and information-sharing with these bodies. One for the MC reports in Gabiley also recognises the “opportunity to support the judicial inspection teams to more systematically conduct the inspections, and support them to improve their reporting skills”

A more detailed analysis could be beneficial for the “MC review workshops”: these excellent initiatives could be more effective if they included a brief session to monitor progress towards set targets. For example UNDP staff or the MC coordinator could give a presentation on the achieved results, disaggregated per region, per typology of cases and outcome of the cases and promote a discussion to explore the reasons for the achievement or non-achievement of the results.

§ 2.2. The achieved results

As illustrated in § 1.1, UNDP is supporting MC in 3 areas in Somalia: Somaliland, Puntland and South Central.

In order to highlight regional trends and briefly analyse how the different contexts are influencing the MC system, the table below gives an overview of the total number of cases filed by MC in each of the 3 different areas of intervention.

| n. of cases filed by the MC system in Somalia |  |  |  |
| --- | --- | --- | --- |
|  | Somaliland | Puntland | South Central |
| 2009 | 255 | 200 | - |
| 2010 | 418 | 321 | - |
| 2011 | 459 | 407 | - |
| 2012 | 447 | 503 | 756 |
| TOTAL | 1.579 | 1.431 | 756 |

To be noted the remarkable results of the MC system in South/Central, which in only 4 months filed more than 70% of the cases filed in Somaliland in a year.

UNDP ROL staff identified several reasons for this success.

- MC are focusing only on IDP communities settled in camps around Mogadishu, which has facilitated the establishment of strong coordination mechanisms structured around a network of community leaders from the camps (both men and women) who conduct awareness raising on the mobile courts, organize the court sessions in advance of their arrival and refer cases.

- The Chief Justice has taken steps to make the MC an “attractive option” by removing all court fees for returnees, refugees and IDPs.

- Instead of travelling across the whole territory of the State as in Somaliland, MC courts missions in South Central are concentrated in areas around MOG that are easily accessible and close;

- Due to the instable security situation Mogadishu has a higher crime rate, so the needs are stronger; as illustrated in a recent HRW report, serious human rights abuses are committed in Mogadishu IDP camps.

- The Xeer system is stronger in Somaliland than in South Central, so in Mogadishu people are more open to address formal courts.

The MC system in Puntland also seems to have achieved better results if the general context is taken into consideration: justice institutions are not yet fully operational and the security situation is more unstable than in Somaliland.

According to the UNDP A2J manager the following reasons can explain these achievements:  “Puntland has established a better reporting system than Somaliland. There has also been consistency with the mobile court coordinator in place for several years and benefiting from sustained capacity building from the A2J team. The Coordinator in Somaliland is relatively new and hasn’t yet had that level of mentoring from the UNDP staff in Hargeisa. In Somaliland courts are often dealing with a lot more serious crimes which require multiple visits and which do not necessarily lead to quick turnaround of cases. In Puntland cases are mostly civil, this means shorter procedures and quicker assessment of the claims of the parties”.

Concerning the results achieved in Somaliland, the total number of cases heard by mobile courts in the five regions increased by 57% from 2009 to 2012.

According to the Justice Sector Strategy, in 2010 the total number of cases (civil and criminal ) filed by Somaliland courts is 6.520, which means that in the same year 6,5 % of the cases where filed by MC.

With reference to the results framework established in the current LoA, the target of 50 cases per month does not appear to be achieved, as in 2012 only 447 cases were filed by MCs (instead of 600); the target of increasing by 10% the number of cases compared to the previous year, was also not achieved.

It must however be considered that 2012 marked the transfer of the MC initiative from the MOJ to the Supreme Court, so MC missions might have been suspended for some period and the new partner might have needed some time to adjust to the system.

For the purpose of the present evaluation the MC Coordinator was requested to provide an overview of the MC quantitative results in 2011 and 2012; table n.4 below consolidates the information produced, however it must be considered strictly indicative as important discrepancies with the data from the quarterly reports have been highlighted.

An aspect that emerges from the table below and which would deserve further analysis is the high number of MC organized by Appeal Courts: 51% of the MC organised in Somaliland hear appeal cases.

General trends about the appeal rate in Somaliland (i.e. the number of lowers court cases that go before a high court) are not available, however feedback collected during the evaluation mission seems to suggest that appeals are common for all courts and not a specific priority for the MC system.

This position is confirmed by a 2009 report that concluded: “Appellate review, on the other hand, appears very robust.  The stronger capacity enjoyed by appellate judges – in terms of education, training and general background – results in much remedying of poorly-decided cases by lower courts at the appellate level.  As explained by the President of the Supreme Court, “We manage to fill errors at the lower courts; though, there are many such cases and we need additional resources to deal with them.”

UNDP A2J staff in Hargeisa identifies the reasons why appeal courts seem to be overloaded in the fact that both District courts and Regional courts are submitting their appeals directly the Appeal Court, as they are both lower courts, only with a distinct competence. Secondly it seems a common practice among lawyers to appeal every Regional Court decision.

The above-mentioned clarifications seem to justify the high number of MC for appeal cases, however some concerns could be raised with regards to the fact that MC are mainly organised to review the decisions of lower courts, because these are not considered adequate.

Although less in line with the objective of facilitating access to justice for the population living in remote areas, MC can also serve the purpose of addressing the shortcomings of the lower courts, but in this case additional activities should be included.  For example the MC team should also dedicate some time to supervise the lower courts judges and eventually carry out on-the job trainings for District Court judges and UNDP could support trainings for lower court judges with the objective to gradually reduce the number of appeals. One of the appeal cases observed during the evaluation mission illustrates these issues: the Hargeisa Appeal court travelled 120 km for a land dispute because the regional court had adjudicated a dispute over a piece of land without demarcating the borders.

Finally it is worth mentioning that one of the interviewed lawyers confirmed the findings of a 2002 report by the Academy for Peace in Somaliland that “In the absence of an evaluation process, judges are often promoted or demoted according to the number of cases they win or lose on appeal”.

According to UNDP staff this practice has changed in the recent years, particularly as a result of the efforts undertaken by the Judiciary, with the support of UNDP, to promote a transparent human resources policy for judicial staff.  In addition the new government has pursued an aggressive recruitment policy of young graduates: just through UNDP’s internship programme they have brought in over 50 new prosecutors and judges in the last 2 years, as well as others from their own initiative.

On the other hand UNDP staff recognises that since Appeal Courts are responsible for organising the MC in their jurisdiction they might have given a priority focus on appeal cases.

| Statistics for Mobile Courts in Somaliland (2011 and 2012) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Jurisdiction | n. MC by COURTS OF APPEAL | n. of cases |  | n. MC by REGIONAL COURTS | n. of cases |  |
|  |  |  | Criminal | Civil |  | Criminal | Civil |
| 1 | Hargeisa region 2011 | 62 | 36 | 2 | 16 | 12 | 0 |
|  | Hargeisa region 2012 | 42 | 23 | 4 | 36 | 18 | 5 |
| 2 | Awdal region 2011 | 26 | 25 | 0 | 40 | 44 | 0 |
|  | Awdal region 2012 | 54 | 49 | 14 | 48 | 50 | 3 |
| 3 | Togdheer region 2011 | 33 | 27 | 6 | 48 | 33 | 17 |
|  | Togdheer region 2012 | 31 | 24 | 14 | 36 | 21 | 11 |
| 4 | Sanaag region 2011 | 14 | 13 | 3 | 30 | 29 | 3 |
|  | Sanaag region 2012 | 41 | 33 | 6 | 37 | 25 | 4 |
| 5 | Sahil region 2011 | 26 | 23 | 0 | 29 | 33 | 0 |
|  | Sahil region 2012 | 30 | 38 | 0 | 29 | 30 | 1 |
| 6 | Sool region 2011 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Sool region 2012 | 0 | 0 | 0 | 0 | 0 | 0 |
|  |  |  | 291 | 49 |  | 295 | 44 |
|  | TOTALS | 359 | 340 |  | 349 | 339 |  |

Given the lack of consolidated statistics on the type of cases filed by MC, reference will be made to the 2011 “MC review workshop” where all presidents of the 5 regions were asked to list the most recurrent cases in their jurisdictions, as illustrated below.

- “Sahil: Mostly criminal cases about murder, terrorism, piracy and rape and also civil cases.

- Togheer:  Most of the cases we concluded were rape, land and farms dispute.

- Awadal:  Mostly criminal, such as rape, theft, serious hurts and robbery, mostly the parties were children, women, IDPs, minorities and persons with disabilities.

- Saanag:  Cases were mostly concerned about children, illegal immigrants, women and minorities

- Hargeisa:  Cases were both criminal and civil, although most of the cases were criminal. We had around 60 cases of alcohol smuggling from Ethiopia; often these cases involve pregnant women as the criminals use them as couriers, because they face milder charges if arrested”.

The target of 8 legal awareness sessions per month carried out by MC teams can not be assessed, because of lack of related data.

During the 18 monitoring missions carried out by UNDP staff in the framework of the Baseline Study, mobile court staff conducted community legal awareness activities during four visits. These sessions included information on basic human rights, the right to a lawyer and legal aid.

It’s worth noting that according to UNDP A2J officers, MCs are often not reporting the legal advices they frequently give, so some of their achievements remain unreported. The monitoring tools described in § 2.1 could address this gap by including a specific indicator, at least to capture clusters of issues that are raised.

Under a different LoA, the Faculty of Law of the University of Hargeisa, achieved remarkable results in delivering legal awareness sessions on MC.

In 2012, 4 sessions of 7 days each were organised in the Districts of Hargeisa, Boroma and Berbera. Indicatively 40 LLB senior students participated in the programme and visited numerous villages in these 3 districts to deliver short awareness raising sessions explaining to the population the role of a MC and how its services can be accessed.

Involving law students to raise awareness on MC is an excellent initiative that shows exemplary intra-project coordination.

The impact of the sessions could be further strengthened if they were organised in closer coordination with the MC, for example by holding the sessions a few days before the arrival of a MC court in a village, so that people would be facilitated in accessing its services. The expansion of this activity, eventually in coordination with the paralegal network of court monitors discussed above, is strongly recommended.

§ 2.3. Challenges in the implementation of a fair trial

The present paragraph will provide a brief analysis of the achieved results in the light of basic fair trial standards and UNDP’s mandate, while acknowledging the strong inter-linkages between the formal and informal legal system.

Legal representation

The current MC LoA provides that “The mobile court shall ensure that they are accompanied by a lawyer representing the remanded prisoner”, however statistics reflecting the number of defence lawyers who have taken part in MC hearings are not available.

A Bar Association is not yet established in Somaliland, but SOLLA is an association representing 130 lawyers (80% of which work in Hargeisa) that is unofficially recognised as a Bar Association, although its mandate is strongly focussed on the representation of the accused.

Somaliland also developed a legal aid scheme for serious crimes supported by the government.  In addition UNDP is supporting a Legal Aid Unit in the MOJ that mainly plays a role in coordination of legal aid, including ensuring that the lawyers are present for serious crimes to fulfil the constitutional mandate. Future plans include the development of the Unit into a publicly funded legal aid commission or public defenders office.

Interviewed persons and some reports reveal that the presence of a defence lawyer is not always ensured during MC hearings. For example one of the Gabiley monitoring reports indicates that “there are 8 criminal cases, (5 cases of alcohol smuggling and 3 rape cases) unfortunately there was no lawyer for all these cases. These four women were sentenced to three years and fine of 3 million S/L. shillings, two of them delivered babies in the prison, the other was 9 months pregnant and the 4th one was of old age about 70 years old” .

The Advisor to the Prosecution office in Hargeisa confirmed that a defense lawyer is not always present and admits that some cases (not the most serious) are decided without lawyer. A judge on the contrary reports that in such cases the hearing is postponed.

Also the Baseline study points out, with reference to 18 MC monitoring missions, that: “the lack of a legal aid lawyer at most hearings has meant many vulnerable people have participated in the formal legal process without legal assistance”.

To be noted that in all 5 trials observed during the evaluation mission the accused persons where represented by lawyers and paralegals.

UNDP is supporting, with remarkable results (18.000 legal aid cases in 2012), the development of legal aid in Somaliland. This component is disciplined by a distinct letter of agreement with SOLLA, that includes the engagement of 12 lawyers to participate in MC hearings, upon request of the courts.

Interviews with SOLLA lawyers revealed some challenges in the coordination of the 2 LoAs. The Supreme Court LoA engages the Judiciary to ensure the presence of defence lawyers in MC sessions and the SOLLA LoA engages 12 lawyers to participate in the MC hearings, however the lack of a “technical plan on the how the Mobile Courts and legal aid projects worked together” has reduced the effectiveness of the initiative, as highlighted by the Chief Justice in one of the MC review workshops .

A suggested solution proposed by the Judiciary is to “prepare weekly schedules from mobile court focal points which can be shared with SOLLA so lawyers can plan”.

Legal awareness

One of the challenges faced by the MC system is the limited knowledge of legal rights by the population, and particularity vulnerable groups as women.

One of the Prosecutors in Hargeisa highlighted that “the population do not perceive the 3 different parties of a case, but they think all MC team members are judges” and recommended to organise more awareness raising sessions and eventually ensure that the “Know your rights session” on the radio would include a discussion on MC.

The president of the Sahil Regional Court alerted that “When a mobile team goes to the site the people think they are coming to make money from the people”. One of the participants in the Puntland MC review workshop reported that “People in villages at times do not even understand who a prosecutor is and get bewildered that a stranger is coming to accuse him in front of his peers and community”

Best practices for other CO show that paralegalism is an effective tool to increase legal awareness among the population. The positive impact of a community based network on MC is demonstrated by the success of the MC pilot-project in Mogadishu where, as illustrated in § 2.2, community leaders from the IDP camps conduct awareness raising on mobile courts, organize the court sessions and refer cases.

Conversely several key programmatic documents mention support to paralegalism as a priority objective for the coming years. For example Point 5.8 of the Justice Strategy aims at “supporting and encouraging the establishment of a Para-legal, justice focused community activists and organizations coalition” and the current UNDP ROL programme states that “the programme will broaden its focus on legal aid to a legal empowerment model where legal awareness building, mediation and community engagement play as large, if not a larger role, as the legal representation of criminal defendants”.

Nagaad Network also suggested that MC could strengthen their linkages with the civil society.

It is therefore recommended to continue exploring the possibility of setting up a network of community-based paralegals at district level. Paralegals could play 3 key roles in the MC system:

- Assist lawyers in preparing their cases. This is a best practice developed in Sierra Leone by the NGO Timap for Justice, where community based paralegals prepare MC cases before the arrival of the lawyer: paralegals contact the parties to the case and ensure that all the required documents are available and the file is ready; for example if the client is minor, the paralegal will assist to provide the birth certificate needed to prove the age of the client.

- Organise awareness raising sessions in their own communities to explain the role of MCs, court procedures and court etiquette. To note the best practice established in DRC by Avocats sans Frontières, where paralegals organise sessions with their communities a few days before the arrival of the MC and a Q&A session after the departure of the MC.

- Monitor court proceedings: following a best practice developed by UNDP in Sierra Leone, a smaller group of paralegal could be trained as court monitors, eventually in cooperation with the UNDP sponsored District  Security Committees, described in § 2.1.

The role of paralegals should be clearly identified and eventually limited to assist people navigating the formal justice system; in particular they should not interfere with police investigations. In a “do no harm “ approach a discussion should be promoted to define the competences between paralegals and Elders with the main objective to ensure that the introduction of an eventual new dispute resolution mechanism overseen by paralegals would not weaken the position of the elders in the communities.

Finally a brief comment on the role of the MC teams in awareness raising activities.

The approach adopted in several documents (LoA, Baseline Study, UNDP Project Document) to encourage MC team members to organise and deliver awareness raising sessions for the population might raise some concerns.

Firstly judges and prosecutors are already overloaded during the short days-mission; one of interviewed judges explained that the MC team spends a lot of additional time in mediating the conflicts that arise in relation to the enrolled cases. Secondly judges do not in general have adequate training skills and might fail to communicate in a simple language that is easily understood by rural communities.

Awareness raising sessions should therefore be delivered by representatives of CSOs with specific competence or law students as UNDP is currently doing; judges and prosecutors can then be invited to join these sessions to share their experience and be introduced to the communities, but the burden of organising the sessions should not fall on the judicial staff.

If judges and prosecutors are to deliver additional activities during their MC missions, they would be more effective in meeting the elders, eventually visiting the prisons and the police detention centres or carrying out on-the-job trainings for District Court judges.

It must finally be recognised, as specified by UNDP staff, that MC judges often find themselves unwittingly involved in explaining the legal procedures to the public, particularly after the hearings when they are approached with questions and requests for advices. It might therefore by useful to assist the Judiciary in identifying some standard key messages, eventually supported by brochures, to facilitate and speed up this process.

Police and prison system

The lack of prisons in some areas and the difficulty in transferring the remandees have been mentioned as challenges affecting the MC system.

One of the interviewed Prosecutors explains that remandees from remote areas are transferred to District police stations where their detention is followed up by the Prosecution office. It is however unclear who is in charge of transferring the remandees: some respondents indicated the Police, other the prison system and a third group said this service is paid by the parties to the cases.

Some respondents maintain that due to the lack of prisons, in remote areas police stations can act as prisons and detain persons for more than the prescribed 48 hours, however this opinion was strongly denied by the acting Chief Prosecutor.

A best practice developed by UNDP in Central African Republic, suggests that during MC visits prosecutors could visit the prisons and detention center to verify the regularity of the pre-trial detentions. The acting Chief Prosecutor found this experience interesting and eventually applicable to Somaliland but noted that “there is a separate mechanism for this kind of activity, as it’s the Inspection Committee of the Judicial Council that has the responsibility of visiting the prisons”.

One of the interviewed judges suggested to improve the security for the MC teams and reported that “sometimes people are standing in front of the courtrooms and chaos can result - you do not know who is who and insecurity can be caused”.

Interference of the elders in court proceedings

Most of the interviewed judges recognised the importance of the support from the elders and their role in the MC system, as illustrated in § 1.6, but also mentioned that occasionally interferences from the elders have affected their work and the adjudication of cases, although they concluded that in general “elders respect the authority of the formal courts”.

For example in civil cases elders sometimes request to suspend the MC hearing while they deal with the matter, or in case of murder the judge may apply a death sentence, but the elders ensure that a discussion with the family takes place to verify  if they accept compensation (diya).

Court fees

A clear policy for the payment of court fees does not seem to be available, but UNDP is planning to  work with the High Judicial Council in developing a court fee system clearly advertised in the courts and understood by court staff.  This is particularly relevant in relation to the issue of corruption: UNDP staff have often experienced that communities cannot differentiate corruption from legitimate fees the court can charge for civil cases.

The president of the Appeal Court in Hargeisa explained that before UNDP started to support MCs, courts used to ask the parties to the cases to pay 50 USD each to support the cost of the MC.

The current practice is unclear, however some respondents referred that court users pay 50 USD as fee for civil cases but no fees for criminal cases.  One of the interviewed court user reported that he had spent 100 USD to file his case (a land dispute) before the Regional Court. (7% of the value of the land). Another beneficiary said she paid 20.000 Somali Shillings to draft the statement, but other fees were waived.

To be noted that according to Somaliland law, “the Chief Justice has the discretion to waive certain court costs in the case that a person cannot afford to pay, however anecdotal evidence from legal aid lawyers suggests that this discretion is rarely used”.

In  the light of the best practice developed in South Central where the Chief Justice waived courts fees for IDPs, it would be recommended to explore further this possibility for Somaliland in addition to assisting the Judiciary in developing clear criteria to assess the vulnerability of court users and identify who is eligible to be exempted from court fees.

Quality of the court decisions

UNDP and the University of Hargeisa reviewed about 60 criminal and civil court judgments and concluded that “ 53% of the cases reviewed were legally sound but procedural law and legal drafting were identified as areas requiring further trainings. In some cases, judges effectively adjudicated cases using Somaliland and International laws while other rulings demonstrated the need for additional trainings on admissibility, engaging witnesses, managing sexual and gender based violence cases and adhering to sentencing requirements”.

It is recommended to continue a regular analysis of a random number of MC court decisions each year in order to monitor the improvement in the judicial practice.

§ 2.4. Observation of mobile court sessions

The consultant had the opportunity to observe 3 MC sessions in Gabiley and 1 session in Waanchale, (about 60 Kms from Gabiley) organized by the Hargeisa Appeal Court.

5 cases were enrolled and the MC team was composed of 3 judges, 3 registrars and 2 prison officers.

A SOLLA legal aid team participated in the MC.

In Gabiley the MC hearing took place in the District Court compound, where approximately 70 males (including 8 accused, 18 custodial corps, elders, and onlookers) and 18 females (3 beneficiaries, 3 prison officers, 3 registrars, 9 onlookers) where present.

A media crew from SOMSAT was covering the MC trials.

SOMSAT journalists are regularly covering court cases by summarising the outcome of the cases and interviewing the judges and lawyers. This could represent an opportunity to further explore in order to disseminate the achievements of the MC system and to follow up how MC are described in the Somali media.

The table below presents a summary of the cases heard during the observed MC sessions.

| Cases heard by the MC sessions in Gabiley and Waanchale (may 8th,2013) |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Type and nature of case | Parties to the case | Outcome of the case | Legal representation |
| Case 1 | Criminal (Human trafficking) | Accused: 4, male | Acquittal (lack of evidence) | Yes, Solla |
| Case 2 | Criminal (Alcohol consumption) | Accused: 1, male | Conviction (8 months of prison) | Yes, Solla female lawyer |
| Case 3 | Criminal (insulting Islam and physical damage) | Accused: 1, male | Conviction (3 months of prison for insulting Islam). The hearing on the second charge was postponed. | No |
| Case 4 | Criminal (alcohol smuggling) | Accused: 1, male | Acquittal | Yes, Solla |
| Case 5 | Civil (Land dispute, concerning boundaries) | Plaintiff: 1, woman Defendant: 1, man | The Appeal Court ruled that the case should be re-opened before the Regional Court of Gabiley | Yes, Solla |
| Case 6 | Criminal (violence related to a land dispute) | Accused: 1, male | Settlement out of court (elders intervened and freed the arrested person before the arrival of the MC) | No |

While the MC mission to Gabiley was effectively organised and achieved good results, the visit to Wajaale  presented some shortcomings reflecting the lack of planning and a clear referral mechanism for the MC system.  The second part of visit was not effective in terms of use of time and resources, as illustrated below.

The first case in Wajaale  was referred by police officers who called the MC to request an immediate intervention for a case of a person in detention, but when the MC arrived the case had been settled by the elders and the accused freed.

The second Wajaale  case concerned an appeal for a land dispute, which did not either have an outcome: the President of the Appeal Court ordered to re-open the case before the Regional court as in first instance the court omitted to measure the disputed land.

It might be concerning that the President of the busiest Appeal Court in the country must travel 120 Km to verify the boundaries of a piece of land, so it could be suggested to explore if alternative mechanisms could achieve the same objective.

# 3. EFFICIENCY

§ 3.1. Cost-effectiveness

Despite in 2011 the Judiciary officially committed to contribute to the MC budget, this has not yet occurred, so MC are mainly funded by UNDP. The Judiciary is currently only contributing with the salaries of the MC staff, stationary  and the maintenance of the 3 vehicles donated by UNDP.

The table below shows that UNDP’s total contribution for the MC system since 2008 has been of 322.290 USD. This amount does not include legal aid, and awareness raising activities, which are managed under different LoAs.

|  | From | To | National Partner | Total budget of the LoA* | Specific budget for MC |
| --- | --- | --- | --- | --- | --- |
| 1 | 1/10/2012 | 30/09/2013 | Supreme Court | 134,380 | 84,600 |
| 2 | 1/9/2011 | 30/06/2012 | Supreme Court | 93,453 | 71,540 |
| 3 | 1/1/2010 | 31/12/2010 | MOJ | 152,515 | 94,150 |
| 4 | 1/6/2008 | 1/5/2009 | MOJ | 72,000 | 72,000 |
| 4 | amendment to LoA n.5 |  | MOJ | 13,800 | 0 |
|  |  |  |  | 466,148 | 322.290 |

* the LoA includes a Case management system component.

To be noted that fuel has been the highest budget line in all LoAs: a total amount of 241.000 USD has been budgeted since the beginning of the MC project in 2008, meaning that 75% of the total UNDP budget for MC was earmarked for fuel.

Such important amounts might raise some concerns, in particular because they are negotiated as lump sums, at least in the last 2 LoA. As UNDP is planning to do for the new LoA, the budget line should be further detailed, for example by indicating how many MC missions per year; how many km travelled; how many vehicles, etc.

This information is currently available, as MCs have to fill in forms indicating the travelled Kilometres and the fuel consumption, but does not seem to be consolidated and analysed for programmatic purposes.

A related issue is the fact that the LoA does not cover Per diems for the MC team, as this should in principle fall under the responsibility of the Judiciary. In practice this is not happening, so the lack of allowances has the consequence that MC are organized for 90% of the cases as day-missions.

The Head of the Financial Department at the Supreme Court explained that the yearly budget for the Per diems for all judicial staff (mobile or permanent) is 6.000 USD and the current Per diem rate for all MC staff (judges, police etc… ) is 12 USD per day. Such amounts are clearly not sufficient and not in line with the current cost of living in Somaliland (she suggested that the rate should be increased to 40 USD).

All interviewed judicial staff and in particularly judges, strongly complained about the lack of Per diems; some mentioned that “sometimes more than 8 hours are needed to go back home”.

Considered the high amounts allocated for fuel expenses and the challenges created by the lack of per diems, it might be worth exploring the possibility of 1) rationalising the number of MC by setting up a circuit court system as illustrated in § 2.1 which should reduce the fuel costs and 2) increasing the duration of each MC by allocating a minimum amount for per diems, which could be obtained from the reduction in the fuel budget line.

An analysis of the MC caseload in 2011 and 2012 shows that 1.576 cases were filed for a budget of 140.000 USD, which indicates an approximate cost of 88 USD per case (UNDP contribution).  Considering that MC also had an impact on the elders and the public assisting the hearings, it can be concluded that in absolute terms the MC initiative is cost effective, although financial resources could be allocated in a more effective way for the above mentioned reasons.

For a more in depth analysis the cost-effectiveness criteria, the disposal rate (and not only the number of filed cases) should be taken into consideration, so it is strongly recommended to include the “outcome of the case” indicator in the monthly reporting forms. (see § 2.1)

Finally it’s worth noting that UNDP has dedicated notable efforts to build the capacities of the Judiciary in financial reporting, for example UNDP staff have organised trainings to explain “how to write financial reports per UNDP standards and the requirements to be fulfilled in their reports as well as the procurement process and financial reporting process”.

§ 3.2. Internal coordination and synergies among justice and security actors

UNDP is the only international partner that is supporting MC in Somalia. Other actors active in the Justice sector are UNODC (legislative reform), UNICEF (justice for children programme) and CESVI (child protection).

Exemplary coordination is in place among the different components of the UNDP A2J project: most of the MC judges have attended the UNDP sponsored 6 months training programme, legal aid lawyers representing MC users are working in the framework of either the LoA with SOLLA or SWLA; and the Hargeisa University is actively involved in raising awareness about MC.

Further linkages could be established with the UNDP Community Security project as described in § 2.1 and the coordination with the Police component could be stronger, in particular to strengthen the investigation procedures and the linkages between Police and Prosecution.

In addition and considered the recurrence of land disputes,  the UNDP Land Tenure project could provide useful support, for example the maps indicating where the land conflicts are most violent could be a useful tool to plan the circuits for the MC.

Likewise linkages could be strengthened with UNHABITAT and their initiatives in the field of urban land disputes (e.g Regional land dispute tribunals and the development of administrative procedures and land dispute resolution guidelines)

As illustrated in § 1.6, elders play an important role in the MC system.

Interviewed MC judges confirmed that inter-linkages with the Xeer system are currently promoted and concluded that “without the assistance of the elders the MC system would not work”.  Several monitoring reports point out that “Mobile Court teams established a strong working relationship with the traditional elders”.

Interviewed judges identified the following activities as the main contribution of elders to the MC system:

- Elders refer cases by calling the judges or contacting the District Courts; the cases mostly consist in civil disputes that they have not managed to settle.

- Elders ensure that the perpetrator is captured and brought before the court with the assistance of the clan; as one judged explained: “there is no police station in villages so traditional elders always play the role of the police.”

- Elders ensure that parties to the case accept the court decision; a UNDP ROL officer clarifies that “they might intervene to mediate if things get out of control”.

- Elders contribute to the enforcement of MC decisions by ensuring that the awarded payments are paid to the concerned party, for example by collecting the fine and giving it to the victim.

- Elders provide information about the MC to the communities. The Baseline Study found that “the most common sources for legal information and assistance were local or community leaders (19%)”

To further improve the linkages between the formal and informal systems some representatives of the elders could be invited to participate in the MC review workshops; in addition more detailed information on the role of elders could be gathered during the MC monitoring visits.

Again it is suggested to include an “outcome of the case” indicator in the monthly reports, to follow up on how many cases entered the formal system, but were finally settled out of court.

§ 3.3. Challenges

All interviewed persons were asked to identify the main challenges in implementing Mobile Courts; most answers were illustrated in the previous paragraphs, but are summarised below for easy reference.

- Procedural challenges, as illustrated in § 2.3 (legal aid not always ensured, weak legal awareness of court users; occasional interference of the elders, lack of procedures for court fees exemption; poor quality of court decisions in lower courts).

- Sustainability (despite efforts and commitment from the Judiciary, the Government is not contributing to the MC budget and the management capacities of the judicial staff are still developing).

- Planning (the “on demand” model does not allow to effectively plan the MC missions)

- Gender mainstreaming (few GBV cases; limited, although growing, number of women represented in MC teams).

- Weak coordination in the criminal justice chain

- Logistical constraints (the lack of perdiems only allows the organisation of day-missions; vehicles are not available for all MC team members; difficult road conditions)

- Security. (Particularly in some areas, as the Sool Region, MC teams are exposed to serious risks for their personal security).

§ 3.4. Best practices

The support to MC in Somaliland has developed a series of best practices that are described below as suggestions for eventual replication in other UNDP County Offices.

Strong monitoring framework

As illustrated is § 2.1, UNDP has engaged notable efforts and adequate resources to develop a consistent monitoring framework, in close cooperation with the Judiciary. As illustrated in § 2.1, MC monitoring missions are undertaken by UNDP staff; monitoring tools and knowledge management products have been developed; regular MC review workshops are organised and finally UNDP is supporting a MC coordinator tasked to ensure the MC reporting.

The framework is being finalised and a few remaining tools are in the process of being developed.

Good cooperation with the Xeer system

Elders can represent a challenge as illustrated in § 2.3, however the MC project also recognises that they play a key role in supporting the MC system and informal linkages are established between the elders and the judges.

Excellent synergy with other A2J project components

Exemplary coordination is in place among the different components of the UNDP A2J project: most of the MC judges have attended the UNDP sponsored 6 months training programme, lawyers representing MC users are working in the framework of either SOLLA or SWLA, the associations that UNDP is supporting for the provision of legal aid; Hargeisa Law Faculty is actively involved in raising awareness about MC and the new case management system is extended to MC.

Finally it’s worth noting that the project recently piloted with the support of UNDP in South Central could develop into a best practice, insofar as the MC implemented in the IDP camps around Mogadishu are representing an effective stop-gap measure while the future permanent courts are in the process of being established.

# 4. SUSTAINABLITY

The evaluation findings suggest that some of the conditions for the MC system to continue without the support of UNDP would be in place, in particular:

- MC are rooted in the judicial system and existed before and during the Siad Barre regime; as put by the Director of SLWA “MC are well suited for the Somali nomadic culture”.

- MC are featured in both the National Development Plan and Judicial Reform strategies: these are Somaliland owned strategies that illustrate the importance the government attaches to mobile courts.

- Since 2008, when UNDP started to support MCs, they have been implemented independently under the lead of the national partner (MOJ initially and Judiciary more recently), so MCs are an institutionalised process that is entirely implemented with local capacities. To be noted that those in the Sool region are implemented without financial support from UNDP.

- The Chief Justice is strongly committed to the initiative and acknowledges that the Judiciary should increase its financial contribution in view of a future exit strategy of UNDP.

- The monitoring aspects of the initiative have been consistently addressed by UNDP, in close cooperation with the Judiciary.

- MCs are well accepted by the elders.

MCs are gradually evolving towards a sustainable initiative from a technical point of view; however in practice, due to the lack of financial contributions from the government, it is unlikely that MC will continue independently from UNDP’s support in the coming years, at least to the same extent as the current system.

It would be suggested to draft, eventually as an annex to the next LoA, an exit strategy identifying the priorities to be addressed in preparation of the transfer of responsibilities to the national partner.

# 5. IMPACT

§  5.1. Changes for the population and the justice system

Changes for the population (right holders)

It is widely recognized that MC are an opportunity to increase access to justice for the rural population; in addition the economic burden of travelling to the court is reduced for litigants.

The president of the Appeal Court in Hargeisa believes that MC have “reduced conflict in the communities”. Similarly the Mobile Court system in Puntland has “ persuaded people to abandon self-help justice, especially the use of violence to settle scores and disputes”.

Women are accessing MC more frequently: the number of female court users increased from 127 in 2011 to 150 in 2012.

MC are an opportunity of change for rural populations: one of the most frequent feedback reported by UNDP staff is “we wouldn’t have used the court if they hadn’t come to us”.

MCs also represent for the communities an alternative to the dispute resolution mechanisms overseen by the elders, which is particularly relevant in a context where the traditional system applies practices that are considered inconsistent with human rights standards, especially with regards to women’s rights. Further analysis is recommended to explore if there have been cases where the decision of an elder has been challenged before a mobile court.

The educational impact of MCs is not yet evident among the population. Interviews with 5 parties to the cases and the observation of MC sessions, revealed that court users had extremely limited awareness of their rights and understanding of court procedures.

Reports indicate that “hundreds show up to watch case hearing proceedings, which is of enormous educational benefit for those who have never seen a formal justice process before.’’ Participation in MC hearings is indeed useful for the population, but would be more effective if combined with regular awareness raising sessions aimed at assisting the communities to understand the legal procedures. Compared to DRC and Sierra Leone, the judicial authorities did not seem fully aware of the educational role of MC, or least this aspect was not mentioned as frequently during the interviews. It is strongly recommended to continue and extend the awareness raising campaign for MC carried out by the University of Hargeisa.

Considered the high numbers of MC to the Mandera prison (108 in 2 years), it can be assumed that MC have been particularly active in protecting the rights of persons in detention. Further analysis would be needed on this point.

Changes for the justice actors (duty bearers)

The presence of MC has strengthened the role of the formal justice system in the districts, as indicates the increase by 57% in the number of cases heard by mobile courts from 2009 to 2012. The arrival of MCs shows the presence of the State in rural areas and contributes to strengthen the state building process.

The Chief Justice mentioned that MCs have facilitated the collection of evidence and the appearance of witnesses before a court, especially in remote areas.

The Director of the prison of Gabiley noted that MCs have reduced the expenses for the transfer of the detainees: in the past all prisoners were transferred to Hargeisa prison, because that’s where the judges sat. He pointed out that 20 detainees (5 women) were released in May 2013 thanks to the intervention of MC.

As illustrated by statistics and confirmed by key informants, MC are taking up a particularly high number of appeal cases (51% of the total caseload), which can be highlighted as a positive impact on the lower courts decisions that are being reviewed.

MC were an opportunity for the judges to establish linkages and mutual cooperation mechanisms with the elders; in addition to clarify the limits of their respective jurisdictions, in particular with regards to rape cases.

MCs have also improved the technical competences of the MC team members, as well as their monitoring skills as a result of the regular workshops organised by UNDP.

Finally MC have represented an important opportunity to improve coordination of the Justice sector: as pointed out by the UNDP A2J manager the 5 day MC workshop was “a historical event for the judiciary, as the first time that judiciary officials meet”

The director of SOLLA legal aid association mentioned that MC contributed to expand the coverage of legal aid in the districts and strengthened the knowledge of lawyers

§ 5.2. The impact of mobile court on the prosecution of international crimes

One of the objectives of the present evaluation is to analyze eventual contributions of the MC system to develop national capacities to prosecute international crimes in complementarity with the International Criminal Court (ICC).

Somalia is not party to the Rome Statute nor has the situation in Somalia been referred by the Security Council, so the ICC has currently no jurisdiction over international crimes committed in the country.

The paragraphs below will however point out a few issues that might be of interest for MCs in view of an eventual future engagement in prosecuting international crimes in complementarity with the ICC .

Somaliland

Acts of terrorism, human trafficking and piracy are committed in some areas of Somaliland. Although not falling under the jurisdiction of the ICC, such international crimes represent serious cases of concern to the international community that would benefit from a stronger engagement at national level.

Asked about the role of MC in the field of international crimes, most respondents replied that they are not heard before MCs but “they are transferred to courts in Hargeisa that are mandated to deal with such high level crimes”.

The president of the Sool Regional Court on the contrary referred that in “terrorist cases” (Al Shabab related), the accused is transferred to Mandera prison (about 400 km away) for security reasons and subsequently his court travels to Mandera as a MC to hear the case (to be noted that these MC are organised without financial support from UNDP).

The President of Sool region reported 8 “terrorist cases” (Al Shabab related) involving 24 accused in 2013.

Additional analysis is suggested to clarify how international crimes are handled by the justice system in Somaliland and to verify if this typology of crime appears in MCs caseload (for example one case of human trafficking was adjudicated during the MC session observed by the consultant).

Meanwhile it would be important to sensitise judicial staff travelling on MC about available mechanisms to prosecute international crimes and eventually ensure that referral mechanism to competent courts are in place. UNODC supports a counter-piracy programme with a specific component aimed at supporting the prosecution of Somali piracy suspects and has a mandate to prevent transnational crimes, so an eventual cooperation with UNODC could be promoted to raise awareness of mobile court staff on these specific aspects.

South-Central Somalia

The discussion seems to evolve differently in South/Central Somalia, where several international reports have denounced war crimes and crimes against humanity committed during the conflict.

HRW and Amnesty International have recently advocated for an independent commission of inquiry or similar mechanism to “to document and map serious international crimes committed in Somalia and recommend measures to improve accountability for mass violence and gross human rights violations”. In November 2007 the UN Secretary-General's special envoy to Somalia called for the ICC to prosecute war crimes suspects and during the Universal Periodic Review of Somalia, a number of States recommended the establishment of commission of enquiry to investigate war crimes and crimes against humanity.

Considered the gradual recognition of the importance of prosecuting international crimes committed in Somalia, it might be worth exploring if MCs could play a role in promoting this debate further in South Central, on the model of the DRC experience. In DRC, the legislative framework for the national prosecution of international crimes is still under discussion, but meanwhile MCs are adjudicating a selected number of war crimes and crimes against humanity and are playing an important role in complementing the ICC prosecutions and also in promoting a debate at national level.

Further analysis is needed to explore if this approach would be appropriate and timely for the Somali context, but it would be suggested to consider it as a long term objective for the MC system that is successfully being piloted in Mogadishu.

PART II: CONCLUSIONS AND RECOMMENDATIONS

§ 6. Conclusions

Despite the difficulties of intervening in a country where the traditional legal system is strongly prevalent and the formal system is still developing, UNDP’s support to mobile courts in Somaliland is achieving results that are progressively improving, particularly in terms of number of cases disposed and inter alia as a result of the notable efforts in implementing a monitoring system in close cooperation with the Judiciary.

The current initiative appears strongly focussed on the supply side of justice, as support is mainly oriented towards the courts, however additional activities (as the awareness raising campaign for the population conducted by the University of Hargeisa) are gradually being introduced in order to assist vulnerable groups to claim their rights before MC and understand the legal procedures.

UNDP’s support to mobile courts in Somaliland is contributing to gradually improve decentralized justice service delivery, but the focus on activities targeting mobile court users to better understand their rights and legal procedures could be reinforced in a stronger access to justice approach.

The main findings for each evaluation criteria are summarized below.

relevance

Mobile courts are aligned with national justice sector strategies and the national partner is strongly committed to the MC initiative, in particular after the transfer of the MC project from the Minister of Justice to the Judiciary. MC are rooted in the Somaliland legal system; the legal basis could be further detailed. Mobile courts have been supported in full respect of the principle of national ownership and were found to be relevant by partners and other key stakeholders.

The context in which MC operate seems to gradually become more responsive to women needs, in particular in the Hargeisa region, but the role of women in accessing MC and the presence of female legal professionals is still to be improved. For SGBV cases the biggest challenge is the withdrawal from the courts in order to be settled by the elders outside the formal system; the option of establishing gender mobile courts does not seem to be appropriate for the Somali context.

effectiveness

MCs are supported by UNDP since 2008 and have been planned in the framework of 4 consecutive Letters of Agreement (LoA). The current MC model “on demand” has not allowed to plan the initiative as effectively as in “circuit court” models. Important efforts were undertaken in monitoring the system (to be noted as a best practice the MC review workshops); the lack of a database to consolidate the collected information remains a challenge to measure progress towards set targets.

Satisfactory results have been achieved, particularly in the light of the strong prevalence of the Xeer system, but are difficult to analyze due to the lack of consolidated data.

1.579 cases were filed by the MC system since the beginning of the project in 2008 and the total number of cases heard by mobile courts in the five regions increased by 57% from 2009 to 2012. In 2010 the MC caseload represented 6.5 % of the total caseload for the formal justice system in Somaliland.

The 2012 targets have not been achieved, which is justified by the transfer of the MC initiative from the MOJ to the Supreme Court. The campaign conducted by the University of Hargeisa (4 sessions of 7 days each in 2012) is to be noted as an exemplary coordination among the different components of the A2J project.

The following aspects of the MC procedures could be improved: i) presence of defense lawyers ii) legal awareness of court users iii) coordination with police and prisons iv) policy for court fees exemption

efficiency

Despite a clear engagement from the Somaliland government to financially contribute to the MC initiative, the system is currently dependent on UNDP for 90% of its budget. The MC initiative is cost effective, although the financial resources could be allocated in a more effective way, in particular with regards to fuel, which represents 75% (241.000 USD) of the total UNDP contribution for MC. Notable efforts were undertaken to build the capacities of the Judiciary in financial reporting.

UNDP is the only international partner that is supporting MC in Somalia. Exemplary coordination is in place among the different components of the UNDP A2J project. Coordination among justice and security actors appears weak and no formal mechanism to promote linkages seems in place.

Synergies and mutual cooperation with the elders have been promoted by MC teams and should be noted, in terms of coordination, as one of the best practices of the Somaliland experience.

sustanablity

Some of the preconditions for the MC system to continue without international support are in place, in particular the fact that they are implemented independently under the lead of the Judiciary and having recourse to only local capacities; in addition MC are well accepted by the elders and rooted in the Somali traditions.

MCs are gradually evolving towards a sustainable initiative from a technical point of view; however in practice, due to the lack of financial contributions from the government, it is unlikely that MC will continue independently from UNDP’s support in the coming years, at least to the same extent as the current system.

impact

MC have fostered positive changes for the population, included: reduced conflict in the communities, reduced economic burden of travelling to courts, possibility of an alternative to the dispute resolution mechanisms overseen by the elders. Mobile courts have yet had a limited, although growing, impact on increasing legal awareness among the rural population.

The technical competences of the MC team members have improved and MC workshops were important opportunities for the Judicial staff to meet as a group. MC have had stronger impact on appeal cases (51% of the total caseload) than first instance cases. The role of the formal justice system in remote areas has been strengthened, in particular by making the courts known (although not yet sufficiently understood) to the population, which is a successful achievement in a country where traditional justice is strongly prevalent.

The contribution of MCs to the prosecution of international crimes is limited as the issue is not relevant for Somaliland and currently at a very early stage in South Central.

§ 7. Recommendations

The recommendations summarized in the table below stem from the findings illustrated in the previous paragraphs and are directed at UNDP and the Judiciary.

| Addressed to | Priority | Recommendation |
| --- | --- | --- |
| Judiciary | Medium | Strengthen the legal basis for MC - Issue a yearly Chief Justice order to identify the areas of intervention for MC. |
| Judiciary UNDP | High Medium Low | Improve the planning of MC - shift from a MC model “on demand” to a “circuit court” model - maintain a limited number of “MC on demand”, eventually in Sool region - conduct an assessment of District Courts to evaluate if they would have the capacity to run MC in their jurisdictions. |
| Judiciary UNDP | High High Low Low Medium High | Complete the monitoring framework - Establish an Excel database to consolidate the statistics compiled by the Judiciary - Refine the monitoring indicators in the quarterly reports ( e.g include the disposal rate, the outcome of the case..) - Explore if data-collection methodologies running on Smart-phones are applicable - Establish a network of community-based Court Monitors eventually in connection with “District and Village Safety Committees” supported by UNDP - Improve the coordination of monitoring activities with the Inspection Services - Continue to train judicial staff, in particular the MC Coordinator, and organize MC review workshops to develop further a RBM culture |
| UNDP SOLLA and CSO | Medium High Low | Promote legal awareness and understating of MC procedures by the population - Set up a network of community-based paralegals at district level aimed at i) assisting lawyers in preparing their cases , ii) organizing awareness raising sessions in their communities, iii) monitor court proceedings - Expand the awareness raising sessions organized by the University of Hargeisa and ensure that the sessions are held a few days before or/and after the MC - Remove the responsibility for the awareness raising component on MC teams, but use CSOs/law students instead. |
| UNDP | Low Medium | Revise budget allocation - Ensure that the budget line for fuel is adequately detailed and not negotiated as a lump sum. - Explore the possibility of reducing the fuel costs and increasing the duration of each MC, by allocating a minimum amount for per diems. |
| Judiciary UNDP | Low High Medium Low Medium | Improve the quality of MC services - Develop criteria to assess the vulnerability of court users and identify who is eligible to be exempted from court fees. - Establish referral mechanisms between legal aid providers and the courts to ensure the presence of lawyers - Strengthen Police investigations and coordination between Police and Prosecution - Assess if MC judges could supervise the District Courts judges and eventually carry out on-the job trainings with the objective to gradually reduce the number of appeals. - Explore the possibility of including a special MC component for prisons and/or if prosecutors on MC teams could visit prisons and detention centers to verify the regularity of pre-trial detentions |
| Judiciary UNDP | High Medium Medium | Continue to promote the sustainability of the MC system - Ensure that the government allocates consistent financial resources to the MC system - Draft, eventually as an annex to the next LoA, an exit strategy identifying the priorities to be addressed in preparation of the transfer of responsibilities to the national partner. - Continue to ensure the support of the elders to the MC system |
| Judiciary UNDP | Medium High Medium | Strengthen the prosecution of SGBV cases and gender/child mainstreaming - Include additional female staff in the MC team, without adopting the “gender mobile court” model - Continue to train judges and judicial staff on the promotion of women’s rights and the prosecution of SGBV cases - Monitor how MC handle cases involving minors, in particular with regards to “discipline cases” |
| Judiciary UNDP | Low Medium Low | Assess the role of MCs in prosecuting international crimes - Clarify how international crimes (acts of terrorism, human trafficking and piracy) are handled by the justice system in Somaliland and verify if this typology of crime appears in MCs caseload - Sensitize judicial staff travelling on MC about available mechanisms to prosecute international crimes and eventually ensure that referral mechanism to competent courts are in place. - In South Central assess if the MC system that is being piloted in Mogadishu could, in the long term, play a role in the prosecution of war crimes and crimes against humanity |

ANNEX 1: Reviewed literature

Consulted documents are available on the shared folder created on Dropbox for the present evaluation:

https://www.dropbox.com/sh/kn177z4dddfvgyp/AbtqXNN4Ai

1. Articles

- Academy for Peace and Development “The Judicial System in Somaliand” Akaademiga Nabadda Horumarka 2002

- Africa Watch,  “Somalia: a government at war with tits own people. Testimonies about the killings and the conflict in the North”, 1990

- Alejandro Bendaña and Tanja Chopra in “Women's Rights, State Centric Rule of Law, and Legal Pluralism in Somaliland” Hague Journal on the Rule of Law / Volume 5 / Issue 01 / March 2013.

- Centre for humanitarian dialogue, « Stateless justice in Somalia: formal and informal rule of law initiatives »,  Andre Le Sage, 2005

- Human Rights Watch, “Hostages of the gatekeepers. Abuses against Internally Displaced in Mogadishu, Somalia”, 2013

- Hussein Mohamed Farah, “Baseline assessment of the Somaliland Judiciary”, unknown year

- IDLO, “Evaluating the Effectiveness of Legal Empowerment Approaches to Customary Law Reform in Somaliland and Puntland”, unknown year

- Margherita Zuin, “A Model of Transitional Justice for Somalia”, Fletcher Journal of Human Security, 2008

- Michael Van Notten “The Somali Legal System” in The Law of the Somalis, Red Sea Press,  2005

- Minority Rights Group “No redress: Somalia’s forgotten minorities”, Martin Hill, 2010

- Report of the Independent Expert on the situation of human rights in Somalia, Shamsul Bari, August 2012

- UNDOS “Assessment of the judiciary system of Somaliland”, October 1999

- UNDP, “empowering rural communities through access: assessing the mobile courts in Somalia and the lessons learned from DRC, Indonesia and Timor” 2013

- University of Hargeisa with support from UNDP, “Strengthening the Quality and Scope of Justice Provision and Policing in Somaliland. A Baseline Study” July 2012

- Geneva International Centre for Humanitarian Demining in “Danish Demining Group Community Safety Programme. Somaliland case study”, September 2012

2. Legislation and other documents

- Letter of Agreement between UNDP and the Ministry of Justice (2008 and 2010)

- Letter of Agreement between UNDP and the Supreme Court (2011 and 2012)

- Somaliland Mobile Courts: procedural guidelines for implementation

- Somaliland Judicail reform workplan (2011-2015)

- UNDP Somalia, Governance and rule of law programme document (2012-2015)

- Report of the 1st Mobile Courts review workshop, 10th to 14th September 2011, Hargeisa, Somaliland

- Report of the 2nd Mobile Courts review workshop, 14th to 18th July 2012, Burao, Somaliland

- Report: training Workshop on the improvement of Mobile Court Services and Court Case Management system 30th Sept. to 3rd Oct. 2012, Borama, Somaliland ,

- UNDP, evalauiotn of ROLSIII programme, 2011

- Mobile court review worshop report, Puntland, 2013

- Sub Outcome Monitoring: Case Study 2.4 JUSTICE AND THE JUDICIARY, UNDP, 2012

- MC monitoring report in Nugal, Puntland

- MC monitoring report in Boon, Somaliland

- MC monitoring report in Gabiley, Somaliland

- Video produced by UNDP on Mobile Courts in Somalia available on You Tube http://www.youtube.com/watch?v=WwXYtze_9J4

ANNEX 2: List of interviewed persons

Evaluation of UNDP supported Mobile Courts – Somaliland (01/05/2013 to 12/05/2013)

- Abdikarim Sheik Mohamed,  Vice-Dean the faculty of Law and legal clinic, Hargeisa University

- Abdirasheed Duraan - President of Appeal Court Hargeisa

- Abdisalam Farah, Access to justice officer, UNDP

- Abdulhakim Mohamed Abdi, Access to Justice Team Leader, UNDP

- Aden Ahmed , Acting Attorney General, Prosecution Office

- Beneficiaries/court users (5 men and 2 women)

- Elizabeth Wamaitha Kang’atta, Access to justice officer, UNDP

- Faysal Abdilahi Ismail - President of Hargeisa Regional court

- Harum Mohamed, Acting Director, Nagaad Women Network for Somaliland

- Hassan Ali Hassan – vice-chairman, Somaliland lawyers Association ( SOLLA)

- Hassan Sudi Gender advisor, Nagaad

- Hussein  Abdilahi – Director, Prison of Gabiley

- Hussein Belel – Judge, Hargeisa regional Court

- Hussein Fadal – Judge, Hargeisa Appeal Court

- Hussein Jama ,Technical Advisor, Prosecution Office

- Jama Ali Ismail-Admin,  Xamze Mohamoud, Mohamoud Abdi Nour, Amina Hassan (SOLLA lawyers)

- Khadra Muse Ahmed, Executive Director, Somaliland Women Lawyers Association

- Mohamed Farah - President of Appeal court – Sool region

- Mohamed Said Hersi – Executive director, SOLLA

- Roda Mohamed –Paralegal, SOLLA

- Sahal Dayax- Judge, Hargeisa Appeal Court

- Sahra Ismail , Head of Finance Department, Supreme Court

- Sharmarke Yusuf,  coordinator for the Mobile Courts, Supreme Court

- Simon Ridley, Access to justice Project manager, UNDP

- Yasin Hassan, vice Chief Justice

- Yusuf Ismail Ali, Chief Justice

ANNEX 3: Map of Somaliland justice institutions

ANNEX 5: Evaluation Matrix

| Evaluation of UNDP support to mobile courts arrangements in post-conflict situations EVALUATION MATRIX |  |  |  |  |
| --- | --- | --- | --- | --- |
| 1. RELEVANCE |  |  |  |  |
| questions & sub-questions |  | data sources |  | data collection method |
| Q.1.1. To what extent do the mobile courts’ support interventions respond to the priorities outlined in national strategies? - What is the legal basis for implementing mobile courts? - Are a national strategy and a national budget available for MC? - Is there an MOU between UNDP and the Judiciary/MOJ to support mobile courts? - Has the Judiciary implemented MC without the support of international donors? If so, what were the results? - How does the country legal system (civil/common law, pluralistic..) influence mobile courts arrangements? |  | - National legislation - National Justice Sector strategies - MOU between UNDP and Judiciary |  | - Online research - Request CO/HQ - Interviews: judicial authorities.. |
| Q.1.2. How well do programming and implementation modalities match the needs of the population and national partners? - What influenced UNDP’s decisions on where, how and to what extent to engage in supporting mobile courts? Was the decision discussed with relevant stakeholders? - Was a needs assessment conducted before launching the mobile court intervention? Was the Judiciary involved? - Which are the most vulnerable groups in the country? Are they targeted by mobile courts interventions? - To what extent were issues related to the restorative v. retributive conception of justice in remote areas taken into consideration? |  | - Needs assessment or baseline analysis reports (by UNDP, Judiciary or other actors) - research reports - reported opinions from key informants |  | - Online research - Request CO/HQ - Interviews: MOJ, judicial authorities, UNDP staff.. |
| Q.1.3. What was the relevance of mobile courts assistance for other priorities of UNDP Rule of Law programmes and the cross-cutting areas of gender equality, capacity building and national ownership? - Were synergies established between MC and other components of UNDP Rule of law programmes? (Legal aid, Paralegalism, Policing, …), If so, what was the added value of a mobile court component? - How was gender mainstreamed across the mobile court intervention? - Have mobile courts interventions utilized existing local capacities of rights holders and duty bearers to achieve their results? How were their capacities strengthened? |  | - UNDP documents: CPAP/UNDP project documents /BCPR field visits reports/ BCPR integrated projects/ evaluation reports… - reported opinions from key informants |  | - Request CO/HQ - Interviews: UNDP staff.. |
| 2. EFFECTIVENESS |  |  |  |  |
| questions & sub-questions | data sources |  | data collection method |  |
| Q.2.1: What model of MC emerges from the CO practice? - What is the composition of the MC? How are the judges/prosecutors/lawyers selected to participate? - What is the jurisdiction of mobile courts with regards to subject matters, litigants and geographical coverage? - What is the average distance between the permanent tribunal and the mobile court? - How long does the mobile court session last and how often does it visit the same area per year? - To what extent have interventions addressed transitional justice process and impunity of international crimes? | - Databases /statistics - Map of the judiciary - project document - Reported opinions from key informants |  | - Interviews: UNDP staff, Ministry of Justice… - Request CO/HQ |  |
| Q.2.2: What results (quantitative and qualitative) were achieved in each phase of mobile court interventions? phase 1: before mobile court sessions - What support did UNDP ensure to the logistical aspects of mobile courts (transport, courtroom, accommodation, office and legal material for judges on circuit)? - Were the population and local authorities informed about the arrival of the mobile court in an appropriate and timely manner? - Were investigations in criminal cases effectively conducted? Were eventual pretrial detention issues addressed? Were linkages between Prosecutors and Police promoted? - Were notifications of procedural acts issued and communicated in a timely manner? - Were specific trainings for mobile court staff organized? (knowledge of the local culture and traditional law practices, gender/child rights…) phase 2: during mobile court sessions - How many and what cases received free legal aid from a lawyer? Was the Bar Association involved? - How many witnesses appeared before the mobile court? Which measures were in place to protect witnesses and victims, and in particular SGBV victims? Is there a “travel cost reimbursement program” to assist witnesses and victims to appear in court? - Were hearings translated into local languages? - How many people participated in the public hearings? Were they assisted in better understanding the hearings? - Were mechanisms in place to ensure the security of mobile court staff? - Were the proceedings adequately recorded? Are there higher rates of adjournment for MC proceedings? phase 3: after mobile court sessions - How many judgments were enforced (criminal/civil)? - Were mechanisms in place to enforce prison sentences in the absence of local prison facilities? - What is the rate of appeal of MC decisions? - Are there mechanisms in place to ensure the communication of MC decisions to the rest of the justice chain to ensure decision enforcement and information sharing? - Were parties assisted to collect eventual financial compensation that they were awarded? - If alternative sanctions to imprisonment were applied (community services), was a follow up ensured? | - Project performance indicators - Databases/ statistics - UNDP quarterly and annual reports - MC reports - Judiciary reports - Research studies - Reported opinions from key informants |  | - Request CO/HQ - Interviews: Ministry of Justice, judicial authorities, police, prison staff, traditional authorities, lawyers, other implementing partners, UNDP staff.. - Focus group with beneficiaries |  |
| Q.2.3: Were planning and monitoring procedures appropriate to achieve results and ensure accountability? - Is a clear results framework with SMART indicators, targets and risks analysis available? - What monitoring tools are available? Are court statistics available? - Are national partners involved in monitoring activities? - Is there a system in place for trial observation? - Is feedback from mobile court users collected to assess needs and adjust services accordingly? - How is the quality of mobile court judgments assessed? - Are landmark cases identified and disseminated? | - Project document and results framework - UNDP quarterly and annual reports - evaluation reports of broader ROL projects - reports drafted by MC staff |  | - Interviews: UNDP staff, Ministry of Justice… |  |
| Q.2.4: What were the reasons for achievement and non-achievement of results and the factors contributing or hindering their achievement? - How can UNDP build upon or replicate the achievements? - How can the shortcomings be overcome? - What are the lessons learned? - Were there any unanticipated events, opportunities or constraints? - What could be done differently in the future? - What were the unintended results (positive/negative) | - Reported opinions from key informants - UNDP quarterly and annual reports - Judiciary reports |  | - Interviews: UNDP staff, Ministry of Justice, Mobile court staff… |  |
| 3. EFFICIENCY |  |  |  |  |
| questions & sub-questions | data sources |  | data collection method |  |
| Q.3.1: Has the MC intervention been implemented within its cost estimates and is it cost-effective? - Were sufficient resources allocated for mobile courts’ support interventions? Is the national government contributing to the budget for MC? - Are the expenditures for MC proportionate to the number of cases and broader indicators as the number of participants in public hearings? - What are the costs per trial? would it be cheaper to build court rooms and provide staff in remote areas? - Are perdiems for judges and MC staff in line with local market? | - Resource frameworks, budgets, AWP, - Reported opinions from key informants - UNDP quarterly and annual reports - MOJ reports |  | - Interviews: UNDP staff, Ministry of Justice.. - Request CO/HQ |  |
| Q.3.2: Has UNDP promoted a partnership strategy at the global, regional and national level to implement MC interventions? If so, was it effective and appropriate? - What was the nature and added value of these partnerships? - Did such partnerships promote an integrated approach aiming at addressing complementary aspects of mobile courts interventions (legal awareness for the population; support to police and prisons; linkages with traditional justice …) - Were UNDP’s comparative advantages perceived/ interpreted and were these reflected in the division of responsibilities? - If the Judiciary received specific support for mobile courts interventions from several donors, were the initiatives efficiently coordinated? | - UNDAF - partnership agreements/MOU - Reported opinions from key informants |  | - Interviews: UNDP staff, Ministry of Justice, Protection cluster, UN agencies and INGOs, civil society organisations, universities… - Request CO/HQ |  |
| Q.3.3: What effect did UNDP technical assistance and management arrangements have on the quality of mobile courts interventions in terms of programming, delivery and monitoring for results? - Were the project management structure and the administrative modalities appropriate and effective? - Was the support from UNDP staff effective and timely? | - Project document and monitoring reports - Reported opinions from key informants |  | - Interviews: UNDP staff, Ministry of Justice, Mobile court staff… |  |
| Q.3.4: Did mobile courts interventions focus on the set of activities that were expected to produce significant results? - Are all the planned activities implemented? Should additional activities be planned? - Are mobile courts ensuring the implementation of the international standards of fair trial? Would some of the fair trial rights need more attention? | - Project document - Reported opinions from key informants - international standards on fair trial |  | - Interviews: UNDP staff, Ministry of Justice, other implementing partners… |  |
| 4. SUSTAINABILITY |  |  |  |  |
| questions & sub-questions | data sources |  | data collection method |  |
| Q.4.1: To what extent were sustainability considerations taken into account in the design and implementation of interventions? - Were exit strategies for mobile courts interventions appropriately defined and implemented? - What steps were taken to ensure that the effects of the intervention would continue beyond UNDP’s support? - Has the development of partnerships contributed to the sustainability of results? | - Project document - annual reports - Reported opinions from key informants |  | - Interviews: UNDP staff, Ministry of Justice, Judiciary other implementing partners… |  |
| Q.4.2: How were different stakeholders engaged designing, monitoring and implementing mobile courts interventions? - Has UNDP promoted and facilitated the coordination among local justice and security actors (Police, Prisons, Traditional justice, local authorities…) ? - Have linkages been established between mobile courts and ADR mechanisms? (for example to establish mandatory court annexed mediations). | - Project document - annual reports - Reported opinions from key informants |  | - Interviews: UNDP staff, Judiciary, Ministry of Justice, Police, Prison staff, traditional authorities, local authorities… |  |
| 5. IMPACT |  |  |  |  |
| questions & sub-questions | data sources |  | data collection method |  |
| Q.5.1: What changes did mobile courts interventions bring for rights holders in terms of making justice more accessible to them? - Have MC interventions promoted a better confidence in the justice system? Is there a perception that impunity is being addressed? - Are vulnerable groups in remote areas more aware of their rights and do they have a better understanding of the formal justice system? - Do MC provide an alternative to traditional justice? | Reported opinions from key informants |  | Focus groups with beneficiaries and interviews with their lawyers / Eventual users perception survey |  |
| Q.5.2: What changes did mobile courts interventions bring for duty bearers in terms of making them more effective in responding to justice need of conflict affected populations in remote/underserved areas? - What is the impact of MCs on ordinary courts? (in terms of case backlog, promoting case management systems, costs) - What was the impact on ordinary courts of assigning judges and other judicial staff to mobile courts? - Have MC interventions led to the re-establishment of the justice system eventually in conflict-affected areas? - Have MC interventions promoted closer coordination among the different actors in the justice chain? - Have judicial authorities acquired additional skills and knowledge in terms of managing a MC intervention? | Reported opinions from key informants |  | Interviews: Judicial authorities and Ministry of Justice, Police, Prison staff, traditional authorities |  |

ANNEX 6 Terms of reference

| ### EVALUATION CONSULTANT: SUPPORT TO MOBILE COURT ARRANGEMENTS IN POST-CONFLICT SITUATIONS |  |
| --- | --- |
| Location : | Home-based with travel to selected countries |
| Application Deadline : | 22-Aug-12 |
| Type of Contract : | Individual Contract |
| Post Level : | International Consultant |
| Languages Required : | English |
| Starting Date : (date when the selected candidate is expected to start) | 24-Sep-2012 |
| Expected Duration of Assignment : | 50 working days spread over 3 months |
| Refer a Friend Apply Now |  |
| ### Background |  |
| Background and Context: UNDP provides rule of law support to over 100 countries, including 37 crisis-affected and fragile situations. Particular attention is paid to 21 priority countries supported through the Global Rule of Law Programme (2008-2011) which provides support to the implementation justice and security programmes in those countries. Recently, UNDP launched the second phase (2012-2015) of the Global Programme (GP) “Strengthening the rule of law in crisis-affected and fragile situations”. The rule of law programmes in countries supported by the GP are focusing on enhancing access to justice and improved justice and security service delivery, tackling impunity for sexual and gender-based violence (SGBV), strengthening security sector governance, and supporting transitional justice processes. This assistance responds to urgent needs for justice and security, and simultaneously lays the foundations for recovery and long term development. The GP also provides support to joint programmes with DPKO, UNHCR, UNODC and UN Women which continue to deepen impact on the ground where it is most needed, particularly in UN mission areas such as Haiti, Liberia, South Sudan and Timor-Leste. Barriers to access justice exist in many societies but they are especially pervasive in conflict and post-conflict contexts. The administration of justice system might have been disrupted and the population displaced as a consequence of the conflict. Consequently, for many people the formal justice system is too far away. UNDP programmes assist people to find their through the justice system by supporting legal aid and by bringing justice closer to conflict-affected populations through the establishment of mobile courts. Support to mobile courts is provided in the aftermath of conflict to provide population to access to justice and seek redress for their grievances. In some countries, support to mobile courts arrangements is provided in the context of the UN’s support to transitional justice processes. UNDP provided support to mobile courts in several countries, including in DRC, Central African Republic, Sierra Leone, Guinea-Bissau and Timor-Leste. In some countries this support was provided jointly with DPKO, OHCHR as well as civil society organizations. UNDP is now conducting a study to evaluate the impact of the UNDP support provided to mobile court arrangements in countries supported by the Global Programme. Evaluation Purpose: The purpose of this evaluation is to assess the progress, achievements and lessons learned, including challenges faced with regard to the support to mobile courts’ systems in the framework of UNDP RoL programmes. The evaluation will review the impact of such activities and interventions at the sub-regional and national levels within the wider context of the technical and financial assistance provided by UNDP and its partners on RoL. In particular, the evaluation will measure the impact UNDP’s support regarding the facilitation of mobile court sessions and capacity development to bring justice closer to conflict-affected population and increase the access to justice of vulnerable people. In a second step, the evaluation will assess the impact of UNDP supported mobile court system for conflict-affected population to seek redress for their grievances and the consequences this might have for transitional justice and peace building and reconciliation efforts. The findings and conclusions of this evaluation will help generate lessons learned and identify best practices and strategies for UNDP’s (and its partners) RoL programming in post conflict-countries and for the continued engagement of UNDP in supporting development of mobile court’s systems and their relevance for legal/justice programming post conflict transitions.. Evaluation Scope and Objectives: The evaluation will review components of RoL programmes supporting mobile courts project components in DRC, Central African Republic, Sierra Leone, Guinea-Bissau and Timor-Leste in terms of their contributions to improve access to justice for the conflict-affected population and increased justice service delivery at the sub-regional and national level in these countries. The evaluation will specifically focus on the mobile courts’ impact for the population i) to seek redress for their grievances and ii) the consequences this might have for transitional justice processes and iii) for peace building and reconciliation efforts. The evaluation will examine the relevance of mobile courts project components in the context of their contributions towards improved justice service delivery and capacity development of justice institutions. Specific objectives of the evaluation are as follows: - To assess the extent to which the mobile courts’ assistance interventions met their intended objectives and contributed to the achievement of outcomes/outputs; - To systematically review the implementation modalities, capacity development efforts, knowledge management and considerations for access to justice for vulnerable groups including women and in particular survivors of sexual violence; - To determine the extent to which support to mobile courts has contributed to increasing access to or decentralizing provision of justice services; - The extent to which mobile courts contribute towards developing and strengthening long term national capacities and strategies; - Assess the exit strategy for UNDP’s support to the mobile courts given their temporary nature; - To present key findings, generate lessons learned, and provide a set of clear and forward-looking recommendations for enhancing the quality of future engagement of UNDP and its partners in supporting mobile courts’ arrangements. The evaluation will assess programme performance against the following criteria: relevance, effectiveness, efficiency and sustainability. Evaluation Questions: This paragraph includes suggested evaluation questions against the 5 criteria listed below: Relevance - To what extent do the mobile courts’ support interventions respond to the priorities outlined in the national development strategies (or similar plans/strategies)? - How does the support for mobile courts’ arrangements contribute to the longer term development results in terms of approaches, capacities, policies and strategies in the Rule of Law/Justice provision. - How well do programming mix and support modalities match the needs of the population and national partners? - What has influenced UNDP’s decisions on where, how and to what extent to engage in supporting decentralization of justice service delivery through mobile courts assistance? - What was the relevance of and possible synergies between mobile courts assistance and other priorities identified in the Rule of Law programmes and the cross-cutting areas of gender equality, capacity building and national ownership? Efficiency - Has the programme been implemented within its deadline and cost estimates? - Did the mobile courts’ support interventions focus on the set of activities that were expected to produce significant results? - Was there any identified synergy between UNDP-funded mobile courts’ support interventions and other similar interventions that contributed to reducing costs while supporting results? - Has there been over expenditure or under expenditure of the mobile courts’ support interventions? - Were there any unanticipated events, opportunities or constraints? Were the anticipated policy influences achieved? Did alternative ones emerge? What could be done differently in the future? - Were there sufficient resources allocated towards achievement of the objectives of the mobile courts’ support interventions? How well did the mobile courts’ support interventions leverage non-core resources towards achievement of results? - What effect did management and institutional arrangements have on the quality of mobile courts’ support interventions in terms of programming, delivery and monitoring for results? What measures were taken to assure the quality of development results and management practices, both in relation to process and products, and to partnership strategies? What monitoring and evaluation procedures were applied by UNDP and partners to ensure greater accountability? Effectiveness - Have the expected development (quantitative and qualitative) results been achieved and what were the supporting or impeding factors? - Were the approaches, resources, models and conceptual frameworks relevant to achieve intended outcomes and outputs? - What are the main lessons learned from the partnership strategies and what are the possibilities of replication? - Were UNDP’s comparative advantages perceived/interpreted and were these reflected in the division of responsibilities? - To what extent have interventions addressed transitional justice process and impunity of international crimes? - Which aspects of the interventions had the greatest achievements? What have been the supporting factors? How can UNDP build upon or replicate these achievements? - In which areas does the project component have the least achievements? What have been the constraining factors and why? How can they be overcome? - Were the approaches, resources, models and conceptual frameworks used for mobile courts support relevant to the achievement of planned outcomes/outputs? - What were the unintended results (positive/negative) of mobile courts assistance interventions? Sustainability - To what extent was the timeframe/timeline of support to mobile courts as an immediate measure to improve access to justice of the conflict-affected population taken into account? - To what extent were sustainability considerations were taken into account in the design and implementation of interventions? How was this concern reflected in the design of the project component, in the implementation of activities at different levels, in the delivery of outputs and the achievement of outcomes? - Were exit strategies for mobile courts’ support interventions appropriately defined and implemented, and what steps have been taken to ensure sustainability of results? - How the development of partnerships at the global, regional and national level contributed to sustainability of the results? - How different stakeholders been engaged in the design and implementation of mobile courts’ support interventions? Have interventions been implemented with appropriate and effective inter-agency and partnership strategies? What has been the nature and added value of these partnerships? |  |
| ### Duties and Responsibilities |  |
| Inception: Based on the indicative questions listed in the above section, project component and content specific questions will be elaborated further by the evaluation consultant in the inception report. The inception report should contain an evaluation matrix that displays for each of the evaluation criteria the questions and sub-questions that the evaluation will answer, and for each question, the primary and secondary data that will be collected. Data collection: In view of the complexity of the evaluation, the consultant will seek to obtain data from a range of sources, including desk reviews and document analyses, surveys and questionnaires, stakeholder consultations, interviews and focus group discussions at UNDP Headquarters and in a range of programme countries, UN agencies, international organizations, and other relevant institutions. The rationale for using a range of data sources (data, perceptions, evidence) is to triangulate findings in a situation where much of the data, due to the very complex nature of interventions, is qualitative, and its interpretation thus critically dependent on the evaluators’ judgment. Triangulation provides an important tool in filtering evidence by using different data sources to inform the analysis of specific issues. The evaluators will provide empirical evidence to support all conclusions and recommendations, and the evidence will be validated from multiple sources. Where possible and appropriate, the evaluation should seek to obtain evidence as to what might or might not have occurred in the absence of these interventions. A three-phased approach will be adopted in conducting the evaluation: First phase (Initial briefings/ meetings in New York and desk reviews): During this phase, the Evaluation consultant will conduct a desk review of relevant project documents and related documentation such as routine monitoring reports, project progress reports, and relevant review and evaluation reports, other analytical studies. The desk review will enable the consultant to: i) examine the quality of results baselines and indicators established for the projects; ii) assess the adequacy of the response strategies as reflected in the results framework; iii) review the quality of project baselines and indicators as well as existing monitoring mechanisms and resources (financial and human), and iv) conduct an initial assessment of progress towards results and/or impact as reflected in available progress reports. During the first two weeks of this phase the Evaluation Consultant will participate in briefings and meetings in UNDP and other UN agencies based in New York and interviews with the members of the Evaluation Reference Group. Within the first two weeks of the assignment the Evaluation Consultant will submit the inception report, describing the methodological/analytical framework for the evaluation and overall timeframe. The second phase (country visits): The in-country evaluations will require extensive review of existing documentation with particular attention to evaluations and studies, consultations with senior and operational managers and field staff, as well as consultations/interviews with a sample of beneficiaries. This will also include review of existing UNDP programme evaluations and assessments, studies, research and evaluations conducted by other development partners, and other relevant documentation. The Evaluation Consultant will conduct individual country visits to validate the documentary data against actual results on the ground. The focus will be to triangulate information from documents and interviews by gathering objective data on key achievements and areas for improvement. At the end of each country visit, the Evaluation Consultant is expected to present initial findings to the concerned country offices for validation of factual information and findings. The third phase (finalizing reports): The third phase of the evaluation will include finalization of the evaluation report, presentation of its findings to the Evaluation Reference Group and dissemination of lessons learned through existing UNDP mechanisms. The report should specifically highlight key lessons learned and good practices that could be replicated in future programs. Evaluation Products / Deliverables: - Inception report— detailing the evaluators’ understanding of what is being evaluated and why, showing how each evaluation question will be answered by way of: proposed methods, proposed sources of data and data collection procedures. The inception report will also include a proposed schedule of tasks, activities and deliverables, designating a team member with the lead responsibility for each task or product; - Draft evaluation report; and - Final evaluation report. Evaluatiuon Ethics: The evaluation will be conducted in accordance with the principles outlined in the UNEG “Ethical Guidelines for Evaluation” and evaluators must address, in the design and implementation of the evaluation critical issues, critical issues including evaluation ethics and procedures to safeguard the rights and confidentiality of information providers, such for example: measures to ensure compliance with legal codes governing areas such as provisions to collect and report data, particularly permissions needed to interview or obtain information about children and young people; provisions to store and maintain security of collected information; and protocols to ensure anonymity and confidentiality. Implementation Arrangements: The ROL Team and the Monitoring and Evaluation team (M&E) of the Bureau for Crisis Prevention and Recovery (BCPR) will jointly manage the evaluation process and ensure the coordination and liaison with concerned agencies at the headquarter level as well as the country level. An Evaluation Reference Group will be established at the outset of the evaluation, consisting of key stakeholders and partners, i.e. focal points/representative from UN agencies, multilateral development banks (the World Bank), academia, as well as client countries’ representatives and implementing partners. The Reference Group will play an important role in providing strategic, methodological and substantive inputs into the evaluation process, as well as feedback on the inception and final evaluation report. In addition, the reference group will ensure that the evaluation results are appropriately disseminated and discussed within their respective organizations. |  |
| ### Competencies |  |
| - Superior leadership and strategic management skills with an excellent understanding of international development issues and knowledge of the UN system; - Strong written and verbal communication skills, in a multi-cultural setting; ability to conduct results-based management and reporting, objectivity and ability to analyze large multi-country data sets in short period; - Experience working collaboratively in small teams with tight deadlines. |  |
| ### Required Skills and Experience |  |
| Education: - Masters or PhD in law or other relevant fields. Experience: - At least 7 years of international development experience or well established and well-functioning organization with at least 5 years of experience in project/programme design and implementation; - Relevant professional experience in evaluation of rule of law or other relevant programmes – at national, regional, and global levels; - Strong monitoring and evaluation background, sound methodological skills and knowledge of evaluation methods and techniques; - Extensive experience in working with the UN/multilateral development agencies, UNDP country offices and/or regional centres is an asset. |  |

L’appui du PNUD dans l’organisation des audiences foraines

RAPPORT D’EVALUATION

Carrefour de la justice, Goma, RDC

Rapport pays n.2

Les audiences foraines en République Démocratique du Congo

Commissionné par le PNUD (Bureau pour la Prévention de Crises et le Relèvement)

Rédigé par Monica Rispo (consultante independente)

Mai 2013

Table des matières

Liste des acronymes et abréviations ………………………………………………………………………………………………	p. 3

Résume Exécutif  ……………………………………………………………………………………………………………………………	p. 4

PARTIE I : INTRODUCTION

1. 	Justification et objectifs de l’évaluation ………………………………………………………………………………	p. 8

2.        Méthodologie et limitations de l’évaluation ……………………………………………………………………….	p. 8

3.        Description des activités évaluées ………………………………………………………………………………………	p. 9

4. 	Hiérarchie des juridictions et carte judiciaire de la RDC ………………………………………………………	p. 10

PARTIE II : EVALUATION DE L’APPUI AUX AUDIENCES FORAINES

5.  	pertinence

5.1. Le modèle congolais d’audience foraine ………………………………………………………………………..	p. 14

5.2. La pertinence avec les politiques nationales en matière de justice…………………………………	p. 20

5.3. La pertinence avec les besoins des bénéficiaires ……………………………………………………………	p. 23

5.4. La pertinence avec le principe d’appropriation nationale ………………………………………………. p. 25

6.  	efficacite

6.1. Planification et suivi ……………………………………………………………………………………………………….	p. 26

6.2. Les résultats atteints ………………………………………………………………………………………………………	p. 30

6.3. La qualité des résultats atteints ……………………………………………………………………………………..	p. 31

6.4. La poursuite des crimes internationaux en complémentarité avec la CPI ………………………. p. 37

7.  	efficiance

7.1. Viabilité financière ………………………………………………………………………………………………………..	p. 40

7.2. La coordination entre partenaires internationaux …………………………………………………………	p. 42

7.3. Contraintes et défis ……………………………………………………………………………………………………….	p. 43

7.4. Meilleures pratiques ……………………………………………………………………………………………………… 	p. 44

7.	durabilite

8.1. La pérennisation des résultats atteints ………………………………………………………………………….	p. 44

9.	impact

9.1. Les changements produits par les AF …………………………………………………………………………… 	p. 45

PARTIE III: CONCLUSIONS ET RECCOMENDATIONS

10. Conclusions ……………………………………………………………………………………………………………………………….	p. 47

11. Recommandations …………………………………………………………………………………………………………………….	p. 49

ANNEXES

- Liste des documents consultés

- Liste des personnes rencontrées

- Tableau récapitulatif des AF appuyées par les PNUD en 2011 et 2012

- Termes de référence

- Matrice d’évaluation 
Acronymes et abréviations

ABA-ROLI: American Bar Association Rule of Law Initiative

AF : Audience foraine

ASF : Avocats sans Frontières

BCNUDH : Bureau Conjoint des Nations Unies aux Droits de l'Homme

BCPR: Bureau for Crisis Prevention and Recovery (UNDP)

BP : Bureau Pays

CAP : Cellule d’appui aux poursuites

CM : Cour Militaire

CPI : Cour Pénale Internationale

FDLR : Forces démocratiques pour la libération du Rwanda

MONUSCO : Mission de l'Organisation des Nations Unies pour la Stabilisation en RDC

PNUD : Programme des Nations Unies pour le développement

RCN : RCN Justice & Démocratie

RDC : République Démocratique du Congo

REJUSCO: European Union Program for the Restoration of Justice in Eastern Congo

STAREC: Programme de Stabilisation et de Reconstruction des zones sortant des conflits armés

SIDA: Swedish International Development Cooperation Agency

CA : Cour d’Appel

SOFEPADI : Solidarité féminine pour la paix et le développent intégral

TDR : Termes de référence

TGI : Tribunal de grande instance

TMG : Tribunal Militaire de Garnison

Tripaix : Tribunal de paix

UNICEF: United Nations Children's Fund

VBG : Violences Basées sur le Genre

Remerciements

C'est avec sincère gratitude que je souhaite remercier toutes les personnes rencontrées au cours du processus d'évaluation. En particulier mes remerciements s’adressent au personnel du PNUD en RDC et au personnel BCPR à New York pour leurs précieuses contributions et entière disponibilité; je tiens aussi à renouveler ma reconnaissance aux représentants des autorités congolaises et aux partenaires de développement rencontrés au cours de la mission à l’Est de la RDC pour le temps qu’ils ont consacré à cette évaluation et le partage d’information.

La consultante

Monica Rispo

Résume Exécutif

Le présent rapport est développé dans le cadre d’une évaluation, commissionnée par le PNUD/BCPR, intitulée « Evaluation of support to mobile courts arrangements in post-conflict situations ». L’objectif est d’évaluer les résultats, identifier les bonnes pratiques et les leçons apprises au cours des interventions du PNUD en appui  la mise en place d’audiences foraines dans le cadre des programmes de renforcement de l’état de droit du PNUD dans les situations de post-conflit.

Comme indiqué dans les TDR et spécifié dans le Rapport de Démarrage, l'évaluation prévoit la visite d'un consultant international dans trois Bureaux Pays du PNUD (Sierra Leone, RDC et Somalie) ainsi qu’une revue documentaire relative à des Bureaux Pays additionnels (Timor Leste et la République Centrafricaine).

Le présent rapport présente les résultats de la mission à l’Est de République Démocratique du Congo (Goma, Bunia, Bukavu).

L’organisation des audiences foraines (AF) a été introduite dans le système judiciaire congolais dans les années 80 et c’est depuis 2004 que les partenaires internationaux appuient les juridictions congolaises à les mettre en place. En Avril 2013 la nouvelle « loi  de reforme de l’organisation judiciaire » a réaffirmé le principe de la justice itinérante.

Le PNUD a appuyé les AF à l’est de la RDC (Nord Kivu, Sud Kivu et Ituri) depuis 2010 avec un engagement financier de 155.000 USD sur la période 2010-2012. Les jurisdictions appuyées par le PNUD dans l’organisation des AF sont en priorité militaires (Tribunal Militaire de Garnison et Cour Militaire), mais les jurisdiction civiles (Tribunal de Grande Instance et Cour d’Appel) sont également soutenues. Les dossiers pris en charge sont exclusivement de nature pénale, avec une priorité pour les VBG.

Le modèle congolais d’AF n’est pas développé dans le cadre d’une stratégie spécifique d’intervention (contrairement au modèle sierra léonais), mais représente un apport conjoncturel pour régler des affaires judiciaires ponctuelles qui émergent du conflit en cours à  l’Est de la RDC.

Un aspect propre au modèle congolais est sa complémentarité avec la Cour Pénale Internationale. De 2011 a 2012 au moins 10 dossiers de crimes internationaux (crimes contre l’humanité et crimes de guerre) ont été traitées par les AF appuyées par le PNUD, ce qui a représenté une importante opportunité pour renforcer les capacités des juridictions nationales dans la poursuite des crimes prévus par le Statut de Rome. Par ailleurs c’est principalement dans le cadre de la justice itinérante que la jurisprudence congolaise en matière de justice pénale internationale est entrain de se consolider.

Des bonnes pratiques ont été développées dans le cadre du système de justice itinérante appuyé par le PNUD, notamment : 1) l’approche intégrée, qui appuie toutes les phases de la chaine pénale 2) la participation en synergie et en complémentarité de différents partenaires internationaux dans l’organisation des AF 3) l’inclusion des AF dans le système de monitoring judiciaire du PNUD.

Le modèle congolais d’AF présente des aspects qui sont objet de débat au sein de la communauté juridique, notamment l’appui prioritaire aux dossiers de violences basées sur le genre et aux juridictions militaires. Le cout élevé d’une AF, par ailleurs entièrement financé par les partenaires internationaux, reste une des majeures contraintes de l’initiative et une faiblesse en termes de durabilité.

Les remarques ci-dessous consolident les observations recueillies au cours des entretiens et présentent des conclusions générales pour chaque critère d’évaluation.

# Pertinence

Les AF sont une priorité reconnue dans la législation congolaise et dans les stratégies nationales du secteur de la justice, toutefois les modalités de leur mise en œuvre pourraient être mieux encadrées,  éventuellement par un Protocole d’entente entre les partenaires internationaux et les autorités judiciaires.  Le manque d’orientation de la part des autorités centrales combiné avec l’absence d’une planification stratégique au niveau provincial s’est traduit dans la pratique avec l’organisation d’AF qui répondent à un besoin ponctuel et représentent un modèle fortement influencé par les priorités des bailleurs de fond.

Les AF ont étés une mesure efficace pour atteindre les zones reculées où les juridictions permanentes étaient absentes et lutter contre l’impunité des crimes internationaux commis dans ces territoires.

Les AF ont été très pertinentes par rapport aux politiques nationales de lutte contre les VBG, notamment dans les cas de VBG commises par les militaires,  vu la priorité accordée par les AF a cette catégorie de dossiers. Une réflexion serait toutefois nécessaire sur l’opportunité de commencer à élargir le champ d’intervention des AF à toutes les infractions : non seulement parce que les auteurs de viol sont de plus en plus des civils, mais aussi dans le but d’assurer aux victimes non-VBG les mêmes opportunités d’accéder à la justice que les victimes VBG. Le PNUD a pris en compte ces aspects en réduisant le nombre minimal de dossiers VBG requis pour appuyer une AF.

# Efficacité

La planification de l’initiative pourrait bénéficier d’un cadre des ressources plus spécifique, éventuellement avec des indicateurs, cibles et aspects financiers harmonisées entre tous les partenaires internationaux qui appuient les AF. Le suivi des AF dans le cadre du projet « monitoring judiciaire » est une excellente initiative qui a permis d’avoir un aperçu impartial des résultats atteints par les AF; des faiblesses ont pourtant été relevées au niveau du système de collecte des données relatives aux AF observées.

Des résultats satisfaisants ont été réalisés, mais en absence d’indicateurs spécifiques il est difficile d’en préciser la mesure par rapport aux cibles. Au courant du 2011 et 2012, un total de 16 audiences foraines ont été organisées avec l’appui du PNUD pour 198 jours en foraine et une contribution de 155.000 USD. 97 avocats et 72 magistrats/juges assesseurs ont participé aux AF. 202 dossiers ont été enrôlés, dont 60% de VBG et 206 jugements ont été prononcés.

La pratique judiciaire des AF apparait en général en bonne voie vers la conformité avec les standards internationaux, sauf pour les aspects suivants qui devraient être renforcés : 1) la parité des armes entre les parties au procès 2) la protection des victimes et des témoins 3) certains aspects de la procédure militaire, comme le régime de la détention préventive 4) l’exécution des jugements 4) la durée et l’excessive célérité des AF.

Efficience

Le cout des AF analysées varie entre 8.000 et 25.000 USD en fonction du nombre de dossiers, de victimes et d’autres éléments; ces frais sont entièrement soutenus par les partenaires internationaux. Les budgets s’élèvent significativement si l’on inclue les activités préliminaires et les services de transport aérien et de sécurité fournis par la MONUSCO, au point qu’ils semblent difficilement soutenables par le gouvernement congolais. Les procédures financières du PNUD ont été jugées trop complexes et la gestion financière administrée uniquement par les partenaires internationaux affaiblis l’appropriation nationale.

L’appui aux AF s’est développé en excellente synergie et en toute complémentarité entre les partenaires internationaux qui contribuent, en termes d’assistance technique et financière et sur la base des respectifs avantages comparatifs, à l’organisation de chaque AF. Cette coordination pourrait bénéficier d’un cadre de travail formel, comme un Protocole d’entente, afin d’améliorer la planification, le suivi et l’harmonisation de certains aspects des interventions.

Durabilité

Certains éléments de durabilité des AF sont évidents: non seulement cette pratique existe dans le système judiciaire congolais depuis 1979, mais aussi les autorités judiciaires ont démontré d’avoir acquis des bonnes compétences dans l’organisation des AF au cours des années de collaboration avec le PNUD. Le manque de moyens financiers pour soutenir les couts élevés des AF combinée avec l’absence d’une stratégie nationale pour les AF, conduit toutefois à la conclusion que les juridictions congolaises ne seront pas en mesure de continuer à organiser les AF dans le futur proche sans un appui de la communauté internationale. Dans quelques rares occasions les juridictions ont organisé des AF sans appui financier extérieur, en particulier le TGI de Bunia.

Malgré les AF soient menées entièrement par les autorités judiciaires nationales et avec un bon niveau de compétence technique, l’appropriation nationale de l’initiative reste faible, notamment dans la planification, le suivi et la gestion financière.

Impact

Les AF ont un effet dissuasif sur les criminels et créent plus de sécurité dans les communautés en réduisant le taux de criminalité. Elles ont favorisé le retour progressif de la confiance de la population dans la justice et le rapprochement de la justice aux justiciables. En observant les procès, la population a pu mieux comprendre le fonctionnement du système judiciaire; la fonction pédagogique des AF pourrait toutefois être renforcée en augmentant et rendent plus systématiques les sensibilisations pour la population visant à expliquer le rôle et les objectifs des AF. Dans certaines zones visitées par les AF c’était la première fois que la population entrait en contact avec le système de justice formelle.

Les AF ont eu un impact positif sur la promotion et l’application du droit pénal international en complémentarité avec la CPI. Les AF ont renforcé la capacité des autorités nationales de poursuivre et juger des crimes internationaux. Un nombre croissant de dossiers de crimes de guerre et crimes contre l’humanité est traité par les AF : au moins 8  de ces dossiers ont été jugés au cours des AF appuyées par le PNUD dans l’est de RDC.  Les importants défis de cette nouvelle branche du droit congolais dérivent principalement de l’absence d’un cadre juridique de référence : le retards dans l’adoption d’une loi de mise en œuvre du Statut de Rome pose aux juridictions la question du choix du droit applicable (Statut de Rome ou législation congolaise) et laisse ouvert le débat sur la compétence exclusive des juridictions miliaires ou civiles pour les crimes internationaux.

Les recommandations illustrées dans le corps du rapport afin d’améliorer la mise en œuvre des AF sont résumées dans les points ci-dessous.

- Appuyer davantage les AF organisées par les juridictions civiles et mener une réflexion sur l’opportunité de graduellement réduire le nombre d’AF militaires ;

- Discuter avec les bailleurs la possibilité d’abolir le critère de la priorité des dossiers VBG pour l’organisation d’une AF et élargir la prise en charge  á toutes les infractions ;

- Développer une stratégie d’intervention pour les AF, éventuellement en adoptant un système d’AF mixte et en rédigeant un Protocole d’entente annuel entre les partenaires internationaux qui appuient les AF et les autorités judiciaires ;

- Prévoir une stratégie de transfert des compétences aux juridictions congolaises et renforcer l’appropriation nationale en vue de ce transfert, en assurant une participation plus active des juridictions dans les activités de suivi, de gestion financière et de planification ;

- Graduellement transférer la gestion financière aux autorités judiciaires congolaises et mener une réflexion sur l’opportunité de créer un basket-fund pour la gestion en commun des fonds que la communauté internationale destine aux AF ;

- Améliorer le suivi et promouvoir la consolidation des acquis des AF ;

- Renforcer certains  aspects juridiques (présence des  avocats des prévenus ; mesures de protection des victimes et des témoins ; exécution des jugements, notamment en matière de condamnation civile…)

PARTIE I : INTRODUCTION

Les Audiences Foraines (AF) sont définies comme « des audiences judiciaires tenues par un Tribunal dans son ressort géographique mais en dehors de son siège ordinaire, normalement dans des localités éloignées où les services de justice ne sont pas disponibles»

Les audiences foraines comportent le déplacement d’une équipe de juges, procureurs, greffiers, policiers dans les territoires reculées avec l’objectif principal de faciliter l'accès à la justice, en particulier pour les groupes vulnérables qui n'auraient autrement pas la possibilité de saisir le système de la justice formelle.

Le présent rapport est développé dans le cadre d’une évaluation commissionnée par le PNUD/BCPR et intitulée « Evaluation of support to mobile courts arrangements in post-conflict situations ».

Le nombre croissant de Bureaux Pays PNUD (BP) qui appuient les AF organisées par des juridictions nationales et le nombre limité d'études approfondies consacrées à ce sujet, ont motivé le Bureau pour la Prévention de Crises et le Relèvement (BCPR) à engager une évaluation pour analyser les résultats, l'impact, les bonnes pratiques et les leçons apprises développées dans le cadre des audiences foraines appuyées par le PNUD, avec une attention particulière au contexte post-conflit.

Comme indiqué dans les TDR et plus en détail dans le Rapport de Démarrage, l'évaluation comprend la mission d'un consultant international dans 3 BP (Sierra Leone, RDC et Somalie) et une revue de la documentation de référence produite par des BP additionnels qui appuient les audiences foraines (République Centrafricaine et Timor Leste).

Le présent rapport présente les conclusions de la mission en République Démocratique du Congo.

§ 1. Justification et objectifs de l’évaluation

Le présent rapport s’adresse au personnel du PNUD/BCPR et aux autorités judiciaires congolaises. Ses deux objectifs principaux sont:

- La présentation de recommandations au Bureau Pays PNUD et au gouvernement congolais pour améliorer l’appui et la mise en œuvre des audiences foraines.

- La consolidation des connaissances, des acquis et des leçons apprises au cours des interventions pour une éventuelle réplication de l’expérience  dans d’autres pays avec le soutien du PNUD.

Le rapport est structuré en 3 parties: la première partie présente une description de la méthodologie et un bref aperçu du contexte; la deuxième partie présente les résultats de l'évaluation selon les critères retenus (pertinence, efficacité, efficience, durabilité et impact) et la troisième partie soumet les conclusions et les recommandations.

§ 2. Méthodologie et limitations de l’évaluation

L’évaluation a été menée par une consultante indépendante et a consisté en une phase d’analyse des documents de base suivie par une mission à l’Est de la RDC du 18 au 23 Mars 2013. Les termes de référence sont disponibles dans l’annexe 4.

La mission à l’Est de la RDC a permis de visiter les 3 Sous-Bureaux  du PNUD qui mettent en œuvre le programme d’accès à la justice dans le cadre duquel sont appuyées les audiences foraines (Goma, Bunia et Bukavu) et de mener des entretiens avec approximativement 35 intervenants clés, y compris les acteurs du système judiciaire, de la police et du système pénitencier, les organisations de la société civile, des partenaires internationaux et les équipes du PNUD.

La consultante a eu l’opportunité de participer à deux réunions des « cadres de concertation des AF » pour la préparation des AF au Nord Kivu et Ituri et a rencontré collectivement les membres de la Task Force Justice au Sud Kivu.

La méthodologie de l'évaluation est illustrée dans le Rapport de Démarrage et fait référence à des méthodes de recherche qualitative et quantitative. (Entretiens individuels et analyse de documents de référence tels que les rapports  du PNUD et d’autres partenaires, littérature juridique)

Les questions de l’évaluation et les sous-questions sont identifiées dans la Matrice d’Evaluation (voir annexe 4) sur la base des TDR et reflètent les 5 critères de pertinence, efficacité, efficience, durabilité et impact.

La contrainte majeure qui s’est manifestée au cours de l’évaluation a été l’impossibilité, pour des raisons logistiques, d’organiser des rencontres avec les usagers des AF et d’observer le déroulement d’une AF : il n’a donc pas été possible de refléter dans le présent rapport le point de vue des bénéficiaires, comme prévu dans le Rapport de Démarrage. Une analyse sera proposée à travers les opinions des personnes rencontrées.

Comme illustré en détail au § 6.1, le système de collecte des données statistiques relatives aux AF présente des faiblesses tant au niveau des partenaires internationaux que des juridictions, ce qui n’a pas permis une analyse des résultats atteints suffisamment détaillée par rapport á certains aspects de l’initiative.

§ 3. Description des activités évaluées

Le PNUD appuie l’organisation des audiences foraines dans l’est de la RDC depuis 2010.

L’appui aux AF est planifié dans le cadre de deux projets suivants qui interviennent au Sud Kivu, Nord Kivu et en Ituri :

- « Renforcement de la capacité du système judiciaire militaire d’enquêter et de poursuivre les crimes des violences sexuelles dans l’est de la RDC », financé par US Department of State Bureau of Democracy, Human Rights and Labor (DRL) (par la suite projet 1888)

- « Renforcement de l'accès des femmes à la justice : sécurisation et autonomisation des populations dans les Kivus et en Ituri », financé par le Swedish International Development Cooperation Agency (par la suite projet SIDA)

Les AF sont planifiées en tant que composante spécifique de projets plus amples dans le domaine de l’accès à la justice. Il est donc justifié qu’au niveau de la planification les AF n’ont pas été objet d’une description détaillée, et ne présentent pas des indicateurs spécifiques dans les documents de projets.

Par ailleurs en RDC l’appui du PNUD aux AF n’est  pas réglé par un Protocole d’entente avec les autorités judiciaires, comme c’est le cas dans d’autres pays (Sierra Leone, Somalie).

Le « cadre de ressources et des résultats » pour la présente évaluation (activités, indicateurs, cibles..) sera donc identifié en consolidant les différents documents disponibles : les comptes rendu des réunions pour l’organisation des AF, les lettres des requête des AF par les juridictions, ainsi que les TRD pour les AF.

Vu la difficulté d’avoir un cadre de référence consolidé, l’objet de la présente évaluation sera identifié génériquement avec l’ensemble des activités appuyées par le PNUD pour l’organisation des AF dans le cadre des deux projets susmentionnés pendant la période 01/2011- 12/2012.

Les activités préliminaires aux AF, comme les enquêtes du Parquet, ne seront pas évaluées.

§ 4. Aperçu de l'organisation judiciaire congolaise

Pour une analyse approfondie du système judiciaire congolais on renvoie aux nombreuses études qui ont été publiées.

Dans le cadre de la présente évaluation, il est toutefois important de rappeler la carte judiciaire pour les juridictions civiles (de droit commun) et militaires afin de mieux comprendre le cadre juridique dans lequel se tiennent les AF.

Les paragraphes suivants illustrent ces aspects, avec une attention aux juridictions qui siègent en foraine et en matière pénale. Généralement il s’agit du Tribunal de Grande Instance (TGI) et de la Cour d’Appel (CA) pour les juridictions civiles et du Tribunal Militaire de Garnison (TMG) et de la Cour Militaire (CM) pour les juridictions militaires (en bleu dans le tableau). Quelques ONG appuient les Tribunaux de Paix itinérants.

Les Tribunaux pour Enfants, créés en 2009 en principe dans chaque chef lieu de province, peuvent aussi siéger en foraine.

Il convient également d’anticiper ci-dessous deux aspects clés par rapport à la compétence des jurisdictions militaires :

- les juridictions militaires ont une compétence personnelle étendue à la police et aux civils.

- Jusqu’ à récemment, comme illustré plus en détail au § 5.1, les militaires avaient une juridiction exclusive en matière de crimes internationaux, mais en Avril 2013 la nouvelle loi portant « organisation fonctionnement et compétences des juridictions de l’ordre judiciaire » a élargi cette compétence aux juridictions civiles, en particulier aux Cours d’Appel.

A) hiérarchie et carte judiciaire des juridictions civiles  :

- 1. Tribunal de paix (Tripaix)

Les Tripaix sont des juridictions de 1er ressort situés dans chaque ville et zone rurale en nombre théorique de 140 à travers le pays. A l’Est de la RDC un certain nombre de Tripaix sont construits (inter alia avec l’appui du PNUD) mais ne sont pas encore opérationnels, faute d’affectation des magistrats.

En matière pénale les Tripaix connaissent des infractions punissables au maximum de 5 ans de servitude pénale, ils ne sont donc pas compétents pour traiter la plupart des dossiers impliquant les violences sexuelles, les peines prévues par le code pénal en cas de violence sexuelle pouvant aller jusqu’à 20 ans.

- 2. Tribunal de grande instance (TGI)

Les TGIs, prévus dans chaque ville de province, connaissent des infractions punissables de la peine de mort et de celles punissables d'une peine excédant cinq ans de servitude pénale principale ou des travaux forcés. Ils connaissent également de l'appel des jugements rendus en première instance  par les tribunaux de paix. Des sièges secondaires des TGI peuvent être crées dans les territoires de leurs ressorts.

- 3. Cour d’appel (CA)

Les CA connaissent des appels des jugements rendus en premier ressort par les TGI et sont situées dans chaque chef-lieu de province. La loi d’Avril 2013 reconnait aux CA la jurisdiction pour « crime de génocide, crime de guerre et crimes contre l’humanité commis par les personnes relevant de leur compétence et de celle des tribunaux de grande instance ». Les CAs sont proposées comme juridictions exclusives compétentes au premier degré pour les crimes internationaux par le projet de loi de mise en œuvre du Statut de Rome en RDC.

- 4. Cour Suprême de la Justice

La Cour Suprême se trouve au sommet de la hiérarchie judiciaire en ce qu’elle connaît de l’appel des arrêts rendus au premier degré  par les Cours d’Appel. Dans le cadre de la réforme introduite par la Constitution de 2006 et toujours en cours, la Cour Suprême de la Justice sera remplacée par 3 institutions: la Cour Constitutionnelle, la Cour de Cassation et le Conseil d’État.

B) hiérarchie et carte judiciaire des juridictions militaires

- 1. Tribunal militaire de police (TMP)

Les TMP peuvent être établis dans le ressort du Tribunal de Garnison et « connaissent des infractions punissables de un an de servitude pénale, au maximum » commises par les militaires des Forces Armées Congolaises, et les membres de la Police Nationale de même rang d’un grade inférieur à celui de Major». Ces tribunaux sont prévus par le code judiciaire militaire, mais ne sont pas encore opérationnels dans les zones qui font l’objet de la présente évaluation.

- 2. Tribunal militaire de garnison (TMG)

Les TMG siègent dans les chefs-lieux des districts ou dans les villes où est situé l’Etat-Major de la garnison. Ils connaissent des infractions punissables de la peine de mort et celles supérieures à un an ainsi que de l’appel des jugements rendus par le Tribunal Militaire de Police. Sont justiciables du TMG les militaires des Forces Armées Congolaises d’un grade inférieur à celui de Major et les membres de la Police Nationale et du Service National de même rang.

- 3. Cour militaire (CM) et Cour militaire opérationnelle

Les CMs, sont prévues dans chaque chef-lieu de province ou dans la localité où se trouve le quartier général de

la Région Militaire. Les CM connaissent, au premier degré, des infractions commises par les personnes

énumérées à l’article 121 du code judiciaire militaire (par exemple les officiers supérieurs des Forces Armées Congolaises) ainsi que de l’appel des jugements rendus par les TMG.

Les Cours militaires opérationnelles sont des juridictions temporaires qui accompagnent les troupes dans les zones d’opération de guerre pour juger les crimes commis dans ces contextes; elles ont le même rang et la même compétence que les CM mais les arrêts qu’elles rendent ne sont pas susceptibles d’appel. Une CM opérationnelle est présente au Nord Kivu depuis 2008.

- 4. Haute Cour militaire

La Haute Cour siège à Kinshasa, mais en temps de guerre le Président de la République peut décider d’organiser des chambres foraines dans les zones opérationnelles. Son ressort s’étend sur tout le territoire de la République.

Il convient finalement de souligner que les efforts du Gouvernement finalisés au recrutement de magistrats additionnels en 2011 ont créé un écart important entre le nombre de magistrats du parquet et le nombre de magistrats du siège dans les juridictions civiles, vu que la première étape dans la carrière d’un magistrat est celle de Substitut Procureur au Parquet. Par exemple au mois d’Avril 2013 á l’est de la RDC, on comptait :

- 43 magistrats au Parquet et 9 au siège pour le TGI de Goma;

- 45 magistrats au Parquet et 5 au siège pour le TGI de Bukavu ; et

- 57 magistrats au Parquet et 4 au siège pour TGI de Bunia.

Par conséquent, les juridictions civiles se retrouvent souvent confrontées au problème que les dossiers envoyés par les Procureurs au tribunal ne peuvent pas être vidés car les Juges sont débordés.

Les statistiques du monitoring judiciaire PNUD reflètent cet écart : par exemple en 2012 le Parquet de Bunia a reçu de la police 500 dossiers, ils ont transféré 420 dossiers au tribunal, mais seulement 50 jugements ont été émis dans la même période.

Dans une approche « ne pas nuire» (do no harm), il faudra assurer une attention particulière à ce que les juridictions civiles, déjà dégarnies de juges, ne soient pas paralysées quand les magistrates siègent en foraine.

A noter que cette problématique se pose en moindre mesure pour les juridictions militaires, qui sont celles appuyées en priorité par le PNUD dans le cadre des AF. En effet les AF militaires prévoient un 1 seul magistrat de carrière et 4 assesseurs (notamment des militaires qui n’ont pas de formation spécifique en droit et qui sont identifiés sur place).

PARTIE II : EVALUATION DE L’APPUI AUX AUDIANCES FORAINES

# 5. PERTINENCE

§ 5.1 Le modèle congolais d’audience foraine

► Modèle, base légale et composition des juridictions en foraine

L’organisation des AF a été introduite dans le système judiciaire congolais par un arrêté de 1979 en application de l’article 67 du code d’organisation et de compétence judiciaire. L’arrêté précise que « les présidents de la Cour d’Appel et du Tribunal de Grande Instance peuvent fixer des audiences foraines qui se tiendront en dehors du siège ordinaire du ressort, si l’administration d’une bonne justice l’exige».

Des dispositions similaires sont prévues dans le code judiciaire militaire de 2003.

En Avril 2013 la nouvelle loi  de reforme de l’organisation judiciaire a introduit une Sous-section intitulée « Des audiences foraines »  qui réaffirme le principe de la justice itinérante; á noter l’article 47 qui prévoit « l’itinérance ne peut empêcher le fonctionnement de la juridiction au siège ordinaire »

Etant entendu que les AF sont un mécanisme bien intégré dans le système judiciaire congolais, il faut reconnaître que depuis 2004 les partenaires internationaux jouent un rôle important dans le processus de redynamisation des AF en appuyant les juridictions congolaises à les organiser. A noter que l’appui du PNUD et de la majorité des partenaires internationaux vise en priorité les dossiers criminels et qu’un nombre croissant de dossiers concerne la poursuite de crimes internationaux en complémentarité avec la Cour Pénale Internationale (CPI)

L’organisation d’une AF se compose de plusieurs étapes en séquence qui demandent d’importants efforts de coordination entre les acteurs du système judiciaire et de sécurité, ainsi qu’entre les partenaires internationaux.

Ces étapes sont résumées ci-dessus.

- La juridiction civile ou militaire identifie un besoin d’organiser une AF dans son ressort de compétence et présente une demande d’appui aux partenaires internationaux. (voire copie dans l’annexe 6). Cette phase est parfois précédée par un appui financier aux Parquets ou aux Auditorats militaires pour mener les enquêtes dans les zones où les infractions ont été commises.

- Un forum de coordination, réunissant les partenaires internationaux et les représentants des juridictions, analyse la pertinence de la demande d’appui, la disponibilité des fonds et l’état des dossiers à traiter en foraine.

- L’appui est octroyé et le Barreau désigne les avocats pour les prévenus et les victimes afin qu’ils vérifient que les prévenus se trouvent effectivement en détention et qu’ils puissent rencontrer les victimes pour les assister dans l’éventuelle constitution de partie civile. Les avocats lisent également les dossiers au greffe en vue de préparer leurs différents moyens.

- Le Président du tribunal fixe la date de l’AF et le greffier descend sur le terrain quelques jours à l’avance pour faire les notifications des dates d’audience aux parties des procès.

- L’équipe foraine se déplace vers les lieux où se tiennent les audiences ; généralement elles sont organisées dans de structures ad hoc, comme des tentes ou d’autres abris temporaires.

La composition des juridictions en foraine est particulièrement nombreuse car, s’agissant toujours d’une formation collégiale, elle implique le déplacement d’un nombre élevé de magistrats.

Par exemple la chambre foraine d’un Tribunal de Grande Instance est composée de 3 juges du siège, 1 juge du Parquet et un 1 greffier.

La chambre foraine d’un Tribunal Militaire de Garnison est composée de 5 juges: 1 magistrat de carrière et 4 assesseurs (notamment des militaires qui n’ont pas de formation spécifique en droit et qui sont identifiés sur place), 1 auditeur militaire (qui exerce les fonctions de Ministère Public); 1 greffier.

D’autres membres intègrent les équipes des AF : les avocats, les interprètes, la police pour l’escorte des prévenus et des condamnés.

► Les activités préliminaires aux AF

La raison principale qui détermine un taux de jugements très élevé par rapport aux dossiers enrôlés au cours des AF sont les efforts dédiés á la préparation des AF. Ces activités préliminaires permettent d’assurer la présence des victimes, des témoins, des prévenus ainsi que la mise en état des tous les dossiers avec la conséquence que les renvois d’audiences ont rarement lieu.

Notamment il s’agit des activités suivantes :

- l’appui au Parquets pour effectuer des descentes sur le terrain afin de mener les enquêtes préliminaires ;

- l’appui aux greffiers pour descendre sur le terrain afin de signifier les actes aux parties du procès ;

- la préparation aux audiences des parties civiles par les avocats ;

- le transfert des prévenus (la plupart étant en détention préventive) ;

- les séances de sensibilisations pour la population sur les procédures judiciaires et le rôle des AF, qui sont occasionnellement organisées avant la tenue les AF.

Concernant le transfert des prévenus il convient de préciser que, quand les juridictions demandent l’appui aux partenaires internationaux pour organiser une AF, les prévenus qui ont été arrêtés dans les territoires reculées se trouvent généralement en détention préventive dans les prisons centrales des provinces (notamment Goma, Bunia et Bukavu) après y avoir être transféré depuis les cachots de la police dans les territoires.

Plus précisément, quand la police appréhende un présumé auteur dans une zone où il n y a pas d’autorités judiciaires, après l’avoir gardé à vue pendent 48 heures elle demande un appui aux partenaires internationaux pour transférer le détenu à la prison centrale de la province afin que le Parquet puisse valider la détention préventive. Avant la date fixée pour l’AF le détenu est re-transféré sur les lieux où a été commise l’infraction et où se tient l’AF.

Cette procédure assure la présence du prévenu au procès, mais implique aussi des importants efforts, inter alia en termes financier, d’autant plus qu’il faut aussi considérer les frais de restauration et de transport de l’escorte.

Dans le cadre des activités complémentaires aux AF, il convient également mentionner le « projet  monitoring judiciaire » mis en place par le PNUD dans l’Est de la RDC afin d’assurer le monitoring des procédures judiciaires et de police, ainsi que l’observation d’un échantillon d’audiences, y compris celles conduites en foraine.  Comme illustré au § 6.1, la présence des équipes de moniteurs judiciaires PNUD a promu l’application des standards internationaux du procès équitable et a permis d’avoir un aperçu impartial des résultats atteints par les AF.

► Aspects controversés du modèle congolais d’audience foraine

Les paragraphes suivants illustrent  des aspects du modèle congolais des AF qui sont objet de débat au sein de la communauté juridique nationale et internationale et méritent donc une réflexion spécifique.

A) L’appui aux juridictions militaires

Les statistiques 2011 et 2012, illustrées au § 6.2, indiquent que le PNUD a appuyé en priorité les AF des juridictions militaires: dans cette période, sur un total de 16 AF organisées dans l’Est de la RDC, 12 étaient des AF menées par des juridictions militaires.

A noter que le soutien aux juridictions militaires est une priorité pour l’un des deux projets PNUD en appui aux  AF. De même, au sein de la MONUSCO des cellules d’appui aux poursuites judiciaires (CAP) ont été mises en place avec le mandat de « aider les autorités des Forces armées de la République démocratique du Congo (FARDC) chargées de la justice militaire à poursuivre les personnes arrêtées par les FARDC »  .

La  collaboration entre le PNUD et les juridictions militaires a produit des résultats satisfaisants comme sera illustré en détail au § 6.2, il convient néanmoins de rappeler que nombreuses études publiées et quelques entretiens au cours de la mission d’évaluation ont révélé certaines faiblesses du système judiciaire militaire. Elles sont brièvement décrites ci-dessous afin qu’elles puissent être tenues en considération dans la planification future et éventuellement inspirer une réflexion sur l’opportunité d’élargir l’appui du PNUD aux juridictions civiles et progressivement réduire l’appui aux militaires.

Un premier aspect controversé concerne la compétence personnelle des juridictions militaires étendue aux civils « qui commettent des infractions impliquant des armes de guerre ou lorsqu’ils sont associés aux militaires dans la commission des crimes de leur compétence ».

Nombreux rapports dénoncent cette loi comme contraire aux standards internationaux et régionaux ainsi qu’à la Constitution congolaise et affirmant que la compétence des juridictions militaires devrait être limitée aux membres des forces armées à l’exclusion des civils.

Interrogées à ce sujet les autorités judiciaires militaires ont précisé que les cas de prévenus civils sont une exception : le Président de la Cour Militaire de Goma a rapporté qu’en 2012 il n’y a  que 12 civils jugés par sa Cour, pour des affaires d’assassinats. Le Président du TMG de Bukavu a présenté la même conclusion pour son tribunal et a tenu à préciser qu’ «il n’y a jamais eu de dossiers de VBG commis par des civils [jugés par ce tribunal] ».  Le Président a encore ajouté qu’en cas de prévenus civils la composition de la Cour Militaire est intégrée par un magistrat civil.

Il convient finalement de noter, comme illustré dans les rapports de monitoring PNUD, que les jugements des tribunaux militaires consistent parfois dans des déclinatoires de compétence en cas de prévenus civils.

Finalement certaines personnes interrogées ont souligné que les juridictions civiles sont plus représentées sur le territoire, donc il parait justifié que les AF militaires soient plus fréquentes et nombreuses.

Un deuxième aspect qui fait objet d’un vif débat au sein de la communauté juridique, concerne la compétence matérielle exclusive que la législation congolaise a reconnu, jusqu’á très récemment, aux juridictions militaires à connaître des crimes internationaux prévus par le Statut de Rome (crimes de génocide, crimes de guerre et crimes contre l’humanité) .

Ce cadre juridique est  entrain de subir des changements importants suite á deux reformes législatives en cours :

- La loi de reforme de l’organisation judiciaire congolaise d’Avril 2013 élargit la compétence des juridictions civiles aux crimes internationaux commis par des civils en prévoyant que les Cours d’Appel « connaissent, en premier degré,  du crime de génocide, des crimes de guerre et des crimes contre l’humanité commis par les personnes relevant de leur compétence et de celle des Tribunaux de Grande Instance ».

- Le projet de loi pour la mise en ouvre du Statut de Rome, actuellement en discussion au Parlement, prévoit le transfert de la compétence sur les crimes internationaux aux juridictions civiles.  « Les crimes internationaux « émigrent » du Code pénal militaire vers le Code pénal ordinaire dans la mesure où les juridictions militaires sont dépossédées de la compétence à connaître des crimes internationaux au profit des Cours d’appel siégeant à cinq juges, bénéficiant du monopole de réprimer ces crimes au premier degré. Les appels sont portés devant la Cour de cassation. Les magistrats militaires peuvent toutefois intégrer la composition de la Cour d’appel siégeant dès lors que le prévenu ou l’un des co-prévenus revêt la qualité de militaire ou assimilé ».

En conclusion depuis le mois d’Avril 2013, les crimes internationaux peuvent être jugés soit par les jurisdictions militaires soit par les civiles en vertu du critère de la compétence personnelle ; le débat reste toutefois ouvert quant á la question d’une éventuelle jurisdiction exclusive en faveur des jurisdictions civiles, comme proposé dans le projet de loi  pour la mise en ouvre du Statut de Rome.

Les juridictions militaires rencontrées au cours de la mission d’évaluation ont mis en évidence les aspects positifs de l’engagement des militaires dans l’organisation des AF dans la lutte contre l’impunité des crimes internationaux.

Par exemple le Président du Tribunal Militaire de Garnison de Bukavu a souligné que dans un contexte de conflit comme celui à l’Est de la RDC, la majorité des crimes internationaux sont commis par des militaires et que les autorités civiles auraient des difficultés à mener des enquêtes sur le terrain des opérations de guerre; de plus les juridictions militaires ont plus de facilité à appréhender les présumés auteurs, vue la résistance de la hiérarchie militaire de livrer ses hommes. Finalement le Président a mentionné les efforts de renforcement des capacités que les partenaires internationaux ont entrepris avec les juridictions militaires et qui ont entrainé des progrès amplement reconnus dans la lutte contre l’impunité pour les crimes internationaux et a exprimé sa préoccupation que ce travail devra être recommencé à zéro avec les juridictions civiles.

Par contre les juridictions militaires ont été critiquées pour certaines violations des garanties du procès équitable, notamment les interférences politiques, le régime de la détention préventive, la présence des juges assesseurs sans compétences juridiques et aussi l’excessive célérité des procédures dans la mesure où elle affecte la qualité du procès.

Finalement une réserve pourrait être émise sur la pratique des AF militaires de traiter certaines infractions à caractère strictement militaire, telles que la détention illégale d’arme de guerre, la violation de consigne, l’abandon de poste ou le détournement d’effets militaires. Cette pratique est possible car le PNUD exige qu’un minimum de dossiers pris en charge par l’AF concerne des cas de VBG, mais laisse aux juridictions le choix d’éventuels dossiers non-VBG à traiter.

Un nombre trop élève d’affaires á caractère strictement militaire pourrait diffuser la perception que l’objectif prioritaire des AF est d’améliorer la discipline militaire plutôt que de faciliter l’accès á la justice des groupes vulnérables.

Un des moniteurs judiciaires PNUD estime qu’au Sud Kivu ce problème ne se pose pas car les infractions á caractère strictement militaire sont prises en compte seulement dans le cas où le prévenu est poursuivi pour plusieurs chefs de prévention dans une même affaire (par exemple meurtre et détention illégale d’arme de guerre). Il serait toutefois recommandé de mener une analyse pour vérifier l’impact de ces infractions sur le total des infractions traitées par les AF.

En général es juridictions militaires semblent mieux outillés que les civiles á travailler sur les dossiers de VBG dans le cadre des AF : les militaires s’adaptent facilement aux exigences des AF, en particulier par leur mobilité et facilité à intervenir dans les zones d’opération de guerre; les arriérés sont moins importants qu’auprès des juridictions civiles et les militaires ont reçu plus de formations de la part des partenaires internationaux  par rapport aux magistrats civils.

Des avocats ont également souligné  l’efficacité de la justice militaire: « les jugements sont rendus dans les délais et les militaires appliquent un droit plus avancé et mieux adapté a la réalité du pays ».

Un rapport de RCN illustre que les justiciables «préfèrent s’en remettre délibérément à la justice militaire, réputée plus expéditive, plus efficace et plus sévère ».

Malgré ces points positifs, l’impression de la justice militaire reste celle d’une justice strictement retributive qui s’inspire au principe de l’exemplarité, comme témoigne le taux élevé des condamnations illustrée au § 6.2 ainsi que la formule utilisée par le Président d’une juridiction pour décrire les AF: « les témoins de l’action doivent être les témoins de la répression ».

En conclusion le débat sur les juridictions militaires apparait clair au niveau de la doctrine, mais reste ouvert dans la pratique judiciaire congolaise.

Vu les questions liées aux standards internationaux susmentionnées et considéré que les juridictions civiles ont été reconnues en Avril 2013 une compétence pour les crimes internationaux et que dans un futur proche elles pourraient avoir une compétence exclusive dans cette matière, il serait opportun d’appuyer davantage les juridictions civiles qui souhaitent organiser des AF.

B) Les violences sexuelles basées sur le genre

La majorité des AF à l’Est de la RDC a été initialement appuyée par les partenaires internationaux pour traiter des dossiers de violences sexuelles basées sur le genre (VBG); ABA se réfère aux AF comme les «mobile gender courts ».

Le débat, illustré plus en détail au § 5.3, sur les effets inattendus des politiques de lutte contre les VBG, a porté les partenaires de développement á progressivement élargir le champ d’intervention des AF: la pratique courante adoptée par le PNUD est d’accepter que les tribunaux traitent en foraine aussi un certain nombre de dossiers pour d’autres infractions.

Les statistiques PNUD montrent qu’en 2011 les dossiers VBG représentaient 80% des dossiers enrôlés au total et qu’en 2012 ce pourcentage a baissé à 60%.

Les AF restent toutefois fortement centrées sur la lutte contre les VBG : la présence d’un minimum de dossiers de violence sexuelle est une condition essentielle que les bailleurs du PNUD exigent pour octroyer l’appui à une AF.

Même si le nombre minimal de dossiers VBG ne semble pas être identifié clairement par le PNUD  il est ressorti très clairement des entretiens que les juridictions perçoivent les AF comme étant très fortement centrées sur les VBG : le Président du TGI de Goma estime que les AF « s’occupent exclusivement de VBG ».

La politique imposée par les bailleurs de prioriser les dossiers de VBG a des effets distorsifs sur la pratique judiciaire: parfois les juridictions ne vident pas tout de suite les dossiers VBG car elles préfèrent attendre d’avoir un nombre significatif de dossiers VBG pour pouvoir organiser une foraine. Dans d’autres cas, des affaires qui pourraient être traitées au siège d’un tribunal (car l’infraction est commise dans une localité proche du siège et la plainte a été déposée directement au tribunal) sont inscrites au rôle d’une AF pour justifier l’organisation d’une AF.

La question de la priorisation des VBG au sein des AF se situe dans le débat plus général sur l’opportunité de créer des structures spécialisées pour les VBG tant au niveau des juridictions que de la police.

Dans le cas des AF il est toutefois important de considérer qu’elles se déroulent normalement dans des territoires où les juridictions permanentes sont absentes et aucune voie de recours au système de justice formel n’est disponible pour la population. La priorisation des VBG dans le cadre des AF pourrait donc donner lieu à une discrimination à l’égard des victimes d’infractions non qualifiées comme VBG, car elles ne sont pas reconnues les même opportunités d’accès á la justice que les femmes victimes de VBG.

Certains chefs de juridictions ont partagé ce point de vue en soulignant que cette approche est en train de créer une justice à deux vitesses qui favorise les victimes de VBG.

Il convient finalement de rappeler que l’Observation Générale n.32 du Comité des Droits de l’Homme concernant l’article 14 du Pacte international relatif aux droits civils et politiques « exclut également toute distinction dans l’accès aux tribunaux et aux cours de justice qui ne serait pas prévue par la loi et fondée sur des motifs objectifs et raisonnables ».

A la lumière de ces discussions, il serait recommandé d’abolir la limite du pourcentage minimal de dossiers VBG requis pour soutenir l’organisation d’une AF et d’utiliser d’autres stratégies pour encourager les juridictions à s’occuper des violences sexuelles. En parallèle il faudrait relancer l’image des AF auprès des acteurs de la justice par une stratégie de communication visant á changer la perception des AF comme des instruments de lutte contre les VBG.

§ 5.2. La pertinence avec les politiques nationales en matière de justice

►Les AF dans les politiques nationales et leur niveau de mise en œuvre

Le Ministre de la Justice a adopté en 2007 un « Plan d'action pour la réforme de la justice »  et en 2009 une « feuille de route » qui identifient les priorités dans la lutte contre l'impunité en RDC.

Les AF sont mentionnées dans les deux documents.

La section « justice de proximité » du Plan d’Action se propose de « Développer les audiences foraines en attendant l’ouverture effective des tribunaux de paix non encore installés ».

Plus spécifiquement le résultat 4 prévoit la mise en place d’un programme national d’audiences foraines a travers:

1) «l’institution de chambres foraines permanentes couvrant les divers degrés de juridiction et des parties isolées du territoire national sans dégarnir les juridictions en place dans les provinces » et

2) « la création d’une section judiciaire affectée exclusivement à l’exécution d’un programme tournant d’audiences foraines (juges supplétifs) ».

Ces indications stratégiques n’ont pourtant pas encore été mises en application dans l’Est de la RDC, malgré l’engagement des chefs de juridictions au niveau des provinces et nonobstant que les partenaires internationaux aient promus á maintes reprises des discussions avec le gouvernement, comme précisé par un des analystes de projet du PNUD.

Un des obstacles semble être la faible coordination entre les autorités judiciaires basées a Kinshasa et celles dans les provinces: par exemple la stratégie nationale pour les AF n’a jamais été mentionnée au cours des entretiens d’évaluation et ne semblait pas être connue par les personnes interrogées.

Le manque d’orientation de la part des autorités centrales combiné avec l’absence d’une planification stratégique au niveau provincial se traduit dans la pratique avec l’organisation d’AF qui répondent a un besoin ponctuel et représentent un modèle fortement influencé par les exigences des bailleurs de fonds, comme sera illustré dans les paragraphes qui suivent.

►Le débat sur la nature ponctuelle ou continue des AF

Les personnes interrogées s’accordent à définir les AF couramment appuyées dans l’Est de la RDC comme une institution temporaire. Le chef de Bureau du PNUD de Bunia les décrits comme un «un apport conjoncturel qui permet de régler un problème ponctuel,» ; le Directeur de ABA estime que « Les AF sont, et doivent rester, une aide ponctuelle qui adresse un besoin spécifique ».

Les AF sont temporaires aussi dans la mesure où elles sont constituées au moment où le besoin est identifié.

Un des rapports de monitorage du PNUD au Sud Kivu confirme cette approche en constatant «une absence complète de planification coordonnée des audiences foraines qui sont organisées au cas par cas par chaque juridiction et en fonction de l’intervention des partenaires. Il n’existe pas de calendrier préalable par territoire et on s’aperçoit qu’au cours d’une même année plusieurs audiences foraines peuvent être organisées au sein d’un même territoire au détriment d’autres territoires »

La question de la programmation stratégique des AF reste un sujet controversé, malgré les partenaires internationaux et les autorités judiciaires reconnaissent un besoin de travailler dans un contexte plus structuré et prévisible et souhaiteraient pouvoir se référer á un planning annuel des AF.

L’obstacle majeur á la planification semble être la difficulté d’estimer les besoins et prévoir en avance le nombre d’AF par année, la raison principale mentionnée par plusieurs répondants étant que « on ne peut pas prévoir où et quand l’infraction sera commise » et donc savoir s’il y aura assez de dossiers pour organiser la chambre foraine.

Cette difficulté est clairement saisissable dans les cas comme Walungu or Mambasa où les AF sont une réponse á des épisodes inattendus de graves violations des droits de l’homme, mais ne s’applique pas aux cas où les juridictions siègent en foraine pour vider le passif judiciaire.

Les autorités judiciaires se sont montrées ouvertes á la possibilité d’une planification annuelle; Avocats Sans Frontières a développé une bonne pratique en appuyant les juridictions à faire une analyse de leurs besoins dans le territoire de Bandolo, dans le Sud Kivu.

Le débat pourrait être approfondi davantage autour de la question du caractère ponctuel ou continu des AF.

Pour clarifier ce point il convient de faire référence aux deux modèles d’AF qui émergent dans la pratique des 3 pays qui contribuent á la présente évaluation, notamment :

- Le modele d’AF ponctuel (ad hoc)

Les AF sont organisées pour adresser des besoins de justice ponctuels, comme la poursuite de graves violations des droits de l’homme commises dans des territoires éloignés où les institutions judiciaires permanentes sont absentes. C’est le modèle appuyé en priorité par le PNUD à l’Est de la RDC et qui s’adapte mieux à un contexte de conflit et á l’absence de structures judiciaires. Ce modèle présente toutefois les difficultés de planification susmentionnées.

- Le modèle d’AF continue

Les AF sont organisées régulièrement comme des descentes sur le terrain pour juger les affaires en appel ou les affaires d’une juridiction inferieure avec une compétence matérielle plus limitée, ou éventuellement juger en substitution d’une juridiction que est établie par la loi mais pas encore opérationnelle. C’est le modèle adopté en Sierra Leone et qui reflet une approche de développement où les AF sont organisées en complémentarité avec les jurisdictions permanentes et sont planifiées chaque année.

Dans le contexte à l’Est de la RDC où le conflit est encore en cours mais, dans le cadre des efforts de restauration de l’Etat, les juridictions commencent à être présentes et ont étés renforcées dans leurs capacités, un modèle mixte d’AF pourrait représenter une solution appropriée.

Un système d’AF continue pourrait être mis en place dans les territoires où le contexte et la cartographie judiciaire le permettent, en capitalisant les leçons tirées et les bonnes pratiques développées. En même temps le PNUD pourrait continuer à appuyer un nombre plus limité d’AF ponctuelles (ad hoc) pour traiter des éventuels dossiers de crimes internationaux ou de graves violations des droits de l’homme commises dans le cadre du conflit suite á des affrontements imprévisibles et soudains.

►L’implantation des juridictions permanentes

La majorité  des personnes interrogées á souligné l’importance de mener, en parallèle avec les efforts pour développer la justice itinérante, des actions visant á implanter des nouvelles juridictions dans les zones reculées.

Le Président du tribunal de Goma a insisté sur l’importance de multiplier les juridictions permanentes de proximité, comme les sièges secondaires des TGI et des Parquets ainsi que les Tripaix afin de réduire les AF ou au moins afin de les organiser dans un ressort géographique plus restreint. La présence de juridictions de proximité est une condition essentielle pour pouvoir établir le « modèle d’AF continue » susmentionné.

L’obstacle majeur ne semble pas être la construction des tribunaux, mais plutôt l’absence de personnel judiciaire. Le Président de la CA de Bukavu a expliqué que non seulement les magistrats ne sont pas en nombre suffisant  mais aussi ils refusent d’être affectés dans les zones reculées, vu l’absence de sécurité et de logement appropriés.

Comme illustré dans un rapport d’ASF et souligné par le Président du TGI de Bunia, « L’installation prochaine des tribunaux de paix ne pourra se substituer à l’organisation d’audiences foraines. La compétence matérielle des tribunaux de paix est relativement restreinte. ». Les AF devront donc continuer à être appuyées même après l’implantation de toutes les juridictions permanentes.

En conclusion les AF sont pertinentes aux stratégies nationales dans le secteur de la justice car elles représentent une priorité reconnue dans ces stratégies; toutefois les modalités de leur mise en œuvre pourraient être mieux encadrées par une meilleure planification, reflétant un modèle plus précis d’intervention. A cette fin il est recommandé de promouvoir un dialogue plus étroit et régulier avec le Ministère de la Justice à Kinshasa et éventuellement mener des actions pour faciliter sa coordination avec les autorités judiciaires dans les provinces pour la planification des AF.

§ 5.3. La pertinence avec les besoins des bénéficiaires, en particulier les victimes de violences sexuelles.

L’appui aux AF au sein du PNUD a été mis en place dans le cadre des stratégies de lutte contre les VBG en RDC sur la base de nombreuses études conduites au courant des années pour lutter contre la récurrence des violences sexuelles à l’Est des la RDC, y compris celles commises par les militaires.

Les documents de projet PNUD permettent d’identifier les usagers des AF par les catégories suivantes: 1) les femmes victimes de violence sexuelle 2) les militaires partis au procès et 3) les parties civiles au procès. Des statistiques indiquant le nombre de bénéficiaires atteint par les AF n’est pas disponible.

Les personnes interrogées ont unanimement reconnu que les AF ont été pertinentes par rapport à l’accès à  la justice des survivantes de VBG : au total les AF analysées par le présent rapport ont enrôlées 128 dossiers de VBG pour un nombre bien plus élevé de victimes.

Deux aspects clefs dans l’analyse de la pertinence des AF dans la lutte aux VBG sont brièvement analysés ci-dessous.

► Le changement de contexte en cours

Un grand nombre de rapports récents montrent que les besoins par rapport aux violences sexuelles en RDC sont entrain de changer : le taux de récurrence reste haut, toutefois elles ne sont plus commises exclusivement par des hommes en uniforme, mais  de plus en plus par les civils .

Les viols en RDC ne sont plus principalement reconnus comme « arme de guerre dans le cadre d’un objectif militaire stratégique”, ce qui avait mobilisé la communauté internationale à intervenir en DRC pour la lutte contre le viol comme crime de guerre, suite a l’adoption de la Résolution 1820 en Juin 2008.

Une etude menée par OXFAM au Sud Kivu rapporte que « After years of military rape in South Kivu, civilian adoption of sexual violence is becoming recognized as its own problem”

Cette tendance est confirmée par la Directrice de SOFEPADI, une ONG de Bunia qui appuie les AF, ainsi que par les statistiques du monitoring judiciaire PNUD, qui rapportent pour 2010 seulement « 5 dossiers VBG du tribunal militaire et 500 du tribunal civil ».

► Les conséquences inattendues des politiques de lutte contre les VBG

Certains rapports ont commencé à mettre en relief les conséquences inattendues des politiques de lutte contre les VBG, par exemple une étude par Disaster Studies soutient la théorie que les interventions pour les VBG  à l’Est de la RDC sont devenues un fonds de commerce.

Certains effets inattendus dénoncés par le rapport devraient être tenues en considération dans la planification future des AF, notamment:

- la diffusion du phénomène d’instrumentalisation la justice pour régler des affaires personnelles : “Framing somebody for rape has become an effective way to ‘get somebody out of the way’ or to claim financial compensation. This is, for example, the case with teenage love affairs that result in pregnancy. When the families cannot agree on marriage or compensation for the costs of the child, sexual violence accusations may result”.

- la tendance du système judiciaire, poussé par la communauté internationale et la politique tolérance zéro du gouvernement, à produire un nombre élevé de condamnations pour viol, parfois dans des situations où le prévenu se retrouve sans une assistance judiciaire adéquate.

Vu que les AF appuyées par le PNUD ont enregistré un taux très élevée de condamnations (presque 80%) dans les 2 dernières années, il serait recommandé de mener des analyses des jugements afin de vérifier que les condamnations aient été prononcées dans le respect des principes du procès équitable.

Comme illustré plus en détail au § 6.4 les AF contribuent á la poursuite des crimes internationaux: non seulement un pourcentage croissant de dossiers de viol est qualifié comme crime de guerre mais les AF adressent aussi les besoins de justice des victimes et des prévenus d’autres crimes internationaux, comme les pillages ou la torture qui relèvent de la définition codifiée dans le Statut de Rome.

Les dossiers de crimes internationaux sont toutefois encore en nombre très réduit, malgré les besoins soient importants et selon certain rapports plus urgents que les VBG. Par exemple les moniteurs judiciaires PNUD rapportent que « les juges sont affectés à travailler en priorité sur les dossiers déterminés par le choix du thème soutenu par l’audience (souvent des violences sexuelles) lequel ne correspond pas forcément aux besoins judiciaires les plus criants du moment »

En conclusion les AF ont été très pertinentes par rapport aux besoins des victimes de violences sexuelles commises par les militaires et par rapport aux politiques nationales de lutte contre les VBG.

La pertinence des AF par rapport aux besoins de justice liés aux infractions non-VBG a été faible.

A la lumières des changements de contexte sous-mentionnés et dans le but de mieux refléter les besoins de la population, la planification future du PNUD pourrait tenir compte des aspects suivants :

- Eliminer la priorité accordée aux dossiers VBG et élargir le champ d’intervention des AF à toutes les infractions pour les AF organisées selon le « modèle continu », tout en gardant une priorité sur les dossiers de crimes internationaux pour les AF organisées selon le « modèle ponctuel (ad hoc) ».

- Engager davantage les juridictions civiles dans la lutte contre les VBG ;

- Assurer que les besoin des prévenus soient adéquatement adressés;

- Assister les victimes dans la phase d’exécution du jugement pour obtenir les réparations/dommages et intérêts.

§ 5.4. La pertinence avec le principe d’appropriation nationale

Il existe une bonne appropriation nationale des AF pour les aspects strictement liés à leur mise en œuvre.

Les AF ainsi que les enquêtes préliminaires du Parquet et les descentes sur terrain du Greffe sont menées entièrement par les autorités judiciaires nationales, qui ont été formées avec l’appui des partenaires internationaux et ont ainsi développé des bonnes connaissances dans la tenue des audiences selon les standards internationaux du procès équitable.

La présence des représentants des juridictions est assurée dans toutes les réunions de coordination des AF menées sous le leadership des partenaires internationaux et un échange régulier est assuré avec le PNUD.

Les demandes d’appui aux AF sont initiées par les juridictions, selon les modalités illustrées au § 5.1; mais il est arrivé que dans certains cas de graves violations des droits de l’homme, les partenaires internationaux ont sollicité les juridictions à organiser une AF.

Néanmoins, la tenue des AF est entièrement financée par les acteurs internationaux, par conséquent le système de la justice civile et militaire itinérante dépend entièrement du soutien de la communauté internationale.

Dans la planification et le suivi de l’initiative on perçoit encore une trop forte influence des partenaires internationaux, en particulier par rapport au aspect suivants:

- Sélection des dossiers traités en foraine : comme illustré au § 5.3 la politique du PNUD (et de la majorité des autres partenaires) reflet la condition imposée par les bailleurs d’appuyer une AF seulement si des dossiers VBG sont enrôlés.

- Manque de contribution du gouvernement congolais au budget des AF.

- La gestion financière des AF. Les juridictions ne gèrent pas les fonds pour les AF mais dépendent  entièrement du PNUD (et des autres partenaires), qui décaisse les montants selon la nécessité.

- Le suivi des AF. Comme illustrée au § 6.1, l’implication des juridictions dans le suivi des AF est faible: actuellement les rapports d’AF sont rédigés par les internationaux présents aux AF en tant qu’observateurs ou moniteurs judiciaires.  Les greffes rédigent des rapports internes qui ne semblent pourtant pas partagés avec les partenaires internationaux et donc pas pris en compte dans suivi des AF.

- La sécurité des AF. Malgré la présence d’éléments de la police nationale et des FARDC, les magistrats dérivent leurs sens de sécurité principalement de la présence des Casques Bleu de la MONUSCO, en particulier quand il s’agit de siéger dans des zones á haut risque d’insécurité.

L’appropriation locale dans la définition du PNUD, pourrait donc être promue davantage, en particulier dans le but de faciliter l’éventuel transfert de l’initiative aux partenaires nationaux et d’assurer qu’un budget national soit alloué à la tenue des AF

# 6. EFFICACITE

§ 6.1. Planification et suivi

► Planification

Comme illustré au § 3, les AF sont planifiées dans le cadre de deux projets PNUD:

- le projet 1888 (Renforcement de la capacité du système judiciaire militaire d’enquêter et de poursuivre les crimes des violences sexuelles dans l’est de la RDC) et

- le projet SIDA (Renforcement de l'accès des femmes à la justice : sécurisation et autonomisation des populations dans les Kivus et en Ituri).

Un extrait des cadres respectifs de ressources et des résultats est présenté ci-dessous :

| A) Abstract of Results Framework for project 1888 (2011 to 2012): |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity result 2.1 | Activity 3 | baseline | indicator | Target |
| Reinforce and strengthen the military judicial actions based on gender and SGBV; | Logistical assistance to investigation, prosecution and trials (mobile) of sexual violence.; | n/a | n/a | - 20 % increase of the number of SGBV cases dealt with by military jurisdictions; - 20% increase of cases dealt with under the legal delays. |
| B) Abstract of Results Framework for project SIDA (2011 to 2012): |  |  |  |  |
| Activity result 2 | Activity 5 | baseline | indicator | Target |
| Reinforce and strengthen the judicial response to civil and criminal action based on gender and SGBV; | Support to audiences foraines; | n/a | % change in the number of SGBV cases dealt with by judicial institutions; | - 10 % increase of the number of SGBV cases dealt with by judicial institutions; 20% increase of cases dealt with under the legal delays. - au moins 50 % des procès sont été intentés par une femme/ou ceux où la femme a été la victime (PTA 2012) |

Etant donné que  l’appui aux AF est une composante mineure de deux plus vastes projets d’accès á la justice, des cibles et des indicateurs spécifiques pour les AF n’ont pas étés identifiés, mais sont les mêmes que  les indicateurs pour les juridictions permanentes.

Les Termes de Référence des AF présentent une description narrative des AF.

Les éléments de la planification qui pourraient être renforcés sont indiqués ci-dessous.

- Renforcer la planification des AF

Le § 5.2 a souligné le besoin ressenti par tous les acteurs qui interviennent dans l’organisation des AF d’une  planification plus spécifique, afin inter alia de faciliter la mesure du progrès des activités envers les résultats escomptés et l’impact de l’initiative.

Une suggestion qui a rencontré l’intérêt des parties intéressés est la rédaction d’un Protocole d’entente annuel entre les partenaires internationaux qui appuient les AF et les autorités judiciaires pour gérer et planifier les AF. Ce document permettrait de définir un cadre de travail cohérent avec des indicateurs, points de repère et aspects financiers harmonisées; il devrait être conçu comme une mesure intérimaire dans l’attente que le système des AF puisse être transféré aux partenaires nationaux et donc devrait inclure une solide stratégie de pérennisation. Le document pourrait aussi régir les aspects financiers avec la création d’un basket fund, comme illustre au § 3.1.

La cheffe de mission d’ASF a suggéré de prévoir un accord de principe avec le Ministère de la Justice au niveau national pour définir la stratégie d’intervention et un accord opérationnel au niveau des provinces.

D’autres partenaires suggèrent d’intégrer dans le Protocole les aspect de renforcement des juridictions permanentes en assurant que le Ministère de la Justice s’engage á affecter des magistrats dans les zones où interviennent les AF.

- Renforcer les indicateurs de performance des AF

La définition du protocole d’entente susmentionné permettrait d’adopter des indicateurs spécifiques aux AF pour mesurer leur performance et impact.

Les indicateurs de performance devraient au moins inclure : 1) nombre de dossiers enrôlés, ventilé par typologie d’infraction ; 2) nombre de décisions rendues, ventilé par résultats de l’affaire et par typologie de sanction  3) nombre de bénéficiaires, ventilé par genre et par rôle dans le procès ; 4) nombre d’avocats déployés, ventilé par genre et par typologie de clients ; 5) statistiques sur les séances de sensibilisation pour la population et les activités préliminaires aux AF, tel que les missions d’enquête du Parquet.

Des indicateurs d’impact devraient également être inclus et pourraient viser á mesurer : 1) si les AF contribuent á améliorer l’accès á la justice dans les zones reculées (pour les AF organisées selon le « modèle continu » 2) si les AF contribuent á la poursuite des crimes internationaux et au renforcement des capacités des juridictions nationales en cette matière (pour les AF organisées selon le « modèle ponctuel/ad hoc »).

Une analyse des indicateurs couramment utilisés suggère que l’indicateur « pourcentage d’augmentation du nombre de dossiers de VBG pris en charge per les AF » et l’indicateur « augmentation du nombre de condamnations des auteurs de violence sexuelle et sexiste » pourraient être reformulées afin d’éviter que les juridictions en foraine se sentent poussées à produire un nombre élevé de jugements de VBG en dépit de la qualité du travail pour satisfaire les exigences des bailleurs. Une révision des indicateurs est par ailleurs en cours au sein de l’équipe accès à la justice du PNUD.

Il serait aussi recommandé d’inclure des indicateurs référés aux bénéficiaires et d’assurer que les données collectées soient ventilées par genre. Par exemple il aurait été intéressant de savoir combien d’avocats femmes ont été engagées dans les AF, ou si parmi les prévenus il y avait des femmes.

► Suivi

Le manque d’une planification spécifique pour les AF s’est reflété sur le suivi des activités, car il n’a pas été possible de mesurer le progrès vers les résultats escomptés.

Les principaux outils de suivi des AF sont :

- les rapports de monitorage judiciaire et les rapports de mission rédigés par les moniteurs PNUD

- les rapports annuels pour les projets 1888 et SIDA .

Dans le cadre des efforts du PNUD pour promouvoir l’accès á la justice, une équipe de 8 moniteurs judiciaires employés par le PNUD (1 en Ituri, 3 au Sud Kivu et 4 au Nord Kivu) a été mise en place afin d’assurer le monitoring des procédures judiciaires et de police ainsi que l’observation d’un échantillon d’audiences, avec un focus spécifique sur les VBG.

Les moniteurs judiciaires ont participé au 90% des AF appuyées par le PNUD dans les 2 dernières années; pour la majorité de ces audiences un rapport de monitoring a été produit.

C’est une excellente initiative qui est reconnue pour avoir poussé les juridictions à respecter les standards internationaux du procès équitable et en même temps d’avoir un aperçu impartial des résultats atteints par les AF.

Les moniteurs judiciaires sont des jeunes juristes compétents et engagés qui ont inter alia contribué au présent rapport avec des opinions pertinentes et bien argumentées.  Des faiblesses ont pourtant été relevées au niveau des statistiques et des informations collectées au cours des AF observées.

Certaines informations essentielles ne sont pas disponibles : par exemple il n’a pas été possible de connaître le nombre total des victimes/ prévenus et parties civiles aux AF. Parfois on relève des écarts importants entre les chiffres fournis dans les différents documents produits : par exemple pour l’AF du TGI de Bunia à Mahagi le rapport de monitorage indique 93 dossiers et le fichier récapitulatif en indique 24.  Des difficultés particulières ont été rencontrées quand il s’agissait de recevoir les informations d’autres partenaires: par exemple il n’a été possible de connaître le coût total des AF au Sud Kivu.

Des recommandations pour renforcer les équipes de moniteurs dans leur travail auprès des AF sont présentées ci-dessous. L’identification d’une personne avec une fonction de coordination et supervision d l’équipe des moniteurs pourrait faciliter la mise en place des recommandations proposées.

- Les rapports de monitoring des AF devraient suivre un format standard afin de faciliter la collecte et l’analyse des données : les moniteurs devraient utiliser un cadre commun pour l’analyse juridique et devraient rapporter tous sur les mêmes aspects légaux, identifiés à l’avance.

Actuellement les moniteurs suivent un format narratif ouvert que chaque moniteur rédige selon son expérience; parfois le format utilisé est celui du rapport de mission du PNUD. Certains rapports présentent des tableaux de synthèse par dossier traités (Mahangi), d’autres présentent un tableau des activités du tribunal par jour (Komanda). Le rapport de l’AF de Mambasa est un rapport en forme de publication qui s’arrête longuement sur la question doctrinale l’applicabilité du Statut de Rome ; le rapport de Walunga présente une description très détaillé de l’audience dans une approche chronologique, mais manque d’analyse légale.

Les moniteurs ont expliqué qu’ils n’assistent pas à toutes les séances de chaque AF, mais seulement à quelques unes. Cette limitation est mentionnée par ailleurs dans un des rapports de monitoring qui recommande d’ « Assister á toutes les audiences pour participer á l’instruction, aux plaidoiries et au prononcé aux fins de faire une analyse complète des dossiers instruits et de présenter un rapport complet d’une chambre foraine ».

Considéré que touts les partenaires envoient normalement des représentants pour observer les AF, on aurait pourtant pu s’attendre á ce qu’un mécanisme pour consolider et éventuellement trianguler les informations soit en place, dans une approche de coordination du suivi des AF.

- Il faudrait assurer que pour toutes les audiences foraines appuyées un rapport soit disponible ainsi que toutes les donnes quantitatives nécessaires au suivi (actuellement seulement 10 rapports sur 16 AF appuyées sont disponibles).

Il serait aussi recommandé de mettre en place une base de donnés sur Excel avec la possibilité de faire des tris et d’obtenir rapidement des informations sur les AF pour faire des analyses et rédiger les rapports internes et des communiques externes.  Actuellement, les résultats quantitatifs des AF ne sont pas facilement consultables, bien que disponibles après un long exercice de lecture et de recherche dans les rapports de monitoring judiciaire.

- Une attention particulière devrait être réservée aux dossiers de crimes internationaux. Dans ce cas les moniteurs devraient vérifier le raisonnement suivi par le juge et le parquet pour identifier les éléments constitutifs des crimes de guerre ou de crimes contre l’humanité afin de s’assurer que l’infraction n’aurai pas du être traitée comme un crime de droit commun.

Dans le but d’engager davantage les partenaires nationaux dans les activités de suivi des projets, le PNUD est entrain d’établir un partenariat avec les Universités à Goma pour établir des mécanismes de monitoring des statistiques produites par les institutions publiques. Dans le cadre de cette initiative et dans une approche de pérennisation des AF, il serait recommandé d’explorer la possibilité que des étudiants en droit participent aux activités de monitoring judiciaire des AF sur le modèle adopté par le PNUD en Somalie .

Une attention particulière devrait être dédiée aux autorités judiciaires, qui ne sont actuellement pas activement impliquées dans le suivi des activités des AF. Un des analystes de projet PNUD explique que « les autorités judiciaires n’ont pas besoin de rédiger les rapports car les moniteurs du PNUD, et parfois aussi d’autres organisations, sont là pour faire ce travail ».

Dans une approche de pérennisation et dans le but de renforcer l’appropriation nationale il faudrait graduellement impliquer les juridictions dans les activités de suivi, par exemple par la rédaction d’un rapport d’audience ou de rapports de suivi semestriels.

Sur les 10 rapports d’AF disponibles pour la présente évaluation, un seul a été rédigé par les juridictions, notamment par Président de la Cour d’Appel de Bukavu pour l’AF de Kamitunga.  Ce rapport est d’excellente qualité: il illustre clairement toutes les activités menées au cours de l’AF et présente un tableau synoptique clair de tous les dossiers traités. Ce document a en outre permis au chef de la juridiction de présenter au PNUD son cahier de doléances avec des recommandations, assurant ainsi le point de vue du partenaire national, qui normalement ne figure pas dans les rapports PNUD.

La promotion d’un éventuel Protocole d’entente pour les AF entre les juridictions et les partenaires internationaux, pourrait faciliter la planification et le suivi des AF par la mise en place d’outils communs et harmonisés et pourrait mieux valoriser le rôle des autorités judiciaires, inter alia dans rédaction des  rapports d’AF.

Pour renforcer d’avantage la visibilité de l’initiative, il serait recommandé de rédiger périodiquement pour la diffusion extérieure un bulletin/newsletter sur les résultats atteints par les AF avec l’illustration d’histoires à succès et dossiers emblématiques.

§ 6.2. Les résultats atteints

Au courant du 2011 et 2012, un total de 16 audiences foraines ont été organisées avec l’appui du PNUD pour 198 jours en foraine et une contribution de 155.000 USD. 97 avocats et 72 magistrats/juges assesseurs ont participé aux AF. 202 dossiers ont été enrôles, dont 60% de VBG. 206 jugements ont été prononcés avec un taux de condamnation de 78%.

La cible prévue dans le document de projet « augmentation de 20% (10% dans le projet SIDA) de dossiers de VBG pris en charge per les juridictions » n’a pas été atteinte car le nombre de dossiers VBG a baissé de 20% de 2011 à 2012 pour les AF. Le résultat apparait pourtant positif et justifié si interprété á la lumière des questions soulevées au § 5.1 sur l’importance d’élargir le champ d’intervention des AF aux dossiers non-VBG. A noter que le résultat n’inclût pas les dossiers de VGB traités par les juridictions permanentes.

Les activités préliminaires visant à la préparation des AF, tel que les enquêtes du Parquet/Auditorat et les descentes sur terrain de la Greffe ont également été appuyées par le PNUD avec les résultats indiqués dans le tableau ci-dessous. Ces activités préliminaires sont illustrées en détail au § 5.1, toutefois il convient de rappeler leur importance pour une implémentation efficace des AF car elles assurent que les AF soient adéquatement préparées et produisent des résultats de qualité ; comme souligné par une des partenaires au cours des entretiens d’évaluation « sans enquêtes du Parquet, il n’y a pas d’audiences foraines ».

| Tableau récapitulatif des résultats des audiences foraines appuyées par le PNUD du 01/2011 au 12/2012 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | total | nord kivu | sud kivu | ituri |
| 1 | n. total audiences foraines | 16 | 3 | 8 | 5 |
|  | → n. AF juridictions civiles | 4 | 1 | 1 | 2 |
|  | → n. AF juridictions militaires | 12 | 2 | 7 | 3 |
|  | → n. AF juridictions appel | 6 | 1 | 5 | 0 |
|  | → n. AF juridictions premier degré | 10 | 2 | 3 | 5 |
| 2 | n. de jours de foraine | 198 | 46 | 92 | 60 |
| 3 | n. dossiers enrôlés | 206 | 74 | 75 | 57 |
|  | → n. dossiers VBG | 128 | 44 | 46 | 38 |
|  | → n. dossiers crimes internationaux | n/d | n/d | 6 | 2 |
| 4 | n. jugements rendus | 202 | 56 | 82 | 64 |
|  | → n. Condemnations | 158 | 42 | 65 | 51 |
|  | → n. Acquittements | 24 | 14 | 6 | 4 |
|  | → n. autre jugements | 20 | 0 | 11 | 9 |
| 5 | n. parties au procès | n/d | n/d | n/d | n/d |
| 6 | n. avocats déployés | 97 | 21 | 39 | 37 |
|  | → avocats victimes/partie civiles | 53 | 10 | 25 | 18 |
|  | → avocat prévenus | 44 | 11 | 14 | 19 |
| 7 | n. moniteurs judiciaires déployés | 12 | 1 | 5 | 6 |
| 8 | n. missions enquêtes du Parquet | n/d | 8 | 6 | 8 |
| 9 | n. missions de la Greffe | 16 | 3 | 8 | 5 |
| 10 | n. sensibilisations sur les AF | n/d | 5 | 0 | 6 |
| 11 | cout des audiences foraines (USD) | n/d | 52.000 | n/d | 65.348 |
|  | → contribution du PNUD (USD) | 155.317 | 33.000 | 62.540 | 59.777 |
|  | → autres contributions (USD) | n/d | 19.000 ABA | n/d | 4.071BCNUDH 1.500 ABA |

§ 6.3. La qualité des résultats atteints

L’objectif de la présente évaluation est également d’évaluer la qualité des services fournis au cours des AF et en particulier leur conformité aux standards internationaux du procès équitable et au mandat du PNUD, avec un focus sur les questions de genre et la complémentarité avec la CPI.

Les rapports de monitoring et les entretiens au cours de la mission ont souligné la bonne qualité de la pratique judiciaire des AF, qui a été jugée en général en conformité avec les standards internationaux.

L’engagement et le travail remarquable menés par des magistrats sont amplement reconnus ; par exemple un rapport d’ASF conclus que « les autorités judiciaires ont les compétences pour faire eux-mêmes»

Sur le plan juridique les aspects qui pourraient être améliorés sont indiqués ci-dessous.

► La parité des armes

Au cours des AF les victimes et les prévenus sont toujours représentés par des avocats ou des défenseurs judiciaires: les statistiques PNUD indiquent au total 44 avocats pour les prévenus et 53 avocats pour les victimes/parties civiles ont été déployés. En termes financiers ces efforts représentent un engagement important: le perdiem pour 6 avocats envoyés en foraine pour 15 jours a un coût approximatif de 5.000 USD.

Ces chiffres semblent indiquer que les parties au procès sont bien représentées aux AF, toutefois une analyse plus approfondie, supportée par les opinions des nombreux répondants, permet de conclure qu’au cours des AF les droits de la victime sont mieux protégées par rapport aux droits du prévenu.

La cause principale de ce déséquilibre est à rechercher dans le fait que les parties au procès sont représentées par deux typologies différentes d’avocats :

- des avocats-consultants, payés mensuellement et formés régulièrement par des ONG comme ABA, représentent les victimes/partie civile,

- des avocats-pro deo, envoyés d’office par les Barreau et payés uniquement le perdiem pour les déplacements en foraine, représentent le prévenu.

Un des rapports de monitoring judiciaire illustre clairement la différence susmentionnée: « Les avocats de la défense (pro deo) n’ont pas d’arguments à présenter devant le juge parce qu’ils ne connaissent pas le dossier en profondeur; certains d’entre eux s’y imprègnent séance tenante. Ces derniers ont peu d’expérience en matière de défense des crimes internationaux et plaident comme si le prévenu avait commis un crime de droit commun. Par contre la partie civile est sérieusement outillée et expérimentée pour plaider les crimes de ces genres.».

Le représentant du Barreau du Sud Kivu a soulevé cette problématique á la réunion avec le Gouverneur et a sollicité le PNUD à fournir plus d’appui aux avocats des prévenus en soulignant « les déséquilibres entre la défense et la partie civile, car ces derniers sont souvent mieux outilles ».  Le Président de la Cour d’Appel de Bukavu a ajouté que « Les partenaires mettent beaucoup plus l’accent sur les victimes et s’attendent à une condamnation. Les prévenus sont diabolisés ».

Souvent les avocats de la défense sont désignés seulement la veille de la première audience, tandis que les avocats de la victime ont le temps de descendre sur le terrain avant l’audience foraine pour la rencontrer et la préparer pour l’audience. En outre, comme illustré par le rapport de monitoring « les prévenus étant en cachot et n’ayant pas d’avocat au cours de toute la durée de l’instruction pré juridictionnelle, ils n’ont pas eu l’occasion de requérir des témoins. Ce pourquoi, à l’audience, seuls étaient présents les témoins à charge qui avaient été identifiés et requis par le ministère public.».

► Le droit á un interprète

Un interprète dans la langue locale est normalement intégré dans l’équipe foraine. Les audiences se déroulent en français mais les parties au procès peuvent s’exprimer dans leur langue (swahili, lingala…) et si les magistrats le souhaitent ils sont autorisés à utiliser la langue locale.

La question de la langue utilisée au procès n’as pas été mentionnée comme problématique au cours des entretiens et n’ayant pas pu observer une AF, la consultante n’as pas pu tirer des conclusions sur cet aspect.

L’analyse des rapports de monitoring permet de noter l’attention particulière que le PNUD porte à cette question. Par exemple le rapport PNUD de l’AF à Walungu indique que « les prévenus ont bénéficié de l’assistance d’un interprète lors de leur interrogatoire, ainsi que les victimes lors de leurs audition parce que parlaient tous Swahili” et que  «le troisième dossier n’a pu être instruit parce que le prévenu a souhaité s’exprimer en Kinyarwanda, et il n’y avait pas d’interprète à cet effet. Son dossier a été renvoyé pour qu’on puisse avoir un interprète, au 16 mars 2011. »

Etant donné que les AF ont aussi un objectif pédagogique car elles représentent une opportunité pour expliquer le droit á la population, il est recommandé de continuer à porter une attention particulière à ce que les parties au procès puissent participer activement aux procédures en assurant qu’elles ne soient pas limités par des barrières linguistiques.

Par exemple les moniteurs pourraient aller au delà de simplement vérifier la présence des interprètes aux audiences et, dans la même approche utilisée pour les avocats, vérifier la qualité de leur apports et éventuellement trianguler les conclusions avec l’opinion des parties au procès.

Comme illustre une étude par RCN, une analyse plus approfondie pourrait faire ressortir des éléments importants : « Au cours des entretiens menés avec les responsables des juridictions, la question de la langue ne semblait jamais constituer un problème. C’est en rencontrant les chefs coutumiers et en lisant les questionnaires des justiciables qu’elle est ressortie avec force ».

► La protection des victimes et des témoins

Des mesures sont en place pour assurer la confidentialité des victimes et des témoins au cours de l’AF : si la victime ne veut pas affronter le prévenu elle peut être voilée ou demander que l’audience ait lieu á huis clos.  Le Président de la Cour Militaire de Goma ajoute qu’en rédigeant l’extrait de rôle, le greffier s’assure de mélanger les dossiers VBG aux autres. L’octroi de codes numériques pour designer les victimes des violences sexuelles tout au long de la procédure est aussi une pratique courante.

Le Commandant de la Police spéciale pour la protection de la femme et de l’enfant à Goma a souligné que le manque d’infrastructures dans les territoires éloignés rends parfois difficile la mise en place de ces mesures, de plus il a assisté à des cas ou les femmes ne demandent pas les huis clos et parlent avec un grand gêne car le public réagit souvent en ridiculisant les témoignages.

La représentante du Ministère de la Justice au Nord Kivu estime que voiler les femmes n’est pas une solution efficace car les gens se connaissent dans les villages, de plus la victime et son bourreau doivent se rencontrer á un certain moment pour des exigences de la procédure.

La Représentante du Ministère de la Justice mentionne que les victimes et les témoins, en particulier les survivantes de viol, reçoivent des menaces par les condamnés une fois sortis de prison ou par leurs familles. La facilité et la fréquence avec laquelle les condamnés s’évadent des prisons congolaises rendent les victimes encore plus exposées au danger.

Les efforts des partenaires internationaux et des ONG nationales pour assurer la présence des victimes au procès et encourager la constitution des parties civiles sont amplement reconnus. Une partie importante du budget des AF (environ le 20%) est en effet réservé au remboursement des frais de transport, de restauration et logement des victimes et des témoins afin d’assurer leur présence pendent les audiences.

►Détention préventive

La détention préventive reste une question ouverte pour le système pénitentiaire en RDC en général, toutefois quelques remarques spécifiques aux AF ont été récoltées au cours de la mission.

A noter qu’avec la procédure de transfert des prévenus illustrée au § 5.1, le problème de la détention préventive illégale des prévenus aux procès en foraine ne se pose pas en termes aussi problématiques que dans d’autres pays, comme la Sierra Leone. En principe et sauf les cas d’évasion, les prévenus aux AF se trouvent dans les prisons centrales des provinces et les délais légaux de leur détention préventive sont sous le contrôle des Parquets.

Un des analystes de projet PNUD au Sud Kivu a souligné que les AF peuvent favoriser les détentions préventives prolongées (bien que légales) en attendant que tous les partenaires se mettent d’accord pour tenir une AF et réunir les conditions logistiques et financières nécessaires.

Une bonne pratique pour assurer le contrôle des détentions préventives s’est développée dans les prisons de Goma et Bunia où les juridictions organisent des AF hebdomadaires à l’intérieur de la prison et la visite d’un magistrat du Parquet. Le directeur de la prison de Goma, souligne que les AF ont un impact positif sur la réduction du taux de détention préventive illégale.

Néanmoins le taux de détention préventive reste alarmant : au mois de Mars 2013 le Directeur de la prison de Goma á rapporté que sur 264 détenus seulement 4 sont des condamnés.

Deux contraintes spécifiques aux juridictions militaires ont été soulevées au cours des entretiens :

- En conséquence de la priorité que le Projet 1888 accorde à la justice militaire, les AF appuyées par le PNUD produisent un nombre particulièrement élevé de condamnés militaires.

Etant donné que la RDC a une seule prison militaire pour tout le pays, c’est une pratique courante d’accueillir les militaires dans les prisons ordinaires où, comme souligné par un rapport de la MONUSCO « Il n’existe pas de séparation entre catégories de détenus civils et militaires, ce qui expose les premiers aux pressions des militaires. ». Les moniteurs PNUD du Nord Kivu ont confirmé des fréquents épisodes de harcèlement des civils de la part des militaires.

A noter qu’un projet de renouvellement de la prisons de Goma a permis de construire un nouveau bâtiment pour séparer les civils des militaires, mais suite aux pillages de Novembre 2012 ce bâtiment est actuellement utilisé pour touts les détenus.

Une autre problématique commune aux détenus (civils et militaires) originaires des territoires éloignés c’est qu’ils ne reçoivent pas l’appui de leurs familles, en particulier pour la nourriture de laquelle ils dépendent fortement vu l’insuffisance des rations alimentaires dans les établissements pénitentiaires.

- Certain rapports dénoncent l’illégitimité du régime de la détention préventive du système de justice militaire, car en violation de la garantie de l’habeas corpus pour la raison que « c’est l’auditeur militaire (lequel occupe les fonctions du ministère public) et non un magistrat du siège, qui statue (pendant 12 mois) par ordonnance sur la détention provisoire » Les personnes en détention préventive, ne peuvent donc pas saisir un juge pour faire examiner la régularité de leur détention dans le 12 premiers mois de détention.

Le président du Tribunal Militaire de Garnison de Bukavu reconnait cette faiblesse dans la législation militaire, mais assure que dans la pratique judiciaire les dossiers sont renvoyées à temps et que c’est l’exception d’arriver aux 12 mois.

► Exécution des décisions relatives aux intérêts civils

La majorité des personnes interrogées a reconnu un faible taux d’exécution de la condamnation civile (versement de dommages-intérêts) par les jugements rendus au cours des AF.

Le Rapport monitoring judiciaire PNUD présente une analyse de l’exécution des décisions relatives aux intérêts de la partie civile et conclus que « le taux d’exécution des jugements en matière de violences sexuelles reste malheureusement totalement nul ».

Les avocats présents à la réunion avec le Barreau de Goma reconnaissent de ne pas poser des actes d’exécution et affirment que «dès que la décision est rendue on se sent déchargés ».

Un rapport de ABA confirme que « it is universally the case in the DRC that the penalties and reparations levied against convicted defendants – and awarded to the victims or civil parties – are never paid”.  Finalement la directrice de l’ONG SOFEPADI reconnaît que bien que les condamnés aillent normalement à la prison, les victimes obtiennent rarement les dommages et intérêts, du fait de l’indigence des condamnés.

Des faiblesses sont également évidentes par rapport au droit des victimes des crimes internationaux à obtenir une réparation pour le préjudice subi: l’absence d’une stratégie globale pour les réparations introduisant inter alia le principe des réparations collectives et non-pécuniaires, ainsi que d’un fonds au profit de ces victimes sont parmi les obstacles mentionnées dans les nombreuses publications disponibles sur cette thématique.

Concernant l’exécution des jugements civils, une bonne pratique développée par Avocats sans Frontières,  qui pourrait être répliquée pour les AF appuyées par le PNUD, est d’organiser des missions pour vérifier l’exécution des jugements civils, quelques semaines après la tenue de l’AF.

►Durée des AF

La durée d’une AF varie en fonction du nombre des dossiers, mais ne dépasse rarement les 15 jours pour des raisons financières.

Plusieurs chefs de juridiction ont souhaité que les AF puissent durer plus longtemps et ont souligné que, surtout en cas de dossiers complexes comme les crimes internationaux, une durée trop limitée a des répercussions sur la qualité de l’AF et du procès équitable.

Le Président du Tribunal Militaire de Garnison de Bukavu estime que la rapidité avec laquelle se déroulent les AF, justifie les déficiences qui se vérifient parfois dans le traitement des dossiers. Il porte comme exemple l’AF de Walungu où il y avait, pour un seul dossier, 106 victimes et 4 prévenus mais seulement 10 jours pour juger. Par ailleurs le Président de la Cour Militaire de Goma a exprimé la préoccupation que la confiance de la population dans la justice puisse diminuer vu que « l’extrait du rôle est affichée publiquement donc les gens s’attendent que leur dossier soit décidé au cours de l’AF, mais cela n’arrive pas par manque de temps » .

Les moniteurs judiciaires ajoutent que, vu le temps limité, certains aspects de la procédure sont traités superficiellement : par exemple touts les témoins disponibles ne sont pas entendus ou quand un témoin est entrain de faire sa déposition, « le juge lui met la pression en l’invitant à se dépêcher » et «parfois pour assurer la célérité du procès, les victimes sont entendues rapidement et interrompues ».

Les personnes interrogées ont mentionné que  parfois des dossiers qui devraient être traités au siège du tribunal, sont jugés en foraine.

Le rapport PNUD de monitoring judiciaire illustre des situations également ambigües : « Dans certains cas, les chefs de juridictions ont attendu l’organisation des audiences foraines pour prendre des ordonnances de fixation des causes en audience foraine alors que les décisions de renvoi leur ont été communiquées 3 mois à 9 mois d’avance.  (…)Dans plusieurs cas, le tribunal a tenu une audience foraine loin du lieu de la commission des faits. Il a même été constaté des situations où le prévenu était en détention mais transportés dans des territoires éloignés du lieu de la commission des faits pour être jugé en foraine.»

Différentes raisons ont été mentionnées pour expliquer ces pratiques.

Un chef de juridiction a clarifié que ça arrive souvent par rapport aux dossiers de VBG, car les juridictions cumulent les dossiers de VBG á traiter au siège du tribunal avec celles á traiter en foraine afin de pouvoir atteindre le pourcentage minimal de dossier de VBG requis pour obtenir l’appui des partenaires internationaux. D’autres personnes recommandent une attention particulière á ces pratiques car elles pourraient refléter l’intérêt de certains acteurs de la justice de participer á un nombre élevé d’AF pour percevoir le Perdiem octroyé.

§ 6.4. La poursuite des crimes internationaux en complémentarité avec la  CPI

L’appui aux AF pour le traitement des crimes internationaux est une des premières expériences de mise en application de l’approche intégré á la justice transitionnelle du PNUD, visant à promouvoir des liens entre développement et justice transitionnelle, en particulier par le renforcement des capacités des acteurs nationaux dans la poursuite de crimes internationaux en complémentarité avec la CPI.

Dans ce but les Parquets dans l’Est de la RDC ont été formés dans la conduite des enquêtes pour les crimes internationaux par les experts de la Cellule d’appui aux poursuites (CAP) de la MONUSCO avec l’appui du PNUD et en collaboration avec le Bureau du Procureur de la CPI.

L’appui aux AF a permis de donner une suite á ces enquêtes et d’atteindre des importants résultats dans l’avancement de la justice pénale internationale.

Une publication d’Avocats sans Frontières montre qu’une jurisprudence en matière de crimes internationaux est graduellement entrain de se consolider au Congo: de 2002 à 2008 plus de 20 dossiers de crimes internationaux ont été jugés dans l’Est de la RDC (7 au Sud Kivu), tous au courant d’audiences foraines.

Les rapports de monitoring PNUD confirment que ce genre de dossier est traité de plus de plus fréquemment par les AF et soulignent que souvent les juridictions appliquent directement le Statut de Rome dans leurs jugements.

On perçoit une nette amélioration par rapport aux conclusions présentées par le Mapping Report de 2003, qui, en illustrant le cadre de la justice pénale internationale en RDC, rapportait que « quelques acteurs de la justice militaire congolaise ont été inspirés et, soutenus par la communauté internationale, ont rendu un petit nombre de décisions courageuses ».

En février 2011 pour la  première fois un haut comandant des FARDC a été condamné pour crimes internationaux par une juridiction congolaise au cours du procès exemplaire connu comme le « procès Fizi », qui a eu lieu pendent une AF appuyée à Baraka par les partenaires internationaux du Sud Kivu, y inclus le PNUD.

Les statistiques disponibles ne permettent pas de présenter un aperçu complet des dossiers de crimes internationaux jugées au cours des AF appuyées par PNUD, toutefois au moins 8 dossiers ont été signalés par les bureaux PNUD en Ituri et Sud Kivu entre 2011 et 2012.

Dans le cadre du projet 1888 on peut mentionner les AF suivantes avec un focus spécifique sur les crimes internationaux :

- L’AF du Tribunal Militaire de Garnison de Bukavu (Sud Kivu) du 7 au 16 octobre 2012 à Walungu.

4 dossiers ont été juges pour des faits qualifiés de crimes de guerre commis à Mupoke par les éléments FARDC contre la population civile. (le 17/01/2010 les FARDC, en mission officielle pour traquer des éléments FDLR, lancent une attaque armée contre le marché de Mupoke causant la mort a plusieurs marchands, des pillages et le viol de femmes). Sur le nombre de 106 victimes, 32 ont comparues à l’audience ; 16 étaient des victimes de violences sexuelles. 4 avocats (2 pour les victimes et 2 pour les prévenus) ont été engagés.

Le prévenu principal, un Sous-lieutenant des FARDC, a été condamné à la peine de 20 ans de servitude pénale pour crime de guerre par torture, viol, traitement inhumain et dégradant, torture et pillage.  Les 3 co-prévenus (en fuite) ont été condamnés in absentia à servitude pénale à perpétuité. Le Tribunal a alloué á chaque victime un montant variable de 50.000 USD (meurtre) à 5.000 USD (pillage) en fonction de la gravite du préjudice subi.

- L’AF du Tribunal Militaire de Garnison de Bunia (Ituri) du 15 au 28 novembre 2012 à Mambasa :

Sur le total de 8 dossiers traités au cours de l’AF, 2 concernent des faits constitutifs de crimes contre l’humanité. Il s’agit des crimes (meurtres, pillages, viols et déportations) commis par des éléments du groupe Mai-Mai Simba au cours de l’attaque au village de Epulu, dans la nuit du 23 au 24 juin 2012. Sur le total de 94 victimes (dont 17 femmes violées), 60 victimes et témoins ont participé à cette procédure (47 parties civiles).

Au total 5 avocats ont été engagés (3 pour les prévenus et 2 pour les victimes). 2 prévenus ont été condamnés à servitude pénale á perpétuité pour crimes contre l’humanité et 3 prévenus ont été acquittés.

Les exemples sous-mentionnés montrent les efforts et les progrès que les juridictions militaires sont entrain de réaliser en matière de crimes internationaux, grâce á l’appui des AF. Un rapport de ABA partage cette conclusion: “Certainly the mobile courts have shown that they can be very effective in meeting the challenges of trying highly visible international crimes”

Les défis sont toutefois encore nombreux.

Tout d’abord la contribution des juridictions congolaises à la justice pénale internationale manque d’une politique de poursuite cohérente telle qu’a été mise en place en Uganda par exemple, et « trahit l’approche opportuniste qui a caractérisé à la fois les poursuites devant les tribunaux militaires et le soutien des bailleurs de fonds à ces poursuites ».

Une autre difficulté que les juridictions militaires connaissent est la question du choix du droit applicable, notamment le Statut de Rome ou la législation congolaise. Ce conflit normatif est une conséquence du fait que, malgré la RDC ait ratifié le Statut de Rome en 2002,  le « projet de loi pour la mise en œuvre du Statut de Rome » dont l’objectif principal est d’introduire des modifications à la législation pénale congolaise afin de la rendre conforme au Statut de Rome, est encore en discussion au Parlement. Entretemps certaines juridictions militaires appliquent les normes du Statut de Rome au lieu du code pénal militaire dans leur pratique judiciaire en vertu du principe de l’applicabilité directe des traités internationaux dans le droit interne énoncé á l’article 215 de la Constitution.

Par exemple dans l’AF de Mambasa, le Ministère Public avait poursuivit les prévenus pour crimes contre l’humanité sur la base des articles pertinents du code pénal ordinaire et du code judiciaire militaire congolais. Faisant suite à la demande des avocats de la défense et des parties civiles d’utiliser le Statut de Rome au cours de la procédure, le tribunal a condamné les prévenus en appliquant ce dernier.

La question du droit applicable entraine des conséquences importantes vu les conflits normatifs qu’il y a  entre les dispositions nationales et celles du Statut de Rome: il s’agit inter alia de divergences dans la définition des crimes ou dans la prévision des peines. Par exemple au cours de l’AF de Mambasa le Ministère Public a demandé la peine de mort pour crimes contre l’humanité, ce qui n’est pas envisageable sous le Statut de Rome.

La compétence des juridictions civiles ou militaires pour les crimes internationaux soulève également des questions au sein de la communauté juridique congolaise. La compétence pour ces crimes était exclusive des juridictions miliaires jusqu’en Avril 2013, quand la loi de reforme de l’organisation judiciaire a reconnu cette compétence aussi aux juridictions civiles. Cette ouverture marque un développement positif, mais laisse toutefois ouvert le débat sur l’opportunité de reconnaitre l’exclusivité de la compétence aux juridictions civiles, comme prévu par le du projet de loi de mise en œuvre du Statut de Rome.

Ces aspects devraient être tenus en considération dans la programmation future du PNUD en matière d’AF, qui devrait envisager un élargissement de l’appui aux juridictions civiles.

Une dernière question qui mériterait une réflexion concerne le fait que les magistrats du Parquet reçoivent en général plus d’assistance de la part de la communauté internationale par rapport aux magistrats du siège: par exemple la CAP/MONUSCO travaille en priorité avec les procureurs de la justice militaire congolaise pour renforcer les enquêtes criminelles et les capacités en matière de poursuites judiciaires. Le projet PNUD 1888 a aussi un focus prioritaire sur les enquêtes et les poursuites du système judiciaire militaire.

Etant entendu l’urgence et l’importance d’appuyer les Parquets afin que l’action pénale soit initiée, il serait important, surtout afin d’éviter de créer un déséquilibre entre l’efficacité des actions du Siege et du Parquet, de mener en parallèle des actions visant à appuyer les magistrats du siège.

Par exemple, comme illustrée par certains rapports de monitoring PNUD et une étude d’ASF, une des faiblesses relevées dans l’analyse des jugements en matière de crimes internationaux est que « les juges ne s’attachent pas à systématiquement rappeler les éléments constitutifs des crimes ou les étapes essentielles à la qualification juridique »

Il serait donc envisageable d’organiser des formations pour renforcer les capacités des juges militaires dans la rédaction des jugements en matière de crimes internationaux. Une publication centrée sur l’analyse des jugements rendus par les AF (sur le modèle de l’étude d’ASF sur la jurisprudence en matière de crimes internationaux) serait un important outil pour renforcer les capacités des magistrats dans la rédaction des jugements sans interférer avec leur travail.

# 7. EFFICIENCE

§ 7.1 Viabilité financière

Dans un effort de coordination de l’appui aux AF, chaque partenaire international prend en charge une rubrique spécifique du budget des AF : par exemple ASF et ABA couvrent des couts relatifs aux victimes (avocats, transport victimes/témoins) et la MONUSCO/BCNUDH prennent en charge le transport en avion et la sécurité de lieux.

Les partenaires internationaux couvrent le 90 % des coûts des AF, considéré que les salaires du personnel judiciaire sont payés par l’Etat.

Le PNUD est le partenaire international qui apporte la contribution financière plus significative aux AF en Ituri et au Nord Kivu: par rapport aux 8 AF qui ont été appuyées par la communauté internationale dans ces zones de 2011 à 2012, le 78% du cout total (113.277 USD) a été soutenu par le PNUD.

Au Sud Kivu la coordination des moyens financiers est particulièrement dynamique vu la présence nombreux projets d’accès à la justice appuyés par les ONG et le système des Nations Unies.

Sur les 19 AF qui ont été appuyées par la communauté internationale en 2011/2012, le PNUD a participé á 8 des ces interventions; l’absence des données fournies par certaines partenaires (comme la BCNUDH) n’a pas permis d’en mesurer l’impact sur le total.

Les budgets des AF varient significativement en fonction du nombre des dossiers, des victimes/témoins, des avocats, des détenus à transporter et des jours d’audience.

Le tableau ci-dessous présente un exemple de budget pour une AF, estimé sur la base des coûts pour l’AF que le PNUD a appuyée à Mambasa pendent une période de 15 jours, avec 16 prévenus, 60 victimes et un coût total de 20.000 USD. Les frais pour les enquêtes préliminaires ne sont pas inclus.

A noter que les frais pour le transport de l’équipe foraine et la sécurité des lieux ne sont pas comptabilisées car ce sont des services fournis par la MONUSCO, mais représentent une partie significative du budget, dont il faudrait tenir compte dans un éventuel plan de transfert des AF au partenaire national.

| Modèle de BUDGET pour 1 AF de 15 jours avec 60 parties civiles, 16 prévenus, 8 dossiers |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | n. pax |  | n. jours | cout unité | cout total |
| Perdiem (logement/restauration) |  |  |  |  |  |
| perdiem juge | 3 |  | 15 | 59 | 2,655 |
| perdiem juge assesseur local | 3 |  | 15 | 7 | 315 |
| perdiem Officier du Ministère Public | 2 |  | 15 | 59 | 1,770 |
| perdiem greffier AF | 2 |  | 15 | 59 | 1,770 |
| perdiem greffier descentes terrain pour la signification actes | 1 |  | 6 | 59 | 354 |
| perdiem avocat de la défense | 6 |  | 15 | 59 | 5,310 |
| perdiem interprete | 1 |  | 15 | 7 | 105 |
| perdiem escorte des detenus | 16 |  | 4 | 20 | 1,280 |
| perdiem victimes et temoins | 60 |  | 10 | 10 | 6,000 |
| restauration des detenus | 16 |  | 15 | 7 | 1,680 |
| Sous total Perdiem |  |  |  |  | 21,239 |
| Transport |  |  |  |  |  |
| location véhicule pour le transport des détenus | 2 |  | 4 | 450 | 3,600 |
| transport du greffier pour les descentes préparatoires á l’audience | 1 |  | 6 | 40 | 240 |
| Sous total transport |  |  |  |  | 3,840 |
| Fournitures et frais de justice |  |  |  |  |  |
| Sonorisation | 1 |  | 15 | 50 | 750 |
| Calicot |  |  | 2 | 80 | 160 |
| fournitures de bureau |  |  |  |  | 500 |
| frais de justice (consignation parties civiles) | 60 |  |  | 10 | 600 |
| Sous total fournitures et frais de justice |  |  |  |  | 2,010 |
| Contributions en nature/non comptabilisées |  |  |  |  |  |
| Sécurité des lieux assurée par la MONUSCO. Par exemple pour l'AF de la Court Militaire de Bukavu a Uvira un TOB (Base opérationnelle temporaire de la force militaire MONUSCO) a été déployé |  |  |  |  |  |
| Transport par avion assure par la MONUSCO. Par exemple pour l'AF de la Court Militaire de Bukavu a Uvira, la MONUSCO a engagé 5 hélicoptères qui ont fait 11 sorties plus un avion gros porteur qui a fait 2 sorties; le cout est estime a plus de 100.000 USD |  |  |  |  |  |
| Sensibilisations pour la population. Ces dépenses ne sont pas couvertes par le budget des AF |  |  |  |  |  |
| Moniteurs judiciaires du PNUD, BCNUDH, ABA, ASF, MONUSCO/CAP… |  |  |  |  |  |
| Avocats de la victime. Ces frais sont payés par les ONG à leurs avocats-consultants sous forme d'indemnités mensuelles |  |  |  |  |  |
| Enquêtes du Parquet. Ces dépenses ne sont pas couvertes par le budget des AF |  |  |  |  |  |
| Salle d'audience. En général les AF se font en plein air; des hangars sont construits la où siège le tribunal. Dans les localités où il y a une salle, généralement les juridictions l'obtiennent gratuitement |  |  |  |  |  |
| TOTAL POUR L'AUDIENCE FORAINE |  |  |  |  | 27,089 |

Une question qui soulève quelques points de discussion est l’harmonisation des Perdiem pour l’équipe foraine. D’un coté on note une différence entre les montants des Perdiem octroyés par les partenaires internationaux : les membres de l’équipe foraine reçoivent 59 USD du PNUD, 48 USD de ABA et un montant indicatif de 45 USD de ASF. A noter que cette question est ressortie très clairement au Sud Kivu, mais ne semble pas poser un problème au Nord Kivu et en Ituri, ou l’harmonisation á 59 USD a été faite sans problème.

Certaines autorités judiciaires ont souhaité introduire une différence entre les Perdiem des différents membres de l’équipe : couramment le fait que le juge perçoive le même montant que le greffier (59 USD) semble poser un problème. Le PNUD insiste d’expliquer aux autorités judicaires que ce montant représente un Perdiem pour les frais de séjour, qui ne peuvent pas être liés au grade au sein des juridictions.

Afin d’éviter des discussions entre les différentes équipes foraines déployées, il serait recommandé que les partenaires internationaux se mettent d’accord pour un adopter le même perdiem.   ABA a souligné qu’il pourrait être difficile de mettre en place cette approche car les partenaires doivent respecter les tarifs qu’ils ont négociés avec le bailleur dans le budget du projet. Cet obstacle pourrait pourtant être surmonté par la signature du Protocole d’entente décrit au § 6.1

Il serait par ailleurs recommandé d’assurer, afin de faciliter un éventuel transfert des activités aux juridictions, que le perdiem octroyé par les partenaires internationaux soit en ligne avec les barèmes fixés par l’état congolais pour les fonctionnaires en mission dans le «Statut des agents de carrière des services publics de l’état ».

Plusieurs personnes ont critiqué les procédures administratives du PNUD pour leur lenteur et complexité. Le président de la Cour Militaire de Goma estime qu’auprès du PNUD «il faut trop de temps pour démarrer la machine des AF ».  Normalement un minimum de 4 semaines s’écoule entre la soumission de la demande d’appui de la part d’une juridiction et la réponse du PNUD. La procédure est particulièrement lourde pour les bureaux de Bunia et Bukavu car les propositions doivent être préliminairement soumises au bureau PNUD de Goma. Le Bureau de Bukavu souhaite pouvoir disposer d’une avance trimestrielle pour gérer les AF de façon indépendante.

Le Président du Tribunal Militaire de Garnison de Bukavu recommande d’accélérer et de rendre plus flexibles les procédures pour octroyer les fonds de fonctionnement des AF afin de pouvoir respecter les délais légaux des procédures judiciaires.

Le Président rappelle que pour les infractions graves les délais sont très courts: seulement 4 mois, qui se réduisent à 3, vu le mois nécessaire pour la planification avec le PNUD. Il souhaiterait que les moyens financiers ne soient pas délivrés par le PNUD le jour même du départ en foraine et rappelle que, surtout pour les infractions flagrantes, il est impératif d’agir rapidement.

§ 7.2. La coordination entre partenaires internationaux

Les modalités d’appui aux AF en DRC représentent une excellente pratique en termes de coordination et complémentarité entre les différents partenaires internationaux, notamment  le PNUD, les sections Droits de l’homme, Etat de droit et CAP de la MONUSCO, Avocats sans Frontières, American Bar Association ainsi que des partenaires nationaux comme Association des femmes juristes, SOFEPADI. Cette approche permet de mieux valoriser l’avantage comparatif de chaque organisation et offre aux juridictions un cadre de référence transparent et partagé.

Des fora de coordination pour l’organisation des AF sont en place dans toutes les 3 zones d’intervention du PNUD (Nord Kivu, Sud Kivu, Ituri) et ont arrangé nombreuses réunions des partenaires depuis la phase des enquêtes du Parquet, comme illustré au § 5.1. L’objectif est non seulement de coordonner les aspects organisationnels et financiers mais aussi d’assurer une assistance technique de qualité grâce aux apports de chaque partenaire selon ses propres avantages comparatifs.

Il s’agit toutefois d’une coopération informelle, qui trouve ses limites dans le fait que chaque partenaire intervient sur la base de son propre mandat et stratégie d’intervention.

Une collaboration mieux encadrée par un Protocole d’entente serait souhaitable pour améliorer la planification et le suivi des AF, en particulier pour ce qui concerne l’adoption d’outils de travail en commun (formulaires, bases de donnes, rapports de monitoring) ainsi que pour éventuellement assurer une meilleure visibilité de l’initiative auprès des bailleurs et au niveau international.

Une solution pour améliorer la gestion financière des AF, qui a été beaucoup discutée au cours des entretiens et qui a été accueillie favorablement par la plupart des partenaires internationaux et toutes les juridictions, est la création d’un basket fund (panier de fonds) pour la gestion en commun des fonds que la communauté internationale destine aux AF. Le chef de mission d’ABA recommande que le basket fund soit installé au niveau de Kinshasa et pas au niveau des provinces.

Les modalités de gestion du basket fund pourraient être disciplinées dans le cadre du Protocole d’entente entre les partenaires internationaux et les autorités judiciaires illustré au § 6.1.

A la question de savoir quelles autorités judicaires devraient représenter la partie nationale dans la gestion du basket fund différentes options ont été avancées, en particulier: le Ministère Provincial de Justice, la Division du Ministère de la Justice dans les Provinces et le Ministère de la Justice au niveau central á Kinshasa.

Un des partenaires internationaux pourrait être identifié pour représenter la partie internationale.

Etant vu que la majorité des répondants a estimé que les juridictions ne seraient pas encore prêtes à gérer directement les fonds pour les AF, le basket fund pourrait représenter un modèle intérimaire en préparation du transfert de la gestion financière aux juridictions.

La Représentante du Ministère de la Justice à Goma a tenu à souligner l’expérience positive du bureau du Ministère au Nord Kivu dans la gestion directe de fonds octroyés par UNICEF : un Protocole d’accord est signé chaque 2 ans, les fonds sont virés dans les comptes du Ministère, qui assure un reporting régulier après avoir mis en place les activités.

Finalement une attention particulière devrait être réservée à la coordination avec le programme Uhaki Safi (« Bonne Justice » en Swahili) lancé par l’Union Européenne en 2013 et exécuté par les ONG ASF et RCN. Il s’agit d’un programme qui inclus des activités en appui aux AF dans les provinces du Nord et du Sud Kivu et le territoire de l'Ituri, et qui succède au « Programme de renforcement de la Justice à l'Est du Congo (REJUSCO) ».

§ 7.3. Contraintes et défis

Les facteurs qui affectent la performance des AF et les contraintes auxquelles sont confrontées les autorités judiciaires et les partenaires internationaux ont été illustrées en détail dans les paragraphes précédents, mais sont résumées ci-dessous pour faciliter la lecture.

- Manque d’une vision stratégique et aspects controversés du modèle d’AF  (appui prioritaire aux juridictions militaires; priorisation des dossiers de VBG; nature conjecturelle des AF)

- Faiblesses dans la planification et le suivi des AF (faiblesse du cadre stratégique d’intervention au niveau du PNUD et absence d’un cadre concerté au niveau de la communauté internationale, faiblesses du système de collecte des données statistiques, procédures administrative PNUD trop lourdes)

- Faible appropriation nationale et absence de stratégie de pérennisation (absence d’une politique nationale pour les AF ; conditions d’appui aux AF définies sur la base des intérêts des bailleurs, aspects financiers et de reporting gérées par les partenaires internationaux, manque de contribution financière du gouvernent congolais)

- Faiblesses dans la procédure judiciaire (temps limité pour la tenue des AF ; violation du principe de la parité des armes au vu de la meilleure qualité des services des avocats des parties civiles; difficultés á assurer la comparution des victimes et témoins au procès ; très faible taux d’exécution de jugements ; absence de mécanismes de réparation pour les victimes; faible protection des victimes et témoins après le procès; écart significatif entre le nombre de juges du siège et du parquet dans les juridictions civiles)

- Faiblesses du système pénitentiaire (fréquentes évasions; couts élevés pour le transfert des condamnées/prévenus des AF)

- Couts élevés pour l’organisation des AF

§ 7.4. Bonnes pratiques

Le système des AF appuyé par les partenaires internationaux en RDC a développé les bonnes pratiques signalées ci-dessous.

- Une approche intégrée qui appuie toutes les phases de la chaine pénale. L’appui du PNUD ne se limite pas aux AF, mais est étendu aux activités préliminaires qui se déroulent avant l’AF, notamment les enquêtes du Parquet, les missions de la Greffe pour la signification des actes, le transfert des prévenus en détention préventive vers les lieux où se tiennent les audiences. Par conséquence touts les dossiers traités en foraine sont en état, ce qui détermine un nombre extrêmement bas de renvoi des audiences.

- Un appui en excellente synergie/complémentarité de la part de la communauté internationale. Plusieurs partenaires internationaux du secteur de la justice contribuent, en termes d’assistance technique et financière et sur la base des respectifs avantages comparatifs, à l’organisation de chaque AF. La coordination est assurée par des « fora de coordination des AF » gérés par les partenaires internationaux avec la participation des autorités nationales.

- La complémentarité avec la Cour Pénale Internationale. De 2011 a 2012 au moins 10 dossiers de crimes internationaux (crimes contre l’humanité et crimes de guerre) ont été traitées par les AF appuyées par le PNUD ; ce qui a représenté une importante opportunité pour renforcer les capacités des juridictions nationales dans la poursuite des crimes prévus par le Statut de Rome.

- L’inclusion des AF dans le système de monitoring judiciaire du PNUD. Sur 16 AF appuies par le PNUD en 2 ans, 12 AF ont été monitorées par des moniteurs judiciaires PNUD, ce qui a permis d’assurer un contrôle sur la conformité aux standards internationaux du procès équitable.

# 8. DURABILITE

§ 8.1. La pérennisation des résultats atteints

Un élément de durabilité des AF est représenté par le fait qu’elles ne sont pas une institution imposée par la communauté internationale ou transplantée depuis d’autres systèmes légaux, mais c’est une pratique enracinée dans le système judiciaire congolais depuis 1979.

Cette appropriation est démontrée par le fait que les juridictions organisent, dans un format plus réduit, des AF sans l’appui financier des partenaires internationaux : par exemple les TGI de Bunia et de Goma organisent des AF hebdomadaires dans les prisons.

Une autre opportunité de pérennisation est représentée par les compétences que les autorités judiciaires ont acquis en organisant les AF : plusieurs chefs de juridictions ont rapporté de se « sentir en mesure d’organiser les AF par eux-mêmes, s’ ils en avaient les moyens ».

A noter par ailleurs que les AF commencent à développer une expertise dans la poursuite des crimes internationaux, qui pourrait éventuellement être mis au service des futures « Chambres spécialisées pour la répression des violations graves du droit international humanitaire ».

Le manque des moyens financiers combiné avec l’absence d’une stratégie spécifique pour les AF au niveau national, conduit pourtant à la conclusion que les juridictions congolaises ne seront pas en mesure de continuer à organiser les AF dans le futur proche sans un appui de la communauté internationale.

Par ailleurs, malgré les juridictions aient acquis une compétence reconnue sur le plan technique, certains aspects clefs dans l’organisation des AF, comme le reporting et la gestion financière sont encore gérés entièrement par les partenaires internationaux.

A la lumière des ces observations, il serait recommandé de dédier une attention particulière à assurer que les interventions s’inscrivent plus dans la durée.

L’éventuel Protocole d’entente avec les autorités judiciaires devrait inclure une stratégie de transfert des activités aux partenaires locaux.

Les activités suivantes pourraient être poursuivies pour promouvoir davantage la pérennisation des AF :

- Mener des actions de plaidoyer auprès du Ministère de la Justice pour adopter une stratégie nationale pour les AF, implanter de juridictions permanentes additionnelles et encourager la progressive contribution financière du gouvernement á l’organisation des AF.

- Graduellement transférer la gestion financière des AF aux autorités judiciaires congolaises, éventuellement en commençant par mettre en place le basket fund illustré au § 7.1.

- Diffuser une culture du suivi de projet en assurant une participation des juridictions aux activités de suivi des AF en particulier pour ce qui concerne la collecte et l’analyse des données statistiques.

- Faciliter la consolidation des acquis des AF.  Les outils et la méthodologie pour organiser les AF développés par les partenaires internationaux pourraient être récoltés dans une publication illustrant les bonnes pratiques, les histoires à succès et l’analyse des jugements afin d’offrir un point de repère dans le  débat pour le développement d’une stratégie nationale pour les AF ainsi que pour la replicabilité des AF dans d’autres provinces de la RDC ou d’autres Bureaux Pays PNUD.

9. IMPACT

§ 9.1. Les changements produits par les AF

►Changements pour les bénéficiaires

Vu que pendent la mission d’évaluation il n’a pas été possible de rencontrer les usagers des AF ni d’observer une AF, les points qui suivent se limitent à rappeler quelques éléments qui ont été mentionnés par les personnes interrogées afin de souligner les changements que les AF auraient produit pour la population.

- Les partenaires internationaux et les autorités judiciaires ont à plusieurs reprises mentionné les aspects pédagogiques des AF, dans la mesure où elles représentent une opportunité pour expliquer le droit à la population.

Quelque réserve pourrait toutefois être avancée sur l’impact pédagogique des AF, car les statistiques indiquent un nombre très réduit de sessions de sensibilisation pour la population, avant et après les AF. Des réseaux de parajuristes ou d’autres mécanismes communautaires pour accompagner les populations dans leur parcours de compréhension du droit ne sont pas en place dans le cadre des AF appuyées par le PNUD. Les annonces passées par les radios communautaires se limitent à annoncer l’arrivée des AF. Le nombre élevé de personnes qui assistent aux AF n’est pas suffisamment indicatif de l’effet pédagogique des AF : vu le niveau de connaissance du droit de la population dans les territoires éloignées des sessions de sensibilisation spécifiques sur les AF seraient nécessaires.

- Dans certaines zones touchées par le conflit en cours, des services de justice formelle pour la population ont été disponibles pour la première fois. Comme précisé par des analyses PNUD á Bunia a précisé que « à Mambasa c’était la première fois que les gens voyaient un tribunal ».

- Un impact positif sur la population a aussi été exprimé en termes de favoriser le retour progressif de la confiance dans la justice et le rapprochement de la justice aux justiciables.

La directrice de SOFEPADI estime au contraire que les AF ont peu d’impact en termes de confiance dans la justice vu qu’il arrive souvent que les peines ne sont pas purgées en prison car « les condamnés sont là quelques mois et après ils se retrouvent dehors, parfois après s’être évadés».

- Plusieurs personnes interrogées ont souligné que les AF ont un effet dissuasif et créent plus de sécurité dans les communautés en réduisant le taux de criminalité.

Les commentaires sur la perception de la justice dispensée par les tribunaux militaires varient : certains représentants des ONG reconnaissent que cela peut être traumatisant pour une femme victime de viol de voir un juge habillé comme celui qui l’a violée ; au contraire le Commandant de l’Unité de Police spéciale pour les femmes de Goma estime que «une femme violée par un homme en uniforme voit qu’il y a une justice, son bourreau est poursuivi par des militaires. L’image des militares est restauree”.

► Changements pour les acteurs de la justice

- Le renforcement des capacités des acteurs de la justice est un changement évident souvent mentionné au cours des entretiens. Par exemple le chef de l’Unité de Police pour la protection des femmes et des enfants à Goma rapporte que « grâce aux AF ils ont appris à s’améliorer, car ils apprennent á bien construire leurs dossier, et bien présenter leurs preuves afin qu’ils soient accueillis par le Parquet».

Le Président du TMG de Bukavu souligne que les AF ont permis aux juges militaires d’acquérir une expérience en matière de crimes internationaux, qui est une matière nouvelle vu qu’elle n’a pas été apprise á la faculté de droit » et d’augmenter le nombre des  dossiers traités par les juridictions militaires. Le président a tenu à souligner l’importance de la participation des partenaires internationaux aux AF car ils ont la possibilité de mieux comprendre les difficultés rencontrées sur le terrain.

- Les AF facilitent la recherche des preuves car les témoins sont atteints plus facilement.

- Le risque de corruption est réduit car les magistrats ne travaillent pas dans leur milieu habituel.

PARTIE III: CONCLUSIONS ET RECCOMANDATIONS

§ 10. Conclusions

Le degré de réalisation des résultats est satisfaisant dans son ensemble et tenant compte des difficultés du contexte d’intervention dans l’Est de la RDC.

Le modèle d’AF mis en place avec l’appui du PNUD est exemplaire pour son approche intégrée, qui appuie toutes les phases de la chaine pénale et pour la participation en synergie et complémentarité de différents partenaires internationaux. Il s’agit d’un modèle qui n’est pas développé dans le cadre d’une stratégique d’intervention, ni au niveau des partenaires internationaux ni au niveau national, mais représente un apport conjoncturel pour régler des affaires judiciaires ponctuelles qui émergent du conflit en cours, parfois qualifiées comme crimes internationaux.

Le modèle congolais présente des aspects controversés, notamment l’appui prioritaire aux dossiers de violences basées sur le genre et aux juridictions militaires (en partie justifié par le fait qu’au début du projet les violences sexuelles étaient commises en priorité par les militaires dans les zones du conflit)

Les remarques ci-dessous consolident les observations recueillies au cours des entretiens et présentent des conclusions générales pour chaque critère d’évaluation.

# Pertinence

Les AF sont une priorité reconnue dans la législation congolaise et dans les stratégies nationales du secteur de la justice, toutefois les modalités de leur mise en œuvre pourraient être mieux encadrées,  éventuellement par un Protocole d’entente entre les partenaires internationaux et les autorités judiciaires.  Le manque d’orientation de la part des autorités centrales combiné avec l’absence d’une planification stratégique au niveau provincial s’est traduit dans la pratique avec l’organisation d’AF qui répondent à un besoin ponctuel et représentent un modèle fortement influencé par les priorités des bailleurs de fond.

Les AF ont étés une mesure efficace pour atteindre les zones reculées où les juridictions permanentes étaient absentes et lutter contre l’impunité des crimes internationaux commis dans ces territoires.

Les AF ont été très pertinentes par rapport aux politiques nationales de lutte contre les VBG, notamment dans les cas de VBG commises par les militaires,  vu la priorité accordée par les AF a cette catégorie de dossiers. Une réflexion serait toutefois nécessaire sur l’opportunité de commencer à élargir le champ d’intervention des AF à toutes les infractions : non seulement parce que les auteurs de viol sont de plus en plus des civils, mais aussi dans le but d’assurer aux victimes non-VBG les mêmes opportunités d’accéder à la justice que les victimes VBG. Le PNUD a pris en compte ces aspects en réduisant le nombre minimal de dossiers VBG requis pour appuyer une AF.

# Efficacité

La planification de l’initiative pourrait bénéficier d’un cadre des ressources plus spécifique, éventuellement avec des indicateurs, cibles et aspects financiers harmonisées entre tous les partenaires internationaux qui appuient les AF. Le suivi des AF dans le cadre du projet « monitoring judiciaire » est une excellente initiative qui a permis d’avoir un aperçu impartial des résultats atteints par les AF ; des faiblesses ont pourtant été relevées au niveau du système de collecte des données relatives aux AF observées.

Des résultats satisfaisants ont été réalisés, mais en absence d’indicateurs spécifiques il est difficile d’en préciser la mesure par rapport aux cibles. Au courant du 2011 et 2012, un total de 16 audiences foraines ont été organisées avec l’appui du PNUD pour 198 jours en foraine et une contribution de 155.000 USD. 97 avocats et 72 magistrats/juges assesseurs ont participé aux AF. 202 dossiers ont été enrôlés, dont 60% de VBG et 206 jugements ont été prononcés.

La pratique judiciaire des AF apparait en général en bonne voie vers la conformité avec les standards internationaux, sauf pour les aspects suivants qui devraient être renforcés : 1) la parité des armes entre les parties au procès 2) la protection des victimes et des témoins 3) certains aspects de la procédure militaire, comme le régime de la détention préventive 4) l’exécution des jugements 4) la durée et l’excessive célérité des AF.

Efficience

Le cout des AF analysées varie entre 8.000 et 25.000 USD en fonction du nombre de dossiers, de victimes et d’autres éléments; ils sont entièrement soutenus par les partenaires internationaux. Les budgets s’élèvent significativement si l’on inclue les activités préliminaires et les services de transport aérien et de sécurité fournis par la MONUSCO, au point qu’ils semblent difficilement soutenables par le gouvernement congolais. Les procédures financières du PNUD ont été jugées trop complexes et la gestion financière administrée uniquement par les partenaires internationaux affaiblis l’appropriation nationale.

L’appui aux AF s’est développé en excellente synergie et en toute complémentarité entre les partenaires internationaux qui contribuent, en termes d’assistance technique et financière et sur la base des respectifs avantages comparatifs, à l’organisation de chaque AF. Cette coordination pourrait bénéficier d’un cadre de travail formel, comme un Protocole d’entente, afin d’améliorer la planification, le suivi et l’harmonisation de certains aspects des interventions.

Durabilité

Certains éléments de durabilité des AF sont évidents: non seulement cette pratique existe dans le système judiciaire congolais depuis 1979, mais aussi les autorités judiciaires ont démontré d’avoir acquis des bonnes compétences dans l’organisation des AF au cours des années de collaboration avec le PNUD. Le manque de moyens financiers pour soutenir les couts élevés des AF combinée avec l’absence d’une stratégie nationale pour les AF, conduit toutefois à la conclusion que les juridictions congolaises ne seront pas en mesure de continuer à organiser les AF dans le futur proche sans un appui de la communauté internationale. Dans quelques rares occasions les juridictions ont organisé des AF sans appui financier extérieur, en particulier le TGI de Bunia.

Malgré les AF soient menées entièrement par les autorités judiciaires nationales et avec un bon niveau de compétence technique, l’appropriation nationale de l’initiative reste faible, notamment dans la planification, le suivi et la gestion financière.

Impact

Les AF ont un effet dissuasif sur les criminels et créent plus de sécurité dans les communautés en réduisant le taux de criminalité. Elles ont favorisé le retour progressif de la confiance de la population dans la justice et le rapprochement de la justice aux justiciables. En observant les procès, la population a pu mieux comprendre le fonctionnement du système judiciaire; la fonction pédagogique des AF pourrait toutefois être renforcée en augmentant et rendent plus systématiques les sensibilisations pour la population visant à expliquer le rôle et les objectifs des AF. Dans certaines zones visitées par les AF c’était la première fois que la population entrait en contact avec le système de justice formelle.

Les AF ont eu un impact positif sur la promotion et l’application du droit pénal international en complémentarité avec la CPI. Les AF ont renforcé la capacité des autorités nationales de poursuivre et juger des crimes internationaux. Un nombre croissant de dossiers de crimes de guerre et crimes contre l’humanité est traité par les AF : au moins 8  de ces dossiers ont été jugés au cours des AF appuyées par le PNUD dans l’est de RDC.  Les importants défis de cette nouvelle branche du droit congolais dérivent principalement de l’absence d’un cadre juridique de référence : le retards dans l’adoption d’une loi de mise en œuvre du Statut de Rome pose aux juridictions la question du choix du droit applicable (Statut de Rome ou législation congolaise) et laisse ouvert le débat sur la compétence exclusive des juridictions miliaires ou civiles pour les crimes internationaux.

§ 11. Recommandations

Les points qui suivent se proposent de résumer les recommandations illustrées dans le corps du rapport afin d’améliorer la mise en œuvre des AF. Elles concernent principalement les aspects stratégiques et de gestion des AF et en mesure mineure les aspects strictement juridiques, qui sont en bonne voie vers les standards internationaux du procès équitable.

1. Appuyer davantage les juridictions civiles

- Considéré que la compétence pour les crimes internationaux a été reconnue aux juridictions civiles á partir d’Avril 2013, et que le taux de violences sexuelles commis par les militaires est entrain de diminuer, il serait opportun d’appuyer d’avantage les juridictions civiles dans l’organisation des AF et graduellement réduire le soutien aux militaires.

2. Elargir les AF á toutes les infractions

- Considéré l’éventualité d’une discrimination á l’égard de victimes d’infractions non-VBG dans leur droit d’accès à la justice, il serait recommandé de discuter avec les bailleurs la possibilité de réduire davantage ou éventuellement abolir le critère relatif au pourcentage minimal de dossiers VBG requis pour organiser une AF.

- En parallèle il faudrait relancer l’image des AF par une stratégie de communication visant á changer la perception des AF comme des instruments de lutte contre les VBG.

3. Adopter une stratégie d’intervention et une planification des AF

- Identifier un modèle d’intervention.

Un système d’AF mixte, intégrant « le modèle continu » et « le modèle ponctuel/ad hoc» d’intervention pourrait être envisagée.  Des AF mises en ouvre selon « le modèle continu » pourraient être appuyées dans les territoires où le contexte et la cartographie judiciaire le permettent, avec l’objectif principal de promouvoir l’accès à la justice pour les groupes vulnérables et en assurant la prise en charge de tout dossier civil ou pénal. En même temps le PNUD pourrait continuer à appuyer un nombre plus limité d’AF selon le « modèle ponctuel/ad hoc » dans les zones reculées où les autorités judiciaires sont absentes et le conflit est en cours, avec l’objectif de lutter contre l’impunité pour les crimes internationaux en complémentarité avec la CPI et en assurant une priorité aux dossiers qui relèvent du Statut de Rome.

- Opérationnaliser la stratégie sous-mentionnée par la rédaction d’un Protocole d’entente annuel entre les partenaires internationaux qui appuient les AF et les autorités judiciaires (un accord de principe avec le Ministère de la Justice au niveau national et un accord opérationnel au niveau des provinces).

- Plaidoyer pour l’implantation des juridictions permanentes dans les zones d’intervention.

4. Promouvoir la durabilité et l’appropriation nationale

- Prévoir une stratégie de transfert des compétences aux juridictions congolaises et renforcer l’appropriation nationale en vue de ce transfert, en assurant une participation plus active des juridictions dans les activités de suivi, de gestion financière et de planification.

Une réflexion pourrait être menée dans le cadre de la stratégie mentionnée à la recommandation n.3, afin d’identifier quel serait le modèle d’AF à pérenniser dans un contexte comme la RDC. En principe les efforts de pérennisation semblent plus pertinents par rapport aux AF mises an place selon le « modèle continu », vu les coûts élevées et la nature temporaire des AF organisées selon le « modèle ponctuel/ad hoc ».

5. Graduellement transférer la gestion financière aux autorités judiciaires congolaises

- Mener une réflexion sur l’opportunité de créer un basket fund (panier de fonds) pour la gestion en commun des fonds que la communauté internationale destine aux AF, en tant que mesure intérimaire en préparation du transfert de la gestion financière aux juridictions.

- Encourager les partenaires internationaux à harmoniser les perdiem octroyés aux équipes en foraine et  s’assurer qu’ils soient en ligne avec les barèmes fixés par l’état congolais.

6. Améliorer le suivi et promouvoir la consolidation des acquis des AF

- Adopter un format standard pour les rapports de monitoring des AF ;

- Mettre en place une base de donnés sur Excel pour faciliter l’analyse des résultats atteints ;

- Assurer la participation des juridictions aux activités de suivi des AF ;

- Rédiger périodiquement pour la diffusion extérieure un bulletin sur les résultats atteints par les AF avec l’illustration d’histoires à succès et dossiers emblématiques.

7. Recommandations concernant les aspects juridiques

- Assurer le principe de la parité des armes au procès en appuyant davantage les avocats des prévenus

- Renforcer les mesures de protection des victimes et des témoins

- Renforcer l’exécution des jugements, surtout en matière de condamnation civile (versement de dommages-intérêts);

- Mener en parallèle avec l’appui aux Parquets des actions visant les magistrats du siège;

- Plaidoyer pour une politique nationale de poursuite des crimes internationaux et pour l’adoption d’une loi pour la mise en œuvre du Statut de Rome.

ANNEXE n.1

Les documents consultés sont disponibles sur le fichier partagé crée pour la présente évaluation sur Dropbox.

https://www.dropbox.com/sh/kn177z4dddfvgyp/AbtqXNN4Ai

Documents consultés

A) Doctrine

- AfriMAP et Open Society Initiative for Southern Africa, « La justice militaire et le respect des droits de l’homme – L’urgence du parachèvement de la réforme », 2009

- American Bar Association/Rule of Law Initiative, “Mobile Courts in the Democratic Republic of Congo: Complementarity in Action?”

- American Bar Association/Rule of Law Initiative, « Mobile courts in the DRC : lessons from development for international criminal justice », 2011.

- Amnesty International, « The time for justice is now: New strategy needed in the Democratic Republic of the Congo”, 2011

- Avocats sans Frontières, “Rapport d’évaluation externe des projets support aux audiences foraines et boutiques de droit dans les provinces de l’Equateur et du Maniema en République Démocratique du Congo », 2008

- Avocats sans Frontières, « Etat des lieux de la détention provisoire en République Démocratique du Congo », 2008

- Avocats sans Frontières, « Une justice équitable en RDC : Les audiences foraines une expérience pilote réussie », 2006

- Avocats sans Frontières, «Etude de jurisprudence : l’application du statut de Rome de la cour pénale internationale par les juridictions de la république démocratique du Congo », 2009

- Club des amis du droit du Congo « La répression des crimes internationaux par les juridictions congolaises », 2011

- Fédération internationale des ligues des droits de l’homme, « Crimes sexuels en République démocratique du Congo (RDC): Briser l'impunité », 2008

- Global Rights, « Le Monitoring du Système Judiciaire Un manuel pratique à l’usage des moniteurs de la société civile congolaise », 2008

- Human Rights center University of California, Berkely and ICTJ, « Vivre dans la peur. Une  étude réalisée au sein de la population sur la paix, la justice et la reconstruction sociale dans l’Est de la République démocratique du Congo », 2008,

- Human Rights Watch, « Les soldats violent, les commandants ferment les yeux Violences sexuelles et réforme militaire en République démocratique du Congo », 2009

- IFPRODUCTIONS, Documentary “Justice for sale” by Ilse and Femke van Velzen, 2011.  www.justiceforsale.nl

- International Alert, « La guerre n’est pas encore finie. Perceptions communautaires des violences sexuelles et leurs fondements à l’est de la RDC », Novembre 2010

- International Justice, « Les tribunaux itinérants dans l’est du Congo », 2013

- International Legal Assistance Consortium and International Bar Association Human Rights Institute, “Rebuilding courts and trust: An assessment of the needs of the justice system in the Democratic Republic of Congo”, August 2009,

- MONUSCO, « Rapport sur la détention dans les prisons et cachots de la RDC », 2004

- Office of the UN High Commissioner for Human Rights , « Rapport du Panel à la Haut Commissaire aux Droits de l'Homme sur les moyens de recours et de réparation pour les victimes de violences sexuelles en République Démocratique du Congo », 2011

- Office of the UN High Commissioner for Human Rights, « Rapport du Projet Mapping concernant les violations les plus graves des droits de l’homme et du droit international humanitaire commises entre mars 1993 et juin 2003 sur le territoire de la République démocratique du Congo », Août 2010

- Open Society Foundations, « Putting Complementarity into Practice: Domestic Justice for International Crimesin DRC, Uganda, and Kenya”, 2011

- Open Society Initiative for Southern Africa, Helping to combat impunity for sexual crimes in DRC: An evaluation of the mobile gender justice courts”, 2012;;

- PNUD, « Monitoring judiciaire 2010-2011. Rapport sur les données relatives à la réponse judiciaire aux cas de violences sexuelles à l’Est de la République démocratique du Congo », 2010

- PNUD «Discussion paper: Complementarity and Transitional Justice: Synthesis of Key Emerging Issues for Development”, 2012

- RCN Justice & Démocratie “La justice de proximité au Bas-Congo”, 2009

- Global Rights, « Rapport d’enquête sur quatre problèmes majeurs de la justice : vers un état de non droit en RDC ? Le cas de la province du Sud Kivu », 2009

- Wageningen University, « Fond de commerce? Sexual violence assistance in the Democratic Republic of Congo”, 2012

B) Législation

- Avant-projet de Loi relative aux Chambres spécialisées pour la répression des violations graves du droit international humanitaire

- LOI N°023/2002 DU 18 NOVEMBRE 2002 PORTANT CODE JUDICIAIRE MILITAIRE

- LOI N° 024/2002 DU 18 novembre 2002 PORTANT  CODE PENAL MILITAIRE

C) Documents PNUD et Ministère de la Justice

- PLAN D’ACTIONS POUR LA REFORME DE LA JUSTICE, Ministère de la Justice, 2007

- Rapport de monitoring judiciaire de l’AF du TMG de Bunia á Mamabasa (Ituri, 2012)

- Rapport de monitoring judiciaire de l’AF du TMG de Bunia á Komanda (Ituri, 2012)

- Rapport de monitoring judiciaire de l’AF du TGI de Bunia á Mahagi (Ituri, 2011)

- Rapport de monitoring judiciaire de l’AF du TMG de Bunia á Opasse (Ituri 2011)

- Rapport de monitoring judiciaire de l’AF de la CM du Nord Kivu á a Butembo (Nord Kivu, 2012)

- Rapport de monitoring judiciaire de l’AF du TMG de Bukavu á Walungu (Sud Kivu, 2011)

- Rapport de monitoring judiciaire de l’AF du TMG de Bukavu á Kalehe (Sud Kivu, 2011)

- Rapport de la Court D’appel de Bukavu pour l’AF á Kamitunga(Sud Kivu, 2012)

- Document de projet 1888

- Document de projet SIDA

- TDR pour les AF

ANNEXE n.2

Personnes rencontrees (du 18/03/13 au 27/03/13)

- Adolfe Mukelenga, Responsable du corps des défenseurs judiciaires près le TGI du Nord-Kivu

- Adolphe Kayumba, moniteur judiciaire, Bureau PNUD Bukavu

- Bernard Amisi, moniteur judiciaire, Bureau PNUD Bukavu

- Camille Kambala, magistrat enquêteur des crimes graves, TMG, Bukavu

- Comite d’appui aux AF de Bunia (Colonel KALALA, 1er Président Cour militaire de la Province Orientale, Major Kabeya, Président du Tribunal militaire de garnison de Bunia, Papy NYANGUILE du BCNUDH ; Me Désiré BALUME de la Section d’Appui à la Justice/Monusco, Me MAGENE Ngoli, Doyen de la section locale de Bunia pour le Barreau de Kisangani).

- Cornelia, Schneider, Chef de Projet Accès à la Justice PNUD

- Cour d’Appel de Bukavu  (Aboubacar Lubenga, premier président de la Cour d’Appel de Bukavu ; le Président Shamavu et les conseillers Tchibola et Mule)

- Cyprien Gangnon, Chef de bureau PNUD Bunia,

- David Bodeli, Commandant, Police spéciale pour la protection de la femme et de l’enfant, Goma

- Guillaume Auditeur judiciaire, Auditorat de Garnison de Goma.

- Guy Makongo, Country Director, American Bar Association Rule of Law Initiative, Goma

- Henri Mashagiro, spécialiste de projet, PNUD

- Herve Mbanda, Président du tribunal pour enfants de Goma

- Ingenge MISHUMBI, Président a.i. du tribunal de grande instance de Bunia

- Isaac Mushokoro, Moniteur judiciare PNUD, Goma

- Jean Mutabesha, Associé Juriste, PNUD Bunia

- Jennifer Tsai, Access to justice advisor, ABA-ROLI, Goma

- Joseph Bahogwerhe moniteur judiciaire, Bureau PNUD Bukavu

- Kasha, substitut Auditeur, Auditorat Militaire de Garnison de Bukavu ;

- Kasuza Mwenge, Responsable du bureau des consultations juridiques gratuites au sein du Barreau de Goma

- Louise Mutalegwa,  Monitrice Juriste, PNUD Bunia

- Louise TAJIKI, Coordinatrice de SOFEPADi, Bunia

- Lydia Masika, Chef de Division du Ministère de la Justice a Goma

- Major Kabeya, Président du Tribunal Militaire de Garnison de Bunia

- Marcellin Chishambo, gouverneru du Sud Kivu (dans le cadre de la réunion avec l’équipe PNUD pour la formulation du programme PNUD 2013-2018)

- Marie Louise Issanda (associée juriste), Bureau PNUD Bukavu

- Membres du Cadre de Concertation Nord Kivu

- Musingi Abonabo, Directeur de la Prison centrale de Goma

- Parfait Ngona, Président du Tribunal de Grande Instance de Goma

- Rémy Kilimpimpi, Premier Président de la Cour Militaire de Goma

- Representats des ONG Dynamique femmes juristes, ABA-ROLI et Synergie pour l’assistance judiciaire

- Serge Pibwe, President du Tribunal militaire de Garnison de Bukavu ;

- Task Force Justice pour le Sud Kivu (Aurora Chapelier et Jolie pour ASF, Olivier Mbasha et Faustin Wessa pour ABA, le colonel Mamy Rasoanaivo pour la MONUSCO/CAP et Richard Kassa pour la section d’appui a la justice MONUSCO)

- Thierry Kambere, spécialiste de projet, Bureau PNUD Bukavu

ANNEXE n.3

| Audiences foraines appuyées par le PNUD du 01/2011 au 12/2012 dans l’est de la RDC |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Juridiction | Lieu | Dates | n. jours | n. Dossiers |  | n. Décisions rendues |  |  | Contributions financières USD |  | Cout total USD | Activités préliminaires et informations additionnelles |
|  |  |  |  |  | VBG | autre | Condamnations | Acquittements | autre | PNUD | autres |  |  |
| → District de l’ITURI |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Tribunal de Grande Instance de l’Ituri | Mahagi | 2011 Du 22/03 au 05/04/2011 | 15 | 13 | 5 | 18 | 0 | 5 | 10.000 | - | 10.000 | Mission de la Greffe : 1 Moniteur PNUD :1 |
| 2 | Tribunal de Grande Instance de l’Ituri | Mahagi | 2011 Du 15/09 au 28/09/2011 | 15 | 9 | 0 | 9 | 0 | 0 | 9.000 | - | 9000 | Mission du Parquet : 2 Mission de la Greffe : 1 Moniteur PNUD :1 |
| 3 | Tribunal Militaire de Garnison de l’Ituri | Opasse | 2011 Du 18/04au 26/04 2011 | 8 | 6 | 0 | 4 | 2 | 0 | 8.000 | - | 8.000 | Mission du Parquet : 2 Mission de la Greffe : 1 Moniteur PNUD :1 |
| 4 | Tribunal Militaire de Garnison de Bunia | Komanda | 2012 du 28/08 au 08/09/2012 | 12 | 8 | 8 | 13 | 1 | 2 | 7.968 | BCNUDH4.071 ASF* | 11.985 | Mission du Parquet : 2 Mission de la Greffe : 1 Moniteur PNUD :2 |
| 5 | Tribunal Militaire de Garnison de Bunia | Mambasa | 2012 Du 15/11 au 28 /11 2012 | 10 | 2 | 6 | 5 | 1 | 2 | 24.909 | - | 24.909 | Dossiers crimes int.naux. : 2 Mission du Parquet : 2 Mission de la Greffe : 1 Moniteur PNUD :2 |
| Total pour le district de l’Ituri |  |  |  | 60 | 38 | 19 | 49 | 4 | 9 | 59.877 |  | 63.894 |  |
| → Province du SUD KIVU |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Cour Militaire du Sud Kivu | Cité d’Uvira | 2011 Du 1/11 au 10/11 011 | 10 | 7 | 0 | 7 | 0 | 0 | 7.820 | n/d | n/d | Dossiers crimes int.naux. : 1 Mission du Parquet : n/d Mission de la Greffe : 1 Moniteur PNUD :0 |
| 2 | Cour Militaire du Sud Kivu | Ihusi) | 2011 Du 24/10 au 29/10 2011 | 15 | 3 | 1 | 4 | 0 | 0 | 7.910 | n/d | n/d | Dossiers crimes int.naux. : 1 Mission du Parquet : n/d Mission de la Greffe : 1 Moniteur PNUD :1 partiellement |
| 3 | Tribunal Militaire de Garnison de Bukavu | Ihusi | 2011 Du 08/08 au 16/08 2011 | 9 | 3 | 5 | 5 | 0 | 2 | 12.322 | n/d | n/d | Dossiers crimes int.naux. : 1 Mission du Parquet : n/d Mission de la Greffe : 1 Moniteur PNUD :1 partiellement |
| 4 | Tribunal Militaire de Garnison de Bukavu | Walungu centre | 2011 Du 13/03 au 26/03 2011 | 14 | 15 | 2 | 13 | 2 | 2 | 5.142 | n/d | n/d | Mission du Parquet : n/d Mission de la Greffe : 1 Moniteur PNUD :1 partiellement |
| 5 | Cour Militaire du Sud Kivu | Ihusi | 2011 Du 28/02 au 9/03 2011 | 10 | 3 | 3 | 3 | 0 | 0 | 13.824 | n/d | n/d | Dossiers crimes int.naux. : 1 Mission du Parquet : n/d Mission de la Greffe : 1 Moniteur PNUD :1 partiellement |
| 6 | Cour Militaire du Sud Kivu | Baraka | 2011 Du 10/02 au 21/02 2011 | 11 | 1 |  | 10 | 1 | 0 | 8.509 | n/d | n/d | Dossiers crimes int.naux. : 1 (Fizi trial) ; Moniteur PNUD :0 Mission Parquet/Greffe : N/d |
| 7 | Tribunal Militaire de Garnison de Bukavu | Walungu centre | 2012 Du 08/10 au 15/10 2012 | 8 | 4 |  | 4 | 0 | 0 | 7.008 | ABA : 3.000 ASF : 4.174 | 14.182* | Dossiers crimes int.naux. : 4 Mission du Parquet : 1 Mission de la Greffe : 1 Moniteur PNUD :1 |
| 8 | Cour d’Appel du Sud Kivu | Kamituga | 2012 Du 23/04 au 06/05 2012 | 15 | 11 | 18 | 19 | 3 | 7 | 5.296 | DPK : 4.681 ABA : 9.626 | 19.603 | Mission du Parquet : 1 Mission Greffe : 1 + 1 Huissier Moniteur PNUD :0 |
|  | TOTAL |  |  | 92 | 46 | 29 | 65 | 6 | 11 | 62.540 |  | n/d | n/d |
| → Province du NORD KIVU |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1 | Tribunal de Grande Instance de Goma | Rutshuru | 2011 Du 03/02 au 17/02/2011 | 15 | 22 | 6 | 17 | 7 | 0 | 10.000 | ABA 5.000 | 15.000 | Mission du Parquet : 2 Mission de la Greffe : 1 Moniteur PNUD 0 |
| 2 | Tribunal Militaire de Garnison de Goma | Rutshuru | 2011 10/02 au 17/02/2011 | 8 | 4 | 9 | 11 | 3 | 0 | 8.000 | ABA 4.000 | 12.000 | Mission du Parquet : 2 Mission de la Greffe : 1 Moniteur PNUD 0 |
| 3 | Cour militaire du Nord-Kivu | Butembo | 2012 Du 04/06 au 26/062012 | 23 | 18 | 15 | 14 | 4 | 0 | 15.000 | ABA 10.000 | 25.000 | Mission du Parquet : 4 Mission de la Greffe : 1 Moniteur PNUD : 1 |
| Total pour la Province du Nord Kivu |  |  |  | 46 | 44 | 30 | 42 | 14 | 0 | 33.000 | 19.000 | 52.000 |  |
| Grand total |  |  |  |  |  |  |  |  |  |  |  |  |  |

* indemnités avocats-consultants

“Helping to combat impunity for sexual crimes in DRC: An evaluation of the mobile gender justice courts”, Open Society Initiative for Southern Africa, 2012; « Une justice équitable en RDC : Les audiences foraines une expérience pilote réussie », Avocats sans Frontières, 2006 ; « Mobile courts in the DRC : lessons from development for international criminal justice », Tessa Khan and Jim Wormington, ABA-ROLI, 2011.

Sierra Leone and CAR

“Strengthening the rule of law in crisis affected and fragile situations”, annual report 2011.

“Improving Access to Justice Programme” 2010-2011

Supra § 1.1.

Supra, § 1.4.

Annex 5

“Handbook on Planning, Monitoring and Evaluating for Development Results”, UNDP, 2009

See Annex 6

Submitted to BCPR on 18/12/2012

Local Court Act, 2011

See for example the World Bank report: “Sierra Leone: legal and judicial sector assessment”, 2004

The  2007 Gender Acts consist of the following:  the Domestic Violence Act, the Devolution of Estates Act, Registration of Customary Marriage and Divorce Act

Universal Periodic Review - Sierra Leone (Compilation of UN information), par. 73,  2011

Varvaloucas, Koroma, Turay and Siddiqi “Improving the justice sector: law and institution building in Sierra Leone”, 2012

Global Development Report 2011 http://hdr.undp.org/en/reports/global/hdr2011

Justice Sector Reform Strategy and Investment Plan II 2011-14

Figures obtained from Government’s draft Agenda for Prosperity

2011 Annual Report of the Human Rights Commission of Sierra Leone

“Handbook on Planning, Monitoring and Evaluating for Development Results”, UNDP, 2009 p. 168

Interview with Consultant Master and Registrar, 31/01/2013

Article 6.1.b. of the 1981 amendment to the Courts Act

For a more detailed analysis of the issues related to the Justices of Peace see § 3.3

See Annex 4.

The Consultant Master and Registrar confirmed that the salary of a magistrate is not commensurate to his role and clarified that the current basic salary is around 400 USD plus a top-up of 450 USD per month. The salary of a High Court judge is around 4.800 USD plus the top-up per month.

On this point see: Betty Alimamy Sesay, “Filling the Gaps in the Justice Sector: More Resident Magistrates Needed in Sierra Leone”, CARL, 2011

UNDP’s support in the past years has already brought about significant improvements in the conditions of service for judicial staff: to be noted the constant capacity building activities and the payment of top-ups for judicial staff salaries; in addition UNDP’s support on mobile courts and SGBV courts should also be seen as increasing the attraction of working as a Judge or Magistrate.

The issue is further explored in § 2.3 under the section “pre-trial detention”.

UPR, supra n. 6

Clare Castillejo, “Strengthening women’s citizenship in the context of state-building: the experience of Sierra Leone”, Friede 2008

Supra, n. 5

The UNDP project manager confirmed that UNDP plans to continue to support the Southern province and not the Eastern one, as indicated (probably by mistake) in the AWP.

PNUD, « Monitoring judiciaire 2010-2011. Rapport sur les données relatives à la réponse judiciaire aux cas de violences sexuelles à l’Est de la République démocratique du Congo », 2010

Avocats sans Frontières, «Etude de jurisprudence : l’application du statut de Rome de la cour pénale internationale par les juridictions de la république démocratique du Congo », 2009

Auditor General report, 2013. Available on http://www.auditservice.gov.sl/reports-ag-annual-report-2011.html

To be noted that the DFID supported “fast track commercial courts” have developed a software for case management.

Braima Koroma “A cost benefit analysis of itinerant courts in the Moyamba district”, p. 15, 2008

UNIPSIL/OHCHR, “The situation of detention in Sierra Leone”, 2012

UPR, supra n.6, p 40

CARL, supra n. 8

In 2009 a Bail Policy for the Judiciary of Sierra Leone was issued in order to clarify the application of section 79 of the CPA on bail. However, as illustrated by an article published on the OSIWA web site, “it is not widely quoted by practitioners and has in some cases been severely lampooned”. Infra, note n.29.

On this point see “Bail in Sierra Leone’s Courts: through the lens of the GAVI trials”, OSIWA, 2013

For a best practice in using mobile courts to address pre-trial detentions, see the “court camps in prison” experience in Malawi: “The Paralegals draw up lists of those on remand that have overstayed, are held unlawfully or have been granted bail but cannot afford the terms set by the court. They discuss the lists in advance with the prosecuting authorities. Magistrates attend court with the court clerk, police prosecutor and work through the list: they grant bail to some, reduce the amount set by an earlier court by way of bond or surety for bail and dismiss cases where the accused has overstayed, or set a date when the accused must appear for trial. The camp court is not a trial court, since the public cannot attend and witnesses are not produced.” Open society Justice Initiative, “Improving pre-trial justice in Malawi”.

According to a report by Friede “The Sierra Leone Bar Association reported that in 2009 there were about 100 lawyers in private practice, but only seven outside Freetown – four in the southern province, two in the eastern province and one in the Northern Province”. Clare Castillejo, “Building Accountable Justice in Sierra Leone”, Friede 2009

A report by Resolve Group specifies that “the average amount, which the State can pay Barristers, in private practice, to represent accused in capital cases, is 500,000 Leones (roughly USD$150) per case. In view of the above, most barristers in private practice decline requests to represent persons charged with capital offences”. Resolve Group “ The feasibility of a legal aid system in Sierra Leone”, 2007

Supra, n. 7.

In addition it’s worth noting that, as stated in a recent UNDP-OSI study, defendants held in pre-trial detention are more likely to be convicted than those who got bail for the same offences. UNDP and Open Society Justice Initiative in “The socio-economic impact of pre-trial detention” 2010

In September 2011, Sierra Leone established an official moratorium on the use of the death penalty.

Resolve Group, supra n. 21

Commonwealth Human rights Initiative, “In pursuit of justice: a report on the Judiciary in Sierra leone”,2002

## The Consultant Master and Registrar explained that interpreters are available in Freetown (and have even received training from Special Court) although not enough and not always in the relevant language. For further information on the issue of interpretation see: Sheku Koroma and John Shangai Koroma “Addressing the Issue of Interpretation in District Magistrate Court in Sierra Leone”, CARL, 2006

The following abstract of an online post on Thinkafricapress gives a clear example of the issue:  “There is a scene, described in a justice report, which takes place in a Sierra Leonean courtroom: a young male villager sits in front of a magistrate charged with committing a sexual offence against a sixteen-year-old girl. The charge of ‘unlawful carnal knowledge’ (an illegal sexual act, in judicial terms) is translated to him from English, the official language, into Krio, the national language. The boy, standing and listening to the English ‘legalese’, is asked whether he would like to ‘modify his statement’, ‘call witnesses to present to the High Court’ or ‘speak on his own behalf’. The boy, the report concludes, seems to have no idea what is going on”.

Avocats sans Frontières, « Une justice équitable en RDC : Les audiences foraine, une expérience pilote réussie »,  2006

Article 30 (2) states that “The Board shall accredit (…) paralegals only in the case (they) have been certified as having gone through the appropriate courses at the Judicial and Legal Training Institute or any other appropriate institution approved by the Board”.

“Eliminating the requirement that a felonious case be referred to High Court before first going through a preliminary investigation (PI) in a magistrates’ court would also help unclog the courts. Revisions to the Criminal Procedures Act of 1965, including legislation dropping ‘preliminary investigations’ and ensuring a case’s committal to High Court within seven weeks, are also expected to pass in the next few months”. Supra n. 7.

Varvaloucas & Koroma, Supra n. 7, page 505

This was however not the case in Moyamba as it was widely recognized, included by court monitors, that the magistrate was always on time in court.

To be noted that article 8.3 of the Courts Act that, establishes that :“whenever a witness is required by summons to give evidence  the magistrate shall direct that he be paid reasonable sum for his travelling expanses”.

Witnesses are reimbursed, after they have testified, on the basis of the covered distances for a maximum amount to 30.000 Leones.

UNDP, court monitors reports, 3rd quarter 2012

Supra n. 5

Caroline Roseveare “Sierra Leone access to justice for survivors of sexual and domestic violence” p 18, IRC/Timap,  2012

The Saturday court annual report indicates that “between February 2012 and July 2012 the Saturday court received 56 cases of domestic violence, out of which 22 were disposed of”.

This issue is illustrated as follows in a recent report: “I worked in the provinces as a magistrate for some years, and I was never provided with a vehicle to travel between courts and to and from home. It is inevitable that you rely on the generosity of others to do your job. And one day you see before you in court the man who gave you a lift a week before”. Centre for the Study of African Economies, Oxford University “Timap Criminal Justice Pilot: Baseline Evaluation Report”, 2010

To be noted that the official government allowances for staff on mission are lower than the ones paid by UNDP: according to the Master and Registrar the government pays a daily rate of 450.000 Leones for judges and 250.000 for support staff.

In 2011 the Anti Corruption Commission publishd a “National Public Perception of Corruption Survey Report” which reveals that Sierra Leoneans perceive  that corruption is more prevalent in the Sierra Leone Police (SLP) force than any other state institution.

The Family Support Units (FSU’s) are specialist units attached to about 40 police stations across Sierra Leone with a mandate for the investigation of all forms of child abuse and violence against women (sexual abuse and violence, physical abuse, exploitation, commercial exploitation, including internal and cross border trafficking).

Supra n. 41.

To be noted that the customary law officer is also recognized jurisdiction to review the Local Court’s decisions.

Braima Koroma, supra n. 15

“Positive complementarity refers to all activities whereby national jurisdictions are strengthened and enabled to conduct genuine national investigations and trials of crimes included in the Rome Statute” in UNDP «Discussion paper: Complementarity and Transitional Justice: Synthesis of Key Emerging Issues for Development”, 2012

Supra n. 6, p. 42

Sigall Horovits “Sierra Leone: interaction between national and international responses to the mass atrocities”, 2009

See Annex 5

Submitted to BCPR on 18/12/2012

UNDP Annual report, 2010

UNDP Somalia, Governance and rule of law programme document (2012-2015)

Adapted from “Draft Somaliland National Development Plan (NDP) 2012 – 2016”, October 2011

See for example Hussein Mohamed Farah, “Baseline assessment of the Somaliland Judiciary”,  October 2009

“The Criminal Procedure Code recognizes the application of customary law, and authorizes the prosecution to withdraw the criminal charge at any stage of the trial process if the victim and the accused agree so and opt for an out of  court settlement. (…) In 2007, 27 criminal murder cases were filed in Erigavo Regional Court, and out of this number, the Court gave judgment in only 2 cases through the application of statutory laws whereas it solved 22 cases through customary law” in Hussein Mohamed Farah, supra n. 6

“Islamic Law imposes the death penalty for rape if the perpetrator is married (for an unmarried accused, the punishment is 90 lashes). The statutory law, in contrast, carries a punishment of imprisonment” Alejandro Bendaña and Tanja Chopra in “Women's Rights, State Centric Rule of Law, and Legal Pluralism in Somaliland” Hague Journal on the Rule of Law / Volume 5 / Issue 01 / March 2013, pp 44-73

University of Hargeisa with support from UNDP, “Strengthening the Quality and Scope of Justice Provision and Policing in Somaliland. A Baseline Study” July 2012

Some of the interviewed persons recalled the so-called “Mobile Military Court” (Maxkamada Wareegta) that was active in Hargeisa during the Siad Barre regime and was travelling on circuit to prosecute cases related to national security. On this point see: Africa Watch, “Somalia: a government at war with its own people”, 1990

Law No. 24, 2003

Law No. 24, 2003 (unofficial translation)

Loi organique n.13/011-B du 13 Avril 2013 portant « organisation fonctionnement et compétences des juridictions de l’ordre judiciaire ». (articles 45-48), Journal Officiel de la RDC, 4/05/2013

5 judges and 1 prosecutor have been killed in this area since 2010

Report of the 2nd Mobile Courts review workshop, 14th to 18th July 2012, Burao, Somaliland

For example “At least 20 persons received legal advice from the Court” (Boon report)

Internal note on MC, 2012.

Dr Shamsul Bari, UN Independent Expert concluded that “Minorities who lack the protection of the major clans are likely to be victims of the discrepancies between customary, criminal and sharia law”, 2010 report on the situation of human rights in Somalia

Minority Rights Group “No redress: Somalia’s forgotten minorities”, Martin Hill, 2010

Training Workshop report “ improvement of Mobile Court Services and Court Case Management system” 30th Sept. to 3rd Oct. 2012, Borama, Somaliland

Agency for Technical Cooperation and Development, January 2013

Baseline Study, supra note 9

Bendaña and Chopra, supra note 8

Currently over 60 women legal professionals are working with SWLA and SOLLA, which is a remarkable achievement, considered that they were only 5 in 2008.

Bendaña and Chopra, supra note 8

“The mobile court in these cases would fundamentally be called upon to address issues of individual impunity for serious crimes including SGBV, and if appropriate, act as a gender mobile court with the corresponding expertise”. UNDP Somalia, Governance and rule of law programme document (2012-2015)

One of the Hargeisa based Prosecutors reported that “the 6 female prosecutors work mainly in Hargeisa as they are not yet accepted in rural areas”

67 minors were parties to the MC cases in 2011

On this point “The Independent Expert conveyed his dismay to the Minister for Justice that, despite his earlier calls, both young girls and boys were still being put in jail for disobedience to their parents”, Report of the Independent Expert on the situation of human rights in Somalia, Shamsul Bari, 22 August 2012.

Somaliland Mobile Courts: procedural guidelines for implementation, UNDP and Judiciary

Report of the 2nd Mobile Courts review workshop, 14th to 18th July 2012, Burao, Somaliland

2nd Mobile Courts review workshop, supra note 15

UNDP Somalia, Governance and rule of law programme document (2012-2015)

For a best practice in using mobile courts to address pre-trial detentions, see the “court camps in prison” experience in Malawi implemented by PASI: “The Paralegals draw up lists of those on remand that have overstayed, are held unlawfully or have been granted bail but cannot afford the terms set by the court. They discuss the lists in advance with the prosecuting authorities. Magistrates attend court with the court clerk, police prosecutor and work through the list: they grant bail to some, reduce the amount set by an earlier court by way of bond or surety for bail and dismiss cases where the accused has overstayed, or set a date when the accused must appear for trial. The camp court is not a trial court, since the public cannot attend and witnesses are not produced.” Open society Justice Initiative, “Improving pre-trial justice in Malawi”.

2nd Mobile Courts review workshop, supra note 15

In line with this approach, the current ROL project recommends “instituting a more proactive and regular circuit for district courts to reach villages” and that “The programme will also expand support to focus on district courts rather than regional and appeals courts”

Sool is the only Region where UNDP is currently not supporting MC; the main reason being that the unstable security situation does not allow UNDP staff to visit the area to monitor the activities.

This was also one of the recommendations presented at one of the MC workshops “The Reports should have a column indicating if a lawyer was present or not so we can raise with lawyer associations if they fail to abide by the terms and conditions of the MCG”, in Report: training Workshop on the improvement of Mobile Court Services and Court Case Management system 30th Sept. to 3rd Oct. 2012, Borama, Somaliland

Further information on this methodology is available on : http://www.kobotoolbox.org/about/take-tour. Methodologies that use mobile phones are also available (e.g Frontline SMS or Texttochange)

Avocats sans Frontières, « Une justice équitable en RDC : Les audiences foraines une expérience pilote réussie », 2006. See also : Global Rights, « Le Monitoring du Système Judiciaire Un manuel pratique à l’usage des moniteurs de la société civile congolaise », 2008

See the report by Geneva International Centre for Humanitarian Demining in “Danish Demining Group Community Safety Programme. Somaliland case study”, September 2012

MC monitoring report in Gabiley, Somaliland

HRW reports that “members of displaced communities in Mogadishu faced serious human rights abuses including rape, beatings, ethnic discrimination, restricted access to food and shelter, restrictions on movement, and reprisals when they dared to protest their mistreatment. The most serious abuses were committed by various militias and security forces, often affiliated with the government, operating within or near camps and settlements for the displaced. Frequently these militias were linked or controlled by managers, or “gatekeepers” as they are known, of the IDP camp”. Human Rights Watch, in “Hostages of the gatekeepers. Abuses against Internally Displaced in Mogadishu, Somalia”, 2013

Somaliland Judicial reform work plan (2011-2015)

The percentage raises to 55% if the 71 MC organised by the Supreme Courts are included.

“Hussein Mohamed Farah, supra note 6

Academy for Peace and Development “The Judicial System in Somaliland” Akaademiga Nabadda Horumarka 2002

Article 7 of the Criminal Procedure Code, requires Courts to appoint a defence counsel for persons accused of a crime punishable with a prison sentence exceeding 10 years.

MC monitoring report in Gabiley, Somaliland

Report of the 1st Mobile Courts review workshop, 10th to 14th September 2011, Hargeisa, Somaliland

Mobile Court review workshop, supra note 15

Mobile court review workshop report, Puntland, 2013

See for example Open Society Justice Initiative in “Community-Based Paralegals: A Practitioner’s Guide”, 2010

“Strengthening governance and rule of law in Somalia, 2012-2015” UNDP

One of challenges identified in the 2nd MC review workshop was that “Legal aid lawyers do not have offices or paralegals in the districts and villages, so they do not have enough information about the victims”.

See the Timap for Justice web site:  http://www.timapforjustice.org/

For example the MC travels to hear a land dispute, but upon arrival discover that one of the parties to the case was kidnapped, so the Judges have to first settle this issue.

Baseline Study, supra note 6. An assessment of the Justice sector conducted in 2009 found that the absence of a court exemption mechanism “paved the way for manipulation and misuse on the part of the courts. As complained by the public it becomes something common that courts exempt court fees from rich individuals who can afford to pay tit while it happened that eligible and poor individuals are refused to exempt court fee, and hence denied their right to access to justice”.

UNDP Somalia report, Observation on the mobile court visit in Gabiley, June 2012.

UNDP, Monitoring report for the mobile court visit in Gabiley, May 2013

See http://somsattv.com

LoA 2012-2013 indicates “monthly fuel support to the mobile services of regional mobile courts as well as that of the supreme court for 12 moths (lump sum of 5.500 per month)”

Such forms were introduced in October 2012, during the MC training workshop, supra note 15

Mobile court review workshop, supra note 15

In 2006 a National Elders Declaration was drafted with UNDP’s assistance to promote a better coordination between the formal and informal system; elders engaged to refer serious crimes to the formal courts including rape and murder.

Interview with the MC judges in Hargeisa, 07/05/2013

MC monitoring report in Nugal, Puntland

Mobile court review workshop, supra note 15

Mobile court review workshop, supra note 51

Baseline Study, supra note 6

The report of the Independent Expert on Human Rights in Somalia denounces that “Unknown assailants shot and killed the Attorney General of the Sool region under Somaliland administration, making him the second judge to be killed in northern Somalia in less than a month. Unknown gunmen armed with pistols opened fire on the judge as he was watching a football match at a location in Las caanood, the capital of the Sool region”

Puntland workshop, supra note 53.

UNDP monitoring report NAGAL, Puntland

Director of the prison of Gabiley referred that “before the MC, 3 years ago, there were many appeals but nobody came”

Mobile court review workshop, supra note 51

UNDP promotes an integrated approach to transitional justice, which focuses on developing the capacities of national institutions to investigate and prosecute international crimes in complementarity with the ICC. “Positive complementarity refers to all activities whereby national jurisdictions are strengthened and enabled to conduct genuine national investigations and trials of crimes included in the Rome Statute” in UNDP «Discussion paper: Complementarity and Transitional Justice: Synthesis of Key Emerging Issues for Development”, 2012

For example the Ugandan International Crime Division is mandated to hear cases of “terrorism, human trafficking, piracy” in addition to the Rome statute crimes. Human Rights Watch, “Justice for serious crimes: Uganda’s international crimes division”, 2012

Interview with MC judges in Hargeisa

Sool is a disputed region between Somaliland and Puntland: the security situation is fragile and very limited justice and security institutions are available compared to the rest of country (see map in Annex 4), so it is considered to be the region where most international crimes occur.

One appeal case involved a group of Al Shabab suspects sentenced to death in first instance for killing 2 police officers and a 14 years old girl because they believe the latter had discovered information about Al Shabab operations.

Human Rights Watch, “London conference on Somalia -  briefing paper”, May 2013

Dans le cadre de la présente évaluation les audiences foraines sont définies comme « des audiences judiciaires tenues par un Tribunal dans son ressort géographique mais en dehors de son siège ordinaire, normalement dans des localités éloignées où les services de justice ne sont pas disponibles».

Voire la liste des documents consultés (Annexe 1)

Voir la liste des personnes rencontrées (Annexe 2)

Pour une description du mandat des ces structures voir la note n. 41.

Voir par exemple les “Letter of Agreement between UNDP and the Judiciary of Sierra Leone regarding itinerant courts”, 2010 and 2012.

Pour une description des activités préliminaires voir § 5.1

Voir par exemple : Amnesty International, « The time for justice is now: New strategy needed in the Democratic Republic of the Congo”, 2011

Pour des cartes avec la répartition géographique des juridictions dans l’est de la RDC, voir le rapport PNUD « Monitoring Judiciaire 2010-2011, infra n.13.

Dans l’est de la RDC le Tribunal pour Enfants est opérationnel à Goma et à Bunia

Titre II  de la loi N° 024/2002 du 18 novembre 2002 portant code pénal militaire congolais

Article 91 de la loi organique n.13/011-B du 13 Avril 2013 portant «organisation fonctionnement et compétences des juridictions de l’ordre judiciaire »

ORDONNANCE-LOI 82-020 portant « Code de l'organisation et de la compétence judiciaires ».

PNUD, « Monitoring judiciaire 2010-2011. Rapport sur les données relatives à la réponse judiciaire aux cas de violences sexuelles à l’Est de la République démocratique du Congo », 2010

Art 86, ORDONNANCE-LOI 82-020 portant « Code de l'organisation et de la compétence judiciaires ».

Art 170 (viol), Code pénal congolais, modifié par la Loi no 06/018 du 20 juillet 2006

Art 91, ORDONNANCE-LOI 82-020 portant « Code de l'organisation et de la compétence judiciaires »

Art 92, ORDONNANCE-LOI 82-020 portant « Code de l'organisation et de la compétence judiciaires »

Art 68, ORDONNANCE-LOI 82-020 portant « Code de l'organisation et de la compétence judiciaires »

Art 94, ORDONNANCE-LOI 82-020 portant « Code de l'organisation et de la compétence judiciaires »

Art 36, ORDONNANCE-LOI 82-020 portant « Code de l'organisation et de la compétence judiciaires ».

Section 4 (Du pouvoir judiciaire) de la Constitution de la RDC, modifiée par Loi no 11/002 du 20 janvier 2011.

Loi 023/2002 du 18 novembre 2002 portant « code judiciaire militaire ».

Article 23,  Loi 023/2002 du 18 novembre 2002 portant « code judiciaire militaire ».

Article 90, Loi 023/2002 du 18 novembre 2002 portant « code judiciaire militaire »

Article 122, Loi 023/2002 du 18 novembre 2002 portant « code judiciaire militaire »

Article 21, Loi 023/2002 du 18 novembre 2002 portant « code judiciaire militaire ».

Article 88, Loi 023/2002 du 18 novembre 2002 portant « code judiciaire militaire ».

Article 122, Loi 023/2002 du 18 novembre 2002 portant « code judiciaire militaire »

Article 12, Loi 023/2002 du 18 novembre 2002 portant « code judiciaire militaire ».

Article 84, Loi 023/2002 du 18 novembre 2002 portant « code judiciaire militaire »

Articles 18 et 87, Loi 023/2002 du 18 novembre 2002 portant « code judiciaire militaire »

Articles 6 et 7, Loi 023/2002 du 18 novembre 2002 portant « code judiciaire militaire »

Pour un cadre complet des statistiques des AF voir le tableau au § 6.2

Arrêté d’Organisation Judiciaire 299/79 portant règlement intérieur des cours, tribunaux et parquets.

Voir le Chapitre III de la Loi 023/2002 du 18 novembre 2002 portant « code judiciaire militaire ». Par exemple pour la CM l’Article 13 établit que « La Cour Militaire peut se réunir en tous lieux de son ressort ».

Loi n.13/011-B du 13 Avril 2013 portant « organisation fonctionnement et compétences des juridictions de l’ordre judiciaire ». Les articles suivants traitent de la justice itinérante : «  Article 45 : s’ils l’estiment nécessaire pour la bonne administration de la justice, les courts et les tribunaux peuvent siéger dans toutes les localités de leur ressort ». Article 46 : le Ministre ayant la justice dans ses attributions peut établir pour toutes les juridictions des sièges secondaires dans la même localité ou les localités de leur ressort autres que celles ou sont établis leur sièges ordinaires (..) Article 47 : l’itinérance ne peut empêcher le fonctionnement de la juridiction au siège ordinaire »

Le PNUD appuie les AF depuis 2010 ; ASF depuis 2004.

ASF prends en charge aussi les dossiers civils. Le bureau PNUD en Ituri a organisé du 16 au 29 septembre 2011 une AF avec le TGI de Bunia où 26 dossiers civils en appel ont été traités.

Sur ce point voir le § 6.4

« Les critères suivants déterminent le choix du lieu où l’audience foraine devra se tenir : 1) la prévalence des cas des violences sexuelles; 2) les facilités d’accès à différentes preuves notamment les certificats médicaux et les témoignages ; 3) la disponibilité des locaux ayant une capacité d’accueil acceptable des auteurs présumés;  4) la disponibilité des infrastructures devant abriter l’audience dans la mesure du possible ; 5) la sécurité sur le lieu ». Termes de référence des AF pour le projet PNUD 1888.

Ces fora sont actifs dans les 3 zones d’intervention du projet PNUD, et sont nommés respectivement « cadre de concertation justice militaire» au Nord kivu, « comite d’appui aux audiences foraines » en Ituri et « task force justice » au sud Kivu. Au Nord Kivu les AF civiles sont discutées dans le cadre du « Groupe de travail lutte contre l’impunité ».

Un seul magistrat pour les dossiers civils.

Au Sud Kivu le PNUD envoie une voiture ou rembourse les frais de transport.

Le PNUD appuie la majorité des AF dans le cadre du projet « Strengthening Investigation and Prosecution Capacity  of the Military Justice System on Sexual Violence in eastern DRC ».

Les CAP sont établies par la résolution du Conseil de Sécurité 1925 (2010).

Titre II  de la loi N° 024/2002 du 18 novembre 2002 portant code pénal militaire congolais.

Voir par exemple « La justice militaire et le respect des droits de l’homme – L’urgence du parachèvement de la réforme », AfriMAP et Open Society Initiative for Southern Africa, 2009

Les Directives et principes sur le droit à un procès équitable et à l’assistance judiciaire en Afrique prévoient que « les tribunaux militaires ne peuvent, en aucune circonstance, juger des civils ».

Article 156 de la Constitution: “Les juridictions militaires connaissent des infractions commises par les membres des Forces armées et de la Police nationale ».

Par exemple le rapport de l’AF du TMG á Komanda signale: « Un prévenu a été renvoyé devant son juge naturel:  le Tribunal a décliné sa compétence par un jugement avant dire droit, le prévenu n’étant  pas militaire ni policier ».

Article 161 du code judiciaire militaire: « En cas d’indivisibilité ou de connexité d’infractions avec des crimes de génocide, des crimes de guerre ou des crimes contre l’humanité, les juridictions militaires sont seules compétentes ».

Article 91, Loi n.13/011-B du 13 Avril 2013 portant « organisation fonctionnement et compétences des juridictions de l’ordre judiciaire »

La proposition de loi a été déposée au Parlement en Mars 2008 et examinée en Commission en Juin 2011, mais elle n’a pas atteint le stade de la discussion en plénière. En Novembre 2012 la proposition a été reproposée et est actuellement en examen devant la commission parlementaire compétente pour les affaires judiciaires.

Pour un aperçu des 3 projets de loi qui ont été soumis au Parlement depuis 2003 pour la réception du Statut de Rome en droit congolais voir : Joseph Kazadi Mpiana, «  La cour Pénale Internationale et la République Démocratique du Congo : 10 ans après. Etude de l’impact du Statut de Rome dans le droit interne congolais » in Revue Québécoise de droit international, volume 25.1/2012

Joseph Kazadi Mpiana, supra n. 53

Voire supra, n. 45

Un rapport de Freedom House souligne: “Military judges can be influenced by their military hierarchies, especially when the accused are high-ranking military officers, as Congolese law stipulates that officers can only be judged by their superiors. In several cases the government has interfered in prosecutions, as in January 2009, when the minister of justice wrote to bar military prosecutors from investigating abuses committed by CNDP soldiers”. Freedom House, “Countries at the crossroad, DRC report”, 2012

RCN Justice & Démocratie “La justice de proximité au Bas-Congo”, 2009

Voir par exemple “Fact Sheet: Democratic Republic of Congo Mobile Gender Courts”, open Society justice Initiative, July 2011

Sur ce point voir Wageningen University, « Fond de commerce? Sexual violence assistance in the Democratic Republic of Congo”, 2012

Le Plan d’action est disponible sur : http://www.justice.gov.cd/files/systeme_judiciaire_rdc.html

Rapport de monitoring judiciaire de l’AF du TMG de Bukavu á Kalehe (Sud Kivu, 2011)

Cette approche a été adoptée par la Court d’Appel de Bukavu pour l’AF auprès du siège secondaire du TGI d’Uvira à Kamituga. La chambre foraine a jugé les affaires en appel et a aussi procédé à inspecter la juridiction inferieure.

Un rapport de ABA conclut que  “it is these violent crimes – by intimates and civilians – that predominate today, as the portrait of the rapist no longer requires that he be wearing a military uniform”. In Open Society Initiative for Southern Africa, Helping to combat impunity for sexual crimes in DRC: An evaluation of the mobile gender justice courts”, 2012

“The analysis also demonstrated a civilian adoption of rape. From 2004 to 2008, the number of civilian rapes increased by an astounding 1733% or 17-fold, while the number of rapes by armed combatants decreased by 77%. These findings imply a normalization of rape among the civilian population”, OXFAM America and Harvard Humanitarian Initiative, “’Now, the world is without me: an investigation of Sexual Violence in Eastern DRC”,2010.

Wageningen University, supra n. 59.

Wageningen University, supra n. 59.

Le documentaire “Justice for sale” illustre les faiblesses du système judiciaire en suivant le cas d’un militaire injustement condamné pour viol au cours d’une audience foraine au Sud Kivu.  “Justice for sale” by Ilse and Femke van Velzen, IFPRODUCTIONS, 2011. Disponible sur http://ifproductions.nl/justiceforsale.nl/

L’analyse de 30 jugements pour des dossiers de viol menée par Wageninen University auprès des juridictions du Nord et Sud Kivu conclu que: « None of the 19 conviction files contained the legally required medical report as evidence. Only one file made mention of the presence of physical proof. The legal examination of the cases resulted in the conclusion that 50% of the convictions lacked sufficient evidence. The cases concluded in acquittal are well argued, possibly out of fear on the side of judges to be criticised by public opinion. The convictions (19 out of 30 cases) all concern lower-class suspects and are much less motivated. Wageningen University, supra n. 59

Un diagnostic des besoins de justice mené en 2008 par l’Université de Berkely identifie les crimes récurrents dans l’Est de la RDC comme suit : disparitions de personnes (60%), travaux forcées ou esclavage (53%), assassinats (61%); violences sexuelles (16%).

PNUD, supra n. 13.

Cela n’a toutefois pas affecté les résultats du projet vu qu’ils étaient centrés sur la lutte aux VBG.

Pour plus de détails sur les fora de coordination des AF voir le § 5.1

Par exemple au Sierra Leone et en Somalie les juridictions envoient régulièrement des rapports de suivi des AF au PNUD avec des statistiques et un narratif.

Un modèle de référence pourrait être le Protocole d’entente rédigé par le PNUD en Sierra Leone.

« Renforcement de la capacité du système judiciaire militaire d’enquêter et de poursuivre les crimes des violences sexuelles dans l’est de la RDC »

« Renforcement de l'accès des femmes à la justice : sécurisation et autonomisation des populations dans les Kivus et en Ituri »

Rapport de monitoring judiciaire de l’AF du TMG de Bukavu á Kalehe (Sud Kivu, 2011)

Une bonne pratique dans une approche de legal empowerment est développée par ASF avec les « observatoires des procès issus des relais communautaires ». Avocats sans Frontières, « Une justice équitable en RDC : Les audiences foraines une expérience pilote réussie », 2006

« Renforcement de l'accès des femmes à la justice : sécurisation et autonomisation des populations dans les Kivus et en Ituri »

Avocats sans Frontières, “Rapport d’évaluation externe des projets support aux audiences foraines et boutiques de droit dans les provinces de l’Equateur et du Maniema en République Démocratique du Congo », 2008

# Sur ce point le rapport de l’Univerisite de Wageningen conclut que « NGOs pay for lawyers on the side of victims, while suspects are usually left with unpaid, and hence unmotivated, public defenders.”, Supra n. 59.

L’état congolais paye les avocats d’office seulement pour les dossiers de meurtre.

Rapport de monitoring judiciaire de l’AF du TMG de Bukavu a Kalehe (Sud Kivu, 2011)

Réunion avec le Gouverneur du Sud Kivu et les autorités judiciaires et de police pour la formulation du projet PNUD 2013-2018, Bukvu, 25/03/2013

Par exemple le Rapport de monitoring pour l’AF du TGM de Bukavu á Walungu signale que « Les Avocats ont déclaré avoir pris connaissance des dossiers qui sont passés le premier jour d’audience que 10 minutes avant l’audience »

Rapport de monitoring judiciaire de l’AF du TMG de Bunia a Mamabasa (Ituri, 2012)

Rapport de monitoring judiciaire de l’AF du TMG de Bukavu a Walungu (Sud Kivu, 2011)

RCN, Supra n. 57.

Certains magistrats ont exprimé des réserves sur cette pratique, comme illustré par le rapport de l’AF à Bunia de la CM de Kisangani en 2013 « Le premier juge avait pris une mesure en attribuant un code à la victime comme mécanisme de protection. La cour militaire a estimé que cette mesure n’était envisageable qu’à la phase de l’instruction pré juridictionnelle. Le faire au niveau de l’instruction juridictionnelle, risquerait de poser un sérieux préjudice à la victime, lorsqu’elle devra réclamer des g qui lui ont été alloués, car elle n’est pas clairement identifiée dans la décision judiciaire ».

Un représentant du PNUD précise que les AF organisées dans les prisons pour rendre des jugements (et non seulement pour valider les détentions préventives) sont objet de débat: la sécurité n’est pas bien garantie pour les parties au procès et les acteurs judiciaires ; la publicité des débats est mise en cause  vue que le public ne fréquente pas volontiers les prisons. Par contre d’autres collègues PNUD soulignent que les AF dans les prisons offrent une solution efficace au problème du manque de transport pour transférer les détenus des prisons aux tribunaux et aux conséquents reports des procès.

En novembre 2012 au cours de l’attaque des M23 les 1.600 détenus de la prison centrale de Goma se sont évades

MONUSCO, « Rapport sur la détention dans les prisons et cachots de la RDC », 2004

MONUSCO, supra n. 91.

L’équipe de monitoring judiciaire du PNUD est entrain de mener une étude sur les causes de non recouvrement des dommages et intérêts sur 80 dossiers (au Nord et Sud Kivu et en Ituri).

ABA-ROLI, supra n. 63

Office of the UN High Commissioner for Human Rights , « Rapport du Panel à la Haut Commissaire aux Droits de l'Homme sur les moyens de recours et de réparation pour les victimes de violences sexuelles en République Démocratique du Congo », 2011. Voir aussi l’étude en cours par Physicians for Human Rights sur l’analyse réparations pour les survivantes de viol dans la jurisprudence congolaise.

Avocats sans Frontières, supra note n.  75

PNUD, supra n. 13

“Positive complementarity refers to all activities whereby national jurisdictions are strengthened and enabled to conduct genuine national investigations and trials of crimes included in the Rome Statute” in UNDP «Discussion paper: Complementarity and Transitional Justice: Synthesis of Key Emerging Issues for Development”, 2012

6 dossiers pour crimes de guerre commis dans l’est de la DRC (principalement en Ituri) ont été ouverts auprès de la CPI

Les CAP sont établies par la résolution du Conseil de Sécurité 1925 (2010)

Avocats sans Frontières, «Etude de jurisprudence : l’application du statut de Rome de la cour pénale internationale par les juridictions de la république démocratique du Congo », 2009

Un rapport de Amnesty International confirme que « Most of the trials for crimes under international law in the DRC have taken place before mobile military courts”. Amnesty International, supra n.7

Par exemple le rapport de monitoring de l’AF de Mambasa explique que: « les faits présentés par le ministère public sont constitutifs de crimes contre l’humanité conformément aux prescrits de l’article 7 du statut de Rome. C’est pour quoi, déjà au cours de l’audience introductive, les avocats que ce soit de la défense ou des parties civiles avaient demandé au tribunal de pourvoir appliquer, tout au long de cette procédure, le statut de Rome en lieu et place des codes pénales et code de justice militaire congolais ».

Le PNUD a participé á cette AF avec une contribution de 8.059 USD.

AF organisée avec l’appui du PNUD, BCNUDH, ABA, MONUSCO/CAP et ASF. Coût total : 19.773 USD.

AF organisée avec l’appui du PNUD, ASF, Monusco (CAP et SAJ). Cout total : 24.909 USD

ABA-ROLI, supra n. 63

Voir par exemple Human Rigths Watch “Justice for Serious Crimes before National Courts : Uganda’s International Crimes Division » 2012 ; ou Open Society Foundations, « Putting Complementarity into Practice: Domestic Justice for International Crimes in DRC, Uganda, and Kenya”, 2011

AfriMAP et OSJI, supra n. 47

Une proposition de loi de mise en œuvre du Statut de Rome a été déposée devant l’Assemblée nationale en mars 2008, mais elle mais n’a toujours pas fait l’objet d’examen et d’adoption. Sur ce point voir supra, n. 53

Rapport de monitoring judiciaire de l’AF du TMG de Bunia á Mamabasa (Ituri, 2012)

Avocats sans Frontières, supra n. 102

Article 91, Loi n.13/011-B du 13 Avril 2013 portant « organisation fonctionnement et compétences des juridictions de l’ordre judiciaire »

Avocats sans Frontières, supra n. 102

Cellule d’appui aux poursuites. Voir supra, n. 100

Entretien avec le Président de la CA de Bukavu, 26/03/13

Voir, supra note 53

Pour une définition des ces deux modèles voir § 5.2