Terminal Evaluation Report

“Strengthening National and Local Capacities

for Disaster Response and Risk Reduction”

Submitted to UNDP Guyana

and

Guyana Civil Defence Commission

February 22, 2014

Hans M. Ewoldsen, Ph.D., P.E.

Table of Contents

Section							          Page

Acknowledgements							3

Acronyms								4			Executive Summary							5

2.0	Introduction

2.1	Overview of the Project						9

2.2	Evaluation Purpose						13

2.3	Description of the Evaluation					13

2.4	Evaluation Methodology					15

2.5	Evaluation Beneficiaries						19

2.6	Limitations and Constraints					19

3.0	Project Components Evaluated

3.1	Project Relevance						20

3.2	Project Effectiveness						21

3.3	Project Efficiency						23

3.4	Project Benefits							28

3.5	Sustainability of Results Achieved				30

4.0	Findings Summary

4.1	Summary of Comments on Ratings				31

4.2	Summary of Ratings for Outputs/Activities			34

4.3	Conclusions							37

4.4	Lessons Learned						37

4.5	Recommendations						38

Tables

Table 1.		Disaster Categories Present in Guyana			10

Table 2.		Consultants Used on the Project				25

Table 3.		Overall Achievement of Project Objectives		29

Table 4.		Summary Table of Ratings for Outputs			31

Table 5.		Ratings Summary Comments				34

5.0	Annexes

Annex 1.	Bibliography of Documents Reviewed			41

Annex 2.	Organizations Interviewed / Interview Guide		42

Annex 3.	Mission Schedule and Agenda				43

Annex 4.	Field Trip to Region 6					45

Annex 5.	Questionnaire Guide and Evaluation Table		46

Annex 6.	Evaluation Matrix from Inception Report	      	49

Annex 9.	Ethics Statement – UNDP				58

Annex 9. 	CV of the Evaluator					59

Annex 7.	Terms of Reference for Terminal Evaluation	      	63

Acknowledgements

The completion of this Terminal Evaluation Report was materially enabled by the support, services and advice provided by the staff of UNDP Guyana, including Ms. Chisa Mikami, Deputy Resident Representative; Ms. Andrea Heath-London; and Ms. Gwenette Mars.  Equal support was provided by the management and staff of the Guyana Civil Defence Commission, including Colonel Francis Abraham, Deputy Director General; Mr. Kester Craig, Operations Officer; and Ms. Michelle John-Klass, Project Coordinator. The Civil Defence Commission kindly provided working space and logistical support in the accomplishment of the mission.

Disclaimer

Please note the analysis and recommendations of this report do not necessarily reflect the views of the United Nations Development Programme, its Executive Board or the United Nations Member States. This publication reflects the views of its author(s).

Acronyms and Abbreviations

CBO                   	Community Based Organization

CDC                  	Community Democratic Council

CDC                    	Civil Defence Commission

CDEMA               Caribbean Disaster Emergency Management Agency

CDM                  	Comprehensive Disaster Management

DANA		Damage Assessment and Needs Analysis

DER		Disaster Emergency Response

DRM                  	Disaster Risk Management

DRR                   	Disaster Risk Reduction

ENSO		El Niño Southern Oscillation

FAO                   	Food and Agricultural Organization

GDF                     Guyana Defence Force

GDP                   	Gross Domestic Product

GINA                 	Government Information Agency

GL&SC               	Guyana Lands & Surveys Commission

GoG                   	Government of Guyana

GRCS		Guyana Red Cross Society

HFA                     Hyogo Framework of Action

IC                       	International Consultant

IDB                   	Inter-American Development Bank

IDRM                	Integrated Disaster Risk Management

MoA                  	Ministry of Agriculture

MoH                 	Ministry of Health

MoH&W          	Ministry of Housing and Water

MSL	             	Mean Sea Level

NDC                   	Neighbourhood Democratic Council

NDIA                  	National Drainage and Irrigation Authority

NDMC 		National Disaster Management Committee

NEOC 		National Emergency Operations Centre

NGO		Non-Governmental Organization

NMHPRP	National Multi Hazard Preparedness and Response Plan

PAHO		Pan American Health Organization

RDC		Regional Democratic Council

SOPs		Standard Operating Procedure(s)

UNDAC 	United Nations Disaster Assessment and Coordination (Team)

UNDAF 		United Nations Development Assistance Framework

UNDP		United Nations Development Programme

1.0	EXECUTIVE SUMMARY

The terminal evaluation of the project ‘Strengthening National and Local Capacities for Disaster Response and Risk Reduction” is designed to evaluate the success the project has achieved in meeting the goals and outcomes that were set out in the design of the project and stated in the Project Document.  The overall goal was to strengthen the capacity at national and local levels for disaster response and risk reduction.  The desired outputs of the project, as stated in the project document, were:

Output 1.	Response Preparedness Capacity Strengthened at National and Local Levels

Output 2.	Strengthened Disaster Risk Reduction Capacity at National and Local Levels

Each of these outputs had a number of results that were to be achieved during the project.  These are listed in Annex 5 to this report, with the degree of achievement, as determined through the interview and questionnaire process, noted for each output.

A summary of the desired results is presented in the following listing (wording has been modified for ease of reading and understanding of the output goals)

- Add significantly to the capacity at national level for the primary implementing agency (CDC), to manage and coordinate regional and local community efforts in risk identification, risk reduction measures and disaster event adaptation

- Add significantly to the capacity at national level for the establishment of early warning systems for disaster occurrence and effect

- Add significantly to the capacity at local (community) levels to identify and implement risk reduction measures, for known disaster events likely to impact the local communities within the respective regions of Guyana

- Implement training programmes to bring the requisite training and implementation information to the local communities, which are the primary entities that will have to prepare for and respond to disaster events

- Develop clear understanding between national level organizations (ministries, departments, NGO’s, etc) of their roles in preparation for and management of disaster response and disaster risk reduction

- Increase national, regional and local awareness of disaster events, disaster damage reduction measures, and adaption to disaster event occurrence, through structural, non-structural (behaviour, insurance, etc.) measures.

The results of the terminal evaluation are to be used by UNDP to guide future project design in Disaster Risk, as a measure of the success of the programme design and funding in making effective use of the funding and staff resources of the UNDP; and by the implementing agency (CDC) and the programme stakeholders in further adapting their entities capability and capacity to address Disaster Response and Disaster Risk Reduction issues that may arise prior to and during disaster events.

Terminal evaluations are required for UNDP and GEF projects and programmes that fall under the “Mid – Size and Large” category within the organizations.  It is understood that the current project falls in the “Mid – Size” category.  The terminal evaluation followed the standard outline of activities noted in the UNDP / GEF Guidance Document for conduct of terminal evaluations, as described in Sections 2.3 and 2.4 of this report.  During the evaluation process, it was found that the interview process with stakeholders was the most effective method of obtaining data on the success of the project, lessons learned, and suggestions for modifications for future disaster risk project assessment and implementation.

The basic conclusions of the terminal evaluation are:

Success in Meeting Overall Goal:

The project has been successful in meeting its overall goal of strengthening the capacity at national and local levels for disaster response and risk reduction.

Success in Achieving Discreet Project Outputs and Results

The project has achieved success in meeting the results of:

- Adding significantly to the capacity at national level for the primary implementing agency (CDC), to manage and coordinate regional and local community efforts in risk identification, risk reduction measures and disaster event adaptation

- Adding significantly to the capacity at national level for the establishment of early warning systems for disaster occurrence and effect

- Developing clear understanding between national level organizations (ministries, departments, NGO’s, etc) of their roles in preparation for and management of disaster response and disaster risk reduction

Due to the timing and implementation of various portions of the project, partial success was achieved in meeting the results of:

- Adding significantly to the capacity at local (community) levels to identify and implement risk reduction measures, for known disaster events likely to impact the local communities within the respective regions of Guyana

- Implementing training programmes to bring the requisite training and implementation information to the local communities, which are the primary entities that will have to prepare for and respond to disaster events

- Increasing national, regional and local awareness of disaster events, disaster damage reduction measures, and adaption to disaster event occurrence, through structural, non-structural (behaviour, insurance, etc.) measures

These partial successes are due to the implementation schedule for achievement of these outputs and results, as they are part of the future (post March 2013) activities planned by CDC, and are not a result of lack of interest, activity or schedule compliance on the part of CDC or other involved entities.

Disaster History in Guyana

The country of Guyana has a long history of flood disasters, particularly along the low elevation coastal zones and inland rivers.  These have had large impacts on the local and national economies, as they can have significant effects on the two major agricultural crops, sugar and rice.  In the last several decades a combination of increased rainfall over shorter periods has produced devastating floods.  The capacity of the country to respond to flooding events, and other disaster events such as drought or large spills of mining or industrial waste, has served to focus the attention of the government on increasing disaster response and risk reduction capacity, at national and local levels.   In 2009, the Government of Guyana, together with the United Nations Development Programme and the Inter-American Development Bank, initiated a project designed to increase capacity in the disaster response and risk reduction area, and to provide an entity that would serve as the national coordination focal point.  In the period 2009 – 2013, this project has successfully built capacity to be used in managing the response and risk reduction to all large scale natural and human caused disasters in Guyana.

The project’s principal implementing partner is the Office of the President of Guyana.  The responsible parties for implementation of the project studies and activities are the Civil Defence Commission, the Ministry of Agriculture, the National Drainage and Irrigation Authority and the UNDP.  Principal funding for the project was provided by UNDP, while the Government of Guyana provided in-kind support through the CDC and other agencies and ministries.

The terminal evaluation report for the UNDP Guyana project “Strengthening National and Local Capacities for Disaster Response and Risk Reduction” has been prepared during the period January 20th – February 11th, 2014, on the basis of a mission to Guyana, review of project documents and other country and regional documents related to disaster history and response in Guyana.  During the mission to Guyana, interviews and discussions were held with most of the governmental ministries and departments involved in disaster response and risk reduction, and several Non-Governmental Organizations (NGOs) that have participated in previous disaster response and prevention effort.  The interview and discussion process had several limitations which prevented the evaluator from obtaining data and opinions regarding the success of the project in strengthening the capacity of the interviewees organization in DRM and DRR; or their organizations capacity to assist in disaster response.  These limitations were:

- Interviews with representatives of the various ministries, departments, agencies and NGO’s were limited to one or two representatives.  Thus the data and opinions gathered during the interview were primarily the interviewees understanding of the contribution of the programme in strengthening the capacity of their particular sector of the overall organization.  Multiple interviews within any entity, of persons within different parts of the organization, would have produced a more encompassing picture of the impact of the project on the whole organization.  Schedule constraints prevented the accomplishment of multiple interviews within any given entity.

- The time and logistical limitations prevented the evaluator from visiting and conducting interviews with local community leaders in several representative Regions and districts within the Regions.  Thus there was no direct input from these representatives on current benefits from the project, their understanding and acceptance of the project, and modifications that they might wish to see in project implementation.  Information on progress and successes at regional and community level had to come from CDC representatives.

Major areas covered in the terminal review were the following:  Relevance of the Project; Effectiveness in Achieving the Objectives; Efficiency in Use of Resources; Impact of the Project on Capacity Building in Risk Response and Risk Reduction at the National and Local Levels; and Sustainability of the Outcomes of the Project.

Overall Project Achievement;

The project has achieved most of the primary objectives identified at the outset of the project, primarily those of developing and strengthening capacity in disaster response and risk reduction at the national level and implementing programmes of training and education that will develop capacity in these two areas at the local community level, while also strengthening current capacity at the regional level in the respective regions of Guyana.  Initiatives are underway in several of the coastal regions (Regions 3 and 6) and one interior region (Region 9) to bring the training and education necessary for adequate disaster response / risk reduction capacity to the communities within these regions.  When the status of the capacity and systemic institutional deficits described in the Project Document are compared to the current strengthened capacity and key actors (CDC) enthusiastic acceptance of the required behavioral and institutional changes, it is apparent that the CDC and other key participants in the implementation of the project are focused on the continued progress of strengthening capacity and moving more responsibility to regional and local community levels.  The programmes that are being implemented at regional and local level, with the overall guidance and management by the CDC, are strong evidence of acceptance of the need to devolve responsibility and authority to the lowest implementing level.

The CDC, which has the day-to-day technical responsibility for managing and supervising the activities on the project, and the development of plans, strategies and implementation facilities for the National Multi Hazard Preparedness and Disaster Response Programme, has performed well in its role over the past three years.  Although the CDC has a limited staff, it has trained them well.  The CDC has been instrumental in forming the National Disaster Platform and Emergency Response Centre, and looks forward to future years of operation.

UNDP has functioned well in its role as the project funding agency, contributor to the technical and management aspects of the project, and reviewer of progress and monitoring of successes.

The overall performance of UNDP, the CDC, the project stakeholders and others contributing to the project was rated as Satisfactory (the second highest rating achievable).  A good number of areas of the project were rated as Very Satisfactory, while a few areas were rated as Marginally Satisfactory.  No areas of lower ratings were identified by the Project Evaluator.

Terminal Evaluation Recommendations:

Principal recommendations resulting from the terminal evaluation include:

- Build on existing programmes, structures and mechanisms:  reinforce existing high level policy framework and reform underway, constantly scan and adapt projects to local reality

- Be certain that the project is responding to clear existing needs

- Emphasize early engagement of stakeholders and keep ownership with them; use participatory approaches, including during the project inception phase

- Work with champions, but still support less engaged stakeholders

- Support a greater involvement of the scientific and academic community, particularly with respect to the impact of management practices on disaster reduction and adaptation

2.0	INTRODUCTION

2.1	Overview of the Project

The project under terminal review, “Strengthening National and Local Capacities for Disaster Risk and Reduction” was established in 2009, with the purpose of strengthening the capacity at national, regional and community levels in Guyana, to respond to natural disaster events.  The project initially focused on development of strategies, implementation plans, and systems necessary to develop and implement a National Disaster Response and Risk Reduction Plan for Guyana.  Subsequent activities included education and training at all levels, establishment of a National Emergency Centre and coordination and cooperation with Guyana’s Ministry, Agency and Department level personnel as appropriate.  The progress towards the achievement of these strategies, plans and systems is noted in Annex 5 to this report, “Evaluation Table Directed at Degree of Achievement, Quality and Guyana Focus in Output Categories.”

The project was funded by UNDP under an agreement with the principal implementing partner, the Office of the President.  The responsible parties for implementation of the project included the Civil Defence Commission, the Ministry of Agriculture, the National Drainage and Irrigation Authority, and the UNDP.  The CDC was the main implementing partner, and served as the focal point for activity management, maintenance of data and other systems, and day-to-day administration of the project.

The project was implemented in parallel with an Inter-American Development Bank (IDB) project “National Integrated Disaster Risk Management Plan and Implementation Strategy for Guyana”, that also focused on disaster response and risk reduction, primarily in the areas of overall national strategies and implementation.  The UNDP and IDB projects, due to their similar nature, shared the cost and services of a Project Coordinator through November 2013.  Subsequent to this date, the Project Coordinator worked solely on the UNDP project.  The UNDP project is slated to end in April of 2014.

## Context of Disaster Management in Guyana

Guyana has an area of 215,000 square kilometers and is located on the north coast of South America.  The coastal plain, one of four natural regions, lies near, and in some locations, below mean sea level (MSL). It supports 90% of the country’s multi-ethnic population and is the administrative, agricultural, commercial and industrial centre of the country.   The primary economic sectors of the country are agricultural products, chiefly rice and sugar; mining, chiefly gold and bauxite; and tourism (eco-tours).  Currently oil and gas resources exploration is being initiated in the Guyana offshore coastal region.  This may result in petroleum and gas becoming a significant income source for the Government of Guyana.  However, at present the mining and agricultural sectors are predominant, and the impacts of disasters on these two sectors could have significant influence on the annual GDP of Guyana.

The country is subject to Atlantic sea swells and experiences high intensity seasonal rainfall. As a result of the dynamic interplay between high tides, high rainfall levels and the aging coastal drainage and irrigation systems designed to support agricultural production and protect the coastal lowlands from high tides and flooding, the populated coastal zone remains at high risk to flooding.

In the mid – interior zones of Guyana there are significant areas of savannah, which are and can be used for livestock based industry and perhaps for agricultural use as irrigation systems are developed.  These areas currently are not subject to significant range fires, but could become so if the current trend in climate change effects becomes more intense and of longer duration.  It has been noted by several ministries and agencies that there are indications of longer lasting drought conditions in the currently more arid portions of the savannah.  Moderate to severe drought was experienced in the savannah during 1997 - 1998.

Other potential disaster events, of both natural and human causes, may be experienced in Guyana in the next decades.  These currently exist and have occurred infrequently, but may become more significant as climate change impacts become more substantial.  A tabulation of present and potential future disaster categories is presented in Table 1.

| Table 1. Disaster Categories Present in Guyana |  |
| --- | --- |
| Natural Disasters | Human Caused Disasters |
| Riverine and Tidal Flooding | Industrial or Mining Waste Spills |
| Savannah and Forest Fires | Disease Epidemic |
| Drought | Illegal Disposal of Process Wastes |
| Landslides | Oil Spill – Offshore |

Of these disaster events, riverine and tidal flooding is the most frequent and the most severe in Guyana.

In addition to the disaster categories noted in the preceding table, there are several other low probability events that should be noted and considered to some extent.  These are:

Earthquakes and Tsunamis: Guyana is not a high or moderate seismic area, with most seismic activity located to the north (along the Caribbean – Atlantic plate boundary) some 300 miles distant, as well as to the west in Venezuela, also several hundred miles distant.  Some seismic shaking is felt in Guyana from moderate to large earthquakes in the noted regions, but it is of low intensity and has not caused damage in Guyana.  Tsunamis (earthquake generated large sea waves) are possible disaster events to Guyana, although no record could be found of any significant tsunamis impacting the Guyana coastal areas.  Potential sources exist to the north (the Trinidad – Tobago area), where seismic events frequently occur; or in the Azores / Canary Islands regions.  The latter could generate tsunamis affecting Guyana, if large aerial / submarine landslides occur on one of the islands due to geologic / hydrologic instability of the island volcanic slopes.  Submarine topography in these islands indicates that pre-historic slides have occurred, and may have generated significant tsunami waves.  Whether such events reached Guyana is unknown, but might have occurred.  Response to such an event should be identified.

Large Cargo Ship Explosions:  It is known that Guyana is contemplating the expansion of the commercial harbor facilities in Georgetown, and perhaps other locations along the coast.  If in the future, large cargos of fertilizers or other chemically explosive materials are imported, the potential and probability for large ship explosions should be assessed.  Although a low probability event, past events in Texas City, Texas, USA (1947) and Halifax, Nova Scotia, Canada (1917) are examples of unforeseen explosion events that took as many as 2,000 lives and devastated the respective harbours.

Economic Impacts of Flooding Events

Between 1988 and 2006, flood events resulted in more than US$ 663 million in economic damage. In January 2005 alone, catastrophic floods in the coastal zone affected at least 30 % of the population, resulting in a near breach of the East Demerara Water Conservancy and total economic losses equivalent to 60% of GDP for that year.  Flood and drought risk are also high in several regions of the interior.   Guyana is an economically developing country, and suffers from high unemployment, insufficient revenue to support many critical infrastructure projects, and marginal funding for many social programmes.  Thus, at present, the impact of the principal disaster events has magnified effects on the overall strength and growth of the economy.

This pattern of flood hazards may be significantly altered in the future five to ten years, due to the effects of climate change and the variability associated with the progressive incremental rise of the levels of sea water.  It is known that in the Caribbean, the rise of sea level is up to 5 times faster than the world's average. This condition will significantly increase the possibility of coastal zone floods in Guyana. The modification of both amounts of rainfall and seasons (months) when these rains become more intense, makes it difficult to the predict flood occurrence. Other seasonal or multi-year events such as El Niño or La Niña can also produce hydro-meteorological alterations to occurrence of high rainfall or extreme droughts. Recently, inland flooding zones have been identified along river courses; this type of flood is becoming more recurrent and may be caused by climate change effects or a short high cycle of rainfall.  It is reported that high flows in Amazon Basin tributaries that flow into Guyana also contribute to the high flood flows that are being experienced in Guyana’s rivers.

As much as the heavy rains can cause problems, similarly the long dry seasons can affect the availability of fresh water for human use and for agricultural use. Small rural populations are being affected during drought periods, since reservoirs dry up and access to water can be significantly reduced.

On the vulnerability side, social vulnerability is high in Guyana since most of the population (estimated 90%) is located on the coast and along the river basins, therefore permanently susceptible to flooding. Structural vulnerability has also increased due to fast and unplanned urbanization, the use of non-traditional construction systems that include the replacement of wooden elevated structures to reinforced concrete ones that are built at the ground level without any considerations for possible floods. The same traditional wooden systems remain vulnerable to fires.

The reliability of sea and river embankments to balance between tidal levels and drainage from the interior along a floodplain has been stressed, so that the network of water conservancies, canals and locks need to be re-evaluated to ensure runoff and flooding control while at the same time making water available for life and livelihoods. The vulnerability of the conservancy and drainage-canals network has been increased due to the poor maintenance and concentration of solid waste and garbage which is disposed directly to the waterways, thus impairing the natural drainage of water.   These factors, combined with poor maintenance of the canals and drains (principally lack of annual removal of sediment and dense vegetation) have impacted the ability of the aging system to effectively drain the low coastal areas.

Additional sources of vulnerability relate to the need of further strengthening of the institutional organization and coordination for Disaster Emergency Response (DER) and Disaster Risk Management (DRM). Despite the efforts of the authorities and other stakeholders, there is a need to increase capacity and assign authority and responsibility to different organizations for specific activities to handle crisis situations or act in prevention and mitigation. The experience of the 2005 floods in Guyana is a key source of information to better understand what worked and what could have worked better.

Economic Impact of Drought Events

Droughts occur almost annually in different parts of the country, and where the ENSO (El Niño Southern Oscillation) is particularly active, severe impacts may be felt. El Niño or La Niña can greatly alter hydro-meteorological patterns as demonstrated also in the severe 1998 drought in Guyana. Long dry seasons can affect production of income crops, or the crops and livestock used by subsistence farmers for their livelihood.  Additionally, should the drought event affect the supply of water currently used for irrigation of rice and sugar cane, the economic effects of this would have significant impact on the GDP of Guyana.

Health Impacts from Flooding and Drought Events

Health hazards may arise from the flood and drought hazards.  Dengue, malaria, leptospirosis and other vector borne diseases are a threat. Similarly, other infectious diseases, such as cholera and yellow fever, can result in severe and widespread effects. While currently under control, the potential for a health related disaster is a constant threat.

2.2	Evaluation Purpose

The overall purpose of this evaluation is to measure how successful the implementation of the project has been, what changes in behavior it may have generated in the implementing agency, if the project benefits will be sustainable in the long-term and what are the lessons learned for future interventions in the country, region and other parts of the globe where UNDP provides its assistance.  Specifically, the evaluation will assess the effectiveness and contribution of the UNDP funded project to strengthening the ability of the main institutional groups involved in national disaster planning and response, to plan, coordinate and respond to future national disasters.  The evaluation would evaluate the extent to which the UNDP support of the project has contributed to the ability of the country to address systemic and structural challenges that affect national capacity to plan for and respond to natural disasters.

Finally, the terminal evaluation fulfills the obligation of the Disaster Response and Risk Reduction project document and Country Office evaluation plan, which mandated Mid-Term and Terminal Evaluations of the project.

Specifically the present terminal evaluation has the following objectives, adapted from Section 3 of the Terms of Reference for the project (Evaluation Scope and Objectives):

  - Analyze and evaluate effectiveness of the results that the project has been able to achieve against the objective, targets and indicators stated in the project document;

  - Assess effectiveness of the work and processes undertaken by the project as well as the performance of all the partners involved in the project implementation;

  - Provide feedback and recommendations for subsequent decision making and necessary steps that need to be taken by the national stakeholders in order to ensure sustainability of the project’s outcomes/results;

  - Reflect on efficiency of the available resource use; and

  - Document and provide feedback on lessons learned and best practices generated by the project during its implementation.

2.3	Description of the Evaluation

This terminal evaluation is a requirement of UNDP procedures applied at the end of mid-sized and large projects, and was initiated by the UNDP Country Office of Guyana as the Implementing Agency. This evaluation provides a professional assessment of the project implementation successfulness against the set objective and indicators, including contribution of the project to achieving global environmental benefits. The terminal evaluation also collates and analyzes lessons learned and best practices obtained during the period of the project implementation that can be further taken into consideration during development and implementation of other UNDP projects.

## Scope

The terminal evaluation focuses on the project achievements and their long term sustainability.  The evaluation takes into consideration the recommendations of the Mid-Term Evaluation (J. McCue, 2012) for increasing and strengthening the national and local capacities for disaster response and risk reduction.  The evaluation considered the project changes during the period 2012 – 2013, in response to the mid-term evaluation recommendations.

As per the Terms of Reference (TOR), it assessed the following aspects:

Relevance of the project:

Assessment of the project activities and overall relevance to:

- Achievement of the Millennium Development Goals of the United Nations;

- Development priorities at the local and national level;

- Direct beneficiaries - Government, local authorities, public services, utilities, residents.

Technical Performance:

Assess the technical progress that has been made by the project relative to the achievement of its immediate objective, outcomes and outputs.

- Quality of technical inputs – have the technical inputs (national and international)  been both sound and pragmatic in the context of the country development circumstances and field conditions found;

- Effectiveness - extent to which the objective has been achieved and how likely it is to be achieved;

- Efficiency – the extent to which the results have been delivered with the least costly

resources possible (cost-effectiveness).

- Adaptability – has the project been adaptable in the face of technical challenges or changing circumstances.

Management Performance:

The assessment will focus on project implementation.

- General implementation and management - assess the project in terms of quality and timeliness of inputs and activities, with particular reference to financial and human resources management;

- Executing agency, Project, and UNDP Country Office (CO) – assess the relative roles, capacities and effectiveness of the key project management players, with particular regard to UNDP CO obligations derived from the Implementing Agency (IA) Fee.

Overall success of the project with regard to the following criteria:

- Results – the positive and negative and the foreseen and unforeseen changes and effects produced by the UNDP intervention. This includes direct project outputs, outcomes and objectives;

- Sustainability - assessment of the prospects for potential replication of the project’s positive results after termination of UNDP support; static sustainability which refers to the continuous flow of the same benefits to the same target groups; dynamic sustainability use and/or adaptation of the project’s results by original target groups and/or other target groups. The sustainability should be assessed in terms of ecological, social, institutional and financial sustainability;

- Contribution to capacity development - extent to which the project has empowered target groups and has made possible for the government and local institutions to use the positive experiences; ownership of project’s results;

- Leveraging – any additional relevant financial or technical support to the project area.

Synergy with other similar projects, funded by the government and/or other donors.

Recommendations, lessons learned and best practices accumulated during the project for achieving sustainability of the project objectives and mechanisms, including future support of project initiated interventions by the Government and other stakeholders. Specific recommendations may also be drawn from the following aspects:

- Any key limitations in the original project proposal / project document;

- Any key lessons (positive and negative) in terms of both the technical and administrative implementation of the project;

- Any key factors in terms of the development environment that impacted the project;

- Any key lessons in terms of the quality of support provided by UNDP as the implementing agency;

- The major implications of any of the above for current or future UNDP projects generally, and specifically those in the country / sub-region in which UNDP is acting.

2.4	Methodology of the Evaluation

The methodology used in the terminal evaluation is based on the evaluation team’s Monitoring and Evaluation (M&E) experience; including experience with UNDP specifically. It complies with international evaluation criteria and professional evaluation norms, standards and ethics. The team used a methodology which promotes a shared understanding of environmental management procedures and priorities. These techniques stress the search for, and application of simple and effective solutions aimed at improving environmental management practices, at both local and global levels.

### Overall Approach

This terminal evaluation was conducted in accordance with the “UNDP-GEF Monitoring and Evaluation Policy”. It was undertaken in line with the UNDP principles such as independence, impartiality, transparency, disclosure, ethical, partnership, competencies, capacities, credibility and utility.  It considered the two overarching UNDP evaluation objectives at the project level:

- promote accountability for the achievement of UNDP objectives; including the global development and environmental benefits; and

- promote learning, feedback and knowledge sharing on results and lessons learned among the UNDP and its partners.

The evaluation team developed/used tools in accordance with the policy to ensure an effective project evaluation. As mentioned in the TOR, the evaluation was conducted and the findings are structured around the UNDP/GEF five major evaluation criteria; which are also the five internationally-accepted evaluation criteria set out by the Development Assistance Committee of the Organization for Economic Cooperation and Development.

These are:

  - Relevance relates to an overall assessment of whether the project kept with its design in addressing the key priorities to ensure that the objectives of the Guyana UNDP CO and the Government of Guyana are met and are in keeping with donor and partner policies, as well as with local needs and priorities.

  - Effectiveness is a measure of the extent to which formally agreed end of project results (outcomes) have been achieved, or can be expected to be achieved.

  - Efficiency is a measure of the productivity of the project intervention process, i.e. to what degree the outcomes achieved derive from efficient use of financial, human and material resources. In principle, it means comparing outcomes and outputs against inputs.

  - Sustainability is an indication of whether the outcomes (end of project results) and the positive impacts (long term results) are likely to continue after the project ends.

A particular emphasis was placed on the achievements of the project, its potential impacts in the long run and the long term sustainability of its achievements.

In addition to the principles and evaluation criteria described in the TOR, the evaluation team also applied the following methodological principles to conduct the evaluation:

- Participatory Consultancy: Participatory data gathering activities;

- Applied Knowledge: the evaluation team’s working knowledge of evaluation theories and approaches and its particular expertise in water resource management, country socio-economic issues, and environmental issues were applied to this project;

- Validity of information:  Limited only by the resources brought to bear, multiple measures and sources were sought out to ensure that the results are accurate, valid and supported by more than one source of information;

- Integrity: Any issues with respect to conflict of interest, lack of professional conduct or misrepresentation were immediately referred to the client if necessary; and

- Respect and anonymity: All participants had the right to provide information in confidence.

The terminal evaluation provides evidence-based information that is credible, reliable and useful.  The findings were triangulated through the concept of “multiple lines of evidence” using different evaluation tools and gathering information from different types of stakeholders and different levels of management. This methodology was presented to UNDP Guyana for their review and comments at the beginning of the assignment.

### Evaluation Methods of Analysis

To conduct this terminal evaluation, the evaluator used the following evaluation instruments and data collection instruments to successfully achieve the mandate of determining how successful the project was in strengthening the capacity at national and local levels for disaster response and risk reduction.  The respective data collection procedures were selected in accordance with the standard protocols of GEF / UNDP project terminal evaluations.  Specific selection reasons are noted in the respective categories of data collection procedures.

Evaluation Matrix: The evaluator developed an evaluation matrix based on the evaluation criteria included in the TOR. This matrix served as a general guide for the evaluation. It provided directions for the evaluation; particularly for the collection of relevant data. It was used as a basis for interviewing people and reviewing project documents. It also provided a basis for structuring the evaluation report as a whole.  It was presented to UNDP for approval before proceeding into the data collection phase.   The creation of an evaluation matrix was selected as a tool to ensure that the evaluation criteria of the TOR were addressed and data collected with respect to those evaluation criteria.  It also provided a guide for interviews and  construction of a questionnaire.

Documentation Review was conducted in Guyana and in the United States by the evaluator. In addition to being a main source of information, the documentation was also used to prepare for the mission to Guyana. A list of documents was provided in the TOR and the evaluator team made sure of access to all relevant documents.  The list of documents that were reviewed at the start-up of the mission is included as Annex 1.   The documentation review was selected as an evaluation tool in that it provided data with respect to previous work on disaster response and risk reduction, provided some indication of disaster areas felt important by other researchers, and described many of the risk areas and events that might require additional capacity and capability at the local level.

Interview Guide: An interview guide was developed - based on the evaluation matrix - to solicit relevant information from the stakeholders who were interviewed. This guide was also used to solicit input from stakeholders who were not able to be interviewed in person; using phone or email (one interview conducted in this manner). An example of the guide is included as Annex 2.

The interview guide was developed to ensure that interviews were conducted in a structured manner and were consistent with all interviewees.

Interviews with the stakeholders were conducted.  This list was reviewed and coordinated with the UNDP and the CDC at the start-up of the assignment. These semi-structured interviews were conducted using standards questions developed from the evaluation matrix and adapted to each particular interview. All interviews were conducted in person in Guyana and one by telephone (see list in Annex 2).  Confidentiality was guaranteed to the interviewees and the findings were analyzed and incorporated in the final report.  Interviews were selected as a data collection tool due to their effectiveness in determining the success within the interviewees organization of the capacity improvement, the opinion of the interviewee with respect to the value of the programme to his/her organizations ability to respond to disasters, and the degree to which the interviewee felt the strengthening should be carried down to the local community level.

Field Visit: As per the TOR, the International Evaluator visited Guyana in January 2014 (see Agenda in Annex 3).  Additionally, the evaluator visited the Demerara Water Conservancy and the CDC Volunteer Group in Region 6 to get an on the ground feel for the topography and other physical conditions in a typical coastal flooding region.  These site visits were coordinated by the CDC.  The field visit was requested by the terminal evaluator in order to get an “on the ground” understanding of the areas affected by disasters, the potential ability of the local communities to implement disaster response actions on a local basis, and implement risk reduction measures.

Data Collection and Analysis: Data collection was initiated prior to and during the mission to Guyana, using the internet to identify and access documents on disaster response and risk reduction relating to Guyana, to identify and access information regarding regional disaster programmes. During the stay in Guyana, the evaluator conducted interviews with most of the primary stakeholders in Guyana (the listing of primary stakeholders is presented in Annex 2); with several NGOs that are not primary stakeholders but are disaster responders; and with a group of volunteers in Region 6 of Guyana.  Additionally, the evaluator had discussions with key managers in the Guyana UNDP CO and the CDC.  Additional documents and reports were requested from the UNDP and the CDC, and these were promptly provided by those entities.

Data analysis was conducted through comparison with the information provided from the data sources against the outputs and objectives of the study, as presented in the Project Document.  In some cases, where “hard data” was not presented, the evaluator had to objectively interpret comments and opinions of the responders.

During many of the interviews, it was apparent that the interviewee’s knowledge of the project and its progress was limited to an area of interest to the interviewee’s organization.  This is a common occurrence, as most organizations contribute to a specific portion of the project objectives and are not involved in the overall progress of the project.

The attainment of the objectives was fairly clearly defined by the annual reports and specific completion of planning and implementation documents that related to the objectives.  Educational materials, training materials and notation of the numbers of trainees that had gone through training programmes also were indicators used in the analysis of the project progress and success.

The evaluation matrix prepared for the Project Inception Report, and subsequently modified with UNDP, was used to guide the collection and analysis of information from multiple sources.  The matrix is included in this report as Annex 5.

## 2.5	EVALUATION BENEFICIARIES

This terminal evaluation report will be disseminated for review to the executing and implementing agencies, national stakeholders and other partners of the project. After finalization, it may be forwarded to UNDP coordination offices for capitalizing on the gained experience and feeding it into formulation of UNDP policies and decision making.

The final evaluation report should also be made available for the public at www.undp.org.gy

2.6	Limitations and Constraints

The findings and conclusions contained in this report rely primarily on a desk review of project documents, a brief visit to a representative flooding area, and more than 15 interviews with key project stakeholders. Within the given resources allocated to this terminal evaluation, the independent evaluator was able to conduct a reasonable, but not intensively detailed assessment of actual results against expected results.  The primary methodological limitation on the data collection and analysis was the following:

The time and logistical limitations prevented the evaluator from visiting and conducting interviews with local community leaders in several representative Regions and districts within the regions.  Thus there was no direct input from these representatives on current benefits from the programme, their understanding and acceptance of the programme, and modifications that they might wish to see in the programme implementation.

A discussion and interview session was completed with a dozen volunteers from Region 6 of Guyana, these volunteers represent the collective volunteer groups across all regions of Guyana, and provided valuable input regarding the focus and contribution of the volunteer groups. The conclusions of the terminal evaluation report are based on information from documents and interviews with Ministry, Agency and Department personnel in the immediate Georgetown area, and the Region 6 volunteers.

The terminal evaluator was able to successfully ascertain whether the project met its main objectives, as laid down in the project design document, and whether the project initiatives are, or are likely to be, sustainable after completion of the project.

The terminal report also makes a number of recommendations that could be useful to reinforce the long term sustainability of the project achievements and also collates lessons learned and best practices obtained during the implementation of the project.

- PROJECT COMPONENTS EVALUATED

Based on the desk review of project documents and on interviews with key project stakeholders and the staff and management of the CDC, this section presents the findings of this terminal evaluation.  As described in Section 2.4, they are structured around the UNDP - GEF five major evaluation criteria, which are also the five internationally-accepted evaluation criteria set out by the Development Assistance Committee of the Organization for Economic Cooperation and Development. These are: Relevance, Effectiveness, Efficiency, Results and Sustainability:

3.1	Project Relevance

The project was designed to strengthen and further develop the capacity in the country of Guyana at national and local level, for disaster response and risk reduction.  This is in response to the frequent coastal flooding that materially affects the livelihood of the inhabitants of the coastal and riverine areas, as well as having significant impact on the overall economy of Guyana. This section presents the findings on the relevance of the project within the context of its original design and the capacity of Guyana in the disaster risk area.

### Development Objectives of Guyana

The project is relevant to the development context of Guyana and particularly within the context of developing a coherent programme for disaster risk recognition, reduction, response and mitigation.  In order to meet this development objective, the increase in capacity and capability to provide adequate disaster management is essential and relevant, and is the primary focus of the UNDP project. The project was designed to develop and test an integrated and participatory approach to disaster risk management, by dealing with all involved governmental bodies, and spreading implementation downward to regional and community levels.

Through the development of the Disaster Risk Platform, the Emergency Response Centre and integrated disaster response and risk reduction strategies and implementation plans, the project supports other Government of Guyana national priorities, such as:

- Creation of additional sources of employment for Guyanese citizens

- Improvement of the general conditions for health throughout the nation

- Reduction of poverty

- Maintenance and improvement of transportation infrastructure

Needs of Project Beneficiaries

The principal project beneficiaries of the capacity strengthening and its implementation at the national and local levels will be the agricultural sector, the inhabitants of the coastal and riverine environments, and the inhabitants of the savannah areas.  Citizens of Guyana that are in the service sectors will benefit from a potentially more stable economy and its employment opportunities. The strengthened disaster response and risk reduction capability and capacity has the potential to better define the areas that may be prone to future disasters, identify mitigation and risk reduction measures, and improve the living conditions in the potential disaster zones.  Knowing what their exposure to disaster events is, and then receiving guidance in how to better reduce that exposure, is to the benefit of all residents of Guyana.

A direct beneficiary of the project is the CDC, which is responsible for the management of the Disaster Response and Risk Reduction efforts in Guyana.  This agency has received training and capacity improvement, and is now better prepared to respond to disaster events.  With the support of other Guyanese ministries, departments and agencies, it can meet the requirements of the DRR strategies.

Synergies with Other Disaster Risk Reduction Projects

Disaster Response and Risk Reduction projects have been the primary focus of several recent and on-going projects in the Caribbean and Northern South American Coast areas.  These include the “National Integrated Disaster Risk Management Plan and Implementation Strategy for Guyana” project, that addressed disasters in Guyana; and the CDEMA “CDM Strategy and Programme Framework” (2007 – 2012), that addressed disaster issues in the Caribbean and coastal areas of Northern South America.   The Guyana CDC cooperated and coordinated with these two projects, and other global disaster projects (where applicable) in developing appropriate communication and data exchange programmes relevant to the regional disaster issues.

In doing so, the CDC and the Government of Guyana recognized that there were significant benefits in using the resource and information of all organizations in the region who are facing similar disaster issues.

## 3.2	Project Effectiveness

Below are the findings on the effectiveness of the project in achieving its expected results.  An overview of the key results achieved by the project is presented, followed by the project contribution to capacity development, the review of any unexpected project achievements and the review of the management of risks and the mitigation measures related to the implementation of the project. These findings are based on a review of project documents and interviews with key informants.

### Achievements of Project Expected Outputs

This is one of the most difficult areas to assess and to rate within the context of this terminal evaluation. The project performed very well, preparing plans, studies, assessments, and implementing many of the activities in the regions of Guyana.

The primary institutional change that could be noted, based on information contained in the Mid – Term Report, was the acceptance by CDC of a more managerial and guidance role in implementation of disaster risk response and risk reduction, rather than attempting to assume the roles or manager and primary implementer of activities in both areas.  It is evident that CDC has recognized that the primary efforts in immediate disaster response, and the implementation of disaster risk reduction measures must be from the local community level.

Nevertheless, based on the review of the project achievements and considering the number of entities that needed to be involved in planning and implementation, the results and achievements are rated as satisfactory. The project was able to utilize its resources to achieve good results and contribute toward the overall outputs of the project. These outputs were to be achieved through a variety of activities.  One output was deleted from the project requirements.  The original desired outputs were:

- Output 1.	Response Preparedness Capacity Strengthened at National / Local Levels

- Output 2.     	Strengthened Disaster Risk Reduction Capacity at National / Local Levels

- Output 3.     	Poverty Reduced to 28%  by 2010  (deleted from this phase of the study)

At some point in the project, Output 3 was deleted from the project outputs

The interviews and the review of project documents indicate that much progress had been made to achieve the two principal outputs noted in the preceding paragraph.  The third original ouput had no influence on the achievement of Outputs 1 and 2, as it related primarily to significant job creation

### Contribution to Capacity Development

The project achievements in capacity development in risk response and risk reduction are also rated as satisfactory. The overall implementation approach emphasized strong participation of stakeholders and most of the project achievements are owned by the relevant stakeholders. It was recognized early in the

strategy and planning of the project that successful implementation of increased capacity for disaster response and risk reduction throughout Guyana would be most effective if done at the regional and local community levels, with the overall management and supervision provided at the national level.  Thus, the strategy of capacity strengthening and development focuses both at the national and local community sectors.  The target groups were empowered through the implementation process and each initiative was developed following a strong assessment.

### Unexpected Project Achievements

Based on the interviews and discussions, there were no unexpected project achievements.

### Risk and Risk Mitigation Management

The management of risks and their mitigation measures is rated as satisfactory.  Risks that were identified in the project document or surfaced in later reviews, and in the evaluation process were:

That central government will fail to adequately support the long term financing and recurrent costs of the CDC (rated as a significant risk)

That local authorities, institutions and communities will lack commitment to the objectives and activities of the project (rated as a moderate to significant risk)

That administrative problems / lack of coordination will occur due to the inclusions of many local communities in any given region, which could lead to “too many cooks stirring the pot” (rated as a small to moderate risk)

That pilot projects will fail to successfully demonstrate the value of risk reduction, adaptation and response measures (rated as a small risk)

These risks were well managed during the project, primarily through the CDC’s strong role in developing logical plans and then communicating them well to regional and local community leaders.

Overall, the project was effective in achieving its expected outcomes and it is rated as satisfactory.  The project was able to utilize its resources to achieve good results and contribute toward the objective of the project which was to strengthen the capacity at national, regional and local levels in risk awareness and risk management. The local (community) level implementation is planned to be conducted during 2014 and in future years. Regional implementation is underway.

Mainstreaming DRR into National Plans

The mainstreaming of DRR into national plans is rated as marginally satisfactory.  This is due to the strong project focus during 2009 – 2013 on planning, development of implementation documents and plans, and assigning many of the required activities to national and regional entities.  This has not allowed sufficient time and effort to be devoted to the mainstreaming of DRR into other national plans and initiatives.  The mainstreaming is recognized as an important issue and to the benefit of Guyana, and presumably will be initiated in the 2014 – 2016 period.

3.3	Project Efficiency

Implementation Approach / Implementing Agency

The project was implemented by the Civil Defense Commission of Guyana, an entity set up as a key component of the Office of the President.  The approach was one of initially coordinating the efforts of the UNDP project with those of a similar Inter-American Development Bank project, which primarily addressed the development of the Strategic Plan and Implementation Plan for Integrated Disaster Response and Risk Reduction for all of Guyana; and a Vulnerability Assessment and Shelter Management Plan for Region 4 in Guyana.  The CDC was initially focused on the development of plans for the creation of an Emergency Response Centre, Risk Management Platform, Over-Arching Management Plan for the CDC in Disaster Reduction and Response, and an Education and Training component.

Once the plans and establishment of the referenced entities and documents had been completed, the implementation emphasis of the CDC shifted to the education and training of Regional and Local Community leaders and citizens in relevant aspects of disaster response and risk reduction.  The CDC has efficiently done so at the regional level and is continuing to do so at the community level, and its performance is rated as satisfactory.

### Project Management Approach and Tools / Adaptive Management

The management of the project is highly satisfactory. The project was well managed and used adaptive management extensively to secure project outcomes while maintaining adherence to the overall project design. The project management team used the project implementation document as a guide to implement the project and a reminder of what the project aimed to achieve. The original framework for the project, used at the design stage, was kept all along the implementation of the project.  The Evaluator noted that the project has been results oriented. The project logic presents the starting with the project goal, then immediate objectives (now called outcomes), outputs and activities and sub-activities. It is very much results-based oriented.

The adaptability and flexibility of the project was not able to be objectively assessed. As analyzed, the scheduling and sequencing of the implementation phase of the project was logical and not overly ambitious. The implementation was step–by-step.

The planned project end date was December 2012.  However, on the basis of the Mid-Term Evaluation (MTE) recommendation (2012), the Parties agreed on a time extension of the project to April 2014.

Finally, the project has produced a large amount of information. This information exists in both electronic form and paper form and it is available for those who are requesting it. Information was used by the project management team to manage and monitor the progress of the project.

### Financial Planning and Management

The accounting and financial system used by the project management team was satisfactory for the management of this project. The project finances were managed by the UNDP, and accurate and timely financial information was produced for the project management team; including on an ad-hoc basis.  A budget was established yearly during the last quarter of the calendar year for the coming year. If some budget revisions were necessary during the year, these revisions needed to be approved by a joint meeting of the CDC and the UNDP CO before it was sent onward to senior UNDP management.

The budget and annual expenditures that have been incurred to date on the project, funded from UNDP Core Funds, are:

Project Budget 	:	USD $	540,000

2009 Expenditures:	USD $	140,000

2010 Expenditures:	USD $    118, 051

2011 Expenditures:	USD $ 	   51,400

2012 Expenditures:	USD $	115,050

2013 Expenditures:	USD $	  97,777

2014 Expenditures:	USD $      47,360    (YTD)

Total Expenditures to Date	USD $    569,638

Additional expenses will be incurred in February and March of 2014, thus the project may exceed its established budget by approximately 8 to 10%.

### Quality of Technical Assistance / Use of National and Local Capacity

The quality of technical assistance used by the project and the development of national and local capacity was high and it is rated highly satisfactory. Despite some turnover near the end of the project, due to resignations of the Project Coordinator (PC), one consultant, and one staff, the project was able to assemble over time a technical assistance team well qualified to carry out day-to-day implementation activities. The staff was also highly motivated and dedicated to the project, going often beyond the call of duty. The project management team developed excellent working relationships with the project stakeholders; a necessary step to implement and succeed in this type of project emphasizing capacity development.

The project used a combination of international and national staff and consultants to bring the necessary mix of skills and knowledge needed to implement the project and also to develop the capacity of national staff over time.  The consultants and their related costs are presented in Table 2.

| Table 2. Consultants Used on the Project |  |  |
| --- | --- | --- |
| Consultant | Assignment / Service | Cost (USD $) |
| CARICAD | Develop strategic implementation plan | $ 34,500 |
| GeoTech Vision | Vulnerability Assessment and Shelter Evaluation Plan for Region 4 | $ 25,000 |
| Christopher Lawrence | CDC Website | $ 10,000 |
| Dr. Rovin Deodat | Facilitator Public Consultations | $ 2,700 |
| Ms. Mary Otto | Finalization of EWS, MHPP and DRM Policies | Not stated |
| Mr. Jonathan McCue | Preparation of Mid – Term Evaluation | $ 14,940 |
| Dr. Hans Ewoldsen | Preparation of Terminal Evaluation | $ 12,050 |

The national staff members were technically employed by the CDC and were considered as CDC employees. They benefited from most of the training activities conducted, contributing to upgrading their skills in various areas of project management. Additionally, the experience itself and the work environment emphasizing team work also contributed greatly to upgrading their technical and management skills. At project end, the project staff members are highly skilled and knowledgeable and are an asset which the CDC and UNDP may consider of value on future projects.

### Project Delivery Mechanisms / Partnerships

The project delivery mechanisms were satisfactory. The Executing Agency of the project is the CDC; a body under the Office of the President. The Executing Agency nominated a Project Coordinator. The responsibility of the Project Coordinator was to provide an official focal point and monitor the progress of the project for the central government level.

The UNDP Country Office, in addition to providing funding for a portion of the project costs, also contributed guidance and monitoring of the progress of the project, suggestions regarding modifications that would make the project more effective, and contributed staff time for meetings and review of reports and progress updates.

The project has a Project Platform Committee (PPC) under the Chairmanship of the Director General of the CDC to oversee project progress and ensure an effective coordination of all parties. The PPC members include the direct project management, the UNDP, the principal stakeholders from the line ministries, joint services organizations, private sector commission and NGO’s. They meet quarterly to give direction to the project but with no decision-making power; this body basically provided advice to the project.

At the local level, the project developed good relationships with all local partners/stakeholders. Once the local communities and local leaders understood the DRR concept and started to see the value of DRR for their livelihoods, they were keen in partnering with the project to benefit from the various training seminars and the technical assistance available to them. The future implementation at the local level will relieve the stakeholders of a significant part of the training and implementation of risk reduction and disaster response activities within the regions of Guyana. This transfers responsibility and authority to the local communities, while still maintaining overall responsibility and authority at the national level.  The project has had no problem to find partners for the implementation of the sub-projects.

### Roles, Capacity and Efficiency of Executing Agency and UNDP-CO

The efficiency of the CDC as the project executing agency was satisfactory. This unit is a national specialized body, responsible for the coordination of disaster response and risk reduction at all levels in Guyana.  It operates under the auspices of the Office of the President and is responsible for its operations and those of the National Emergency Centre.  The CDC does not have regional representations, but depends on regional and community leadership for implementation of Disaster Risk Reduction programmes. The CDC provides an official focal point for risk and risk reduction.

The efficiency of the UNDP CO is rated overall as excellent. The UNDP provided overall guidance to the project, and stepped in where required, to ensure that deadlines were met.  The UNDP provided funding for 50 % of the Project Coordinator, who proved very valuable to the project and to the parallel IDB project.

However, the procedures to administer the UNDP project funds are perceived as long and cumbersome. This was felt to cause delay in payments to consultants and subcontractors through the CDC, as all expenditures had to go through the UNDP process.

### Country Ownership / Stakeholders Participation

The country ownership of the project is satisfactory, given the current state of the project (disaster risk capacity building programme designed, but not fully implemented).  True country ownership will depend on the results of placement of full implementation in the regional and community levels.

The approach used to implement the sub-activities emphasized the development of local capacities and will be based on a strong participation of local stakeholders. The participation of stakeholders at the national level is very satisfactory. As a result, the achievements of these sub-projects should be guaranteed as sustainable. A good example of local ownership is the creation of the CDC volunteers in Regions 3 and 6. The project with the support of local leaders (mostly nurses from the local health facilities) surveyed several villages to assess the locations of disabled citizens and access requirements in case of flooding.  The volunteers approached the local authorities to get a room for meetings and training, and this was provided on an ‘as needed’ basis.

### Fund Leveraging

Overall, the capacity of the project to leverage funds to co-finance project activities is rated as marginally satisfactory. While additional funding in the form of grants and other services was requested, apparently none was received. The major co-financing contribution was an in-kind contribution from the GoG in the form of CDC services.

### Monitoring Approach and Progress Reporting

The monitoring and progress reporting of the project is rated as satisfactory. It was done according to UNDP / GEF procedures. Annual reports include basic project data, progress and rating of achievement of project objectives, progress and rating of project implementation, review of risks, any adjustments to project strategy and timeframe, financial information, procurement data, and lessons learned.

A list of two or more indicators per expected result was identified during the design phase.  These indicators were used in the annual reports where a baseline and a target had been established. The review of these reports shows that the monitoring of these indicators measured well the actual progress made toward the achievements of the expected results.

However, it is important to note that despite good progress made in various areas, the ultimate project long term sustainability (success) relies mostly on one indicator that is “the long term continued existence of the CDC” as the overall management body for the Risk Response and Risk Reduction programme.  In conclusion, the project was well managed and the resources utilised efficiently; it is rated as satisfactory. It used adaptive management extensively to secure project outcomes while maintaining adherence to the overall project design. Despite some staff turnover during the last year of the project, the technical assistance team was well qualified to implement the project, was highly motivated toward goal achievement and used/developed the capacity of the national staff. The project delivery mechanisms were good with a PC to oversee the progress of the project on a continuing basis. The implementation approach emphasized a strong participation of stakeholders and most of the project achievements are owned by the relevant stakeholders.

## 3.4	Project Benefits

This section comments on the potential to achieve the long term goal and objectives of the project based on the outcomes achieved during the lifetime of the project.

Increased Sensitivity to Gender and Participation by Ethnic Groups

The project has recognized that at the community level, where implementation of the disaster response and risk reduction measures is most important, women play an important part in encouraging the local community to adopt the recommended practices to the extent possible.  Women seek to have a safe environment for their families, to avoid the losses that a disaster event can bring, and recognize that cooperative efforts are effective.  The bulk of the CDC volunteers that are participating in Regions 3 and 6 of Guyana are women.  Representation at meetings of the DRR Platform during 2013 was reported by the CDC to be on the order of 40% women.  Additionally, trainings at regional and community levels are seeking to have women’s participation to levels of at least 20 to 25%.

The disaster response and risk reduction programme is being implemented at the community level in Region 9 (education and training to community leaders in this region).  Region 9 has a large component of Amerindian ethnicity, who do not always have the economic or technical resources to recover from disaster events as easily as other ethnic groups.  The focus on training in Region 9 demonstrates that the CDC is sensitive to the need to spread information to all ethnic groups in Guyana, as any disaster event will affect these groups relatively equally.

### Potential to Achieve Long Term Project Goal and Objectives

The potential for the project to achieve its long term goal and objectives exists.  The long term strategy will only be fully achieved if the sustainability is created. Additionally, the long term potential for the project to make an impact on the local communities and their citizens will depend on continued attention, periodic training upgrades, and like processes.

As with the rating for the achievements of project expected outcomes, this is also a difficult area to assess and to rate. This terminal evaluation report is written almost at project end in April 2014.  It was noted during the interviews with stakeholders and with the CDC volunteers in Region 6 that there was recognition that the issues of disaster response, and more importantly disaster risk reduction and adaptation to risk events are critical to those areas that are currently under yearly flood threat.  Additionally, several of the stakeholders, including those from the Guyana Defence Force and the Guyana Police Force, recognized that disaster events other than flooding would require response from their entities, particularly in the more remote regions of the country.  Thus, there is acceptance of the issues of disaster response, risk reduction and adaptation to disasters by the principal stakeholders in the project.  The CDC, as the primary focal point for disaster response management, is keenly aware of the interest of stakeholders and the importance of maintaining and continuing to build awareness of, and capacity to respond to future disaster events.

The project delivered most of the expected results:

- Generated an understanding within authorities in the respective regions of Guyana that significant responsibility for disaster response and risk reduction will be passed to them, and the central government entities will support their efforts in these areas

- The CDC has recognized that its role is both in management of disaster response and risk reduction programmes, overall training programmes for the country, and implementation of major responses in the event of a major disaster

- Prepared and submitted all basic documents for the establishment of the National Disaster Response and Risk Reduction programme

- Created, in consultation with key stakeholders, a Disaster Management Platform

- Built public, local authority and community awareness, support and participation in disaster risk management

- Built capacity of national, regional and local authorities, key decision makers and communities to effectively plan and play a role in disaster risk adaptation and mitigation

Key elements that needed to be implemented over the life of the project, verification indicators for completion of the key elements, and the status of verification, are included as Table 3.

| Table 3. |  |  |  |
| --- | --- | --- | --- |
| Disaster Response Preparedness Capacity Strengthening |  |  |  |
| Achievement Measure (1) | Verification of Achievement | Achievement Met |  |
| National assessment of disaster events | Completion of an assessment of the natural disaster events that can affect areas of Guyana | Yes |  |
| National vulnerability assessment | Completion of a national disaster vulnerability study | Yes |  |
| Assessment of capacity of national entities for disaster response | Completion of a capacity assessment for disaster response and risk reduction | Yes |  |
| Development of a strategy for disaster risk response at locations in Guyana | Completion of a disaster response and risk reduction strategy for Guyana | Yes |  |
| Development of plan for education / training at national, regional / local levels | Completion of a plan for education and training regarding disaster response | Yes |  |
| Development of training materials for delivery at national, regional / local levels | Preparation and initial delivery of education and training programmes | Yes |  |
| Identification of leadership positions at regional and local levels | Completion of identification of leaders at regional and local levels | Partial |  |
| Development of volunteer corps to assist in disaster response in regions | Organization of a volunteer corps, recruitment and training | Yes |  |
| Definition of responsibility and authority levels for regional and local authorities | Assignment of responsibility and authority at regional and local levels | Continuing |  |
| Central communication and disaster management platform established | Completion of national communication and disaster management centres | Yes |  |
| Disaster Risk Reduction Capacity Strengthening |  |  |  |
| Delineation of disaster vulnerable areas | Completion of a national vulnerability assessment |  | Yes |
| Information developed for national / local levels on risk reduction measures | Preparation of information packages regarding risk reduction measures |  | Yes |
| Land use planning and building code provisions provided to local areas | Development of land use plans and building codes for disaster risk reduction |  | Very Limited |
| Sea defenses and drainage provisions surveyed | Surveys of sea and drainage structures, identification of upgrading requirements |  | Yes |
| Adaptation measures for disaster events provided at regional and local levels | Development and dissemination of measures for adaptation to disasters |  | Very Limited |

- These measures were taken from the Initiation Plan and Project Document for the project, with some text modification and shortening

### Potential Impacts on Local Environment, Welfare and Other Socio-Economic Issues

The project has the potential to impact positively on the local environment and risk reduction socio-economic aspects, including the welfare of the low income population. However, for this potential to become a reality, the implementation must be focused at the local level, with appropriate authority and responsibility assigned.

### 3.5	Sustainability of Results Achieved by the Project

As for the sub-activity achievements, their long term sustainability is good. The capacity of the recipients is being developed and what is being accomplished should be sustained dynamically in the long run.  The issues of flooding, drought and other disaster events which can directly impact the livelihood, health, and economics of the local areas are apparent to the local authorities and leaders.  If they are to retain their positions, they should ensure the sustainability of the achievements and subsequent disaster mitigation and adaptation activities.

Sustainability Strategy

The sustainable strategy developed during the project document is rated as satisfactory. The overall logic was a stepped approach with training and capacity development in disaster response and risk reduction initially at the national level, and then devolvement down to regional level, followed by the final step of training and implementation of capacity development at the local level.

### Financial and Human Resources Sustainability

The financial and human resources sustainability of the project is strongly linked to the overall sustainability of the project achievements and particularly linked to continuance of the CDC as a strong governmental agency.  The government appears to be supportive of continued maintenance of the Emergency Centre, and this should, together with continuance of the CDC, provide the necessary staffing, resources and facilities for the programme.  The Disaster Act, currently before the Parliament, if passed, should contain provisions for financial support in the country’s annual budget.

Enabling Environment – Policy, Legislation and Institutions

The legislative draft for the National Disaster Response Act has been created and forwarded to the Parliament for review and enactment.  If this is successful, the enabling environment will exist.  Subsequent modifications to policy may be required, depending on the final form of the Act.  The institutions already exist for the implementation of current and future activities under the Act.

### Environmental Sustainability

The environmental sustainability of the project is rated satisfactory as there are no environmental risks which can undermine the future flow of project environmental benefits. Project activities can improve the environment if upgrading of the flood structures is achieved, and some effort is given to the cleaning of drainage channels and removal of solid waste that is prevalent in and adjacent to them.

### Replication and Scaling-Up

The review indicates that the opportunity for replication and scaling-up of the project achievements are good, if they are applied to the remaining regions of Guyana.

4.0	FINDINGS SUMMARY

# This section presents the ratings, lessons learned, and recommendations for the project.  The ratings were established based on the rating scale of UNDP / GEF, which has a total of six (6) possible ratings for evaluation criteria or other key aspects of the project which may have been noted in the TOR.

4.1	Summary Comments on Ratings

A summary of the basis for the ratings is given in Table 4, below, for each evaluation criteria or TOR item.

4.2	Summary of Ratings for Outputs / Activities

A tabulation of all ratings of the Outputs and Activities noted for the project is presented in Table 5, following:

Table 4.   Summary of Ratings for Outputs / Activities

| Evaluation Criteria : Relevance / Appropriateness “Are the project partnership strategies appropriate, relevant and contributing to the project effectiveness?” |  |
| --- | --- |
| Are the activities being carried out relevant to the projects objectives? | HS |
| Is the project relevant to Guyana’s development objectives? | HS |
| Are the project outcomes timely, appropriate to country needs, able to build capacity and appropriately prioritised? | S |
| Evaluation Criteria : Effectiveness “Were the planned outputs achieved or are they on track to be achieved?” |  |
| Is the project effective in achieving its planned outcomes? | S |
| Are the project activities designed to achieve the project outcomes? | HS |
| Are the project risks being managed effectively? | S |
| Are the future directions for the project effective in achieving more capacity in risk response and risk reduction? | S |
| Are the future actions timely in achieving the desired outcomes? | MS |
| Are the professionals and staff on the project well qualified to manage and implement the project ? | S |
| Evaluation Criteria : Efficiency “How efficiently is the project implemented?” and “What progress has been made towards the outcomes stated in the project document?” |  |
| Is the project support channeled in an efficient way? | S |
| Are the partnership arrangements for the project efficient? | HS |
| Are the future directions for the project efficiently planned? | S |
| Have the operations of the project performed against the objectives efficiently? | S |
| Have the project resources been used in the best possible way? | S |
| Evaluation Criteria : Coherence “What factors have contributed to achieving or not achieving intended outputs?” and “to what extent have project outputs contributed to achieving UNDP Country programme goals ?” |  |
| Were clear disaster risk reduction and management principles utilized in the programme? | S |
| Were the objectives and activities consistent? | HS |
| Were the cross – cutting issues treated coherently? | S |
| Are the links to other programmes and initiatives coherent? | HS |
| Evaluation Criteria : Sustainability “What adjustments are needed to the projects Results and Resources framework, implementation approach, and arrangements, to achieve planned outputs?” |  |
| Have stakeholders in Guyana been involved in the design and implementation of the UNDP project ? | MS |
| Is the process of stakeholder engagement robust within the CDM – UNDP programme in Guyana ? | S |
| Has the impact of the UNDP project been clearly understood by all governmental and institutional stakeholders in Guyana, and has it been clearly communicated? | MS |

Evaluation Rating Categories:

Highly Satisfactory		(HS)

Project is expected to achieve or exceed all its project objectives, without major  shortcomings

Satisfactory			(S)

Project is expected to achieve most of its major objectives, with only minor shortcomings

Marginally Satisfactory		(MS)

Project has achieved most of its major objectives, but with some shortcomings or limited relevance

Marginally Unsatisfactory	(MU)

Project has achieved major objectives with major shortcomings

Unsatisfactory			(U)

Project is not expected to achieve most of its major objectives

Highly Unsatisfactory		(HU)

Project has failed to achieve any of its major objectives

Table  5.   :   Ratings Summary Comments

| Evaluation Criterion | Summary Comments | Rating |
| --- | --- | --- |
| Relevance | The project was highly relevant in meeting the objectives of the UNDP and GoG, in responding to the development objectives of increasing capacity in Disaster Response and Risk Reduction, and in meeting the needs of the target beneficiaries. Its design was satisfactory and the project document contains a convincing approach to address the existing problems. | Highly Satisfactory |
| Effectiveness | The project was partially effective in achieving its expected outcomes. The project was able to utilise its resources to achieve good results and contribute toward the first objective of the project, the increasing of capacity at the national level. Completion of the remaining objectives, increased capacity at the regional and local levels has only been partially implemented. | Satisfactory |
| Efficiency | The project was well managed and the resources utilised efficiently. It used adaptive management extensively to secure project outcomes while maintaining adherence to the overall project design. The project management team used the Initiation Plan as a guide to implement the project. The project finances were managed by the UNDP and were adequate. Despite some staff turnover during the last year of the project, the technical assistance team was well qualified to implement the project; was highly motivated toward goal achievement; used/developed the capacity of the national staff; and developed excellent relationships with the project stakeholders. The project delivery mechanisms were good with a PC to oversee the progress of the project. The implementation approach emphasised a strong participation of stakeholders and most of the project achievements are owned by the relevant stakeholders. | Satisfactory |
| Impact | Despite an effective implementation (satisfactory) of the project, the potential impact to achieve its long term goal and objective is mixed. This potential impact does exist; however, it requires that the CDC and the Emergency Response Centre be maintained in the future. This rating is valid within the current context of the project that is pending for the legal establishment of the Disaster Response Act. The impact of the project will reside mostly with the stakeholders, and with local and regional officials who were engaged in the project during its implementation and who acquired skills and knowledge in the area of disaster response and risk reduction. | Marginally Satisfactory |
|  | The UNDP contribution to DRR benefits does exist on this project. The capacity of the people involved in the project was developed and the concept of DRR is now well understood in the regions but also in national institutions. These skills and this knowledge are already used in several cases to design new projects to strengthen the flood resilience. |  |
| Evaluation Criterion | Summary Comments | Rating |
| Sustainability | Similar to the impact, the sustainability of the project achievements is dependent on the continued existence of the CDC and the Emergency Response Centre. However, the sub-project achievements are sustainable. The capacity of the recipients was developed and the achievements should be sustained dynamically in the long run. The national education programme has produced both Compact Discs and booklets/pamphlets, which will be distributed to schools and volunteer groups in the communities. People will use the skills and knowledge acquired with the project support and will continue with their day-to-day activities using the achievements as a basis to expand their resilience to floods and other natural and human caused disaster events. In addition to sustainability, the replication and scaling-up potential of the project is good. The project concept, lessons learned and best practices can be applied to all regions of the country. | Marginally Satisfactory |

| Specific Criteria (from TORs) |  |  |
| --- | --- | --- |
| Conceptualisation/ Design | The project document approved by UNDP and other parties contains an adequate justification and convincing approach to address the disaster response and risk reduction in Guyana. It notes the great need for increased capacity at all levels and lays out a logical path toward achievement of that capacity. The logic of the project strategy was well laid out in the project document. The initiation plan contained the logic of project intervention; including the expected outputs and the major activities to be implemented. It also included performance indicators which were used during the implementation of the project to measure progress. | Satisfactory |
| Stakeholder participation (in project formulation) | The participation of stakeholders in project formulation was encouraged by the project team. There were some concerns expressed by stakeholders that they felt that more consultations may have increased the levels of communication and coordination in the early stages of the project. The relevant national institutions were engaged during this design phase. However, the participation of the local communities in the formulation of the project was initiated gradually, and most communities were not familiar with the concepts of disaster response and risk reduction (they were well aware of these issues in the primary hazard, flooding, for their communities, albeit in a less formal sense). | Satisfactory |
| Coherence | The coherence of the project is rated as satisfactory. To be able to bring coherence to a project that involves a significant number of stakeholders and a geography that includes remote and difficult access areas, requires strong planning, communication and management skills. The CDC and UNDP have done this well. | Satisfactory |
| Implementation Approach | See Efficiency above | Satisfactory |
| Monitoring and Evaluation | The monitoring and progress reporting of the project was done according to UNDP procedures. The indicators measured well the actual progress made toward the achievements of the expected results. The progress of the project was also reported in the annual reports by measuring its contribution against the UNDP strategic targets in Disaster Response and Risk Reduction. | Satisfactory |
| Stakeholder Participation (in project implementation) | Stakeholders responded well to the needs of the target groups at national and local levels. During the first phase of the project to prepare the documents for the creation of the National Programme, the relevant institutions appear to have been appropriately engaged in the process. | Marginally Satisfactory |
|  | The approach that is being used to implement the sub-activities emphasised the development of local capacities and was based on a strong participation of local stakeholders. As a result, the achievements of these sub-projects will be owned by the recipient stakeholders and the long term sustainability of these achievements should be guaranteed. |  |

| Evaluation Criterion | Summary Comments | Rating |
| --- | --- | --- |
| Attainment of Outcomes | See Effectiveness above. | Satisfactory |
| Achievement of Objective | See Impact above | Marginally Satisfactory |
| Overall Rating | Overall, the achievements of the project are satisfactory. The project contributed to the development of the capacity of many people and organizations that are responsible for disaster risk reduction, adaptation, and response. | Satisfactory |

4.3	CONCLUSIONS

Overall Project Outcome

The overall desired project outcome, strengthened capacity at local and national levels, for the management of disaster response and risk reduction has been achieved.  Secondary desired outcomes of the project were also achieved, including:

- Increased capacity in Guyana for the handling of any future disasters

- Training of Ministry stakeholders, CDC,  and non-governmental personnel in the handling of disasters

- Increasing awareness of Ministry stakeholders and other non-governmental personnel in risk reduction and climate change adaptation

- Initiation of a continuing effort to bring the implementation of disaster programmes down to the local community level

- Procedures and centres established for emergency communication and coordination

# 4.4	LESSONS LEARNED

Based on the review of project documents, interviews with key participants, and analysis of the information collected, the evaluator team provides the following lessons learned:

- In projects where the stakeholder group includes government ministries, departments and agencies not directly focused on the project objectives, it is difficult to identify a key contact person within the entity that has a comprehensive picture of how the achievement of the project objectives was or was not successful, and how achievement would affect the entity’s primary mission.

- Capacity development mainly focuses on broadening the base of individuals / entities that have uniform or semi-uniform knowledge and skill sets in the area of interest, in this case disaster response and risk reduction.  There is also a need for capability development on many projects, the upgrading of technical skills and knowledge to bring new technologies or disaster response procedures to the table.

- Where the project results are to be implemented at multiple layers, it is necessary to provide each layer with well-defined statements of authority and responsibility.  Confusion regarding “who does what” needs to be avoided.

- The earlier the project achievements are institutionalised, the better the long term sustainability will be. A more integrated implementation approach emphasizes the development of capacity and maintains more ownership with the stakeholders during the implementation phase.

- Accurate and relevant information and communication are important components of the management framework of disaster planning and risk management. Good and accessible information is key for good decision-making but also to keep people abreast of new developments, to offer information on best practices, etc.  A project such as the UNDP project produces a lot of relevant and useful information which should be more accessible by all through the web. Despite the fact that only a moderate percentage of the population has access to the internet today in Guyana (30.3 %, South American Internet Usage Survey, 2013), it will change over the coming years and projects of this type should emphasise the dissemination of this information online.

# 4.5	RECOMMENDATIONS

Based on the findings of this Terminal Evaluation, the following recommendations are made:

- The body of knowledge from the project should be catalogued in the end of project report to leave a transparent paper trail available.

- The data collected during the programme could be more utilised; its access should be extended to all. Using web technologies, this body of knowledge should be loaded onto the web and anybody should be able to access it. The numerous models, manuals, plans, assessments and other pieces of project information should be posted to a website and be available to whoever wants to access it (to be considered by CDC or future implementing entities).

- In moving forward on any continuation of the current programme, or on a new project that carries forward on the devolution of authority and responsibility for DRR and DRM to the regional and local level, consider the findings of the Mid-Term and Terminal Evaluations of the current programme.

- When designing new projects, particularly in the natural hazard / resource management area and the implementation of national programmes, emphasise a capacity development approach with some key features such as:

  - Build on existing programmes, structures & mechanisms: reinforce existing high level policy framework and reform underway, constantly scan and adapt projects to the local reality and build the “transmission belts” among institutions;

  - Consider and integrate into the design of the programme ‘lessons learned” from previous similar programmes;

  - Respond to explicit needs and not “constructed” needs; be sure the project is responding to clear existing needs;

  - Emphasise early engagement of stakeholders and keep ownership with them: use participatory approaches, share decisions and build consensus. Focus on building trust among partners, leave space for dialogue and share resources through partnership agreements;

  - Work with champions but still support less engaged stakeholders: work with “pockets of energy” including political champions, foster networking, obtain high level government support and support the less engaged but important organizations;

  - Support a greater involvement of the scientific community in this type of project; particularly with a focus on the impact of management practices on disaster reduction and adaptation. The scientific community needs to be more involved in these projects and to focus particularly on the disaster mitigation and adaptation methods.

(These items are to be considered by UNDP and programme implementing authorities).

Terminal Evaluation Report Annexes

“Strengthening National and Local Capacities

for Disaster Response and Risk Reduction”

ANNEX 1.	Document List:  Reviewed Documents

Documents Reviewed Prior to Mission

- UNDP “Strengthening National and Local Capacity for Disaster Response and Risk Reduction Project” Initiation Plan (2009)

- Project Document - Strengthening National and Local Capacity for Disaster Response and Risk Reduction, inclusive of Results and Resources Framework;

- Mid Term Review  -  Strengthening National and Local Capacity for Disaster Response and Risk Reduction, inclusive of Results and Resources Framework;

- Indigenous Perception of Climate Change, Its Impacts and Coping Strategies for Sustainable Livelihoods in Guyana and Suriname, Paulette Bynoe, University of Guyana, 2012

- Key Disaster Risk Management Projects in Guyana, Denise Fraser, Project Coordinator, CDC; Symposium on Agricultural Risk and Insurance; December 2009

- Comprehensive Approach to Disaster Management in the Caribbean Project; Baseline Study, 2001

- UNDP Guyana, Annual Progress Report January – December 2013

- UNDP Guyana, Annual Progress Report December 2008 – December 2009

- CPAP Guyana 2012 – 2016

- Final Evaluation Report;  Design and Implementation of an Integrated Disaster Risk Management Plan (IDB ATN/OC-1178-64; Paulette Bynoe, December 2013

- Numerous Articles extracted from the internet for the period 2000 – 2013

- CDC Concept Note for Project Continuation

- Annual Report (UNDP Project)  -  December 2008 – December 2009

- Project Document for Finish of Project Activities  :  Q2/Q3 – 2013

- Summary Report, National Consultation #3; Disaster  Risk Management Policy; May 23, 2013

- Detailed Report on Review of Draft National Multi-Hazard Preparedness and Response Plan & Sector Guidelines for  Preparation of a Preparedness and Response Plan; CDC, Guyana (undated)

- Review of the Disaster Risk Management Policy for Guyana; UNDP Crisis Prevention and Recovery Area; 18 March 2012

- Comments on the DRM Policy, Strengthening National and Local Capacity; June 2011

- Annex 2 to Comments on the DRM Policy, Strengthening National and Local Capacity; June 2011

- IADB (2009) Design and Implementation of an Integrated Disaster Risk Management Plan (GY-T1050); Project Plan of Operations.

- Concept Paper – Comprehensive Disaster Management; CDC; December 18, 2012

- National Integrated Disaster Risk Management Plan and Implementation Strategy for Guyana; Integrated Disaster Risk Management Plan; IDB July 2013

- National Integrated Disaster Risk Management Plan and Implementation Strategy for Guyana; Integrated Disaster Risk Management Implementation Plan; IDB July 2013

Documents Reviewed During Mission and Draft Report Preparation

- Draft Country Programme Document (CPD) for UNDP (2012-2016);

- UNDP “Strengthening National and Local Capacity for Disaster Response and Risk Reduction Project” Revised Detailed Initiation Plan (2009)

- CDC Annual Work Plan (2012)

- Capacity Assessment Report Disaster Risk Management in Guyana (2009)

- Disaster Risk Management Policy - Revision Draft  June 2011

- National Emergency Operations Centre - Standard Operating Procedure (2010)

- Guyana Civil Defence Commission, Annual Report 2013

Annex 2.	Organizations Interviewed/Interview Guide

| Appt # | Date / Day Time | Organization | Meeting Address | Contacts |
| --- | --- | --- | --- | --- |
| 1 | Monday 20 Jan 0900 | UNDP Briefing | Brickdam and UN Place | Ms. Chisa Mikami |
| 2 | Monday 20 Jan 1400 | CDC Headquarters Introduction | Thomas Road | Colonel Abraham Mr. Kester Craig Ms. John-Klass |
| 3 | Tuesday 21 Jan 1000 | UNICEF | CDC Conference Room | Mr. Ian Jones |
| 4 | Tuesday 21 Jan 1300 | EPA | EPA Office | Ms. Sonia Gumbs-Luke |
| 5 | Wednesday 22 Jan 1000 | UNDP Res Rep | UNDP | Ms. Khadija Musa |
| 6 | Wednesday 22 Jan 1100 | Office of Climate Change | OCC Office | Ms. Preeya Rampersaud |
| 7 | Thursday 23 Jan 1400 | Hydromet | Hydromet Office | Ms. Donessa David |
| 8 | Thursday 23 Jan 1000 | Guyana Lands & Survey Commission | GLS Office | Mr. Naseem Nasir |
| 9 | Thursday 23 Jan 1300 | Habitat for Humanity | CDC Conference Room | Ms. Ashema Franklin |
| 10 | Friday 24 Jan 1100 | Ministry of Agriculture | Ministry of Agriculture Office | Dr. Jean David |
| 11 | Friday 24 Jan 1300 | Ministry of Health | IDB | Ms. Cassandra Rogers |
| 12 | Monday 27 Jan 1000 | Guyana Red Cross | CDC Conference Room | Ms. Dorothy Fraser |
| 13 | Wednesday 29 Jan 1500 | University of Guyana | CDC Conference Room | Dr. Paulette Bynoe |

ANNEX 3.	Mission Schedule and Activities

| Appt # | Date / Day Time | Organization | Meeting Address | Contacts |
| --- | --- | --- | --- | --- |
| 0 | Sunday 19 Jan | Arrive in Georgetown |  |  |
| 1 | Monday 20 Jan 0900 | UNDP Briefing | Brickdam and UN Place | Ms. Chisa Mikami |
| 2 | Monday 20 Jan 1400 | CDC Headquarters Introduction | Thomas Road | Colonel Abraham Mr. Kester Craig Ms. John-Klass |
| 3 | Tuesday 21 Jan 1000 | UNICEF | CDC Conference Room | Mr. Ian Jones |
| 4 | Tuesday 21 Jan 1300 | EPA | EPA Office | Ms. Sonia Gumbs-Luke |
| 5 | Wednesday 22 Jan 1000 | UNDP Res Rep | UNDP | Ms. Khadija Musa |
| 6 | Wednesday 22 Jan 1100 | Office of Climate Change | OCC Office | Ms. Preeya Rampersaud |
| 7 | Thursday 23 Jan 1400 | Hydromet | Hydromet Office | Ms. Donessa David |
| 8 | Thursday 23 Jan 1000 | Guyana Lands & Survey Commission | GLS Office | Mr. Naseem Nasir |
| 9 | Thursday 23 Jan 1300 | Habitat for Humanity | CDC Conference Room | Ms. Ashema Franklin |
| 10 | Friday 24 Jan 1100 | Ministry of Agriculture | Ministry of Agriculture Office | Dr. Jean David |
| 11 | Friday 24 Jan 1300 | Ministry of Health | IDB | Ms. Cassandra Rogers |
| 12 | Saturday 25 Jan 0900 | Field Trip Berbice | CDC Control | N.A. |
| 13 | Sunday 26 Jan As Required | Hotel - Work | Hotel Cara Lodge | N.A. |
| 14 | Monday 27 Jan 1000 | Guyana Red Cross | CDC Conference Room | Ms. Dorothy Fraser |
| 15 | Monday 27 Jan 1300 | WHO / PAHO | CDC Conference Room | Cancelled |
| 16 | Tuesday 28 Jan All Day | Hotel - Work | Hotel Cara Lodge | N.A. |
| 17 | Wednesday 29 Jan 1500 | University of Guyana | CDC Conference Room | Dr. Paulette Bynoe |
| 18 | Thursday 30 Jan All Day | Hotel – Work Presentations | Hotel Cara Lodge | N.A. |
| 19 | Friday 31 Jan 1000 | CDC | CDC Conference Room | Briefing to Stakeholders |
| 20 | Friday 31 Jan Afternoon | UNDP | Small Conference Room – UNDP CO | Briefing to UNDP |
| 21 | Saturday 1 February | Depart Georgetown |  |  |

ANNEX 4.	Report of Field Trip to Region 6

Through the auspices of CDC, a field trip was scheduled on the 25th of January, to Region 6 of Guyana.  The purpose of the trip was to provide the Terminal Evaluator an opportunity to view coastal areas that have experienced frequent flooding, review a typical seawall defence system, and other areas of importance with respect to disaster risk (principally flood risk).

The itinerary for the field trip was:

- Visit the Plaisance sea wall defence system immediately east of Georgetown

- Discuss performance of sea wall and pumping station with operator

- Travel to Region 6, observing irrigation and drainage systems on the way

- Visit East Demerara Water Conservancy District

- Observe water control systems of the Demerara Water Conservancy District

- Visit Fort Ordinance Canje, observe lack of flood defence and sanitary system

- Visit flood prone areas along the east bank of the Berbice River

- Meet with CDC Volunteers in New Amsterdam

- Return to Georgetown

Observations from the trip and from East Demerara operational staff, include:

- The canals and irrigation channels are heavily sedimented

- Canals and intake areas to pumping stations are clogged with aquatic plant growth

- Sea wall defences are sufficiently high in some areas, deficient in height in other areas

- Reduction in available irrigation water, through climate change impacts, will have severe consequence on agricultural crops

- Small runoff channels along roadways have significant accumulations of solid wastes, impeding flow

- Housing developments along the rivers and streams are not flood resilient

- There appears to be a lack of adherence to planning guidance for housing locations

- CDC volunteers are motivated and understand flood response and risk reduction

Annex 5.

Questionnaire Guide for Interviews

For Use in Terminal Evaluation of the UNDP Disaster Risk Response and Risk Reduction Project

(DRR)

Questionnaire Respondee Organization: _____________________________

Name & Title (Optional):  _________________________________________

Please E-mail response to ewoldsenh@aol.com no later than 30 January 2014

Note:	All responses will remain anonymous, with only summaries of the evaluation presented

This questionnaire is being circulated to interviewees for commenting on the progress and results of the UNDP project on “Strengthening National and Local Capacities for Disaster Response and Risk Reduction”.  If you believe that any of your colleagues would be interested in commenting also, please forward this to them.

It is an essential part of the Terminal Evaluation process of the project.  Thus your input is very valuable in the evaluation.  If you could please go through the questionnaire and provide your input, it would be greatly appreciated.  The questionnaire consists of general questions regarding the project and its implementation.

General Questions Regarding the Project and Its Implementation

(Please provide comments.  If the question is not relevant to your role, leave blank)

- Were the stated outputs achieved or are they on track towards being achieved? (effectiveness)

- What progress has been made toward the outcomes stated in the project document? (efficiency)

- What factors contributed to effectiveness or ineffectiveness? (effectiveness)

- What adjustments are needed to the project’s Results and Resources Framework (RRF), implementation approach and arrangements to achieve planned outputs? (sustainability)

- Are the project partnership strategies appropriate, relevant and contributing to project’s effectiveness (relevance)?

- Do you feel that the Stakeholders for the DRR project have taken, and will continue to take, ownership of the project?

- What worked well on the project?

- What did not work well on the project?

- How can we improve coordination among key stakeholders in planning for natural disasters?

- To what extent did the project contribute to building national capacity for strategic leadership In DRR?

- To what extent has the project improved CDCs and community level capacity to manage floods and droughts?

- What are the opportunities to improve public-private partnerships for flood management?

- Do you believe the political will exists for continuation and support of Disaster Risk and Reduction Programmes?

Evaluation Table Directed at Degree of Achievement, Quality and Guyana Focus in Output Categories

In responding to the following output categories, please type or place an X in the box that reflects your evaluation of how the project met the output stated for the activity number.  If you do not feel that the question relates to your role in the project, or your observations of the project progress, leave the question un-answered.   The activities and their descriptions are contained in the Table

In making your selections, note the following:

The columns headed “Achieved” are to indicate the degree to which you think the project met the activity goal

The columns headed “Quality” are your evaluation of the technical or management quality of the activity product

The columns headed “Appropriate” are intended to obtain your opinion of how the activity product meets the requirements and realities of Guyana  (economic situation, capacity and capability, etc.)

H  =  High		M =  Moderate or Average		Low = Low or Minimally Acceptable

| Description |  | Achieved |  |  |  | Quality |  |  |  | Appropriate |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Output 1. Response Preparedness Capacity Strengthened at National and Local Levels |  | H | M | L |  | H | M | L |  | H | M | L |  |
| 1.1.1 | Equipped CDC and National Emergency Operations Centre with Appropriately Trained Staff |  |  | M |  |  |  | X |  |  |  | X |  |  |
| 1.1.2 | Strengthened Early Warning System for Floods and Droughts |  |  |  | X |  |  |  | X |  |  |  | X |  |
| 1.1.3 | Flood Awareness Increased at National Level |  |  | X |  |  |  | X |  |  |  | X |  |  |
| 1.1.4 | Update of the National Disaster Preparedness Plan Initiated |  | X |  |  |  |  | X |  |  |  | X |  |  |
| 1.1.5 | Damage Assessment and Needs Analysis System Established |  |  | X |  |  |  | X |  |  |  | X |  |  |
| 1.2.1 | Disaster Preparedness Plans Developed / Response Preparedness Strengthened |  |  | X |  |  |  | X |  |  |  | X |  |  |
| 1.2.2 | Emergency Communications System Enhanced |  |  |  | X |  |  |  | X |  |  |  | X |  |
| 1.2.3 | Targeted Flood Awareness Campaign Expanded at Community Levels |  |  | X |  |  |  | X |  |  |  | X |  |  |
| 1.2.4 | Search and Rescue Capacity Strengthened |  |  | X |  |  |  | X |  |  |  | X |  |  |
| 1.3.1 | Emergency Shelters Meet Minimum Acceptable Standards |  |  | X |  |  |  | X |  |  |  | X |  |  |
| 1.3.2 | Relief Supplies Management Capacity Strengthened |  |  | X |  |  |  | X |  |  |  | X |  |  |
| 1.3.3 | Mass Casualty Plans Developed in Selected Vulnerable Communities |  |  | X |  |  |  | X |  |  |  | X |  |  |
| Activity | Description |  | Achieved |  |  |  | Quality |  |  |  | Appropriate |  |  |  |
|  | Output 2. Strengthened Disaster Risk Reduction Capacity |  | H | M | L |  | H | M | L |  | H | M | L |  |
| 2.1.1 | National DR Management Co-ordination Platform in Place |  |  | X |  |  |  | X |  |  |  | X |  |  |
| 2.1.2 | DR Management Policy & Disaster Risk Management Act Drafted |  | X |  |  |  |  | X |  |  |  | X |  |  |
| 2.1.3 | Disaster Risk Assessment Conducted at National Level |  |  | X |  |  |  | X |  |  |  | X |  |  |
| 2.1.4 | Integrated Disaster Risk Management Strategy Developed |  | X |  |  |  |  | X |  |  |  | X |  |  |

Annex 6. 	Evaluation Matrix - Project Inception Report, 5 February 2014

| Evaluation Criteria | Key Question | Sub-questions | Data Sources | Data Collection Method | Indicator / Success Standards For Question / Criteria | Methods of Data Analysis |
| --- | --- | --- | --- | --- | --- | --- |
| Relevance | Are the project partnership strategies appropriate | - Were the projects partnership strategies relevant to the project - To what extent did the project support the objectives of UNDP in Guyana - How does the project support the objectives of CDC - Are the project outcomes able to build capacity - Are the project outcomes timely, appropriate to country needs - Is the project relevant to Guyana’s development objectives | CDC UNDP Interviewees Project Planning and Implementation Documents Interviews with Beneficiaries Interviews with stakeholders | Interview Notes Annual Reports Internet Search Project Reports Questionnaires | Comparison of project activities against project objectives shows relevance UNDP objective of strengthened disaster risk capacity is supported by activities of project UNDP objective of DRM response supported by plans / activities of the project Project supports the increased capacity of CDC through training at CDC Project supports strategic plans and management capacity Project plans and is implementing education / training in all regions of Guyana Project recognizes that logistics of regions requires flow down of capacity / responsibility Project is addressing the mitigation of flood and drought risk at local beneficiary level Project to reduce flooding /drought impacts, allowing future development Project to reduce flooding /drought impacts, allowing future development plans /training to determine whether applicable to human caused disaster risks Review of plans and training indicates that CC has been considered Review of partners and involvement strategies are relevant to project Comparison of project outcome status and coherence with country needs indicates relevance Project outcomes for training given, management skills enhanced The initial part of the project developed capacity in disaster response and understanding The second part of the project developed plans for disaster mitigation and adaptation | Document Analysis Analysis - of notes from beneficiary interviews (review of reports / documents referenced by stakeholders; interpretation of comments, data, and opinions given by beneficiaries) Analysis of data and opinions obtained during Interviews with Stakeholders (review of reports / documents referenced by stakeholders; interpretation of comments, data, and opinions given by Stakeholders) |
| Evaluation Criteria | Key Question | Sub-questions | Data Sources | Data Collection Method | Indicator / Success Standards For Question / Criteria | Methods of Data Analysis |
| Effectiveness | Were the planned outputs achieved or are they on track to be achieved | - What factors contributed to achieving or not achieving the stated outputs - Is the project effective in achieving its planned outcomes - Were the projects partnership strategies effective in achieving the project objectives - Did the project stakeholders participate in the project design - Are the project stakeholders going to participate in the project implementation - Are the project activities designed to achieve the project outcomes - Are the project risks being managed effectively - How could the project have been more effective in achieving its results - Are the future directions for the project effective in achieving more capacity in disaster response - Are the future directions for the project effective in achieving more capacity in risk reduction and adaptation - Are the future actions timely in achieving the desired outcomes - Are the professionals and staff on the project well qualified to manage and implement the project - How can the project improve coordination among key stakeholders in planning for natural disasters - To what extent did the project contribute to building national capacity to provide strategic leadership to disaster risk management - To what extent did the project contribute to building regional / local DRM capacity - To what extent has the project improved CDC’s capacity to provide respond to major floods and drought - To what extent has the project improved regional and local capacity to provide respond to major floods and drought | CDC UNDP Interviewees Project Planning and Implementation Documents CDC UNDP Interviewees Project Planning and Implementation Documents | Interview Notes Annual Reports Internet Search Project Reports Questionnaires | Evidence has been provided to show that planned outputs have been achieved Under the current plan, the outputs have been achieved The project outcomes have been achieved roughly on project schedule and budget Partnerships were established that enabled the project outputs to be achieved Evidence from CDC indicates that the right partnerships were selected for success Records exist of stakeholder participation in project design Comments indicate that there was some non-participation, during interviews The stakeholders are currently involved in the implementation phases The future plans of CDC indicate that stakeholders will be involved in future implementation Stakeholder and CDC activities are directly tied to an outcome achievement The project reports indicate that project risks were addressed in a timely manner There is awareness on the part of management regarding risks Notation of unexpected delays in project implementation Notation of adaptation measures that had to be taken on the project Current CDC project plans indicate continued and upgraded training Current CDC project strategies indicate acquisition of updated technologies Current CDC project plans have a focus on risk reduction and adaptation There is noted urgency by CDC in getting risk reduction and adaptation to local levels Interviews with CDC and review of qualifications and experience indicate well qualified staff A central communications facility and SOP has been developed There is legislation in process (the Disaster ACT) to establish disaster risk as a national priority Annual and periodic reports indicate that national ministry and department leaders been involved as stakeholders The training and education programme of CDC is being conducted at regional and local levels Project documents and future plans reflect increased CDC capacity Staffing plans are being developed by CDC, for increased staff assigned to the disaster risk area | Document Analysis Analysis - of notes from beneficiary interviews (review of reports / documents referenced by stakeholders; interpretation of comments, data, and opinions given by beneficiaries) Analysis of data and opinions obtained during Interviews with Stakeholders (review of reports / documents referenced by stakeholders; interpretation of comments, data, and opinions given by Stakeholders |
| Evaluation Criteria | Key Question | Sub-questions | Data Sources | Data Collection Method | Indicator / Success Standards For Question / Criteria | Methods of Data Analysis |
| Efficiency | How efficiently is the project being implemented | - Was adaptive management used or needed to ensure efficient resource use when personnel left the project - Was progress reporting accurate and timely - Is the project support channeled in an efficient way - Are the partnership strategies appropriate - Are the partnership arrangements for the project efficient - Have the operations of the project performed against the objectives efficiently - Were financial resources used efficiently | CDC UNDP Interviewees Project Planning and Implementation Documents | Interview Notes Annual Reports Internet Search Project Reports Questionnaires | Discussion with CDC and UNDP indicates that adaptive management was used during personnel changes and when project direction was needed Discussion with CDC and UNDP indicates that Project planning and support was done in an efficient manner Attainment of objectives indicates that the operations of the project were efficient | Document Analysis Analysis - of notes from beneficiary interviews (review of reports / documents referenced by stakeholders; interpretation of comments, data, and opinions given by beneficiaries) Analysis of data and opinions obtained during Interviews with Stakeholders (review of reports / documents referenced by stakeholders; interpretation of comments, data, and opinions given by Stakeholders |
|  | What progress has been made towards the outcomes stated in the project document | - Did the project mainstream gender, disadvantaged and disabled issues and groups into the project - Are the future directions for the project efficiently planned - Have the project resources been used in the best possible way - Will the project utilize local resources efficiently | CDC UNDP Interviewees Project Planning and Implementation Documents | Interview Notes Annual Reports Internet Search Project Reports Questionnaires | Annual reports and discussion with interviewees and regional volunteers indicates that gender and other disadvantaged issues were mainstreamed Discussion with CDC verifies that future directions of the programme are being efficiently planned CDC verifies that local resources are currently and in the future will be used. CDC review indicates that their limited disaster risk resources have been used efficiently | Document Analysis Analysis - of notes from beneficiary interviews (review of reports / documents referenced by stakeholders; interpretation of comments, data, and opinions given by beneficiaries) Analysis of data and opinions obtained during Interviews with Stakeholders (review of reports / documents referenced by stakeholders; interpretation of comments, data, and opinions given by Stakeholders |
| Evaluation Criteria | Key Question | Sub-questions | Data Sources | Data Collection Method | Indicator / Success Standards For Question / Criteria | Methods of Data Analysis |
| Coherence | What factors have contributed to achieving or not achieving the intended outputs | - Is actual project implementation coherent with project design - Were the objectives and activities consistent with those in the project document and subsequent plans - Were the cross cutting issues treated coherently - Were clear disaster risk reduction principles utilized in the programme | CDC UNDP Interviewees Project Planning and Implementation Documents | Interview Notes Annual Reports Internet Search Project Reports Questionnaires | Objectives been achieved with stable staffing and limited consultants There have there been no significant overruns on project budget Examples of adaptive management noted by UNDP or CDC Progress reporting is accurate and timely Project annual reports submitted in a timely manner Project reports and interviews document mainstreaming of these groups Discussion indicates that partners were selected for areas of their expertise Records and interviews indicate that partners acted in a timely and professional manner Review of future directions indicate effective continuation of the project long term goals In disaster events or simulations, the system operation worked smoothly A limited number of tasks or activities had to be redone The quality of the products has been to professional standards The budget and project results been completed on budget or near budget The project has made an extra effort to utilize local resources efficiently. | Document Analysis Analysis - of notes from beneficiary interviews (review of reports / documents referenced by stakeholders; interpretation of comments, data, and opinions given by beneficiaries) Analysis of data and opinions obtained during Interviews with Stakeholders (review of reports / documents referenced by stakeholders; interpretation of comments, data, and opinions given by Stakeholders |
|  | To what extent have project outputs contributed to achieving UNDP Country programme goals | - Were clear disaster risk management principles utilized in the programme - Are the links to other programmes and initiatives coherent - Are the project activities compatible with the principles of integrated project management | CDC UNDP Interviewees Project Planning and Implementation Documents | Interview Notes Annual Reports Internet Search Project Reports Questionnaires | The project documents clearly indicate that disaster risk principles were considered The arrangements for links to other programmes have been identified and implemented Project reports and plans contain evidence that there is integrated project management | Document Analysis Analysis - of notes from beneficiary interviews (review of reports / documents referenced by stakeholders; interpretation of comments, data, and opinions given by beneficiaries) Analysis of data and opinions obtained during Interviews with Stakeholders (review of reports / documents referenced by stakeholders; interpretation of comments, data, and opinions given by Stakeholders |
| Sustainability | What adjustments were needed to the projects Results and Resources framework to achieve planned outputs | - Were the law making measures taken adequate to ensure sustainability - What is the level of political commitment to the project and its outcomes - Are the recurrent costs after project completion sustainable | CDC UNDP Interviewees Project Planning and Implementation Documents | Interview Notes Annual Reports Internet Search Project Reports Questionnaires | The actual project implementation is coherent with project design Clear disaster risk reduction principles were utilized in the plans and future directions noted in the project reports Clear disaster risk management principles were utilized in the programme The objectives and activities were consistent The cross cutting issues were treated coherently The links to other programmes and initiatives are coherent The project activities are compatible with the principles of integrated project management | Document Analysis Analysis - of notes from beneficiary interviews (review of reports / documents referenced by stakeholders; interpretation of comments, data, and opinions given by beneficiaries) Analysis of data and opinions obtained during Interviews with Stakeholders (review of reports / documents referenced by stakeholders; interpretation of comments, data, and opinions given by Stakeholders |
| Sustainability | What adjustments were needed to the projects implementation approach to achieve planned outputs | - Have stakeholders in Guyana been involved in the design and implementation of the UNDP project - Has the impact of the UNDP project been clearly communicated to all governmental and institutional stakeholders in Guyana - Has the impact of the UNDP project been clearly understood by all governmental and institutional stakeholders in Guyana - Is the capacity in place at the national and local levels adequate to ensure sustainability of the results achieved to date | CDC UNDP Interviewees Project Planning and Implementation Documents | Interview Notes Annual Reports Internet Search Project Reports Questionnaires | Interview discussion with stakeholders in Guyana indicates that they have been involved in the design and implementation of the UNDP project The process of stakeholder engagement is robust within the Clean Development Mechanism – UNDP programme in Guyana CDC is seeking opportunities to develop Public Private Partnerships for flood management Discussion with interviewees indicates that they clearly understand the impact of the UNDP project in Guyana Stakeholders indicate in interviews that the impact of the UNDP project has been clearly communicated to all governmental and institutional stakeholders in Guyana Stakeholders and CDC indicate in interviews that the capacity in place at the national and local levels is adequate to ensure sustainability of the results achieved to date Were the law making measures taken adequate to ensure sustainability CDC indicates that the recurrent costs after project completion will maintain the programme sustainable Stakeholders and CDC indicate in interviews that the level of political commitment to the project and its outcomes is sufficient |  |
| Sustainability | What adjustments were needed to the projects arrangements to achieve planned outputs | - Is the process of stakeholder engagement robust within the Clean Development Mechanism – UNDP programme in Guyana - What are the opportunities to develop Public Private Partnerships for flood management - Are the recurrent costs after project completion sustainable - What is the degree of local ownership of initiatives | CDC UNDP Interviewees Project Planning and Implementation Documents | Interview Notes Annual Reports Internet Search Project Reports Questionnaires | CDC and National Police and Defence Force indicate that the capacity in place at the national and local levels is adequate to ensure sustainability of the results achieved to data CDC indicates that if the Disaster Act is passed by the government, the law making measures taken will be adequate to ensure sustainability CDC statement that the recurrent costs after project completion will ensure sustainability, if current and future budgets are maintained CDC and other ministry interviewees state that the level of political commitment to the project and its outcomes is high, as disasters are political nightmares Limited number of Interviews with regional representatives indicate that there is currently a moderate to high degree of local ownership of initiatives | Document Analysis Analysis - of notes from beneficiary interviews (review of reports / documents referenced by stakeholders; interpretation of comments, data, and opinions given by beneficiaries) Analysis of data and opinions obtained during Interviews with Stakeholders (review of reports / documents referenced by stakeholders; interpretation of comments, data, and opinions given by Stakeholders |

# Hans M. Ewoldsen

ewoldsenh@aol.com					                 (425) 444 5422

# Summary of Qualifications

Thirty years of increasing responsibility in leading, marketing, and managing consulting operations and major projects and programmes.  Expertise in governmental, energy and industrial sectors.  Strong business and programme management skills developed through domestic and international assignments.

Senior project / programme management experience on projects related to energy, water supply and resource development sectors.  Management of geologic, environmental and geotechnical responsibilities for projects / programmes.  Provision of leadership in effective completion of project, avoidance of project risk issues and delays, and management of interfaces with local and regional interests.

## Key Attributes

- Successful development of new business initiatives

- Continuing technical participation on projects

- Initiated three international and two domestic startups

- Leadership of groups of more than 150 professionals

- Project experience in over forty countries

- Remote area operations experience

Professional Experience

Hans M. Ewoldsen, Ph.D., P.E., R.G., Consulting Engineer	2010 – present

Consultant

Consultant to UNDP in environment, disaster risk and solid waste management.  Work on water projects, development of grant applications to the European Union for UNDP Azerbaijan.  Various geotechnical and engineering geologic projects in the Western United States.

Hydrodec North America LLC						2007 - 2009

Manager, Special Projects

Manger of Special Projects, including front end geotechnical and environmental site selection and permitting for the construction of specialized refining plants in Canton, OH and Laurel, MS.  Plants will provide refining of used electrical transformer oil, to original specification and return to the electrical transformer industry.

Hans M. Ewoldsen, P.E., Consulting Engineer		          		 2005 - 2006

Consultant

Consultant to major engineering corporations, international sustainable project development programme, and multinational oil & gas company.  Focus on enterprise risk and provision of project / programme development in water resources and energy.

Parsons Water & Infrastructure					               2003 – 2005

Consultant & Project Development

Provision of consulting services in hydropower development, water and wastewater projects and general infrastructure development.

AMEC Earth & Environmental	                                               		  1997 – 2003

Vice President

Regional Manager for multi-discipline consulting operations of a major international engineering company in Pacific Northwest.  Responsible for overall management of three offices completing commercial assignments.  Increased staffing from 65 to 110 over two year period.  Responsible for P&L on $ 12 million per year in revenues.

# Geocentric				                                                                1996- 1997

Managing Director

Sole proprietor of consulting practice focused on provision of geotechnical, rock mechanics and geologic services to the mining industry.  Projects developed in Nevada, California, Washington and Chile.

### Camp Dresser & McKee Federal Programmes		                           1993 – 1996

Sr. Vice President

Programme and operations manager for multi-year environmental support to DOE M&O contractor.  Responsible for overall management of three offices carrying out work at five DOE facilities.  Increased staffing from 22 to 104 in 12 month period.

# Camp Dresser & McKee International		                                      1989 – 1993

Sr. Vice President

Established and managed joint venture environmental consulting firm in The Hague, The Netherlands, directed at the North European industrial sector.  Initiated joint venture agreements leading to establishment of environmental firms in Germany and England.

# Woodward Clyde Consultants			                      		 1970 – 1989

Principal, Vice President

Initiated Pacific Northwest practice for firm, led transition from federal project focus to multi-disciplinary staff serving governmental and private sectors.

Established and managed firm’s participation in four year nationwide EPA hazardous waste programme.  Selected and supervised over 20 project managers, monitoring schedule and multiple budgets of up to $ 2,000,000 each.  Achieved superior rating in two EPA regions

Initiated and managed firm’s entry into high-level nuclear waste isolation programme.  Managed 70 engineers and scientists in completing work on six federal contracts with values between one and fifty million dollars.  Increased annual revenues from $ 500,000 to $ 8,000,000.  Led firms proposal contribution on team that won Yucca Mountain Nuclear Waste Repository geologic and engineering contract ( 600 million value ).

Opened and managed offices in England and Iran.  Established operations, financial and business relationships within host countries.  Multiple projects in Middle East in power and electrical transmission sector. Provision of geotechnical and engineering geologic services for a wide variety of geologic conditions.

## Principal Areas of Expertise

Principal areas of expertise are:

Geotechnical Engineering	:	dams, infrastructure, buildings

Engineering Geology		:	specialize in underground openings

Environmental			:	nuclear and hazardous wastes, climate change

## Education

Ph.D., Geological Engineering

M.S., Geotechnical Engineering

B.S., Civil Engineering

B.A., Mining Geology

University of California, Berkeley

## Professional Registrations

Registered Civil Engineer:      California, Washington

Registered Geologist and Engineering Geologist:      California

Geographic Experience

Projects have been completed in the following countries. In most cases multiple projects are represented.

North America

United States

Canada

Mexico

Nicaragua

Costa Rica

South America

Ecuador

Colombia

Venezuela

Chile

Argentina

Peru

Aruba

Puerto Rico

Asia

Australia

Brunei

China

Taiwan

Japan

Marshall Islands

Myanmar

Mongolia

New Zealand

Nepal

India					Pakistan

Middle East / Eurasia

Iran

Iraq

Oman

Saudi Arabia

Azerbaijan

Kazakhstan

Turkey

Africa

Egypt

Morocco

Algeria

Ethiopia

Lesotho

Mauritius

South Africa

Nigeria

Europe

England

Denmark

France

Germany

Holland

Czechoslovakia

Switzerland

Spain					Italy

Greece