|  |  | GEF |
| --- | --- | --- |
| United Nations Development Programme | Fishery Agency of Russian Federation | Global Environment Facility |

- PROJECT

UNDP/GEF 00014641

Conservation and Sustainable Use of Wild Salmonid Biological Diversity in Russia’s Kamchatka Peninsula

Mid-Term Evaluation Report:  Final Copy

November 28, 2006

Table of Contents

## Executive Summary	1

## Introduction	3

## Part One:  The Project and Its Development Context	6

## Part Two:  Findings and Conclusions	12

## Part Three:  Lessons Learned and Recommendations

1.	Research and Decision-Making	18

2.	Hatchery Management	20

3.	Law and Policy	21

4.	Sport Angling	22

5.	Economic Research	24

6.	Poaching and Over-harvest	24

7.	Poaching of Non-Commercial Species	25

8.	Commercial Harvest	26

9.	Protected Area Establishment and Management	27

10.	Mitigation of Habitat Degradation	27

11.	Education and Public Awareness	28

12. 	Community Development and Alternative Livelihoods	29

13,	Sustainable Financing	30

14.	Project Management and Implementation	31

Annexes

Summary of Project Activity:  Project Progress Matrix	35

Project Reports	61

Project Steering Committee	64

Itinerary and List of Persons Interviewed	65

Terms of Reference	68

## Executive Summary

Brief description of the project

This project is designed to improve the conservation and sustainable use of salmonid diversity in four river systems on Russia’s Kamchatka Peninsula. Upon successful completion of the project, stakeholders will devise innovative and adaptive ecosystem management practices to mitigate and prevent threats to river ecosystem integrity and apply new partnerships, conservation tools, information, and sustainable livelihoods to conserve salmonid diversity maintained therein.

Context and purpose of the evaluation

The purposes of this mid-term evaluation are:

Monitor and evaluate results and impacts;

Provide a basis for decision making on necessary amendments and improvements;

Promote accountability for resource use; and

Document, provide feedback on, and disseminate lessons learned.

A “good faith effort” was made by all parties to present the details of the project accurately.  However, this was an unrealistically rapid assessment of an unusually complex project.  As a result, the evaluation certainly contains false assumptions, errors and omissions.  This is quite serious in that the conclusions of the evaluation may have significant political and professional implications for individuals and agencies.  It will hopefully be understood that the general assessment is positive and any criticisms are not intended to be specific to any individual or organization.

Recommendations are provided as suggestions for consideration only and should not necessarily be perceived as pre-requisites for continued funding.  Many recommendations may be unrealistic in light of remaining project financing and time.  In these cases, consideration should be given to adopting these recommendations for implementing Phase II of the project.

General Conclusions

The overall rating of this project is “satisfactory”.

The project is in its first of two intended funding phases. The current “Phase I” is to last approximately forty-nine (49) months.  Approximately thirty-one (31) months have passed and eighteen (18) months remain.

The project seems to be “on track”.  The project is making substantial progress towards overall objectives. The project continues to accurately address threats/root causes identified during project development.  The project is realizing major achievements, with many activities successfully launched and preparations for others seemingly well underway.  Stakeholder support remains strong.  Project oversight and management is positive.  The implementation staff is professional and committed.  Budget allocations are generally in-line with the project’s logical framework.  Transparency and reporting are generally acceptable but should be improved in the future with expanded Project Steering Committee involvement.

Although the project has successfully achieved many benchmarks and completed substantial preparatory work for others, it will be a major challenge to finalize all outstanding tasks in the remaining time period.  The project is working under an overly ambitious timeframe and faced un-expected delays primarily due to significant modification of Russia’s fisheries administration.  Although the project seems to have adapted quite well to this shifting management environment, numerous critical activities have not been fully realized and/or implemented.

If the project’s Phase I is to be successful in meeting it’s objective of conserving species diversity and effectively “mainstreaming” conservation into the productive sector, the project will require from Government and its implementation partners sustained support and specific pro-active measures. The completion of most outstanding tasks requires significant Government action.  Perhaps most important of all is the need for the Government to continue and expand its laudable efforts to strengthen and implement the fundamental enabling environment required for the achievement of Phase I project results.

The project has done an admirable job of setting the stage under challenging circumstances.  Now there is a strong need to see the Government and other implementation partners use the tools provided through the project to seriously address issues of over-exploitation and habitat conservation, including safeguarding of important habitats in each of the four pilot sites, reduction of poaching threats, and improved management of commercial fishing.  There is a need to see how the results of scientific research and other project activities will be applied in a systematic way to facilitate salmonid management that is re-oriented towards greater concern for species diversity, benefits from transparent decision-making and the participation of an informed public, and maintains and creates local economic opportunities for salmonid-based, sustainable livelihoods.

In the near-term, a more comprehensive, time-constrained strategy and work-plan for the finalization of all Phase I project activities should be completed with clear reference to the project’s logical framework and lessons learned to date.  To enhance cohesion and coordination amongst diverse stakeholders, this effort should be coordinated with and approved by the Project Steering Committee to make certain all stakeholders are fully aware of project activity and firmly resolved and accountable to addressing and supporting the critical tasks remaining. The Project Steering Committee should review the project achievements detailed in this report (including the annex summarizing activity) and begin laying the groundwork to prepare the Phase II proposal.  In addition, consideration should be given to expanding the current Phase 1 period to cover an additional eighteen to twenty-four months using the existing budget.  This would provide time to address outstanding tasks and provide a “funding bridge” between Phase 1 and Phase II.

## Introduction

Project Phase One and Phase Two

This project is designed for implementation in two phases, each with its own distinct achievements. The current implementation period is Phase I. If endorsed by an independent results-based evaluation, GEF funding will be requested to support the incremental costs of the second and final phase (Phase II).

According to the Project Document, Phase I is intended to be both preparatory and implementation oriented.  At the end of Phase I, stakeholders should be enabled to make the financial and policy commitments necessary, protect crucial salmonid habitat by establishing protected areas and participatory management regimes, construct a diversity information baseline by conducting field surveys, lay the foundation for long-term financing of salmonid diversity conservation, pilot diversity-friendly commercial fishing practices and sport-fishing ecotourism, forge new partnerships among local and international stakeholders, and strengthen the capacity of civil society institutions.  Phase II would consolidate the achievements of Phase I.

Project background

The objective of this project is the conservation and sustainable use of salmonid biological diversity in four river systems on Russia’s Kamchatka Peninsula.  Upon successful completion, stakeholders will devise innovative and adaptive ecosystem management practices to mitigate and prevent threats to river ecosystem integrity and apply new partnerships, conservation tools, information, and sustainable livelihoods to conserve salmonid diversity maintained therein.

The project aims to conserve and sustainably utilize salmonid biological diversity in four river systems on Russia’s Kamchatka Peninsula. The salmonid fish in these river systems still exhibit the full range of genetic and life history diversity derived in part from the different physical and bio-chemical characteristics of each river.   The innovative conservation approaches applied to these four “representative” river systems should serve as models for sustainable replication throughout the peninsula as well as examples for the conservation of salmonids globally.

The Kamchatka peninsula extends 1,500 kilometers south from Russia’s Siberian mainland, separating the Sea of Okhotsk from the North Pacific Ocean. The Kamchatka Peninsula harbors the largest grouping of healthy salmon rivers along the Pacific Rim.  Designated a World Wildlife Fund “Global 200” ecoregion, the peninsula is a global priority for the long-term conservation of wild anadromous salmon and steelhead as well as riverine trout and char.

An estimated one fifth of the world’s total salmon population spawn in Kamchatka Rivers. The peninsula is home to one of the last remaining assemblages of “wild” salmonids. At least eleven species are known to occur in these river systems, more than any other place in the world, with remarkably high diversity at the species, intra-species (stock), and genetic levels.

Roughly 60% of the Russian Federation’s fishery resources occur in the waters around Kamchatka, including walleye pollack, crab, cod, herring, halibut and salmonids.  Commercial fishing is an economic mainstay in the peninsula and salmonid fish comprise a significant proportion of commercial catches. Five of the eleven salmonid species are commercially fished and six are non-commercial species, including the endangered “steelhead” sea-run rainbow trout. In the Sopochnaya and Utkholok site areas salmon support over 2,200 indigenous Itelmen, Koryak and Even people.  In the project’s Bolshaya site area salmon are important to the livelihoods of 9,000 people who have remained in the wake of the collapsed agricultural and fishery economy.

GEF support is intended to secure the global benefits of conserving salmonid diversity of actual and potential value for food and aquaculture.  Russian and international partner co-financing provides the crucial foundation for GEF’s incremental investment by enhancing the sustainability of the existing economic development baseline.

The global benefits of this project are enhanced by a significant number of species and ecosystems that will gain protection as a result of salmon conservation efforts. Salmon and the nutrients they bring to freshwater and terrestrial ecosystems are the biological cornerstone of aquatic and terrestrial biodiversity in Kamchatka and essential to the ecological integrity of aquatic ecosystems. Large vertebrates that depend on salmon in Kamchatka include the world’s largest population of brown bears (5,000-10,000 individuals), over 50% of the global population of the world's largest eagle, Steller sea eagle, and 1,800 Steller sea lions, a species that has declined 95% worldwide in the last 20 years.  Diversity of salmonids on both inter and intra-river levels plays an important contributory role to ecological processes with the life cycles of various species and races occurring at different and complimentary times and locations, providing spatial and temporal variations in food supplies critical to maintaining healthy populations of hosts of dependent species, including large predators.  Clearly, efforts to protect Kamchatka’s biodiversity must include measures to ensure the continued diversity of salmonid fish and integrity of their freshwater and marine habitats outside of existing protected areas.  Any sustainable, long-term biodiversity conservation approach for Kamchatka must seek to maintain the interactive ecological linkages among healthy salmon and steelhead stocks, natural river ecosystems and human communities.

Significant and strategic project co-financing is provided by a variety of sources, including the Government of Russia and the Wild Salmon Center.

Purpose of the evaluation

The evaluation provides a comprehensive, overall assessment of the project. The evaluation is an opportunity for project stakeholders to discuss and critically assess administrative and technical strategies, issues and constraints. The evaluation assesses progress in addressing the baseline, threats, and root causes.  The evaluation identifies any difficulties in project implementation and their causes.  The evaluation provides general and specific recommendations to improve the project’s potential to achieve expected outcomes and meet objectives within the timeframe.

Key issues addressed

As a mid-term evaluation, the key issues addressed were:

- Is this project “on-track” to achieving what it set out to accomplish?

- What improvements should be considered to increase the likelihood of success?

Project performance was measured based on the quantitative and qualitative indicators.  The evaluation considered issues related to management and substantive/technical implementation, including project delivery, implementation, and finances.  Particular attention was given to the strategic approaches taken relevant to achievement of project objectives.

The outputs of the evaluation and how will they be used

Both the assessment process and resulting report should be considered as outputs of this evaluation.

The mid-term evaluation process provided all stakeholders with an opportunity step back from their daily implementation efforts to reflect upon and discuss the efficacy of project activity to date.  The resulting report will ideally assist the project implementation team to:  (1) assess and consider project success at achieving anticipated outcomes given current benchmarks and planned activities; and, (2) consider possible improvements/approaches to increase the likelihood of success.

Findings of this review will be incorporated as recommendations for enhanced implementation of the current project phase in the future years as well as for the design of the subsequent project phases.  Effective action to rectify any identified issues hindering implementation should be a requirement prior to determining whether implementation should proceed.

Methodology of the evaluation

An independent consultant was hired to conduct this review. The consultant has extensive experience with both the design and implementation of GEF projects.  He has “hands-on” knowledge of several relevant topic areas, including; salmonid conservation and production (commercial fisheries and sustainable sport fishing/eco-tourism), community-based natural resource management, targeted research, protected area design and management, and conservation law/policy.

Prior to field travel, the consultant was provided with all project documentation available in English, conducted pre-trip interviews with several stakeholders/partners and developed a strategic approach for project evaluation.

The consultant visited Russia for nearly two weeks, traveling to both Moscow and Kamchatka. (Please see the attached itinerary).  While in Russia, the consultant conducted comprehensive interviews with all primary project stakeholders.  These interviews were approached as an opportunity to study project activity/results and stimulate reflective, constructive and candid dialog with various stakeholders regarding project progress and direction.  The consultant visited activity locations such as classrooms, the interpretative center, and a hatchery.  Due to early spring scheduling, the consultant was not able to physically visit pilot sites to review “on-the-ground” activities.  Although perhaps not debilitating to the mid-term assessment, future evaluations should certainly include field site visits. These visits should include opportunities to hold discussions with residents – particularly commercial fishing operators, “poachers”, anti-poaching field staff, field researchers, and indigenous communities.

After returning from Russia, the consultant spent a significant amount of time carefully comparing all project documentation and results frameworks with field trip findings.  The consultant developed a comprehensive, condensed matrix summarizing all project expectations and submitted this to the project management unit for clarification.  (Please see the summary included within the annex).  The consultant conducted post-trip interviews with various stakeholders and, finally, compiled this brief summary report.

Of Note:  The project implementation team should be congratulated for the incredibly efficient and professional organizational support provided during this evaluation.

## Part One:  The Project and Its Development Context

1.1	Project start, implementation status, and duration

The project was officially launched on September 1, 2003.  Phase One is currently scheduled to close on August 31, 2007.  The evaluation took place in April 2006 during the project’s thirty-first (31) month with approximately eighteen (18) months of project time remaining.

1.2	Problems that the project seeks to address

The project seeks to address the following threats to Kamchatka’s wild salmon diversity:

- 1. 	Production-oriented management of salmonid fishery and genetic erosion

- 2. 	Poaching

- 3. 	Aquatic ecosystem degradation

The threats are primarily represented by management systems that do not adequately incorporate diversity conservation principles; illegal harvest by licensed commercial operators and un-licensed salmon roe collectors; and, habitat degradation caused by un-mitigated mining, road, pipeline and hydroelectric development.

The project is designed to effectively mitigate these threats and their root causes in the four river sites: Bolshaya Basin, Kol/Kekhta, Sopochnaya River, and Utkholok-Kvachina.  To enhance the probability of broad replication, these sites were chosen as representatives of various challenges.

This is considered an “early intervention” project.  Although Kamchatka’s salmonid diversity remains intact in nearly all of its river systems, threats to salmonid biodiversity have emerged during the transition to a market economy and under a baseline scenario will continue to grow. The danger of the international community not acting now is that this globally significant biological diversity important to food and aquaculture will be lost in the face of these growing threats.

1.3	Immediate and development objectives of the project

The Overall Objective of the project is the sustained conservation of Kamchatka’s salmonid genetic and life history diversity and the maintenance of river ecosystem integrity.

The Development Objective is the conservation and sustainable use of salmonid biological diversity in four river systems on Russia’s Kamchatka Peninsula.

1.4	Main Partners and Stakeholders

- Government of Russia

- Global Environment Facility

- Russian State Fisheries Committee

- Kamchatka Oblast/Koryak Okrug

- Moscow State University

- Wild Salmon Center

- Indigenous communities

- U.S. National Science Foundation/Flathead Biological Station

There are five Government bodies directly responsible for fisheries management in Kamchatka.

- Sevvostrybvod:  Allocates fishing sites, manages hatcheries, oversees sport fishing, determines fishing equipment types and monitoring.

- Kamchatka Department for Fisheries:  KO and KAO: Allocates quotas – commercial, sport, indigenous, etc. – based upon approval by other agencies.

- Russian Federal Fishery Agency: Ministry of Agriculture.  Reviews fishery quota.  Generates regulations.

- K-NIRO.  Federally funded fisheries research institute responsible for basic research and setting initial quota numbers.

- Rosselkhoznadzor: Fisheries Supervisory Body:  Ministry of Agriculture. Responsible for enforcement through both national and local representatives.

1.5	Results expected

Upon successful completion of the project, stakeholders will devise innovative and adaptive ecosystem management practices to mitigate and prevent threats to river ecosystem integrity and apply new partnerships, conservation tools, information, and sustainable livelihoods to conserve salmonid diversity maintained therein.  Government agencies and local communities and indigenous peoples will be conserving salmonid diversity in the project’s four river sites by applying a new diversity-oriented approach, conservation tools, and sustainable livelihoods.  The project will use an adaptive management approach that is designed to respond to emergent threats and orient conservation activities to threat mitigation.

Phase I of the project will:

Enable stakeholders to make the financial and policy commitments necessary,

Protect crucial salmonid habitat by establishing protected areas and participatory management regimes,

Construct a diversity information baseline by conducting field surveys,

Lay the foundation for long-term financing of salmonid diversity conservation,

Pilot diversity-friendly commercial fishing practices and sport-fishing ecotourism,

Forge new partnerships among local and international stakeholders, and

Strengthen the capacity of civil society institutions.

Phase II would consolidate the achievements of Phase I.  Equally important, during Phase II the long-term financing mechanism for salmonid conservation would be permanently established and funded primarily by non-GEF, partner financing.

1.6	Outcomes/Outputs/Indicators

This project has one of the most dizzying assortments of indicators ever encountered.  The “evaluation criteria” have changed at least three times in the life of the project.  These alterations are the result of several factors including time gaps between project formulation and start-up, project responses to emerging needs, and GEF requirements.  Certainly improvements to the logical framework and associated indicators are worthwhile and based upon learned adaptation. However, there are inherent dangers with frequent alteration of the project’s “success” criteria related to accountability, management, implementation success, stakeholder support, monitoring and evaluation.  Clearly there are lessons to be learned here for future GEF projects.

The project seems to have remained largely on-track despite these variances and the fluctuations seem to have settled upon a set of standards agreeable to the Steering Committee. The indicators are fairly relevant measurements of the conservation of salmonid diversity.  However, the current indicators – particularly the objective- level indicators - have been weakened over time.  Examples include:

- Fewer hectares of habitat protected than required in original documents (habitat conservation can be measured in ways other than the establishment of ‘protected’ areas);

- No indicators measuring the reduction of poaching activity;

- No indicators requiring adoption and implementation of specific conservation principles, only broad concepts; and,

- Few indicators requiring achievement of measurable impacts related to mainstreaming activity, public awareness, education, and/or the creation of incentives for conservation supportive behavior.

If the project intends to support an “ecosystem” approach to salmonid conservation, objective-level indicators might reflect measurements of ecosystem integrity such as health of salmon dependent species like bears, raptors, and certain plants.  Indicators should also reflect issues of habitat connectivity, on both inter- and intra-basin levels.  This should include conservation not only of spawning and rearing grounds but also of migratory routes throughout known ranges.  These are the areas where Kamchatka salmonids face real threats.  Habitat conservation should indicate not only that habitat is protected, but that the selected “conserved” habitat represents priority areas relevant to conservation of species diversity and that “successful protection” is measured according to specific criteria.  Not that the Kol is such a thing, but creating a “paper park” does not indicate successful conservation of habitat.  Indicators should also show that salmonid diversity is being secured at genetic levels. This is particularly germane when dealing with issues related to hatchery management, one of the project’s main concerns.  For instance, the indicator “salmonid diversity” may more accurately be stated as “presence” with other indicators of diversity being conserved including the mentioned; habitat, distribution, and abundance.   However, “presence” alone does not discern between hatchery and wild stocks.

All of these issues should be re-visited and scrutinized.

As noted later in this report, the linkages between indicators and strategic project planning/funded activities could be strengthened.

Outcome 4 currently focuses upon alternative livelihoods.  However, updated activities are correctly concerned with both alternative and sustainable livelihoods. This is important since the project is attempting to “mainstream” conservation practices into the sustainable use of salmonids.

The following was used as the basic framework for review.  For a detailed summary of project objectives and related indicators, please see the report’s annex.

Objective-level Indicators

| Description of Impact Indicators | Value in year 0 | Mid-term Target Value (2005) | End of Project Target Value (2007) |
| --- | --- | --- | --- |
| Indicator 1. Salmonid diversity | List of species recorded in all four river sites; | Very Good: All historical species present in river sites. | Very Good: All historical species present in river sites w/ more complete data set. |
| Indicator 2. Distribution: Adult or juvenile presence by stream segment. | Incomplete information on commercial species, absence of information on non-commercial species. | New information on commercial and non-commercial species. | Very good: Occupy 100% of historical range within each river system. More complete data on commercial and non-commercial species |
| Indicator 3. Number of hectares of salmonid habitat protected; | No specific protected areas for salmonids. | 1 PA created; 280,000 ha protected. | 1 PA established. Design of the 2nd PA is developed. Total # of hectares: 400,000 heсtares. |
| Indicator 4. Insect biomass and diversity | Incomplete information for Bolshaya river, absence of information on other river sites | List of insect species enlarged and biomass determined for three river sites | Very good: 66-100% of median biomass. Good: 40-66% of average. |
| Indicator 5. Abundance of salmon. | River basin escapement levels Bolshaya, Kohl, U-K. | Very Good (see footnote) Existing information incorporated into the common database | Very Good (see footnote). Information database is used by the decision makers. |
| Indicator 6. In-stream habitat a)Sediment transport; b) Road density in watershed; c) Spawning habitat (SH); Rearing habitat (RH). | a) These not defined for river sites at Year 0. b) These not defined for river sites at Year 0. c) Information on commercial species in-stream habitats exists. No information on non-commercial species in-stream habitats | a) Will be defined by mid-term. b) Will be defined by mid-term. c) More complete information on commercial and non-commercial species spawning habitats. Status of rearing habitats determined on model sites | a) Sediment transport: Very Good (fluctuates no more than 15% up or down each year). b) Road density in watershed: AR. c) SH 90-100% of historical figures; RH: 90-100% of historical figures. |

Output/Outcome Level Indicators

Output 1:

Salmonid fishery stewards apply new diversity conservation approach in river sites.

Outcome One:	Improved fishery management practices for salmonid diversity conservation purposes.

Indicator 1:	Diversity management principles and criteria are developed, proposed, and approved for 2 hatcheries in Bolshaya basin

Indicator 2:	Salmonid diversity and ecosystem health requirements incorporated into escapement goals for project river sites.

Indicator 3:	New public-private partnership for management of non-commercial fish species.

Indicator 4:	Russian fishery legislation incorporates salmonid diversity conservation principles.

Indicator 5:	Fisheries agencies manage project river sites based on systematized and up to dated information on biodiversity

Output 2:

Salmonid diversity and aquatic ecosystem integrity is maintained by applying a range of resource management and conservation tools in river sites.

Outcome Two:	River ecosystem integrity is conserved in four sites using a variety of conservation tools and approaches

Indicator 1:	Community partnerships demonstrated for river site management

Indicator 2:	New conservation tools applied in protected areas management.

Indicator 3:	Environmental mitigation plan for pipeline and best practices in environmental mitigation introduced to key stakeholders at workshop in PK, strengthening environmental mitigation of development activities in Kamchatka

Output 3:

Information shared widely, conservation constituency built and indigenous knowledge conserved.

Outcome Three	Implementation of educational programs, information sharing, preservation of indigenous peoples’ knowledge, and awareness raising build constituencies for salmon diversity conservation in four river sites

Indicator 1:	Level of support for salmonid conservation among school students and general public in Kamchatka.

Indicator 2:	Kamchatka Salmon Ecological Center and other interpretive displays operational.

Indicator 3: 	Salmonid diversity and ecology curricula developed and introduced throughout local school curriculum.

Indicator 4	Indigenous people begin to record knowledge and develop education programs

Output 4:

Alternative Livelihoods applied in river site areas

Outcome Four	Stakeholders successfully develop alternative livelihoods in river site areas

Indicator 1:	Local communities pursuing sustainable livelihood options based upon local salmon resources by end year 5.

Indicator 2	Local stakeholder capacity to develop alternative livelihoods being strengthened through access to micro-credit & business training.

Indicator 3:	Eco-tourism operating in at least one project site and involving local people in project site.

Indicator 4:	Sustainable use incentives and alternative livelihood programs target local population in project sites.

Output 5:

Salmonid Diversity Conservation Fund (SCDF) supports conservation in perpetuity.

Outcome Five	Sustainable financing for salmonid conservation

Indicator 1:	Salmonid Diversity Conservation Fund legally established by end of year 3

Indicator 2:	Commitments for Fund endowment.

## Part Two:  Findings and Conclusions

2.1	Project delivery

Progress

Progress towards the implementation of activities and achievement of project goals has been generally quite good.  The project is addressing the “threats” to salmonid diversity and is basically “on-track”.  However, the scope of this project relevant to the implementation timeframe is proving to be quite ambitious and there are real concerns about the project’s ability to successfully complete all deliverables in the short period remaining.

Salmon fishing makes up one of the largest sectors of Kamchatka’s economy.  The health, status, and availability of salmonids run to the very core of the region’s social and economic fabric. Almost every citizen of the region is somehow involved in some aspect of the salmon industry.  Sport fishing is an important cultural aspect.  Many residents, and in particular members of the indigenous communities, rely upon salmon for their subsistence.  Any proposals regarding “improving” the management of this resource must respectfully dance through a very complicated social and political landscape.  This takes time and consensus building; something the project seems to have done an outstanding job of addressing.

In addition, the project was faced with a major upheaval during 2005 when the Russian Government’s administration of salmonid management was completely altered by new legislation.  The changed management structure created new agencies and re-distributed responsibilities amongst existing agencies, creating a near hiatus for many project activities while waiting for the dust to settle.  To date, the project has done an outstanding job of adapting to these changes and building a very strong level of support on the national and regional level that proved resilient.  This is very impressive and the project team must be commended for their efforts in this regard.

As a result, this project has a significant amount left to accomplish.  The remaining activities are primary to measuring final project success at addressing the “threats/root causes” in a meaningful way and setting the stage for Phase II.

Major accomplishments to date include:

- Identifying and recruiting talented and dedicated project staff, including establishment of an apparently well functioning administration and management structure;

- Facilitating the establishment of Russia’s first Salmonid Protected Area;

- Creating solid links, cooperation and opportunities for learning and exchange between project stakeholders, collaborators and co-funders through formal mechanisms (the Project Steering Committee) and informal mechanisms, including between UNDP, the Government of Russia, the Wild Salmon Center, and other projects such as UNDP/GEF “Demonstrating Sustainable Conservation of Biological Diversity in Four Protected Areas in Russia's Kamchatka Peninsula” project;

- Stimulating expansive thought amongst all stakeholders regarding improved approaches to salmonid management;

- Sponsoring numerous research and data management activities, including identification of possible methods to mitigate damage from proposed development, improving hatchery management, and understanding of salmonid and related ecosystem biology;

- Facilitating an improved policy framework, including assisting the passage of a new umbrella fisheries management law;

- Designing and implementing an outstanding public awareness and children’s education program;

- Creating very strong and innovative programs for maintaining and supporting indigenous culture;

- Identifying opportunities for improved livelihoods that support long-term salmonid conservation such as the Community Development Quota, reindeer husbandry, and sport fishing; and,

- Supporting anti-poaching efforts, including designing and equipping a very interesting anti-poaching data-base/alert system and establishing an effective “pilot” river keepers program.

Each of these achievements represents very positive and real progress towards removing barriers and addressing root causes.  Much of the activity to date has been ‘preparatory’.  This is understandable with the project just beginning Phase I of a presumed two-phase project. The project now faces the difficult challenges of more fully transitioning from preparation to implementation.

Major challenges remaining to be more fully addressed during Phase I include:

- Fully integrating scientific research/monitoring programs and species needs within productive sector decision-making to create real linkages between conservation, production, science and management, including “diversity friendly” fisheries and quota management;

- Determine and implement tangible management approaches for the first legally established protected area, including recording of lessons learned;

- Creation/management of additional “protected areas” reflecting creative, responsive, and holistic management approaches;

- Facilitating implementation of passed legislation, including adoption of several regulations, identifying “gaps” and capacity building needs, and improving synergy between the various management bodies;

- Piloting of model “on-the-ground” diversity friendly commercial fishing methods;

- Showing that project activity substantially reduces poaching activities;

- Actively improving hatchery management;

- Providing for actual mitigation of habitat degradation;

- Expanding and replicating successful initiatives such as the indigenous knowledge, school education and river keepers activities;

- Creating tangible and compelling examples of improved “sustainable” livelihoods, including implementing sound strategies for community-based management and model sport fishing initiatives;

- Finalizing and making operational the Trust Fund and micro-credit schemes; and,

- Enhancing the probability of broad replication through information dissemination, lessons learned seminars, and coalition building.

According to the project’s current evaluation criteria, most of the activities listed above should be launched and/or finalized during Phase I with expansion and replication supported during Phase II.

Recommendations

- The Steering Committee along with the PMU may wish to revisit the results framework and associated indicators in light of this review to create a very detailed, time-constrained workplan to strategically guide and support the transition from preparation to fuller implementation.

This should include a determination of priorities and what can be realistically achieved with remaining funding and time constraints.

Effectiveness

As noted, much of the project activity to date has been preparatory. This makes actual effectiveness difficult to assess.

The threats/root causes analysis seems to remain valid in the four project sites.  The productive sector continues to degrade salmonid integrity through both legal and “illegal” practices.  Industrial scale poaching of salmon for their roe is a very serious and real threat to diversity.  Habitat continues to be threatened, primarily by un-mitigated energy and mineral sector development.

However, nearly all persons interviewed stated that this project is well founded and based upon a logically written and accurate project document. Some may hope that the project’s impacts would be realized more quickly, but there is general concensus that this project is necessary and effective.  All stakeholders seem to genuinely view this project positively and firmly believe that the project has effectively assisted them to address the root causes, reduce the threats, and move Kamchatka towards the realization of the overall project objective. These positions were confirmed through the evaluation with several stakeholders interviewed proclaiming that the project has already assisted them to generally improve baseline understanding and their specific salmonid management efforts, positively affecting a change towards more diversity oriented management regimes.

Stakeholder Participation

Stakeholder participation in terms of individual project activities seems to be quite strong. It is clear that the project’s implementation team enjoys fluid working relations with the various stakeholders participating in the individual activity sets.  Each of the major government agencies on the national and Kamchatka level have been significantly and regularly involved in various aspects of the project.

Both national and local government support is strong in terms of co-financing and participation in project activities/management.

The project benefits greatly from the involvement of a US-based conservation NGO, the Wild Salmon Centre (WSC).  WSC is an important partner and catalyst providing significant and strategically coordinated parallel co-financing and technical support. For GEF, this project is an example of very “real” co-financing.  As with nearly any partnership, the relationship between the “project” and the WSC is not always smooth.  This is normal and has certainly not been debilitating.  Differences of opinion are resolved using very open and collegial approaches.  Both parties remain firmly committed to working together, to strengthening cooperation, and to achieving long-term project objectives.

The contributions of the Government of Russia, the Wild Salmon Center, and several other implementation partners/stakeholders to this project’s success should continue to be fully credited and recognized.

The Project Steering Committee was formed to provide national and international guidance and support to project implementation.  (Please see attached a list of 2006 Steering Committee Members and Participants).  Unfortunately, the mid-term evaluation could not be timed to coincide with a Steering Committee meeting.  However, both international and Russian members of the Steering Committee noted that expansion of this organization’s role could be a very positive contribution to overall project success.  The committee meets only once a year for a single day.  As a result, the meetings seem to be focused   upon reporting rather than strategic planning.

On the regional level, the project has regular, extensive, informal interface with local stakeholders. The project does benefit from a formal “Indigenous People’s Working Group”.  This body has seven member representatives, one person from the project, one person from the administration responsible for indigenous people and five indigenous people from the project site.  The project also helped to support the development of “Salmon Protected Area Working Group.”

The project has not formed a Local Stakeholder Group(s) as proposed by the project document.

Due to the complexities of Russia’s salmon management bureaucracy, the project’s ecosystem approach and the diversity of “collaborating partners” and interests, this project is particularly vulnerable to losing efficacy if it does not benefit from exceptionally strong inter-stakeholder and intra-project activity linkages.  This is particularly true in terms of backstopping project management, promoting long-term strategic and integrated decision-making, dissemination/mainstreaming of project results, and development of a strong, informed constituency to support project sustainability.

Although cooperation with individual stakeholders is generally strong, coordination and integration between various stakeholders could be improved to strengthen broad-based support for salmonid diversity conservation objectives.

To successfully transition from the current preparatory phase to fuller implementation of proposed concepts, the project will require the complete technical and political support of the Steering Committee and close coordination with stakeholders in each pilot area.

Recommendations

- The services of the Steering Committee as a body with representation of nearly all interested parties will be critical in the coming months if the project is going to be a “success”.  It would be very beneficial if the Steering Committee meetings were both a mechanism for reporting project activity as well as an opportunity for more in-depth strategic thinking, transparency and guidance regarding general project direction relevant to achievement of project objectives.

Consideration should be given to holding a special Steering Committee meeting in the near future that is focused upon identifying strategic needs for the remaining project period. This meeting should be well planned and organized.  This should be a multiple day, substantial decision-making event that includes a:   (1) Thorough reporting and discussion of project activity to date; (2) Identification and discussion of project needs/issues, and (3) Determination and agreement regarding the "way forward".

This should include presentation and discussion of a clear, detailed and time constrained strategic workplan for project completion.  During these Steering Committee meetings, there should be candid and informed discussions regarding budget matters, including allocations to date and remaining financing.

The project should consider (1) Inviting the consultant responsible for assisting with drafting the Phase II proposal to participate; and (2) Hiring a third party facilitator to assist with meeting preparation, guidance and reporting.

- In the long-term, the project would likely benefit from the development of a LSG to provide a more regular sounding board for project activity.  The LSG might include membership from stakeholders such as tourism operators, wildlife biologists, ecotourism organizations, national and international NGO’s, indigenous groups, hatcheries, Government agencies, and commercial fishery operators (particularly those located in project sites.)

- The project may benefit if representatives of each government agency responsible for salmonid management in Kamchatka would come together on a regular basis to meet as a group with the project implementation team to discuss project activity.  This would greatly facilitate strategic planning and information dissemination.

2.2	Project implementation

The Ministry of Agriculture of the Russian Federation (MA) executes the project with direct joint participation of the Kamchatka fishery committee (Sevvostrybvod) and Kamchatka Oblast Administration (KOA). As noted, the Wild Salmon Centre (WSC) is provides parallel co-financing to the project. The implementation of project activities are done by a Project Implementation Unit situated in Petropavlosk, Kamchatka, and overall management of the project is the responsibility of Project Manager, who is a full time employee of the project.

The National Project Director was not present during the Mid-Term Evaluation.  A meeting was held with Mr. Sergei Maksimov, Russian Federal Fishery Agency, appointed to represent the National Project Director.

In general, all issues related to project implementation and oversight appear to be fine. Both the UNDP national office and GEF regional headquarters are in regular and sustained contact with the project management offices.  There is fluid and cordial communication between UNDP Moscow and the project offices in Moscow and P-K.  The UNDP Resident Representative is actively involved and interested in the success of this project.

The project creates brief yearly workplans that are submitted to the Project Steering Committee for approval and quarterly reports are submitted to UNDP/Russia. The project submits annual project reports (APR/PIR) to UNDP/GEF using standardized forms.  This Mid-Term Evaluation represents the first “major” project monitoring/evaluation effort.  An end of project evaluation is also planned.  Both of these efforts will ideally serve to inform the development of the project’s Phase II.

The project implementation team seems to be competent and professional.  Project staff is well suited for their positions/tasks and seem to work effectively.  Although the project managers were changed mid-stream, the project seems to have recovered well from this shift. The current project manager appears to run the project very professionally.  He seems to be sincerely concerned for the well being of Kamchatka’s wild salmon stocks and has a very good understanding of the salmon business and related issues.  The deputy manager is a very experienced expert with a strong understanding of nature conservation issues.  Both are well suited for their positions.

To date, the project seems to be managing “identified risks”.  No significant new risks relevant to project implementation were identified.

Recommendations

- It is critical that UNDP/GEF on both the regional and national level allocate significant time in the coming months to make certain the project implementation unit receives enhanced support and guidance to complete the many outstanding tasks.  This should include budgeting for additional site visits.

- The project would benefit greatly if the details of yearly plans were extended, particularly in terms of achievement of specific project indicators.  In addition, it is strongly recommended that in the future the yearly workplans be closely aligned with a more strategic long-term or project duration plan, showing how all project activities will be completed prior to project close.

- To facilitate understanding between the project and co-financing partners, it may be useful to conclude a brief, formal MOU that clearly details expectations and re-visit this MOU periodically during project implementation.

2.3	Project finances

Due to time constraints, the Mid-Term Evaluation did not investigate project financing “in-depth”.  However, project staff was very forth-with in providing requested information and general conclusions relevant to proposed strategic approaches could be made.

The total GEF contribution to the project’s Phase I budget is approximately US$ 3 million.  To date, the project has depleted approximately US$ 1.4 million of these funds leaving approximately US$ 1.6 million to be used prior to project close in 18 months.

The project budget and disbursements are managed directly by UNDP/Russia according to standardized budget and accounting practices.  All parties seem to be relatively satisfied with budget management and efficiency.

Annual operating expenses  (full-time/part-time project staff and general operations) are approximately US$100,000.

To date, the largest expenditures include:

- Scientific research and related infrastructure/equipment;

- Anti-poaching equipment and data-base;

- Law and policy development;

- Advocacy, information, and education; and,

- Non-expendable equipment.

The project has significant reserves in the following budget categories:

- Various sub-contracts, including, economics studies, habitat and species conservation planning, alternative livelihoods development, and infrastructure/construction related to research;

- International technical assistance;

- Training and workshops; and

- Equipment.

The current budget status generally conforms to the project’s over-all workplan as conceived in the project document.  The project does not seem at risk of depleting funds prior to completion date with ample funds available for implementing remaining and expanded tasks. The project has significant finances remaining to be used for training and securing technical expertise.

Recommendations

- If the project is going to successfully achieve its objectives, strong consideration should be given to adding additional support staff and increasing expenditures on technical assistance.  The current staff seems well qualified and dedicated.  However, strategic involvement of additional human resources with appropriate skill sets would greatly increase project momentum needed to integrate biodiversity conservation objectives into productive salmonid fishery management practices.  These expenditures should remain within project capacity to provide oversight and be strategically targeted to address project “weaknesses” as identified by this evaluation and subsequent steering committee meetings. Potential increased allocations may include technical assistance for stimulating activities such as:

- Alternative and sustainable livelihood interventions (community-based management and sports fishing initiatives),

- Protected areas (establishment, lessons learned, management and planning),

- Information dissemination and training (replication, networking, capacity building, informed decision-making),

- Developing and piloting diversity friendly hatchery practices,

- Public awareness and education (expansion of indigenous and school work),

- Piloting of sustainable commercial fishing options (training, demonstrations),

- Anti-poaching initiatives (creating source, processing, transit and market impacts),

- Funding additional steering committee meetings (strategic planning), and;

- Regulatory development and implementation (sport fishing, community-based management, diversity reflective quota, hatcheries management, endangered species and habitat management).

- In view of current budget reserves, the preponderance of outstanding project tasks, the cost-effectiveness of maintaining current full-time project staff and an already equipped project office and the seasonality of project implementation (most project activity occurs during the short summer months), consideration may be given to extending the period of Phase I for an additional year to 2008.  This recommendation is offered only as a cautious suggestion requiring more serious contemplation by those responsible for project implementation.  Part of this extension period should be used to maximize opportunities for a project Phase II.

- Consideration should be given to providing full budget reports to the Steering Committee to increase transparency during expanded, strategic management discussions.

## Part Three:	Lessons Learned and Recommendations

1. 	Research and Decision-Making

One of the most important items for this project to achieve is to facilitate a gradual shift from management regimes that are primarily production-focused to management regimes that encompass both production values and conservation of over-all salmonid and ecosystem diversity.

Detailed discussions were held with responsible parties in both Moscow and Kamchatka on this issue.  The project seems to have laid some solid ground work to facilitate this change, including passage of legislation, broader recognition and support amongst stakeholders, and development of substantial research initiatives.

A variety of reports and other documents have been produced by this project and are generally available only in Russian.  Long conversations were held with Dr. Leman, the principal investigator, and his associates regarding these activities.  Several achievements can be identified.  Recognition must be made of the contributions of both the Russian Government and WSC regarding these achievements.  Examples include:

- The project supported GIS work is quite remarkable.  Solid baseline maps with several layers for each of the four project sites were produced and are operational.  This system coordinates previously disparate information and represents a potentially powerful management tool.  The system holds five basic databases:  spawning, catch, hatchery, sport fishing, human impacts, and hydro meteorological.

- With significant support from the Wild Salmon Center, the project was able to facilitate very interesting work on salmonid diversity relative to ecosystem function.  This is hugely important to informing management in biological systems such as Kamchatka where salmonids provide an extraordinary amount of nutrients to a wide variety of species.

- A very comprehensive mitigation report on the gas pipeline was concluded, reviewing more than 150 points where the pipeline potentially interferes with fish migration.

- The capacity of Russian researchers and institutions was strengthened significantly through international exchange, the delivery of “state of the art” equipment and the establishment of impressive infrastructure to support long-term research activity within two of the project sites.

- A habitat research and zonation effort was conducted on the Bolshaya River.  This included the positioning of fish monitoring stations and the creation of a preliminary database on salmonid and habitat diversity was compiled.

- Through this project, Kamchatka is a participant in the Salmonid Rivers Observatory Network (SaRON) Project being implemented by The Flathead Lake Biological Station (FLBS) of The University of Montana with the Wild Salmon Center (WSC) and Moscow State University (MGU). http://www.umt.edu/flbs/Research/SaRON.htm

All of this is very interesting and potentially useful work.  Simultaneously integrating commercial use, salmonid conservation, and ecosystem integrity represents in many ways a new and exciting way of doing business. Information generated to date has been incorporated within the existing monitoring and management systems.

The critical question is: How will the Government of Russia use this knowledge to systematically inform salmonid management decisions in order to achieve the long-term project objective of securing salmonid and associated biological diversity?

The project was designed to utilize sponsored research in two primary ways: (1) providing a baseline to evaluate project effectiveness; and (2) creating a monitoring approach that would inform and improve long-term management and salmonid conservation.  This includes the generation of baseline information and “sustainable research and monitoring program” to determine:

Project Effectiveness:  The research sponsored by the project is responsible for creating a baseline of information for measuring whether activity is having a positive or negative impact on salmonid diversity. The scientists are the doctors and should be providing regular advice as to the status of the patient.  This work should be answering the question, “Is the project succeeding in saving the patient or not?”

Inform Salmonid Management:  The research should provide a framework for fisheries agencies to manage project-river sites based on systematized and up to date information on biodiversity.  In essence, the project’s intent is to begin to lay a more firm foundation for informed, science-based decision-making, particularly for the four pilot areas in terms of escapement, quotas, habitat conservation, mitigation of ecosystem degradation and other related issues.  For instance, recent research shows that individual runs of salmon in particular rivers are genetically distinct.  However, current quota management systems continue to “mine” particular runs as if these genetic distinctions do not exist.  In the future, how will the results of the monitoring programs be incorporated within these decision-making structures?

Inform Project Activity:  How will the results of the research programs inform the following project activities?  The links between targeted research and all other aspects of the project must be sustained and constantly clarified.  Detailed examples from the project documents include:

Diversity conservation policies developed and approved and applied by year 3;

Re-oriented commercial fishery management practices in two sites;

Escapement goals for each river site enable species and ecosystem health by year 3;

Improved national and regional fisheries conservation laws;

Community development quota;

Public awareness/education; and,

Sport fishing activities.

Recommendations

- Further review the strategic purposes of existing research activities and develop a strategy/policy to embed science and decision-making. For instance, sponsor regular round-table or presentations bringing together researchers, policy makers and other stakeholders as an opportunity for researchers to publicly present and discuss their findings. This would be a useful practice to institutionalize even if current results are “pre-mature” due to the incompatible time requirements of research and project outputs.

- Generate list of baseline parameters that are or will be generated by the project to serve as “indicators” of project success and identify how research activity will deliver these indicators.

- Create an informal mechanism for the five major management agencies and the project research teams to meet together regularly (once or twice a year) to discuss initiatives and outcomes.  For instance, providing an introduction to the project sponsored GIS.

- Upgrade GIS to newest version of Arcview/info with applications;

- Review law/policy framework to identify opportunities for incorporating results of research and monitoring program in fisheries management.  The links within and outside of the project between information generated by the scientists regarding the system management requirements and policy makers is particularly important in light of the alterations of the newly revised legislation.  It would be very useful if the project were to facilitate this process.

2.	Hatchery Management

There are two salmon hatcheries located within the project’s four pilot sites.  Both of these hatcheries are located on the Bolshaya river system. During the mid-term evaluation, we were able to visit only the “Malkinskaya” hatchery.  This hatchery has been in operation for approximately 25 years.  From appearances, the hatchery is quite modern and run by a knowledgeable staff clearly supportive of attempting mechanisms to improve diversity supportive endeavors such as limiting hybridization and competition.

The hatchery is located downstream from all natural spawning grounds.  The hatchery breeds sockeye and king salmon.  The Bolshaya has one of the few river spawning red populations.  King salmon, being one of the first to return to the river each year, are a primary target for eager anglers and poachers. Although the original stock used for the hatchery came from Bolshaya river fish, the hatchery currently uses only hatchery fish for breeding.

Due in part to its proximity to PK, the Bolshaya is a “high pressure” river.  The river’s wild red and king populations are in steep decline as a result of excessive harvest pressure. The hatchery manager has worked at the hatchery for nearly 25 years and believes that the number of fish have decreased by a factor of 10 during this period. In addition, the over-all size of king salmon is diminishing.  The current average size of king salmon is 6.5 kgs, less than half of the average two decades ago.  The river has very developed commercial fishing, sport (primarily local Russian) fishing and significant “illegal” roe harvesting. These interests harvest most fish of the hatchery’s fish.  Their return is very low, with less than 6% of reds and 1% of kings returning each year.  Some theorize that pressure on other rivers is diminished due to the existence of hatchery fish on the Bolshaya.

Although the hatchery managers feel that it is difficult to tell currently how the project has improved management for diversity (two years is too short relative to the salmon life cycle), there have been some improvements of note and the hatchery manager likes the assistance of the project.  For instance, Dr. Leman’s group has been working with the hatchery to determine the most appropriate timing for releasing fish to minimize interference and food competition with wild stocks, including identification of in-stream nutrition.  In addition, the hatchery regularly monitors wild spawning grounds to determine presence/absence of hatchery stocks.  Hatchery stock is “marked” through the density of inner ear rings.  Because the hatchery utilizes natural hot springs, the growth of hatchery fry is significantly faster than wild stocks making inner ear bone rings much more dense.

Recommendations

- It would likely be very beneficial if the hatchery were to consider clipping the adipose fin of fish prior to release. This would assist management in several ways:  (1) the accuracy of presence/absence of hatchery fish at wild spawning grounds would be easier to determine; (2) the number of hatchery fish harvested commercially relevant to wild stocks would be easier to determine; and (3) sport and commercial fishing targets could be managed to allow anglers and others to “keep” hatchery fish and “release” wild fish.  This could be augmented by public awareness, anti-poaching and policy activities.  This is a common management method used for stocks in the US.

- The king salmon in the Bolshaya are considered to be under grave threat.   It might be interesting to explore options with the hatchery and other stakeholders to work cooperatively to assist with simultaneously conserving the wild spawning grounds and wild stock gene pool.

- The hatchery staff would be very interested to have an opportunity to learn best management and practices/principles from other hatchery experiences globally.  Again, the project does have a budget to provide support for this sort of activity, including bringing in international experts in hatchery/biodiversity management to help identify a sound, long-term strategy for hatchery management on the Bolshaya that may be replicated in other parts of Kamchatka.

- The proposed recommendations for hatchery management improvement developed with project support are based primarily upon the Alaskan models.  It may be useful to consider additional models/tools as management alternatives for Kamchatka’s system.

3.	Law and Policy

Unfortunately the mid-term evaluation did not include a specific interview with the Moscow attorney, B.V. Kokotov, retained for this activity.  However, detailed conversations were held with several “stakeholders” and the project provided the evaluator with a summary of activity.

To date, the law and policy component seems to have focused upon national legislation.  This has included some impressive successes including assisting the Government to pass the new Federal Law On Fisheries and Preservation of Aquatic Biological Resources.  This law seems to be umbrella legislation for fisheries management and will require significant refinement in the form of regulatory instruments.  For instance, the law contains broad requirements for the following:

- Streamlines most fisheries legislation into a single document;

- Objectives for participatory management;

- “Listing” of endangered salmonids;

- Fisheries management regulations to be concluded;

- Permitting for commercial and non-commercial harvest; and,

- Determination of quota’s and total allowable catch.

One very interesting and positive achievement is the recognition of fisheries conservation and protected areas.  Although the distinction between these two designations is not clear from the summary provided, the law does apparently suggest that the four project pilot areas each be give protected area status.

Recommendations

Facilitating the development of stakeholder driven policies, regulations, and strategies in each of the following areas would greatly strengthen project success, including replication, conflict mitigation and long-term sustainability:

- Implementation Support: The project may consider providing greater technical assistance regarding implementation of the relatively new fisheries act.

Gaps may exist that warrant a more thorough investigation, including specifically how "best-available science" and species conservation issues are integrated into the legal structure.  In particular, if the "species monitoring program" established by the project is somehow directly linked - legally - with the determination of quotas and other fisheries management issues to somehow improve long-term issues such as by-catch. The law requires that 48 individual regulations bet drafted to support implementation.  It may also be beneficial to include defining how “participatory decision making” as required by the law is specifically to occur in the process of determining fishery management objectives.  In addition, the mechanisms for quota setting require significant attention.  Finally, with passage of the federal law, all regional legislation became invalid.  This may necessitate a review of regional legislation;

- Sport Fishing Policy:  Development of a strategy/policy paper to guide the development of sport fishing as a very tangible tool for mainstreaming conservation within the private sector and providing increased anti-poaching advocacy and vigilance on river systems.  This would include working to identify legal mechanisms to describe exclusivity of access, either through reservation of specific river stretches and/or launch dates, equitable mechanisms for decision making, methods to insure quality control, and many other factors.  Other factors/tools such as “catch-and-release”, seasons, and slot management could be considered.  Community development and management of sport fisheries is an intriguing and very feasible concept, particularly for indigenous groups.  Particular attention should be paid to balancing the desires/demands of international destination anglers, local sport anglers, and subsistence anglers to make certain products and opportunities exist for each of these sectors. There are several good international best practices/experiences that could benefit Kamchatka;

- Detailed Salmon Listing and Habitat Requirements:  Regulations allowing for the listing of salmon stocks in particular rivers and/or stretches of river.  This should involve complimenting listing regimes with requirements for identifying and implementing management actions, including designation and conservation of habitat.

- Detailed Protected Area Definitions and Conditions:  The concept of a salmonid protected area is new and complex.  The project is in a very good position to help the Government of Russia and other stakeholders to learn from the current experience and build a strong basis for replication, particularly in the short-term for the four additional protected areas that the project is dedicated to creating. Create a track record for success.  Should be easier now that the law has been passed recognizing the four areas.  Should be considered as an opportunity for applying creative management tools.

- Embed Science with Decision-Making:  As noted, there is a significant need to more closely match quota and other management tools with the health/status of the species based upon rigorous study, recognizing the integral role salmonids play in the greater diversity of Kamchatka This might include working with stakeholders to more carefully detail roles/responsibilities regarding implementation of the Act and subsequent regulations.  More attention could be given to permitting requirements and making the management system more responsive;

- Commercial Management Strategy:  Detail a clear policy or strategy describing exactly how diversity principles will be incorporated into commercial harvest management systems.

- Community Development Quota:  Create a CBNRM policy for creation of community development quota describing the parameters of allocation and use.

- Trust Fund:  Create fundamental principles for trust fund development and management.

- Participatory Decision-Making Regimes:  Work to generate principles/policies for improving greater public participation in salmonid management decision-making.

- International Best Practices:  There are many very good templates and experiences to borrow from out there.  It would be quite useful in nearly all of this work to benefit from someone else’s experiences.

4.	Sport Angling

As recognized by the Project Document, sport fishing is a management, productive center, and conservation/anti-poaching issue.  There are many opportunities for sport fishing to positively contribute to the long-term survival of Kamchatka’s salmonid diversity. Anglers are capable of providing data on fish populations and trends, generate revenue for alternative valuation of the resource, and provide vigilance on rivers where current enforcement is lacking.  According to nearly sources interviewed, rivers with active sport fishing operations – particularly those catering to high-end international clients - generally have far less poaching and much healthier fish stocks.

National anglers and particular Kamchatka anglers represent a potentially powerful constituency for long-term salmonid conservation.  Fishing is very popular amongst residents and public awareness campaigns, river management programs, and other initiatives focused upon improving support by local sport anglers – particularly on the Bolshaya river – could be a very useful tool for promoting conservation.

Although sport-fishing in Kamchatka is legendary particularly amongst catch-and-release fly anglers who target rainbow trout, Kamchatka’s reputation as an international destination suffers from a general international market perception that investment is too risky due to unreliable management practices, insecure regulatory and fishery management practices, and low-availability of local business partners with adequate capacity/understanding of international market expectations. Logistical and cost issues related to both destination and internal transportation further limit market demand.

Early in the project period fishing for steelhead and the innovative and quite useful sport-fishing/research operations of the Wild Salmon Center were somehow suspended.  This led to a significant slow-down in project movement towards sport fishing objectives.  Never-the-less, the project to date has made some progress, including:

- Organizing an innovative and very popular Kamchatka fly-fishing celebration.  More than sixty persons participated.  This should become an annual event;

- Providing support for public awareness activities such as a sport fishing show;

- Conducting a general assessment of sport fishing’s impact on the health of some rainbow trout stocks working closely with sport anglers to generate baseline, survey data; and,

- Generating strong working links and support with Kamchatka level government agencies.

However, sport fishing continues to fail to provide it’s full potential as a conservation tool as envisioned by the Project Document.

The Kamchatka Government does regulate sport fishing based on the total number of fish in the river.  They issue quotas to sport fishing companies who invest part of their profit into development of infrastructure on the river such as helicopter pads and sleeping huts.  Quotas are allocated only for rivers that are certified for sport fishing.  Currently there are 8 - 10 “certified” sport fishing rivers and approximately 12 licensed operators.  However, this system is not stable due to the changed government structure.

Sevvostrybvod has a capable full-time staff person responsible for sport fishing management, including licensing.  He stated that they get about 200 letters a year from anglers asking for improvement of the system, even asking for some places to be closed because it is dangerous for the salmon.  People are starting to understand that there is a danger of over-exploitation.

Recommendations

- Sport Fishing Strategy/Policy:  Support for the development of a sustainable sport fishing industry for both local and international anglers should be a significant focus of this project.  This might be greatly enhanced by facilitating the development of a comprehensive sport fishing policy or strategy as described in the law and policy section.  This should be considered as critical first step.  The goal should be to create an environment that supports the development of a sustainable sport fishing industry.  Effort should include detailing long-range policies for sport fishing vision, fishery and river management, stream access and permitting/licensing issues, integration with the automated licensing system, destination marketing, guide certification/training, management planning, tendering and other policy related issues in order to create a more sustainable environment for business development.  This process should bring together Kamchatka and international outfitters as well as national/regional fisheries management professionals. It is strongly recommended that this activity benefit from the involvement of international professionals who clearly understand what is involved in development of sustainable sport fishing industries, including service, market and policy aspects.

- Model Operation:  Facilitate the development of model sport fishing operation on one or several of the pilot rivers based upon the outcome of the policy/strategy exercise.  There are very many interesting opportunities here, including linking the protected area status with innovative sport fishery management.  For instance, the Bolshaya could have stretches designated for catch/release and slot fishing, commercial/non-commercial, etc. applying a montage of management tools in order to secure long-term integrity of the river system.  Another opportunity may be working with indigenous communities to designate rivers or stretches of river for their development of a sustainable sport-fishing product.   Finally, the project could consider facilitate the creation of partnerships within the umbrella of the policy/strategy between local outfitters, international marketers, and regional government to provide a replicable model for sustainable sport-fishery management.

- Training Program:  Facilitate/sponsor the creation of a fly-fishing guide-training program to create more professionalism/interest in the industry.

5.	Economic Research

To date the project has retained the services of several highly qualified Russian economists to conduct a macro-economic study to determine the total value in both near and short-terms of Kamchatka’s salmonids. The study focused upon establishing the “total economic value” of salmon on commercial, ecosystem, recreation, and genetic levels.  This included looking at the value of sport fishing in Alaska and dividing it by several factors to determine the ultimate value of sport fishing in Kamchatka.  Ultimately, the economists concluded that the value of salmon is approximately the same as the value of gold or oil development.

It is understandable that the project would wish to generate figures attempting to quantify the total value of salmonids relevant to other resources and management approaches such as mining, timber, and energy production that will undoubtedly negatively impact salmonid conservation.  However, the basis for this quantification contains significant shortcomings and interesting assumptions that warrant more careful scrutiny.  If this study is to be used to compare the value of salmon versus oil, gas, gold, copper or other “non-sustainable” economic activity, the researchers must be very careful to get it right. If not accurate and thoroughly defendable it could be dangerous.  The many unknowns, assumptions, and externalities that may not reasonably be accounted for when attempting to attach a monetary value to habitat and species conservation compared with “hard” economic endeavors such as mineral and energy production can easily make such a tool a two-edged instrument.

The project has not yet endeavored to complete a “micro-economic” review as envisioned by the Project Document. The project manager has a very clear understanding of the economics related to commercial fishing.  This would be a very useful and necessary tool to inform project implementation.

Recommendations

- Review and revise as necessary the macro-economic analysis.

- Conduct a micro-economic review/analysis of the Kamchatka salmon industry to inform the community development, sport fishing, anti-poaching, quota setting, and other project sponsored activities related to management of the fishery.

The purpose of this review should be in part to determine:  The contributions made by commercial, poaching, sport, and subsistence fishing to the local economy; and, Economic instruments required (permits, fines, alternative livelihoods) required in order to serve as an incentive to promote behavioral changes from un-sustainable to sustainable.

6.	Poaching and Over-harvest

Over-harvest and poaching of salmon poaching is a serious and complicated business in Kamchatka. Even with significant enforcement efforts, numerous commercial fish operations (set nets or traps located near the mouths of rivers) will reportedly cheat on their quota allotments, either over-fishing, target non-quota species, fail to release by-catch, and/or fish during prohibited periods.  Salmon roe collectors regularly slaughter spawning salmon for their roe.  This has become an industrialized activity during the past ten years, with helicopters regularly servicing roe collectors in places such as the Bolshaya during the harvest season to transport illegal fish eggs.  “Subsistence” or “sport” harvesters illegally harvest fish off nests for their eggs.

The project supplied several pieces of equipment (i.e., snowmobiles, jet boats, and satellite phones) as well as a poaching database and response system.  This equipment was supplied to Kamchatrybvod and, as of summer 2005, Rosselkhoznadzor is now primarily responsible for anti-poaching enforcement. Rosselkhoznadzor has responsibility for both veterinary services and enforcement of poaching, meaning they can supervise fish processing plants, fish harvest, and transport.  They are promising to take a very active and aggressive stance against poaching.  During later review missions, it will be important to determine how effective these instruments were in alleviating poaching efforts.

In should also be recognized that in many ways, nearly all of the project’s efforts – sport fishing, children’s education, public awareness, research, and indigenous community development – help to alleviate poaching.

Recommendations

There are “options” being discussed by government.  All of these are potential activities that the project could be looking into to strengthen government capacity.  The activities “target” the entire chain of poaching activity – harvest, processing, transport, and market.  They also look towards improving incentives and capacity for all stakeholders.

- Continue to push forward with development of model enforcement activities on the project rivers, including establishing a clear nexus between supply of equipment and alleviation of impacts.

- Greater enforcement of transport points such as helicopters.  Nearly all commercial salmon roe is transported via helicopter to the airport in P-K for export out of Kamchatka.

- Improved licensing systems for sport and commercial fishing operations.  This is linked to the supplied database.

- Creating a consumer awareness campaign particularly in Moscow.  This worked quite well with black caviar and could be replicated for salmon, including the labeling of legal salmon products.

- Better comparison of numbers between fish caught in nets with numbers of fish processed. This will be particularly important now that the number of on-shore processing plants has grown tremendously.

- Implement mechanisms to legitimize “poaching” of salmon roe while placing production control in more localized hands, i.e., communities.

- Enhance sport fishing operations to get more “eyes and ears” on the river.

- Expand the very successful river keepers program to other river systems.

- Continue community-based natural resource management schemes as incentives for community enforcement, vigilance, and responsible use.

7.	Poaching of Non-Commercial Species

The current “river keepers” program seems to be an incredibly cost-effective and successful method to curtailing poaching of “non-commercial” species such as steelhead.  Only a few thousand dollars have been spent on this activity.  In the future, sport angling promises to provide an additional mechanism.  The issue and harm caused as a result of steelhead “by-catch” by coastal net anglers is not clear.

Recommendations

Expand river keepers program to other project sites

Continue support for development of “sound” sport fishing activities.

Implement model programs for the reduction of “by-catch”.

8.	Commercial Harvest

The project concluded a contract with several Kamchatka agencies to produce recommendations for improving commercial harvest methods that incorporate conservation of salmonid diversity. The team is to develop an analysis of current practices and develop recommendations for improvement.  The team submitted a draft paper based upon Alaska’s programs.  Next they hope to develop these practices on the Kol River.  The outputs of this activity should be recorded and monitored very closely for possible replication and linkage with policy.

The project organized two high-level round-tables with the fisherman to get their opinions about what is needed to improve management practices.   The conclusion was that a need exists to improve government regulation and management.

As noted, the project should be working to improve the integration of diversity management principles in the overall quota setting and management process.

Currently, the quota is set according to long-range forecasts of commercial species by KNIRO.  The quota for the entire west coast is based on fifty locations for chum and pink salmon and one location for red salmon.  These 101 numbers are lumped into two big numbers (quota for the north and quota for the south) and then sent to review by various government agencies before allocation to commercial, sport and indigenous consumers.  There are more than 140 net sites allocated in Kamchatka, nearly all of them along the western coast.

Apparently, there is no legal requirement for management authorities to review factors such as:  ecosystem health, specific status of particular runs/rivers, status and potential impact to non-commercial species such as steelhead, etc.  In addition, there does not seem to be any public review of quotas, contrary to the requirements of the Aarhus Convention.  These are certainly issues that the project was designed to address and should be considered very carefully during the remainder of the implementation phase.

Recommendations

- Apply science/research programs to create models for more precise quota management, especially on the Kol and Bolshaya rivers, that could eventually be replicated in other regions.  According to some parties, this is already occurring informally.  These models should be used to create management quotas based upon ecosystem conservation rather than simple production targets.

- Link the new enforcement data-base/communication system to the quota management system in order to more closely track the amount of legal/illegal take.

- Provide technical support to the government related to leasing of fishing concession and integration of conservation principles.

- Develop programs for monitoring processing plant production.

- Continue assisting KNIRO to develop river-based assessments.

- Initiate “on-the-ground” activities in the four pilot sites that clearly demonstrate commercial fishing methods that are both profitable and diversity supportive.  Review and widely disseminate results to responsible government agencies, commercial operators, and other stakeholders.  This might require identifying and securing international technical assistance capable of providing specific recommendations based upon international best practices.

9.	Protected Area Establishment and Management

The project partners and particularly the Government of Russia should all be congratulated on the establishment of the Kol Protected Area.  This is quite possibly the first “Salmonid Conservation Area” in the world and a remarkable achievement.

Recommendations

- Lessons Learned:  The project should carefully reflect upon lessons learned during this process.  What steps were necessary to achieve the goal?  What was positive and negative about this process?  One purpose of this formal exercise should be to inform the development process of the remaining three protected areas to be authorized.

- Management Planning:  The project will want to work to facilitate the development and formalization of specific management conditions and strategies for the protected area, including securing and training of staff.  As noted in the law and policy section, the words “protected areas” mean different things to all interests.  This particular protected area includes commercial fishing, research, sport fishing, indigenous use, poaching, and a newly constructed pipeline and access road.  All of these are complicating factors to be considered when designing the ultimate management plan.

- Strategy for Additional Protected Areas: The project document commit to the project to designation of an additional three protected areas:  Bolshaya Basin, Sopochnaya River, and Utkholok-Kvachina.  If the project is to achieve this goal, it might be very useful for a clear strategy to be detailed and approved by the Project Steering Committee. This should include reference to stakeholder analysis and the development of creative zoning designations to accommodate a variety of uses, including reference to the project’s piloting of innovating conservation approaches such as sustained livelihoods, hatchery management, and improved commercial fishing methods.  These pilot sites were each selected as being representative of various salmonid conservation issues.  Likewise, their protected area designation should creatively reflect the variety of issues.

10.	Mitigation of Habitat Degradation

As noted, national scientists compiled a very impressive and thorough review of all “crossings” by the road/pipeline along the western coast of Kamchatka.  The study revealed significant problems, primarily related to design flaws that cause potential blockage for salmon to upstream spawning grounds.  The issue will now be whether industry and authorities take on board the study’s recommendations.

Recommendations

Secure firm commitments from government and other stakeholders to implement mitigation plans/needs identified in the impact assessment. This should likely include model mitigation in the project sites and particularly linkages to requirements related to newly created protected areas and ‘study’ areas.

Identify and prioritize pending habitat degradation activities (i.e., hard rock mining) and consider formal mechanisms for utilizing baseline scientific knowledge developed through the project to legally inform mitigation requirements.

11.	Education and Public Awareness

The project supports a wide variety of strategic and useful general public awareness initiatives, including:

- Launching a website; www.kamchatkasalmon.ru

- Co-financing with the Wild Salmon Center and Protected Areas Project a very professional and widely distributed (30 issues/1,500 copier per issue), full-color “protected areas” newspaper;

- Presentations in local media;

- Participation in several festivals related to salmonid conservation, including indigenous “salmon” festivals;

With significant project support, a very vibrant school curriculum program was launched and is fully operational.  This is another significant and tangible project achievement.  The program involves nearly all ages of students and is embedded in more than sixteen schools.  To date, more than 200 students have participated in the quarter-long course.  With student demand out-pacing availability, not enough positive things can be said about this program.  There is excitement amongst teachers and students alike.   Prior to launching the curriculum in each own school, participating teachers go through a short certification course.  The teachers are working cooperatively, volunteering their time and energy to constantly upgrade and improve their curriculum.  They organize salmon festivals, plays and school excursions.  The project has a lovely and very professional salmon interpretative center located near their office.  The center is filled with interesting and informative displays.  The project staff worked with the individual participating schools to develop mini-interpretative and teaching centers within the schools based upon the main center’s models.

Recommendations

- Secure funding for a “Salmon Bus” to provide transport for participating students to both field study areas and the salmon interpretative center.

- Provide digital video equipment to enable students to make their own teaching documentaries.

- Support replication of this program in other areas of Kamchatka.

- Place the Kamchatka teachers in contact with similar school based salmonid and stream conservation programs.

- Generate an on-going summer program for students, including stream and spawning monitoring programs.

- Provide additional sets of laboratory and monitoring equipment for the teachers/clubs.

- Create linkages between the project’s on-going research and conservation efforts and the school programs, including sponsoring talks/discussions between school children and international/national experts and providing opportunities for select students to participate as interns in on-going research and monitoring activities.

- Continue pursuing innovative public awareness initiatives such as supporting indigenous salmon festivals, replication of indigenous information centers, and financial support for conservation media.

- Expand public awareness initiatives such as the fly fishing festival and licensing procedures to more strategically target and inform local sport fishing enthusiasts.

- Continue and expand linkages between salmonid conservation and general tourism initiatives in Kamchatka.

12. 	Community Development and Alternative Livelihoods

Based upon lessons learned from contemporary project implementation, the entire activity set has been re-organized as follows.  Sseveral of these activities represent very interesting and innovative programs initiated in cooperation with local communities.

General Alternative Livelihood Development Activities

- Market Assessment

- Linkage between company and supplier (reindeer, fishing, etc.)

- Business Planning

- Micro-Credit

- Small and medium enterprise training

Non-Fish Specific Activities

- Alternative livelihood study

- Ecotourism: Demonstration project, guidelines, etc

- Reindeer herding

Consumptive Fishing Activities

- CDQ

- Processing plant

- Advisor on traditional/alternative

- Diversity friendly fishing techniques

- Traditional Knowledge

- River Keepers Program

Non-Consumptive Fishing Activities (Sport Fishing)

- Sport fishing demonstration project

- Policy

- Organization of sport anglers

- Marketing

- Guide Training

- Fly Fishing Festival

Community Awareness and Education

  - Traditional Knowledge Program

  - Ecological Center in Kovran

Recommendations

- Replicate the river keepers program in other project areas.  This appears to be a very cost-effective conservation mechanism.

- Improve incorporation of indigenous knowledge in long-term management of river systems.  This should include continued support and expansion of lessons learned through the innovative indigenous knowledge program and building support amongst traditional community leaders for sustainable management objectives.

- Support innovative, community-driven mechanisms for Community-Based Management such as the “Community Development Quota”.

An indigenous quota currently exists in Kamchatka.  Essentially what is required to create a CBNRM program is to more carefully define the terms of allocation and use.  This will require generating support and consensus from both the Government and indigenous communities.  The advice of the retained consultant is correct in that the first step should be to work with indigenous communities to determine a policy or strategy that clearly details the potential program parameters.  The project should provide an international facilitator to assist project staff with this process.

The project should possibly look beyond the example of Alaska. There are literally hundreds of CBNRM models that could possibly be adapted to more closely match the specific requirements of Kamchatka.  Nearly all of these models follow similar patterns with the development of a Community Based Organization that serves as a “Representative and Accountable Legal Entity” responsible for managing the community’s resource rights on behalf of its members.  The CBO then works to generate revenue from the resource and redistribute this benefit in ways that create clear linkages between the existence of the benefit and sustainable use or conservation.  The natural resource use may be consumptive and/or non-consumptive.  For instance, in Kamchatka communities may be given the right to harvest salmon and/or the exclusive right to operate sport-fishing camps.

Although in the long-term, the target communities may include both indigenous and non-indigenous communities, the project may next wish to first capitalize on the existing framework the “indigenous quota” provides and work with indigenous communities to select a site within the project’s four watersheds of concern to pilot an experimental approach.  This effort may be closely linked with the designation and management planning of the site as a “protected area.”

Activate the micro-credit fund in project sites with clear protocols for disbursement linked to salmonid conservation.  Explore possibilities of linking micro-credit with CBNRM initiatives;

Facilitate linkages between reindeer herders in Kamchatka with similar programs in Buryatia, Scandinavia, etc.  Work to identify niche and boutique markets for reindeer meat and other products, i.e., tourist camps, hotels, high-end restaurants and butcher shops;

Continue working with the network of indigenous people’s organizations to generate a strong constituency for conservation of salmonid diversity and alternative livelihoods.

13.	Sustainable Financing

Working in tandem, the Protected Areas Project and Salmonid Projects are benefiting from a very committed, enthusiastic and capable staff tasked with development of the sustainable financing activities.

To date, only the basic elements for the trust fund seem to be in place, i.e., registered in 2005.  Following the advice of a highly experienced international consultant, the fund is to be operated as one institution with two accounts:  Protected Areas and Salmonid Conservation Projects.  There are also Ruble and Dollar accounts. The Dollar account will operate as a trust fund (corpus intact with interest dispersed). The Ruble account will simply be a bank account with funds regularly dispersed.

The team is currently working hard to determine ways to generate small amounts of revenue for the Ruble account, such as green programs with local eco-tour operators and sophisticated donation boxes with flat screen TV’s at the airport.  Meanwhile the international trust fund has stalled while waiting for a fourth donor in order to qualify for Delaware, USA registration.  This international trust fund apparently has by-laws, charter, and tentative board of directors.

The project is just now developing the charter for the management of the local trust fund.  They are proposing a single board of directors for both funds with a single manager (who also does fund raising), accountant, and a fund-raiser (in Moscow).  There will be two committees one for salmon experts and one for biodiversity that will conduct an initial review and the board will approve or disapprove the applications.

Recommendations

- Provide technical assistance for the development of sound trust fund management protocols, including fund raising and allocation. Unless the charter, by-laws and other documents describing the workings of this body are very clear and precise, there will almost certainly be significant conflict and competition.  This may be addressed adequately in the draft operations manual.  The fund’s legal documents must be drafted clearly in order to secure the faith of potential donors.  If the documents are perceived as in conflict or otherwise unwieldy, potential donors will be hesitant to contribute.

- Clarify Trust Fund goals and work plan for both the dollar and ruble accounts, including realistic time frames for making operational. According to statements made within the Project Document, the international or “dollar account” Trust Fund is to become operational during Phase II.  However, indicators for Phase I state that the Trust Fund will be fully operational during Phase I with nearly US$ 1.5 million secured.

- Identify types of activities that will require long-term funding support from the Trust Fund and the amounts of revenue needed

14.	Project Management and Implementation

As noted in Part I, several steps could be taken to strengthen project management in terms of strategic planning and support for achievement of objectives.

Recommendations

- Expand Role of Steering Committee:  The services of the Steering Committee as a body with representation of nearly all interested parties will be critical in the coming months if the project is going to be a “success”.  It would be very beneficial if the Steering Committee meetings were both a mechanism for reporting project activity as well as an opportunity for more in-depth strategic thinking and guidance regarding general project direction relevant to achievement of project objectives.  These are clearly ideals reflected in the Project Document’s TOR’s.  The objective should be to strengthen the capacity of the Steering Committed to provide support to the PMU.

- Review Project Achievements in Light of “Lessons Learned” and Create Long-Range Workplan: The project would generally benefit if the details of yearly plans were extended, particularly in terms of achievement of specific project indicators. To date, the project has created three workplans (2004, 2005, and 2006).  Each year, these show substantial improvement in terms of detail and logical organization.  However, they would be strengthened significantly and flow more smoothly into M&E requirements if they were organized by output and indicator showing how each activity is specifically focused In addition, it is strongly recommended that in the future the yearly workplans be closely aligned with a more strategic long-term or project duration plan, showing how all project activities will be completed prior to project close.

There are many improved responses being considered to address evolving conservation needs. The Steering Committee along with the PMU may wish to revisit the results framework and associated indicators in light of this review to create a very detailed, time-constrained workplan to strategically guide and support the transition from preparation to fuller implementation.

As noted in the main report, consideration should be given to holding a special Steering Committee meeting in the near future that is focused upon identifying gaps and strategic needs.  This will be very important to informing final evaluation of Phase I and setting the stage for development of Phase II.

Prior to gathering the Steering Committee, this activity might commence with a working retreat with the project staff and key stakeholders in P-K to further identify and clarify bottlenecks, propose harmonized approaches, and devise a clear strategy for resolution.

- Formalize Local Stakeholder Groups:  In the long-term, the project would likely benefit from the development of a LSG to provide a more regular sounding board for project activity.  The LSG might include membership from stakeholders such as tourism operators, wildlife biologists, ecotourism organizations, national and international NGO’s, indigenous groups, hatcheries, Government agencies, and commercial fishery operators (particularly those located in project sites.)

Consideration should be given to expanding participation to parties concerned with greater ecosystem conservation issues, reflecting the important role salmonids play in this system.

- Establish Informal Mechanisms for Kamchatka Level Agency Information Exchange:  The project may benefit if representatives of each government agency responsible for salmonid management in Kamchatka would come together on a regular basis to meet as a group with the project implementation team to discuss project activity.  This would greatly facilitate strategic planning and information dissemination.

- Develop an MOU for Project Partners:  To facilitate understanding between the project and co-financing partners, it may be useful to conclude a brief, formal MOU describing expectations, communication, information sharing and other important “partnership” details.  This would be particularly useful to enhance the relationship between the project, the Wild Salmon Center, and key Government agencies.  As a co-funding mechanism, it is surprising that creation of such an MOU is not a standard practice for all GEF projects.

- Retain Additional Staff, including Short-Term Technical Assistance: If the project is going to successfully achieve its objectives, strong consideration should be given to adding additional support staff and increasing expenditures on technical assistance to stimulate more rapid achievement of project objectives based upon lessons learned to date.

- Extend Project Period: In view of current budget reserves, the preponderance of outstanding project tasks, the cost-effectiveness of maintaining current full-time project staff and an already equipped project office and the seasonality of project implementation (most project activity occurs during the short summer months), consideration may be given to extending the period of Phase I for an additional year to 2008.

- Begin Planning for Phase II:  This project was designed to be funded under a second phase.  Work should commence in the near-term to begin setting the stage to secure funds in order to minimize the probability of having a hiatus in project activity between funding periods.

- Allocate Time for Site Visits:  It is critical that UNDP/GEF on both the regional and national level allocate significant time in the coming months to make certain the project implementation unit receives enhanced support and guidance to complete the many outstanding tasks.  This should include budgeting for additional site visits.

For instance, due to early spring scheduling, the mid-term evaluation did not include an opportunity to physically visit pilot sites to review “on-the-ground” activities.  Although not debilitating to the final assessment, future supplemental project evaluations and/or final project evaluation should certainly include field site visits. These visits should include opportunities to hold discussions with residents – particularly commercial fishing operators, “poachers”, anti-poaching field staff, field researchers, sports anglers, and indigenous communities.

- Expand Time Allocated for Monitoring and Evaluation:  As noted, the time required for this evaluation mission was woefully under estimated.  If future M&E missions are to be meaningful and comprehensive, it must be recognized that this is a complex project requiring significant time/energy to fairly evaluate and provide thoughtful recommendations for strategic improvements.  Future M&E missions may benefit from holding a participatory workshop with representation from all project stakeholder groups, especially those represented in the Steering Committee.

## Annexes

- Summary of Project Activity:  Project Progress Matrix

- Project Reports

- Project Steering Committee

- Mid-Term Evaluation:  Itinerary and list of persons interviewed

- Mid-Term Evaluation:  TOR

Summary of Project Activity:  Project Progress Matrix

Following is a summary of Project Progress by Output, Outcome, and Indicator.  This was compiled by referencing the Project Document, various annual reports, and information provided during the Mid-Term Evaluation.  Status of each result was completed by the project implementation team and reviewed by the evaluator.

Objective-level Indicators

| Description of Impact Indicators | Value in year 0 | Mid-term Target Value (2005) | Status as of April 2006 | End of Project Target Value (2007) |
| --- | --- | --- | --- | --- |
| Indicator 1. Salmonid diversity | List of species recorded in all four river sites; | Very Good: All historical species present in river sites. | Species present. Decline of many species continues particularly in southern rivers. | Very Good: All historical species present in river sites w/ more complete data set. |
| Indicator 2. Distribution: Adult or juvenile presence by stream segment. | Incomplete information on commercial species, absence of information on non-commercial species. | New information on commercial and non-commercial species. | Ranges known. Ecosystem health and abundance vulnerable. Species such as Kings in the Bolshaya are threatened with extinction | Very good: Occupy 100% of historical range within each river system. More complete data on commercial and non-commercial species |
| Indicator 3. Number of hectares of salmonid habitat protected; | No specific protected areas for salmonids. | 1 PA created; 280,000 ha protected. | One protected area established (the Kol) in May 2006. Establishment of the 2nd Phase I protected area underway with improved prognosis based on success of PA 1. | 1 PA established. Design of the 2nd PA is developed. Total # of hectares: 400,000 heсtares. |
| Indicator 4. Insect biomass and diversity | Incomplete information for Bolshaya river, absence of information on other river sites | List of insect species enlarged and biomass determined for three river sites | Much of this has been studied. Specific project impact not yet known. | Very good: 66-100% of median biomass. Good: 40-66% of average. |
| Indicator 5. Abundance of salmon. | River basin escapement levels Bolshaya, Kohl, U-K. | Very Good (see footnote) Existing information incorporated into the common database | Much of this has been studied. Specific project impact on escapement not yet known. | Very Good (see footnote). Information database is used by the decision makers. |
| Indicator 6. In-stream habitat a)Sediment transport; b) Road density in watershed; c) Spawning habitat (SH); Rearing habitat (RH). | a) These not defined for river sites at Year 0. b) These not defined for river sites at Year 0. c) Information on commercial species in-stream habitats exists. No information on non-commercial species in-stream habitats | a) Will be defined by mid-term. b) Will be defined by mid-term. c) More complete information on commercial and non-commercial species spawning habitats. Status of rearing habitats determined on model sites | Much of this has been studied. Specific project impact on habitat integrity not yet known. | a) Sediment transport: Very Good (fluctuates no more than 15% up or down each year). b) Road density in watershed: AR. c) SH 90-100% of historical figures; RH: 90-100% of historical figures. |

| Revised Outcome One Improved fishery management practices for salmonid diversity conservation purposes. |  |  |  |  |
| --- | --- | --- | --- | --- |
| Indicators | Value in year 0 | Mid-term Target Value (2005) | Status as of April 2006 | End of Project Target Value (2007) |
| Indicator 1. Diversity management principles and criteria are developed, proposed, and approved for 2 hatcheries in Bolshaya basin | Diversity management principles and criteria are not addressed with enough attention in hatcheries practices | Program elaborated for this task and adopted by SVR and KNIRO. | The ad hoc working group analyzed existing practices in Kamchatka, best world practices and elaborated main strategies for improvement | Diversity management principles and criteria are developed, proposed, and approved |
| Indicator 2. Salmonid diversity and ecosystem health requirements incorporated into escapement goals for project river sites. | Not specified in escapement goal establishment process. | Work towards establishment of diversity-friendly escapement goals initiated | Field research is being conducted in 3 river sites (Bolshaya, Kohl, Utkholok) and proposals are being developed for better ecosystems management. | Diversity and ecosystem health escapement goals are established and applied to project sites. |
| Indicator 3. New public-private partnership for management of non-commercial fish species. | No partnership for management of non-commercial species. | Association of fly fishers and fly-fishing businesses formed. | Fly fishing awareness raising program and training programs are being developed and implemented. Rivers caring capacity assessment program targeted at partnerships with commercial outfitters is being developed. | Fish management agencies utilize public-private partnership to manage sport fishery on two pilot sites. |
| Indicator 4. Russian fishery legislation incorporates salmonid diversity conservation principles. | Not reflected in existing fishery legislation. | Analysis of law with recommendations for change | New fishery law (2004) reflects diversity conservation principles. Subordinate legislation is being elaborated. | New system of fishery regulations and policy reflecting salmonid diversity conservation. |
|  |  | New fishery law reflects diversity conservation principles. |  |  |
| Indicator 5: Fisheries agencies manage project river sites based on systematized and up to dated information on biodiversity | No systematized and up to dated information on biodiversity in the project river sites. | Existing information collected, analyzed and gaps identified; Database designed. | River ecosystems health database is created, tied to GIS and is being integrated into practices of fisheries management agencies. | Fisheries agencies maintain complete picture of site ecosystem health through a continually updated database for project sites. |

| Output One: Workplan from Project Document |  |
| --- | --- |
| Target Output/Activities | Status as of April 2006 |
| Target Output 1. Baseline river ecosystem quality described and quantified in project sites by end of year 3. | “Completed” |
| 1.1. Reach consensus on and establish information needs, database design and function | “Completed” |
| 1.2. Reach consensus upon inventory methods/specific workplan w/specific responsibilities and outcomes. | “Completed” |
| 1.3. Conduct complete inventory of aquatic/riparian biodiversity and habitat type, incl. salmonid genetic & life history diversity in three sites | “On-Going” |
| Target Output 2. Sustainable research and monitoring program developed and implemented by end of year 3. | “Completed” |
| 2.1 Research priorities finalized. | “Completed” |
| 2.2 Monitoring methods and infrastructure established | “On-Going” |
| Target Output 3. Diversity conservation policies developed and approved and applied by year 3; | “On-Going” |
| 3.1 Policy options discussed with main stakeholders. | “Completed” |
| 3.2 Recommendations developed and endorsed. | “On-Going” |
| Target Output 4. Re-oriented commercial fishery management practices in two sites. | Planned |
| 4.1 Develop training materials for diversity conservation by end of year 1 | “On-Going” |
| Target Output 5. Escapement goals for each river site enable species and ecosystem health by year 3. | “On-Going” |
| 5.1 Guidelines for integrating diversity objectives into salmonid fishery operations finished by year 2. 1st draft by e/o year 1; final draft approved and adopted by e/o year 2. | “On-Going” |
| 5.2 Diversity management principles & protocols developed for two hatcheries in Bolshaya basin. | “On-Going” |
| 5.3 Fishery management regimes adopted emphasize conservation of steelhead/salmonids. | Planned |
| Target Output 6. Guidelines for public participation in diversity-management approved by year 3. |  |
| 6.1 Develop guidelines and recommendations and secure approval from Sevvostrybvod. | “On-Going” |
| Target Output 7. Poaching prevention efforts for commercial salmonid species are increased by 30%. | “On-Going” |
| - Increase patrolling of sites in important seasons; community involvement. | “On-Going” |
| Target Output 8a. Kamchatka’s law and policy framework strengthened and expanded. Legal brief integrating salmonid diversity objectives into draft fishery law under consideration by the Duma by middle year 2. | “Completed” |
| Targeted Output 8b. Amended KamO’s and KorO’s Fishery laws recognizing diversity of salmonids and specifying proactive management by end of year 2. | Not Planned Salmonids are under the federal government management |
| - Conduct consultations with stakeholder groups as to best legal approach, draft legal brief, openly review and finalize. | “On-Going” |
| 8.1.a. Support consultations in Kamchatka among key decision makers to lay the groundwork for such amendments. | “Completed” |
| 8.1.b. In-country and study tour training for policy makers in how to assess values and services provided by salmonids, and how to use regulatory incentives to promote salmonid conservation. | Planned |
| 8.1.c. Set escapement goals that sustain not only commercial fishery, but also allow for diversity maintenance by middle year 2. | “On-Going” |

| Output One: Output Targets from Project Document Results Framework | Status as of April 2006 |
| --- | --- |
| - Complete inventory of aquatic/riparian biodiversity and habitat type, incl. salmonid genetic & life history diversity. | “On-Going” |
| - Database operational and information accessible from database beginning year 3. | “Completed” |
| - Database tied to GIS by end of year 3. | “Completed” |
| - Sustainable research and monitoring program developed and implemented by end of year 2. | “Completed” |
| - Training materials prepared by end 2003. | Planned for 2006 |
| - Diversity conservation policies developed and approved and applied by year 3 | “On-Going” |
| - Commercial fishery management regimes adopted emphasize conservation of steelhead/salmonids and ecosystem health in two river sites by year 3. | “On-Going” |
| - Diversity management principles & protocols developed for two hatcheries in Bolshaya basin. | “On-Going” |
| - Guidelines for public participation in diversity-management approved by year 3. | “On-Going” |
| - Poaching prevention efforts for commercial salmonid species are increased by 30%. | “On-Going” |
| - Legal brief integrating salmonid diversity objectives into draft fishery law under consideration by the Duma. | “Completed” |
| - Amended KO’s Aquatic and Marine Fishery Law and KAO’s Fishery Law to recognize diversity inherent in salmonids and require proactive management for this diversity. | Not Planned Salmonids are under the federal government management |
| - Policy makers trained in ecosystem value assessment and proactive use of fiscal and other policies and regulations for conservation purposes. | “On-Going” |

| Output One: Indicative Activities – Project Document’s Results Framework | Status as of April 2006 |
| --- | --- |
| - Field inventories in at least two sites. | “On-Going” |
| - Develop database that meets international standards. | “Completed” |
| - Link database to GIS in as low cost manner as possible. | “Completed” |
| - Research priorities finalized, monitoring methods and infrastructure established | “Completed” “On-Going” |
| - Develop training materials for diversity conservation. | Planned for 2006 |
| - Policy options discussed with main stakeholders, recommendations developed and endorsed. | “Completed” |
| - Guidelines for integrating diversity conservation objectives into salmonid fishery operations finished by year 2. 1st draft by e/o year 1; final draft approved and adopted by e/o year 2. | “Completed” |
| - Same as #6. Set escapement goals to sustain commercial fishery, and maintain diversity. | “On-Going” |
| - Increased patrolling of sites in important seasons; community involvement. | “On-Going” |
| - Conduct consultations with stakeholder groups in Moscow as to best legal approach, draft legal brief, openly review, finalize, and circulate for consideration. | “Completed” |
| - Support consultations in Kamchatka among key decision makers to lay the groundwork for such amendments. | “Completed” |
| - In-country and study tour training for policy makers in how to assess values and services provided by salmonids, and how to use regulatory incentives to promote salmonid conservation. | Planned for 2007 |

| Output One: Contracts | Status as of April 2006 |
| --- | --- |
| - GIS Database Development - Digitize maps - Link GIS framework to biodiversity database - Strengthen GIS capacity within most appropriate institution | “Completed” |
| - Develop policy “white paper” on strengthening fishery law for diversity conservation - The purpose of this subcontract is to secure legal expertise in Moscow to provide members of the Duma with a work of high-quality legal analysis that will recommend biodiversity conservation and public participation-related improvements to the existing Draft Fisheries Law currently on hold in the Duma. - Note: this subcontract could also be converted to a contract for one or more individuals. - Produce output 11 under Output 1 of the Results Framework. - Conduct consultations with stakeholder groups as to best legal approach and key elements needed in legal brief. - Draft legal brief for review - Incorporate comments into legal brief and finalize brief. - Prepare guidelines on strengthening public participation | “Completed” |
| - Revise Kamchatka and Koryak Okrug Fishery Laws so that they are more salmonid diversity-friendly. Main Tasks: - Conduct consultations in Kamchatka among key decision makers to lay the groundwork for such amendments; - Translate existing laws and policies into English; - Work closely with international law and policy advisor, SC members, fish management institutions, and the NGO community on options for strengthening existing law; - Draft proposed changes and circulate for review and secure preliminary agreement on them; - Incorporate changes, stakeholder input and forward revised policies for formal consideration. | Not Planned Salmonids are under the federal government management |
| - Sustainable fishery economics study - Assess values and services provided by salmonids, how to use regulatory incentives to promote conservation. - Generate recommendations for strengthened coastal fishery and for strengthening local peoples' stake in sustainable fishery management | Macro-economic analysis - “On-Going” Micro-economic analysis and recommendations - Planned for 2006 |
| - Develop training materials for diversity-oriented fishery management & conduct training - Conduct consultations on what “diversity oriented fishery management” means in practical terms and secure consensus on the main points. - Identify and describe key fish management actors in need of training - Develop simple, practical training materials for these key actors - Conduct training for up to 30 individuals per year beginning in year 3. | Planned for 2006 in form of developing recommendations to fisheries managers on how better organize diversity friendly fishery |

| Revised Outcome Two River ecosystem integrity is conserved in four sites using a variety of conservation tools and approaches |  |  |  |  |
| --- | --- | --- | --- | --- |
| Indicators | Value in year 0 | Mid-term Target Value (2005) | Status as of April 2006 | End of Project Target Value (2007) |
| Indicator 1: Community partnerships demonstrated for river site management (Protected Area management, Environment protection programs, Incentive program) | Local communities do not participate in river systems protection or management | PA management discussions with indigenous group; | On-Going regular consultations with indigenous people association and communities | Kol River PA partnership; Utkholok River PA partnership; Monitoring partnership involving river keepers. Community development program pilot for one river site area; Environmental and monitoring program underway with high school groups for Bolshaya River. |
|  |  | Annual State of the River reports produced | On-Going River keepers produce regular reports on Sopochnaya river |  |
|  |  | Incentive program concept paper prepared and under consideration. | On-Going Concept paper on communities involvement in costal fisheries management is being discussed and adjusted with key stakeholders |  |
| Indicator 2: New conservation tools applied in protected areas management. | No PAs in the river sites. | Kohl River protected area is being designed in such a way that makes it possible in future to pilot salmon diversity conservation programs. | On-Going Kohl River PA is established. Salmon diversity conservation programs are being developed | Salmon conservation programs are piloted in Kohl. Utkholok protected area is being designed in such a way that makes it possible in future to pilot salmon diversity conservation programs. |
| Indicator 3: Environmental mitigation plan for pipeline and best practices in environmental mitigation introduced to key stakeholders at workshop in PK, strengthening environmental mitigation of development activities in Kamchatka | Construction of the gas pipeline endangers integrity of spawning rivers in Western Kamchatka | Impact assessment completed. Mitigation recommendations and training program under preparation. | Mitigations recommendations prepared. Awareness raising program is being implemented | Key ecological issues discussed among stakeholders. Pipeline company adopts environmental mitigation tools into their work. |

| Output Two: Workplan from Project Document |  |
| --- | --- |
| Target Output/Activities | Status as of April 2006 |
| Target Output 1. Legally established PA in Utholok-Kavachina, Kol-Kekhta, and Bolshaya by end of year 2. | Kohl-Kekhta – Completed Utholok-Kavachina – On-Going Bolshaya – planned for Phase I |
| 1.1 Conduct consultations w/stakeholders and prepare paperwork for PA designation. | Kohl-Kekhta – Completed Utholok-Kavachina – On-Going |
| Target Output 2. Conservation operationalized in each PA. |  |
| - Establish PA infrastructure and demarcate PA boundaries; (biostations?) | Kohl-Kekhta – Completed Utholok-Kavachina – On-Going |
| 2.2 Provide modest equipment. | “On-Going” |
| 2.3 Establish monitoring infrastructure. | “On-Going” |
| 2.5 GoR/KO/KoA fund adequate staff beginning year 4. | Planned for 2007 |
| 2.6 Species and habitat conservation plans developed for 2 sites. | “On-Going” for Bolshaya, Kohl and Utkholok |
| Targeted Output 3: Community partnerships established for river site management by end of year 3. | “On-Going” for Kohl and Utkholok |
| 3.1. Develop & implement cooperative management agreements and plans with user groups in two areas. | “On-Going” for Kohl and Utkholok |
| 3.2 Establish resource user groups for two areas; hire up to two community members in each area as “riverkeepers” for conducting basic, ongoing monitoring of key environmental parameters. | “Completed” for Sopochnaya Not planned for other sites as professional scientific programs are implemented there. |
| 3.3. Local people prepare simple, practical state of the river reports covering environmental, resource use, and socio-economic conditions. | “On-Going” |
| 3.2.3 Training for PA managers in participatory & community-based management and cons biology. | Planned for 2006 together with WSC |
| Targeted Output 4: Poaching of non-commercial salmonid species stopped by end of year 4 in project sites. | “On-Going” |
| 4.1 Conduct anti-poaching patrols to stop harvest of non-commercial species. | “On-Going” in partnership with Sevvostrybvod and Rosselkhoznadzor |
| 4.1.a. Develop community-based enforcement regimes in at least one site and train local stakeholders and fishery managers in these methods. | On-Going on Sopochnaya |
| 4.2 Develop and implement violation tracking database by end of year 3 | Completed |
| Targeted Output 5: Strengthened environmental mitigation of road and pipeline construction and other development activities. a) Environmental mitigation plan for pipeline and best practices in environmental mitigation introduced to key stakeholders at workshop in PK. |  |
| 5.1 Develop plan to mitigate the impact of pipeline construction, including culvert size and construction scheduling recommendations by end of 1st year. | “Completed” Impact assessment completed. Mitigation recommendations prepared. Awareness raising program is being launched |
| 5.2 Integrate salmonid habitat conservation objectives into environmental management plans; | Planned for 2006 |

| Output Two: Output Targets from Project Document Results Framework | Status as of April 2006 |
| --- | --- |
| - Legally established PA in U-K and K-K, and Bolshaya by end of year 2, in Sopochnaya by end of year 3. | Kohl-Kekhta – Completed Utholok-Kavachina – On-Going Bolshaya – planned for PhaseII |
| - Conservation infrastructure established in each PA. Targeted research and monitoring infrastructure established; | “On-Going” |
| - Species and habitat conservation plans developed for 2 sites & research/monitoring conducted. | “On-Going” |
| - Community partnerships established for river site management by end of year 2. | On-Going on Sopochnaya |
| - Annual State of the River reports produced beginning year 2. | Completed on Sopochnaya |
| - Poaching of non-commercial salmonid species stopped in two sites by end of year 4. | “On-Going” |
| - Environmental mitigation plan for pipeline and best practices in environmental mitigation introduced to key stakeholders at workshop in PK, strengthening environmental mitigation of development activities in Kamchatka. | “Completed” Impact assessment completed. Best practices analyzed. Mitigation recommendations prepared. Awareness raising program is being launched |

| Output Two: Indicative Activities – Project Document’s Results Framework | Status as of 2006 |
| --- | --- |
| - Conduct consultations w/stakeholders and prepare paperwork for PA designation. | Kohl-Kekhta – Completed Utholok-Kavachina – On-Going |
| - Demarcate PA boundaries; Establish PA infrastructure/provide modest equipment. Fund modest staffing of two areas through year 3. - SRBVD/KO/KoA fund staffing beginning year 4. | Kohl-Kekhta – Completed Utholok-Kavachina – On-Going In partnership with WSC |
| - Identify priority species and habitats and develop conservation plans for them. | “On-Going” |
| - Establish resource user groups for two areas; hire up to two community members in each area as “riverkeepers” for conducting basic, ongoing monitoring of key environmental parameters. Develop & implement cooperative management agreements/plans with user groups in two areas. Local people prepare simple, practical state of the river reports covering environmental, resource use, and socio-economic conditions. Training for PA managers in participatory & community-based management and cons biology. | “Completed” for Sopochnaya Not planned for other sites as professional scientific programs are implemented there. On-Going on Kohl, Planned on Utkholok Completed on Sopochnaya Planned for 2006 together with WSC |
| - Conduct anti-poaching patrols to stop harvest of non-commercial species. - Develop community-based enforcement regimes in at least one site. Provide training to this end. | “On-Going” in partnership with Sevvostrybvod and Rosselkhoznadzor On-Going onSopochnaya |
| - Integrate salmonid habitat cons objectives into environmental management plans; Develop plan to mitigate the impact of pipeline construction, including culvert size and scheduling recommendations by end of 1st year. | “Completed” Impact assessment completed. Best practices analyzed. Mitigation recommendations prepared. Awareness raising program is being launched |

| Output Two: Contracts | Status as of April 2006 |
| --- | --- |
| Plan appropriate Biostation and Protected Area Management Infrastructure - Secure agreement among key stakeholders as to the most appropriate plans for infrastructure that is good quality but not too expensive to maintain over the long-term. | On-Going |
| Construct biostation and protected area management infrastructure | On-Going |
| Construct and rehabilitate appropriate monitoring infrastructure & equipment | On-Going |
| Conduct diversity-friendly salmonid hatchery demonstration program Bring diversity-friendly hatchery expert to Kamchatka and begin a process of collaboration between Kamchatka based hatchery organizations and North American. | On-Going |
| Develop species and habitat conservation plans for two sites Develop species conservation plans and habitat conservation plans for priority species and habitats in the Kol-Kehta and the Utholok-Kavachina sites. | On-Going |
| Develop and implement anti-poaching enforcement program for non-commercial species. | On-Going |
| Develop and Implement Enforcement Tracking Database | Completed |
| Environmental mitigation plan (This sub-contract to be funded from non-GEF resources.) | Completed |

| Revised Outcome Three Implementation of educational programs, information sharing, preservation of indigenous peoples’ knowledge, and awareness raising build constituencies for salmon diversity conservation in four river sites |  |  |  |  |
| --- | --- | --- | --- | --- |
| Indicators | Value in year 0 | Mid-term Target Value (2005) | Status as of April 2006 | End of Project Target Value (2007) |
| Indicator 1. Level of support for salmonid conservation among school students and general public in Kamchatka. | Not determined. | To be determined through student surveys and public survey. | Determined through sociological poll. | Increased by 20%. |
| Indicator 2: Kamchatka Salmon Ecological Center and other interpretive displays operational. | No visitor center exists; no interpretive materials. | Kamchatka Salmon Ecological Education Center exists and educates 1000 visitors. | Kamchatka Salmon Ecological Education Center premier destination for tour groups; partnerships established with educational institutions, tour companies. | Kamchatka Salmon Ecological Education Center premier destination for tour groups; partnerships established with educational institutions, tour companies. Center on sustainable financial footing. |
| Indicator 3: Salmonid diversity and ecology curricula developed and introduced throughout local school curriculum. | No salmonid diversity education materials or curricula exists in ecological education | Curriculum completed; Officially adopted by Education authorities and Teacher Training University. | Curriculum implemented in 16 schools | Components on salmonid diversity, ecology and sustainable use developed and in use in 20 local schools by year 4 |
| Indicator 4: Indigenous people begin to record knowledge and develop education programs | No databases; No synthesized materials, No interviews of elders to capture knowledge in modern media form; Traditional knowledge not being recorded and learned. | TEK expeditions to indigenous communities; cooperative relationships established with local institute for native languages; use of materials in this institute. | TEK Database available on DVD and CD created | TEK Database available on DVD and CD created and used indigenous communities and associations. |

| Output Three: Workplan from Project Document |  |
| --- | --- |
| Target Output/Activities | Status as of April 2006 |
| Target Output 1. Indigenous people enabled to preserve and maintain their traditional knowledge of biodiversity resources. |  |
| - Communities conduct cultural and biodiversity resource assessments and map information in site areas in a form that can be used and maintained locally. | On-Going |
| 1.3.a. Oral histories and narratives preserved in a way that is accessible to future generations – young people given training in knowledge. | On-Going |
| Target Output 2. Project captures lessons learned and effectively shares them cross-project, cross-agency, cross-country. |  |
| 2.1 Integrate information into national/regional plans and strategies for sustainable development and use of salmonid diversity. | On-Going |
| - Strengthen international linkages for conservation and sustainable fish management and establish an information exchange network. | On-Going |
| 2.3 Establish web-based information exchange; print annual newsletter. | On-Going |
| - Share best practices on web-based information exchange and through exchanges | On-Going |
| - Organize pacific basin conference in collaboration with key national and international partners | Planned for 2006 |
| - Organize lessons learned workshop | Planned for 2007 |
| Target Output 3. Education program developed and implemented. |  |
| 3.1 Design and construct interactive interpretative exhibit on salmonid diversity by end of year 2 with active outreach program w/local schools. | Completed |
| 3.1.a. Hire interpretive display design specialist and develop salmonid diversity interpretive and education center in cooperation with SevesRybvod and K-Niro. | Completed |
| 3.2 Develop and secure adoption of salmonid diversity/ecology/sustainable use curricula by at least 10 middle and high schools by e/o year 3. | Completed |
| 3.3 Develop field guide and an atlas on salmonid diversity. | On-Going |
| 3.4 Organize salmonid field trips/lectures for two school groups per year by e/o year 4. | Planned for 2006 |
| Target Output 4. Synthesis of aquaculture policy analyses already available, aquaculture’s effects on wild salmon, and the importance of wild salmon to the long-term health of salmon farming. |  |
| 4.1 Summarize, synthesize and translate existing analyses of international aquacultural policy and practice for effects on wild salmon. | Completed |

| Output Three: Output Targets from Project Document Results Framework | Status as of April 2006 |
| --- | --- |
| - Indigenous people enabled to preserve and maintain their traditional knowledge of biodiversity resources. | On-Going |
| - Strengthen international linkages for conservation and sustainable fish management and establish an information exchange network | On-Going |
| - Interactive education center designed and finalized and displays by end of year 2 with active outreach program w/local schools. - Salmonid diversity/ecology/sustainable use curricula developed and adopted by at least 10 middle/high schools by e/o year 3. - Field guide and atlas on salmonid diversity. | Completed On-Going |
| - Synthesis of existing analyses of aquaculture policy, its effects on wild salmon, and the importance of wild salmon to the long term health of the farmed salmon business. | On-Going |

| Output Three: Indicative Activities – Project Document’s Results Framework | Status as of April 2006 |
| --- | --- |
| - Communities conduct cultural and biodiversity resource assessments and map information in form that can be used and maintained locally in Sopochnaya and UK sites. - Oral histories and narratives preserved in a way that is accessible to future generations – young people given training in knowledge. | On-Going |
| - Establish web-based information exchange; print annual newsletter. - Organize round table discussions/Pacific basin conference. | On-Going |
| - Hire professional interpretive display design specialist and develop salmonid diversity interpretive and education exhibit in cooperation with SRYBVOD and KNIRO. - Develop curricula and organize field trips/ lectures for two school groups/year by year 2. - Develop field guide and atlas. | On-Going |
| - Summarize, synthesize and translate existing analyses of international aquacultural policy and practice for effects on wild salmon. | Completed |

| Output Three: Contracts | Status as of April 2006 |
| --- | --- |
| Conduct cultural and biodiversity knowledge assessments with indigenous people to map and otherwise secure their knowledge for use and preservation. | On-Going |
| Training/outreach for young indigenous people in art of preserving traditional knowledge | On-Going |
| Develop & secure adoption of diversity educational curricula for local middle and high schools. | Completed |
| Develop field guides & atlas on salmonid diversity | On-Going |

| Revised Outcome Four Stakeholders successfully develop alternative livelihoods in river site areas |  |  |  |  |
| --- | --- | --- | --- | --- |
| Indicators | Value in year 0 | Mid-term Target Value (2005) | Status as of April 2006 | End of Project Target Value (2007) |
| Indicator 1: Local communities pursuing sustainable livelihood options based upon local salmon resources by end year 5. | No tradition of community development rooted in local salmon resources. | Concept paper on community development approach under consideration by stakeholders. | Concept paper on community development is being adapted to existing situation. | Pilot community development program underway in one project site. |
| Indicator 2 Local stakeholder capacity to develop alternative livelihoods being strengthened through access to micro-credit & business training. | No access of local people to micro-credit facilities and business training; No training in business development or management. | Market studies in project sites; Recommendations for development of viable livelihoods made; Five people from project sites trained in business development. | Market studies in project sites; Recommendations for development of viable livelihoods made; Five people from project sites trained in business development. | 20 people from project sites are trained in business development and operate new biodiversity friendly small business successfully. 20 micro-loans in project site areas. |
| Indicator 3: Eco-tourism operating in at least one project site and involving local people in project site. | Ecotourism development is hampered by lack of information. | Assessment of ecotourism potential in project sites underway. | Eco-tourism development program targeted at involvement of local people is being launched. | Ecotourism enterprise successfully operating in at least one project site and employing local people. |
| Indicator 9. Sustainable use incentives and alternative livelihood programs target local population in project sites. | 0% -- Incentive mechanisms do not exist; alternative livelihood options do not exist. | Opportunities identified and programs under development for people in project sites. | Programs under development for people in project sites. | Pilot programs cover local population in two project sites. |

| Output 4: Workplan from Project Document |  |
| --- | --- |
| Target Output/Activities | Status as of April 2006 |
| Targeted Output 1. Indigenous people enabled to access markets for natural resources. |  |
| - Generate recommendations for alternative livelihood options | Completed |
| - Assess market feasibility for goods and help to establish economically viable contacts with wholesaling companies or producers - Russian and international; | On-Going |
| 1.3 Extend micro-credit to viable ideas for marketing and selling of goods (trade posts) | On-Going |
| 1.4 Assess existing fish processing factories for their potential restructuring/use of their assets for establishing new SMEs and devise business plan for one if appropriate. | Not Planned as fish processing is effectively done by existing businesses |
| Targeted Output 2. Pilot model alternative livelihood options in priority areas. |  |
| 2.1 Enable local communities to develop business plans and pursue sustainable livelihood options using micro-credit & business training by e/o year 3. | On-Going |
| 2.2 Eco-tourism demonstration on the Sopochnaya or U-K rivers involves at least 20% of the stakeholders, establishing routes, infrastructure, trained guides and service folks. | On-Going Eco-tourism development program is being launched. |
| 2.3 Indigenous people strengthen their animal husbandry livelihoods. | On-Going Rain deer herding development program is being prepared for KAO. |
| 2.4 Develop pilot program to strengthen coastal salmonid fishery by increasing quotas for coastal community stakeholders. | On-Going |
| 2.5 Develop biodiversity guidelines for eco-tourism enterprise development. | On-Going |
| 2.6 Bring in an advisor on traditional/alternative fishery options to work in the SME Fund of the PA project; | Completed Consultant on community based fishery development was hired |
| 2.7 Demonstrate diversity-friendly fishing techniques and equipment. | On-Going Fly fishing development program is being launched |
| 2.8 Conduct small and medium enterprise development training | On-Going |

| Output Four: Output Targets from Project Document Results Framework | Status as of April 2006 |
| --- | --- |
| - Market study clarifies what the viable markets are for local resources. | On-Going |
| - Market links established for local resources. | On-Going |
| - Local communities pursuing sustainable livelihood options (e.g. accessing micro-credit & business training) by end year 3. | On-Going |
| - Eco-tourism demonstration on the Sopochnaya and U-K rivers involves at least 25% of the stakeholders (establishing routes, modest infrastructure, trained guides). | On-Going Eco-tourism development program is being launched. |
| - Indigenous people strengthen their animal husbandry livelihoods. | On-Going Rain deer herding development program is being prepared for KAO. |

| Output Four: Indicative Activities – Project Document’s Results Framework | Status as of April 2006 |
| --- | --- |
| Conduct small and medium enterprise development training | On-Going |
| Extend micro-credit program for alternative livelihood investment. | On-Going |
| Strengthen traditional livelihoods among indigenous groups | On-Going |
| Develop biodiversity guidelines for eco-tourism enterprise development. | On-Going |
| Demonstrate diversity-friendly fishing techniques and equipment. | On-Going |

| Output Four: Contracts | Status as of April 2006 |
| --- | --- |
| Conduct market study and establish links to viable markets for local resources. | On-Going |
| Demonstrate diversity-friendly fishing techniques/ methods/equipment - Pilot strengthened coastal fishery and strengthened property rights of local people. | On-Going |

| Revised Outcome Five Sustainable financing for salmonid conservation |  |  |  |  |
| --- | --- | --- | --- | --- |
| Indicators | Value in year 0 | Mid-term Target Value (2005) | Status as of April 2006 | End of Project Target Value (2007) |
| Indicator 1: Salmonid Diversity Conservation Fund legally established by end of year 3 | No sustainable financing mechanisms for diversity conservation exist | Conservation Fund registered. | Conservation Fund internal policies, regulations and structural framework are being developed. | Salmonid Diversity Conservation Fund legally established |
| Indicator 2: Commitments for Fund endowment. | No funding for long-term mechanism. | Best funding prospects identified. | Fund-raising opportunities identified. Two Kamchatka based pilot fund-raising programs are being launched. | Preliminary commitment of US $1.5 million obtained |

| Output Five: Workplan from Project Document |  |
| --- | --- |
| Target Output/Activities | Status as of April 2006 |
| Target Output 1: SDCF legally established by beginning of year 3. |  |
| 1.1 Trust Fund expert conducts stakeholder consultations on fund purpose, design, structure. | On-Going |
| 1.2 Draft structure proposed and considered by year middle year 2. | On-Going |
| 1.3 Draft structure accepted by Steering Committee by middle year 3. | Planned for 2006-2007 |
| 1.4 Kamchatka-based sport fishing funding mechanism established by end of year 3. | On-Going |
| Target Output 3: Preliminary commitment of $1.5 million to the fund by end of year 4. |  |
| 3.1 Promotional material produced; Professional fund raising efforts target most promising investors. | On-Going |

| Output Five: Output Targets from Project Document Results Framework | Status as of April 2006 |
| --- | --- |
| - SDCF legally established by e/o year 3. | Completed |
| - Kamchatka-based, sustainable angling funding mechanism established by end of year 3. | On-Going |
| - Preliminary commitment of $1.5 million to the fund by end of year 4. | On-Going |

| Output Five: Indicative Activities – Project Document’s Results Framework | Status as of April 2006 |
| --- | --- |
| Trust Fund expert conducts stakeholder consultations on fund purpose, design, structure. | On-Going |
| Devise detailed structure of fund and circulate for review. | On-Going |
| Fund structure designed/approved. | On-Going |
| Promotional material produced; Professional fund raising efforts target most promising investors. | On-Going |

| Output Five: Contracts | Status as of April 2006 |
| --- | --- |
| Secure funding for the Salmonid Diversity Conservation Fund Produce promotional material; Target most promising investors & Secure funding commitments. | On-Going |

Project Implementation and Management:  Outcome and Indicators Matrix

No outcome and indicators matrix provided.

| Project Implementation and Management: Workplan from Project Document |  |
| --- | --- |
| Target Output/Activities | Status as of April 2006 |
| 1. Conduct regular steering committee meetings | On-Going |
| 2. Report on project progress per UNDP requirements. |  |
| - Preparation of an Inception report | Completed |
| - Prepare Annual Project Report (APR) at the end of each year | On-Going (2004, 2005) |
| - Conduct annual Tripartite Reviews (TPR) | On-Going (September 2004, October 2005) |
| - Prepare Project Implementation Review (PIR) reports prior to | On-Going |
| - Terminal evaluation for Phase I | On-Going |
| 3. Ongoing review and analysis of project’s work and experiences to develop best practices. | On-Going |
| 4. Organize round table discussions. | On-Going |
| 5. Prepare for second phase of the project by drafting project brief by end of year 3. | Planned for 2006 |
| 6. Submit project brief for second phase by beginning of year 4. | Planned for 2006 |

| Project Implementation and Management: Output Targets from Project Document Results Framework | Status as of April 2006 |
| --- | --- |
| Regular PSC meetings and guidance | On-Going |
| Report on Inception report | Completed |
| Annual Project Report (APR) | On-Going (2004, 2005) |
| Annual Tripartite Reviews (TPR) | On-Going (September 2004, October 2005) |
| Annual review of project’s work experiences and assessment of best practices. | On-Going |
| Second phase of project brief prepared by end of year 3. | Planned for 2006 |

| Project Implementation and Management: Indicative Activities – Project Document’s Results Framework |  |
| --- | --- |
| Indicative Activities | Status as of April 2006 |
| Conduct regular steering committee meetings; | On-Going |
| Report on project progress per UNDP requirements; | On-Going |
| Prepare an Inception report; | Completed |
| Prepare Annual Project Report (APR); | On-Going (2004, 2005) |
| Conduct annual Tripartite Reviews (TPR); | On-Going (September 2004, October 2005) |
| Prepare Project Implementation Review (PIR) reports prior to terminal evaluation for Phase I; | Completed |
| Ongoing review and analysis of project’s work and experiences to develop best practices; | On-Going |
| Organize round table discussions; | On-Going |
| Prepare second phase project brief by e/o year 3; | Planned for 2006 |
| Submit project brief for second phase by beginning of year 4. | Planned for 2006 |

| Project Implementation and Management: Monitoring, Reporting and Evaluation |  |
| --- | --- |
| Activity | Status as of April 2006 |
| Baseline surveys: Determine the nature and extent of threats in each site to be reduced; Conduct ecological surveys within the site areas to determine specific health and size of key habitats and richness of habitat mosaic; Conduct attitude and awareness level surveys of key stakeholder groups, from top-level policy makers to local village level stakeholders; and, Conduct economic surveys of local communities around site areas to quantify their use of resources and their current income levels. | Completed On-Going On-Going Completed |
| Indicators: - Threat reduction and prevention, and; - Salmonid ecosystem/biodiversity health. | On-Going Completed – ecosystems health indicators developed |
| National Project Director | Exists |
| Steering Committee | Functioning |
| Local Stakeholder Groups | Indigenous group is functioning |
| 3. Mid-Term Evaluation | On-Going |
| 4. Final Evaluation | Planned for 2007 |

| Project Implementation and Management: Professional Staff and Consultants |  |
| --- | --- |
| Position | Status as of April 2006 |
| National Professionals |  |
| Project office manager/Administration | Exists |
| Project Manager | Exists |
| Re-oriented biodiversity-friendly fishery officer | Exists |
| Community participation/Impact assessment officer | Exists |
| Website building/management/computer support | Exists |
| Education/Awareness program manager | Exists |
| Project Accountant (3 mos year) | Exists |
| River keepers | Exist on Sopochnaya |
| Synthesize data from inventories into standard format | Completed |
| Biodiversity field survey team short-term experts | Exist |
| Protected area designation expert(s) | Exists |
| Diversity monitoring/research (experts) | Exists |
| Salmonid Diversity Conservation Fund Expert | Exists |
| International Professionals |  |
| - Advisor on int'l experience w/environmental policy | Not identified |
| - Community-based Management Expert | Exists |
| - Educational/interactive Exhibit Expert | Changed to study tour in Oregon for identifying best int’l practices |
| - Salmonid Diversity Conservation Fund Expert | Provided by PA Project |
| - Adaptive Management Advisor | Exists |
| - Unspecified expertise | Provided as necessary |

| Planned Training and Workshop Activities from Project Document |  |
| --- | --- |
| Training and Workshops | Status as of April 2006 |
| - Salmonid value assessment and diversity management practices | On-Going |
| - Protected area establishment roundtables | On-Going |
| - Amending Kam and Koryak O's laws on fisheries | Not relevant |
| - Trust fund consultations/workshops | On-Going |
| - Re-orienting fishery management regimes for diversity management | Planned for 2006 |
| - Participatory, community based management training for PA managers/stakeholders | Planned in partnership with WSC and PA Project |
| - Environmental mitigation plan workshop | On-Going meetings and consultations |
| - Salmonid diversity conservation conference | Planned for 2006 |
| - Steering Committee Meetings | On-Going regular meetings |
| - Lessons Learned Round Table | Planned |
| - Replication knowledge transfer, cross organizational learning | Planned |

Project Reports

OUTCOME 1

Final documents

1. A Brief on Current Condition of Salmonid Biological Diversity in UNDP/GEF Project River Sites (Leman V.N.). 2004. – 37 p.

2. Impact of estuary ecosystems on number of salmon generations. The Bolshaya River. Industrially-impacted transformation of the Bolshaya River Estuary hydrological regime (Gorin S.L., Podpiadukhin А.А., Leman V.N.). Final Report,  2004-2005  // Petropavlovsk-Kamchatsky, Moscow: UNDP/GEF Project , VNIRO, KamchatNIRO, 2005.

3. Socio-Economic and Environmental Aspects of the development of salmon potential in the Bolshaya River basin. (M.Yu. Dyakov, E.I. Shirkov, E.E. Shirkova). Petropavlovsk-Kamchatsky: UNDP/GEF Project «Conservation and Sustainable Use of Wild Salmonid Biological Diversity in Kamchatka’s Peninsula» , 2005. – 50 p.

Progress Reports

4. Ecosystems of small spawning rivers of Kamchatka. Reference Watercourse – the Nachilova River. Salmonid Community and Habitat. Report, 2004 - 2005. (Esin Е.V., Chalov  S.R., Chebanova V.V., under leadership of V.N. Leman). Petropavlovsk-Kamchatsky: UNDP/GEF Project  "Conservation and Sustainable Use of Wild Salmonid Biological Diversity in Kamchatka’s Peninsula", VNIRO , 2005. - 154 p.

5. Salmonid diversity and habitat research in the Bolshaya River. Inventory and biotopic zoning of the river site. Report, 2005 . (Esin, Е.V., Chalov S.R., Sorokin Yu.V., Manukhov А.V., under leadership of V.N. Leman). Petropavlovsk-Kamchatsky: UNDP/GEF Project  "Conservation and Sustainable Use of Wild Salmonid Biological Diversity in Kamchatka’s Peninsula", VNIRO, 2005. – 178 p.

6. Salmonid diversity research at UNDP project sites “Kol/Kekhta” and “Utkholok/Kvachina”. Report,  2004 – 2005 (D.S.Pavlov, Ac.,  К.А.Savvaitova, Prof.,   R.V.Kuzishin, Prof., S.D. Pavlov, М.А. Gruzdeva, s.s.,P.I. Kirillov, А.Yu. Maltsev, Е.А. Maslova) // Moscow: ichthyology department of Moscow State University, 2005.

7. GIS Development: Conservation And Sustainable Use Of Kamchatka Salmonids. Text  part. Project river sites “the Bolshaya”, “the Sopochnaya”,  “the Kol/Kekhta”  and “the Utkholok/Kvachina”. Local GIS data bases “The Nachilova River”, “Salmon Hatcheries”, “Sport fishing and Angling”, “the Bolshaya River Estuary”, “Cross country gas pipeline”. I and  II stages// Petropavlovsk-Kamchatsky: UNDP/GEF Project  "Conservation and Sustainable Use of Wild Salmonid Biological Diversity in Kamchatka’s Peninsula", KamchatNIRO, Sevvostrybvod, 2005. – 27 p.

8. Design layout of Kamchatka Juvenile Salmonid Identification Atlas. Spreads of Chinook, White-spotted Char and Masu salmon. Electronic version// Moscow, Petropavlovsk-Kamchatsky: UNDP/GEF Project , VNIRO, 2005. – 20 p.

9. Development Of Demonstration Program On Sustainable And Conservation-Oriented Salmonid Hatchery Management  And Production. The Bolshaya River Basin. Salmon hatcheries. 1 stage// Petropavlovsk-Kamchatsky, Moscow: UNDP/GEF Project  "Conservation and Sustainable Use of Wild Salmonid Biological Diversity in Kamchatka’s Peninsula", Sevvostrybvod, VNIRO, KamchatNIRO, 2005. – 185 p.

10. Sport fishing and Angling. Assessment of sport fishing capacity and sport fishing resource health (steelhead, white-spotted char, grayling, Chinook, Coho). The Bolshaya River Basin. The Bystraya River. Report, 2004 - 2005. (Shatilo I.V., Leman V.N.) // Petropavlovsk-Kamchatsky: UNDP/GEF Project  Conservation and Sustainable Use of Wild Salmonid Biological Diversity in Kamchatka’s Peninsula, KamchatNIRO, Sevvostrybvod, 2005.

11. Current condition and industrially-induced transformation of Tolmachev aquatic ecosystem caused by construction and operation of hydroelectric plants. Report, 2004-2005. (Leman V.N., Markevitch G.B.) // Petropavlovsk-Kamchatsky : UNDP/GEF Project  Conservation and Sustainable Use of Wild Salmonid Biological Diversity in Kamchatka’s Peninsula, KamchatNIRO, VNIRO , 2005.

12. A practical guide to construction of conservation-oriented watercourse crossings across fishery rivers (Leman V.N., Muzurov Е.L.) // Petropavlovsk-Kamchatsky: UNDP/GEF Project  Conservation and Sustainable Use of Wild Salmonid Biological Diversity in Kamchatka’s Peninsula, KamchatNIRO, VNIRO , 2005.

13.  Investigation of sustainable and conservation-oriented salmonid resource economy (Bobylev, Kasyanov, Stetsenko) // Moscow: UNDP/GEF Project  “Conservation and Sustainable Use of Wild Salmonid Biological Diversity in Kamchatka’s Peninsula”, economics department of MSU, 2005.

14. “Analysis and Strengthening of Federal Legislation, Kamchatka Legislation, Legislation of Koriakia Autonomous Okrug and Departmental Regulatory Documents to implement  Conservation and Sustainable Use of Kamchatka Salmonid Diversity”

(B.V. Kokotov)// Moscow: UNDP/GEF Project  “Conservation and Sustainable Use of Wild Salmonid Biological Diversity in Kamchatka’s Peninsula”, OOO “Center of Legal Groundwork for Nature Use”, 2004-2005.

15. Development of Pacific Salmon Multi-Species Fishery Strategy Based on Differentiated Approach to Determination of Pacific Salmon Population Groupings in the West Kamchatka Region  (Е.А. Shevliakov, V.G. Davidov) // Petropavlovsk-Kamchatsky: UNDP/GEF “Project  Conservation and Sustainable Use of Wild Salmonid Biological Diversity in Kamchatka’s Peninsula”, KamchatNIRO, 2005.

OUTCOME 2

1. Materials for salmonid/habitat impact mitigation plan and certification of watercourse crossings. Cross-country gas pipeline construction phase "Kshuk gas condensate field – Petropavlovsk-Kamchatsky  and  motorway “Karimay settlement – Sobolevo village” V category. Book 1. Recommended plan of activities. Text part. Book 2. Certificates of watercourse crossings. Report,  2004 г. (V.N. Leman, Е.L. Muzurov). Petropavlovsk-Kamchatsky: UNDP/GEF Project «Conservation and Sustainable Use of Wild Salmonid Biological Diversity in Kamchatka’s Peninsula», Sevvostrybvod, KamchatNIRO, 2004. – 205 p.

2. Fishery underpinning for the Kol Salmon Refuge Design (the Kol/Kekhta river basins). Fishery certification. Fishery zoning. Functional zoning. Resource use regimes. Scientific Research Work Program. Maps. (Leman V.N., Vronsky B.B., Loshkareva А.А., Chalov S.R., Ulatov А.V.) // Petropavlovsk-Kamchatsky, 2005. – 63 p.

OUTCOME 3

1. Development and tutorial assistance in introducing Kamchatka Salmon elective education course into secondary schools of Kamchatka Oblast (М.P. Kulakova, Е.А. Maksimenko, А.V. Volkov). Petropavlovsk-Kamchatsky: UNDP/GEF Project «Conservation and Sustainable Use of Wild Salmonid Biological Diversity in Kamchatka’s Peninsula», Institute of Teachers Improvement, 2005.

2. Traditional knowledge and their importance for Kamchatka salmonid diversity conservation / Kamchatka State University, Muradov S.V. – 2005-2006  (under preparation). Report includes 115 pages, 8 pictures, 12 sections and 136 references.  TEK data base

3. Final Report of Kovran-based Ecological Center (Tigil district), Kruchinina L.K., Nedotopa М.М., Project  Coordinator, Shupakova V.S., Director of Ecological Circle. Period of 01.10. 2004 through 31.03. 2005.

4. Kovran-based Ecological Center (Tigil district), Kruchinina L.K., Nedotopa М.М., Project  Coordinator, Shupakova V.S., Director of Ecological Circle. Period of 01.07. 2005 through 31.12. 2005.  Final report and TEK materials are under preparation.

OUTCOME  4

1. Prospects of alternative livelihoods development on river sites in KO and KAO / Kamchatka State Technical University, Management  Department, Work director Оgiy О.G. - 2005  (Agreement #1 of 15.07.2004)

2.  Concept Paper  Community Development in Kamchatka/ Norman A. Cohen Community-based Development Management Advisor – 2005

OUTCOME 5

# 1.  Sustainable Financing Mechanisms for Kamchatka Biodiversity Conservation Trust Fund (G.А.Mazmaniants, I.А.Prokhorova) // Moscow, Petropavlovsk-Kamchatsky, January – June 2005

Project Steering Committee

Members

1.   Elena Armand Head of UNDP Environment Unit

2.   Alexander  Chistyakov   The First Deputy Governor of Kamchatka Oblast

3.   Nikolai Tokmantsev Chairman of the Soviet of Peoples’ Deputies of Kamchatka  Oblast

4.   Nikolay Gavrilov  Administration of the Koriak Autonomous Okrug, vice- governor

5.   Mikhail Korolyov  Director a.i. of Sevvostrybvod

6.   Sergey Maksimov Representative of  Federal Agency of Fishery

7.   Yuri Garaschenko  Ministry of Natural Resources of the Russian Federation

8.   Dmitry Berezhkov The President of Association of Indigenous Peoples of  Kamchatka Oblast

9.   Andrei Klimenko Kanchatka Programs Director of the Wild Salmon Center

10.  Dmitry Pavlov Moscow State University, Head of the sub-faculty of  ichthyology

11.  Nikolaiy Antonov  Director of KamchatNIRO

12.  Tamara Kurinova Head of Kamchatka Regional Council of  All-Russian  Association for Wildlife Conservation

Participants

1.  	Uriy Netchitailov  Deputy Head of Natural Recourses Environmental Protection  Department of Kamchatka Oblast

2.  	Alexander Michaylov Deputy governor, Chief  of Public Relations Department of  Kamchatka Oblast

3.  	Tamara Tutushkina  Chief of the Department of external economic links and tourism  of Administration of Kamchatka Oblast

4.  	Robert Moiseev  Director of Kamchatka Branch of the Pacific Institute of  Geography

5.  	Vyacheslav  Bondarenko   Deputy Chairman of the Soviet of People`s Deputies of  Kamchatka Oblast

6.  	Yury Karmadonov  Project Manager of  UNDP/GEF “Demonstrating Sustainable  Conservation of Biological Diversity in Four Protected Areas of  Russia`s  Kamchatka Oblast”

7.  	Olga Chernyagina  The President of Kamchatka League of Indepebdant Experts

8.  	Dmitry Berezhkov The President of Association of Indigenous Peoples of  Kamchatka Oblast

9.  	Oleg Zaporotsky The President of the Council of Itelmens of Kamchatka  “Tkhsanom”

10.  Vyacheslav  Zvyagintsev  General Director of ecological Fund “Wild Fish and  biodiversity”

11.  Evgeny Muzurov  Executive Director of the Foundation of protection of costal  ecosystems and sustainable fishery of Kamchatka

12.  Greg Block  Conservation Director of Wild Salmon Center

13.  Evgeniy Shevlyakov    KNIRO

14.  Vladimir Pischelev Deputy National Director

15.  Alexander  Tchumikov  General Director of  «International Press Club», SCS

16.   Evgeniy Lobkov  Administration of Elizovo Municipal Entity

Itinerary and List of Persons Interviewed

March 27 – April 10, 2006

Date	Activity

Monday, March 27	Depart Montana, USA

Tuesday, March 28	Arrive Moscow Russia

Teleconference:

- Guido Rahr, Wild Salmon Center

- Andrey Klimenko, Wild Salmon Center

- Jeffrey Griffin, UNDP/GEF Senior Expert

- Elena Armand, UNDP

- Nataly Olofinskaya, UNDP

- Vladimir Pischelev, Salmonid Diversity Project:

Wednesday, March 29 	UNDP Country Offices:

- Elena Armand

- Nataly Olofinskaya

- Vladimir Pischelev

FGUP "VNIRO": (Working group on  salmonid diversity study)

        - Dr. Vsevolod Leman, Leader of the biodiversity research project team

        - Dr. Kotenev, Director of the Russian Federal Research Institute of Fisheries and Oceanography

        - Dr. Vasily Sokolov, Deputy Director of the Russian Federal Research Institute of Fisheries and Oceanography

        - Alia Loshkareva, GIS expert

Thursday, March 30	Visit of “Rosselkhoznadzor”  (a Federal Service for state control for fisheries and veterinaries under auspicious of Russian Ministry of Agriculture)

Mr. Gregory Kovalyov, deputy head

Vladimir Arseniev, department head of “Rosselkhoznadzor”

Sergey Uvarov, head of the division fore fish protection

Russian Federal Fishery Agency:

Mr. Sergei Maksimov, head of  water bio-recourses expeditionary research,  project  curator representing the National Project Director

Conservation Economic Studies Research Group,

Sergey Bobylev, Economics of Natural Resources and Environment, Faculty of economics  , sbobylev@rclm.ru Moscow State University;

- Pavel Kasianov,  a consulting firm for Environmental  economics

Friday, March 31 	FGUP "VNIRO":

        - Dr. Vsevolod Leman, Leader of the biodiversity research project team

        - Alexandra Loshkareva, GIS expert

Saturday, April 1	Arrival Petropavlovsk-Kamchatski

Sunday, April 2 	Meeting in the Project Office, discussion of the visit program, discussion of key-issues.

- Mr. Evgeny Svyazhin, Project Manager

- Mr. Vladimir Pischelev, Project National Director Assistant

Monday, April 3 	Work in the project office, review of documentation,  interviews with the project team:

- Mr. Evgeny Svyazhin, Project Manager

- Mr. Vladimir Pischelev, Project National Director Assistant

- Mr. Evgeny Muzurov, Deputy Project Manager

- Ms. Victoria Sharakhmatova, alternative livelihoods development officer

Indigenous Information Centre «Lach»:

- Mr. Dmitry Berezhkov,  Chief of Association of Minor Peoples of the North

- Nina Zaporotskaya, Indigenous information center “Lach”

- Interviews with indigenous community representatives

Tuesday, April 4 	Kamchatka Branch of Pacific Geography Institute FED RAS (KFTIG):

- Mr. Robert Moiseev, Director

“Rosprirodnadzor” (Natural Resources and Environment Protection Agency of MNR RF for Kamchatka Oblast and Koryak Autonomous Okrug):

- Mr. Anatoliy Matvienko, Deputy Head

Administration of Kamchatka Oblast:

- Mr. Yuri Starikov, Head of Fishery Department

Kamchatka Regional Council of All-Russian Association for Wildlife Conservation

Ms. Tamara Kurinova, Chairwoman

Kamchatka Biodiversity Conservation  Fund and SME SF “Sodruzhestvo”:

- Ms. Svetlana Prosina, Director

- Ms. Tatiana Oborskaya, fundraising expert of Kamchatka biodiversity conservation fund

Wednesday, April 5	“Rosselkhozdnadzor” (Kamchatka regional body of Federal Service for state control for fisheries and veterinaries )

- Alexandr Kriukov, Deputy Head

- Alexey Naumov, Deputy Head

Project site visit:

- Bolshaya River, Malki Hatchery

Thursday, April 6

Kamchatka Salmon Education Center:

- Ms. Margarita Kulakova, project expert on ecological education

FGU “Sevvostrybvod” (Northeastern Fishery Monitoring Service)

-  Alexandr Firsov, Deputy Head

- Alexandr  Kaliuzny, Deputy Head of sport fishing division

Visit to secondary school. Demonstration of the elective course «Kamchatka Salmon»

Visit to «KamchatNIRO»:

Mr. Nikolai Antonov, director

Friday, April 7 	Discussions with Project Management Team

- Mr. Evgeny Svyazhin, Project Manager

- Mr. Vladimir Pischelev, Project National Director Assistant

Wild Fishes and Biodiversity Foundation

Mr. Vyacheslav Zvyagintsev, director

Saturday, April 8	Field Trip

Sunday, April 9	Depart Petropavlovsk-Kamchatski Transit, Vladivostok, Russia

Monday, April 10	Return to Montana, USA

Additional Communication

Electronic and telephone communication was made with the following persons periodically during the process of review.

- Project Management Staff

- UNDP/GEF Regional Office

- Jeffrey Griffin, Senior Expert, UNDP/GEF

- Staff of Wild Salmon Center

- Dr. Michael Schwartz, Genetist, USFS

- Several international fly-fishing operators

DRAFT

Terms of Reference

for the

Mid-term Evaluation of the UNDP/GEF Project

“Conservation and Sustainable Use of Wild Salmonid Biological Diversity in Russia’s Kamchatka Peninsula. Phase I”

00014641

# 1. Introduction

## Standard UNDP/GEF Monitoring and Evaluation requirements

The Monitoring and Evaluation (M&E) policy at the project level in UNDP/GEF has four objectives: i) to monitor and evaluate results and impacts; ii) to provide a basis for decision making on necessary amendments and improvements; iii) to promote accountability for resource use; and iv) to document, provide feedback on, and disseminate lessons learned. A mix of tools is used to ensure effective project M&E. These might be applied continuously throughout the lifetime of the project – e.g. periodic monitoring of indicators -, or as specific time-bound exercises such as mid-term reviews, audit reports and final evaluations.

In accordance with UNDP/GEF policies and procedures, projects with long term implementation periods or standing at any other critical milestone of project implementation are strongly encouraged to conduct mid-term evaluations. In addition to providing reviews of the implementation process, the evaluation is responsive to GEF Council decisions on transparency and better access of information during the implementation. Evaluations are intended to identify project design problems and to be conducted by an independent evaluator not associated with the implementation of the project.

## Project objectives

The objective of this project is the sustained conservation of salmonid genetic and life history diversity and the maintenance of river ecosystem integrity in four river systems on Russia’s Kamchatka Peninsula.  Upon successful completion of the project, stakeholders will devise innovative and adaptive ecosystem management practices to mitigate and prevent threats, and apply new partnerships, conservation tools, information, and sustainable livelihoods to conserve salmonid diversity.

GEF support will secure the global benefits of conserving salmonid diversity of actual and potential value for food and aquaculture.  Russian and international partner co-financing provides the crucial foundation for GEF’s incremental investment by enhancing the sustainability of the existing economic development baseline.  This project is designed to be implemented in two phases, each with its own distinct achievements; this project document requests GEF funding for Phase I.  If supported by an independent results-based evaluation of the Phase I, GEF funding will be requested to support the incremental costs of the second and final phase (Phase II).

Phase I of the project will enable stakeholders to make the financial and policy commitments necessary, protect crucial salmonid habitat by establishing protected areas and participatory management regimes, construct a diversity information baseline by conducting field surveys, lay the foundation for long-term financing of salmonid diversity conservation, pilot diversity-friendly commercial fishing practices and sport-fishing ecotourism, forge new partnerships among local and international stakeholders, and strengthen the capacity of civil society institutions.  Phase II would consolidate the achievements of Phase I.  For example, during Phase II stakeholders would consolidate policy and program commitments made during Phase I by adopting participatory approaches to river system management and securing partnerships for cooperative research, salmonid habitat management, and eco-tourism business development.  Equally important, during Phase II the long-term financing mechanism for salmonid conservation would be permanently established and funded primarily by non-GEF, partner financing.

Project location: Petropavlovsk-Kamchatsky, Kamchatka Oblast, Koryak Autonomous Okrug

Project sites: four river systems along the Western Coast of the Kamchatka Peninsula: 1) the Bolshaya; 2) the Kol/Kekhta; 3) the Sopochnaya; and 4) the Utkholok/Kvachina.

The main expected outputs of the project are:

Improved fishery management practices for salmonid diversity conservation purposes

River ecosystem integrity is conserved in four sites using a variety of conservation tools and approaches

Implementation of educational programs, information sharing, preservation of indigenous peoples’ knowledge, and awareness raising build constituencies for salmon diversity conservation in four river sites

Stakeholders successfully develop alternative livelihoods in river site areas

Sustainable financing for salmonid conservation

The project is executed by the Ministry of Agriculture of the Russian Federation (MA) with direct joint participation of the Kamchatka fishery committee (Sevvostrybvod) and Kamchatka Oblast Administration (KOA). A US-based conservation NGO Wild Salmon Centre (WSC) is an important partner providing parallel co-financing to the project. The implementation of project activities are done by a Project Implementation Unit situated in Petropavlosk, Kamchatka, and overall management of the project is the responsibility of Project Manager, who is a full time employee of the project.

# 2. Objective and purpose of the Mid-Term Evaluation

The evaluation is intended to provide a comprehensive overall assessment of the project and provides an opportunity to critically assess administrative and technical strategies, issues and constrains associated with large international and multi-partner initiatives. The evaluation should also provide recommendations for strategies, approaches and/or activities to improve the potential of the Project to achieve expected outcomes and meet objectives within the Project timeframe. Findings of this review will be incorporated as recommendations for enhanced implementation of the current project phase in the future years as well as for the design of the subsequent project phases.

The purpose of the Mid-Term Evaluation is:

To assess overall performance against the Project objectives as set out in Project Document and other related documents

To assess the effectiveness and efficiency of the Project

To critically analyze the implementation and management arrangements of the Project

To list and document initial lessons concerning Project design, implementation and management

To assess Project outcomes to date and review planned strategies and plans for achieving the overall objectives of the Project within the timeframe

To assess Project relevance to national priorities

To provide guidance for the future Project activities and, if necessary, for the implementation and management arrangements.

In particular, this evaluation will assess progress in establishing the information baseline, reducing threats, and identifying any difficulties in project implementation and their causes, and recommend corrective courses of action.  Effective action to rectify any identified issues hindering implementation will be a requirement prior to determining whether implementation should proceed.

Project performance will be measured based on the quantitative and qualitative indicators (see Annex 2).  Many of these indicators relate to the reduction/prevention of the key threats to biodiversity in each of the four sites.  Other indicators to be considered are defined in the Logical Framework and the Results Framework of the Project Document.  The logical framework for this project sets out a range of impact/implementation indicators that will be used to gauge impact.  Success and failure will be determined in part by monitoring relative changes in baseline conditions established during year one of the project.  Where possible, indicator species that are sensitive to habitat change and indicative of increased pressure should be identified and monitored.  If populations of rare or endangered species are shown to be in decline, measures will be taken to identify the reason for the decline, and alternative management strategies will be developed to ensure the long-term health of populations and incorporated into site management.

The Report of the Mid-Term Evaluation will be stand-alone document that substantiates its recommendations and conclusions.

The Report will be targeted to meet the evaluation needs of all key stakeholders (GEF, UNDP, MA, Sevvostrybvod, KOA, WSC, PSC, indigenous groups, and other stakeholders in Kamchatka, in  Russia and internationally).

# 3. Evaluation

Project elements to be evaluated include:

## Project Management and Administration

Collect, document and assess relevant elements and processes including:

- Project related administrative procedures

- Key decisions and outputs

- Major project implementation documents prepared with an indication of how the documents and reports have been useful

Assess processes to support national components and transboundary dimension of the project

## Project Substantive and Technical Implementation

### 1. Project Delivery

The evaluation will assess to what extent the Project has achieved its immediate objectives. It will also identify what outputs have been produces and how they have enabled the Project to achieve its objectives.

This section will focus on following priority areas:

#### Progress of the Project as whole in achieving anticipated outcomes:

- Efficiency of Project activities

- Progress in achieving of immediate objectives (level of indicator achievements when available – with reference to the project’s Logical Framework for indicators – see Annex 2.)

- Interim results with regard to the indicators of progress;

- Quality of Project activities

#### Partnership:

Assessment of collaboration between governments, intergovernmental and non-governmental organizations

Assessment of collaboration between implementation units of other related projects (in particular, UNDP/GEF project “Demonstrating sustainable conservation of biodiversity in four protected areas in Russian Kamchatka oblast” and projects of the WSC)

Assessment on national-level involvement and perceptions

Assessment of local partnerships

Transfer of capacity to the national institutions;

Assessment on involvement of stakeholders

### 2. Project Implementation

The Evaluation Team will be provided with an explanation of the implementation structure of the project by MA and KOA and UNDP (on need basis).

This section will focus on following areas of implementation:

#### Project oversight:

- MA / Sevvostrybvod / KOA

- PIU in Petropavlosk

- UNDP

- Steering Committee

#### Project Execution:

MA as executing agency (under the UNDP NEX )

PIU (efficiency of project management, including the delivery of inputs in terms of quality, quantity and timeliness; and the monitoring system)

#### Monitoring and evaluation:

Has there been a monitoring and evaluation framework for the project, is it efficient?

Is the reporting framework effective/appropriate?

Is this framework suitable for replication/continuation for any future project support?

#### Risk Management:

Identify problems/constraints which have impacted or might have impact on the successful delivery of the Project

Are they likely to repeat or occur in next phase?

### 3. Project finances

Review the changes to fund allocations as a result of budget revisions and provide an opinion on the appropriateness and relevance of such revisions, taking into account the project activity timeframe

Review the effectiveness of financial coordinating mechanisms

# 4. Methodology for Evaluation Approach

The mid-term Evaluation will be done through a combination of processes including a desk study, site visit and interviews  - involving all stakeholders (but not restricted to): MA/Sevvostrybvod, KOA, UNDP, WSC, Government officials on different levels, local municipalities, local NGO’s, communities etc.

Evaluators should seek guidance for their work in the following materials, which could be found at (www.undp.org/gef):

- UNDP Handbook on Monitoring and Evaluation for Results

- UNDP/GEF M&E Resource Kit

- Measuring Results of the GEF Biodiversity Programme

The methodology for the evaluation is envisaged to cover the following areas:

Desk study review of all relevant Project documentation

Consultations with MA/Sevvostrybvod / KOA, UNDP , PIU

Site visit (Moscow and Petropavlovsk-Kamchatsky)

Interviews with stakeholders

- Russian Ministry of Agriculture and its territorial bodies

- Kamchatka Oblast Administration

- WSC

- Local Municipalities

- Local community representatives

- NGO’s from Kamchatka region

- Indigenous community groups

# 5. Products

The main product of the Mid-Term Evaluation will be:

## Mid-Term Evaluation Report

The Mid-Term Evaluation report will include:

- Findings and conclusions in relation to issues to be addressed identified under the Evaluation section of this TOR

- Project impact assessed on:

- The assisted institution and its staff;

- End-users including specific groups;

Sustainability of the project based on:

- Commitment of the host government to the project targets

- Involvement of the local organizations (participatory process)

- Management and organizational factors

- Funding

- Human resources development

Recommendations for further implementation of current project phase and for the design of the subsequent phases

The draft and final report will be written in the format outlines in Annex 1 of this TOR. The draft report will be submitted to UNDP/GEF and the Ministry of Agriculture no later than March 15th 2006. Based on the feedback received from stakeholders a final report will be prepared by 25th of March 2006.

The report will be submitted both electronically and in printed version, in Russian and English.

The report will be supplemented by a Summary presentation of findings.

# 6. Evaluation Team

The Mid-term Evaluation will be carried out by team of two external consultants:

International consultant - expert on areas of international projects’ monitoring and evaluation with the focus on biodiversity conservation, agrobiodiversity, fishery, mainstreaming conservation into production sectors (fishery sector), conservation trust fund development and sustainable livelihoods, participatory approaches;

Russian consultant – expert on areas of environmental management, fishery management and conservation, additional knowledge on NGO/indigenous community would be an asset

The evaluation team is responsible for the successful completion of the evaluation and finalizing the Mid-term Evaluation report. The team is expected to be familiar with the region and have basic knowledge of the project area (such as region’s biodiversity, socio-economic and legislative context, threats to biodiversity)

# 7. Implementation Arrangements

## Evaluation management arrangements

Role of Project Manager (located in Petropavlosk)

- Coordination of evaluation activities and logistics in Kamchatka

- Organization of site visits

- Organization of meetings with selected stakeholders

Role of UNDP

- Coordination of evaluation activities in Moscow

- Administrative and logistical support for Evaluation Team in Moscow

## Tentative timeframe (timeframe in table format is attached as Annex 2.)

Selection of evaluators				December 2005  - January 2006

Briefings for evaluators				January-February 2006

Desk review 					February 2006

Debriefing  and participation in the Steering

Committee meeting in Moscow			February 2006

Trip to Kamchatka, site visits, interviews with

local stakeholders, questionnairs			February 2006

Validation of preliminary findings with stakeholders through circulation of initial reports for comments, meetings, and other types of feedback mechanisms

March 2006

Preparation of final evaluation report 		March 2006

# TOR Annex 1: Outline of Mid-Term Evaluation Report

## Executive summary

- Brief description of  the project

- Context and purpose of the evaluation

- Main conclusions, recommendations and lessons learned

## Introduction

- Project background

- Purpose of the evaluation

- Key issues addressed

- The outputs of the evaluation and how will they be used

- Methodology of the evaluation

- Structure of the evaluation

## The Project and its development context

- Project start and its duration

- Implementation status

- Problems that the project seek to address

- Immediate and development objectives of the project

- Main stakeholders

- Results expected

## Findings and Conclusions

- Project delivery

  - Progress of the project as a whole in achieving its stated objectives

  - Effectiveness, efficiency and timeliness of project implementation

  - Stakeholder participation, partnerships

- Project implementation

  - Project oversight

  - Project execution

  - Project implementation

  - Project administration

  - Project planning

  - Monitoring and evaluation

  - Risk management

- Project finances

  - Financial planning

  - Budget procedure

  - Disbursements

  - Effectiveness of funding mechanism

  - Risks

## Recommendations

    - Corrective actions for the design, implementation, monitoring and evaluation of the project

    - Proposals for future directions underlining main objectives

## Lessons learned

- Best and worst practices in addressing issues relating to relevance, performance and success

## Annexes

- TOR

- Itinerary

- List of persons interviewed

- Summary of field visits

- List of documents reviewed

- Questionnaire used and summary of results

## Other relevant material

TOR Annex 2 Logical Framework. Evaluation Indicators

Revised Objective-level Indicators.

| Description of Impact Indicators | Value in year 0 | Mid-term Target Value (2005) | End of Project Target Value (2007) |
| --- | --- | --- | --- |
| Indicator 1. Salmonid diversity | List of species recorded in all four river sites; | Very Good: All historical species present in river sites. | Very Good: All historical species present in river sites w/ more complete data set. |
| Indicator 2. Distribution: Adult or juvenile presence by stream segment. | Incomplete information on commercial species, absence of information on non-commercial species. | New information on commercial and non-commercial species. | Very good: Occupy 100% of historical range within each river system. More complete data on commercial and non-commercial species |
| Indicator 3. Number of hectares of salmonid habitat protected; | No specific protected areas for salmonids. | 1 PA created; 280,000 ha protected. | 1 PA established. Design of the 2nd PA is developed. Total # of hectares: 400,000 heсtares. |
| Indicator 4. Insect biomass and diversity | Incomplete information for Bolshaya river, absence of information on other river sites | List of insect species enlarged and biomass determined for three river sites | Very good: 66-100% of median biomass. Good: 40-66% of average. |
| Indicator 5. Abundance of salmon. | River basin escapement levels Bolshaya, Kohl, U-K. | Very Good (see footnote) Existing information incorporated into the common database | Very Good (see footnote). Information database is used by the decision makers. |
| Indicator 6. In-stream habitat a)Sediment transport; b) Road density in watershed; c) Spawning habitat (SH); Rearing habitat (RH). | a) These not defined for river sites at Year 0. b) These not defined for river sites at Year 0. c) Information on commercial species in-stream habitats exists. No information on non-commercial species in-stream habitats | a) Will be defined by mid-term. b) Will be defined by mid-term. c) More complete information on commercial and non-commercial species spawning habitats. Status of rearing habitats determined on model sites | a) Sediment transport: Very Good (fluctuates no more than 15% up or down each year). b) Road density in watershed: AR. c) SH 90-100% of historical figures; RH: 90-100% of historical figures. |

Revised Outcome Indicators.

| Outcome 1: | Improved fishery management practices for salmonid diversity conservation purposes. |  |  |
| --- | --- | --- | --- |
| Indicators | Value in year 0 | Mid-term Target Value (2005) | End of Project Target Value (2007) |
| Indicator 1. Diversity management principles and criteria are developed, proposed, and approved for 2 hatcheries in Bolshaya basin | Diversity management principles and criteria are not addressed with enough attention in hatcheries practices | Program elaborated for this task and adopted by SVR and KNIRO. | Diversity management principles and criteria are developed, proposed, and approved |
| Indicator 2. Salmonid diversity and ecosystem health requirements incorporated into escapement goals for project river sites. | Not specified in escapement goal establishment process. | Work towards establishment of diversity-friendly escapement goals initiated | Diversity and ecosystem health escapement goals are established and applied to project sites. |
| Indicator 3. New public-private partnership for management of non-commercial fish species. | No partnership for management of non-commercial species. | Association of fly fishers and fly-fishing businesses formed. | Fish management agencies utilize public-private partnership to manage sport fishery on two pilot sites. |
| Indicator 4. Russian fishery legislation incorporates salmonid diversity conservation principles. | Not reflected in existing fishery legislation. | Analysis of law with recommendations for change New fishery law reflects diversity conservation principles. | New system of fishery regulations and policy reflecting salmonid diversity conservation. |
| Indicator 5: Fisheries agencies manage project river sites based on systematized and up to dated information on biodiversity | No systematized and up to dated information on biodiversity in the project river sites. | Existing information collected, analyzed and gaps identified; Database designed. | Fisheries agencies maintain complete picture of site ecosystem health through a continually updated database for project sites. |

| Outcome 2: | River ecosystem integrity is conserved in four sites using a variety of conservation tools and approaches |
| --- | --- |

| Indicators | Value in year 0 | Mid-term Target Value (2005) | End of Project Target Value (2007) |
| --- | --- | --- | --- |
| Indicator 1: Community partnerships demonstrated for river site management (Protected Area management, Environment protection programs, Incentive program) | Local communities do not participate in river systems protection or management | PA management discussions with indigenous group; Annual State of the River reports produced Incentive program concept paper prepared and under consideration. | Khol River PA partnership; Utkholok River PA partnership; Monitoring partnership involving river keepers. Community development program pilot for one river site area; Environmental and monitoring program underway with high school groups for Bolshaya River. |
| Indicator 2: New conservation tools applied in protected areas management. | No PAs in the river sites. | Kohl River protected area is being designed in such a way that makes it possible in future to pilot salmon diversity conservation programs. | Salmon conservation programs are piloted in Kohl. Utkholok protected area is being designed in such a way that makes it possible in future to pilot salmon diversity conservation programs. |
| Indicator 3: Environmental mitigation plan for pipeline and best practices in environmental mitigation introduced to key stakeholders at workshop in PK, strengthening environmental mitigation of development activities in Kamchatka | Construction of the gas pipeline endangers integrity of spawning rivers in Western Kamchatka | Impact assessment completed. Mitigation recommendations and training program under preparation. | Key ecological issues discussed among stakeholders. Pipeline company adopts environmental mitigation tools into their work. |

| Outcome 3: | Implementation of educational programs, information sharing, preservation of indigenous peoples’ knowledge, and awareness raising build constituencies for salmon diversity conservation in four river sites |
| --- | --- |

| Indicators | Value in year 0 | Mid-term Target Value (2005) | End of Project Target Value (2007) |
| --- | --- | --- | --- |
| Indicator 1. Level of support for salmonid conservation among school students and general public in Kamchatka. | Not determined. | To be determined through student surveys and public survey. | Increased by 20%. |
| Indicator 2: Kamchatka Salmon Ecological Center and other interpretive displays operational. | No visitor center exists; no interpretive materials. | Kamchatka Salmon Ecological Education Center exists and educates 1000 visitors. | Kamchatka Salmon Ecological Education Center premier destination for tour groups; partnerships established with educational institutions, tour companies. Center on sustainable financial footing. |
| Indicator 3: Salmonid diversity and ecology curricula developed and introduced throughout local school curriculum. | No salmonid diversity education materials or curricula exists in ecological education | Curriculum completed; Officially adopted by Education authorities and Teacher Training University. | Components on salmonid diversity, ecology and sustainable use developed and in use in 20 local schools by year 4 |
| Indicator 4 Indigenous people begin to record knowledge and develop education programs | No databases; No synthesized materials, No interviews of elders to capture knowledge in modern media form; Traditional knowledge not being recorded and learned. | TEK expeditions to indigenous communities; cooperative relationships established with local institute for native languages; use of materials in this institute. | TEK Database available on DVD and CD created and used indigenous communities and associations. |

| Outcome 4: | Stakeholders successfully develop alternative livelihoods in river site areas |
| --- | --- |

| Indicators | Value in year 0 | Mid-term Target Value (2005) | End of Project Target Value (2007) |
| --- | --- | --- | --- |
| Indicator 1: Local communities pursuing sustainable livelihood options based upon local salmon resources by end year 5. | No tradition of community development rooted in local salmon resources. | Concept paper on community development approach under consideration by stakeholders. | Pilot community development program underway in one project site. |
| Indicator 2 Local stakeholder capacity to develop alternative livelihoods being strengthened through access to micro-credit & business training. | No access of local people to micro-credit facilities and business training; No training in business development or management. | Market studies in project sites; Recommendations for development of viable livelihoods made; Five people from project sites trained in business development. | 20 people from project sites are trained in business development and operate new biodiversity friendly small business successfully. 20 micro-loans in project site areas. |
| Indicator 3: Eco-tourism operating in at least one project site and involving local people in project site. | Ecotourism development is hampered by lack of information. | Assessment of ecotourism potential in project sites underway. | Ecotourism enterprise successfully operating in at least one project site and employing local people. |
| Indicator 9. Sustainable use incentives and alternative livelihood programs target local population in project sites. | 0% -- Incentive mechanisms do not exist; alternative livelihood options do not exist. | Opportunities identified and programs under development for people in project sites. | Pilot programs cover local population in two project sites. |

| Outcome 5: | Sustainable financing for salmonid conservation |
| --- | --- |

| Indicators | Value in year 0 | Mid-term Target Value (2005) | End of Project Target Value (2007) |
| --- | --- | --- | --- |
| Indicator 1: Salmonid Diversity Conservation Fund legally established by end of year 3 | No sustainable financing mechanisms for diversity conservation exist | Conservation Fund registered. | Salmonid Diversity Conservation Fund legally established |
| Indicator 2: Commitments for Fund endowment. | No funding for long-term mechanism. | Best funding prospects identified. | Preliminary commitment of US $1.5 million obtained |

UNDP/GEF M&E GUIDANCE TABLES

PLEASE NOTE

The following tables are provided as templates for M&E from GEF.  Without any background knowledge of this project, they give a very narrow and inappropriately negative view.  There are details, issues and complexities connected with much of the project that cannot fairly be summarized with a simple one-letter rating.   As noted in the report, many of the indicators (particularly on the “objective” level) have changed and may no longer represent the original project’s true intent and breadth.  Finally, the importance of some indicators and activities to achieving the project objective of conservation and sustainable use is much higher than others.  The tables “level” this hierarchy making each indicator equally important.  This does not reflect the on-the-ground situation.

TABLE 1:  STATUS OF OBJECTIVE / OUTCOME DELIVERY AS PER MEASURABLE INDICATORS

| OBJECTIVE | MEASURABLE INDICATORS FROM PROJECT LOGFRAME |  | MID TERM TARGET | STATUS OF DELIVERY* | RATING** |
| --- | --- | --- | --- | --- | --- |
| Conservation and sustainable use of salmonid biological diversity in four river systems on Russia’s Kamchatka Peninsula | Salmonid diversity |  | Very Good: All historical species present in river sites. | Completed | S |
|  | Distribution: Adult or juvenile presence by stream segment |  | New information on commercial and non-commercial species. | Expected | S |
|  | Number of hectares of salmonid habitat protected |  | 1 PA created; 280,000 ha protected. | Completed | HS |
|  | Insect biomass and diversity |  | List of insect species enlarged and biomass determined for three river sites | Completed | S |
|  | Abundance of salmon (Very Good=All escapements 66-100% of historical. Good=Most escapements 66-100% and all > 33%; Fair=All > 33%.) |  | Very Good (see footnote). Existing information incorporated into the common database | Unknown |  |
|  | In-stream habitat a)Sediment transport; b) Road density in watershed; c) Spawning habitat (SH); Rearing habitat (RH). |  | a) Will be defined by mid-term. b) Will be defined by mid-term. c) More complete information on commercial and non-commercial species spawning habitats. Status of rearing habitats determined on model sites | Unknown |  |
| OUTCOMES | MEASURABLE INDICATORS FROM PROJECT LOGFRAME |  | MID TERM TARGET | STATUS OF DELIVERY | RATING |
| Improved fishery management practices for salmonid diversity conservation purposes | Diversity management principles and criteria are developed, proposed, and approved for 2 hatcheries in Bolshaya basin |  | Program elaborated for this task and adopted by SVR and KNIRO. | Expected | S |
|  | Salmonid diversity and ecosystem health requirements incorporated into escapement goals for project river sites. |  | Work towards establishment of diversity-friendly escapement goals initiated | Expected | MS |
|  | New public-private partnership for management of non-commercial fish species. |  | Association of fly fishers and fly-fishing businesses formed. | Expected | S |
|  | Russian fishery legislation incorporates salmonid diversity conservation principles. |  | Analysis of law with recommendations for change New fishery law reflects diversity conservation principles. | Completed | S |
|  | Fisheries agencies manage project river sites based on systematized and up to dated information on biodiversity |  | Existing information collected, analyzed and gaps identified; Database designed. | Expected | S |
| River ecosystem integrity is conserved in four sites using a variety of conservation tools and approaches | Community partnerships demonstrated for river site management (Protected Area management, Environment protection programs, Incentive program) |  | - PA management discussions with indigenous group; - Annual State of the River reports produced - Incentive program concept paper prepared and under consideration. | Expected | S |
|  | New conservation tools applied in protected areas management. |  | Kohl River protected area is being designed in such a way that makes it possible in future to pilot salmon diversity conservation programs. | Expected | S |
|  | Environmental mitigation plan for pipeline and best practices in environmental mitigation introduced to key stakeholders at workshop in PK, strengthening environmental mitigation of development activities in Kamchatka |  | Impact assessment completed. Mitigation recommendations and training program under preparation. | Expected | HS |
| Implementation of educational programs, information sharing, preservation of indigenous peoples’ knowledge, and awareness raising build constituencies for salmon diversity conservation in four river sites | Level of support for salmonid conservation among school students and general public in Kamchatka. |  | To be determined through student surveys and public survey. | Expected | HS |
|  | Kamchatka Salmon Ecological Center and other interpretive displays operational. |  | Kamchatka Salmon Ecological Education Center exists and educates 1000 visitors. | Completed | HS |
|  | Salmonid diversity and ecology curricula developed and introduced throughout local school curriculum. |  | Curriculum completed; Officially adopted by Education authorities and Teacher Training University. | Completed | HS |
|  | Indigenous people begin to record knowledge and develop education programs |  | TEK expeditions to indigenous communities; cooperative relationships established with local institute for native languages; use of materials in this institute. | Completed | HS |
| Stakeholders successfully develop alternative livelihoods in river site areas | Local communities pursuing sustainable livelihood options based upon local salmon resources by end year 5. |  | Concept paper on community development approach under consideration by stakeholders. | Expected | S |
|  | Local stakeholder capacity to develop alternative livelihoods being strengthened through access to micro-credit & business training. |  | Market studies in project sites; Recommendations for development of viable livelihoods made; Five people from project sites trained in business development. | Expected | MS |
|  | Eco-tourism operating in at least one project site and involving local people in project site. |  | Assessment of ecotourism potential in project sites underway. | Expected | S |
|  | Sustainable use incentives and alternative livelihood programs target local population in project sites. |  | Opportunities identified and programs under development for people in project sites. | Expected | S |
| Sustainable financing for salmonid conservation | Salmonid Diversity Conservation Fund legally established by end of year 3 |  | Conservation Fund registered. | Expected | MS |
|  | Commitments for Fund endowment. |  | Best funding prospects identified. | Expected | MS |
| * Status of Delivery: |  |  | ** RATINGS: | Highly Satisfactory = HS |  |
| GREEN / COMPLETED | = Indicators show successful achievement |  |  | Satisfactory = S |  |
| YELLOW | = Indicators show expected completion by end of Project |  |  | Marginally Satisfactory = MS |  |
| RED | = Indicators show poor achievement - unlikely to be complete by end of Project |  |  | Unsatisfactory = U |  |

TABLE 2: 	Project Ratings

Highly Satisfactory (HS), Satisfactory (S), Marginally Satisfactory (MS), and Unsatisfactory (U)

| PROJECT COMPONENT OR OBJECTIVE | Rating scale |  |  |  | RATING |
| --- | --- | --- | --- | --- | --- |
|  | U | MS | S | HS |  |
| Project Formulation |  |  |  |  |  |
| Conceptualization/Design |  |  |  | X | HS |
| Stakeholder participation |  |  | X |  | S |
| Project Implementation |  |  |  |  |  |
| Implementation Approach |  |  | X |  | S |
| The use of the logical framework |  | X |  |  | MS |
| Adaptive management |  |  |  | X | HS |
| Use/establishment of information technologies |  |  | X |  | S |
| Operational relationships between the institutions involved |  | X |  |  | MS |
| Technical capacities |  |  | X |  | S |
| Monitoring and evaluation |  |  | X |  | S |
| Stakeholder participation |  |  | X |  | S |
| Production and dissemination of information |  |  | X |  | S |
| Local resource users and NGOs participation |  | X |  |  | MS |
| Establishment of partnerships |  |  | X |  | S |
| Involvement and support of governmental institutions |  |  | X |  | S |
| Project Results |  |  |  |  |  |
| Attainment of Outcomes/ Achievement of objectives |  |  |  |  |  |
| Achievement of objective |  |  |  |  |  |
| Outcome 1: Improved Fisheries Management |  | X |  |  | MS |
| Outcome 2: River Ecosystem Integrity |  | X |  |  | MS |
| Outcome 3: Education, Indigenous Knowledge, PA |  |  |  | X | HS |
| Outcome 4: Alternative Livelihoods |  |  | X |  | S |
| Outcome 5: Sustainable Financing |  | X |  |  | MS |
| OVERALL PROJECT ACHIEVEMENT & IMPACT |  |  | X |  | S |

Very Good: All escapements 66-100% of historical.  Good:  Most escapements 66-100% and all > 33%; Fair: All > 33%.

Acceptable Range (AR): 0-2.5% of basin covered in roads?; AR: < 2% with no valley bottom roads; Fair: < 2-3% with some valley bottom roads; Poor: >3% with many valley bottom roads

Very Good: All escapements 66-100% of historical.  Good:  Most escapements 66-100% and all > 33%; Fair: All > 33%.

Acceptable Range (AR): 0-2.5% of basin covered in roads?; AR: < 2% with no valley bottom roads; Fair: < 2-3% with some valley bottom roads; Poor: >3% with many valley bottom roads

Very Good: All escapements 66-100% of historical.  Good:  Most escapements 66-100% and all > 33%; Fair: All > 33%.

Acceptable Range (AR): 0-2.5% of basin covered in roads?; AR: < 2% with no valley bottom roads; Fair: < 2-3% with some valley bottom roads; Poor: >3% with many valley bottom roads