Annex 7. MSP Logical framework

Logical Framework Matrix

| # Intervention Strategy | # Objectively Verifiable Indicators | # Means of Verification | # Assumptions |
| --- | --- | --- | --- |
| # Project Goal # Conserve a highly threatened Arid and Semi-arid ecosystem through the participatory planning and sustainable use of natural resources. | # (Measures of Objective Achievement) - Density of animals grazing, hunting pressure, and species recovery techniques within the specifications set by the project Implementation unit. - Grazing rotation schedules within the specifications set by the project Implementation unit. | - Reports on habitat restoration. - Surveys on density of animal grazing, rotation patterns, and hunting activities. | # (Concerning Long-Term Value of Project) - Grazing and hunting activities that respect the ecosystem estimated carrying capacity complemented with restoration activities will result in conservation of currently threatened biodiversity. |
| Immediate Objectives: - To increase coordination among countries concerned in participatory planning and sustainable management of natural resources. - To develop agreed alternative land use strategies aimed at recovering and protecting the ecosystem and key species # To increase awareness and develop management techniques for the sustainable use of biological resources among land users and other stakeholders | # (Conditions that will indicate immediate objectives have been achieved) - Quarterly meetings (at least 10 by the end of the project) and monthly consultations among representatives of governments, public organizations, and local users. - An official agreement by stakeholders on proposed alternative land uses by the 13th month of the project - Statistically significant difference (between baseline situation and end of project) in awareness and management skills of land users and local communities. | - Official minutes and transcripts from meetings and consultations. - Official minutes and transcripts from meetings and consultations. - Polls and questionnaires taken at the beginning and end of project | # (Affecting Immediate to Project Goal Link) - The governments are committed to carry out agreed measures for biodiversity protection. - Local stakeholders inputs are genuinely taken into account in the development of the management plan - A critical number of land users and other stakeholders agree that medium-term benefits from preserving the arid and semi-arid area outweigh short-term gains from unsustainable use. |

(cont.)

| # Intervention Strategy | # Objectively Verifiable Indicators | # Means of Verification | # Assumptions |
| --- | --- | --- | --- |
| # Outputs: - An arid and semi-arid zone Coordination unit established for formulation, information management, communication, and implementation of protection activities; - Developed agreed principles, guidelines and actions for conservation of the arid and semi-arid zone conservation. - The establishment of replicable pilot demonstration projects based on the principles of the agreed management criteria. - A biodiversity monitoring system for the arid and semi-arid zone. - Replicable capacity and public awareness strengthening programs | # (Magnitude of Outputs sufficient to achieve immediate objectives) - By the third month of the project, Governments and NGOs recognize the unit as the coordinating body for development of transboundary management criteria. - Delivery of document at the 13th month of the project with a description of critical habitats, species protection needs, grazing rotation scheme, allowed levels of hunting activities, enforcement and monitoring needs, feasible sources of funding, and execution arrangements. - Between the 13 and 29 months selected stakeholders will be involved in 5 alternative land use and species recovery activities proposed by the project - An agreed yearly calendar of sampling, agreed indicators, and thresholds completed within the first eight months of the project. - At the end of the first year, a database containing at least 75% of known species in the arid zone, together with their status, current threats, and proposed management is accessible through the WWW. - Monthly execution of seminars and/or community workshops, and publication of material. | - Formal (written) appointments from respective government units and NGOs representatives to the implementation unit. - Formal (written) agreement with the document from government units. - Field surveys and interviews with local communities - Minutes from the coordination meetings approving the establishment of the monitoring system. - Access to the WWW - Reports of seminars and workshops. | # (Affecting Output to Immediate Objectives Link) - Government units are committed to follow the management criteria agreed by the implementation unit. - The management criteria addresses conservation targets and its implementation proves feasible. - Pilot projects are successful in demonstrating the viability of alternative land use strategies and recovery of species. - Information reaches the public and it is used as input in the arid and semi-arid zone’s decision making process. - Unmet demand for training programs. - The public awareness programs are successful in demonstrating the benefits from conservation of the arid and semi-arid zone |

| # Intervention Strategy | # Inputs |  | # Preconditions |
| --- | --- | --- | --- |
| # Activities (for output #1) - To set up the steering committee which includes government units, and NGOs; - To establish a project implementation unit for the formulation and implementation of protection activities; - To establish built-in mechanisms within the coordinating unit to ensure stakeholders’ involvement in planning and management of resources; - To design information dissemination mechanisms. (for output #2) - To complete an inventory of status of biodiversity resources, and other baseline data; - To collect information on current and projected numbers of animals grazing in the area; - To identify numbers of animals involved in national and transboundary migration flows; - To reassess habitat carrying capacity analysis in the light of current erosion levels; - To analyze land ownership issues, including land use dynamics in the face of the rapid transformation that have taken place since the collapse of the Soviet regime; - To design grazing rotation scheme; - Identify needed changes in sheep grazing patterns; | - 6 month-work for the establishment of the coordination structure and financial resources for 5 meetings of the Steering Committee. - Financial resources for 29-month operation of the coordinating unit, and transferring of management activities to government agencies and public organizations. - Financial resources for 13-month work of national and international expertise on baseline activities of land use plans, initial surveying, and social, and legal assessment in the target area. - 13-month work of national and international expertise in the preparation of the management criteria. |  | # None |

| # Intervention Strategy | # Inputs |  | # Preconditions |
| --- | --- | --- | --- |
| - To estimate the potential economic impact on stakeholders arising from changes in sheep grazing and hunting patterns; - To assess the relevant environmental legislation; - To assess the feasibility of a network of transboundary protected areas; - To identify both financial and human resources needed for the monitoring and enforcement of the agreed management criteria; - To explore potential long-term financial mechanisms; - To ratify the agreed management criteria with relevant governments units. (for output #3) - To select areas and target groups involved; - To identify necessary changes in grazing and hunting patterns; - To implement desired changes in selected portions of the ecosystem; - To analyze response from targeted groups to incentives and other mechanisms implemented to restore protected habitats; - To design information dissemination strategy on lessons learnt in pilot projects | - Financial resources for 21 month-work of national and international experts in the design and implementation of replicable demonstration projects. |  | None |

| # Intervention Strategy | # Inputs |  | # Preconditions |
| --- | --- | --- | --- |
| (for output #4) - To create a Transcaucasus database of habitats and species for the collection, collation, and dissemination of information; - To design a long-term information updating mechanisms - To make database accessible through the World Wide Web. (for output #5) - To conduct a series of training activities for stakeholders involved in the project management; - To execute seminars to increase technical capacity in both non-governmental and governmental agencies that are involved in the project management; - To carry out environmental awareness workshops among shepherds, hunters, and other target groups. | - Financial resources for 6-month work for national and international expertise - Financial resources to cover 33 month-work of national and international consultants in capacity building programs. |  | None |