Local Governance and Decentralization Programme

for Union Parishad and Upazila Parishad

UNION PARISHAD GOVERNANCE PROJECT (UPGP)

&

UPAZILA GOVERNANCE PROJECT (UZGP)

MIDTERM EVALUATION

FINAL REPORT

04 December 2014

| Midterm Evaluation Team |  |  |
| --- | --- | --- |
| Jens Peter Christensen | Team Leader | Local Government Denmark |
| Salahuddin Aminuzzaman | Team Member | University of Dhaka |
| Salma Akhter | Team Member | University of Dhaka |
| Jesper Steffensen | Team Member | Dege Consult |
| Taiabur Rahman | Team Member | University of Dhaka |
| K M Mahiuddin | Team Member | Jahangirnagar University |
| Ekram Hossain | Team Member | Brac University |
| M. Firoz-Ul.Hassan | Team Member | Jahangirnagar University |

Abbreviations and Acronyms

| ADP | Annual Development Plan |
| --- | --- |
| ADR | Alternative Dispute Resolution |
| APA | Annual Performance Assessment |
| AWP | Annual Work Plan |
| BARD | Bangladesh Academy for Rural Development |
| BBG | Basic Block Grants |
| BIDS | Bangladesh Institute of Development Studies |
| BIM BMDF | Bangladesh Institute of Management Bangladesh Municipal Development Fund |
| CB | Capacity Building |
| CBO | Community-Based Organization |
| CEDAW | UN Convention on the Elimination of All forms of Discrimination Against Women |
| CPS | Citizens Perception Study, Sept 2014 |
| CSO | Civil Society Organization |
| DC | Deputy Commissioner |
| DDLG | Deputy Director, Local Government |
| DF | District Facilitator |
| DLG | Director, Local Government |
| DVF | Divisional Facilitator |
| EPBG | Expanded Performance-Based Grants |
| EU | European Union |
| EWR | Elected Women Representatives |
| FP | Focal Person |
| FY | Financial Year |
| FYP | Five-Year Plan (e.g. 6FYP means 6th Five-Year Plan) |
| GoB | Government of Bangladesh |
| ICT | Information and Communications Technology |
| IPF | Institute of Public finance |
| ITA | International Technical Assistant |
| JICA | Japan International Cooperation Agency |
| LCD | Local Consultative (Sub-group) on Local Governance |
| LD | Line Department (Deconcentrated department at UZP level) |
| LED | Local Economic Development |
| LG | Local Government |
| LGD | Local Government Division |
| LGI | Local Government Institution |
| LGRDC | Local Government, Rural Development and Cooperatives |
| LGSP | Local Governance Support Project |
| LGSP-LIC | Local Governance Support Project - Learning and Innovation Component |
| LM | Line Ministry |
| MC | Minimum Condition |
| MDG | Millennium Development Goal |
| M&E | Monitoring and Evaluation |
| MIE | Monitoring, Inspection, Evaluation (Wing of LGD) |
| MIS | Management Information System |
| MP | Member of Parliament |
| MoF | Ministry of Finance |
| MoU | Memorandum of Understanding |
| MSPVAW | Multi-Sectoral Programme on Violence Against Women |
| MTE NAPD NEX | Midterm Evaluation National Academy for Planning and Development National Execution |
| NILG | National Institute of Local Government |
| NGO | Non-government Organization |
| NPD | National Project Director |
| NWDP | National Women Development Policy |
| OSR | Own-source revenues |
| PAG | Policy Advisory Group |
| PA | Preparatory Assessment |
| PB | Project Board |
| PBG | Performance-Based Grant |
| PBGS | Performance-Based Grant System |
| PFM | Public Financial Management |
| PM | Project Manager |
| PMU | Project Management Unit |
| PPP | Public-Private Partnership |
| PSC | Project Steering Committee |
| QA | Quality Assurance |
| R&D | Research and Development |
| RDA | Rural Development Academy |
| RTI | Right to Information |
| SC | Steering Committee |
| SDC | Swiss Agency for Development and Cooperation |
| SLGDP | Sirajganj Local Government Development Project |
| SPEMP | Strengthening Public Expenditure Management Program |
| ToR | Terms of Reference |
| ToT | Training of Trainers |
| UFF | Upazila Fiscal Facility |
| UISC | Union Information and Service Centre |
| UN | United Nations |
| UNCDF | United Nations Capital Development Fund |
| UNDAF | United Nations Development Assistance Framework |
| UNDP | United Nations Development Programme |
| UNO | Upazila Nirbahi Officer |
| UP | Union Parishad |
| UPGP | Union Parishad Governance Project |
| UZP | Upazila Parishad |
| UZGP | Upazila Parishad Governance Project |
| VC | Vice Chairman |
| VAW | Violence Against Women |
| WB | World Bank |
| WDF | Women Development Forum |
| WS | Ward Shavas |

Map of Bangladesh with the seven UPGP and UZGP pilot districts

Executive Summary

The Union Parishad Governance Project 2011-2016 (UPGP) and the Upazila Parishad Governance Project 2011-2016 (UZGP) are uniquely positioned in the support to local government institutions (LGIs) in Bangladesh. The UZGP provides capacity building (CB) support, fiscal support, and policy advice on systemic improvements for the reestablished Upazila Parishads (UZPs) and represents the only international support project to this government tier. A successful revival of the UZPs has great potential, since local planning and service delivery can tap into the resources of the line ministries (LMs) and take advantage of strong multi-stakeholder synergies. The UPGP has a similar project design and is linked to the larger World Bank financed LGSP 2. One of the raisons d’etre of the UPGP is its ability to add value to LGSP 2; spearheading local governance, CB and fiscal innovations as well as regulatory improvements and best practices which can be upscaled and disseminated nationwide though LGSP.

From Sept. to Nov. 2014, the UPGP and UZGP were subject to an external midterm evaluation (MTE). The objectives of the MTE were to 1) assess the progress of the projects and the likelihood of achieving end targets in 2016; to 2) assess the relevance and progress of the projects against UNDAF 2012-2016 and the Government of Bangladesh’s (GoB) policies on decentralization and local governance; and to 3) extract lessons learnt and provide recommendations for the remainder of the project duration. Since discussions had already started in relation to LGI support beyond 2016, the MTE was also requested to provide inputs to this discussion.

In order to consolidate findings and validate secondary data extracted from the project MIS and surveys, the MTE conducted field data sampling in six districts: four of the pilot districts and two control districts outside project coverage. In total, twelve UZPs and twelve UPs were included in the MTE field research.

The overall conclusion of the MTE is that both projects remain relevant vis-à-vis UNDAF and the GoB policy on LGIs. The MTE also noted that the concept paper for the upcoming 7th Five-Year Plan (7FYP) reiterates a commitment to work towards stronger LGIs and recognizes that the reform agenda is ”unfinished”.

Despite delays, political turmoil for most of 2013 and a foreshortened implementation time, both UPGP and UZGP maintain good progress and are likely to achieve most of their objectives by 2016. Based on the outcomes of the extended field research, and key secondary data such as the annual performance assessments (APAs), the baseline surveys and the Citizens Perspective Survey (CPS), the MTE also concludes, that the projects provide important value additions to the development of the UP and UZP tier, which is strongly documented by significant improvements in core functional areas in the pilot districts compared to baseline data and developments in non-covered districts. Equally important, support extended to the UZPs has contributed to sustaining this government tier at a difficult time, when it was re-established and faced with political power struggles. It has also had a significant impact on emerging UZP operations and linkages to the Line Departments (LDs).

Both projects have improved transparency, accountability and participation in LGIs, especially at UP level, and there is credible documentation of improved pro-poor, gender friendly planning and MDG service delivery in pilot areas. The projects have improved women’s participation in local government through the rollout of WDFs and CB support to female leaders, and the overall message from the field is that beneficiaries at both levels and citizens in general highly appreciate the support rendered by the projects.

Both projects have piloted an enhanced performance-based grant system, which has become important catalyst for the achievement of project objectives within local governance, pro-poor development planning, MDG service delivery, and increased own-source revenues (OSR) mobilization. The performance elements are highly appreciated by the LGIs and have instilled a stronger awareness on good governance and internal competition. As per design, they have also contributed to the identification of capacity gaps, which can be fed back into the CB activities of the projects and highlight systemic malfunctions, which needs to be addressed at the policy level.

These important achievements successfully build on lessons learned from previous support projects, such as the Sirajganj Local Government Development Project (SLGDP 2000-2006), the Local Government Support Program – Learning and Innovation Component (LGSP-LIC 2007-2011) and the Upazila Preparatory Assessment (UZP PA 2009-2012). They include important innovations such as

- Formula and performance based block grants, allocated through direct funds transfers

- Participatory multi-year development planning

- Standing committees

- Open budget meetings and ward shavas (UP level)

- Women’s Development Forums (at district and UZP level),

- Various accountability measures such as disclosure of information, citizens’ charters, etc.

- Increased transparency and participation as a means of mobilizing own-source revenues

- Peer learning and cascading training delivery

Many of these innovations have already been upscaled through the regulatory LGI framework, making best practice achievements of UPGP and UZGP on transparency, accountability and participation more sustainable. It is also very important to note, that both projects currently have unique upscale opportunities, which, if addressed successfully, considerably improve the sustainability of project innovations and promote countrywide rollout of results. The MIS and the PBGS promoted by UPGP, can be upscaled through LGSP 2 and its successor, respectively, while the UZGP results, including the PBGS, are likely to be upscaled through the upcoming JICA funded ”Integrated Development Project for Upazilas” covering the whole country.

It is within the more policy-oriented areas, rather than within applied project approaches in the pilot districts, that the projects are facing most challenges and there is need for special attention. Most of the constraining factors affecting the implementation, relates to systemic issues such as ambiguous division of roles and responsibilities and parallel management structures between the political and executive branches and tiers of government. The UZP level, in particular, is prone to partisan conflicts and needs further governance reforms in order to emerge as a strong tier of local government. The UPs on the other hand are faced with fundamental capacity constraints vis-à-vis their mandate, and there is a serious risk that democratic gains achieved through innovations such as ward shavas and open budget meetings are not sufficiently matched by the limited funding available for community development. Participatory exercises without proper means is a classic way of demotivating citizens, and public engagement in local government runs a risk of being eroded, if funding is not increased over time.

It is none the less also within the objectives of the projects to address such shortcomings and to advice on how the system can be strengthened in line with internationally recognized local self-government principles such as the ”International Guidelines on Decentralization and Access to Basic Services for All” (UN Habitat, 2009) or the ”European Charter of Local Self-Government” (Council of Europe, 1985). The projects support a number of policy studies, which may provide further input to LGI reforms and the lessons learned from the project implementation and the policy dialogues forums conducted throughout Bangladesh do also provide valuable input to new reform initiatives.

Looking beyond project termination in 2016, it is evident that international support to LGIs and reforming of the subnational government system, will still be needed. Even if a LGSP 3 and the upcoming JICA-support to UZPs move ahead and successfully roll out UPGP and UZGP results, they cannot stand alone. Local government reforms take time and the need for support to policy development and “systemic” improvements such as the implementation of a national CB framework or an enhanced local fiscal framework remain, notwithstanding successful policy support rendered by the projects. The WB and JICA support are also based on loans, not grants, and most likely there will also be a need to push for new innovations on the ground, e.g. through another ”LIC” project linked to LGSP and the JICA project. These arguments alone fully justify another joint UN-led LGI support program from 2016.

The MTE has also highlighted the need for a more programmatic approach, bringing relevant ministries on board on a more comprehensive reform program addressing additional dimensions of the LGI framework. The policy studies initiated by the projects highlights many of the critical issues that need to be addressed in future reforms, and the scale of a joint support program linked to such reforms needs to be discussed between the GoB and the development partners, in order to link international support to the government reform priorities emerging from the 7FYP and similar policy documents.

The MTE has provided a number of recommendations on where the projects and LGD, respectively, should focus their attention in order to address implementation shortcomings and improve overall performance and sustainability of results during the remaining time of the projects. The recommendations are listed in a table in the concluding chapter 16 and include support to the upscale opportunities through LGSP and JICA and more attention on activating the Policy Advisory Group and designing the national CB framework. Based on discussions in the Steering Committee meetings, a joint action plan should be drafted for quick implementation.

List of Contents

Foreword	12

1.	Introduction	13

1.1 Time schedule and presentation of the MTE team	14

2.	Evaluation Design	16

2.1 Methodology for the field work	17

2.2 Special considerations and limitations of the methodology	18

3.	The UPs and UZPs and the local government system	19

3.1 Elections	21

3.2 Functions of the LGIs	21

3.3 Fiscal Decentralisation Issues	23

3.4 Women in Local Government	24

4.	UPGP and UZGP Intervention Logic and Strategy	27

4.1 Relevance	27

4.2 Geographical coverage	29

4.3 Funding	29

4.4 Project organisation and management	30

4.5 Linking to previous projects and the LG framework for sustainability	31

4.6 Links with LGSP 2	36

5.	Relevance of Project interventions	39

5.1 UNDAF 2012-2016	39

5.2 Government of Bangladesh Policy framework	41

5.3 Conclusion	43

6.	Assessments of Results - UPGP Output 1	45

1.1 Coaching and Support to UP Chairs, and members for roles and responsibilities defined by UP Act 2009	46

1.2 Activating Ward Shavas for Inclusive Decision-Making	47

1.3 Strengthening Standing Committees for Effective Governance	49

1.4 Up-Scaling of Women’s Development Forum	50

1.5 Building Citizenship and Promoting Downward Accountability	51

1.6 Effectiveness	51

1.7 Efficiency	51

1.8 Sustainability of results	52

1.9 Conclusion	53

7.	Assessment of Results – UPGP Output 2	54

7.1 Development plans with MDG and needs assessments	57

7.2 Grants targeting pro-poor or MDG projects	58

7.3 Accounting and Records	61

7.4 Revenue collection	64

7.5 Effectiveness of operations	65

7.6 Efficiency	66

7.7 Sustainability of results	66

7.8 Conclusion	67

8.	Assessment of Results – UZGP Output 1	69

8.1 UZP members	70

8.2 Right to Information	71

8.3 Standing Committees	71

8.4 WDF	72

8.5 Citizens Charter	72

8.6 Effectiveness	72

8.7 Efficiency	73

8.8 Sustainability of results	73

8.9 Conclusion	74

9.	Assessment of Results – UZGP Output 2	75

9.1 Plans linked to Line Departments	77

9.2 Development plans based on needs assessments	78

9.3 Development plans with interventions addressing vulnerable groups	78

9.4 Grants allocated for MDG targeted projects	79

9.5 Effectiveness	84

9.6 Efficiency	84

9.7 Sustainability of results	85

9.8 Conclusion	85

10. Assessment of results – Output 3 (shared)	86

10.1 Support to a Policy Advisory Group and National Framework for Local Government Policy and Capacity Development	86

10.2. Support to LGD (MIE wing), DLG/DDLG for UZP/UP backstopping and monitoring	90

10.3 R&D for Knowledge Generation	94

10.4 Effectiveness	97

10.5 Efficiency	98

10.6 Sustainability of results	98

10.7 Conclusion	99

11. Management	101

11.1 Funds flow and use of funds	101

11.2 M&E	101

11.3 Project staffing	102

11.4 Back stopping support	102

11.5 Steering arrangements	102

11.6 UNDP Risk management	102

11.7 Conclusion	103

12. External factors affecting successful implementation and results achievement	104

13. Partnership and linkages	106

13.1 Conclusion	110

14. Lessons Learned	111

15. Looking beyond 2016	114

16. Overall conclusion and recommendations	117

Annex 1. Terms of Reference	122

Annex 2. Inception Itinerary	140

Annex 3. Inception workshop program	143

Annex 4. Itinerary for the second MTR mission	147

Annex 5. Questionnaires for the central level	150

Annex 6. Questionnaires for the field work	158

Annex 7. Selection of districts, planning and division of field work	169

Annex 8. Data collection plan, Team 1	174

Annex 9. Data collection plan, Team 2	179

Annex 10. List of people met	182

Annex 11. List of documents	185

Annex 12. UPGP Results achievements	190

Annex 13. UZGP Results achievements	194

Annex 14. Ongoing and planned policy support studies	199

Annex 15. UPGP monitoring plan	204

Annex 16. UZGP monitoring plan	205

Annex 17. Overview of Fund Utilization	207

Annex 18. APA Timing and EPGS Disbursements	209

Annex 19: Trends in Performance from First to Second APA.	215

Annex 20. Framework for UP Performance Measurement	216

Annex 21. Comparison of the Performance on the Common 12 Performance Measures between the 1st and the 2nd APA	217

Annex 22. Scheme Information under the Performance Block Grant of UZGP FY 2012/13	218

Annex 23. UPGP Logical Framework	226

Annex 24. UZGP Logical Framework	230

Annex 25. Examples of parallel committee structures at UP level	234

# Foreword

The midterm evaluation (MTE) of the UPGP and UZGP took place from 10 September - 11 November 2014 and was conducted by a team of four core consultants and four data collectors. The MTE comprised of interviews, workshops and data collection at the central and local levels and included three weeks of data sampling in six districts.

The two projects are implemented in accordance with separate project documents. They are, however, mutually interlinked both in terms of approach, intervention areas, technical assistance and management. Hence, the report integrates MTE assessments, where interventions are jointly managed by the two projects, while interventions unique to each of the projects are assessed in separate sections.

The MTE team would like to thank for the warm hospitality and open discussions during all meetings and for sharing of valuable experiences in a structured manner at the inception workshop. The MTE team has done its best to reflect the views expressed during discussions with project stakeholders, although findings and recommendations in this report ultimately represent the assessments of the team and are subject to further review and discussions among project stakeholders.

The assignment could not be accomplished without substantial logistical support from the UNDP and UNCDF staff. The team would like to extend a special thank you for all support to the arrangement of meetings, workshops, transportation and accommodation.

4 December, 2014

Jens Peter Christensen

Salahuddin Aminuzzaman

Salma Akhter

Jesper Steffensen

Taiabur Rahman

K M Mahiuddin

Ekram Hossain

M. Firoz-Ul.Hassan

# Introduction

The overall purpose of the MTE was to assess progress and achievements of (emerging) results of the two programs and provide recommendations for the remaining duration of the programs as well as guidance to future support beyond 2016.

More specifically, the TOR of the MTE (see Annex 1) defines a threefold purpose of the evaluation:

- Assess the performance of the UPGP and UZGP since their commencement in 2011 against the outcome and outputs on the basis of indicators as set out in the Results Frameworks;

- Assess the performance of the UPGP and UZGP against the UNDAF outcome specified for local governance

- Draw lessons learned and make recommendations to assist further improvements in the implementation of the program over the remainder of its duration and areas of potential support in a follow up to the UPGP and UZGP.

Further, the MTE was requested to assess the application of the rights-based and gender oriented approaches adopted by the projects and potential ideas for next project phases.

The MTE applied a standard evaluation approach as outlined in the TOR, taking point of departure in:

- The five DAC evaluation criteria (relevance, impact, sustainability, efficiency and effectiveness) and

- The results framework embedded in the respective project designs.

The MTE was mainly based on qualitative assessments, focusing on results, emerging outcomes and impact and combining primary data (interviews) and secondary data such as progress reporting, policy studies and surveys produces by the projects and other stakeholders, baseline data, perception studies, performance assessments in-built in the program, rather than producing basic data on its own. However, the addition of four data collectors to the team made it possible to strengthen the qualitative assessments through substantial data samplings from the field.

Both projects are complex in terms of geography, interventions and composition of stakeholders and beneficiaries. They build on successes and lessons learned from a number of previous projects, including SLGDP (2000-2006), LGSP-LIC (2007-2011) and UZP PA (2009-2012), which to a large extent has already been adopted into the regulatory framework of UZPs and UPs. They include important innovations such as:

- Formula and performance-based block grants, allocated through direct funds transfers

- Multi-year participatory development planning

- Standing committees, open budget meetings, Womens Development Forums (at district and UZP level), and ward shavas (UP level)

- Various accountability measures such as disclosure of information, citizens’ charters, etc.

- Increased transparency and participation as a means of mobilising own-source revenues

- Incremental and needs-based approach to innovations

- Peer learning

- Cascading training delivery

The MTE has assessed the extent to which the projects have been able to successfully build on these innovations, added further refinements to them and produced new innovations, which can be up-scaled nationwide.

Overall, the two projects, and especially UPGP, are supplementing the nationwide WB supported LGSP 2. The UZGP is the only international support program for the Upazila level, which provides fiscal grants, CB and policy advice, and a crucial aspect of the MTE has been to assess the continued GoB support to this tier of government. A successful development of the UZP tier has great potential, as planning and service delivery can tap into the resources on the LMs and establish strong multi-stakeholder synergies. One of the raison d’etre of the UPGP, on the other hand, is its ability to add value to the bigger LGSP 2 and feed innovations into the larger program for upscaling and nationwide dissemination in the next phase of LGSP and/or in the future legal and regulatory framework and systemic practices. These aspects of the two projects are tightly connected to the sustainability of project results and have been key focal points of the MTE.

### 1.1 Time schedule and presentation of the MTE team

The MTE took place from 10 september–11 November 2014 and included the following activities:

- Desk study 10 - 20 September

- Inception workshop and meetings in Dhaka 24 September - 1 October

- Inception debriefing 2 October

- Field data sampling 12 - 31 October

- Follow up meetings in Dhaka 22 - 23 October and 1 - 5 November

- Field data assessment, drafting of report and debriefing slides 6 - 10 November

- MTE debriefing on 11 November

Time schedules and workshop agenda for specific phases of the MTE are included in Annex 2 - 4, while a list of persons met can be found in Annex 10.

The MTE team consisted of eight members who worked mutually together on all aspects, although each team member’s work was assigned to specific responsibilities as listed in the table below.

Table. MTE team and division of responsibilities

| Name | Main responsibility | Detailed tasks |
| --- | --- | --- |
| Jens Peter Christensen | Team leader | Overall team leader, M&E, program management and institutional issues (support on all outcomes) Overall reporting and deliverables. Backstopping and QA on all inputs. |
| Salahuddin Aminuzzaman | Core expert (CB/Accountability) | Lead on CB (outcome 1) and accountability issues, activities on policy advice and outcome 3. Input on chapters in the draft report and final report on these areas. |
| Salma Akhter | Core expert (Gender/Service Delivery) | Lead on cross-cutting issues, and service delivery (cross-cutting from outcome 1-3). Input on chapters in the draft report and final report. |
| Jesper Steffensen | Core expert (fiscal issues) | Lead on fiscal issues, fiscal grants, revenues and PFM (outcome 2). Input on chapter in the draft report and final report. |
| Taiabur Rahman | Data collection | Focus on CB /accountability issues, gender aspects and cross-cutting issues. Submission of field level reports in collaboration with the other data collector on the team and support to data collection throughout the evaluation. |
| K M Mahiuddin | Data collection | Focus on fiscal issues and M&E. Submission of field level reports in collaboration with the other data collector on the team and support to data collection throughout the evaluation. |
| Ekram Hossain | Data collection | Focus on CB/accountability issues, gender aspects and cross-cutting issues. Submission of field level reports in collaboration with the other data collector on the team and support to data collection throughout the evaluation. |
| M. Firoz Hassan | Data collection | Focus on fiscal issues and M&E. Submission of field level reports in collaboration with the other data collector on the team and support to data collection throughout the evaluation. |

# Evaluation Design

The MTE was conducted according to a standard triangulation approach, combining quantitative and qualitative evaluation methodologies and using basically three main data collection sources:

- Primary data: This included field observations, semi-structured fact-finding interviews and focal group discussions with key project beneficiaries, development partners and implementers in order to validate and further assess the findings and critical issues identified during the desk review. The interviews were supported by the annexed questionnaires developed during the inception phase and dedicated for the central and local level, respectively.

- Secondary data: (Desk) review and tracking of results in more than 200 documents and program records (see Annex 11), such as:

  - The UZGP and UPGP results matrix, baseline surveys

  - The UZGP and UPGP project cycle management documentation and allocation of funds

  - Policy studies

  - Training outcome assessment reports,

  - UPGP performance assessment reports for the expanded performance-based grants

  - UZGP performance assessment reports under the UFF

  - Relevant legal framework and government policy papers related to the overall reform progress

  - Previous and ongoing associated support programs

  - UNDAF and relevant development partner strategies

- Workshops and round table discussions with project beneficiaries, implementers and development partners to validate draft findings and recommendations and discuss the way forward. This included a final team presentation of findings and recommendations at the mission debriefing session.

M&E is a shared focus area of both projects and a capacity development intervention in its own right. The projects build M&E capacity at the LGD MIE wing according to an M&E strategy, which outlines an incremental approach starting from basic project monitoring and support through to strengthening ministry capability to extract best practises and upscale them to policy level and nationwide implementation. Due to the particular focus on M&E, the projects are producing a considerable amount of data on progress and results, which is available through the UNDP quality assurance and the data management in the MIE wing of LGD.

The annual UP and UZP performance assessments, subject to external performance audits based on clearly specified indicators, are another key source of information for tracking of results and capacity improvements at UP and UZP level, which may (or may not) be attributed to project interventions. Assessing emerging outcomes of capacity development support is not easy, but in general a results-based approach takes point of departure in defining ”capacity” as the ability of LGIs to fulfil their mandates and functions according to their legal mandate, development plans and resource envelope. Any improvement over time may serve as a proxy for improved institutional capacity. Starting with the identification of the results achieved since project start causality links between these results and the support provided by the project can be assessed and critical capability gaps identified. The PBGS applied in the UPGP and UZGP provides a very useful platform from which the MTE assessments could be further unfolded in accordance with the DAC criteria.

### 2.1 Methodology for the field work

The MTE selected a sample of six districts, 12 UZPs and 12 UPs for the field data collection. In order to be able to compare the development and progress made since the onset of the program in 2012, the six districts comprised of four districts covered by the UPGP and UZGP programs, and two districts outside of the program area for a counterfactual assessment. The selection was made to reflect various economic, geographical and variations in the performance of the LGI/capacity. Although the field sampling was focusing mostly on qualitative issues, it enabled a comparison of areas covered and not covered by the programs as well as reflecting on various levels of performance/capacity in the sample LGIs.

The four program-targeted districts were selected based on the annual performance assessment for allocations FY 2013/14 in order to ensure some variations in the performance:

Table: Districts and average scores of UPs in these

| Sl. | District | Previous Average score | Current Average score | % improvement in average score |
| --- | --- | --- | --- | --- |
| 1 | Barguna | 62 | 76 | 23 % |
| 2 | Brahmanbaria | 60 | 69 | 15 % |
| 3 | Khulna | 53 | 58 | 9 % |
| 4 | Kishoreganj | 40 | 50 | 25 % |
| 5 | Rangpur | 38 | 38 | 0 % |
| 6 | Sirajganj | 54 | 65 | 20 % |
| 7 | Sunamganj | 64 | 66 | 3 % |

The four program districts selected were:

- Sirajganj (long history of support, but somewhat fluctuating performance for average UP scores)

- Rangpur (very weak performance for average UP scores)

- Khulna (medium performance for average UP scores)

- Bramanbari (strong performance for average UP scores)

For counterfactual assessments of project outcomes, Tangal and Jessore districts were selected among districts not covered by project support.

In each of the selected districts, two UZPs, and two UPs were covered. The UZPs were selected to ensure that

- A minimum of five UZPs were covered by both specialized CB support from the UZGP and grants from the UZGP Fiscal Facility,

- Three UZPs were covered by specialized CB support, but not the fiscal facility

- Four UZPs were selected within the two non-targeted districts, two in each district.

The field data collection took three consecutive weeks and the data collectors split into two teams, each covering one district, two UZPs and two UPs per week. The data collectors selected the UPs in a random manner, in collaboration with program officials in consideration of logistical support needed. The detailed criteria for selecting UZPs and UPs can be found in the annex along with the data collection plans of the two teams and overall division of work with the MTE team.

### 2.2 Special considerations and limitations of the methodology

In general, the MTE was able to utilize the substantial amount of data being produced by the two projects. The amount of time and resources made available for the MTE also made it possible to address all relevant MTE aspects in depth. There were, however, certain aspects and conditions which needed special attention during the evaluation or which had a limiting influence on the methodology applied in the evaluation.

The two project results frameworks are generally elaborated, but complex, and somehow impacted by the fact that there apparently have been: 1) work on the results framework and fine-tuning of indicators and targets after program start-up, which has not been internalized amongst all parties; 2) that there are multiple formats and tables with indicators (e.g. for annual reports, for reports to EU, on the quarterly reports, etc.), not always tallying, and results targets in the various frameworks are not similar, as illustrated in Annex, 3) and there is field-level data from the annual performance assessments, which could be referred to in an aggregated form , instead of selecting new indicators. Furthermore, the baseline surveys and perception studies are referring to a number of indicators, which are not clearly linked to the results framework in the PD although they largely cover the information needs. Change of indicators and targets during implementation is a serious challenge for an evaluation. Especially, if not adhered to uniformly as it seems to be the case in these projects. While fine-tuning of indicators may serve better monitoring, change of targets moves the results framework from the original project document and hence from the legal agreements, funding was based on.

In response to this, the MTE team has applied a pragmatic approach by using the results framework of the original program documents as benchmark for tracking results. Where results have been further defined in other documents, and where clearly defined trend data is available, this was used as well with defined source for information. This included results from the annual performance assessments where the team retrieved data from two nationwide UP assessments of 12 performance indicators for two years, and a set of additionally 29 elaborated indicators for the UPGP target area. Similarly in respect of the UZPs, where the performance assessments for seven UZPs in the first year’s assessment and 14 UZPs for the second year’s assessments were used to review performance and areas in need for CB, etc.

A limiting factor for the MTE results assessment has been the impact of other ongoing support programs targeting LGIs in the pilot districts. UPs or UZPs may receive training and support from five to six different programs, potentially ”crowding out” and blurring the impact, contributions and attributions of specific project support in individual LGIs. The MTE team has tried to address this aspect by carefully mapping ongoing support in the sample districts, and tried to be very explicit in interviews on support and results and by utilizing available surveys (baseline, TNAs, citizens perception survey, etc.) to support overall assessments and conclusions.

A final aspect of consideration for the MTE was the serious delay in project implementation caused by the political turmoil in 2013 (see the annex for further information). The impact caused by the civil disturbances has effectually shortened the time for results achievements to be tracked by the MTE and has been factored into the overall MTE assessments on progress and results achievements.

# The UPs and UZPs and the local government system

The government of Bangladesh does not have any specific sector policy on local government and/ or decentralization. However, the constitutional provisions, sector polices and especially the most recent FYPs recognize the importance of a local government system and its role in development management and service delivery in Bangladesh, and the system is backed up by recently refined comprehensive legal framework for UPs (2009) and UZPs (2011).

The Constitution of Bangladesh describes the local government system and its board of generic functions in Article 59 and Article 60 (powers of local government bodies). In addition, there is a number of supplementary Acts and Rules regulating the different tiers of the local government system in Bangladesh.

The recent acts on the UP and UZP have recognized the importance of community participation, transparency and accountability by including specific sections on formation of ward committees, participatory planning, open budget sessions, access to information, and extended authority of the Standing Committees, etc.

The system of local governance and local administration is complex with several layers of administration and decision-making. The largest unit is the division, which is divided into districts, which are in turn divided into Upazilas and Unions.

Local Government Institutions (LGIs) of Bangladesh include 11 City Corporations, 313 Pourashavas (Municipalities), 61 Zila Parishads (Districts), 487 Upazila Parishads (sub-districts) and 4545 Union Parishads (rural local governments). Besides these, there are 3 Hill District Councils. These local government institutions are served by nearly 77,000 elected representatives and 75,000 government officials. Since inception, these local government institutions were given responsibilities for the maintenance of law and order, infrastructure development, promotion of health, education, and some other basic social services.

Democratically elected local government bodies termed parishads, meaning ”councils”, exist at both the upazila and union levels throughout rural Bangladesh. While the urban centres are covered by various categories of Pourashava (municipalities), and city corporations.

There are Zilla Parishads (at the district level), which are now run by an appointed administrator drawn from among the members of the ruling party. The local government system is overseen at the central government level by the Ministry of Local Government, Rural Development and Cooperatives (MoLGRDC).

The UPGP targets the lowest level of elected LGs and the rural part of this – the Union Parishads and the UZGP the second lowest tier of local government - the Upazila Parishads. The figure below shows the organisation of these tiers.

Figure: The Union and Upazila Local Government Structure

The UP Act 2009 is a comprehensive and far reaching LG Act that has incorporated some of the fundamental features of good governance, women’s empowerment, accountability, transparency, participation and social control, effective service delivery, and if effectively implemented will address some of the challenges in the existing system. There is therefore a focus in the UPGP on supporting the implementation of this as well as related rules and regulations.

Union Parishad (UP) is governed by an elected body composed of 13 members; one from each of the nine wards, three women members (from reserved seats – one from each of three wards)and the chairman elected by the total electorate of the UP. The UP is staffed by a full time secretary, appointed by the deputy commissioner who is head of district administration, and local police (1 Dafadar and 9-12 Gram Police). The UP secretary is responsible for accounting and record keeping and all kinds of registration e.g. birth, death, etc. The UPs are mostly involved in the selection and implementation of schemes, sanitation programs, local level revenue collection, registration of births and deaths, social safety net activities such as, distribution of relief goods and Vulnerable Group Feeding (VGF), preparation of list of widows for pension distribution and organization of food/cash for work activities (popularly known as Kabikha); maintenance of law and order including conflicts resolution and administration of justice (village court). The UP Act 2009 introduced new governance dimensions such as the Ward Shava, Open budget, Citizen Charters, provisions to implement Right to Information Act, use of information technology and deployment of additional staff from different line departments of seven Ministries. These new dimensions aim at strengthening the downward democratic accountability aspects of the UP operations and foresee a significant increase in the role and impact of the UPs on local development.

Upazila Parishad (UZP) is the second tier of local government, re-introduced in 2009 after a gap of 18 years, with the election of 475 UZPs. The number of Upazilas now stands at 487, each with an average population of approx. 250,000. The UZPs are entrusted to anchor local democracy, undertake local development and ensure efficient public service delivery within the realm of citizen engagement, accountability and transparency. Through deconcentration of LM functions, 17 designated departments now operate at Upazila level. The Upazila Nirbhai Officer (UNO) has been appointed to act as the vertical and horizontal point of administrative coordination with the Central Government, UZP and local administration.

### 3.1 Elections

The UP and Upazila elections are held regularly after every 5 years on a single day. However, in 2011 and 2014, respectively, the government staggered elections over three month for better monitoring and management.

The last Upazila elections were conducted from February to May 2014 in six phases and in 458 out of 487 Upazilas. However, as of recent date, the Election Commission has not published the detailed electoral data on a web site except formally announced the gross results. The election has been characterized by violence and irregularities. Media reports and election observers have labelled it as one of the most violent and rigged election of the local governments of the recent past. For the UPs the last election was in 2011, and the next one is due in 2016.

By law, none of the LGI elections can be held on party basis. The candidates cannot use the symbol of any party nor can they even use the picture of any party leaders. However, in reality, all major parties formally and publicly announce their support for a given candidate, who in almost all cases is a local party chapter leader.

### 3.2 Functions of the LGIs

Although the UP has a long list of role and functional responsibilities, its institutional visibility is yet limited. The UPs are broadly responsible for economic, social and community development. As set out in the Local Government (Union Parishad) Act 2009, the UPs have several functions including: Maintenance of law and order, including assistance to the law enforcement agencies and resolution of disputes; adoption of measures to prevent disorder and smuggling; conducting of censuses of all kinds; registration of births, deaths, blind people, beggars and destitutes; planning and implementation of development schemes in the field of agriculture, forestry, fisheries, livestock, education, health, small and micro enterprises, communications, irrigation and flood control; implementation of other development schemes as assigned; development and use of local resources; motivation of people to use sanitary latrines; promotion of family planning; monitoring of development activities undertaken by different agencies (government, semi-government) in the Union; protection and maintenance of public property such as roads, bridges, canals, embankments, markets, telephones and electricity lines. In addition, specific rural infrastructure responsibilities defined for UPs are the maintenance of rural roads and the Planning and implementation of small construction projects, these include improvement of works on rural roads - for example schemes under some food-aided infrastructure projects are implemented through the UPs.

The UPs are also responsible, through the Union Market Management Committees (UMMC), for the operation and maintenance of markets within the union. Water supply, rural sanitation and building rural road network are also included in the list of the core responsibilities of the UPs. In addition, the DPHE works closely with the WATSAN Committee at UP level for supply of drinking water and sanitation. LGED has number of dedicated project for rural road and infrastructure projects at UP level. However, in such projects the UP’s role is nominal.

The functions of the Upazila Parishads are mentioned in the Second Schedule to the Upazila Act. However, the Government may include new functions if necessary by issuing Government notifications. After consultation with the UZP, the Government may direct any institution or service managed by a UP be transferred to the management and control of the Government.

The Upazila Parishads are assigned with a wide range of functions which broadly includes preparation of Five-Year Plans planning, Implementation of the programs of different Government agencies, infrastructure development including roads, irrigation and agricultural projects.

Furthermore, as per the Third schedule of the Upazila Act, services and support of 10 different Ministries and their attached department are “transferable by the Government to an Upazila Parishad”. The institutions and services transferable by the Government to an Upazila Parishad include: Upazila Youth Development Officer and other employees and human resources of Department of Youth Development, Ministry of Youth and Sports; The offices and functions of the UNOs and other subordinate employees, Ministry of Public Administration; the Upazila Fisheries Officer and subordinate employees, Department of Fisheries, Ministry of Fisheries and Livestock; the Upazila Health and Family-planning Officer, Ministry of Health and Family Welfare; the Upazila Women Affairs Officer, Ministry of Women and Children; the Upazila Primary Education Officer of the Department of Primary Education; the Upazila Executive Engineer, Local Government & Engineering Department, Sub-assistant Engineer, Public Health and Engineering Department, Ministry of Local Government, Rural Development and Cooperatives; the Upazila Agriculture Officer, Department for Agricultural Extension, Ministry of Agriculture; Project Implementation Officer Ministry of Disaster Management; the Upazila Social Services Officer, Department of Social Services, Ministry of Social Welfare.

The Annual Performance Report of the officers performing such transferred responsibilities is prepared by the Parishad and its Annual Confidential Report is prepared by the respective superior officers of the concerned Division.

The concerned Member of the Parliament from each local area acts as the Advisor to the Parishad, and the Parishad is obliged to follow the advices of such Advisor.

### 3.3 Fiscal Decentralisation Issues

Fiscal decentralisation has slowly started in Bangladesh, but the entire LG “sector” only accounts for a relatively smaller share of the total public budget. The GoB has introduced a substantial block grant system to the UPs, starting with the piloting under the SLGDG and up-scaled under the LGSP-LIC (2006-2011) and continued under the LGSP 2 and UPGP, and the legal framework for taxes is also being somehow improved/clarified. A comparison between the total budget for the GoB and the transfers from the LGSP 2 block grants and UPGP grants show that the total block grants to the UPs constitute only approximate 1  % of the total GoB development expenditures and only about 0.3-0.4  % of the total GoB expenditures and despite some per capita increase over the years, it is still below 1 USD per capita.

The review also shows that the block grants, despite some increase, do not follow the trends in the general increase of expenditures. The table also shows the relatively small size of the LGSP (BBG &PBG) and UPGP grants (EPBG) compared to the total public expenditure and development expenditures. This finding is also supported by evidence in the field, which shows that increases in the grants are needed to support the participatory planning process, involvement of citizens in meaningful planning and local service delivery and to build better trust and interactions with the citizens in all LGI operations. It should also be noted that the per capita allocation of grants in Bangladesh is relatively low compared to all neighbouring countries.

Table: Comparison of the Block Grants with the Total GoB Budget

|  | 2012/13 Taka | 2012/13 USD | 2013/14 Taka | 2013/14 USD |
| --- | --- | --- | --- | --- |
| Total GoB Expenditures | 1,740,130,000,000 | 24,168,472,222 | 2,162,220,000,000 | 30,030,833,333 |
| Total GoB Devt Expenditures | 531,720,000,000 | 7,385,000,000 | 651,450,000,000 | 9,047,916,667 |
| LGSP - Basic block grants | 5,477,000,000 | 76,069,444 | 6,191,300,000 | 85,990,278 |
| LGSP PBG | 830,700,000 | 11,537,500 | 924,100,000 | 12,834,722 |
| UPGP EPBG | 133,471,779 | 1,853,775 | 132,955,770 | 1,846,608 |
| Total block grants to UPs | 6,441,171,779 | 89,460,719 | 7,248,355,770 | 100,671,608 |
| Block grant to UPs as share of total GoB budget (%) | 0.37 | 0.37 | 0.34 | 0.34 |
| Block grants to UPs as share of total GOB Devt. Exp. (%) | 1.21 | 1.21 | 1.11 | 1.11 |
| UPGP grants as share of total GOB Devt. Exp (%) | 0.025 | 0.025 | 0.020 | 0.020 |
| Exchange rate (Used form LGSP MTR, August 2014) | 72 |  |  |  |

Source: Budget Ministry of Finance, Finance Division, Annual Budget 2014/15 and figures from the LGSP 2, MTR Final Report, August 2014, and from the allocations to UPs under the UPGP, 2013 and 2014 reports.

Each of the Local Government Units has been empowered by the Constitution to impose tax and tax mobilisation has improved in many UPs in the last 5 years, especially in the ones supported by the UPGP. Each of the LGIs has its own tax schedule. However, there are some overlapping areas where tax bases are shared on some formula basis. Empirical evidences suggest that such overlapping bases create confusion and conflict between and among the tiers of the LGIs like the UP, Upazila and Zilla Parishad. Also, the OSR still typically constitute below 10 % of the total revenues at the local level, but it is mentioned by field stakeholders to be important to ensure ownership, accountability and linkages between the LGIs and the citizens. It should be noted that the UZGP has provided block grants to 7 UZPs in FY 2013/14 and 14 in FY 2014/15, in tune of total 35 million Thaka and 70 million Thaka, respectively, which will continue in the coming years. Despite the importance of these grants, it appears from this review, that they are still insignificant compared to the total resources available at the UZP within the service LDs, and constitute a small share (less than one %) of the total public budget.

### 3.4 Women in Local Government

The Constitution of Bangladesh prohibits gender-based disparities and ensures equal rights, equal opportunities and economic and social equity for all the citizens of the country. Under the Constitution, women’s rights1 are protected. Bangladesh is a signatory to major global commitments and instruments on gender equality such as CEDAW 1979, the 1995 Beijing Declaration and Platform for Action, and the Millennium Declaration which strongly affirm that gender equality is a development goal and a human right. The constitution and key policies, specifically the Government’s Sixth Five-Year Plan, Vision 2021, the National Women’s Development Policy, and the National Action Plan, acknowledge the importance of promoting women’s economic and political empowerment and have provided special targets to establish equal opportunities for women in economic and social sectors of society.

Despite all efforts, gender inequality remains a significant barrier to development in Bangladesh in spite of the progress made during the past several decades. Despite significant gains in gender parity with regard to health and education, Bangladesh is still ranked in the lower quintile of the UN Gender Inequality Index (146 out of 186). Key reasons for this position are: limited access to justice, low levels of participation in public and political life and violence against women (UNDP 2013 and Report of the special Rapporteur on violence against women, its causes and consequences, 2014).It is noted that Bangladeshi women and girls face severe social barriers, including high rates of early marriage, demands for dowry, and gender-based violence.

Bangladesh has made significant achievements in raising women’s voices in decision-making at the national and sub-national levels: 50 seats out of 350 seats being reserved for women at the national parliament; 33 % of the women are nominated by political parties to directly context parliamentary elections; 10 % of recruitment to cadre posts in public administration are reserved for women; one of the elected vice-chairman at the sub-national level is a woman and at the local level, (rural and urban) three of the twelve councilor posts are occupied by women.

Women’s political participation is still limited. Politicization of local government is hampering progressing women’s political empowerment; huge investment in politics is another hindrance for women’s wide participation in elections. For poor and socially excluded women who have won elections are more as relatives of more powerful male politicians rather than political actors in their own right. Women candidates, especially poor and socially excluded women who have been nurtured and encouraged into representative politics through CSO networks or through NGO support, do not have the political networks or the resources. In both cases they are not expected to challenge gender norms and male dominance of political life. The lack of political institutionalization means significant numbers of EWR maintain and reproduce “welfarist” and “patron-politics” within local and national government (Hossain and Akter, 2011). There has been slow and gradual progress towards more inclusive constituency-based and democratic processes of engagement between EWR and their constituent. However, the increase in violence against women in public life and the denial of their rights suggest that women, without powerful (male and party-based) allies, may be more reluctant to engage in constituency politics and challenge accepted norms and modes of engagement.

This stereo typing of women’s role in politics consequently effects their political participation, mainstreaming of women perspective and postelection extent of their authority in development and financial decision making and functioning of respective LGIs. The mix of indirectly elected women members each representing a Union and directly elected Chair and Vice Chairs each representing the entire Upazila has the potential to provide the basis for strong Citizen-Parishad relations. It also has the capacity to address development perspective across the entire Upazila as well as connecting to the Union & Zila Parishads.

Despite efforts to increase their representation, women’s decision-making remains limited. For example, at the local level, a review of the revised UP Act of 2009 found that women have difficulties playing an effective role and their opinions on important ward matters were not binding. To address this, efforts have focused on introducing several accountability mechanisms at the Union Parishad level. These include: (a) formation of the Women Development Forum (WDF) at the Upazila to mobilize Union Parishad women members to better exercise their rights in decision-making; (b) earmarking 30 % of supplementary block grants for schemes identified as high-priority by women; and (c) chairing one third of the Ward Development Committees.

It is perceived that women’s political empowerment is particularly affected by violence against women. Of concern is that incidences of violence - physical, sexual, and psychological harm - are on the increase in Bangladesh. Anecdotal evidence from project partners suggests Elected Women Representative and women activists are experiencing higher levels of public harassment and threats to their personal safety as a result of the rising political instability (e.g. Aparajita, Sharique, ASK). A trend also highlighted by the UN Special Rapporteur on violence against women in the Bangladesh mission report (2014).

# UPGP and UZGP Intervention Logic and Strategy

The UPGP and UZGP were both launched in 2012. The projects are similar in design, with almost identical objectives, intervention logic and management setup, albeit targeting different tiers of government. Each project has a component dedicated to capacity development of the respective tier of government, a component dedicated to allocation of performance based block grants and a shared component dedicated to development of M&E capacity and policy advice within LGD. A fourth component in each project relates to project management.

Table. Project objectives and results by design

|  | UPGP | UZGP |
| --- | --- | --- |
| Overall objective | Capacities of local governments and other stakeholders are strengthened to foster participatory local development service delivery for the MDGs | Government institutions at the national and sub-national levels are able to more effectively carry out their mandates, including delivery of public services, in a more accountable, transparent and inclusive manner |
| Specific objective | Piloting and evaluation of innovations to improve the functional and institutional capacity, as well as the democratic accountability of Union Parishads, thereby increasing citizen involvement leading to more effective, efficient and accountable delivery of pro-poor infrastructure and services | Capacities of local governments and other stakeholders are strengthened to foster participatory local development services for the MDGs |
| Results | 1. Strengthened Democratic Accountability of the Union Parishads through Citizen Engagement | 1. Strengthened Upazila Parishads as more functional, transparent and accountable |
|  | 2. Innovations in Pro-Poor and MDG-Oriented Planning and Financing of Service Delivery by Union Parishads | 2. Strengthened Planning and Budgetary system at UZP with MDG orientation and pro-poor service delivery mechanism |
|  | 3. Strengthened national capacity for effective policy review, monitoring, lesson learning and capacity development of local government institutions (LGIs) for enhanced Local Governance. (Shared) |  |

.

### 4.1 Relevance

Both UPGP and UZGP are targeting capacity constraints faced by the respective tier of government to demonstrate improved absorption capacity to manage increase resource envelope in a transparent, accountable and participatory manner. The strategic interventions are directly linked to development objectives within the sixth Five-Year Plan (6FYP) and related strategic policy documents, which are further assessed in the separate relevance chapter. The objective to assist the GoB in improving the functional, institutional and democratic capacities of LGIs and strengthen their capacity to deliver pro-poor development planning and MDG related services links up with these plans as well as the UNDAF 2006-2011 in force at time of the project designs.

Relevance of the project designs

The design of the two programs was based on analytical work from previous programs, including the PA for the UZPs, and the SLGDG and LIC reviews, as well as dedicated analysis of flow of funds, review of the impact of performance incentives in the LGSP-LIC and grant guidelines, and reviews of challenges with the existing structure and systems in 2010-11 and a longer consultative process with other programs, stakeholders and development partners as well as testing of certain core elements. The impression of the MTE is that the design was relevant for the identified issues, and that it has proved its continued relevance for the current situation as well.

The capacity building support addresses some of the core weaknesses in the LGI performance, and will when fully implemented, contribute to the enhanced performance in the targeted areas such as planning, PFM, revenue mobilization and accountability. Compared to SLGSP and LGSP-LIC, the UPGP and UZGP aim to strengthen a broader approach to capacity development in order to capture both individual and institutional capacity gaps. Capacity development is not limited to training of individual key players at local the level, but is also focusing on legal frameworks, funding envelopes, planning and budgeting guidelines, leverage of partnerships with LMs and civil society and improvement of institutional incentives for transparent, participatory governance, strengthened planning and budgeting framework and a more sophisticated performance-based grants system.

Another addition to the broadened approach is the launch of the PAG, policy research on the LG framework and action research on project innovations as well as the formulation of a national framework for capacity development. The latter is a crucial instrument in sustaining capacity development targeting local government. Without such a framework, LGIs are faced with multiple approaches provided by multiple providers and often financed through support programs. Such often uncoordinated approaches easily result in capacity gaps not being addresses or duplications of efforts which are not cost-effective. Vesting capacity development in support projects with ad hoc interventions and funding is another sustainability risk which the CD framework will try to overcome.

UZGP and UPGP have jointly developed a gender strategy aligned with the national gender commitments of the Government of Bangladesh and the National Women Development Policy (NWDP). Both projects are committed to strengthen the capacity of elected women members, Parishad members and concerned governmental counterparts; ensure due resource allocation for gender focused activities; and to mainstream women members’ roles in political and development decision making for effective functioning of the respective Parishad and local democracy. The objectives and results frame of the gender strategy are embedded and mainstreamed in the project log frames and assessments of gender interventions will be addressed in this report, as and when the project interventions target gender aspects.

The second output with the main emphasize on the grant system for UPs provide important lessons on the expanded performance based systems, and lessons learned for future up-scaling. The potential is to demonstrate that UPs can handle more funds, and that expanded incentives can contribute to enhanced performance and service delivery outputs, and that performance assessment can be used to identify and address weaker areas of LGIs’ performance. The grants (UFF) under UZGP were a new innovation, and this is contributing to important lessons learned about discretionary funding at the UZP level, which aims to strengthen the links between UZPs and the Line Departments and the cross UP-coordination with stronger focus on MDG and focus on vulnerable groups in the allocation of funds. The system is showing that a combination of incentives, clear guidelines and technical support can contribute to reduce some of the challenges observed at this level and strengthen the mandatory roles of the UZP as a corporate body, and is addressing some of the challenges and problems with the existing system, although it is operating in a challenging structure with unclear responsibilities and authorities, including conflicts between UZP as a corporate body and the roles and perception of the MPs. Furthermore, the introduction of co-financing between the UZPs and UPs along with community participation should be mentioned as an innovative approach in local development taken by the project under its fiscal facility component.

Finally, the third joint output of the two projects was relevant for the issues identified prior to project start-up with gaps in coordination of CB, absence of clear policies on decentralization and gaps in the M&E systems and capacity and improvements in these areas are still pertinent for the sustainability of the governance and intergovernmental reform process, although this is a challenging area where progress is likely to take time.

The overall project approach is addressing the critical challenges in making decentralization work, which is often related with the lack of sufficient funding for service delivery, lack of capacity of the LGIs and incentives for performance improvements, and challenges in the framework conditions such as the legal framework, regulations, guidelines etc. and the objectives of targeting and improving on the local level MDGs. Especially the latter has been strengthened with the design of the UPGP and UZPG compared to previous interventions, and as concluded in this report is showing some impact, e.g. on the composition of the LGI investments and performance on planning.

The decision to go for two programs – the UPGPs and UZPG instead of one program was understandable in the light of the government structure, the risks identified, and the funding modalities and requests from DPs, but it is also creating challenges in terms of sharing staffing, funding, resource utilization and coordination.

The UPGP and UZGP logical frameworks with results, interventions, activities, means of verification and risks/assumptions can be found in Annexes 23 and 24, respectively.

### 4.2 Geographical coverage

The projects are implemented in seven pilot districts and UZPs and UPs selected according to poverty and MDG ranking, considerations to ensure that some of the previously supported LIC districts were captured and need to ensure a variation of the geographical coverage (one district from each division). The UZGP provides capacity building support to all UZPs in the country, but is topping up with special training to the 65 UZPs in the seven pilot districts. A special annual performance grant- the Upazila Fiscal Facility (UFF) - has been allocated to seven UZPs in FY 2012/13 and 14 UZPs in FY 2013/14, respectively and selection of future 14 UZPs of the next fiscal year’s allocations will be based on competition between the 65 UZP in the 7 districts. The UPGP provides capacity support to all 564 UPs in the seven districts and is piloting an annual UP performance grant, which is allocated to the best performing (approximately 70 %) UPs, in FY 2012/13, this was 404 UPs and in FY 2013/14 this was 410 UPs. The shared component three of the projects provides capacity support to LGD on M&E and policy advice to central government, including support to the legislative and regulatory frameworks.

### 4.3 Funding

The projects receive multi-donor funding, which apart from UNDP and UNCDF also include funding from the EU (both programs), SDC (UZGP) and Danida (UPGP).The total project budget for UZGP is USD 19,312,916 and for UPGP USD 18,391,108, hereof GoB’s contribution is around USD 0.9 mill each.

Table. Project funding sources

| UPGP |  | UZGP |  |
| --- | --- | --- | --- |
| Government | BDT 800 lakh | Government | BDT 700 lakh |
| UNDP | USD 2,000,000 | UNDP | USD 2,000,000 |
| UNCDF | USD 1,500,000 | UNCDF | USD 1,000,000 |
| European Union* | USD 9,305,556 | European Union* | USD 10,138,889 |
| DANIDA* | USD 5,585,552 | SDC* | USD 4,920,000 |

*Contributions are provided in EUR, DKK and CHF, respectively and subject to exchange rate variations

Progress reporting is to a large degree made separate and follows individual donor reporting formats and country program frameworks.

### 4.4 Project organisation and management

Both projects are nationally implemented projects (NEX) managed by LGD and supported by UNPD and UNCDF in terms of QA and thematic TA. Although both projects are anchored within the LGD, each project is managed by its own steering committee and project board, and has its own G-G agreements, budget and funds allocations. The UZGP was also started six month before the UPGP.

Chart. UPGP & UZGP have similar project organisations

The Management and project Implementation setup is similar in the two projects and to a large extent merged in at the advisory and implementation level (second part of the table below).

Table. Role and responsibilities in UZGP and UPGP

| Management & project support | Functions |
| --- | --- |
| Steering Committee - Chaired by the Secretary, LGD - Representatives of all relevant ministries, UP and UZP ass., DPs, Training institutes, NGOs | Policy advice and guidance linking between project activities and national development initiatives Meets twice a year |
| Project Board - Chaired by the National Project Director: Joint Secretary, LGD (resp. for UPs and UZPs, respectively) - Representatives from UP/UZP, UNO/UP secretaries, UNDP, UNCDF | Responsible for the project implementation Meets twice a year (minimum) |
| LGD Focal Person - Additional Secretary, LGD (resp. for UPs and UZPs, respectively). | Day-to-day project executive assisting the NPD |
| Project Manager | Accountable to the Project Board, the NPD and UNDP/UNCDF on day-to-day activities and overall coordination, work plans |
| Monitoring and Evaluation Team - 1 M&E Officer and 1 MIS Officer | Support to LGD MIE wing |
| Operations Team - 1 Operation Manager, 1 Finance Officer, Admin support staff. | Operational support to project management |
| Project Assurance - UNDP and UNCDF CO teams | Ensuring project management delivers planned outputs as per the annual work plan on the basis of the monthly, quarterly and annual progress reports. Organizing monthly reviews with the PEG and other reviews at the level of the PB. |
| Implementation |  |
| Divisional Team | Division government officials and project-supported technical staff resp. for implementation of Output 1 activities in all 487 UZPs and all targeted Ups, respectively (also shared with LGSP II) |
| District Team | District government officials and project-supported technical staff, will ensure implementation of Output 2 activities in the selected 14 target UZP and all targeted UPs in 7 Districts (also shared with LGSP II) |
| Policy & Capacity Development Team | LGD officials and project-supported technical staff responsible for implementation of Output 3 at the central level |
| Technical Advisory Team - 1 local governance advisor will work largely on Output 1 - 1 fiscal decentralization advisor will work mainly on Output 2 - 1 gender officer | Policy advice to LGD. Working across outputs |

### 4.5 Linking to previous projects and the LG framework for sustainability

The sustainability criteria of project results are defined somewhat similarly in the two project documents. The project interventions are designed in order to promote scalable innovations, which are simple, robust and implementable, build on previous lessons and link up to strategic focal areas of the local government framework.

The sustainability rests on a number of assumptions, including GoB ownership to project results, mutual horizontal and vertical cooperation between the MLGRDC and the line ministries (LM), the ability to overcome rent seeking, ensure strong incentives for performance and facilitate genuine local participation, rights-based and gender oriented planning and MDG service delivery etc.

The anchoring of the projects in LGD and interventions directly linked to the legal framework of local governance (UP Act 2009, UZP Act 2009, RTI Act 2009, the Union Parishad Operational manual and the Upazila Parishad Operational Manual) is assumed to sustain project achievements through political support to both projects, of which the UZP level is particularly dependent as it has just been re-introduced with elections to the UZP, few years before project start.

Sustainability is further planned enhanced by the shared support for the MIE wing to gradually build capacity to monitor projects and upscale of pilot innovations to policy advice and nationwide replication. The anticipated national upscaling in particular is also vested in the support from complementary local governance programs financed by other development partners, first and foremost LGSP 2 (supported by World Bank-IDA) on which the UPGP is linked in a rather similar role as the linkages in LGSP-LIC. The infusion of new innovative top-up grants through the performance-based grant system is expected to create further incentives for cooperation between all stakeholders at UP and UZP level on the annual and five-year development plans, ensuring participation and a higher degree of MDG oriented service provision and strengthening of the linkage between the UPZ and the Line Departments at the Upazila level.

The project interventions build on innovations piloted by previous support projects, SLGDP, LGSP-LIC and Upazila PA with an aim to up-scaling them and further refining the development tools and approaches applied. Innovations from previous projects include

- Formula and performance-based block grants, allocated through direct funds transfers

- Multi-year participatory development planning

- Standing committees, open budget meetings , Women’s Development Forums (at District and UZP level), and ward shavas (UP level)

- Various accountability measures such as disclosure of information, citizens’ charters, etc.

- Increased transparency and participation as a means of mobilising own-source revenues

- Incremental and needs-based approach to innovations

- Peer learning

- Cascading approach to capacity building

The UZGP was conceived on the lessons learned from especially the Preparatory Assistance Project (PA) from 2009-2011, which contained support to capacity needs assessment, TA/CB support, support to the regulatory framework and planning as well as policy advocacy and awareness raising on the roles and functions of the UZPs and the MDG piloting on planning in selected UZPs. It was based on a solid analysis of the fiscal and governance challenges for this level of government. However, compared to previous interventions, the new performance-based UFF and the enhanced focus on planning, budgeting, accountability and up-scaling of the gender aspects such as especially the support to the WDFs were interventions, which aimed at deepening and strengthening of the reform process and the capacity of the UZP to fulfil their mandatory role with a view on future options for up-scaling. The UFF design also learned from the block grant experiences from the SLGDP and LGSP-LIC, but customized these to the special Upazila-level needs and conditions to address the special challenges identified in the preparatory work for the project, see below on a review of some of the similarities and some core variations:

Table: Links in Features between UP and UZP Support

| Features of the block grants | UP block grants (LGSP-LIC, LGSP 2, PBG, UPGP EPBG | Upazila Fiscal Facility (UFF) |
| --- | --- | --- |
| Formula-based | Yes | Yes |
| Performance-based with a number of clearly defined MCs and PMs | Yes | Yes |
| Performance Assessment Manual | Yes | Yes |
| Robust reporting system and accountability measures and gradual development of MIS | Yes | Yes |
| Performance assessments contracted out to neutral assessors/auditors | Yes | Yes, however, with more involvement of the division/ district-based staff (DLG and DDLG) in support of this. |
| Clearly defined multi-sectorial investment menu | Yes | Yes |
| Focusing on development expenditures (mainly capital) | Yes | Not only: The investment menu is broader and covers, in addition to capital investments, other forms of support to service delivery, e.g. operational support to health and education, with a very strong focus on MDG targeting. |
| Coverage areas/beneficiaries of the scheme selected by LGIs | Mainly within one UP | Supposed to link up and cover benefits for several UPs and projects linking closely with the line departments. |

EPBG: Expanded performance-based grants, PBG: Performance-based grants, MCs= Minimum Conditions, PM= Performance Measures, UFF=Upazila Fiscal Facility.

Similarly UPGP was based on previous experiences from interventions under the SLGDP and LGSP-LIC with a number of refinements, based on good lessons learned from more than a decade of support to LGIs, see below.

Table: Comparison of UPGP with LGSP-LIC and Lessons Learned

| Features of the projects with main focus on the grant system | LGSP-LIC | UPGP |
| --- | --- | --- |
| Institutional arrangements at the local level | Special piloted bodies for scheme supervision, decision-making, coordination, etc. of which some have been mainstreamed in the UP act and subsequent regulations. | Focus on use of the common UP-Operational Manual and focus on strengthening of the mainstreamed model of the LGI system, including UP councils, standing committees, WDFs, and Ward Shavas as per the UP Act and regulations. Compared to LGSP/LIC, there is more focus on the lower level of planning, especially the Ward Shavas. |
| CB approach | Cascading approach, which is largely based on the government resource base and Training of Trainers (ToT) in a mainstreamed model. | Carried over of the cascading approach, but refined. UPGP is using a flexible approach depending on the areas and beneficiaries. More use of other tools such as Peer-to-Peer review, TA, backstopping support, MIS support, exchange visits, video/skype support, etc. Closer linkage between the objectives of the project, the results of the performance assessment system and the CB support rendered through analysis of the results in the APA. |
| Grants | Performance-based grants (PBGS), with formula and assessments. Direct transfer of funds to UPs. | Carried over but refined. Formula- and performance-based allocations. Direct transfer of funds. New elements (not applied in the previous projects): Performance-based as LIC, but with strengthening of the MC and PMs, more targeting towards core objectives of the project, and strengthening of the QA, appeal as well as institutionalization in the Ministry (MLGRDC-LGD). Performance measures are stronger in their focus on MDG planning and support of vulnerable groups. Performance element directly integrated in the general formula in a weighted manner (second generation of PBGS), in a more competitive model. Performance in one UP is compared with the performance in other UPs within the same district, i.e. not across districts (i.e. a fairer model). Improved workbooks /guidance for the assessment teams. Joint training of assessment teams and joint auditing and performance assessments. More formalized system of QA in cooperation with the LGSP II. |
| Use of funds | Capital investments (practice, the majority of investments went on the road sector). | Capital investments. New elements: Strong incentives to use funds on MDG targeting and with an option to use 10 % for CB /support. Strong incentives in the performance measures to spent on vulnerable groups and MDG targets. Funds can be rolled over from one FY to another FY. Stronger accountability measures. |
| MIS | Was emerging, but not substantial and robust. | New and stronger system, including system of quarterly reporting. Strengthening of the reporting and MIS + piloting of computerized system of MIS in 146 UPs to be rolled out in 2014-2015, + linked to measures of taxation, such as tax databases etc. Strengthening of backstopping and monitoring missions. |
| Performance measures | LIC had separate performance measures (PMs). | Carried over, but refined and integrated with LGSP. UPGP and LGSP have a common set of 12 PMs, but UPGP expands on these to a total of 41 PMs with the aim to generate lessons and future up-scaling options and to support the project objectives and CB needs identification. |
| Factor in of performance in formula | Rigid system of performance groups (bands). | Gradual innovative “third generation” model of incorporation of performance scores in the allocation formula where every point counts in a weighted and balanced manner without distorting the basic formula and where all have equal incentives to improve. |
| System of performance assessment | Contracted out with QA, training and contracting done separately from the remaining LGSP system. | Contracted out with QA but now done jointly with LGSP and with a strong anchoring in LGD (incl. audit cell) and with joint training, QA and decision-making on results. Audit and performance assessments are made jointly. Audit review and appeal systems are institutionalized and formalized. |

### 4.6 Links with LGSP 2

UPGP is not a component in the nation-wide LGSP 2 unlike LIC, which was integrated in the management structures of LGSP l. But there are several common features and links (see below). This has also been facilitated by a joint MoU between the World Bank and UN agencies on collaboration on core initiatives under the projects (see also the partnership section). It may even be argued that compared to the LGSP-LIC, which was under one management umbrella, there are more joint arrangements in the new set-up, as i) the general UP Operational Manual is used by both programs, ii) as there is an extensive cooperation on the audit/performance assessments, iii) stronger linkages in the performance indicators, see Annex 20 (MCs and Performance Measures) where the LGSP II PMs are a sub-set of the more expanded UPGP PMs, and iv) joint cooperation on part of the CB support, including the support of the DFs. The joint design elements on the PBGS, e.g. in the linkage of indicators and training of auditors/assessors have benefitted reduced transaction costs and enhanced better understanding of the systems on the ground, and the review shows that this is highly appreciated by the UPs, the auditors and the facilitators involved. This system of linkage of a pilot with a national system is rather unique of its kind internationally and was an innovation compared to LGSP/LIC. However, there is still room for strengthening of this cooperation in terms of policy studies undertake by UPGP, MIS for UP reporting, where the two programs have moved in parallel, and improved planning and financial management.

Table: Differences and Linkages between LGSP 2 and UPGP

| Features | LGSP 2 | UPGP |
| --- | --- | --- |
| Management arrangements | LGSP 2 SC but with the same NPD as for UPGP. | UPGP - SC but with the same NDP as for the LGSP 2. |
| CB support | Mostly cascading approach, with TOTs and Upazila Resource Teams. | Various approaches depending on subject area and beneficiaries and with most of the support rendered by the 5 strong national training providers. |
| Grants | Two major types: i) Basic block grants to all UPs, divided in two components (one entitlement grant and one based on compliance with the MCs). ii) Performance-based grants (to best performing 75 % Ups. | Expanded (top-up) performance-base grants to around 400 (70 % best) out of 564 in the target areas, and based on compliance with joint MCs and where size depends on performance. |
| MCs | 3 core MCs | Similar to LGSP – II |
| Performance measures for the PBGS | 12 performance measures. | 41 performance measures of which the 12 PMs in LGSP are part of these (sub-set). PMs focusing more on qualitative aspects of PFM, governance, transparency and use of funds (MDG and gender sensitive areas). |
| Performance Competition system | Performance in one UP is compared with performance of other UPs within an Upazila. | Performance in one UP is compared with the performance of other UPs within the entire district. |
| MIS | Simple monitoring and reporting system, but with plans to up-scale to a computerized MIS. | Piloting of MIS systems in 146 UPs and elaborated system of data capturing. Advanced system of MIS, computerized and prepared for up-scaling. |
| Legal framework and policy research | Limited. | Extensive support to regulatory and policy framework on local governance and future studies and support to LG advisory group when fully operational. |
| Joint arrangements |  |  |
| Assessments | Assessments contracted out to audits. | Similar. |
|  | Structure of the performance assessment manual. | Similar, but more elaborated and clearly linked. |
|  | Quality assurance by LGD and project. | Similar. |
|  | Similar. Training of audit teams supported by UPGP. | Similar. Conducted by UPGP, which covers LGSP needs. |
|  | Performance measures (PMs) has a joint group of PMs with UPGP. | Joint group of PMs with LGSP but refined and elaborated (29 additional indicators). |
| UP Operational Manual | Many joint features with a brief annex on the LGSP arrangements (e.g. similar investment menu). | Many joint features with a brief annex to the OM on the UPGP grants. |
| Backstopping support | Jointly shared District Facilitators. | Jointly shared District Facilitators, stronger support to the DDLGs and other operations. |

.

# Relevance of Project interventions

Both projects were designed in 2011 within the framework of UNDAF 2006-2011, the 2009 MDG progress report for Bangladesh and aligned to strategic interventions in support of GoB policies towards decentralization and local governance, first and foremost expressed through the sixth five-year plan (6FYP) interventions targeting the subnational framework of UPs and UZPs. The question for the MTE is whether the projects have remained relevant vis-à-vis current trends in GoB local government policies and the new UNDAF 2012-2016.

### 5.1 UNDAF 2012-2016

In 2011, the UPGP and UZGP intervention strategies referred to UNDAF 2006-2011, outcome 1: ”Government institutions at the national and sub-national levels are able to more effectively carry out their mandates, including delivery of public services, in a more accountable, transparent, and inclusive manner”. Since the implementation started in 2012, the five-year UNDAF 2006-2011 was superseded by UNDAF 2012-2016.

In essence, the commitment to support local governance is carried over the present framework. The overarching goal of UNDAF 2012-2016 is to support the GoB and its development partners, with applying the principles of the Millennium Declaration and accelerating the achievement of the Millennium Development Goals with Equity. In order to achieve this, five core strategies has been outlined for the five-year plan, which includes:

- High-level advocacy for UN core values, including equity, human rights, gender equality, human security and dignity, and environmental sustainability

- Capacity development at individual, institutional and societal levels, within central and decentralized structures

- System strengthening, including modelling of service delivery systems in deprived areas and then taking them to scale

- Strengthen the role of civil society and building partnerships between stakeholders

- Strong focus on targeting (geographically) the most deprived groups

These core strategies are spanning across seven thematic intervention areas or UNDAF pillars:

UNDAF Pillar 1: Democratic Governance and Human Rights

UNDAF Pillar 2: Pro-Poor Economic Growth with Equity

UNDAF Pillar 3: Social Services for Human Development

UNDAF Pillar 4: Food Security and Nutrition

UNDAF Pillar 5: Climate Change, Environment, and Disaster Risk Reduction & Response

UNDAF Pillar 6: Pro-Poor Urban Development

UNDAF Pillar 7: Gender Equality and Women’s Advancement

The core strategies within the seven UNDAF pillars set out to achieve twelve corresponding outcomes in the UNDAF results framework. The strategic linkage between UNDAF and UPGP and UZGP and hence the relevance of the projects within the UNDAF can be found under especially Pillar 1:

Table. UNDAF Pillar 1 with MDG linkages

| UNDAF Pillar 1 - Democratic Governance and Human Rights |  |  | MDG Linkages |
| --- | --- | --- | --- |
| OUTCOME 1.1 | Output 1.1.5 | Indicator: | Goal 3: Promote gender equality and empower women Millennium Declaration |
| Government institutions at the national and subnational levels are able to more effectively carry out their mandates, including delivery of public services, in a more accountable, transparent, and inclusive manner | Selected local government mechanisms have improved capacity to deliver public services | No. of Unions and Upazillas (sub-districts) in selected areas that have functional coordination forums, addressing communities’ demands for quality services and promoting dialogue between service providers and community members (UNDP, UNCDF and UNICEF ) |  |

The UNDAF outcome/output above can be seen as the primary justification for the projects, but there are other entry points for local governments in UNDAF, which may also have ramifications for UPGP and UZGP or at least indicate potential linkages to and partnerships with other project in the UN family. The latter will be explored further in the section on partnerships.

The other UNDAF selected pillars with a bearing on Local Government, and with linkages to the projects include:

UNDAF Pillar 2: Pro-Poor Growth with Equity

Output 2.1.3: Vulnerable and disadvantaged populations gain better access to productive resources (– where LGIs are taking lead in local development).

UNDAF Pillar Three: Social Services for Human Development

Output 3.1.7: Authorities in LGIs have the technical and managerial capacity to implement WASH package to ensure safety and sustainability of drinking water, especially for the poor.

UNDAF Pillar Five: Climate Change, Environment, Disaster Risk Reduction and Response

Output 5.1.2: Community and Local Institutions have greater capacity on Disaster Risk Reduction and climate change adaptation.

However, also UNDAF Pillar 7: Gender Equality and Women’s Advancement, is addressed through several interventions of the projects, especially under the support to operationalization of the Women Development Fora at the Upazila and District levels.

### 5.2 Government of Bangladesh Policy framework

As such the government of Bangladesh does not have a specific sector policy on Local government and/or decentralization. However, Constitutional provisions and selected sector polices as well as the overall development strategies do recognize the importance of the local government system and its role in development management and service delivery in Bangladesh.

All major policy documents irrespective of the regime have emphasized the need for decentralization and strengthening of local government. Importance of local government in Bangladesh has been recognized by the Constitution and several policy documents, including the National Rural Development Policy (NRDP) and the Poverty Reduction Strategy Paper (PRSP). The National Rural Development Policy provides support for the development of mechanisms and the 6FYP. Of late the concept paper of the 7FYP has also highlighted the need for strengthening of local governments.

The Constitution of Bangladesh describes about local government system and its broad generic functions in Articles 59 and 60 (Powers of local government bodies). Article 60 provides the foundation of the broader role and functions of the LGIs. In addition, there are numbers of supplementary Acts and Rules regarding different tiers of the local government system in Bangladesh.

In line with the Constitution, the Government of Bangladesh enacted the Union Parishad Act 2009 replacing the old UP Ordinance of 1983. The new UP Act recognizes the importance of community participation, transparency and accountability by including specific sections on formation of ward committees, participatory planning, access to information, and extended authority of the Standing Committees, etc.

The National Rural Development Policy provides support for the development of mechanisms to develop the role of the local government as a facilitator and creator of ”necessary conducive environment for the required services to be provided to the rural people and also expand the opportunities”. It underlines the importance of ”accountable and responsive” local government institutions, where ”people will be made aware of and given access to services and opportunities offered by government”. The document further asserts: ”The centre-piece of the National Rural Development Policy is a strong and accountable system of local government, especially the Union Parishads. Union Parishads need to be empowered with additional resources, authority and training. A transparent formula needs to be put in place by which a significant amount of funds will be devolved to the union level as a matter of right, rather than as a function of central control. Union Parishads also need to be made accountable to the people through a system of regular village meetings as well as mandatory public display of information regarding government expenditure at all levels”.

MDG policy of Bangladesh noted the importance of ”institutional reforms to strengthen local governments”. In order to ensure power of local government institution the MDG policy also noted the need for ”enhancing the financial and administrative power of local government institutions”.

The PRSP as policy document has duly recognized the need and importance of the role of local government. The PRSP emphasized the need for: ”empowering local government as the engine for delivering services and carrying out development activities, ensuring equal status for women in all spheres of society and state, and creating gainful employment for the labor force”.

The Second Poverty Reduction Strategy underlines the multidimensional nature of poverty and suggests few important areas of intervention of LGIs (Local Government Institution/UPs. PRSP has recognized the need, importance and the role of Local Governments as an active partner/ implementers of the program. PRSP categorically noted that: a. ”Local governments will be involved in microcredit delivery”; b. ”In order to mainstream rural non-farm activities in rural development, an institutional set-up will be formed with different stakeholders, including local government institutions”; c. ”There will be involvement of local government bodies and NGOs for greater participation of the community with a view to ensuring community driven primary health care services”; d. In extending the rural road connectivity ”more involvement of local government institutions (LGIs)” will be made and the LGIs will be involved in “ensuring utilization and maintenance of constructed facilities; e. For Disaster management ”greater involvement of local government bodies and emphasis on non-structural mitigation” will be given; f. For the Control of Non-communicable Diseases “the government will, in partnership with local government administration and private sector create greater awareness”; g. For promoting good governance the PRSP acknowledged the importance of local government for “Improving the quality and predictability of public service delivery, expand citizens” participation and promotion open hearings to ensure that local government is responsive to citizens’ needs.”

The 6FYP provides the following vision: “The local governments  will  be  strengthened  and much of the responsibility for  delivering  basic services such as irrigation, district roads, education, health, population management, water and sanitation services will progressively be decentralized to local governments”.

The 6FYP strongly emphasized that “a strong local government that has well defined responsibilities and accountabilities can play a major positive role in delivering basic public services. Strengthening of local government and decentralization of authority imply delegating powers of the central government to the local level with the aim to addressing major issues like poverty reduction, good governance, infrastructure development and disaster management. Efficient and dedicated local government bodies can deliver services and generate social and economic awareness to achieve the national goals”.

The 6FYP therefore noted that: “promoting devolution to local governments” as one of the four pillars of development management. The Plan document further recognized that “Efficient and dedicated local government bodies can deliver services and generate social and economic awareness to achieve the national goals”. As regards the local government, the main strategic elements of the 6FYP include developing a well-designed legal framework for decentralized governance; increasing the transparency and improving the accountability of local governments; building the capacity of local governments, expanding and strengthening participation of the citizens in prioritizing in the implementing and monitoring of development programs and other functions of the local government.

The 6FYP recognized that: “the potential of local government bodies, particularly the Union Parishad, to coordinate a streamlined institutional strategy needs to be actively explored”. Furthermore, it acknowledged the need for strengthening local government and decentralization of authority imply delegating powers of the central government to the local level with the aim at addressing major issues like poverty reduction, good governance, infrastructure development and disaster management. Efficient and dedicated local government bodies can deliver services and generate social and economic awareness to achieve the national goals.

Noting the importance of the grassroots-based local government, the 6FYP observed that “an important corollary of moving towards a comprehensive approach on social protection programs will be the need to streamline the institutional strategy on implementation. The potential of local government bodies, particularly the Union Parishad, to coordinate a streamlined institutional strategy needs to be actively explored”.

This focus is continued in the coming FYP. The 7FYP of Bangladesh, which is under preparation, recognizes (in the Concept note) that some of the reform agenda is “unfinished”. The concept note reiterates that the government is keen to initiate several reform agendas to strengthen institutions and improve the capacity of the core government agencies. Progress in several institution building efforts, such as the development of local governments and municipalities has been below the expected level. This is an unfinished agenda.” The Concept note also notes that additional efforts are needed concerning the adaptation to climate change”. And “adaptation to alleviate the long term adverse implications of climate change requires substantial efforts”. Furthermore, the 7FYP aims at strengthening planning, budgeting and development program implementation at the local level and plans to include a dedicated chapter on Strategy for Local Government.

The Ruling Party Awami League in its election manifesto has also highlighted the role of grassroots based local government. The manifesto noted that the Union and Upazilla will be strengthened through decentralization of power. Every union will be made the headquarter for development and administration of the area and be developed as a planned rural township. And every Upazilla headquarter will be developed as an industrial growth centre and a planned township”.

### 5.3 Conclusion

Upon review of the UNDAF and all major policies of Government of Bangladesh, it is evident that the goals, objectives and interventions of UPGP and UZGP are directly relevant and consistent to those policies. As it will appear in the results assessments chapter later in this report, both projects have made good progress against the outcome and output indicator under pillar 1, which measures progress in establishment of functional UP and UZP coordination forums, addressing communities’ demands for quality, services and promoting dialogue between service providers and community members. But specific targets are still under review and could not be taken into account. The involvement of women has also increased, with WDFs as the mobilizing innovation.

It is also well recognized by GoB in the preparation of the coming FYP that progress in the overall implementation of overall decentralization process has been slow and that more needs to be done in the coming phase.

Both the current UNDAF and the GoB support the development of empowered LGIs and a conducive framework for a participatory, transparent and accountable subnational system, which can be a key player in local planning for development and equitable delivery of MDG services. This underlines the continued relevance of UPGP and UZGP, also in relation to the upcoming 7FYP and does potentially outline future linkages and partnerships

What is not so clear from the broad statements in the government policies and strategies mentioned above, is how a local government reform can be outlined in the future in terms of strategic entry points, administrative-territorial changes, fiscal reforms, devolution of functional responsibilities and staffing and capacity building framework. The design of the UPGP and UZGP recognized this gap in specific strategies and implementation frameworks and include support and inputs to this discussion as one of the key intervention areas under the shared output 3.

# Assessments of Results - UPGP Output 1

Output 1: Strengthened Democratic Accountability and transparency of the Union Parishads through Citizen Engagement

The UPGP is designed to work directly with four institutional platforms that form the core of local governance: the Union Parishad, the Standing Committees of the Union Parishad, the Ward Shavas, and the Women Development Forum (WDF). These platforms have created democratic space for citizens who were otherwise deprived and or ignored by the local power structure and the political elite, including the UP representatives. This output has facilitated the process of installing a formal mechanism for promoting of consultative processes and open hearings to ensure that UPs are responsive to citizens’ needs. The project has applied a combination of CB support and performance incentives in the performance-based grant allocation system, which has clearly defined indicators to promote accountability and transparency, see Annex 20.

Field data, observations visits and the Citizen Perception Survey (CPS, September 2014) demonstrated that UPGP has brought some positive changes in the overall governance of UP. The citizens have now better access to information and are more aware of the roles and responsibilities of UPs. All meetings including Ward Shava, Parishad and Standing Committee and other UP Committees are almost up to the standard set by UP Act 2009. Significant improvement has been observed in preparing the Annual Plan and Five Year Plan mainly due to the capacity development training under UPGP, and the incentives created under Output 2, see following chapter.

Monitoring and supervision has been increased and as a result the quality of service delivery regarding project selection and implementation has also been improved. The newly installed MIS system has been playing a great role to get updated information. Through WDF, women, particularly elected women representatives of UPs, have become more aware of their rights and other issues. They have got a platform to raise their voice and do not feel helpless any more.

The intervention has strengthened the capacities of UP to foster participatory local development planning and service delivery including addressing the MDGs, see Output 2. By installing an accountability system, the output has ensured the inclusion of pro-poor infrastructure and services in its planning and project selection process. Furthermore, it has installed a democratic accountability system through community engagement and mandatory public display of information regarding UP expenditures.

In line with the GoB policy () framework, this project output appears to have noticeably contributed towards developing “a strong and accountable system of local government at the Union Parishad level”.

The project has provided considerable support to activate the six most critically important Standing Committees. The performance, as documented from the first to the second APA, see Annex 21, has improved significantly, and the field work has confirmed a marked difference in this area. Furthermore, the project output has supported women’s empowerment, and organized Women Development Forum – a platform of the female Members of the UPs.

In all cases the achievements of the indicators are above the base line (see Annex 12 with the complete results framework) and in one case significantly exceeded the end target, and there are significant performance improvements in most areas of the annual performance assessments when it comes to transparency, accountability and citizens’ involvement, see Annex 19. The table below show selected core areas of performance.

Table: Selected indicators of UP performance

| Indicators | Base line | Target | 2014 |
| --- | --- | --- | --- |
| % of target UPs with at least 6 key standing committees producing at least 2 monitoring reports per year. | 28 % | 50 % | 100 % |
| % of targeted UPs which have at least 1 woman representative participating in officially registered women Development Forum at the Upazila Level. | 61 % | 50 % | 91 % |
| UPs shared Annual Budget in open sessions | 13 % | N/A | 87 % |
| UPs where monthly meetings conducted regularly | 89 % | N/A | 93 % |

See annex 12: UPGP Results achievements 2014

### 1.1 Coaching and Support to UP Chairs, and members for roles and responsibilities defined by UP Act 2009

Under the project/and in cooperation with LGSP, an Operational Manual for the Union Parishads has been prepared. The manual provides operational guidelines to implement key actions to strengthen democratic accountability. Furthermore, for capacity building and community engagement interventions, 16 different packages of training modules have been designed.

The main  contents of the training sessions were organizational structure and functions  of UP, Ward Shava, Standing Committee formation and functioning, preparation of 5-year development plan and annual plan, budgeting, implementation, monitoring, supervision as well as steps to enhance service by UPs for the people. The UP rules were also discussed. During the training, every UP has prepared an action-plan for three months; the main activities of the action plan were preparation of UP information book, budget, UP plan book, update different registers, annual tax assessment etc.

The vast majority of the target area, 545 UPs out of total 564, has received 2 days training in planning and management. The project has reached the target of training 7,809 people, which is 96  % of the targeted participants. The DDLG, District Facilitators, District and Upazila level Government officials acted as facilitators of the training program held at Upazila level.

A total of 307 UPs (55 % of the total) have been provided with backstopping support through regular communication and visits by the officials. District Facilitators have provided technical support to the UPs to track completion of mandatory tasks and implement work-plans. The DFs have also provided backstopping and technical assistance to UPs to prepare MDG linked five year and annual development plans, which are also areas promoted by the APA and linked with grant allocation, see Output 2.

In addition to conventional training, the project applied peer learning visits to foster exchange of knowledge, experiences and good practice and enhance efficiency of Union Parishad governance and service delivery mechanism towards beneficiaries. The UP representatives got the chance to get first-hand information about good practices and processes, how the achievements have been done, who were the catalysts, which has expedited the learning.

As a result of enhanced capacity, UPs have been able to prepare five year development plans, been capable of identifying and initiating specific schemes to serve poor households; become more MDG-focused in the choice of investments, see Output 2, and have strengthened as grassroot-based institutions. UPs have become more transparent by disclosing their income and expenditure (note that disclosure of core PFM information was one of the areas with more than 20  % improvements from the 1st to the 2nd APAP, see Annex 21) and disseminating the Citizens Charter. In such indicators, UPs have made significant progress compared to what was in the base line and from the first to the second APA, with expected further improvements in the ongoing one. The capacity improvements are also reflected in the table below.

Table: Selected indicators of UP performance in planning, responsiveness, disclosure

| UP performance in Planning, Responsiveness, Disclosure | Base line | 2013 | +/- Baseline |
| --- | --- | --- | --- |
| UPs who have 5-year comprehensive development plan | 71 % | 91 % | +20 % |
| UPs which initiated specific schemes to serve poor households | 0 % | 10 % | +10 % |
| UPs which disclose income and expenditure report to public | 62 % | 77 % | +15 % |
| UPs that have Citizens charter | 58 % | 64 % | +6 % |

Source: UPGP Annual Report p.8

Field observations by the MTE confirm that the UP elected officials in general are more aware and conversant about their roles, as stated in the UP Act 2009 and the CPS provides further evidence that the responsiveness of the UPs are considerably better in project areas, see table below.

Table 4: Comparative picture of performance of the UPs under UPGP Project as against Controlled areas

| Selected Indicators of UP performance and governance | Project Areas | Controlled Area | Difference |
| --- | --- | --- | --- |
| Effectiveness of standing committee | 47.8 % | 40.9 % | 6.90 % |
| Knowledge about the Project Implementation committee | 26.3 % | 22.3 % | 4.00 % |
| Participation in schemes/projects | 18.1 % | 15.3 % | 2.80 % |
| Improved the condition of marginalized community | 69.4 % | 47.1 % | 22.30 % |
| Satisfaction about the quality of implemented project | 62.5 % | 39.3 % | 23.20 % |
| Knowledge about Annual Planning of UP | 26.9 % | 22.9 % | 4.00 % |
| Knowledge about Five Year Plan | 9.9 % | 4.4 % | 5.50 % |
| Knowledge about Open budget | 84.2 % | 67.1 % | 17.10 % |
| Level of satisfaction regarding open budget meeting | 70.2 % | 40.6 % | 29.60 % |
| Average difference over score of indicators |  |  | 10.72 % |

Source: Extracted from Citizens Perspective Survey, September 2014

### 1.2 Activating Ward Shavas for Inclusive Decision-Making

Target Indicator: % of Ward Shavas that transact business according to UP Act 09 - Baseline value: Baseline survey (preliminary 0 %)Target: 50 %. Status: 76 %.

The UP Act 2009 made it mandatory for UPs to have Ward Shava. With the project interventions the Ward Shava is gradually getting institutionalized and has emerged as a platform for community participation and decision making.

Table: UP performance on Transaction of Business of Ward Shava

| Business of Ward Shava | Base line | Target | 2013 | +/- Baseline |
| --- | --- | --- | --- | --- |
| % of Ward Shavas that transact business according to UP Act 09 | 33 % | 50 % | 53 % | + 20 % |

Source: UPGP Annual Report 2013

The project has exceeded the target of formation and activating Ward Shavas. Grossly it is 20 percent above the baseline and 3 % above overall target, and operations of the Ward Shavas have improved according to the independent APA from the 1st to the 2nd year, see Annex 21.

The CPS reveals that almost half of the community members are fully aware of the role of Ward Shava. 95 % of the community members observed that the development plans and budget were discussed in Ward Shava and community based projects have been identified and shortlisted. Community members also noted that: “we had equal chance to talk in the Ward Shava meetings”. More importantly 71.4 % of the community members in the project area are “satisfied” with the performance of Ward shava as against 40 % community members in the control area, showing noticeable improvement and institutionalization of Ward Shava in the project areas.

About the awareness on Ward Shava, 46.4 % respondents in project area and 39.1 % in control area were aware of it. However, as regards orientation and strengthening the capacity of Ward Shava, for effective meetings, conflict resolution, and documentation, no hard evidence could be obtained from the field observations or other monitoring data/records. It was also observed that there were no specific initiatives to enhance the skill and technical competence for the Ward Shava to prepare pro-poor and MDG focused planning at community level, but that a MDG planning manual is being prepared by a consultant commissioned by the Project.

In general, Ward Shava has empowered the community members and their involvement in community decision making process at the grassroots level and has made the project selection and planning process responsive to the need of the poor and marginalized, created a demand side of accountability, and their needs and aspirations are heard and mainstreamed. MDG targeting of the investments have improved both in the APA on this indicator from the 1st to the 2nd APA, but also in the actual investments implemented by the UPs, see Output 2 and Annex 19.

However, from interviews conducted by the MTE team it is also evident that the small funding available for UPs, is quickly being outpaced by the new entry points for participation. In a planning exercise in nine wards (nine WS), perhaps three are likely to get their priorities met, while the six other wards will not receive anything. While this can be seen as healthy competition, it can also quickly erode motivation for participating in future WS, especially if it is linked to high opportunity costs for poor people. The answer to this dilemma is not to reduce democratic space in the UPs, but to expand the UP resource envelope, before the likelihood of achieving any impact by participating in UP meetings becomes too remote.

### 1.3 Strengthening Standing Committees for Effective Governance

Target Indicator: % of target UPs with at least 6 key standing committee producing at least 2 monitoring reports per year. Baseline value: 28 %. Target: 50 %. Status: 100 %

This intervention primarily attempts to strengthen the institutional capacity of the UP by duly recognizing and strengthening the selected six Standing Committees of the UP Act. Community survey data reveal that only 20.4 % of respondents in project area and 18.6 % of respondents in control areas are aware of the Standing Committees of UP. 79.6 % of respondents in project do not know about standing committee meeting corresponding to 81.4 % in control area. The survey further reveals that the overall visibility and performance of the Standing Committee is poor and weak. However, with the backstopping services of the DF, UPs are now in a process of bringing the role and function of the Standing Committees up to UP Act standard.

MTE field observations draw that:

- All 13 Standing Committees are formed and have started functioning. In some Ups, the names and contact numbers of the Standing Committee members are placed on the UP Notice Board. Furthermore, Standing Committees are doing relatively better in the Project areas compared to control areas.

- Input from the standing committees to the planning process has improved, but still modestly; see Annex 19 from the 1st to the 2nd APA.

- However, the overall capacities of the UP Standing Committees are still very low. The members are not fully aware of and to some extent concerned about their role.

- Standing committees are formed but not yet fully effective, visible and functional. The Standing committees in general have not yet taken sufficient special initiatives to develop pro-poor, MDG oriented sector plans in consultation with Ward members and to negotiate with the Union Parishad for effective implementation of such interventions.

- There appears to be a “huge coordination gap” between Standing committees and extension workers of the LMs at the field levels.

There are number of parallel committees at both UP and UZP level which are formed by different ministries of the Government and operate in parallel with the UP Standing Committees/Upazila Standing Committee.

The LD committee at the UP level is formed usually by executive orders/ministerial orders, while the UP Standing Committees are formed as per the Section 45 of the UP Act 2009. Examples of parallel committee structures at Union Parishad level can be found in Annex 25.

On the whole, this sub-output reflects some improvements compared to the targets, and compared to control groups. Due to the late upstart and the fact that most activities in the first phase focused on general UP council operations, the standing committees will be further targeted in the coming interventions and presumably realize more potential in the second phase of UPGP.

### 1.4 Up-Scaling of Women’s Development Forum

Target Indicator: % of targeted UPs which have at least 1 woman representative participating in officially registered women Development Forum at the Upazila Level. Baseline value: 61 % Target: 50 %.Status: 91 %

The achievements on this indicator is 91 %, see Annex 12, which is well above the original target, and there have been substantial activities and results achievements within this area.

The objectives of the Women Development Forum (WDF) are to create a platform for elected female representatives, for networking and monitoring, strengthen UP and UZP linkages and  pursue advocacy on women’s issues.

A total of 65 Upazila-level WDFs have been formed successfully till 2013 and now 409 WDFs have been formed nationwide. In the project area, as many as 645 elected female members have been involved in WDF and among them 555 are from UPs. The main aim of forming the forums is to enhance the capacity of the elected women representatives in UPs and UZP and Municipalities to play a significant role as a pressure group in solving LGI governance issues with special attention to gender rights and participation. The WDF members have been trained by the project on gender issues at LGIs, gender responsive planning and budgeting, networking and resource mobilization, women empowerment, etc.

MTE field observations reveal that:

- WDF created enthusiasm and a new hope to work more beyond the Upazilla and Union Parishads among elected members of the local governments, and they are now working as change agents in the Union, Upazila and Districts. WDF members are gradually getting more inroads to influence government officials and public prosecutors.

- WDF is providing motivational visits to inspire parents for the schooling of their children and motivate against drop-outs as well as protesting abuse of drug and making awareness programe on anti-drug.

- WDF is facilitating women rights through successfully creating good examples to ensure justice in the alternative dispute resolution and litigating the case in women’s favouring coordination with the public prosecutors.

- However, it has also been observed from the field data that the WDF as a new body is yet to mature and become capable of “leading and running successful women organisation in the Upazila and Districts”. They need more conceptual and technical skills to promote, bargain and advocate on gender issues and social disparity. There is also a non-tapped potential to cooperate more closely with NGOs supported similar initiatives at the local level.

The MTE field-work confirmed that the WDF platform to a great extent have encouraged the UP members to take an active role at Ward Shava and Standing committee meetings. At local level advocacy work, the WDF members were instrumental, in some cases with the support from local NGOs and DF, to promote women’s voices in various social and gender focused advocacy issues within health, education and other social services. There are also a few cases where WDF members have successfully mobilized collective actions and raised their voices in addressing violence against women.

There is a by-law which regulates WDF activities. However, opening of a bank account and getting registered as a cooperative by WDF does not seem to be guided by strong guidance and oversight, and there is a risk of creating yet another parallel body to LGIs where the prime purpose of the Forum may get diffused and may focus on fundraising and parallel activities not sufficiently linked to LGI operations.

### 1.5 Building Citizenship and Promoting Downward Accountability

Openness and access to information is a precondition for public engagement and promotion of equitable service delivery in LGIs and citizens should interact with the LGI on an informed background. In line with the provision of UP Act 2009, the project has supported the UPs to design and disseminate the Citizens Charter for greater social awareness and ensure and institutionalize local accountability. There has been a 6 % improvement in this particular intervention as against the base data of 58 %.

The project has not yet addressed the identification of key rights and entitlements by writing RTI applications. Field data indicates that inhabitants of the Union Parishads even in the UPGP covered areas are not yet aware of the entitlements and supports provided by the Union Parishad. A recent RTI study undertaken by the UPGP noted an observation of an UP resident. He observed that: “We got no idea of what information is, and how to get that. If we go to UP office to ask for anything the Secretary and the Chairman do not like to share anything rather they try to keep us at bay. So we have no interest left in UP office, to go there and ask for anything”.

The UPs have on the other hand become more transparent in their disclosure of information on UP resources and their use. There has been a dramatic change in this indicator. 77 % of the UP now practices open budget sessions which is an improvement as compared to the base-line figure. In terms of the CB support rendered, the UPs visited during the MTE team were generally satisfied with the support, but mentioned that it should be expanded. New CB modalities were introduced as well. The project organized a number of peer visits to study best practices. 20 secretaries and 251 UP members have participated in peer learning process. They visited both best and poor performing UPs to get a comparative understanding of the operational business of UP under the new framework of UP Act 2009.

The UP elected officials and Secretaries have found the peer to peer learning as not only enriching their understanding but also exposing them to their respective institutional limits and poor practices.

### 1.6 Effectiveness

The project has addressed all the relevant sections of the UP Act and evidence from project monitoring and the MTE field findings suggest improved capacity in project UPs compared to control groups. There are specific project interventions of activating and strengthening the Ward Shava, the UPs are trained and capacitated to have their respective Citizens Charter. In the project areas the UPGP has been helping the UPs in developing a MIS system in collaboration with the UISC. The UP Act Section 78 has also been addressed through installing provision of dissemination of information, specially, on open budgets. However, the project has not yet initiated any specific intervention to address the RTI section of the UP Act 2009 apart from the information disclosure aspects

### 1.7 Efficiency

The UPGP has been very efficient in diversifying the UP capacity building through a combination of cascading training delivery using TOT and though direct training delivery to key actors (UP secretary, UP Chair etc.) by the national training institutions. This approach maximises the efficiency and effectiveness of the training delivery. Initial assessments of the training conducted on UP planning training, provided a mixed feedback and identified a need for more practise based training, less classroom and textbooks, more interaction and role-plays. This feedback is now infused into the new training delivery, which hopefully will change accordingly.

The links between the annual performance assessments and the CB support has also been strengthened through analytical work by the project of relative weaker and stronger areas of performance, and targeting of the CB support. The institutions involved include the National Institute of Local Government, Bangladesh Academy of Rural Development and Academy for Rural Development. The training is in most cases tailormade to cater the specific need of the LGI officials.

### 1.8 Sustainability of results

As of recent date there is no National Framework of capacity building for the LG officials. NILG has been using a comprehensive module called Capacity Development (CapDev) Framework for Union Parishads through a Joint Partnership agreement with SDC in September 2012. But that framework is yet to be formally recognized as the National Capacity Development Strategy for Local Government, and has not led to a strong coordination of efforts across various programs. Without a formal strategy, training delivery will continue to be fragmented and rely on ad hoc funding through support projects.

The project has contributed towards developing a participatory culture and a demand side of accountability. This emergence of a participatory culture and increasing demand side for accountability, transparency, awareness of gender rights as a whole is likely to strongly contribute towards a sustainable democratic system of governance. With adequate emphasis on capacity building and training, the UPs are better prepared to identify and design projects that are more responsive, pro-poor and gender sensitive. The positive output of the project has helped UPs to develop a positive image and that also appears to have influenced the mind-set of the rural people towards UPs. Considering the role of capacitated UPs, new image, and added with the growing demand side of good governance, the impact of the project is very likely to sustain, although not without external support to CB and increase in funding. The overall good progress has also been supported by the enhanced focus on performance improvement and competition in this area across UPs, promoted by the incentives in the PBGS, see Output 2.

Through a five year planning system, UPs are at an initial stage of producing integrated development plans with horizontal links with national priorities, which will make development activities delivered by UPs more sustainable and effective. UPGP training delivery is targeting plan development skills and it is important to focus on gradually improving the quality of the plan documents (as these are still rather rudimentary in some of the UPs), and to expand the funding envelope for planning to sustain democratic voice and targeting needs according to local priorities. In this respect, it should be noted that the annual block grants per capita are still relatively modest compared to most developing and transitional countries. Lack of funding for social protection entitlements may also put the UPs in a situation where they have to choose between beneficiaries who all may otherwise be entitled to receive benefits according to national program objective law.

Functional partnerships with the Local Governance Support Project 2 have opened a wider space for mainstreaming the lessons and new practices of the UPGP, see the Partnership Section. Most of the project activities, including those of the UPGP District Facilitators, work closely with national systems by supporting functions for the LGSP II program and thus also creating a new sense of belongingness of the DDLG and district administration towards the project and project implications.

### 1.9 Conclusion

The project has tested and documented that some of the democratic innovations introduced and promoted can become viable in the context of the changing political and administrative reality of Bangladesh. The project has significantly made UPs understand, internalize and institutionalize the new provisions of the UP Act 2009, despite a challenging political context.

Through technical support and backstopping, UP operations, Standing Committees, Ward Shavas, and WDFs are gradually getting institutionalized in the local governance process. It has also created an alternative counter balancing force in the otherwise authoritative role of old fashioned working modalities of the UPs. Evidence show that UPs are on their way to become more transparent, accountable and responsive to the community needs along the targets of the project. The project interventions have made the UPs relatively more gender sensitive and responsive to the need of the poor and marginalized community segments and diversified investments to better target the MDG needs.

However, a number of more systemic constraints needs of be addressed at policy level to further enhance UP capacity: e.g. funds are rather limited and needs to be improved to catch up with the participatory gains, which may otherwise erode if citizens perceive that outcomes of their participatory efforts do not match up. The parallel and overlapping committee structures under UP and LD, respectively, is another issue which needs to be addressed at policy level. Full empowerment of the UP standing committees cannot be realised without clearer institutional arrangements and division of roles vis-à-vis the LD committees.

Another critical governance aspect is found within access and right to information. Here, the project is yet to sufficiently address and ensure community members’ access to and active use of RTI.

Training is still provided ad hoc-wise. The project should now launch the work on the comprehensive LG Capacity Development Framework to ensure that CB efforts are well coordinated across various projects.

Finally, the mandate, role and overall modus operandi of the WDF need to be revisited to ensure that the key role of empowering women in LGI operations and strengthen their voice and impact on the decision-making and implementation of LGI operations remains the key focus.

# Assessment of Results – UPGP Output 2

Output 2: Strengthening Innovations in Pro-Poor and MDG-Oriented Planning, Financing and Implementation of Service Delivery by Union Parishads

Output 2 has been delivered through a combination of system development, linked with performance-based grant system (PBGS) and capacity development support. The establishment of the PBGS was delayed due to the delays in the start–up of the project, see enclosed Annex 18 on the overview of planned annual assessments and disbursements of grants against actual timing. As per October 2014 two full rounds of Annual Performance Assessments (APAs) and PBG allocations have taken place and the third is ongoing, and the system is currently fully operational.

Funds from the first round were released in June 2013 with deadline for utilization in December 2013, and the second year’s disbursement was released in June 2014 to be used by UPs before December 2014. As it appears, the original plans to have two annual disbursements (August and February) could not be affected due to the delays in the APAs. However, as it also appears below, UPs have been able to spend all the funds from the first FY’s disbursement (FY 2012/13) and a total of 1,567 projects have been implemented, reflecting core areas of service delivery with approximately 48  % targeting directly MDG sectors and 1,442 new projects are planned. There is an increase, and strengthening of the targeting, compared to previous experiences from LIC and higher than the LGSP 2 level. A second major achievement on this output is the cooperation with LGSP 2, where UPGP has been in charge of the joint training of the auditors/assessment teams (2,750 auditors have been trained in two rounds) and with gradual improvement in the quality of these audits through a concerted effort on QA, audit reviews, complaint mechanism and thorough preparation, monitoring and follow-up.

The table below summarizes some of the core design features of the main component of output 2, the expanded performance-based grants.

Table: Overview of Design Elements

| Design Elements | 2012/13 | 2013/14 | 2014/15 | 2015/16 |
| --- | --- | --- | --- | --- |
| No. of UPs being targeted and assessed | 564 UPs | 564 Ups | 564 Ups | 564 UPs |
| No. of UPs getting access to the EPBG | 404 (or 70 % best performing) | 410 (70.9 % of UPs) | Around 400 (70 %) | Around 400 (70 %) |
| Auditors trained for audit/ assessments | 1,375 | 1,375 | 1,094 | 1,100 |
| Average allocation per eligible UP | 323,000 | 323,000 | 320,000 | 320,000 |
| Disbursed amount for EPBG | 1,72 million USD | 1.72 million USD | Expected 1.72 million USD | Expected 1.72 million USD |
| Allocation criteria (basic formula) | 30 % equal share, 35 % population, 35 % based on area | 30 % equal share, 35 % population, 35 % based on area | 30 % equal share, 35 % population, 35 % based on area | 30 % equal share, 35 % population, 35 % based on area |
| Minimum conditions | 1 MC (similar to LGSP) | 2 MCs (similar to LGSP) | 3 MCs (similar to LGSP) | 3 MCs (similar to LGSP) |
| Performance measures | 41 (standard guideline for assessment) | 41 Performance Assessment tool was improved (work-book) | 41 | 41 |
| Number of projects | 1,567 schemes implemented | 1,442 schemes planned for implementation | To be defined | To be defined |
| MDG targeted | 47 % |  |  |  |

The sections below present a systematic overview of the progress against the 4 major outputs envisaged in the UPGP PD of 2011. Other core findings supplement these results in areas where outputs are not fully operationalized. Some of the major overall innovations of this output have been:

- A new set of innovative performance measures supporting the MDG, vulnerable groups/women, a wider set of PFM and governance areas.

- The specific performance indicators are widely accepted by the LGs according to field-work conducted during the MTE. LGIs had no queries on the number and detailed shape of the performance measures, which were also the view of the contracted auditors and local officials and which helps UPs to identify CB gaps (see Annex X3 for an overview of the performance measures)

- UPGP has supported the LGSP 2 and the general grant system by provision of training of all auditors under the various block grant systems for LGSP II and UPGP, a support which has been evaluated to be highly satisfactory in the recent Second LGSP MTR, August 2014

- Strong support to ensure quality and robustness of the assessment results (training, QA etc.) and institutionalisation of this system in cooperation with LGSP. Of the 12 UPs and 4 UZPs, which have been visited by the MTE team, there was only one official who complained about the quality and method of assessments, others – both politicians and officials were satisfied with the method and results, which are deemed objective

- Integration of the performance assessment results with the general needs-based formula in a weighted manner instead of rigid classification of UPs in fixed groups, i.e. every point is having impact on the size of the allocation

- New guidance to the assessors on how to internalise the indicators in a common and neutral manner (work-books). This is already applied by both programs (LGSP and UPGP)

- Together with output 3 support, development of a MIS and UP own source revenue mobilisation

- Use of backstopping support and monitoring missions

- Improved (compared to LGSP-LIC) linkages between the results from the annual performance assessments and the CB support provided.

- Internal assessments conducted prior to the annual external assessments for the first two rounds of UP assessments (these could not be conducted for the 3rd round due to time constraints)

- The performance-based grant system, with its more elaborated performance indicators show that performance incentives, when combined with CB and funding, can provide enhanced performance and be an important element in building trust in UPs for future enhanced support

  - Performance has improved by an average of 13 % and there have been improvements on 37 of the 41 performance measures (PMs) of which 21 of the PMs have improved by more than 10 % and 9 areas by more than 20 % which are core areas such as: i) disclosure, ii) tax assessments, iii) projects benefitting more than 1 ward, iv) tax rates, v) revenue mobilisation, vi) MDG planning targeting, vii) medium term planning, viii) project implementation, ix) functioning of the standing committees, see Annex 18

  - Some of the areas with significant improvements are the average performance on medium-term planning – improved by (92 %), MDG planning (62 %), timely preparation of the annual plan (17 %), projects benefitting more than one ward (24  %) establishing of standing committees (19 %), tax assessments (27 %) and revenue improvements (26 %)

  - As the first year of the support has focused on planning a revenue mobilisation and to a less extent on PFM (core accounting), which is an area to be targeted in the coming year, this is reflected in the results from the APA, and the field-work where it is clear that areas such as books of accounts, bank reconciliations and addressing audit queries are weaker areas which have improved less or not yet improved

  - Improved performance on the APA performance measures compared with the baseline and with the LGSP UPs. UPGP targeted UPs are performing better than non-covered areas when the performance on 12 common performance indicators are compared. The UPGP UPs have improved their performance on the 12 common indicators from 13.72 points in 2013 to 16.03 points in 2014 (out of possible maximum score on 30 points), i.e. 17 % improvement, whereas the LGSP 2 supported UPs country-wide has improved from 13.98 points to 14.65 points or about 5 %, i.e. the target group UPGP UPs started on basis of an average lower level, but has managed to pass the larger group of UPs under the national LGSP 2 program, see also Annex 21.

At the outcome level this has been reflected in improvements in the citizens’ satisfaction with the services provided for the target UPGP area compared to control groups where 68 % of the citizens in 2014 were highly satisfied or satisfied with service provided in the UPGP target areas compared to only 47 % in the control group.

Similarly, citizens’ knowledge about budget process and openness of this is higher and the level of satisfaction with and project implementation process is much higher in the areas covered by the program (71 % against 55 %), and the quality of the projects implemented (66 % satisfied in target areas against only 43 % in the non-covered areas (CPS, p. 31). Similarly, there are is a significant higher level of involvement and awareness of citizens in the UP governance operations such as planning, budgeting and project implementation in the target area documented in the recent Citizen Perception Survey and confirmed by more qualitative findings from the field visits.

According to the UPGP Program Document, Output 2 had four clearly operationalized output targets. Below is a review of some of the core results against planned targets in the UPGP Program Document – Output 2.

### 7.1 Development plans with MDG and needs assessments

Target indicator 1: By end of the project, % of targeted UPs have completed comprehensive development plans responding to local MDG assessments that will have also identified needs of the locally relevant most vulnerable groups. Baseline value: 0; Target 70 %. Status: Formally on-target, but continued need to focus on the quality of the planning documents.

The project is in good progress regarding this indicator, as the number of UPs that have a 5-year development plan has increased from baseline (2012) level of 71 % to 91 % (current status in 2014) or by 20 percentage points. The progress is also reflected in the improvement on the Medium planning and MDG targeting PMs from the 1st the 2nd APA, see Annex 19, and confirmed by the qualitative field work where target areas (8 UPs) where compared with 4 UPs in non-target areas.

However, although there is progress, efforts will have to continue to ensure that UPs are strengthening their targeting of the vulnerable and women in scheme selection as only 10 % (up from 0 % in baselines) of the schemes in 2013 were targeting specifically the poor households, see below, and the quality of the document can be improved. The feed-back from the field-level was that the project is gradually strengthening the targeting of projects in the development plans focusing on women’s needs – with a stronger focus on health, education and water and sanitation and with an increasing number of specific projects focusing specifically on women’s development (17 out of the 676 project targeting MDG sectors) and with a strong role of women in the planning process supported by a combination of CB support, awareness raising, operations of WDFs, and incentives in the APA. Especially the WDF is empowering the UP women members to raise their voices in the UP meetings, awareness about their roles and responsibilities in the standing committee, bargain for their prescribed 30 % share of the scheme selection in the UP level. This is also helping them through peer learning with other UP women members for sharing success cases or dealing with challenges within the UPs with the other members and outside the UP to deal with patriarchal social and cultural barriers.

The initial step towards establishing comprehensive development plans at the UP level is a core ongoing focal area. Work is commissioned on MDG sensitive planning guidelines, which will be used for awareness raising and training. It will also be necessary to strengthen the linkages with the citizens as only 16 % of the citizens in the target area (against 11 % in the control area) are aware of the annual plan, only 31 % (against 21 % in the control group) are aware of the Five- Year Plan (FYP), and only 27 % area aware of the UP budget (against 22 % in the control group)

### 7.2 Grants targeting pro-poor or MDG projects

Target indicator 2: By end of the project, % of targeted UPs allocate % of block grant funds to projects explicitly identified as pro-poor (including those responding to vulnerable groups’ needs) or MDG-responsive in plans. Baseline value: 0 %; Target: 70 %. Status: Improvements and target likely to be achieved with planned efforts. Planned for FY 2013/14: 47 % of schemes and 50 % of the grants.

The system of EPBG was established from 2012 and fully operational from 2013. However, due to delays in the up-start and approval of the UPGP, the first allocations took place only in June 2013, and 404 UPs in the 7 districts (out of 487 UPs) benefitted from this and managed to complete 1,567 schemes by end of 2013. The second year’s allocation took place in June 2014 and provided grants to 410 UPs to be used by end of December 2014, see Annex 18. Compared to previous project interventions where the majority of the funding went on roads/culverts and hard core infrastructure, especially in the first years, the UPGP has managed to take further steps towards changing the mind-set of the UPs and stimulated a more diversified use of the grants, and promoted a greater level of targeting towards the MDG relevant areas such as health, education and water & sanitation, through indicators of performance and CB support to planning and with an increased focus on the women’s needs as well. The field-work in the 12 UPs confirmed this trend, and 7 out of 8 UPs in the target area were of the opinion that investments are now targeting core MDG, which was not previously the case. This was not the general case in the 4 non-covered UPs.

Of the 1,567 schemes implemented through funding from the first round of the EPBG 46, % of the schemes (and this is expected to increase) were targeting MDG relevant areas (health, water & sanitation and education), and the use of funds on typical areas such as roads and culverts is now under only 47 % compared to a similar figure of 62 % during the MTR of the LIC in 2010, where MDG targeted projects constituted only 34 %. The planned schemes for FY 2013/14 had 47 % of the schemes on MDG targeted areas and 50 % of the expenditures. The composition of expenditures is also somehow different from the LGSP grants where more than 50  % (namely 52  %) are spent on roads and related areas, and only 37 % on health, education and water & sanitation, see the pie-charts below. This was also one of the areas in the APA with a most significant improvement in performance, see Annex 19.

Second, UPs are spending a larger share of their own source revenues on development related expenditures (42 % against the target of 20 %). It is expected that this trend will be further strengthened with the ongoing work on the MDG sensitive planning guidelines, incentives in the APA, and the related TA/CB support, especially through strengthening of the UP standing committees, which makes the target achievable within the remaining two years.

Third, the support from the UPGP is reflected in a higher level of citizens’ satisfaction with the service provided by the UPs, as mentioned above.

The diagrams below show the composition of fund utilization under i) LGSP-LIC, ii) UPGP and iii) LGSP II.

Chart. Composition of Schemes under LGSP-LIC, 2010 (MTR) (34 % MDG

Chart. UPGP Schemes – Composition of Schemes in the First Round of PBG Allocations 2013 (46 % of expenditures MDG targeting)

Chart: LGSP 2 – Composition of Schemes under LGSP 2013 (37 % MDG)

Source: Based on data from the LGSP–2 MTR. It should be noted that this encompasses the UPs in the UPGP; hence the difference may be greater than showed when the two pie-charts are compared.

The number of UPs under the UPGP, which have special schemes targeting the vulnerable groups is 64 % according to the most recent UPGP quarterly monitoring report, and the MDG targeting in the planning process is the performance areas with the second highest improvement (62 %) from the 1st to the 2nd APA. This is expected to spill over into investments targeting poor and vulnerable groups (which has improved by 11 % in the planning, and actual projects implemented targeting social issues and MDG which has increased by 10 %, see Annex 19 on trends in Performance.

The composition of the MDG targeting projects planned in FY 2013/14 shows sectors, which are typically benefitting women, as well a substantial number of project directed directly towards women development, e.g. through support to the WDFs.

Table: MDG Targeting in FY 2013/14 – UPGP EPBG

| MDG | Schemes | Taka |
| --- | --- | --- |
| 1.Community Clinic | 33 | 2,436,943 |
| 2.Equipments for school | 127 | 13,237,113 |
| 3.Health | 3 | 1,277,514 |
| 4.Human resources development | 7 | 293,327 |
| 5.School building construction | 74 | 9,255,335 |
| 6.Women development | 17 | 1,647,916 |
| 7.Sports and cultural | 10 | 640,500 |
| 8.Water sanitation & Drainage | 405 | 34,315,747 |
| Total | 676 | 63,104,395 |

Source. UPGP MIS data-base on schemes for FY 2013/14.

The field-work also proved that the scheme selection and allotment related to MDG sectors are increasing and more targeted in the UPGP supported areas. Awareness regarding this is increasing too. Gender issues and schemes related to women empowerment are also increasingly included in the UPGP priorities. During field visits, women UP members mentioned that their awareness has increased. Women UP members find WDF an effective forum for their experience share, bargaining with male UP members, more gender focused scheme selections and awareness rising of women participating in Ward Shavas for selecting gender friendly schemes an also to work for social justice and rights on women’s issues such as child marriage, dowry, polygamy, family disputes.

### 7.3 Accounting and Records

Target indicator 3: By end of the project, % of target UPs comply with 90 % of accounting and record keeping requirements. Baseline value: First round of Performance Assessment; Target: 90  %. Status: Some progress, but indicator is composite, and additional efforts already planned in this area will be required to fulfill the target.

According to evidence, the qualitative interviews during the field-work and interviews with other stakeholders, especially the auditors, it is clear that there has been a significant improvement in the PFM performance of the UPs in the target areas and that part of this can be attributed to the UPGP support. It appears from the average figures in the APAs that the performance on core dimensions has improved from the first to the second APA.

The recent APA of 564 Union Parishads indicated that a large proportion (75 %) of these UPs were able to improve their performance scores. Overall, the average performance score of 564 Union Parishads improved from 52 to 59 points, out of a maximum score of 100. However, it was also evident that a proportion of the Union Parishads reported weaker performance (22 %) while a small set maintained the same level (3 %). The positive nature of the change in performance is reflected in the table below.

Table: Trends in performance form the first to the second APA.

| Sl. | Extent of change | Proportion of UPs |
| --- | --- | --- |
| 1 | <90 % of previous score | 9 % |
| 2 | 90–99 % of previous score | 13 % |
| 3 | 100 % of previous score – same | 3 % |
| 4 | 101–110 % of previous score | 26 % |
| 5 | 111–150 % of previous score | 37 % |
| 6 | >150 % of previous score | 12 % |

Source: Data from the annual UPGP report on results from assessments, 2014.

Some of the core sub-indicators to indicate UP improvements are:

- Open sessions: The number of UPs that has shared annual budget in open session, which has increased from 13 % in baseline year 2012 to 77% in 2013;

- Frequency of meetings: 70 % UZPs and 93 % UPs held mandatory Monthly Parishad meetings, as compared to 30 % UZPs and 89 % UPs in 2012;

- Operations of standing committees: 100  % UZP and UP level Standing Committees formed, as compared to 50  % at UZP and 74  % at UP level in the baseline of 2012;

- Meetings in standing committees: 70 % UZP and 36 % UP level Standing Committees conducted mandatory meetings, as compared to 30 % in UZPs and 28 % in UPs in 2012;

- Annual budget: 100 % UZPs and 65 % UPs prepared Annual Budget, as compared to 25  % UZPs in 2012, but UP data of 2012 is not available;

- Community engagement: UPs facilitated community engagement in the planning process where 53 % of the UPs completed two Ward Shavas in all 9 wards;

- Public disclosure of budget information and income and expenditures: Increased from 62  % baseline to 99 % (current September 2014) status (October 1, 2014, MTE workshop presentation);

- UPs that shared annual budget in open sessions: Increased from 13 % baseline (2012) to 80 % in the current status (October 1, MTE, 2014 workshop presentation).

- Accountability: From the recent Citizen’s Perception Survey, September 2014, it appears that:

  - 68 % of the citizens are satisfied with the tax collection systems in the UPGP target group compared to only 36 % in the control group;

  - 63 % of the citizens find the UP operations transparent compared with 36 % in the control group and

  - 70 % of citizens find the UP accountable compared with 54 % in the control group (CPS, p. 36).

Public Financial Management (PFM)

Within the core areas of PFM there have been some improvements as well, although there is still work to be done. The average score on bookkeeping and accounting has improved by 8 % from the first to the second assessment, but bank reconciliations have been stable (no improvements), tax management has improved, e.g. tax assessment performance has improved by 26 % from average score 0.99 to 1.26 for all UPs in the target area. Performance on tax defaulter has improved from 0.48 to 0.57 (i.e. 19 %) but is still low (as the max score is 2 points). Performance on tax register up-date has improved by 10 %. These improvements are also supported by the views of the auditing companies met during the MTE, who informed that they can now focus on audit rather than on supporting UPs with up-dating of the accounts.

However, as audit of the UPs has been strengthened during the implementation through stronger training of teams, enhanced QA and control, all the PFM improvements have not yet been reflected in the results from the APA, which are stagnant in some areas. Also, core PFM improvements are only anticipated from the final part of 2014 and in 2015, as this will be one of the focal areas for CB support, based on the systems and procedures piloted in the 100 UPs in Brahmanbaria districts and 46 other selected UPs. Hence the modest performance improvements in this area are linked with the phasing of the CB support to UPs, where first phases focused on the core governance operations, planning and revenue awareness.

The assessment shows that UP planning has improved more than financial management, and that there is need to strengthen this area in the future (also planned as part of the MIS/accounting package and backstopping support).

Also, the most recent quarterly monitoring UPGP report from the 2th quarter of 2014 provides information on core PFM areas, and show the current status on core dimensions such as assets register up-dated in 81 % of UPs, tax assessment register: 89 %, cash book: 99 %, annual schemes posted on signposts: 75 % of the UPs in the target area (out of 564 UPs). With a concerted effort, the output target is likely to be achieved.

### 7.4 Revenue collection

Target indicator 4: By end of the project, % of increase, on average, of revenue collection in target UPs. Baseline value: No figure for the baseline at the PD design phase; Target: 90 %.. Status: Progress, but evidence from e.g. from sample in Brahmanbaria, based on 42 UPs, shows that additional already planned efforts will be required to achieve the target.

Improvements in UPs own source revenues (OSR) are significant although there is not comprehensive data-set on trends in OSR over the years for all UPs, all UPGP and the special target areas. One of the reasons is that financial audited statements only are available 1.5 years after the end of the FY, and that the auditors are in the field for data on FY 2012/13.

Based on data from the MIS, the % of UPs, which were able to exceed their revenues from previous year by 10 % or more was 57 % in 2013 and average revenue increased by 25 % from FY 2011/12 to FY 2012/13. The total generated revenues increased from the baseline year 2012 on TK 97,801 (average UP TK for targeted UPs under UPGP) to TK 127,793 (average TK for target UPs in 2013) or an increase on 31 % within only one year. Performance improvements are also shown in two APA conducted, where the average score on the tax assessments has improved by 27 % and average score on the revenue enhancement by 26 %. According the MIS data, 73 % of UPs carried out fresh holding-tax assessment to enhance own source revenue.

The MTE team supplemented this data with the data of 42 UPs in Brahmanbaria, which shows an increase from FY 2011/12 to 2013/14 on 57 % (smaller increases in the second year), as the interruptions during elections may have reduced the increase.

In a smaller sample of UPs across the 8 target UPs visited during the MTR (from six districts) the improvement from FY 2011/12 to FY 2013/14 was also high, 84 % (without the data from Pirganj, which had a large increase this was 55 %) against the sample non-target areas on 47 %. However, this sample is small, and can only indicate the directions.

It is expected that the OSR will increase significantly with the roll-out of the tax modules and the MIS being piloted in Brahmanbaria districts and 46 other UPs. Furthermore, most of the intermediate process indicators on OSR mobilization are improving as per the APA, see Annex 19.  According to the MIS system, the percentage of UPs that collected more holding tax that previous year also increased from 25 % in 2012/2013 to 46 % in 2013/2014. The number of UPs that have completed their annual tax assessments increased from 19 % in the baseline year (2012) to 80 % in 2013, and other process indicators for tax mobilization has shown significant improvements from the first to the second APA, which is expected to impact on future improvements

However, there is still room for improvements on areas such as achievement on budgeted revenues and in the performance measures on creativity in tax collection where performance has been stable over the two years.

Use of OSR

However, one thing is revenue mobilization, another is effective use of revenues on development/service delivery. According to the most recent quarterly UPGP monitoring report, the percentage of UPs using more than 10 % of the OSR on development is currently only 33 %, and this is still a performance area with modest improvement, see Annex 19. The percentage of the 564 UPs that used more than 10 % of OSR on own development and service delivery was 42  % in 2013 against the annual target on only 20 %.

Attribution

The data-base data and data from the APA, which show improvements, have been supported by views from the visited UPs, where all target UPs, are of the views that there are significant improvements in the performance due to incentives generated in the APA, as well as through the CB support and awareness raising. Only 1 out of 8 target UPs did not expect further improvements. However, some of the non-targeted areas have also managed to improve, and the support from the LGSP focusing on OSR makes it hard to isolate impact, as there is CB support as well as performance measures on OSR in both systems, and as up-dated data is not available for the entire country (most recent data is FY 2011/12).

With a concerted effort in the remaining part of the project and with many initiatives on OSR mobilization during 2013-2014, there are good prospects that the overall very high target (90 % improvements compared to baseline, which was put very high) will be reached by end of project.

### 7.5 Effectiveness of operations

Through the close interaction with the LGSP on especially the training of a total of 2,355 auditors, development of clear workbooks/guidance for performance assessment and clear and robust indicators for performance, UPGP has contributed to the overall intergovernmental fiscal transfer system in Bangladesh. However, it is too early to judge the impact of the elaborated set of indicators on the overall MC/PM system running countrywide. The project has documented that enhanced and concerted efforts and incentives on specific subjects such as MDG and women targeting in the projects has an impact on the composition of expenditures on the ground. The approach whereby performance-based funding, incentives, high quality assessments, CB support and awareness raising and backstopping support has been effective in terms of results on the progress indicators. This is also confirmed by the qualitative assessment from the field-visits to 12 UPs.

However, the project will have to continue to document impact of the assessment system to ensure that useful features can be incorporated in the future reform progress at the national level. In addition to the PFM and grant system, the project has focused on improving OSR for UPs, and progress has been noted, but most of the impact is still be expected in 2015 and 2016 with the roll-out of the specified CB and MIS. The effectiveness on some of the PFM support will also hinge on the implementation of the GoB’s promise to ensure that each UP will get an accountant/cum IT operator in a phased manner over the coming years.

Whereas the PBGS has been an effective means to improve the overall performance of the vast majority of UPs, especially in the area of planning and governance, some UPs are persistently poor, and needs special attention in the future.

The MTE team also noted a need to strengthen accountability on the results and wider publication at central, district and local levels, e.g. of the APA results, to maximize downward accountability and increased pressure on performance improvements. Also the UPs need more detailed information about their performance scores and follow-up on the scores to ensure that the weaker areas are addressed by CB support and other initiatives. The MTE team noted that sharing of results from the APA is one of the weakest performance areas in the assessment scores, and needs a concerted effort beyond just having it as a performance measures in the manual. This means that the full potential in the performance incentives is not yet realized.

### 7.6 Efficiency

As the performance assessments for UPGP have been conducted in collaboration with LGSP 2, costs have been reduced, and transaction costs minimized. DFs have been shared with the LGSP 2, which has also reduced costs. The UPs have been able to implement the projects within provided time, but there is no doubt that advancing of the timing of the APAs and grant allocations to fit better with the UP planning and budgeting cycle and fiscal years may enhance the future efficiency gains (see Annex 18) and support a more integrated and efficient planning and budgeting process.

The field-work proved that the UPs have learned to cope with the delayed allocations by picking projects from the FYPs. However, it requires another round of meetings, consultations etc. and impacts on the efficiency of the overall integrated planning and budgeting process as well as accountability as funds allocated in one year will be utilized and reported in the subsequent year.

### 7.7 Sustainability of results

The fact that the CB/TA support and system development are closely related to the national legal and regulatory framework, and make use of the government institutional set-up to a maximum extent reduces the transaction costs, and enhance sustainability of the results. The minimum conditions and performance measures are closely aligned with the legal framework and related guidelines. The UPGP’s inputs within CB and grant scheme, not only complement the support provided by the LGD/LGSP, but also act as catalytic support to trigger better performance by the UPs. The linkage of UPGP with nationwide LGSP 2, offers a mechanism for transferring lessons and good practices that are newly developed by the project, and this has e.g. been practiced through the joint training of the auditors/assessors, sharing of the support from DFs etc. However, this is an area which can be further exploited in the future, e.g. when it comes to the roll-out of the third generation of the performance indicators and in terms of development of common and robust MIS and PFM systems for UPs. The elaborated set of indicators is also an important tool for UPs and the project to identify CB gaps for future interventions.

The relatively small amount of block grants makes it relatively easy to up-scale and ensured realism in the achievements, but the overall grant allocations in general needs to increase to ensure that the planning process and resources applied on this and other governance procedures is sustainable. All the UPs met stressed the importance of increasing the grant allocations from GoB to UPs to ensure that the participatory planning and budgeting processes are meaningful for the people involved.

The performance-based grants and the focus on OSR mobilisation, which has shown initial impacts on services and tax mobilisation has contributed to building up of a stronger trust in UP operations and thereby provided important input to the future overall policy reform process on decentralisation along the objectives in the sixth and the coming seven FYP. It is also the views of the UPs, UZPs, and district and central government officials met, that the UPGP has influenced important changes in the mid-sets of the officials and elected representatives at the UP level, especially through the enhanced focus on good governance, PFM and performance incentives. A great part of the innovative performance-based features of the system are likely to continue after the project completion, as the competitive approach is supported at all local levels.

The MTE team also appraises the complementary focus on UP’s OSR as a means to strengthen longer-term sustainable, as UPs over time will be able to generate more revenues, ensure stronger ownership and accountability vis-à-vis their citizens. Tax payment will stimulate interactions and demands from the citizens vis-à-vis the UPs. This approach, combined with supplementary accountability and awareness raising measures, see output 1, is likely to create community demand for strengthening of the service delivery (“when you pay, you can also demand”), good practices, and sustain the achievements in the coming years. Development of the OSR is also crucial for operations and maintenance of the infrastructures (roads, buildings, etc.) created.

The strong involvement of the elected and officials in all phases of the work and at all tiers – UP, Upazila, District and divisional level with gradual improvement of the vertical linkages offers stronger sustainability for the impact when the project ends, as capacity and institutional arrangements are evolving.

Links with other projects, especially projects supporting the downward accountability, and NGOs are, however, not fully utilised, and could be strengthened in the coming years. Although there has been collaboration with LGSP in core areas such as training of the assessment teams, the transmission belt between lessons learned and activities could be further strengthened to enhance longer-term impact.

There is also a need for a strong level of interactions and exchange between the annual performance assessments conducted by the auditors/assessors under the LGSP 2/UPGP and the current monitoring conducted by MIE – Wing in the LGD to ensure that results are more actively utilised and followed up by interventions.

### 7.8 Conclusion

After initial delays of the project start-up affecting especially the annual performance assessments and grant allocations, the system of elaborated (third generation) of PBGS is established and functioning, although still with some delays, which have to be rectified in the coming years, to fully utilize its potential. UPs have been able effectively to implement projects, and with an increasing focus on MDG targets and needs of the vulnerable and greater involvement of women in all phases. UPs have also been able to improve their planning and OSR mobilization efforts, although better data from the new MIS will provide more robust evidence, and has improved their performance faster than in non-targeted areas. The UPGP has already demonstrated that UPs can do more than just hard-core infrastructure and the diversification of projects and implementation ratio in future will be a strong show-case for future reforms.

The funding system has focused on important multi-sectorial interventions. However, in the future there is perhaps room for additional attention and support to sector interventions, with testing of (performance-based) sector funding schemes and review of lessons learned from this. Furthermore, the issues on environment and climate change have not yet been addressed under the two programs, but linkages with these initiatives could be further explored for the future interventions. From the field-work it is evident, that the PBGS is strongly supported, and that the procedures have been improved since LGSP 1/LIC. There is, however, a strong need to speed up on the APAs, and the grant allocations to ensure all fund allocations and targets are be reached by end of program.

# Assessment of Results – UZGP Output 1

The UZGP has noticeably contributed to enhancing the capacity of elected and government officials vis-à-vis the institutional capacity of the Upazila Parishad (UZP) and augmented the institutional competence and effectiveness in compliance with the Upazila Act. Achievements of results against targets can be found in the results framework in Annex 13, which the data below is referring to.

The level of CB support has been high since project start, although more support is requested by most UZP visited during the field-work as the operations of the newly elected UZP councillors are happening in a challenging governance environment. Project support included training of 9,292 elected and government officials both in terms of generalized and specialized training which was targeting responsive governance and pro-poor / MDG oriented planning.

Divisional and District level facilitators (DLG, DDLG and DF) helped the elected and government officials in enhancing their understanding of legal, administrative and institutional functions and their corresponding roles which in turn, resulted in promoting pro-poor service delivery and strengthening the local democracy.

The project published an Upazila Parishad Manual, a compendium of Rules, Circulars, and Government Orders (GOs) related to UZPs to facilitate effective functioning of UZP and better understanding of the legal, administrative and institutional framework of Upazila Parishads.

Good results has also been achieved in democratic functioning and leadership in Upazila Parishads (UZPs) as 70 % of the UZPs held mandatory Monthly Parishad meetings in 2013, as compared to 30 % UZPs in 2012. Four hundred eighty one (481) Upazila Parishads have submitted annual budgets to LGD on time as compared to only 95 in 2012 in compliance with Upazila Act 2009. The 14 UFF pilot UZPs could also prepare and publish their first ever Annual Plan Book with five-year development vision.

The technical support provided through the District and Divisional Facilitators have helped UZPs conducting the monthly Standing Committee meetings, increasingly in conformity with legal requirements that include assistance in preparation of meeting agenda, working paper and meeting minutes etc. It helped the Parishads in holding monthly meetings and Standing Committees in meeting regularly and effectively. The MTE field-work confirmed a marked difference between the target areas, where standing committees were established and mostly operating, and the control group (4 UZPs outside of the target areas which performed very weak). In total, due to capacity building provided by the project, 100 %of UZPs became able to form Standing Committees as compared to 50 % in 2012, while 40 %cent of the UZP Standing Committees conducted mandatory meetings.

The project documentation and the MTE field work confirm that democratic oversight, civic engagement, transparency and accountability are improving significantly in target UZPs compared to non-targeted UZP. This has been promoted through workshops at UZP level with the local administration, civil society, NGOs and CBOs and through support to the Standing Committees and to the formulation of UZP development plans.

The UZGP, along with UPGP, facilitated the establishment of Women Development Fora (WDF) as a mobilizing platform for elected women’s participation in local government. The project has formed 214 WDF, of which 191 are at UZP level and 23 at District level. The total number of WDF member as per 2013 were 7,311.

In pursuit of raising public awareness and as a part of advocacy on 21 functions mandated to the UZP, the UZGP has supported the LGD in designing, developing and installing UZP Information Billboard to all UZPs across the country.

The project has to a great extent contributed to improving functional and institutional capacities of Upazila Parishad in the target areas to ensure effective and accountable delivery of services and responsive governance, but also contributed through general CB to the performance of all UZP in the country. However, the analysis has also shown a number of core challenges, which need to be addressed to make the future activities fully efficient and more sustainable. The table below shows a snapshot of some of the marked differences from the field work between the target UZPs (in the 7 districts) and UZPs outside (from Tanguil and Jessore).

Table: Comparison between 8 UZPs in the 7 target Districts with 4 UZPs in non-target Districts.

| Intervention area | Target Group | Control group |
| --- | --- | --- |
| Planning | Marked improvements in all 8 UZPs | No/low development |
| Budgeting | Marked improvements in all 8 UZPs | No/low development |
| Links with Line Depts. | Improved significantly | No improvement |
| Involvement of citizens in decision-making | 7 out of 8. | Very low and limited improvement. |
| MDG targeting of use of funds | All UZPs has started this, but particularly the ones covered by the UFF | No targeting. |
| Performance assessments | Satisfied as it enhances the completion and focus | Request to be enrolled in the system. |
| OSR improvements | 6 out of 8 have improved significantly | 1 out of 4 have improved |

Source: Field level data: Target group is Kazipur, Ullapura, Pirganj, Pirgache, Sariai, Brahmanbaria UZP, Dacobe, Dumiria and control group is: Tangail Sadar, Jickargacha, Ghatail, and Jessore Sadar UZP.

### 8.1 UZP members

Target Indicator. Percentage of women and men UPZ councilors who report they can participate effectively in debate and influence decision making by the end of the project. Baseline: 27.2 %. Status: 40 %

The improvements in conducting mandatory monthly meetings and preparing minutes as compared to the baseline, is supported by evidence from the eight target UZP and the four non-targeted UZP visited during the field work in October 2014, where there were significant changes in this area between the target and control UZPs. Upazila Parishad meeting proceedings are better recorded and maintained, showing evidences of participation of both male and female councilors. MTE field observations revealed that the nature of engagement and quality of understanding of the Upazila governance processes and procedures are relatively better among the UPZ councilors in the project areas as compared to those in the control

The UZP councilors and officials stressed that the CB support rendered, including the fact that 9,293 elected and government officials received generalized and specialized training since 2013, had some impact on the engagement and quality of the performance of the Upazila Councilors. All 8 UPZs met in the target areas in October 2014 were of the opinion that the UZGP has contributed significantly to stronger roles of the UZP councilors in planning, budgeting and project monitoring. The role of the VC in the standing committees and the operations of these have improved significantly since the start of the program, although there are still challenges in some of the UPZs.

### 8.2 Right to Information

Target Indicator: Number of UZPs with are compliant with at least 90 % of the provisions of the Right to Information Act by the end of the project. Baseline 35.7 %. Status: 100 %

There is no specific and designated focal point for the implementation of the RTI provisions but appointments of Information Officers in each of the fourteen pilot UPZs have taken place as a result of UZGP advocacy and the performance assessment of the UZPs also promote access to information in core UZP operations, including planning, budgeting and project selection.

The draft RTI study sponsored by the project noted that the RTI guidelines, manuals, instructions, circulars have clauses and sub-clauses with no clear provision of direct information dissemination about the services and entitlements for the recipients of those services. The most common provision for information dissemination found in those documents were the Billboards, which may be a good instrument for information dissemination but in many cases the intended beneficiaries cannot read those, and it cannot stand alone as a means of publication. The target UZPs have improved areas such as information about decision-making and open budget meetings (all eight field level target UZPs had this) compared with the control group and field observations showed that the Billboards were more visible and appeared to be better maintained in the UZGP covered areas as compared to those in the control areas.

### 8.3 Standing Committees

Target indicator: Average number of key Standing Committees functioning in UZPs by the end of the project. Baseline; 34.6 %. Status: 85.7 %

By the end of 2013, all 17 Standing Committees are formed at the UZGP covered Upazilas. Currently, 85.7 % the UZP Standing Committees conduct mandatory meetings and prepared minutes and all targeted UZPs prepared and submitted their budget to LGD as mentioned above. The fourteen target UZPs prepared and printed Annual Plan Books (Annual Plan + Budget + FYP). This basic statistic was supported by field evidence, which show a marked improvement in the operations of the standing committees in the eight target UZPs compared to the control group of four UZPs. This improvement concerned areas such as activity level, involvement of line departments in the work and management and decision-making procedures, with stronger involvement of the UZP chairman, vice chairmen and the councilors and emerging increasing interactions between the LDs and the UZP as a corporate body.

### 8.4 WDF

Target indicator: Number of Women’s Development Forum registered at the District level by the end of the project. Baseline: 6. Status: 23

There has been a significant improvement in the establishment of operations of the WDFs since project start and the support has gone beyond the core target area of seven districts. 409 WDF have now been formed of which 386 are at Upazila and 23 at District level with 13,497 women representatives from LGIs. Interviews at the UPZs confirmed the significance of this development for the empowerment of women. However, it should be noted that none of the district level WDFs has been officially registered yet and that the roles of the WDF may need to be further clarified, see chapter 6. In terms of impacting planning and service delivery of the UZPs, the significant rise in MDG services in target areas compared to control areas is a credible proxy indicator for improved voice for female councilors, especially combined with the MTE field interviews with WDF members, which confirmed this trend.

### 8.5 Citizens Charter

Target indicator: Number of UZPs that have prepared a “Citizen's Charter” incorporating arrangements for UZP-constituent relation by the end of the project. Baseline: 85.6 %. Status: 100 %

All targeted UZPs prepared and published citizens’ charters although furthering of entitlements for social protection benefits is lagging in all UZPs, in line with the situation experienced at UP level. This is an area that needs attention, not only as an access to information issue, but first and foremost as a funding issue backed up by strong incentives for LGIs to perform and firm government oversight.

### 8.6 Effectiveness

To evaluate effectiveness the after only 1.5 years of operations is hard in this new challenging governance area, but the MTE has shown signs of promising impact in all core targeted areas, except for RTI/access to entitlements. During field visits, a good number of officials, including the members of the Upazila Parishad, have raised their concerns regarding the number of Standing Committees. During an interview, one Upazila Vice Chair noted that “there were too many ornamental Standing Committees with vague and sometimes overlapping jurisdictions”.

Overall, Upazila faces a broad range of institutional, functional and political challenges, which include capacity constraints, strained relationship with LD officials, dominance and control of the ruling party Members of Parliament, limited institutional practice of process under law and non-availability of elaborative rules and regulations. At the functional and institutional level there is still vague coordination between Upazila Parishads and the LDs which have strong implications on the development planning, management and ensuring service delivery.

The authority structure is politically and administratively divided between the Upazila Chairman and the Upazila Nirbahi Officer. In some cases there are triangular conflicts among the elected representatives, Upazila Chairman and the Member of Parliament. LD officials in reality are neither accountable to the UNO nor to the Upazila Chairman, which often results in inefficiency, poor coordination and lack of administrative accountability. In many places the standing committees established under UZPs run in parallel to the LD’s standing committees with lack of coordination.

While UZP committees are formed according to the UZP Act, LD committees are formed according to government circulars. At the UPZ level, LDs set up one or more committees. Activities of the LD committees are program based and many of them are time bound depending upon program needs and direction from the Line Ministry. The issue over overlapping responsibilities could easily be solved at policy level, by making the standing committees supreme over the LD committees and/or dissolving some of the LD committees by issuing office order/circular.

The issue of overlaps and blurred responsibilities seems to be much better addressed in the target UZPs and with the UFF as a broker in the conflicts and with the aim to strengthen the linkages, but for the tier as such, there is an urgent need for enhanced focus on the institutional set up, legal framework as well as conflict resolution in the areas where cooperation is a challenge.

### 8.7 Efficiency

Despite the late start-up of the UFF and the delays in allocations, the target UZPs has been effective in speeding up of the investments and use of funds in targeted areas of the program, and UZP has shown a remarkable performance in project implementation within this new framework. .

Further, the collaboration between UZGP and UPGP facilitated strengthening service delivery in 138 UPs, which are located in the 14 Upazilas supported by UZGP grants. Integration and synergy were achieved in planning and supporting 27 service delivery investments across 20 UPs. This alliance with UPGP also helped link 20 UPs with 14 Upazila level WDFs. This partnership also made it possible to initiate coordinated planning and implementation of service delivery investments across 404 UPs, which utilized the grant assistance of $1.72 million from the UPGP. Leveraging the partnerships among LGSP 2 and UPGP and UZGP has helped the Joint program to widen and deepen its impact. The breadth of impact that this partnership has made across the country, in relation to Performance Based Grants and MDG oriented investments has been accompanied by diligence in complying with norms and procedures and a fruitful completion across the LGIs on performance enhancements. On the other hand, the partnership between UPGP and UZGP has facilitated deeper collaboration between the two tiers of local government, and important results in empowering women representatives.

Some of the training and workshop programs organized by the UZGP and UPGP on gender sensitization, service delivery, coordination and mapping of NGOs have complementary effects on both projects, which ultimately add to the efficient use of resource and output impacts.

The services offered by the District Facilitators have been used for monitoring and backstopping services have also contributed to a more efficient use of resources. Similarly, the DDLGs played an important role in providing technical and monitoring services for both the projects and optimized the level of efficient utilization of the resources.

### 8.8 Sustainability of results

The UZP level is vulnerable in terms of adverse political influence, governance practices and institutional set-up, and it should be noted that a longer time-frame is need to ensure sustainability of results. Some of the critical institutional and political issues identified needs to be addressed to seriously enhance sustainability. However, on the positive side the posting of a DLG (with the rank and status of Joint Secretary) at the DDLG at the district level has created mechanisms of monitoring as well as back up support for the institutional strengthening of the Upazila system. The Cabinet has taken some initiatives to devolve more responsibilities and resources to the Upazilas that could further excel the decentralization process and make the UZGP impact more sustainable and institutionalized.

The sustainability of training delivery is faced with similar, if not graver, challenges as UP trainings, since there is no national framework for CB of LGIs. In the case of UZPs, there has been very little time to target training delivery overall and it is urgent to start work on the framework and include the UZP level.

### 8.9 Conclusion

The UZGP has provided important support to the UZPs and helped sustaining the tier in very difficult times. Most of the challenges facing the project concerns institutional issue, which needs to be solved at policy level and advocated for through the policy advice of the project The long-term impact of UZGP depends on the manner in which the learning generated from the project can be shared and mainstreamed in government policies and strategies and harmonized with donor supported projects in the field, see chapter 13.

The training programs have considerably developed the level of confidence and functional skills of the UPZ Councillors, especially female Vice Chairs, who according to MTE field work findings have become more active in decision making of the Upazila Parishad, supported by the emerging expanding role of the WDFs.

Through training and workshops, UZGP appears to have been able to infuse some democratic values among the LD officials and MTE field evidence suggests that they are gradually accepting the authority of the political executives. This change of mindset is paving the way better accountability and induced a new (emerging) democratic culture at the local level.

The CB/TA rendered by the project will need to be continued in the remaining project duration as per envisaged time-plans. But there is a need to compliment the TA/CB with a dialogue on the more substantial governance and institutional issues mentioned above, such as the role of the MPs, the links between the UZP (and the standing committees) the LD committees, staffing issues and funding arrangements. Considering the scope of activities, overlapping of boundaries and resources constraints, the number of Upazila Parishad Standing Committees (at present 17) needs to be rationalized in line with the links with the LDs committees, which over time should be merged with the standing committees.

Finally, advocacy should be initiated on the options for establishing a UZP budget and accounts section, as the existing CA and UNOs are overloaded and as the accounting is fragmented in some places.

# Assessment of Results – UZGP Output 2

Output 2 Strengthening of Planning and Budgeting system at UZP with MDG orientation and pro-poor service delivery mechanism.

Activities under this output have centered around establishment of a new innovative performance-based Upazila Fiscal Facility (UFF), which is aiming at addressing some of the challenges with the weak linkages between the Line Departments (LDs) and the Upazila Parishads (UZPs), and to boost the democratic interactions at the UZP level, as well as to enhance service delivery in areas of core value for MDG achievement. The UFF was designed to ensure that the capacity building support and TA, and other instruments could be backed up by fiscal support to make the planning and budgeting process more meaningful, and to strengthen the collaboration and interactions between UZP and the LDs and the horizontal coordination across UPs with the UPZ. The fund has been designed to ensure that grants would be allocated with a clear allocation formula whereby performance of the UZP is incorporated together with objective criteria such as size of area, size of the population, poverty level, targeting 7 UZPs in the first year and 14 UZPs in the second year. In the future years, the funds will be allocated in a competitive manner to the best 14 performing UZP in the target area. Guidelines and performance assessment tools have been developed, and two rounds of performance assessments have taken place and the third is being planned for, see Annex 18.

The two rounds of allocations have enabled the UZP to gain access to important discretionary funds, which has provided the assemblies with meaningful means for the UZP planning and budgeting process and enabled the UZPs to link up with the sectors and other actors as this level. Compared to previous initiatives, these are major milestone, and the delays experienced in the previous phases are planned reduced over the coming years. The table below shows the main features and coverage:

Table: Core features of the Upazila Fiscal Facility

| Core operations | 2012 – First Project Year | 2012/2013 | 2013/2014 | 2014/2015 |
| --- | --- | --- | --- | --- |
| Guidelines | UZP Grant guidelines approved (updated in June 2013). Performance Assessment manual completed and revised in 2013. | Refined manual and detailed work-book for the assessors elaborated in 2013. | Fully operational | Fully operational |
| Performance assessments | First APA (contracted out) | Second APA (contracted out) | Third APA being planned; expected completed by end of 2014 (contract to BIM). UZPs are aware of the coming assessments. | Third assessment will impact on this. A fourth will be initiated in 2015 |
| Number of UZP being assessed |  | 7 | 14 | 65 |
| Coverage of UZP by the UFF |  | 7 (one in each district) | 14 (two in each district). In the future there will be a screening of all 65 UZP to identify the 14 qualifying UZPs. | 14 |
| Grant allocated |  | 35 million TK (average 5 million each, depend on formula and performance) | 2 trances (May 2014 and September 2014) @ 35 million TK = 70 million TK have been disbursed | To be allocated |
| Projects funded |  | 104 schemes No of beneficiaries: 316,455 | 120 schemes No of beneficiaries 304,666 | To be decided |
| MDG targeting of the schemes |  | 62 % of the schemes | 81 % of the schemes (97 out of 120 schemes) | No data yet |

Support on planning, budgeting and governance issues has also been provided to all 487 UZPs at a general level and more specialized training to the 65 target UZPs covered by the interventions in the 7 districts, and again extra support to selected 14 UZP (covered by the UFF) in terms of fiscal support and guidance on the grant utilization and planning system. Specialized support has been provided to all 65 UZPs in the 7 districts to develop annual plans, plan-books and visions for the future 5 years, which is a crucial instrument in the planning and budget process. Furthermore, planning guidelines for the UZP are currently being reviewed by the LGD to be issued soon. 134 UZP are currently in the process of finalizing their FYPs (including the 65 UZPs in the 7 districts), which are expected to be completed by December 2014. Below is a review of some of the main achievements against the four planned results from the project document. The new innovative performance-based UFF was highly appreciated amongst the target UZPs, and is promoting a stronger sense of focus on performance and fruitful competition across the UZPs.

At the outcome level there are emerging impact of the UZGP investments reflected in the level of citizens satisfaction with the services provided by UZP within the target area UZPs compared with the control group (not covered), where 58 % of the citizens against only 40 % in the control group are highly satisfied/satisfied with the services.

The number of highly satisfied/satisfied citizens with the services targeting poor groups and MDG targets were 53 % against only 31 % in the control group. Below is a review of progress on outputs against the targets.

### 9.1 Plans linked to Line Departments

Target indicator 1: Number of line department activities integrated with UZP plans and budget. Baseline = 0. Status: All target UZPs in the target area (65) have taken first steps towards this, but the activities will be continued along the work on the coming FYPs (expected completion December 2014). 14 UZPs in the UFF has included LD budget proposals in the budget.

Work is in progress on this result area, and further initiatives will need to be undertaken to make it fully effective. 65 UZPs in the target areas have been through an intensive 9 days interactive process of developing a plan-book, which encompass the linkages between UZP and Line Departments’ interventions. All 65 UZPs in the target area now have a strategic FYP. Standing committees have started being operative with involvement of elected representatives as well as LD officials. 70 % of the mandatory UZP meetings were conducted in 2013 against only 30 % in 2012. The formation of 17 standing committees in all UZPs is completed, but some of these in many UZP are still not complying with the Act and regulations. Guidelines have been developed to integrate the proposals form the line departments into the general operations and priorities of the UZP through the planning and budgeting process, and with funding arrangements from the UFF. Guidelines have also been developed on the UFF to guide the planning, budgeting and implementation process.

The field-work showed a marked difference in the level of operations of the standing committees, involvement of the LDs in these, and interactions between LDs and the UPZs between the eight target UZP and the four UZPs from Tangail and Jessore Districts. All eight visited UZPs in the target area expressed a strong view that the UZGP has promoted this change, which was especially pronounced in the areas where CB was combined with the performance-based grant system – the UFF.

### 9.2 Development plans based on needs assessments

Taget indicator 2: Number of participating UZP that have produced development plans responding to local MDG assessment and identifying needs and actions related to the most vulnerable groups (such as the *Dalits or other locally relevant excluded groups) by end of project. Baseline value: 0 %. Status: Significant progress. All 65 UZP have produced plan-books with some visions, annual plans with MDG considerations. Quality of these is the current focal area moving towards the MDG targeting FYP.

There are major achievements on this result. 65 target UZPs produced annual plans and Upazila Plan Books with review of needed areas, MDG reviews, and MDG linkages against a baseline of zero UZPs when the project started in 2012. The plan books all have MDG discussions as an integrated part of the product, although the quality varies.

Furthermore 481 UZPs have been supported and been able to submit their annual budget on time in 2013 in compliance with the UZP act 2009 compared with only 4 % in 2009/10. Currently 134 UZPs (including 65 UZPs in selected 7 districts) are in a process of preparing five-year plan and some of them already prepared the first draft and as per the plan they would finalize and publish up-dated Plan Book within December 2014. 65 Upazilas, which have developed one-year plan with some visions in previous year is now developing five-year plan using the information of previous plan book.

The field work in the 8 target UZPs and the 4 control UZPs also showed a marked difference in the performance in this area, especially when it comes to strategic planning, operations of the standing committees and involvement of the LDs in this process.

This is supported by a recent citizens’ perception survey. According to this, 57.1 % of the citizens in the target UZPs find that UZPs have given priority to the MDG against 46.2 % in the control group. The citizens’ perception of the UZPs that developed plans for local poor and marginalized groups were stated to be 85.7 % in the target group compared with only 69.2 % in the non-targeted UZP group.

The field work showed that all the 8 UZPs in the target group (cross-checked with various respondents) were of the impression that the processes budgeting, planning (including MDG and gender targeting) and involvement of citizens in this process have changed significantly over the past 2 years, whereas this was not the case in the 4 UZPs in the control group. None of the four target UZPs has started reviews of MDGs and targeting of this in their development plans.

### 9.3 Development plans with interventions addressing vulnerable groups

Target Indicator 3: Number of participating UZPs with development plans that have at least one development intervention addressing needs of the identified most vulnerable groups (such as the Dalits or other locally excluded groups). Baseline value 0. Status: 9 out of 14 targeted UZP has such schemes in FY 2013/14.

By 2013, 104 schemes have been adopted by the UZPs and approved by LGD and 99 schemes were implemented by end of 2013. 63 schemes have been reported to be MDG/gender responsive i.e. 61 % of the total number schemes increasing to 81 % of the schemes in FY 2013/14. For both years, 15 % or 33 out of the 224 (104 projects in 2012/13 and 120 in 2013/14) of the projects are directly addressing the most vulnerable groups of which 16 schemes were included under 6 UZPs (out of the 7 target UZPs) in FY 2012/13 and 17 schemes were under 9 UZPs (out of the 14 target UZPs) in FY 2013/14. Around 10 % of total grants were used to address the needs of marginalized and vulnerable groups.

Examples of MDG and gender targeting projects are included in Annex 22, from the field-work, which confirmed a marked difference in the manner and results of the allocation of projects. The majority of the UZPs in the target area, and especially the ones with the UFF, had increased their focus on MDG and gender targeting, and included projects in support of vulnerable groups, e.g. through support to poor school children, improved access to health and initiatives to reduce child maternity, support to women’s groups coordinated by the WDF, etc. Previously the ADB funds were often just divided across the UPs without due attention the needs of the vulnerable, but these procedures have gradually changed. Furthermore, most of the schemes undertaken by the WDF and female members at the UP level are women-focused. All the participants are women. They have receiving practical training (tailoring) that will help them earning money, combined with input support such as sewing machines.

The clear impression from the field and interviews with women involved proved that the UZPG support is helping the female UP members to plan and formulate issue-based (women development) scheme (33 %) for women development and influencing the UP chairmen to allocate money for implementation at the UP level. In some case the activating role of the WDF has led to funds received from the UZGP/MP to implement projects as well. It has prepared an annual plan for the forum already. It has emerged as a strong platform for uniting the elected UP female members and played an instrumental role for women’s articulation of development need at the UZP level (as well as the UP level).

### 9.4 Grants allocated for MDG targeted projects

Target Indicator 4: Percentage of performance based grants allocated to projects identified as  MDG-responsive in annual development plans in final year of project. Baseline value: First round PMS. Status: 81  % of the schemes in FY 2013/14.

In the second year of the UFF (2014), a total of 120 schemes have been adopted in the 14 UZP and 81  % of the schemes in 2013/14 were reported to be MDG focused along the lines in the UFF grant operational guidelines increasing from 61  % of the projects in FY 2012/13. Of the total schemes implemented in FY 2012/13, female beneficiaries accounted for 53  % (or 166,168 out of 316,455 beneficiaries). The MDG focused projects constitute a very high level compared to the previous experiences and the experiences amongst non-covered UZP (e.g. in the four non-covered UZP visited), was that the ADP grants did not have a MDG focus in any of the projects and that there is a marked difference with the UFF.

The utilization of the UZGP- Upazila Fiscal Facility (UFF) has significantly focused on the MDG relevant areas and the combination of CB support, incentives and grants have been instrumental in achieving a greater level of targeting, see below.

Table: Beneficiaries of UFF in 2012/2013 (first year)

| SL | Name of UZP | Number of Project | Direct Beneficiaries |  | Total |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Female | Male |  |
| 1 | B.baria | 9 | 12050 | 9850 | 21900 |
| 2 | Kishorgonj Sadar | 8 | 39370 | 41030 | 80400 |
| 3 | Jagannathpur | 20 | 47088 | 15334 | 62422 |
| 4 | Dumuria | 9 | 20535 | 18618 | 39153 |
| 5 | Betagi | 28 | 30200 | 48100 | 78300 |
| 6 | Kazipur | 17 | 9840 | 10440 | 20080 |
| 7 | Pirgonj | 13 | 7085 | 6915 | 14000 |
|  | Total | 104 | 166168 | 150287 | 316455 |

Source: UZPG database/MIS.

Table: Beneficiaries from UFF in 2013/14 allocations (second year).

| Table: Direct and Indirect Schemes Beneficiaries by District |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SL | Name of UZPs | Total # schemes | Direct Beneficiaries |  |  | Indirect Beneficiaries |  |  |
|  |  |  | Female | Male | Total | Female | Male | Total |
| 1 | B.Baria | 11 | 12800 | 13200 | 25000 | 19000 | 18500 | 37500 |
| 2 | Bancharampur | 11 | 8500 | 10200 | 18700 | 12500 | 14500 | 27000 |
| 3 | Barguna | 6 | 6250 | 9000 | 15250 | 1650 | 2900 | 4550 |
| 4 | Betagi | 7 | 6800 | 8650 | 15450 | 1650 | 2550 | 4200 |
| 5 | Jagannathpur | 17 | 12200 | 16050 | 28250 | 4650 | 4950 | 9600 |
| 6 | Sulla | 9 | 6000 | 4700 | 10700 | 3800 | 4150 | 7950 |
| 7 | Kazipur | 8 | 18530 | 23400 | 41930 | 8875 | 8875 | 17750 |
| 8 | Pirgaccha | 9 | 6772 | 7659 | 14441 | 12902 | 22199 | 35221 |
| 9 | Pirgonj | 9 | 570 | 325 | 895 | 2560 | 380 | 2940 |
| 10 | Ullapara | 8 | 9250 | 9000 | 18250 | 450 | 450 | 900 |
| 11 | Dakop | 7 | 30240 | 29000 | 59240 | 4100 | 3275 | 7375 |
| 12 | Dumuria | 10 | 11580 | 9410 | 20990 | 5750 | 4650 | 10400 |
| 13 | Kishorgonj | 3 | 8100 | 6500 | 14600 | 19000 | 25500 | 44500 |
| 14 | Mithamoin | 5 | 9970 | 11000 | 20970 | 2350 | 3000 | 5350 |
|  | Total | 120 | 147562 | 158094 | 304666 | 99237 | 115879 | 215236 |

Source: UZGP database on schemes/MIS.

Chart: MDG targeting of schemes in FY 2013/2014

Out of the 120 schemes adopted, a total 97 schemes are directly MDG-focused. It is observed from the graph that out of 97 MDG targeting schemes 32 schemes are directly focused to MDG 1 which is contributing to eradicate extreme poverty and Hunger with creation of income generating activities, 38 schemes are direct focused on MDG 2 which is contributing to universal primary education and 14 schemes is directly focused on MDG 3 which is contributing to promote Gender equality and empowerment and 6 schemes are directly focused on MDG 7, which is contributing to ensure environmental sustainability in local areas.

The figures below also show that the schemes for the two Fiscal Years 2012/13 and 2013/2014 are addressing a variety of sectors as per the objective of the UFF.

Chart: Overview of Schemes – FY 2012/2013 (104 schemes)

Chart: Overview of Schemes – FY 2013/2014 (120 schemes)

Observations from the field proved the importance of the UFF in terms of investments in service delivery, but also to improve governance issues such as meaningful operations of the standing committees (they now have some means to discuss) and linkages with the LDs.

Investments are generally targeting the investment menu as per the guidelines, MDG and gender sensitive area, e.g. supporting operations of WDFs etc. There are numerous good case examples from documentation, annual and quarterly reports, and from the field-work on investments along the objectives of the facility, see Annex 22, but the review also documented a need to ensure that these investments are always targeting “public goods”, not private investments/support to individual businesses, etc. and not investments targeting only a single or a few beneficiaries. The UFF grant guidelines (June 2013) need to be refined and clarified in respect of the main objectives of the UFF, which is multi-sectorial focus (i.e. can be used for all sectors), promote linkages with the LDs and their investments, promote focus on projects which benefit more than one UP, but with a discretion of the UZPs to choose investments, which are responding to their local needs with the view to improve on MDGs, but which are not within the short negative list of non-eligible investments, such as private goods.

Below is an overview summary of the progress on a few related output indicators, developed subsequently in various project related documents:

- % of all UZP with a five year plan: The figure on this was all 65 UPZs in the 7 districts have annual plans and some visions for the next five years and are in the process of finalisation the genuine FYP, expected completed by December 2014 (2014);

- Progress towards and integrated plan in the 14 Upazilas: The plan-book and annual budget has shown progress on this in all 14 UZPs;

- Establishment of an Upazila Fiscal Support System. Fully established and operational from 2012 with first disbursement from June 2013 (however, with some delays, see Annex 18. The UFF generally operates as per intension with a high number of projects targeting MDGs and women’s needs and with a high level of co-funding with UPs and other sources. The facility is highly appreciated by the UZPs and there is a strong request to roll it out to all UZPs in the country;

- Disbursements: (progress but with some delays in allocations). 2 rounds of disbursements have been made;

- No. of Upazilas receiving support: Result: 7 UZP in 2013 and 14 in 2014 and following fiscal years the plan is to target the best performing 14 UZPs every year), see Annex 18;

- Performance measures on democratic governance (composite 4 sub-indicators, where max is 20 points) and annual scores on core areas of performance. It is too early to judge the progress on this as indicators have only been rolled-out recently and in phases only covering 7 UZPs in the first year and 14 in the subsequent year (recently completed assessment). However data with comparison of the indicators applied in the first and second assessment show some improvements overall (12 % from a total of 200 points to 224 points), and improvements in 6 UZPs out of the 7 UZPs covered and the same score for the remaining UZP. This performance is expected to improve further with the new training and CB + additional incentives in the competitive method of UZP selection. The qualitative interviews with UZPs during the field work strongly supported the view that the UFF and the incentives included in the annual performance assessment promoted enhanced performance in targeted areas. The general impression was that the system introduced a fruitful competition across the UZPs.

  - The performance assessment system and the indicators in the UFF were highly appreciated amongst the UZPs visited. Two of the indicators – i) projects, which address several UPs and ii) the co-funding from other schemes, were hard for the UZPs to comply with, but that was also the reason why they were included to promote progressive changes in this challenging area, and some of the UZPs have managed to improve.

In addition to these results, the MTE noted a marked difference in the performance on OSR generation between 7 UZPs included in the program area, where data was available from FY 2011/12-FY 2013/14 and the 4 UZPs in the control group (105  % increase in the target area from FY 2011/12 to FY 2013/14 against only 18  % in the control group).

### 9.5 Effectiveness

The activities under the Output 2 with the UFF and supporting CB initiatives have within a relatively short time shown some remarkable results, which are promising in terms of options for up-scaling and replication. With a relatively small amount of funds the UFF has provided the means, which can provide the “glue” to link the UZP with the Line Departments’ operations and the UPs, creating better opportunities for democratic interactions both vertically and horizontally. The performance assessments, combined with grants and CB support at a general (to all UZPs) and specialized level (to 65 UZPs and extra guidance to the UFF targeted UZPs) have shown impact in terms of enhanced capacity of the UZP and promoted meaningful investments in service delivery and infrastructure, largely targeting the intended areas – MDG, women, and vulnerable groups, and with a large share of co-funded projects. Furthermore, the schemes are reflecting needs of various departments such as health, education, agriculture, etc. and not only used for hard-core infrastructure as was the previous practice, but also other types of service delivery. The soft guidance and incentives, instead of rigid rules on utilization, has enabled that intended sectors and types of investments have been supported. The field-work proved significant changes in target areas, but also the need to continue supporting the UZPs, which are characterized by challenging and vulnerable governance structures.

### 9.6 Efficiency

The support to the UZPs is rather heavy in terms of CB/TA compared to the costs of supporting service delivery (the UFF). However, as this is a relatively new initiative at a government level with numerous challenges in terms of relationship between UZP and LD, UZP and MPs, and with a challenging governance set-up at this tier of government this is found necessary. The project makes use of the government procedures and capacity to the extent possible through close involvement of e.g. the LGD officials, the DLG, the DDLG and support to UNOs and other staff at the Upazila level. The UZPs have been able to actually use and implement the projects largely in accordance with the intended objectives. Elections, changes of staffing positions, political interference, lack of capacity, also in the PFM functions, see output 1, are factors, which reduces efficiency of the UZP fiscal and service delivery operations, but the initiatives under the UFF and TA/CB support have managed to strengthen capacity and service delivery functions within a relatively short time-frame. Strengthening of the UFF grant guidelines and awareness raising on these may further increase efficiency in spending.

### 9.7 Sustainability of results

The capacity built at the Upazila level is likely to be maintained for some time, and will catalyze other improvements even with the existence of some turn-over of staff and officials. However, the relatively smaller pilot is still vulnerable, and need further time to ensure sustainability, and will need to be scaled up to a larger area to further test instruments and provisions. Focus on the functional assignment and the UZP’s own source revenues to compliment the grant schemes will be needed in the future programming as well a focus on the structural issues in the governance operations at the UZP level.

Also, the UFF has a significant potential to inform reforms of the general GoB’s ADP grant system, which has not yet been fully exploited. Up-scaling of the UFF, which has taken a series of the lessons learned from the UFF, is underway with support from JICA, where a new grant scheme will be rolled out to all UZPs in the country over a 4-5 years period. This new initiative is expected to use the experiences from the UZGP UFF, especially on issues such as performance-based allocations, performance indicators, investment menu, size of the allocations, etc. The relatively modest size of the grants in the UFF (average figure in the tune of 5 million Taka per UZP) makes it realistic to up-scale, and the dialogue between UN and JICA and the GoB on this (adjusted) up-scaling in the coming months will be of crucial importance for the future overall UZP funding system. The level of allocations under the existing ADP and the way these are handled without current considerations on the performance and the linkages between the LD and the UZP, will need to be reviewed with a view on expanding the use of the performance-based elements along the future UFF design.

### 9.8 Conclusion

Output 2 of the UZGP is on a path of good progress in achieving the intended results, especially in terms of strengthening of the target UZP’s planning and budgeting system, MDG targeting and capacity building of the UZP as a corporate body. A number of challenges, which need to be addressed in the short to medium-term, have been identified. Some of these are: delays in fund allocations, the linkages between the UZP and the MPs (unclear roles of the MP in the areas of planning, budgeting and decision-making), insufficient interactions with citizens and concerned groups, and capacity gaps in core areas and persistent parallel planning and implementation systems through the LD (LD committees) and UZP (UZP standing committees) delivery mechanisms, although the latter stream has been activated and gradually strengthened.

# 10. Assessment of results – Output 3 (shared)

Output 3: Strengthened technical capacity of Local Government Division for effective policy review, monitoring, lesson learning and capacity development of LGIs for enhanced Local Governance

This output targets policy development and M&E of the capacity support of UPs and UZPs. It is anchored in the UP, UZP and MIE wing of LGD, respectively and is designed as an important link between the governance innovations piloted under output 1 and 2 and the attempts to upscale of these innovations into new policies, legislation and mainstreaming of support and guidance to LGIs. The approach to M&E and national policy development is broadly based on multiple stakeholders. It attempts to create a continuous citizen state collaboration, including the engagement of civil society organizations (CSOs), experts, politicians and elected and non-elected officials of local government. The supervision, backstopping and M&E of UPs and UZPs build on a collaboration with the DLG, and DDLGs at divisional and district levels, but the performance assessment results linked to the grant system are also crucial in the monitoring of capacity gaps.

Despite the delays in the up-start of the program and the turmoil in 2013, the projects have managed to achieve important results, which includes

- Drafting and dissemination of UP and UZP rules, regulations and guidelines which are at various states of approval and coming into force:

  - UP Act - 7 rules, 1 regulation and 1 guideline

  - UZP Act - 6 rules and 3 regulations

- Operational M&E Strategy and a toolkit for monitoring the performance of key local governance mechanisms and quarterly reviews & joint monitoring organized at district level and using the monitoring tools

- Four policy studies, see annex 14

- Operational gender strategy and communications strategy

- Pioneering of a UP e-based MIS and accounting system in 146 Ups

- Initiation of regular benchmark surveys, including the UP and UZP baseline studies, the citizens perception survey and a RTI study and reviews of the cascading training delivery applied by the projects

### 10.1 Support to a Policy Advisory Group and National Framework for Local Government Policy and Capacity Development

Target Indicator: Existence of a National Framework for Local Government Capacity Development by the end of the project. Baseline: No draft framework exists. Target: 1. Status: 0

Target Indicator: Number of drafted legislative or regulatory instruments influenced by outcome of piloting activities by the end of the project. Baseline: current set of legislative and regulatory instruments. Target: 2 (UP), NA (UZP). Status: 7 Rules/1 Regulation/1 Guideline (UP), 6 Rules/3 Regulations (UZP)

The Policy Advisory Group (PAG)

In order to ensure a broadly informed and participation based policy development around the LG framework, the UPGP and UZGP foresee the establishment of a Policy Advisory Group with experts from government and academia. As per the joint project design, the PAG will develop a national framework for policy and capacity development for local governance. Input to the PAG discussions will draw on various sources, including the M&E data on the quality of local governance which will systematically collected by the Monitoring, Inspection and Evaluation Wing of the LGD and the R&D interventions sponsored by the projects, including broad thematic policy studies and learning through action research from best practices under output 1 and 2, respectively.

Hence, the PAG is to be entrusted with the activities concerning review of laws, rules and regulations, policy study in LG areas and to recommend any revisions, if deemed necessary; on formulation of administrative and territorial reforms, provide support to reviews of innovations and learning from the field, provide recommendations on strengthening LGI capacity; offer advisory for effective coordinating of development partners support in local governance. One the anticipated key results of the PAG work is the formation of a national CB framework for LGIs.

So far, the PAG has not functioned as a link between project interventions and policy formulation. A PAG was formed in September 2012 and reconstituted by May 20, 2014. The reconstituted PAG has not convened for any meetings yet. When it does eventually, it will be composed of 17 members and chaired by the Secretary of LGD. Two academics (a gender expert and a management expert) have been inducted to the PAG. The other members are twelve GoB officials from LGD, the project managers of UPGP and UZGP and a retired Secretary. However, there seems to be no recognized experts on Local government or local governance in the advisory committee, neither from among the academics and LGI practitioners, nor from any CSOs.

Recently, an inter-ministerial committee on local governance has been established chaired by the cabinet secretary and with representation of 17 ministries, the intention is to move the decentralization agenda forward, especially by addressing some of the core bottlenecks such as the lack of clear linkages between the LM and the UPZ as a corporate body.

This committee has produced some important outcomes, which are crucially linked to UPGP and UZGP. One important outcome has been to actually implement the decision taken a few years ago to strengthen UPs by adding an accountant cum IT officer. It has been raised by several studies and reviews that the UP level is understaffed and has a serious capacity gap vis-à-vis the functions outlined in the UP Act. The addition of an accountant cum computer assistant to the UP secretariat also tallies with the recommendations of the final evaluation of LGSP-LIC and is an important step forward. The roll-out of this decision will take place over the coming five years, according to the ministerial order below.

Textbox. Ministry of Finance Order on UP Accountant Assistants.

Ministry of Finance Order: Name of the Post: Account Assistant No of post approved : 4571 Phases: First Phase : Financial Year 2013-2014 – 1000 Second Phase : Financial Year 2014-2015 – 1100 Third Phase : Financial Year 2015-2016 – 1200 Fourth Phase : Financial Year 2016-2017 – 1271 Salary will be shared by Government and UPs: Government 75 % and UP 25 % UPs eligible for the new post of Account Assistant if it has Annual Own Income of Tk 400,000 or above

The minimum OSR access threshold of Tk 400,000 raises some serious concerns about the actual impact on the ground. The average OSR of the UPs in Tk 223,000; well below the minimum threshold.

Another important initiative of the committee is the reallocation of funds flow to LD salaries at UZP level to go through the UZP. If realized, this enhancement of UZP discretion could change the dynamics of the relationships between UZPs/UPs and the LDs by strengthened horizontal accountability and oversight in favor of the elected UZPs and UPs and assist the standing committees in being more responsive to the needs and demands of the constituents.

The PAG could serve as an important link between innovations piloted by UPGP and UZGP (and other support programs), research on needs for systemic reforms and the policy options discussed at the inter-ministerial level. While LGSP 2, and a future LGSP 3 (if this is decided) can upscale specific innovations in upcoming programs, if to be launched, the more programmatic approach to LG reforms needs to be discussed at policy level.

To some degree, (although not formalized) the two projects actually seem to link up to the inter-ministerial committee work and there is evidence that LGD is using the inter-ministerial committee for coordination and dialogue. A draft UP planning guideline has been circulated in the committee for comments and inputs, indicating some links between project innovations and the committee work.

A National Framework for Local Government Capacity Development

UPGP and UZGP deliver capacity support based on needs assessments and comprehensive CB delivery experience based on approached pioneered by SLGSP and LGSP-LIC and through a broadly based cooperation with national training institutions. There is, however, no national CB framework, which can sustain all these efforts, build synergies across sectors and stakeholders and ensure comprehensive funding. Hence, one of the core recommendations from the final evaluation of LGSP-LIC was to institutionalize capacity development within a common national capacity development framework and this recommendation was carried over into the UPGP/UZGP projects and has become a key shared output of the projects.

There are many CB stakeholders in local government in Bangladesh, both within the government, within the private sector and CSOs and through support multiple (often ad hoc-based) funding sources such as various developing programs. This is not a unique challenge to Bangladesh and many developing countries are faced with numerous, ad hoc oriented CB approaches linked to (sector oriented) project support and hence limited in time and coverage. Some countries have however moved forward and targeted local government CB within a comprehensive strategic framework mutually agreed upon with the development partners.

Unfortunately, the absence of PAG activity is matched by the absence of a comprehensive CB framework. The projects have yet to start drafting the framework and work on this is planned for 2015. Whilst NILG already has developed a strategic document with support from SDC, this only covers the UPs; the UZP and Pourashava level are not targeted. Furthermore, the NILG strategy has yet been formally adopted and operationalized by the GoB.

Legislative or regulatory instruments influenced by the projects

The implementation of the UP Act and the UZP Act rests on development of a number of secondary legislation instruments and guidelines. At the onset of the two projects, 0 and 5 rules respectively were in force. The projects have made good progress in drafting new secondary legislation and the table below presents the current status of the legal instruments submitted through support from the UPGP and UZGP.

Table. List of Rules and Regulations drafted by UZGP and UPGP

| # | Title | Category | Status | Project |
| --- | --- | --- | --- | --- |
| 1 | Upazila Parishad (Maintenance and Publication of Record, Reports, etc.) Rules, 2014 | Rule | Final Draft submitted and LGD is reviewing | UZGP |
| 2 | Upazila Parishad Fund (Custody, Administration, regulation and Investment) Rules, 2014 | Rule | Final Draft submitted and LGD is reviewing | UZGP |
| 3 | Upazila Parishad (Maintenance of Accounts and Audit) Rules, 2014 | Rule | Final Draft submitted and LGD is reviewing | UZGP |
| 4 | Upazila Parishad Employees (Service) Rules, 2010; | Rule | Final Draft submitted and LGD is reviewing | UZGP |
| 5 | Upazila Parishad (Appeal against Orders) Rules, 2014 | Rule | Final Draft submitted and LGD is reviewing | UZGP |
| 6 | Upazila Parishad Chairmen, Vice Chairmen and Members (Resignation, Removal and Vacation of Office) Rules, 2014 | Rule | Final Draft submitted and LGD is reviewing | UZGP |
| 7 | Upazila Parishad (Tax) Rules, 2014 | Rule | 1st draft prepared | UZGP |
| 8 | Upazila Parishad (Conduct of Business) Model Regulations, 2014 | Regulation | Final Draft submitted and LGD is reviewing | UZGP |
| 9 | Upazila Parishad (Conduct of Meetings) Model Regulations, 2014 | Regulation | Final Draft submitted and LGD is reviewing | UZGP |
| 10 | Upazila Parishad (Delegation of Power) Model Regulations, 2014 | Regulation | Final Draft submitted and LGD is reviewing | UZGP |
| 11 | Union Parishad Regulation, 2014 | Regulation | 1st draft and final draft prepared. LGD to forward for enactment | UPGP |
| 12 | Union Parishad Disclosure Guideline, 2014 | Guideline | Circulated | UPGP |
| 13 | MDG Planning Guidelines | Guideline | Final draft submitted | UPGP |

While most of the legal instruments are still under review, the overall assessment is that good progress has been made in the establishment of the legal framework for UPs and UZPs. Many of the rules and regulations listed above were initiated under LGSP LIC and UZP PA, and since finalized or revised under UZGP and UPGP. Another UP regulation is still under preparation.

### 10.2. Support to LGD (MIE wing), DLG/DDLG for UZP/UP backstopping and monitoring

Target Indicator: Implementation of a functioning M&E and MIS system in the Monitoring, Investigation and Evaluation Wing of LGD (capturing key data on local government performance) by the end of the project. Baseline: Only a project based MIS (and in early design stage) is used by LGD. Status: 1st Phase completed according to the M&E strategy.

Target Indicator: Number of DLGs who have a sustainable system for monitoring and backstopping local governments by the end of the project. Baseline: No system in place. Status: Joint monitoring implemented at district and UZP level.

LGD oversight and backstopping of UPs (and UZPs) has not been systematic in the past and a key objective of the two projects is to build capacity within the MIE wing of LGD (MIE wing), DLG (Division level) and DDLG (District level) for backstopping and monitoring of the UZP and UP level of local government. This includes:

- Support to LGD (MIE wing) to develop and operationalize an M&E system for UP and UZP performance monitoring

- Support to DLG to develop, collect and analyze governance and ”democracy” indicators

- Support national training institutions and private sector agencies in training and backstopping of UPs and UZPs

- Creation of national data base of local government plan, finance and services

Each of the two projects have set up an elaborate support and data collection system in order to strengthen LGDs M&E capacity and outreach to UZPs and UPs:

UPGP

The M&E interventions targeting UPs are anchored within the UPGP M&E strategy designed in 2012. It foresees a four step implementation phase, moving from basic project M&E in 2013 to a countrywide LGI monitoring and backstopping in 2016, assisted by a MIS for all UPs:

Chart of the UPGP M&E strategy

In order to make the strategy work, an elaborate reporting system has been established within the project area, which builds on monthly or quarterly data samplings, monitoring the governance mechanisms which are supported by the project. For these purposes a number of monitoring tools have been developed:

- UP visit checklist

- Session Monitoring Checklist

- Ward Shava checklist

- UP SC Meeting checklist

- Scheme Monitoring Checklist

- Spot Interview checklist

- UP Self-Assessment Tool (Spider Net)

The work flow of the reporting system, where these tools are utilized, is illustrated in the chart below:

The UPGP Reporting flow chart

The monitoring plan guiding the reporting work flow can be found in Annex 14. The responsibility for M&E has yet to be transferred to the MIE wing and function as outlined in the flow chart above.

An associated e-based MIS system which captures the data sampling is already in place at pilot district level. It has also been implemented on a pilot basis in 100 UPs in Brahmanbaria district and a further 46 UPs across the other six project districts (UPs in one UZP in each of the 6 other districts). It features an integrated UP accounting system, which contains basic information on

- The five year plan, annual plan, scheme implementation, standing committee work, minutes

- Assets, households, resources, tax assessment & collection

- Budgeting, funds flow, cash and funds management as per fiscal year.

The purpose of the MIS cum accounting system is dual. It provides the UP secretary with an integrated planning and budgeting tool facilitating a more efficient planning, budgeting and service delivery, tax collection and servicing of the Union Parishad. At the same time, it will be linked to the LGD data sampling system and feeding into the (eventually nationwide) M&E framework.

In general, UP secretaries are satisfied with the MIS. It assists them in their planning and budgeting work, OSR and assets management. This was documented by the CPS and confirmed by the MTE field work. UP secretaries do also get valuable assistance from the UISC to cope with the IT aspects of the MIS.

Until now, the projects have developed the systems and procedures in a rather isolated manner to get it up and running quickly, but it is now urgent to ensure close linkages with the LGD MIE wing and other programs planning M&E design, especially the LGSP 2. The latter has planned for the development of a project specific MIS and without proper coordination there is a risk of having two systems running in parallel, where the LGSP 2 just review the experiences from the UPGP and UZP and then move ahead with another system, with some joint features, adding to transaction costs of the UPs.

UZGP

Similar to the UPGP, monitoring tools and an M&E work flow arrangement has been established in order to monitor the UZP performance and provide backstopping from the LGD through the division and district support envelope (DLG/DDLG/DivF/DF). Based on a needs assessment of the LGD and a subsequently outlined ”UZP Monitoring & Evaluation Guideline & Tools”, a monitoring tool kit has been developed, which includes:

- UZP operation reporting tools

- WDF ToT reporting format

- WDF reporting format

- Training reporting format

- Schemes reporting format

- Schemes Dairy

The M&E reporting work flow works as follows:

The work plan by which the M&E data sampling and backstopping is implemented, can be found in Annex 16. As it appears above, the M&E approach for the first phases, although closely linked up at the district level, is rather isolated from general M&E system and procedures at the LGD level (except for the strong involvement of LGD staff up to the district level), and is focusing on a strongly operating PMU. Also there is more room to link the M&E system with the findings from the annual performance assessments, to use the results in design of CB strategies and actions plans to address weaker performance areas identified.

Control groups

According to the original design, a control group of non-targeted UPs was envisaged in the annual performance assessment to follow the improvements and to measure impact of the project activities, especially the selection of performance measures. However, this has not been conducted. Instead a baseline survey was completed by UPGP, but only in 2013, covering target as well as and non-targeted UPs, but this only covers some of the performance measures in the performance assessment manual, and data on trends in performance will only be available upon the next survey planned in 2015. This reduces the options for impact assessment and reviews of attribution of the UPGP. However, there are still some areas where performance can be compared in the citizens perception survey just completed in September 2014, which has selected indicators for target and non-target UPs (e.g. in the level of citizens satisfaction and MDG targeting of investments, see under Output 2, and in the possibility to review the performance on the 12 common indicators covered by the entire country versus performance for the 564 UPGP target UPs. Second, the team has reviewed qualitative aspects of the performance during the field-mission as part of the MTE of UPGP/UZGP, and compared UPs/UZPs targeted against selected UPs in two control districts, and for both tiers there are significant improvements. However, in future piloting and design it should be ensured that baseline survey and control groups are covered from the on-set of the program and followed systematically through the project implementation.

### 10.3 R&D for Knowledge Generation

A number of studies to support project implementation and policy development have either been initiated or completed, through funding from the special R&D facility provided by the projects. These studies include:

Table. R&D activity

| # | Study, Assessment | Status |
| --- | --- | --- |
| 1 | First phase of Policy Review of Functional Assignments of Local Government (health and education services) | Completed |
| 2 | Policy Study on Unified legal Framework of Local Government | Ongoing |
| 3 | Study on key Rights and Entitlements for Poor and Disadvantage Citizens where the RTI Act can be Effective | Draft report submitted |
| 4 | Citizen Perception Survey on Services Provided by Local Government Institutions and Assessment of Results Achieved by UZGP and UPGP | Completed |
| 5 | Mapping of Fiscal flow and local government financing in Bangladesh | Ongoing |
| 6 | Review of local government revenue regimes of Bangladesh and the prospect of a uniform local government revenue policy/taxation schedule | Ongoing |
| 7 | Study on Local Government System in Bangladesh: A Comparative Analysis of Perspective and Practices | Ongoing |
| 8 | Assessment of the quality and effectiveness of the Training & Training Institutes under UZGP and UPGP | Completed |

Unfortunately, these studies could not be guided by the PAG, which per design is intended as the link between research and policy advice. Hence, the links to the overall policy level may be weak as long as there is no PAG or framework in place for how the various studies will be linked together, how they will be used, and how the results could shape future decentralization policies.

Judged by the policies outlined in government plans and strategies (refer to relevance section above), Bangladesh is most likely going to continue introducing incremental changes to the local government framework (tallying with the intervention areas of output 1 and 2) rather than opting for a big-bang reform. This also stresses the need for more action research targeting the pilot innovations of the projects. E.g. the good experiences from SLGDP led to up-scaling of the direct block grants to UPs, and were based on evidence-based studies of how the system was operating. Such studies, which took point of departure in the actual innovative measures in the projects and provided lessons learned for future adjustments and up-scaling, are missing on this list above.

Identification of relevant action research studies needs to be discussed by LGD and the projects, but there appear to be several relevant areas in need of review for learning and policy targeting. One example could be to focus on the UPs that constantly perform most poorly in reviews despite being supported by capacity building and financial support. Why do we see such persisting poor performance and how can poor performance be improved in the future? If launched quickly, such a study could also feed into the design of a new UPGP 2 and become a future intervention area.

Another example could be a thorough review of the Upazila Grant Facility and options for up-scaling in order to supplement perhaps rather theoretical discussions of various international models for grant allocations to local governments and studies of how the PFM can be improved at the LG level and how reforms can be linked to the overall PFM reform program of the GoB, especially under the SPEMP and the successor of this program (to be defined), especially the linkages with the accounting reform program and the IBASS++.

Two proposals for action research to promote gender equality have also been brought forward by the SDC gender reviews:

- the gendered impacts of the politicization of local government exploring the opportunities, barriers and risks to women’s political empowerment;

- what is working or not in supporting gender equitable planning, budgeting and resource allocation within the LG system.  The opportunity here is to establish regular and routinised light touch action research in selected UZP, once a year involving interviews with EW (male and female) and government officials, civil society representatives, observation, focus group discussions, small-scale survey instruments. Potentially, three rounds (until the end of project), of research would enable stakeholders to build up a picture of how the system is evolving over time, emerging issues and what may need attention or adjustment.

The project has supported training of LGD and other departments with exposure of international experiences from decentralization through two rounds of in-country trainings by the Academy of Hague and through an international study visit to a. o. the Hague. The outcome has been an action plan for drafting a waste management strategy for UP/UZGPs. The MTE did not go further into the relevance and follow up on the study tours, but recommends that travel reports and action plans also will be drafted for future study tours..

Policy dialogue forums

LGD has also organized policy dialogues in five divisions in 2013 on future LG policies, inviting a broad section of society to provide input to upcoming reform work. A total of 954 participants (772 male and 192 female) attended the dialogues. Another divisional dialogue forum is still pending. A technical key note paper entitled “Service to Citizen through LGIs: Coordination, Cooperation, Potential and Challenges” initiated the policy dialogues. The dialogues identified the following seven challenges and suggested ten different way forward approaches:

Table. Policy dialogue forums on challenges and the way forward

| # | Challenges | Way forward |
| --- | --- | --- |
| 1 | Lack of coordination among LGIs at different levels such as UP, UZP and Zilla Parishad on the one hand, and Pourashava and UZP on the other. All the relevant stakeholders need to be linked institutionally to create an environment of inclusive development. | - Withdrawal of the advisory role of Member of Parliament (MP) in the Upazila Parishad. - Comprehensive Charter of duties for elected and government officials of devolved departments including UNOs for improved coordination. - Enhanced administrative support to operationalize and functioning of Standing Committees of UP, UZP, Pourashava and City Corporation. - In the wake of diminishing Rural and Urban divide of LG, initiation of Policy Reform debate to integrate/reduce the number of existing LGIs e.g. merging small Pourashavas and UZPs, not creating or dividing new UPs or declaring them part of Pourashavas. - Each haat must disclose status of their revenues and services for public consumption. - Sectorial and departmental resource mapping for each LGI. - Increased fiscal allocation for all LGIs. - Introduction of a new cadre "Local Government Services” was recommended as against the deputation system. - Removal of discrepancies among LG tiers with reference to allowance and honorarium for elected representatives. - The re-establishment of Local Government Commission and appointment of Ombudsman - Reform of organizational structure of LGI from "Single post (Chair/Mayor) dominated system” to Council-led institutions' popularly expressed as ”Presidential system to Parliamentary system". |
| 2 | The existing mechanisms established for ensuring transparency and accountability of LGIs local functionaries and service providers at different levels are inadequate and non-enforceable, hence needs urgent review. |  |
| 3 | Citizens are not well informed about the rights and obligations of the respective Parishad as well as ambit of services available at Upazila and Unions. Each LGI should disclose the status of their resources and services every year |  |
| 4 | Absenteeism among the elected representatives and government officials at the duty stations is alarming. Many of the Upazila level officials do not stay at upazila residences, which is a violation of rule. |  |
| 5 | Vehicle usage does not follow the rules at Upazila level. Vice-chairs and other Parishad members generally do not have access to official vehicles for official duties |  |
| 6 | All the resources spent through the Project Implementation Office do not come under UZP or UP plan. Similarly, sectorial expenditures at Upazila and Union are not reflected in the plan and budget of the respective LG unit. It contradicts Constitutional provisions, LG laws and relevant rules. |  |
| 7 | The legal provision regarding suspension of elected representatives with an executive order from the Ministry is perceived as against the principle of electoral democracy, which needs revision. No confidence from the electorates should get the prime consideration unless any criminal offence is committed by any of the elected person. |  |

These recommendations address core challenges and strategies for the present subnational framework and are generally supported by the field work of the MTE. It will be crucial for the final evaluation of UPGP/UZGP to assess any impact from the policy dialogue forums, PAG and the policy studies on the reform work. The PAG, if finally convening, can be instrumental in elaborating further on the outcomes of the dialogue forums and consolidate recommendations for LGD and the inter-ministerial committee.

### 10.4 Effectiveness

The broader policy impact on the overall local government framework is still too early to assess. While the projects have been able to facilitate broad policy discussions across the country on the future directions of local government reforms and to initiate thematic studies on the LG framework, it is yet to be seen how these inputs can influence future policy developments. Tangible outputs like the formulation of the national framework on LG capacity development or de facto establishment of the PAG have also yet to be realised.

However, the projects have been effective in terms of producing amendments to the local government regulatory framework (legal instruments, guidelines) although some of these still need to be finally adopted and implemented by LGD. In this way, the projects have contributed to upscaling, institutionalising and sustaining local governance mechanisms on strengthened transparency, accountability and participation (standing committees, WDF, ward shavas, open budget meetings, citizens’ charter). Similarly, with the demonstration of the performance-based grant allocations at the UP and UZP level, where it has shown impact on performance and utilisation of funds. On the other hand, there is a need to establish a “transmission belt “ of the specific innovative experiences from the field level in the projects to the national level, through use of data, use of studies, use of dialogue etc. and perhaps regulations regarding the WDFs.

LGD has also been successful in lobbying for more UP staff through the planned roll out of UP accountants (albeit with high access threshold) and in strengthening UZPs accountability links to LM staff through the decision to transfer of salaries for LM staff to the UZPs. There is a similar need to ensure that funding follows assignments. The level of fiscal decentralisation is still very low compared to international and regional standards, and needs to be enhanced to boost local service delivery, accountability and sustained public engagement.

The M&E framework strategy and vertical division of work among DLGs and DDLGs have been established and implemented according to plan, despite changes and vacancies in the project staff. M&E data are produced assisted by the monitoring tool kit developed by the projects. The next important step will be to anchor these outputs in the MIE wing and upscale the framework for nationwide monitoring. The UPGP has also successfully piloted the e-based MIS, which now needs to be up-scaled.

### 10.5 Efficiency

The list of policy studies may have some overlaps to previous studies or studies currently supported by development partners within decentralisation and local governance in Bangladesh. E.g. the comprehensive ”Assessment of Fund Flows to Union Parishads” was conducted as part of the preparatory studies for the UPGP (UNCDF, September 2011). This and other previous studies are not explicitly referred to in the ToR of the current flow of funds study. The WB also supports a new flow of funds study in Bangladesh called ”Boost”, which is quite comprehensive on LG funds. Sharique is supporting a number of policy studies, which is almost identical to the list of studies supported by UPGP/UZGP.

The M&E framework and implementation of the e-based MIS has made good progress, but changes in the results indicators and targets during project implementation has brought some confusion to the overall M&E reporting system, which make the M&E framework less stringent and a bit blurred at times. Introduction of log frame revisions after implementation has to be formalised to ensure full ownership by all stakeholders. It is also questionable whether the M&E framework has exploited the results of the annual performance assessments to full extent. Lots of effort is going into external monitoring missions and updating of performance indicators in the projects’ results framework, and the generated data could perhaps be more efficiently used to monitoring LGI performances and identification of capacity gaps.

### 10.6 Sustainability of results

The production of legal instruments related to the governance mechanisms pioneered by the projects not only paves the way for upscaling of results nationwide, but it also provides a safeguard for sustaining the new mechanisms.

All the training delivered by the projects, however are still project based interventions. Despite being delivered through five national training institutes, there is a strong need to embed UPGP/UZGP as well as other training deliveries targeting local government within a unified national CB framework. Until this can be achieved, training initiatives will still be linked to ad hoc funding and project based innovations, which ultimately may not be sufficiently linked to strategic focal areas within the LG policy.

Sustaining the achievements and further development of the M&E framework and work flow established so far, will depend on a successful transition of the project based M&E to a nationwide M&E of the local government system, aligned to LGD M&E systems and managed by the MIE Wing. The projects have opted for a bottom up approach to the M&E development by pioneering the system first in the seven pilot districts and then transfer the results for final adoption by the MIE wing. The latter is only going to be commenced in 2015. It is not clear from the discussions with the MIE wing, how it perceives the transition phase. The AWP incorporates a number of training activities targeting the MIE wing. The question is whether this is enough since the M&E strategy and tool were developed within the project and apparently without significant involvement of the MIE wing.

The sustainability the newly piloted e-based MIS in 146 UPs depends on a successful national upscaling, preferably through the LGSP 2, which in its MTR has promised to look into the experience from UPGP. According to discussions with the WB, there is a positive attitude towards upscaling the UPGP results within the LGSP2, but UPGP needs to follow up on this with LGSP 2 and its recently hired MIS consultant. In any case, the M&E system developed by UPGP and UZGP is much more elaborated than the scope of the MIS under LGSP, which is more project based. It is therefore encouraging the WB agrees to align its MIS efforts with the UPGP strategy.

### 10.7 Conclusion

Most of the challenges faced by the projects at local level pertain to national policy and strategies which needs to be pushed forward. The projects have been successful in strengthening the legal frameworks of both tiers of government, but a number of policy areas now need to be addressed:

The PAG should start functioning and expand its membership to include local governance expertise (academic and practise based) and link up with the inter-ministerial group to inform this about various reform issues. The LCD should also be linked up to.

The work on the CB framework should commence immediately building on the broad approach to capacity building already adopted in the project (basic supply driven training, backstopping/on-the job training, peer learning, help desk) and targeting councillors, staff and citizens at all subnational levels. It should as a minimum include:

- Stakeholder identification (beneficiaries and service providers)

- Joint CB needs assessments and linkages to capacity gaps identified through the M&E system and the annual performance assessments

- Listing of capacity building measures (backstopping, technical support, etc.) that needs to be taken to ensure that CB activities are of adequate quality and depth, including:

  - Development of joint in-training modules

  - Career path options/staff rotations (UP secretaries have limited options)

  - Institutional performance incentives (preferably PBG with attached (ring-fenced) CB grants, self-assessment tools)

  - Individual performance incentives (e.g. best performance awards)

- Special attention to LGIs not meeting minimum conditions

- Funding modalities for training delivery – combining demand and supply driven delivery

- Multi-year budget estimate and a funding arrangement with DPs

- Implementation plan for delivery of CB services to LGIs, preferably moving gradually from supply to demands driven CB over time

- Management and oversight arrangements of the CB framework:

  - Regular quality assurance of CB delivery

  - A clear monitoring and evaluation framework (with indicators and an appropriate M&E plan), which will allow LGD to track outcomes and outputs arising from CB activities. The APA is a good source for this.

In order to operationalize the work and try to achieve quick gains, the MTE recommends breaking down the work into phases. Since the UZP level is relatively new and needs to get its support consolidated, it is recommended to start working on a framework for the UZP level and then gradually expanding the framework to comprise the other members of the LGI family

The transition of the M&E/MIS system to LGD needs to be attended to carefully, as LGD staff have not been involved before and will need to take a strong ownership and upscale the system for nationwide monitoring and learning. The MIS should be more closely linked with the results of the external annual performance assessments, which over time will be a QA of some of the indicators imputed in the M&E system; this will reduce the costs of both systems and enhance sustainability and internal learning. The projects should also be careful in overloading the LGIs with M&E demands – e.g. could bi-annual and annual reports be sufficient instead of quarterly reports.

The gender strategy needs further attention. The regular SDC gender monitoring report recommends more qualitative monitoring, which can track women’s political empowerment. There is no such indicator in the strategy M&E framework, which clearly defines which qualitative analyses need to be conducted to track this development. This needs to be attended to in the planning of surveys.

The need for action research should be revisited in order to review actual reform initiatives launched by the projects, e.g. the UFF, WDF, grant equalisation system, links to climate change initiatives, and extended support to poorly performing UPs. These studies can also serve as preparatory studies which can provide input to a next phase of UPGP or UZGP.

Study initiatives in general should be harmonised with other DPs in order to exploit synergies, common learning and lowering transaction costs. Overlapping initiatives seems to take place and there is an urgent need to look at experience from alternative/supplementary approaches in similar projects in Bangladesh, e.g. on WDF/female councillors, use of performance based grants, strategic planning, local PFM (see chapter 13 on linkages).

# 11. Management

The program management and support to UPGP and UZGP is stated as an output in its own right in the project documents, although it should be seen as the facilitation of interventions leading to output 1-3, respectively. Using the NEX modality, however, the projects are implemented by LGD and QA/backstopping provided by UNDP/UNCDF and this working arrangement is intended to build capacity within the LGD.

Overall, the projects have made good progress as documented in the previous sections of this report. This progress has been achieved despite the political turmoil in 2013 and subsequent political impasse, which caused significant delay in the project implementation and which have left the project 18 months to achieve the results to be reviewed by the MTE. The steering committees and project boards have met as scheduled in order to guide and supervise the projects and the implementation of capacity development interventions and roll out of performance based grants to both LGIs have proceeded, despite some delay.

### 11.1 Funds flow and use of funds

A lot of the critical issues experienced on grants allocation in the LGSP-LIC have been eliminated in UPGP and UZGP. The MTR and final evaluation of the LGSP-LIC project raised some concern about the multiple funds flows and differing block grant expenditure menus, which to some extent fragmented the local planning process and biased grants investments towards labour intensive infrastructure projects at the expense of MDG service priorities. Such issues have to a large extent been avoided in the UPGP and UZGP as investment funds are allocated directly to the LGIs through MLGRDC and can be utilised according to a defined menu, which has considered the challenges observed in previous support schemes. This in turn, has contributed to more diverse planning and service priorities as documented in the section on results achievements and a composition of investments reflecting several service areas more directly linked with the MDG targets.

There are, however, still problems with fund delays, which are cause by delays in start-up of the program, delays in contracting of the audit companies, ae described under the output 2 assessment

The use of funds in the two projects are overall in line with the budgets of UPGP and UZGP, see Annex 17. Discussion with project management also led to the conclusion that there is no need for budget reallocations at this point in time, and no-cost extensions are also not expected.

### 11.2 M&E

The overall M&E generate a vast amount of data, also compared to reviews of similar systems in many other places. However, there are also challenges.

In general, M&E and in particular the management of log frames and indicators are difficult and calls for a certain discipline in shaping and refining indicators and follow-up. The projects have a shared intervention on strengthening the capacity of the MIE wing of LGD in monitoring and backstopping the LGIs. For M&E of UPGP and UZGP, the results frames and indicators of the project documents were overhauled quite substantially in 2012 to the extent that subsequent progress reporting, surveys and performance assessments were not quite aligned to the revised framework (see discussion of this issue in the methodology section). Various progress reporting to meet DP accountability requirements and feed into donor country programs may also have caused some confusion in the M&E framework management with higher transaction costs and some confusion in the actual consolidation of overviews of results against targets (which data set to apply).

The boost in numbers of targets and indicators, which has not been followed through in the subsequent progress reporting and surveys, illustrates how difficult it can be to strike a balance between a complex log frame and the need to monitor developments in detail on the one hand, and the costs involved and the careful data management and maintenance which is needed to update it. It is an important lesson learned, especially since the projects are promoting good M&E systems and practises in the M&E wing of LGD.

The continuous monitoring of project progress foresees regular survey being undertaken, which includes the two baseline surveys, the citizens perspective survey, the RTI survey and updates on the gender strategy. So far, only the actual baselines surveys were conducted in 2011 and the first citizens perspective survey has just been released in 2014 along with the RTI survey (in draft). There are plans, however to repeat the baseline and the citizens perspective surveys in 2015; the latter in a more focused version, though.

### 11.3 Project staffing

The UPGP and UZGP have a total of 60 project staff employed, including the project managers and support staff, the ITAs and the division and district facilitators in the field. There are no indications of high staff turnovers which could have adverse consequences on project implementation. The DDLGs are also more stable now compared to the LGSP-LIC implementation, which suffered from frequent turnover of DDLGs.

There are a number of vacant project positions, however, which needs to be attended to. The UPGP manager, the UPGP M&E officer and the ITA on CB are all vacant at the moment, although UNDP is already in the process of recruiting new staff for employment shortly. The UPGP manager and M&E officer are important, since the transfer of M&E responsibility to the MIE wing of LGD is about to start.

UNDP plans for the vacant ITA position on CB is to opt for ad hoc support through its retainer consultancy rather than recruiting another ITA expert for the projects. The MTE agrees with this plan. The feedback from the previous ITA confirms that at this stage of the project implementation it will be more cost-effective to have short-term consultancy on specific TORs than a fulltime employee. The ITA on PFM and performance grants on the other hand is still needed on fulltime basis to ensure a continuous implementation of the PBG and to cooperate with LGD and JICA on upscaling the UZP innovations to nationwide coverage, which is currently being drafted for implementation by march 2015 with a five-year incremental upscale building on lessons learned from UZGP (and UPGP and LGSP).

### 11.4 Back stopping support

There seems to be a transportation issue concerning the facilitators. The project provides a project car for them, but the vehicle seems to be used by the DDLG only, while the DFs have to use public transport. UZGP has provided a motorbike for its DFs, but this is not the case for UPGP. The MTE received mixed messages about the scale of the problem, but recommends that project management and the LGD discuss this matter and make sure DF mobility is not hampering project implementation. Some UPs are very remote and difficult to access.

### 11.5 Steering arrangements

The program board meetings and SC committees have been operational as outlined by the project designs, although more strategic discussions, e.g. on the overall M&E system, linkages with other programs seems not to be addressed in depth.

### 11.6 UNDP Risk management

The political disturbance that took place for most of 2013, presented a serious challenge for the continued implementation of the projects. The turmoil resulted in disruption of public life, business and development activities and in general reduced the mobility of people hampered a smooth implementation of projects.

As a response to this, the Local Governance (LG) Cluster adopted a three pronged approach to minimize the impact of political impasse on project implementation and monitoring, which included 1) Virtual communication through Skype with project staff, 2) Bi-lateral consultations with DPs and the Government and 3) regular situation reports on project activities from field. Through these measures, the projects were kept going and most activities within the pilot districts could continue, albeit with some changes to the training delivery such as the introduction of e-learning.

In order to strengthen the robustness of the project implementation vis-à-vis reemergence of political turmoil and disruptions, the LG cluster has adopted a risk management strategy with four levels of risks and corresponding management actions (annex).

The MTE has reviewed the abatement actions taken in 2013 and has concluded that the approach adopted by the LG Cluster in consultation with development partners and the government has worked very well despite the political unrest, which also affected the UZP elections and disrupted mobility in the districts and caused delays in the allocation of funds for FY 2013/14, as it was decided not to allocated funds during election time. The initiative to only travel in weekends and conduct training during hartals minimized the impact on project implementation and the introduction of e-learning via skype may even have expedited the introduction of modern distance learning as a supplement to workshops, class room teachings etc.

The risk management strategy also presents a prudent response to future political crisis should they reemerge and it builds on the lessons learned during 2013.

### 11.7 Conclusion

Overall, project management works well despite the obvious challenges a parallel management setup poses for two projects, which also depend on mutual cooperation and shared implementation structures and resources. The most pressing issue right now seems to be the mobility problems associated with the DFs lack of access to project cars. This should urgently be reviewed by the project management before it affects the efficiency and effectiveness of the projects.

# 12. External factors affecting successful implementation and results achievement

The project logical frameworks presented in the respective project documents include a list of risks and assumptions, which remain valid in terms of relevance and risk assessment. The risks and assumptions mainly deal with the GoB backing of the project interventions at implementation level (output 1 and 2) and for new strategic interventions such as the CB framework. The chapter on relevance concluded that there is sufficient backing in the policy and strategic framework of GoB to sustain the relevance of both projects, but it is also quite evident that the context, in which the projects are implemented, remains challenging. Key external factors affecting project implementation are listed below. The risks and challenges they present to project results have been assessed in the previous chapters. Since the projects per design operate at policy level, and have some access to influence these external factors, they may also contribute to the removal of some of them, if they are successfully addressed.

No local government reform framework

Despite attempting to move the strategic agenda on decentralisation forward, both the projects are currently implemented without links to a broader decentralisation strategy and roadmap, which can address some of the external factor listed in this section. Sustainability of results depends to a large extent on the ability to influence the decentralisation agenda through policy advice produced under output 3. This includes activating the PAG and commencing on a national CB framework for all LGIs. Without the latter, the sustainability of training delivery cannot be ensured.

Politicised UZP level

Maintaining a long-term political consensus on decentralisation objectives is perhaps the most crucial precondition for any local government reform, and political consensus is not present at the moment in Bangladesh, at least not to the extent that a broader reform program could be formulated . This affects both projects, and has caused political turmoil in 2013 and a continuously tense political environment, which is not particularly conducive for large-scale reforms

The difficult political situation has affected the UZP level in particular, when the opposition decided to participate in UZP election in 2014. The sequenced execution of elections in five batches also opened the floor for rigging of election outcomes and elections for the reserved seats for female UZP members could not be held at all.

The Upazila Act 2009 assigns an advisory role to MPs in the decision making process of the Upazila Parishad, which to a great extent curtails the decision making power and institutional authority of UPZs and largely undermines the functional authority of any elected local body.

The interference of MPs in the work of UZPs is particularly a problem, where MPs and UZP Chairs are from opposite political parties. The ambiguous and overlapping definition of roles and responsibilities creates a platform for political power struggles between the MPs, UZP chairs and vice chairs, who also shares the same constituencies. MPs also have access to their own constituency fund for investment grants to UZPs. These grants are allocated in parallel to UZP grants; de facto bypassing the UZP planning and budgeting process, although projects are signed off by the UZP. The role of MPs were flagged at the policy dialogue forums and presumably going to addressed in the forthcoming reform discussions.

LD relations to UZPs and UPs

The legal framework for needs to be reviewed in order to examine and assess the roles and relationship between the LD and the Upazila Chair and Vice Chairs, and UPs. As highlighted in previous chapters, there is evidence of parallel LD committee structures (often program-based and ad hoc in nature), which effectively side-lines the elected UZP and UP members and standing committees, and exclude them from access to technical LD backing. The two LG tiers can also become better linked in terms of planning and budgeting. E.g. the block grant coordination committee was established and supported under LGSP-LIC, but this has the UNO as the chair, (which limits the role and information level of the UZP chair and VCs) and is limited mostly to deal with the block grants. There is a need to strengthen the intergovernmental coordination and to strengthen the role of UZPs in the coordination of the linkages.

PFM reforms stalled

At the national level, reform work on PFM has stalled. This also has a bearing on the development of a sound local PFM system, which is another precondition for enhancing the fiscal absorption capacity in LGIs and improve the credibility of LGI budgeting and accounting systems. PFM reform initiatives at national level should link up to subnational government as part of a comprehensive local government reform, which over time devolve functions, staff and funding to LGIs. Currently, both projects are not linked to such a PFM reform initiative, which limits the scope of LGI budget and accounting development.

Limited funding of LGIs

As illustrated in the introductory chapter on the local government system, the fiscal envelope of UPs and UZPs is tight despite the added funding through the PBGS. Limited funding affects the scope of local self-government in general, and is a constraining factor for the attempt to deepen democratic space through the designated governance platforms introduced in the LGI Acts. Without further fiscal decentralisation and discretion of grants allocations, there is a serious risk of undermining the good results achieved through the WS, open budget meetings and the council work per se. The overall funding situation needs to be addressed within a broader LG reform framework that targets all relevant dimensions of devolution in a concerted effort.

UP staffing

It has been pointed out in several studies and by previous project evaluations such as the final LGSP-LIC evaluation, that the serious gap between the number  of staff at UP level and permissive functions (38) outlined in the UP Act, has an adverse impact on how far decentralisation can proceed in terms of broadening the UP role in local governance and service delivery. The heavy work load for UP secretaries was confirmed by the field visits. The UP Secretary is also faced with a lack of career opportunities. In essence, the position is a lifelong assignment, and there is a need to look at improvements, such as promotion opportunities to become Assistant Secretary of the Upzila Parishad. The systemic imbalance between staffing and functions (and funding) cannot be bridged by increased training, district backstopping or reliance on local partnerships. It has to be solved at policy level. The decision to rollout UP accountant cum IT assistants, over the next five years could strengthen the capacity of the UPs, but the prohibitive access threshold puts the position out of reach for most UPs.

Delayed project approvals

Finally, the late approval of the projects has also affected project implementation and shortened the project duration and time available for achieving results. Given the difficult reform aspects of the project interventions and long timespans of local reforms, the loss of valuable time for influencing the overall reform agenda for decentralisation is very unfortunate.

# 13. Partnership and linkages

As noted in the chapter 4, the projects are implemented through multiple linkages and partnerships. The projects themselves are jointly funded and bring together government and important development partners in the support to UPs and UZPs. At present, UZGP unites the only existing support project to the UZP level and UPGP is crucially linked to LGSP 2 as an entity piloting new governance and grants mechanisms, which can be upscaled by LGSP.

During the preparation of the second LGSP and UPGP, an agreement was signed between the World Bank, UNDP and UNCDF about coordination and cooperation between LGSP 2 and the UPGP. The cooperation is based on the principles of complementarity, scalability and simplicity with quality. This agreement has been instrumental in the linkages and cooperation between the two programs, and there have been activities in most areas as envisaged, see below.

Table. UPGP-LGSP 2 cooperation agreement

| Areas of cooperation | Idea | Progress |
| --- | --- | --- |
| Performance-based grants, coordination between the LGSP limited number of performance measures (PMs) and the more elaborated UPGP system with a larger number of PMs | A joint system of one set of indicators has been elaborated whereby the 12 LGSP PMs constitutes a sub-set of the overall system of 41 UPGP PMs, and where the expanded set is used in the 564 UPs in the 7 districts. + common minimum access conditions | Good progress (4) |
| Performance Assessment Manual | Joint PAM between the two programs | Good progress (4). Most recently a work-book has been elaborated to the auditors on how to measure the various indicators, and the feedback is very positive. |
| Training of auditing teams | Joint training of auditing teams | Good progress (4). Joint training supported by UPGP has been appreciated by all and lead to common assessments/audits. |
| Assessments | Jointly between LGSP and UPGP as audit is covering the elaborated number of PMs as well | Good progress (4). Development of joint QA tools and systems and procedures. Still need for more information and dissemination of audit/performance assessment results |
| Manuals | Joint Union Parishad Operational Manual | Good Progress (3-4). A joint OM has been applied with a short annex on the LGSP and the UPGP features. |
| M&E and MIS | MIS developed in joint consultations | Modest progress (2). MIS has been piloted by UPGP, but not yet linked with the LGSP initiatives. However, the LGSP MTR flagged the need for coordination. This is an important future area for coordination to avoid two parallel systems, and the initial stages have been done separately. However, plans are to coordinate more closely in the future. |
| Capacity building | Coordination under the NILG | Some progress (2-3). Operational CB plans are not always fully shared, but the DFs in the seven districts are operated jointly and coordinate at this level. 10 % of the block grant can be used by the UPs, and this is appreciated but more guidance is needed on this. Various training initiatives under the two programs, and lack of an overall CB strategy for the national level. |
| Institutional and policy development at the national level | Sharing of agendas and information etc. | Modest (2). The activities on this area are not strongly coordinated, also as there has been less progress on the policy level and with the establishment of the PAC etc. |
| Program management | Small committee with inter-program coordination and joint participation in SC, if possible a single SC should be established | Some progress (2-3). Separate SCs, but participation of UPGP in the WB discussions, but this is an area, which may be strengthened to ensure a strong “transmission” belt. |

Rating from: 1) weak, 2) modest, 3) some to 4) good progress.

Project implementation also relies on the cooperation with other multiple stakeholders, such as the national training institutions and auditor companies. Further, some synergies are also exploited through the M&E assistance on the gender strategy provided by SDC/Sharique.

During its stakeholder consultations, the MTE has explored the potential for establishing further partnerships and linkages. It is important that project management is not overburdened with new co-operations; however the MTE would like to flag a few areas, where extended cooperation could or should be explored further for synergies and to avoid overlapping support and added costs.

As mentioned in Chapter 10.6, the piloting of the e-based MIS for UPs needs to be upscaled nationwide and LGSP 2 has similar plans for rolling out of an MIS. The MTR aide memoir of LGSP 2 proposes that ”the LGSP 2 MIS consultant review the work supported by UNDP/UNCDF”, but it is important to avoid parallel MIS systems and actually roll out the MIS piloted by UPGP through the LGSP 2, and the cooperation should go beyond “just review”. The WB agrees to this.

On a grander scale, JICA is currently designing a nationwide support program for all UZPs, which builds extensively on the lessons learnt from UZGP, UPGP and LGSP. The upcoming program will be financed through a loan, similar to the LGSP 2, and will be anchored within the LGD. Negotiations on the actual design are still ongoing, but implementation should go forward by March 2015, if an agreement is reached. Compared to the UZGP, the new JICA program called ‘Project for Integrated Development of Upazilas’ will include a Upazila-based facilitator and also anticipates transfer of additional UZP staff. It also includes a performance-based grant system  rather similar to, and based on the experiences from, the UFF. The new program provides a textbook opportunity to upscale the results of the UZGP for nationwide implementation, and should be supported by the UZGP/UPGP.

There is similar need for strengthening of links and cooperation between UPGP/UZGP and other related programs and initiatives, including Danida’s projects in support of local governance and local service delivery; especially on rural road construction with piloting of sector grants and support to HYSAWA on water & sanitation, the support to the GoBs action plan to address violence against women (VAW), and the work of NGOs on governance and transparency issues supported by Danida. Both the supply side programs, where the UPGP and UZGP have a strong focus and the demand side of the programs in support of the NGOs have opportunities for synergies, not yet utilized, and the awareness of the NGOs about the UPGP/UZGP is generally incipient (Danida, Report on Synergies, May 2014).

Similarly, there is room for further exploitation of the linkages between the local level PFM initiatives, promoted by LGSP/UPGP/UZGP, and the central level SPEMP/PFM reform program to ensure that national accounts and information can be consolidated and that the central systems and procedures can be used for effective funding flows in the future with strong levels of accountability. This will also pave the way for strengthening  trust and accountability at the local level and decentralization of funding (if funds can be quickly and robustly accounted for, they are more likely to increase in future).

The support to UPs from the Sharique program has important linkages and potential synergies not yet utilized, as this program is allocating performance-based grants to 207 UPs in the coming years, based on a combination of self-assessment and external verification, which is conducted jointly by the UPs, NGOs and the program. Sharique is providing support on CB especially within PFM, and is linked up with MoF and the newly established training institute for accountancy (IPF). This is another area where strong cooperation with UPGP would be of benefit, since PFM training is planned for in continuation of the MIS implementation. Also within the guidelines on planning, and the coming UPGP innovation on MDG targeting local planning guidelines it is utmost important that UPs are not faced with a series of conflicting regulations and guidelines.

Within the UNDP project portfolio, linkages could be extended to existing and planned governance support. The village court project is already under implementation, and has several bearings on the UPGP support. E.g. the new accounting cum IT staff will also cover secretarial assistance to the village courts and it is important that this staff has a fair work balance and that support projects respect all duties foreseen by the ToR. The training of village court members, especially the UP chair in ADR, is an important synergy area, since it may assist in conflict mediation, where the chair is involved in local disagreements, with or without relations to the village court. The upcoming IRINA project, being piloted in 2015, can also link up to the projects, as it can facilitate dialogues as the local level. E.g. the concept of youth councils could be further explored as a means of engaging young people in local governance.

On piloting of climate change funding to LGIs (supported by UN, EU and in the future also Danida), it is important to ensure strong linkages in areas of performance assessment and grant guidelines and strong synergies between the initiatives.

The SDC thematic backstopping on downward accountability, gender and social inclusion does also suggest that there is an untapped potential for linking WDFs to strategic partnerships or alliances, which builds on shared goals such as ending child marriages or improving birth/death registrations rates. WDFs are still at a formation stage and mostly event-oriented, focusing on seminars and peer learning and community support.

The RTI study (still in draft) proposes that the projects enter into partnership with the RTI Forum and Governance Advocacy Forum (a coalition of NGOs, educational institutions and civil society organizations) in order to support advocacy for increased inclusion of the Dalits, marginalized, poor and disadvantaged people in the beneficiary selection committees and other institutional forums vis-a-vis the UP, UZP, division, district and national level. It is also proposed to engage in peer discussions with organizations like Manusher Jonno Foundation; Democracy watch; Nijera Kori; Research Initiatives Bangladesh (RIB); Sharique; Horizontal Learning Program, DNET and MRDI. on how to use RTI to secure the rights of the Dalits, marginalized, poor and disadvantaged people, initially focusing on the entitlements and services offered by the Ministries of Social welfare, Women and Children Affairs and Education and LGIs like the UZPs and UPs.

These proposals above are not exhaustive, but illustrate the broad potential for linkages and partnerships that can still be explored. Full exploitation of the links to LGSP and JICA, as mentioned above, is considered mandatory to sustain and upscale project results; the key objective and success criteria of the projects. The table below summarizes the potential partnerships and linkages mentioned in this section.

Table. Potential partnerships and linkages

| Linkages | Partners | Focal areas |
| --- | --- | --- |
| UZP support | JICA | Upscaling UZGP results nationwide |
| MIS/PBGS | LGSP 2/successor | Upscaling UPGP results nationwide |
| Strategic planning | Sharique | Training tools |
| PFM | SPEMP | Linking PFM reform and local PFM |
|  | IPF/Ministry of Finance Sharique Other DPs | Curriculum and training in UP budget formation, implementation and procurement |
| Policy studies/ Action research | Sharique | Coordinate study and research portfolio. Almost 100 % overlap in policy study portfolio. |
| Sector funding | Danida (e.g. on road funding and water/sanitation) | Ensure coordination of grant guidelines, planning and budgeting tools, performance indicators and assessments etc. |
| Climate change | EU, Danida, UNDP programs and others | Grant guidelines and planning tools |
| Gender | Sharique, Aparajita | WDF - CB of female councilors |
|  | Danida’s MSPVAW project under the Ministry of Women and Children Affairs, CSOs | UP standing committee for women and children, WDF: Strategic partnerships on VAW, child marriages, birth/death registration etc. |
| RTI | RTI Forum and Governance Advocacy Forum Manusher Jonno Foundation; Democracy watch; Nijera Kori; Research Initiatives Bangladesh (RIB); Sharique; Horizontal Learning Program, DNET and MRDI. Transparency International | Advocacy on inclusion and equal access to social protection program benefits |
| Public engagement | Sharique Danida | Tools for citizens cooperation (council, open budget) anti-corruption, HR |
|  | UNDP programs | Youth councils/innovation camps CSO cooperation |
| Access to justice | UNDP programs, including the village court program | Village courts/ADR/conflict mediation Workload of new accountant/IT support/village court secretary |

### 13.1 Conclusion

The projects are already engaged in many partnerships as per design. Given the scale and scope of all project interventions combined, it is not surprising also, that many other linkages could or should be explored. First and foremost, the important upscale opportunities presented through the cooperation with LGSP 2 and the upcoming UZP project financed through JICA. These linkages need to be prioritized in order to sustain and upscale project results.

The other linkages mentioned here are more optional choices, but each of them entails significant synergies and potential for further increasing the impact of both project interventions. It is recommended that the project managements go through the list and discuss which linkages should be explored further.

# 14. Lessons Learned

This section draws a few general lessons learned from the design and operations of the UPGP and UZPG over the past two years, some of which may also have a wider interest for future project designs and implementations.

M&E

The general recommendation is that log-frame revisions should be approached with care in future projects. While certain updates of the log frames are needed and justified, the timing and management of such changes, especially in projects with many stakeholders and multiple ways of collecting performance data, must be attended to with care. Updates of targets and indicators should be mutually discussed and accomplished no later than during the inception phase of a project and be in place when implementation commences. Once finalized, the log-frames should then be included in updated project documents for ease of reference and transparency and to facilitate coming external reviews and evaluations. All changes also need to be internalized and formalized in various decision-making bodies (including the SC).

The boost in target and indicator numbers experienced here, which has not been fully harmonized in subsequent progress reporting and surveys, illustrates how difficult it can be to strike a balance between a complex log frame and the need to monitor developments in detail on the one hand, and the costs involved and the careful data management and maintenance which is needed to update it on the other. This is an important lesson learned, especially since the projects are promoting good M&E systems and practices in the MIE wing of LGD.

Another emerging lesson, as in many other countries, is that if not probably coordinated in the near future, there will be a multiplicity of reporting systems and MIS operating in the same LGIs, and in LGIs with weak capacity to respond. It is utmost important to ensure a strong coordination, not only information sharing, between these, including between the MIS piloted in Brahmanbaria and the coming second LGSP- MIS, but also with other projects. Poor coordination as the central level in general always has an adverse impact on the work of LGIs.

Control group

Control groups have been applied in the baseline and citizen perception survey, but not in the annual performance assessment systems. It would be useful in the future to include this as well, as originally intended, as this will enable a more robust comparison of impact of the indicators on performance. Fortunately some of the core indicators are tracked in the baselines and CPS, but these – as mentioned above – did not reflect the situation from the start of the project, i.e. 2011.

Links between capacity building, funding and incentives

The field research and secondary data confirm the important lessons experienced in other countries as well, of ensuring the linkages between CB, funding and incentives. CB alone will not provide sufficient incentives for people to be involved, and planning without sufficient funding, may over time erode the interest and meaning for citizens and officials involved. These lessons are also generated from other evaluations around the world, and the funds allocated in Bangladesh, also considering the functional assignments of the LGIs, are comparably modest. On one hand, the project has transferred limited capital funds (per capita), and it is thereby easier to learn from the system and ensure future up-scaling. On the other hand, the MTE has pointed at the problem with lack of funding (block grants is below 1 % of the total public budget), and the need to expand the room for LGI discretionary funding and decision-making to ensure that the full benefits from support to systems, procedures and CB are reaped. Future programs should factor this into the design as well as strengthen the advocacy during the policy dialogue for revenue sharing and increase in allocations for local level investments.

Capacity development

Lessons learned from CB show that a flexible approach using various modalities for CB support achieve most impact and are more cost-effective. Such modalities include support to training, technical assistance, equipment, institutional support, individual and institutional performance incentives, etc. The projects have utilized various means, but needs to strengthen the support – in future – in terms of the LGI institutional framework and the overall strategic framework for CB, especially to strengthen coordination amongst the multiple and often overlapping interventions. Some countries have to various degrees worked on such CB frameworks, e.g. Bhutan and Uganda, and the lessons are that this is indeed needed and useful, but also challenging and that longer-term interventions, plus coordination across projects/programs, will be needed. Most of all, strong government ownership to such a framework is essential, also to secure sufficient funding and to embed the framework within broader LG reform initiatives.

Participation, accountability, transparency

The project has made remarkable achievements within these areas, but could strengthen its focus in the remaining period on wider publication of APA results and promotion of new means for downwards accountability; especially through the linkages between LGI and the NGOs/CBOs. New and innovative means of accountability such as social audit, more web-paged solutions for information sharing, etc. could be explored as well. The challenge of communicating APA results to LGI and the electorates is common in most countries, which underline the need for a strict communication discipline when publishing APA results reports.

MDG targeting

The project has been successful in changing the mindsets and priorities of the LGIs to focus not only on hard-core infrastructure, especially roads, but also on the MDGs and activities within education, health, water and sanitation etc. This can be achieved through soft incentives in the PBGS, awareness raising and CB and the combination of CB and PBGS creates synergies and stronger impact than using CB and grants allocations as separate support modalities. Of course, there is also a limit to this, as some LGIs have needs for investments in areas benefitting local economic development such as roads, markets etc. Hence, the instrument has been useful, but should be implemented in a balanced manner, leaving sufficient discretion at the LGI level.

Improved planning

The projects have taken important steps to improve the planning documents (annual plans, budgets, plan-books and FYPs) and procedures for planning, although there is room for improvements in both areas. The experiences have shown the importance of having clear, simple planning guidelines, supported by grant guidelines with a clearly defined investments menu (eligible investments), combined with guidance, support and incentives. The work on this, especially the MDG guidelines should be expedited, if the full potential of this support should be realized in the remaining period. Second, it is important to advocate for increased funding for UZP and UP operations, both revenue sharing and transfers, to ensure that there is a meaningful relationship between system, procedures and practices for participation, level of efforts and means at hand for implementation of priorities.

PFM

The central government PFM program has been delayed and problematic (e.g. under the SPEMP), and has not been linked with the local level initiatives under e.g. UPGP, UZGP and the second LGSP. However international experiences show the importance of including LGIs in these emerging PFM reforms, with clear linkages between central and local budgeting and accounting systems to be able to get consolidated national accounts, full accountability for fund allocation etc. and to build trust in the LGI system for service delivery and fund management.

PPP

There is some confusion at the field level on the concepts of LED, PPP and investments from block grant schemes. It is important to clarify that although block grant investments can promote LED, it should not be used for any investments for the benefit of individuals or smaller groups of private persons, farmers etc. PPP is suitable for other types of program, which has another set of controls and checks and balances. The experiences from other countries have been that projects like UPGP and UZGP should be cautious, as public investments can easily be fragmented, and diluted, and used – in the “spirit of good development” – on issues, which are better handled through other modalities, such as micro-credit schemes and revolving funds, and outside of the LGI system. LGIs should focus on creation of a conducive environment for the private sector, including access (infrastructure, suitable location), markets, facilities, knowledge, fast-tracking of permits etc. rather than investing directly in these.

Linkages

The lessons learned from the link between LGSP and UPGP have been useful and reduced the transaction costs for the UPs involved. However, there are other initiatives at the project level, which needs to be better linked and harmonized, such as transfer scheme to LGIs under sector funding programs, area-based programs and support to NGOs, CBOs etc.

# 15. Looking beyond 2016

Apart from conducting the midterm evaluation, the MTE team was also requested to provide brief inputs to the discussion on potential support areas, after the projects terminate in 2016. There is good reason for this, since key development partners have already started formulation of new support programs planned for implementation in 2015 and 2016. Given their long background in support to decentralization in Bangladesh, UNDP and UNCDF are in a unique strategic position to lead and coordinate future joint support to decentralization. It is therefore important for the organizations to link up to ongoing or imminent program formulations among likeminded development partners, such as Danida, which has just started planning its new country programme.

Looking beyond project termination in 2016, it is evident that there will still be a need for international support to LGIs and reforming of the subnational government system. Even if a LGSP 3 and the upcoming JICA-support to UZPs move ahead and successfully roll out UPGP and UZGP results, they cannot stand alone. Local government reforms take time and the need for support to policy development and ”systemic” improvements such as the implementation of a national CB framework or an enhanced local fiscal framework remains, notwithstanding successful policy support for the remainder of the project duration. The WB and JICA support is also based on loans, not grants, and most likely there will be a need to push for new innovations on the ground, e.g. through another “LIC” project linked to LGSP and the JICA project. These arguments alone fully justify another joint UN-led LGI support program from 2016.

Based on discussions with stakeholders and the outcome of the MTE, a few guiding considerations and recommendations for future programming are listed below:

Moving from project to program approach

An attempt was made in the design of the UPGP and UZPG to link these two through a programmatic framework, but due to issues on funding, timing, risks assessments, etc. it was decided to move ahead with two separate projects; each with their own SC and set-up; but with some joint support elements and staff under a programmatic pillar.

Although the projects are jointly funded, the assessment presented of external factors and potential linkages and partnerships is a reminder that much more could be done in terms of addressing key dimensions of a local government reform in a more programmatic manner, bringing together relevant ministries and harmonizing international support to decentralization and local governance. The extent to which a more programmatic approach can move forward ultimately depends on the ability of the Government of Bangladesh to formulate a comprehensive strategy and roadmap for decentralization. Without such a strategic framework, support to decentralization would probably continue to focus on more incremental (project-based) improvements.

Other developing countries have successfully established a programmatic framework for decentralization in close coordination with development partners. E. g in Uganda, where reform interventions are embedded in a common programmatic framework and cooperation between the Ministry of Local Government, the Ministry of Finance, the LMs and development partners. Development partners contribute to the reform through various support projects and all efforts are monitored within a common Joint Assessment Framework (JAF). JAF is updated by ”joint annual reviews of decentralization”, providing input to the common AWPs. Through this programmatic framework, Uganda attempts to steer its devolution agenda within governance, finance and the sectors in a concerted manner, which also includes a comprehensive PBGS with sector grant and capacity development grant support. Similar experience can be found in other countries such as Ghana, Tanzania, Nepal and Bhutan.

If the policy advice extended from the projects results in a demand for a more comprehensive policy to decentralize in Bangladesh, future support could become embedded in a more programmatic support to LGIs, which also links to other relevant ministries. Such a programmatic framework should be elaborated in a manner whereby each development partner can focus its support on specific elements (projects) but within a joint support program aligned to the government strategy. Part of the international support could even focus on designing a reform strategy, based a. o. on the outcomes of the policy studies.

Such a support program should have joint overall coordination/monitoring arrangement - if possible linked to the new (informal) inter-ministerial committee on LGI issues under the Cabinet Secretary-, and joint annual reviews as input to AWPs rather than multiple reporting and reviews.

Geographical focus areas

As UPGP and UZPG are piloting new innovative means, it was important to ensure that a sample of both stronger and weaker LGIs were included in the coverage areas. However, there are good reasons for a future program to focus more on the weaker LGIs in terms of management capacity, funding capacity and actual performance. As the MTE has shown there are “pockets” of persistently low development and poverty where general support programs have difficulties in targeting and impacting.

A study should therefore be conducted during the remaining project period to identify these areas, based on issues such as poverty, MDG targeting, performance results in the APAs, etc. It is already clear from the APAs in the LGSP and UPGP that some of the UPs have not been able to improve performance, and analytical work to determine the reasons for this should be ready for support in the new program, or even – if possible - with some upstart activities in the ongoing support, in terms of “fire brigade” support, TA, institutional support, etc. where performance is not improving despite the incentives, and the CB support rendered through the current aid modalities. Some of the weaker UPs and UZPs need substantial “hands on” support to change the working environment. The new decision to improve staffing of the UPs with an accountant/cum IT operator will focus on the larger UPs, but it is important also to ensure that smaller and weaker UPs - and problematic UZPs - get up and running to be able to enhance the generic CB support and incentives in the performance-based grant system.

The study will identify reasons for this non-performance, and will then fit into a strong targeting of the efforts in the subsequent program, linking it with a strong poverty targeting and review of MDG achievements, as well as other LGI vulnerabilities. The support will still be performance-based and with strong incentives to improve, but will focus especially on the areas, which are “left behind/do not catch the train” in terms of development and performance enhancements.

The future program from 2016 should therefore entail support to weaker UPs, e.g. in form of a kind of a (performance-based) grant equalization system or funding to vulnerable areas; backstopping support etc. and review and studies of the challenges for persistently poorly performing UPs and mitigating measures.

In a situation with increasing urbanization of the society and establishment of new urban LGIs , another focus area could be to provide support to the transition stage and emerging challenges in these suburban areas, when they move from rural to urban status.

Finally, at the Upazila level it is expected that the coming JICA support program will roll out UFF-like modalities for grants, and a new joint program could focus on specific support to weaker areas and to institutional and organizational reforms, especially linkages between main actors of importance for good governance, and closer involvement of sector issues and linkages.

Funding modalities and support

The general cross-cutting PBGS has proved its efficiency and operations, and efforts should be made in the remaining period to fix the smaller challenges and to ensure transmission of good lessons learned into the general block grant system, including future LGSP design work and the overall intergovernmental fiscal framework with closer interactions with both MLGRD&C, LGD and MoF.

In the coming phase, opportunities for moving the good experiences from block grant funding into innovations on sector funding, could be explored as well as opportunities - as mentioned above - to ensure that vulnerable areas are not lost in terms of reaping the proceed from development.

Thematic areas

The coming program could focus on a continuation of the work on core LGI operations, governance, downwards accountability, PFM etc., but combine this with stronger mainstreaming of cross-cutting interventions such as human rights, local economic development, and climate change issues in local governance (climate change through a separate focused but linked project in the programmatic framework), planning and service delivery.

The program could also have a stronger focus and element of core structural and institutional PFM reforms at the LGI level and linkages of this with the central government reform program, in terms of planning, budgeting, accounting and report, as well as the MIS system development.

Finally, the program, in addition to CB support, should focus on more institutional challenges and bottlenecks such as relationship between various actors at the UZP level (MPs, LD, UZP, civil society), and at the UP level (sectors, UPs, civil society), to ensure strong linkages vertically and horizontal from planning to implementation.

The work on the policy issues should be stronger linked with the intra-governmental discussions at the central level and will have an important role in the program as well, and be based on evidence and research of the achievements and challenges.

CB is an important intervention area in its own right. Given that a national framework emerges before 2016, there will be a lot of work to implement the framework and combine and introduce different modalities, practices and funding mechanisms.

# 16. Overall conclusion and recommendations

The overall conclusion of the MTE is that both projects have retained their relevance vis-à-vis the new UNDAF 2012-2016 and the GoB policy on LGIs. The MTE also noted that the concept paper for the upcoming 7th Five-Year Plan (7FYP) reiterates a commitment to work towards stronger LGIs and recognizes that the reform agenda is ”unfinished”.

Despite delays, political turmoil for most of 2013 and a foreshortened implementation time, both UPGP and UZGP maintain good progress and are likely to achieve most of their objectives by 2016. Based on the extended field research, and key secondary data such as the APAs, the baseline surveys and the CPS, the MTE also concludes, that the projects provide important value additions to the development of the UP and UZP tier, which is strongly documented by significant improvements in core functional areas in the target districts compared to baselines and developments in non-covered districts. Equally important, support extended to the UZP level has contributed to sustaining this government tier at a difficult time, when it was re-established and faced with political power struggles. It has also had a significant impact on emerging UZP operations and linkages to the LDs.

Both projects have improved transparency, accountability and participation in LGIs, especially at UP level, and there is credible documentation of improved pro-poor, gender friendly planning and MDG service delivery in project areas, compared to control groups not receiving support from UPGP and UZGP, respectively. The projects have improved women’s participation in local government through the rollout of WDFs and CB support to female leaders, and the overall picture from the field is that beneficiaries and citizens in general express their appreciation of the support rendered by the projects.

Both projects have also piloted an enhanced performance-based grant system, which have become important catalysts for the achievement of project objectives within local governance, pro-poor development planning, MDG targeted service delivery, and increased OSR mobilization. The performance elements are highly appreciated by the LGIs and have instilled a stronger awareness on good governance and internal competition. As per design, they have also contributed to the identification of capacity gaps, which can be fed back into the CB activities of the projects and highlight systemic malfunctions, which needs to be addressed at the policy level.

It is also very important to note, that both projects currently have unique upscale opportunities, which, if addressed successfully, could improve the sustainability of project innovations considerably and promote countrywide rollout of results. The MIS and the PBGS promoted by UPGP, can be upscaled through LGSP 2 and its successor, respectively, while the UZGP results, including the PBGS, are likely to be upscaled through the upcoming JICA funded ”Integrated Development Project for Upazilas” covering the whole country.

It is within the more policy-oriented areas, rather than the applied project approaches in the pilot districts, where the projects are facing most challenges and there is need for special attention. Most of the constraining factors affecting the implementation, relates to systemic issues such as ambiguous division of roles and responsibilities and parallel management structures between the political and executive branches and tiers of government. The UZP level, in particular, is prone to partisan conflicts and needs further governance reforms in order to emerge as a strong tier of local government. The UPs on the other hand are faced with fundamental capacity constraints vis-à-vis their mandate, and there is a serious risk that democratic gains achieved through innovations such as ward shavas and open budget meetings are not sufficiently matched by the limited funding available for community development. Participatory exercises without proper means is a classic way of demotivating citizens, and public engagement in local government runs a risk of being eroded, if funding is not increased over time.

It is none the less also within the objectives of the projects to address such shortcomings and to advice on how the system can be strengthened in line with internationally recognized local self-government principles such as the ”International Guidelines on Decentralization and Access to Basic Services for All” (UN Habitat, 2009) or the ”European Charter of Local Self-Government” (Council of Europe, 1985). The projects support a number of policy studies, which may provide further input to LGI reforms and the lessons learned from project implementation and the policy dialogues forums conducted throughout Bangladesh may also provide valuable input to new reform initiatives.

The table below sums up the MTE recommendations on where the projects and LGD, respectively, should focus their attention in order to address implementation shortcomings and improve overall performance and sustainability of results during the remaining time of the projects. Based on discussions in the Steering Committee meetings, a joint action plan should be drafted for quick implementation.

Table. MTE Recommendations

| # | Recommendations |
| --- | --- |
|  | UPGP Management |
| 1 | The annual performance assessments should be advanced to fit with the UP planning and budgeting process |
| 2 | The performance assessment results should be widely shared, disseminated, compared and followed-up |
| 3 | The training of the auditors should continue and the LGIs should perform internal self-assessments prior to the external audit/assessments |
| 4 | The system of comparing performance assessments with non-covered areas should be strengthened; if possible by introducing assessments of an external UP control group not supported by UPGP, as per the project design. Alternatively, follow-up through the Citizens Perception Survey combined with reviews of performance should be continued |
|  | UZGP Management |
| 5 | The performance assessment process should be accelerated to ensure that it fits with the UZP annual planning and budgeting cycle (results should be ready before the planning process starts) |
| 6 | The performance assessment results must be communicated in full detail to the LGIs and their citizens to ensure maximum transparency, accountability and incentives |
| 7 | The performance assessments should continue to be conducted by external, neutral teams of assessors/auditors as per the UPGP/LGSP and the first rounds of assessments under the UZGP. The principle that assessors involved in CB support cannot at the same time do the assessments of the same UZPs should be maintained |
| 8 | The internal performance assessments by UZP, conducted in 2013 prior to the external assessments, should be reintroduced to ensure that LGIs are well prepared and aware, when the external assessments are launched. This will serve as a strong internal learning tool and also supports the external assessment |
| 9 | The system of QA of the performance results, decision-making and appeal should be formalized, as per the lessons learned from the UPGP/LGSP |
| 10 | The information and internalization of the investment menu should be strengthened to enhance a strict focus on public services (i.e. avoid the area of private investments) and to uphold the multi-sectorial discretionary objectives of the grant system. |
| 11 | Advocate for improvement of the ADP grant system and related guidelines to ensure that lessons learned from the piloting of UFF is impacting on review and up-date of the ADP grant guidelines |
| 12 | Strong linkages between the MIS and the annual performance assessments and the subsequent CB support should be supported by the project for learning and enhancing synergies (jointly with UPGP) |
| 13 | The planned support to the MIE Wing of LGD should be revisited. It should be considered to base a project M&E officer in LGD for a few months to ensure a comprehensive transfer of the project M&E/MIS system for national upscale. Furthermore, the links with the planned MIS development under LGSP should be intensified (jointly with UPGP) |
| 14 | The linkage between the external performance assessment system and the M&E system under the MIE Wing of LGD should be strengthened in terms of reviewing the indicators applied by the MIE Wing, monitoring etc. to ensure that APA results are applied in the monitoring and follow up by LGD (jointly with UPGP) |
|  | LGD policy making |
| 15 | The number of UP and UZP standing committees should be considered reduced. The current numbers are high and imply too many meetings for the elected members. |
| 16 | The parallel committee structures at both UP and UZP level and the advisory role of MPs need to be addressed. The current roles and responsibilities of UPs and UZPs get mixed up and diminished by the current mandates of MPs, UNOs, and LMs and should be revisited in order to fully empower the LGIs in line with international principles of local self-government |
| 17 | The WDF mandate should be clarified vis-à-vis its original objective of establishing a platform for mobilization of female UP members voice in UP and UZP council work. It is important to prevent a drift towards community work at the expense of the council work and the creation of parallel funding and implementation structures for LGI service delivery |
| 18 | The total LGI funding envelope should be increased, discretionary aspects of funds utilization strengthened and ex-post legal and financial audits applied in line with international principles of local self-government |
| 19 | The OSR-threshold for access to UP accountant assistants is too high at almost twice the size of the average UP annual OSR. The threshold should be abolished and more attention aimed at improving the UP resource envelope and the intergovernmental fiscal transfer system per se |
| 20 | Options to introduce a more poverty focused allocation formula in the future UP grant system should be reviewed, based on available data and proxies and without reducing the performance incentives |
| 21 | The UZP grant allocation formula should be reviewed, especially the poverty targeting of the grants and the use of indexes to ensure that poverty indexes are weighted with the size of the UZPs |
| 22 | Options for rolling out grant modalities for multi-sectorial support with complementing sector funding/thematic schemes (e.g. in roads, water/sanitation etc.) should be reviewed |
| 23 | The PAG should be activated and representatives from academia, local government and civil society should be added as PAG members |
| 24 | The PAG should link its advisory work to the inter-ministerial group on local government and the Local Consultative (Sub- Group) on Local Governance |
| 25 | The work on the national CB framework should commence immediately in order to sustain training delivery of UPGP, UZGP and similar project support to LGIs. To speed up the work and make it operational, a phase-wise approach should be considered, starting with the UZP-level. |
| 26 | The policy studies should be supplemented with more action research on challenges and best practice experiences from the project interventions within governance, finance, gender and CB. This should include analytical work on why some UPs are persistently poor performing and not improving, and development of a strategy to mitigate this particular challenge. Action research on challenges and best practices may also inform upscale opportunities and strategic interventions for a new project phase |
|  | Project Linkages & Partnerships |
| 27 | The transmission belt from the UPGP supported expanded performance-based grants to the LGSP 2 should be strengthened, especially for preparation of the LGSP 2 successor (indicators, scoring system, integration of the performance in the allocation formula etc.) which may start soon (UPGP) |
| 28 | The upcoming ”UZP integrated support project” to be (loan) financed by JICA, is a unique opportunity to upscale UZGP innovations on CB and performance-based grants nationwide, and should be supported by the UZGP. It may also open up an opportunity to define a UNDP ”LIC project” for UZPs, which can innovate new governance and financing mechanisms (UZGP) |
| 29 | In order to enhance training of female councilors and to strengthen the WDF platform, strong cooperation with Sharique and various NGOs supported by the development partners behind UPGP and UZGP, should be established to enhance common learning and synergies in training of local female leaders. (UPGP/UZGP) |
| 30 | It is recommended that the projects support advocacy initiatives by the RTI Forum and likeminded NGOs for improving poor and vulnerable groups entitlements and better access to social protection programs (UPGP/UZGP) |
|  | Project Management & Budgeting |
| 31 | The last installment of grants should be transferred to the LGIs by December 2015, which will require speeding up the APAs to allow LGIs sufficient time to spend funds within the remaining project period |
| 32 | A review of the budget to encompass the recommended initiatives above will have to take place and be incorporated in the AWP for 2015 |
| 33 | The mobility of the DFs should be reviewed. Feedback from the field suggests that DFs do not get access to the project cars |

# Annex 1. Terms of Reference

Terms of Reference for Mid-term Evaluation

Union Parishad Governance Project

Upazila Governance Project

The Term of Reference has been designed to conduct the Mid-term Evaluation for both Upazila Governance Project and Union Parishad Governance project as part of UNDP’s decentralized evaluation process. This MTE should provide the basis for learning and accountability for programme managers and stakeholders. It will have to provide convincing evidence to support its findings/ratings. Particular emphasis should be put on the project results attained thus far, the lessons learned from the projects and recommendations for the follow-up activities.

- Background and context

Local Governance and Decentralization Programme for Union Parishad and Upazila Parishad is part of the overall Programmatic Framework for UNDP and UNCDF support to the Government of Bangladesh in Local Governance reforms, assisted by the European Union and the Governments of Denmark and Switzerland. The two components of the Programme - UPGP (Union Parishad Governance Project) and UZGP (Upazila Governance Project) - are based on successes and lessons learned from the previously implemented projects - Sirajganj Local Government Development Fund Project (SLGDFP) piloted in 2000-2006, Local Government Support Project Learning and Innovation Component (LGSP-LIC) in 2007-2012 and Preparatory Assistance to Upazila Parishads (UZP) in 2009-2011. Upazila Parishad Governance Project (UZGP) is a five-year (August 2011- July 2016) project with an estimated budget of 19.3 million dollar. On the other hand, Union Parishad Governance Project (UPGP) is a five-year (Dec 2011- Nov 2016) project with an estimated budget of 18.3 million dollar

Union Parishad (UP) is an elected local government institution, responsible for providing various services to citizen and coordinating many aspects of local rural development in Bangladesh. The Union Parishad Act 2009 introduced new dimensions in the operations of UPs, which include a citizen participation platform (Ward Shava), provisions to implement Citizen Charters, provisions to implement Right to Information Act, use of information technology and deployment of additional staff from different line departments. These new dimensions have the potential to significantly enhance the role and impact of UPs on development. UPGP complements LGSP II (Local Governance Support Project) in addressing fiscal issues of UP and, simultaneously, strengthening their democratic accountability and governance.

Upazila Parishads (UZP), being the middle tier of local government, occupies a very strategic position in the country’s governance system. The re-establishment of the Upazila Parishads (UZP) in 2009, after a gap of 18 years, created democratically elected institutions at sub-national level that act as structural linkages between Union Parishads (UP) and service-delivery line agencies at Upazila level. The Upazila Act amended in 2009 and 2011 empowered Upazila Parishads to play a major role in the process of promoting local democracy and management and delivery of basic social services.

After the elections of 481 Upazilas, strengthening of institutional capacities of the newly elected leadership of UZP and Upazila Parishad members/UP Chairmen, in related rules, regulations, and processes to ensure effective functioning of UZP, became a priority.

Although there exists a favourable national policy environment on local governance (UP Act 2009, UZP Act 2009), local government institutions are facing a number of challenges that hamper their effective performance. The challenges include lack of fiscal resources, lack of appropriate planning to utilize the scarce resources, lack of staff, holistic, strategic and targeted use of resources to address local level development, and poor coordination between Upazila Parishads (councils) and the local offices of line Ministries, etc.

UPGP and UZGP were positioned to assist the Government of Bangladesh in implementation of the local governance reforms and to contribute in redressal of landscape of challenges. Both projects are designed to improve functional and institutional capacities of local government institutions for effective, efficient and accountable delivery of pro-poor infrastructure and services.

The UZGP and UPGP are Nationally Implemented Projects (NIM), in accordance with the National Implementation Manual, adopted in December 2004 by the Economic Relations Division (ERD), Ministry of Finance and UNDP. Following an identical implementation modality both UZGP and UPGP projects have independent structure as elaborated below:

The National Project Director (NPD), the Additional Secretary of LGD, leads the project. The NPD is assisted by the Joint Secretary who is the project’s Focal Person from the LGD and by the National Project Manager provided by UNDP.

The Project Steering Committee (PSC) is chaired by the Secretary, LGD, and serves as strategic guidance provider and oversight body for the project. The PSC is the key decision-making body for UPGP and the UZGP. The PSC provides policy guidelines, reviews all aspects of the project progress against targeted results, including examination of lessons learned and service delivery and ensures coordination with other national initiatives and development projects. The PSC members include representatives from relevant ministries and departments of the Government of Bangladesh and respective development partners.

The Project Board (PB), chaired by the NPD, is responsible to oversee the implementation of project activities. The PB is responsible for preparing and endorsing the annual and quarterly work plans and progress reports. It supervises the overall project implementation and day-to-day management of the project. There are two PBs (UZGP and UPGP) comprising representatives from UP and UZP, UNDP and UNCDF. In UZGP the PB also include UNOs.

The Project Assurance (PA) role is vested upon UNDP and UNCDF. UNDP Local Governance Head of Cluster has the overall responsibility for quality assurance for UNDP related activities. UNCDF Regional Office has the overall responsibility for quality assurance for UNCDF related activities. The two POs for both agencies are to ensure that the projects deliver planned outputs as per the annual work plan, project documents and results on the basis of monthly, quarterly, and annual progress reports.

Seven Districts have been designated as project area for the UPGP and UZGP in consultation with the Government. They are - Barguna, Brahmanbaria, Kishorganj, Khulna, Rangpur, Sirajganj and Sunamganj. This selection was based on four criteria i.e.

(a) proportion of population below the upper poverty line and with different levels of capacity;

(b) two districts formerly covered by LGSP-LIC;

(c) one district covered by MDG localization pilot project;

(d) and one district supported through SHARIQUE project funded by SDC.

Under the selected 7 Districts, 65 Upazila and Upazilla Parishads are the target for UZGP and consequently 564 Union and Union Parishads falling under 65 Upazilla are targeted by the UPGP.

The two projects targeted outreach is as follows:

| Output | UPGP target coverage | UZGP target coverage |
| --- | --- | --- |
| Output 1: capacity building | 564 Union Parishads (UP) | 481 Upazila Parishads (UZP) |
| Output 2: Fiscal Facility | 400 UP / year | 14 UZP / year |
| Output 3: Policy Research | Nationwide and shared output between the 2 projects |  |

The UPGP and UZGP results are similar, but envisaged to be achieved at different levels – i.e. at the Upazila level and the Union Parishad level respectively. The third expected result in both projects - UPGP and UZGP - is shared.

| UPGP Results |  | UZGP Results |
| --- | --- | --- |
| - Strengthened Democratic Accountability of the Union Parishads though Citizen Engagement |  | - Strengthened Upazila Parishads as more functional, transparent and accountable institutions; |
| - Innovations in Pro-Poor and MDG-Oriented Planning and Financing of Service Delivery by Union Parishads |  | - Strengthened Planning and Budgetary system at UZP with MDG orientation and pro-poor service delivery mechanism; |
| - Strengthened national capacity for effective policy review, monitoring, lesson learning and capacity development of local government institutions (LGIs) for enhanced Local Governance. |  |  |

2. Evaluation purpose and timing:

The purpose of the Mid-Term Evaluation of the UPGP and UZGP in Bangladesh is to:

- Assess the performance of the UPGP and UZGP since their commencement in 2011 to date against the outcome and outputs on the basis of indicators as set out in the Results Framework

- Assess the performance of the UPGP and UZGP against UNDAF outcome specified for local governance

- Draw lessons learned and to make recommendations to assist further improvement in the implementation of the programme over the remainder of its term and way forward for future intervention

The primary audience for this evaluation is the Local Government Division, Development Partners, UNDP, UNCDF and all concerned stakeholders including Union and Upazila parishads. The evaluation will be carried out by independent consultants under the direct supervision of UNDP and UNCDF in close coordination with Local Government Division.

The mid-term evaluation is scheduled to start in September until December with the proposed timing:

| Phase | Duration | Proposed time |
| --- | --- | --- |
| Desk review | One week | Within 10 – 20 September 2014 |
| Inception and Mission in Dhaka | Two weeks | Within 21 September – 15 October 2014 |
| Field visits | Two weeks | 16 – 31 October 2014 |
| Debriefing, draft report | Two weeks | Within 1 – 30 November 2014 |
| Report finalization | Two weeks | Within 1 – 15 December 2014 |

4. Evaluation scope and objectives:

The objectives of this Mid-Term Evaluation (MTE) are:

- To assess the relevance, effectiveness, efficiency, sustainability and likely impact of the projects drawn from its design and implementation in the context of Bangladesh

- To assess the stakeholders’ and beneficiaries’ level of satisfaction with the programme’s results so far

- To assess the extent to which the application of the rights-based approach and gender-mainstreaming are sought

- To make recommendations for adjustments in terms of programmatic approach and resource allocation in the remaining months of project implementation (December 2014 to November 2016)

- To assess whether the projects have fully utilized the success and lessons learned from the previously implemented/piloted projects, namely Sirajganj Local Government Development Fund Project (SLGDFP) piloted in 2000-2006, Local Government Support Project Learning and Innovation Component (LGSP-LIC) in 2007-2012 and Preparatory Assistance to Upazila Parishads (UZP) in 2009-2011.

- To draw the positive and negative, and foreseen and unforeseen, changes and effects driven by project-supported interventions.

- To draw lessons learned and good practices for replication and/or up-scaling and provide forward looking recommendations for next programming phase.

The MTE will examine in particular results at the outputs level with a focus on overall implementation process and progress towards project targets at the time of the mid-term evaluation, covering the period from the project launch. This includes a review of allocated resources for the spent/planned outputs and an identification of implementation issues at the activity level to pin down any alarming barriers and bottlenecks and come up recommendations. This will also cover the re-assurance of results chain envisaged in the project document towards achieving the overall objectives. Taking into account the Output 3 of the both projects that aim strengthened national capacity on policy review and monitoring, the MTE will need to review alignment with the government national policies as well as its current capacity on policy review and monitoring.

While the geographic coverage of both projects are spread in the selected seven districts, the MTE will cover all the districts for desk review and attempt to cover as many district as possible if not all for field visits given the budgetary and time constraints of the MTE. The location of field visits will be consulted and agreed among the Evaluation Team and Local Governance Cluster. The MTE will include all the relevant stakeholders for assessment but incorporate in particular a gender equity perspective and human right approach.

4. Implementation arrangements

The Local Governance Cluster in the Country Office will be in charge of the overall management of the Mid-term Evaluation with technical guidance from the Results and Resource Management Cluster (RRMC). The Evaluation Team led by the international team leader will be closely working with the Project Management Team of UPGP and UZGP and seek guidance from Programme Analyst in the Local Governance Cluster who coordinates the whole evaluation process in consultation with UNCDF Programme Analyst who are responsible for the project assurance. They will be responsible for arranging all types of meetings and field visits. The RRMC will be working as an oversight body and will be responsible for ensuring the quality of the evaluation in line with the UNEG Evaluation principles.

5. Evaluation questions:

The evaluation should cover the following aspects:

a) Overall Results Achievement at the mid-term stage

- Has the programme made satisfactory progress in terms of achievement of overall results (as per RRF/logframe) of “Strengthened capacities of local governments and other stakeholders to foster participatory local development service delivery for the MDGs”?

b) Results achievement at the output and outcome level

- Has the programme made satisfactory progress in terms of achievement of programme outputs (as per RRF/logframe indicators and annual work plan targets) and related delivery of inputs and activities?

- How effectively and efficiently have results been achieved, and to what level of quality? (analysed by output)

c) Factors affecting successful implementation and results achievement

- Were programme implementation and results achieved according to plan, or were there any obstacles/bottlenecks/issues on the UNDP/UNCDF/Government/programme partner side that limited the successful implementation and results achievement of the programme?

- What are the success factors to keep for the future phase and how can shortcoming be factored in to be prevented in the future?

d) External Factors:

- Has the policy environment had consequences for programme performance?

- To what extent does the broader policy environment remain conducive to the replication of the lessons learnt from the pilot programme?

- Are there any other factors external to the programme that have affected successful implementation and results achievement, and prospects for policy impact and replication?

- How could the identified positive or negative external factors be mitigated or exploited further for the next programme phase?

e) Programme-related Factors:

Programme design (relevance and quality):

- Was the programme logic, design and strategy optimal to achieve the desired programme objectives/outputs, given the national/local context and the needs to be addressed?

- Clarity and consistency of the design and results framework

- Adequacy of resources allocated and management arrangements;

- Adequacy and usefulness of the baseline;

- Were relevant gender issues adequately addressed in programme design?

- Is the programme rooted in and effectively integrated with national strategies (e.g. Five year plan) and UN planning and results frameworks (UNDAF, CPD etc.) at country level?

- Have the programme’s objectives remained valid and relevant? Has any progress in achieving these objectives added significant value?

- What lessons from the programme design could be retained for the next programme phase?

Institutional and implementation arrangements:

- Were the programme’s institutional and implementation arrangements appropriate, effective and efficient for the successful achievement of the programme’s objectives?

- Where there any institutional obstacles hindering the implementation/operations of the programme?

- What lessons from the institutional and implementation arrangements could be retained for the future interventions?

Programme management:

    - Were the management arrangements for the programme adequate and appropriate?

    - How effectively has the programme been managed at all levels?

    - Is programme management results-based and innovative?

    - Has financial management been sound?

    - Have the programme’s management systems, including M&E, reporting and financial systems functioned as effective management tools, and facilitated effective implementation of the programme?

    - Have the programme’s logical framework, performance indicators, baseline data and monitoring systems provided a sufficient and efficient basis for monitoring and evaluating programme performance? Has the M&E system supported effective programme management, corporate decision-making and learning?

    - What lessons from the programme management arrangements should be considered for the next programme phase?

f) Future phase of joint programming

    - What are findings and lessons from the mid-term evaluation of the current programme that should influence any decision on a future intervention for UNDP and UNCDF and its partners?

    - Analyse and comment on any emerging vision, strategy and measures proposed for the planned next phase of programming or, if appropriate, disengaging or continuing UNDP and UNCDF’s local governance programming in the country.

    - What are the remaining challenges and gaps in the area of decentralization in the country? How are various actors positioned to address these? Is there a conducive environment for further progress on decentralization?

    - Do the envisaged overall objectives and results of the next phase of programme seem adequate and relevant in light of the UPGP and UZGP MTE findings?

    - Have key factors (external, programme or partnership related) changed, with respect to those existing at the time of the UPGP and UGZP design, in a way that needs to be taken into consideration for the next phase?

6. Methodology:

Standard Evaluation approach will be used for this mid-term evaluation. In accomplishing the aforementioned tasks, the evaluation team will adopt both quantitative and qualitative methodologies like rapid assessment methods, key informant interviews, focus group discussions, collecting information for determining the overall effectiveness of the program. The review process should be participatory engaging Government high officials, implementing and donor partners, project concerns, key stakeholders and a wide cross-section of staff and beneficiaries incorporating gender equity. It should consider the diversified components/interventions of the overall project. The methods used for the evaluation may include the followings:

- Meeting or interview with key project personnel and stakeholders- European Union, Swiss Agency for Development and Cooperation, DANIDA, LGD, local government organizations, relevant government ministries, selected community participants, partner NGOs.

- Key informant interview with potential key stakeholders, civil society members and policy influencers;

- Focus group and group interviews with contestants and respondents - to determine benefits of the project, unanticipated consequences and possible areas of modification or redesign;

- Direct observations of activities through site visits-assess technical practices, quality of activities, confirm recorded outputs, assess impact of activities;

- Review of different study reports (baseline, impact baseline study, case study etc.) to measure the changes of target groups for achieving the results;

- Review of program records- to establish outputs and financial accountability;

- Review of program and organizational documents-to assess institutional strengthening of various partners and organizations;

7. Gender and Human Rights:

The evaluation must include an assessment of the extent to which the design, implementation and results of the project have incorporated a gender equality perspective and rights-based approach. The evaluators are requested to review UNEG’s Guidance in Integrating Human Rights and Gender Equality in Evaluation during the inception phase.

In addition, the methodology used, data collection and analysis methods should be human rights and gender sensitive to the greatest extent possible, with evaluation data and findings disaggregated by sex, ethnicity, age etc.

8. Evaluation Work Plan and sequence:

The distribution of number of days per team member and evaluation phase is as follows:

|  | Team Leader | International Team Member | National Team Members | Investigator |
| --- | --- | --- | --- | --- |
| Inception Phase (dates) | 10 days | 10 days | 10 days | 10 days |
| In-country Phase | 45 days | 45 days | 45 days | 45 days |
| Post-mission Phase | 5 days | 5 days | 5 days | 5 days |
| Total number of days | 60 | 60 | 60 | 60 |

The sequence of evaluation steps are as follows:

1. Desk Review/ Pre-mission briefing

  - Pre-mission briefing to ensure understanding of evaluation methodology and familiarize the Evaluation team with the programme.

  - Review of secondary data such as background literature and project documentation lead by the Evaluation Team Leader in consultation with his/her team. It will involve necessary clarifications by UNDP and UNCDF personnel, UPGP and UZGP Project Managers and other national and international staff, Assistant Country Director and other UNDP and UNCDF Cluster staff, UNDP CO senior management and UNCDF Regional Office in Bangkok.

  - This phase will culminate in the preparation of a brief Inception Report to be forwarded to UNDP and UNCDF for comments. The Inception report should incorporate the information from the desk review, present the reconstructed intervention logic, spell out the evaluation questions and a plan for how these will be tackled by the team including draft interview questions.

  - This phase will help the team to prepare for the team hypothesis meeting that is held when the team assembles in Dhaka and for the Inception Workshop with stakeholders.

2. Kick- Off meeting

- Kick- Off meeting to share evaluation team approach and questions and receive feedback with the senior management of UNDP and UNCDF.

- Inception workshop for key stakeholders set up to interact with the Evaluation Team.

- Interviews by the team with national stakeholders such as key ministries and donors; initial consultations in Dhaka with Project team, UNDP and UNCDF CO office teams, MLGRD&C, development partners (European Commission, SDC and Danida) and LGSP partner, the World Bank.

- Data collection Phase: Field visits to the implementation areas – local level (visits to sample of 4 intervention areas from seven divisions generally considered the minimum requirement):

4. Debriefing / Post-mission phase

- Debrief UNDP and UNCDF CO teams and project team and LGD.

- Debriefing of the UNDP Country Director and Deputy Country Director (Programme)

- Debriefing of the MLGRD&C and other relevant Ministerial staff

- National debriefing workshop with key stakeholders to present and discuss findings & recommendations – this workshop will generally review an Aide Memoire which presents the key findings, recommendations (conveyed in power point) and collect feedback from stakeholders.

- Global Debriefing UNDP and UNCDF senior management at HQ and regional office via teleconference generally conducted with the evaluation team leader and with participation from the country level.

- Incorporate feedback as well as observations from stakeholders during the MTE.

5. Completion of Management Response

- The Management Response will be circulated with the final report for completion by all relevant stakeholders (a 30-day turn-around time is expected). The completed Management Response will then be uploaded on the Evaluation Resource Database maintained by UNDP Headquarters

9. Evaluation Products (Deliverables)

Deliverables: The mission will be responsible for submitting the following deliverables:

- Inception Report (10-20 pages)

- The Draft report (30-40 pages excluding Annex )

- The final report: (max 35-40 pages excluding annexes) and Executive Summary (max 2-3 pages). It should also contain a matrix of recommendations to be used for the Management Response and action, and recommendations for the next phase of the programme.

- Brief synopsis of evaluation and key findings and recommendations (1000 words for corporate communications use)

The UNDP CO is responsible for circulating the finalized report to all concerned parties, for inclusion on the UNCDF website and the UNDP Evaluation Resource Centre database.

| MAIN DELIVERABLES | SUBMISSION DATE |
| --- | --- |
| Inception report | 30 September, 2014 |
| Draft Evaluation Report. | 30 November, 2014 |
| Power Point Presentation for debriefing | 30 November, 2014 |
| Final Evaluation Report, Executive Summary and Management Response with main recommendations listed in order of priority. | 15 December, 2014 |

10. Evaluation team composition and required competencies

The Evaluation Team will be conducted by a team of an international team leader, an international team member, 2 national experts and 4 field investigators. They will be selected according to the following profiles and along UNEG gender and human rights guidelines.

1. EVALUATION TEAM LEADER (International)

A senior consultant with strong international experience in the field of decentralization and local government such as: fiscal decentralization, decentralized infrastructure and service delivery; local government capacity building for decentralized public expenditure management and operationalisation of decentralized systems of planning and budgeting; policy, legal and regulatory reform related to decentralization; rural development; and decentralised cooperation involving non-state actors such as civil society organisation and private sector bodies.

He/she has extensive experience in undertaking evaluations. The team leader will allocate roles and responsibilities within the team, including meeting schedules and drafting duties, and be responsible for timely delivery.

Duration: 60 working days

Responsibilities:

- Documentation review

- Inception Report

- Leading the evaluation team in planning, execution and reporting (hypothesis workshop, Inception workshop, kick-off and feedback meeting, national and global debriefings).

- Deciding and managing division of labour within the evaluation team

- Use of best practice evaluation methodologies in conducting the evaluation

- Conducting the debriefing for the UNDP Country Office in Bangladesh and the UNCDF HQ

- Leading the national debriefing for programme stakeholders in Bangladesh

- Leading the drafting and finalization/quality control of the evaluation report

- Preparing the Management Response template in terms of Findings and Recommendations

Corporate Competencies:

- Demonstrates integrity and fairness by modeling UN values and ethical standards;

- Displays cultural and gender sensitivity and adaptability;

- Treats all people fairly and without favoritism; and

- Shows strong corporate commitment.

Functional Competencies

Development and Operational Effectiveness:

- Ability to lead strategic planning and facilitate crucial decision making at the highest levels of government;

- Ability to lead the formulation, implementation, monitoring and evaluation of strategic policies and sound development program;

- Ability to generate creative, practical approaches to overcome challenging situations;

- Strong technical and practical leadership and knowledge in issues related to aid management, coordination and effectiveness;

- Familiarity with UN system and role of key stakeholders in the area of national development plans, local-level planning, aid management, coordination and effectiveness;

- Ability to work well in multi-disciplinary and multi-cultural teams.

Knowledge Management and Learning:

- Promotes knowledge management and a learning environment through leadership and personal example;

- Ability to promote UNDP as a learning/knowledge sharing organization Experience in capacity development and facilitating positive transformational change.

Management and Leadership:

- Ability to build strong relationships with clients, to focus on impact and to responds positively to constructive feedback;

- Personal attributes to consistently approaching work with energy and a positive constructive attitude;

- Excellent oral and written communication skills, including the ability to write in a clear and concise manner;

- Excellent presentation skills;

- Excellent computer skills, and applications for report and project planning;

- Excellent organizational skills and proven ability to deliver programs/projects within assigned deadlines;

- Openness to change and ability to manage complexities;

- Excellent interpersonal skills and objectivity.

Qualifications:

      - Master’s degree or higher on governance specializing in public administration, public policy, decentralization, local governance and other relevant fields;

      - At least 15 years of professional experience in decentralization and local development, especially in developing countries;

      - Sound knowledge and experience in evaluation of development programmes/projects;

      - Thorough understanding of key elements of results-based programme management;

      - Strong capacity for data collection and analysis, as well as report writing;

      - Demonstrated evaluation team management skills

      - Experience or knowledge of decentralization in Bangladesh and/or regional experience in the area of decentralization would be considered as an advantage;

      - Sound knowledge and understanding of gender sensitivity and social inclusion;

      - A good level of experience in the strategic positioning of decentralization and local development programmes in relationship to donors/development partners and local authorities;

      - Ability to assess the effectiveness and sustainability of programme structure and implementation modalities to inform UNDP and UNCDF;

      - Strong task management and team leading competencies;

      - Fluency in English, in speaking and writing. Knowledge of Bengali would be an asset.

2. 2. TEAM MEMBER (International on fiscal decentralization)

A consultant with relevant background and experience in the field of fiscal decentralization and local government particularly in fiscal transfer within the context of service delivery; local resource mobilization; local government capacity building on financial management.

Duration: 60 working days

Responsibilities:

- Evaluate fiscal transfer operations conducted thus far

- Assess the performance assessment lessons learnt from the project’s target areas to the national level, based on the lessons learned from the piloting project

- Review the achievements in MDG/service delivery using grants money, with specific focus on financial management of LGIs

- Assist the team leader as necessary

Qualifications:

      - Master degree or higher in public administration reform, local/rural development, capacity building, planning and other relevant fields

      - At least 10 years of professional experience in the field of local development, planning, capacity building, preferably in the Asian developing countries;

      - Sound knowledge and experience in evaluating development programmes/projects particularly decentralization and local governance programmes;

      - Experience in assessing capacity building and knowledge management skills which are expected to be a core element of the LIC aspect of this programme would be an asset

      - Strong ability for data collection and analysis, as well as report writing;

      - Sound knowledge and understanding of gender sensitivity and social inclusion;

      - Fluency in English, in speaking and writing. Knowledge of Bengali would be an asset.

Corporate Competencies:

- Demonstrates integrity and fairness by modeling UN values and ethical standards;

- Displays cultural and gender sensitivity and adaptability;

- Treats all people fairly and without favoritism; and

- Shows strong corporate commitment.

Functional Competencies

Development and Operational Effectiveness:

- Ability to lead strategic planning and facilitate crucial decision making at the highest levels of government;

- Ability to lead the formulation, implementation, monitoring and evaluation of strategic policies and sound development program;

- Ability to generate creative, practical approaches to overcome challenging situations;

- Strong technical and practical leadership and knowledge in issues related to aid management, coordination and effectiveness;

- Familiarity with UN system and role of key stakeholders in the area of national development plans, local-level planning, aid management, coordination and effectiveness;

- Ability to work well in multi-disciplinary and multi-cultural teams.

Knowledge Management and Learning:

- Promotes knowledge management and a learning environment through leadership and personal example;

- Ability to promote UNDP as a learning/knowledge sharing organization Experience in capacity development and facilitating positive transformational change.

Management and Leadership:

- Ability to build strong relationships with clients, to focus on impact and to responds positively to constructive feedback;

- Personal attributes to consistently approaching work with energy and a positive constructive attitude;

- Excellent oral and written communication skills, including the ability to write in a clear and concise manner;

- Excellent presentation skills;

- Excellent computer skills, and applications for report and project planning;

- Excellent organizational skills and proven ability to deliver programs/projects within assigned deadlines;

- Openness to change and ability to manage complexities;

- Excellent interpersonal skills and objectivity.

3. NATIONAL EXPERT 1 – Capacity Development and women empowerment

Specialised on Capacity Development to assess programme performance with respect to

improve the capacity of elected UP and UZP officials in running their portfolio, in enhancing people’s participation in planning and implementation, women empowerment etc.

Duration: 60 working days

Responsibilities:

- Take responsibility for relevant questions and sub-questions falling under their areas of expertise

- Provide overall assistance the team in terms of data collection and data analysis;

- Assist with the focused group discussions at all levels;

- Assist with the conduct of interviews at all levels

- Attend the briefing and debriefings with UNDP CO and government agencies both at central and local levels;

- Provide translation and other assistance to the team;

- Be responsible for report writing covering their areas of competence.

Qualifications:

- Master’s degree or higher in public administration, law, development studies, and other relevant fields such as gender;

- At least 5 years of professional experience in the field of local development, planning, capacity building in Bangladesh;

- Have experience in assessing the outcomes of development project preferred.

- Strong ability for data collection and analysis, as well as report writing;

- Understanding of political structure and sub-national government systems;

- Sound knowledge and understanding of gender sensitivity and social inclusion;

- Strong interpersonal and communication skills;

- Fluency in English and Bangla, in speaking and writing.

Corporate Competencies:

- Demonstrates integrity and fairness by modeling UN values and ethical standards;

- Displays cultural and gender sensitivity and adaptability;

- Treats all people fairly and without favoritism; and

- Shows strong corporate commitment.

Functional Competencies

Development and Operational Effectiveness:

- Ability to lead strategic planning and facilitate crucial decision making at the highest levels of government;

- Ability to lead the formulation, implementation, monitoring and evaluation of strategic policies and sound development program;

- Ability to generate creative, practical approaches to overcome challenging situations;

- Strong technical and practical leadership and knowledge in issues related to aid management, coordination and effectiveness;

- Familiarity with UN system and role of key stakeholders in the area of national development plans, local-level planning, aid management, coordination and effectiveness;

- Ability to work well in multi-disciplinary and multi-cultural teams.

Knowledge Management and Learning:

- Promotes knowledge management and a learning environment through leadership and personal example;

- Ability to promote UNDP as a learning/knowledge sharing organization Experience in capacity development and facilitating positive transformational change.

Management and Leadership:

- Ability to build strong relationships with clients, to focus on impact and to responds positively to constructive feedback;

- Personal attributes to consistently approaching work with energy and a positive constructive attitude;

- Excellent oral and written communication skills, including the ability to write in a clear and concise manner;

- Excellent presentation skills;

- Excellent computer skills, and applications for report and project planning;

- Excellent organizational skills and proven ability to deliver programs/projects within assigned deadlines;

- Openness to change and ability to manage complexities;

- Excellent interpersonal skills and objectivity.

- NATIONAL EXPERT 2 - Service Delivery

Specialised in design, management, and supervision of service delivery projects (including infrastructure) ideally from a public sector perspective to assess the quality of implementation, and the replicability of the systems introduced, to manage the micro-projects (schemes) supported by the project

Duration: 60 working days

Responsibilities:

- Take responsibility for relevant questions and sub-questions falling under their areas of expertise

- Provide overall assistance the team in terms of data collection and data analysis;

- Assist with the focused group discussions at all levels;

- Assist with the conduct of interviews at all levels

- Attend the briefing and debriefings with UNDP CO and government agencies both at central and local levels;

- Provide translation and other assistance to the team;

- Be responsible for report writing covering their areas of competence.

Qualifications:

- Master’s degree or higher in public administration, development studies, engineering and other relevant fields;

- At least 5 years of professional experience in the field of local development, planning, capacity building

- Have experience in assessing the outcomes of development project

- Strong ability for data collection and analysis, as well as report writing;

- Understanding of political structure and sub-national government systems;

- Sound knowledge and understanding of gender sensitivity and social inclusion;

- Strong interpersonal and communication skills;

- Fluency in English and Bangla, in speaking and writing.

- Field Investigator (4)

Duration: 60 working days

Duties and responsibilities

- Develop detailed work plan for the selected area

- Collect data as per the instruction of team leader

- Assist to revise data collection tools and instruments

- Analyze all data gathered from the selected areas

- Develop the report for the selected areason the basis of the field data and Chapter outline provided by the team leader

Corporate competencies:

- Demonstrates commitment to UNDP’s mission, vision and values;

- Displays cultural, gender, religion, race, nationality and age sensitivity and adaptability;

- Highest standards of integrity, discretion and loyalty.

Functional competencies:

Communication:

- Communicates effectively with staff at all levels of the organization and is comfortable in handling external relations at all levels;

- Outstanding writing and oral communication skills.

Professionalism:

- Capable of meeting deadlines, managing tasks simultaneously;

- Able to complete tasks accurately and thoroughly, with great attention to detail;

- Exercises the highest level of responsibility and is able to handle confidential and politically sensitive issues in a responsible and mature manner.

Teamwork:

- Works well in a team to service all of PG and BDP as a whole;

- Projects a positive image and is ready to take on a wide range of tasks to create an enabling environment for local development programme;

- Focuses on result for the client and responds positively to feedback.

Technical Skills:

- Able to conduct thorough qualitative and quantitative research, able to synthesize and summarize extensive research material into succinct briefings, able to draft communications and outreach materials for the PG;

- Excellent computer, writing and oral skills.

Knowledge Management and Learning:

- Willingly shares knowledge and experience and makes contributions to UNDP practice area s (e.g., documented knowledge, community of practice building initiatives);

Actively develops deep understanding and experience in one or more

Education and technical expertise

- Masters’ in Public Policy, Political Science, Economics, Sociology, Development Studies or relevant experiences in development research;

- Professional achievements in the relevant fields research and analysis;

Ability to work under critical situation with regard to political environment.

Experiences

- An expert in the field of democratic governance

- Minimum 10 years of experiences in the relevant field;

- Working experiences in Bangladesh at the local governance related fields.

11. Evaluation ethics

The evaluation will be conducted in accordance with the principles outlined in the UNEG ‘Ethical Guidelines for Evaluation’ (http://www.uneval.org/search/index.jsp?q=ethical+guidelines.) See Annex

The evaluation team has to safeguard the rights and confidentiality of information providers, for example: measures to ensure compliance with legal codes governing areas such as provisions to collect and report data.

11. Cost

The project will bear the costs for all kinds of activities including the fee, field visit costs as per the approved work plan, 2014.

12. Annexes:

1. Project Document along with Results framework

2. Ethical guideline

# Annex 2. Inception Itinerary

Schedule for the first mission (24 September, 2014-2 October, 2014)

| Date | Event | Venue/remarks | Remarks |
| --- | --- | --- | --- |
| 24 September, 2014 |  |  |  |
| 09.00-10.30 | Meeting with Local governance cluster, UNDP | Village Well, UNDP | Confirmed |
| 11.00-12.00 | Meeting with RRMC, UNDP | UNDP | TBC |
| 12.30-01.00 | Meeting with UNDP Senior Management team | CD’s room | Confirmed |
| 14.00-15.30 | Meeting with UPGP Project Manager | BIAM | Confirmed |
| 15.30-17.00 | Internal meetings of Mid-term evaluation team members | BIAM, UPGP Office | Confirmed |
| 25 September, 2014 |  |  |  |
| 10.00-11.00 | Meeting with ITA, UZGP | UNDP | Confirmed |
| 11.00-12.00 | Meeting with ITA, UPGP | UNDP | Confirmed |
| 12.00-13.00 | Lunch Break |  |  |
| 14.30-15.30 | Meeting with DANIDA | DANIDA office, Gulshan | Confirmed |

| Date | Event | Venue/remarks | Remarks |
| --- | --- | --- | --- |
| 26 September, 2014 (Friday) | Team members meetings for developing tools for data collection | Village Well, UNDP | Weekend |
|  | Skype call with UNCDF at 2.00 PM |  |  |
| 27 September, 2014 (Saturday) | Team members meetings developing tools for data collection | Village Well, UNDP | Weekend |
| 28 September, 2014 |  |  |  |
| 09.30-10.30 | Meeting with Audit firm | LGSP-2 | Confirmed |
| 10.30-12.00 | Meeting with LGSP 2 Team | LGSP Office | Confirmed |
| 12.00-12.45 | Travel |  |  |
| 12.45-14.00 | Lunch |  |  |
| 14.15-15.30 | Meeting with NILG | NILG | Confirmed |
| 16.00-17.00 | Meeting with UZGP Audit Team (Mobasser) | UNDP | Confirmed |
| 29 September, 2014 |  |  |  |
| 09.00-10.00 | Meeting with UZGP Project Manager | NILG | Confirmed |
| 10.00-11.00 | Meeting with NPD, UZGP | NILG | Confirmed |
| 11.00-12.00 | Meeting with ACD, LG, UNDP | UNDP | Confirmed |
| 12.00-13.00 | Lunch | UNDP |  |
| 13.00-14.00 | Travel |  |  |
| 14.00-15.00 | Meeting with UZGP Focal Person | LGD | Confirmed |
| 15.00-16.00 | Meeting with UPGP Focal Person | LGD | Confirmed |
| 16.00-17.00 | Meeting with UPGP NPD | LGD | TBC |
| 30 September, 2014 |  |  |  |
| 09.00-17.00 | Workshop | NILG Dhaka | Confirmed |
| 17.00-18.00 | Meeting with UPGP DF | Workshop venue | Confirmed |
| 18.00-19.00 | Meeting with UZGP DivF | Workshop Venue | Confirmed |
| 1 October, 2014 |  |  |  |
| 09.00-14.00 | Workshop | NILG, Workshop venue | Confirmed |
| 15.00-16.00 | SDC | SDC Office | Confirmed |
| 16.00-17.30 | Meeting with EU | EU | Postponed |
| 2 October, 2014 |  |  |  |
| 02.00-3.30 | Presentation of inception report | UNDP | Confirmed |

# Annex 3. Inception workshop program

Venue: NILG

Date: 30 September, 2014 - 1 October, 2014

Day – 1

| Time | Subject | Resource Persons |
| --- | --- | --- |
| 30 September, 2014 |  |  |
| 09.00-09.30 | Registration |  |
| 09.30-10.00 | Inauguration and objectives | Mr. Md. Shah Kamal, NPD, UZGP, Ms. Shaila Khan Assistant Country Director Mr. Jens Peter Christensen, Team Leader, MTR |
| 10.00-11.00 | Presentation and discussion on Union Parishad Governance Project: An overview of Achievement, challenges and way forward | Ms. Shamima Nargis, Focal Person, UPGP |
| 11.00 -11.30 | Tea Break |  |
| 11.30 -12.30 | Presentation and discussion on Upazila Governance Project: An overview of Achievement, challenges and way forward | Mr. Akram Al-Hossain, Focal Person, UZGP |
| 12.30-13.30 | Presentation and discussion on Union Parishad Governance Project: Implementation success, good practices and lesson learned from the field | Mr. Emdadul Haque, DDLG, Kishoreganj |
| 13.30-14.30 | Lunch & Prayer |  |
| 14.30-15.30 | Presentation and discussion on Upazila Governance Project: Implementation success, good practices and lesson learned from the field | Mr. Aminul Islam, DLG, Rajshahi |
| 15.30-16.00 | Tea Break |  |
| 16.00-17.00 | Capacity development of Union Parishad: Success, lessons learned & impact | Dr. Sarwar Bari/Mr. Mahbubur Rahman, DF, UPGP, Rangpur |
|  | Capacity development of Upazila Parishad: Success, lessons learned & impact | Mozammel Haque, Project Manager, UZGP |

Day - 2

| Time | Subject | Resource Persons |
| --- | --- | --- |
| 1 October, 2014 |  |  |
| 09.00-09.45 | Women Development Forum: A Journey | Mr. Aziz Sarder, WEO and Mozammel Haque, PM, UZGP |
| 09.45-10.45 | Fiscal Transfer: Facilitating pro-poor development | Dr. Suresh Balakrishnan, International Technical Adviser, UPGP/UNCDF |
| 10.45 -11.00 | Tea Break |  |
| 11.00 -11.45 | Pursuing policy reform towards decentralization in Bangladesh: Policy advocacy by UPGP and UZGP | Akram Al Hossain, Joint Secretary, LGD |
| 11.45-13.00 | Monitoring strategy of UPGP and UZGP | Mr. Hasanuzzaman, MIS Officer, UPGP and Mizanur Rahman, M&E Officer, UZGP |
| 13.00-13.30 | Closing of workshop with concluding remarks | Mr. Md. Mozammel Huq, NPD, UPGP & and Mr. Md. Shah Kamal, NPD, UZGP, Ms. Shaila Khan, Assistant Country Director, UNDP Mr. Jens Peter Christensen, Team Leader, MTR |
|  | Lunch & Departure |  |

Participant’s Attendance Sheet, day 1

| Sl. No. | Name |
| --- | --- |
| 1 | Jens Peter Christensen |
| 2 | Jesper Steffensen |
| 3 | Salauddin M. Aminuzzaman |
| 4 | Shaila Khan |
| 5 | Shamima Nargis |
| 6 | Md. Mozammel Haque |
| 7 | Dr. Md. Sarwar Bari |
| 8 | Md. Mizanur Rahman |
| 9 | Prof. K.M. Mahiuddin |
| 10 | Salma Akter |
| 11 | Prof. Taiabur Rahman |
| 12 | A.S. M. Firoz Ul Hassan |
| 13 | Ekram Hossain |
| 14 | Md. Emdadul Hoq |
| 15 | Suresh Balakrishnan |
| 16 | Sk. Iqbal Hossen |
| 17 | Mohammad Mahbubur Rahman |
| 18 | Muhammad Zahir Uddin |
| 19 | Abu Tahir Muhammad Zaber |
| 20 | Taufique Mohiuddin |
| 21 | Md. Hassanuzzaman |
| 22 | Md. Mizanur Rahman |
| 23 | Mohammad Mohebur Rahman |
| 24 | Md. Habebur Rahman |
| 25 | Md. Jahangir Hossain |
| 26 | M. Rafiqul Islam |
| 27 | Md. Aminul Islam |
| 28 | Ataul Gani Osmani |
| 29 | Md. Sydur Rahman Molla |
| 30 | H. M. Nazrul Islam |
| 31 | Mohammad Sahab Uddin |
| 32 | Faisal Ahmed |
| 33 | Khaleda Jannat |
| 34 | Kazi Obaidur Rahman |
| 35 | Kazi Md. Zilla Haider |

Participant’s Attendance Sheet, Day 2

| Sl. No. | Name |
| --- | --- |
| 1 | Jesper Steffensen |
| 2 | Jens Peter Christensen |
| 3 | Salauddin M. Aminuzzaman |
| 4 | Md. Aminul Islam |
| 5 | Prof. Taiabur Rahman |
| 6 | Prof. K.M. Mahiuddin |
| 7 | Salma Akter |
| 8 | Dr. Md. Sarwar Bari |
| 9 | Muhammad Zahir Uddin |
| 10 | Ekram Hossain |
| 11 | Md. Emdadul Hoq |
| 12 | Sk. Iqbal Hossen |
| 13 | Asma Abbasi |
| 14 | Md. Mizanur Rahman |
| 15 | Mohammad Mahbubur Rahman |
| 16 | Taufique Mohiuddin |
| 17 | Md. Hassanuzzaman |
| 18 | Mohammad Mohebur Rahman |
| 19 | A.S. M. Firoz Ul Hassan |
| 20 | Dalia Das |
| 21 | Md. Mizanur Rahman |
| 22 | Md. Habebur Rahman |
| 23 | Md. Jahangir Hossain |
| 24 | M. Rafiqul Islam |
| 25 | H. M. Nazrul Islam |
| 26 | Md. Sydur Rahman Molla |
| 27 | Jesmul Hasan |
| 28 | Ataul Gani Osmani |
| 29 | Azizul Haque Sarder |
| 30 | Shaila Khan |
| 31 | Faisal Ahmed |
| 32 | Kazi Obaidur Rahman |
| 33 | Khaleda Jannat |
| 34 | Kazi Md. Zilla Haider |
| 35 | Md. Mozammel Haque |

# Annex 4. Itinerary for the second MTR mission

| Date | Event | Venue/remarks | Remarks |
| --- | --- | --- | --- |
| 22 October, 2014 |  |  |  |
| 09.00-12.00 | Internal meeting | Lake Castle Hotel | Done |
| 13.00-14.30 | Meeting with UNDP and UNCDF | UNDP | Done |
| 15.00-16.00 | Meeting with former NTA | BRAC University | Done |
| 23 October, 2014 |  |  |  |
| 9.00-10.00 | Meeting with Dr. Akira Monakata, technical Adviser, JICA | NILG | Done |
| 10.30-11.30 | Meeting with Mr. Swapan Kumar Sarker, Former DG, MIE wing | UNDP | Done |
| 14.00 0-14.45 | Meeting with Mr. Rustam Pulatov, Assistant Country Director, Governance, UNDP | UNDP | Done |
| 27 -29 October, 2015 | Field Visit | Brahmanbaria | Done |
| 30 October, 2014 |  |  |  |
| 09.30-10.00 | Meeting with DG, MIE Wing | Secretariat | Cancelled. To be fixed again |
| 11.00-12.00 | Meeting with LG Cluster | UNDP | Cancelled. To be fixed again |
| 12.00-13.00 | Meeting with PM, UZGP | NILG | Done |
| 14.30-15.30 | Meeting with SHARIQUE/Helvetas Ms. Lilia Tverdun (Programme Director) and Tirtha Sarathi Sikder, National Coordinator | Gulshan | Done |
| 2 November, 2014 |  |  |  |
| 09.00-10.30 | Meeting with Mr. Suresh Balakrishnana Menon, ITA, UPGP | Hotel Lake Castel | Confirmed |
| 11.00-12.30 | Meeting with PATZELT Luc, Programme Manager, EU, Bangladesh | EU | Confirmed |
| 3 November, 2014 |  |  |  |
| 09.00-10.00 | Meeting with Mr. Khurshid Alam Assistant Country Director, (Climate Change, Environment and Disaster Reduction Cluster, UNDP) | UNDP (18th Floor) | Confirmed |
| 10.00-11.00 | Meeting with Ms. Blerta Cela Assistant Country Director, (Results and Resource Management Cluster, UNDP) | UNDP (19th Floor) | Confirmed |
| 4 November, 2014 |  |  |  |
| 09.00-16.00 | MTR Internal meeting |  |  |
| 5 November, 2014 |  |  |  |
| 09.30-10.30 | Meeting with World Bank (Dr. Zahed Khan and Mr. Pablo) | World Bank Office | Confirmed |
| 12.30-13.30 | Meeting with Abul Quasem, Joint Secretray, MIE Wing | Secretariat | Confirmed |
| 16.00-17.00 | Meeting with . K M Mozammel Hoq Additional Secretary, Local Govt. Division and NPD, UPGP | Officer’s Club, Baily Road | Confirmed |
| 6-12 November, 2015 | Report writing |  |  |
| 13 November, 2014 |  |  |  |
| 11.30-13.00 | Debriefing | LGD | Confirmed |

# Annex 5. Questionnaires for the central level

General Questions – Central Level (ministries, program officials and Development partners)

Context

- General political context ? instability etc. ?

- Signs of overall government commitment to decentralization?

  - Reform strategies etc.?... any recent developments?

  - Recent or planned decentralization of functions, staff, fiscal assignments, transfers, planning framework etc.

  - Relationship between ministries?

- Establishment of coordination arrangements,

  - Inter-ministerial local governance committee – TOR, linkage to UZGP/UPGP comp 3? PAG?

  - PAG – why is it not yet operating?

Design

- How was the design based on previous experiences and lessons learned?

  - What has been lifted over?

  - What is different from previous phases?

- Overall design strategy?

- Strategy for up-scaling, transmission?

- Links between the two programs?

- M&E system and results framework

  - Seems to be multiple M&E systems – baseline-study (2013 –was it too late?), RF in DP, results framework from 2012 by consultant, M&E reporting formats, quarterly, etc. ? – what is the best basis for evaluation?

- Relevance: Is the overall design still relevant ?

Overall Results Achievement at the mid-term stage

- Has the programme(s) made satisfactory progress in terms of achievement of overall results (as per RRF/logframe) of “Strengthened capacities of local governments and other stakeholders to foster participatory local development and service delivery for the MDGs”?

  - Documentation of trends?

  - Indicators for this?...

  - Sources of information ? ….

  - Main reasons?

Results achievement at the output and outcome level

- Has the programme made satisfactory progress in terms of achievement of programme outputs (as per RRF/logframe indicators and annual work plan targets) and related delivery of inputs and activities?

    - Go through the 3 main outputs for each programs:

      - impact on capacity for democratic accountability/citizens engagement,

      - impact on the finance system & pro poor service delivery,

      - impact on national systems and legal framework?

      - impact on coordination of national CB support?

      - Impact on M&E ?

- How effectively and efficiently have results been achieved, and to what level of quality? (by output)

Cross-cutting Issues

- Gender – how has it been addressed by the programs? … Main results? …Challenges?... Recommendations?

- MDG – how has it been addressed ? … Main results?... Challenges?... Recommendations?...

- Rights-based approach, transparency, accountability and HR? Main results?... Challenges?... Recommendations?

- Environment and social safeguards?... Main results?... Challenges?... Recommendations?...

Factors affecting successful implementation and results achievement

- Have the programme implementation and results been achieved according to plan?

- Any obstacles/bottlenecks/issues on the UNDP/UNCDF/Government/ programme partner side that limited the successful implementation and results achievement of the programme?

- What are the success factors to keep for the future phase?

- Constraining factors?

    - Financial envelope

    - Staff? .. lack of UP staff, turn over etc. ?

    - Elite capture?

    - Other

- How can shortcomings be factored in to be prevented in the future?

External Factors:

- Has the policy environment had consequences for programme performance?

- To what extent does the broader policy environment remain conducive to the replication of the lessons learnt from the pilot programme?

- Are there any other factors external to the programme that have affected successful implementation and results achievement, and prospects for policy impact and replication?

- How could the identified positive or negative external factors be mitigated or exploited further for the next programme phase?

Programme-related Factors impacting implementation:

Programme design (relevance and quality):

- Was the programme logic, design and strategy optimal to achieve the desired programme objectives/outputs, given the national/local context and the needs to be addressed?

- Clarity and consistency of the design and results framework?

- Adequacy of resources allocated and management arrangements?

- Adequacy and usefulness of the baseline?

  - Baseline was published in 2013 (i.e. some time after the start?) How is it being used?

- Were relevant gender issues adequately addressed in programme design?

- Is the programme rooted in and effectively integrated with national strategies (e.g. Five year plan) and UN planning and results frameworks (UNDAF, CPD etc.) at country level?

- Have the programme’s objectives remained valid and relevant? Has any progress in achieving these objectives added significant value?

- What lessons from the programme design could be retained for the next programme phase?

Institutional and implementation arrangements:

- Were the programme’s institutional and implementation arrangements appropriate, effective and efficient for the successful achievement of the programme’s objectives?

  - NEX procedures – lessons learned??

  - SCs and Program Boards? Have the operated effectively?

  - Links to other programs? – have these been effective? … challenges?...

- Where there any institutional obstacles hindering the implementation/operations of the programme?

- What lessons from the institutional and implementation arrangements could be retained for the future interventions?

Programme management issues:

    - Were the management arrangements for the programme adequate and appropriate?

    - How effectively has the programme been managed at all levels?

  - Experiences from the system of NPD and Program managers + CTAs and QA by UNDP/UNCDF?

    - Is programme management results-based and innovative?

    - Has financial management been sound?

    - E.g. timely and audited financial accounts

    - Demands for funding agencies, DPs etc. ?... have these been fulfilled?.... Yes… No…

    - Have the programme’s management systems, including M&E, reporting and financial systems functioned as effective management tools, and facilitated effective implementation of the programme?

    - Have the programme’s logical framework, performance indicators, baseline data and monitoring systems provided a sufficient and efficient basis for monitoring and evaluating programme performance?

- Has the M&E system supported effective programme management, corporate decision-making and learning?

    - What lessons from the programme management arrangements should be considered for the next programme phase?... General management issues… M&E issues?....

SPECIFIC QUESTIONS ON SPECIAL ISSUES

Capacity building (for two programs) and Result Area One

- Main areas where CB has provided?....

- Strategy for CB support?....

- Methodology ? ., . any changes from the LIC?...

  - Delivery mechanism?

  - Top down training? … Cascading approach versus direct contact between training providers and the beneficiaries?...

  - Other methods – what is the feed back from assessment reports?

- System of feed–back and QA on training?

- Links with LGSP?

- Lessons learned from various tools?

- Role of the District Facilitators (DFs)?

- Role of the Upazila Facilitating Teams (UFTs)?

- Role of training provides?

- Lessons learned

- Challenges?

- Opportunities in the coming years?.... recommenations?...

Accountability and citizens’ engagement (for both programs)

- Main activities?...

- Main results? ….

- Impact of the program?...

- Challenges?...

- Future recommendations?...

Outcome area 2: Specific Questions on Finance/Grant System related with Ups – Central Level

- Main activities under component 2

  - Grants..

  - Other activities?

  - Achievements

  - Challenges

- Most up-dated grant manual? And changes hereof and why (lessons learned from this)?

- Most updated assessment manual? And changes hereof and why (lessons learned from this)?

- Target areas – number of Ups covered ?

- Minimum conditions – original plans in PD versus the reality?

- Size of the grants?

  - Size of the UPGP grants?....

  - Size of other grants?...

- Allocation formula

  - Basic formula (criteria), poverty focus etc. ?

    - Is it needs based?

    - Based on objective data?

  - Method for factoring in of the performance element, and impact of the performance?

- Fund flow? I) system, ii) timing…. Iii) requirement on the use of funds (timing of this)?..

- Rounds of allocations, timing of these?

  - For the two first rounds? FY 2012/13?.... 2013/2014?...

  - Planned allocations for other FYs?.... 2014/2015?...

- Timing of assessments – start and completion of first and second?

  - Delays – reasons?

  - Recent assessment seem to be delayed as the previous one by 1.5 years ? (PBGS allocations for FY 2013/14 should have been announced in February 2013, but now in June 2014)?

  - Future plans to reduce delays? …. For the third and fourth assessments?

  - When will the review of the performance 2013/14 (to impact on FY 2015/16) be started and completed?

  - How to ensure that results fit with the local planning process?

- Composition of the audit/assessment teams? … selection process?

- Experiences from training of the assessment teams?

- System of appeal and establishment of complaints committee? (as per guidelines, however in Nov. 2013, it was not established) – any new developments?...

- Quality assurance and audit review teams – any work of this?

- Approval of results – assessment committees as per design?

- Publication of results?.... nation-wide ? … for the Ups?

- Control group to ensure impact of assessments? (as per the PD where this was envisaged)?

- How is CB support linked to assessments?...... are the assessment results used?

- Time-span for utilization of grants (deadline for fund utilization for allocations in 2014 (deals with allocations from FY 2013/14))

- Use of funds

  - Number of projects funded by the Expanded performance based grants?....

  - % on each area; (roads, health, education, water and sanitation, etc.?

  - MDG targeting?

  - Gender targeting?

  - Evidence of quality and maintenance?

  - Autonomy to choose – the investment menu?

  - Future plans on the grant system?

    - Targeting

    - Links to sectors?

    - Links to climate change and other cross cutting areas?

- Major challenges in the grant system?

- Future opportunities?

- Activities on UP own source revenue mobilization?

  - Size of the UP OSR in 2012/2013?... 2013/2014?..... Trends?...

  - Coverage of activities?

  - Impact of activities?

  - Challenges

  - Lessons learned?

  - Future plans?

Questions for the UGZP (Finance) – Component 2 – Central Level

- Main activities under Output 2

  - Grants provided?

  - Other activities?

  - Achievements from support under Output 2?

  - Challenges

- Most up-dated grant manual? And changes hereof?.... Why?

- Most updated assessment manual? And changes hereof?.... Why?

- Target areas – number of UZPs covered ?

  - From 7 to 14, how ? and when?

- Minimum conditions- plans from PD versus reality?

- Allocation formula (is the grant guideline, p. 8 followed?)

  - Basic formula

  - Method for factoring in of the performance element – is the relative performance as per guidelines applied? (p. 9).

  - Maximum allocation per UZP – how does this fit with the performance and incentive system ?

- Fund flow? … Flows, …. Timing?..... Deadline for utilization?

  - Time-span for utilization (when funds have to be utilized)?

- Timing of assessments – start and completion? … First… Second… third – and impact on which FY ?

  - Second assessment impact on FY 2013/14?

  - FY 2014/15 – which assessment will impact on this ?

  - FY 2015/16?

  - Delays – reasons?

  - Future plans to reduce delays?

  - How to ensure that results fit into the local planning process?

- Selection of audit teams, composition etc.?

- System of quality assurance of the assessments?

- System of decision-making on the final results?

- How is CB support linked to assessment?

- Rounds of allocations, timing of these?

  - For the two first rounds?

  - Planned allocations for other FYs?

- Assessments – organization, training etc.?

- Assessments- grievance committee? – when and how? (previously this was not established (see TA – report from November 2013)….

- Approval /final decision on results – assessment committee?

- Publication of results? … nation-wide? … for the UZPss ?

- Use of funds

  - Number of projects funded by the facility?...

  - % on each sector area; (education, health, water and sanitation etc.?)

  - Characteristic of the projects, size, type (infrastructure versus services etc)?

    - MDG targeting?

    - Gender targeting?

  - Autonomy to choose – the investment menu?

  - Plans needs according guidelines (p. 15) to be endorsed by LGD- Project Board ? how is this approval made?....

    - Why is prior ratification needed ? …. Could it be handled through the annual assessment system ?

  - Is the negative list of eligible investments adhered with? Yes…No…

- Links with the departments sector plans?

- Support from the program on CB on planning and PFM?

- How has co-funding worked ? Average level on various projects?

- Impact on service delivery from output 2?

- Impact on relations with sectors?

- Impact on relations with Ups?

- Challenges?

- Future plans on roll out of the UZP grant facility

- Other plans?

Policy level capacity, policy advice and M&E (component 3) (for two programs)

- Main activities under this component?

- Main achievements?

- Strategy for this output?

- PAG?

  - Roles, composition activities etc.?

  - Why has it been hard to establish? future role?

- Strategic framework for the studies:

  - What are the objectives,

  - Strategy and impact?...

  - Why started at the same time ?...

  - Are they based on program evidence? .. How?...

- Next steps in the policy advice and activities?

- National framework for capacity building? Steps taken?... impact? .. challenges?

- Decentralisation policy? . Any development?... What has been the strategy from the programs?... achievements?..challenges?

- Legal framework and status:

  - Results?

  - Challenges? …

  - Future plans?

- How to involve sectors in the decentralization strategic work?

- Lessons learned?

- Future plans for this output?

Links between programs with other initiatives (two programs)

- Synergies between UPGP and UZGP?

- Any links with other initiatives?

- Links with LGSP ? … Has there been a transmission belt of experiences?

- Operational cooperation? …

- Cooperation on M&E?...

- Cooperation CB ?

Aid effectiveness for all components and sustainability (for two programs)

- Effectiveness of the results?

- Efficiency?

- Sustainability ? documentation of this? …

  - Service delivery?

  - Systems and procedures?

  - Capacity created?

  - Prospects for scaling up?

  - Ownership of GoB?...

  - Lessons learned?

  - Challenges?

  - Recommendations?

Future phase of joint programming (for two programs)

    - What are findings and lessons should influence any decision on a future intervention for UNDP and UNCDF and its partners?

    - Any emerging vision, strategy and measures proposed for the planned next phase of programming or, if appropriate, disengaging or continuing UNDP and UNCDF’s local governance programming in the country?

    - What are the remaining challenges and gaps in the area of decentralization in the country? How are various actors positioned to address these? Is there a conducive environment for further progress on decentralization?

    - Do the envisaged overall objectives and results of the next phase of programme seem adequate and relevant in light of the UPGP and UZGP MTE findings?

    - Have key factors (external, programme or partnership related) changed, with respect to those existing at the time of the UPGP and UGZP design, in a way that needs to be taken into consideration for the next phase?

# Annex 6. Questionnaires for the field work

FIELD LEVEL QUESTIONS

- QUESTIONs MARKED WITH BOLD ARE CORE FOCAL QUESTIONS

DISTRICT LEVEL

DDLG, DF, ADC General/Development, Women Development Officer, LGED, others,

Questions to the District level, DFs and Program Support at the Local Level

- Major lessons learned from UPGP… and UZGP….?

- Major achievements UPGP… ? and UZGP?....

  - Capacity building? …. achievements?...

  - Grant system? …. achievements?...

  - Other areas? …. achievements?...

- Lessons learned?....

- Major challenges?......

- Major roles of the DF and the DDLG?.......

- Major activities since start of program?.......

- Activities on HR and good governance?......

- Development in MDG targeting of investments?

- Gender issues and support?.......

  - Tangible evidence of WDF impact on planning and service delivery

- Documented relevance of the program ? … impact? … effectiveness?.... efficiency?... of activities?........

- Workload of program staff?......

- Coordination and synergies with other programs?

  - LGSP?......

  - Other programs, national NGOs, Line Ministries? , MoWCA.........

- Institutional issues?....

  - Views on the program set-up?...

  - Coordination of activities?...

  - Role of the BGCC?...

  - Role of various committees and support to establishment and operations from the Program?....

- Work of the M&E system?

  - General system of M&E?....

  - Reporting system from UPs/UZPs?

  - Coverage and quality?... timeliness? … trends in progress?

    - Achievements?..

    - Challenges?...

- Multiyear Local development planning & budgeting

  - Improvements in the planning approach (inclusive participation, multi-year focus, co-financing, MDG investments)

  - Limiting factors

- Views on the annual performance assessments?

  - Procedures?

  - Achievements and impact?

  - Challenges?

- Sustainability of the support for the overall future results?

  - How are the outputs and capacity created at the local level made sustainable?

  - Scalable?

  - Effective?

- Ideas for the future program?...

- Ideas on the future delivery modalities and future changes?

UPAZILA PARISHAD LEVEL

Informants to be interviewed UZP level:

- UZP Chairman……..

- UZP Vice chairmen…….. (Men and Female VCs)

- UZP members………..

- Women Development Forum representatives

- UNO………..

- If any secretary in support of the UZP?

- 2-3 Representatives from the LMs (LGED, Agriculture, Education, Health, Livestock, Women development offices)………

- Representatives from the Finance Dept/Unit (UZP audit officer)………..

- Representatives from the Planning Dept/Unit (LGED /PIO)………

- Field visits to projects, viewpoint from CBO (if possible) preferable regional NGOs………….

Questions on Upazila Parishads’ capacity:

- Major challenges in capacity and performance since program start-up?

- Relevance and Impact of the program on capacity?

- Challenges?

- Recent trend with the integration of the Line Departments – any changes with this development in the past two years?

- Number of UZP staff?..........

- How can the UZP make use of the LMs staff and coordination of staff?.......

- Capacity in the staffing positions in planning, budgeting and accounting?

- Future recommendations?

Questions on institutional links –UZP- LMs and UPs

- Links with the Line Departments?

  - Links with the decentralized versus centralized depts.?

  - Coordination

  - Have they improved over the past two years?

- Impact of the program on this?

- Challenges?

- Links between the UZP and the UNOs

- Links between the UZP chairman and Vice Chairs

- Role and status of female Vice-Chair?

- Links with the MP and influence of the MP ?

- Links between the UZP chairman and the UP chairmen?

  - Opinion on the UZP Act on institutional issues?

- Future recommendations?

  - Please comment on number of standing committees?... Preferences?

  - Five –year plans?...

Questions on Operations of the UZPs and Governance

- Major changes over the past two years?.... which ?

  - General changes?...

  - Involvement of citizens?...

  - Involvement of women in decision-making?...

- Any impact of the UZGP on these changes?

- Challenges?

- Recommendations?

- Conduction of number of meetings in the UPZ?... how many meetings in FY 2013/14.. How many in FY 2012/13? (any improvements?)

  - Announcement of UPZ meetings?

  - Representation in the meetings .. whom?… numbers? etc.

  - Agenda for the meetings?

  - Minutes of these meetings?

  - Disclosure of these meetings?.... and of the minutes?...

  - Involvement of the LMs in the meetings?

  - Chairmanship in the meetings?... formal and informal?

  - Meetings on the UZP plans?... if so,… when… frequency?

  - Meetings on the UZP budget? …. If so … when…. frequency?

  - Meetings on the UZP progress and annual reports?

- Functioning of the standing committees? … any changes?...

- Disclosure of activities – plans, budgets, projects, accounts, audit reports?

- Project supervision – how, who?

- Procurement? How, how, when? … Project implementation committees?

Questions on the planning and budgeting system

- Progress in planning and budgeting in the past two years?....

- Has the UZGP program supported this? .. how ?

- Challenges?

- Availability of annual plans?.... which year ? … when submitted? .. to whom ?

- Availability of annual budget? … which year? … when submitted? … to whom ?

- Availability of 5-year development plan?

- Content of these plans (chapters, etc.)

- Any use of planning guidelines?

- Any plans to change the planning process?

- How are they formed? who are involved? When?

- Decision-making – who takes the final decision? .. how?

  - How are the citizens involved?...

  - Involvement of women?

  - Project attribution to pro-poor, gender oriented investment priority

- How are the UZP plans linked to : a) UPs’ investments……. B) LMs’ investment plans?...MDG share of investments? Links with NGOs? …

- Upazila Unnayan prokolpo bachay committee (UZP project select committee)? Operations of this?.... and links with the use of grant facility and use of OSR?...

- Are there plans for each sector/LM?

  - How are the ADP grants used ? … division and support of which areas ? links with sector investments?

  - How are the sector plans linked with the UZP planning?

- Which kind of information do you use for the planning – profile of the UZP, development in poverty etc. ?

- Do you have a map of the services/infrastructure?

- Vulnerability and needs assessments?

- How many proposals came up during the last planning exercise? … how many were approved? …

- How do you prioritize?...

- Any planning of maintenance costs implications of projects?....

- Any links between plans and budgets (if both)?...

Questions on Grants (very important)

- Improvements in the grant system over the past two years?

- Impact of the Upazila Grant Facility?

- Challenges?

|  | 2011/2012 | 2012/2013 | 2013/2014 |
| --- | --- | --- | --- |
| Size of the UZP budget |  |  |  |
| Size of the UZGP grant (fiscal facility) revenues |  |  |  |
| Size of income form other grants |  |  |  |
| Size of own source revenues |  |  |  |
| When were the grants from facility received? |  | Date: | Date: |

- Implications of the timing of release of funds?

- When is the information available about the size of the Upazila Grant Facility?

- How are the decisions on use of these made?

- Do you follow the April 2010 ADP Grant guidelines or UZGP OM?

  - What is your opinion about these?

  - Level of autonomy to spent across sectors ?

- Any other guidelines?

- How is the use of funds accounted for?.... any reports?

- Utilisation of grants?

  - Overview and composition of expenditures sources by the grants? FY 2012/13 by sectors and type of investments?

  - Main areas and types of investments?...

  - Gender focused?...

  - Poverty and MDG focused?....

  - Changes over the past two years in type of projects?

  - Impact of the grants on service delivery in general?... poverty reduction?....

| Use of Grants | FY 2012/2013 | FY2013/14 |
| --- | --- | --- |
| Total UZGP grants used? |  |  |
| MDG focused projects? |  |  |
| Gender focused projects? |  |  |
| Other types of projects |  |  |

- Performance assessments – timing of these: When was the performance assessment conducted? Last time ? … the previous one? ..

- Awareness of the assessments?

  - Any Prior information about the assessments?.... How?....

  - How does the LG prepare for the assessment? .. e.g. internal review/assessment?

  - Feedback on the results ? how?

  - Exit conference with the assessment teams and the LG?....

- General views on the assessments

  - 1) Satisfied….2) Neural…. 3) not satisfied…?

  - What is working and is good?

  - Are the assessments objective and neutral ? Yes… No…

  - Timing? Does it fit with the LG planning and budgeting cycle? Yes.. No…

  - Duration?

  - What could be improved?

- Appeal options? Yes… No…

  - Any need for this system? Yes/No…. – did you agree in results? Yes/No….

  - Knowledge about the appeal options? Yes… No…

  - Procedures?...

- Impact of the assessment system on the performance of the UZP?

  - In which areas?....

    - PFM: Yes. … No…

    - Governance (transparency , accountability, etc.): Yes…. NO…

    - Impact on way gender issues are treated?...Yes… No…

    - Other areas… which?

- Do you make use of the assessment results? … How?

- Suggestions for changes in the system

  - MCs?...

  - Performance measures?

Questions on TA/CA support

- Areas in need for Capacity Building support?....i)….ii)…….iii)….

- CB support provided by the program?

  - Training?…

  - Advice?…

  - PEER review support?

  - Other types of support?

- Usefulness of this support from UZGP ? … coverage ? … Modalities?...

- Impact of this CB on the administrative performance of UZP? PFM ?... Accountability? … Operations of democratic procedures? …

- Role of the DF?...

- Suggested changes for the future CB support?

Questions on Financial Management

- Any progress on PFM since the start of the UZGP?... which areas: i)…. ii)……..iii)

- Impact of the UZGP on PFM performance ?

- Challenges?

- Future recommendations?...

- If time permits, the questions below …

- Who is involved in the UPZ PFM process?

- Accounts? Who? .. How ? – are they maintained?

- Cash books and registers ? how, who… are they up-to date?

- Which registers do you maintain for the UPZ functions?... are they up-to-date?

- Bank reconciliation?: Up-to-date?...

- Reporting? … how?... when?-.. to whom?.. (finance and physical progress reports)?

- Auditing… when. … ? who ? … up-to-date?

- How to follow up on the audit findings?

- Who signs the invoices?... when?

- Who controls the spending ?.... against the budget?

- Internal auditing ?

Revenue mobilization

- Size of the own source revenues?..... increase from 2011/12-2012/13?...., 2012/13/2013/14…..? (nominal figures)

|  | 2011/2012 | 2012/2013 | 2013/2014 |
| --- | --- | --- | --- |
| Own source revenues collected |  |  |  |

- Major challenges in revenue mobilization?

- Any autonomy to improve on the size of these?... major bottlenecks in improving these?

- Any changes in the most recent two years in the procedures for revenue mobilization?... which?....

- Any impact of the UZGP on this performance?

- Major challenges?

- Future recommendations?

Questions on Transparency and Accountability

- Any changes over the past 2 years?

- Has the UZGP impacted on this?

- Challenges?

- Recommendations?

- Any interactions with citizens ?.... when? … How? … which areas?....

- Any disclosure of information?

- Role of the RTI Act?...

- Any publication?

- Signposts?

- Any other means of interactions?

- How to account of use of funds? .. OSR? … Grants?....

Gender issues

- Any activities from program to promote gender equality ?

- Achievements and impact of the UZGP?

  - Have they promoted stronger participation?

  - Stronger voice?

- Role of the WDF?

- Composition, links and impact from the standing committee for Women/Children?

- Choice of projects – beneficiaries?

- Means to improve the role of women in development?...

- Impact?

- Challenges?

- Recommendations?

Special Questions at the UP level

Informants to be interviewed:

- UP Chairman

- UP members

- UP Secretary

- Women representatives (if any)

- Other stakeholders

- Selected projects

General Focal Questions:

- Changes of this over the past two years in UP capacity?..... which areas?..

    - Any perceived changes in:

      - i) Planning,

      - ii) PFM,

      - iii) procurement,

      - iv) revenue mobilization,

      - v) transparency,

      - vi) involvement of citizens,

      - vii) gender equity,

      - viii) other areas?

- Impact of the program on these areas?

- Why ? … Why not? …

- Challenges?

- Future recommendations?

- Functional Performance of the UP

  - Operations of Council and Committees?

  - System of UP planning

  - System on PFM

  - System on Procurement

  - Own source revenue mobilisation

  - Governance and decision-making

  - Capacity to tackle cross-cutting issues, gender, MDG, environment etc. in planning, budgeting and implementation?

  - Transparency?

  - Downward accountability – means and tools?

  - Stronger and weaker areas of performance?

- Planning and budgeting process and links with the allocations of grants

  - Has the program impacted on this ? .. how and why ?...

  - Challenges?

  - Suggested changes?

- Test the results quickly on the 41 performance indicators and compared with previous year’s assessment:

  - Why has performance score changed from 1st to 2nd assessment?

  - Impact of the program on this? .. Yes… No…Why?

Questions on Grants (important)

Size of grants and timing issues

- Size of the UP budget FY 2011/12,… 2012/2013… 2013/2014…?

- Size of the UPGP grants received 2012/12….. and 2013/14?.....

- Size of other grants? 2012/2013….. and 2013/14…….?

- Timing of the receipt of grants (2012/2013) Date:… ? and date for 2013/14 ? ….

  - Implications of the delays in allocations? … How is it cooped with? …..

|  | 2011/12 | 2012/13 | 2013/14 |
| --- | --- | --- | --- |
| Total UP budget |  |  |  |
| UPGP grants received |  |  |  |
| Size of other grants |  |  |  |
| Own source revenues |  |  |  |

Use of grants?

  - Overview and composition of expenditures sources by the grants?

  - Main areas and types of investments?

  - Gender focused projects?  %.... and type of projects?...

  - Poverty/MDG Focused?  %... types of projects?

  - How are decisions made?

  - Changes over the past two years? Change in participation and influence of vulnerable groups and women

  - Impact of the program on this composition of utilization of grants?

|  | FY 2012/13 | FY 2013/14 |
| --- | --- | --- |
| Overall UPGP – Expanded performance based grants utilized |  |  |
| Of this Gender focused |  |  |
| Of this MDG /poverty focused |  |  |
| Use on Main sector areas |  |  |
| Education .. |  |  |
| Etc. |  |  |

Performance Assessments

- Timing of these: When was the performance assessment conducted? Last time ? … the previous one? ..

- Awareness of the assessments?

  - Any Prior information about the assessments?.... How?....

  - How does the LG prepare for the assessment? .. e.g. internal review/assessment? ….

  - Internal assessments?

  - Feed back on the results ? how?

  - Exit conference with the assessment teams and the LG?....

- General views on the assessments

  - 1) Satisfied….2) Neural…. 3) not satisfied…?

  - What is working well?

  - Challenges?

  - Objective and neutral ? Yes… No…

  - Timing? Does it fit with the LG planning and budgeting cycle? Yes.. No…

  - Duration?

- Appeal options? Yes… No…

  - Any need for this system? Yes/No…. – did you agree in results? Yes/No….

  - Knowledge about the appeal options? Yes… NO…

  - Procedures?...

- Impact of the assessment system on the performance of the LG?

  - In which areas?....

    - Public financial management: Yes. … No…

    - Governance (transparency , accountability, etc.): Yes…. NO…

    - Impact on way gender issues are treated? Yes… No…

    - Other areas… which?

- Do you make use of the assessment results? … How?

- Do you publish results?

- Suggestions for changes in the system

  - Minimum conditions?...

  - Performance measures?

Own source revenue mobilization

- Trends: Own source revenues: 2011/12……; 2012/2013…… and 2013/14…. ?

|  | 2011/12 | 2012/13 | 2013/14 |
| --- | --- | --- | --- |
| Total revenues |  |  |  |
| Holding tax |  |  |  |
| Other main taxes |  |  |  |

- Impact of UPGP on these trends?.... Why?...

- Challenges?

- Suggestions for the future?

- Transparency on OSR?

- Use of OSR? .. any changes in the past two years? …

- Reasons?

Questions on TA/CA support

- Areas in need for CB?

- CB support provided by the program?

  - Training

  - Advice

  - PEER

  - Other?

- Usefulness of this support ? … coverage ? … Modalities?...

- Impact of this CB on the performance of the UP?

- Efficiency in the support from the UPGP ?

- Role of the DF?...

- Suggested changes for the future CB support?

Gender

- Any changes in the involvement of women in UP operations over the past 2 years?

- Stronger participation?... How?

- Stronger voice ? … How?

- Reasons?

- Impact of UPGP?

- Role of the WDF?

- Challenges?

- Suggested changes?

Questions to Citizens, Community Groups, NGOs, women groups, etc.

- Any knowledge about programs supporting UP ? which ?

- Did you participate in any activities within your UP during last year?

  - Planning and budgeting meetings at UP level?

  - Ward Shavas?

  - Scheme Supervision Committees?

  - Other activities – which

  - Do you feel that anything has changed in the engagement with the UP during last two years?

- Have you benefitted from any development project funded by UP during the past two years ? … Which ?...

- How is the UP supporting women’s priorities/rights in your area?

- Do you receive information from the UP about its operations (budget, plans, projects etc.) ? … How?...

- How can the UP strengthen its relationship with the citizens?

- Do you need more information about the operations of the UPs?... which ?

# Annex 7. Selection of districts, planning and division of field work

The tables below provides an overview of the geographical areas covered and criteria for UZPs and UPs :

Table 4: Sample LGIs

| LGI | District | UZP | UP | Characteristics | Comments |
| --- | --- | --- | --- | --- | --- |
| District 1 | Sirajganj (fluctuating performance for average UP scores) |  |  | Covered by programs (UPGP and UZGP). Average score of UPs in the district: 65 points. | Was included in the first program, the SLGSP, enabling to generate lessons learned. |
| UZP 1.1 |  |  |  | Covered by CB and the Upazila Grant Facility from first year, strong performance (two years coverage of UFF) | Kazipur UZP (77 points in 2014) |
| UZP 1.2 |  |  |  | Covered by CB (covered by the grant facility only one year ) | Ullahpara: (34 points in 2014) |
| UP 1.1.1 (within UZP 1.1) |  |  |  | Strong performance |  |
| UP 1.2.1 (within UZP 1.2) |  |  |  | Poor performance |  |
| District 2 | Rangpur (very weak performance for average UP scores) |  |  | Covered by programs (UPGP and UZGP) Average score 38 points |  |
| UZP 2.1 |  |  |  | Covered by CB and Grant facility, low performance | Pirganj UZP (66 points in 2014) |
| UZP 2.2 |  |  |  | Covered by CB (and facility only one year) | Peergacha (33 points in 2014) |
| UP 2.1.1 |  |  |  | Strong performance |  |
| UP 2.2.1 |  |  |  | Poor performance |  |
| District 3 | Khulna (medium performance for average UP scores) |  |  | Covered by programs (UPGP and UZGP) Average score: 58 points |  |
| UZP 3.1 |  |  |  | Covered by CB and grant facility, average performing UZP | Dumiria UZP (average performance, 69 points) |
| UZP 3.2 |  |  |  | Covered by CB (not facility) | Tarok/Rupska |
| UP 3.1.1 |  |  |  | Strong performance |  |
| UP 3.2.1 |  |  |  | Poor performance |  |
| District 4 | Bramanbari (strong performance for average UP scores) |  |  | Covered by programs (UPGP and UZGP) Average score 69 points | Part of the MIS/OSR piloting activities, which enable a review of these. |
| UZP 4.1 |  |  |  | Covered by CB but not UFF | Sarail Upaziala |
| UZP 4.2 |  |  |  | Covered by CB (not UFF) | Ashuganj |
| UP 4.1.1 |  |  |  | Strong performance |  |
| UP 4.2.1 |  |  |  | Poor performance |  |
| District 5 (Outside of UPGP and UZGP) | Tangal |  |  | Not Covered by programs (UPGP and UZGP) | Located close to Sirajganj, which reduce logistical challenges and enable comparison. |
| UZP 5.1 |  |  |  | No assessments made under the program | Ghatail UZP |
| UZP 5.2 |  |  |  | No assessments | Tangail UZP |
| UP 5.1.1 |  |  |  | Strong performance in the annual performance assessment |  |
| UP 5.2.1 |  |  |  | Weak performance |  |
| District 6 (outside of UPGP and UZGP) | Jessore |  |  | Not Covered by programs (UPGP and UZGP) | Is next to Kulna, reducing logistical challenges and enables comparison. |
| UZP 6.1 |  |  |  | No assessments | Bangher Para Upazila |
| UZP 6.2 |  |  |  | No assessments | Jessore Sadar Upazila |
| UP 6.2.1 |  |  |  | Strong performance |  |
| UP 6.2.2 |  |  |  | Weak performance |  |

Each team had a minimum of two core team members, plus support from the core thematic area experts. In each team, there will be team-members focusing on fiscal issues and one on capacity building issues as well as cross-cutting issues, gender, poverty etc. The data collection teams each produced district reports and a consolidated field reports which served as background for the MTE assessments. The team compositions were:

Table: Division of tasks for the field-work

| Main issues to be covered | Team 1 | Team 2 |
| --- | --- | --- |
| Data Collection |  |  |
| Fiscal issues, PFM, M&E, etc. (output 2) | K M Mahiuddin (3 weeks) | S.M.Firoz Hassan (3 weeks) |
| Capacity building and accountability issues + cross cutting issues /Outputs 1 and 3 | Taiabur Rahman (3 weeks) | Ekram Hossain (3 weeks) |
| Support |  |  |
| Support on cross-cutting issues – gender and service delivery | Salma Akhter (1 week) | Salma Akhter (1 week) |
| Backstopping – general support – fiscal issues | Jesper Steffensen (2 days) | Jesper Steffensen (2 days) |
| Backstopping – CB and accountability issues | Salahuddin M. Aminuzzaman (2-4 days) | Salahuddin M. Aminuzzaman (2-4 days) |
| Backstopping – overall issues, program management, general support and QA + backstopping on all issues in the TOR | Jens Peter Christensen (1 week) | Jens Peter Christensen (1 week) |

The two teams organized the field samplings according to the guideline below.

Table: Timing of the team-work

| Timing | Team one | Team two |
| --- | --- | --- |
| October 12-16 | District XX Day 1: District level visit Day 2: Upazila No. 1 Day 3: UP No. 1.1. Day 4: Upazila No. 2 Day 5: UP No. 2.1 | District XX Day 1: District level visit Day 2: Upazila No. 1 Day 3: UP No. 1.1. Day 4: Upazila No. 2 Day 5: UP No. 2.1 |
| October 19-23 | District XX Day 1: District level visit Day 2: Upazila No. 1 Day 3: UP No. 1.1. Day 4: Upazila No. 2 Day 5: UP No. 2.1 | District XX Day 1: District level visit Day 2: Upazila No. 1 Day 3: UP No. 1.1. Day 4: Upazila No. 2 Day 5: UP No. 2.1 |
| October 26-30 | District XX Day 1: District level visit Day 2: Upazila No. 1 Day 3: UP No. 1.1. Day 4: Upazila No. 2 Day 5: UP No. 2.1 | District XX Day 1: District level visit Day 2: Upazila No. 1 Day 3: UP No. 1.1. Day 4: Upazila No. 2 Day 5: UP No. 2.1 |
| Dates in between district visits = travel time etc. |  |  |
| Submission of field trip findings: no later than November 4, 2014 | LGI reports + consolidated report | LGI reports + consolidated reports. |
| November 4, 2014 | Team meeting to assess the results from the field |  |

The actual data collection plans for the two teams developed can be found in the next annexes.

# Annex 8. Data collection plan, Team 1

Team Members: Professor Dr. Taibur Rahman and Professor Dr. K.M.Mahiuddin

| Date | District | Upzila | UP |
| --- | --- | --- | --- |
| 12-17 October, 2014 | Khulna | Dumuria | Bhandarpur Union Parishad |
|  |  | Dacope | Pankahali Union |
| 18-23 October, 2014 | Jessore District | Jhikargacha | Jhikargacha Sadar Union Parisad |
|  |  | Jessore Sadar Upazila | Nowpara Union Parisad |
| 25-30 October, 2014 | Brahmanbaria | Brahmanbaria Sadar Upazila | Mojlishpur Union Parishad |
|  |  | Sarail Upazila | Pakshimul Union Parishad |

| Khulna District (From 12-17 October, 2014) |  |  |  |
| --- | --- | --- | --- |
| Date | Event | Venue/remarks | Remarks |
| 12 October, 2014 | Travel from Dhaka to Khulna |  |  |
| 13 October, 2014 09.30 am | Meeting with Union Parisad,Atra Gilatala ,Fultala Upazila under Khulna District. | Union Parisad Atra Gillatala |  |
| 13 October, 2014 03.00 pm | Meeting with DDLG and district level line department officials at DC`s Office | DC office |  |
| 14 October, 2014 09.30 -10.00 am | Meeting with DLG, Khulna | DLG Office |  |
| 14 October, 2014 10.00 am | Travel to Dumuria Upazila. Meeting with Upzila Chairman, Vice-chairman, TNO and other Government Officers | UZP, Dumuria |  |
| 14 October, 2014 02.30 pm | Travel to Bhandarpur Union Parishad (Dumuria Upazila). Meeting with UP Chairman, members, Secretary and local beneficiaries/citizens as per requirement | Bhandarpur UP Complex |  |
| 15 October, 2014 08.30 am | Travel to Dacope Upazila . Meeting with Upzila Chairman, Vice-chairmen, TNO and other Government officers as per requirement | Dacope Upzila Complex |  |
| 15 October, 2014 02.30pm | Travel to Pankhali Union Parishad.Dacope. Meeting with UP Chairman, members, Secretary and local beneficiaries/citizens as per requirement | Pankhali UP Complex |  |

| Jessore District (From 18-23 October, 2014) |  |  |  |
| --- | --- | --- | --- |
| Date | Event | Venue/remarks | Remarks |
| 18 October, 2014 | Travel from Dhaka to Jessore | Work in the Hotel/Guest House | Saturday |
| 19 October, 2014 | Meeting with District Government Officers as per requirement | DC Office |  |
| 20 October, 2014 09.00am | Travel to Jhikargacha Upazila. Meeting with Upzila Chairman, Vice-chairmen, TNO and other Government Officers | Jhikargacha UPZ Complex,Jessore |  |
| 20 October, 2014 02.30 pm | Travel to Jhikargacha Sadar Union Parishad. Meeting with UP Chairman, members, Secretary and local beneficiaries/citizens as per requirement | UP Complex |  |
| 21 October, 2014 | Travel to Jessore Sadar Upazila complex. Meeting with Upzila Chairman, Vice-chairmen, TNO and other Government Officers | Jessore Sadar UPZ Complex |  |
| 21 October, 2014 02.30 pm | Travel to Nowpara Union Parishad, Jessore Meeting with UP Chairman, members, Secretary and local beneficiaries/citizens as per requirement | UP Complex |  |
| 22 October | Gap filling |  | Work in the Hotel/Guest House |
| 23 October, 2014 | Travel to Dhaka |  |  |

| Brahmanbaria (25 -31 October, 2014) |  |  |  |
| --- | --- | --- | --- |
| Date | Event | Venue/remarks | Remarks |
| 25 October, 2014 | Travel to Brahmanbaria | Work at the Hotel/Guest House at Brahmanbaria | Saturday |
| 26 October, 2014 | Travel to Mojlishpur Union Parishad (Brahmanbaria sadar) Meeting with UP Chairman, members, Secretary and local beneficiaries/citizens as per requirement | UP Complex |  |
| 27 October, 2014 | 1) Meeting with DDLG and DLG. 2) Meeting with District Government Officers as per requirement | Project Office DC Office |  |
| 27 October, 2014 | Travel to Brahmanbaria Sadar Upazila Complex. Meeting with Upzila Chairman, Vice-chairmen, TNO and other Government Officers as per requirement | UPZ Complex |  |
| 28 October, 2014 | Travel to Sarail Upazila Upazila. Meeting with Upzila Chairman, Vice-chairmen, TNO and other Government Officers as per requirement | Sarail UPZ Complex |  |
| 28 October, 2014 | Travel to Pakshimul Union Parishad (Sarail Upazila). Meeting with UP Chairman, members, Secretary and local beneficiaries/citizens as per requirement | Pakshimul UP Complex |  |
| 29 October, 2014 | Gap filling |  | Work in Hotel/Guest House |
| 30 October, 2014 | Travel to Dhaka |  | Friday |

# Annex 9. Data collection plan, Team 2

Group 2

Team members:

- Ekram Hossain, Communications Manager, BIGD, BRACU, 0171 306 5023, ekram1952@gmail.com

- ASM Firoz-Ul-Hassan, Asst. Professor, JU, 0175 012 2305, firoz_gp_ju@yahoo.com

Overview:

| Date | District | Upazila | Union Parishad |
| --- | --- | --- | --- |
| 11 – 16 October, 2014 | Sirajganj | Kazipur | Maizbari |
|  |  | Ullahpara | Ramkrishnapur |
| 18 – 23 October, 2014 | Rangpur | Peerganj | Peerganj Sadar |
|  |  | Peergacha | Itakumari |
| 26 – 30 October, 2014 | Tangail | Ghatail | Dighar |
|  |  | Tangail Sader | Katali |

Detailed plan:

Trip 1: Sirajganj, 11 – 16 October 2014

Contact persons:

- Ms. Mukti Rani Chakraborty, District Facilitator (DF), UPGP, 0171 284 4228, muktirani15@yahoo.com

- Mr. Matiur Rahman, DF, UZGP, 0171 548 2044, matiur.rahman@uzgp.org

| Date & time | Description | District/Upazila/Venue | Remarks/Comments |
| --- | --- | --- | --- |
| Saturday, 11 October 3:00 pm | Departure from Dhaka for Sirajganj | Stay at Sirajganj Circuit House |  |
| Sunday, 12 October 10:00 am | Sirajganj: Meetings/consultations with DF, DD-LG, DC and other relevant officials of Sirajganj district | DD-LG’s office, DC’s conference room/other venues | Day long meetings, consultations, KII and other means and ways of collecting data |
| Monday, 13 October 10:00 am | Kazipur: Meeting with Upazila Parishad Chairman, Vice Chairs, Members, UNO, WDO, & others relevant, project visits | Upazila Parishad Office, Vice chairs offices, UNO Office, & other in other venues | Day long meetings, Consultations, KII and others |
| Tuesday, 14 October, 10:00 am | Maizbari UP, Kazipur Upazila: Meeting with UP Chairman, Secy., Members, concerned citizens, relevant others, projects visits | Union Parishad Office, and in convenient other venues | Will be selected in consultation with DF |
| Wednesday, 15 October, 10:00 am | Ullahpara: Meeting with Upazila Parishad Chairman, Vice Chairs, Members, UNO, WDO, & others relevant, project visits | Upazila Parishad Office, Vice chairs offices, UNO Office, & other in other venues | Day long meetings, Consultations, KII and others |
| Thursday, 16 October, 10:00 am | Ramkrishnapur UP, Kazipur Upazila: Meeting with UP Chairman, Secy., Members, concerned citizens, relevant others, projects visits | Union Parishad Office, and in convenient other venues | Will be selected in consultation with DF |
| Thursday, 16 0ctober, 5:30 pm | Departure from Sirajganj for Dhaka |  |  |

Trip 2: Rangpur, 18 – 23 October, 2014

Contact Persons:

- Mr. Muhammed Mahbubur Rahman, DF, UPGP, 0171 637 1535, mahbub.undp@gmail.com

- Mr. Jahagir Hossain, DF, UZGP, 0171 246 5804, Jahangir.hossain@uzgp.org

- Mr. Musa . . . . . . . . ., Div. Facilitator, Rangpur, 0171 144 1676

- Mr. Golum Azizul Hoque, Project Assistant, UPGP, 0171 265 8356, gahgem@gmail.com

| Date & time | Description | District/Upazila/Venue | Remarks/Comments |
| --- | --- | --- | --- |
| Saturday, 18 October, 2:00 pm | Departure from Dhaka for Rangpur | Stay at Rangpur Circuit House |  |
| Sunday, 19 October, 10:00 am | Rangpur: Meetings/consultations with DF, DD-LG, DC and other relevant officials of Rangpur district | DD-LG’s office, DC’s conference room/other venues | Day long meetings, consultations, KII and other means and ways of collecting data |
| Monday, 20 October, 10:00 am | Peerganj Upazila: Meetings/consultations with Upazila Parishad Chairman, Vice Chairs, Members, UNO, WDO, & relevant others, project visits | Upazila Parishad Office, Vice Chairs offices, UNO Office, and in other venues | Day long meetings, consultations, KII and others |
| Tuesday, 21 October, 10:00 am | Peerganj Sadar UP: Meetings/consultations with UP Chairman, UP Secretary, Members, concerned citizens, relevant others, project visits | Union Parishad Office, and in convenient other venues | Day long meetings, consultations, KII and others |
| Wednesday, 22 October, 10:00 am | Peergacha Upazila: Meetings/consultations with Upazila Parishad Chairman, Vice Chairs, Members, UNO, WDO, & relevant others, project visits | Upazila Parishad Office, Vice Chairs offices, UNO Office, and in other venues | Day long meetings, consultations, KII and others |
| Thursday, 23 October, 10:00 am | Parul/Itakumari UP: Meetings/consultations with UP Chairman, UP Secretary, Members, concerned citizens, relevant others, project visits | Union Parishad Office, and in convenient other venues | Day long meetings, consultations, KII and others |
| Thursday, 23 October, 04:00 pm | Departure from Rangpur for Dhaka |  |  |

Trip 3: Tangail, 26 – 30 October 2014

Contact Person:

- Dr. Sohel Iqbal, Divisional Facilitator, Dhaka, 0176 770 3380, dr.soheliqbal@yahoo.com

| Date & time | Description/District/Upazila/ | Venue | Remarks/Comments |
| --- | --- | --- | --- |
| Sunday, 26 October, 06:30 am | Departure from Dhaka for Tangail | Stay at Tangail Circuit House |  |
| Sunday, 26 October, 10:00:00 am | Tangail: Meetings/consultations with DF, DD-LG, DC and other relevant officials of Tangail district | DD-LG’s office, DC’s conference room/other venues | Day long meetings, consultations, KII and others |
| Monday, 27 October, 10:00 am | Ghatail Upazila: Meetingsconsultations with Upazila Parishad Chairman, Vice Chairs, Members, UNO, UWAO, & others relevant, project visits | Upazila Parishad Office, Vice chairs offices, UNO Office, & other in other venues | Day long meetings, consultations, KII and others |
| Tuesday, 28 October, 10:00 am | Dighar UP: Meetings/consultations with UP Chairman, Secy., Members, concerned citizens, relevant others, projects visits | Union Parishad Office, and in convenient other venues | Day long meetings, consultations, KII and others |
| Wednesday, 29 October, 10:00 am | Tangail Sader: Meetings/consultations with Upazila Parishad Chairman, Vice Chairs, Members, UNO, UWAO, & others relevant, project visits | Upazila Parishad Office, Vice chairs offices, UNO Office, & other in other venues | Day long meetings, consultations, KII and others |
| Thursday, 30 October, 10 am | Katali UP: Meetings/consultations with UP Chairman, Secy., Members, concerned citizens, relevant others, projects visits | Union Parishad Office, and in convenient other venues | Day long meetings, consultations, KII and others |
| Thursday, 30 October, 5:00 pm | Departure from Tangail for Dhaka |  |  |

# Annex 10. List of people met

Government of Bangladesh, Dhaka

- Md. Shah Kamal, Additional Secretary, Local Government Division, Ministry of Local Government, Rural Development & Cooperatives

- Md. Akram –Al-Hossain, Joint Secretary, Local Government Division, Ministry of Local Government, Rural Development & Cooperatives

- Md. Shafi Ul Haque, Deputy Secretary, Local Government Division, Ministry of Local Government, Rural Development & Cooperatives

- Abul Kashem, Joint Secretary Local Government Division, Ministry of Local Government, Rural Development & Cooperatives, MIE Wing.

National Institute of Local Government (NILG)

- Akramul Hoque, Joint Secretary, Director (on Deputation), National Institute of Local Government

UN Country Office and Project Staff, Dhaka

- Pauline Tamesis, Country Director UNDP, Bangladesh

- Nick Beresford, Deputy Country Director

- Henrik Larsen, Director of the Chittagong Hill Track Programme

- Shaila Khan, Assistant Country Director, Head, Governance Cluster, United Nations Development Programme, Dhaka
Sydur Rahman, Programme Analyst, Local Governance, United Nations Development Programme, Dhaka

- Jesmul Hasan, Programme Analyst, United Nations Capital Development Fund/United Nations Development Programme, Dhaka

- Nazrul Islam, Governance Program Officer

- Ataul Gana Osmani, Communications Office, Upazila Governance Project and Union Parishads Project

- Md. Mozammel Haque, Program Manager, Upazila Governance Project

- Dalia Das, Capacity Building/Training Associate, UZGP and UPGP

- Fauzia Yazdani, International Technical advisor, UZGP, UNDP.

- Mohammed Zahir Uddin, Operations Manager UZGP and UPGP

- Dr. Md. Sarwar Bari (former) Project Manager of UPGP, Deputy Secretary Local Government Division, Ministry of Local Government, Rural Development & Cooperatives

- Miyuki Fujii, Monitoring and Evaluation Analyst, Results and Resource Management Cluster

- Md. Khurshid Alam, Assistant Country Director, Climate Change and Disaster Cluster

- Rystam Pulatov, Program Specialist, Democratic Governance Cluster

- Suresh Balakrishnan, Chief Technical Adviser, UNCDF

UNCDF, New York

- David Jackson, Local Finance Director, United Nations Capital Development Fund, Bangkok

UNCDF, Bangkok

- Shalima Mia, Office Manager

- Fakri Karim, Climate Change /LoCAL program manager

JICA

- Retsu Hagiwara, Deputy Team Leader /Public Financial Management, The Study Project for Integrated Development of Upazilas

- Akiraa Munakata, Adviser, Local Governance, Ministry of Local Government, Rural Development and Cooperatives, Local Government Division

Royal Danish Embassy

- Mogens Strunge Larsen, Counsellor Development

- Mahal Montarin Aminuzzaman, Governance Officer

Upazila Governance Project – locally based staff

- M. Rafiqul Islam, Division Facilitator

Union Parishad Governance Project

- Sk. Iqbal Hossen, District Facilitator, UPGP, UNDP

Second Local Governance Support Project

- Ajit Kuma Paul FCA, Sr. Local Government Audit Specialist, LGSP- II.

- Md. Aminul Islam, Sr. Public Finance Specialist, LGSP 2

World Bank

- Zahed, Khan, Senior Urban Specialist, Social, Urban, Rural and Resilience

Swiss Development Cooperation, Dhaka

- Melina Papageorgiou Trippolini, Programme Manager, Local Governance Portfolio

Sharique Program

- Dr. Lilla Tverdum, Director, Local Governance Program Sharique,

- Tirtha Sarathi Sikder, National Coordinator, Local Governance Programme, Sharique

European Union, Delegation

- Luc Patzelt, Program Manager Governance

Auditors/Assessors

- Muhammed Farhad Hussain, FCA, the Institute of Chartered Accountants of Bangladesh (auditor on LGSP/UPGP)

- M Farhad Hussain, FCA, Managing Partner, Hussain Farhad & Co (auditor)

- Several other audit companies covering all divisions in the country

Others

- Swapan Kumar Sarkar, consultant and previous Joint Secretary, Directorate General, Local Governance Division, Ministry of Local Government and Rural Development

- Tofail Ahmed, previously Governance Adviser on UPGP/UZGP, Dhaka

- Frank Runchel, TL for the design of the coming Danida supported country program

- Hans B. Olsen, Dege Consult, process consultant on the coming Danida supported country program for Bangladesh

The team would like to apologize to any persons met not listed above.

In addition to these stakeholders the MTE met representatives from the 6 districts, 12 UZPs, 12 UPs, DFs, DLGs, WDFs, NGOs, CBOs and civil society. The team has a 30 pages list with overview of these core respondents, and has opted not to include these here. All support rendered from the visits to the field is highly appreciated, none the less, and essential for the conclusion of the assignment.

# Annex 11. List of documents

UP Act 2009

UZP Act 2011

RTI Act 2009

Prodocs

Bangladesh UNDAF 2012-2016

IRRF Indicators

UPGP Final version

UZGP Final version

Latest Annual Work Plan of UPGP, July 2014

Latest Annual work Plan of UZGP, July 2014

UZGP Draft indicator framework 2012

UPGP Draft indicator framework 2012

Review reports

EU report for 2012

EU report for first instalment 2013

EU Report on UP and UZP 2014 Final

Quarterly progress reports

UPGP and UZGP Output Budget against Expenditures 2011-2014

Other support programs

MTR Local Governance Support Project (LGSP-2), 2014

MTR Evaluation Report on LGSP-LIC

Final Evaluation Report on LGSP-LIC

MTR SLGDP

LGSP-LIC - Grants study No 2 (UP Funds flow) - Final

ADR draft report

UZP PA final report

UPGP/UZGP baseline

UNDP Draft Final Report UPGP Baseline 25 August 2013

UNDP Draft Final Report UPGP Baseline 25 August 2013 correction a point

Appendix 1 List of Selected Sample Unions by UPGP District and Control D...

Appendix 2 Tables of Household Survey

Appendix 3 Tables of Stakeholders Findings

Appendix 4 Union Parishad Observation Findings

UZP Baseline Report 2013

Gender

Brief Report on WDF TOT

Brief Write up & Success Stories on WDF

Gender Report for LGD-2013

Module-Capacity Development Training

Module-Gender & Leadership Development

Outline on Capacity Development Training

Outline on Gender & Leadership Training

SDC GEM REPORT 2013

WDF Formation Guideline-District

WDF Formation Guideline-Upazila

WDF Result Capture Report 2013

WDF Sample Bye Laws

Training report format 30 January 2014 (spreadsheet)

WDF ToT format-Master trainer (spreadsheet)

WDF Training Report Format (spreadsheet)

WDF Workshop Report Format (spreadsheet)

Fiscal component

MoU for grants

Latest performance assessment manual for UZGP

Annex 4 UZGP - Upazila Parishad Fiscal Facility Operating Manual 25April...

Annex 5 UPGP - Union Parishad Performance Assessment Manual 13Nov12

Annex 6 UZGP Upazila Performance Assessment Final Report April 2013

Annex 7 UPGP - Union Parishad Performance Assessment Report 2013

Annex 10 UZGP - Upazila Performance Assessment Report_Oct13

Annex 12 UPGP - UPGP 2013-14 Grants Allocation Report May14

Fund Transfer to Bank

PAM Workbook - UPGP Set v2

UPGP-OM - Annex to UP-OM (revised draft November 2012 v6.1 - NTC)

Comparative performance based grants allocations to UPs and Upazilas (two spreadsheets)

EPBG Final Allocation

Scheme list June 2014

Program study reports, guidelines, TORs

TOR for the PAG

Final Report of Upazila study

Need assessment for UZP

TORs and inception reports on studies initiated on local government legal, tax and finance framework

Study on “First Phase of Policy Review of Functional Assignment to Local Governments (Union Parishad and Upazila levels) in the delivery of health and education services” ( Terms of Reference, Inception report, Final report on Component 2 (report on Component 1 is being prepared)

Terms of Reference on “Local Government System in Bangladesh: A Comparative Analysis of Perspective and Practices” (the study has just started last week)

Citizens Perception Survey, 2014

Draft RTI Study, 2014

Assessment of quality and effectiveness of UPGP training, 2014

Assessment of quality and effectiveness of UZGP training, 2013

Facilitator's Guideline, 6th May 2014 - for general training (Bengali)

Materials, UZP-General training, 6th May 2014 (Bengali)

General Training Report (spreadsheet)

PBGS review mission – November 2013

Draft Final Mission Report - Review of PBGs for UPs and UPZs - 2013 - Nov. 8

Note in the Timing of the Annual Performance Assessments-Oct 30

Annex 4- Updated UPGP- Nov 8 - 2013

Annex 5 - New proposed PAM for Upazila Parishads- Nov-8

Annex 6 - Debriefing Note 2013

UPGP M&E

M&E Strategy v2

M&E Guidance notes

Guidance Note....UP Self Assessment Tool_SpiderNet_v2

Guidance Note...Joint Monitoring v2

UP Self-Assessment SpiderNet_Bangla

UP Self-Assessment SpiderNet_Bangla

M&E tools

1. UP visit checklist v2

2. Session Monitoring Checklist v2-1

3. Ward Shava checklist v2

4. UP SC Meeting v2

5. Scheme Monitoring Checklist v2

6. Spot Interview v2

UZGP M&E

M&E tools

MIS flow chart UZGP New

Scheme UFF -format - April 2014 V3

Training report format 30 January 2014

UFF Schemes 2013-14 Execution Ledger 6.8.2014

WDF ToT format 2014 -Master trainer

WDF Training report format 2014

Data flow chart of UZGP

Log frame UZGP Final

M&E Plan of UZGP

UPGP Minutes

1st PB meeting of UPGP

1st PSC Meetings of UPGP

3rd UPGP PB Meeting Minutes_21 May 2014

Minute on 2nd meeting of Project Board of UPGP

Minutes of UPGP 3rd PSC

Signed Minutes of 2nd PSC meeting of UPGP

UZGP Minutes

3rd PB meeting of UZGP

5th PSC of UZGP

2014-07-29 Tender MEG step1,final

Minutes of 1st PSC

Minutes of 2nd steering committee meeting

Minutes of 3rd PSC Meeting

Minutes of 4th PSC Meeting

UZGP 4th Project Board Meeting Minutes

2dn PB meeting of UZGP

# Annex 12. UPGP Results achievements

| UNDAF Outcome Government institutions at the national and sub-national levels are able to more effectively carry out their mandates, including delivery of public services, in a more accountable, transparent, and inclusive manner |  |  |  |  |
| --- | --- | --- | --- | --- |
| Joint Program Outcome Strengthened capacities of local governments and other stakeholders to foster participatory local development service delivery for the MDGs Legal and Regulatory Framework in Place: By end of project, secondary legislation instruments (Rules and regulations) required by UP Act 09 are operational. Baseline: 0 Target: 12 Status: 7 rules (2014) Functional and Institutional Capacity Improved: By end of project, overall compliance with administrative requirements of UP Act 09 by project-supported UPs exceeds 80 % Baseline; Status 2014. 1. 12 UP Monthly Meetings/year: 2. 13 Standing Committees set up: 3. 2 Ward Shavas per year in 9 wards: 4. Five year plans in use: 5. Open budget meeting annually: 6. Citizen Charter in place:; 89 % 74 % 33 % 71 % 87 % 58 %; 93 % 100 % 53 % 91 % 87 % 64 %. Source: MIS Increased citizen involvement: By end of the project, % of women/men (which also include Dalits and Indigenous People) who have attended at least one participatory planning meeting. Target: 50 % increase from baseline. Baseline; Status 2014. Poor HH in Ward Shava (UPGP):; 4 %; 13.9 %. Poor HH in in Ward Shava (other):; 3 %; 10.7 %. Source: Citizens perception Survey, Sept 2014 Pro-poor infra and services: % of citizens who have responded that they are very satisfied with service delivery by their UP. Target: To be determined. Baseline; Status 2014. Satisfaction-poor/marginal UPGP:; 37 %; 65.5 %. Satisfaction other areas:; 26 %; 43.4 %. Source: Citizens perception Survey, Sept 2014 |
| Joint Program Outputs | Baseline value | Target value | Achievement by 2014 | Comments |
| Output 1: Strengthened Democratic Accountability and transparency of the Union Parishads through Citizen Engagement | (Control UP values in brackets) |  |  |  |
| - % of Ward Shavas that transact business according to UP Act 09 | 33 % | 50 % | 76 % (Inception workshop) | Based on 9 sample wards (MIS) |
| - % of target UPs with at least 6 key standing committee producing at least 2 monitoring reports per year. | 74 % (52 %) | 50 % | 100 % (MIS) |  |
| - % of targeted UPs which have at least 1 woman representative participating in officially registered women Development Forum at the Upazila Level. | 61 % | 50 % | 91 % (MIS, Inception workshop) |  |
| Output 2: Strengthened innovations in Pro-Poor and MDG-Oriented Planning, Financing and Implementation of Service Delivery by Union Parishads |  |  |  |  |
| - By end of the project % of targeted UPs have completed comprehensive development plans responding to local MDG assessments that will have also identified needs of the locally relevant most vulnerable groups. | 0 % | 90 % | 91 % (MIS) | Significant improvement, also more targeting towards MDG (sources: APA, CPS, LIC and compared to control group) |
| - By end of the project, 90 % of targeted UPs allocate 70 % of block grant funds to projects explicitly identified as pro-poor (including those responding to vulnerable groups’ needs) or MDG-responsive in plans | Baseline value: 0 % | 70 % | 46 % (source: Data on scheme utilisation from the UPGP MIS). | Significant improvement compared to MDG target in LGSP 37 %, LIC 34 % |
| - By end of the project, % of target UPs comply with 90 % of accounting and record keeping requirements. | - Cash book: 99 %: - Tax collection register: 36 % - Tax assessment register:18 % - Tax defaulter register: 1 % - Asset register: 29 %: |  | The average performance of UPs on PFM and governance indicators has improved from the first to the second APA from 52 to 59 points. (source APA 2012/13 and 2013/14) The average score on bookkeeping and accounting has improved by 8 % from the first to the second assessment, but bank reconciliations have been stable (no improvements), tax management has improved, e.g. tax assessment performance has improved by 26 % from average score 0.99 to 1.26 for all UPs in the target area. Performance on tax defaulter has improved from 0.48 to 0.57 (i.e. 19 %) but is still low (max score is 2 points). Performance on tax register up-date has improved by 10 %. (Source APA from 2012/13 and 2013/14). | The EU progress report refers to the CPS for data, but there is no status in the CPS. The indicator was too broadly defined, and progress on specific indicators should be reviewed, e.g. % of UPs with books of accounts up-to-date and bank reconciliations done |
| - By end of the project, % of increase, on average, or revenue collection in target UPs | Mean holding tax collected: Tk 97,801 | 90 % | Mean holding tax collected: Tk 122,721 According to the MIS for UPGP the % of UPs that collected more holding tax than previous year increased from 25 % in 2013 to 46 5 in 2014. The figure for UPs that used more than 10 % of their OSR on development /service delivery increased to 42 % in 2013 (compared to a target of 20 %). (MIS data from UPGP) | Target was not clearly defined in the Program Document. In 2012, another unclear indicator was introduced: % of UPGP supported UPs that mobilise more than 10 % more revenues than 2 years ago and % of UPs that use more than 10 % of OSR on developed or service delivery |
| Output 3: Strengthened technical capacity of Local Government Division for effective policy review, monitoring, lesson learning and capacity development of LGIs for enhanced Local Governance |  |  |  |  |
| - Number of drafted legislative or regulatory instruments influenced by outcome of piloting activities by the end of the project. |  | 2 | 7 |  |
| - Existence of a National Framework for Local Government Capacity Development by the end of the project. | No draft framework exists | 1 | 0 |  |
| - Implementation of a functioning M&E and MIS system in the Monitoring, Investigation and Evaluation Wing of LGD ( capturing key data on local government performance) by the end of the project. | Baseline: Only a project based MIS(and in early design stage) is used by LGD |  | 1st phase completed. A general manual MIS system is up and running in the 564 UPs covered, and a computerised MIS in the 146 is being piloted. System is planned to be rolled out in 2014 and 2015, and linked to the LGD system. | As per the M&E strategy |
| - Number of DLGs who have a sustainable system for monitoring and backstopping local governments by the end of the project. | Baseline: No system in place |  | Joint monitoring implemented, but still rather project specific. The system is still to be mainstreamed with the system in the M&E Wing of LGD. |  |

# Annex 13. UZGP Results achievements

| UNDAF Outcome Government institutions at the national and sub-national levels are able to more effectively carry out their mandates, including delivery of public services, in a more accountable, transparent, and inclusive manner |  |  |  |  |
| --- | --- | --- | --- | --- |
| Joint Program Outcome Joint Program Outcome (if different from UNDAF Outcome) , including corresponding indicators and baselines, Project Outcome: Strengthened capacities of local governments and other stakeholders to foster participatory local development service delivery for the MDGs Legal and Regulatory Framework in Place: No. of effective secondary legislation instruments required by UZP Act 09 by the end of the project Baseline: 5 Target: 13 (2016) – 2012 revision Status: 6 rules + 3 regulations drafted and under review (2014) – one rule on taxation under preparation Functional and Institutional Capacity Improved: No. of UZPs that have adopted internal rules and by-laws including an anti-corruption strategy and a Citizens’ Charter by the end of the project Baseline: 0 % Target: 50 % (2016) – 2012 revision Status: (2014): Citizen Charter was available in 100 % upazilas of project area and in 84.6 % upazilas of control area. (CPS, p. 113) It was found through the self-reported check lists, that Citizen Charter was displayed in 100 % of the upazilas in project area compared to 76.9 % of the upazilas in control area. Democratic Accountability: % of citizens aware of the roles and responsibilities of UZP Baseline: 33.2 % - 32.55 % in non-program area Target: NA Status: 77.5 % (2014) – 73.3 % in non-program area (CPS, p. 113) Pro-poor infra and services: % of citizens satisfied with services specifically targeted by Upazilas through pro-poor and MDG-responsive planning Baseline: 12.9 % - 15.15 % in non-program area Target: NA Status: 57.5 % - 40.3 % in non-program area (CPS, p. 115) |  |  |  |  |
| Joint Program Outputs |  |  |  |  |
|  | Baseline value | Target value | Achievement by 2014 | Comments |
| Output 1: Strengthened Upazila Parishads as more functional, democratic, transparent and accountable institutions | (Control UZP values in brackets) | No targets stated at output level in PD | (Control UZP values in brackets) |  |
| - Percentage of women and men UZP councilors who report they can participate effectively in debate and influence decision making by the end of the project.. | 27.2 % (42.3 %) |  | 40 % (MIS) |  |
| - Number of UZPs with are compliant with at least 90 % of the provisions of the Right to Information Act By the end of the project | 35.71 % (21.4 %) |  | 14 UZPs, i.e. all in the target area (100 %) (92.3 %) |  |
| - Average number (!) of key standing committees functioning in UZPs by the end of the project. | 34.6 %! (74.8 %) |  | 85.7 % (76.9 %) | Percentage of UZPs having formed all 17 standing committees (no reporting on average numbers) |
| - Number of women’s development fora registered at the District level by the end of the project. | 6 (3) |  | 23 191 at UZP level |  |
| - Number of UZPs that have prepared a “Citizen's Charter” incorporating arrangements for UZP-constituent relations by the end of the project. | 85.7 % (92.85 %) |  | According to the CPS, Citizens Charter was available in 100 % Upazilas of project area and in 84.6 % Upazilas in control area. It was found that Citizen Charter was displayed in 100 % of the Upazilas in project area compared to 76.9 % of the Upazilas in control area (p. 77). |  |
| Output 2: Strengthened Planning and Budgeting system at UZP with MDG orientation and pro-poor service delivery mechanism |  |  |  |  |
| - Number of line department activities integrated with UZP plans and budget | 0 (0) |  | 17 Line Department in all the 64 UZPs | UFF has linked Line Dept |
| - Number of participating UZP that have produced development plans responding to local MDG assessment and identifying needs and actions related to the most vulnerable groups (such as the *Dalits or other locally relevant excluded groups) by end of project | 0 (0) |  | 13 % for the entire country but 100 % of the targeted areas. (monitoring reports) According to the Citizens Survey (September 2014), UZP in the target areas have higher focus on MDG 8 out of 14 UZPs compared to 6 out of 14 in the control group (p. 80) Confirmed by the MTE field work. | In comparison to 487 UZPs (64 UZPs out of 65 UZPs in 7 target Districts) Planning is responding more to MDG needs (FYP and annual plans) |
| - Number of participating UZPs with development plans that have at least one development intervention addressing needs of the identified most vulnerable groups (such as the Dalits or other locally excluded groups). | NA |  | 15 % of all projects supported by the UFF grants | 9 out of 14 UFF targeted UZP has schemes for vulnerable groups in Fy 2013/14 (17 schemes are targeted) (field work, CPS) |
| - Percentage of performance based grants allocated to projects identified as MDG-responsive in annual development plans in final year of project. | First round PMS |  | 81 % (2014) | Performance assessment outcome |
| Output 3: Strengthened technical capacity of Local Government Division for effective policy review, monitoring, lesson learning and capacity development of LGIs for enhanced Local Governance |  |  |  |  |
| - Number of legislative or regulatory instruments influenced by outcome of piloting activities by the end of the project. |  | 2 (UP) NA (UZP) | 7 Rules/1 Regulation/1 Guideline (UP), 6 Rules/3 Regulations (UZP) |  |
| - Existence of a National Framework for Local Government Capacity Development by the end of the project. | No draft framework exists | 1 | 0 |  |
| - Existence of a functioning M&E and MIS system in the Monitoring, Investigation and Evaluation Wing of LGD ( capturing key data on local government performance) by the end of the project. | Only a project based MIS(and in early design stage) is used by LGD |  | M&E tools are piloted and MIS system are introduced in the field as pilot basis. However the system is not mainstreamed with the LGD MIE Wing, which is a planned activity for 2015. | Point score 1+1+1+1+5 in 2012 framework revision = max 9, - but not reported against |
| - Number of DLGs who have a sustainable system for monitoring and backstopping local governments by the end of the project. | No system in place | 7 | M&E tools are in final stage to printing and hand over to DDLG, DLG for backstopping. Regular monitoring missions are taken place, and LGIs in the project area are reporting on a quarterly basis using the M/E tools and checklists. | M&E tools in place for DLG/DDLG backstopping |

# Annex 14. Ongoing and planned policy support studies

| # | Study | Who conduct this (consultant (s)) | Start ? | Expected completion | Status? | Objective? | Links to other studies? | Reports produced so far? | Comments on the study approach etc. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Mapping of Fiscal flow and local government financing in Bangladesh | Local Consultant Dr. Mohammad Mahfuz Kabir [Senior Fellow, Bangladesh Institute of International and Strategic Studies, BIISS] | 1 July 2014 | 30 November 2014 | Final draft | Mapping/review of financial flow mechanism including streams of financial flow, average size of fiscal resource pool and level of fiscal decentralization from central to LGIs and derive recommendations for LGD for effective fiscal decentralization | This study is closely linked to the following studies: Functional Assignment (health & education) related policy study; Review of local government revenue regimes | Inception Report | KII. The study has provision of field visit to India, which will allow to collect good practices for a comparative analysis |
| 2. | Review of local government revenue regimes of Bangladesh towards prospect of a uniform local government taxation schedule /revenue policy | Local Consultant AMM Nasir Uddin [Former Secretary, Government of Bangladesh] | 1 July 2014 | 30 November 2014 | Inception report submitted; interview with Key Informant is ongoing | Review of tax schedules of various Local Governments units, and derive recommendations for LGD on prospect of a uniform local government taxation schedule/policy | This study is closely linked to the following study: Mapping of Fiscal flow and local government financing; | Inception Report | Review the previous study on revenue mobilization, national revenue policies, tax schedules of various LG units and consult with stakeholders. A field visit to neighbouring India |
| 3. | Review of local government laws of Bangladesh towards prospect of a local govenrment uniform/framework legislation as mother law | Consultant Dr. Mohammad Nazmuzzaman Bhuian | 1 July 2014 | 30 November 2014 | Final draft | Review of key laws on various Local Governments units, and derive recommendations for LGD on prospect of a local government framework/uniform legislation as Mother Law with directives for LG unit legislations | This study is closely linked to the following study: Local Government System in Bangladesh: A Comparative Analysis of Perspective and Practices | Inception Report | Review of secondary materials including constitutional and legal provisions and international practices, and consult with stakeholders. A field visit to neighbouring India |
| 4. | Study on key rights and entitlements for poor and disadvantage citizens where RTI (Right to Information) Act can be effective | Local Firm IRG Development Ltd. | October 2013 | August 2014 | Final draft submitted | Identify basic rights and entitlements in relation to which poor and disadvantaged citizens face challenges and identifying how RTI act can be used to address these challenges. | Linked to Citizen Perception Survey | Inception report, final draft report | Due to political unrest in later part of 2013 and early 2014 the study took more time than stipulated. This is a qualitative study based on FGD, KII, etc. |
| 6. | Citizen Perception Survey on Services Provided by Local Government Institutions as well as Assessment of Results Achieved by UZGP and UPGP | Local Firm The Survey and Research System (SRS) | November 2013 | August 2014 | Final | Find out the understanding how citizens perceive and value services made available by Local Government Institutions, and to assess the results achieved so far by UZGP & UPGP against their respective annul workplan. | Linked to study on Right to Information | Inception Report, Final draft | Due to political unrest in later part of 2013 and early 2014 the study took more time than stipulated. The approach includes Household survey, FGD, KII and Case Study |
| 7. | First Phase of Policy Review of Functional Assignment to Local Governments (Union Parishad and Upazila levels) in the delivery of health and education services | Dr. Jamie Boex, Dr. Arfina Osman, Dr. Mokshedul Hamid, Mr. Abdul Hannan | April 2014 | October 2014 | Inception report and report on Component 2 submitted; report on Component 1 is being written | conduct the policy review of the current assignment of functions to Local Governments (Union Parishad and Upazila levels) in delivering of health and education services, and develop a knowledge platform for LGD to facilitate dialogue between relevant stakeholders on clarifying and improving the assignment functions and expenditure in these sectors | Linked to the study on Local Government System in Bangladesh: A Comparative Analysis of Perspective and Practices | Inception report and report on Component 2 submitted | Policy analysis, field data collection and KII |
| 8. | Local Government System in Bangladesh: A Comparative Analysis of Perspective and Practices | Dr. Jamie Boex, Dr. Nizamuddin Ahmed, Dr. Mobasser Monem and Dr. Pranab Panday | September 2014 | December 2014 | Just started | Analyse the local government system in Bangladesh, particularly focusing on institutional and legal frameworks within which local governments operate in Bangladesh. It will also draw a comparative picture between local government system in Bangladesh and systems that are being practiced in some other countries. | Linked to the study First Phase of Policy Review of Functional Assignment to Local Governments (Union Parishad and Upazila levels) in the delivery of health and education services | None | Policy analysis, field data collection and KII |

# Annex 15. UPGP monitoring plan

# Annex 16. UZGP monitoring plan

# Annex 17. Overview of Fund Utilization

| Union Parishad Governance Project (UPGP) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Output-wise Budget and Expenditures |  |  |  |  |  |  |  |  |
| For the period covering from inception - 10 November 2014 |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | In USD |
| Cost items/Outputs |  | Actual Expenditure 2012 | Actual Expenditure 2013 | Actual Expenditure (Jan-10 Nov. 14) | Cumulative actual expenditure (Inception - 10 Nov. 2014) | Cumulative expenditure (in %) | Total project budget (2011-2016) | Total project budget balance (10 Nov. 2014-Dec 2016) |
|  |  | A | B | C | D=A+B+C | E = (D/F) % | F | G=F-D |
| Programme Costs: |  |  |  |  |  |  |  |  |
| Output 1 |  | 65,121 | 625,462 | 69,354 | 759,936 | 41 % | 1,834,250 | 508,497 |
| Output 2 |  | 224,593 | 2,124,024 | 2,529,486 | 4,878,103 | 47 % | 10,316,899 | 5,843,068 |
| Output 3 |  | 11,156 | 126,719 | 512,383 | 650,257 | 31 % | 2,100,263 | 1,782,960 |
| Output 4 |  | 99,525 | 685,955 | 416,425 | 1,201,905 | 53 % | 2,267,658 | 1,171,803 |
| Total Programme Costs |  | 400,394 | 3,562,159 | 3,527,648 | 7,490,201 | 45 % | 16,519,070 | 9,306,328 |
| Indirect Support Costs: |  |  |  |  |  |  |  |  |
| GMS and AA fee |  | 20,194 | 141,876.54 | 152,463 | 364,617 | 38 % | 967,190 | 602,573 |
| Total Indirect Support Costs |  | 20,194 | 141,877 | 152,463 | 364,617 | 38 % | 967,190 | 602,573 |
| Unprogrammed budget |  |  |  |  |  |  | 904,848 | 904,848 |
| Grand Total |  | 420,588 | 3,704,035 | 3,680,111 | 7,854,819 | 43 % | 18,391,108 | 10,813,748 |

| Upazila Governance Project (UZGP) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Output-wise Budget and Expenditures |  |  |  |  |  |  |  |  |
| For the period covering from inception - November 10, 2014 |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  | In USD |
| Cost items/Outputs |  | Actual Expenditure 2012 | Actual Expenditure 2013 | Actual Expenditure (Jan-June 14) | Cumulative actual expenditure (Inception - June 2014) | Cumulative expenditure (in %) | Total project budget (2011-2016) Including unfunded budget | Total project budget balance (July 2014-Dec 2016) |
|  |  | A | B | C | D=A+B+C | E = (D/F) % | F | G=F-D |
| Programme Costs: |  |  |  |  |  |  |  |  |
| Output 1 |  | 410,618 | 1,506,241 | 2,103,450 | 4,020,309 | 58 % | 6,024,712 | 2,004,403 |
| Output 2 |  | 352,916 | 354,017 | 961,703 | 1,668,636 | 16 % | 6,797,785 | 5,129,149 |
| Output 3 |  | 245,059 | 122,324 | 298,969 | 666,352 | 17 % | 2,689,525 | 2,023,173 |
| Output 4 |  | 425,889 | 1,017,214 | 704,578 | 2,147,681 | 74 % | 2,687,712 | 540,031 |
| Total Programme Costs |  | 1,434,482 | 2,999,796 | 4,068,701 | 8,502,979 | 38 % | 18,199,735 | 9,696,755 |
| Indirect Support Costs: |  |  |  |  |  |  |  |  |
| GMS and AA fee |  | 62,642 | 42,942 | 96,541 | 202,125 | 10 % | 1,113,181 | 911,056 |
| Total Indirect Support Costs |  | 62,642 | 42,942 | 96,541 | 202,125 | 10 % | 1,113,181 | 911,056 |
|  | Unfunded budget USD 12,54,027 |  |  |  |  |  |  |  |
| Grand Total |  | 1,497,124 | 3,042,738 | 4,165,242 | 8,705,104 | 37 % | 19,312,916 | 10,607,812 |

# Annex 18. APA Timing and EPGS Disbursements

This Annex reviews the timing of the assessments vis-à-vis the Union Parishads’ and Upazila Parishads’ planning and budgeting cycle and planned timing. Although the assessments have been delayed from the on-set with about 1.5 years, especially due to the project start-up and delays in contracting, it appears that with multi-years contracted and speed up of the process, the delays are expected to brought down to some months. However, by end of project, the system is not expected to be fully synchronized with the UP and UZP planning and budgeting process, which is completed by UPs and UZPs in May prior to each FY.

As per international good practice, the UPGP and the UZGP were designed in a manner whereby the annual performance assessments (APAs) were supposed to fit with the UP and UPZ planning and budgeting processes, such that the results from each year’s APA would be ready prior to the start of the local planning and budgeting process with a well-known budget figure for the coming Fiscal Year. Assessments were to be carried out in year N (“assessment year”) of the performance of Year N-1 (“performance year”, i.e. last Fiscal Year), with impact on Fiscal Year: N+ 1 (“allocation year”, i.e. next Fiscal Year).

According to the first draft Grant Operational Manual, the APA should ideally be completed in December/January prior to the allocation year, and should follow the calendar below:

- April (two years prior to the allocation year): Process of procurement of assessment teams;

- August: training of the teams and information to the LGs (in the year prior to the allocation);

- August /September: internal assessments (in the year prior to the allocation;

- September /October audit and external assessments (in the year prior to the allocation)

- November information about preliminary results (in the year prior to the allocation);

- December quality assurance, possibility of appeal, review in the assessment review committee (in the year prior to the allocation);

- December/January in the year prior to the actual allocation year: Final decision on the results and official announcement:

- July/August first allocation of funds

- January/February second allocation of funds

It was acknowledged that there would some delays in the first assessment due to project start up and that the first results from the FY 2010/11 Performance Year, would be ready by March /April 2012 only, but that the process could be speeded up from then on to match the above-mentioned objectives.

However, in reality the first assessment of the UPs took place in March/April 2013 of the performance of FY 2010/11 (more than a year late), and with allocations in the last month of the FY 2012/13 (June 2013), i.e. without time for UPs to plan and budget with a known budget envelope. Second, assessment of performance year FY 2011/12, started April 2013, and was completed in May 2014, for allocations for FY 2013/14, i.e. after the start of the FY 2013/14 (i.e. was also more than a one year after the original schedule). Assessment of the performance year FY 2012/13 has started and is expected completed by October/November 2014 (from the field work it was clear that some audits were conducted by September) for allocations in FY 2014/15, and it is hoped that the performance assessment of FY 2013/14 can be completed by June 2015 for grant allocations in 2015/16 (i.e. then about 4 – 5 months behind the original schedule, which was January /February 2015 to allow the results to be integrated in the planning and budgeting process at the local level).

Similarly for the assessments of the UZP performance, where the first assessments were completed in April 2013 of the performance of FY 2010/11, with impact on FY 2012/13, and with allocation of the first tranche only in the last quarter of the Fiscal Year FY2012/13 (April/May 2013), and where the second tranche for FY 2012/13 was subsequently allocated in second part of 2013.

The second assessment was completed by November 2013 (but only announced to UZPs in June 2014), of the Performance Year FY 2011/12, with impact on the allocation year FY 2013/14. Hence the allocations of the second year’s allocation (supposed to be in two tranches in FY 2013/14) was done in the last part of the FY, May 2014 for the first tranche, and second tranche was only released in September in the following FY which is FY 2014/15, i.e. after the end of the FY, which has already started on July 1, 2013. Hence, there are no options for the UZP to plan and budget in accordance with the results and well-known budget envelopes, and the UZP then makes an additional round of planning with the new coming funds.

Although these delays in assessments, and allocation is well known from many other countries, it is utmost important that the assessment, allocations and planning and budgeting cycle of LGIs are synchronised so that the LGIs know the amounts available prior to the start of the planning and budgeting process for the next Fiscal Year. The challenges have been mitigated by the fact that LGIs have been allowed to spend funds in the subsequent FY, but still it is not synchronized with the planning, and the delays has also lead to other delays in disbursements, as some of the DPs have requirements on spending levels prior to release of funds (EU).

The table overleaf shows the timing of assessments against planned timing.

Table 1: Overview of Ideal and Actual Timing of Assessments

| Planned timing | Actual Timing | Implications |
| --- | --- | --- |
| First Assessment for Upazila Parishads (Performance Year FY 2010/11) |  |  |
| Ideally it should be conducted in Sept-Dec. 2011 of Performance in 2010/11, but it was planned for March/April 2012 due to late project start (which ended up being even later) | Actually conducted in December 2012- March 2013 For 2012/13: 1st tranche in April 2013 to 7 UZPs (BDT 17,478,650), second was transferred by the end of 2013 in December: BDT 17,521,350. The transfers were supposed to be in July 2012 and January 2013 for FY 2012/13 according to the original design. All funds are used. | No options for UZP to include the amounts in the plans and budgets for FY 2012/13. Short time to utilise the funds, and allocations of two fiscal years budget in one FY (2013/14), i.e. half of FY 2012/13 and FY 2013/14’s allocations. Allocations in one FY may be impacted by several assessments and their results, and allocations. Time-lags between performance and actual allocations of up to more than 2 years. UZPs will have to decide on the spending as a top-up of their annual plan, but will typically use projects already identified in the five-years plans, and will have to meet another time in the UZP to decide on the priorities. |
| Second Assessment of UZP |  |  |
| Sept-Dec. 2012 of the performance in FY 2011/12 with impact on allocations for FY 2013/14. | April-October 2013, but only announcement of results by end of the FY in June 2014. For 2013-14: 1st Tranche: to new 7 UZPs on 19 May 2014, BDT: 17282175 1st Tranche: to old 7 UZPs on 18 June 2014, BDT: 17,717,825 (prior to receiving of their report). 2nd Tranche: to all 14 UZPs on 11 September 2014, BDT: 35,000,000 | As above. (i.e. more than a year delayed). UZP will have to spent FY 2013/14 allocations in FY 2014/15, and allocations are not synchronized with the UZP fiscal year. UZP will then have to pick projects from their development plan and have an extra round of prioritisation during a UZP meeting. |
| Third assessment of the UZP |  |  |
| Sept-Dec. 2013 of the performance in FY 2012/13 with impact on allocations for FY 2014/15. | Assessment firm appointed (BIM), and assessment expected completed by end of 2014 of the 65 UZPs. Allocations are planned to be in the second part of FY 2014/15. | This means that the allocations will be in the second part of the FY, and that information will be after the completion of the planning and budgeting process for this FY. FY 2014/15 allocations will have to be rolled over to FY 2015/16 and not be synchronised with the planning and budgeting process as well as the fiscal year. |
| Union Parishads First Assessment |  |  |
| Sept. – December 2011 (with some delays expected, March 2012) | Completed May 2013. First tranche allocated in the last month of the FY 2012/13, June 2013 versus the plan, which was in July 2012 and January 2013. The full tranche was allocated with deadline for utilisation December 2013. | As above (1.5 years delayed). Funds are utilised in the FY after the allocation year. UPs will have to decide on the spending as a top-up of their annual plan, but will typically use projects already identified in the five-years plans. |
| Second Assessment of UPs |  |  |
| Sept. – Dec. 2012 of the performance in FY 2011/12 with impact on FY 2013/14. | May 2013-May 2014. All funds allocated in the last month of the FY, i.e. in June 2014 for FY 2013/14 with a deadline for utilisation in the subsequent FY (December 2014). | As above. (about 1 year delayed). Funds are used in the FY after the allocation year. |
| Third Assessment of UPs |  |  |
| Sept. – Dec. 2013 of the performance in FY 2012/13 with impact on FY 2014/15. | May 2014- expected completed in October /November 2014 of the performance of UPs in FY 2012/13 with impact on fiscal allocations for FY 2014/15. | Will be about 11 months delayed compared to design. Decisions will have to be taken on the duration of the use of funds and deadlines. |
| Fourth Assessment of the UPs |  |  |
| Sept. – Dec. 2014 of the performance in FY 2013/14 with impact on FY 2015/16. | (Expected): January–June 2015 with impact on allocations for FY 2015/16 | Results are ready prior to the FY, but not prior to the start of the UP planning and budgeting process. I.e. the allocation can be synchronized with the FY, but will results will not yet be ready prior to the UP planning and budgeting process. About 5 months delayed compared to original design. |

The implications of this are that:

- UPs and UPZ have no chance to integrate the results in the local planning and budget processes, which the programs are supposed to support and monitor;

  - For the UPs, it is easier to predict what they may receive (although delayed) and they will over time know that funds are about 1 year delayed, however, they can only make rough estimates prior to the planning process as they are not sure about their relative performance and thereby the exact grant figures;

- Funds are allocated in the end of a FY, within limited options for local governments to spend the funding on time, and with negative impact on the possibilities to achieve planned targets (which is also being assessed in the performance of the UPs/UZPs in the annual performance assessments);

- The linkages between planning, budgeting and project execution are getting blurred;

- Some FYs will have allocations from several allocation years, as assessments are completed before funds from previous assessments have been fully released.

- It will be frustrating for local governments to be assessed on indicators, which systemically cannot be achieved due to delays in announcement of results and late transfers compared to design.

- However, especially for the UPs, they are used to the delays and can factor in some parts of it, as the fund allocations are about a year delayed and as they can roll-over the funds to the new FY, and as most of the LGIs have five-years plans, they selected projects from this plan when the allocations are known, and add some new decisions to the annual plans and budgets.

Suggestions during a TA-review mission in November 2013 to bring the system in harmony with the fiscal years were not approved. Options could have been the following:

Union Parishads – Discussions of options to speed up the process:

Option 1) The results of the assessment of performance in (at this point of time) FY 2011/12 would be triggering the allocations for two Fiscal Years, i.e. the coming nearly completed assessment will have impact on allocations for both FY 2013/14 (as it was supposed to have), and FY 2014/15, and this would mean that UPs can plan properly from the coming planning and budgeting cycle, starting January 2014 for FY 2014/15.

The assessment to be conducted in September /October 2014 will then review both the FY 2012/13 and the FY 2013/14 and impact on allocations for FY 2015/16 performance and an average scoring could be made of the results of the two years (or alternatively only on the last FY 2013/14). This could, in fact be the future principles for the pilot, as average score will reduce the variations in allocations from year to year, and move toward a multi-year budgeting process. However, it any case it is important to adjust to the budget cycle as soon as possible.

Option 2) Conduct the assessments nearly on the same time (i.e. start another assessment immediately) to ensure that the process is speeded up, but this will still be hard due to contracting issues, delays, etc. and UPs may be surprised that another assessment starts just after completion of the recent one. Second, it was expected that it would not be possible to complete this in time before several rounds of assessments have been completed, which will then lead to a situation where this is not fixed before the end of the program.

This latter the option was actually pursued, and the future will see some improvements, although not ideal, see above.

Upazila Parishads:

A review of the delays in November 2013, discussed the implications of this for the local planning process. The future system of timing of the assessments will be influenced by the recent decision in the program board to ensure that UZPs are selected on the basis of performance. This means thall all 65 UZP in the 7 districts will have to be assessed in order to identify the best 2 performing UZPs in each district. The question was then the phasing in/start of this system, i.e. either from next assessment, which was undertaken immediately, or from the assessment from September –November 2014 with impact on FY 2015/16. Hence, in November 2013 two options were outlined:

Option 1: To use the results from the second assessment (expected completed primo November) for allocations in both FYs 2013/14, and FY 2014/15, and then start with the new system of full assessments from September –November 2014, with impact on budget allocations from FY 2015/16.

Option 2: Immediately start the procurement and as fast as possible conduct the assessments of the 65 UZPs for screening, and identification of UZPs, which comply with the MCs and which are the best performing. This will then impact on the allocations for FY 2014/15. However, if the results of the assessments should fit wit the UZP planning process for FY 2014/15, they should have been ready by February 2014. A sub-option to this was only to make the assessment for the 65-14 UZPs, as the 14 have just been assessed, and then use these results for the coming allocations in FY 2014/15, with announcement of budget figures in February 2014.

The option to conduct the assessment of all 65 UZP was chosen, and the delays are then expected to continue for some time, unless the assessments starts immediately after each other’s, and are speeded up an completed earlier on to fit into the UZP planning and budgeting process, and not as an addendum by the end of the year to this or in the following FY.

# Annex 19: Trends in Performance from First to Second APA.

# Annex 20. Framework for UP Performance Measurement

# Annex 21. Comparison of the Performance on the Common 12 Performance Measures between the 1st and the 2nd APA

# Annex 22. Scheme Information under the Performance Block Grant of UZGP FY 2012/13

Name of the Upazila: Pirgonj

Total Performance Grant Received (in Taka): 59,63,032 (1st and 2nd installments)

Total budget without co-finance: 59,63,032

Total co-financing amount: 800,000

Total budget with co-financing: 6,763,032

| Sl N | Name of the Project | Sector/Department | Name of the place of the project (UP/UZP) | Duration |  | Budget In TK | Financing Source (Single or Co Finance) | Financing Proportion in TK (in case of co-financing) | MDG goal Compliance (State the goal Number) | Implementation Department in UZP | Number of Beneficiaries anticipate (Female: Male) | Any Remark |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Start | End |  |  |  |  |  |  |  |
| 1 | Cultivation of medicine plants for creating employment and increase income of the poor farmers | Agriculture | UZP | Sep/13 | Dec/13 | 396,000 | Co-financing | 50,000 | Goal-1, 4,5,7 | Agriculture depart. | 875 persons | 15 UPs |
| 2 | Reducing drop out rate and improving the quality of education through provide school uniforms and bags among children | Education | UZP | Sept/13 | Dec/13 | 7,50000 | Single |  | Goal-2,3 | Primary Education | 1500 children |  |
| 3 | Improving sports activities through providing sports materials to the educational institutions | Education | UZP | Sep/13 | Dec/13 | 4,79,000 | Single |  | Goal-2,3 | Primary & education depart. | 23,950 students | 479 schools In 15 UPs |
| 4 | Recognizing and encouraging the best performing students and best performing schools by providing rewards | Education | UZP | Sept/13 | Dec/13 | 328,000 | Single |  | Goal-2,3 | Primary education depart. | 656 students | 328 schools |
| 5 | Reducing child and maternal mortality by Imparting training on ”Family planning and Pregnant mother care” | Health & Family Planning | UZP | Sep/13 | Dec/13 | 352,500 | Single |  | Goal-4,5 | Family planning Depart. | 450 mothers | 15 UPs |
| 6 | Supply of Ring Slab for ensuring 100 % sanitation in Upazila area | Water & Sanitation | UP | August/13 | Dec/13 | 500,000 | Co-financing | 100,000 | Goal-4,5,6,7 | DPHE | 2500 beneficiaries | 500 families |
| 7 | Ensuring safe drinking water by supplying tube-wells with making platform and support for Arsenic testing in the upazila area | Water & Sanitation | UZP | Sept/13 | Dec/13 | 800,000 | Co-financing | 100,000 | Goal-1,4,5,7 | DPHE | 1000 families | 200 tube-wells |
| 8 | Develop women entrepreneurs on ”Sataranji” through skill training and the necessary support . | Women empowerment | UZP | Sep/13 | Dec/13 | 6,32,000 | Co-financing | 200,000 | Goal-1,3 | Women affair depart. | 200 women | 1000 family members |
| 9 | Creating self-employment for disadvantaged women through skill training on “Tailoring” and providing the necessary supports. | Women empowerment | UP | Sept/13 | Dec/13 | 365,000 | Co-finacing | 90,000 | Goal-1,3 | Women Affair | 45 women | 15 UPs |
| 10 | Empowering vulnerable women trough imparting training on “Goat rearing” and providing the necessary supports. | Women Empowerment | UZP | Sep/13 | Dec/13 | 406,000 | Co-financing | 60,000 | Goal-1,2,3 | Women Affair departs. | 120 women | 600 family members |
| 11 | Implementing project on “Management and demonstration of local fish culture” | Fishery | UZP | August/13 | Dec/13 | 2,72,000 | Single |  | Goal-1,7 | Fishery depart. | 100 Fish farmers | 500 family members |
| 12 | Extension of the modern beef fattening technology | Livestock | UZP | Sep/13 | Dec/13 | 2,16,000 | Single |  | Goal-1 | Livestock | 180 farmers | 540 family members |
| 13 | Improving and promotion of local pottery works | Women Empowerment | UZP | Sep/13 | Dec/13 | 4,66,500 | Co-financing | 100,000 | Goal-1,3 | Social welfare | 200 potters | Improving and promotion of local pottery works |

Name of the Upazila: Pirgonj

Total Performance Grant Received (in Taka):

Total budget without co-finance: Tk 5,200,314 Total co-financing amount: Tk 402,000

Total budget with co-financing: Tk 56,02,314

| Sl N | Name of the Project | Sector/Department | Name of the place of the project (UP/UZP) | Duration |  | Budget In TK | Financing Source (Single or Co Finance) | Financing Proportion in TK (in case of co-financing) | MDG goal Compliance (State the goal Number) | Implementation Department in UZP | Number of Beneficiaries anticipate (Female: Male) | Any Remark |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Start | End |  |  |  |  |  |  |  |
| 1 | Improve the soil condition through producing and applying vermi composed | Agriculture | UPs | Sep./14 | Nov./14 | 5.00 | Single |  | Goal-1 | Agriculture depart. | 300 persons | 6 UPs |
| 2 | Providing training to youth on “Mobil Repairing and servicing” | Youth dev. | UPs | Sep./14 | Nov./14 | 5.00 | Single |  | Goal-1 | Youth depart. | 30 youth | 15 UPs |
| 3 | Providing need based training and support to the youth with disability | Social Welfare | UZP | Sep./14 | Nov./14 | 5.00 | Single |  | Goal-1 | Social Welfare depart. | 30 youth | 15 UPs |
| 4 | Imparting training on ”Family planning and Pregnant mother care” to the birth attendants | Family Planning | UZP | Sep./14 | Nov./14 | 6.04 | Single |  | Goal-4,5 | Family planning Depart. | 250 Birth Attendants | 10 UPs |
| 5 | Provide the necessary support to the trained women entrepreneurs on “Shataranji” for marketing their products | Women empowerment | UZP | Sep./14 | Nov./14 | 4.06 | Co-financing | 70,000 | Goal-1 | Women affair depart. | 70 women | 5 UPs |
| 6 | Creating self-employment for disadvantaged women through skill training on “Handicrafts” and providing the necessary supports. | Women empowerment | UP | Sep./14 | Nov./14 | 5.00 | Single |  | Goal-1 | Women Affair | 30 women | 15 UPs |
| 7 | Providing training on Talapia culture and demonstration to the poor fish farmers | Fishery | UZP | Sep./14 | Nov./14 | 2.00 | Co-financing | 74,000 | Goal-1 | Livestock | 148 fish farmers | 15 UPs |
| 8 | Provide the necessary support to the trained local potters for marketing their products | Social Welfare | UZP | Sep./14 | Nov./14 | 6.50 | Co-financing | 70,000 | Goal-1 | Social welfare | 70 potters | 4 UPs |
| 9 | Provide training to the school teachers on “Computer common software’s” | Education | UZP | Sep./14 | Nov./14 | 5.00 | Single |  | Goal-1 | Secondary Education depart. | 100 girls | 15 UPs |
| 10 | Provide need based training and necessary supports (bicycles and mobile) to village police for ensuring effectively and timely services. | UZP | UPs | Sep./14 | Nov./14 | 7.00 | Co-financing | 1,88000 | Goal-7 | UZP | 150 Village Police | 15 UPs |
| 11 | Meeting, workshop and monitoring | UZP | UZP | Sep./14 | Nov./14 | 1.40 | Single |  | Goal-7 | UZP |  |  |

Name of Upazila Chairman: Nur Mohammed Mondol, Mobil: 01786752244

Name and contact number of UNO: ATM Ziaul Islam, Mobil: 01720563929

Names and contact number of DDLG: Md. Ershadul Islam, Mobil: 01711000860

Submitted by:

Nur Mohammed Mondol

Upazila Chairman, Pirgonj Upazila Parishad.

Date: 17/6/2014

Name of the Upazila: Pirgaccha

Total Performance Grant Received (in Taka):

Total budget without co-finance: 4,813,750

Total co-financing amount: 350,000

Total budget with co-financing: 5,163,750

| Sl N | Name of the Project | Sector/Department | Name of the place of the project (UP/UZP) | Duration |  | Budget In TK | Financing Source (Single or Co Finance) | Financing Proportion in TK (in case of co-financing) | MDG goal Compliance (State the goal Number) | Implementation Department in UZP | Number of Beneficiaries anticipate (Female: Male) | Any Remark |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Start | End |  |  |  |  |  |  |  |
| 1 | Provide food bearing trees among poor farmers | Agriculture | All UPs | Sep/14 | Dec/14 | 300,000 | Single |  | Goal-1 | Agriculture depart. | 3000 farmers | 9 UPs |
| 2 | Installation RCC pipe underground of agriculture field for irrigation | Agriculture | All UPs | April/14 | May/14 | 500,000 | Single |  | Goal-1 | Agriculture depart. | 1000 Farmers | 9 UPs |
| 3 | Creating self-employment for disadvantaged women through skill training on “Tailoring” and providing the necessary supports. | Women empowerment | UZP | April/14 | May/14 | 654,705 | Co-financing | 100,000 | Goal-1 | Women Affairs | 100 women | 9 UPs |
| 4 | Rewarding the best performing poor students | Education | UZP | April/14 | May/14 | 400,000 | Single |  | Goal-2 | Primary & Secondary education depart. | 250 students (Male-125, Female-125) | 9 UPs |
| 5 | Providing sports materials to education Institutions | Education | UZP | April/14 | May/14 | 500,000 | Single |  | Goal-2 | Primary & Secondary education depart. | 232 schools (Pirmary-150, secondary -82) | 9 UPs |
| 6 | Providing vaccination for the treatment of rabies at Upazila Health Complex | Health | UZP | April/14 | May/14 | 500,000 | Co-financing | 50,000 | Goal-4,5 | Upazila health depart. | 100 patients |  |
| 7 | Ensuring safe drinking water by supplying tube-wells with making platform and support for Arsenic testing in the upazila area | Water & Sanitation | UZP | April/14 | May/14 | 700,000 | Co-financing | 100,000 | Goal-7 | DPHE | 1200 families | 100 tube-wells |
| 8 | Supply of Ring Slab for ensuring 100 % sanitation in Upazila area | Water & Sanitation | UP | April/14 | May/14 | 500,000 | Co-financing | 100,000 | Goal-7 | DPHE | 2500 beneficiaries | 500 families |
| 9 | Rehabilitation of fishermen and release the fingerlings in “Avoyasrom” at Upazila level | Fishery | UZP | April/14 | May/14 | 500,000 | Single |  | Goal-1 | Fishery depart. | 100 Fish farmers |  |
| 10 | Meeting, training, orientation, workshop | Upazila Parishad | UZP | March/14 | May/14 | 259,445 | Single |  | Goal-1 | Upazila Parishad | UZP functionary | UZP level |

Name and contact number of Chairman: Abu Naser Shah Md. Mahabubar Rahman, Mobil: 01717277223

Name and contact number of UNO: Mrs. Alia Ferdus Jahan, Mobil: 01716520047

Names and contact number of Vice Chairs: Abdur Rashid Sarkar, Mobil: 01716609857

Names and contact number of Vice Chairs (Women) : Mrs. Tanzina Afroz, Mobil: 01745285253

Names and contact number of DDLG: Md. Ershadul Haque, Mobil: 01711000860

Submitted by:

Mrs. Alia Ferdus Jahan

Upazila Nirbahi officer

Pirgaccha Upazila Parishad.

Date: 17/6/2014

Box: Investment in environment friendly crops - grey area of private goods

In one of the Upazila Parishads, the UFF was used to support a farmer to promote new ecological friendly farming methods and new crops. The funding from the UFF was a small investment (1 Lak Taka) and was topping up with funding from the farmer (supported by bank loans, etc.). Although the investment may indirectly support the other farmers in the area through the demonstration impact and lessons learned from this new production method, this types of support to individual farmers are beyond the investment menu, and related with risk for concentrating benefits for selected individuals and mixing private and public goods. The investment should rather have been supporting the UZP’s LDs on agriculture training and demonstrating efforts, and/or ensured that a common project was initiated for all farmers in the area, through e.g. leasing of land, or co-funding arrangements. UFF should not be applied for private investments, as a private investment program and e.g. PPP arrangements, require a significant different set up and fiscal controls.

Field trip, October 27, 2014.

# Annex 23. UPGP Logical Framework

| Joint Programme Outcome | Means of Verification | Risk & Assumptions |
| --- | --- | --- |
| Strengthened capacities of local governments and other stakeholders to foster participatory local development service delivery for the MDGs Legal and Regulatory Framework in Place: By end of project, .. Secondary legislation instruments (Rules and regulations) required by UP Act 09 are operational. Baseline: 0. Target: 12 Functional and Institutional Capacity Improved: By end of project, overall compliance with administrative requirements of UP Act 09 by project-supported UPs exceeds 80 % Baseline: First round of UP Performance Assessment Increased citizen involvement: By end of the project, % of women/men (which also include Dalits and Indigenous People) who have attended at least one participatory planning meeting Baseline: Baseline survey to be done Target: 50 increase from baseline. Pro-poor infra and services: % of citizens who have responded that they are very satisfied with service delivery by their UP Baseline: Baseline survey to be done. Target: To be determined. | - Project reporting - UP Performance Assessment - Citizen perception survey – as part of baseline and follow-up surveys during project period. - Mid-term and final evaluations | Continued political support from GoB Risk – change of government leading to change in policy Assessed: Medium Continued support to local governance from other donors creates opportunities to scale up successful pilots Risk – other donors support withdrawn or approach not compatible with UPGP Assessed: Low Strengthened UP willing and able to direct discretionary resources to effective, pro-poor, MDG-responsive service delivery |

| OUTPUT | ACTIVITIES | Means of Verification | Risk & Assumptions |
| --- | --- | --- | --- |
| Output 1: Strengthened Democratic Accountability and transparency of the Union Parishads through Citizen Engagement - % of Ward Shavas that transact business according to UP Act 09 Baseline value: Baseline survey (preliminary 0 %) Target: 50 % % of target UPs with at least 6 key standing committee producing at least 2 monitoring reports per year. Baseline value: Baseline survey to be done Target: 50 % - % of targeted UPs which have at least 1 woman representative participating in officially registered women Development Forum at the Upazila Level. Baseline value: Baseline survey to be done Target: 50 % | 1.1 Coaching and Support to UP Chairs, and members for roles and responsibilities defined by UP Act 2009 1.2 Activating Ward Shavas for Inclusive Decision-Making 1.2.1 Support the UP for Ward Shava formation process (based on UP Act 2009 and relevant rules and regulations) 1.2.2 Support the UP to conduct awareness raising of Ward Shavas’ role, functions and citizen’s engagement 1.2.3 Orientation and strengthening the capacity of Ward Shava members for effective meetings, conflict resolution, documentation, interface with elected UP representatives and citizens etc 1.2.4 Support Ward Shavas to conduct pro-poor planning at ward level 1.3 Strengthening Standing Committees for Effective Governance 1.3.1 Support the UP for Standing Committee formation 1.3.2 Support the UP to conduct awareness raising of Standing Committees role, functions and citizen’s engagement with the SC 1.3.3 Orienting and strengthening the capacity of Standing Committee members for effective meetings, conflict resolution, documentation, interface with elected UP representatives and citizens etc 1.3.4 Support to Standing Committees to develop pro-poor sector plans in consultation with Ward members and to negotiate with the Union Parishad for effective implementation 1.4 Up-Scaling Women’s Development Forum 1.4.1 Support to formation, orientation and registration of Women’s Development For a (WDF) 1.4.2 Promoting the participation of women at Ward Shava meetings and encouraging them to join standing committees 1.4.3 Strengthening of women’s voice in planning for better health, education and other services 1.4.4 Supporting action to reduce violence against women 1.4.5 Monitoring efficient use of the gender UP budget 1.5 Building Citizenship and Promoting Downward Accountability 1.5.1 Identification of key rights and entitlements by writing RTI applications 1.5.2 Disclosure of Information on UP resources and use 1.5.3 Demonstration of best practice (peer to peer exchanges) 1.5.4 Training of WDF to educate women to apply for entitlements independently | - Baseline survey and analysis - Development of training materials - Training reports Communications products disseminated. - Development of model guidelines for standing committees - District Facilitator activity reports - Training of SC members Development of training materials - Dissemination of advocacy materials - Cross-visit reports to record best practice | Continued political support from GoB Regulation for Ward Shava is in place and implementation is supported by GoB Regulation for Standing Committees is in place and implementation is supported by GoB |
| Output 2: Strengthened innovations in Pro-Poor and MDG-Oriented Planning, Financing and Implementation of Service Delivery by Union Parishads - By end of the project % of targeted UPs have completed comprehensive development plans responding to local MDG assessments that will have also identified needs of the locally relevant most vulnerable groups. Baseline value: 0 %.Target: 90 % - By end of the project, % of targeted UPs allocate % of block grant funds to projects explicitly identified as pro-poor (including those responding to vulnerable groups’ needs) or MDG-responsive in plans Baseline value: 0 %. Target: 70 % - By end of the project, % of target UPs comply with 90 % of accounting and record keeping requirements. Baseline value: First round of Performance Assessment. Target: 90 - By end of the project, % of increase, on average, or revenue collection in target UPs Baseline value: To be done. Target: 90 % | 2.1 Enhanced Planning and Financial Management through Performance Based Grants system 2.1.1 Support to management and implementation of the Enhanced Planning and UP performance grant system. 2.1.2 Support to the further development of the UP performance grant system 2.2 Own revenue mobilization and improved local financial management 2.2.1 Design pilot strategy for enhanced revenue mobilization by UPs (including option for 2-3 simultaneous pilots in different UP groups) 2.2.2 Orient and train UPs (including peer learning, exposure visits, sharing of good practices) and other LG levels for pilot activities on planning and revenue mobilization 2.2.3 Roll out pilot revenue mobilization enhancement activities 2.2.4 Conduct Own-Revenue Raising promotional activities (tax fair, rewarding top 10 taxpayers etc) including awareness raising and citizen oversight; 2.2.5 Roll out successful innovations to all target UPs by end of project |  | Continued political support from GoB Availability of adequate data for local-level MDG assessment and targeting Pro-poor and MDG-responsive projects seen as priority by UPs Agreement (continued from LGSP-LIC) by LGD to permit piloting of simplified approach to revenue collection by UPs Willingness of UPs to participate in revenue collection pilots |
| Output 3: Strengthened technical capacity of Local Government Division for effective policy review, monitoring, lesson learning and capacity development of LGIs for enhanced Local Governance | Shared with UZGP |  |  |

# Annex 24. UZGP Logical Framework

| Joint Programme Outcome | Means of Verification | Risk & Assumptions |
| --- | --- | --- |
| Project Outcome: Strengthened capacities of local governments and other stakeholders to foster participatory local development service delivery for the MDGs Legal and Regulatory Framework in Place: No. of effective secondary legislation instruments required by UZP Act 09 by the end of the project Baseline: 5 Functional and Institutional Capacity Improved: No. of UZPs that have adopted internal rules and by-laws including an anti-corruption strategy and a Citizens’ Charter by the end of the project Baseline:0 Democratic Accountability: % of citizens aware of the roles and responsibilities of UZP Baseline: Baseline survey to be done Pro-poor infra and services: % of citizens satisfied with services specifically targeted by Upazilas through pro-poor and MDG-responsive planning Baseline: Baseline survey to be done | - Project reporting - Performance Monitoring System - Citizen’s Perceptions Survey – baseline and two follow-up surveys during project period. - Mid-term and Final Evaluation | 1. Continued political support from GoB Risk – change of government leading to change in policy Assessed: Medium 2. Expected resistance to change from Upazila officials and line agencies can be overcome. Risk – officials actively resist change to extent where project implementation is compromised Assessed: Medium 3. Strengthened UZP willing and able to direct discretionary resources to effective, pro-poor, MDG-responsive service delivery Risk: UP chairs unable agree on strategic response to Upazila-level development challenges Assessed: Medium |

| OUTPUT | ACTIVITIES | Means of Verification | Risk & Assumptions |
| --- | --- | --- | --- |
| Output 1: Strengthened Upazila Parishads as more functional, democratic, transparent and accountable institutions - Percentage of women and men UPZ councillors who report they can participate effectively in debate and influence decision making by the end of the project. Baseline: Councillor perception baseline - Number of UZPs with are compliant with at least 90 % of the provisions of the Right to Information Act By the end of the project. Baseline: to be determined - Average number of key standing committees functioning in UZPs by the end of the project. Baseline: 0 - Number of women’s development fora registered at the District level by the end of the project. Baseline value: 0 - Number of UZPs that have prepared a “Citizen's Charter” incorporating arrangements for UZP-constituent relations by the end of the project. Baseline value: 0 | 1.1.1: Capacity development initiatives for all UZPs 1.1.2: Support UZP for effective meetings and active Committees 1.1.3: Support LGD in drafting of sub-legislation (Delegated legislation) as per UZP Act 2009 1.2.1: Establishing linkages between UZP and other stakeholders and CSOs 1.2.2: Enhance Right to Information and Digital Bangladesh vision 1.3.1: Capacity building initiatives for women elected leaders 1.3.2: Raising awareness on gender equality within the Upazila | - Evaluation/assessment reports - Progress reports - Media reports - Training Reports - MIS reports - Monitoring reports Audit reports | Continued political support from GoB |
| Output 2: Strengthened Planning and Budgeting system at UZP with MDG orientation and pro-poor service delivery mechanism - Number of line department activities integrated with UZP plans and budget - Number of participating UZP that have produced development plans responding to local MDG assessment and identifying needs and actions related to the most vulnerable groups (such as the *Dalits or other locally relevant excluded groups) by end of project. Baseline value: 0 % - Number of participating UZPs with development plans that have at least one development intervention addressing needs of the identified most vulnerable groups (such as the Dalits or other locally excluded groups). Baseline value: 0 - Percentage of performance based grants allocated to projects identified as MDG-responsive in annual development plans in final year of project. Baseline value: First round PMS | 2.1.1:Support to develop of Upazila Development Planning and budgeting guidelines 2.1.2: Design and deliver local planning and budgeting training based on the guidelines prepared under 2.1.1 2.1.3: Developing Upazila integrated 5 years plan plan with emphasis on MDG achievement in all UZPs with special emphasize in 14 Upazila 2.1.4: Support in preparation of Upazila monitoring and evaluation framework 2.2.1: Design and capacitate on Upazila Fiscal Support system tools: 2.2.2: Support to management and implementation of the UZP pilot fiscal support system 2.2.3: Support to further development | - Evaluation/assessment reports - Progress reports - Media reports - Training Reports - MIS reports - Monitoring reports - Audit reports | - Continued political support from GoB - Availability of adequate data for local-level MDG assessment and targeting - Pro-poor and MDG-responsive projects seen as priority by UPs |
| Output 3: Strengthened technical capacity of Local Government Division for effective policy review, monitoring, lesson learning and capacity development of LGIs for enhanced Local Governance - Number of drafted legislative or regulatory instruments influenced by outcome of piloting activities by the end of the project. Baseline: current set of legislative and regulatory instruments. Target: 2 - Existence of a National Framework for Local Government Capacity Development by the end of the project. Baseline: No draft framework exists. Target: 1 - Implementation of a functioning M&E and MIS system in the Monitoring, Investigation and Evaluation Wing of LGD ( capturing key data on local government performance) by the end of the project. Baseline: Only a project based MIS(and in early design stage) is used by LGD - Number of DLGs who have a sustainable system for monitoring and backstopping local governments by the end of the project. Baseline: No system in place | 3.1 Support to a Policy Advisory Group (PAG) and National Framework for Local Government Policy and Capacity Development 3.1.1: Facilitate core functions of the Policy Advisory Group. 3.1.2: Support the development of a National Framework for Local Government Capacity Development. 3.1.3: Support to research and dissemination of research findings on local governance. 3.1.4: Support to prepare Manuals and rules for UPs and UZPs 3.2 Support to LGD (MIE wing), DLG (Division level) and DDLG (District level) for backstopping and monitoring of local government (UZP and UP) 3.2.1: Support to LGD (MIE wing) to develop and operationalize an M&E system for UP and UZP performance monitoring (including roll out to Division and District level). 3.2.2: Support the DLG to develop, collect and analyze governance and ‘democracy’ indicators. 3.2.3: Support National training institutions and private sector agencies in training and backstopping of UPs and UZPs. 3.2.4 Creation of national data base of local government plan, finance and services 3.3 R&D for Knowledge Generation 3.3.1 R&D fund for knowledge Generation activities 3.3.2 M&E and project learning review | - Legislation and regulatory instruments amendments - LG Policy and Capacity Development Framework document - Research reports - LGD MIE wing MIS - Training reports - Meeting minutes - Media report - Course curricula | Various National training agencies (NILG, BARD RDA etc..) to agree on a common capacity development framework Policy and regulatory framework in place in time for finalization of curriculum LGD MIE wing maintain expressed interest in adopting M&E strategy and MIS, and District level cooperates |

# Annex 25. Examples of parallel committee structures at UP level

| Line Department sponsored UP level Committee | Standing Committees (Based on UP Act 2009) |
| --- | --- |
| Ministry of Health | UP Standing Committee |
| Union Family Planning Management Committee | UP Standing Committee of Health and Family Planning |
| For each UP there is Union Family Planning Management Committee. Composition of Union Family Planning Committee - Chairman, Union Parishad Chairperson - Member, Union Parishad (all) Member - Union Level Officials (all) Member - Head Master/Teachers/Principals from 1 selected 1 Primary school, 1 boys high school, 1 girls high school and one college (if available) within the union (nominate by the Union Parishad) Member - Ansar Commander Member - President, Union Imam’s Society Member - President, Union Kazi Society Member - One representative from any NGO working for family planning (nominate by the Union Parishad) Member - President of local mother’s club/Women’s society/Cooperative society Member - Sub-Assistant Community Medical Officer Member - Family Planning Inspector (female) Member - Family Planning Inspector (male) Member Secretary Functions of the Union Family Planning Committee - organize union based programs, fix target, evaluate achievement in the monthly meeting and take necessary steps after the evaluation in the meeting and forward problems and recommendations to the Upazila committee - evaluate and supervise the activities of individual workers at union level and take remedial action for the failure and negligence in the work - take necessary action for the improvement through motivation meeting/seminar/courtyard meeting discussion addressing the less developed area, slum, Char, remote and hilly areas to disseminate family planning activities and health issues of mother and child - arrange a motivational meeting along with the representative of teachers, Imam, Kazi and local elites for building awareness regarding family planning and health of mothers and children - take initiative to form a Village committee chaired by local member of the Ward committee or any respectable person - evaluate the overall management and the progress of work of the community clinic within the Union - take initiative to form local mother’s club/Women’s society/Cooperative society and coordinate the family planning and mothers and child health program - actively take action and coordinate and evaluate the work of community based - voluntary project within the union 2. The Secretary of the UP will provide support and assistance in the execution of routine work of the Committee. 3. If necessary the committee will co-opt the influential respected, educated or religious person as the member of the committee. | Modus operandi A Standing Committee shall elect one of its members, other than a co-opted member to be its Chairman and minimum one third of the total number of Chairmen of the Standing Committees shall be elected from amongst the members elected in reserved seats for women Provided that, the Chairman of the Union Parishad shall be the Chairman of the Standing Committee dealing with maintenance of law and order only. A Standing Committee shall consist of five to seven members and if necessary, the Committee may co-opt expert member, but such member shall not have any right to vote. The other member shall be nominated from the local people, but who may possess special qualifications for serving on the concerned Standing Committee. (6) The recommendations of the Standing Committees may be considered to be passed in the subsequent meeting of the Parishad and if any of the recommendations may not passed by the Union Parishad, the justification and reason for such shall be informed in written to the Standing Committee. (7) All the proceedings of the Standing Committees shall be finalized subject to approval at the general meeting of the Union Parishad. |
| Ministry of Disaster Management and Relief | UP Standing Committee |
| Union Disaster Management Committee (UDMC) | UP Standing Committee on Social welfare and Disaster Management |
| A Union Disaster Management Committee is comprised of the following members - Union Parishad Chairman 1 Chairperson - Members of the Union Parishad 12 Member - Teacher Representative (Nominated by Chairman) 1 Member - Government officials working at Union Level (Sub-Assistant Agriculture - Officer, Union Health and Family Planning Centre in-charge, Union Tax - Collector (Tahshildar), BRDB Field Worker, Representative of Social - welfare department) Other members include: - 1 Representative of Vulnerable Women (Nominated by Chairman) 1 Member - 1 Representative of the CPP (in appropriate case) 1 Member - 1 Representative of Bangladesh Red Crescent Society (in appropriate case) 1 Member - 1 Representatives of NGOs (one representative each from Local, National and International NGOs nominated by the Chairman) - Representative of the Peasant and Fishermen Society (If no society, person will be nominated by Chairman) - Socially Reputed Persons or Civil Society Representatives (Nominated by the Chairman) - Representative of Freedom Fighter (Nominated by Upazila Freedom - Fighters Command Council) - Imam/Priest/Other religious leader (Nominated by Chairman) 2 Member - Representative of Ansar and VDP (Nominated by Upazila Ansar VDP - Officer) - Secretary, Union Parishad 1 Member Secretary The chairperson of the Committee can co-opt maximum 3 (three) more members and form groups and sub-groups considering the local situation and special circumstances. - During normal time, the committee will meet once in a month. - During warning phase and pre-disaster period, the committee shall meet more than one time in a week. - During disaster period the committee shall meet as and when needed (once daily), at least once in a week. - In recovery phase the committee will meet once a week. - The committee can meet any time if needed or part of the committee can meet with the other development committees bi-laterally or multilaterally. - The committee can request any member(s) or specialist(s) of the locality to attend any particular meeting. - An updated list of members of UDMC will have to be submitted to UzDMC by 15 January of each year duly signed by the chairperson of the UDMC. | Modus operandi Same as above |

However the Local Government Division upon World Bank demand prepared a Sector Policy on Local Governance policy document during the design stage of the LGSP–I. But the sector policy on decentralization has not been widely circulated and or published.

Local Government (City Corporation) (Amended) Act, 2011; Local Government (City Corporation) Election Rules 2008; Zila Parishad Act 2000; Upazila Parishad (Amended) Act 2011; Upazila Parishad (Service) Rules 2010; Upazila Parishad (Program Implementation) Rules 2010; Local Government (Paurashava)(Amended) Act, 2010; Local Government (Paurashava) Election Rules 2008; Local Government (Union Parishad) Act 2009; Union Parishad (Development Planning) Rules 2013; Union Parishad (Tax Schedule) Rules 2012; Union Parishad (Property) Rules 2012; Union Parishad (Agreement) Rules 2012; Union Parishad (Accounts & Audit) Rules 2012; Village Court Act 2006.

The Third Schedule of UP Act 2009 – Power of the government to deploy government officers and employees at the Union Parishad

The UPs are broadly responsible for economic, social and community development. As set out in the Local Government (Union Parishad) Act 2009 they have several functions including: Maintenance of law and order, including assistance to the law enforcement agencies and resolution of disputes; Adoption of measures to prevent disorder and smuggling; Conducting of censuses of all kinds; Registration of births, deaths, blind people, beggars and destitutes; Planning and implementation of development schemes in the field of agriculture, forestry, fisheries, livestock, education, health, small and micro enterprises, communications, irrigation and flood control; Implementation of other development schemes as assigned; Development and use of local resources; Motivation of people to use sanitary latrines; Promotion of family planning; Monitoring of development activities undertaken by different agencies (government, semi-government) in the union; Protection and maintenance of public property such as roads, bridges, canals, embankments, markets, telephones and electricity lines. In addition, specific rural infrastructure responsibilities defined for the UPs are the maintenance of Rural Roads and the Planning and implementation of small construction projects, these include improvement of works on rural roads – e.g. schemes under some food-aided infrastructure projects are implemented through the UPs. The UPs are also responsible, through the Union Market Management Committees (UMMC) for the operation and maintenance of markets within the Union

Detail functions include: 1. Preparation of development plans, including Five-Year Plans, to be implemented in different periods of time, 2. Implementation of the programs of different Government agencies that may be transferred by the Government to the Parishad, and supervision and coordination of the activities of any such agencies; 3. Construction, repair and maintenance of inter-union link-roads; 4. Adaptation and implementation of small scale irrigation projects, in accordance with the directions of the Government, for the purpose of the best utilization of the surface water; 5. Ensuring the services of public health, nutrition and family planning.’ 6. Development of sanitation and sewerage system and adaptation of proper measures for supplying drinking water; 7. (a) Providing motivation and aid for the extension of education at Upazila level,(b) Providing supervision and aid to the concerned institutions for the purpose of further development of the secondary and madrasah education systems; 8. Adopting programs for establishment and extension of small and cottage industries; 9. Providing support and coordination to the cooperative societies and non-Government voluntary organizations. 10. Implementing and aiding the programs of women, children, social welfare, youth, sports and cultural activities; 11. Adopting and implementing programs for the development of agriculture, livestock, fisheries and forest resources; 12. Review of the activities of the police department along with the development of law and order situation in the Upazila and sending reports regularly to the higher authorities; 13. Adopting and implementing own programs for generating self-employment and for reduction of poverty, and providing necessary assistances to the Government in the implementation of the Government programs in this relation; 14. Coordination and assessment of the development programmes undertaken by the union Parishads and providing them with necessary cooperation; 15. Organizing public opinion, and taking other preventive measures, to resist the crimes of repressions against women and children etc.; 16. Organizing public opinion and taking other preventive measures to resist the crimes of hooliganism, theft, robbery, smuggling, abuse of drugs etc; 17. Adopting social forestry and other programs with the aim of preservation and development of environment; 18. Performing such other functions as the Government may assign from time to time.

It should be noted that this level is much lower than the block grant allocations in e.g. Nepal (above 3 USD) and Bhutan, where it is above 30 USD per capita, but where the cost of service delivery is of course also higher due to geographical conditions, lower economies of scales etc.

Article 60 of the Constitution of Bangladesh narrates that “For the purpose of giving full effect to the provisions of article 59, Parliament shall, by law, confer powers on the local government bodies referred to in that article, including power to impose taxes for local purposes, to prepare their budgets and to maintain funds”

See e.g. the UPGP Annual Progress Report, 2013.

Md. Anwar Ullah , Financial Resources Mobilization Performance of Rural Local Government: Case Study of Three Union Parishad in Bangladesh, Asian Social Science Vol. 6, No. 11; November 2010.

WID focal points in the Ministries are in line with international commitments to gender parity. An inter-ministerial Women and Child Abuse Prevention Committee has been formed to establish rights and resist abuse of women. The Woman and Child Abuse Prevention Cell and Women Abuse Prevention Committee have been formed at district and Upazila levels that are linked to the Ministry of Women and Children Affairs and Women Affairs Department.

The Gender Inequality Index (GII) reflects gender-based inequalities in three dimensions: reproductive health, empowerment, and economic activity. Reproductive health is measured by maternal mortality and adolescent fertility rates; empowerment is measured by the share of parliamentary seats held by each gender and attainment at secondary and higher education by each gender; and economic activity is measured by the labor market participation rate for each gender. The GII replaced the previous Gender related Development Index and Gender Empowerment Index. The GII shows the loss in human development due to inequality between female and male achievements in the three GII dimensions. (UNDP, 2013).

Sixth Five Year Plan, Part 1. P 112.2010 MDG assessment.

MPs are nominated by parties having representation in the Parliament on a proportional representation basis.

Naomi Hossain and Salma Akhter, Gender, Power and Politics in Bangladesh: a baseline study for the Upazila Support Project, Report prepared on behalf of the UNDP Bangladesh Local Governance Cluster April 2011.

Fewer women were elected as UP chairs or in general seats at the last UP election. In Sharique’s working area only 7 % of EWR in reserved seats were re-elected, well below the 19 % re-election rate of general male members (Sharique pers.com.).

LGSP-LIC study of women’s participation in local development in the LIC districts in Bangladesh, Ms. Zarina Rahman Khan, UNDP/UNCDF, December 2009.

These include mechanisms introduced by UNDP project UPZ in five districts.

Sharique for example reported, in their annual gender report 2013, the public stabbing of a woman UP member by a male colleague in Chapai Nawabganji district.

An example of this was the prior testing in 2011 of the performance indicators applied in the EPBG to ensure that the system was possible to manage and useful and meaningful for the UPs involved as well as the assessment teams. During these missions, UPs requested new indictors to be included, and the process was indeed very interactive.

One example of this was a comprehensive study of the flow of funds.

One of the features of this was that some general CB support is provided to all UZPs in the country, more specialised support to 65 UZP in the target areas and UFF to only 14 UZPs, opening up for a future up-scaling of the more intensive support. This is one of the features, which will enable and smoother up-scaling as all have certain capacity.

Note that the recent contracting of BIM is in the grey area of “neutrality”, as the same institution is in charge of some of the CB activities within the program.

The target indicators under output 1.1.5 in the UNDAF results framework were under review during the MTE, and a detailed progress assessment was not conducted, except for inputs to the IRRF after the team left Bangladesh.

Government of the People’s Republic of Bangladesh, National Strategy for Accelerated Poverty Reduction II FY 2009–11, General Economics Division, Planning Commission, 2009

Bangladesh Sixth five Year Plan FY 2011-2015 - Accelerating Growth and Reducing Poverty, General Economics Division, Planning Commission, 2011. P.216

Local Government (City Corporation) (Amended) Act, 2011; Local Government (City Corporation) Election Rules 2008; Zila Parishad Act 2000; Upazila Parishad (Amended) Act 2011; Upazila Parishad (Service) Rules 2010; Upazila Parishad (Program Implementation) Rules 2010; Local Government (Paurashava)(Amended) Act, 2010; Local Government (Paurashava) Election Rules 2008; Local Government (Union Parishad) Act 2009; Union Parishad (Development Planning) Rules 2013; Union Parishad (Tax Schedule) Rules 2012; Union Parishad (Property) Rules 2012; Union Parishad (Agreement) Rules 2012; Union Parishad (Accounts & Audit) Rules 2012; Village Court Act 2006

Government of Bangladesh, National Rural Development Policy, Rural Development Division, Ministry of LGRD& Cooperatives, 2000, p. 5.

General Economics Division (GED), Bangladesh Planning Commission, The Millennium Development Goals - Bangladesh Progress Report 2012, Government of the People’s Republic of Bangladesh, June 2013.

Government of the People’s Republic of Bangladesh, National Strategy for Accelerated Poverty Reduction II FY 2011–15, General Economics Division, Planning Commission, 2009 p.116.

Bangladesh Sixth five Year Plan FY 2011-2015 - Accelerating Growth and Reducing Poverty, General Economics Division, Planning Commission, 2011, p.211.

Opcit, p. 227.

Opcit, p. 229.

Opcit p.164.

Opcit, p. 164.

General Economics Division, Planning Commission, Government of People’s Republic of Bangladesh, the Seventh Five-Year Plan of Bangladesh (FY 2016-FY2020) – Accelerating Growth with Equality – A Concept Note. June 2013, p.2.

Opcit, p.8.

Bangladesh Awami League, Election Manifesto, Item 6.

See the Draft Concept Note for the 7FYP.

National Rural Development Policy 2000, Sixth and Draft Approach paper on Seventh Five Year Plan.

Such observations are drawn from the Field Data Collectors and the findings of Citizen Perception Survey on Services Provided by Local Government Institutions as well as Assessment of Results Achieved by UZGP and UPGP, September 2014

Drawn by the Data Collectors of the MTR team

The Study on Key Rights and Entitlements for Poor and Disadvantaged Citizens where the RTI Act can be Effective, p.54

This led to a more projectized approach for allocations as and when the assessments are completed instead of regular fixed and predictable tranches of grants to UPs.

This training was highly appraised by both LGD, the LGSP team and the auditors, and has been appraised very positively in the recent Second LGSP MTR, August 2014.

Source: Data from the two annual performance assessments under UPGP.

Data from the LGSP 2 MTR, 2014 report.

See Draft Report on Citizens Perception Survey, September 2014 by the Survey and Research System (referred to as CPS, 2014 in the following sections) pages 43 and 64. This was based on comprehensive data from 14 districts (7 covered and 7 not covered), 28 UPZs (14 covered and 14 not covered) and 168 UPs (84 covered and 84 not covered).

Source: MIS data from UPGP presented at the MTE workshop on October 1, 2014 and confirmed from the field level work, October 2014.

Source: MIS data from UPGP presented at MTE workshop on October 1, 2014.

Of course many of the other projects also benefitted poor households but were not defined as such.

CPS, September 2014, p. 33.

According to the project database on schemes under the UPGP MIS.

Based on UPGP database on schemes.

Source: MTR of the LGSP 2 2014. As LGSP is also focusing on improved planning, it is hard to establish a clear control group to measure progress against, and impact may even be higher.

UPGP second quarterly monitoring report, June 2014, page. 15.

Note that this target is too broadly defined, and should have been broken down in the PD on specific indicators.

It should be noted that this was despite the challenging external environment of political turmoil related with the election, demonstrations etc.

Data from the annual performance assessment under UPGP, Suresh B, CTA, UPGP.

Based on data from the MIS system provided by the UPGP project team.

Source: APA for 2012/13 and FY 2013/14 results, see Annex 19.

Interviews with 7 of the auditing companies under the LGSP/UGPG annual audits all confirmed improvements in the UP PFM performance.

This indicator has subsequently (2012 M&E report from UN) been proposed to read: “ % of the UPGPs supported UPs that mobilize 10 % more revenues than 2 years ago, and % of UPs that use more than 10 % of OSR on development or service delivery.

As there is no comprehensive data from FY 2011-12- FY 2013/14 for all UPs, all UPs in the UGPG and all 146 UPs in the special pilot, the team collected revenue data from UPs in Brahmanbaria and from the field sample UPs.

Based on data presented by the UPGP during the MTE workshop from MIS.

Data from the 2013 Annual Report on UPGP, page 14.

From the MIS data base in UPGP presented at the workshop on October 1, 2014. See also annex on trends in performance scores from the 1st to 2nd assessment.

UPGP, 2th quarterly monitoring report, June 2014, page 15.

Based on UPGP M&E system data.

This is a good sign and the results of a longer-term advocacy for strengthening of the local staffing situation.

Note that one of the weakest performance areas was the UPs’ publication of previous APA results (average score of UPs was only 0.54 points out of maximum 2 points).

Examples of this is the Danida support to HYSAWA with funds going to UPs, and the support to block grants to rural roads, under the LGED.

Based on one day field trip to each of the UZP, and the self-assessment of leading officials and councilors.

The Study on Key Rights and Entitlements for Poor and Disadvantaged Citizens where RTI can be effective, 2014 – Study conducted by UPGP

Annual Report UZGP, Statement of Expenditure 2013

On the one hand this strengthens the incentives for UZP to compete for the funds, but on the other hand this also reduces the option to test and pilot whether the system can work in stronger as well as weaker UZPs, which a genuine sample choice of UZP for coverage of the UFF would have ensured.

Citizens Perception Survey (CPS), September 2014, pages 60-70.

CPS, September 2014, page 69.

UZPG MIS and information from Program Manager, back up by qualitative interviews in the field.

UZPG scheme list from the data-base.

Brahmanbaria UZP, Kazipur UZP, Pirganj UZP, Sarial UZP, Dacope UZP, Ullapura UZP, Pirgancha UZP and Dumuria UZP.

Source: MIS data from UZGP, field level data and CPS.

Information from the program manager of UZGP, November 10, 2014.

Source: Presentation at the MTE Workshop on October 1, 2014.

Based on the elaborated field trip reports from each of the 12 UZPs covered, October 2014.

Source: MIS UZGP supported by field level reviews, sse annex on scheme examples.

Source: Database provided by UPGP MIS, October 2014.

Data from the PM, UZGP, November 10, 2014.

Database on schemes under the MIS- UZGP, backed by qualitative review in the field.

MIS data presented at the MTE inception workshop on October 1, 2014.

Based on field trips to: Ghatail UZP, Tangail Sadar UZP Jhikargacha UZP and Jessore Sadar UZP.

Source: UZGP database on schemes/MIS.

Source. UZGP data-base on scheme composition.

Source: UZGP data-base on scheme composition.

Investments in individual private businesses to support development require another project set-up with other checks and balances.

E.g. the guideline’s suggestion to focus on infrastructure in the first year is against the spirit of the UFF as designed. Another place, it is mentioned that all 17 LDs should benefit – this is not possible every year and may be against the spirit of the UFF, which should target the specific needs of the UZP/LDs in special needs in this area.

These indicators were developed subsequently by a UN M&E mission in 2012, and may add to the review of the overall progress on this output.

Data provided by the project based on the 2 rounds of APAs.

Source: Field level information gathered directly from the UZPs – UNOs.

Including the relationship between the MPs and the UZP, and the relationship between the LD committees and the UZP standing committees.

The future up-scaling could be envisaged as when the SLGDP experiences on block grants were up-scaled under the LGSP/LIC initiative.

Minister of Finance Order, Reference No: 07.00.0000.129.15.005.12-73, Date 03.06.2014

UPGP areas as of FY 2013/14

Section 25 of the Upazila Act 2009 narrates “ Advisor to the Parishad .- The concerned Member of the Parliament from each local areas, elected under Article 65 of the Constitution of the People’s Republic of Bangladesh, shall be the Advisor to the Parishad, and the Parishad shall receive the advices of such Advisor”.

Framework for cooperation between Local Government Division and World Bank, UNDP and UNCDF regarding Coordination and Cooperation Between the Second Local Governance Support Project and the Union Parishad Governance Project, 18 September 2012, Local Government Division.

See Steffensen and Aminuzzaman: ”Analytical Work on the Links and Synergies Between Central and Local Governance Interventions in the Country Program for Bangladesh (2016-2021)” Danida, May 2014 for a detailed review of the potential for strengthening of these linkages and opportunities for synergies across programs (Danida, May 2014).

UPs with OSR above 400,000 p.a.

An example of this is the Backward Region Grant Fund in India or the equalisation grant system in Uganda and in the Scandinavian countries, Australia, Canada and many other places.

This should be based on review of some piloting of this in other programs, e.g. under the Danida support programs for rural road maintenance and water and sanitation under HYSAWA.

Chairmen of all the UPs under an Upazila are members (by default) of that Upazila.

http://www.uneval.org/papersandpubs/documentdetail.jsp?doc_id=980

http://www.uneval.org/papersandpubs/documentdetail.jsp?doc_id=980

See annex 1 on the extract from the most recent annual performance assessment, which impacted on the FY 2013/14 allocations.

Note that UPGP and LGSP rely on the same auditors/assessors, hence if the LGSP contracting is delayed it impacts on the UPGP project as well. However, there are obvious advantages of having one common system of performance assessment instead of parallel initiatives.

October 2011.

In most places, the assessments were completed in December 2013, but it took time to finalise and make QA, etc. of all UPs.

Experiences from other countries have shown that it is hard to catch up, when assessments are being delayed from project start up. Experiences have also show that this is one of the major bottlenecks, which has to be fixed early on in every program/grant scheme.

This was due to the election to the UZPs, which affected the timing of the allocations.

One of the reasons for the further delays of allocations was the election to the UZPs and the wish not to send funds out during this process.

For LGSP, the announcement of 3 years indicative planning figures mitigate this somehow, but for the performance-based grants, the access and size can only be known after the completion of the assessments.