REPUBLIC OF SEYCHELLES

# United Nations Development Programme (UNDP)

# Global Environment Facility (GEF)

# Seychelles Energy Commission, Ministry of Home Affairs, Environment, Transport and Energy, Government of the Seychelles

Midterm Review (MTR)

for the project

# Grid-Connected Rooftop PV Systems

(GEF Project ID: 4164 – UNDP PIMS ID 4331)

Final MTR Report

June 2015

# Acknowledgements

The consultant wishes to express his gratitude for the time and effort expended by all project participants and stakeholders during the review process. They provided valuable insights, shared their perspectives, and provided a warm welcome to the project they have shaped over the past couple of years. In particular, the consultant wishes to thank the UNDP Country Office, the Project Management Unit, the Seychelles Energy Commission, and the Public Utilities Corporation. It is my hope that this report will be of some small use, not only in evaluating the events of the past but in helping to shape the future of solar energy in the Seychelles.

# Table of Contents

Acknowledgements	2

Table of Contents	3

Acronyms and Abbreviations	5

1.	Executive Summary	7

1.1.	Project description and summary	7

1.2 Summary of findings	8

1.2.	Summary of MTR ratings	17

1.3.	Summary of conclusions	19

1.4.	Summary of recommendations	20

2.	Introduction	21

2.1.	Purpose and objectives of the MTR	21

2.2.	Scope and methodology	21

2.3.	Structure of the MTR report	22

3.	Project Description and Background Context	23

3.1.	Development context	23

3.2.	Project description and strategy	23

3.3.	Project implementation arrangements	24

3.4.	Project timing and milestones	24

3.5.	Main stakeholders	25

4.	Findings	27

4.1.	Project strategy	27

4.2.	Progress towards results	28

4.3.	Project implementation and adaptive management	44

4.4.	Sustainability	47

5.	Conclusions and Recommendations	50

5.1.	Conclusions	50

5.2.	Summary of recommendations	50

Annex 1: 	MTR ToR (excluding ToR annexes)	52

Annex 2: 	Ratings scale	61

Annex 3: 	MTR Mission Itinerary	62

Annex 4: 	List of persons interviewed	63

Annex 5: 	List of documents reviewed	64

Annex 6: 	Signed UNEG Code of Conduct	65

Annex 7: 	Signed MTR Final Report Clearance Form	66

List of Tables

Table 1: Project information summary table	7

Table 2: Summary of progress towards results matrix (based on log-frame in the ProDoc)	10

Table 3: MTR Ratings & Achievement Summary Table	17

Table 4: Summary of progress towards results matrix (based on log-frame in the ProDoc)	28

Table 5 Main outstanding items and stakeholders for these items	45

Table 6 Project information summary table	46

Table 7: Summary of co-finance as anticipated at CEO ER	46

List of Figures

Figure 1 Number of projects installed each month September 2013 - June 2015	35

Figure 2 Capacity installed each month September 2013 - June 2015	36

Figure 3 Cumulative number of projects as a function of time	37

Figure 4 Cumulative installed capacity as a function of time	38

Figure 5 Example of a residential installation that suffers shading in the afternoon and thus significant unnecessary losses (in this case the owner was apparently aware and insisted on having it in this location)	39

Figure 6 Example of a successful commercial installation at a hotel used as shading for a car park (Praslin).	40

Figure 7 Off-grid PV modules on the home of a hobbyist on Praslin	41

Figure 8 Example of a poor installation. The installation is not performing and was perhaps poorly sized to start with. The client has been unable to get the installer to be responsive to his requests. This is a demonstration of the need for some kind quality assurance and consumer protection mechanism. The inverter for this installation is in the following figure.	42

Figure 9 Example of a poorly installed PV system. The system is not performing and the owner is unable to get a response from the installer. . Despite having paid for a data-logger to allow the owner to access the PV system data online, the owner cannot access the information.	43

# Acronyms and Abbreviations

| ADFD | Abu Dhabi Fund for Development |
| --- | --- |
| APR | Annual Performance Review |
| AWP | Annual Work Plan |
| CESD | Climate and Environmental Services Division |
| CO2 | Carbon dioxide |
| COI | Commission de l'Océan Indien / Indian Ocean Commission |
| DBS | Development Bank of Seychelles |
| GCF | Green Climate Fund |
| GEF | Global Environment Facility |
| GDP | Gross Domestic Product |
| GHG | Greenhouse gas |
| GOS | Government of Seychelles |
| IAEA | International Atomic Energy Agency |
| IDC | Islands Development Company |
| IER IFC | Independent Electricity Regulator International Finance Corporation |
| IPP | Independent Power Producer |
| M&E | Monitoring and Evaluation |
| MHAETE | Ministry of Home Affairs, Environment, Transport and Energy |
| MoF | Ministry of Finance |
| MND | Ministry of National Development |
| NCCC | National Climate Change Committee |
| NGO | Non-Governmental Organisation |
| NPA | National Performance Assessment |
| PIR | Project Implementation Review |
| PPG | Project Preparation Grant |
| PUC | Public Utilities Corporation |
| PV | Photovoltaic |
| QPR | Quarterly Progress Report |
| RCU | UNDP/GEF Regional Coordinating Unit in Addis Ababa |
| RET | Renewable Energy Technology |
| SC | Steering Committee |
| SCCSP | Seychelles Climate Change Support Programme |
| SEC | Seychelles Energy Commission |
| SEEREP | Seychelles Energy Efficiency and Renewable Energy Programme |
| SEYPEC | Seychelles Petroleum Company |
| SIDS | Small Island Developing State |
| SIF | Seychelles Islands Foundation |
| SIT | Seychelles Institute of Technology |
| SNCCS | Seychelles National Climate Change Strategy |
| TPR | Tripartite Review |
| TTR | Terminal Tripartite Review |
| UNDAF | United Nations Development Assistance Framework |
| UNDP | United Nations Development Programme |
| UNDP-CO | United Nations Development Programme Country Office |
| UNFCCC | United Nations Framework Convention on Climate Change |
| UniSey | University of Seychelles |

# Executive Summary

## Project description and summary

The UNDP-implemented, GEF-financed project, “Grid-connected Rooftop Photovoltaic Systems”, received CEO Endorsement for a four-year period in May 2012 with the objective of increasing the use of grid-connected photovoltaic (PV) systems as a sustainable means of generating electricity in selected main islands and smaller islands of the Seychelles, with a focus on small-scale producers who are already connected to the national electricity grid. The Project Document was signed in September 2012 and a project manager was hired in November 2012. Work on the project began in earnest in February 2013, when the project funds were received.

Table 1: Project information summary table

| Project Title: | Grid-Connected Rooftop Photovoltaic Systems |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| UNDP Project ID: | PIMS 4331 | Project financing | at endorsement (Million US$) | at MTR (Million US$) | MTR Co-finance as percentage of CEO ER co-finance |
| ATLAS Project ID: | 00065515 | GEF financing: | 1,740,000 | 880,910 | 51 |
| Country: | Seychelles | UNDP: | $60,000 | 30,000 | 50 |
| Region: | Africa | Others: | 6,077,138 | 3,302,000 | 54 |
| Focal Area: | Climate Change Mitigation | Total co-financing: | 6,137,138 | 3,302,000 | 54 |
| GEF Focal Area Strategic Programme | Promote low-GHG energy technologies, through the increased production of renewable energy in electricity grids. | Total Project Cost in cash: | 7,287,138 | 4,212,910 | 58 |
| Executing Agency: | Seychelles Energy Commission |  |  |  |  |
| Other Partners involved: | Public Utilities Corporation | ProDoc Signature (date project began): |  | Sep. 2012 |  |
|  |  |  | Planned closing date: September 2016 | Revised closing date: September 2016 (no revision) |  |

Through examination of the available documents and interviews with stakeholders, it is clear that the project is highly relevant to the Seychelles, where all electricity prior to the project was dependent on imported diesel. While there had clearly been prior interest in PV within the islands, it is reasonable to state that the project has played a pivotal role in bringing together the elements needed to start the market. In particular, the project has established regulation and an independent energy regulator, as well as supporting the Public Utilities Corporation (PUC) in initiating the integration of PV into its grid. The UNDP-GEF project has the potential to transform the energy landscape in the Seychelles, leading to a significantly more adaptive, robust and sustainable electricity sector in the medium and long-term.

The project has also enabled collaboration with other entities, such as the Clinton Climate Initiative and the Development Bank of the Seychelles. The project is in a position to attract development funds for the long-term support of the Seychelles, including potentially from the Green Climate Fund (GCF).

The delay between CEO endorsement and signature of the Project Document, hiring of a project manager and commencement of work means that what is in theory a four-year project actually has three years and two months (starting February 2013 instead of April 2012) to achieve its objective.

## 1.2 Summary of findings

Progress towards results

The Grid-Connected Rooftop Photovoltaic Project in the Seychelles has been highly successful in meeting its major targets, such as establishing an independent energy regulatory body, putting in place regulations to allow the installation of photovoltaics, private generation of electricity, and supply of electricity to the national grid by private producers. The project had a target of installing 1.3 MW of PV. As of the Mid-Term Review (MTR) in June 2015, there are 1.24 MW on the rooftops with a further 1.1 MW in planning. An independent energy regulator exists, as well as a net-metering scheme. This net metering scheme has been effective in incentivising the installation of PV, particularly for those in the higher tariff brackets. This scheme is, however, not sustainable because the high-consuming customers are a relatively small population, and because it deprives the PUC of its highest profit stream by reducing its sales of electricity in the highest tariff brackets. Further, PUC is currently under no contractual or other legal obligation to continue net-metering in the long-term, meaning that PV system owners’ may not be assured of financial payback if PUC changes policy. As a result, those who invest in PV are those who: can take financial risk, have relatively short payback expectations, believe that change in public policy is sufficiently slow to take a calculated risk, and have enough of their own consumption such that, even if there is a change in policy, the PV system will replace enough of their own energy consumption to still be viable. These are, by definition, consumers in the top tier or, at most, top two tiers of consumption and tariffs. Alternatively, some owners may simply have installed without a thorough analysis of long-term possibilities.

The project has made progress on other objectives, such as putting in place a training and certification programme for installers. While such a programme is not in place yet, there is a competent responsible entity (the Seychelles Institute of Technology), two individuals have been trained to train others, and there are discussions towards establishing certification criteria based on those of City and Guilds in the UK. This is a model that the Seychelles have adopted in other contexts.

The project has not yet begun implementation of two activities that are important in the longer-term: establishment of secondary legislation to promote the sustainable expansion of PV installations in the Seychelles, and national solar radiation mapping (discussion of the latter is underway with the National Meteorological Service). The project still has the opportunity to initiate these and perhaps to complete them before its end. While the current legislation allows installation of PV systems, allows their output to be fed into the grid and net-metered against the PV system owner’s consumption, it does not present any long-term obligations on PUC to continue in this manner and, in principle, could be reversed or replaced by another policy (e.g. a feed-in tariff at an unspecified value) at any time.

The Solar Radiation Mapping stands out as the only activity that has a high likelihood of not being completed by the project end because a complete year of ground-measured meteorological data is required. Instead, it should be possible to complete the proposed National Performance Assessment (NPA) before the end of the project based on data from existing PV systems as well as satellite data. The NPA would compile the performance of PV systems on the islands and use their performance as a measure for realistic outputs that can be expected from PV systems (which is the objective of a solar radiation map), and eventually as a proxy for solar radiation. While the approach is not a replacement for a solar radiation map as it does not account for losses resulting from less than optimal performance of the PV units, it does provide a reasonable assessment of what is practically achievable. Lack of capacity at PUC and SEC are both impediments to the scaling-up of PV adoption. A focus on capacity building and increased hiring or alteration of procedures to put less strain on resources should be considered (e.g. reducing the number of site visits that have to be conducted by PUC or SEC for a particular installation, perhaps spot-checking only). Similarly, increasing SEC capacity to regulate, propose and support legislation is an important step not only in scaling-up PV specifically but also advancing the Seychelles electricity sector in general.

Table 2: Summary of progress towards results matrix (based on log-frame in the ProDoc)

| Outcomes/Outputs | Indicator | Baseline | Targets | Status at MTR | Risks and Assumptions |
| --- | --- | --- | --- | --- | --- |
| Project Objective: Increase the use of grid-connected photovoltaic (PV) systems as a sustainable means of generating electricity in selected main islands and smaller islands of the Seychelles | - Amount of reduced CO2 emissions from the power sector (compared to the project baseline) by EOP, tons CO2eq | - 0 | - 1,512 | 1,094 tCO2/yr, 21,875 tCO2 over 20 years | Continued commitment of project partners, including Government agencies and investors / developers |
|  | - Cumulative installed capacity of grid-connected PV systems (kWp) | - 0 | - 1,305 | 1.242 MW, expected to reach target |  |
|  | - Cumulative total electricity generation from installed grid-connected PV systems (kWh) | - 0 | - 1,696,419 | 1,589,760 kWh/yr, 31,795,200kWh over project life |  |
| Outcome 1: Comprehensive and strengthened policy and legal frameworks adopted to promote RETs and enable grid-connected renewable energy production | - No. of grid-connected RE production projects approved and facilitated by the IER by EOP | - 0 | - At least 30 | 98 | Commitment of the various Government institutions, private sector actors and project stakeholders |
|  | - No. of grid-connected RE production projects that benefitted from the enforcement of the strengthened legal frameworks by EOP | - 0 | - At least 30 | 98 |  |
|  | - Volume of funding mobilized or granted) from the incentives scheme by EOP, US$ | - 0 | - 1,473,707 | ~$750,000 mobilised, ~$150,000 disbursed |  |
| Output 1.1 – Completed National Energy Master Plan and Energy Resource Assessment | - Government-approved National Energy Master Plan (NEMP) by Year 1 | - None | - NEMP by end of 2013 | Published NEMP document | Unchanged commitment of relevant Government institutions |
|  | - Completed and published Energy Resource Assessment Report by Year 2 | - None | - By end of 2014 | Not yet started |  |
| Output 1.2 - National Solar Irradiation Map | - Completed and published solar map by Year 2 | - 0 | - 15 months from project start | Initiated as National Performance Assessment | Unchanged commitment of relevant Government institutions |
|  | - % of regions covered with comprehensive solar radiation data by Year 2 | - General solar insolation data only | - 80% | 0% |  |
| Output 1.3 – Approved National Energy Policy | - Government-approved National Energy Policy (NEP) by Year 2 | - 0 | - End of first year | Energy Act, published | Continued interest of policymakers to expand the use of RETs in the country |
|  | - No. of approved policies on RET promotion that are strictly enforced by EOP | - No policies on RET | - At least 3 | Net-metering, SEEREP, Energy Act |  |
| Output 1.4 – Approved and enforced detailed regulations and secondary legislation in support of a new Energy Act | - No. of formulated and recommended implementing rules and regulations (IRRs) on the NEP by end of 2013 | - 0 | - At least 2 | Net-metering | Unchanged commitment of relevant Government institutions |
|  | - No. of approved and enforced secondary legislations in support of the NEP by end of 2013 | - 0 | - At least 2 | Expected results from legislation largely achieved. |  |
| Output 1.5 – Approved and enforced revised PUC Act | - Approved and enforced subsidiary legislation under the PUC Act, Business Tax Act, and Fair Trade Commission Act by end of first year | - Existing PUC Act | - By end of first year | Accomplished | Unchanged Commitment of relevant Government institutions |
| Output 1.6 – Established and Operational Independent Electricity Regulator (IER) | - No. of grid-connected RE production projects approved and facilitated by the Independent Electricity Regulator (IER) by EOP | - 0 | - 10 | 98 | IER will be authorised by law |
| Output 1.7 – Developed, Approved and Implemented Financial Mechanisms to support Purchase / Operation of Solar PV Systems | - No. of financing schemes developed, established and operational by end Year 2 | - 0 | - At least 1 | Rebate scheme, Seychelles Energy Efficiency & Renewable Energy Programme (SEEREP) | Effective coordination of various partners to establish incentive scheme |
|  | - Volume of funding mobilized or granted from the established financing scheme by EOP, US$ | - 0 | - At least US$1,473,706 | ~$750,000 mobilised ~$150,000 disbursed |  |
| Output 1.8 – Completed education and awareness campaigns promoting the benefits of RETs | - No. of designed and completed education and awareness campaigns targeting key decision-makers, potential users of PV technology, and the general public by EOP | - 0 | - At least 2 | Completed, advertisements, workshops, leaflets. | Participation by decision-makers |
|  | - No. of customers enquiring for information about PV systems from the SEC and PV dealers EOP | - 0 | - 50 | 98 systems installed | Market actors are willing to cooperate in providing this information |
| Outcome 2: Enhanced national capacity for the development, operation, and financing of RET systems | - No. of entities in the country gainfully engaged in the various supply chain activities of the PV and RET markets by EOP | - 0 | - At least 10 | 3 Main installers, unclear that market will support more. PUC, SEC. | Cooperation of concerned entities. |
|  | - No. of personnel of the MOF, local banks and FIs that are actively working on the formulation and implementation of incentive schemes and on the evaluation of the economic/financial viability of grid-connected PV system projects by end Year 1 | - 0 | - 4 | There are three to four people involved between MOF and SEC, but they are not focused full-time on understanding and developing incentive schemes |  |
|  | - No. of local banks/FIs that are providing financial assistance to grid-connected PV system projects by EOP. | - 0 | - 3 | SEEREP available at several banks, but under-subscribed. |  |
|  | - No. of joint ventures and/or licensing agreements between foreign PV manufacturers and local PV and RET companies facilitated by the business association by EOP | - 0 | - 3 | Enough to support installers |  |
| Output 2.1 – Completed Capacity Needs Assessment and Developed Capacity Building Strategy | - Finalized capacity needs assessment (CNA) finalised by Year 1 | - 0 | - 6 months of project start | CNA conducted | Continuous active participation of stakeholders in strategy development |
|  | - No. of capacity building programmes based on the CNA report designed and implemented by Year 2 | - 0 | - 2 | SIT, Training for trainers |  |
| Output 2.2 – Completed Outreach on Policy/Economic Issues | - No. of personnel of the MOF, SEC and financial institutions actively working on the formulation and implementation of incentive schemes and on the evaluation of the economic / financial viability of grid-connected PV system projects by Year 1 | - 0 | - 4 | There are 3-4 people involved between MOF and SEC, but they are not focused full-time on understanding and developing incentive schemes | Continuous active participation of government and private sector partners |
| Output 2.3 – Completed Training Program on Technical Issues | - No. of training courses on solar PV system installation, operation and maintenance designed, organized and conducted by EOP | - 0 | - 5 | One | Constant active participation of private sector partners |
|  | - Number of individuals trained by EOP | - 0 | - At least 50 | ~40, but not in depth |  |
|  | - % of trainees still involved in PV system projects by EOP, % | - 0 | - 80% | Unknown |  |
|  | - No. of private sector actors certified as solar PV technicians by EOP | - 0 | - 5 | No certification yet |  |
| Output 2.4 – Completed Training Program on Financial Issues | - No. of training courses on financing grid-connected solar PV system projects designed, organised and conducted by EOP | - 0 | - 5 | No, not clearly needed yet 0, practically, ~5 | Constant active participation of private sector partners |
|  | - Number of individuals trained by EOP | - 0 | - At least 50 | 0-5 |  |
|  | - No. of local banks / financial institutions that are providing financial assistance to grid-connected PV system projects by EOP | - 0 | - At least 3 | SEEREP, but under-subscribed |  |
| Output 2.5 – Completed Training Program to support Market Development | - No. of training courses on supply chain business operations for solar PV and other RET systems designed, organised and conducted by Year 4 | - 0 | - 5 | None, unclear need | Availability of persons in the country with sufficient technical education and capacity |
|  | - Number of individuals trained by Year 4 | - 0 | - At least 50 | Major installers learned by doing |  |
|  | - % of trainees still involved in the supply chain businesses for PV systems and other RET systems by EOP, % | - 0 | - 80 | Unknown |  |
|  | - No. of fully certified and operational entities in the country engaged in the various supply chain activities of the PV and RET markets by EOP | - 0 | - 6 | No certification in place, market unlikely to support 6 |  |
| Output 2.6 – Established Partnership and Information Sharing Platforms | - Average no. of meetings held each year of the business association starting Year 2 | - 0 | - 4 | Not Applicable | Complete cooperation of all energy sector players and project partners in data collection |
|  | - No. of joint ventures and/or licensing agreements between foreign PV manufacturers and local PV and RET companies facilitated by the business association by EOP | - 0 | - 2 | Suppliers have their relations, not joint ventures per se |  |
| Outcome 3: Increased electricity production from RET systems (e.g., PV systems) and interest among energy sector investors and operators. | - Cumulative amount of reduced CO2 emissions compared to the project baseline from the demo projects by EOP, tonnes CO2eq | - 0 | - 1,512 | 969 tCO2/yr, 19,374 tCO2 over 20 years | Continued commitment of project partners, GOS agencies and investors / developers EIB and/or other partners continue financial incentive programs after project end |
|  | - Cumulative total electricity generation from grid-connected PV systems by EOP, kWh | - Minimal | - 1,696,419 | 1,408,000 kWh/yr, 28,160,000 kWh/project life |  |
|  | - No. of replication projects implemented that are based on or influenced by the success of the PV system demonstrations by EOP | - 0 | - 3 | None for now |  |
| Output 3.1 - Technical Report on Grid Capacity and Requirements | - Completed report on grid capacity requirements by Year 1 | - None | - 6 months after project start | Completed | Active participation of PUC in drafting guidelines and standards |
| Output 3.2 – Completed Grid Upgrade, Expansion and Refurbishments | - Total installed capacity of grid-connected RE-based power systems in the Seychelles by EOP, MW | - Minimal | - At least 8 | Grid after upgrades reported to be capable of absorbing 8 MW | PUC carries out grid upgrade work according to schedule |
| Output 3.3 – Test Demonstration PV System with PUC | - Total installed capacity of grid-connected demo PV systems by Year 3, kWp | - 1 | - 5 | Fewer installed but not needed given uptake of PV. | PUC is actively involved in testing PV systems and training technicians |
|  | - Total power generation from the demo PV systems by EOP, kWh | - Minimal | - 6,500 kWh/year |  |  |
| Output 3.4 –Purchase Strategy for PV Systems | - Completed purchase strategy report on reliable and cost-effective options for purchase and installation of solar PV systems in the Seychelles | - None exists | - End Year 1 | Has not occurred as envisaged. Market has developed independently. Will be of use in the remaining phase. | Renewable energy technologies available for purchase / delivery to Seychelles at competitive prices |
|  | - No. of solar PV system project developers that considered the information in the purchase strategy report useful in their projects by Year 1 | - 0 | - 50 |  |  |
| Output 3.5 – Selected Project Demonstration Partners | - No. of interested entities that have applied for hosting demo PV system projects by Year 4 | - 0 | - 30 | Market mechanisms have taken place of envisaged public tender process; a better result overall. | Sufficient interest among potential partners |
|  | - No. of planned and approved grid-connected demo PV system projects by Year 2 | - 0 | - At least 10 |  |  |
| Output 3.6 – Completed Feasibility Analyses for Project Demonstrations | - No. of completed technical and economic feasibility analyses of potential demo sites projects by Year 4 | - 0 | - At least 10 | Feasibility analyses no longer applicable | Sufficient trained technical personnel are available |
| Output 3.7 – Signed Installation and Financing Agreements with Demonstration Partners | - No. of signed installation agreements for grid-connected PV demo projects by Year 4 | - 0 | - At least 10 | Demonstration no longer applicable given installation volume | Project financing scheme is in place in a timely manner |
| Output 3.8 - Installed Demonstration PV systems with Private Partners | - Cumulative installed capacity of grid-connected PV demo projects (kWp) by EOP | - 0 kWp | - 1,305 | Volume has been taken up by the market | Sustained participation by demonstration partners |
| Output 3.9 – Reports on the Operational Performance of Demonstration PV Systems | - No. of demo project profiles prepared and disseminated by EOP | - 0 | - At least 15 | Collection and reporting of data is lagging behind installations. | Sustained participation by demonstration partners |
|  | - No. of replication projects planned by EOP | - 0 | - At least 15 |  |  |

Project implementation and adaptive management

The ProDoc presents a well-formulated project with a clear development path, which is an asset in the implementation of a project. The project design is effective, particularly in selection of the project subject, outcomes, objectives and timing of implementation. The project entered the Seychelles at an opportune time and, as a result, found considerable demand for PV. With the project enabling deployment of PV, for example through support to PUC, the result has been rapid dissemination of PV units.

The project has been successfully adapted in three main ways. First, the project design envisaged preparing a national solar resource map, and issuing public tenders for the “the vast majority of the 1,280 kWp” to be installed. The project successfully adapted by recognizing that there is a market demand which is not waiting for such demonstrations or solar map. Thus, by making the project open to installation of solar PV by private businesses and individuals immediately, rather than pursuing a tendering process as in the project design, the project was able to successfully take advantage of market mechanisms to nearly achieve its installed PV capacity targets by mid-term. The project has also successfully adapted its rebate scheme to both residential and commercial users, applying a decreasing rebate scheme as market demand has evolved.

Second, the project design envisaged the installation of solar radiation measurement instruments (pyranometers) around the island to create a national solar irradiation map. While this is still a valuable undertaking and should be pursued, the mapping will not be completed in the project lifetime because it requires one year of data (it should be expected that the instruments are installed and measuring within the project lifetime unless this activity is abandoned). Instead, the project is proceeding with a National Performance Assessment, assessing the performance of installed PV systems and using their output as a proxy for the available solar radiation, and to ultimately determine what practical performance can be expected of installed systems.

Such an approach has the benefit that it can be completed much more quickly and at lower cost than a full national solar irradiation map. It is also more straightforward to translate the results into practical outputs of a PV system and may have more credibility with potential owners than simple solar resource measurements. On the other hand, care must be taken to remove the effect of design and installation errors and establish a benchmark for what an ideal system may produce. This is almost impossible to do without an independent solar resource measurement. From the perspective of long-term development of PV in the Seychelles, particularly if it involves larger installations (hundreds of kilowatts or megawatts) where optimization of power output is necessary, a reliable solar radiation map will be of value. A sort of hybrid mapping, where solar radiation sensors are installed and data from six months of measurements are correlated with data from existing PV systems, could relatively quickly produce a reliable assessment of solar resource.

Third, the project has effectively managed a rebate scheme with different rebates for residential and commercial PV owners and decreasing rebate over time. The decreasing rebate scheme has spurred demand for PV to an extent as potential owners try to install early to take advantage of a larger rebate (though many early adopters installed without a rebate). However, the primary benefit of the decreasing rebate scheme has been a more efficient use of GEF funds such that the funds can support the largest possible installed capacity, which is likely to be well in excess of the target by the end of the project.

Half of the installations, at the time of MTR, have taken advantage of the rebate scheme. The other half have been installed with no rebate. While, on the one hand, the rebate mechanism can be seen to have contributed to half of the current installed capacity, on the other hand half the current installed capacity was not in need of a rebate and owners have foregone the rebate which they could have earned. This may be an issue of awareness, or early adopters with financial resources simply wishing to proceed as quickly as possible without regard for a rebate. In 2014, there were 24 applications for rebates. In the first quarter of 2015, there were 25 applications. During this time period, a total of 98 PV systems were installed.

The project is in line with Seychelles energy and environmental objectives, and contributes to the stated aim of achieving 15% of electricity generation from renewable resources by 2030. It has also reasonably estimated the demand for PV during project years. The project, though, perhaps overestimated the need for the rebate scheme early on, though it has not been detrimental. Installations of PV to date remain restricted to those households with financial means. This is as should be expected two years after introduction. A financial mechanism to support the sustainable deployment of PV to other segments of society is not yet in place.

Project sustainability

The project is Moderately Likely to be sustainable. The most obvious threats to sustainability are: 1) the lack of long-term legislation and regulations supporting PV; 2) the lack of a rebate/financing mechanism that makes PV attractive to the large number of consumers of middle-income and mid-tier consumption; and 3) the lack of a replacement for PUC for the high-profit revenue that it loses when consumers in higher tiers install PV.

The current net-metering scheme is not protected by any long-term legislation. It may be changed or rescinded at any time. As a result, only those who can expect to recoup their investment quickly, and are capable of betting that this will be before a change is made in legislation, would be willing to make an investment in PV under the current regulations.

The lack of capacity at PUC and SEC to support large-scale adoption of PV also presents a threat to long-term sustainability of the project. Outside of these items, the limits on PV are the limits on the grid’s ability to absorb a fluctuating power source, which are essentially technical (this limit is expected to be around 8 MW based on the current infrastructure. The project targets the installation of 1.3 MW). The Seychelles can continue to grow its installed PV base as it grows its ability to manage a grid with ever larger solar penetration.

## Summary of MTR ratings

MTR ratings, as defined in UNDP MTR guidelines, revolve around expectations of project achievement by the end of the project. In order to make the best use of the ratings, the ratings below are made on the realistic (as assessed at MTR by the consultant) assumption that the project is able to work efficiently in the time remaining until its end.

Table 3: MTR Ratings & Achievement Summary Table

| Measure | MTR Rating | Achievement Description |
| --- | --- | --- |
| Progress Towards Results |  |  |
| Project Objective: Increase the use of grid-connected photovoltaic (PV) systems as a sustainable means of generating electricity in selected main islands and smaller islands of the Seychelles | HS | The project is well on-track to achieve its installed capacity target, with some 1.24 MW of a 1.3 MW target already installed. |
| Outcome 1: Comprehensive and strengthened policy and legal frameworks adopted to promote RETs and enable grid-connected renewable energy production | HS | The policy framework allowing grid-connected PV is in place. Secondary legislation as well as resource assessments are not yet in place but may be in place by end of project. |
| Outcome 2: Enhanced national capacity for the development, operation and financing of RET systems | HS | Capacity needs assessment has been undertaken as well as an initial training. SIT is tasked with developing further training. Training and capacity building are in general lagging behind but can be expected to be achieved by the end of the project given a focused effort. |
| Outcome 3: Increased electricity production from RET systems (e.g. PV systems) and interest among energy sector investors and operators | HS | There is clearly increased production from RET systems and increased interest. Grid upgrades have been implemented. Assessment of performance has not occurred but can be expected by the end of the project. |
| Project Implementation & Adaptive Management | S | Project implementation has been successful and project management very effective in bringing together stakeholders and supporting the issuance of the main legislation required for connection to the grid. Implementation is delayed or has not started on secondary legislation, capacity building and resource assessment. The project has successfully made important adaptations that have allowed it to essentially achieve installed capacity targets ahead of schedule. Having achieved installed capacity targets, the remaining items can be a focus in the remaining project time. Implementation of most of the seven components is leading to efficient and effective project implementation and adaptive management except for only a few that are subject to improvement. Work planning, reporting and tracking of co-finance would benefit from some improvement. |
| Sustainability | ML | Project sustainability is moderately likely with the main barriers being adoption of legislation guaranteeing long-term return on PV units and availability of a sustainable financing mechanism. |

If the project were to be rated on its progress to date, instead of an expectation of its status at project end, it would be rated as “Satisfactory” because it has satisfactorily achieved its main objectives, but has not initiated activities, such as the National Performance Assessment and secondary legislation, which were scheduled to be completed by the second year of the project. The project is in a position to receive a Highly Satisfactory rating at its terminal evaluation, provided that it is able to efficiently execute the outstanding tasks. The project is in somewhat of a precarious position because, although it has been successful in reaching major targets, if it fails to develop the supporting environment before its end it may find that sustainability is limited and adoption fails in the long-term.

## Summary of conclusions

- The project is well designed, with an opportune selection of topic and timing such that the removal of barriers has resulted in the desired adoption rate.

- The project is ahead of schedule in reaching its installed capacity, energy generation and GHG emissions reduction targets. Project management has been highly effective in engaging stakeholders around these targets.

- As a result of reaching its main objectives, the project has the opportunity to address some factors beyond its original design, such as supporting a feed-in tariff or other mechanism to expand sustainability and adoption beyond that originally envisaged, and a more comprehensive quality assurance programme.

- Project management has been highly effective in bringing together national stakeholders, such as the Public Utilities Corporation, the Seychelles Energy Commission and the Development Bank of the Seychelles to support the deployment of PV. Without such effective inclusion of stakeholders it is likely the adoption of PV would have been delayed many years or not achieved.

- The relationship between the rebate scheme (and SEEREP financing mechanism) and the adoption of PV remains poorly understood, as evidenced by half of the installations essentially ignoring the rebate. Further understanding of the financial mechanism or streamlining of its processes is needed to make it more attractive to potential PV system owners.

- The project has not yet addressed some items, most specifically the solar radiation mapping (the NPA is to be pursued in its place, a good adaptation in view of current circumstances of a large PV installed base), capacity building and training, and implementation of secondary legislation to support long-term adoption of PV. Addressing these issues should be a priority in the remaining project time.

- Record-keeping for main documents, PIRs and reports is to be commended, not just for this project but for the web portal which supports such functions for all Seychelles projects under UNDP-GEF.

- In terms of design, timing and intervention, the project can be considered best practice as it identified an opportunity where UNDP-GEF intervention could effectively remove barriers to adoption of a technology and thus facilitate its uptake.

- Adoption on Praslin has lagged adoption on Mahé. While this should be expected, further effort to encourage adoption can be effective, in particular supporting one or two installers on the island.

- The overall practice of establishing a PCU to support and administer such projects seems to be particularly conducive to effective project management and collaboration amongst projects. The camaraderie in having the various project managers in one location appears to be to the overall benefit of the projects managers and projects. Establishment of such a PCU may be considered good practice for replication in other areas.

- Lack of capacity at PUC and SEC is a limitation which should be addressed.

## Summary of recommendations

- The project should prioritise in the coming period: establishment of sustainable legislation, capacity building and training (for installers, PUC, and SEC), and implementation of the National Performance Assessment (NPA).

- The relationship between financial incentives and adoption is not clearly understood. Better study of the current financial mechanism and how to increase its appeal to consumers (in combination with legislation) is necessary.

- It is necessary to establish a system that removes current delays and bottle-necks in installation, whether by increasing resources at PUC and SEC, or by changing installation procedures to require reduced PUC and SEC resources.

- Increasing capacity at PUC and SEC, through capacity building, increased hiring, and/or outsourcing should be carefully considered as the electricity sector in general takes on ever-larger changes. Where hiring of additional staff is not possible or not favourable, specific functions may be outsourced (potentially at no cost to PUC and SEC). Examples include filing of paperwork, or particular site activities or inspections which may be done by qualified and certified personnel (potentially the installers) and only spot-checked by PUC and SEC, as compared with the present system where PUC and SEC must visit each PV installation multiple times (initial inspection, at construction and commissioning).

- There is currently no mechanism to ensure quality or hold installers responsible. A sort of consumer protection mechanism, supported for example by standard contracts, should be put in place. Such a mechanism should track installers and hold them accountable. It should also track system performance (perhaps making cumulative performance of system by an installer available to the public). Such a mechanism should also protect installers from unreasonable customer claims.

- Follow-up of co-finance commitments for the remaining tasks as these can be important resources in supporting and achieving remaining tasks.

- There are presently no installers on Praslin. The support of one or two installers on Praslin could make PV much more accessible to the residents of Praslin as compared with having to request installers from the main island.

- Given resources, the project may have an opportunity for further cooperation with other entities (e.g. the Clinton Climate Initiative and/or the Green Climate Fund) to promote longevity of the project, support study and research related to PV and Seychelles climate mitigation, or enable projects and other development vehicles to accept external investment.

# Introduction

In accordance with the UNDP and GEF Monitoring and Evaluation (M&E) policies and procedures, a Midterm Review (MTR) of the project “Grid-Connected Rooftop Photovoltaic Systems in Seychelles”, implemented by Seychelles Energy Commission, is to be undertaken at the mid-point of project implementation, which – according to the project schedule in the ProDoc – occurs in the 2nd quarter 2014. However, the actual project start date was February 2013 (when the funds were received), and therefore the Midterm Review mission was held in May 2015.

## Purpose and objectives of the MTR

The Project Document states:

“The project will undergo an independent Mid-Term Evaluation at the mid-point of project implementation. The Mid-Term Evaluation will determine progress being made toward the achievement of outcomes and will identify course correction if needed. It will focus on the effectiveness, efficiency and timeliness of project implementation; will highlight issues requiring decisions and actions; and will present initial lessons learned about project design, implementation and management. Findings of this review will be incorporated as recommendations for enhanced implementation during the final half of the project’s term.”

The objective of the MTR is to gain an independent analysis of the progress of the project so far. The MTR identifies potential project design problems, assesses progress towards the achievement of the project objective, identifies and documents lessons learned about project design, implementation and management.

The MTR Report focuses on the impact, effectiveness, efficiency, relevance and sustainability and highlight challenges as well as lessons learned in the project implementation thus far. The MTR assesses early signs of project success or failure and identifies the necessary changes to be made. Findings of this review will be incorporated as recommendations for enhanced implementation during the remaining project term.

Project performance is rated based on the indicators of the project’s logical framework (as presented in the Project Document) and the rating scales identified in the Guidance for Conducting Midterm Reviews of UNDP-Supported, GEF-Financed projects. Where it is found that present indicators may not be applicable or ideal, alternatives are recommended.

## Scope and methodology

Overall guidance on project-level monitoring methodologies is provided by the UNDP Guidance for Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects. The approach of the MTR consultant is based on the Guidance document together with the ToRs, and in consultation with the UNDP Country Office.

In preparing the Midterm Review Report, several sources of information were consulted. These include interviews with stakeholders, review of project documents and evaluation of public sources of information.

In addition, the consultant carried out case-specific analysis of the available information and compared it with observations from the mission.

The Midterm Review considers the adequacy of the overall project concept and design, and the extent to which the project has achieved its stated targets and can be expected to achieve them by its end. The Midterm Review similarly considers what remains to be done, gaps in implementation, threats to success of the project, and new opportunities that have developed or been exposed as a result of the project development to-date. The project’s impact on GHG emissions as presented in the UNDP ProDoc and GEF CEO ER are also reviewed in accordance with GEF guidelines.

The timeliness of performance is evaluated, as is the use of GEF funds and co-finance.

Finally, the Midterm Review considers the effect on Government, and the overall assessment and perception of the situation in Seychelles since the beginning of the project, and until the time of the Midterm Review. The effect the project has had on policy and development within Seychelles is assessed, for the implemented portion, and/or what remains to be done during the second half of the Project’s lifetime.

A presentation of the initial findings was made at the end of the review mission to the project management, UNDP CO, and other stakeholders.

The findings of the MTR and its recommendations are captured in this report.

## Structure of the MTR report

This report contains the MTR Report body, Executive Summary, and an Introduction to the report. The body of this report is structured around three main chapters: a description of the project and its context (Chapter Three); the findings of the evaluation (Chapter Four); and the conclusions and recommendations (Chapter Five). The Annexes provide information on the Terms of Reference, mission details, information collected, evaluation questions, and the applicable rating scales for each measure assessed.

The project description (Chapter Three) presents a summary of project facts, such as start date, duration, the context in which the project started its objectives and stakeholders.

Chapter Four presents the findings of the report with respect to project design, implementation, monitoring, risk management and reporting. It provides quantitative evaluation of several aspects of the project, as required by UNDP guidelines.

Chapter Five presents the conclusions, recommendations and lessons learned from the project. These include actions that might be taken now to help ensure the sustainability and continuity of project achievements, as well as steps that can be taken to help improve the design and implementation of future projects.

# Project Description and Background Context

The Grid-Connected Rooftop Photovoltaic System project was funded under the Seychelles GEF-4 Climate Change Mitigation (CCM) Country Allocation.

The CEO Endorsement Request was submitted in March 2012, and the Project Document signed in September 2012.

## Development context

Prior to project commencement, the Seychelles was almost 100% dependent on imported oil to meet its energy needs, including electricity production. The project aims to increase the use of grid-connected photovoltaic (PV) systems as a sustainable means of generating electricity in selected main islands and smaller islands of the Seychelles, with a focus on small-scale producers who are already connected to the national electricity grid.

The project’s revision of the legal, regulatory and policy framework will better support the adoption of renewable energy technologies, and grid-connected PV systems in particular. It also provides for the implementation of financial mechanisms that will make the purchase and installation of solar PV systems more attractive to the private sector; establish the first market supply chain for solar PV systems in the country; provide training to establish local capacity for the installation and maintenance of PV systems; and demonstrate for the first time in the Seychelles the viability and practicality of grid-connected PV systems through demonstration PV systems.

Together, these actions are designed to play a critical role in “jump-starting” the adoption of solar PV technology in the Seychelles, and in setting the stage for broad-scale replication by reducing the costs of PV technology through a market-based approach that will establish financial incentive mechanisms for PV systems and reduce transaction costs (by creating a reliable supply chain and establishing local capacity for installation and maintenance). In this way, the project is designed to help transform an energy sector that today is almost 100% dependent on imported fossil fuels into one where solar PV and other RETs provide a significant percentage of national energy production going forward. In the national context, the project provides important background information and serves as a pilot for the Seychelles’ target of generating 15% of its electricity from renewable resources by 2030. In the greater development context, the project also puts in place mechanism to later support the deployment of other RETs, as well as energy savings and energy efficiency mechanisms.

## Project description and strategy

The project seeks to increase the use of grid-connected photovoltaic (PV) systems as a sustainable means of generating electricity on main islands and smaller islands of the Seychelles. On the main islands, where the Public Utilities Corporation (PUC) is the supplier of almost all electricity, there is a well-established grid system that can support the feed-in of PV-generated electricity into the grid. Most importantly, the PUC is willing, for the first time, to support the sale of power back to the grid (due to new national policies that prioritise renewable energy and to the country’s desire for WTO accession, which requires it to "open up" its energy market).

The project is designed to transform an energy sector that today is almost 100% dependent on imported fossil fuel (diesel) into one where solar PV and other renewable energies provide a 15% of national electricity generation.

The project offers a rebate scheme for those who install PV units. The project initially offered a rebate of 35% of the cost of a PV system on up to 3 kW of PV installation for residential consumers, later decreasing to 25% (at the time of MTR, installers reported that this decrease in rebate had created a surge in demand just before the expiry of the higher rebate at the end of April 2015). Commercial installations receive a 15% rebate on up to 15 kW of installed capacity. The cost of a system, per kilowatt, is fixed and announced as an index by the project for the purposes of calculating the rebate. The index price is adjusted as market prices change. This also serves to create a sort of guideline to market prices. As of the MTR, the index prices are US$2.8/Wp for residential systems and US$3.2/Wp for commercial systems.

Before installation of a system, the property is inspected by PUC. Once a PV system is installed by a certified installer, the system is inspected by PUC and SEC, and the owner is eligible to receive the rebate as described above. Only systems installed by certified installers are eligible for rebate.

There is also a loan scheme, the Seychelles Energy Efficiency and Renewable Energy Programme (SEEREP), that provides loans at 5% interest rate to support projects that promote energy efficiency or renewable energy, with loan terms of up to five years. Those installing PV units can take advantage of the loan scheme.

## Project implementation arrangements

The Executing Agency is the Seychelles Energy Commission (SEC) formed under the Ministry of Environment and Energy. UNDP is the Implementing Agency. The project is implemented under the National Implementation Modality (NIM).

UNDP and the Government of Seychelles have formed a centralised Programme Coordination Unit (PCU) as a unit within the MEECC that supports, administers and coordinates the implementation of all GOS-UNDP-GEF environment projects in the Seychelles. The PCU is comprised of a Programme Coordinator/Chief Technical Advisor, and administrative and accounts support staff. The Project Managers sit within the PCU.

## Project timing and milestones

The following is the project implementation schedule proposed at the design stage in the ProDoc.

## Main stakeholders

The following is a list of the Stakeholders referred to in the Project Document:

- UNDP

- Seychelles Energy Commission (SEC)

- Ministry of Environment  and Energy

- Ministry of Finance (MoF)

- Public Utilities Cooperation (PUC)

- Seychelles Petroleum Company (SEYPEC)

- Seychelles Institute of Technology (SIT)

- University of Seychelles (UniSey)

- Seychelles Islands Foundations (SIF)

- Ministry of National Development (MNB)

- National Climate Change Committee (NCCC)

- Climate and Environmental Services Division (CESD), under MHAETE

- National Meteorological Services (NMS)

- Independent Energy Regulatory (planned to be established in the design phase)

- Environmental NGO community

- MASDAR

- Private sector partners (PV system operators)

Some of these stakeholders were interviewed during the MTR mission. A detailed mission itinerary and list of people interviewed by the MTR consultant during the mission are included in Annexes 4 and 5 of this report. Not all stakeholders have been engaged at this stage of the project.

# Findings

## Project strategy

Project design

The ProDoc presents a well-formulated project with a clear development path, which is an asset in the implementation of a project. The project design is effective, particularly in selection of the project subject, outcomes, objectives, and timing of implementation. The project entered the Seychelles at an opportune time and as a result found considerable (baseline) demand for PV. With the project enabling deployment of PV, for example through support to PUC, the result has been rapid dissemination of PV units.

The project also facilitated dissemination of PV units under the rebate scheme. Half of the installations, at the time of MTR, have taken advantage of the rebate scheme. The other half have been installed with no rebate. While, on the one hand, the rebate mechanism can be seen to have contributed to half of the current installed capacity, on the other hand half the current installed capacity was not in need of a rebate and owners have foregone the rebate which they could have earned. This may be an issue of awareness, or early adopters with financial resources simply wishing to proceed as quickly as possible without regard for a rebate. In 2014, there were 24 applications for rebates. In the first quarter of 2015, there were 25 applications. During this time period, 98 total PV systems were installed.

The project is in line with Seychelles energy and environmental objectives and contributes to the stated aim of achieving 15% of electricity generation from renewable resources by 2030. The use of renewable energy is a main sustainable development goal for the Seychelles. The Seychelles’ Second National Communication to the UNFCCC states “The GHG mitigation options proposed for the commercial, institutional and residential sectors are all aimed at increasing the use of solar energy technologies and energy conservation technologies. The use of these solar energy technologies will contribute to reduce the consumption of gasoil for electricity production in hotels that are situated on outlying islands.” (p45).

The 2015 Africa Economic Outlook Country Profile for the Seychelles states, “According to the last Millennium Development Goals (MDG) report in 2013, the country has partially met MDG Goal 7 (ensuring environmental sustainability): only partially, though, as a result of still high carbon dioxide emission per capita given that most energy is based on fuel-based consumption.”

Thus it is reasonable to conclude that the project is very much in line with, indeed is enabling, one of the Seychelles’ main development goals. Solar and wind energy are of particular importance to islands such as the Seychelles and other remote areas that require the import of fuel. They are, in a sense, the oil derricks, refineries, and power plants of regions that have no oil.

The project has also reasonably estimated the demand for PV during project years,, though perhaps overestimated the need for the rebate scheme early on. This has not been detrimental. Installations of PV to date remain restricted to those households with financial means. This is as should be expected two years after introduction. A financial mechanism to support the sustainable deployment of PV to other segments of society is not yet in place.

## Progress towards results

The following table presents a summary of the status of project activities as of the MTR. Under the “Status at MTR” column, cells coloured yellow indicate targets which can be expected to be met by project end. Cells coloured green indicate targets already met.

Table 4: Summary of progress towards results matrix (based on log-frame in the ProDoc)

| Outcomes/Outputs | Indicator | Baseline | Targets | Status at MTR | Risks and Assumptions |
| --- | --- | --- | --- | --- | --- |
| Project Objective: Increase the use of grid-connected photovoltaic (PV) systems as a sustainable means of generating electricity in selected main islands and smaller islands of the Seychelles | - Amount of reduced CO2 emissions from the power sector (compared to the project baseline) by EOP, tons CO2eq | - 0 | - 1,512 | 1,094 tCO2/yr, 21,875 tCO2 over 20 years | Continued commitment of project partners, including Government agencies and investors / developers |
|  | - Cumulative installed capacity of grid-connected PV systems (kWp) | - 0 | - 1,305 | 1.242 MW, expected to reach target |  |
|  | - Cumulative total electricity generation from installed grid-connected PV systems (kWh) | - 0 | - 1,696,419 | 1,589,760 kWh/yr, 31,795,200 kWh over project life |  |
| Outcome 1: Comprehensive and strengthened policy and legal frameworks adopted to promote RETs and enable grid-connected renewable energy production | - No. of grid-connected RE production projects approved and facilitated by the IER by EOP | - 0 | - At least 30 | 98 | Commitment of the various Government institutions, private sector actors and project stakeholders |
|  | - No. of grid-connected RE production projects that benefitted from the enforcement of the strengthened legal frameworks by EOP | - 0 | - At least 30 | 98 |  |
|  | - Volume of funding mobilized or granted) from the incentives scheme by EOP, US$ | - 0 | - 1,473,707 | ~$750,000 mobilised, ~$150,000 disbursed |  |
| Output 1.1 – Completed National Energy Master Plan and Energy Resource Assessment | - Government-approved National Energy Master Plan (NEMP) by Year 1 | - None | - NEMP by end of 2013 | Published NEMP document | Unchanged commitment of relevant Government institutions |
|  | - Completed and published Energy Resource Assessment Report by Year 2 | - None | - By end of 2014 | Not yet started, behind schedule but may be achieved by project end with concentrated effort |  |
| Output 1.2 - National Solar Irradiation Map | - Completed and published solar map by Year 2 | - 0 | - 15 months from project start | Not yet started, behind schedule but may be achieved by project end with concentrated effort | Unchanged commitment of relevant Government institutions |
|  | - % of regions covered with comprehensive solar radiation data by Year 2 | - General solar insolation data only | - 80% | 0%, behind schedule but may be achieved by project end with concentrated effort |  |
| Output 1.3 – Approved National Energy Policy | - Government-approved National Energy Policy (NEP) by Year 2 | - 0 | - End of first year | Energy Act, published | Continued interest of policymakers to expand the use of RETs in the country |
|  | - No. of approved policies on RET promotion that are strictly enforced by EOP | - No policies on RET | - At least 3 | Net-metering, SEEREP, Energy Act |  |
| Output 1.4 – Approved and enforced detailed regulations and secondary legislation in support of a new Energy Act | - No. of formulated and recommended implementing rules and regulations (IRRs) on the NEP by end of 2013 | - 0 | - At least 2 | Net-metering | Unchanged commitment of relevant Government institutions |
|  | - No. of approved and enforced secondary legislations in support of the NEP by end of 2013 | - 0 | - At least 213 | Expected results from legislation largely achieved. |  |
| Output 1.5 – Approved and enforced revised PUC Act | - Approved and enforced subsidiary legislation under the PUC Act, Business Tax Act, and Fair Trade Commission Act by end of first year | - Existing PUC Act | - By end of first year | Accomplished | Unchanged Commitment of relevant Government institutions |
| Output 1.6 – Established and Operational Independent Electricity Regulator (IER) | - No. of grid-connected RE production projects approved and facilitated by the Independent Electricity Regulator (IER) by EOP | - 0 | - 10 | 98 | IER will be authorised by law |
| Output 1.7 – Developed, Approved and Implemented Financial Mechanisms to support Purchase / Operation of Solar PV Systems | - No. of financing schemes developed, established and operational by end Year 2 | - 0 | - At least 1 | Rebate scheme, SEEREP | Effective coordination of various partners to establish incentive scheme |
|  | - Volume of funding mobilized or granted from the established financing scheme by EOP, US$ | - 0 | - At least US$1,473,706 | ~$750,000 mobilised ~$150,000 disbursed |  |
| Output 1.8 – Completed education and awareness campaigns promoting the benefits of RETs | - No. of designed and completed education and awareness campaigns targeting key decision-makers, potential users of PV technology, and the general public by EOP | - 0 | - At least 2 | Completed, advertisements, workshops, leaflets. | Participation by decision-makers |
|  | - No. of customers enquiring for information about PV systems from the SEC and PV dealers EOP | - 0 | - 50 | 98 systems installed | Market actors are willing to cooperate in providing this information |
| Outcome 2: Enhanced national capacity for the development, operation, and financing of RET systems | - No. of entities in the country gainfully engaged in the various supply chain activities of the PV and RET markets by EOP | - 0 | - At least 10 | 3 Main installers, unclear that market will support more. PUC, SEC. | Cooperation of concerned entities. |
|  | - No. of personnel of the MOF, local banks and FIs that are actively working on the formulation and implementation of incentive schemes and on the evaluation of the economic/financial viability of grid-connected PV system projects by end Year 1 | - 0 | - 4 | >4, not full-time. This remains an issue to be addressed. |  |
|  | - No. of local banks/FIs that are providing financial assistance to grid-connected PV system projects by EOP. | - 0 | - 3 | SEEREP available at several banks, but under-subscribed. |  |
|  | - No. of joint ventures and/or licensing agreements between foreign PV manufacturers and local PV and RET companies facilitated by the business association by EOP | - 0 | - 3 | Sufficient to support installers |  |
| Output 2.1 – Completed Capacity Needs Assessment and Developed Capacity Building Strategy | - Finalized capacity needs assessment (CNA) finalised by Year 1 | - 0 | - 6 months of project start | CNA conducted | Continuous active participation of stakeholders in strategy development |
|  | - No. of capacity building programmes based on the CAN report designed and implemented by Year 2 | - 0 | - 2 | SIT, ToT, Shaun White |  |
| Output 2.2 – Completed Outreach on Policy/Economic Issues | - No. of personnel of the MOF, SEC, and financial institutions actively working on the formulation and implementation of incentive schemes and on the evaluation of the economic / financial viability of grid-connected PV system projects by Year 1 | - 0 | - 4 | >4 | Continuous active participation of government and private sector partners |
| Output 2.3 – Completed Training Program on Technical Issues | - No. of training courses on solar PV system installation, operation and maintenance designed, organized and conducted by EOP | - 0 | - 5 | One | Constant active participation of private sector partners |
|  | - Number of individuals trained by EOP | - 0 | - At least 50 | ~40, but not in depth |  |
|  | - % of trainees still involved in PV system projects by EOP, % | - 0 | - 80% | Unknown |  |
|  | - No. of private sector actors certified as solar PV technicians by EOP | - 0 | - 5 | No certification yet |  |
| Output 2.4 – Completed Training Program on Financial Issues | - No. of training courses on financing grid-connected solar PV system projects designed, organised and conducted by EOP | - 0 | - 5 | No, not clearly needed yet 0, practically, ~5 | Constant active participation of private sector partners |
|  | - Number of individuals trained by EOP | - 0 | - At least 50 | 0-5 |  |
|  | - No. of local banks / financial institutions that are providing financial assistance to grid-connected PV system projects by EOP | - 0 | - At least 3 | SEEREP, but under-subscribed |  |
| Output 2.5 – Completed Training Program to support Market Development | - No. of training courses on supply chain business operations for solar PV and other RET systems designed, organised and conducted by Year 4 | - 0 | - 5 | None, unclear need | Availability of persons in the country with sufficient technical education and capacity |
|  | - Number of individuals trained by Year 4 | - 0 | - At least 50 | Major installers learned by doing |  |
|  | - % of trainees still involved in the supply chain businesses for PV systems and other RET systems by EOP, % | - 0 | - 80 | Unknown |  |
|  | - No. of fully certified and operational entities in the country engaged in the various supply chain activities of the PV and RET markets by EOP | - 0 | - 6 | No certification in place, market unlikely to support 6 |  |
| Output 2.6 – Established Partnership and Information Sharing Platforms | - Average no. of meetings held each year of the business association starting Year 2 | - 0 | - 4 | Not Applicable | Complete cooperation of all energy sector players and project partners in data collection |
|  | - No. of joint ventures and/or licensing agreements between foreign PV manufacturers and local PV and RET companies facilitated by the business association by EOP | - 0 | - 2 | Suppliers have their commercial relationships, not joint ventures per se |  |
| Outcome 3: Increased electricity production from RET systems (e.g., PV systems) and interest among energy sector investors and operators. | - Cumulative amount of reduced CO2 emissions compared to the project baseline from the demo projects by EOP, tonnes CO2eq | - 0 | - 1,512 | 969 tCO2/yr, 19,374 tCO2 over 20 years | Continued commitment of project partners, GOS agencies and investors / developers EIB and/or other partners continue financial incentive programs after project end |
|  | - Cumulative total electricity generation from grid-connected PV systems by EOP, kWh | - Minimal | - 1,696,419 | 1,408,000 kWh/yr, 28,160,000 kWh/project life |  |
|  | - No. of replication projects implemented that are based on or influenced by the success of the PV system demonstrations by EOP | - 0 | - 3 | None for now |  |
| Output 3.1 - Technical Report on Grid Capacity and Requirements | - Completed report on grid capacity requirements by Year 1 | - None | - 6 months after project start | Completed | Active participation of PUC in drafting guidelines and standards |
| Output 3.2 – Completed Grid Upgrade, Expansion and Refurbishments | - Total installed capacity of grid-connected RE-based power systems in the Seychelles by EOP, MW | - Minimal | - At least 8 | Grid reported to be capable of absorbing 8 MW after upgrades | PUC carries out grid upgrade work according to schedule |
| Output 3.3 – Test Demonstration PV System with PUC | - Total installed capacity of grid-connected demo PV systems by Year 3, kWp | - 1 | - 5 | Fewer installed but not needed given uptake of PV. | PUC is actively involved in testing PV systems and training technicians |
|  | - Total power generation from the demo PV systems by EOP, kWh | - Minimal | - 6,500 kWh/year |  |  |
| Output 3.4 –Purchase Strategy for PV Systems | - Completed purchase strategy report on reliable and cost-effective options for purchase and installation of solar PV systems in the Seychelles | - None exists | - End Year 1 | Has not occurred as envisaged. Market has developed independently. Will be of use in the remaining stages of the project. | Renewable energy technologies available for purchase / delivery to Seychelles at competitive prices |
|  | - No. of solar PV system project developers that considered the information in the purchase strategy report useful in their projects by Year 1 | - 0 | - 50 |  |  |
| Output 3.5 – Selected Project Demonstration Partners | - No. of interested entities that have applied for hosting demo PV system projects by Year 4 | - 0 | - 30 | Market mechanisms have taken place of envisaged public tender process; a better result overall. | Sufficient interest among potential partners |
|  | - No. of planned and approved grid-connected demo PV system projects by Year 2 | - 0 | - At least 10 |  |  |
| Output 3.6 – Completed Feasibility Analyses for Project Demonstrations | - No. of completed technical and economic feasibility analyses of potential demo sites projects by Year 4 | - 0 | - At least 10 | Feasibility analyses no longer applicable | Sufficient trained technical personnel are available |
| Output 3.7 – Signed Installation and Financing Agreements with Demonstration Partners | - No. of signed installation agreements for grid-connected PV demo projects by Year 4 | - 0 | - At least 10 | Demonstration no longer applicable given installation volume | Project financing scheme is in place in a timely manner |
| Output 3.8 - Installed Demonstration PV systems with Private Partners | - Cumulative installed capacity of grid-connected PV demo projects (kWp) by EOP | - 0 kWp | - 1,305 | Volume has been taken up by the market | Sustained participation by demonstration partners |
| Output 3.9 – Reports on the Operational Performance of Demonstration PV Systems | - No. of demo project profiles prepared and disseminated by EOP | - 0 | - At least 15 | Collection and reporting of data is lagging behind installations. | Sustained participation by demonstration partners |
|  | - No. of replication projects planned by EOP | - 0 | - At least 15 |  |  |

The project has progressed steadily, with increasing adoption of PV over time. The charts on the following pages show how the installation of PV has progressed until June 2015. Of a total of 98 projects installed to June 25, 2015, representing 1,243 kW of installed capacity, 26 projects were commercial installations, representing 872 kW of installed capacity (70% of the total installed capacity). Sixty nine projects were residential installations, representing a total installed capacity of 359 kW. Three projects were considered demonstration projects (installations on PUC, and by installers on their own facilities), representing 12 kW of installed capacity.

Figure 1 Number of projects installed each month September 2013 - June 2015

Figure 2 Capacity installed each month September 2013 - June 2015

Figure 3 Cumulative number of projects as a function of time

Figure 4 Cumulative installed capacity as a function of time

Figure 5 Example of a residential installation that suffers shading in the afternoon and thus significant unnecessary losses (in this case the owner was apparently aware and insisted on having it in this location)

Figure 6 Example of a successful commercial installation at a hotel used as shading for a car park (Praslin).

Figure 7 Off-grid PV modules on the home of a hobbyist on Praslin

Figure 8 Example of a PV system that is not performing and was perhaps poorly sized to start with. The client complained that the installer has been unresponsive to requests to troubleshoot the project. This is a demonstration of the need for some kind quality assurance and consumer protection mechanism. In this case, the client paid for a system and is not able to reap the benefits. Uncertainty over the performance of even a few PV systems will harm the overall market as potential owners will be afraid to invest lest they end up with a under-performing system. The inverter for this installation is in the following figure.

Figure 9 Example of a poorly installed PV system. The system is not performing and the owner is unable to get a response from the installer. Despite having paid for a data-logger to allow the owner to access the PV system data online, the owner cannot access the information and is not aware of any rights that owners may have to the data generated by their systems.

Remaining barriers to achieving the project objectives

There do not seem to be any insurmountable barriers to achieving project objectives. It will, however, require a dedicated and focused effort to achieve the outputs which at this point are not achieved.

The main barrier may be the limited time before project closing in September 2016.

## Project implementation and adaptive management

Adaptive management

The project has been successfully managed, which has enabled it to focus on, and largely achieve, ahead of schedule the main targets for installed capacity and existence of enabling legislation.

The project has been successfully adapted in three main ways. First, the project design envisaged preparing a national solar resource map, and issuing public tenders for the “the vast majority of the 1,280 kWp” to be installed. The project successfully adapted by recognizing that there is a market demand which is not waiting for such demonstrations or solar map. Thus, by making the project open to installation of solar PV by private businesses and individuals immediately, rather than pursuing a tendering process as in the project design, the project was able to successfully take advantage of market mechanisms to nearly achieve its installed PV capacity targets by mid-term. The project has also successfully adapted its rebate scheme to both residential and commercial users, applying a decreasing rebate scheme as market demand has evolved.

Second, the project design envisaged the installation of solar radiation measurement instruments (pyranometers) around the island to create a national solar irradiation map. While this still a valuable undertaking and should be pursued, the mapping will not be completed in the project lifetime because it requires one year of data (it should be expected that the instruments are installed and measuring within the project lifetime unless this activity is abandoned). Instead, the project is proceeding with a National Performance Assessment, assessing the performance of installed PV systems and using their output as a proxy for the available solar radiation, and to ultimately determine what practical performance can be expected of installed systems.

Such an approach has the benefit that it can be completed much more quickly and at lower cost than a full national solar irradiation map. It is also more straightforward to translate the results into practical outputs of a PV system and may have more credibility with potential owners than simple solar resource measurements. On the other hand, care must be taken to remove the effect of design and installation errors and establish a benchmark for what an ideal system may produce. This is almost impossible to do without an independent solar resource measurement. From the perspective of long-term development of PV in the Seychelles, particularly if it involves larger installations (hundreds of kilowatts or megawatts) where optimization of power output is necessary, a reliable solar radiation map will be of value. A sort of hybrid mapping, where solar radiation sensors are installed and data from six months of measurements are correlated with data from existing PV systems could relatively quickly produce a reliable assessment of solar resource.

Third, the project has effectively managed a rebate scheme with different rebates for residential and commercial PV owners and decreasing rebate over time. The decreasing rebate scheme has spurred demand for PV to an extent as potential owners try to install early to take advantage of a larger rebate (though many early adopters installed without rebate). However, the primary benefit of the decreasing rebate scheme has been a more efficient use of GEF funds such that the funds can support the largest possible installed capacity, which is likely to be well in excess of the target by the end of the project.

In the remaining part of the project, management focus on more detailed tasks will be required to help the project achieve its remaining targets. The main outstanding tasks and their stakeholders are listed in Table 5 below.

Table 5 Main outstanding items and stakeholders for these items

| Item | Stakeholders |
| --- | --- |
| Legislation and regulations to promote the long-term sustainability of PV in the Seychelles | SEC/PUC |
| Strategy to promote financial sustainability and even profitability for PUC from PV | PUC/SEC |
| Streamlining the licensing, construction, grid connection and certification of PV installations, either through increased capacity at PUC/SEC or streamlining of the process and outsourcing elements | SEC/PUC |
| Quality Control and Assurance, as well as consumer protection to ensure installers perform proper work; consumers have a grievance mechanism and are protected from poor installers, and installers are protected from unreasonable consumer demands. Such a programme should include elements to ensure installers do not oversize a system (for the benefit of selling more PV when the client cannot use it or it will not perform); and should clarify rights of access to the data generated by the PV unit (the data should reasonably belong to the PV system owner). | SEC/PUC/Installers |
| Training | SIT, Installers, SEC, PUC |
| Sustainable finance mechanism to spread PV to lower tier consumers | DBS, SEC |
| National Performance Assessment, Solar Radiation Mapping | NMS, SEC |

Work planning

While the PIRs effectively capture project achievements, they do not include sufficient emphasis on work planning. As such, this is one of the main areas to be improved in the remaining project time. This should begin with the formulation of a work plan immediately and periodic revisions as the project progresses.

Financing and co-financing

The table below shows the overall status of finance and co-finance to-date.

Table 6 Project information summary table

| Project Title: | Grid-Connected Rooftop Photovoltaic Systems |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| UNDP Project ID: | PIMS 4331 | Project financing | at endorsement (Million US$) | at MTR (Million US$) | MTR Co-finance as percentage of CEO ER co-finance |
| ATLAS Project ID: | 00065515 | GEF financing: | 1,740,000 | 880,910 | 51 |
| Country: | Seychelles | UNDP: | $60,000 | -- | 0 |
| Region: | Africa | Others: | 6,077,138 | 3,302,000 | 54 |
| Focal Area: | Climate Change Mitigation | Total co-financing: | 6,137,138 | 3,302,000 | 54 |
| GEF Focal Area Strategic Program | Promote low-GHG energy technologies, through the increased production of renewable energy in electricity grids. | Total Project Cost in cash: | 7,287,138 | 4,182,910 | 57 |
| Executing Agency: | Seychelles Energy Commission |  |  |  |  |
| Other Partners involved: | Public Utilities Corporation | ProDoc Signature (date project began): |  | Sep. 2012 |  |
|  |  |  | Planned closing date: September 2016 | Revised closing date: September 2016 (no revision) |  |

Table 7: Summary of co-finance as anticipated at CEO ER

| Name of Co-financier (source) | Classification | Type | Amount at CEO Endorsement Request | Amount at Mid-Term Review |
| --- | --- | --- | --- | --- |
| Seychelles Energy Commission | Government | Cash + In-Kind | $423,956 | $30,000 |
| Public Utilities Commission | Parastatal | Cash & In-Kind | $1,405,738 | $400,000 |
| Ministry of Finance | Government | Cash | $740,741 | $222,000 |
| Department of Environment | Government | Cash | $60,000 | -- |
| PV System End-Users | Private Sector | Cash | $3,159,223 | $2,600,000 |
| Seychelles Islands Foundation | NGO | Cash | $100,000 | 0 |
| Intl. Atomic Energy Agency | Multilateral Agency | Cash | $112,480 | $50,000 |
| European Investment Bank | Multilateral Agency | Cash | $65,000 | 0 |
| UNDP | Multilateral Agency | Cash & In-kind | $60,000 | -- |
| Total Co-financing |  |  | 6,127,138 | $3,302,000 |

Some $150,000 (of combined GEF and GoS funds) have been disbursed as rebates under the rebate scheme as of the MTR. The Government of Seychelles has allocated some $220,000 for rebates, of a total of approximately $750,000 allocated for rebates. The remaining approximately $530,000 have been from GEF funds allocated for rebates.

Project-level monitoring, reporting, and evaluation systems

The project has filed consistent quarterly progress reports through Q1 2015 which are available online and easily accessible. The project, and in fact all UNDP-GEF projects in the Seychelles, are to be commended on their basic reporting and accessibility of basic data. This can be considered best practice and should be encouraged in other countries and regions. The online database should also be expanded to include further documentation of studies, reports, etc. to the extent possible. Recovery of data not in the online database has proven difficult.

The tracking of activities by various stakeholders (grid improvements by PUC, development of training by SIT, and others) could in general be improved, as much of this information is not readily available in an organised manner. This, in turn, also makes it more difficult to utilise the efforts of partners and stakeholders to achieve remaining outcomes.

Stakeholder engagement

The stakeholders have in general been quite engaged. There is a high level of awareness and support for the project from the various stakeholders. Increased direct interaction with the various stakeholders in the coming period to achieve the remaining outcomes will be necessary, in particular coordination to achieve policy, regulatory and financial outcomes.

Communications

The project enjoys fluent communication among the various stakeholders. The project manager at the time of the MTR enjoys a good rapport with all the main stakeholders, which has facilitated communication and project implementation.

In the remaining project term, the project would benefit from engagement of stakeholders on the items remaining to be completed (please see Table 5 above).

## Sustainability

Financial risks to sustainability

There are no regulations in place guaranteeing PV buyers’ long-term benefit. Those investing in PV now are betting that their systems will pay-off before the present status quo changes. Thus, PV is restricted to those with the highest electricity rates. This obviously presents a risk to sustainability.

The table below shows electricity tariffs in the Seychelles for residential consumers based on consumption. It also shows the simple pay-back period for a PV system, using the UNDP-GEF index cost of uS$2.8/kW and 25% rebate (the figure in effect at time of MTR).

Consumption (kWh/month); Tariff SCR/kWh (USD/kWh); Simple payback of a residential PV system (years), based on index price of US$2.8/kW; Simple payback of a 3 kW PV system (years), with 25% rebate. 0 - 200; 0.58 (0.044); 48.3; 36.2. 201 - 300; 0.84 (0.065); 33.3; 25. 301 – 400; 2.66 (0.204); 10.5; 7.9. 401 – 600; 3.04 (0.234); 9.2; 6.9. Above 600; 3.72 (0.286); 7.5; 5.6.

In order for PV to be financially sustainable, there must be in place reliable regulations to provide a long-term financial return for PV owners, as well as a finance mechanism to allow them to offset the initial cost. This has been noted in the project risk log.

A threat to the overall financial sustainability of the project is the threat to the financial sustainability of PV installations for PUC. PUC relies on revenue from consumers in the highest tariff tiers to subsidise those in the lower tiers and finance its own activities. With the loss of revenue from this category of consumers, PUC’s finances are adversely impacted. PUC must therefore find a way to profit from PV (for example, by installing some of its own capacity near consumers to reduce what it must generate and reduce grid losses), or by establishing a feed-in tariff that is near PUC’s marginal cost of supply.

Socio-economic risks to sustainability

At present, PV systems in Seychelles are adopted by those in the high electricity tariffs, with large electricity bills, the ability to finance the systems and overall knowledge, awareness, and financial security to take a risk on installation of PV, since there is no regulatory guarantee that the present status quo of PUC allowing net-metering will continue. In other words, PV is mostly adopted by wealthy individuals and businesses. As a result, PV is seen as something for the wealthier classes, which creates a socio-economic risk to sustainability.

In order to mitigate this risk, regulations are needed to ensure the long-term sustainability of PV (ensuring quality of components and installation and ensuring long-term value for the power generated), as well as financial mechanisms to reduce the capital requirement associated.

From the point of view of PUC, implementation of PV reduces its revenue from the most profitable consumers (those with the highest tariffs). The revenues from high-tariff consumers are used to subsidise those who consume at lower tariffs. In order for the use of PV to be sustainable for PUC, it is necessary for it to be an income-generating activity for PUC. This may come about through a restructuring of tariffs, or use of a Feed-in Tariff at the marginal cost of generation to PUC. PUC may also use PV generated by some producers to supply power to others nearby, thereby reducing its losses in transmission (this happens inherently on the network, PUC simply needs to be aware and account for and manage it).

Institutional framework and governance risks to sustainability

The institutional framework in the Seychelles has evolved considerably to allow the participation of private power producers in the generation of the islands’ energy needs.

Still, at present the framework under which consumers feed power to the grid is non-contractual and non-binding on PUC, with the result that only consumers who believe they can obtain their return on investment relatively quickly before a change is made make the effort to participate.

Thus, a clear, stable, regulatory framework with long-term policies supporting the adoption of PV technology is needed and as of yet is not in place. This is not to diminish the advances that have been made. They are a necessary step for future developments and have been sufficient to enable successful adoption thus far in the project. However, they are not likely to be able to sustain wider adoption in the future. GoS has announced a target of generating 15% of the islands’ electricity from renewable resources by 2030. The presently installed PV capacity generates some 1.4 GWh per year, approximately 0.4% of the Seychelles consumption of 350 GWh/year.

Environmental risks to sustainability

There are limited environmental risks to project sustainability. These are principally those related to climate change, such as potentially increased cloudiness and reduced solar insolation. More frequent or stronger storms may also adversely impact PV installation, potentially damaging those which are not fixed well enough to withstand the increased wind speeds.

The disposal of PV modules and associated components receives attention worldwide through programmes and associations such as PV Cycle which seek to recycle modules. It may be necessary to ship components out of the Seychelles for recycling. This is not expected to be prohibitive as shipping usually does not represent more than one or two pennies per watt for solar modules, and perhaps similar for inverters.

The large variations in micro-climate and consequent effectiveness of PV at various locations on the islands creates a risk to sustainability in that PV systems installed in areas of poor irradiation may under-perform, leaving their owners unsatisfied and potentially with a financial loss.

# Conclusions and Recommendations

## Conclusions

- The project is well designed with an opportune selection of topic and timing such that the removal of barriers has resulted in the desired adoption rate.

- The project is ahead of schedule in reaching its installed capacity, energy generation and GHG emissions reduction targets. Project management has been highly effective in engaging stakeholders around these targets.

- As a result of reaching its main objectives, the project has the opportunity to address some factors beyond its original design, such as supporting a feed-in tariff or other mechanism to expand sustainability and adoption beyond that originally envisaged.

- The financing mechanism and its relation to adoption remains poorly understood as evidenced by half of the installations essentially ignoring it. Further understanding of the financial mechanism is needed.

- The project has left some items unaddressed, most specifically the NPA, capacity building and training, and implementation of secondary legislation to support long-term adoption of PV. Addressing these issues should be a priority in the remaining project time. In particular, the NPA requires attention as it may take a year or more to address and would thus be the only project output not reached by project close, though it can be expected within a few months of close.

- Record keeping for main documents, PIRs and reports is to be commended, not just for this project but for the portal which supports such functions for all Seychelles projects under UNDP-GEF.

- In terms of design, timing and intervention, the project can be considered best practice as it identified an opportunity where UNDP-GEF intervention could effectively remove barriers to adoption of a technology and thus facilitate its uptake.

- Adoption on Praslin has lagged adoption on Mahé. While this should be expected, further effort to encourage adoption can be effective, in particular supporting one or two installers on the island.

- The overall practice of establishing a PCU to support and administer such projects seems to be particularly conducive to effective project management and collaboration amongst projects. The camaraderie in having the various project managers in one location appears to be to the overall benefit of the projects managers and projects. Establishment of such a PCU may be considered good practice for replication in other areas.

- Lack of capacity at PUC and SEC is a limitation that should be addressed.

## Summary of recommendations

- The project should prioritise in the coming period: establishment of sustainable legislation, capacity building and training (for installers, PUC, and SEC), and implementation of resource assessment and national performance assessment.

- The relationship between financial incentives and adoption is not clearly understood. Better study of the current financial mechanism and how to make it more effective (in combination with legislation) is necessary.

- It is necessary to establish a system that removes current delays and bottle-necks in installation, whether by increasing resources at PUC and SEC, or by changing installation procedures to require reduced PUC and SEC resources.

- Increasing capacity at PUC and SEC, through capacity building, increased hiring, and/or outsourcing should be carefully considered as the electricity sector in general takes on ever-larger changes. Where hiring of additional staff is not possible or not favourable, specific functions may be outsourced (potentially at no cost to PUC and SEC). Examples include filing of paperwork, or particular site activities or inspections which may be done by qualified and certified personnel (potentially the installers) and only spot-checked by PUC and SEC, as compared with the present system where PUC and SEC must visit each PV installation multiple times (initial inspection, at construction, and commissioning).

- There is currently no mechanism to ensure quality or hold installers responsible. A sort of consumer protection mechanism, supported for example by standard contracts, should be put in place. Such a mechanism should track installers and hold them accountable. It should also track system performance (perhaps making cumulative performance of system by an installer available to the public). Such a mechanism should also protect installers from unreasonable customer claims.

- Follow-up of co-finance commitments for the remaining tasks as these can be important resources in supporting and achieving remaining tasks.

- There are presently no installers on Praslin. The support of one or two installers on Praslin could make PV much more accessible to the residents of Praslin as compared with having to request installers from the main island. Given resources, the project may have an opportunity for further cooperation with other entities (e.g. the Clinton Climate Initiative and/or the Green Climate Fund) to promote longevity of the project, support study and research related to PV and Seychelles climate mitigation, or enable projects and other vehicles to accept external investment.

# Annex 1: 	MTR ToR (excluding ToR annexes)

UNDP-GEF Midterm Review Terms of Reference

- INTRODUCTION

This is the Terms of Reference (ToR) for the UNDP-GEF Midterm Review (MTR) of the full-sized project titled Grid-connected rooftop photovoltaic systems (PIMS 4331) implemented through the Government of Seychelles Ministry of Environment, Energy and Climate Change (MEECC) - specifically the Seychelles Energy Commission (SEC) - which is to be undertaken in May 2015. The project started on the 12th September 2012 and is in its third year of implementation. In line with the UNDP-GEF Guidance on MTRs, this MTR process was initiated before the submission of the second Project Implementation Report (PIR). This ToR sets out the expectations for this MTR.  The MTR process must follow the guidance outlined in the document Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects (http://web.undp.org/evaluation/documents/guidance/GEF/mid-term/Guidance_Midterm%20Review%20_EN_2014.pdf).

2.  PROJECT BACKGROUND INFORMATION

The project was designed to support the Government of Seychelles in moving towards its targets for incorporation of renewable energy into its overall energy mix. Currently, the Seychelles is approximately 90% dependent on imported oil to meet its energy needs, including electricity production. The objective of the project is to increase the use of grid-connected photovoltaic (PV) systems as a sustainable means of generating electricity in selected main islands and smaller islands of the Seychelles, with a focus on small-scale producers who are already connected to the national electricity grid. The project will revise the legal, regulatory and policy framework to better support the adoption of renewable energy technologies, and grid-connected PV systems in particular; design and implement financial mechanisms that will make the purchase and installation of solar PV systems more attractive to the private sector; establish the first market supply chain for solar PV systems in the country; provide training to establish local capacity for the installation and maintenance of PV systems; and demonstrate for the first time in the Seychelles the viability and practicality of grid-connected PV systems through demonstration PV systems. Together, these actions are designed to play a critical role in “jump-starting” the adoption of solar PV technology in the Seychelles, and in setting the stage for broad-scale replication by reducing the costs of PV technology through a market-based approach that will establish financial incentive mechanisms for PV systems and reduce transaction costs (by creating a reliable supply chain and establishing local capacity for installation and maintenance). In this way, the project is designed to transform an energy sector that today is almost 100% dependent on imported fossil fuels into one where solar PV and other RETs provide a significant percentage of national energy production going forward.

The project is implemented over a period of four years, with a budget of $1,160,000 and co-financing of $6,127,138.  The project is implemented by MEECC and the SEC, with the engagement of stakeholders including other Government organizations, the commercial banks (in regard to the project financing mechanism) and the private sector. The project is aligned with and supports implementation of the Seychelles Energy Policy and Energy Act, and is implemented in close cooperation with other donors, notably the IAEA and EIB.

3.  OBJECTIVES OF THE MTR

The MTR will assess progress towards the achievement of the project objectives and outcomes as specified in the Project Document, and assess early signs of project success or failure with the goal of identifying the necessary changes to be made in order to set the project on-track to achieve its intended results. The MTR will also review the project’s strategy and its risks to sustainability.

4. MTR APPROACH & METHODOLOGY

The MTR must provide evidence based information that is credible, reliable and useful. The MTR consultant will review all relevant sources of information including documents prepared during the preparation phase (i.e. PIF, UNDP Initiation Plan, UNDP Environmental & Social Safeguard Policy, the Project Document, project reports including Annual Project Review/PIRs, project budget revisions, lesson learned reports, national strategic and legal documents, and any other materials that the team considers useful for this evidence-based review). The MTR consultant will review the baseline GEF focal area Tracking Tool submitted to the GEF at CEO endorsement, and the midterm GEF focal area Tracking Tool that must be completed before the MTR field mission begins.

The MTR consultant is expected to follow a collaborative and participatory approach ensuring close engagement with the Project Team, government counterparts (the GEF Operational Focal Point), the UNDP Country Office(s), UNDP-GEF Regional Technical Advisers, and other key stakeholders.

Engagement of stakeholders is vital to a successful MTR. Stakeholder involvement should include interviews with stakeholders who have project responsibilities, including but not limited to: executing agencies (MEECC and SEC), senior officials of project stakeholder institutions (Public Utilities Corporation, Ministry of Finance, Trade and the Blue Economy, Seychelles Institute of Technology), key experts and consultants in the subject area, Project Board, project stakeholders (Private Sector Partners, Environmental NGOs, community members and SMEs investing in solar PV), academia (University of Seychelles), etc. Additionally, the MTR consultant is expected to conduct field missions on Mahe and possibly other inner islands, including project demo sites.

The final MTR report should describe the full MTR approach taken and the rationale for the approach making explicit the underlying assumptions, challenges, strengths and weaknesses about the methods and approach of the review.

5.  DETAILED SCOPE OF THE MTR

The MTR consultant will assess the following four categories of project progress. See the Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects for extended descriptions.

i.    Project Strategy

Project design:

- Review the problem addressed by the project and the underlying assumptions.  Review the effect of any incorrect assumptions or changes to the context to achieving the project results as outlined in the Project Document.

- Review the relevance of the project strategy and assess whether it provides the most effective route towards expected/intended results.  Were lessons from other relevant projects properly incorporated into the project design?

- Review how the project addresses country priorities. Review country ownership. Was the project concept in line with the national sector development priorities and plans of the country (or of participating countries in the case of multi-country projects)?

- Review decision-making processes: were perspectives of those who would be affected by project decisions, those who could affect the outcomes, and those who could contribute information or other resources to the process, taken into account during project design processes?

- Review the extent to which relevant gender issues were raised in the project design. See Annex 9 of Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects for further guidelines.

- If there are major areas of concern, recommend areas for improvement.

Results Framework/Logframe:

- Undertake a critical analysis of the project’s logframe indicators and targets, assess how “SMART” the midterm and end-of-project targets are (Specific, Measurable, Attainable, Relevant, Time-bound), and suggest specific amendments/revisions to the targets and indicators as necessary.

- Are the project’s objectives and outcomes or components clear, practical, and feasible within its time frame?

- Examine if progress so far has led to, or could in the future catalyse beneficial development effects (i.e. income generation, gender equality and women’s empowerment, improved governance etc...) that should be included in the project results framework and monitored on an annual basis.

- Ensure broader development and gender aspects of the project are being monitored effectively.  Develop and recommend SMART ‘development’ indicators, including sex-disaggregated indicators and indicators that capture development benefits.

ii.    Progress Towards Results

Progress Towards Outcomes Analysis:

- Review the logframe indicators against progress made towards the end-of-project targets using the Progress Towards Results Matrix and following the Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects; colour code progress in a “traffic light system” based on the level of progress achieved; assign a rating on progress for each outcome; make recommendations from the areas marked as “Not on target to be achieved” (red).

Table. Progress Towards Results Matrix (Achievement of outcomes against End-of-project Targets)

| Project Strategy | Indicator | Baseline Level | Level in 1st PIR (self- reported) | Midterm Target | End-of-project Target | Midterm Level & Assessment | Achievement Rating | Justification for Rating |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective: | Indicator (if applicable): |  |  |  |  |  |  |  |
| Outcome 1: | Indicator 1: |  |  |  |  |  |  |  |
|  | Indicator 2: |  |  |  |  |  |  |  |
| Outcome 2: | Indicator 3: |  |  |  |  |  |  |  |
|  | Indicator 4: |  |  |  |  |  |  |  |
|  | Etc. |  |  |  |  |  |  |  |
| Etc. |  |  |  |  |  |  |  |  |

Indicator Assessment Key

| Green= Achieved | Yellow= On target to be achieved | Red= Not on target to be achieved |
| --- | --- | --- |

In addition to the progress towards outcomes analysis:

- Compare and analyse the GEF Tracking Tool at the Baseline with the one completed right before the Midterm Review.

- Identify remaining barriers to achieving the project objective in the remainder of the project.

- By reviewing the aspects of the project that have already been successful, identify ways in which the project can further expand these benefits.

iii.   Project Implementation and Adaptive Management

Management Arrangements:

- Review overall effectiveness of project management as outlined in the Project Document.  Have changes been made and are they effective?  Are responsibilities and reporting lines clear?  Is decision-making transparent and undertaken in a timely manner?  Recommend areas for improvement.

- Review the quality of execution of the Executing Agency/Implementing Partner(s) and recommend areas for improvement.

- Review the quality of support provided by the GEF Partner Agency (UNDP) and recommend areas for improvement.

Work Planning:

- Review any delays in project start-up and implementation, identify the causes and examine if they have been resolved.

- Are work-planning processes results-based?  If not, suggest ways to re-orientate work planning to focus on results?

- Examine the use of the project’s results framework/ logframe as a management tool and review any changes made to it since project start.

Finance and co-finance:

- Consider the financial management of the project, with specific reference to the cost-effectiveness of interventions.

- Review the changes to fund allocations as a result of budget revisions and assess the appropriateness and relevance of such revisions.

- Does the project have the appropriate financial controls, including reporting and planning, that allow management to make informed decisions regarding the budget and allow for timely flow of funds?

- Informed by the co-financing monitoring table to be filled out, provide commentary on co-financing: is co-financing being used strategically to help the objectives of the project? Is the Project Team meeting with all co-financing partners regularly in order to align financing priorities and annual work plans?

Project-level Monitoring and Evaluation Systems:

- Review the monitoring tools currently being used:  Do they provide the necessary information? Do they involve key partners? Are they aligned or mainstreamed with national systems?  Do they use existing information? Are they efficient? Are they cost-effective? Are additional tools required? How could they be made more participatory and inclusive?

- Examine the financial management of the project monitoring and evaluation budget.  Are sufficient resources being allocated to monitoring and evaluation? Are these resources being allocated effectively?

Stakeholder Engagement:

- Project management: Has the project developed and leveraged the necessary and appropriate partnerships with direct and tangential stakeholders?

- Participation and country-driven processes: Do local and national government stakeholders support the objectives of the project?  Do they continue to have an active role in project decision-making that supports efficient and effective project implementation?

- Participation and public awareness: To what extent has stakeholder involvement and public awareness contributed to the progress towards achievement of project objectives?

Reporting:

- Assess how adaptive management changes have been reported by the project management and shared with the Project Board.

- Assess how well the Project Team and partners undertake and fulfil GEF reporting requirements (i.e. how have they addressed poorly-rated PIRs, if applicable?)

- Assess how lessons derived from the adaptive management process have been documented, shared with key partners and internalized by partners.

Communications:

- Review internal project communication with stakeholders: Is communication regular and effective? Are there key stakeholders left out of communication? Are there feedback mechanisms when communication is received? Does this communication with stakeholders contribute to their awareness of project outcomes and activities and investment in the sustainability of project results?

- Review external project communication: Are proper means of communication established or being established to express the project progress and intended impact to the public (is there a web presence, for example? Or did the project implement appropriate outreach and public awareness campaigns?)

- For reporting purposes, write one half-page paragraph that summarizes the project’s progress towards results in terms of contribution to sustainable development benefits, as well as global environmental benefits.

iv.   Sustainability

- Validate whether the risks identified in the Project Document, Annual Project Review/PIRs and the ATLAS Risk Management Module are the most important and whether the risk ratings applied are appropriate and up to date. If not, explain why.

- In addition, assess the following risks to sustainability:

Financial risks to sustainability:

- What is the likelihood of financial and economic resources not being available once the GEF assistance ends (consider potential resources can be from multiple sources, such as the public and private sectors, income generating activities, and other funding that will be adequate financial resources for sustaining project’s outcomes)?

Socio-economic risks to sustainability:

- Are there any social or political risks that may jeopardize sustainability of project outcomes? What is the risk that the level of stakeholder ownership (including ownership by governments and other key stakeholders) will be insufficient to allow for the project outcomes/benefits to be sustained? Do the various key stakeholders see that it is in their interest that the project benefits continue to flow? Is there sufficient public / stakeholder awareness in support of the long term objectives of the project? Are lessons learned being documented by the Project Team on a continual basis and shared/ transferred to appropriate parties who could learn from the project and potentially replicate and/or scale it in the future?

Institutional Framework and Governance risks to sustainability:

- Do the legal frameworks, policies, governance structures and processes pose risks that may jeopardize sustenance of project benefits? While assessing this parameter, also consider if the required systems/ mechanisms for accountability, transparency, and technical knowledge transfer are in place.

Environmental risks to sustainability:

- Are there any environmental risks that may jeopardize sustenance of project outcomes?

Conclusions & Recommendations

The MTR consultant will include a section of the report setting out the MTR’s evidence-based conclusions, in light of the findings.

Recommendations should be succinct suggestions for critical intervention that are specific, measurable, achievable, and relevant. A recommendation table should be put in the report’s executive summary. See the Guidance For Conducting Midterm Reviews of UNDP-Supported, GEF-Financed Projects for guidance on a recommendation table.

The MTR consultant should make no more than 15 recommendations total.

Ratings

The MTR consultant will include its ratings of the project’s results and brief descriptions of the associated achievements in a MTR Ratings & Achievement Summary Table in the Executive Summary of the MTR report. See Annex E for ratings scales. No rating on Project Strategy and no overall project rating is required.

Table. MTR Ratings & Achievement Summary Table for Grid-connected Rooftop PV systems project

| Measure | MTR Rating | Achievement Description |
| --- | --- | --- |
| Project Strategy | N/A |  |
| Progress Towards Results | Objective Achievement Rating: (rate 6 pt. scale) |  |
|  | Outcome 1 Achievement Rating: (rate 6 pt. scale) |  |
|  | Outcome 2 Achievement Rating: (rate 6 pt. scale) |  |
|  | Outcome 3 Achievement Rating: (rate 6 pt. scale) |  |
|  | Etc. |  |
| Project Implementation & Adaptive Management | (rate 6 pt. scale) |  |
| Sustainability | (rate 4 pt. scale) |  |

- TIMEFRAME

The total duration of the MTR will be 20 days over a time period of approximately 8 weeks starting 13th April 2015, and shall not exceed five months from when the consultant is hired. The tentative MTR timeframe is as follows:

| TIMEFRAME | ACTIVITY |
| --- | --- |
| 31st March 2015 | Application closes |
| 10th April 2015 | Select MTR consultant |
| 13th April 2015 | Prep the MTR consultant (handover of Project Documents) |
| 25th April 2015, 3 days | Document review and preparing MTR Inception Report |
| 2nd May 2015 | Finalization and Validation of MTR Inception Report- latest start of MTR mission |
| 3rd -11th May 2015, 10 days | MTR mission: stakeholder meetings, interviews, field visits |
| 13th May 2015 | Mission wrap-up meeting & presentation of initial findings- earliest end of MTR mission |
| 18th – 22nd May, 5 days | Preparing draft report |
| 10th - 12th June, 2 days | Incorporating audit trail from feedback on draft report/Finalization of MTR report |
| By 30th June | Preparation & Issue of Management Response |
| - | (optional) Concluding Stakeholder Workshop (not mandatory for MTR consultant) |
| By 30th June | Expected date of full MTR completion |

Options for site visits should be provided in the Inception Report.

- MIDTERM REVIEW DELIVERABLES

| # | Deliverable | Description | Timing | Responsibilities |
| --- | --- | --- | --- | --- |
| 1 | MTR Inception Report | MTR consultant clarifies objectives and methods of Midterm Review | No later 4 days before the MTR mission: 30th April | MTR consultant submits to the Commissioning Unit and project management |
| 2 | Presentation | Initial Findings | End of MTR mission: 13th May | MTR consultant presents to project management and the Commissioning Unit |
| 3 | Draft Final Report | Full report (using guidelines on content outlined in Annex B) with annexes | Within 10 days of the MTR mission: 22nd May | Sent to the Commissioning Unit, reviewed by RTA, Project Coordinating Unit, GEF OFP |
| 4 | Final Report* | Revised report with audit trail detailing how all received comments have (and have not) been addressed in the final MTR report | Within 5 days of receiving UNDP comments on draft: 12th June | Sent to the Commissioning Unit |

*The final MTR report must be in English. If applicable, the Commissioning Unit may choose to arrange for a translation of the report into a language more widely shared by national stakeholders.

- MTR ARRANGEMENTS

The principal responsibility for managing this MTR resides with the Commissioning Unit. The Commissioning Unit for this project’s MTR is UNDP Country Office Mauritius and Seychelles.

The commissioning unit will contract the consultants and ensure the timely provision of per diems and travel arrangements within Seychelles for the MTR consultant. The Project Manager will be responsible for liaising with the MTR consultant to provide all relevant documents (see also the project website at www.pcusey.sc/index.php/pcu-projects/repository/Photovoltaic-Systems-(PV)-Project), set up stake-holder interviews, and arrange field visits.

- TEAM COMPOSITION

One independent international consultant (with experience and exposure to projects and evaluations in other regions globally) will conduct the MTR. The consultants cannot have participated in the project preparation, formulation, and/or implementation (including the writing of the Project Document) and should not have a conflict of interest with project’s related activities.

The selection of consultant will be aimed at maximizing experience in the following areas:

- A Master’s degree in Environment, Renewable Energy, or other closely related field; work experience in relevant technical areas for at least 10 years (30 points)

- Recent experience with result-based management evaluation methodologies; experience working with the GEF or GEF-evaluations; experience applying SMART indicators and reconstructing or validating baseline scenarios (20 points)

- Competence in adaptive management, as applied to renewable energy and CCM projects (15 points)

- Experience working in Small Island Developing States (15 points)

- Demonstrated understanding of issues related to gender and renewable energy; experience in gender sensitive evaluation and analysis (10 points)

- Excellent communication skills; demonstrable analytical skills (10 points)

- Project evaluation/review experiences within United Nations system will be considered an asset

- PAYMENT MODALITIES AND SPECIFICATIONS

10% of payment upon approval of the final MTR Inception Report

30% upon submission of the draft MTR report

60% upon finalization of the MTR report

Or, as otherwise agreed between the Commissioning Unit and the MTR consultant.

- APPLICATION PROCESS

Applicants are requested to apply online http://jobs.undp.org. Individual consultants are invited to submit applications & below requirements by 31st March 2015.  Incomplete applications will be excluded from further consideration.

Recommended Presentation of Proposal:

- Letter of Confirmation of Interest and Availability using the template provided by UNDP;

- CV and a Personal History Form (P11 form);

- Brief description of approach to work/technical proposal of why the individual considers him/herself as the most suitable for the assignment, and a proposed methodology on how they will approach and complete the assignment; (max 1 page)

- Financial Proposal that indicates the all-inclusive fixed total contract price and all other travel related costs (such as flight ticket, per diem, etc), supported by a breakdown of costs, as per template attached to the Letter of Confirmation of Interest template.  If an applicant is employed by an organization/company/institution, and he/she expects his/her employer to charge a management fee in the process of releasing him/her to UNDP under Reimbursable Loan Agreement (RLA), the applicant must indicate at this point, and ensure that all such costs are duly incorporated in the financial proposal submitted to UNDP.

Criteria for Evaluation of Proposal:  Only those applications which are responsive and compliant will be evaluated.  Offers will be evaluated according to the Combined Scoring method – where the educational background and experience on similar assignments will be weighted at 70% and the price proposal will weigh as 30% of the total scoring.  The applicant receiving the Highest Combined Score that has also accepted UNDP’s General Terms and Conditions will be awarded the contract.

# Annex 2: 	Ratings scale

According to the Guidance for Conducting Midterm Reviews of UNDP-Supported GEF-Financed Projects, the following are the rating scales used in the MTR.

Progress Towards Results rating scale:

| Highly Satisfactory (HS) | The objective/outcome is expected to achieve or exceed all its end-of-project targets, without major shortcomings. The progress towards the objective/outcome can be presented as “good practice”. |
| --- | --- |
| Satisfactory (S) | The objective/outcome is expected to achieve most of its end-of-project targets, with only minor shortcomings. |
| Moderately Satisfactory (MS) | The objective/outcome is expected to achieve most of its end-of-project targets but with significant shortcomings. |
| Moderately Unsatisfactory (MU) | The objective/outcome is expected to achieve its end-of-project targets with major shortcomings. |
| Unsatisfactory (U) | The objective/outcome is expected not to achieve most of its end-of-project targets. |
| Highly Unsatisfactory (HU) | The objective/outcome has failed to achieve its midterm targets, and is not expected to achieve any of its end-of-project targets. |

Project Implementation & Adaptive Management Rating Scale:

| Highly Satisfactory (HS) | Implementation of all seven components –management arrangements, work planning, finance and co-finance, project-level monitoring and evaluation systems, stakeholder engagement, reporting, and communications –is leading to efficient and effective project implementation and adaptive management. The project can be presented as “good practice”. |
| --- | --- |
| Satisfactory (S) | Implementation of most of the seven components is leading to efficient and effective project implementation and adaptive management except for only few that are subject to remedial action. |
| Moderately Satisfactory (MS) | Implementation of some of the seven components is leading to efficient and effective project implementation and adaptive management, with some components requiring remedial action. |
| Moderately Unsatisfactory (MU) | Implementation of some of the seven components is not leading to efficient and effective project implementation and adaptive, with most components requiring remedial action. |
| Unsatisfactory (U) | Implementation of most of the seven components is not leading to efficient and effective project implementation and adaptive management. |
| Highly Unsatisfactory (HU) | Implementation of none of the seven components is leading to efficient and effective project implementation and adaptive management. |

Sustainability Rating Scale:

| Likely (L) | Negligible risks to sustainability, with key outcomes on track to be achieved by the project’s closure and expected to continue into the foreseeable future |
| --- | --- |
| Moderately Likely (ML) | Moderate risks, but expectations that at least some outcomes will be sustained due to the progress towards results on outcomes at the Midterm Review |
| Moderately Unlikely (MU) | Significant risk that key outcomes will not carry on after project closure, although some outputs and activities should carry on |
| Unlikely (U) | Severe risks that project outcomes as well as key outputs will not be sustained |

# Annex 3: 	MTR Mission Itinerary

List of interviews held during the mission (May 15 – 20, 2015)

| Time | Organization | Name of delegate | Title |
| --- | --- | --- | --- |
| Friday, 15 May |  |  |  |
| 08:00 | UNDP Seychelles Office | Dominic Rassool | Project Manager |
| 09:30 | Ministry of Finance (MoF) | Roger Toussaint | Programme Administrator for the Seychelles Energy Efficiency and Renewable Energy Programme (SEEREP) Advisor, Ministry of Finance Previous managing director of DBS |
|  | Public Utilities Corporation (PUC) | Said Afif | Senior Electric Engineer at PUC |
|  | Sea & Sun Technology | Richard Hoareau | Managing Director at Sea & Sun Technology |
| Monday, 18 May |  |  |  |
| Tuesday, 19 May |  |  |  |
| 10:00 | Seychelles Energy Commission (SEC) | Tony Imaduwa | Chief Executive Officer |
|  | Development Bank of Seychelles (DSB) | Jean Preira | Head of Finance at DBS |
| 13:30 | Seychelles Institute of Technology (SIT) | Hubert Barbe | Director of SIT |
| Wednesday, 20 May |  |  |  |
| 12:30 | UNDP GEF PCU (Project Control Unit) | Andrew Grieser Johns | Chief Technical Advisor / Program Coordinator |
|  |  | Norman Lucas | Finance Manager at UNDP GEF PCU |
|  |  | Fiona K. Wilson | Project Manager at Clinton Foundation |
| Thursday, 21 May: Field visit |  |  |  |
| Friday, 22 May: MTR Debriefing Presentation |  |  |  |

# Annex 4: 	List of persons interviewed

List of persons interviewed during the mission – in alphabetical order

Andrew Grieser Johns

Chief Technical Advisor / Program Coordinator

UNDP GEF PCU (Project Control Unit)

Dominic Rassool

Project Manager

UNDP Seychelles

Fiona K. Wilson

Project Manager

Clinton Foundation

Hubert Barbe

Director

Seychelles Institute of Technology

Jean Preira

Head of Finance

Development Bank of Seychelles

Norman Lucas

Finance Manager

UNDP GEF PCU

Richard Hoareau

Managing Director

Sea & Sun Technology (Seychelles)

Roger Toussaint

Programme Administrator for the Seychelles Energy Efficiency and Renewable Energy Programme (SEEREP)

Advisor, Ministry of Finance

Previous managing director of DBS

Said Afif

Senior Electric Engineer

Public Utilities Corporation (PUC)

Steve Khambatta

Managing Director

Amalgamated Tobacco Co. (Seychelles) Ltd.

Tony Imaduwa

Chief Executive Officer

Seychelles Energy Commission (SEC)

# Annex 5: 	List of documents reviewed

Documents named in red were not obtained

| # | Document name/description |
| --- | --- |
| 1 | Project document |
| 2 | Inception report |
| 3 | Guidelines and Procedures for national implementation of UNDP-Supported GEF-Financed Projects |
| 4 | Guidance for Conducting MTRs of UNDP-Supported GEF-Financed Projects |
| 5 | Project quarterly reports and PIRs ?? |
| 6 | Project CEO Endorsement Request |
| 7 | Cabinet Memorandum on Feed-in Tariff for Grid-Tied Renewable Energy Generation 2013 |
| 8 | Capacity Needs Assessment Report October 2013 |
| 9 | Financial Mechanisms to Support the Purchase and Operation of Solar PV Systems October 2013 |
| 10 | Grid Connected Rooftop PS Systems – Independent Auditor’s Report to UNDP |

# Annex 6: 	Signed UNEG Code of Conduct

# Annex 7: 	Signed MTR Final Report Clearance Form

Midterm Review Report Reviewed and Cleared By:

Commissioning Unit

Name: _____________________________________________

Signature: __________________________________________     Date: _______________________________

UNDP-GEF Regional Technical Advisor

Name: _____________________________________________

Signature: __________________________________________     Date: _______________________________

Colour-coding reflects UNDP Guidelines. Red indicates targets that are not expected to be achieved. Yellow indicates targets expected to be achieved. Green indicates targets already achieved.

GHG emissions from electricity generation scheduled to increase from 189,968 tCO2 /year (2009) to 299,957 tCO2/year by 2020

Total installed capacity target for project is 1,305 kWp, which would reduce GHG emissions by 840 tonnes of CO2eq per year.  However, the PV demonstration systems will be installed through the project. Accordingly, the “direct reduction” target assumes the following rate of installation during the project: average installed capacity is 25% during year 2 of project; 65% during year 3 of project; and 90% during year 4 of project. About 21,831 tCO2eq post-project, assuming a 20-year equipment life and no replication factor. The estimated indirect reduction of GHG emissions is at least 70,028 tCO2eq, on the basis of a replication factor of 3 and a 20-year projected life for equipment.

The only active PV systems in the entire country are three very small systems: a 1kWp PV system installed by the PUC and 10kWp and 0.6 kWp private systems.

The size (and thus number) of projects will be determined by various factors and policies, including the new National Energy Policy and grid adsorption capacity.

Funds from the GEF and Government of Seychelles.

Only existing out-of-date energy resource assessment.

Currently-available solar radiation data insufficient to accurately design on-grid PV systems.

SEC is to undertake this activity as of 2016. Discussion has been initiated to collect and process data from existing PV systems under a National Performance Assessment, to serve as a proxy for available solar irradiation, and as a direct indicator of the practically anticipated yield at each location.

SEC has no regulatory and/or enforcement powers.

No IER in place.

No funding exists for financial incentive schemes in support of RET systems.

20 customers enquiring for information about PV systems from the SEC and PV dealers by Year 2 and 50 by EOP.

Very limited information on capacities in Seychelles to develop RETs.

Expected CO2 emissions from power sector are 189,968 tonnes/year (2009) and 299,957 tonnes/year by 2020.

Total installed capacity target for project is 1,305 kWp, which would reduce GHG emissions by 840 tCO2eq per year. However, the PV demonstration systems will be installed through the project. Accordingly, the “direct reduction” target assumes the following rate of installation during the project: average installed capacity is 25% during year 2 of project; 65% during year 3 of project; and 90% during year 4 of project.

Estimated to be produced annually when all systems are operational at EOP; cumulative targets will be calculated and pro-rated based on assumptions as to when systems will come online.

No technical guidelines exist for grid-connected RETs.

Limits on the size of PV systems installed at any given site will be determined during the first year of the project, based in part on the requirements of the grid code.

This includes SIF purchase, installation and operation of its own PV systems – totalling 25 kWp – on remote islands.

As linked to related targets for Output 3.8.

As linked to related targets for Outputs 3.3, 3.5 and 3.8.

According to the Guidance for Conducting Midterm Reviews of UNDP-Supported GEF-Financed Projects, the MTR rating for each measure follows the rating scales detailed in Annex 3 of this report.

It may be simply be the case that early adopters have proceeded without regard for a rebate and that future participation will naturally increase to expected levels. Still, it is somewhat surprising that PV system owners would simply give up rebates on the order of $3,000 for a residential system.

The Seychelles National Energy Policy 2010 – 2030 targeted 15% percent of electricity generation from renewables by 2030.

GHG emissions from electricity generation scheduled to increase from 189,968 tCO2 /year (2009) to 299,957 tCO2 /year by 2020

Total installed capacity target for project is 1,305 kWp, which would reduce GHG emissions by 840 tonnes of CO2eq per year.  However, the PV demonstration systems will be installed through the project. Accordingly, the “direct reduction” target assumes the following rate of installation during the project: average installed capacity is 25% during year 2 of project; 65% during year 3 of project; and 90% during year 4 of project. About 21,831 tCO2eq post-project, assuming a 20-year equipment life and no replication factor. The estimated indirect reduction of GHG emissions is at least 70,028 tCO2, on the basis of a replication factor of 3 and a 20-year projected life for equipment.

The only active PV systems in the entire country are three very small systems: a 1 kWp PV system installed by the PUC and 10 kWp and 0.6 kWp private systems.

The size (and thus number) of projects will be determined by various factors and policies, including the new National Energy Policy and grid adsorption capacity.

As noted above, the size (and thus number) of RE projects will be determined by various policies and technical studies. While the aggregate installed capacity target has been defined, as per the details in the project objective row, the size specifications for the PV systems to be installed as part of the financial incentive RFP will be developed during the design of the scheme.

Funds from the GEF and Government of Seychelles.

Only existing out-of-date energy resource assessment.

Currently-available solar radiation data insufficient to accurately design on-grid PV systems.

Target coverage to be finalised with SEC.

SEC has no regulatory and/or enforcement powers.

Target to be finalised based on findings and recommendations from the EU - Seychelles Climate Change Support Programme (SCCSP) which is supporting the GoS in the process of approving a new Energy Act, as well as provisions for the entire energy sector and formulation of policies and institutional authority under the Act.

No IER in place.

Currently, no funding exists for financial incentive schemes in support of RET systems.

20 customers enquiring for information about PV systems from the SEC and PV dealers by Year 2 and 50 by EOP.

To be confirmed or adjusted during the project inception phase.

Very limited information on capacities in Seychelles to develop RETs.

The results of the Capacity Needs Assessment will be used to refine the proposed capacity building and information sharing activities and targets described in Outputs 2.2 – 2.6.

Expected CO2 emissions from power sector are 189,968 tonnes/year (2009) and 299,957 tonnes/year by 2020.

Total installed capacity target for project is 1,305 kWp, which would reduce GHG emissions by 840 tCO2eq per year.  However, the PV demonstration systems will be installed through the project. Accordingly, the “direct reduction” target assumes the following rate of installation during the project: average installed capacity is 25% during year 2 of project; 65% during year 3 of project; and 90% during year 4 of project.

Estimated to be produced annually when all systems are operational at EOP; cumulative targets will be calculated and pro-rated based on assumptions as to when systems will come online.

No technical guidelines exist for grid-connected RETs.

Target to be confirmed or adjusted based on the results of grid work and assessment of grid stability in Year 1.

Limits on the size of PV systems installed at any given site will be determined during the first year of the project, based in part on the requirements of the grid code.

This includes SIF purchase, installation and operation of its own PV systems – totalling 25 kWp – on remote islands.

As linked to related targets for Output 3.8.

As linked to related targets for Outputs 3.3, 3.5 and 3.8.

The project manager is anticipated to leave the project to continue his studies abroad shortly after this MTR is concluded.

The payback period is based on a capacity factor of 14.8%, or 1,300 equivalent full-load hours/year. This is the factor assumed in the Project Document, though several systems have underperformed this in practice.

At an exchange rate of SCR 13/USD

For residential systems, since only the first 3 kW are eligible for rebate the payback period for larger systems increases, eventually approaching the payback period without rebate.

A wind farm on Mahé contributes a further approximately 2%.  If the estimated current maximum grid capacity for PV of 8 MW is reached, the Seychelles would generate approximately 3% of its electricity from PV.

For ideas on innovative and participatory Monitoring and Evaluation strategies and techniques, see UNDP Discussion Paper: Innovations in Monitoring & Evaluating Results, 05 Nov 2013.

For more stakeholder engagement in the M&E process, see the UNDP Handbook on Planning, Monitoring and Evaluating for Development Results, Chapter 3, pg. 93.

Populate with data from the Logframe and scorecards

Populate with data from the Project Document

If available

Colour code this column only

Use the 6 point Progress Towards Results Rating Scale: HS, S, MS, MU, U, HU

Alternatively, MTR conclusions may be integrated into the body of the report.

Engagement of the consultants should be done in line with guidelines for hiring consultants in the POPP: https://info.undp.org/global/popp/Pages/default.aspx

https://intranet.undp.org/unit/bom/pso/Support%20documents%20on%20IC%20Guidelines/Template%20for%20Confirmation%20of%20Interest%20and%20Submission%20of%20Financial%20Proposal.docx

http://www.undp.org/content/dam/undp/library/corporate/Careers/P11_Personal_history_form.doc